65 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15
66 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21
67 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24
68 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21
69 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29
70 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21
71 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39
72 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39
73 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29
74 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15
75 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29
76 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29
77 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15
78 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39
79 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47
80 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39
81 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15
82 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21
83 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39
84 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47
85 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26
86 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21
87 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29
88 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21
89 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21
90 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47
91 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39
92 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39
93 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26
94 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29
95 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39
96 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15
97 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15
98 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29
99 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39
100 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26
| Running Total for Trial 1 |  |  | Running Total for Trial 2 |  |  | Running Total for Trial 3 |  |  | Running Total for Trial 4 |  |  | Running Total for Trial 5 |  |  | Running Total for Trial 6 |  |  | Running Total for Trial 7 |  |  | Running Total for Trial 8 |  |  | Running Total for Trial 9 |  |  | Running Total for Trial 10 |  |  | Running Total for Trial 11 |  |  | Running Total for Trial 12 |  |  | Running Total for Trial 13 |  |  | Running Total for Trial 14 |  |  | Running Total for Trial 15 |  |  | Running Total for Trial 16 |  |  | Running Total for Trial 17 |  |  | Running Total for Trial 18 |  |  | Running Total for Trial 19 |  |  | Running Total for Trial 20 |  |  | Running Total for Trial 21 |  |  | Running Total for Trial 22 |  |  | Running Total for Trial 23 |  |  | Running Total for Trial 24 |  |  | Running Total for Trial 25 |  |  | Running Total for Trial 26 |  |  | Running Total for Trial 27 |  |  | Running Total for Trial 28 |  |  | Running Total for Trial 29 |  |  | Running Total for Trial 30 |  |  | Running Total for Trial 31 |  |  | Running Total for Trial 32 |  |  | Running Total for Trial 33 |  |  | Running Total for Trial 34 |  |  | Running Total for Trial 35 |  |  | Running Total for Trial 36 |  |  | Running Total for Trial 37 |  |  | Running Total for Trial 38 |  |  | Running Total for Trial 39 |  |  | Running Total for Trial 40 |  |  | Running Total for Trial 41 |  |  | Running Total for Trial 42 |  |  | Running Total for Trial 43 |  |  | Running Total for Trial 44 |  |  | Running Total for Trial 45 |  |  | Running Total for Trial 46 |  |  | Running Total for Trial 47 |  |  | Running Total for Trial 48 |  |  | Running Total for Trial 49 |  |  | Running Total for Trial 50 |  |  | Running Total for Trial 51 |  |  | Running Total for Trial 52 |  |  | Running Total for Trial 53 |  |  | Running Total for Trial 54 |  |  | Running Total for Trial 55 |  |  | Running Total for Trial 56 |  |  | Running Total for Trial 57 |  |  | Running Total for Trial 58 |  |  | Running Total for Trial 59 |  |  | Running Total for Trial 60 |  |  | Running Total for Trial 61 |  |  | Running Total for Trial 62 |  |  | Running Total for Trial 63 |  |  | Running Total for Trial 64 |  |  | Running Total for Trial 65 |  |  | Running Total for Trial 66 |  |  | Running Total for Trial 67 |  |  | Running Total for Trial 68 |  |  | Running Total for Trial 69 |  |  | Running Total for Trial 70 |  |  | Running Total for Trial 71 |  |  | Running Total for Trial 72 |  |  | Running Total for Trial 73 |  |  | Running Total for Trial 74 |  |  | Running Total for Trial 75 |  |  | Running Total for Trial 76 |  |  | Running Total for Trial 77 |  |  | Running Total for Trial 78 |  |  | Running Total for Trial 79 |  |  | Running Total for Trial 80 |  |  | Running Total for Trial 81 |  |  | Running Total for Trial 82 |  |  | Running Total for Trial 83 |  |  | Running Total for Trial 84 |  |  | Running Total for Trial 85 |  |  | Running Total for Trial 86 |  |  | Running Total for Trial 87 |  |  | Running Total for Trial 88 |  |  | Running Total for Trial 89 |  |  | Running Total for Trial 90 |  |  | Running Total for Trial 91 |  |  | Running Total for Trial 92 |  |  | Running Total for Trial 93 |  |  | Running Total for Trial 94 |  |  | Running Total for Trial 95 |  |  | Running Total for Trial 96 |  |  | Running Total for Trial 97 |  |  | Running Total for Trial 98 |  |  | Running Total for Trial 99 |  |  | Running Total for Trial 100 |  |  | Running Total for Trial 101 |  |  | Running Total for Trial 102 |  |  | Running Total for Trial 103 |  |  | Running Total for Trial 104 |  |  | Running Total for Trial 105 |  |  | Running Total for Trial 106 |  |  | Running Total for Trial 107 |  |  | Running Total for Trial 108 |  |  | Running Total for Trial 109 |  |  | Running Total for Trial 110 |  |  | Running Total for Trial 111 |  |  | Running Total for Trial 112 |  |  | Running Total for Trial 113 |  |  | Running Total for Trial 114 |  |  | Running Total for Trial 115 |  |  | Running Total for Trial 116 |  |  | Running Total for Trial 117 |  |  | Running Total for Trial 118 |  |  | Running Total for Trial 119 |  |  | Running Total for Trial 120 |  |  | Running Total for Trial 121 |  |  | Running Total for Trial 122 |  |  | Running Total for Trial 123 |  |  | Running Total for Trial 124 |  |  | Running Total for Trial 125 |  |  | Running Total for Trial 126 |  |  | Running Total for Trial 127 |  |  | Running Total for Trial 128 |  |  | Running Total for Trial 129 |  |  | Running Total for Trial 130 |  |  | Running Total for Trial 131 |  |  | Running Total for Trial 132 |  |  | Running Total for Trial 133 |  |  | Running Total for Trial 134 |  |  | Running Total for Trial 135 |  |  | Running Total for Trial 136 |  |  | Running Total for Trial 137 |  |  | Running Total for Trial 138 |  |  | Running Total for Trial 139 |  |  | Running Total for Trial 140 |  |  | Running Total for Trial 141 |  |  | Running Total for Trial 142 |  |  | Running Total for Trial 143 |  |  | Running Total for Trial 144 |  |  | Running Total for Trial 145 |  |  | Running Total for Trial 146 |  |  | Running Total for Trial 147 |  |  | Running Total for Trial 148 |  |  | Running Total for Trial 149 |  |  | Running Total for Trial 150 |  |  | Running Total for Trial 151 |  |  | Running Total for Trial 152 |  |  | Running Total for Trial 153 |  |  | Running Total for Trial 154 |  |  | Running Total for Trial 155 |  |  | Running Total for Trial 156 |  |  | Running Total for Trial 157 |  |  | Running Total for Trial 158 |  |  | Running Total for Trial 159 |  |  | Running Total for Trial 160 |  |  | Running Total for Trial 161 |  |  | Running Total for Trial 162 |  |  | Running Total for Trial 163 |  |  | Running Total for Trial 164 |  |  | Running Total for Trial 165 |  |  | Running Total for Trial 166 |  |  | Running Total for Trial 167 |  |  | Running Total for Trial 168 |  |  | Running Total for Trial 169 |  |  | Running Total for Trial 170 |  |  | Running Total for Trial 171 |  |  | Running Total for Trial 172 |  |  | Running Total for Trial 173 |  |  | Running Total for Trial 174 |  |  | Running Total for Trial 175 |  |  | Running Total for Trial 176 |  |  | Running Total for Trial 177 |  |  | Running Total for Trial 178 |  |  | Running Total for Trial 179 |  |  | Running Total for Trial 180 |  |  | Running Total for Trial 181 |  |  | Running Total for Trial 182 |  |  | Running Total for Trial 183 |  |  | Running Total for Trial 184 |  |  | Running Total for Trial 185 |  |  | Running Total for Trial 186 |  |  | Running Total for Trial 187 |  |  | Running Total for Trial 188 |  |  | Running Total for Trial 189 |  |  | Running Total for Trial 190 |  |  | Running Total for Trial 191 |  |  | Running Total for Trial 192 |  |  | Running Total for Trial 193 |  |  | Running Total for Trial 194 |  |  | Running Total for Trial 195 |  |  | Running Total for Trial 196 |  |  | Running Total for Trial 197 |  |  | Running Total for Trial 198 |  |  | Running Total for Trial 199 |  |  | Running Total for Trial 200 |  |  | Running Total for Trial 201 |  |  | Running Total for Trial 202 |  |  | Running Total for Trial 203 |  |  | Running Total for Trial 204 |  |  | Running Total for Trial 205 |  |  | Running Total for Trial 206 |  |  | Running Total for Trial 207 |  |  | Running Total for Trial 208 |  |  | Running Total for Trial 209 |  |  | Running Total for Trial 210 |  |  | Running Total for Trial 211 |  |  | Running Total for Trial 212 |  |  | Running Total for Trial 213 |  |  | Running Total for Trial 214 |  |  | Running Total for Trial 215 |  |  | Running Total for Trial 216 |  |  | Running Total for Trial 217 |  |  | Running Total for Trial 218 |  |  | Running Total for Trial 219 |  |  | Running Total for Trial 220 |  |  | Running Total for Trial 221 |  |  | Running Total for Trial 222 |  |  | Running Total for Trial 223 |  |  | Running Total for Trial 224 |  |  | Running Total for Trial 225 |  |  | Running Total for Trial 226 |  |  | Running Total for Trial 227 |  |  | Running Total for Trial 228 |  |  | Running Total for Trial 229 |  |  | Running Total for Trial 230 |  |  | Running Total for Trial 231 |  |  | Running Total for Trial 232 |  |  | Running Total for Trial 233 |  |  | Running Total for Trial 234 |  |  | Running Total for Trial 235 |  |  | Running Total for Trial 236 |  |  | Running Total for Trial 237 |  |  | Running Total for Trial 238 |  |  | Running Total for Trial 239 |  |  | Running Total for Trial 240 |  |  | Running Total for Trial 241 |  |  | Running Total for Trial 242 |  |  | Running Total for Trial 243 |  |  | Running Total for Trial 244 |  |  | Running Total for Trial 245 |  |  | Running Total for Trial 246 |  |  | Running Total for Trial 247 |  |  | Running Total for Trial 248 |  |  | Running Total for Trial 249 |  |  | Running Total for Trial 250 |  |  | Running Total for Trial 251 |  |  | Running Total for Trial 252 |  |  | Running Total for Trial 253 |  |  | Running Total for Trial 254 |  |  | Running Total for Trial 255 |  |  | Running Total for Trial 256 |  |  | Running Total for Trial 257 |  |  | Running Total for Trial 258 |  |  | Running Total for Trial 259 |  |  | Running Total for Trial 260 |  |  | Running Total for Trial 261 |  |  | Running Total for Trial 262 |  |  | Running Total for Trial 263 |  |  | Running Total for Trial 264 |  |  | Running Total for Trial 265 |  |  | Running Total for Trial 266 |  |  | Running Total for Trial 267 |  |  | Running Total for Trial 268 |  |  | Running Total for Trial 269 |  |  | Running Total for Trial 270 |  |  | Running Total for Trial 271 |  |  | Running Total for Trial 272 |  |  | Running Total for Trial 273 |  |  | Running Total for Trial 274 |  |  | Running Total for Trial 275 |  |  | Running Total for Trial 276 |  |  | Running Total for Trial 277 |  |  | Running Total for Trial 278 |  |  | Running Total for Trial 279 |  |  | Running Total for Trial 280 |  |  | Running Total for Trial 281 |  |  | Running Total for Trial 282 |  |  | Running Total for Trial 283 |  |  | Running Total for Trial 284 |  |  | Running Total for Trial 285 |  |  | Running Total for Trial 286 |  |  | Running Total for Trial 287 |  |  | Running Total for Trial 288 |  |  | Running Total for Trial 289 |  |  | Running Total for Trial 290 |  |  | Running Total for Trial 291 |  |  | Running Total for Trial 292 |  |  | Running Total for Trial 293 |  |  | Running Total for Trial 294 |  |  | Running Total for Trial 295 |  |  | Running Total for Trial 296 |  |  | Running Total for Trial 297 |  |  | Running Total for Trial 298 |  |  | Running Total for Trial 299 |  |  | Running Total for Trial 300 |  |  | Running Total for Trial 301 |  |  | Running Total for Trial 302 |  |  | Running Total for Trial 303 |  |  | Running Total for Trial 304 |  |  | Running Total for Trial 305 |  |  | Running Total for Trial 306 |  |  | Running Total for Trial 307 |  |  | Running Total for Trial 308 |  |  | Running Total for Trial 309 |  |  | Running Total for Trial 310 |  |  | Running Total for Trial 311 |  |  | Running Total for Trial 312 |  |  | Running Total for Trial 313 |  |  | Running Total for Trial 314 |  |  | Running Total for Trial 315 |  |  | Running Total for Trial 316 |  |  | Running Total for Trial 317 |  |  | Running Total for Trial 318 |  |  | Running Total for Trial 319 |  |  | Running Total for Trial 320 |  |  | Running Total for Trial 321 |  |  | Running Total for Trial 322 |  |  | Running Total for Trial 323 |  |  | Running Total for Trial 324 |  |  | Running Total for Trial 325 |  |  | Running Total for Trial 326 |  |  | Running Total for Trial 327 |  |  | Running Total for Trial 328 |  |  | Running Total for Trial 329 |  |  | Running Total for Trial 330 |  |  | Running Total for Trial 331 |  |  | Running Total for Trial 332 |  |  | Running Total for Trial 333 |  |  | Running Total for Trial 334 |  |  | Running Total for Trial 335 |  |  | Running Total for Trial 336 |  |  | Running Total for Trial 337 |  |  | Running Total for Trial 338 |  |  | Running Total for Trial 339 |  |  | Running Total for Trial 340 |  |  | Running Total for Trial 341 |  |  | Running Total for Trial 342 |  |  | Running Total for Trial 343 |  |  | Running Total for Trial 344 |  |  | Running Total for Trial 345 |  |  | Running Total for Trial 346 |  |  | Running Total for Trial 347 |  |  | Running Total for Trial 348 |  |  | Running Total for Trial 349 |  |  | Running Total for Trial 350 |  |  | Running Total for Trial 351 |  |  | Running Total for Trial 352 |  |  | Running Total for Trial 353 |  |  | Running Total for Trial 354 |  |  | Running Total for Trial 355 |  |  | Running Total for Trial 356 |  |  | Running Total for Trial 357 |  |  | Running Total for Trial 358 |  |  | Running Total for Trial 359 |  |  | Running Total for Trial 360 |  |  | Running Total for Trial 361 |  |  | Running Total for Trial 362 |  |  | Running Total for Trial 363 |  |  | Running Total for Trial 364 |  |  | Running Total for Trial 365 |  |  | Running Total for Trial 366 |  |  | Running Total for Trial 367 |  |  | Running Total for Trial 368 |  |  | Running Total for Trial 369 |  |  | Running Total for Trial 370 |  |  | Running Total for Trial 371 |  |  | Running Total for Trial 372 |  |  | Running Total for Trial 373 |  |  | Running Total for Trial 374 |  |  | Running Total for Trial 375 |  |  | Running Total for Trial 376 |  |  | Running Total for Trial 377 |  |  | Running Total for Trial 378 |  |  | Running Total for Trial 379 |  |  | Running Total for Trial 380 |  |  | Running Total for Trial 381 |  |  | Running Total for Trial 382 |  |  | Running Total for Trial 383 |  |  | Running Total for Trial 384 |  |  | Running Total for Trial 385 |  |  | Running Total for Trial 386 |  |  | Running Total for Trial 387 |  |  | Running Total for Trial 388 |  |  | Running Total for Trial 389 |  |  | Running Total for Trial 390 |  |  | Running Total for Trial 391 |  |  | Running Total for Trial 392 |  |  | Running Total for Trial 393 |  |  | Running Total for Trial 394 |  |  | Running Total for Trial 395 |  |  | Running Total for Trial 396 |  |  | Running Total for Trial 397 |  |  | Running Total for Trial 398 |  |  | Running Total for Trial 399 |  |  | Running Total for Trial 400 |  |  | Running Total for Trial 401 |  |  | Running Total for Trial 402 |  |  | Running Total for Trial 403 |  |  | Running Total for Trial 404 |  |  | Running Total for Trial 405 |  |  | Running Total for Trial 406 |  |  | Running Total for Trial 407 |  |  | Running Total for Trial 408 |  |  | Running Total for Trial 409 |  |  | Running Total for Trial 410 |  |  | Running Total for Trial 411 |  |  | Running Total for Trial 412 |  |  | Running Total for Trial 413 |  |  | Running Total for Trial 414 |  |  | Running Total for Trial 415 |  |  | Running Total for Trial 416 |  |  | Running Total for Trial 417 |  |  | Running Total for Trial 418 |  |  | Running Total for Trial 419 |  |  | Running Total for Trial 420 |  |  | Running Total for Trial 421 |  |  | Running Total for Trial 422 |  |  | Running Total for Trial 423 |  |  | Running Total for Trial 424 |  |  | Running Total for Trial 425 |  |  | Running Total for Trial 426 |  |  | Running Total for Trial 427 |  |  | Running Total for Trial 428 |  |  | Running Total for Trial 429 |  |  | Running Total for Trial 430 |  |  | Running Total for Trial 431 |  |  | Running Total for Trial 432 |  |  | Running Total for Trial 433 |  |  | Running Total for Trial 434 |  |  | Running Total for Trial 435 |  |  | Running Total for Trial 436 |  |  | Running Total for Trial 437 |  |  | Running Total for Trial 438 |  |  | Running Total for Trial 439 |  |  | Running Total for Trial 440 |  |  | Running Total for Trial 441 |  |  | Running Total for Trial 442 |  |  | Running Total for Trial 443 |  |  | Running Total for Trial 444 |  |  | Running Total for Trial 445 |  |  | Running Total for Trial 446 |  |  | Running Total for Trial 447 |  |  | Running Total for Trial 448 |  |  | Running Total for Trial 449 |  |  | Running Total for Trial 450 |  |  | Running Total for Trial 451 |  |  | Running Total for Trial 452 |  |  | Running Total for Trial 453 |  |  | Running Total for Trial 454 |  |  | Running Total for Trial 455 |  |  | Running Total for Trial 456 |  |  | Running Total for Trial 457 |  |  | Running Total for Trial 458 |  |  | Running Total for Trial 459 |  |  | Running Total for Trial 460 |  |  | Running Total for Trial 461 |  |  | Running Total for Trial 462 |  |  | Running Total for Trial 463 |  |  | Running Total for Trial 464 |  |  | Running Total for Trial 465 |  |  | Running Total for Trial 466 |  |  | Running Total for Trial 467 |  |  | Running Total for Trial 468 |  |  | Running Total for Trial 469 |  |  | Running Total for Trial 470 |  |  | Running Total for Trial 471 |  |  | Running Total for Trial 472 |  |  | Running Total for Trial 473 |  |  | Running Total for Trial 474 |  |  | Running Total for Trial 475 |  |  | Running Total for Trial 476 |  |  | Running Total for Trial 477 |  |  | Running Total for Trial 478 |  |  | Running Total for Trial 479 |  |  | Running Total for Trial 480 |  |  | Running Total for Trial 481 |  |  | Running Total for Trial 482 |  |  | Running Total for Trial 483 |  |  | Running Total for Trial 484 |  |  | Running Total for Trial 485 |  |  | Running Total for Trial 486 |  |  | Running Total for Trial 487 |  |  | Running Total for Trial 488 |  |  | Running Total for Trial 489 |  |  | Running Total for Trial 490 |  |  | Running Total for Trial 491 |  |  | Running Total for Trial 492 |  |  | Running Total for Trial 493 |  |  | Running Total for Trial 494 |  |  | Running Total for Trial 495 |  |  | Running Total for Trial 496 |  |  | Running Total for Trial 497 |  |  | Running Total for Trial 498 |  |  | Running Total for Trial 499 |  |  | Running Total for Trial 500 |  |  | Running Total for Trial 501 |  |  | Running Total for Trial 502 |  |  | Running Total for Trial 503 |  |  | Running Total for Trial 504 |  |  | Running Total for Trial 505 |  |  | Running Total for Trial 506 |  |  | Running Total for Trial 507 |  |  | Running Total for Trial 508 |  |  | Running Total for Trial 509 |  |  | Running Total for Trial 510 |  |  | Running Total for Trial 511 |  |  | Running Total for Trial 512 |  |  | Running Total for Trial 513 |  |  | Running Total for Trial 514 |  |  | Running Total for Trial 515 |  |  | Running Total for Trial 516 |  |  | Running Total for Trial 517 |  |  | Running Total for Trial 518 |  |  | Running Total for Trial 519 |  |  | Running Total for Trial 520 |  |  | Running Total for Trial 521 |  |  | Running Total for Trial 522 |  |  | Running Total for Trial 523 |  |  | Running Total for Trial 524 |  |  | Running Total for Trial 525 |  |  | Running Total for Trial 526 |  |  | Running Total for Trial 527 |  |  | Running Total for Trial 528 |  |  | Running Total for Trial 529 |  |  | Running Total for Trial 530 |  |  | Running Total for Trial 531 |  |  | Running Total for Trial 532 |  |  | Running Total for Trial 533 |  |  | Running Total for Trial 534 |  |  | Running Total for Trial 535 |  |  | Running Total for Trial 536 |  |  | Running Total for Trial 537 |  |  | Running Total for Trial 538 |  |  | Running Total for Trial 539 |  |  | Running Total for Trial 540 |  |  | Running Total for Trial 541 |  |  | Running Total for Trial 542 |  |  | Running Total for Trial 543 |  |  | Running Total for Trial 544 |  |  | Running Total for Trial 545 |  |  | Running Total for Trial 546 |  |  | Running Total for Trial 547 |  |  | Running Total for Trial 548 |  |  | Running Total for Trial 549 |  |  | Running Total for Trial 550 |  |  | Running Total for Trial 551 |  |  | Running Total for Trial 552 |  |  | Running Total for Trial 553 |  |  | Running Total for Trial 554 |  |  | Running Total for Trial 555 |  |  | Running Total for Trial 556 |  |  | Running Total for Trial 557 |  |  | Running Total for Trial 558 |  |  | Running Total for Trial 559 |  |  | Running Total for Trial 560 |  |  | Running Total for Trial 561 |  |  | Running Total for Trial 562 |  |  | Running Total for Trial 563 |  |  | Running Total for Trial 564 |  |  | Running Total for Trial 565 |  |  | Running Total for Trial 566 |  |  | Running Total for Trial 567 |  |  | Running Total for Trial 568 |  |  | Running Total for Trial 569 |  |  | Running Total for Trial 570 |  |  | Running Total for Trial 571 |  |  | Running Total for Trial 572 |  |  | Running Total for Trial 573 |  |  | Running Total for Trial 574 |  |  | Running Total for Trial 575 |  |  | Running Total for Trial 576 |  |  | Running Total for Trial 577 |  |  | Running Total for Trial 578 |  |  | Running Total for Trial 579 |  |  | Running Total for Trial 580 |  |  | Running Total for Trial 581 |  |  | Running Total for Trial 582 |  |  | Running Total for Trial 583 |  |  | Running Total for Trial 584 |  |  | Running Total for Trial 585 |  |  | Running Total for Trial 586 |  |  | Running Total for Trial 587 |  |  | Running Total for Trial 588 |  |  | Running Total for Trial 589 |  |  | Running Total for Trial 590 |  |  | Running Total for Trial 591 |  |  | Running Total for Trial 592 |  |  | Running Total for Trial 593 |  |  | Running Total for Trial 594 |  |  | Running Total for Trial 595 |  |  | Running Total for Trial 596 |  |  | Running Total for Trial 597 |  |  | Running Total for Trial 598 |  |  | Running Total for Trial 599 |  |  | Running Total for Trial 600 |  |  | Running Total for Trial 601 |  |  | Running Total for Trial 602 |  |  | Running Total for Trial 603 |  |  | Running Total for Trial 604 |  |  | Running Total for Trial 605 |  |  | Running Total for Trial 606 |  |  | Running Total for Trial 607 |  |  | Running Total for Trial 608 |  |  | Running Total for Trial 609 |  |  | Running Total for Trial 610 |  |  | Running Total for Trial 611 |  |  | Running Total for Trial 612 |  |  | Running Total for Trial 613 |  |  | Running Total for Trial 614 |  |  | Running Total for Trial 615 |  |  | Running Total for Trial 616 |  |  | Running Total for Trial 617 |  |  | Running Total for Trial 618 |  |  | Running Total for Trial 619 |  |  | Running Total for Trial 620 |  |  | Running Total for Trial 621 |  |  | Running Total for Trial 622 |  |  | Running Total for Trial 623 |  |  | Running Total for Trial 624 |  |  | Running Total for Trial 625 |  |  | Running Total for Trial 626 |  |  | Running Total for Trial 627 |  |  | Running Total for Trial 628 |  |  | Running Total for Trial 629 |  |  | Running Total for Trial 630 |  |  | Running Total for Trial 631 |  |  | Running Total for Trial 632 |  |  | Running Total for Trial 633 |  |  | Running Total for Trial 634 |  |  | Running Total for Trial 635 |  |  | Running Total for Trial 636 |  |  | Running Total for Trial 637 |  |  | Running Total for Trial 638 |  |  | Running Total for Trial 639 |  |  | Running Total for Trial 640 |  |  | Running Total for Trial 641 |  |  | Running Total for Trial 642 |  |  | Running Total for Trial 643 |  |  | Running Total for Trial 644 |  |  | Running Total for Trial 645 |  |  | Running Total for Trial 646 |  |  | Running Total for Trial 647 |  |  | Running Total for Trial 648 |  |  | Running Total for Trial 649 |  |  | Running Total for Trial 650 |  |  | Running Total for Trial 651 |  |  | Running Total for Trial 652 |  |  | Running Total for Trial 653 |  |  | Running Total for Trial 654 |  |  | Running Total for Trial 655 |  |  | Running Total for Trial 656 |  |  | Running Total for Trial 657 |  |  | Running Total for Trial 658 |  |  | Running Total for Trial 659 |  |  | Running Total for Trial 660 |  |  | Running Total for Trial 661 |  |  | Running Total for Trial 662 |  |  | Running Total for Trial 663 |  |  | Running Total for Trial 664 |  |  | Running Total for Trial 665 |  |  | Running Total for Trial 666 |  |  | Running Total for Trial 667 |  |  | Running Total for Trial 668 |  |  | Running Total for Trial 669 |  |  | Running Total for Trial 670 |  |  | Running Total for Trial 671 |  |  | Running Total for Trial 672 |  |  | Running Total for Trial 673 |  |  | Running Total for Trial 674 |  |  | Running Total for Trial 675 |  |  | Running Total for Trial 676 |  |  | Running Total for Trial 677 |  |  | Running Total for Trial 678 |  |  | Running Total for Trial 679 |  |  | Running Total for Trial 680 |  |  | Running Total for Trial 681 |  |  | Running Total for Trial 682 |  |  | Running Total for Trial 683 |  |  | Running Total for Trial 684 |  |  | Running Total for Trial 685 |  |  | Running Total for Trial 686 |  |  | Running Total for Trial 687 |  |  | Running Total for Trial 688 |  |  | Running Total for Trial 689 |  |  | Running Total for Trial 690 |  |  | Running Total for Trial 691 |  |  | Running Total for Trial 692 |  |  | Running Total for Trial 693 |  |  | Running Total for Trial 694 |  |  | Running Total for Trial 695 |  |  | Running Total for Trial 696 |  |  | Running Total for Trial 697 |  |  | Running Total for Trial 698 |  |  | Running Total for Trial 699 |  |  | Running Total for Trial 700 |  |  | Running Total for Trial 701 |  |  | Running Total for Trial 702 |  |  | Running Total for Trial 703 |  |  | Running Total for Trial 704 |  |  | Running Total for Trial 705 |  |  | Running Total for Trial 706 |  |  | Running Total for Trial 707 |  |  | Running Total for Trial 708 |  |  | Running Total for Trial 709 |  |  | Running Total for Trial 710 |  |  | Running Total for Trial 711 |  |  | Running Total for Trial 712 |  |  | Running Total for Trial 713 |  |  | Running Total for Trial 714 |  |  | Running Total for Trial 715 |  |  | Running Total for Trial 716 |  |  | Running Total for Trial 717 |  |  | Running Total for Trial 718 |  |  | Running Total for Trial 719 |  |  | Running Total for Trial 720 |  |  | Running Total for Trial 721 |  |  | Running Total for Trial 722 |  |  | Running Total for Trial 723 |  |  | Running Total for Trial 724 |  |  | Running Total for Trial 725 |  |  | Running Total for Trial 726 |  |  | Running Total for Trial 727 |  |  | Running Total for Trial 728 |  |  | Running Total for Trial 729 |  |  | Running Total for Trial 730 |  |  | Running Total for Trial 731 |  |  | Running Total for Trial 732 |  |  | Running Total for Trial 733 |  |  | Running Total for Trial 734 |  |  | Running Total for Trial 735 |  |  | Running Total for Trial 736 |  |  | Running Total for Trial 737 |  |  | Running Total for Trial 738 |  |  | Running Total for Trial 739 |  |  | Running Total for Trial 740 |  |  | Running Total for Trial 741 |  |  | Running Total for Trial 742 |  |  | Running Total for Trial 743 |  |  | Running Total for Trial 744 |  |  | Running Total for Trial 745 |  |  | Running Total for Trial 746 |  |  | Running Total for Trial 747 |  |  | Running Total for Trial 748 |  |  | Running Total for Trial 749 |  |  | Running Total for Trial 750 |  |  | Running Total for Trial 751 |  |  | Running Total for Trial 752 |  |  | Running Total for Trial 753 |  |  | Running Total for Trial 754 |  |  | Running Total for Trial 755 |  |  | Running Total for Trial 756 |  |  | Running Total for Trial 757 |  |  | Running Total for Trial 758 |  |  | Running Total for Trial 759 |  |  | Running Total for Trial 760 |  |  | Running Total for Trial 761 |  |  | Running Total for Trial 762 |  |  | Running Total for Trial 763 |  |  | Running Total for Trial 764 |  |  | Running Total for Trial 765 |  |  | Running Total for Trial 766 |  |  | Running Total for Trial 767 |  |  | Running Total for Trial 768 |  |  | Running Total for Trial 769 |  |  | Running Total for Trial 770 |  |  | Running Total for Trial 771 |  |  | Running Total for Trial 772 |  |  | Running Total for Trial 773 |  |  | Running Total for Trial 774 |  |  | Running Total for Trial 775 |  |  | Running Total for Trial 776 |  |  | Running Total for Trial 777 |  |  | Running Total for Trial 778 |  |  | Running Total for Trial 779 |  |  | Running Total for Trial 780 |  |  | Running Total for Trial 781 |  |  | Running Total for Trial 782 |  |  | Running Total for Trial 783 |  |  | Running Total for Trial 784 |  |  | Running Total for Trial 785 |  |  | Running Total for Trial 786 |  |  | Running Total for Trial 787 |  |  | Running Total for Trial 788 |  |  | Running Total for Trial 789 |  |  | Running Total for Trial 790 |  |  | Running Total for Trial 791 |  |  | Running Total for Trial 792 |  |  | Running Total for Trial 793 |  |  | Running Total for Trial 794 |  |  | Running Total for Trial 795 |  |  | Running Total for Trial 796 |  |  | Running Total for Trial 797 |  |  | Running Total for Trial 798 |  |  | Running Total for Trial 799 |  |  | Running Total for Trial 800 |  |  | Running Total for Trial 801 |  |  | Running Total for Trial 802 |  |  | Running Total for Trial 803 |  |  | Running Total for Trial 804 |  |  | Running Total for Trial 805 |  |  | Running Total for Trial 806 |  |  | Running Total for Trial 807 |  |  | Running Total for Trial 808 |  |  | Running Total for Trial 809 |  |  | Running Total for Trial 810 |  |  | Running Total for Trial 811 |  |  | Running Total for Trial 812 |  |  | Running Total for Trial 813 |  |  | Running Total for Trial 814 |  |  | Running Total for Trial 815 |  |  | Running Total for Trial 816 |  |  | Running Total for Trial 817 |  |  | Running Total for Trial 818 |  |  | Running Total for Trial 819 |  |  | Running Total for Trial 820 |  |  | Running Total for Trial 821 |  |  | Running Total for Trial 822 |  |  | Running Total for Trial 823 |  |  | Running Total for Trial 824 |  |  | Running Total for Trial 825 |  |  | Running Total for Trial 826 |  |  | Running Total for Trial 827 |  |  | Running Total for Trial 828 |  |  | Running Total for Trial 829 |  |  | Running Total for Trial 830 |  |  | Running Total for Trial 831 |  |  | Running Total for Trial 832 |  |  | Running Total for Trial 833 |  |  | Running Total for Trial 834 |  |  | Running Total for Trial 835 |  |  | Running Total for Trial 836 |  |  | Running Total for Trial 837 |  |  | Running Total for Trial 838 |  |  | Running Total for Trial 839 |  |  | Running Total for Trial 840 |  |  | Running Total for Trial 841 |  |  | Running Total for Trial 842 |  |  | Running Total for Trial 843 |  |  | Running Total for Trial 844 |  |  | Running Total for Trial 845 |  |  | Running Total for Trial 846 |  |  | Running Total for Trial 847 |  |  | Running Total for Trial 848 |  |  | Running Total for Trial 849 |  |  | Running Total for Trial 850 |  |  | Running Total for Trial 851 |  |  | Running Total for Trial 852 |  |  | Running Total for Trial 853 |  |  | Running Total for Trial 854 |  |  | Running Total for Trial 855 |  |  | Running Total for Trial 856 |  |  | Running Total for Trial 857 |  |  | Running Total for Trial 858 |  |  | Running Total for Trial 859 |  |  | Running Total for Trial 860 |  |  | Running Total for Trial 861 |  |  | Running Total for Trial 862 |  |  | Running Total for Trial 863 |  |  | Running Total for Trial 864 |  |  | Running Total for Trial 865 |  |  | Running Total for Trial 866 |  |  | Running Total for Trial 867 |  |  | Running Total for Trial 868 |  |  | Running Total for Trial 869 |  |  | Running Total for Trial 870 |  |  | Running Total for Trial 871 |  |  | Running Total for Trial 872 |  |  | Running Total for Trial 873 |  |  | Running Total for Trial 874 |  |  | Running Total for Trial 875 |  |  | Running Total for Trial 876 |  |  | Running Total for Trial 877 |  |  | Running Total for Trial 878 |  |  | Running Total for Trial 879 |  |  | Running Total for Trial 880 |  |  | Running Total for Trial 881 |  |  | Running Total for Trial 882 |  |  | Running Total for Trial 883 |  |  | Running Total for Trial 884 |  |  | Running Total for Trial 885 |  |  | Running Total for Trial 886 |  |  | Running Total for Trial 887 |  |  | Running Total for Trial 888 |  |  | Running Total for Trial 889 |  |  | Running Total for Trial 890 |  |  | Running Total for Trial 891 |  |  | Running Total for Trial 892 |  |  | Running Total for Trial 893 |  |  | Running Total for Trial 894 |  |  | Running Total for Trial 895 |  |  | Running Total for Trial 896 |  |  | Running Total for Trial 897 |  |  | Running Total for Trial 898 |  |  | Running Total for Trial 899 |  |  | Running Total for Trial 900 |  |  | Running Total for Trial 901 |  |  | Running Total for Trial 902 |  |  | Running Total for Trial 903 |  |  | Running Total for Trial 904 |  |  | Running Total for Trial 905 |  |  | Running Total for Trial 906 |  |  | Running Total for Trial 907 |  |  | Running Total for Trial 908 |  |  | Running Total for Trial 909 |  |  | Running Total for Trial 910 |  |  | Running Total for Trial 911 |  |  | Running Total for Trial 912 |  |  | Running Total for Trial 913 |  |  | Running Total for Trial 914 |  |  | Running Total for Trial 915 |  |  | Running Total for Trial 916 |  |  | Running Total for Trial 917 |  |  | Running Total for Trial 918 |  |  | Running Total for Trial 919 |  |  | Running Total for Trial 920 |  |  | Running Total for Trial 921 |  |  | Running Total for Trial 922 |  |  | Running Total for Trial 923 |  |  | Running Total for Trial 924 |  |  | Running Total for Trial 925 |  |  | Running Total for Trial 926 |  |  | Running Total for Trial 927 |  |  | Running Total for Trial 928 |  |  | Running Total for Trial 929 |  |  | Running Total for Trial 930 |  |  | Running Total for Trial 931 |  |  | Running Total for Trial 932 |  |  | Running Total for Trial 933 |  |  | Running Total for Trial 934 |  |  | Running Total for Trial 935 |  |  | Running Total for Trial 936 |  |  | Running Total for Trial 937 |  |  | Running Total for Trial 938 |  |  | Running Total for Trial 939 |  |  | Running Total for Trial 940 |  |  | Running Total for Trial 941 |  |  | Running Total for Trial 942 |  |  | Running Total for Trial 943 |  |  | Running Total for Trial 944 |  |  | Running Total for Trial 945 |  |  | Running Total for Trial 946 |  |  | Running Total for Trial 947 |  |  | Running Total for Trial 948 |  |  | Running Total for Trial 949 |  |  | Running Total for Trial 950 |  |  | Running Total for Trial 951 |  |  | Running Total for Trial 952 |  |  | Running Total for Trial 953 |  |  | Running Total for Trial 954 |  |  | Running Total for Trial 955 |  |  | Running Total for Trial 956 |  |  | Running Total for Trial 957 |  |  | Running Total for Trial 958 |  |  | Running Total for Trial 959 |  |  | Running Total for Trial 960 |  |  | Running Total for Trial 961 |  |  | Running Total for Trial 962 |  |  | Running Total for Trial 963 |  |  | Running Total for Trial 964 |  |  | Running Total for Trial 965 |  |  | Running Total for Trial 966 |  |  | Running Total for Trial 967 |  |  | Running Total for Trial 968 |  |  | Running Total for Trial 969 |  |  | Running Total for Trial 970 |  |  | Running Total for Trial 971 |  |  | Running Total for Trial 972 |  |  | Running Total for Trial 973 |  |  | Running Total for Trial 974 |  |  | Running Total for Trial 975 |  |  | Running Total for Trial 976 |  |  | Running Total for Trial 977 |  |  | Running Total for Trial 978 |  |  | Running Total for Trial 979 |  |  | Running Total for Trial 980 |  |  | Running Total for Trial 981 |  |  | Running Total for Trial 982 |  |  | Running Total for Trial 983 |  |  | Running Total for Trial 984 |  |  | Running Total for Trial 985 |  |  | Running Total for Trial 986 |  |  | Running Total for Trial 987 |  |  | Running Total for Trial 988 |  |  | Running Total for Trial 989 |  |  | Running Total for Trial 990 |  |  | Running Total for Trial 991 |  |  | Running Total for Trial 992 |  |  | Running Total for Trial 993 |  |  | Running Total for Trial 994 |  |  | Running Total for Trial 995 |  |  | Running Total for Trial 996 |  |  | Running Total for Trial 997 |  |  | Running Total for Trial 998 |  |  | Running Total for Trial 999 |  |  | Running Total for Trial 1000
1 |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47
2 |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73
3 |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112
4 |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133
5 |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172
6 |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187
7 |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216
8 |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240
9 |  | 279 |  |  | 261 |  |  | 255 |  |  | 266 |  |  | 261 |  |  | 279 |  |  | 264 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 264 |  |  | 266 |  |  | 261 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 261 |  |  | 287 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 266 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 266 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 266 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 264 |  |  | 269 |  |  | 255 |  |  | 261 |  |  | 261 |  |  | 255 |  |  | 255 |  |  | 287 |  |  | 266 |  |  | 287 |  |  | 287 |  |  | 287 |  |  | 287 |  |  | 255 |  |  | 287 |  |  | 266 |  |  | 255 |  |  | 261 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 266 |  |  | 261 |  |  | 269 |  |  | 264 |  |  | 269 |  |  | 255 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 255 |  |  | 255 |  |  | 266 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 266 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 255 |  |  | 287 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 266 |  |  | 264 |  |  | 266 |  |  | 287 |  |  | 266 |  |  | 264 |  |  | 266 |  |  | 266 |  |  | 264 |  |  | 269 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 287 |  |  | 261 |  |  | 266 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 264 |  |  | 261 |  |  | 264 |  |  | 255 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 261 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 261 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 255 |  |  | 255 |  |  | 264 |  |  | 255 |  |  | 261 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 269 |  |  | 261 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 287 |  |  | 261 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 269 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 264 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 255 |  |  | 261 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 264 |  |  | 255 |  |  | 261 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 261 |  |  | 266 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 287 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 266 |  |  | 287 |  |  | 287 |  |  | 266 |  |  | 264 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 269 |  |  | 255 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 255 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 261 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 264 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 264 |  |  | 266 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 266 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 279 |  |  | 264 |  |  | 261 |  |  | 261 |  |  | 264 |  |  | 266 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 287 |  |  | 266 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 261 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 264 |  |  | 264 |  |  | 269 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 261 |  |  | 261 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 264 |  |  | 287 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 255 |  |  | 255 |  |  | 264 |  |  | 264 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 269 |  |  | 266 |  |  | 264 |  |  | 264 |  |  | 279 |  |  | 255 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 264 |  |  | 269 |  |  | 269 |  |  | 264 |  |  | 287 |  |  | 287 |  |  | 287 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 264 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 264 |  |  | 266 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 261 |  |  | 266 |  |  | 255 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 287 |  |  | 266 |  |  | 255 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 287 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 266 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 287 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 287 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 266 |  |  | 266 |  |  | 287 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 269 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 264 |  |  | 287 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 264 |  |  | 264 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 261 |  |  | 264 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 287 |  |  | 266 |  |  | 264 |  |  | 287 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 264 |  |  | 261 |  |  | 255 |  |  | 261 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 264 |  |  | 261 |  |  | 261 |  |  | 261 |  |  | 261 |  |  | 264 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 287 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 261 |  |  | 266 |  |  | 261 |  |  | 264 |  |  | 269 |  |  | 264 |  |  | 261 |  |  | 287 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 266 |  |  | 264 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 261 |  |  | 266 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 269 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 287 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 269 |  |  | 261 |  |  | 269 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 261 |  |  | 266 |  |  | 269 |  |  | 261 |  |  | 255 |  |  | 266 |  |  | 269 |  |  | 269 |  |  | 266 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 264 |  |  | 287 |  |  | 287 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 255 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 266 |  |  | 255 |  |  | 264 |  |  | 261 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 261 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 255 |  |  | 266 |  |  | 261 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 261 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 261 |  |  | 287 |  |  | 261 |  |  | 261 |  |  | 269 |  |  | 266 |  |  | 261 |  |  | 255 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 264 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 269 |  |  | 269 |  |  | 261 |  |  | 264 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 261 |  |  | 255 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 264 |  |  | 266 |  |  | 269 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 264 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 255 |  |  | 269 |  |  | 255 |  |  | 287 |  |  | 255 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 269 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 255 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 287 |  |  | 261 |  |  | 269 |  |  | 264 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 255 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 266 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 269 |  |  | 266 |  |  | 264 |  |  | 261 |  |  | 264 |  |  | 269 |  |  | 261 |  |  | 264 |  |  | 255 |  |  | 287 |  |  | 287 |  |  | 266 |  |  | 261 |  |  | 264 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 255 |  |  | 264 |  |  | 264 |  |  | 261 |  |  | 266 |  |  | 279 |  |  | 269 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 264 |  |  | 255 |  |  | 266 |  |  | 266 |  |  | 261 |  |  | 266 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 264 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 255 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 264 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 279 |  |  | 255
10 |  | 303 |  |  | 285 |  |  | 281 |  |  | 305 |  |  | 287 |  |  | 318 |  |  | 293 |  |  | 279 |  |  | 318 |  |  | 295 |  |  | 279 |  |  | 305 |  |  | 284 |  |  | 318 |  |  | 287 |  |  | 305 |  |  | 326 |  |  | 284 |  |  | 318 |  |  | 294 |  |  | 326 |  |  | 285 |  |  | 326 |  |  | 316 |  |  | 281 |  |  | 311 |  |  | 292 |  |  | 287 |  |  | 295 |  |  | 334 |  |  | 318 |  |  | 300 |  |  | 303 |  |  | 308 |  |  | 295 |  |  | 308 |  |  | 311 |  |  | 316 |  |  | 300 |  |  | 303 |  |  | 287 |  |  | 298 |  |  | 290 |  |  | 293 |  |  | 318 |  |  | 302 |  |  | 293 |  |  | 313 |  |  | 303 |  |  | 305 |  |  | 293 |  |  | 290 |  |  | 295 |  |  | 294 |  |  | 303 |  |  | 308 |  |  | 290 |  |  | 308 |  |  | 302 |  |  | 290 |  |  | 308 |  |  | 270 |  |  | 270 |  |  | 311 |  |  | 292 |  |  | 308 |  |  | 326 |  |  | 313 |  |  | 302 |  |  | 294 |  |  | 308 |  |  | 290 |  |  | 281 |  |  | 282 |  |  | 305 |  |  | 302 |  |  | 308 |  |  | 290 |  |  | 316 |  |  | 288 |  |  | 326 |  |  | 326 |  |  | 287 |  |  | 300 |  |  | 313 |  |  | 287 |  |  | 284 |  |  | 293 |  |  | 284 |  |  | 302 |  |  | 294 |  |  | 316 |  |  | 318 |  |  | 302 |  |  | 284 |  |  | 318 |  |  | 302 |  |  | 292 |  |  | 270 |  |  | 294 |  |  | 292 |  |  | 290 |  |  | 276 |  |  | 300 |  |  | 302 |  |  | 293 |  |  | 284 |  |  | 300 |  |  | 305 |  |  | 308 |  |  | 308 |  |  | 287 |  |  | 300 |  |  | 279 |  |  | 302 |  |  | 295 |  |  | 276 |  |  | 308 |  |  | 276 |  |  | 313 |  |  | 318 |  |  | 313 |  |  | 316 |  |  | 276 |  |  | 302 |  |  | 298 |  |  | 300 |  |  | 285 |  |  | 287 |  |  | 303 |  |  | 313 |  |  | 326 |  |  | 290 |  |  | 288 |  |  | 281 |  |  | 292 |  |  | 290 |  |  | 298 |  |  | 300 |  |  | 298 |  |  | 279 |  |  | 308 |  |  | 326 |  |  | 294 |  |  | 308 |  |  | 270 |  |  | 298 |  |  | 287 |  |  | 313 |  |  | 279 |  |  | 300 |  |  | 302 |  |  | 276 |  |  | 281 |  |  | 290 |  |  | 302 |  |  | 284 |  |  | 326 |  |  | 284 |  |  | 318 |  |  | 311 |  |  | 285 |  |  | 311 |  |  | 276 |  |  | 294 |  |  | 290 |  |  | 318 |  |  | 326 |  |  | 292 |  |  | 303 |  |  | 316 |  |  | 282 |  |  | 308 |  |  | 300 |  |  | 305 |  |  | 303 |  |  | 308 |  |  | 295 |  |  | 302 |  |  | 294 |  |  | 285 |  |  | 290 |  |  | 326 |  |  | 281 |  |  | 294 |  |  | 303 |  |  | 308 |  |  | 290 |  |  | 293 |  |  | 290 |  |  | 284 |  |  | 303 |  |  | 298 |  |  | 305 |  |  | 287 |  |  | 294 |  |  | 305 |  |  | 298 |  |  | 295 |  |  | 311 |  |  | 311 |  |  | 305 |  |  | 276 |  |  | 294 |  |  | 326 |  |  | 284 |  |  | 294 |  |  | 294 |  |  | 303 |  |  | 279 |  |  | 290 |  |  | 279 |  |  | 302 |  |  | 303 |  |  | 300 |  |  | 298 |  |  | 313 |  |  | 305 |  |  | 300 |  |  | 326 |  |  | 281 |  |  | 326 |  |  | 279 |  |  | 308 |  |  | 290 |  |  | 316 |  |  | 285 |  |  | 294 |  |  | 303 |  |  | 302 |  |  | 311 |  |  | 287 |  |  | 284 |  |  | 295 |  |  | 318 |  |  | 287 |  |  | 276 |  |  | 294 |  |  | 290 |  |  | 334 |  |  | 308 |  |  | 285 |  |  | 290 |  |  | 318 |  |  | 285 |  |  | 290 |  |  | 311 |  |  | 293 |  |  | 326 |  |  | 318 |  |  | 276 |  |  | 302 |  |  | 285 |  |  | 300 |  |  | 302 |  |  | 303 |  |  | 318 |  |  | 302 |  |  | 287 |  |  | 293 |  |  | 276 |  |  | 287 |  |  | 308 |  |  | 300 |  |  | 318 |  |  | 308 |  |  | 316 |  |  | 303 |  |  | 295 |  |  | 282 |  |  | 305 |  |  | 294 |  |  | 318 |  |  | 290 |  |  | 300 |  |  | 308 |  |  | 290 |  |  | 305 |  |  | 287 |  |  | 305 |  |  | 282 |  |  | 303 |  |  | 311 |  |  | 295 |  |  | 288 |  |  | 294 |  |  | 326 |  |  | 302 |  |  | 298 |  |  | 292 |  |  | 303 |  |  | 318 |  |  | 279 |  |  | 281 |  |  | 326 |  |  | 318 |  |  | 308 |  |  | 294 |  |  | 313 |  |  | 334 |  |  | 303 |  |  | 285 |  |  | 281 |  |  | 326 |  |  | 284 |  |  | 270 |  |  | 308 |  |  | 270 |  |  | 300 |  |  | 313 |  |  | 318 |  |  | 316 |  |  | 276 |  |  | 318 |  |  | 311 |  |  | 288 |  |  | 303 |  |  | 290 |  |  | 294 |  |  | 290 |  |  | 292 |  |  | 302 |  |  | 326 |  |  | 287 |  |  | 288 |  |  | 305 |  |  | 287 |  |  | 293 |  |  | 282 |  |  | 334 |  |  | 294 |  |  | 311 |  |  | 305 |  |  | 293 |  |  | 294 |  |  | 285 |  |  | 303 |  |  | 318 |  |  | 318 |  |  | 308 |  |  | 270 |  |  | 326 |  |  | 270 |  |  | 298 |  |  | 284 |  |  | 303 |  |  | 287 |  |  | 303 |  |  | 326 |  |  | 313 |  |  | 290 |  |  | 308 |  |  | 303 |  |  | 284 |  |  | 288 |  |  | 279 |  |  | 300 |  |  | 279 |  |  | 308 |  |  | 288 |  |  | 326 |  |  | 326 |  |  | 294 |  |  | 303 |  |  | 279 |  |  | 290 |  |  | 326 |  |  | 305 |  |  | 294 |  |  | 308 |  |  | 300 |  |  | 284 |  |  | 290 |  |  | 308 |  |  | 293 |  |  | 300 |  |  | 290 |  |  | 300 |  |  | 285 |  |  | 311 |  |  | 294 |  |  | 318 |  |  | 295 |  |  | 282 |  |  | 303 |  |  | 313 |  |  | 300 |  |  | 303 |  |  | 290 |  |  | 276 |  |  | 287 |  |  | 334 |  |  | 281 |  |  | 302 |  |  | 305 |  |  | 294 |  |  | 279 |  |  | 326 |  |  | 284 |  |  | 288 |  |  | 318 |  |  | 279 |  |  | 282 |  |  | 300 |  |  | 285 |  |  | 281 |  |  | 294 |  |  | 300 |  |  | 305 |  |  | 292 |  |  | 326 |  |  | 326 |  |  | 287 |  |  | 302 |  |  | 292 |  |  | 318 |  |  | 326 |  |  | 281 |  |  | 326 |  |  | 326 |  |  | 282 |  |  | 285 |  |  | 287 |  |  | 270 |  |  | 300 |  |  | 326 |  |  | 293 |  |  | 293 |  |  | 279 |  |  | 284 |  |  | 305 |  |  | 292 |  |  | 303 |  |  | 290 |  |  | 300 |  |  | 290 |  |  | 316 |  |  | 285 |  |  | 318 |  |  | 284 |  |  | 298 |  |  | 318 |  |  | 308 |  |  | 290 |  |  | 270 |  |  | 305 |  |  | 313 |  |  | 326 |  |  | 308 |  |  | 313 |  |  | 294 |  |  | 290 |  |  | 288 |  |  | 334 |  |  | 318 |  |  | 288 |  |  | 294 |  |  | 276 |  |  | 300 |  |  | 294 |  |  | 308 |  |  | 318 |  |  | 308 |  |  | 318 |  |  | 326 |  |  | 305 |  |  | 285 |  |  | 326 |  |  | 311 |  |  | 334 |  |  | 326 |  |  | 281 |  |  | 313 |  |  | 276 |  |  | 302 |  |  | 293 |  |  | 303 |  |  | 308 |  |  | 270 |  |  | 305 |  |  | 295 |  |  | 281 |  |  | 311 |  |  | 288 |  |  | 318 |  |  | 294 |  |  | 300 |  |  | 305 |  |  | 284 |  |  | 326 |  |  | 294 |  |  | 318 |  |  | 279 |  |  | 308 |  |  | 295 |  |  | 305 |  |  | 308 |  |  | 305 |  |  | 303 |  |  | 316 |  |  | 284 |  |  | 303 |  |  | 334 |  |  | 308 |  |  | 334 |  |  | 298 |  |  | 290 |  |  | 294 |  |  | 318 |  |  | 294 |  |  | 288 |  |  | 276 |  |  | 326 |  |  | 334 |  |  | 293 |  |  | 303 |  |  | 303 |  |  | 326 |  |  | 290 |  |  | 305 |  |  | 300 |  |  | 300 |  |  | 326 |  |  | 293 |  |  | 318 |  |  | 282 |  |  | 305 |  |  | 294 |  |  | 305 |  |  | 281 |  |  | 308 |  |  | 313 |  |  | 270 |  |  | 293 |  |  | 308 |  |  | 281 |  |  | 318 |  |  | 318 |  |  | 294 |  |  | 293 |  |  | 282 |  |  | 300 |  |  | 308 |  |  | 294 |  |  | 302 |  |  | 308 |  |  | 285 |  |  | 308 |  |  | 279 |  |  | 284 |  |  | 300 |  |  | 326 |  |  | 292 |  |  | 302 |  |  | 284 |  |  | 290 |  |  | 318 |  |  | 281 |  |  | 302 |  |  | 308 |  |  | 318 |  |  | 308 |  |  | 300 |  |  | 300 |  |  | 313 |  |  | 305 |  |  | 311 |  |  | 294 |  |  | 316 |  |  | 294 |  |  | 302 |  |  | 308 |  |  | 318 |  |  | 290 |  |  | 302 |  |  | 316 |  |  | 276 |  |  | 308 |  |  | 287 |  |  | 295 |  |  | 334 |  |  | 302 |  |  | 308 |  |  | 294 |  |  | 308 |  |  | 303 |  |  | 294 |  |  | 316 |  |  | 318 |  |  | 326 |  |  | 303 |  |  | 326 |  |  | 281 |  |  | 318 |  |  | 282 |  |  | 298 |  |  | 295 |  |  | 326 |  |  | 285 |  |  | 326 |  |  | 294 |  |  | 313 |  |  | 308 |  |  | 288 |  |  | 313 |  |  | 308 |  |  | 316 |  |  | 316 |  |  | 285 |  |  | 311 |  |  | 294 |  |  | 290 |  |  | 326 |  |  | 279 |  |  | 293 |  |  | 279 |  |  | 318 |  |  | 318 |  |  | 290 |  |  | 290 |  |  | 300 |  |  | 288 |  |  | 313 |  |  | 313 |  |  | 300 |  |  | 313 |  |  | 326 |  |  | 270 |  |  | 295 |  |  | 282 |  |  | 287 |  |  | 326 |  |  | 295 |  |  | 303 |  |  | 334 |  |  | 334 |  |  | 305 |  |  | 318 |  |  | 287 |  |  | 308 |  |  | 288 |  |  | 290 |  |  | 302 |  |  | 290 |  |  | 298 |  |  | 316 |  |  | 284 |  |  | 318 |  |  | 294 |  |  | 308 |  |  | 308 |  |  | 279 |  |  | 282 |  |  | 282 |  |  | 285 |  |  | 285 |  |  | 285 |  |  | 305 |  |  | 295 |  |  | 318 |  |  | 294 |  |  | 305 |  |  | 294 |  |  | 300 |  |  | 316 |  |  | 311 |  |  | 313 |  |  | 334 |  |  | 318 |  |  | 281 |  |  | 294 |  |  | 287 |  |  | 292 |  |  | 300 |  |  | 303 |  |  | 308 |  |  | 311 |  |  | 300 |  |  | 326 |  |  | 308 |  |  | 318 |  |  | 287 |  |  | 294 |  |  | 294 |  |  | 316 |  |  | 276 |  |  | 311 |  |  | 303 |  |  | 326 |  |  | 294 |  |  | 295 |  |  | 288 |  |  | 308 |  |  | 281 |  |  | 318 |  |  | 284 |  |  | 305 |  |  | 300 |  |  | 313 |  |  | 295 |  |  | 285 |  |  | 300 |  |  | 316 |  |  | 308 |  |  | 300 |  |  | 318 |  |  | 300 |  |  | 313 |  |  | 290 |  |  | 294 |  |  | 305 |  |  | 302 |  |  | 298 |  |  | 326 |  |  | 292 |  |  | 281 |  |  | 316 |  |  | 300 |  |  | 308 |  |  | 285 |  |  | 305 |  |  | 303 |  |  | 303 |  |  | 276 |  |  | 305 |  |  | 316 |  |  | 287 |  |  | 302 |  |  | 281 |  |  | 316 |  |  | 298 |  |  | 290 |  |  | 276 |  |  | 282 |  |  | 302 |  |  | 313 |  |  | 281 |  |  | 303 |  |  | 290 |  |  | 305 |  |  | 303 |  |  | 305 |  |  | 326 |  |  | 285 |  |  | 311 |  |  | 302 |  |  | 308 |  |  | 318 |  |  | 279 |  |  | 294 |  |  | 308 |  |  | 279 |  |  | 279 |  |  | 285 |  |  | 293 |  |  | 302 |  |  | 281 |  |  | 294 |  |  | 311 |  |  | 300 |  |  | 294 |  |  | 305 |  |  | 294 |  |  | 287 |  |  | 276 |  |  | 276 |  |  | 290 |  |  | 316 |  |  | 270 |  |  | 305 |  |  | 276 |  |  | 290 |  |  | 308 |  |  | 318 |  |  | 300 |  |  | 308 |  |  | 279 |  |  | 300 |  |  | 293 |  |  | 270 |  |  | 294 |  |  | 287 |  |  | 326 |  |  | 300 |  |  | 290 |  |  | 293 |  |  | 305 |  |  | 308 |  |  | 294 |  |  | 316 |  |  | 270 |  |  | 308 |  |  | 305 |  |  | 316 |  |  | 279 |  |  | 285 |  |  | 300 |  |  | 326 |  |  | 326 |  |  | 298 |  |  | 294 |  |  | 290 |  |  | 305 |  |  | 318 |  |  | 326 |  |  | 300 |  |  | 298 |  |  | 298 |  |  | 298 |  |  | 308 |  |  | 303 |  |  | 326 |  |  | 294 |  |  | 308 |  |  | 308 |  |  | 276 |  |  | 318 |  |  | 318 |  |  | 295 |  |  | 303 |  |  | 295 |  |  | 316 |  |  | 305 |  |  | 290 |  |  | 302 |  |  | 318 |  |  | 290 |  |  | 303 |  |  | 285 |  |  | 318 |  |  | 300 |  |  | 302 |  |  | 284 |  |  | 303 |  |  | 305 |  |  | 293 |  |  | 308 |  |  | 290 |  |  | 326 |  |  | 293 |  |  | 316 |  |  | 294 |  |  | 313 |  |  | 318 |  |  | 318 |  |  | 308 |  |  | 311 |  |  | 300 |  |  | 290 |  |  | 276 |  |  | 300 |  |  | 303 |  |  | 293 |  |  | 308 |  |  | 308 |  |  | 300 |  |  | 276 |  |  | 293 |  |  | 284 |  |  | 326 |  |  | 294 |  |  | 300 |  |  | 276 |  |  | 318 |  |  | 303 |  |  | 298 |  |  | 293 |  |  | 326 |  |  | 282 |  |  | 318 |  |  | 300 |  |  | 287 |  |  | 270 |  |  | 308 |  |  | 313 |  |  | 308 |  |  | 300 |  |  | 302 |  |  | 326 |  |  | 276 |  |  | 284 |  |  | 285 |  |  | 326 |  |  | 279 |  |  | 298 |  |  | 300 |  |  | 305 |  |  | 284 |  |  | 318 |  |  | 316 |  |  | 308 |  |  | 276 |  |  | 326 |  |  | 311 |  |  | 326 |  |  | 290 |  |  | 290 |  |  | 300 |  |  | 305 |  |  | 284 |  |  | 298 |  |  | 281 |  |  | 303 |  |  | 290 |  |  | 311 |  |  | 284 |  |  | 290 |  |  | 279 |  |  | 276 |  |  | 316 |  |  | 311 |  |  | 305 |  |  | 300 |  |  | 311 |  |  | 318 |  |  | 305 |  |  | 308 |  |  | 284 |  |  | 302 |  |  | 287 |  |  | 326 |  |  | 308 |  |  | 290 |  |  | 318 |  |  | 326 |  |  | 316 |  |  | 305 |  |  | 318 |  |  | 318 |  |  | 326 |  |  | 303 |  |  | 290 |  |  | 308 |  |  | 285 |  |  | 300 |  |  | 284 |  |  | 276 |  |  | 303 |  |  | 292 |  |  | 308 |  |  | 279 |  |  | 285 |  |  | 285 |  |  | 285 |  |  | 292 |  |  | 318 |  |  | 308 |  |  | 311 |  |  | 279 |  |  | 326 |  |  | 311 |  |  | 285 |  |  | 326 |  |  | 300 |  |  | 298 |  |  | 287 |  |  | 308 |  |  | 294 |  |  | 305 |  |  | 294 |  |  | 279 |  |  | 305 |  |  | 270 |  |  | 288 |  |  | 279 |  |  | 294 |  |  | 292 |  |  | 290 |  |  | 285 |  |  | 290 |  |  | 282 |  |  | 334 |  |  | 326 |  |  | 300 |  |  | 285 |  |  | 294 |  |  | 288 |  |  | 318 |  |  | 293 |  |  | 326 |  |  | 290 |  |  | 303 |  |  | 302 |  |  | 300 |  |  | 290 |  |  | 270 |  |  | 276 |  |  | 288 |  |  | 276 |  |  | 318 |  |  | 282 |  |  | 311 |  |  | 303 |  |  | 308 |  |  | 294 |  |  | 308 |  |  | 308 |  |  | 276 |  |  | 308 |  |  | 279
11 |  | 327 |  |  | 324 |  |  | 296 |  |  | 352 |  |  | 302 |  |  | 333 |  |  | 314 |  |  | 318 |  |  | 365 |  |  | 342 |  |  | 326 |  |  | 352 |  |  | 331 |  |  | 339 |  |  | 326 |  |  | 320 |  |  | 352 |  |  | 305 |  |  | 344 |  |  | 341 |  |  | 365 |  |  | 324 |  |  | 350 |  |  | 355 |  |  | 307 |  |  | 332 |  |  | 331 |  |  | 313 |  |  | 334 |  |  | 358 |  |  | 347 |  |  | 324 |  |  | 350 |  |  | 347 |  |  | 319 |  |  | 323 |  |  | 350 |  |  | 337 |  |  | 315 |  |  | 329 |  |  | 302 |  |  | 324 |  |  | 316 |  |  | 332 |  |  | 333 |  |  | 341 |  |  | 322 |  |  | 334 |  |  | 332 |  |  | 334 |  |  | 332 |  |  | 314 |  |  | 321 |  |  | 333 |  |  | 329 |  |  | 332 |  |  | 329 |  |  | 355 |  |  | 349 |  |  | 329 |  |  | 347 |  |  | 317 |  |  | 309 |  |  | 358 |  |  | 339 |  |  | 332 |  |  | 341 |  |  | 352 |  |  | 341 |  |  | 333 |  |  | 332 |  |  | 305 |  |  | 305 |  |  | 303 |  |  | 344 |  |  | 323 |  |  | 355 |  |  | 314 |  |  | 345 |  |  | 335 |  |  | 350 |  |  | 365 |  |  | 334 |  |  | 324 |  |  | 334 |  |  | 326 |  |  | 308 |  |  | 314 |  |  | 313 |  |  | 317 |  |  | 309 |  |  | 331 |  |  | 347 |  |  | 341 |  |  | 305 |  |  | 344 |  |  | 323 |  |  | 318 |  |  | 317 |  |  | 318 |  |  | 313 |  |  | 305 |  |  | 323 |  |  | 315 |  |  | 341 |  |  | 317 |  |  | 310 |  |  | 339 |  |  | 326 |  |  | 337 |  |  | 337 |  |  | 313 |  |  | 347 |  |  | 326 |  |  | 341 |  |  | 321 |  |  | 315 |  |  | 347 |  |  | 302 |  |  | 328 |  |  | 365 |  |  | 334 |  |  | 363 |  |  | 323 |  |  | 326 |  |  | 337 |  |  | 329 |  |  | 309 |  |  | 334 |  |  | 342 |  |  | 337 |  |  | 373 |  |  | 314 |  |  | 312 |  |  | 307 |  |  | 331 |  |  | 314 |  |  | 337 |  |  | 347 |  |  | 327 |  |  | 300 |  |  | 323 |  |  | 341 |  |  | 318 |  |  | 337 |  |  | 299 |  |  | 313 |  |  | 326 |  |  | 352 |  |  | 318 |  |  | 329 |  |  | 323 |  |  | 315 |  |  | 296 |  |  | 329 |  |  | 341 |  |  | 299 |  |  | 341 |  |  | 305 |  |  | 357 |  |  | 358 |  |  | 324 |  |  | 358 |  |  | 305 |  |  | 309 |  |  | 316 |  |  | 333 |  |  | 347 |  |  | 331 |  |  | 342 |  |  | 363 |  |  | 321 |  |  | 347 |  |  | 339 |  |  | 326 |  |  | 332 |  |  | 332 |  |  | 324 |  |  | 328 |  |  | 318 |  |  | 311 |  |  | 311 |  |  | 341 |  |  | 307 |  |  | 309 |  |  | 324 |  |  | 337 |  |  | 314 |  |  | 332 |  |  | 311 |  |  | 308 |  |  | 350 |  |  | 345 |  |  | 352 |  |  | 326 |  |  | 341 |  |  | 334 |  |  | 327 |  |  | 342 |  |  | 358 |  |  | 350 |  |  | 344 |  |  | 291 |  |  | 333 |  |  | 355 |  |  | 313 |  |  | 323 |  |  | 323 |  |  | 327 |  |  | 300 |  |  | 337 |  |  | 326 |  |  | 317 |  |  | 342 |  |  | 326 |  |  | 324 |  |  | 360 |  |  | 320 |  |  | 339 |  |  | 347 |  |  | 328 |  |  | 341 |  |  | 326 |  |  | 329 |  |  | 337 |  |  | 337 |  |  | 306 |  |  | 333 |  |  | 350 |  |  | 331 |  |  | 326 |  |  | 302 |  |  | 323 |  |  | 324 |  |  | 342 |  |  | 313 |  |  | 305 |  |  | 318 |  |  | 337 |  |  | 358 |  |  | 329 |  |  | 324 |  |  | 319 |  |  | 365 |  |  | 314 |  |  | 305 |  |  | 332 |  |  | 332 |  |  | 365 |  |  | 365 |  |  | 291 |  |  | 331 |  |  | 324 |  |  | 324 |  |  | 341 |  |  | 324 |  |  | 357 |  |  | 317 |  |  | 334 |  |  | 332 |  |  | 323 |  |  | 311 |  |  | 323 |  |  | 321 |  |  | 347 |  |  | 355 |  |  | 340 |  |  | 329 |  |  | 334 |  |  | 297 |  |  | 331 |  |  | 341 |  |  | 357 |  |  | 311 |  |  | 347 |  |  | 337 |  |  | 305 |  |  | 320 |  |  | 313 |  |  | 344 |  |  | 308 |  |  | 332 |  |  | 358 |  |  | 310 |  |  | 317 |  |  | 318 |  |  | 341 |  |  | 341 |  |  | 345 |  |  | 339 |  |  | 318 |  |  | 347 |  |  | 326 |  |  | 320 |  |  | 350 |  |  | 365 |  |  | 355 |  |  | 333 |  |  | 352 |  |  | 349 |  |  | 318 |  |  | 314 |  |  | 320 |  |  | 341 |  |  | 308 |  |  | 299 |  |  | 355 |  |  | 317 |  |  | 326 |  |  | 352 |  |  | 344 |  |  | 340 |  |  | 305 |  |  | 357 |  |  | 326 |  |  | 314 |  |  | 324 |  |  | 329 |  |  | 318 |  |  | 314 |  |  | 316 |  |  | 326 |  |  | 341 |  |  | 316 |  |  | 314 |  |  | 329 |  |  | 316 |  |  | 317 |  |  | 308 |  |  | 358 |  |  | 320 |  |  | 358 |  |  | 352 |  |  | 319 |  |  | 341 |  |  | 314 |  |  | 342 |  |  | 357 |  |  | 357 |  |  | 337 |  |  | 317 |  |  | 365 |  |  | 299 |  |  | 327 |  |  | 308 |  |  | 329 |  |  | 316 |  |  | 350 |  |  | 373 |  |  | 342 |  |  | 314 |  |  | 347 |  |  | 350 |  |  | 331 |  |  | 303 |  |  | 326 |  |  | 315 |  |  | 318 |  |  | 355 |  |  | 335 |  |  | 350 |  |  | 365 |  |  | 341 |  |  | 342 |  |  | 303 |  |  | 337 |  |  | 365 |  |  | 331 |  |  | 333 |  |  | 334 |  |  | 339 |  |  | 308 |  |  | 329 |  |  | 347 |  |  | 332 |  |  | 324 |  |  | 319 |  |  | 339 |  |  | 309 |  |  | 332 |  |  | 323 |  |  | 333 |  |  | 334 |  |  | 321 |  |  | 324 |  |  | 328 |  |  | 315 |  |  | 332 |  |  | 329 |  |  | 302 |  |  | 302 |  |  | 360 |  |  | 320 |  |  | 323 |  |  | 344 |  |  | 341 |  |  | 308 |  |  | 365 |  |  | 308 |  |  | 312 |  |  | 339 |  |  | 300 |  |  | 311 |  |  | 326 |  |  | 314 |  |  | 328 |  |  | 333 |  |  | 347 |  |  | 331 |  |  | 331 |  |  | 355 |  |  | 347 |  |  | 311 |  |  | 328 |  |  | 339 |  |  | 344 |  |  | 350 |  |  | 307 |  |  | 347 |  |  | 365 |  |  | 321 |  |  | 311 |  |  | 311 |  |  | 309 |  |  | 326 |  |  | 365 |  |  | 308 |  |  | 340 |  |  | 303 |  |  | 310 |  |  | 329 |  |  | 339 |  |  | 332 |  |  | 337 |  |  | 321 |  |  | 311 |  |  | 331 |  |  | 324 |  |  | 344 |  |  | 313 |  |  | 313 |  |  | 339 |  |  | 323 |  |  | 329 |  |  | 285 |  |  | 326 |  |  | 334 |  |  | 347 |  |  | 329 |  |  | 334 |  |  | 323 |  |  | 314 |  |  | 309 |  |  | 355 |  |  | 365 |  |  | 314 |  |  | 333 |  |  | 305 |  |  | 326 |  |  | 323 |  |  | 347 |  |  | 357 |  |  | 334 |  |  | 365 |  |  | 350 |  |  | 344 |  |  | 300 |  |  | 347 |  |  | 350 |  |  | 355 |  |  | 365 |  |  | 320 |  |  | 352 |  |  | 300 |  |  | 317 |  |  | 322 |  |  | 329 |  |  | 347 |  |  | 296 |  |  | 334 |  |  | 319 |  |  | 328 |  |  | 350 |  |  | 327 |  |  | 333 |  |  | 333 |  |  | 329 |  |  | 326 |  |  | 308 |  |  | 352 |  |  | 309 |  |  | 333 |  |  | 308 |  |  | 337 |  |  | 321 |  |  | 331 |  |  | 355 |  |  | 326 |  |  | 342 |  |  | 337 |  |  | 331 |  |  | 342 |  |  | 381 |  |  | 337 |  |  | 360 |  |  | 337 |  |  | 329 |  |  | 320 |  |  | 344 |  |  | 315 |  |  | 327 |  |  | 305 |  |  | 365 |  |  | 360 |  |  | 314 |  |  | 329 |  |  | 332 |  |  | 373 |  |  | 314 |  |  | 329 |  |  | 347 |  |  | 324 |  |  | 373 |  |  | 322 |  |  | 342 |  |  | 329 |  |  | 329 |  |  | 315 |  |  | 344 |  |  | 296 |  |  | 332 |  |  | 337 |  |  | 285 |  |  | 340 |  |  | 347 |  |  | 305 |  |  | 342 |  |  | 365 |  |  | 333 |  |  | 308 |  |  | 297 |  |  | 339 |  |  | 347 |  |  | 323 |  |  | 331 |  |  | 337 |  |  | 324 |  |  | 337 |  |  | 318 |  |  | 323 |  |  | 321 |  |  | 365 |  |  | 307 |  |  | 341 |  |  | 308 |  |  | 311 |  |  | 357 |  |  | 320 |  |  | 341 |  |  | 347 |  |  | 333 |  |  | 329 |  |  | 324 |  |  | 339 |  |  | 339 |  |  | 326 |  |  | 350 |  |  | 320 |  |  | 363 |  |  | 323 |  |  | 317 |  |  | 347 |  |  | 342 |  |  | 319 |  |  | 326 |  |  | 331 |  |  | 305 |  |  | 329 |  |  | 334 |  |  | 316 |  |  | 360 |  |  | 331 |  |  | 329 |  |  | 318 |  |  | 332 |  |  | 329 |  |  | 323 |  |  | 340 |  |  | 333 |  |  | 365 |  |  | 332 |  |  | 365 |  |  | 296 |  |  | 365 |  |  | 329 |  |  | 327 |  |  | 334 |  |  | 355 |  |  | 324 |  |  | 365 |  |  | 320 |  |  | 334 |  |  | 355 |  |  | 309 |  |  | 328 |  |  | 323 |  |  | 340 |  |  | 345 |  |  | 300 |  |  | 350 |  |  | 318 |  |  | 316 |  |  | 347 |  |  | 308 |  |  | 308 |  |  | 303 |  |  | 357 |  |  | 357 |  |  | 337 |  |  | 337 |  |  | 339 |  |  | 309 |  |  | 360 |  |  | 328 |  |  | 326 |  |  | 360 |  |  | 355 |  |  | 309 |  |  | 324 |  |  | 306 |  |  | 313 |  |  | 355 |  |  | 316 |  |  | 324 |  |  | 373 |  |  | 358 |  |  | 320 |  |  | 339 |  |  | 311 |  |  | 332 |  |  | 312 |  |  | 311 |  |  | 341 |  |  | 319 |  |  | 327 |  |  | 340 |  |  | 308 |  |  | 357 |  |  | 323 |  |  | 334 |  |  | 355 |  |  | 308 |  |  | 297 |  |  | 311 |  |  | 309 |  |  | 314 |  |  | 300 |  |  | 334 |  |  | 334 |  |  | 347 |  |  | 315 |  |  | 334 |  |  | 320 |  |  | 326 |  |  | 331 |  |  | 326 |  |  | 360 |  |  | 358 |  |  | 344 |  |  | 296 |  |  | 318 |  |  | 302 |  |  | 331 |  |  | 321 |  |  | 342 |  |  | 337 |  |  | 335 |  |  | 347 |  |  | 350 |  |  | 329 |  |  | 344 |  |  | 311 |  |  | 318 |  |  | 318 |  |  | 331 |  |  | 302 |  |  | 350 |  |  | 327 |  |  | 341 |  |  | 323 |  |  | 316 |  |  | 327 |  |  | 334 |  |  | 320 |  |  | 342 |  |  | 308 |  |  | 344 |  |  | 339 |  |  | 339 |  |  | 310 |  |  | 300 |  |  | 321 |  |  | 340 |  |  | 347 |  |  | 326 |  |  | 357 |  |  | 339 |  |  | 339 |  |  | 311 |  |  | 333 |  |  | 344 |  |  | 326 |  |  | 324 |  |  | 365 |  |  | 339 |  |  | 296 |  |  | 345 |  |  | 315 |  |  | 329 |  |  | 309 |  |  | 344 |  |  | 329 |  |  | 342 |  |  | 297 |  |  | 334 |  |  | 345 |  |  | 316 |  |  | 317 |  |  | 328 |  |  | 342 |  |  | 324 |  |  | 329 |  |  | 302 |  |  | 311 |  |  | 326 |  |  | 339 |  |  | 310 |  |  | 324 |  |  | 329 |  |  | 326 |  |  | 350 |  |  | 334 |  |  | 347 |  |  | 332 |  |  | 350 |  |  | 331 |  |  | 323 |  |  | 365 |  |  | 308 |  |  | 309 |  |  | 355 |  |  | 318 |  |  | 326 |  |  | 324 |  |  | 322 |  |  | 323 |  |  | 320 |  |  | 315 |  |  | 350 |  |  | 339 |  |  | 333 |  |  | 344 |  |  | 320 |  |  | 316 |  |  | 300 |  |  | 297 |  |  | 316 |  |  | 363 |  |  | 317 |  |  | 326 |  |  | 323 |  |  | 314 |  |  | 347 |  |  | 357 |  |  | 339 |  |  | 355 |  |  | 318 |  |  | 339 |  |  | 319 |  |  | 291 |  |  | 341 |  |  | 311 |  |  | 365 |  |  | 339 |  |  | 314 |  |  | 322 |  |  | 326 |  |  | 329 |  |  | 333 |  |  | 355 |  |  | 299 |  |  | 323 |  |  | 326 |  |  | 355 |  |  | 318 |  |  | 324 |  |  | 315 |  |  | 355 |  |  | 350 |  |  | 324 |  |  | 320 |  |  | 311 |  |  | 326 |  |  | 357 |  |  | 341 |  |  | 329 |  |  | 322 |  |  | 327 |  |  | 324 |  |  | 347 |  |  | 342 |  |  | 355 |  |  | 318 |  |  | 323 |  |  | 334 |  |  | 297 |  |  | 344 |  |  | 342 |  |  | 321 |  |  | 350 |  |  | 316 |  |  | 340 |  |  | 331 |  |  | 305 |  |  | 349 |  |  | 357 |  |  | 305 |  |  | 329 |  |  | 311 |  |  | 333 |  |  | 326 |  |  | 331 |  |  | 305 |  |  | 327 |  |  | 344 |  |  | 319 |  |  | 329 |  |  | 311 |  |  | 355 |  |  | 319 |  |  | 363 |  |  | 333 |  |  | 339 |  |  | 339 |  |  | 347 |  |  | 347 |  |  | 326 |  |  | 329 |  |  | 319 |  |  | 315 |  |  | 315 |  |  | 350 |  |  | 314 |  |  | 334 |  |  | 347 |  |  | 315 |  |  | 305 |  |  | 314 |  |  | 299 |  |  | 352 |  |  | 333 |  |  | 339 |  |  | 302 |  |  | 344 |  |  | 329 |  |  | 327 |  |  | 317 |  |  | 365 |  |  | 297 |  |  | 342 |  |  | 324 |  |  | 308 |  |  | 317 |  |  | 347 |  |  | 339 |  |  | 355 |  |  | 339 |  |  | 328 |  |  | 365 |  |  | 297 |  |  | 323 |  |  | 324 |  |  | 355 |  |  | 303 |  |  | 345 |  |  | 315 |  |  | 329 |  |  | 305 |  |  | 357 |  |  | 337 |  |  | 323 |  |  | 302 |  |  | 373 |  |  | 337 |  |  | 350 |  |  | 319 |  |  | 305 |  |  | 329 |  |  | 326 |  |  | 331 |  |  | 322 |  |  | 328 |  |  | 329 |  |  | 316 |  |  | 350 |  |  | 331 |  |  | 329 |  |  | 308 |  |  | 297 |  |  | 355 |  |  | 358 |  |  | 331 |  |  | 347 |  |  | 358 |  |  | 342 |  |  | 334 |  |  | 332 |  |  | 313 |  |  | 326 |  |  | 313 |  |  | 365 |  |  | 347 |  |  | 319 |  |  | 333 |  |  | 347 |  |  | 355 |  |  | 344 |  |  | 347 |  |  | 347 |  |  | 355 |  |  | 342 |  |  | 337 |  |  | 347 |  |  | 324 |  |  | 339 |  |  | 310 |  |  | 297 |  |  | 329 |  |  | 331 |  |  | 329 |  |  | 305 |  |  | 309 |  |  | 332 |  |  | 332 |  |  | 321 |  |  | 344 |  |  | 337 |  |  | 332 |  |  | 318 |  |  | 350 |  |  | 326 |  |  | 306 |  |  | 341 |  |  | 315 |  |  | 337 |  |  | 334 |  |  | 347 |  |  | 333 |  |  | 329 |  |  | 320 |  |  | 300 |  |  | 344 |  |  | 309 |  |  | 327 |  |  | 318 |  |  | 323 |  |  | 331 |  |  | 311 |  |  | 324 |  |  | 316 |  |  | 329 |  |  | 363 |  |  | 350 |  |  | 347 |  |  | 300 |  |  | 315 |  |  | 309 |  |  | 365 |  |  | 319 |  |  | 347 |  |  | 305 |  |  | 327 |  |  | 323 |  |  | 321 |  |  | 305 |  |  | 299 |  |  | 297 |  |  | 303 |  |  | 297 |  |  | 347 |  |  | 297 |  |  | 350 |  |  | 332 |  |  | 332 |  |  | 341 |  |  | 332 |  |  | 337 |  |  | 315 |  |  | 323 |  |  | 303
12 |  | 366 |  |  | 348 |  |  | 325 |  |  | 378 |  |  | 341 |  |  | 354 |  |  | 343 |  |  | 365 |  |  | 404 |  |  | 357 |  |  | 373 |  |  | 391 |  |  | 360 |  |  | 378 |  |  | 352 |  |  | 367 |  |  | 391 |  |  | 352 |  |  | 373 |  |  | 356 |  |  | 394 |  |  | 363 |  |  | 397 |  |  | 394 |  |  | 331 |  |  | 371 |  |  | 378 |  |  | 352 |  |  | 373 |  |  | 387 |  |  | 373 |  |  | 345 |  |  | 389 |  |  | 386 |  |  | 340 |  |  | 349 |  |  | 389 |  |  | 352 |  |  | 362 |  |  | 376 |  |  | 328 |  |  | 353 |  |  | 355 |  |  | 379 |  |  | 380 |  |  | 388 |  |  | 343 |  |  | 363 |  |  | 347 |  |  | 373 |  |  | 379 |  |  | 361 |  |  | 342 |  |  | 380 |  |  | 344 |  |  | 379 |  |  | 368 |  |  | 394 |  |  | 388 |  |  | 368 |  |  | 394 |  |  | 341 |  |  | 348 |  |  | 384 |  |  | 378 |  |  | 361 |  |  | 380 |  |  | 391 |  |  | 380 |  |  | 359 |  |  | 356 |  |  | 344 |  |  | 344 |  |  | 327 |  |  | 365 |  |  | 338 |  |  | 370 |  |  | 329 |  |  | 384 |  |  | 374 |  |  | 389 |  |  | 404 |  |  | 381 |  |  | 339 |  |  | 373 |  |  | 352 |  |  | 347 |  |  | 353 |  |  | 352 |  |  | 341 |  |  | 324 |  |  | 357 |  |  | 394 |  |  | 362 |  |  | 344 |  |  | 370 |  |  | 362 |  |  | 357 |  |  | 332 |  |  | 342 |  |  | 337 |  |  | 331 |  |  | 338 |  |  | 354 |  |  | 365 |  |  | 356 |  |  | 339 |  |  | 368 |  |  | 341 |  |  | 366 |  |  | 376 |  |  | 352 |  |  | 394 |  |  | 355 |  |  | 365 |  |  | 336 |  |  | 354 |  |  | 362 |  |  | 326 |  |  | 349 |  |  | 389 |  |  | 349 |  |  | 402 |  |  | 338 |  |  | 355 |  |  | 358 |  |  | 344 |  |  | 348 |  |  | 358 |  |  | 389 |  |  | 358 |  |  | 412 |  |  | 340 |  |  | 333 |  |  | 336 |  |  | 370 |  |  | 335 |  |  | 384 |  |  | 368 |  |  | 356 |  |  | 339 |  |  | 347 |  |  | 365 |  |  | 365 |  |  | 352 |  |  | 323 |  |  | 328 |  |  | 355 |  |  | 376 |  |  | 333 |  |  | 355 |  |  | 362 |  |  | 336 |  |  | 325 |  |  | 350 |  |  | 380 |  |  | 325 |  |  | 356 |  |  | 329 |  |  | 383 |  |  | 379 |  |  | 345 |  |  | 405 |  |  | 344 |  |  | 338 |  |  | 337 |  |  | 372 |  |  | 394 |  |  | 355 |  |  | 389 |  |  | 378 |  |  | 360 |  |  | 394 |  |  | 363 |  |  | 373 |  |  | 353 |  |  | 347 |  |  | 371 |  |  | 367 |  |  | 333 |  |  | 358 |  |  | 350 |  |  | 367 |  |  | 336 |  |  | 348 |  |  | 371 |  |  | 366 |  |  | 353 |  |  | 353 |  |  | 335 |  |  | 347 |  |  | 389 |  |  | 392 |  |  | 373 |  |  | 365 |  |  | 356 |  |  | 373 |  |  | 353 |  |  | 371 |  |  | 373 |  |  | 397 |  |  | 365 |  |  | 315 |  |  | 357 |  |  | 370 |  |  | 339 |  |  | 347 |  |  | 338 |  |  | 366 |  |  | 347 |  |  | 384 |  |  | 350 |  |  | 346 |  |  | 368 |  |  | 352 |  |  | 350 |  |  | 386 |  |  | 344 |  |  | 368 |  |  | 373 |  |  | 349 |  |  | 380 |  |  | 347 |  |  | 344 |  |  | 361 |  |  | 376 |  |  | 345 |  |  | 357 |  |  | 365 |  |  | 352 |  |  | 347 |  |  | 341 |  |  | 370 |  |  | 371 |  |  | 381 |  |  | 328 |  |  | 320 |  |  | 342 |  |  | 361 |  |  | 379 |  |  | 350 |  |  | 371 |  |  | 366 |  |  | 404 |  |  | 353 |  |  | 326 |  |  | 371 |  |  | 379 |  |  | 386 |  |  | 389 |  |  | 306 |  |  | 378 |  |  | 348 |  |  | 371 |  |  | 362 |  |  | 348 |  |  | 383 |  |  | 356 |  |  | 373 |  |  | 371 |  |  | 362 |  |  | 335 |  |  | 338 |  |  | 360 |  |  | 386 |  |  | 379 |  |  | 369 |  |  | 368 |  |  | 373 |  |  | 323 |  |  | 370 |  |  | 380 |  |  | 404 |  |  | 358 |  |  | 386 |  |  | 363 |  |  | 331 |  |  | 341 |  |  | 328 |  |  | 383 |  |  | 323 |  |  | 356 |  |  | 373 |  |  | 336 |  |  | 356 |  |  | 365 |  |  | 367 |  |  | 380 |  |  | 371 |  |  | 360 |  |  | 347 |  |  | 371 |  |  | 347 |  |  | 359 |  |  | 389 |  |  | 404 |  |  | 394 |  |  | 380 |  |  | 391 |  |  | 375 |  |  | 357 |  |  | 361 |  |  | 367 |  |  | 367 |  |  | 329 |  |  | 320 |  |  | 402 |  |  | 364 |  |  | 365 |  |  | 391 |  |  | 391 |  |  | 366 |  |  | 329 |  |  | 404 |  |  | 352 |  |  | 335 |  |  | 353 |  |  | 355 |  |  | 344 |  |  | 335 |  |  | 355 |  |  | 365 |  |  | 370 |  |  | 345 |  |  | 353 |  |  | 344 |  |  | 340 |  |  | 341 |  |  | 337 |  |  | 382 |  |  | 335 |  |  | 397 |  |  | 391 |  |  | 358 |  |  | 380 |  |  | 338 |  |  | 371 |  |  | 404 |  |  | 378 |  |  | 363 |  |  | 356 |  |  | 391 |  |  | 320 |  |  | 348 |  |  | 329 |  |  | 368 |  |  | 340 |  |  | 376 |  |  | 402 |  |  | 363 |  |  | 353 |  |  | 376 |  |  | 365 |  |  | 360 |  |  | 318 |  |  | 365 |  |  | 339 |  |  | 365 |  |  | 394 |  |  | 350 |  |  | 374 |  |  | 380 |  |  | 365 |  |  | 357 |  |  | 327 |  |  | 358 |  |  | 394 |  |  | 370 |  |  | 362 |  |  | 358 |  |  | 354 |  |  | 329 |  |  | 376 |  |  | 394 |  |  | 356 |  |  | 339 |  |  | 345 |  |  | 363 |  |  | 348 |  |  | 371 |  |  | 370 |  |  | 380 |  |  | 373 |  |  | 368 |  |  | 345 |  |  | 352 |  |  | 344 |  |  | 371 |  |  | 350 |  |  | 328 |  |  | 323 |  |  | 384 |  |  | 367 |  |  | 362 |  |  | 383 |  |  | 356 |  |  | 323 |  |  | 412 |  |  | 347 |  |  | 338 |  |  | 378 |  |  | 329 |  |  | 340 |  |  | 350 |  |  | 353 |  |  | 352 |  |  | 357 |  |  | 386 |  |  | 355 |  |  | 370 |  |  | 394 |  |  | 368 |  |  | 337 |  |  | 354 |  |  | 365 |  |  | 359 |  |  | 389 |  |  | 328 |  |  | 386 |  |  | 394 |  |  | 360 |  |  | 340 |  |  | 332 |  |  | 348 |  |  | 341 |  |  | 412 |  |  | 347 |  |  | 379 |  |  | 342 |  |  | 349 |  |  | 344 |  |  | 365 |  |  | 379 |  |  | 361 |  |  | 360 |  |  | 340 |  |  | 355 |  |  | 339 |  |  | 370 |  |  | 352 |  |  | 352 |  |  | 365 |  |  | 338 |  |  | 368 |  |  | 324 |  |  | 365 |  |  | 381 |  |  | 386 |  |  | 350 |  |  | 381 |  |  | 349 |  |  | 335 |  |  | 333 |  |  | 370 |  |  | 412 |  |  | 338 |  |  | 348 |  |  | 331 |  |  | 347 |  |  | 347 |  |  | 362 |  |  | 372 |  |  | 381 |  |  | 389 |  |  | 389 |  |  | 359 |  |  | 315 |  |  | 376 |  |  | 365 |  |  | 379 |  |  | 404 |  |  | 344 |  |  | 376 |  |  | 324 |  |  | 356 |  |  | 369 |  |  | 344 |  |  | 368 |  |  | 322 |  |  | 373 |  |  | 343 |  |  | 349 |  |  | 365 |  |  | 351 |  |  | 372 |  |  | 357 |  |  | 368 |  |  | 341 |  |  | 347 |  |  | 381 |  |  | 335 |  |  | 359 |  |  | 323 |  |  | 358 |  |  | 347 |  |  | 346 |  |  | 381 |  |  | 365 |  |  | 368 |  |  | 384 |  |  | 360 |  |  | 381 |  |  | 407 |  |  | 384 |  |  | 381 |  |  | 358 |  |  | 368 |  |  | 335 |  |  | 383 |  |  | 354 |  |  | 356 |  |  | 344 |  |  | 404 |  |  | 407 |  |  | 353 |  |  | 376 |  |  | 356 |  |  | 397 |  |  | 353 |  |  | 344 |  |  | 371 |  |  | 363 |  |  | 412 |  |  | 343 |  |  | 389 |  |  | 344 |  |  | 368 |  |  | 354 |  |  | 383 |  |  | 335 |  |  | 347 |  |  | 376 |  |  | 324 |  |  | 369 |  |  | 394 |  |  | 352 |  |  | 357 |  |  | 380 |  |  | 362 |  |  | 347 |  |  | 318 |  |  | 368 |  |  | 362 |  |  | 370 |  |  | 370 |  |  | 366 |  |  | 363 |  |  | 384 |  |  | 365 |  |  | 362 |  |  | 360 |  |  | 389 |  |  | 331 |  |  | 362 |  |  | 329 |  |  | 326 |  |  | 396 |  |  | 367 |  |  | 370 |  |  | 386 |  |  | 357 |  |  | 353 |  |  | 363 |  |  | 368 |  |  | 378 |  |  | 365 |  |  | 397 |  |  | 346 |  |  | 410 |  |  | 344 |  |  | 343 |  |  | 376 |  |  | 366 |  |  | 366 |  |  | 373 |  |  | 360 |  |  | 344 |  |  | 368 |  |  | 363 |  |  | 342 |  |  | 386 |  |  | 355 |  |  | 353 |  |  | 333 |  |  | 356 |  |  | 350 |  |  | 370 |  |  | 355 |  |  | 380 |  |  | 389 |  |  | 371 |  |  | 412 |  |  | 335 |  |  | 380 |  |  | 368 |  |  | 342 |  |  | 355 |  |  | 394 |  |  | 350 |  |  | 412 |  |  | 367 |  |  | 373 |  |  | 394 |  |  | 330 |  |  | 375 |  |  | 349 |  |  | 364 |  |  | 384 |  |  | 321 |  |  | 365 |  |  | 339 |  |  | 340 |  |  | 394 |  |  | 329 |  |  | 347 |  |  | 342 |  |  | 396 |  |  | 396 |  |  | 361 |  |  | 366 |  |  | 365 |  |  | 348 |  |  | 399 |  |  | 343 |  |  | 350 |  |  | 399 |  |  | 381 |  |  | 348 |  |  | 363 |  |  | 345 |  |  | 339 |  |  | 376 |  |  | 340 |  |  | 348 |  |  | 412 |  |  | 382 |  |  | 359 |  |  | 365 |  |  | 358 |  |  | 371 |  |  | 327 |  |  | 326 |  |  | 356 |  |  | 348 |  |  | 353 |  |  | 387 |  |  | 355 |  |  | 396 |  |  | 338 |  |  | 381 |  |  | 394 |  |  | 329 |  |  | 344 |  |  | 350 |  |  | 348 |  |  | 338 |  |  | 315 |  |  | 355 |  |  | 358 |  |  | 371 |  |  | 344 |  |  | 355 |  |  | 359 |  |  | 350 |  |  | 355 |  |  | 352 |  |  | 375 |  |  | 387 |  |  | 373 |  |  | 343 |  |  | 365 |  |  | 331 |  |  | 370 |  |  | 368 |  |  | 368 |  |  | 363 |  |  | 374 |  |  | 386 |  |  | 371 |  |  | 368 |  |  | 373 |  |  | 350 |  |  | 342 |  |  | 365 |  |  | 355 |  |  | 326 |  |  | 379 |  |  | 356 |  |  | 370 |  |  | 344 |  |  | 342 |  |  | 366 |  |  | 355 |  |  | 346 |  |  | 389 |  |  | 355 |  |  | 391 |  |  | 363 |  |  | 378 |  |  | 331 |  |  | 339 |  |  | 350 |  |  | 364 |  |  | 386 |  |  | 350 |  |  | 383 |  |  | 363 |  |  | 360 |  |  | 337 |  |  | 372 |  |  | 370 |  |  | 365 |  |  | 371 |  |  | 391 |  |  | 363 |  |  | 311 |  |  | 392 |  |  | 362 |  |  | 355 |  |  | 348 |  |  | 383 |  |  | 350 |  |  | 357 |  |  | 321 |  |  | 373 |  |  | 392 |  |  | 363 |  |  | 356 |  |  | 357 |  |  | 363 |  |  | 353 |  |  | 368 |  |  | 349 |  |  | 350 |  |  | 365 |  |  | 368 |  |  | 339 |  |  | 353 |  |  | 368 |  |  | 352 |  |  | 365 |  |  | 373 |  |  | 376 |  |  | 358 |  |  | 374 |  |  | 352 |  |  | 370 |  |  | 391 |  |  | 347 |  |  | 356 |  |  | 394 |  |  | 357 |  |  | 341 |  |  | 345 |  |  | 337 |  |  | 362 |  |  | 359 |  |  | 330 |  |  | 365 |  |  | 368 |  |  | 354 |  |  | 365 |  |  | 335 |  |  | 355 |  |  | 315 |  |  | 336 |  |  | 355 |  |  | 392 |  |  | 341 |  |  | 347 |  |  | 347 |  |  | 338 |  |  | 394 |  |  | 372 |  |  | 363 |  |  | 402 |  |  | 347 |  |  | 368 |  |  | 334 |  |  | 312 |  |  | 365 |  |  | 350 |  |  | 404 |  |  | 354 |  |  | 329 |  |  | 348 |  |  | 365 |  |  | 368 |  |  | 357 |  |  | 394 |  |  | 328 |  |  | 347 |  |  | 341 |  |  | 376 |  |  | 333 |  |  | 339 |  |  | 339 |  |  | 394 |  |  | 389 |  |  | 363 |  |  | 346 |  |  | 337 |  |  | 347 |  |  | 396 |  |  | 367 |  |  | 350 |  |  | 361 |  |  | 374 |  |  | 348 |  |  | 386 |  |  | 366 |  |  | 394 |  |  | 344 |  |  | 370 |  |  | 360 |  |  | 336 |  |  | 365 |  |  | 366 |  |  | 360 |  |  | 379 |  |  | 342 |  |  | 361 |  |  | 370 |  |  | 344 |  |  | 388 |  |  | 378 |  |  | 329 |  |  | 350 |  |  | 335 |  |  | 362 |  |  | 341 |  |  | 370 |  |  | 344 |  |  | 353 |  |  | 368 |  |  | 343 |  |  | 350 |  |  | 350 |  |  | 381 |  |  | 340 |  |  | 392 |  |  | 359 |  |  | 386 |  |  | 365 |  |  | 362 |  |  | 362 |  |  | 355 |  |  | 368 |  |  | 348 |  |  | 339 |  |  | 330 |  |  | 397 |  |  | 329 |  |  | 381 |  |  | 386 |  |  | 362 |  |  | 352 |  |  | 353 |  |  | 338 |  |  | 381 |  |  | 372 |  |  | 363 |  |  | 326 |  |  | 383 |  |  | 368 |  |  | 366 |  |  | 356 |  |  | 394 |  |  | 323 |  |  | 381 |  |  | 348 |  |  | 332 |  |  | 332 |  |  | 368 |  |  | 378 |  |  | 376 |  |  | 368 |  |  | 349 |  |  | 404 |  |  | 336 |  |  | 362 |  |  | 339 |  |  | 394 |  |  | 342 |  |  | 360 |  |  | 330 |  |  | 344 |  |  | 326 |  |  | 383 |  |  | 384 |  |  | 344 |  |  | 349 |  |  | 412 |  |  | 384 |  |  | 376 |  |  | 348 |  |  | 344 |  |  | 350 |  |  | 352 |  |  | 378 |  |  | 369 |  |  | 367 |  |  | 350 |  |  | 337 |  |  | 397 |  |  | 360 |  |  | 353 |  |  | 347 |  |  | 318 |  |  | 370 |  |  | 382 |  |  | 355 |  |  | 376 |  |  | 384 |  |  | 389 |  |  | 360 |  |  | 379 |  |  | 328 |  |  | 352 |  |  | 337 |  |  | 394 |  |  | 371 |  |  | 358 |  |  | 372 |  |  | 376 |  |  | 376 |  |  | 383 |  |  | 386 |  |  | 371 |  |  | 376 |  |  | 357 |  |  | 376 |  |  | 368 |  |  | 350 |  |  | 378 |  |  | 331 |  |  | 336 |  |  | 344 |  |  | 352 |  |  | 355 |  |  | 344 |  |  | 333 |  |  | 371 |  |  | 361 |  |  | 342 |  |  | 359 |  |  | 361 |  |  | 361 |  |  | 344 |  |  | 389 |  |  | 373 |  |  | 345 |  |  | 367 |  |  | 339 |  |  | 361 |  |  | 381 |  |  | 394 |  |  | 362 |  |  | 350 |  |  | 346 |  |  | 326 |  |  | 359 |  |  | 335 |  |  | 351 |  |  | 347 |  |  | 344 |  |  | 378 |  |  | 350 |  |  | 371 |  |  | 355 |  |  | 368 |  |  | 384 |  |  | 371 |  |  | 368 |  |  | 324 |  |  | 336 |  |  | 324 |  |  | 380 |  |  | 343 |  |  | 368 |  |  | 344 |  |  | 348 |  |  | 352 |  |  | 360 |  |  | 320 |  |  | 323 |  |  | 323 |  |  | 342 |  |  | 326 |  |  | 373 |  |  | 326 |  |  | 397 |  |  | 371 |  |  | 356 |  |  | 380 |  |  | 371 |  |  | 366 |  |  | 344 |  |  | 338 |  |  | 342
13 |  | 405 |  |  | 369 |  |  | 351 |  |  | 417 |  |  | 370 |  |  | 378 |  |  | 390 |  |  | 404 |  |  | 451 |  |  | 386 |  |  | 388 |  |  | 420 |  |  | 386 |  |  | 407 |  |  | 391 |  |  | 388 |  |  | 406 |  |  | 378 |  |  | 420 |  |  | 377 |  |  | 409 |  |  | 378 |  |  | 426 |  |  | 423 |  |  | 357 |  |  | 395 |  |  | 417 |  |  | 381 |  |  | 394 |  |  | 408 |  |  | 397 |  |  | 384 |  |  | 428 |  |  | 401 |  |  | 387 |  |  | 373 |  |  | 415 |  |  | 367 |  |  | 401 |  |  | 423 |  |  | 343 |  |  | 392 |  |  | 384 |  |  | 405 |  |  | 409 |  |  | 414 |  |  | 382 |  |  | 389 |  |  | 362 |  |  | 388 |  |  | 426 |  |  | 385 |  |  | 366 |  |  | 395 |  |  | 365 |  |  | 418 |  |  | 392 |  |  | 420 |  |  | 427 |  |  | 397 |  |  | 433 |  |  | 388 |  |  | 369 |  |  | 431 |  |  | 393 |  |  | 387 |  |  | 395 |  |  | 415 |  |  | 427 |  |  | 398 |  |  | 395 |  |  | 391 |  |  | 391 |  |  | 351 |  |  | 389 |  |  | 377 |  |  | 394 |  |  | 355 |  |  | 408 |  |  | 413 |  |  | 428 |  |  | 428 |  |  | 402 |  |  | 354 |  |  | 399 |  |  | 378 |  |  | 376 |  |  | 379 |  |  | 378 |  |  | 380 |  |  | 363 |  |  | 378 |  |  | 441 |  |  | 401 |  |  | 370 |  |  | 399 |  |  | 401 |  |  | 372 |  |  | 371 |  |  | 363 |  |  | 384 |  |  | 352 |  |  | 367 |  |  | 383 |  |  | 394 |  |  | 377 |  |  | 354 |  |  | 397 |  |  | 380 |  |  | 392 |  |  | 397 |  |  | 391 |  |  | 441 |  |  | 376 |  |  | 404 |  |  | 375 |  |  | 401 |  |  | 377 |  |  | 365 |  |  | 388 |  |  | 436 |  |  | 378 |  |  | 441 |  |  | 364 |  |  | 394 |  |  | 405 |  |  | 383 |  |  | 395 |  |  | 379 |  |  | 415 |  |  | 382 |  |  | 436 |  |  | 355 |  |  | 372 |  |  | 357 |  |  | 385 |  |  | 361 |  |  | 405 |  |  | 397 |  |  | 382 |  |  | 365 |  |  | 373 |  |  | 404 |  |  | 404 |  |  | 376 |  |  | 347 |  |  | 354 |  |  | 370 |  |  | 415 |  |  | 380 |  |  | 402 |  |  | 383 |  |  | 360 |  |  | 364 |  |  | 365 |  |  | 419 |  |  | 349 |  |  | 403 |  |  | 355 |  |  | 430 |  |  | 394 |  |  | 374 |  |  | 420 |  |  | 359 |  |  | 353 |  |  | 361 |  |  | 387 |  |  | 409 |  |  | 394 |  |  | 404 |  |  | 404 |  |  | 381 |  |  | 415 |  |  | 384 |  |  | 388 |  |  | 374 |  |  | 368 |  |  | 400 |  |  | 388 |  |  | 372 |  |  | 373 |  |  | 397 |  |  | 393 |  |  | 375 |  |  | 387 |  |  | 395 |  |  | 392 |  |  | 379 |  |  | 392 |  |  | 364 |  |  | 373 |  |  | 418 |  |  | 439 |  |  | 394 |  |  | 380 |  |  | 395 |  |  | 388 |  |  | 392 |  |  | 392 |  |  | 399 |  |  | 412 |  |  | 394 |  |  | 336 |  |  | 381 |  |  | 399 |  |  | 386 |  |  | 362 |  |  | 385 |  |  | 413 |  |  | 368 |  |  | 423 |  |  | 389 |  |  | 367 |  |  | 407 |  |  | 373 |  |  | 374 |  |  | 415 |  |  | 373 |  |  | 389 |  |  | 394 |  |  | 364 |  |  | 395 |  |  | 371 |  |  | 368 |  |  | 376 |  |  | 400 |  |  | 384 |  |  | 372 |  |  | 386 |  |  | 373 |  |  | 371 |  |  | 365 |  |  | 391 |  |  | 395 |  |  | 405 |  |  | 375 |  |  | 349 |  |  | 368 |  |  | 382 |  |  | 400 |  |  | 376 |  |  | 386 |  |  | 395 |  |  | 430 |  |  | 392 |  |  | 365 |  |  | 392 |  |  | 426 |  |  | 415 |  |  | 418 |  |  | 345 |  |  | 425 |  |  | 395 |  |  | 392 |  |  | 401 |  |  | 363 |  |  | 404 |  |  | 371 |  |  | 399 |  |  | 410 |  |  | 401 |  |  | 361 |  |  | 359 |  |  | 399 |  |  | 425 |  |  | 394 |  |  | 408 |  |  | 389 |  |  | 388 |  |  | 370 |  |  | 409 |  |  | 427 |  |  | 443 |  |  | 384 |  |  | 433 |  |  | 378 |  |  | 370 |  |  | 388 |  |  | 375 |  |  | 409 |  |  | 362 |  |  | 377 |  |  | 412 |  |  | 351 |  |  | 395 |  |  | 386 |  |  | 396 |  |  | 419 |  |  | 386 |  |  | 384 |  |  | 362 |  |  | 410 |  |  | 368 |  |  | 398 |  |  | 410 |  |  | 433 |  |  | 423 |  |  | 401 |  |  | 430 |  |  | 399 |  |  | 396 |  |  | 385 |  |  | 414 |  |  | 382 |  |  | 355 |  |  | 367 |  |  | 449 |  |  | 388 |  |  | 389 |  |  | 438 |  |  | 430 |  |  | 395 |  |  | 368 |  |  | 430 |  |  | 381 |  |  | 350 |  |  | 392 |  |  | 394 |  |  | 391 |  |  | 382 |  |  | 376 |  |  | 412 |  |  | 399 |  |  | 374 |  |  | 382 |  |  | 368 |  |  | 361 |  |  | 356 |  |  | 352 |  |  | 403 |  |  | 356 |  |  | 444 |  |  | 438 |  |  | 382 |  |  | 404 |  |  | 362 |  |  | 397 |  |  | 451 |  |  | 425 |  |  | 389 |  |  | 403 |  |  | 406 |  |  | 367 |  |  | 395 |  |  | 368 |  |  | 394 |  |  | 364 |  |  | 391 |  |  | 431 |  |  | 402 |  |  | 368 |  |  | 402 |  |  | 404 |  |  | 399 |  |  | 333 |  |  | 386 |  |  | 386 |  |  | 404 |  |  | 415 |  |  | 397 |  |  | 400 |  |  | 395 |  |  | 391 |  |  | 378 |  |  | 374 |  |  | 397 |  |  | 433 |  |  | 417 |  |  | 401 |  |  | 397 |  |  | 378 |  |  | 350 |  |  | 400 |  |  | 433 |  |  | 377 |  |  | 365 |  |  | 374 |  |  | 387 |  |  | 372 |  |  | 410 |  |  | 399 |  |  | 419 |  |  | 402 |  |  | 383 |  |  | 371 |  |  | 391 |  |  | 383 |  |  | 397 |  |  | 371 |  |  | 367 |  |  | 352 |  |  | 405 |  |  | 406 |  |  | 401 |  |  | 407 |  |  | 395 |  |  | 347 |  |  | 438 |  |  | 386 |  |  | 385 |  |  | 417 |  |  | 355 |  |  | 369 |  |  | 389 |  |  | 379 |  |  | 367 |  |  | 372 |  |  | 433 |  |  | 379 |  |  | 385 |  |  | 420 |  |  | 389 |  |  | 352 |  |  | 401 |  |  | 412 |  |  | 374 |  |  | 418 |  |  | 367 |  |  | 425 |  |  | 418 |  |  | 407 |  |  | 387 |  |  | 356 |  |  | 369 |  |  | 362 |  |  | 459 |  |  | 368 |  |  | 408 |  |  | 381 |  |  | 375 |  |  | 365 |  |  | 412 |  |  | 400 |  |  | 390 |  |  | 399 |  |  | 379 |  |  | 379 |  |  | 386 |  |  | 396 |  |  | 391 |  |  | 381 |  |  | 380 |  |  | 367 |  |  | 407 |  |  | 363 |  |  | 412 |  |  | 420 |  |  | 433 |  |  | 389 |  |  | 420 |  |  | 375 |  |  | 364 |  |  | 354 |  |  | 394 |  |  | 441 |  |  | 353 |  |  | 372 |  |  | 346 |  |  | 371 |  |  | 362 |  |  | 377 |  |  | 419 |  |  | 420 |  |  | 436 |  |  | 415 |  |  | 406 |  |  | 336 |  |  | 423 |  |  | 389 |  |  | 400 |  |  | 433 |  |  | 359 |  |  | 397 |  |  | 348 |  |  | 380 |  |  | 408 |  |  | 368 |  |  | 407 |  |  | 348 |  |  | 412 |  |  | 364 |  |  | 388 |  |  | 391 |  |  | 390 |  |  | 387 |  |  | 381 |  |  | 389 |  |  | 388 |  |  | 386 |  |  | 420 |  |  | 356 |  |  | 388 |  |  | 338 |  |  | 373 |  |  | 386 |  |  | 385 |  |  | 405 |  |  | 380 |  |  | 394 |  |  | 413 |  |  | 389 |  |  | 396 |  |  | 446 |  |  | 413 |  |  | 402 |  |  | 382 |  |  | 394 |  |  | 374 |  |  | 412 |  |  | 380 |  |  | 377 |  |  | 368 |  |  | 419 |  |  | 436 |  |  | 377 |  |  | 415 |  |  | 382 |  |  | 444 |  |  | 382 |  |  | 373 |  |  | 397 |  |  | 402 |  |  | 441 |  |  | 382 |  |  | 410 |  |  | 359 |  |  | 389 |  |  | 393 |  |  | 409 |  |  | 374 |  |  | 376 |  |  | 402 |  |  | 350 |  |  | 416 |  |  | 420 |  |  | 367 |  |  | 404 |  |  | 409 |  |  | 409 |  |  | 386 |  |  | 365 |  |  | 407 |  |  | 391 |  |  | 399 |  |  | 409 |  |  | 381 |  |  | 410 |  |  | 413 |  |  | 404 |  |  | 391 |  |  | 381 |  |  | 418 |  |  | 378 |  |  | 391 |  |  | 353 |  |  | 373 |  |  | 417 |  |  | 382 |  |  | 394 |  |  | 425 |  |  | 378 |  |  | 392 |  |  | 378 |  |  | 397 |  |  | 404 |  |  | 404 |  |  | 436 |  |  | 393 |  |  | 425 |  |  | 373 |  |  | 364 |  |  | 400 |  |  | 381 |  |  | 381 |  |  | 402 |  |  | 386 |  |  | 365 |  |  | 383 |  |  | 402 |  |  | 366 |  |  | 407 |  |  | 394 |  |  | 368 |  |  | 362 |  |  | 403 |  |  | 374 |  |  | 394 |  |  | 394 |  |  | 401 |  |  | 436 |  |  | 386 |  |  | 451 |  |  | 350 |  |  | 419 |  |  | 407 |  |  | 389 |  |  | 394 |  |  | 415 |  |  | 389 |  |  | 427 |  |  | 391 |  |  | 388 |  |  | 415 |  |  | 356 |  |  | 396 |  |  | 388 |  |  | 385 |  |  | 399 |  |  | 342 |  |  | 391 |  |  | 386 |  |  | 387 |  |  | 409 |  |  | 358 |  |  | 386 |  |  | 381 |  |  | 443 |  |  | 420 |  |  | 382 |  |  | 405 |  |  | 404 |  |  | 395 |  |  | 438 |  |  | 369 |  |  | 397 |  |  | 438 |  |  | 407 |  |  | 387 |  |  | 384 |  |  | 366 |  |  | 360 |  |  | 415 |  |  | 366 |  |  | 374 |  |  | 427 |  |  | 397 |  |  | 398 |  |  | 404 |  |  | 397 |  |  | 400 |  |  | 348 |  |  | 352 |  |  | 377 |  |  | 387 |  |  | 392 |  |  | 416 |  |  | 370 |  |  | 420 |  |  | 362 |  |  | 420 |  |  | 423 |  |  | 353 |  |  | 365 |  |  | 376 |  |  | 369 |  |  | 377 |  |  | 354 |  |  | 384 |  |  | 379 |  |  | 395 |  |  | 383 |  |  | 370 |  |  | 398 |  |  | 389 |  |  | 379 |  |  | 367 |  |  | 390 |  |  | 426 |  |  | 399 |  |  | 369 |  |  | 389 |  |  | 355 |  |  | 417 |  |  | 415 |  |  | 415 |  |  | 389 |  |  | 413 |  |  | 412 |  |  | 386 |  |  | 415 |  |  | 412 |  |  | 374 |  |  | 381 |  |  | 404 |  |  | 394 |  |  | 373 |  |  | 394 |  |  | 395 |  |  | 391 |  |  | 383 |  |  | 368 |  |  | 381 |  |  | 384 |  |  | 375 |  |  | 428 |  |  | 394 |  |  | 417 |  |  | 410 |  |  | 399 |  |  | 360 |  |  | 365 |  |  | 371 |  |  | 385 |  |  | 401 |  |  | 389 |  |  | 412 |  |  | 392 |  |  | 381 |  |  | 361 |  |  | 393 |  |  | 409 |  |  | 404 |  |  | 386 |  |  | 415 |  |  | 402 |  |  | 340 |  |  | 418 |  |  | 386 |  |  | 394 |  |  | 377 |  |  | 422 |  |  | 389 |  |  | 404 |  |  | 345 |  |  | 394 |  |  | 421 |  |  | 378 |  |  | 377 |  |  | 372 |  |  | 410 |  |  | 382 |  |  | 389 |  |  | 396 |  |  | 397 |  |  | 389 |  |  | 389 |  |  | 368 |  |  | 392 |  |  | 407 |  |  | 391 |  |  | 404 |  |  | 402 |  |  | 405 |  |  | 405 |  |  | 398 |  |  | 391 |  |  | 385 |  |  | 430 |  |  | 394 |  |  | 377 |  |  | 423 |  |  | 381 |  |  | 362 |  |  | 384 |  |  | 366 |  |  | 401 |  |  | 398 |  |  | 377 |  |  | 404 |  |  | 397 |  |  | 393 |  |  | 412 |  |  | 356 |  |  | 394 |  |  | 330 |  |  | 357 |  |  | 379 |  |  | 431 |  |  | 367 |  |  | 368 |  |  | 368 |  |  | 359 |  |  | 423 |  |  | 411 |  |  | 384 |  |  | 423 |  |  | 368 |  |  | 383 |  |  | 363 |  |  | 359 |  |  | 404 |  |  | 374 |  |  | 433 |  |  | 383 |  |  | 353 |  |  | 377 |  |  | 380 |  |  | 397 |  |  | 383 |  |  | 420 |  |  | 354 |  |  | 376 |  |  | 367 |  |  | 415 |  |  | 359 |  |  | 368 |  |  | 360 |  |  | 433 |  |  | 404 |  |  | 402 |  |  | 385 |  |  | 384 |  |  | 362 |  |  | 417 |  |  | 406 |  |  | 365 |  |  | 400 |  |  | 389 |  |  | 395 |  |  | 433 |  |  | 381 |  |  | 423 |  |  | 383 |  |  | 409 |  |  | 386 |  |  | 357 |  |  | 404 |  |  | 387 |  |  | 384 |  |  | 405 |  |  | 381 |  |  | 376 |  |  | 391 |  |  | 383 |  |  | 409 |  |  | 417 |  |  | 368 |  |  | 397 |  |  | 382 |  |  | 409 |  |  | 370 |  |  | 396 |  |  | 383 |  |  | 392 |  |  | 407 |  |  | 369 |  |  | 371 |  |  | 365 |  |  | 410 |  |  | 387 |  |  | 416 |  |  | 388 |  |  | 415 |  |  | 412 |  |  | 391 |  |  | 391 |  |  | 384 |  |  | 394 |  |  | 363 |  |  | 354 |  |  | 369 |  |  | 436 |  |  | 358 |  |  | 396 |  |  | 401 |  |  | 401 |  |  | 391 |  |  | 379 |  |  | 377 |  |  | 402 |  |  | 387 |  |  | 402 |  |  | 373 |  |  | 422 |  |  | 397 |  |  | 405 |  |  | 382 |  |  | 433 |  |  | 347 |  |  | 420 |  |  | 369 |  |  | 371 |  |  | 371 |  |  | 392 |  |  | 404 |  |  | 405 |  |  | 415 |  |  | 388 |  |  | 430 |  |  | 375 |  |  | 377 |  |  | 386 |  |  | 433 |  |  | 368 |  |  | 407 |  |  | 351 |  |  | 359 |  |  | 365 |  |  | 430 |  |  | 408 |  |  | 359 |  |  | 364 |  |  | 451 |  |  | 410 |  |  | 405 |  |  | 363 |  |  | 370 |  |  | 374 |  |  | 376 |  |  | 399 |  |  | 416 |  |  | 406 |  |  | 389 |  |  | 352 |  |  | 418 |  |  | 399 |  |  | 392 |  |  | 373 |  |  | 357 |  |  | 417 |  |  | 403 |  |  | 376 |  |  | 405 |  |  | 399 |  |  | 404 |  |  | 375 |  |  | 408 |  |  | 354 |  |  | 391 |  |  | 358 |  |  | 441 |  |  | 410 |  |  | 384 |  |  | 401 |  |  | 397 |  |  | 402 |  |  | 407 |  |  | 401 |  |  | 397 |  |  | 423 |  |  | 386 |  |  | 415 |  |  | 394 |  |  | 376 |  |  | 399 |  |  | 378 |  |  | 360 |  |  | 391 |  |  | 399 |  |  | 379 |  |  | 383 |  |  | 372 |  |  | 386 |  |  | 376 |  |  | 368 |  |  | 374 |  |  | 400 |  |  | 400 |  |  | 391 |  |  | 413 |  |  | 420 |  |  | 384 |  |  | 393 |  |  | 360 |  |  | 382 |  |  | 428 |  |  | 420 |  |  | 391 |  |  | 371 |  |  | 367 |  |  | 350 |  |  | 385 |  |  | 359 |  |  | 366 |  |  | 373 |  |  | 373 |  |  | 407 |  |  | 374 |  |  | 386 |  |  | 394 |  |  | 389 |  |  | 413 |  |  | 400 |  |  | 415 |  |  | 339 |  |  | 365 |  |  | 363 |  |  | 404 |  |  | 382 |  |  | 392 |  |  | 373 |  |  | 387 |  |  | 399 |  |  | 399 |  |  | 344 |  |  | 362 |  |  | 344 |  |  | 366 |  |  | 352 |  |  | 388 |  |  | 355 |  |  | 436 |  |  | 397 |  |  | 371 |  |  | 406 |  |  | 400 |  |  | 381 |  |  | 391 |  |  | 353 |  |  | 368
14 |  | 452 |  |  | 398 |  |  | 390 |  |  | 443 |  |  | 396 |  |  | 425 |  |  | 429 |  |  | 419 |  |  | 490 |  |  | 433 |  |  | 427 |  |  | 459 |  |  | 401 |  |  | 436 |  |  | 415 |  |  | 409 |  |  | 453 |  |  | 417 |  |  | 441 |  |  | 392 |  |  | 430 |  |  | 402 |  |  | 452 |  |  | 438 |  |  | 396 |  |  | 434 |  |  | 456 |  |  | 396 |  |  | 441 |  |  | 434 |  |  | 421 |  |  | 405 |  |  | 475 |  |  | 422 |  |  | 413 |  |  | 397 |  |  | 441 |  |  | 391 |  |  | 422 |  |  | 447 |  |  | 369 |  |  | 407 |  |  | 431 |  |  | 444 |  |  | 456 |  |  | 453 |  |  | 411 |  |  | 413 |  |  | 383 |  |  | 427 |  |  | 465 |  |  | 432 |  |  | 390 |  |  | 434 |  |  | 412 |  |  | 457 |  |  | 421 |  |  | 446 |  |  | 456 |  |  | 436 |  |  | 472 |  |  | 427 |  |  | 390 |  |  | 452 |  |  | 419 |  |  | 402 |  |  | 421 |  |  | 454 |  |  | 466 |  |  | 413 |  |  | 424 |  |  | 412 |  |  | 415 |  |  | 375 |  |  | 428 |  |  | 392 |  |  | 418 |  |  | 381 |  |  | 423 |  |  | 442 |  |  | 443 |  |  | 452 |  |  | 431 |  |  | 375 |  |  | 428 |  |  | 399 |  |  | 397 |  |  | 426 |  |  | 404 |  |  | 427 |  |  | 392 |  |  | 417 |  |  | 462 |  |  | 430 |  |  | 409 |  |  | 428 |  |  | 427 |  |  | 411 |  |  | 410 |  |  | 402 |  |  | 431 |  |  | 373 |  |  | 406 |  |  | 422 |  |  | 441 |  |  | 398 |  |  | 375 |  |  | 423 |  |  | 406 |  |  | 421 |  |  | 423 |  |  | 412 |  |  | 456 |  |  | 405 |  |  | 425 |  |  | 414 |  |  | 430 |  |  | 403 |  |  | 404 |  |  | 427 |  |  | 451 |  |  | 404 |  |  | 462 |  |  | 403 |  |  | 418 |  |  | 431 |  |  | 422 |  |  | 434 |  |  | 403 |  |  | 462 |  |  | 421 |  |  | 457 |  |  | 384 |  |  | 398 |  |  | 381 |  |  | 400 |  |  | 408 |  |  | 431 |  |  | 436 |  |  | 408 |  |  | 394 |  |  | 388 |  |  | 419 |  |  | 425 |  |  | 397 |  |  | 371 |  |  | 383 |  |  | 409 |  |  | 439 |  |  | 395 |  |  | 426 |  |  | 430 |  |  | 381 |  |  | 411 |  |  | 389 |  |  | 448 |  |  | 396 |  |  | 442 |  |  | 394 |  |  | 469 |  |  | 433 |  |  | 413 |  |  | 446 |  |  | 385 |  |  | 392 |  |  | 376 |  |  | 411 |  |  | 435 |  |  | 409 |  |  | 433 |  |  | 428 |  |  | 410 |  |  | 444 |  |  | 413 |  |  | 412 |  |  | 413 |  |  | 407 |  |  | 439 |  |  | 435 |  |  | 401 |  |  | 412 |  |  | 436 |  |  | 422 |  |  | 401 |  |  | 413 |  |  | 442 |  |  | 407 |  |  | 394 |  |  | 421 |  |  | 388 |  |  | 420 |  |  | 447 |  |  | 463 |  |  | 433 |  |  | 401 |  |  | 416 |  |  | 403 |  |  | 418 |  |  | 416 |  |  | 414 |  |  | 433 |  |  | 418 |  |  | 375 |  |  | 410 |  |  | 446 |  |  | 433 |  |  | 391 |  |  | 424 |  |  | 437 |  |  | 394 |  |  | 470 |  |  | 413 |  |  | 396 |  |  | 431 |  |  | 399 |  |  | 389 |  |  | 454 |  |  | 402 |  |  | 428 |  |  | 423 |  |  | 385 |  |  | 434 |  |  | 386 |  |  | 392 |  |  | 397 |  |  | 415 |  |  | 408 |  |  | 411 |  |  | 410 |  |  | 399 |  |  | 418 |  |  | 412 |  |  | 412 |  |  | 434 |  |  | 434 |  |  | 422 |  |  | 375 |  |  | 394 |  |  | 397 |  |  | 439 |  |  | 423 |  |  | 415 |  |  | 416 |  |  | 454 |  |  | 439 |  |  | 386 |  |  | 416 |  |  | 465 |  |  | 454 |  |  | 442 |  |  | 384 |  |  | 451 |  |  | 442 |  |  | 439 |  |  | 440 |  |  | 387 |  |  | 419 |  |  | 418 |  |  | 414 |  |  | 425 |  |  | 440 |  |  | 390 |  |  | 374 |  |  | 423 |  |  | 451 |  |  | 415 |  |  | 434 |  |  | 436 |  |  | 414 |  |  | 396 |  |  | 424 |  |  | 456 |  |  | 469 |  |  | 423 |  |  | 457 |  |  | 417 |  |  | 391 |  |  | 403 |  |  | 399 |  |  | 424 |  |  | 383 |  |  | 416 |  |  | 441 |  |  | 377 |  |  | 434 |  |  | 407 |  |  | 435 |  |  | 443 |  |  | 425 |  |  | 408 |  |  | 391 |  |  | 436 |  |  | 407 |  |  | 413 |  |  | 449 |  |  | 462 |  |  | 462 |  |  | 448 |  |  | 459 |  |  | 414 |  |  | 411 |  |  | 414 |  |  | 429 |  |  | 406 |  |  | 394 |  |  | 391 |  |  | 470 |  |  | 414 |  |  | 413 |  |  | 462 |  |  | 469 |  |  | 410 |  |  | 415 |  |  | 477 |  |  | 428 |  |  | 365 |  |  | 407 |  |  | 418 |  |  | 420 |  |  | 408 |  |  | 415 |  |  | 451 |  |  | 438 |  |  | 403 |  |  | 408 |  |  | 407 |  |  | 387 |  |  | 395 |  |  | 391 |  |  | 450 |  |  | 382 |  |  | 468 |  |  | 477 |  |  | 411 |  |  | 430 |  |  | 391 |  |  | 436 |  |  | 480 |  |  | 464 |  |  | 404 |  |  | 424 |  |  | 432 |  |  | 388 |  |  | 434 |  |  | 397 |  |  | 441 |  |  | 390 |  |  | 430 |  |  | 455 |  |  | 417 |  |  | 392 |  |  | 426 |  |  | 433 |  |  | 438 |  |  | 354 |  |  | 415 |  |  | 410 |  |  | 430 |  |  | 439 |  |  | 423 |  |  | 429 |  |  | 416 |  |  | 415 |  |  | 417 |  |  | 395 |  |  | 436 |  |  | 448 |  |  | 438 |  |  | 440 |  |  | 436 |  |  | 407 |  |  | 365 |  |  | 447 |  |  | 480 |  |  | 416 |  |  | 391 |  |  | 413 |  |  | 426 |  |  | 396 |  |  | 439 |  |  | 423 |  |  | 448 |  |  | 431 |  |  | 422 |  |  | 395 |  |  | 412 |  |  | 430 |  |  | 426 |  |  | 410 |  |  | 396 |  |  | 391 |  |  | 444 |  |  | 427 |  |  | 440 |  |  | 433 |  |  | 416 |  |  | 362 |  |  | 453 |  |  | 407 |  |  | 414 |  |  | 464 |  |  | 381 |  |  | 395 |  |  | 415 |  |  | 418 |  |  | 393 |  |  | 401 |  |  | 472 |  |  | 418 |  |  | 406 |  |  | 467 |  |  | 418 |  |  | 367 |  |  | 440 |  |  | 459 |  |  | 421 |  |  | 439 |  |  | 391 |  |  | 472 |  |  | 457 |  |  | 422 |  |  | 408 |  |  | 380 |  |  | 408 |  |  | 383 |  |  | 485 |  |  | 407 |  |  | 434 |  |  | 407 |  |  | 390 |  |  | 380 |  |  | 459 |  |  | 426 |  |  | 414 |  |  | 414 |  |  | 405 |  |  | 418 |  |  | 401 |  |  | 425 |  |  | 406 |  |  | 407 |  |  | 395 |  |  | 393 |  |  | 436 |  |  | 392 |  |  | 433 |  |  | 459 |  |  | 459 |  |  | 428 |  |  | 467 |  |  | 404 |  |  | 411 |  |  | 401 |  |  | 423 |  |  | 480 |  |  | 392 |  |  | 401 |  |  | 393 |  |  | 410 |  |  | 401 |  |  | 403 |  |  | 466 |  |  | 444 |  |  | 451 |  |  | 444 |  |  | 435 |  |  | 351 |  |  | 452 |  |  | 436 |  |  | 415 |  |  | 472 |  |  | 383 |  |  | 436 |  |  | 395 |  |  | 427 |  |  | 429 |  |  | 394 |  |  | 454 |  |  | 387 |  |  | 438 |  |  | 388 |  |  | 412 |  |  | 420 |  |  | 414 |  |  | 434 |  |  | 420 |  |  | 404 |  |  | 409 |  |  | 401 |  |  | 449 |  |  | 395 |  |  | 403 |  |  | 362 |  |  | 412 |  |  | 415 |  |  | 424 |  |  | 431 |  |  | 419 |  |  | 423 |  |  | 434 |  |  | 428 |  |  | 411 |  |  | 470 |  |  | 452 |  |  | 423 |  |  | 406 |  |  | 441 |  |  | 395 |  |  | 451 |  |  | 401 |  |  | 416 |  |  | 407 |  |  | 458 |  |  | 462 |  |  | 392 |  |  | 444 |  |  | 403 |  |  | 468 |  |  | 397 |  |  | 397 |  |  | 436 |  |  | 428 |  |  | 456 |  |  | 403 |  |  | 434 |  |  | 388 |  |  | 428 |  |  | 432 |  |  | 456 |  |  | 400 |  |  | 402 |  |  | 441 |  |  | 374 |  |  | 455 |  |  | 441 |  |  | 406 |  |  | 428 |  |  | 456 |  |  | 448 |  |  | 415 |  |  | 389 |  |  | 454 |  |  | 420 |  |  | 428 |  |  | 448 |  |  | 402 |  |  | 425 |  |  | 434 |  |  | 425 |  |  | 415 |  |  | 402 |  |  | 457 |  |  | 393 |  |  | 417 |  |  | 379 |  |  | 412 |  |  | 464 |  |  | 406 |  |  | 423 |  |  | 446 |  |  | 417 |  |  | 418 |  |  | 399 |  |  | 423 |  |  | 443 |  |  | 428 |  |  | 457 |  |  | 414 |  |  | 446 |  |  | 412 |  |  | 393 |  |  | 429 |  |  | 396 |  |  | 420 |  |  | 426 |  |  | 407 |  |  | 404 |  |  | 407 |  |  | 417 |  |  | 387 |  |  | 431 |  |  | 423 |  |  | 407 |  |  | 386 |  |  | 442 |  |  | 400 |  |  | 409 |  |  | 420 |  |  | 427 |  |  | 462 |  |  | 410 |  |  | 490 |  |  | 365 |  |  | 458 |  |  | 431 |  |  | 418 |  |  | 420 |  |  | 454 |  |  | 410 |  |  | 451 |  |  | 415 |  |  | 417 |  |  | 454 |  |  | 371 |  |  | 420 |  |  | 427 |  |  | 432 |  |  | 423 |  |  | 371 |  |  | 438 |  |  | 425 |  |  | 416 |  |  | 430 |  |  | 387 |  |  | 425 |  |  | 402 |  |  | 467 |  |  | 441 |  |  | 408 |  |  | 434 |  |  | 433 |  |  | 442 |  |  | 462 |  |  | 408 |  |  | 423 |  |  | 462 |  |  | 422 |  |  | 413 |  |  | 405 |  |  | 392 |  |  | 381 |  |  | 454 |  |  | 390 |  |  | 389 |  |  | 474 |  |  | 436 |  |  | 437 |  |  | 419 |  |  | 418 |  |  | 439 |  |  | 387 |  |  | 391 |  |  | 416 |  |  | 426 |  |  | 421 |  |  | 442 |  |  | 417 |  |  | 449 |  |  | 386 |  |  | 459 |  |  | 462 |  |  | 368 |  |  | 394 |  |  | 391 |  |  | 384 |  |  | 406 |  |  | 375 |  |  | 408 |  |  | 403 |  |  | 434 |  |  | 407 |  |  | 399 |  |  | 437 |  |  | 415 |  |  | 405 |  |  | 414 |  |  | 429 |  |  | 452 |  |  | 425 |  |  | 393 |  |  | 413 |  |  | 384 |  |  | 432 |  |  | 439 |  |  | 454 |  |  | 404 |  |  | 437 |  |  | 451 |  |  | 407 |  |  | 441 |  |  | 438 |  |  | 398 |  |  | 410 |  |  | 443 |  |  | 418 |  |  | 420 |  |  | 415 |  |  | 416 |  |  | 420 |  |  | 409 |  |  | 392 |  |  | 420 |  |  | 423 |  |  | 404 |  |  | 467 |  |  | 420 |  |  | 456 |  |  | 436 |  |  | 423 |  |  | 399 |  |  | 394 |  |  | 418 |  |  | 400 |  |  | 448 |  |  | 404 |  |  | 433 |  |  | 431 |  |  | 396 |  |  | 400 |  |  | 414 |  |  | 435 |  |  | 443 |  |  | 415 |  |  | 439 |  |  | 417 |  |  | 366 |  |  | 465 |  |  | 410 |  |  | 415 |  |  | 401 |  |  | 446 |  |  | 415 |  |  | 451 |  |  | 374 |  |  | 433 |  |  | 460 |  |  | 407 |  |  | 416 |  |  | 398 |  |  | 457 |  |  | 421 |  |  | 428 |  |  | 435 |  |  | 444 |  |  | 428 |  |  | 428 |  |  | 407 |  |  | 439 |  |  | 433 |  |  | 415 |  |  | 443 |  |  | 428 |  |  | 444 |  |  | 420 |  |  | 422 |  |  | 417 |  |  | 409 |  |  | 445 |  |  | 423 |  |  | 406 |  |  | 470 |  |  | 407 |  |  | 377 |  |  | 413 |  |  | 387 |  |  | 440 |  |  | 437 |  |  | 416 |  |  | 433 |  |  | 412 |  |  | 408 |  |  | 459 |  |  | 403 |  |  | 409 |  |  | 351 |  |  | 386 |  |  | 408 |  |  | 457 |  |  | 414 |  |  | 407 |  |  | 389 |  |  | 374 |  |  | 470 |  |  | 450 |  |  | 431 |  |  | 452 |  |  | 415 |  |  | 407 |  |  | 384 |  |  | 374 |  |  | 425 |  |  | 413 |  |  | 457 |  |  | 422 |  |  | 374 |  |  | 406 |  |  | 419 |  |  | 436 |  |  | 407 |  |  | 449 |  |  | 393 |  |  | 405 |  |  | 388 |  |  | 436 |  |  | 385 |  |  | 389 |  |  | 386 |  |  | 462 |  |  | 433 |  |  | 449 |  |  | 424 |  |  | 399 |  |  | 409 |  |  | 438 |  |  | 453 |  |  | 389 |  |  | 415 |  |  | 436 |  |  | 410 |  |  | 472 |  |  | 420 |  |  | 444 |  |  | 412 |  |  | 456 |  |  | 401 |  |  | 396 |  |  | 430 |  |  | 416 |  |  | 431 |  |  | 452 |  |  | 420 |  |  | 397 |  |  | 412 |  |  | 404 |  |  | 438 |  |  | 443 |  |  | 392 |  |  | 444 |  |  | 403 |  |  | 424 |  |  | 385 |  |  | 443 |  |  | 409 |  |  | 418 |  |  | 436 |  |  | 408 |  |  | 410 |  |  | 412 |  |  | 434 |  |  | 434 |  |  | 445 |  |  | 414 |  |  | 454 |  |  | 441 |  |  | 406 |  |  | 406 |  |  | 408 |  |  | 441 |  |  | 378 |  |  | 375 |  |  | 408 |  |  | 460 |  |  | 382 |  |  | 422 |  |  | 430 |  |  | 440 |  |  | 430 |  |  | 405 |  |  | 398 |  |  | 426 |  |  | 411 |  |  | 426 |  |  | 399 |  |  | 451 |  |  | 423 |  |  | 444 |  |  | 411 |  |  | 480 |  |  | 394 |  |  | 449 |  |  | 398 |  |  | 395 |  |  | 410 |  |  | 421 |  |  | 428 |  |  | 420 |  |  | 454 |  |  | 409 |  |  | 477 |  |  | 401 |  |  | 424 |  |  | 425 |  |  | 459 |  |  | 407 |  |  | 454 |  |  | 398 |  |  | 398 |  |  | 404 |  |  | 459 |  |  | 437 |  |  | 383 |  |  | 393 |  |  | 490 |  |  | 449 |  |  | 444 |  |  | 387 |  |  | 417 |  |  | 398 |  |  | 405 |  |  | 425 |  |  | 442 |  |  | 453 |  |  | 428 |  |  | 378 |  |  | 457 |  |  | 446 |  |  | 431 |  |  | 412 |  |  | 396 |  |  | 441 |  |  | 418 |  |  | 415 |  |  | 444 |  |  | 420 |  |  | 433 |  |  | 404 |  |  | 434 |  |  | 380 |  |  | 420 |  |  | 397 |  |  | 470 |  |  | 449 |  |  | 431 |  |  | 440 |  |  | 418 |  |  | 441 |  |  | 436 |  |  | 440 |  |  | 412 |  |  | 452 |  |  | 425 |  |  | 430 |  |  | 415 |  |  | 405 |  |  | 446 |  |  | 407 |  |  | 389 |  |  | 438 |  |  | 438 |  |  | 408 |  |  | 422 |  |  | 398 |  |  | 425 |  |  | 400 |  |  | 392 |  |  | 389 |  |  | 426 |  |  | 439 |  |  | 430 |  |  | 434 |  |  | 467 |  |  | 423 |  |  | 432 |  |  | 399 |  |  | 429 |  |  | 475 |  |  | 435 |  |  | 420 |  |  | 400 |  |  | 406 |  |  | 371 |  |  | 409 |  |  | 374 |  |  | 395 |  |  | 412 |  |  | 399 |  |  | 454 |  |  | 389 |  |  | 425 |  |  | 415 |  |  | 428 |  |  | 442 |  |  | 415 |  |  | 436 |  |  | 354 |  |  | 391 |  |  | 392 |  |  | 451 |  |  | 408 |  |  | 439 |  |  | 397 |  |  | 413 |  |  | 428 |  |  | 438 |  |  | 391 |  |  | 409 |  |  | 391 |  |  | 387 |  |  | 376 |  |  | 435 |  |  | 394 |  |  | 451 |  |  | 421 |  |  | 400 |  |  | 430 |  |  | 415 |  |  | 420 |  |  | 412 |  |  | 400 |  |  | 415
15 |  | 491 |  |  | 424 |  |  | 429 |  |  | 458 |  |  | 435 |  |  | 440 |  |  | 444 |  |  | 458 |  |  | 511 |  |  | 448 |  |  | 474 |  |  | 506 |  |  | 440 |  |  | 475 |  |  | 444 |  |  | 448 |  |  | 482 |  |  | 443 |  |  | 467 |  |  | 421 |  |  | 469 |  |  | 449 |  |  | 467 |  |  | 453 |  |  | 435 |  |  | 481 |  |  | 495 |  |  | 435 |  |  | 480 |  |  | 463 |  |  | 447 |  |  | 444 |  |  | 504 |  |  | 437 |  |  | 437 |  |  | 436 |  |  | 462 |  |  | 438 |  |  | 461 |  |  | 468 |  |  | 408 |  |  | 422 |  |  | 470 |  |  | 468 |  |  | 495 |  |  | 474 |  |  | 450 |  |  | 452 |  |  | 422 |  |  | 442 |  |  | 480 |  |  | 471 |  |  | 419 |  |  | 463 |  |  | 427 |  |  | 486 |  |  | 460 |  |  | 485 |  |  | 471 |  |  | 460 |  |  | 511 |  |  | 456 |  |  | 437 |  |  | 467 |  |  | 434 |  |  | 428 |  |  | 468 |  |  | 483 |  |  | 513 |  |  | 439 |  |  | 439 |  |  | 441 |  |  | 436 |  |  | 396 |  |  | 475 |  |  | 431 |  |  | 433 |  |  | 396 |  |  | 447 |  |  | 481 |  |  | 482 |  |  | 467 |  |  | 457 |  |  | 422 |  |  | 452 |  |  | 428 |  |  | 436 |  |  | 441 |  |  | 428 |  |  | 442 |  |  | 407 |  |  | 443 |  |  | 491 |  |  | 454 |  |  | 456 |  |  | 457 |  |  | 442 |  |  | 440 |  |  | 434 |  |  | 441 |  |  | 455 |  |  | 388 |  |  | 435 |  |  | 451 |  |  | 465 |  |  | 413 |  |  | 414 |  |  | 447 |  |  | 445 |  |  | 436 |  |  | 449 |  |  | 433 |  |  | 482 |  |  | 434 |  |  | 449 |  |  | 461 |  |  | 456 |  |  | 429 |  |  | 433 |  |  | 451 |  |  | 490 |  |  | 430 |  |  | 501 |  |  | 442 |  |  | 439 |  |  | 470 |  |  | 461 |  |  | 473 |  |  | 418 |  |  | 501 |  |  | 460 |  |  | 483 |  |  | 408 |  |  | 422 |  |  | 428 |  |  | 439 |  |  | 437 |  |  | 478 |  |  | 465 |  |  | 432 |  |  | 409 |  |  | 427 |  |  | 448 |  |  | 446 |  |  | 418 |  |  | 410 |  |  | 407 |  |  | 438 |  |  | 465 |  |  | 421 |  |  | 452 |  |  | 459 |  |  | 407 |  |  | 435 |  |  | 418 |  |  | 469 |  |  | 420 |  |  | 468 |  |  | 423 |  |  | 516 |  |  | 480 |  |  | 437 |  |  | 475 |  |  | 409 |  |  | 407 |  |  | 397 |  |  | 440 |  |  | 461 |  |  | 456 |  |  | 472 |  |  | 452 |  |  | 449 |  |  | 459 |  |  | 452 |  |  | 459 |  |  | 442 |  |  | 428 |  |  | 460 |  |  | 482 |  |  | 425 |  |  | 427 |  |  | 483 |  |  | 469 |  |  | 422 |  |  | 434 |  |  | 481 |  |  | 446 |  |  | 420 |  |  | 447 |  |  | 414 |  |  | 441 |  |  | 486 |  |  | 478 |  |  | 472 |  |  | 422 |  |  | 455 |  |  | 418 |  |  | 457 |  |  | 445 |  |  | 453 |  |  | 472 |  |  | 442 |  |  | 399 |  |  | 457 |  |  | 485 |  |  | 454 |  |  | 415 |  |  | 463 |  |  | 458 |  |  | 433 |  |  | 496 |  |  | 437 |  |  | 420 |  |  | 452 |  |  | 446 |  |  | 410 |  |  | 469 |  |  | 449 |  |  | 449 |  |  | 452 |  |  | 409 |  |  | 473 |  |  | 425 |  |  | 413 |  |  | 423 |  |  | 462 |  |  | 455 |  |  | 440 |  |  | 457 |  |  | 420 |  |  | 465 |  |  | 451 |  |  | 451 |  |  | 460 |  |  | 458 |  |  | 446 |  |  | 414 |  |  | 441 |  |  | 412 |  |  | 460 |  |  | 438 |  |  | 444 |  |  | 455 |  |  | 478 |  |  | 478 |  |  | 410 |  |  | 463 |  |  | 504 |  |  | 469 |  |  | 463 |  |  | 399 |  |  | 490 |  |  | 468 |  |  | 486 |  |  | 479 |  |  | 426 |  |  | 443 |  |  | 447 |  |  | 435 |  |  | 440 |  |  | 479 |  |  | 411 |  |  | 413 |  |  | 444 |  |  | 475 |  |  | 462 |  |  | 463 |  |  | 465 |  |  | 429 |  |  | 443 |  |  | 453 |  |  | 503 |  |  | 495 |  |  | 462 |  |  | 472 |  |  | 432 |  |  | 412 |  |  | 450 |  |  | 414 |  |  | 471 |  |  | 404 |  |  | 455 |  |  | 467 |  |  | 424 |  |  | 460 |  |  | 454 |  |  | 459 |  |  | 472 |  |  | 472 |  |  | 423 |  |  | 417 |  |  | 457 |  |  | 454 |  |  | 442 |  |  | 470 |  |  | 491 |  |  | 486 |  |  | 469 |  |  | 506 |  |  | 443 |  |  | 450 |  |  | 461 |  |  | 458 |  |  | 435 |  |  | 441 |  |  | 417 |  |  | 494 |  |  | 453 |  |  | 460 |  |  | 501 |  |  | 498 |  |  | 439 |  |  | 436 |  |  | 501 |  |  | 452 |  |  | 380 |  |  | 446 |  |  | 457 |  |  | 449 |  |  | 432 |  |  | 439 |  |  | 480 |  |  | 459 |  |  | 418 |  |  | 447 |  |  | 454 |  |  | 416 |  |  | 434 |  |  | 438 |  |  | 476 |  |  | 408 |  |  | 507 |  |  | 524 |  |  | 435 |  |  | 459 |  |  | 420 |  |  | 465 |  |  | 527 |  |  | 511 |  |  | 451 |  |  | 448 |  |  | 479 |  |  | 427 |  |  | 455 |  |  | 444 |  |  | 462 |  |  | 405 |  |  | 454 |  |  | 494 |  |  | 438 |  |  | 431 |  |  | 473 |  |  | 472 |  |  | 477 |  |  | 383 |  |  | 436 |  |  | 449 |  |  | 456 |  |  | 478 |  |  | 462 |  |  | 453 |  |  | 440 |  |  | 444 |  |  | 464 |  |  | 410 |  |  | 457 |  |  | 495 |  |  | 485 |  |  | 487 |  |  | 457 |  |  | 436 |  |  | 404 |  |  | 471 |  |  | 501 |  |  | 440 |  |  | 420 |  |  | 442 |  |  | 465 |  |  | 411 |  |  | 465 |  |  | 462 |  |  | 463 |  |  | 470 |  |  | 461 |  |  | 421 |  |  | 451 |  |  | 469 |  |  | 465 |  |  | 457 |  |  | 425 |  |  | 417 |  |  | 491 |  |  | 448 |  |  | 487 |  |  | 459 |  |  | 455 |  |  | 391 |  |  | 479 |  |  | 433 |  |  | 440 |  |  | 485 |  |  | 428 |  |  | 410 |  |  | 439 |  |  | 465 |  |  | 414 |  |  | 416 |  |  | 498 |  |  | 444 |  |  | 445 |  |  | 506 |  |  | 465 |  |  | 396 |  |  | 464 |  |  | 488 |  |  | 460 |  |  | 468 |  |  | 417 |  |  | 511 |  |  | 483 |  |  | 451 |  |  | 432 |  |  | 401 |  |  | 423 |  |  | 412 |  |  | 509 |  |  | 433 |  |  | 463 |  |  | 446 |  |  | 405 |  |  | 395 |  |  | 480 |  |  | 450 |  |  | 461 |  |  | 429 |  |  | 420 |  |  | 465 |  |  | 448 |  |  | 446 |  |  | 445 |  |  | 433 |  |  | 410 |  |  | 432 |  |  | 465 |  |  | 431 |  |  | 472 |  |  | 498 |  |  | 498 |  |  | 467 |  |  | 482 |  |  | 443 |  |  | 458 |  |  | 427 |  |  | 452 |  |  | 519 |  |  | 416 |  |  | 440 |  |  | 417 |  |  | 425 |  |  | 448 |  |  | 427 |  |  | 513 |  |  | 473 |  |  | 477 |  |  | 491 |  |  | 464 |  |  | 398 |  |  | 478 |  |  | 451 |  |  | 454 |  |  | 501 |  |  | 398 |  |  | 460 |  |  | 442 |  |  | 456 |  |  | 468 |  |  | 441 |  |  | 478 |  |  | 408 |  |  | 477 |  |  | 414 |  |  | 436 |  |  | 444 |  |  | 453 |  |  | 460 |  |  | 459 |  |  | 419 |  |  | 456 |  |  | 430 |  |  | 488 |  |  | 442 |  |  | 432 |  |  | 401 |  |  | 433 |  |  | 441 |  |  | 471 |  |  | 452 |  |  | 448 |  |  | 438 |  |  | 460 |  |  | 449 |  |  | 435 |  |  | 485 |  |  | 476 |  |  | 470 |  |  | 445 |  |  | 480 |  |  | 416 |  |  | 475 |  |  | 416 |  |  | 431 |  |  | 431 |  |  | 497 |  |  | 501 |  |  | 407 |  |  | 465 |  |  | 418 |  |  | 507 |  |  | 444 |  |  | 423 |  |  | 451 |  |  | 475 |  |  | 503 |  |  | 432 |  |  | 481 |  |  | 403 |  |  | 467 |  |  | 458 |  |  | 485 |  |  | 426 |  |  | 449 |  |  | 467 |  |  | 413 |  |  | 494 |  |  | 480 |  |  | 453 |  |  | 457 |  |  | 482 |  |  | 477 |  |  | 454 |  |  | 404 |  |  | 475 |  |  | 459 |  |  | 467 |  |  | 487 |  |  | 441 |  |  | 446 |  |  | 481 |  |  | 454 |  |  | 430 |  |  | 428 |  |  | 481 |  |  | 408 |  |  | 432 |  |  | 418 |  |  | 433 |  |  | 511 |  |  | 435 |  |  | 462 |  |  | 472 |  |  | 443 |  |  | 447 |  |  | 446 |  |  | 462 |  |  | 469 |  |  | 454 |  |  | 496 |  |  | 461 |  |  | 470 |  |  | 459 |  |  | 432 |  |  | 444 |  |  | 417 |  |  | 467 |  |  | 447 |  |  | 446 |  |  | 443 |  |  | 436 |  |  | 456 |  |  | 402 |  |  | 457 |  |  | 470 |  |  | 446 |  |  | 410 |  |  | 481 |  |  | 429 |  |  | 435 |  |  | 449 |  |  | 448 |  |  | 488 |  |  | 449 |  |  | 516 |  |  | 412 |  |  | 505 |  |  | 460 |  |  | 457 |  |  | 449 |  |  | 501 |  |  | 431 |  |  | 475 |  |  | 439 |  |  | 441 |  |  | 501 |  |  | 400 |  |  | 459 |  |  | 466 |  |  | 453 |  |  | 449 |  |  | 395 |  |  | 459 |  |  | 449 |  |  | 455 |  |  | 477 |  |  | 434 |  |  | 464 |  |  | 431 |  |  | 491 |  |  | 462 |  |  | 432 |  |  | 460 |  |  | 454 |  |  | 457 |  |  | 483 |  |  | 429 |  |  | 462 |  |  | 491 |  |  | 446 |  |  | 434 |  |  | 444 |  |  | 416 |  |  | 410 |  |  | 493 |  |  | 429 |  |  | 413 |  |  | 513 |  |  | 465 |  |  | 476 |  |  | 434 |  |  | 442 |  |  | 486 |  |  | 434 |  |  | 438 |  |  | 445 |  |  | 450 |  |  | 445 |  |  | 457 |  |  | 456 |  |  | 475 |  |  | 407 |  |  | 483 |  |  | 509 |  |  | 383 |  |  | 418 |  |  | 417 |  |  | 431 |  |  | 432 |  |  | 414 |  |  | 447 |  |  | 442 |  |  | 460 |  |  | 431 |  |  | 425 |  |  | 484 |  |  | 439 |  |  | 431 |  |  | 429 |  |  | 468 |  |  | 473 |  |  | 472 |  |  | 417 |  |  | 434 |  |  | 399 |  |  | 461 |  |  | 478 |  |  | 493 |  |  | 430 |  |  | 476 |  |  | 472 |  |  | 436 |  |  | 467 |  |  | 462 |  |  | 445 |  |  | 439 |  |  | 482 |  |  | 439 |  |  | 467 |  |  | 439 |  |  | 455 |  |  | 444 |  |  | 433 |  |  | 413 |  |  | 435 |  |  | 449 |  |  | 433 |  |  | 493 |  |  | 459 |  |  | 495 |  |  | 475 |  |  | 452 |  |  | 438 |  |  | 433 |  |  | 433 |  |  | 415 |  |  | 463 |  |  | 443 |  |  | 472 |  |  | 470 |  |  | 411 |  |  | 447 |  |  | 429 |  |  | 461 |  |  | 458 |  |  | 439 |  |  | 463 |  |  | 456 |  |  | 381 |  |  | 504 |  |  | 436 |  |  | 454 |  |  | 448 |  |  | 485 |  |  | 430 |  |  | 480 |  |  | 413 |  |  | 457 |  |  | 489 |  |  | 431 |  |  | 442 |  |  | 437 |  |  | 486 |  |  | 445 |  |  | 467 |  |  | 474 |  |  | 470 |  |  | 452 |  |  | 467 |  |  | 446 |  |  | 465 |  |  | 472 |  |  | 454 |  |  | 464 |  |  | 475 |  |  | 470 |  |  | 441 |  |  | 437 |  |  | 443 |  |  | 433 |  |  | 471 |  |  | 449 |  |  | 445 |  |  | 509 |  |  | 433 |  |  | 392 |  |  | 460 |  |  | 402 |  |  | 461 |  |  | 461 |  |  | 431 |  |  | 448 |  |  | 438 |  |  | 447 |  |  | 474 |  |  | 424 |  |  | 424 |  |  | 366 |  |  | 415 |  |  | 432 |  |  | 496 |  |  | 453 |  |  | 446 |  |  | 436 |  |  | 403 |  |  | 496 |  |  | 465 |  |  | 478 |  |  | 476 |  |  | 439 |  |  | 431 |  |  | 399 |  |  | 413 |  |  | 449 |  |  | 442 |  |  | 486 |  |  | 443 |  |  | 413 |  |  | 445 |  |  | 440 |  |  | 457 |  |  | 436 |  |  | 478 |  |  | 417 |  |  | 426 |  |  | 409 |  |  | 465 |  |  | 424 |  |  | 413 |  |  | 407 |  |  | 486 |  |  | 480 |  |  | 488 |  |  | 471 |  |  | 438 |  |  | 438 |  |  | 477 |  |  | 492 |  |  | 410 |  |  | 462 |  |  | 462 |  |  | 434 |  |  | 511 |  |  | 459 |  |  | 491 |  |  | 438 |  |  | 495 |  |  | 427 |  |  | 417 |  |  | 454 |  |  | 440 |  |  | 478 |  |  | 491 |  |  | 446 |  |  | 423 |  |  | 433 |  |  | 451 |  |  | 462 |  |  | 490 |  |  | 413 |  |  | 459 |  |  | 427 |  |  | 463 |  |  | 424 |  |  | 490 |  |  | 448 |  |  | 465 |  |  | 451 |  |  | 429 |  |  | 449 |  |  | 441 |  |  | 449 |  |  | 473 |  |  | 469 |  |  | 453 |  |  | 493 |  |  | 470 |  |  | 445 |  |  | 421 |  |  | 432 |  |  | 467 |  |  | 417 |  |  | 396 |  |  | 429 |  |  | 499 |  |  | 406 |  |  | 451 |  |  | 454 |  |  | 479 |  |  | 469 |  |  | 434 |  |  | 422 |  |  | 465 |  |  | 450 |  |  | 441 |  |  | 420 |  |  | 498 |  |  | 452 |  |  | 491 |  |  | 432 |  |  | 495 |  |  | 409 |  |  | 496 |  |  | 437 |  |  | 434 |  |  | 439 |  |  | 436 |  |  | 475 |  |  | 467 |  |  | 501 |  |  | 448 |  |  | 492 |  |  | 416 |  |  | 448 |  |  | 472 |  |  | 480 |  |  | 446 |  |  | 469 |  |  | 422 |  |  | 424 |  |  | 425 |  |  | 474 |  |  | 466 |  |  | 404 |  |  | 432 |  |  | 529 |  |  | 470 |  |  | 470 |  |  | 408 |  |  | 432 |  |  | 424 |  |  | 434 |  |  | 454 |  |  | 463 |  |  | 492 |  |  | 454 |  |  | 417 |  |  | 472 |  |  | 470 |  |  | 470 |  |  | 438 |  |  | 443 |  |  | 456 |  |  | 442 |  |  | 436 |  |  | 465 |  |  | 459 |  |  | 480 |  |  | 430 |  |  | 473 |  |  | 401 |  |  | 435 |  |  | 421 |  |  | 491 |  |  | 488 |  |  | 455 |  |  | 487 |  |  | 457 |  |  | 465 |  |  | 457 |  |  | 455 |  |  | 451 |  |  | 473 |  |  | 451 |  |  | 454 |  |  | 444 |  |  | 420 |  |  | 467 |  |  | 431 |  |  | 428 |  |  | 477 |  |  | 464 |  |  | 447 |  |  | 451 |  |  | 422 |  |  | 472 |  |  | 439 |  |  | 439 |  |  | 404 |  |  | 441 |  |  | 468 |  |  | 469 |  |  | 455 |  |  | 496 |  |  | 470 |  |  | 456 |  |  | 438 |  |  | 450 |  |  | 496 |  |  | 464 |  |  | 444 |  |  | 447 |  |  | 435 |  |  | 410 |  |  | 456 |  |  | 389 |  |  | 421 |  |  | 433 |  |  | 423 |  |  | 469 |  |  | 436 |  |  | 449 |  |  | 444 |  |  | 452 |  |  | 489 |  |  | 454 |  |  | 457 |  |  | 378 |  |  | 438 |  |  | 416 |  |  | 480 |  |  | 432 |  |  | 454 |  |  | 426 |  |  | 439 |  |  | 449 |  |  | 477 |  |  | 417 |  |  | 430 |  |  | 412 |  |  | 408 |  |  | 391 |  |  | 461 |  |  | 418 |  |  | 498 |  |  | 436 |  |  | 447 |  |  | 454 |  |  | 430 |  |  | 449 |  |  | 451 |  |  | 429 |  |  | 454
16 |  | 512 |  |  | 448 |  |  | 453 |  |  | 497 |  |  | 459 |  |  | 479 |  |  | 465 |  |  | 487 |  |  | 532 |  |  | 487 |  |  | 498 |  |  | 532 |  |  | 479 |  |  | 501 |  |  | 483 |  |  | 477 |  |  | 497 |  |  | 469 |  |  | 491 |  |  | 436 |  |  | 490 |  |  | 496 |  |  | 482 |  |  | 500 |  |  | 456 |  |  | 520 |  |  | 524 |  |  | 459 |  |  | 519 |  |  | 510 |  |  | 462 |  |  | 473 |  |  | 551 |  |  | 484 |  |  | 466 |  |  | 457 |  |  | 477 |  |  | 477 |  |  | 485 |  |  | 494 |  |  | 423 |  |  | 461 |  |  | 485 |  |  | 507 |  |  | 519 |  |  | 500 |  |  | 489 |  |  | 499 |  |  | 443 |  |  | 481 |  |  | 504 |  |  | 510 |  |  | 458 |  |  | 502 |  |  | 451 |  |  | 510 |  |  | 499 |  |  | 524 |  |  | 495 |  |  | 489 |  |  | 558 |  |  | 503 |  |  | 458 |  |  | 493 |  |  | 460 |  |  | 467 |  |  | 492 |  |  | 522 |  |  | 552 |  |  | 454 |  |  | 478 |  |  | 456 |  |  | 475 |  |  | 425 |  |  | 499 |  |  | 446 |  |  | 472 |  |  | 443 |  |  | 471 |  |  | 510 |  |  | 521 |  |  | 514 |  |  | 478 |  |  | 461 |  |  | 476 |  |  | 467 |  |  | 457 |  |  | 456 |  |  | 443 |  |  | 489 |  |  | 446 |  |  | 472 |  |  | 530 |  |  | 493 |  |  | 471 |  |  | 504 |  |  | 463 |  |  | 487 |  |  | 473 |  |  | 456 |  |  | 481 |  |  | 417 |  |  | 456 |  |  | 480 |  |  | 480 |  |  | 434 |  |  | 453 |  |  | 476 |  |  | 484 |  |  | 475 |  |  | 475 |  |  | 462 |  |  | 497 |  |  | 481 |  |  | 473 |  |  | 500 |  |  | 495 |  |  | 453 |  |  | 454 |  |  | 475 |  |  | 511 |  |  | 469 |  |  | 516 |  |  | 481 |  |  | 460 |  |  | 494 |  |  | 485 |  |  | 499 |  |  | 447 |  |  | 530 |  |  | 499 |  |  | 530 |  |  | 434 |  |  | 446 |  |  | 454 |  |  | 463 |  |  | 484 |  |  | 507 |  |  | 491 |  |  | 461 |  |  | 433 |  |  | 453 |  |  | 487 |  |  | 467 |  |  | 465 |  |  | 449 |  |  | 431 |  |  | 467 |  |  | 486 |  |  | 460 |  |  | 476 |  |  | 480 |  |  | 454 |  |  | 461 |  |  | 457 |  |  | 516 |  |  | 444 |  |  | 489 |  |  | 444 |  |  | 563 |  |  | 527 |  |  | 466 |  |  | 504 |  |  | 430 |  |  | 446 |  |  | 436 |  |  | 461 |  |  | 485 |  |  | 485 |  |  | 501 |  |  | 467 |  |  | 473 |  |  | 498 |  |  | 491 |  |  | 498 |  |  | 489 |  |  | 457 |  |  | 499 |  |  | 508 |  |  | 449 |  |  | 474 |  |  | 522 |  |  | 508 |  |  | 443 |  |  | 473 |  |  | 502 |  |  | 475 |  |  | 467 |  |  | 468 |  |  | 461 |  |  | 462 |  |  | 510 |  |  | 517 |  |  | 487 |  |  | 446 |  |  | 484 |  |  | 433 |  |  | 486 |  |  | 484 |  |  | 474 |  |  | 493 |  |  | 471 |  |  | 414 |  |  | 472 |  |  | 524 |  |  | 493 |  |  | 462 |  |  | 502 |  |  | 497 |  |  | 472 |  |  | 535 |  |  | 452 |  |  | 467 |  |  | 499 |  |  | 472 |  |  | 449 |  |  | 508 |  |  | 475 |  |  | 478 |  |  | 491 |  |  | 448 |  |  | 488 |  |  | 464 |  |  | 439 |  |  | 449 |  |  | 483 |  |  | 494 |  |  | 479 |  |  | 486 |  |  | 467 |  |  | 504 |  |  | 472 |  |  | 498 |  |  | 499 |  |  | 497 |  |  | 485 |  |  | 429 |  |  | 465 |  |  | 459 |  |  | 475 |  |  | 467 |  |  | 491 |  |  | 481 |  |  | 507 |  |  | 499 |  |  | 436 |  |  | 502 |  |  | 543 |  |  | 508 |  |  | 484 |  |  | 420 |  |  | 529 |  |  | 492 |  |  | 510 |  |  | 503 |  |  | 441 |  |  | 482 |  |  | 486 |  |  | 474 |  |  | 466 |  |  | 503 |  |  | 450 |  |  | 428 |  |  | 473 |  |  | 514 |  |  | 509 |  |  | 502 |  |  | 489 |  |  | 476 |  |  | 472 |  |  | 468 |  |  | 524 |  |  | 534 |  |  | 483 |  |  | 519 |  |  | 447 |  |  | 438 |  |  | 479 |  |  | 443 |  |  | 500 |  |  | 419 |  |  | 470 |  |  | 506 |  |  | 463 |  |  | 499 |  |  | 469 |  |  | 485 |  |  | 493 |  |  | 511 |  |  | 470 |  |  | 443 |  |  | 486 |  |  | 493 |  |  | 471 |  |  | 509 |  |  | 512 |  |  | 501 |  |  | 490 |  |  | 545 |  |  | 482 |  |  | 476 |  |  | 500 |  |  | 479 |  |  | 459 |  |  | 488 |  |  | 446 |  |  | 533 |  |  | 468 |  |  | 481 |  |  | 540 |  |  | 545 |  |  | 468 |  |  | 451 |  |  | 516 |  |  | 478 |  |  | 419 |  |  | 485 |  |  | 472 |  |  | 478 |  |  | 453 |  |  | 478 |  |  | 519 |  |  | 498 |  |  | 433 |  |  | 473 |  |  | 493 |  |  | 440 |  |  | 481 |  |  | 459 |  |  | 505 |  |  | 455 |  |  | 528 |  |  | 545 |  |  | 482 |  |  | 485 |  |  | 467 |  |  | 504 |  |  | 551 |  |  | 540 |  |  | 490 |  |  | 474 |  |  | 500 |  |  | 466 |  |  | 494 |  |  | 465 |  |  | 483 |  |  | 452 |  |  | 469 |  |  | 541 |  |  | 453 |  |  | 457 |  |  | 488 |  |  | 511 |  |  | 503 |  |  | 407 |  |  | 465 |  |  | 470 |  |  | 482 |  |  | 507 |  |  | 477 |  |  | 474 |  |  | 455 |  |  | 473 |  |  | 490 |  |  | 439 |  |  | 483 |  |  | 542 |  |  | 524 |  |  | 511 |  |  | 504 |  |  | 483 |  |  | 430 |  |  | 492 |  |  | 522 |  |  | 469 |  |  | 459 |  |  | 471 |  |  | 504 |  |  | 440 |  |  | 494 |  |  | 501 |  |  | 510 |  |  | 496 |  |  | 508 |  |  | 460 |  |  | 480 |  |  | 493 |  |  | 480 |  |  | 504 |  |  | 472 |  |  | 443 |  |  | 530 |  |  | 487 |  |  | 502 |  |  | 498 |  |  | 476 |  |  | 406 |  |  | 518 |  |  | 472 |  |  | 455 |  |  | 532 |  |  | 452 |  |  | 434 |  |  | 468 |  |  | 512 |  |  | 429 |  |  | 442 |  |  | 545 |  |  | 483 |  |  | 460 |  |  | 521 |  |  | 491 |  |  | 422 |  |  | 479 |  |  | 527 |  |  | 507 |  |  | 492 |  |  | 441 |  |  | 540 |  |  | 530 |  |  | 475 |  |  | 471 |  |  | 448 |  |  | 447 |  |  | 438 |  |  | 548 |  |  | 454 |  |  | 484 |  |  | 493 |  |  | 426 |  |  | 419 |  |  | 527 |  |  | 489 |  |  | 476 |  |  | 450 |  |  | 459 |  |  | 491 |  |  | 477 |  |  | 472 |  |  | 492 |  |  | 472 |  |  | 449 |  |  | 461 |  |  | 504 |  |  | 457 |  |  | 511 |  |  | 537 |  |  | 522 |  |  | 506 |  |  | 508 |  |  | 467 |  |  | 473 |  |  | 451 |  |  | 499 |  |  | 558 |  |  | 440 |  |  | 469 |  |  | 456 |  |  | 472 |  |  | 495 |  |  | 453 |  |  | 539 |  |  | 512 |  |  | 498 |  |  | 538 |  |  | 488 |  |  | 424 |  |  | 504 |  |  | 466 |  |  | 480 |  |  | 522 |  |  | 427 |  |  | 489 |  |  | 463 |  |  | 485 |  |  | 483 |  |  | 467 |  |  | 502 |  |  | 447 |  |  | 516 |  |  | 429 |  |  | 475 |  |  | 483 |  |  | 500 |  |  | 499 |  |  | 498 |  |  | 440 |  |  | 482 |  |  | 469 |  |  | 509 |  |  | 481 |  |  | 479 |  |  | 422 |  |  | 480 |  |  | 488 |  |  | 486 |  |  | 473 |  |  | 472 |  |  | 477 |  |  | 475 |  |  | 496 |  |  | 464 |  |  | 500 |  |  | 515 |  |  | 509 |  |  | 469 |  |  | 504 |  |  | 463 |  |  | 504 |  |  | 455 |  |  | 455 |  |  | 470 |  |  | 544 |  |  | 530 |  |  | 446 |  |  | 504 |  |  | 465 |  |  | 546 |  |  | 473 |  |  | 449 |  |  | 477 |  |  | 514 |  |  | 527 |  |  | 471 |  |  | 505 |  |  | 429 |  |  | 506 |  |  | 497 |  |  | 514 |  |  | 441 |  |  | 496 |  |  | 482 |  |  | 460 |  |  | 515 |  |  | 504 |  |  | 482 |  |  | 496 |  |  | 521 |  |  | 516 |  |  | 475 |  |  | 430 |  |  | 490 |  |  | 485 |  |  | 488 |  |  | 511 |  |  | 488 |  |  | 470 |  |  | 520 |  |  | 475 |  |  | 445 |  |  | 467 |  |  | 496 |  |  | 437 |  |  | 447 |  |  | 447 |  |  | 454 |  |  | 532 |  |  | 464 |  |  | 483 |  |  | 487 |  |  | 490 |  |  | 473 |  |  | 470 |  |  | 501 |  |  | 508 |  |  | 480 |  |  | 535 |  |  | 500 |  |  | 509 |  |  | 483 |  |  | 471 |  |  | 473 |  |  | 441 |  |  | 514 |  |  | 473 |  |  | 467 |  |  | 482 |  |  | 462 |  |  | 471 |  |  | 423 |  |  | 504 |  |  | 485 |  |  | 467 |  |  | 449 |  |  | 520 |  |  | 453 |  |  | 459 |  |  | 488 |  |  | 472 |  |  | 527 |  |  | 473 |  |  | 537 |  |  | 451 |  |  | 531 |  |  | 486 |  |  | 486 |  |  | 478 |  |  | 525 |  |  | 455 |  |  | 501 |  |  | 454 |  |  | 456 |  |  | 540 |  |  | 424 |  |  | 485 |  |  | 513 |  |  | 468 |  |  | 470 |  |  | 421 |  |  | 488 |  |  | 488 |  |  | 479 |  |  | 501 |  |  | 455 |  |  | 511 |  |  | 452 |  |  | 515 |  |  | 501 |  |  | 453 |  |  | 486 |  |  | 483 |  |  | 472 |  |  | 504 |  |  | 444 |  |  | 483 |  |  | 520 |  |  | 493 |  |  | 455 |  |  | 483 |  |  | 440 |  |  | 431 |  |  | 519 |  |  | 468 |  |  | 428 |  |  | 560 |  |  | 504 |  |  | 497 |  |  | 460 |  |  | 489 |  |  | 515 |  |  | 463 |  |  | 453 |  |  | 492 |  |  | 479 |  |  | 471 |  |  | 496 |  |  | 495 |  |  | 496 |  |  | 454 |  |  | 504 |  |  | 538 |  |  | 398 |  |  | 439 |  |  | 432 |  |  | 452 |  |  | 479 |  |  | 453 |  |  | 468 |  |  | 481 |  |  | 507 |  |  | 460 |  |  | 446 |  |  | 505 |  |  | 478 |  |  | 455 |  |  | 458 |  |  | 497 |  |  | 494 |  |  | 498 |  |  | 456 |  |  | 458 |  |  | 446 |  |  | 476 |  |  | 525 |  |  | 540 |  |  | 454 |  |  | 491 |  |  | 511 |  |  | 465 |  |  | 514 |  |  | 486 |  |  | 460 |  |  | 463 |  |  | 529 |  |  | 454 |  |  | 493 |  |  | 463 |  |  | 502 |  |  | 491 |  |  | 472 |  |  | 439 |  |  | 459 |  |  | 488 |  |  | 462 |  |  | 522 |  |  | 488 |  |  | 516 |  |  | 514 |  |  | 491 |  |  | 453 |  |  | 472 |  |  | 448 |  |  | 439 |  |  | 478 |  |  | 458 |  |  | 519 |  |  | 485 |  |  | 440 |  |  | 486 |  |  | 455 |  |  | 500 |  |  | 505 |  |  | 460 |  |  | 502 |  |  | 471 |  |  | 410 |  |  | 551 |  |  | 475 |  |  | 480 |  |  | 487 |  |  | 500 |  |  | 469 |  |  | 527 |  |  | 442 |  |  | 486 |  |  | 515 |  |  | 470 |  |  | 463 |  |  | 461 |  |  | 525 |  |  | 492 |  |  | 493 |  |  | 513 |  |  | 499 |  |  | 499 |  |  | 488 |  |  | 461 |  |  | 512 |  |  | 498 |  |  | 475 |  |  | 490 |  |  | 496 |  |  | 491 |  |  | 456 |  |  | 484 |  |  | 472 |  |  | 472 |  |  | 500 |  |  | 478 |  |  | 474 |  |  | 535 |  |  | 448 |  |  | 418 |  |  | 499 |  |  | 417 |  |  | 487 |  |  | 500 |  |  | 470 |  |  | 469 |  |  | 464 |  |  | 494 |  |  | 495 |  |  | 445 |  |  | 450 |  |  | 390 |  |  | 454 |  |  | 471 |  |  | 517 |  |  | 477 |  |  | 461 |  |  | 462 |  |  | 424 |  |  | 522 |  |  | 486 |  |  | 525 |  |  | 515 |  |  | 468 |  |  | 470 |  |  | 438 |  |  | 428 |  |  | 496 |  |  | 471 |  |  | 533 |  |  | 482 |  |  | 434 |  |  | 484 |  |  | 487 |  |  | 481 |  |  | 475 |  |  | 525 |  |  | 446 |  |  | 455 |  |  | 435 |  |  | 491 |  |  | 471 |  |  | 437 |  |  | 454 |  |  | 501 |  |  | 527 |  |  | 527 |  |  | 486 |  |  | 462 |  |  | 485 |  |  | 506 |  |  | 518 |  |  | 439 |  |  | 486 |  |  | 477 |  |  | 473 |  |  | 532 |  |  | 488 |  |  | 512 |  |  | 464 |  |  | 510 |  |  | 442 |  |  | 446 |  |  | 501 |  |  | 479 |  |  | 502 |  |  | 515 |  |  | 485 |  |  | 452 |  |  | 472 |  |  | 477 |  |  | 486 |  |  | 514 |  |  | 434 |  |  | 498 |  |  | 456 |  |  | 478 |  |  | 471 |  |  | 511 |  |  | 463 |  |  | 480 |  |  | 490 |  |  | 468 |  |  | 475 |  |  | 462 |  |  | 488 |  |  | 488 |  |  | 484 |  |  | 477 |  |  | 514 |  |  | 517 |  |  | 474 |  |  | 442 |  |  | 471 |  |  | 493 |  |  | 441 |  |  | 435 |  |  | 453 |  |  | 528 |  |  | 421 |  |  | 475 |  |  | 469 |  |  | 526 |  |  | 490 |  |  | 455 |  |  | 451 |  |  | 491 |  |  | 474 |  |  | 465 |  |  | 459 |  |  | 519 |  |  | 499 |  |  | 512 |  |  | 456 |  |  | 534 |  |  | 448 |  |  | 535 |  |  | 458 |  |  | 449 |  |  | 465 |  |  | 451 |  |  | 504 |  |  | 493 |  |  | 540 |  |  | 487 |  |  | 518 |  |  | 437 |  |  | 487 |  |  | 487 |  |  | 495 |  |  | 467 |  |  | 493 |  |  | 461 |  |  | 471 |  |  | 472 |  |  | 489 |  |  | 495 |  |  | 428 |  |  | 471 |  |  | 568 |  |  | 496 |  |  | 509 |  |  | 447 |  |  | 471 |  |  | 463 |  |  | 463 |  |  | 475 |  |  | 489 |  |  | 516 |  |  | 469 |  |  | 456 |  |  | 511 |  |  | 485 |  |  | 494 |  |  | 462 |  |  | 469 |  |  | 485 |  |  | 468 |  |  | 462 |  |  | 512 |  |  | 474 |  |  | 519 |  |  | 477 |  |  | 488 |  |  | 425 |  |  | 456 |  |  | 447 |  |  | 515 |  |  | 517 |  |  | 494 |  |  | 526 |  |  | 486 |  |  | 480 |  |  | 472 |  |  | 476 |  |  | 498 |  |  | 512 |  |  | 477 |  |  | 493 |  |  | 473 |  |  | 441 |  |  | 514 |  |  | 470 |  |  | 449 |  |  | 503 |  |  | 511 |  |  | 486 |  |  | 480 |  |  | 461 |  |  | 498 |  |  | 465 |  |  | 478 |  |  | 443 |  |  | 467 |  |  | 515 |  |  | 495 |  |  | 479 |  |  | 543 |  |  | 499 |  |  | 480 |  |  | 453 |  |  | 474 |  |  | 520 |  |  | 511 |  |  | 491 |  |  | 473 |  |  | 450 |  |  | 457 |  |  | 485 |  |  | 428 |  |  | 450 |  |  | 448 |  |  | 470 |  |  | 493 |  |  | 451 |  |  | 478 |  |  | 483 |  |  | 473 |  |  | 513 |  |  | 478 |  |  | 486 |  |  | 407 |  |  | 464 |  |  | 442 |  |  | 527 |  |  | 456 |  |  | 478 |  |  | 455 |  |  | 463 |  |  | 464 |  |  | 503 |  |  | 438 |  |  | 459 |  |  | 451 |  |  | 455 |  |  | 438 |  |  | 476 |  |  | 444 |  |  | 537 |  |  | 483 |  |  | 468 |  |  | 493 |  |  | 477 |  |  | 464 |  |  | 475 |  |  | 450 |  |  | 501
17 |  | 527 |  |  | 487 |  |  | 482 |  |  | 544 |  |  | 506 |  |  | 526 |  |  | 491 |  |  | 526 |  |  | 558 |  |  | 534 |  |  | 524 |  |  | 571 |  |  | 500 |  |  | 516 |  |  | 530 |  |  | 524 |  |  | 512 |  |  | 498 |  |  | 520 |  |  | 460 |  |  | 505 |  |  | 543 |  |  | 506 |  |  | 515 |  |  | 477 |  |  | 544 |  |  | 550 |  |  | 498 |  |  | 543 |  |  | 539 |  |  | 509 |  |  | 499 |  |  | 577 |  |  | 510 |  |  | 481 |  |  | 504 |  |  | 501 |  |  | 503 |  |  | 511 |  |  | 533 |  |  | 444 |  |  | 490 |  |  | 524 |  |  | 533 |  |  | 558 |  |  | 539 |  |  | 510 |  |  | 528 |  |  | 472 |  |  | 496 |  |  | 551 |  |  | 549 |  |  | 473 |  |  | 517 |  |  | 477 |  |  | 531 |  |  | 546 |  |  | 539 |  |  | 534 |  |  | 528 |  |  | 582 |  |  | 518 |  |  | 505 |  |  | 508 |  |  | 481 |  |  | 496 |  |  | 531 |  |  | 537 |  |  | 576 |  |  | 469 |  |  | 504 |  |  | 482 |  |  | 501 |  |  | 451 |  |  | 523 |  |  | 485 |  |  | 496 |  |  | 490 |  |  | 510 |  |  | 536 |  |  | 568 |  |  | 540 |  |  | 502 |  |  | 500 |  |  | 491 |  |  | 496 |  |  | 478 |  |  | 503 |  |  | 469 |  |  | 510 |  |  | 485 |  |  | 496 |  |  | 577 |  |  | 522 |  |  | 486 |  |  | 543 |  |  | 510 |  |  | 502 |  |  | 512 |  |  | 477 |  |  | 505 |  |  | 441 |  |  | 495 |  |  | 519 |  |  | 509 |  |  | 473 |  |  | 477 |  |  | 515 |  |  | 499 |  |  | 504 |  |  | 496 |  |  | 477 |  |  | 526 |  |  | 528 |  |  | 497 |  |  | 524 |  |  | 534 |  |  | 482 |  |  | 478 |  |  | 522 |  |  | 550 |  |  | 490 |  |  | 555 |  |  | 507 |  |  | 475 |  |  | 509 |  |  | 500 |  |  | 538 |  |  | 486 |  |  | 569 |  |  | 538 |  |  | 569 |  |  | 460 |  |  | 467 |  |  | 480 |  |  | 502 |  |  | 523 |  |  | 546 |  |  | 530 |  |  | 500 |  |  | 454 |  |  | 477 |  |  | 526 |  |  | 514 |  |  | 504 |  |  | 496 |  |  | 470 |  |  | 514 |  |  | 525 |  |  | 481 |  |  | 491 |  |  | 506 |  |  | 493 |  |  | 500 |  |  | 483 |  |  | 537 |  |  | 473 |  |  | 528 |  |  | 473 |  |  | 587 |  |  | 548 |  |  | 513 |  |  | 533 |  |  | 469 |  |  | 475 |  |  | 465 |  |  | 485 |  |  | 509 |  |  | 506 |  |  | 522 |  |  | 493 |  |  | 494 |  |  | 524 |  |  | 538 |  |  | 513 |  |  | 510 |  |  | 478 |  |  | 528 |  |  | 532 |  |  | 478 |  |  | 503 |  |  | 561 |  |  | 547 |  |  | 482 |  |  | 488 |  |  | 549 |  |  | 501 |  |  | 482 |  |  | 507 |  |  | 482 |  |  | 477 |  |  | 539 |  |  | 546 |  |  | 502 |  |  | 467 |  |  | 523 |  |  | 462 |  |  | 515 |  |  | 513 |  |  | 513 |  |  | 532 |  |  | 518 |  |  | 443 |  |  | 487 |  |  | 563 |  |  | 532 |  |  | 501 |  |  | 523 |  |  | 526 |  |  | 511 |  |  | 564 |  |  | 478 |  |  | 493 |  |  | 525 |  |  | 493 |  |  | 473 |  |  | 529 |  |  | 514 |  |  | 507 |  |  | 530 |  |  | 477 |  |  | 527 |  |  | 503 |  |  | 460 |  |  | 475 |  |  | 507 |  |  | 541 |  |  | 500 |  |  | 501 |  |  | 488 |  |  | 519 |  |  | 501 |  |  | 524 |  |  | 528 |  |  | 536 |  |  | 500 |  |  | 453 |  |  | 491 |  |  | 498 |  |  | 514 |  |  | 506 |  |  | 520 |  |  | 520 |  |  | 546 |  |  | 528 |  |  | 451 |  |  | 541 |  |  | 569 |  |  | 537 |  |  | 508 |  |  | 449 |  |  | 555 |  |  | 531 |  |  | 549 |  |  | 542 |  |  | 462 |  |  | 521 |  |  | 533 |  |  | 500 |  |  | 505 |  |  | 550 |  |  | 489 |  |  | 475 |  |  | 520 |  |  | 561 |  |  | 533 |  |  | 549 |  |  | 510 |  |  | 491 |  |  | 496 |  |  | 515 |  |  | 571 |  |  | 555 |  |  | 512 |  |  | 548 |  |  | 473 |  |  | 462 |  |  | 526 |  |  | 490 |  |  | 526 |  |  | 458 |  |  | 496 |  |  | 527 |  |  | 489 |  |  | 538 |  |  | 495 |  |  | 532 |  |  | 514 |  |  | 535 |  |  | 494 |  |  | 464 |  |  | 512 |  |  | 517 |  |  | 492 |  |  | 535 |  |  | 541 |  |  | 516 |  |  | 519 |  |  | 584 |  |  | 529 |  |  | 491 |  |  | 521 |  |  | 518 |  |  | 498 |  |  | 512 |  |  | 485 |  |  | 580 |  |  | 483 |  |  | 520 |  |  | 566 |  |  | 584 |  |  | 489 |  |  | 498 |  |  | 542 |  |  | 499 |  |  | 448 |  |  | 509 |  |  | 498 |  |  | 502 |  |  | 492 |  |  | 493 |  |  | 566 |  |  | 519 |  |  | 480 |  |  | 520 |  |  | 522 |  |  | 487 |  |  | 502 |  |  | 498 |  |  | 552 |  |  | 484 |  |  | 567 |  |  | 584 |  |  | 521 |  |  | 524 |  |  | 488 |  |  | 528 |  |  | 590 |  |  | 564 |  |  | 514 |  |  | 495 |  |  | 515 |  |  | 505 |  |  | 518 |  |  | 489 |  |  | 509 |  |  | 473 |  |  | 493 |  |  | 580 |  |  | 492 |  |  | 486 |  |  | 527 |  |  | 550 |  |  | 542 |  |  | 446 |  |  | 486 |  |  | 509 |  |  | 511 |  |  | 554 |  |  | 501 |  |  | 503 |  |  | 470 |  |  | 499 |  |  | 537 |  |  | 454 |  |  | 522 |  |  | 563 |  |  | 548 |  |  | 558 |  |  | 551 |  |  | 504 |  |  | 469 |  |  | 513 |  |  | 561 |  |  | 493 |  |  | 480 |  |  | 495 |  |  | 528 |  |  | 469 |  |  | 518 |  |  | 516 |  |  | 539 |  |  | 525 |  |  | 555 |  |  | 486 |  |  | 495 |  |  | 517 |  |  | 495 |  |  | 543 |  |  | 493 |  |  | 482 |  |  | 545 |  |  | 508 |  |  | 517 |  |  | 527 |  |  | 523 |  |  | 445 |  |  | 533 |  |  | 511 |  |  | 494 |  |  | 571 |  |  | 476 |  |  | 481 |  |  | 507 |  |  | 527 |  |  | 468 |  |  | 481 |  |  | 566 |  |  | 530 |  |  | 499 |  |  | 547 |  |  | 520 |  |  | 451 |  |  | 518 |  |  | 553 |  |  | 546 |  |  | 516 |  |  | 465 |  |  | 564 |  |  | 559 |  |  | 522 |  |  | 510 |  |  | 495 |  |  | 494 |  |  | 453 |  |  | 572 |  |  | 483 |  |  | 523 |  |  | 508 |  |  | 452 |  |  | 445 |  |  | 542 |  |  | 510 |  |  | 497 |  |  | 476 |  |  | 506 |  |  | 512 |  |  | 498 |  |  | 519 |  |  | 531 |  |  | 511 |  |  | 478 |  |  | 487 |  |  | 533 |  |  | 478 |  |  | 526 |  |  | 576 |  |  | 561 |  |  | 535 |  |  | 532 |  |  | 491 |  |  | 520 |  |  | 480 |  |  | 525 |  |  | 597 |  |  | 455 |  |  | 493 |  |  | 495 |  |  | 511 |  |  | 521 |  |  | 482 |  |  | 586 |  |  | 559 |  |  | 537 |  |  | 553 |  |  | 514 |  |  | 463 |  |  | 543 |  |  | 513 |  |  | 509 |  |  | 548 |  |  | 474 |  |  | 504 |  |  | 510 |  |  | 509 |  |  | 530 |  |  | 488 |  |  | 523 |  |  | 473 |  |  | 555 |  |  | 453 |  |  | 501 |  |  | 507 |  |  | 524 |  |  | 525 |  |  | 522 |  |  | 464 |  |  | 497 |  |  | 495 |  |  | 538 |  |  | 528 |  |  | 518 |  |  | 469 |  |  | 527 |  |  | 535 |  |  | 533 |  |  | 494 |  |  | 511 |  |  | 501 |  |  | 522 |  |  | 511 |  |  | 488 |  |  | 539 |  |  | 541 |  |  | 548 |  |  | 508 |  |  | 519 |  |  | 484 |  |  | 528 |  |  | 479 |  |  | 494 |  |  | 491 |  |  | 573 |  |  | 559 |  |  | 461 |  |  | 528 |  |  | 491 |  |  | 575 |  |  | 497 |  |  | 475 |  |  | 501 |  |  | 540 |  |  | 556 |  |  | 510 |  |  | 544 |  |  | 444 |  |  | 553 |  |  | 512 |  |  | 553 |  |  | 467 |  |  | 517 |  |  | 521 |  |  | 507 |  |  | 554 |  |  | 543 |  |  | 508 |  |  | 522 |  |  | 550 |  |  | 545 |  |  | 490 |  |  | 456 |  |  | 505 |  |  | 524 |  |  | 512 |  |  | 550 |  |  | 527 |  |  | 509 |  |  | 549 |  |  | 490 |  |  | 471 |  |  | 506 |  |  | 535 |  |  | 463 |  |  | 486 |  |  | 468 |  |  | 493 |  |  | 561 |  |  | 503 |  |  | 498 |  |  | 511 |  |  | 519 |  |  | 499 |  |  | 494 |  |  | 527 |  |  | 529 |  |  | 519 |  |  | 556 |  |  | 515 |  |  | 535 |  |  | 522 |  |  | 510 |  |  | 488 |  |  | 470 |  |  | 540 |  |  | 497 |  |  | 514 |  |  | 503 |  |  | 491 |  |  | 510 |  |  | 462 |  |  | 528 |  |  | 524 |  |  | 514 |  |  | 496 |  |  | 549 |  |  | 477 |  |  | 480 |  |  | 503 |  |  | 493 |  |  | 551 |  |  | 488 |  |  | 584 |  |  | 490 |  |  | 570 |  |  | 512 |  |  | 501 |  |  | 517 |  |  | 554 |  |  | 502 |  |  | 522 |  |  | 483 |  |  | 480 |  |  | 569 |  |  | 463 |  |  | 524 |  |  | 552 |  |  | 494 |  |  | 496 |  |  | 442 |  |  | 527 |  |  | 512 |  |  | 500 |  |  | 540 |  |  | 481 |  |  | 526 |  |  | 481 |  |  | 541 |  |  | 516 |  |  | 492 |  |  | 512 |  |  | 522 |  |  | 511 |  |  | 533 |  |  | 459 |  |  | 530 |  |  | 549 |  |  | 514 |  |  | 479 |  |  | 509 |  |  | 487 |  |  | 460 |  |  | 566 |  |  | 507 |  |  | 467 |  |  | 599 |  |  | 530 |  |  | 526 |  |  | 486 |  |  | 515 |  |  | 554 |  |  | 484 |  |  | 500 |  |  | 521 |  |  | 526 |  |  | 500 |  |  | 520 |  |  | 542 |  |  | 511 |  |  | 501 |  |  | 551 |  |  | 585 |  |  | 427 |  |  | 468 |  |  | 471 |  |  | 491 |  |  | 494 |  |  | 482 |  |  | 515 |  |  | 520 |  |  | 536 |  |  | 507 |  |  | 470 |  |  | 552 |  |  | 504 |  |  | 502 |  |  | 482 |  |  | 523 |  |  | 518 |  |  | 527 |  |  | 480 |  |  | 505 |  |  | 485 |  |  | 515 |  |  | 540 |  |  | 566 |  |  | 475 |  |  | 515 |  |  | 550 |  |  | 480 |  |  | 538 |  |  | 515 |  |  | 499 |  |  | 487 |  |  | 576 |  |  | 483 |  |  | 522 |  |  | 478 |  |  | 541 |  |  | 515 |  |  | 487 |  |  | 468 |  |  | 480 |  |  | 535 |  |  | 483 |  |  | 548 |  |  | 509 |  |  | 537 |  |  | 535 |  |  | 515 |  |  | 482 |  |  | 501 |  |  | 477 |  |  | 460 |  |  | 525 |  |  | 482 |  |  | 548 |  |  | 509 |  |  | 466 |  |  | 501 |  |  | 484 |  |  | 539 |  |  | 531 |  |  | 499 |  |  | 528 |  |  | 497 |  |  | 434 |  |  | 580 |  |  | 496 |  |  | 519 |  |  | 513 |  |  | 547 |  |  | 484 |  |  | 566 |  |  | 466 |  |  | 525 |  |  | 554 |  |  | 499 |  |  | 492 |  |  | 500 |  |  | 549 |  |  | 513 |  |  | 508 |  |  | 528 |  |  | 514 |  |  | 546 |  |  | 509 |  |  | 490 |  |  | 559 |  |  | 527 |  |  | 504 |  |  | 519 |  |  | 511 |  |  | 530 |  |  | 480 |  |  | 523 |  |  | 496 |  |  | 498 |  |  | 524 |  |  | 502 |  |  | 495 |  |  | 574 |  |  | 487 |  |  | 439 |  |  | 525 |  |  | 443 |  |  | 511 |  |  | 521 |  |  | 509 |  |  | 493 |  |  | 503 |  |  | 518 |  |  | 534 |  |  | 469 |  |  | 474 |  |  | 405 |  |  | 475 |  |  | 510 |  |  | 538 |  |  | 524 |  |  | 476 |  |  | 491 |  |  | 445 |  |  | 548 |  |  | 533 |  |  | 554 |  |  | 536 |  |  | 489 |  |  | 496 |  |  | 462 |  |  | 452 |  |  | 535 |  |  | 497 |  |  | 572 |  |  | 529 |  |  | 481 |  |  | 523 |  |  | 511 |  |  | 520 |  |  | 496 |  |  | 546 |  |  | 461 |  |  | 494 |  |  | 474 |  |  | 515 |  |  | 497 |  |  | 476 |  |  | 483 |  |  | 525 |  |  | 551 |  |  | 551 |  |  | 525 |  |  | 477 |  |  | 524 |  |  | 530 |  |  | 557 |  |  | 463 |  |  | 501 |  |  | 503 |  |  | 488 |  |  | 571 |  |  | 514 |  |  | 541 |  |  | 479 |  |  | 525 |  |  | 481 |  |  | 485 |  |  | 522 |  |  | 503 |  |  | 531 |  |  | 539 |  |  | 506 |  |  | 491 |  |  | 493 |  |  | 498 |  |  | 533 |  |  | 540 |  |  | 463 |  |  | 537 |  |  | 503 |  |  | 502 |  |  | 495 |  |  | 532 |  |  | 502 |  |  | 527 |  |  | 511 |  |  | 483 |  |  | 504 |  |  | 501 |  |  | 527 |  |  | 509 |  |  | 513 |  |  | 498 |  |  | 561 |  |  | 564 |  |  | 503 |  |  | 466 |  |  | 492 |  |  | 514 |  |  | 465 |  |  | 450 |  |  | 468 |  |  | 557 |  |  | 442 |  |  | 522 |  |  | 498 |  |  | 547 |  |  | 529 |  |  | 476 |  |  | 466 |  |  | 530 |  |  | 489 |  |  | 504 |  |  | 474 |  |  | 566 |  |  | 538 |  |  | 551 |  |  | 482 |  |  | 555 |  |  | 477 |  |  | 559 |  |  | 505 |  |  | 470 |  |  | 504 |  |  | 490 |  |  | 543 |  |  | 514 |  |  | 561 |  |  | 511 |  |  | 557 |  |  | 458 |  |  | 534 |  |  | 526 |  |  | 510 |  |  | 482 |  |  | 514 |  |  | 485 |  |  | 518 |  |  | 501 |  |  | 504 |  |  | 516 |  |  | 449 |  |  | 500 |  |  | 607 |  |  | 525 |  |  | 538 |  |  | 486 |  |  | 486 |  |  | 484 |  |  | 502 |  |  | 514 |  |  | 510 |  |  | 555 |  |  | 498 |  |  | 471 |  |  | 558 |  |  | 509 |  |  | 518 |  |  | 501 |  |  | 498 |  |  | 524 |  |  | 489 |  |  | 477 |  |  | 538 |  |  | 498 |  |  | 543 |  |  | 516 |  |  | 512 |  |  | 472 |  |  | 471 |  |  | 476 |  |  | 536 |  |  | 556 |  |  | 533 |  |  | 552 |  |  | 525 |  |  | 519 |  |  | 511 |  |  | 505 |  |  | 537 |  |  | 538 |  |  | 503 |  |  | 532 |  |  | 494 |  |  | 467 |  |  | 538 |  |  | 494 |  |  | 496 |  |  | 518 |  |  | 535 |  |  | 525 |  |  | 506 |  |  | 487 |  |  | 524 |  |  | 486 |  |  | 499 |  |  | 464 |  |  | 506 |  |  | 530 |  |  | 521 |  |  | 500 |  |  | 569 |  |  | 523 |  |  | 495 |  |  | 500 |  |  | 489 |  |  | 549 |  |  | 532 |  |  | 517 |  |  | 512 |  |  | 471 |  |  | 496 |  |  | 511 |  |  | 443 |  |  | 497 |  |  | 474 |  |  | 509 |  |  | 540 |  |  | 477 |  |  | 504 |  |  | 504 |  |  | 488 |  |  | 534 |  |  | 507 |  |  | 533 |  |  | 422 |  |  | 488 |  |  | 468 |  |  | 551 |  |  | 503 |  |  | 499 |  |  | 502 |  |  | 489 |  |  | 485 |  |  | 527 |  |  | 464 |  |  | 480 |  |  | 490 |  |  | 481 |  |  | 459 |  |  | 502 |  |  | 483 |  |  | 563 |  |  | 530 |  |  | 515 |  |  | 508 |  |  | 516 |  |  | 490 |  |  | 499 |  |  | 479 |  |  | 548
18 |  | 566 |  |  | 534 |  |  | 506 |  |  | 565 |  |  | 527 |  |  | 550 |  |  | 530 |  |  | 541 |  |  | 579 |  |  | 560 |  |  | 553 |  |  | 600 |  |  | 521 |  |  | 555 |  |  | 554 |  |  | 563 |  |  | 533 |  |  | 545 |  |  | 567 |  |  | 481 |  |  | 529 |  |  | 567 |  |  | 553 |  |  | 544 |  |  | 501 |  |  | 559 |  |  | 579 |  |  | 537 |  |  | 582 |  |  | 560 |  |  | 533 |  |  | 520 |  |  | 624 |  |  | 536 |  |  | 505 |  |  | 525 |  |  | 516 |  |  | 532 |  |  | 537 |  |  | 572 |  |  | 470 |  |  | 529 |  |  | 553 |  |  | 580 |  |  | 573 |  |  | 565 |  |  | 534 |  |  | 557 |  |  | 498 |  |  | 520 |  |  | 566 |  |  | 573 |  |  | 520 |  |  | 564 |  |  | 506 |  |  | 552 |  |  | 585 |  |  | 578 |  |  | 563 |  |  | 567 |  |  | 621 |  |  | 544 |  |  | 529 |  |  | 555 |  |  | 505 |  |  | 511 |  |  | 560 |  |  | 576 |  |  | 605 |  |  | 516 |  |  | 551 |  |  | 497 |  |  | 516 |  |  | 475 |  |  | 544 |  |  | 514 |  |  | 535 |  |  | 516 |  |  | 549 |  |  | 575 |  |  | 583 |  |  | 564 |  |  | 523 |  |  | 547 |  |  | 530 |  |  | 535 |  |  | 504 |  |  | 529 |  |  | 484 |  |  | 557 |  |  | 524 |  |  | 525 |  |  | 616 |  |  | 537 |  |  | 515 |  |  | 558 |  |  | 549 |  |  | 531 |  |  | 527 |  |  | 498 |  |  | 520 |  |  | 488 |  |  | 524 |  |  | 558 |  |  | 548 |  |  | 512 |  |  | 506 |  |  | 536 |  |  | 525 |  |  | 525 |  |  | 535 |  |  | 516 |  |  | 552 |  |  | 543 |  |  | 526 |  |  | 563 |  |  | 581 |  |  | 497 |  |  | 499 |  |  | 569 |  |  | 589 |  |  | 514 |  |  | 584 |  |  | 531 |  |  | 501 |  |  | 535 |  |  | 539 |  |  | 553 |  |  | 510 |  |  | 590 |  |  | 577 |  |  | 595 |  |  | 481 |  |  | 493 |  |  | 501 |  |  | 523 |  |  | 544 |  |  | 575 |  |  | 556 |  |  | 515 |  |  | 501 |  |  | 524 |  |  | 552 |  |  | 553 |  |  | 528 |  |  | 535 |  |  | 491 |  |  | 540 |  |  | 546 |  |  | 520 |  |  | 506 |  |  | 532 |  |  | 519 |  |  | 539 |  |  | 522 |  |  | 576 |  |  | 497 |  |  | 549 |  |  | 512 |  |  | 616 |  |  | 587 |  |  | 537 |  |  | 554 |  |  | 508 |  |  | 522 |  |  | 504 |  |  | 511 |  |  | 535 |  |  | 553 |  |  | 569 |  |  | 532 |  |  | 541 |  |  | 539 |  |  | 562 |  |  | 539 |  |  | 525 |  |  | 504 |  |  | 567 |  |  | 558 |  |  | 517 |  |  | 542 |  |  | 600 |  |  | 586 |  |  | 521 |  |  | 509 |  |  | 564 |  |  | 522 |  |  | 521 |  |  | 522 |  |  | 521 |  |  | 506 |  |  | 563 |  |  | 567 |  |  | 523 |  |  | 514 |  |  | 552 |  |  | 501 |  |  | 530 |  |  | 552 |  |  | 534 |  |  | 556 |  |  | 539 |  |  | 490 |  |  | 534 |  |  | 592 |  |  | 553 |  |  | 525 |  |  | 562 |  |  | 552 |  |  | 550 |  |  | 585 |  |  | 517 |  |  | 532 |  |  | 572 |  |  | 532 |  |  | 488 |  |  | 558 |  |  | 538 |  |  | 531 |  |  | 569 |  |  | 492 |  |  | 553 |  |  | 542 |  |  | 499 |  |  | 490 |  |  | 546 |  |  | 562 |  |  | 539 |  |  | 525 |  |  | 512 |  |  | 534 |  |  | 522 |  |  | 571 |  |  | 567 |  |  | 551 |  |  | 547 |  |  | 500 |  |  | 506 |  |  | 527 |  |  | 553 |  |  | 553 |  |  | 559 |  |  | 544 |  |  | 593 |  |  | 575 |  |  | 480 |  |  | 565 |  |  | 598 |  |  | 558 |  |  | 529 |  |  | 496 |  |  | 579 |  |  | 557 |  |  | 588 |  |  | 581 |  |  | 477 |  |  | 536 |  |  | 572 |  |  | 547 |  |  | 534 |  |  | 579 |  |  | 515 |  |  | 514 |  |  | 559 |  |  | 576 |  |  | 580 |  |  | 575 |  |  | 549 |  |  | 515 |  |  | 520 |  |  | 562 |  |  | 600 |  |  | 584 |  |  | 559 |  |  | 577 |  |  | 512 |  |  | 477 |  |  | 573 |  |  | 519 |  |  | 573 |  |  | 497 |  |  | 543 |  |  | 542 |  |  | 510 |  |  | 553 |  |  | 534 |  |  | 571 |  |  | 538 |  |  | 574 |  |  | 518 |  |  | 490 |  |  | 559 |  |  | 532 |  |  | 507 |  |  | 559 |  |  | 565 |  |  | 555 |  |  | 558 |  |  | 613 |  |  | 568 |  |  | 538 |  |  | 550 |  |  | 533 |  |  | 545 |  |  | 536 |  |  | 532 |  |  | 609 |  |  | 512 |  |  | 544 |  |  | 587 |  |  | 623 |  |  | 528 |  |  | 513 |  |  | 563 |  |  | 538 |  |  | 495 |  |  | 548 |  |  | 537 |  |  | 531 |  |  | 531 |  |  | 532 |  |  | 587 |  |  | 558 |  |  | 506 |  |  | 559 |  |  | 537 |  |  | 516 |  |  | 549 |  |  | 527 |  |  | 599 |  |  | 510 |  |  | 593 |  |  | 623 |  |  | 542 |  |  | 571 |  |  | 509 |  |  | 557 |  |  | 619 |  |  | 579 |  |  | 535 |  |  | 521 |  |  | 530 |  |  | 531 |  |  | 533 |  |  | 510 |  |  | 533 |  |  | 494 |  |  | 532 |  |  | 627 |  |  | 531 |  |  | 525 |  |  | 566 |  |  | 576 |  |  | 557 |  |  | 493 |  |  | 515 |  |  | 530 |  |  | 526 |  |  | 578 |  |  | 530 |  |  | 529 |  |  | 499 |  |  | 525 |  |  | 552 |  |  | 483 |  |  | 561 |  |  | 589 |  |  | 577 |  |  | 584 |  |  | 590 |  |  | 543 |  |  | 498 |  |  | 534 |  |  | 600 |  |  | 514 |  |  | 495 |  |  | 516 |  |  | 552 |  |  | 508 |  |  | 539 |  |  | 540 |  |  | 578 |  |  | 564 |  |  | 594 |  |  | 525 |  |  | 534 |  |  | 532 |  |  | 534 |  |  | 567 |  |  | 508 |  |  | 508 |  |  | 574 |  |  | 547 |  |  | 532 |  |  | 542 |  |  | 552 |  |  | 474 |  |  | 557 |  |  | 550 |  |  | 509 |  |  | 610 |  |  | 515 |  |  | 528 |  |  | 522 |  |  | 553 |  |  | 492 |  |  | 510 |  |  | 605 |  |  | 559 |  |  | 538 |  |  | 586 |  |  | 544 |  |  | 480 |  |  | 539 |  |  | 568 |  |  | 593 |  |  | 555 |  |  | 491 |  |  | 603 |  |  | 583 |  |  | 551 |  |  | 534 |  |  | 519 |  |  | 523 |  |  | 479 |  |  | 596 |  |  | 512 |  |  | 549 |  |  | 555 |  |  | 499 |  |  | 484 |  |  | 581 |  |  | 549 |  |  | 526 |  |  | 505 |  |  | 535 |  |  | 551 |  |  | 524 |  |  | 540 |  |  | 578 |  |  | 537 |  |  | 507 |  |  | 526 |  |  | 554 |  |  | 507 |  |  | 565 |  |  | 615 |  |  | 576 |  |  | 561 |  |  | 579 |  |  | 520 |  |  | 544 |  |  | 509 |  |  | 540 |  |  | 621 |  |  | 479 |  |  | 532 |  |  | 519 |  |  | 550 |  |  | 550 |  |  | 508 |  |  | 633 |  |  | 583 |  |  | 576 |  |  | 582 |  |  | 538 |  |  | 484 |  |  | 590 |  |  | 552 |  |  | 538 |  |  | 595 |  |  | 500 |  |  | 543 |  |  | 539 |  |  | 533 |  |  | 559 |  |  | 527 |  |  | 547 |  |  | 488 |  |  | 581 |  |  | 500 |  |  | 530 |  |  | 554 |  |  | 545 |  |  | 540 |  |  | 543 |  |  | 503 |  |  | 536 |  |  | 516 |  |  | 564 |  |  | 575 |  |  | 544 |  |  | 508 |  |  | 553 |  |  | 574 |  |  | 572 |  |  | 509 |  |  | 537 |  |  | 530 |  |  | 561 |  |  | 550 |  |  | 535 |  |  | 560 |  |  | 580 |  |  | 569 |  |  | 537 |  |  | 534 |  |  | 499 |  |  | 549 |  |  | 508 |  |  | 523 |  |  | 538 |  |  | 620 |  |  | 598 |  |  | 485 |  |  | 549 |  |  | 530 |  |  | 604 |  |  | 523 |  |  | 504 |  |  | 527 |  |  | 564 |  |  | 582 |  |  | 549 |  |  | 570 |  |  | 491 |  |  | 592 |  |  | 538 |  |  | 600 |  |  | 506 |  |  | 543 |  |  | 568 |  |  | 531 |  |  | 580 |  |  | 572 |  |  | 547 |  |  | 548 |  |  | 571 |  |  | 574 |  |  | 511 |  |  | 495 |  |  | 552 |  |  | 548 |  |  | 551 |  |  | 571 |  |  | 548 |  |  | 524 |  |  | 573 |  |  | 529 |  |  | 500 |  |  | 527 |  |  | 550 |  |  | 487 |  |  | 533 |  |  | 492 |  |  | 540 |  |  | 576 |  |  | 529 |  |  | 537 |  |  | 532 |  |  | 558 |  |  | 525 |  |  | 533 |  |  | 574 |  |  | 550 |  |  | 540 |  |  | 603 |  |  | 554 |  |  | 559 |  |  | 546 |  |  | 525 |  |  | 503 |  |  | 509 |  |  | 555 |  |  | 544 |  |  | 540 |  |  | 542 |  |  | 517 |  |  | 536 |  |  | 491 |  |  | 557 |  |  | 539 |  |  | 561 |  |  | 522 |  |  | 564 |  |  | 498 |  |  | 527 |  |  | 518 |  |  | 532 |  |  | 572 |  |  | 535 |  |  | 623 |  |  | 511 |  |  | 594 |  |  | 527 |  |  | 516 |  |  | 546 |  |  | 580 |  |  | 528 |  |  | 537 |  |  | 509 |  |  | 527 |  |  | 608 |  |  | 510 |  |  | 553 |  |  | 591 |  |  | 533 |  |  | 525 |  |  | 481 |  |  | 566 |  |  | 541 |  |  | 539 |  |  | 569 |  |  | 502 |  |  | 555 |  |  | 510 |  |  | 562 |  |  | 555 |  |  | 513 |  |  | 527 |  |  | 548 |  |  | 550 |  |  | 572 |  |  | 483 |  |  | 559 |  |  | 573 |  |  | 538 |  |  | 508 |  |  | 535 |  |  | 516 |  |  | 484 |  |  | 595 |  |  | 536 |  |  | 482 |  |  | 646 |  |  | 556 |  |  | 555 |  |  | 507 |  |  | 539 |  |  | 569 |  |  | 508 |  |  | 521 |  |  | 545 |  |  | 547 |  |  | 547 |  |  | 559 |  |  | 581 |  |  | 558 |  |  | 540 |  |  | 590 |  |  | 609 |  |  | 453 |  |  | 492 |  |  | 492 |  |  | 517 |  |  | 533 |  |  | 511 |  |  | 554 |  |  | 559 |  |  | 583 |  |  | 536 |  |  | 517 |  |  | 576 |  |  | 551 |  |  | 549 |  |  | 506 |  |  | 544 |  |  | 542 |  |  | 574 |  |  | 509 |  |  | 552 |  |  | 532 |  |  | 536 |  |  | 569 |  |  | 587 |  |  | 501 |  |  | 562 |  |  | 576 |  |  | 509 |  |  | 585 |  |  | 539 |  |  | 546 |  |  | 526 |  |  | 615 |  |  | 522 |  |  | 551 |  |  | 517 |  |  | 580 |  |  | 562 |  |  | 534 |  |  | 483 |  |  | 504 |  |  | 561 |  |  | 522 |  |  | 587 |  |  | 548 |  |  | 584 |  |  | 564 |  |  | 562 |  |  | 521 |  |  | 540 |  |  | 516 |  |  | 489 |  |  | 549 |  |  | 503 |  |  | 569 |  |  | 548 |  |  | 490 |  |  | 540 |  |  | 531 |  |  | 565 |  |  | 578 |  |  | 538 |  |  | 554 |  |  | 536 |  |  | 449 |  |  | 619 |  |  | 535 |  |  | 545 |  |  | 560 |  |  | 576 |  |  | 505 |  |  | 587 |  |  | 487 |  |  | 551 |  |  | 601 |  |  | 520 |  |  | 539 |  |  | 515 |  |  | 578 |  |  | 552 |  |  | 555 |  |  | 543 |  |  | 553 |  |  | 593 |  |  | 533 |  |  | 529 |  |  | 583 |  |  | 548 |  |  | 533 |  |  | 548 |  |  | 540 |  |  | 577 |  |  | 495 |  |  | 562 |  |  | 525 |  |  | 524 |  |  | 545 |  |  | 517 |  |  | 516 |  |  | 589 |  |  | 502 |  |  | 478 |  |  | 554 |  |  | 464 |  |  | 535 |  |  | 560 |  |  | 530 |  |  | 519 |  |  | 542 |  |  | 539 |  |  | 555 |  |  | 508 |  |  | 521 |  |  | 444 |  |  | 496 |  |  | 531 |  |  | 559 |  |  | 548 |  |  | 515 |  |  | 520 |  |  | 466 |  |  | 577 |  |  | 572 |  |  | 601 |  |  | 562 |  |  | 518 |  |  | 520 |  |  | 509 |  |  | 499 |  |  | 556 |  |  | 521 |  |  | 596 |  |  | 576 |  |  | 520 |  |  | 562 |  |  | 535 |  |  | 559 |  |  | 517 |  |  | 585 |  |  | 485 |  |  | 509 |  |  | 495 |  |  | 530 |  |  | 512 |  |  | 505 |  |  | 498 |  |  | 572 |  |  | 577 |  |  | 572 |  |  | 551 |  |  | 503 |  |  | 563 |  |  | 569 |  |  | 583 |  |  | 487 |  |  | 527 |  |  | 524 |  |  | 503 |  |  | 595 |  |  | 529 |  |  | 570 |  |  | 503 |  |  | 564 |  |  | 520 |  |  | 506 |  |  | 561 |  |  | 532 |  |  | 546 |  |  | 560 |  |  | 527 |  |  | 520 |  |  | 517 |  |  | 513 |  |  | 554 |  |  | 569 |  |  | 489 |  |  | 563 |  |  | 532 |  |  | 531 |  |  | 510 |  |  | 561 |  |  | 541 |  |  | 556 |  |  | 540 |  |  | 512 |  |  | 543 |  |  | 525 |  |  | 542 |  |  | 533 |  |  | 539 |  |  | 545 |  |  | 590 |  |  | 603 |  |  | 524 |  |  | 487 |  |  | 531 |  |  | 540 |  |  | 512 |  |  | 479 |  |  | 492 |  |  | 596 |  |  | 466 |  |  | 548 |  |  | 522 |  |  | 576 |  |  | 550 |  |  | 523 |  |  | 505 |  |  | 545 |  |  | 528 |  |  | 533 |  |  | 495 |  |  | 592 |  |  | 564 |  |  | 580 |  |  | 508 |  |  | 594 |  |  | 516 |  |  | 583 |  |  | 544 |  |  | 517 |  |  | 519 |  |  | 529 |  |  | 567 |  |  | 538 |  |  | 590 |  |  | 537 |  |  | 572 |  |  | 497 |  |  | 563 |  |  | 552 |  |  | 536 |  |  | 521 |  |  | 529 |  |  | 500 |  |  | 539 |  |  | 540 |  |  | 543 |  |  | 555 |  |  | 488 |  |  | 524 |  |  | 628 |  |  | 546 |  |  | 562 |  |  | 510 |  |  | 501 |  |  | 510 |  |  | 523 |  |  | 543 |  |  | 557 |  |  | 576 |  |  | 537 |  |  | 510 |  |  | 582 |  |  | 548 |  |  | 547 |  |  | 548 |  |  | 513 |  |  | 545 |  |  | 504 |  |  | 524 |  |  | 559 |  |  | 527 |  |  | 564 |  |  | 555 |  |  | 559 |  |  | 487 |  |  | 497 |  |  | 505 |  |  | 551 |  |  | 595 |  |  | 554 |  |  | 591 |  |  | 546 |  |  | 545 |  |  | 535 |  |  | 529 |  |  | 561 |  |  | 585 |  |  | 532 |  |  | 579 |  |  | 523 |  |  | 496 |  |  | 577 |  |  | 523 |  |  | 543 |  |  | 544 |  |  | 564 |  |  | 564 |  |  | 527 |  |  | 526 |  |  | 539 |  |  | 515 |  |  | 546 |  |  | 479 |  |  | 545 |  |  | 559 |  |  | 536 |  |  | 524 |  |  | 584 |  |  | 562 |  |  | 519 |  |  | 529 |  |  | 528 |  |  | 570 |  |  | 571 |  |  | 564 |  |  | 559 |  |  | 510 |  |  | 535 |  |  | 550 |  |  | 458 |  |  | 518 |  |  | 489 |  |  | 548 |  |  | 587 |  |  | 492 |  |  | 525 |  |  | 543 |  |  | 503 |  |  | 560 |  |  | 533 |  |  | 572 |  |  | 443 |  |  | 503 |  |  | 494 |  |  | 598 |  |  | 542 |  |  | 514 |  |  | 541 |  |  | 536 |  |  | 511 |  |  | 556 |  |  | 479 |  |  | 527 |  |  | 514 |  |  | 507 |  |  | 488 |  |  | 541 |  |  | 512 |  |  | 602 |  |  | 551 |  |  | 539 |  |  | 547 |  |  | 545 |  |  | 529 |  |  | 528 |  |  | 500 |  |  | 577
19 |  | 613 |  |  | 573 |  |  | 532 |  |  | 604 |  |  | 566 |  |  | 576 |  |  | 569 |  |  | 567 |  |  | 605 |  |  | 599 |  |  | 592 |  |  | 647 |  |  | 547 |  |  | 579 |  |  | 569 |  |  | 587 |  |  | 557 |  |  | 566 |  |  | 582 |  |  | 505 |  |  | 568 |  |  | 606 |  |  | 592 |  |  | 583 |  |  | 522 |  |  | 588 |  |  | 618 |  |  | 563 |  |  | 606 |  |  | 599 |  |  | 557 |  |  | 546 |  |  | 663 |  |  | 557 |  |  | 520 |  |  | 551 |  |  | 545 |  |  | 553 |  |  | 561 |  |  | 611 |  |  | 496 |  |  | 568 |  |  | 592 |  |  | 609 |  |  | 612 |  |  | 604 |  |  | 555 |  |  | 604 |  |  | 537 |  |  | 544 |  |  | 605 |  |  | 612 |  |  | 549 |  |  | 590 |  |  | 527 |  |  | 578 |  |  | 606 |  |  | 625 |  |  | 602 |  |  | 606 |  |  | 642 |  |  | 583 |  |  | 550 |  |  | 579 |  |  | 520 |  |  | 532 |  |  | 599 |  |  | 615 |  |  | 652 |  |  | 555 |  |  | 590 |  |  | 536 |  |  | 545 |  |  | 514 |  |  | 583 |  |  | 538 |  |  | 556 |  |  | 540 |  |  | 573 |  |  | 604 |  |  | 609 |  |  | 588 |  |  | 547 |  |  | 586 |  |  | 569 |  |  | 564 |  |  | 530 |  |  | 568 |  |  | 508 |  |  | 583 |  |  | 545 |  |  | 564 |  |  | 663 |  |  | 552 |  |  | 544 |  |  | 573 |  |  | 596 |  |  | 555 |  |  | 553 |  |  | 545 |  |  | 559 |  |  | 509 |  |  | 563 |  |  | 584 |  |  | 572 |  |  | 551 |  |  | 530 |  |  | 575 |  |  | 564 |  |  | 564 |  |  | 556 |  |  | 531 |  |  | 573 |  |  | 558 |  |  | 565 |  |  | 602 |  |  | 607 |  |  | 512 |  |  | 528 |  |  | 608 |  |  | 636 |  |  | 535 |  |  | 613 |  |  | 560 |  |  | 516 |  |  | 582 |  |  | 578 |  |  | 582 |  |  | 539 |  |  | 614 |  |  | 592 |  |  | 619 |  |  | 496 |  |  | 514 |  |  | 525 |  |  | 538 |  |  | 583 |  |  | 596 |  |  | 585 |  |  | 554 |  |  | 516 |  |  | 548 |  |  | 573 |  |  | 579 |  |  | 575 |  |  | 550 |  |  | 517 |  |  | 566 |  |  | 585 |  |  | 535 |  |  | 521 |  |  | 571 |  |  | 545 |  |  | 578 |  |  | 561 |  |  | 615 |  |  | 518 |  |  | 578 |  |  | 536 |  |  | 640 |  |  | 626 |  |  | 552 |  |  | 569 |  |  | 523 |  |  | 546 |  |  | 525 |  |  | 550 |  |  | 574 |  |  | 568 |  |  | 608 |  |  | 558 |  |  | 565 |  |  | 568 |  |  | 601 |  |  | 568 |  |  | 551 |  |  | 525 |  |  | 591 |  |  | 605 |  |  | 538 |  |  | 589 |  |  | 639 |  |  | 601 |  |  | 545 |  |  | 548 |  |  | 611 |  |  | 543 |  |  | 547 |  |  | 569 |  |  | 560 |  |  | 545 |  |  | 602 |  |  | 606 |  |  | 570 |  |  | 535 |  |  | 581 |  |  | 540 |  |  | 554 |  |  | 576 |  |  | 563 |  |  | 585 |  |  | 568 |  |  | 537 |  |  | 558 |  |  | 631 |  |  | 600 |  |  | 546 |  |  | 601 |  |  | 591 |  |  | 589 |  |  | 624 |  |  | 546 |  |  | 553 |  |  | 619 |  |  | 571 |  |  | 517 |  |  | 584 |  |  | 577 |  |  | 560 |  |  | 608 |  |  | 516 |  |  | 592 |  |  | 589 |  |  | 538 |  |  | 519 |  |  | 567 |  |  | 601 |  |  | 565 |  |  | 572 |  |  | 538 |  |  | 558 |  |  | 537 |  |  | 618 |  |  | 582 |  |  | 577 |  |  | 568 |  |  | 524 |  |  | 535 |  |  | 542 |  |  | 600 |  |  | 592 |  |  | 598 |  |  | 570 |  |  | 614 |  |  | 601 |  |  | 509 |  |  | 604 |  |  | 624 |  |  | 597 |  |  | 558 |  |  | 522 |  |  | 603 |  |  | 583 |  |  | 614 |  |  | 596 |  |  | 516 |  |  | 557 |  |  | 587 |  |  | 576 |  |  | 573 |  |  | 608 |  |  | 541 |  |  | 538 |  |  | 598 |  |  | 600 |  |  | 601 |  |  | 604 |  |  | 564 |  |  | 562 |  |  | 559 |  |  | 601 |  |  | 639 |  |  | 599 |  |  | 606 |  |  | 603 |  |  | 536 |  |  | 516 |  |  | 602 |  |  | 543 |  |  | 620 |  |  | 536 |  |  | 572 |  |  | 566 |  |  | 534 |  |  | 600 |  |  | 573 |  |  | 618 |  |  | 577 |  |  | 598 |  |  | 565 |  |  | 511 |  |  | 588 |  |  | 579 |  |  | 546 |  |  | 606 |  |  | 604 |  |  | 602 |  |  | 587 |  |  | 652 |  |  | 592 |  |  | 559 |  |  | 574 |  |  | 548 |  |  | 574 |  |  | 551 |  |  | 547 |  |  | 635 |  |  | 559 |  |  | 568 |  |  | 608 |  |  | 649 |  |  | 549 |  |  | 528 |  |  | 610 |  |  | 577 |  |  | 524 |  |  | 563 |  |  | 584 |  |  | 560 |  |  | 570 |  |  | 553 |  |  | 616 |  |  | 579 |  |  | 521 |  |  | 574 |  |  | 563 |  |  | 555 |  |  | 588 |  |  | 542 |  |  | 646 |  |  | 539 |  |  | 632 |  |  | 644 |  |  | 589 |  |  | 597 |  |  | 538 |  |  | 604 |  |  | 648 |  |  | 626 |  |  | 574 |  |  | 568 |  |  | 569 |  |  | 560 |  |  | 580 |  |  | 534 |  |  | 548 |  |  | 533 |  |  | 547 |  |  | 653 |  |  | 570 |  |  | 554 |  |  | 590 |  |  | 591 |  |  | 596 |  |  | 522 |  |  | 544 |  |  | 577 |  |  | 565 |  |  | 607 |  |  | 577 |  |  | 555 |  |  | 538 |  |  | 551 |  |  | 591 |  |  | 512 |  |  | 582 |  |  | 618 |  |  | 616 |  |  | 623 |  |  | 616 |  |  | 558 |  |  | 519 |  |  | 558 |  |  | 639 |  |  | 538 |  |  | 534 |  |  | 537 |  |  | 591 |  |  | 532 |  |  | 586 |  |  | 561 |  |  | 617 |  |  | 579 |  |  | 620 |  |  | 549 |  |  | 573 |  |  | 571 |  |  | 573 |  |  | 614 |  |  | 547 |  |  | 523 |  |  | 613 |  |  | 568 |  |  | 561 |  |  | 581 |  |  | 567 |  |  | 489 |  |  | 581 |  |  | 597 |  |  | 535 |  |  | 634 |  |  | 562 |  |  | 567 |  |  | 537 |  |  | 579 |  |  | 507 |  |  | 534 |  |  | 644 |  |  | 588 |  |  | 585 |  |  | 601 |  |  | 559 |  |  | 527 |  |  | 568 |  |  | 615 |  |  | 619 |  |  | 594 |  |  | 512 |  |  | 642 |  |  | 612 |  |  | 577 |  |  | 581 |  |  | 545 |  |  | 570 |  |  | 518 |  |  | 622 |  |  | 527 |  |  | 596 |  |  | 581 |  |  | 528 |  |  | 510 |  |  | 610 |  |  | 575 |  |  | 565 |  |  | 544 |  |  | 559 |  |  | 598 |  |  | 539 |  |  | 566 |  |  | 593 |  |  | 561 |  |  | 554 |  |  | 573 |  |  | 593 |  |  | 522 |  |  | 604 |  |  | 662 |  |  | 600 |  |  | 600 |  |  | 618 |  |  | 541 |  |  | 570 |  |  | 556 |  |  | 569 |  |  | 642 |  |  | 526 |  |  | 571 |  |  | 534 |  |  | 576 |  |  | 576 |  |  | 523 |  |  | 648 |  |  | 609 |  |  | 602 |  |  | 629 |  |  | 567 |  |  | 508 |  |  | 605 |  |  | 581 |  |  | 577 |  |  | 621 |  |  | 524 |  |  | 572 |  |  | 568 |  |  | 580 |  |  | 580 |  |  | 556 |  |  | 576 |  |  | 527 |  |  | 605 |  |  | 529 |  |  | 559 |  |  | 593 |  |  | 569 |  |  | 579 |  |  | 569 |  |  | 550 |  |  | 560 |  |  | 555 |  |  | 593 |  |  | 596 |  |  | 559 |  |  | 537 |  |  | 568 |  |  | 613 |  |  | 596 |  |  | 548 |  |  | 566 |  |  | 569 |  |  | 600 |  |  | 571 |  |  | 564 |  |  | 581 |  |  | 601 |  |  | 608 |  |  | 552 |  |  | 563 |  |  | 523 |  |  | 575 |  |  | 532 |  |  | 562 |  |  | 585 |  |  | 659 |  |  | 637 |  |  | 514 |  |  | 588 |  |  | 569 |  |  | 651 |  |  | 549 |  |  | 533 |  |  | 566 |  |  | 603 |  |  | 621 |  |  | 588 |  |  | 585 |  |  | 506 |  |  | 607 |  |  | 553 |  |  | 647 |  |  | 521 |  |  | 558 |  |  | 589 |  |  | 546 |  |  | 604 |  |  | 619 |  |  | 562 |  |  | 587 |  |  | 600 |  |  | 595 |  |  | 550 |  |  | 516 |  |  | 591 |  |  | 587 |  |  | 590 |  |  | 586 |  |  | 572 |  |  | 539 |  |  | 612 |  |  | 553 |  |  | 539 |  |  | 551 |  |  | 574 |  |  | 502 |  |  | 557 |  |  | 516 |  |  | 561 |  |  | 605 |  |  | 576 |  |  | 563 |  |  | 558 |  |  | 573 |  |  | 554 |  |  | 554 |  |  | 613 |  |  | 579 |  |  | 566 |  |  | 632 |  |  | 580 |  |  | 583 |  |  | 593 |  |  | 554 |  |  | 524 |  |  | 533 |  |  | 576 |  |  | 573 |  |  | 564 |  |  | 581 |  |  | 556 |  |  | 562 |  |  | 506 |  |  | 596 |  |  | 586 |  |  | 587 |  |  | 537 |  |  | 603 |  |  | 519 |  |  | 551 |  |  | 565 |  |  | 571 |  |  | 619 |  |  | 564 |  |  | 638 |  |  | 550 |  |  | 615 |  |  | 556 |  |  | 545 |  |  | 570 |  |  | 627 |  |  | 549 |  |  | 563 |  |  | 530 |  |  | 556 |  |  | 632 |  |  | 549 |  |  | 574 |  |  | 630 |  |  | 572 |  |  | 554 |  |  | 502 |  |  | 590 |  |  | 565 |  |  | 568 |  |  | 584 |  |  | 541 |  |  | 576 |  |  | 531 |  |  | 591 |  |  | 602 |  |  | 528 |  |  | 553 |  |  | 577 |  |  | 576 |  |  | 619 |  |  | 509 |  |  | 598 |  |  | 602 |  |  | 562 |  |  | 555 |  |  | 556 |  |  | 555 |  |  | 513 |  |  | 621 |  |  | 575 |  |  | 521 |  |  | 675 |  |  | 595 |  |  | 570 |  |  | 533 |  |  | 578 |  |  | 593 |  |  | 537 |  |  | 568 |  |  | 560 |  |  | 573 |  |  | 568 |  |  | 598 |  |  | 602 |  |  | 584 |  |  | 564 |  |  | 616 |  |  | 648 |  |  | 474 |  |  | 539 |  |  | 531 |  |  | 538 |  |  | 572 |  |  | 558 |  |  | 575 |  |  | 598 |  |  | 612 |  |  | 565 |  |  | 564 |  |  | 623 |  |  | 575 |  |  | 564 |  |  | 553 |  |  | 565 |  |  | 563 |  |  | 613 |  |  | 548 |  |  | 599 |  |  | 547 |  |  | 575 |  |  | 593 |  |  | 608 |  |  | 522 |  |  | 577 |  |  | 615 |  |  | 524 |  |  | 624 |  |  | 565 |  |  | 561 |  |  | 541 |  |  | 630 |  |  | 551 |  |  | 566 |  |  | 546 |  |  | 627 |  |  | 586 |  |  | 573 |  |  | 504 |  |  | 525 |  |  | 608 |  |  | 561 |  |  | 602 |  |  | 577 |  |  | 631 |  |  | 579 |  |  | 583 |  |  | 545 |  |  | 555 |  |  | 542 |  |  | 528 |  |  | 573 |  |  | 532 |  |  | 590 |  |  | 595 |  |  | 514 |  |  | 579 |  |  | 546 |  |  | 604 |  |  | 593 |  |  | 562 |  |  | 575 |  |  | 560 |  |  | 470 |  |  | 645 |  |  | 561 |  |  | 571 |  |  | 607 |  |  | 615 |  |  | 520 |  |  | 613 |  |  | 508 |  |  | 572 |  |  | 616 |  |  | 559 |  |  | 578 |  |  | 562 |  |  | 593 |  |  | 573 |  |  | 602 |  |  | 582 |  |  | 574 |  |  | 622 |  |  | 554 |  |  | 576 |  |  | 622 |  |  | 587 |  |  | 572 |  |  | 595 |  |  | 564 |  |  | 616 |  |  | 534 |  |  | 588 |  |  | 564 |  |  | 548 |  |  | 574 |  |  | 541 |  |  | 531 |  |  | 610 |  |  | 541 |  |  | 499 |  |  | 593 |  |  | 479 |  |  | 559 |  |  | 584 |  |  | 554 |  |  | 558 |  |  | 581 |  |  | 563 |  |  | 570 |  |  | 534 |  |  | 536 |  |  | 459 |  |  | 522 |  |  | 546 |  |  | 598 |  |  | 572 |  |  | 530 |  |  | 541 |  |  | 481 |  |  | 616 |  |  | 611 |  |  | 640 |  |  | 588 |  |  | 544 |  |  | 559 |  |  | 530 |  |  | 546 |  |  | 595 |  |  | 547 |  |  | 643 |  |  | 615 |  |  | 567 |  |  | 601 |  |  | 582 |  |  | 583 |  |  | 541 |  |  | 606 |  |  | 532 |  |  | 556 |  |  | 521 |  |  | 556 |  |  | 533 |  |  | 529 |  |  | 537 |  |  | 593 |  |  | 598 |  |  | 593 |  |  | 572 |  |  | 527 |  |  | 578 |  |  | 593 |  |  | 630 |  |  | 516 |  |  | 553 |  |  | 563 |  |  | 518 |  |  | 619 |  |  | 555 |  |  | 594 |  |  | 518 |  |  | 585 |  |  | 535 |  |  | 545 |  |  | 585 |  |  | 561 |  |  | 593 |  |  | 586 |  |  | 566 |  |  | 546 |  |  | 543 |  |  | 552 |  |  | 575 |  |  | 598 |  |  | 536 |  |  | 602 |  |  | 561 |  |  | 552 |  |  | 534 |  |  | 576 |  |  | 580 |  |  | 577 |  |  | 579 |  |  | 551 |  |  | 567 |  |  | 549 |  |  | 581 |  |  | 580 |  |  | 578 |  |  | 571 |  |  | 629 |  |  | 642 |  |  | 548 |  |  | 534 |  |  | 560 |  |  | 566 |  |  | 536 |  |  | 505 |  |  | 516 |  |  | 611 |  |  | 490 |  |  | 587 |  |  | 561 |  |  | 600 |  |  | 589 |  |  | 552 |  |  | 544 |  |  | 592 |  |  | 552 |  |  | 572 |  |  | 519 |  |  | 618 |  |  | 590 |  |  | 606 |  |  | 547 |  |  | 609 |  |  | 545 |  |  | 622 |  |  | 568 |  |  | 546 |  |  | 543 |  |  | 553 |  |  | 588 |  |  | 562 |  |  | 614 |  |  | 561 |  |  | 619 |  |  | 512 |  |  | 602 |  |  | 567 |  |  | 565 |  |  | 568 |  |  | 555 |  |  | 539 |  |  | 560 |  |  | 569 |  |  | 558 |  |  | 579 |  |  | 535 |  |  | 553 |  |  | 649 |  |  | 593 |  |  | 586 |  |  | 525 |  |  | 527 |  |  | 557 |  |  | 562 |  |  | 569 |  |  | 586 |  |  | 597 |  |  | 566 |  |  | 534 |  |  | 603 |  |  | 569 |  |  | 562 |  |  | 587 |  |  | 534 |  |  | 569 |  |  | 530 |  |  | 563 |  |  | 583 |  |  | 566 |  |  | 603 |  |  | 576 |  |  | 588 |  |  | 516 |  |  | 518 |  |  | 534 |  |  | 580 |  |  | 624 |  |  | 578 |  |  | 638 |  |  | 572 |  |  | 584 |  |  | 559 |  |  | 550 |  |  | 600 |  |  | 614 |  |  | 561 |  |  | 600 |  |  | 552 |  |  | 517 |  |  | 598 |  |  | 570 |  |  | 564 |  |  | 573 |  |  | 579 |  |  | 603 |  |  | 556 |  |  | 565 |  |  | 578 |  |  | 539 |  |  | 585 |  |  | 526 |  |  | 569 |  |  | 606 |  |  | 562 |  |  | 550 |  |  | 623 |  |  | 588 |  |  | 545 |  |  | 555 |  |  | 567 |  |  | 585 |  |  | 610 |  |  | 590 |  |  | 585 |  |  | 536 |  |  | 574 |  |  | 565 |  |  | 482 |  |  | 542 |  |  | 513 |  |  | 587 |  |  | 602 |  |  | 513 |  |  | 564 |  |  | 558 |  |  | 542 |  |  | 575 |  |  | 554 |  |  | 611 |  |  | 472 |  |  | 542 |  |  | 518 |  |  | 613 |  |  | 581 |  |  | 561 |  |  | 562 |  |  | 557 |  |  | 558 |  |  | 571 |  |  | 494 |  |  | 553 |  |  | 561 |  |  | 554 |  |  | 509 |  |  | 562 |  |  | 533 |  |  | 626 |  |  | 590 |  |  | 586 |  |  | 586 |  |  | 566 |  |  | 555 |  |  | 567 |  |  | 547 |  |  | 616
20 |  | 652 |  |  | 612 |  |  | 571 |  |  | 643 |  |  | 605 |  |  | 615 |  |  | 584 |  |  | 606 |  |  | 629 |  |  | 623 |  |  | 607 |  |  | 686 |  |  | 594 |  |  | 626 |  |  | 608 |  |  | 611 |  |  | 604 |  |  | 605 |  |  | 621 |  |  | 529 |  |  | 615 |  |  | 630 |  |  | 616 |  |  | 622 |  |  | 569 |  |  | 627 |  |  | 639 |  |  | 592 |  |  | 645 |  |  | 623 |  |  | 586 |  |  | 585 |  |  | 702 |  |  | 572 |  |  | 567 |  |  | 572 |  |  | 571 |  |  | 577 |  |  | 600 |  |  | 658 |  |  | 535 |  |  | 592 |  |  | 613 |  |  | 656 |  |  | 638 |  |  | 633 |  |  | 594 |  |  | 619 |  |  | 563 |  |  | 568 |  |  | 644 |  |  | 641 |  |  | 570 |  |  | 616 |  |  | 553 |  |  | 604 |  |  | 632 |  |  | 651 |  |  | 617 |  |  | 632 |  |  | 689 |  |  | 607 |  |  | 597 |  |  | 608 |  |  | 541 |  |  | 556 |  |  | 638 |  |  | 644 |  |  | 673 |  |  | 594 |  |  | 605 |  |  | 575 |  |  | 584 |  |  | 553 |  |  | 630 |  |  | 559 |  |  | 603 |  |  | 561 |  |  | 594 |  |  | 628 |  |  | 648 |  |  | 627 |  |  | 571 |  |  | 612 |  |  | 595 |  |  | 611 |  |  | 545 |  |  | 607 |  |  | 534 |  |  | 630 |  |  | 592 |  |  | 590 |  |  | 702 |  |  | 599 |  |  | 583 |  |  | 599 |  |  | 617 |  |  | 594 |  |  | 592 |  |  | 566 |  |  | 598 |  |  | 548 |  |  | 578 |  |  | 608 |  |  | 619 |  |  | 577 |  |  | 569 |  |  | 604 |  |  | 603 |  |  | 611 |  |  | 603 |  |  | 570 |  |  | 612 |  |  | 597 |  |  | 591 |  |  | 617 |  |  | 622 |  |  | 559 |  |  | 567 |  |  | 655 |  |  | 665 |  |  | 561 |  |  | 660 |  |  | 575 |  |  | 542 |  |  | 608 |  |  | 625 |  |  | 611 |  |  | 560 |  |  | 653 |  |  | 618 |  |  | 666 |  |  | 522 |  |  | 543 |  |  | 572 |  |  | 585 |  |  | 612 |  |  | 611 |  |  | 632 |  |  | 593 |  |  | 545 |  |  | 587 |  |  | 597 |  |  | 608 |  |  | 604 |  |  | 574 |  |  | 532 |  |  | 581 |  |  | 632 |  |  | 550 |  |  | 545 |  |  | 618 |  |  | 584 |  |  | 625 |  |  | 608 |  |  | 636 |  |  | 539 |  |  | 625 |  |  | 565 |  |  | 687 |  |  | 652 |  |  | 573 |  |  | 590 |  |  | 547 |  |  | 561 |  |  | 546 |  |  | 565 |  |  | 589 |  |  | 607 |  |  | 655 |  |  | 584 |  |  | 586 |  |  | 589 |  |  | 622 |  |  | 607 |  |  | 580 |  |  | 549 |  |  | 630 |  |  | 652 |  |  | 559 |  |  | 628 |  |  | 665 |  |  | 630 |  |  | 560 |  |  | 569 |  |  | 658 |  |  | 590 |  |  | 576 |  |  | 608 |  |  | 584 |  |  | 571 |  |  | 617 |  |  | 653 |  |  | 591 |  |  | 550 |  |  | 596 |  |  | 555 |  |  | 580 |  |  | 615 |  |  | 584 |  |  | 600 |  |  | 607 |  |  | 561 |  |  | 584 |  |  | 660 |  |  | 621 |  |  | 561 |  |  | 616 |  |  | 630 |  |  | 628 |  |  | 663 |  |  | 561 |  |  | 582 |  |  | 634 |  |  | 592 |  |  | 541 |  |  | 631 |  |  | 598 |  |  | 586 |  |  | 647 |  |  | 555 |  |  | 616 |  |  | 628 |  |  | 567 |  |  | 548 |  |  | 593 |  |  | 640 |  |  | 612 |  |  | 611 |  |  | 567 |  |  | 587 |  |  | 558 |  |  | 633 |  |  | 606 |  |  | 603 |  |  | 589 |  |  | 548 |  |  | 561 |  |  | 568 |  |  | 639 |  |  | 631 |  |  | 637 |  |  | 585 |  |  | 643 |  |  | 630 |  |  | 533 |  |  | 651 |  |  | 663 |  |  | 626 |  |  | 587 |  |  | 551 |  |  | 627 |  |  | 622 |  |  | 640 |  |  | 643 |  |  | 540 |  |  | 583 |  |  | 608 |  |  | 615 |  |  | 599 |  |  | 634 |  |  | 588 |  |  | 585 |  |  | 624 |  |  | 615 |  |  | 616 |  |  | 619 |  |  | 579 |  |  | 601 |  |  | 598 |  |  | 630 |  |  | 654 |  |  | 638 |  |  | 632 |  |  | 650 |  |  | 575 |  |  | 542 |  |  | 617 |  |  | 558 |  |  | 649 |  |  | 551 |  |  | 611 |  |  | 581 |  |  | 555 |  |  | 647 |  |  | 599 |  |  | 642 |  |  | 616 |  |  | 637 |  |  | 589 |  |  | 558 |  |  | 612 |  |  | 603 |  |  | 572 |  |  | 645 |  |  | 633 |  |  | 649 |  |  | 626 |  |  | 667 |  |  | 613 |  |  | 588 |  |  | 621 |  |  | 595 |  |  | 603 |  |  | 577 |  |  | 586 |  |  | 674 |  |  | 580 |  |  | 597 |  |  | 623 |  |  | 678 |  |  | 578 |  |  | 552 |  |  | 631 |  |  | 606 |  |  | 563 |  |  | 602 |  |  | 605 |  |  | 607 |  |  | 599 |  |  | 579 |  |  | 655 |  |  | 618 |  |  | 550 |  |  | 598 |  |  | 589 |  |  | 602 |  |  | 614 |  |  | 566 |  |  | 667 |  |  | 578 |  |  | 671 |  |  | 673 |  |  | 628 |  |  | 636 |  |  | 562 |  |  | 633 |  |  | 674 |  |  | 652 |  |  | 595 |  |  | 594 |  |  | 590 |  |  | 575 |  |  | 601 |  |  | 573 |  |  | 574 |  |  | 572 |  |  | 586 |  |  | 682 |  |  | 609 |  |  | 569 |  |  | 629 |  |  | 630 |  |  | 611 |  |  | 561 |  |  | 573 |  |  | 598 |  |  | 586 |  |  | 633 |  |  | 606 |  |  | 579 |  |  | 562 |  |  | 580 |  |  | 630 |  |  | 551 |  |  | 606 |  |  | 642 |  |  | 631 |  |  | 649 |  |  | 631 |  |  | 573 |  |  | 534 |  |  | 587 |  |  | 663 |  |  | 562 |  |  | 560 |  |  | 561 |  |  | 606 |  |  | 547 |  |  | 601 |  |  | 587 |  |  | 638 |  |  | 600 |  |  | 649 |  |  | 575 |  |  | 620 |  |  | 597 |  |  | 602 |  |  | 638 |  |  | 576 |  |  | 547 |  |  | 660 |  |  | 592 |  |  | 585 |  |  | 596 |  |  | 593 |  |  | 528 |  |  | 620 |  |  | 621 |  |  | 559 |  |  | 673 |  |  | 609 |  |  | 606 |  |  | 552 |  |  | 608 |  |  | 546 |  |  | 581 |  |  | 683 |  |  | 627 |  |  | 600 |  |  | 627 |  |  | 583 |  |  | 556 |  |  | 592 |  |  | 641 |  |  | 640 |  |  | 618 |  |  | 551 |  |  | 681 |  |  | 636 |  |  | 598 |  |  | 620 |  |  | 560 |  |  | 596 |  |  | 539 |  |  | 661 |  |  | 574 |  |  | 635 |  |  | 620 |  |  | 567 |  |  | 549 |  |  | 657 |  |  | 614 |  |  | 591 |  |  | 583 |  |  | 574 |  |  | 624 |  |  | 563 |  |  | 592 |  |  | 619 |  |  | 587 |  |  | 601 |  |  | 599 |  |  | 622 |  |  | 569 |  |  | 619 |  |  | 688 |  |  | 639 |  |  | 621 |  |  | 644 |  |  | 580 |  |  | 591 |  |  | 603 |  |  | 593 |  |  | 671 |  |  | 565 |  |  | 595 |  |  | 573 |  |  | 600 |  |  | 615 |  |  | 547 |  |  | 669 |  |  | 635 |  |  | 641 |  |  | 668 |  |  | 606 |  |  | 547 |  |  | 652 |  |  | 620 |  |  | 592 |  |  | 642 |  |  | 571 |  |  | 587 |  |  | 592 |  |  | 609 |  |  | 627 |  |  | 577 |  |  | 623 |  |  | 542 |  |  | 626 |  |  | 550 |  |  | 585 |  |  | 617 |  |  | 595 |  |  | 626 |  |  | 584 |  |  | 574 |  |  | 575 |  |  | 594 |  |  | 608 |  |  | 625 |  |  | 588 |  |  | 576 |  |  | 583 |  |  | 639 |  |  | 635 |  |  | 572 |  |  | 595 |  |  | 608 |  |  | 647 |  |  | 610 |  |  | 593 |  |  | 628 |  |  | 648 |  |  | 647 |  |  | 576 |  |  | 587 |  |  | 538 |  |  | 622 |  |  | 553 |  |  | 591 |  |  | 609 |  |  | 680 |  |  | 661 |  |  | 538 |  |  | 627 |  |  | 608 |  |  | 680 |  |  | 588 |  |  | 557 |  |  | 595 |  |  | 642 |  |  | 660 |  |  | 627 |  |  | 600 |  |  | 532 |  |  | 622 |  |  | 592 |  |  | 694 |  |  | 560 |  |  | 597 |  |  | 618 |  |  | 570 |  |  | 625 |  |  | 634 |  |  | 591 |  |  | 608 |  |  | 621 |  |  | 621 |  |  | 579 |  |  | 540 |  |  | 630 |  |  | 634 |  |  | 619 |  |  | 610 |  |  | 587 |  |  | 563 |  |  | 636 |  |  | 600 |  |  | 568 |  |  | 580 |  |  | 613 |  |  | 549 |  |  | 572 |  |  | 537 |  |  | 600 |  |  | 634 |  |  | 600 |  |  | 602 |  |  | 579 |  |  | 620 |  |  | 601 |  |  | 569 |  |  | 652 |  |  | 618 |  |  | 605 |  |  | 671 |  |  | 595 |  |  | 622 |  |  | 632 |  |  | 583 |  |  | 548 |  |  | 548 |  |  | 597 |  |  | 599 |  |  | 590 |  |  | 607 |  |  | 571 |  |  | 577 |  |  | 527 |  |  | 635 |  |  | 615 |  |  | 608 |  |  | 584 |  |  | 650 |  |  | 558 |  |  | 572 |  |  | 612 |  |  | 586 |  |  | 658 |  |  | 611 |  |  | 664 |  |  | 576 |  |  | 654 |  |  | 580 |  |  | 574 |  |  | 585 |  |  | 656 |  |  | 564 |  |  | 578 |  |  | 569 |  |  | 580 |  |  | 679 |  |  | 573 |  |  | 600 |  |  | 651 |  |  | 601 |  |  | 593 |  |  | 541 |  |  | 619 |  |  | 604 |  |  | 583 |  |  | 599 |  |  | 588 |  |  | 602 |  |  | 552 |  |  | 620 |  |  | 649 |  |  | 543 |  |  | 574 |  |  | 606 |  |  | 605 |  |  | 643 |  |  | 530 |  |  | 645 |  |  | 649 |  |  | 583 |  |  | 594 |  |  | 603 |  |  | 576 |  |  | 534 |  |  | 668 |  |  | 614 |  |  | 550 |  |  | 704 |  |  | 634 |  |  | 599 |  |  | 572 |  |  | 625 |  |  | 617 |  |  | 576 |  |  | 607 |  |  | 581 |  |  | 599 |  |  | 615 |  |  | 624 |  |  | 623 |  |  | 623 |  |  | 590 |  |  | 640 |  |  | 672 |  |  | 503 |  |  | 578 |  |  | 578 |  |  | 577 |  |  | 596 |  |  | 579 |  |  | 622 |  |  | 637 |  |  | 659 |  |  | 612 |  |  | 579 |  |  | 662 |  |  | 614 |  |  | 611 |  |  | 592 |  |  | 591 |  |  | 602 |  |  | 652 |  |  | 587 |  |  | 628 |  |  | 594 |  |  | 614 |  |  | 622 |  |  | 634 |  |  | 561 |  |  | 616 |  |  | 641 |  |  | 571 |  |  | 671 |  |  | 589 |  |  | 608 |  |  | 580 |  |  | 677 |  |  | 566 |  |  | 605 |  |  | 570 |  |  | 642 |  |  | 612 |  |  | 612 |  |  | 533 |  |  | 554 |  |  | 647 |  |  | 587 |  |  | 628 |  |  | 592 |  |  | 657 |  |  | 618 |  |  | 598 |  |  | 584 |  |  | 594 |  |  | 557 |  |  | 567 |  |  | 620 |  |  | 579 |  |  | 629 |  |  | 619 |  |  | 538 |  |  | 618 |  |  | 572 |  |  | 643 |  |  | 614 |  |  | 609 |  |  | 601 |  |  | 584 |  |  | 491 |  |  | 684 |  |  | 582 |  |  | 592 |  |  | 646 |  |  | 662 |  |  | 541 |  |  | 642 |  |  | 532 |  |  | 611 |  |  | 642 |  |  | 583 |  |  | 593 |  |  | 577 |  |  | 619 |  |  | 612 |  |  | 641 |  |  | 597 |  |  | 598 |  |  | 643 |  |  | 580 |  |  | 615 |  |  | 669 |  |  | 626 |  |  | 619 |  |  | 642 |  |  | 603 |  |  | 631 |  |  | 563 |  |  | 612 |  |  | 593 |  |  | 572 |  |  | 598 |  |  | 580 |  |  | 578 |  |  | 625 |  |  | 556 |  |  | 514 |  |  | 622 |  |  | 494 |  |  | 598 |  |  | 631 |  |  | 583 |  |  | 597 |  |  | 628 |  |  | 610 |  |  | 617 |  |  | 555 |  |  | 551 |  |  | 506 |  |  | 546 |  |  | 567 |  |  | 622 |  |  | 601 |  |  | 556 |  |  | 562 |  |  | 496 |  |  | 640 |  |  | 658 |  |  | 661 |  |  | 627 |  |  | 565 |  |  | 598 |  |  | 569 |  |  | 567 |  |  | 616 |  |  | 573 |  |  | 682 |  |  | 662 |  |  | 593 |  |  | 622 |  |  | 603 |  |  | 598 |  |  | 565 |  |  | 635 |  |  | 561 |  |  | 603 |  |  | 560 |  |  | 577 |  |  | 572 |  |  | 553 |  |  | 566 |  |  | 608 |  |  | 645 |  |  | 617 |  |  | 593 |  |  | 548 |  |  | 617 |  |  | 640 |  |  | 645 |  |  | 555 |  |  | 592 |  |  | 610 |  |  | 557 |  |  | 634 |  |  | 594 |  |  | 633 |  |  | 542 |  |  | 609 |  |  | 564 |  |  | 592 |  |  | 624 |  |  | 587 |  |  | 632 |  |  | 625 |  |  | 595 |  |  | 585 |  |  | 572 |  |  | 573 |  |  | 604 |  |  | 637 |  |  | 565 |  |  | 631 |  |  | 587 |  |  | 578 |  |  | 555 |  |  | 602 |  |  | 601 |  |  | 601 |  |  | 626 |  |  | 590 |  |  | 593 |  |  | 573 |  |  | 605 |  |  | 604 |  |  | 599 |  |  | 592 |  |  | 655 |  |  | 663 |  |  | 595 |  |  | 560 |  |  | 586 |  |  | 605 |  |  | 560 |  |  | 520 |  |  | 537 |  |  | 626 |  |  | 537 |  |  | 602 |  |  | 587 |  |  | 629 |  |  | 618 |  |  | 591 |  |  | 573 |  |  | 631 |  |  | 567 |  |  | 587 |  |  | 543 |  |  | 642 |  |  | 629 |  |  | 632 |  |  | 586 |  |  | 656 |  |  | 571 |  |  | 669 |  |  | 594 |  |  | 585 |  |  | 590 |  |  | 582 |  |  | 609 |  |  | 583 |  |  | 635 |  |  | 585 |  |  | 648 |  |  | 538 |  |  | 631 |  |  | 591 |  |  | 594 |  |  | 607 |  |  | 594 |  |  | 560 |  |  | 607 |  |  | 608 |  |  | 597 |  |  | 626 |  |  | 574 |  |  | 577 |  |  | 696 |  |  | 632 |  |  | 612 |  |  | 564 |  |  | 556 |  |  | 572 |  |  | 601 |  |  | 616 |  |  | 612 |  |  | 612 |  |  | 581 |  |  | 581 |  |  | 632 |  |  | 608 |  |  | 577 |  |  | 626 |  |  | 560 |  |  | 595 |  |  | 569 |  |  | 587 |  |  | 598 |  |  | 595 |  |  | 642 |  |  | 605 |  |  | 617 |  |  | 563 |  |  | 557 |  |  | 563 |  |  | 601 |  |  | 671 |  |  | 607 |  |  | 664 |  |  | 611 |  |  | 613 |  |  | 598 |  |  | 574 |  |  | 615 |  |  | 653 |  |  | 608 |  |  | 615 |  |  | 567 |  |  | 546 |  |  | 627 |  |  | 617 |  |  | 588 |  |  | 594 |  |  | 594 |  |  | 624 |  |  | 595 |  |  | 589 |  |  | 617 |  |  | 565 |  |  | 624 |  |  | 547 |  |  | 593 |  |  | 621 |  |  | 609 |  |  | 579 |  |  | 670 |  |  | 635 |  |  | 569 |  |  | 602 |  |  | 596 |  |  | 606 |  |  | 639 |  |  | 637 |  |  | 614 |  |  | 565 |  |  | 613 |  |  | 604 |  |  | 506 |  |  | 589 |  |  | 560 |  |  | 611 |  |  | 626 |  |  | 537 |  |  | 593 |  |  | 587 |  |  | 566 |  |  | 604 |  |  | 593 |  |  | 626 |  |  | 501 |  |  | 568 |  |  | 539 |  |  | 628 |  |  | 610 |  |  | 587 |  |  | 601 |  |  | 578 |  |  | 573 |  |  | 586 |  |  | 533 |  |  | 592 |  |  | 587 |  |  | 593 |  |  | 538 |  |  | 586 |  |  | 562 |  |  | 650 |  |  | 616 |  |  | 625 |  |  | 612 |  |  | 592 |  |  | 602 |  |  | 606 |  |  | 571 |  |  | 642
21 |  | 691 |  |  | 651 |  |  | 618 |  |  | 672 |  |  | 652 |  |  | 641 |  |  | 608 |  |  | 653 |  |  | 676 |  |  | 638 |  |  | 654 |  |  | 715 |  |  | 641 |  |  | 665 |  |  | 647 |  |  | 632 |  |  | 619 |  |  | 644 |  |  | 647 |  |  | 544 |  |  | 636 |  |  | 656 |  |  | 655 |  |  | 661 |  |  | 584 |  |  | 656 |  |  | 678 |  |  | 639 |  |  | 684 |  |  | 649 |  |  | 625 |  |  | 624 |  |  | 723 |  |  | 611 |  |  | 593 |  |  | 598 |  |  | 618 |  |  | 598 |  |  | 647 |  |  | 682 |  |  | 561 |  |  | 621 |  |  | 660 |  |  | 677 |  |  | 677 |  |  | 680 |  |  | 633 |  |  | 658 |  |  | 587 |  |  | 594 |  |  | 673 |  |  | 662 |  |  | 596 |  |  | 655 |  |  | 574 |  |  | 633 |  |  | 647 |  |  | 690 |  |  | 646 |  |  | 671 |  |  | 710 |  |  | 654 |  |  | 626 |  |  | 629 |  |  | 562 |  |  | 577 |  |  | 685 |  |  | 691 |  |  | 688 |  |  | 641 |  |  | 631 |  |  | 622 |  |  | 610 |  |  | 579 |  |  | 656 |  |  | 588 |  |  | 650 |  |  | 608 |  |  | 633 |  |  | 649 |  |  | 677 |  |  | 653 |  |  | 586 |  |  | 627 |  |  | 619 |  |  | 635 |  |  | 574 |  |  | 631 |  |  | 581 |  |  | 645 |  |  | 631 |  |  | 619 |  |  | 741 |  |  | 646 |  |  | 607 |  |  | 623 |  |  | 656 |  |  | 623 |  |  | 616 |  |  | 613 |  |  | 627 |  |  | 587 |  |  | 617 |  |  | 647 |  |  | 634 |  |  | 616 |  |  | 598 |  |  | 625 |  |  | 642 |  |  | 632 |  |  | 624 |  |  | 599 |  |  | 627 |  |  | 626 |  |  | 617 |  |  | 643 |  |  | 661 |  |  | 606 |  |  | 591 |  |  | 681 |  |  | 694 |  |  | 582 |  |  | 675 |  |  | 596 |  |  | 557 |  |  | 655 |  |  | 654 |  |  | 658 |  |  | 584 |  |  | 692 |  |  | 642 |  |  | 692 |  |  | 561 |  |  | 558 |  |  | 596 |  |  | 624 |  |  | 627 |  |  | 650 |  |  | 653 |  |  | 622 |  |  | 566 |  |  | 634 |  |  | 612 |  |  | 632 |  |  | 619 |  |  | 603 |  |  | 558 |  |  | 602 |  |  | 679 |  |  | 579 |  |  | 566 |  |  | 657 |  |  | 608 |  |  | 664 |  |  | 632 |  |  | 665 |  |  | 554 |  |  | 664 |  |  | 604 |  |  | 726 |  |  | 678 |  |  | 612 |  |  | 619 |  |  | 576 |  |  | 590 |  |  | 593 |  |  | 604 |  |  | 610 |  |  | 628 |  |  | 676 |  |  | 599 |  |  | 610 |  |  | 628 |  |  | 669 |  |  | 646 |  |  | 619 |  |  | 573 |  |  | 669 |  |  | 691 |  |  | 588 |  |  | 649 |  |  | 691 |  |  | 651 |  |  | 599 |  |  | 584 |  |  | 682 |  |  | 629 |  |  | 623 |  |  | 637 |  |  | 605 |  |  | 610 |  |  | 646 |  |  | 692 |  |  | 612 |  |  | 576 |  |  | 611 |  |  | 570 |  |  | 601 |  |  | 654 |  |  | 610 |  |  | 629 |  |  | 646 |  |  | 608 |  |  | 610 |  |  | 689 |  |  | 650 |  |  | 585 |  |  | 655 |  |  | 651 |  |  | 652 |  |  | 702 |  |  | 582 |  |  | 603 |  |  | 658 |  |  | 621 |  |  | 562 |  |  | 660 |  |  | 613 |  |  | 633 |  |  | 673 |  |  | 581 |  |  | 655 |  |  | 675 |  |  | 606 |  |  | 563 |  |  | 632 |  |  | 655 |  |  | 641 |  |  | 635 |  |  | 596 |  |  | 602 |  |  | 584 |  |  | 654 |  |  | 632 |  |  | 642 |  |  | 628 |  |  | 574 |  |  | 587 |  |  | 597 |  |  | 686 |  |  | 646 |  |  | 658 |  |  | 600 |  |  | 658 |  |  | 656 |  |  | 580 |  |  | 690 |  |  | 689 |  |  | 650 |  |  | 626 |  |  | 598 |  |  | 653 |  |  | 646 |  |  | 661 |  |  | 667 |  |  | 569 |  |  | 598 |  |  | 632 |  |  | 644 |  |  | 646 |  |  | 663 |  |  | 609 |  |  | 624 |  |  | 663 |  |  | 630 |  |  | 655 |  |  | 645 |  |  | 594 |  |  | 616 |  |  | 637 |  |  | 659 |  |  | 701 |  |  | 677 |  |  | 658 |  |  | 689 |  |  | 622 |  |  | 563 |  |  | 632 |  |  | 584 |  |  | 696 |  |  | 566 |  |  | 650 |  |  | 620 |  |  | 570 |  |  | 671 |  |  | 638 |  |  | 671 |  |  | 645 |  |  | 676 |  |  | 636 |  |  | 573 |  |  | 659 |  |  | 642 |  |  | 619 |  |  | 674 |  |  | 662 |  |  | 664 |  |  | 655 |  |  | 696 |  |  | 660 |  |  | 627 |  |  | 660 |  |  | 624 |  |  | 650 |  |  | 598 |  |  | 633 |  |  | 689 |  |  | 606 |  |  | 618 |  |  | 644 |  |  | 725 |  |  | 599 |  |  | 578 |  |  | 670 |  |  | 627 |  |  | 602 |  |  | 649 |  |  | 626 |  |  | 622 |  |  | 614 |  |  | 603 |  |  | 679 |  |  | 657 |  |  | 576 |  |  | 622 |  |  | 604 |  |  | 628 |  |  | 661 |  |  | 590 |  |  | 696 |  |  | 607 |  |  | 695 |  |  | 697 |  |  | 657 |  |  | 675 |  |  | 591 |  |  | 680 |  |  | 695 |  |  | 699 |  |  | 616 |  |  | 641 |  |  | 619 |  |  | 599 |  |  | 627 |  |  | 588 |  |  | 598 |  |  | 601 |  |  | 610 |  |  | 708 |  |  | 633 |  |  | 598 |  |  | 658 |  |  | 651 |  |  | 635 |  |  | 600 |  |  | 594 |  |  | 627 |  |  | 625 |  |  | 648 |  |  | 645 |  |  | 605 |  |  | 591 |  |  | 606 |  |  | 669 |  |  | 590 |  |  | 653 |  |  | 657 |  |  | 670 |  |  | 696 |  |  | 652 |  |  | 588 |  |  | 558 |  |  | 602 |  |  | 684 |  |  | 577 |  |  | 575 |  |  | 600 |  |  | 630 |  |  | 568 |  |  | 622 |  |  | 626 |  |  | 685 |  |  | 621 |  |  | 670 |  |  | 614 |  |  | 644 |  |  | 636 |  |  | 626 |  |  | 677 |  |  | 615 |  |  | 573 |  |  | 699 |  |  | 613 |  |  | 624 |  |  | 635 |  |  | 632 |  |  | 543 |  |  | 635 |  |  | 647 |  |  | 580 |  |  | 712 |  |  | 633 |  |  | 630 |  |  | 591 |  |  | 623 |  |  | 585 |  |  | 596 |  |  | 712 |  |  | 666 |  |  | 615 |  |  | 674 |  |  | 630 |  |  | 603 |  |  | 639 |  |  | 667 |  |  | 666 |  |  | 642 |  |  | 577 |  |  | 707 |  |  | 657 |  |  | 624 |  |  | 644 |  |  | 575 |  |  | 635 |  |  | 578 |  |  | 687 |  |  | 613 |  |  | 656 |  |  | 667 |  |  | 606 |  |  | 564 |  |  | 683 |  |  | 653 |  |  | 630 |  |  | 609 |  |  | 589 |  |  | 663 |  |  | 589 |  |  | 631 |  |  | 666 |  |  | 626 |  |  | 622 |  |  | 625 |  |  | 651 |  |  | 595 |  |  | 640 |  |  | 712 |  |  | 654 |  |  | 650 |  |  | 665 |  |  | 604 |  |  | 612 |  |  | 624 |  |  | 632 |  |  | 710 |  |  | 594 |  |  | 624 |  |  | 620 |  |  | 621 |  |  | 654 |  |  | 576 |  |  | 708 |  |  | 674 |  |  | 667 |  |  | 683 |  |  | 635 |  |  | 573 |  |  | 681 |  |  | 659 |  |  | 621 |  |  | 681 |  |  | 610 |  |  | 634 |  |  | 631 |  |  | 648 |  |  | 666 |  |  | 592 |  |  | 644 |  |  | 563 |  |  | 647 |  |  | 589 |  |  | 624 |  |  | 656 |  |  | 616 |  |  | 665 |  |  | 631 |  |  | 595 |  |  | 614 |  |  | 609 |  |  | 632 |  |  | 646 |  |  | 609 |  |  | 623 |  |  | 622 |  |  | 665 |  |  | 659 |  |  | 619 |  |  | 621 |  |  | 637 |  |  | 686 |  |  | 625 |  |  | 614 |  |  | 654 |  |  | 677 |  |  | 671 |  |  | 623 |  |  | 613 |  |  | 577 |  |  | 643 |  |  | 582 |  |  | 606 |  |  | 633 |  |  | 706 |  |  | 690 |  |  | 553 |  |  | 648 |  |  | 647 |  |  | 719 |  |  | 603 |  |  | 581 |  |  | 634 |  |  | 663 |  |  | 699 |  |  | 651 |  |  | 639 |  |  | 553 |  |  | 637 |  |  | 631 |  |  | 715 |  |  | 599 |  |  | 618 |  |  | 642 |  |  | 609 |  |  | 640 |  |  | 660 |  |  | 606 |  |  | 647 |  |  | 647 |  |  | 645 |  |  | 603 |  |  | 564 |  |  | 677 |  |  | 663 |  |  | 658 |  |  | 636 |  |  | 608 |  |  | 589 |  |  | 675 |  |  | 647 |  |  | 597 |  |  | 627 |  |  | 628 |  |  | 596 |  |  | 611 |  |  | 561 |  |  | 639 |  |  | 673 |  |  | 626 |  |  | 641 |  |  | 626 |  |  | 659 |  |  | 640 |  |  | 608 |  |  | 681 |  |  | 644 |  |  | 634 |  |  | 710 |  |  | 634 |  |  | 669 |  |  | 671 |  |  | 604 |  |  | 574 |  |  | 563 |  |  | 626 |  |  | 623 |  |  | 616 |  |  | 628 |  |  | 600 |  |  | 601 |  |  | 566 |  |  | 682 |  |  | 636 |  |  | 629 |  |  | 623 |  |  | 665 |  |  | 579 |  |  | 587 |  |  | 659 |  |  | 615 |  |  | 705 |  |  | 658 |  |  | 688 |  |  | 591 |  |  | 701 |  |  | 595 |  |  | 598 |  |  | 632 |  |  | 695 |  |  | 579 |  |  | 604 |  |  | 608 |  |  | 601 |  |  | 718 |  |  | 602 |  |  | 626 |  |  | 680 |  |  | 640 |  |  | 619 |  |  | 565 |  |  | 648 |  |  | 643 |  |  | 609 |  |  | 628 |  |  | 612 |  |  | 641 |  |  | 591 |  |  | 646 |  |  | 678 |  |  | 569 |  |  | 598 |  |  | 621 |  |  | 631 |  |  | 672 |  |  | 545 |  |  | 671 |  |  | 664 |  |  | 604 |  |  | 620 |  |  | 624 |  |  | 615 |  |  | 581 |  |  | 683 |  |  | 638 |  |  | 576 |  |  | 730 |  |  | 673 |  |  | 614 |  |  | 611 |  |  | 654 |  |  | 664 |  |  | 615 |  |  | 631 |  |  | 610 |  |  | 623 |  |  | 639 |  |  | 645 |  |  | 644 |  |  | 647 |  |  | 629 |  |  | 679 |  |  | 693 |  |  | 550 |  |  | 617 |  |  | 607 |  |  | 601 |  |  | 635 |  |  | 603 |  |  | 651 |  |  | 661 |  |  | 680 |  |  | 627 |  |  | 618 |  |  | 686 |  |  | 643 |  |  | 658 |  |  | 631 |  |  | 630 |  |  | 631 |  |  | 667 |  |  | 608 |  |  | 675 |  |  | 620 |  |  | 653 |  |  | 637 |  |  | 673 |  |  | 600 |  |  | 642 |  |  | 662 |  |  | 597 |  |  | 710 |  |  | 604 |  |  | 623 |  |  | 606 |  |  | 701 |  |  | 592 |  |  | 644 |  |  | 594 |  |  | 689 |  |  | 636 |  |  | 659 |  |  | 562 |  |  | 583 |  |  | 686 |  |  | 626 |  |  | 667 |  |  | 607 |  |  | 672 |  |  | 657 |  |  | 613 |  |  | 631 |  |  | 609 |  |  | 572 |  |  | 596 |  |  | 641 |  |  | 608 |  |  | 676 |  |  | 643 |  |  | 567 |  |  | 642 |  |  | 601 |  |  | 682 |  |  | 643 |  |  | 635 |  |  | 627 |  |  | 623 |  |  | 506 |  |  | 731 |  |  | 606 |  |  | 618 |  |  | 661 |  |  | 688 |  |  | 562 |  |  | 666 |  |  | 556 |  |  | 640 |  |  | 666 |  |  | 630 |  |  | 619 |  |  | 606 |  |  | 666 |  |  | 627 |  |  | 662 |  |  | 612 |  |  | 645 |  |  | 682 |  |  | 619 |  |  | 630 |  |  | 690 |  |  | 673 |  |  | 658 |  |  | 668 |  |  | 629 |  |  | 660 |  |  | 602 |  |  | 633 |  |  | 614 |  |  | 611 |  |  | 624 |  |  | 609 |  |  | 617 |  |  | 664 |  |  | 582 |  |  | 529 |  |  | 646 |  |  | 523 |  |  | 624 |  |  | 670 |  |  | 607 |  |  | 623 |  |  | 667 |  |  | 649 |  |  | 656 |  |  | 602 |  |  | 575 |  |  | 553 |  |  | 585 |  |  | 582 |  |  | 646 |  |  | 640 |  |  | 585 |  |  | 583 |  |  | 535 |  |  | 666 |  |  | 705 |  |  | 676 |  |  | 656 |  |  | 604 |  |  | 619 |  |  | 608 |  |  | 588 |  |  | 631 |  |  | 612 |  |  | 703 |  |  | 701 |  |  | 608 |  |  | 661 |  |  | 650 |  |  | 637 |  |  | 591 |  |  | 664 |  |  | 608 |  |  | 642 |  |  | 589 |  |  | 592 |  |  | 611 |  |  | 592 |  |  | 613 |  |  | 632 |  |  | 674 |  |  | 664 |  |  | 632 |  |  | 587 |  |  | 638 |  |  | 655 |  |  | 671 |  |  | 579 |  |  | 607 |  |  | 634 |  |  | 578 |  |  | 673 |  |  | 618 |  |  | 654 |  |  | 581 |  |  | 638 |  |  | 593 |  |  | 631 |  |  | 650 |  |  | 626 |  |  | 661 |  |  | 640 |  |  | 634 |  |  | 611 |  |  | 619 |  |  | 602 |  |  | 633 |  |  | 684 |  |  | 591 |  |  | 670 |  |  | 611 |  |  | 593 |  |  | 581 |  |  | 617 |  |  | 622 |  |  | 616 |  |  | 673 |  |  | 611 |  |  | 632 |  |  | 612 |  |  | 629 |  |  | 628 |  |  | 646 |  |  | 631 |  |  | 694 |  |  | 687 |  |  | 610 |  |  | 581 |  |  | 625 |  |  | 644 |  |  | 586 |  |  | 541 |  |  | 576 |  |  | 647 |  |  | 584 |  |  | 623 |  |  | 608 |  |  | 653 |  |  | 657 |  |  | 620 |  |  | 588 |  |  | 670 |  |  | 606 |  |  | 613 |  |  | 567 |  |  | 681 |  |  | 655 |  |  | 647 |  |  | 633 |  |  | 703 |  |  | 592 |  |  | 716 |  |  | 620 |  |  | 624 |  |  | 629 |  |  | 608 |  |  | 648 |  |  | 630 |  |  | 674 |  |  | 624 |  |  | 687 |  |  | 585 |  |  | 655 |  |  | 617 |  |  | 618 |  |  | 633 |  |  | 633 |  |  | 575 |  |  | 628 |  |  | 637 |  |  | 636 |  |  | 665 |  |  | 621 |  |  | 592 |  |  | 743 |  |  | 656 |  |  | 633 |  |  | 611 |  |  | 577 |  |  | 611 |  |  | 627 |  |  | 631 |  |  | 651 |  |  | 638 |  |  | 620 |  |  | 602 |  |  | 658 |  |  | 637 |  |  | 606 |  |  | 647 |  |  | 589 |  |  | 610 |  |  | 608 |  |  | 608 |  |  | 637 |  |  | 619 |  |  | 689 |  |  | 644 |  |  | 656 |  |  | 592 |  |  | 578 |  |  | 610 |  |  | 616 |  |  | 710 |  |  | 622 |  |  | 703 |  |  | 650 |  |  | 642 |  |  | 622 |  |  | 603 |  |  | 639 |  |  | 679 |  |  | 637 |  |  | 654 |  |  | 582 |  |  | 567 |  |  | 674 |  |  | 641 |  |  | 614 |  |  | 618 |  |  | 633 |  |  | 645 |  |  | 621 |  |  | 628 |  |  | 632 |  |  | 594 |  |  | 650 |  |  | 568 |  |  | 632 |  |  | 660 |  |  | 648 |  |  | 608 |  |  | 691 |  |  | 659 |  |  | 608 |  |  | 623 |  |  | 643 |  |  | 632 |  |  | 686 |  |  | 676 |  |  | 635 |  |  | 589 |  |  | 652 |  |  | 619 |  |  | 545 |  |  | 618 |  |  | 599 |  |  | 626 |  |  | 655 |  |  | 566 |  |  | 632 |  |  | 611 |  |  | 590 |  |  | 630 |  |  | 608 |  |  | 647 |  |  | 540 |  |  | 589 |  |  | 586 |  |  | 649 |  |  | 657 |  |  | 602 |  |  | 630 |  |  | 617 |  |  | 612 |  |  | 601 |  |  | 572 |  |  | 616 |  |  | 634 |  |  | 632 |  |  | 567 |  |  | 615 |  |  | 577 |  |  | 665 |  |  | 642 |  |  | 664 |  |  | 636 |  |  | 639 |  |  | 623 |  |  | 635 |  |  | 618 |  |  | 657
22 |  | 730 |  |  | 677 |  |  | 665 |  |  | 696 |  |  | 699 |  |  | 665 |  |  | 623 |  |  | 677 |  |  | 700 |  |  | 667 |  |  | 693 |  |  | 741 |  |  | 680 |  |  | 691 |  |  | 686 |  |  | 671 |  |  | 648 |  |  | 670 |  |  | 686 |  |  | 583 |  |  | 662 |  |  | 703 |  |  | 684 |  |  | 682 |  |  | 610 |  |  | 677 |  |  | 704 |  |  | 660 |  |  | 708 |  |  | 670 |  |  | 649 |  |  | 663 |  |  | 752 |  |  | 637 |  |  | 622 |  |  | 637 |  |  | 639 |  |  | 637 |  |  | 673 |  |  | 703 |  |  | 576 |  |  | 660 |  |  | 699 |  |  | 703 |  |  | 703 |  |  | 704 |  |  | 657 |  |  | 679 |  |  | 602 |  |  | 609 |  |  | 702 |  |  | 701 |  |  | 611 |  |  | 694 |  |  | 613 |  |  | 648 |  |  | 694 |  |  | 714 |  |  | 672 |  |  | 686 |  |  | 739 |  |  | 693 |  |  | 650 |  |  | 676 |  |  | 586 |  |  | 598 |  |  | 711 |  |  | 717 |  |  | 709 |  |  | 667 |  |  | 646 |  |  | 661 |  |  | 649 |  |  | 626 |  |  | 682 |  |  | 627 |  |  | 676 |  |  | 655 |  |  | 680 |  |  | 688 |  |  | 692 |  |  | 677 |  |  | 625 |  |  | 651 |  |  | 666 |  |  | 656 |  |  | 613 |  |  | 652 |  |  | 610 |  |  | 666 |  |  | 678 |  |  | 658 |  |  | 767 |  |  | 685 |  |  | 654 |  |  | 662 |  |  | 685 |  |  | 644 |  |  | 642 |  |  | 639 |  |  | 674 |  |  | 616 |  |  | 656 |  |  | 668 |  |  | 663 |  |  | 637 |  |  | 645 |  |  | 649 |  |  | 681 |  |  | 671 |  |  | 650 |  |  | 638 |  |  | 666 |  |  | 665 |  |  | 656 |  |  | 667 |  |  | 676 |  |  | 621 |  |  | 617 |  |  | 702 |  |  | 733 |  |  | 597 |  |  | 701 |  |  | 622 |  |  | 596 |  |  | 670 |  |  | 678 |  |  | 679 |  |  | 623 |  |  | 716 |  |  | 657 |  |  | 739 |  |  | 587 |  |  | 597 |  |  | 622 |  |  | 645 |  |  | 674 |  |  | 697 |  |  | 668 |  |  | 661 |  |  | 613 |  |  | 673 |  |  | 651 |  |  | 647 |  |  | 640 |  |  | 629 |  |  | 579 |  |  | 626 |  |  | 726 |  |  | 618 |  |  | 587 |  |  | 704 |  |  | 623 |  |  | 690 |  |  | 671 |  |  | 680 |  |  | 593 |  |  | 693 |  |  | 633 |  |  | 765 |  |  | 693 |  |  | 627 |  |  | 658 |  |  | 597 |  |  | 605 |  |  | 617 |  |  | 643 |  |  | 625 |  |  | 667 |  |  | 691 |  |  | 614 |  |  | 634 |  |  | 649 |  |  | 684 |  |  | 672 |  |  | 645 |  |  | 612 |  |  | 693 |  |  | 720 |  |  | 617 |  |  | 678 |  |  | 720 |  |  | 698 |  |  | 628 |  |  | 623 |  |  | 729 |  |  | 655 |  |  | 662 |  |  | 666 |  |  | 629 |  |  | 634 |  |  | 675 |  |  | 731 |  |  | 651 |  |  | 615 |  |  | 637 |  |  | 617 |  |  | 640 |  |  | 683 |  |  | 636 |  |  | 676 |  |  | 685 |  |  | 655 |  |  | 636 |  |  | 715 |  |  | 676 |  |  | 606 |  |  | 676 |  |  | 690 |  |  | 691 |  |  | 723 |  |  | 603 |  |  | 627 |  |  | 687 |  |  | 668 |  |  | 577 |  |  | 684 |  |  | 642 |  |  | 648 |  |  | 712 |  |  | 628 |  |  | 694 |  |  | 704 |  |  | 653 |  |  | 587 |  |  | 671 |  |  | 702 |  |  | 656 |  |  | 664 |  |  | 643 |  |  | 626 |  |  | 631 |  |  | 680 |  |  | 647 |  |  | 681 |  |  | 667 |  |  | 600 |  |  | 626 |  |  | 621 |  |  | 715 |  |  | 685 |  |  | 697 |  |  | 624 |  |  | 697 |  |  | 682 |  |  | 595 |  |  | 705 |  |  | 713 |  |  | 679 |  |  | 652 |  |  | 624 |  |  | 692 |  |  | 670 |  |  | 700 |  |  | 706 |  |  | 584 |  |  | 624 |  |  | 671 |  |  | 668 |  |  | 675 |  |  | 702 |  |  | 648 |  |  | 639 |  |  | 702 |  |  | 651 |  |  | 684 |  |  | 674 |  |  | 633 |  |  | 642 |  |  | 676 |  |  | 698 |  |  | 748 |  |  | 698 |  |  | 673 |  |  | 704 |  |  | 651 |  |  | 602 |  |  | 671 |  |  | 599 |  |  | 720 |  |  | 605 |  |  | 676 |  |  | 659 |  |  | 599 |  |  | 692 |  |  | 662 |  |  | 710 |  |  | 660 |  |  | 697 |  |  | 651 |  |  | 612 |  |  | 698 |  |  | 681 |  |  | 666 |  |  | 713 |  |  | 688 |  |  | 703 |  |  | 676 |  |  | 725 |  |  | 699 |  |  | 642 |  |  | 689 |  |  | 663 |  |  | 689 |  |  | 637 |  |  | 657 |  |  | 728 |  |  | 635 |  |  | 644 |  |  | 670 |  |  | 764 |  |  | 614 |  |  | 604 |  |  | 709 |  |  | 653 |  |  | 641 |  |  | 678 |  |  | 652 |  |  | 637 |  |  | 640 |  |  | 627 |  |  | 718 |  |  | 672 |  |  | 623 |  |  | 661 |  |  | 630 |  |  | 649 |  |  | 690 |  |  | 611 |  |  | 743 |  |  | 631 |  |  | 716 |  |  | 723 |  |  | 696 |  |  | 722 |  |  | 617 |  |  | 719 |  |  | 716 |  |  | 738 |  |  | 637 |  |  | 656 |  |  | 658 |  |  | 638 |  |  | 656 |  |  | 627 |  |  | 637 |  |  | 630 |  |  | 649 |  |  | 747 |  |  | 680 |  |  | 619 |  |  | 687 |  |  | 675 |  |  | 659 |  |  | 624 |  |  | 618 |  |  | 666 |  |  | 654 |  |  | 687 |  |  | 666 |  |  | 644 |  |  | 630 |  |  | 645 |  |  | 716 |  |  | 629 |  |  | 668 |  |  | 683 |  |  | 694 |  |  | 717 |  |  | 691 |  |  | 627 |  |  | 597 |  |  | 641 |  |  | 699 |  |  | 601 |  |  | 590 |  |  | 647 |  |  | 659 |  |  | 594 |  |  | 661 |  |  | 665 |  |  | 732 |  |  | 668 |  |  | 696 |  |  | 635 |  |  | 665 |  |  | 660 |  |  | 673 |  |  | 706 |  |  | 636 |  |  | 612 |  |  | 728 |  |  | 639 |  |  | 671 |  |  | 674 |  |  | 671 |  |  | 582 |  |  | 659 |  |  | 662 |  |  | 619 |  |  | 741 |  |  | 662 |  |  | 651 |  |  | 617 |  |  | 638 |  |  | 600 |  |  | 620 |  |  | 741 |  |  | 705 |  |  | 636 |  |  | 695 |  |  | 651 |  |  | 624 |  |  | 678 |  |  | 682 |  |  | 705 |  |  | 681 |  |  | 601 |  |  | 722 |  |  | 686 |  |  | 663 |  |  | 683 |  |  | 622 |  |  | 661 |  |  | 599 |  |  | 713 |  |  | 652 |  |  | 695 |  |  | 696 |  |  | 645 |  |  | 588 |  |  | 722 |  |  | 682 |  |  | 669 |  |  | 633 |  |  | 613 |  |  | 702 |  |  | 610 |  |  | 660 |  |  | 690 |  |  | 673 |  |  | 643 |  |  | 646 |  |  | 698 |  |  | 619 |  |  | 661 |  |  | 759 |  |  | 675 |  |  | 689 |  |  | 691 |  |  | 625 |  |  | 641 |  |  | 663 |  |  | 647 |  |  | 736 |  |  | 618 |  |  | 653 |  |  | 649 |  |  | 650 |  |  | 693 |  |  | 623 |  |  | 747 |  |  | 721 |  |  | 706 |  |  | 704 |  |  | 661 |  |  | 620 |  |  | 702 |  |  | 685 |  |  | 660 |  |  | 696 |  |  | 634 |  |  | 649 |  |  | 655 |  |  | 677 |  |  | 705 |  |  | 639 |  |  | 659 |  |  | 610 |  |  | 676 |  |  | 628 |  |  | 663 |  |  | 671 |  |  | 640 |  |  | 694 |  |  | 655 |  |  | 642 |  |  | 653 |  |  | 638 |  |  | 653 |  |  | 693 |  |  | 648 |  |  | 647 |  |  | 651 |  |  | 680 |  |  | 683 |  |  | 658 |  |  | 645 |  |  | 676 |  |  | 733 |  |  | 664 |  |  | 653 |  |  | 693 |  |  | 716 |  |  | 710 |  |  | 644 |  |  | 634 |  |  | 606 |  |  | 682 |  |  | 621 |  |  | 635 |  |  | 657 |  |  | 745 |  |  | 714 |  |  | 568 |  |  | 669 |  |  | 676 |  |  | 740 |  |  | 642 |  |  | 628 |  |  | 673 |  |  | 692 |  |  | 725 |  |  | 690 |  |  | 665 |  |  | 592 |  |  | 676 |  |  | 660 |  |  | 736 |  |  | 646 |  |  | 644 |  |  | 668 |  |  | 638 |  |  | 666 |  |  | 681 |  |  | 627 |  |  | 694 |  |  | 694 |  |  | 671 |  |  | 650 |  |  | 603 |  |  | 701 |  |  | 710 |  |  | 679 |  |  | 665 |  |  | 647 |  |  | 636 |  |  | 714 |  |  | 676 |  |  | 623 |  |  | 642 |  |  | 667 |  |  | 622 |  |  | 626 |  |  | 608 |  |  | 663 |  |  | 702 |  |  | 652 |  |  | 662 |  |  | 641 |  |  | 680 |  |  | 679 |  |  | 634 |  |  | 710 |  |  | 691 |  |  | 673 |  |  | 749 |  |  | 663 |  |  | 698 |  |  | 710 |  |  | 625 |  |  | 613 |  |  | 584 |  |  | 650 |  |  | 662 |  |  | 663 |  |  | 667 |  |  | 629 |  |  | 616 |  |  | 581 |  |  | 706 |  |  | 662 |  |  | 658 |  |  | 638 |  |  | 689 |  |  | 603 |  |  | 611 |  |  | 680 |  |  | 644 |  |  | 720 |  |  | 682 |  |  | 709 |  |  | 612 |  |  | 730 |  |  | 634 |  |  | 645 |  |  | 653 |  |  | 734 |  |  | 594 |  |  | 643 |  |  | 647 |  |  | 630 |  |  | 733 |  |  | 628 |  |  | 673 |  |  | 719 |  |  | 679 |  |  | 645 |  |  | 589 |  |  | 695 |  |  | 669 |  |  | 633 |  |  | 654 |  |  | 641 |  |  | 680 |  |  | 630 |  |  | 693 |  |  | 717 |  |  | 593 |  |  | 637 |  |  | 642 |  |  | 657 |  |  | 711 |  |  | 569 |  |  | 718 |  |  | 703 |  |  | 651 |  |  | 659 |  |  | 648 |  |  | 654 |  |  | 628 |  |  | 707 |  |  | 659 |  |  | 600 |  |  | 769 |  |  | 702 |  |  | 640 |  |  | 635 |  |  | 693 |  |  | 685 |  |  | 654 |  |  | 657 |  |  | 631 |  |  | 670 |  |  | 668 |  |  | 692 |  |  | 691 |  |  | 686 |  |  | 668 |  |  | 718 |  |  | 717 |  |  | 571 |  |  | 656 |  |  | 628 |  |  | 648 |  |  | 674 |  |  | 627 |  |  | 690 |  |  | 682 |  |  | 695 |  |  | 656 |  |  | 665 |  |  | 707 |  |  | 690 |  |  | 687 |  |  | 660 |  |  | 677 |  |  | 660 |  |  | 691 |  |  | 623 |  |  | 704 |  |  | 649 |  |  | 677 |  |  | 676 |  |  | 699 |  |  | 626 |  |  | 663 |  |  | 688 |  |  | 621 |  |  | 731 |  |  | 643 |  |  | 638 |  |  | 630 |  |  | 740 |  |  | 618 |  |  | 665 |  |  | 620 |  |  | 710 |  |  | 657 |  |  | 698 |  |  | 588 |  |  | 609 |  |  | 701 |  |  | 673 |  |  | 688 |  |  | 628 |  |  | 719 |  |  | 696 |  |  | 628 |  |  | 678 |  |  | 648 |  |  | 593 |  |  | 625 |  |  | 670 |  |  | 637 |  |  | 700 |  |  | 667 |  |  | 606 |  |  | 671 |  |  | 616 |  |  | 703 |  |  | 682 |  |  | 656 |  |  | 666 |  |  | 647 |  |  | 532 |  |  | 746 |  |  | 653 |  |  | 665 |  |  | 700 |  |  | 703 |  |  | 591 |  |  | 681 |  |  | 577 |  |  | 679 |  |  | 681 |  |  | 669 |  |  | 658 |  |  | 632 |  |  | 705 |  |  | 648 |  |  | 691 |  |  | 627 |  |  | 684 |  |  | 721 |  |  | 645 |  |  | 651 |  |  | 711 |  |  | 694 |  |  | 673 |  |  | 694 |  |  | 644 |  |  | 689 |  |  | 617 |  |  | 657 |  |  | 640 |  |  | 650 |  |  | 645 |  |  | 656 |  |  | 632 |  |  | 688 |  |  | 621 |  |  | 553 |  |  | 693 |  |  | 562 |  |  | 648 |  |  | 694 |  |  | 636 |  |  | 644 |  |  | 691 |  |  | 696 |  |  | 680 |  |  | 626 |  |  | 614 |  |  | 568 |  |  | 632 |  |  | 621 |  |  | 670 |  |  | 679 |  |  | 611 |  |  | 622 |  |  | 550 |  |  | 681 |  |  | 744 |  |  | 700 |  |  | 685 |  |  | 630 |  |  | 648 |  |  | 634 |  |  | 603 |  |  | 670 |  |  | 633 |  |  | 732 |  |  | 748 |  |  | 637 |  |  | 708 |  |  | 665 |  |  | 676 |  |  | 620 |  |  | 693 |  |  | 634 |  |  | 681 |  |  | 618 |  |  | 639 |  |  | 650 |  |  | 639 |  |  | 634 |  |  | 658 |  |  | 700 |  |  | 703 |  |  | 679 |  |  | 611 |  |  | 685 |  |  | 681 |  |  | 686 |  |  | 605 |  |  | 622 |  |  | 681 |  |  | 599 |  |  | 697 |  |  | 657 |  |  | 693 |  |  | 628 |  |  | 677 |  |  | 614 |  |  | 670 |  |  | 674 |  |  | 655 |  |  | 685 |  |  | 679 |  |  | 655 |  |  | 626 |  |  | 634 |  |  | 623 |  |  | 654 |  |  | 723 |  |  | 630 |  |  | 699 |  |  | 635 |  |  | 622 |  |  | 610 |  |  | 664 |  |  | 646 |  |  | 655 |  |  | 699 |  |  | 626 |  |  | 658 |  |  | 641 |  |  | 668 |  |  | 657 |  |  | 672 |  |  | 655 |  |  | 718 |  |  | 726 |  |  | 631 |  |  | 596 |  |  | 640 |  |  | 673 |  |  | 612 |  |  | 556 |  |  | 615 |  |  | 676 |  |  | 623 |  |  | 638 |  |  | 647 |  |  | 679 |  |  | 704 |  |  | 644 |  |  | 635 |  |  | 699 |  |  | 653 |  |  | 639 |  |  | 606 |  |  | 720 |  |  | 702 |  |  | 686 |  |  | 648 |  |  | 729 |  |  | 621 |  |  | 731 |  |  | 659 |  |  | 650 |  |  | 668 |  |  | 634 |  |  | 663 |  |  | 659 |  |  | 695 |  |  | 648 |  |  | 734 |  |  | 632 |  |  | 679 |  |  | 646 |  |  | 642 |  |  | 654 |  |  | 657 |  |  | 604 |  |  | 652 |  |  | 684 |  |  | 660 |  |  | 694 |  |  | 668 |  |  | 613 |  |  | 782 |  |  | 695 |  |  | 680 |  |  | 658 |  |  | 616 |  |  | 640 |  |  | 642 |  |  | 646 |  |  | 690 |  |  | 662 |  |  | 635 |  |  | 628 |  |  | 697 |  |  | 676 |  |  | 632 |  |  | 686 |  |  | 628 |  |  | 649 |  |  | 637 |  |  | 647 |  |  | 684 |  |  | 666 |  |  | 715 |  |  | 683 |  |  | 703 |  |  | 616 |  |  | 617 |  |  | 631 |  |  | 655 |  |  | 736 |  |  | 651 |  |  | 718 |  |  | 679 |  |  | 681 |  |  | 669 |  |  | 629 |  |  | 654 |  |  | 703 |  |  | 666 |  |  | 678 |  |  | 608 |  |  | 591 |  |  | 698 |  |  | 662 |  |  | 653 |  |  | 665 |  |  | 680 |  |  | 666 |  |  | 647 |  |  | 654 |  |  | 661 |  |  | 609 |  |  | 671 |  |  | 594 |  |  | 671 |  |  | 684 |  |  | 695 |  |  | 623 |  |  | 730 |  |  | 688 |  |  | 647 |  |  | 647 |  |  | 682 |  |  | 671 |  |  | 725 |  |  | 715 |  |  | 664 |  |  | 613 |  |  | 681 |  |  | 640 |  |  | 571 |  |  | 647 |  |  | 625 |  |  | 655 |  |  | 670 |  |  | 605 |  |  | 658 |  |  | 635 |  |  | 605 |  |  | 656 |  |  | 647 |  |  | 662 |  |  | 561 |  |  | 636 |  |  | 610 |  |  | 664 |  |  | 683 |  |  | 628 |  |  | 651 |  |  | 643 |  |  | 638 |  |  | 640 |  |  | 611 |  |  | 631 |  |  | 681 |  |  | 656 |  |  | 582 |  |  | 636 |  |  | 592 |  |  | 689 |  |  | 681 |  |  | 711 |  |  | 675 |  |  | 660 |  |  | 638 |  |  | 674 |  |  | 647 |  |  | 696
23 |  | 756 |  |  | 692 |  |  | 680 |  |  | 725 |  |  | 714 |  |  | 704 |  |  | 662 |  |  | 706 |  |  | 726 |  |  | 696 |  |  | 717 |  |  | 762 |  |  | 706 |  |  | 730 |  |  | 715 |  |  | 692 |  |  | 663 |  |  | 699 |  |  | 725 |  |  | 604 |  |  | 701 |  |  | 742 |  |  | 731 |  |  | 729 |  |  | 634 |  |  | 701 |  |  | 730 |  |  | 684 |  |  | 747 |  |  | 699 |  |  | 664 |  |  | 710 |  |  | 791 |  |  | 676 |  |  | 651 |  |  | 676 |  |  | 678 |  |  | 652 |  |  | 702 |  |  | 750 |  |  | 623 |  |  | 681 |  |  | 728 |  |  | 724 |  |  | 742 |  |  | 733 |  |  | 704 |  |  | 705 |  |  | 641 |  |  | 633 |  |  | 726 |  |  | 722 |  |  | 626 |  |  | 741 |  |  | 642 |  |  | 663 |  |  | 709 |  |  | 743 |  |  | 693 |  |  | 712 |  |  | 768 |  |  | 722 |  |  | 671 |  |  | 691 |  |  | 612 |  |  | 624 |  |  | 740 |  |  | 743 |  |  | 724 |  |  | 696 |  |  | 693 |  |  | 685 |  |  | 664 |  |  | 673 |  |  | 721 |  |  | 651 |  |  | 700 |  |  | 702 |  |  | 719 |  |  | 703 |  |  | 713 |  |  | 716 |  |  | 664 |  |  | 690 |  |  | 713 |  |  | 671 |  |  | 642 |  |  | 691 |  |  | 649 |  |  | 690 |  |  | 699 |  |  | 697 |  |  | 806 |  |  | 709 |  |  | 693 |  |  | 677 |  |  | 714 |  |  | 683 |  |  | 671 |  |  | 663 |  |  | 698 |  |  | 631 |  |  | 680 |  |  | 683 |  |  | 689 |  |  | 666 |  |  | 671 |  |  | 664 |  |  | 720 |  |  | 695 |  |  | 676 |  |  | 667 |  |  | 705 |  |  | 691 |  |  | 682 |  |  | 682 |  |  | 715 |  |  | 660 |  |  | 656 |  |  | 731 |  |  | 754 |  |  | 621 |  |  | 730 |  |  | 637 |  |  | 622 |  |  | 709 |  |  | 707 |  |  | 703 |  |  | 662 |  |  | 737 |  |  | 678 |  |  | 763 |  |  | 611 |  |  | 626 |  |  | 648 |  |  | 684 |  |  | 700 |  |  | 726 |  |  | 715 |  |  | 687 |  |  | 637 |  |  | 694 |  |  | 672 |  |  | 662 |  |  | 661 |  |  | 655 |  |  | 618 |  |  | 665 |  |  | 750 |  |  | 647 |  |  | 613 |  |  | 719 |  |  | 662 |  |  | 719 |  |  | 710 |  |  | 704 |  |  | 614 |  |  | 714 |  |  | 648 |  |  | 780 |  |  | 722 |  |  | 653 |  |  | 705 |  |  | 636 |  |  | 652 |  |  | 641 |  |  | 669 |  |  | 640 |  |  | 688 |  |  | 712 |  |  | 653 |  |  | 658 |  |  | 688 |  |  | 713 |  |  | 693 |  |  | 684 |  |  | 636 |  |  | 717 |  |  | 746 |  |  | 646 |  |  | 725 |  |  | 759 |  |  | 713 |  |  | 643 |  |  | 662 |  |  | 768 |  |  | 684 |  |  | 677 |  |  | 705 |  |  | 650 |  |  | 660 |  |  | 714 |  |  | 752 |  |  | 672 |  |  | 654 |  |  | 652 |  |  | 641 |  |  | 687 |  |  | 730 |  |  | 683 |  |  | 691 |  |  | 709 |  |  | 676 |  |  | 675 |  |  | 762 |  |  | 715 |  |  | 653 |  |  | 705 |  |  | 719 |  |  | 720 |  |  | 749 |  |  | 642 |  |  | 674 |  |  | 708 |  |  | 697 |  |  | 603 |  |  | 723 |  |  | 668 |  |  | 687 |  |  | 751 |  |  | 654 |  |  | 723 |  |  | 728 |  |  | 668 |  |  | 616 |  |  | 710 |  |  | 749 |  |  | 695 |  |  | 690 |  |  | 682 |  |  | 673 |  |  | 646 |  |  | 704 |  |  | 676 |  |  | 707 |  |  | 706 |  |  | 621 |  |  | 665 |  |  | 645 |  |  | 762 |  |  | 706 |  |  | 726 |  |  | 639 |  |  | 726 |  |  | 721 |  |  | 619 |  |  | 729 |  |  | 752 |  |  | 705 |  |  | 681 |  |  | 645 |  |  | 731 |  |  | 717 |  |  | 721 |  |  | 745 |  |  | 610 |  |  | 645 |  |  | 710 |  |  | 689 |  |  | 696 |  |  | 741 |  |  | 674 |  |  | 678 |  |  | 723 |  |  | 672 |  |  | 710 |  |  | 698 |  |  | 662 |  |  | 666 |  |  | 700 |  |  | 745 |  |  | 777 |  |  | 745 |  |  | 697 |  |  | 743 |  |  | 690 |  |  | 631 |  |  | 692 |  |  | 625 |  |  | 741 |  |  | 652 |  |  | 702 |  |  | 706 |  |  | 623 |  |  | 718 |  |  | 701 |  |  | 731 |  |  | 686 |  |  | 726 |  |  | 675 |  |  | 627 |  |  | 745 |  |  | 720 |  |  | 713 |  |  | 728 |  |  | 709 |  |  | 742 |  |  | 715 |  |  | 764 |  |  | 714 |  |  | 681 |  |  | 715 |  |  | 678 |  |  | 710 |  |  | 658 |  |  | 696 |  |  | 775 |  |  | 674 |  |  | 683 |  |  | 685 |  |  | 779 |  |  | 653 |  |  | 619 |  |  | 733 |  |  | 679 |  |  | 667 |  |  | 693 |  |  | 699 |  |  | 652 |  |  | 664 |  |  | 651 |  |  | 733 |  |  | 698 |  |  | 670 |  |  | 690 |  |  | 645 |  |  | 696 |  |  | 729 |  |  | 626 |  |  | 782 |  |  | 646 |  |  | 755 |  |  | 770 |  |  | 717 |  |  | 746 |  |  | 632 |  |  | 743 |  |  | 742 |  |  | 762 |  |  | 663 |  |  | 682 |  |  | 697 |  |  | 662 |  |  | 671 |  |  | 656 |  |  | 663 |  |  | 659 |  |  | 678 |  |  | 762 |  |  | 709 |  |  | 658 |  |  | 716 |  |  | 690 |  |  | 685 |  |  | 645 |  |  | 633 |  |  | 690 |  |  | 678 |  |  | 716 |  |  | 681 |  |  | 668 |  |  | 669 |  |  | 669 |  |  | 763 |  |  | 655 |  |  | 694 |  |  | 712 |  |  | 723 |  |  | 738 |  |  | 720 |  |  | 653 |  |  | 621 |  |  | 688 |  |  | 728 |  |  | 630 |  |  | 614 |  |  | 671 |  |  | 683 |  |  | 633 |  |  | 700 |  |  | 686 |  |  | 753 |  |  | 694 |  |  | 711 |  |  | 661 |  |  | 704 |  |  | 699 |  |  | 720 |  |  | 727 |  |  | 657 |  |  | 651 |  |  | 749 |  |  | 663 |  |  | 695 |  |  | 713 |  |  | 697 |  |  | 603 |  |  | 674 |  |  | 688 |  |  | 640 |  |  | 780 |  |  | 688 |  |  | 666 |  |  | 664 |  |  | 677 |  |  | 615 |  |  | 659 |  |  | 780 |  |  | 734 |  |  | 665 |  |  | 719 |  |  | 690 |  |  | 671 |  |  | 717 |  |  | 706 |  |  | 734 |  |  | 710 |  |  | 625 |  |  | 746 |  |  | 701 |  |  | 692 |  |  | 722 |  |  | 669 |  |  | 700 |  |  | 625 |  |  | 734 |  |  | 691 |  |  | 734 |  |  | 711 |  |  | 669 |  |  | 627 |  |  | 743 |  |  | 729 |  |  | 698 |  |  | 654 |  |  | 652 |  |  | 731 |  |  | 657 |  |  | 699 |  |  | 705 |  |  | 720 |  |  | 664 |  |  | 685 |  |  | 713 |  |  | 645 |  |  | 687 |  |  | 783 |  |  | 696 |  |  | 710 |  |  | 738 |  |  | 672 |  |  | 656 |  |  | 684 |  |  | 686 |  |  | 765 |  |  | 665 |  |  | 668 |  |  | 688 |  |  | 679 |  |  | 740 |  |  | 652 |  |  | 768 |  |  | 750 |  |  | 727 |  |  | 733 |  |  | 685 |  |  | 644 |  |  | 728 |  |  | 724 |  |  | 675 |  |  | 735 |  |  | 660 |  |  | 664 |  |  | 694 |  |  | 716 |  |  | 720 |  |  | 668 |  |  | 683 |  |  | 639 |  |  | 723 |  |  | 643 |  |  | 702 |  |  | 710 |  |  | 655 |  |  | 715 |  |  | 684 |  |  | 657 |  |  | 692 |  |  | 662 |  |  | 692 |  |  | 719 |  |  | 663 |  |  | 662 |  |  | 677 |  |  | 695 |  |  | 709 |  |  | 697 |  |  | 684 |  |  | 700 |  |  | 772 |  |  | 693 |  |  | 668 |  |  | 714 |  |  | 731 |  |  | 731 |  |  | 691 |  |  | 673 |  |  | 645 |  |  | 721 |  |  | 660 |  |  | 664 |  |  | 683 |  |  | 771 |  |  | 753 |  |  | 594 |  |  | 698 |  |  | 700 |  |  | 787 |  |  | 681 |  |  | 667 |  |  | 712 |  |  | 718 |  |  | 764 |  |  | 719 |  |  | 680 |  |  | 631 |  |  | 697 |  |  | 686 |  |  | 757 |  |  | 685 |  |  | 668 |  |  | 707 |  |  | 662 |  |  | 705 |  |  | 710 |  |  | 642 |  |  | 733 |  |  | 718 |  |  | 695 |  |  | 689 |  |  | 642 |  |  | 748 |  |  | 736 |  |  | 694 |  |  | 704 |  |  | 676 |  |  | 660 |  |  | 729 |  |  | 700 |  |  | 662 |  |  | 657 |  |  | 714 |  |  | 643 |  |  | 652 |  |  | 647 |  |  | 687 |  |  | 717 |  |  | 678 |  |  | 701 |  |  | 662 |  |  | 719 |  |  | 700 |  |  | 673 |  |  | 757 |  |  | 730 |  |  | 688 |  |  | 788 |  |  | 684 |  |  | 745 |  |  | 757 |  |  | 651 |  |  | 634 |  |  | 613 |  |  | 671 |  |  | 701 |  |  | 702 |  |  | 706 |  |  | 668 |  |  | 642 |  |  | 620 |  |  | 732 |  |  | 691 |  |  | 705 |  |  | 685 |  |  | 736 |  |  | 632 |  |  | 626 |  |  | 719 |  |  | 683 |  |  | 767 |  |  | 708 |  |  | 756 |  |  | 638 |  |  | 769 |  |  | 658 |  |  | 660 |  |  | 692 |  |  | 781 |  |  | 633 |  |  | 658 |  |  | 671 |  |  | 669 |  |  | 780 |  |  | 667 |  |  | 699 |  |  | 740 |  |  | 700 |  |  | 671 |  |  | 618 |  |  | 724 |  |  | 690 |  |  | 662 |  |  | 669 |  |  | 688 |  |  | 719 |  |  | 654 |  |  | 740 |  |  | 756 |  |  | 622 |  |  | 666 |  |  | 689 |  |  | 704 |  |  | 750 |  |  | 608 |  |  | 733 |  |  | 750 |  |  | 677 |  |  | 674 |  |  | 677 |  |  | 675 |  |  | 657 |  |  | 746 |  |  | 706 |  |  | 626 |  |  | 784 |  |  | 728 |  |  | 669 |  |  | 659 |  |  | 719 |  |  | 724 |  |  | 678 |  |  | 683 |  |  | 678 |  |  | 694 |  |  | 697 |  |  | 721 |  |  | 738 |  |  | 701 |  |  | 694 |  |  | 747 |  |  | 746 |  |  | 595 |  |  | 695 |  |  | 649 |  |  | 669 |  |  | 713 |  |  | 651 |  |  | 737 |  |  | 708 |  |  | 742 |  |  | 703 |  |  | 704 |  |  | 736 |  |  | 729 |  |  | 711 |  |  | 675 |  |  | 724 |  |  | 689 |  |  | 730 |  |  | 662 |  |  | 730 |  |  | 688 |  |  | 698 |  |  | 700 |  |  | 738 |  |  | 652 |  |  | 687 |  |  | 709 |  |  | 636 |  |  | 760 |  |  | 682 |  |  | 664 |  |  | 677 |  |  | 755 |  |  | 633 |  |  | 694 |  |  | 659 |  |  | 757 |  |  | 704 |  |  | 727 |  |  | 614 |  |  | 635 |  |  | 730 |  |  | 699 |  |  | 709 |  |  | 654 |  |  | 758 |  |  | 711 |  |  | 675 |  |  | 717 |  |  | 677 |  |  | 617 |  |  | 664 |  |  | 709 |  |  | 652 |  |  | 724 |  |  | 682 |  |  | 645 |  |  | 718 |  |  | 631 |  |  | 727 |  |  | 721 |  |  | 680 |  |  | 692 |  |  | 686 |  |  | 571 |  |  | 772 |  |  | 677 |  |  | 694 |  |  | 724 |  |  | 742 |  |  | 617 |  |  | 705 |  |  | 601 |  |  | 726 |  |  | 707 |  |  | 684 |  |  | 684 |  |  | 679 |  |  | 744 |  |  | 669 |  |  | 720 |  |  | 642 |  |  | 713 |  |  | 747 |  |  | 660 |  |  | 680 |  |  | 740 |  |  | 709 |  |  | 712 |  |  | 715 |  |  | 683 |  |  | 715 |  |  | 656 |  |  | 678 |  |  | 661 |  |  | 676 |  |  | 669 |  |  | 682 |  |  | 661 |  |  | 735 |  |  | 660 |  |  | 592 |  |  | 708 |  |  | 577 |  |  | 677 |  |  | 723 |  |  | 665 |  |  | 670 |  |  | 730 |  |  | 735 |  |  | 701 |  |  | 647 |  |  | 638 |  |  | 607 |  |  | 679 |  |  | 642 |  |  | 717 |  |  | 708 |  |  | 650 |  |  | 637 |  |  | 579 |  |  | 720 |  |  | 791 |  |  | 721 |  |  | 714 |  |  | 677 |  |  | 674 |  |  | 673 |  |  | 632 |  |  | 691 |  |  | 659 |  |  | 747 |  |  | 787 |  |  | 652 |  |  | 747 |  |  | 694 |  |  | 715 |  |  | 635 |  |  | 719 |  |  | 660 |  |  | 696 |  |  | 665 |  |  | 686 |  |  | 689 |  |  | 665 |  |  | 673 |  |  | 684 |  |  | 739 |  |  | 742 |  |  | 705 |  |  | 635 |  |  | 714 |  |  | 720 |  |  | 701 |  |  | 652 |  |  | 637 |  |  | 696 |  |  | 638 |  |  | 723 |  |  | 696 |  |  | 717 |  |  | 654 |  |  | 701 |  |  | 653 |  |  | 709 |  |  | 713 |  |  | 681 |  |  | 709 |  |  | 718 |  |  | 694 |  |  | 673 |  |  | 660 |  |  | 670 |  |  | 683 |  |  | 747 |  |  | 659 |  |  | 746 |  |  | 656 |  |  | 646 |  |  | 625 |  |  | 693 |  |  | 693 |  |  | 702 |  |  | 738 |  |  | 665 |  |  | 682 |  |  | 656 |  |  | 707 |  |  | 704 |  |  | 687 |  |  | 684 |  |  | 742 |  |  | 765 |  |  | 670 |  |  | 622 |  |  | 655 |  |  | 697 |  |  | 641 |  |  | 603 |  |  | 636 |  |  | 723 |  |  | 670 |  |  | 662 |  |  | 694 |  |  | 703 |  |  | 725 |  |  | 659 |  |  | 664 |  |  | 725 |  |  | 668 |  |  | 665 |  |  | 653 |  |  | 741 |  |  | 723 |  |  | 733 |  |  | 687 |  |  | 744 |  |  | 642 |  |  | 778 |  |  | 674 |  |  | 674 |  |  | 692 |  |  | 663 |  |  | 678 |  |  | 698 |  |  | 742 |  |  | 687 |  |  | 773 |  |  | 653 |  |  | 718 |  |  | 661 |  |  | 663 |  |  | 701 |  |  | 686 |  |  | 625 |  |  | 673 |  |  | 713 |  |  | 675 |  |  | 733 |  |  | 683 |  |  | 642 |  |  | 806 |  |  | 734 |  |  | 695 |  |  | 673 |  |  | 642 |  |  | 664 |  |  | 663 |  |  | 685 |  |  | 705 |  |  | 677 |  |  | 650 |  |  | 652 |  |  | 736 |  |  | 691 |  |  | 671 |  |  | 710 |  |  | 654 |  |  | 688 |  |  | 658 |  |  | 686 |  |  | 708 |  |  | 681 |  |  | 744 |  |  | 722 |  |  | 729 |  |  | 663 |  |  | 656 |  |  | 678 |  |  | 702 |  |  | 757 |  |  | 677 |  |  | 739 |  |  | 726 |  |  | 720 |  |  | 708 |  |  | 650 |  |  | 678 |  |  | 724 |  |  | 713 |  |  | 717 |  |  | 655 |  |  | 615 |  |  | 713 |  |  | 709 |  |  | 668 |  |  | 686 |  |  | 709 |  |  | 713 |  |  | 686 |  |  | 693 |  |  | 676 |  |  | 635 |  |  | 692 |  |  | 623 |  |  | 695 |  |  | 699 |  |  | 734 |  |  | 670 |  |  | 745 |  |  | 703 |  |  | 694 |  |  | 673 |  |  | 706 |  |  | 710 |  |  | 772 |  |  | 744 |  |  | 711 |  |  | 652 |  |  | 728 |  |  | 655 |  |  | 610 |  |  | 676 |  |  | 649 |  |  | 670 |  |  | 717 |  |  | 644 |  |  | 697 |  |  | 674 |  |  | 644 |  |  | 695 |  |  | 686 |  |  | 683 |  |  | 600 |  |  | 683 |  |  | 625 |  |  | 703 |  |  | 722 |  |  | 649 |  |  | 680 |  |  | 658 |  |  | 685 |  |  | 687 |  |  | 658 |  |  | 670 |  |  | 707 |  |  | 695 |  |  | 608 |  |  | 651 |  |  | 607 |  |  | 710 |  |  | 707 |  |  | 740 |  |  | 722 |  |  | 675 |  |  | 662 |  |  | 695 |  |  | 694 |  |  | 720
24 |  | 770.5 |  |  | 699.5 |  |  | 703.5 |  |  | 744.5 |  |  | 721.5 |  |  | 714.5 |  |  | 676.5 |  |  | 720.5 |  |  | 738 |  |  | 709 |  |  | 736.5 |  |  | 772.5 |  |  | 725.5 |  |  | 743 |  |  | 727 |  |  | 711.5 |  |  | 682.5 |  |  | 706.5 |  |  | 744.5 |  |  | 617 |  |  | 720.5 |  |  | 754 |  |  | 741.5 |  |  | 736.5 |  |  | 646 |  |  | 720.5 |  |  | 749.5 |  |  | 694.5 |  |  | 754.5 |  |  | 718.5 |  |  | 678.5 |  |  | 722 |  |  | 798.5 |  |  | 688 |  |  | 670.5 |  |  | 689 |  |  | 701.5 |  |  | 671.5 |  |  | 709.5 |  |  | 757.5 |  |  | 636 |  |  | 691.5 |  |  | 741 |  |  | 738.5 |  |  | 755 |  |  | 740.5 |  |  | 723.5 |  |  | 724.5 |  |  | 648.5 |  |  | 646 |  |  | 738 |  |  | 734 |  |  | 639 |  |  | 751.5 |  |  | 661.5 |  |  | 682.5 |  |  | 728.5 |  |  | 762.5 |  |  | 712.5 |  |  | 724 |  |  | 780 |  |  | 732.5 |  |  | 681.5 |  |  | 714.5 |  |  | 626.5 |  |  | 636 |  |  | 759.5 |  |  | 755 |  |  | 734.5 |  |  | 709 |  |  | 707.5 |  |  | 708.5 |  |  | 683.5 |  |  | 692.5 |  |  | 740.5 |  |  | 661.5 |  |  | 707.5 |  |  | 714 |  |  | 732 |  |  | 713.5 |  |  | 732.5 |  |  | 723.5 |  |  | 683.5 |  |  | 709.5 |  |  | 725 |  |  | 690.5 |  |  | 649.5 |  |  | 710.5 |  |  | 668.5 |  |  | 702 |  |  | 712 |  |  | 720.5 |  |  | 825.5 |  |  | 719.5 |  |  | 705 |  |  | 690 |  |  | 727 |  |  | 706.5 |  |  | 681.5 |  |  | 675 |  |  | 705.5 |  |  | 645.5 |  |  | 693 |  |  | 696 |  |  | 699.5 |  |  | 678 |  |  | 683 |  |  | 678.5 |  |  | 743.5 |  |  | 709.5 |  |  | 695.5 |  |  | 680 |  |  | 724.5 |  |  | 714.5 |  |  | 701.5 |  |  | 705.5 |  |  | 729.5 |  |  | 679.5 |  |  | 675.5 |  |  | 744 |  |  | 773.5 |  |  | 640.5 |  |  | 749.5 |  |  | 644.5 |  |  | 636.5 |  |  | 728.5 |  |  | 721.5 |  |  | 722.5 |  |  | 676.5 |  |  | 760.5 |  |  | 685.5 |  |  | 776 |  |  | 623 |  |  | 640.5 |  |  | 667.5 |  |  | 707.5 |  |  | 719.5 |  |  | 738 |  |  | 725.5 |  |  | 697.5 |  |  | 656.5 |  |  | 701.5 |  |  | 679.5 |  |  | 676.5 |  |  | 673 |  |  | 669.5 |  |  | 632.5 |  |  | 684.5 |  |  | 760.5 |  |  | 654.5 |  |  | 623.5 |  |  | 726.5 |  |  | 674 |  |  | 732 |  |  | 733.5 |  |  | 723.5 |  |  | 633.5 |  |  | 724.5 |  |  | 671.5 |  |  | 793 |  |  | 729.5 |  |  | 672.5 |  |  | 724.5 |  |  | 650.5 |  |  | 665 |  |  | 651.5 |  |  | 688.5 |  |  | 652 |  |  | 701 |  |  | 722.5 |  |  | 660.5 |  |  | 677.5 |  |  | 707.5 |  |  | 720.5 |  |  | 705 |  |  | 694.5 |  |  | 659.5 |  |  | 724.5 |  |  | 760.5 |  |  | 660.5 |  |  | 744.5 |  |  | 766.5 |  |  | 732.5 |  |  | 653.5 |  |  | 675 |  |  | 775.5 |  |  | 707.5 |  |  | 691.5 |  |  | 724.5 |  |  | 664.5 |  |  | 670.5 |  |  | 727 |  |  | 765 |  |  | 679.5 |  |  | 668.5 |  |  | 666.5 |  |  | 654 |  |  | 701.5 |  |  | 740.5 |  |  | 696 |  |  | 703 |  |  | 728.5 |  |  | 695.5 |  |  | 694.5 |  |  | 774 |  |  | 734.5 |  |  | 672.5 |  |  | 728.5 |  |  | 726.5 |  |  | 727.5 |  |  | 756.5 |  |  | 656.5 |  |  | 687 |  |  | 718.5 |  |  | 716.5 |  |  | 622.5 |  |  | 733.5 |  |  | 691.5 |  |  | 706.5 |  |  | 758.5 |  |  | 664.5 |  |  | 730.5 |  |  | 741 |  |  | 680 |  |  | 626.5 |  |  | 733.5 |  |  | 768.5 |  |  | 714.5 |  |  | 709.5 |  |  | 701.5 |  |  | 686 |  |  | 658 |  |  | 723.5 |  |  | 686.5 |  |  | 721.5 |  |  | 720.5 |  |  | 633 |  |  | 675.5 |  |  | 658 |  |  | 781.5 |  |  | 729.5 |  |  | 745.5 |  |  | 658.5 |  |  | 745.5 |  |  | 733 |  |  | 632 |  |  | 748.5 |  |  | 764 |  |  | 717 |  |  | 695.5 |  |  | 664.5 |  |  | 743 |  |  | 736.5 |  |  | 733 |  |  | 764.5 |  |  | 624.5 |  |  | 668.5 |  |  | 729.5 |  |  | 703.5 |  |  | 710.5 |  |  | 755.5 |  |  | 688.5 |  |  | 691 |  |  | 735 |  |  | 682.5 |  |  | 723 |  |  | 705.5 |  |  | 681.5 |  |  | 679 |  |  | 723.5 |  |  | 764.5 |  |  | 790 |  |  | 764.5 |  |  | 716.5 |  |  | 766.5 |  |  | 703 |  |  | 644 |  |  | 711.5 |  |  | 639.5 |  |  | 748.5 |  |  | 671.5 |  |  | 714 |  |  | 729.5 |  |  | 637.5 |  |  | 731 |  |  | 708.5 |  |  | 743 |  |  | 696.5 |  |  | 733.5 |  |  | 694.5 |  |  | 646.5 |  |  | 758 |  |  | 739.5 |  |  | 725 |  |  | 741 |  |  | 728.5 |  |  | 761.5 |  |  | 727 |  |  | 787.5 |  |  | 726 |  |  | 700.5 |  |  | 727 |  |  | 697.5 |  |  | 720.5 |  |  | 677.5 |  |  | 703.5 |  |  | 794.5 |  |  | 688.5 |  |  | 702.5 |  |  | 697 |  |  | 789.5 |  |  | 676.5 |  |  | 633.5 |  |  | 752.5 |  |  | 692 |  |  | 674.5 |  |  | 716.5 |  |  | 718.5 |  |  | 662.5 |  |  | 683.5 |  |  | 670.5 |  |  | 756.5 |  |  | 705.5 |  |  | 680.5 |  |  | 713.5 |  |  | 655.5 |  |  | 710.5 |  |  | 736.5 |  |  | 649.5 |  |  | 794 |  |  | 659 |  |  | 767 |  |  | 784.5 |  |  | 724.5 |  |  | 769.5 |  |  | 639.5 |  |  | 762.5 |  |  | 761.5 |  |  | 769.5 |  |  | 670.5 |  |  | 696.5 |  |  | 716.5 |  |  | 681.5 |  |  | 681.5 |  |  | 679.5 |  |  | 675 |  |  | 673.5 |  |  | 692.5 |  |  | 774 |  |  | 722 |  |  | 681.5 |  |  | 729 |  |  | 709.5 |  |  | 708.5 |  |  | 658 |  |  | 652.5 |  |  | 709.5 |  |  | 691 |  |  | 730.5 |  |  | 695.5 |  |  | 687.5 |  |  | 688.5 |  |  | 682 |  |  | 773.5 |  |  | 674.5 |  |  | 706 |  |  | 731.5 |  |  | 735 |  |  | 757.5 |  |  | 730.5 |  |  | 660.5 |  |  | 635.5 |  |  | 702.5 |  |  | 751.5 |  |  | 649.5 |  |  | 621.5 |  |  | 678.5 |  |  | 706.5 |  |  | 652.5 |  |  | 712 |  |  | 698 |  |  | 760.5 |  |  | 706 |  |  | 725.5 |  |  | 680.5 |  |  | 718.5 |  |  | 718.5 |  |  | 734.5 |  |  | 746.5 |  |  | 676.5 |  |  | 661.5 |  |  | 761 |  |  | 676 |  |  | 709.5 |  |  | 727.5 |  |  | 716.5 |  |  | 622.5 |  |  | 688.5 |  |  | 707.5 |  |  | 647.5 |  |  | 790.5 |  |  | 707.5 |  |  | 685.5 |  |  | 687.5 |  |  | 691.5 |  |  | 634.5 |  |  | 678.5 |  |  | 799.5 |  |  | 748.5 |  |  | 678 |  |  | 738.5 |  |  | 713.5 |  |  | 690.5 |  |  | 736.5 |  |  | 719 |  |  | 748.5 |  |  | 729.5 |  |  | 635.5 |  |  | 753.5 |  |  | 720.5 |  |  | 699.5 |  |  | 736.5 |  |  | 676.5 |  |  | 719.5 |  |  | 644.5 |  |  | 753.5 |  |  | 703 |  |  | 746 |  |  | 730.5 |  |  | 679.5 |  |  | 640 |  |  | 750.5 |  |  | 748.5 |  |  | 711 |  |  | 673.5 |  |  | 664 |  |  | 750.5 |  |  | 669 |  |  | 718.5 |  |  | 728.5 |  |  | 732 |  |  | 678.5 |  |  | 698 |  |  | 736.5 |  |  | 655.5 |  |  | 700 |  |  | 797.5 |  |  | 706.5 |  |  | 729.5 |  |  | 745.5 |  |  | 691.5 |  |  | 675.5 |  |  | 703.5 |  |  | 705.5 |  |  | 777 |  |  | 679.5 |  |  | 678.5 |  |  | 707.5 |  |  | 691 |  |  | 750.5 |  |  | 662.5 |  |  | 775.5 |  |  | 760.5 |  |  | 750.5 |  |  | 743.5 |  |  | 704.5 |  |  | 651.5 |  |  | 740 |  |  | 743.5 |  |  | 682.5 |  |  | 747 |  |  | 670.5 |  |  | 676 |  |  | 701.5 |  |  | 728 |  |  | 733 |  |  | 681 |  |  | 702.5 |  |  | 662.5 |  |  | 730.5 |  |  | 657.5 |  |  | 716.5 |  |  | 729.5 |  |  | 665.5 |  |  | 729.5 |  |  | 696 |  |  | 676.5 |  |  | 715.5 |  |  | 676.5 |  |  | 699.5 |  |  | 732 |  |  | 673.5 |  |  | 681.5 |  |  | 684.5 |  |  | 714.5 |  |  | 728.5 |  |  | 709 |  |  | 694.5 |  |  | 723.5 |  |  | 791.5 |  |  | 700.5 |  |  | 675.5 |  |  | 733.5 |  |  | 741.5 |  |  | 738.5 |  |  | 705.5 |  |  | 683.5 |  |  | 668.5 |  |  | 728.5 |  |  | 667.5 |  |  | 683.5 |  |  | 702.5 |  |  | 783 |  |  | 765 |  |  | 604.5 |  |  | 712.5 |  |  | 710.5 |  |  | 800 |  |  | 695.5 |  |  | 674.5 |  |  | 722.5 |  |  | 737.5 |  |  | 776 |  |  | 738.5 |  |  | 687.5 |  |  | 641.5 |  |  | 704.5 |  |  | 698 |  |  | 771.5 |  |  | 695.5 |  |  | 681 |  |  | 721.5 |  |  | 685.5 |  |  | 715.5 |  |  | 717.5 |  |  | 656.5 |  |  | 756.5 |  |  | 730 |  |  | 708 |  |  | 696.5 |  |  | 661.5 |  |  | 771.5 |  |  | 746.5 |  |  | 708.5 |  |  | 723.5 |  |  | 689 |  |  | 679.5 |  |  | 736.5 |  |  | 714.5 |  |  | 676.5 |  |  | 669 |  |  | 724.5 |  |  | 656 |  |  | 666.5 |  |  | 661.5 |  |  | 701.5 |  |  | 736.5 |  |  | 685.5 |  |  | 720.5 |  |  | 674 |  |  | 733.5 |  |  | 714.5 |  |  | 680.5 |  |  | 764.5 |  |  | 753.5 |  |  | 700 |  |  | 811.5 |  |  | 691.5 |  |  | 755.5 |  |  | 764.5 |  |  | 665.5 |  |  | 644.5 |  |  | 623.5 |  |  | 678.5 |  |  | 714 |  |  | 721.5 |  |  | 729.5 |  |  | 678.5 |  |  | 652.5 |  |  | 639.5 |  |  | 745 |  |  | 710.5 |  |  | 712.5 |  |  | 698 |  |  | 755.5 |  |  | 655.5 |  |  | 636.5 |  |  | 738.5 |  |  | 690.5 |  |  | 786.5 |  |  | 720 |  |  | 779.5 |  |  | 661.5 |  |  | 779.5 |  |  | 681.5 |  |  | 679.5 |  |  | 699.5 |  |  | 794 |  |  | 645 |  |  | 668.5 |  |  | 690.5 |  |  | 683.5 |  |  | 793 |  |  | 686.5 |  |  | 718.5 |  |  | 747.5 |  |  | 719.5 |  |  | 681.5 |  |  | 632.5 |  |  | 736 |  |  | 709.5 |  |  | 672.5 |  |  | 676.5 |  |  | 695.5 |  |  | 738.5 |  |  | 664.5 |  |  | 747.5 |  |  | 766.5 |  |  | 629.5 |  |  | 680.5 |  |  | 712.5 |  |  | 723.5 |  |  | 764.5 |  |  | 620 |  |  | 743.5 |  |  | 769.5 |  |  | 689 |  |  | 697.5 |  |  | 696.5 |  |  | 685.5 |  |  | 680.5 |  |  | 753.5 |  |  | 729.5 |  |  | 645.5 |  |  | 807.5 |  |  | 751.5 |  |  | 688.5 |  |  | 671 |  |  | 729.5 |  |  | 747.5 |  |  | 691 |  |  | 690.5 |  |  | 691 |  |  | 713.5 |  |  | 716.5 |  |  | 728.5 |  |  | 757.5 |  |  | 724.5 |  |  | 713.5 |  |  | 770.5 |  |  | 765.5 |  |  | 614.5 |  |  | 718.5 |  |  | 668.5 |  |  | 692.5 |  |  | 732.5 |  |  | 674.5 |  |  | 750 |  |  | 720 |  |  | 754 |  |  | 722.5 |  |  | 716 |  |  | 743.5 |  |  | 748.5 |  |  | 730.5 |  |  | 694.5 |  |  | 738.5 |  |  | 701 |  |  | 742 |  |  | 675 |  |  | 744.5 |  |  | 711.5 |  |  | 717.5 |  |  | 714.5 |  |  | 757.5 |  |  | 659.5 |  |  | 706.5 |  |  | 732.5 |  |  | 650.5 |  |  | 779.5 |  |  | 689.5 |  |  | 687.5 |  |  | 687.5 |  |  | 767 |  |  | 652.5 |  |  | 713.5 |  |  | 666.5 |  |  | 771.5 |  |  | 716 |  |  | 741.5 |  |  | 633.5 |  |  | 642.5 |  |  | 743 |  |  | 711 |  |  | 722 |  |  | 677.5 |  |  | 768.5 |  |  | 730.5 |  |  | 687 |  |  | 736.5 |  |  | 691.5 |  |  | 631.5 |  |  | 674.5 |  |  | 732.5 |  |  | 665 |  |  | 738.5 |  |  | 696.5 |  |  | 664.5 |  |  | 730 |  |  | 645.5 |  |  | 741.5 |  |  | 744.5 |  |  | 687.5 |  |  | 706.5 |  |  | 698 |  |  | 594.5 |  |  | 782.5 |  |  | 690 |  |  | 701.5 |  |  | 737 |  |  | 754 |  |  | 630 |  |  | 717 |  |  | 608.5 |  |  | 733.5 |  |  | 719 |  |  | 703.5 |  |  | 703.5 |  |  | 686.5 |  |  | 763.5 |  |  | 692.5 |  |  | 739.5 |  |  | 661.5 |  |  | 736.5 |  |  | 760 |  |  | 673 |  |  | 694.5 |  |  | 759.5 |  |  | 723.5 |  |  | 719.5 |  |  | 738.5 |  |  | 696 |  |  | 722.5 |  |  | 679.5 |  |  | 688.5 |  |  | 680.5 |  |  | 695.5 |  |  | 682 |  |  | 694 |  |  | 675.5 |  |  | 748 |  |  | 679.5 |  |  | 611.5 |  |  | 731.5 |  |  | 590 |  |  | 696.5 |  |  | 733.5 |  |  | 678 |  |  | 689.5 |  |  | 744.5 |  |  | 745.5 |  |  | 724.5 |  |  | 657.5 |  |  | 650 |  |  | 621.5 |  |  | 702.5 |  |  | 656.5 |  |  | 736.5 |  |  | 715.5 |  |  | 673.5 |  |  | 651.5 |  |  | 589.5 |  |  | 732 |  |  | 810.5 |  |  | 733 |  |  | 726 |  |  | 691.5 |  |  | 687 |  |  | 680.5 |  |  | 642.5 |  |  | 703 |  |  | 682.5 |  |  | 760 |  |  | 797.5 |  |  | 675.5 |  |  | 754.5 |  |  | 706 |  |  | 722.5 |  |  | 645.5 |  |  | 732 |  |  | 674.5 |  |  | 719.5 |  |  | 677 |  |  | 709.5 |  |  | 703.5 |  |  | 678 |  |  | 683.5 |  |  | 697 |  |  | 758.5 |  |  | 754 |  |  | 718 |  |  | 645.5 |  |  | 721.5 |  |  | 732 |  |  | 720.5 |  |  | 671.5 |  |  | 649 |  |  | 708 |  |  | 648.5 |  |  | 736 |  |  | 715.5 |  |  | 724.5 |  |  | 673.5 |  |  | 724.5 |  |  | 667.5 |  |  | 716.5 |  |  | 725 |  |  | 694 |  |  | 728.5 |  |  | 732.5 |  |  | 704.5 |  |  | 696.5 |  |  | 667.5 |  |  | 684.5 |  |  | 697.5 |  |  | 770.5 |  |  | 678.5 |  |  | 759 |  |  | 668 |  |  | 665.5 |  |  | 637 |  |  | 712.5 |  |  | 706 |  |  | 721.5 |  |  | 745.5 |  |  | 677 |  |  | 689.5 |  |  | 666.5 |  |  | 717.5 |  |  | 723.5 |  |  | 700 |  |  | 694.5 |  |  | 755 |  |  | 779.5 |  |  | 689.5 |  |  | 645.5 |  |  | 662.5 |  |  | 716.5 |  |  | 655.5 |  |  | 617.5 |  |  | 646.5 |  |  | 736 |  |  | 684.5 |  |  | 685.5 |  |  | 706 |  |  | 713.5 |  |  | 735.5 |  |  | 666.5 |  |  | 687.5 |  |  | 735.5 |  |  | 691.5 |  |  | 684.5 |  |  | 672.5 |  |  | 751.5 |  |  | 735 |  |  | 746 |  |  | 697.5 |  |  | 754.5 |  |  | 656.5 |  |  | 791 |  |  | 688.5 |  |  | 684.5 |  |  | 711.5 |  |  | 686.5 |  |  | 685.5 |  |  | 711 |  |  | 761.5 |  |  | 700 |  |  | 787.5 |  |  | 676.5 |  |  | 737.5 |  |  | 671.5 |  |  | 676 |  |  | 724.5 |  |  | 709.5 |  |  | 639.5 |  |  | 696.5 |  |  | 720.5 |  |  | 694.5 |  |  | 743.5 |  |  | 702.5 |  |  | 654 |  |  | 820.5 |  |  | 741.5 |  |  | 714.5 |  |  | 685 |  |  | 655 |  |  | 677 |  |  | 677.5 |  |  | 697 |  |  | 724.5 |  |  | 687.5 |  |  | 669.5 |  |  | 671.5 |  |  | 748 |  |  | 710.5 |  |  | 681.5 |  |  | 723 |  |  | 673.5 |  |  | 698.5 |  |  | 670 |  |  | 705.5 |  |  | 722.5 |  |  | 704.5 |  |  | 756 |  |  | 734 |  |  | 741 |  |  | 686.5 |  |  | 666.5 |  |  | 688.5 |  |  | 721.5 |  |  | 770 |  |  | 687.5 |  |  | 752 |  |  | 745.5 |  |  | 733 |  |  | 715.5 |  |  | 657.5 |  |  | 688.5 |  |  | 737 |  |  | 727.5 |  |  | 731.5 |  |  | 669.5 |  |  | 625.5 |  |  | 725 |  |  | 716.5 |  |  | 678.5 |  |  | 705.5 |  |  | 719.5 |  |  | 726 |  |  | 696.5 |  |  | 700.5 |  |  | 689 |  |  | 654.5 |  |  | 702.5 |  |  | 635 |  |  | 705.5 |  |  | 718.5 |  |  | 741.5 |  |  | 682 |  |  | 752.5 |  |  | 716 |  |  | 717.5 |  |  | 683.5 |  |  | 718 |  |  | 720.5 |  |  | 782.5 |  |  | 754.5 |  |  | 721.5 |  |  | 664 |  |  | 742.5 |  |  | 662.5 |  |  | 629.5 |  |  | 688 |  |  | 661 |  |  | 684.5 |  |  | 729 |  |  | 658.5 |  |  | 710 |  |  | 693.5 |  |  | 663.5 |  |  | 714.5 |  |  | 696.5 |  |  | 702.5 |  |  | 619.5 |  |  | 693.5 |  |  | 632.5 |  |  | 716 |  |  | 741.5 |  |  | 672.5 |  |  | 690.5 |  |  | 670 |  |  | 698 |  |  | 697.5 |  |  | 677.5 |  |  | 684.5 |  |  | 714.5 |  |  | 702.5 |  |  | 627.5 |  |  | 670.5 |  |  | 621.5 |  |  | 729.5 |  |  | 717.5 |  |  | 747.5 |  |  | 745.5 |  |  | 689.5 |  |  | 672.5 |  |  | 714.5 |  |  | 708.5 |  |  | 732
25 |  | 770.5 |  |  | 699.5 |  |  | 703.5 |  |  | 744.5 |  |  | 721.5 |  |  | 714.5 |  |  | 676.5 |  |  | 720.5 |  |  | 738 |  |  | 709 |  |  | 736.5 |  |  | 772.5 |  |  | 725.5 |  |  | 743 |  |  | 727 |  |  | 711.5 |  |  | 682.5 |  |  | 706.5 |  |  | 744.5 |  |  | 617 |  |  | 720.5 |  |  | 754 |  |  | 741.5 |  |  | 736.5 |  |  | 646 |  |  | 720.5 |  |  | 749.5 |  |  | 694.5 |  |  | 754.5 |  |  | 718.5 |  |  | 678.5 |  |  | 722 |  |  | 798.5 |  |  | 688 |  |  | 670.5 |  |  | 689 |  |  | 701.5 |  |  | 671.5 |  |  | 709.5 |  |  | 757.5 |  |  | 636 |  |  | 691.5 |  |  | 741 |  |  | 738.5 |  |  | 755 |  |  | 740.5 |  |  | 723.5 |  |  | 724.5 |  |  | 648.5 |  |  | 646 |  |  | 738 |  |  | 734 |  |  | 639 |  |  | 751.5 |  |  | 661.5 |  |  | 682.5 |  |  | 728.5 |  |  | 762.5 |  |  | 712.5 |  |  | 724 |  |  | 780 |  |  | 732.5 |  |  | 681.5 |  |  | 714.5 |  |  | 626.5 |  |  | 636 |  |  | 759.5 |  |  | 755 |  |  | 734.5 |  |  | 709 |  |  | 707.5 |  |  | 708.5 |  |  | 683.5 |  |  | 692.5 |  |  | 740.5 |  |  | 661.5 |  |  | 707.5 |  |  | 714 |  |  | 732 |  |  | 713.5 |  |  | 732.5 |  |  | 723.5 |  |  | 683.5 |  |  | 709.5 |  |  | 725 |  |  | 690.5 |  |  | 649.5 |  |  | 710.5 |  |  | 668.5 |  |  | 702 |  |  | 712 |  |  | 720.5 |  |  | 825.5 |  |  | 719.5 |  |  | 705 |  |  | 690 |  |  | 727 |  |  | 706.5 |  |  | 681.5 |  |  | 675 |  |  | 705.5 |  |  | 645.5 |  |  | 693 |  |  | 696 |  |  | 699.5 |  |  | 678 |  |  | 683 |  |  | 678.5 |  |  | 743.5 |  |  | 709.5 |  |  | 695.5 |  |  | 680 |  |  | 724.5 |  |  | 714.5 |  |  | 701.5 |  |  | 705.5 |  |  | 729.5 |  |  | 679.5 |  |  | 675.5 |  |  | 744 |  |  | 773.5 |  |  | 640.5 |  |  | 749.5 |  |  | 644.5 |  |  | 636.5 |  |  | 728.5 |  |  | 721.5 |  |  | 722.5 |  |  | 676.5 |  |  | 760.5 |  |  | 685.5 |  |  | 776 |  |  | 623 |  |  | 640.5 |  |  | 667.5 |  |  | 707.5 |  |  | 719.5 |  |  | 738 |  |  | 725.5 |  |  | 697.5 |  |  | 656.5 |  |  | 701.5 |  |  | 679.5 |  |  | 676.5 |  |  | 673 |  |  | 669.5 |  |  | 632.5 |  |  | 684.5 |  |  | 760.5 |  |  | 654.5 |  |  | 623.5 |  |  | 726.5 |  |  | 674 |  |  | 732 |  |  | 733.5 |  |  | 723.5 |  |  | 633.5 |  |  | 724.5 |  |  | 671.5 |  |  | 793 |  |  | 729.5 |  |  | 672.5 |  |  | 724.5 |  |  | 650.5 |  |  | 665 |  |  | 651.5 |  |  | 688.5 |  |  | 652 |  |  | 701 |  |  | 722.5 |  |  | 660.5 |  |  | 677.5 |  |  | 707.5 |  |  | 720.5 |  |  | 705 |  |  | 694.5 |  |  | 659.5 |  |  | 724.5 |  |  | 760.5 |  |  | 660.5 |  |  | 744.5 |  |  | 766.5 |  |  | 732.5 |  |  | 653.5 |  |  | 675 |  |  | 775.5 |  |  | 707.5 |  |  | 691.5 |  |  | 724.5 |  |  | 664.5 |  |  | 670.5 |  |  | 727 |  |  | 765 |  |  | 679.5 |  |  | 668.5 |  |  | 666.5 |  |  | 654 |  |  | 701.5 |  |  | 740.5 |  |  | 696 |  |  | 703 |  |  | 728.5 |  |  | 695.5 |  |  | 694.5 |  |  | 774 |  |  | 734.5 |  |  | 672.5 |  |  | 728.5 |  |  | 726.5 |  |  | 727.5 |  |  | 756.5 |  |  | 656.5 |  |  | 687 |  |  | 718.5 |  |  | 716.5 |  |  | 622.5 |  |  | 733.5 |  |  | 691.5 |  |  | 706.5 |  |  | 758.5 |  |  | 664.5 |  |  | 730.5 |  |  | 741 |  |  | 680 |  |  | 626.5 |  |  | 733.5 |  |  | 768.5 |  |  | 714.5 |  |  | 709.5 |  |  | 701.5 |  |  | 686 |  |  | 658 |  |  | 723.5 |  |  | 686.5 |  |  | 721.5 |  |  | 720.5 |  |  | 633 |  |  | 675.5 |  |  | 658 |  |  | 781.5 |  |  | 729.5 |  |  | 745.5 |  |  | 658.5 |  |  | 745.5 |  |  | 733 |  |  | 632 |  |  | 748.5 |  |  | 764 |  |  | 717 |  |  | 695.5 |  |  | 664.5 |  |  | 743 |  |  | 736.5 |  |  | 733 |  |  | 764.5 |  |  | 624.5 |  |  | 668.5 |  |  | 729.5 |  |  | 703.5 |  |  | 710.5 |  |  | 755.5 |  |  | 688.5 |  |  | 691 |  |  | 735 |  |  | 682.5 |  |  | 723 |  |  | 705.5 |  |  | 681.5 |  |  | 679 |  |  | 723.5 |  |  | 764.5 |  |  | 790 |  |  | 764.5 |  |  | 716.5 |  |  | 766.5 |  |  | 703 |  |  | 644 |  |  | 711.5 |  |  | 639.5 |  |  | 748.5 |  |  | 671.5 |  |  | 714 |  |  | 729.5 |  |  | 637.5 |  |  | 731 |  |  | 708.5 |  |  | 743 |  |  | 696.5 |  |  | 733.5 |  |  | 694.5 |  |  | 646.5 |  |  | 758 |  |  | 739.5 |  |  | 725 |  |  | 741 |  |  | 728.5 |  |  | 761.5 |  |  | 727 |  |  | 787.5 |  |  | 726 |  |  | 700.5 |  |  | 727 |  |  | 697.5 |  |  | 720.5 |  |  | 677.5 |  |  | 703.5 |  |  | 794.5 |  |  | 688.5 |  |  | 702.5 |  |  | 697 |  |  | 789.5 |  |  | 676.5 |  |  | 633.5 |  |  | 752.5 |  |  | 692 |  |  | 674.5 |  |  | 716.5 |  |  | 718.5 |  |  | 662.5 |  |  | 683.5 |  |  | 670.5 |  |  | 756.5 |  |  | 705.5 |  |  | 680.5 |  |  | 713.5 |  |  | 655.5 |  |  | 710.5 |  |  | 736.5 |  |  | 649.5 |  |  | 794 |  |  | 659 |  |  | 767 |  |  | 784.5 |  |  | 724.5 |  |  | 769.5 |  |  | 639.5 |  |  | 762.5 |  |  | 761.5 |  |  | 769.5 |  |  | 670.5 |  |  | 696.5 |  |  | 716.5 |  |  | 681.5 |  |  | 681.5 |  |  | 679.5 |  |  | 675 |  |  | 673.5 |  |  | 692.5 |  |  | 774 |  |  | 722 |  |  | 681.5 |  |  | 729 |  |  | 709.5 |  |  | 708.5 |  |  | 658 |  |  | 652.5 |  |  | 709.5 |  |  | 691 |  |  | 730.5 |  |  | 695.5 |  |  | 687.5 |  |  | 688.5 |  |  | 682 |  |  | 773.5 |  |  | 674.5 |  |  | 706 |  |  | 731.5 |  |  | 735 |  |  | 757.5 |  |  | 730.5 |  |  | 660.5 |  |  | 635.5 |  |  | 702.5 |  |  | 751.5 |  |  | 649.5 |  |  | 621.5 |  |  | 678.5 |  |  | 706.5 |  |  | 652.5 |  |  | 712 |  |  | 698 |  |  | 760.5 |  |  | 706 |  |  | 725.5 |  |  | 680.5 |  |  | 718.5 |  |  | 718.5 |  |  | 734.5 |  |  | 746.5 |  |  | 676.5 |  |  | 661.5 |  |  | 761 |  |  | 676 |  |  | 709.5 |  |  | 727.5 |  |  | 716.5 |  |  | 622.5 |  |  | 688.5 |  |  | 707.5 |  |  | 647.5 |  |  | 790.5 |  |  | 707.5 |  |  | 685.5 |  |  | 687.5 |  |  | 691.5 |  |  | 634.5 |  |  | 678.5 |  |  | 799.5 |  |  | 748.5 |  |  | 678 |  |  | 738.5 |  |  | 713.5 |  |  | 690.5 |  |  | 736.5 |  |  | 719 |  |  | 748.5 |  |  | 729.5 |  |  | 635.5 |  |  | 753.5 |  |  | 720.5 |  |  | 699.5 |  |  | 736.5 |  |  | 676.5 |  |  | 719.5 |  |  | 644.5 |  |  | 753.5 |  |  | 703 |  |  | 746 |  |  | 730.5 |  |  | 679.5 |  |  | 640 |  |  | 750.5 |  |  | 748.5 |  |  | 711 |  |  | 673.5 |  |  | 664 |  |  | 750.5 |  |  | 669 |  |  | 718.5 |  |  | 728.5 |  |  | 732 |  |  | 678.5 |  |  | 698 |  |  | 736.5 |  |  | 655.5 |  |  | 700 |  |  | 797.5 |  |  | 706.5 |  |  | 729.5 |  |  | 745.5 |  |  | 691.5 |  |  | 675.5 |  |  | 703.5 |  |  | 705.5 |  |  | 777 |  |  | 679.5 |  |  | 678.5 |  |  | 707.5 |  |  | 691 |  |  | 750.5 |  |  | 662.5 |  |  | 775.5 |  |  | 760.5 |  |  | 750.5 |  |  | 743.5 |  |  | 704.5 |  |  | 651.5 |  |  | 740 |  |  | 743.5 |  |  | 682.5 |  |  | 747 |  |  | 670.5 |  |  | 676 |  |  | 701.5 |  |  | 728 |  |  | 733 |  |  | 681 |  |  | 702.5 |  |  | 662.5 |  |  | 730.5 |  |  | 657.5 |  |  | 716.5 |  |  | 729.5 |  |  | 665.5 |  |  | 729.5 |  |  | 696 |  |  | 676.5 |  |  | 715.5 |  |  | 676.5 |  |  | 699.5 |  |  | 732 |  |  | 673.5 |  |  | 681.5 |  |  | 684.5 |  |  | 714.5 |  |  | 728.5 |  |  | 709 |  |  | 694.5 |  |  | 723.5 |  |  | 791.5 |  |  | 700.5 |  |  | 675.5 |  |  | 733.5 |  |  | 741.5 |  |  | 738.5 |  |  | 705.5 |  |  | 683.5 |  |  | 668.5 |  |  | 728.5 |  |  | 667.5 |  |  | 683.5 |  |  | 702.5 |  |  | 783 |  |  | 765 |  |  | 604.5 |  |  | 712.5 |  |  | 710.5 |  |  | 800 |  |  | 695.5 |  |  | 674.5 |  |  | 722.5 |  |  | 737.5 |  |  | 776 |  |  | 738.5 |  |  | 687.5 |  |  | 641.5 |  |  | 704.5 |  |  | 698 |  |  | 771.5 |  |  | 695.5 |  |  | 681 |  |  | 721.5 |  |  | 685.5 |  |  | 715.5 |  |  | 717.5 |  |  | 656.5 |  |  | 756.5 |  |  | 730 |  |  | 708 |  |  | 696.5 |  |  | 661.5 |  |  | 771.5 |  |  | 746.5 |  |  | 708.5 |  |  | 723.5 |  |  | 689 |  |  | 679.5 |  |  | 736.5 |  |  | 714.5 |  |  | 676.5 |  |  | 669 |  |  | 724.5 |  |  | 656 |  |  | 666.5 |  |  | 661.5 |  |  | 701.5 |  |  | 736.5 |  |  | 685.5 |  |  | 720.5 |  |  | 674 |  |  | 733.5 |  |  | 714.5 |  |  | 680.5 |  |  | 764.5 |  |  | 753.5 |  |  | 700 |  |  | 811.5 |  |  | 691.5 |  |  | 755.5 |  |  | 764.5 |  |  | 665.5 |  |  | 644.5 |  |  | 623.5 |  |  | 678.5 |  |  | 714 |  |  | 721.5 |  |  | 729.5 |  |  | 678.5 |  |  | 652.5 |  |  | 639.5 |  |  | 745 |  |  | 710.5 |  |  | 712.5 |  |  | 698 |  |  | 755.5 |  |  | 655.5 |  |  | 636.5 |  |  | 738.5 |  |  | 690.5 |  |  | 786.5 |  |  | 720 |  |  | 779.5 |  |  | 661.5 |  |  | 779.5 |  |  | 681.5 |  |  | 679.5 |  |  | 699.5 |  |  | 794 |  |  | 645 |  |  | 668.5 |  |  | 690.5 |  |  | 683.5 |  |  | 793 |  |  | 686.5 |  |  | 718.5 |  |  | 747.5 |  |  | 719.5 |  |  | 681.5 |  |  | 632.5 |  |  | 736 |  |  | 709.5 |  |  | 672.5 |  |  | 676.5 |  |  | 695.5 |  |  | 738.5 |  |  | 664.5 |  |  | 747.5 |  |  | 766.5 |  |  | 629.5 |  |  | 680.5 |  |  | 712.5 |  |  | 723.5 |  |  | 764.5 |  |  | 620 |  |  | 743.5 |  |  | 769.5 |  |  | 689 |  |  | 697.5 |  |  | 696.5 |  |  | 685.5 |  |  | 680.5 |  |  | 753.5 |  |  | 729.5 |  |  | 645.5 |  |  | 807.5 |  |  | 751.5 |  |  | 688.5 |  |  | 671 |  |  | 729.5 |  |  | 747.5 |  |  | 691 |  |  | 690.5 |  |  | 691 |  |  | 713.5 |  |  | 716.5 |  |  | 728.5 |  |  | 757.5 |  |  | 724.5 |  |  | 713.5 |  |  | 770.5 |  |  | 765.5 |  |  | 614.5 |  |  | 718.5 |  |  | 668.5 |  |  | 692.5 |  |  | 732.5 |  |  | 674.5 |  |  | 750 |  |  | 720 |  |  | 754 |  |  | 722.5 |  |  | 716 |  |  | 743.5 |  |  | 748.5 |  |  | 730.5 |  |  | 694.5 |  |  | 738.5 |  |  | 701 |  |  | 742 |  |  | 675 |  |  | 744.5 |  |  | 711.5 |  |  | 717.5 |  |  | 714.5 |  |  | 757.5 |  |  | 659.5 |  |  | 706.5 |  |  | 732.5 |  |  | 650.5 |  |  | 779.5 |  |  | 689.5 |  |  | 687.5 |  |  | 687.5 |  |  | 767 |  |  | 652.5 |  |  | 713.5 |  |  | 666.5 |  |  | 771.5 |  |  | 716 |  |  | 741.5 |  |  | 633.5 |  |  | 642.5 |  |  | 743 |  |  | 711 |  |  | 722 |  |  | 677.5 |  |  | 768.5 |  |  | 730.5 |  |  | 687 |  |  | 736.5 |  |  | 691.5 |  |  | 631.5 |  |  | 674.5 |  |  | 732.5 |  |  | 665 |  |  | 738.5 |  |  | 696.5 |  |  | 664.5 |  |  | 730 |  |  | 645.5 |  |  | 741.5 |  |  | 744.5 |  |  | 687.5 |  |  | 706.5 |  |  | 698 |  |  | 594.5 |  |  | 782.5 |  |  | 690 |  |  | 701.5 |  |  | 737 |  |  | 754 |  |  | 630 |  |  | 717 |  |  | 608.5 |  |  | 733.5 |  |  | 719 |  |  | 703.5 |  |  | 703.5 |  |  | 686.5 |  |  | 763.5 |  |  | 692.5 |  |  | 739.5 |  |  | 661.5 |  |  | 736.5 |  |  | 760 |  |  | 673 |  |  | 694.5 |  |  | 759.5 |  |  | 723.5 |  |  | 719.5 |  |  | 738.5 |  |  | 696 |  |  | 722.5 |  |  | 679.5 |  |  | 688.5 |  |  | 680.5 |  |  | 695.5 |  |  | 682 |  |  | 694 |  |  | 675.5 |  |  | 748 |  |  | 679.5 |  |  | 611.5 |  |  | 731.5 |  |  | 590 |  |  | 696.5 |  |  | 733.5 |  |  | 678 |  |  | 689.5 |  |  | 744.5 |  |  | 745.5 |  |  | 724.5 |  |  | 657.5 |  |  | 650 |  |  | 621.5 |  |  | 702.5 |  |  | 656.5 |  |  | 736.5 |  |  | 715.5 |  |  | 673.5 |  |  | 651.5 |  |  | 589.5 |  |  | 732 |  |  | 810.5 |  |  | 733 |  |  | 726 |  |  | 691.5 |  |  | 687 |  |  | 680.5 |  |  | 642.5 |  |  | 703 |  |  | 682.5 |  |  | 760 |  |  | 797.5 |  |  | 675.5 |  |  | 754.5 |  |  | 706 |  |  | 722.5 |  |  | 645.5 |  |  | 732 |  |  | 674.5 |  |  | 719.5 |  |  | 677 |  |  | 709.5 |  |  | 703.5 |  |  | 678 |  |  | 683.5 |  |  | 697 |  |  | 758.5 |  |  | 754 |  |  | 718 |  |  | 645.5 |  |  | 721.5 |  |  | 732 |  |  | 720.5 |  |  | 671.5 |  |  | 649 |  |  | 708 |  |  | 648.5 |  |  | 736 |  |  | 715.5 |  |  | 724.5 |  |  | 673.5 |  |  | 724.5 |  |  | 667.5 |  |  | 716.5 |  |  | 725 |  |  | 694 |  |  | 728.5 |  |  | 732.5 |  |  | 704.5 |  |  | 696.5 |  |  | 667.5 |  |  | 684.5 |  |  | 697.5 |  |  | 770.5 |  |  | 678.5 |  |  | 759 |  |  | 668 |  |  | 665.5 |  |  | 637 |  |  | 712.5 |  |  | 706 |  |  | 721.5 |  |  | 745.5 |  |  | 677 |  |  | 689.5 |  |  | 666.5 |  |  | 717.5 |  |  | 723.5 |  |  | 700 |  |  | 694.5 |  |  | 755 |  |  | 779.5 |  |  | 689.5 |  |  | 645.5 |  |  | 662.5 |  |  | 716.5 |  |  | 655.5 |  |  | 617.5 |  |  | 646.5 |  |  | 736 |  |  | 684.5 |  |  | 685.5 |  |  | 706 |  |  | 713.5 |  |  | 735.5 |  |  | 666.5 |  |  | 687.5 |  |  | 735.5 |  |  | 691.5 |  |  | 684.5 |  |  | 672.5 |  |  | 751.5 |  |  | 735 |  |  | 746 |  |  | 697.5 |  |  | 754.5 |  |  | 656.5 |  |  | 791 |  |  | 688.5 |  |  | 684.5 |  |  | 711.5 |  |  | 686.5 |  |  | 685.5 |  |  | 711 |  |  | 761.5 |  |  | 700 |  |  | 787.5 |  |  | 676.5 |  |  | 737.5 |  |  | 671.5 |  |  | 676 |  |  | 724.5 |  |  | 709.5 |  |  | 639.5 |  |  | 696.5 |  |  | 720.5 |  |  | 694.5 |  |  | 743.5 |  |  | 702.5 |  |  | 654 |  |  | 820.5 |  |  | 741.5 |  |  | 714.5 |  |  | 685 |  |  | 655 |  |  | 677 |  |  | 677.5 |  |  | 697 |  |  | 724.5 |  |  | 687.5 |  |  | 669.5 |  |  | 671.5 |  |  | 748 |  |  | 710.5 |  |  | 681.5 |  |  | 723 |  |  | 673.5 |  |  | 698.5 |  |  | 670 |  |  | 705.5 |  |  | 722.5 |  |  | 704.5 |  |  | 756 |  |  | 734 |  |  | 741 |  |  | 686.5 |  |  | 666.5 |  |  | 688.5 |  |  | 721.5 |  |  | 770 |  |  | 687.5 |  |  | 752 |  |  | 745.5 |  |  | 733 |  |  | 715.5 |  |  | 657.5 |  |  | 688.5 |  |  | 737 |  |  | 727.5 |  |  | 731.5 |  |  | 669.5 |  |  | 625.5 |  |  | 725 |  |  | 716.5 |  |  | 678.5 |  |  | 705.5 |  |  | 719.5 |  |  | 726 |  |  | 696.5 |  |  | 700.5 |  |  | 689 |  |  | 654.5 |  |  | 702.5 |  |  | 635 |  |  | 705.5 |  |  | 718.5 |  |  | 741.5 |  |  | 682 |  |  | 752.5 |  |  | 716 |  |  | 717.5 |  |  | 683.5 |  |  | 718 |  |  | 720.5 |  |  | 782.5 |  |  | 754.5 |  |  | 721.5 |  |  | 664 |  |  | 742.5 |  |  | 662.5 |  |  | 629.5 |  |  | 688 |  |  | 661 |  |  | 684.5 |  |  | 729 |  |  | 658.5 |  |  | 710 |  |  | 693.5 |  |  | 663.5 |  |  | 714.5 |  |  | 696.5 |  |  | 702.5 |  |  | 619.5 |  |  | 693.5 |  |  | 632.5 |  |  | 716 |  |  | 741.5 |  |  | 672.5 |  |  | 690.5 |  |  | 670 |  |  | 698 |  |  | 697.5 |  |  | 677.5 |  |  | 684.5 |  |  | 714.5 |  |  | 702.5 |  |  | 627.5 |  |  | 670.5 |  |  | 621.5 |  |  | 729.5 |  |  | 717.5 |  |  | 747.5 |  |  | 745.5 |  |  | 689.5 |  |  | 672.5 |  |  | 714.5 |  |  | 708.5 |  |  | 732
26 |  | 770.5 |  |  | 699.5 |  |  | 703.5 |  |  | 744.5 |  |  | 721.5 |  |  | 714.5 |  |  | 676.5 |  |  | 720.5 |  |  | 738 |  |  | 709 |  |  | 736.5 |  |  | 772.5 |  |  | 725.5 |  |  | 743 |  |  | 727 |  |  | 711.5 |  |  | 682.5 |  |  | 706.5 |  |  | 744.5 |  |  | 617 |  |  | 720.5 |  |  | 754 |  |  | 741.5 |  |  | 736.5 |  |  | 646 |  |  | 720.5 |  |  | 749.5 |  |  | 694.5 |  |  | 754.5 |  |  | 718.5 |  |  | 678.5 |  |  | 722 |  |  | 798.5 |  |  | 688 |  |  | 670.5 |  |  | 689 |  |  | 701.5 |  |  | 671.5 |  |  | 709.5 |  |  | 757.5 |  |  | 636 |  |  | 691.5 |  |  | 741 |  |  | 738.5 |  |  | 755 |  |  | 740.5 |  |  | 723.5 |  |  | 724.5 |  |  | 648.5 |  |  | 646 |  |  | 738 |  |  | 734 |  |  | 639 |  |  | 751.5 |  |  | 661.5 |  |  | 682.5 |  |  | 728.5 |  |  | 762.5 |  |  | 712.5 |  |  | 724 |  |  | 780 |  |  | 732.5 |  |  | 681.5 |  |  | 714.5 |  |  | 626.5 |  |  | 636 |  |  | 759.5 |  |  | 755 |  |  | 734.5 |  |  | 709 |  |  | 707.5 |  |  | 708.5 |  |  | 683.5 |  |  | 692.5 |  |  | 740.5 |  |  | 661.5 |  |  | 707.5 |  |  | 714 |  |  | 732 |  |  | 713.5 |  |  | 732.5 |  |  | 723.5 |  |  | 683.5 |  |  | 709.5 |  |  | 725 |  |  | 690.5 |  |  | 649.5 |  |  | 710.5 |  |  | 668.5 |  |  | 702 |  |  | 712 |  |  | 720.5 |  |  | 825.5 |  |  | 719.5 |  |  | 705 |  |  | 690 |  |  | 727 |  |  | 706.5 |  |  | 681.5 |  |  | 675 |  |  | 705.5 |  |  | 645.5 |  |  | 693 |  |  | 696 |  |  | 699.5 |  |  | 678 |  |  | 683 |  |  | 678.5 |  |  | 743.5 |  |  | 709.5 |  |  | 695.5 |  |  | 680 |  |  | 724.5 |  |  | 714.5 |  |  | 701.5 |  |  | 705.5 |  |  | 729.5 |  |  | 679.5 |  |  | 675.5 |  |  | 744 |  |  | 773.5 |  |  | 640.5 |  |  | 749.5 |  |  | 644.5 |  |  | 636.5 |  |  | 728.5 |  |  | 721.5 |  |  | 722.5 |  |  | 676.5 |  |  | 760.5 |  |  | 685.5 |  |  | 776 |  |  | 623 |  |  | 640.5 |  |  | 667.5 |  |  | 707.5 |  |  | 719.5 |  |  | 738 |  |  | 725.5 |  |  | 697.5 |  |  | 656.5 |  |  | 701.5 |  |  | 679.5 |  |  | 676.5 |  |  | 673 |  |  | 669.5 |  |  | 632.5 |  |  | 684.5 |  |  | 760.5 |  |  | 654.5 |  |  | 623.5 |  |  | 726.5 |  |  | 674 |  |  | 732 |  |  | 733.5 |  |  | 723.5 |  |  | 633.5 |  |  | 724.5 |  |  | 671.5 |  |  | 793 |  |  | 729.5 |  |  | 672.5 |  |  | 724.5 |  |  | 650.5 |  |  | 665 |  |  | 651.5 |  |  | 688.5 |  |  | 652 |  |  | 701 |  |  | 722.5 |  |  | 660.5 |  |  | 677.5 |  |  | 707.5 |  |  | 720.5 |  |  | 705 |  |  | 694.5 |  |  | 659.5 |  |  | 724.5 |  |  | 760.5 |  |  | 660.5 |  |  | 744.5 |  |  | 766.5 |  |  | 732.5 |  |  | 653.5 |  |  | 675 |  |  | 775.5 |  |  | 707.5 |  |  | 691.5 |  |  | 724.5 |  |  | 664.5 |  |  | 670.5 |  |  | 727 |  |  | 765 |  |  | 679.5 |  |  | 668.5 |  |  | 666.5 |  |  | 654 |  |  | 701.5 |  |  | 740.5 |  |  | 696 |  |  | 703 |  |  | 728.5 |  |  | 695.5 |  |  | 694.5 |  |  | 774 |  |  | 734.5 |  |  | 672.5 |  |  | 728.5 |  |  | 726.5 |  |  | 727.5 |  |  | 756.5 |  |  | 656.5 |  |  | 687 |  |  | 718.5 |  |  | 716.5 |  |  | 622.5 |  |  | 733.5 |  |  | 691.5 |  |  | 706.5 |  |  | 758.5 |  |  | 664.5 |  |  | 730.5 |  |  | 741 |  |  | 680 |  |  | 626.5 |  |  | 733.5 |  |  | 768.5 |  |  | 714.5 |  |  | 709.5 |  |  | 701.5 |  |  | 686 |  |  | 658 |  |  | 723.5 |  |  | 686.5 |  |  | 721.5 |  |  | 720.5 |  |  | 633 |  |  | 675.5 |  |  | 658 |  |  | 781.5 |  |  | 729.5 |  |  | 745.5 |  |  | 658.5 |  |  | 745.5 |  |  | 733 |  |  | 632 |  |  | 748.5 |  |  | 764 |  |  | 717 |  |  | 695.5 |  |  | 664.5 |  |  | 743 |  |  | 736.5 |  |  | 733 |  |  | 764.5 |  |  | 624.5 |  |  | 668.5 |  |  | 729.5 |  |  | 703.5 |  |  | 710.5 |  |  | 755.5 |  |  | 688.5 |  |  | 691 |  |  | 735 |  |  | 682.5 |  |  | 723 |  |  | 705.5 |  |  | 681.5 |  |  | 679 |  |  | 723.5 |  |  | 764.5 |  |  | 790 |  |  | 764.5 |  |  | 716.5 |  |  | 766.5 |  |  | 703 |  |  | 644 |  |  | 711.5 |  |  | 639.5 |  |  | 748.5 |  |  | 671.5 |  |  | 714 |  |  | 729.5 |  |  | 637.5 |  |  | 731 |  |  | 708.5 |  |  | 743 |  |  | 696.5 |  |  | 733.5 |  |  | 694.5 |  |  | 646.5 |  |  | 758 |  |  | 739.5 |  |  | 725 |  |  | 741 |  |  | 728.5 |  |  | 761.5 |  |  | 727 |  |  | 787.5 |  |  | 726 |  |  | 700.5 |  |  | 727 |  |  | 697.5 |  |  | 720.5 |  |  | 677.5 |  |  | 703.5 |  |  | 794.5 |  |  | 688.5 |  |  | 702.5 |  |  | 697 |  |  | 789.5 |  |  | 676.5 |  |  | 633.5 |  |  | 752.5 |  |  | 692 |  |  | 674.5 |  |  | 716.5 |  |  | 718.5 |  |  | 662.5 |  |  | 683.5 |  |  | 670.5 |  |  | 756.5 |  |  | 705.5 |  |  | 680.5 |  |  | 713.5 |  |  | 655.5 |  |  | 710.5 |  |  | 736.5 |  |  | 649.5 |  |  | 794 |  |  | 659 |  |  | 767 |  |  | 784.5 |  |  | 724.5 |  |  | 769.5 |  |  | 639.5 |  |  | 762.5 |  |  | 761.5 |  |  | 769.5 |  |  | 670.5 |  |  | 696.5 |  |  | 716.5 |  |  | 681.5 |  |  | 681.5 |  |  | 679.5 |  |  | 675 |  |  | 673.5 |  |  | 692.5 |  |  | 774 |  |  | 722 |  |  | 681.5 |  |  | 729 |  |  | 709.5 |  |  | 708.5 |  |  | 658 |  |  | 652.5 |  |  | 709.5 |  |  | 691 |  |  | 730.5 |  |  | 695.5 |  |  | 687.5 |  |  | 688.5 |  |  | 682 |  |  | 773.5 |  |  | 674.5 |  |  | 706 |  |  | 731.5 |  |  | 735 |  |  | 757.5 |  |  | 730.5 |  |  | 660.5 |  |  | 635.5 |  |  | 702.5 |  |  | 751.5 |  |  | 649.5 |  |  | 621.5 |  |  | 678.5 |  |  | 706.5 |  |  | 652.5 |  |  | 712 |  |  | 698 |  |  | 760.5 |  |  | 706 |  |  | 725.5 |  |  | 680.5 |  |  | 718.5 |  |  | 718.5 |  |  | 734.5 |  |  | 746.5 |  |  | 676.5 |  |  | 661.5 |  |  | 761 |  |  | 676 |  |  | 709.5 |  |  | 727.5 |  |  | 716.5 |  |  | 622.5 |  |  | 688.5 |  |  | 707.5 |  |  | 647.5 |  |  | 790.5 |  |  | 707.5 |  |  | 685.5 |  |  | 687.5 |  |  | 691.5 |  |  | 634.5 |  |  | 678.5 |  |  | 799.5 |  |  | 748.5 |  |  | 678 |  |  | 738.5 |  |  | 713.5 |  |  | 690.5 |  |  | 736.5 |  |  | 719 |  |  | 748.5 |  |  | 729.5 |  |  | 635.5 |  |  | 753.5 |  |  | 720.5 |  |  | 699.5 |  |  | 736.5 |  |  | 676.5 |  |  | 719.5 |  |  | 644.5 |  |  | 753.5 |  |  | 703 |  |  | 746 |  |  | 730.5 |  |  | 679.5 |  |  | 640 |  |  | 750.5 |  |  | 748.5 |  |  | 711 |  |  | 673.5 |  |  | 664 |  |  | 750.5 |  |  | 669 |  |  | 718.5 |  |  | 728.5 |  |  | 732 |  |  | 678.5 |  |  | 698 |  |  | 736.5 |  |  | 655.5 |  |  | 700 |  |  | 797.5 |  |  | 706.5 |  |  | 729.5 |  |  | 745.5 |  |  | 691.5 |  |  | 675.5 |  |  | 703.5 |  |  | 705.5 |  |  | 777 |  |  | 679.5 |  |  | 678.5 |  |  | 707.5 |  |  | 691 |  |  | 750.5 |  |  | 662.5 |  |  | 775.5 |  |  | 760.5 |  |  | 750.5 |  |  | 743.5 |  |  | 704.5 |  |  | 651.5 |  |  | 740 |  |  | 743.5 |  |  | 682.5 |  |  | 747 |  |  | 670.5 |  |  | 676 |  |  | 701.5 |  |  | 728 |  |  | 733 |  |  | 681 |  |  | 702.5 |  |  | 662.5 |  |  | 730.5 |  |  | 657.5 |  |  | 716.5 |  |  | 729.5 |  |  | 665.5 |  |  | 729.5 |  |  | 696 |  |  | 676.5 |  |  | 715.5 |  |  | 676.5 |  |  | 699.5 |  |  | 732 |  |  | 673.5 |  |  | 681.5 |  |  | 684.5 |  |  | 714.5 |  |  | 728.5 |  |  | 709 |  |  | 694.5 |  |  | 723.5 |  |  | 791.5 |  |  | 700.5 |  |  | 675.5 |  |  | 733.5 |  |  | 741.5 |  |  | 738.5 |  |  | 705.5 |  |  | 683.5 |  |  | 668.5 |  |  | 728.5 |  |  | 667.5 |  |  | 683.5 |  |  | 702.5 |  |  | 783 |  |  | 765 |  |  | 604.5 |  |  | 712.5 |  |  | 710.5 |  |  | 800 |  |  | 695.5 |  |  | 674.5 |  |  | 722.5 |  |  | 737.5 |  |  | 776 |  |  | 738.5 |  |  | 687.5 |  |  | 641.5 |  |  | 704.5 |  |  | 698 |  |  | 771.5 |  |  | 695.5 |  |  | 681 |  |  | 721.5 |  |  | 685.5 |  |  | 715.5 |  |  | 717.5 |  |  | 656.5 |  |  | 756.5 |  |  | 730 |  |  | 708 |  |  | 696.5 |  |  | 661.5 |  |  | 771.5 |  |  | 746.5 |  |  | 708.5 |  |  | 723.5 |  |  | 689 |  |  | 679.5 |  |  | 736.5 |  |  | 714.5 |  |  | 676.5 |  |  | 669 |  |  | 724.5 |  |  | 656 |  |  | 666.5 |  |  | 661.5 |  |  | 701.5 |  |  | 736.5 |  |  | 685.5 |  |  | 720.5 |  |  | 674 |  |  | 733.5 |  |  | 714.5 |  |  | 680.5 |  |  | 764.5 |  |  | 753.5 |  |  | 700 |  |  | 811.5 |  |  | 691.5 |  |  | 755.5 |  |  | 764.5 |  |  | 665.5 |  |  | 644.5 |  |  | 623.5 |  |  | 678.5 |  |  | 714 |  |  | 721.5 |  |  | 729.5 |  |  | 678.5 |  |  | 652.5 |  |  | 639.5 |  |  | 745 |  |  | 710.5 |  |  | 712.5 |  |  | 698 |  |  | 755.5 |  |  | 655.5 |  |  | 636.5 |  |  | 738.5 |  |  | 690.5 |  |  | 786.5 |  |  | 720 |  |  | 779.5 |  |  | 661.5 |  |  | 779.5 |  |  | 681.5 |  |  | 679.5 |  |  | 699.5 |  |  | 794 |  |  | 645 |  |  | 668.5 |  |  | 690.5 |  |  | 683.5 |  |  | 793 |  |  | 686.5 |  |  | 718.5 |  |  | 747.5 |  |  | 719.5 |  |  | 681.5 |  |  | 632.5 |  |  | 736 |  |  | 709.5 |  |  | 672.5 |  |  | 676.5 |  |  | 695.5 |  |  | 738.5 |  |  | 664.5 |  |  | 747.5 |  |  | 766.5 |  |  | 629.5 |  |  | 680.5 |  |  | 712.5 |  |  | 723.5 |  |  | 764.5 |  |  | 620 |  |  | 743.5 |  |  | 769.5 |  |  | 689 |  |  | 697.5 |  |  | 696.5 |  |  | 685.5 |  |  | 680.5 |  |  | 753.5 |  |  | 729.5 |  |  | 645.5 |  |  | 807.5 |  |  | 751.5 |  |  | 688.5 |  |  | 671 |  |  | 729.5 |  |  | 747.5 |  |  | 691 |  |  | 690.5 |  |  | 691 |  |  | 713.5 |  |  | 716.5 |  |  | 728.5 |  |  | 757.5 |  |  | 724.5 |  |  | 713.5 |  |  | 770.5 |  |  | 765.5 |  |  | 614.5 |  |  | 718.5 |  |  | 668.5 |  |  | 692.5 |  |  | 732.5 |  |  | 674.5 |  |  | 750 |  |  | 720 |  |  | 754 |  |  | 722.5 |  |  | 716 |  |  | 743.5 |  |  | 748.5 |  |  | 730.5 |  |  | 694.5 |  |  | 738.5 |  |  | 701 |  |  | 742 |  |  | 675 |  |  | 744.5 |  |  | 711.5 |  |  | 717.5 |  |  | 714.5 |  |  | 757.5 |  |  | 659.5 |  |  | 706.5 |  |  | 732.5 |  |  | 650.5 |  |  | 779.5 |  |  | 689.5 |  |  | 687.5 |  |  | 687.5 |  |  | 767 |  |  | 652.5 |  |  | 713.5 |  |  | 666.5 |  |  | 771.5 |  |  | 716 |  |  | 741.5 |  |  | 633.5 |  |  | 642.5 |  |  | 743 |  |  | 711 |  |  | 722 |  |  | 677.5 |  |  | 768.5 |  |  | 730.5 |  |  | 687 |  |  | 736.5 |  |  | 691.5 |  |  | 631.5 |  |  | 674.5 |  |  | 732.5 |  |  | 665 |  |  | 738.5 |  |  | 696.5 |  |  | 664.5 |  |  | 730 |  |  | 645.5 |  |  | 741.5 |  |  | 744.5 |  |  | 687.5 |  |  | 706.5 |  |  | 698 |  |  | 594.5 |  |  | 782.5 |  |  | 690 |  |  | 701.5 |  |  | 737 |  |  | 754 |  |  | 630 |  |  | 717 |  |  | 608.5 |  |  | 733.5 |  |  | 719 |  |  | 703.5 |  |  | 703.5 |  |  | 686.5 |  |  | 763.5 |  |  | 692.5 |  |  | 739.5 |  |  | 661.5 |  |  | 736.5 |  |  | 760 |  |  | 673 |  |  | 694.5 |  |  | 759.5 |  |  | 723.5 |  |  | 719.5 |  |  | 738.5 |  |  | 696 |  |  | 722.5 |  |  | 679.5 |  |  | 688.5 |  |  | 680.5 |  |  | 695.5 |  |  | 682 |  |  | 694 |  |  | 675.5 |  |  | 748 |  |  | 679.5 |  |  | 611.5 |  |  | 731.5 |  |  | 590 |  |  | 696.5 |  |  | 733.5 |  |  | 678 |  |  | 689.5 |  |  | 744.5 |  |  | 745.5 |  |  | 724.5 |  |  | 657.5 |  |  | 650 |  |  | 621.5 |  |  | 702.5 |  |  | 656.5 |  |  | 736.5 |  |  | 715.5 |  |  | 673.5 |  |  | 651.5 |  |  | 589.5 |  |  | 732 |  |  | 810.5 |  |  | 733 |  |  | 726 |  |  | 691.5 |  |  | 687 |  |  | 680.5 |  |  | 642.5 |  |  | 703 |  |  | 682.5 |  |  | 760 |  |  | 797.5 |  |  | 675.5 |  |  | 754.5 |  |  | 706 |  |  | 722.5 |  |  | 645.5 |  |  | 732 |  |  | 674.5 |  |  | 719.5 |  |  | 677 |  |  | 709.5 |  |  | 703.5 |  |  | 678 |  |  | 683.5 |  |  | 697 |  |  | 758.5 |  |  | 754 |  |  | 718 |  |  | 645.5 |  |  | 721.5 |  |  | 732 |  |  | 720.5 |  |  | 671.5 |  |  | 649 |  |  | 708 |  |  | 648.5 |  |  | 736 |  |  | 715.5 |  |  | 724.5 |  |  | 673.5 |  |  | 724.5 |  |  | 667.5 |  |  | 716.5 |  |  | 725 |  |  | 694 |  |  | 728.5 |  |  | 732.5 |  |  | 704.5 |  |  | 696.5 |  |  | 667.5 |  |  | 684.5 |  |  | 697.5 |  |  | 770.5 |  |  | 678.5 |  |  | 759 |  |  | 668 |  |  | 665.5 |  |  | 637 |  |  | 712.5 |  |  | 706 |  |  | 721.5 |  |  | 745.5 |  |  | 677 |  |  | 689.5 |  |  | 666.5 |  |  | 717.5 |  |  | 723.5 |  |  | 700 |  |  | 694.5 |  |  | 755 |  |  | 779.5 |  |  | 689.5 |  |  | 645.5 |  |  | 662.5 |  |  | 716.5 |  |  | 655.5 |  |  | 617.5 |  |  | 646.5 |  |  | 736 |  |  | 684.5 |  |  | 685.5 |  |  | 706 |  |  | 713.5 |  |  | 735.5 |  |  | 666.5 |  |  | 687.5 |  |  | 735.5 |  |  | 691.5 |  |  | 684.5 |  |  | 672.5 |  |  | 751.5 |  |  | 735 |  |  | 746 |  |  | 697.5 |  |  | 754.5 |  |  | 656.5 |  |  | 791 |  |  | 688.5 |  |  | 684.5 |  |  | 711.5 |  |  | 686.5 |  |  | 685.5 |  |  | 711 |  |  | 761.5 |  |  | 700 |  |  | 787.5 |  |  | 676.5 |  |  | 737.5 |  |  | 671.5 |  |  | 676 |  |  | 724.5 |  |  | 709.5 |  |  | 639.5 |  |  | 696.5 |  |  | 720.5 |  |  | 694.5 |  |  | 743.5 |  |  | 702.5 |  |  | 654 |  |  | 820.5 |  |  | 741.5 |  |  | 714.5 |  |  | 685 |  |  | 655 |  |  | 677 |  |  | 677.5 |  |  | 697 |  |  | 724.5 |  |  | 687.5 |  |  | 669.5 |  |  | 671.5 |  |  | 748 |  |  | 710.5 |  |  | 681.5 |  |  | 723 |  |  | 673.5 |  |  | 698.5 |  |  | 670 |  |  | 705.5 |  |  | 722.5 |  |  | 704.5 |  |  | 756 |  |  | 734 |  |  | 741 |  |  | 686.5 |  |  | 666.5 |  |  | 688.5 |  |  | 721.5 |  |  | 770 |  |  | 687.5 |  |  | 752 |  |  | 745.5 |  |  | 733 |  |  | 715.5 |  |  | 657.5 |  |  | 688.5 |  |  | 737 |  |  | 727.5 |  |  | 731.5 |  |  | 669.5 |  |  | 625.5 |  |  | 725 |  |  | 716.5 |  |  | 678.5 |  |  | 705.5 |  |  | 719.5 |  |  | 726 |  |  | 696.5 |  |  | 700.5 |  |  | 689 |  |  | 654.5 |  |  | 702.5 |  |  | 635 |  |  | 705.5 |  |  | 718.5 |  |  | 741.5 |  |  | 682 |  |  | 752.5 |  |  | 716 |  |  | 717.5 |  |  | 683.5 |  |  | 718 |  |  | 720.5 |  |  | 782.5 |  |  | 754.5 |  |  | 721.5 |  |  | 664 |  |  | 742.5 |  |  | 662.5 |  |  | 629.5 |  |  | 688 |  |  | 661 |  |  | 684.5 |  |  | 729 |  |  | 658.5 |  |  | 710 |  |  | 693.5 |  |  | 663.5 |  |  | 714.5 |  |  | 696.5 |  |  | 702.5 |  |  | 619.5 |  |  | 693.5 |  |  | 632.5 |  |  | 716 |  |  | 741.5 |  |  | 672.5 |  |  | 690.5 |  |  | 670 |  |  | 698 |  |  | 697.5 |  |  | 677.5 |  |  | 684.5 |  |  | 714.5 |  |  | 702.5 |  |  | 627.5 |  |  | 670.5 |  |  | 621.5 |  |  | 729.5 |  |  | 717.5 |  |  | 747.5 |  |  | 745.5 |  |  | 689.5 |  |  | 672.5 |  |  | 714.5 |  |  | 708.5 |  |  | 732
27 |  | 783.5 |  |  | 707 |  |  | 716.5 |  |  | 755 |  |  | 734.5 |  |  | 734 |  |  | 700 |  |  | 735 |  |  | 752.5 |  |  | 721 |  |  | 747 |  |  | 783 |  |  | 736 |  |  | 755 |  |  | 734.5 |  |  | 723.5 |  |  | 690 |  |  | 726 |  |  | 768 |  |  | 624.5 |  |  | 740 |  |  | 767 |  |  | 761 |  |  | 756 |  |  | 669.5 |  |  | 744 |  |  | 769 |  |  | 705 |  |  | 769 |  |  | 733 |  |  | 686 |  |  | 729.5 |  |  | 810.5 |  |  | 698.5 |  |  | 685 |  |  | 712.5 |  |  | 713.5 |  |  | 684.5 |  |  | 729 |  |  | 768 |  |  | 655.5 |  |  | 699 |  |  | 764.5 |  |  | 751.5 |  |  | 778.5 |  |  | 752.5 |  |  | 736.5 |  |  | 732 |  |  | 672 |  |  | 665.5 |  |  | 750 |  |  | 757.5 |  |  | 653.5 |  |  | 766 |  |  | 685 |  |  | 697 |  |  | 752 |  |  | 782 |  |  | 723 |  |  | 743.5 |  |  | 799.5 |  |  | 745.5 |  |  | 689 |  |  | 734 |  |  | 646 |  |  | 659.5 |  |  | 774 |  |  | 769.5 |  |  | 747.5 |  |  | 728.5 |  |  | 715 |  |  | 719 |  |  | 698 |  |  | 705.5 |  |  | 752.5 |  |  | 674.5 |  |  | 720.5 |  |  | 737.5 |  |  | 746.5 |  |  | 725.5 |  |  | 745.5 |  |  | 738 |  |  | 691 |  |  | 717 |  |  | 732.5 |  |  | 701 |  |  | 661.5 |  |  | 718 |  |  | 679 |  |  | 721.5 |  |  | 726.5 |  |  | 740 |  |  | 840 |  |  | 731.5 |  |  | 717 |  |  | 709.5 |  |  | 734.5 |  |  | 719.5 |  |  | 694.5 |  |  | 689.5 |  |  | 720 |  |  | 656 |  |  | 706 |  |  | 715.5 |  |  | 712.5 |  |  | 692.5 |  |  | 693.5 |  |  | 698 |  |  | 763 |  |  | 721.5 |  |  | 703 |  |  | 699.5 |  |  | 744 |  |  | 734 |  |  | 714.5 |  |  | 716 |  |  | 749 |  |  | 699 |  |  | 690 |  |  | 763.5 |  |  | 786.5 |  |  | 653.5 |  |  | 773 |  |  | 659 |  |  | 651 |  |  | 736 |  |  | 733.5 |  |  | 733 |  |  | 688.5 |  |  | 771 |  |  | 709 |  |  | 783.5 |  |  | 646.5 |  |  | 648 |  |  | 680.5 |  |  | 731 |  |  | 743 |  |  | 751 |  |  | 736 |  |  | 717 |  |  | 676 |  |  | 712 |  |  | 687 |  |  | 696 |  |  | 692.5 |  |  | 689 |  |  | 647 |  |  | 695 |  |  | 768 |  |  | 669 |  |  | 647 |  |  | 737 |  |  | 697.5 |  |  | 745 |  |  | 746.5 |  |  | 734 |  |  | 657 |  |  | 736.5 |  |  | 691 |  |  | 800.5 |  |  | 753 |  |  | 692 |  |  | 736.5 |  |  | 670 |  |  | 684.5 |  |  | 671 |  |  | 708 |  |  | 662.5 |  |  | 720.5 |  |  | 733 |  |  | 672.5 |  |  | 689.5 |  |  | 718 |  |  | 740 |  |  | 724.5 |  |  | 707.5 |  |  | 672.5 |  |  | 748 |  |  | 775 |  |  | 684 |  |  | 752 |  |  | 786 |  |  | 744.5 |  |  | 673 |  |  | 698.5 |  |  | 787.5 |  |  | 715 |  |  | 706 |  |  | 736.5 |  |  | 677.5 |  |  | 681 |  |  | 750.5 |  |  | 784.5 |  |  | 687 |  |  | 683 |  |  | 690 |  |  | 673.5 |  |  | 721 |  |  | 752.5 |  |  | 715.5 |  |  | 715 |  |  | 741.5 |  |  | 719 |  |  | 718 |  |  | 787 |  |  | 742 |  |  | 692 |  |  | 743 |  |  | 746 |  |  | 747 |  |  | 767 |  |  | 676 |  |  | 710.5 |  |  | 730.5 |  |  | 731 |  |  | 637 |  |  | 741 |  |  | 704.5 |  |  | 719.5 |  |  | 771.5 |  |  | 675 |  |  | 750 |  |  | 755.5 |  |  | 687.5 |  |  | 638.5 |  |  | 753 |  |  | 788 |  |  | 734 |  |  | 729 |  |  | 721 |  |  | 705.5 |  |  | 672.5 |  |  | 731 |  |  | 706 |  |  | 729 |  |  | 735 |  |  | 645 |  |  | 687.5 |  |  | 671 |  |  | 789 |  |  | 749 |  |  | 765 |  |  | 670.5 |  |  | 769 |  |  | 745 |  |  | 645 |  |  | 768 |  |  | 778.5 |  |  | 730 |  |  | 715 |  |  | 672 |  |  | 757.5 |  |  | 749.5 |  |  | 743.5 |  |  | 772 |  |  | 648 |  |  | 683 |  |  | 753 |  |  | 723 |  |  | 722.5 |  |  | 763 |  |  | 701.5 |  |  | 701.5 |  |  | 758.5 |  |  | 690 |  |  | 746.5 |  |  | 720 |  |  | 701 |  |  | 686.5 |  |  | 735.5 |  |  | 779 |  |  | 813.5 |  |  | 777.5 |  |  | 736 |  |  | 781 |  |  | 710.5 |  |  | 663.5 |  |  | 731 |  |  | 651.5 |  |  | 763 |  |  | 691 |  |  | 721.5 |  |  | 749 |  |  | 652 |  |  | 738.5 |  |  | 728 |  |  | 753.5 |  |  | 704 |  |  | 753 |  |  | 714 |  |  | 666 |  |  | 768.5 |  |  | 759 |  |  | 739.5 |  |  | 748.5 |  |  | 741.5 |  |  | 785 |  |  | 737.5 |  |  | 807 |  |  | 738 |  |  | 713.5 |  |  | 750.5 |  |  | 717 |  |  | 733.5 |  |  | 701 |  |  | 714 |  |  | 807.5 |  |  | 708 |  |  | 714.5 |  |  | 716.5 |  |  | 801.5 |  |  | 691 |  |  | 648 |  |  | 767 |  |  | 702.5 |  |  | 698 |  |  | 728.5 |  |  | 733 |  |  | 682 |  |  | 691 |  |  | 694 |  |  | 767 |  |  | 716 |  |  | 700 |  |  | 733 |  |  | 670 |  |  | 723.5 |  |  | 756 |  |  | 660 |  |  | 808.5 |  |  | 673.5 |  |  | 790.5 |  |  | 797.5 |  |  | 735 |  |  | 777 |  |  | 651.5 |  |  | 775.5 |  |  | 773.5 |  |  | 793 |  |  | 681 |  |  | 707 |  |  | 731 |  |  | 692 |  |  | 692 |  |  | 699 |  |  | 685.5 |  |  | 686.5 |  |  | 712 |  |  | 784.5 |  |  | 745.5 |  |  | 692 |  |  | 742 |  |  | 729 |  |  | 728 |  |  | 677.5 |  |  | 664.5 |  |  | 721.5 |  |  | 704 |  |  | 742.5 |  |  | 715 |  |  | 707 |  |  | 703 |  |  | 689.5 |  |  | 793 |  |  | 685 |  |  | 713.5 |  |  | 739 |  |  | 749.5 |  |  | 781 |  |  | 743.5 |  |  | 684 |  |  | 647.5 |  |  | 714.5 |  |  | 771 |  |  | 664 |  |  | 641 |  |  | 693 |  |  | 718.5 |  |  | 672 |  |  | 725 |  |  | 717.5 |  |  | 772.5 |  |  | 725.5 |  |  | 733 |  |  | 693.5 |  |  | 731.5 |  |  | 730.5 |  |  | 745 |  |  | 766 |  |  | 689.5 |  |  | 669 |  |  | 774 |  |  | 699.5 |  |  | 717 |  |  | 742 |  |  | 731 |  |  | 637 |  |  | 701.5 |  |  | 719.5 |  |  | 671 |  |  | 798 |  |  | 731 |  |  | 705 |  |  | 695 |  |  | 704.5 |  |  | 647.5 |  |  | 693 |  |  | 807 |  |  | 768 |  |  | 685.5 |  |  | 750.5 |  |  | 724 |  |  | 705 |  |  | 756 |  |  | 733.5 |  |  | 760.5 |  |  | 737 |  |  | 655 |  |  | 768 |  |  | 740 |  |  | 710 |  |  | 756 |  |  | 687 |  |  | 732.5 |  |  | 664 |  |  | 764 |  |  | 715 |  |  | 756.5 |  |  | 750 |  |  | 694 |  |  | 652 |  |  | 758 |  |  | 768 |  |  | 723 |  |  | 688 |  |  | 674.5 |  |  | 762.5 |  |  | 688.5 |  |  | 733 |  |  | 739 |  |  | 751.5 |  |  | 689 |  |  | 717.5 |  |  | 749.5 |  |  | 666 |  |  | 712 |  |  | 810.5 |  |  | 726 |  |  | 753 |  |  | 769 |  |  | 715 |  |  | 690 |  |  | 723 |  |  | 720 |  |  | 800.5 |  |  | 703 |  |  | 698 |  |  | 727 |  |  | 703 |  |  | 765 |  |  | 673 |  |  | 790 |  |  | 780 |  |  | 770 |  |  | 756.5 |  |  | 716.5 |  |  | 663.5 |  |  | 754.5 |  |  | 758 |  |  | 693 |  |  | 766.5 |  |  | 690 |  |  | 688 |  |  | 713.5 |  |  | 747.5 |  |  | 746 |  |  | 688.5 |  |  | 715.5 |  |  | 677 |  |  | 754 |  |  | 677 |  |  | 736 |  |  | 742.5 |  |  | 676 |  |  | 742.5 |  |  | 715.5 |  |  | 691 |  |  | 735 |  |  | 688.5 |  |  | 710 |  |  | 739.5 |  |  | 681 |  |  | 694.5 |  |  | 696.5 |  |  | 726.5 |  |  | 741.5 |  |  | 723.5 |  |  | 702 |  |  | 743 |  |  | 804.5 |  |  | 720 |  |  | 686 |  |  | 741 |  |  | 749 |  |  | 750.5 |  |  | 725 |  |  | 694 |  |  | 688 |  |  | 741.5 |  |  | 687 |  |  | 691 |  |  | 726 |  |  | 790.5 |  |  | 777 |  |  | 624 |  |  | 720 |  |  | 730 |  |  | 810.5 |  |  | 715 |  |  | 687.5 |  |  | 737 |  |  | 761 |  |  | 790.5 |  |  | 762 |  |  | 698 |  |  | 653.5 |  |  | 712 |  |  | 710 |  |  | 779 |  |  | 708.5 |  |  | 700.5 |  |  | 745 |  |  | 705 |  |  | 728.5 |  |  | 730.5 |  |  | 667 |  |  | 780 |  |  | 749.5 |  |  | 727.5 |  |  | 709.5 |  |  | 674.5 |  |  | 784.5 |  |  | 754 |  |  | 721.5 |  |  | 743 |  |  | 701 |  |  | 699 |  |  | 751 |  |  | 727.5 |  |  | 684 |  |  | 681 |  |  | 737.5 |  |  | 670.5 |  |  | 686 |  |  | 674.5 |  |  | 713.5 |  |  | 760 |  |  | 696 |  |  | 731 |  |  | 693.5 |  |  | 753 |  |  | 727.5 |  |  | 704 |  |  | 779 |  |  | 765.5 |  |  | 712 |  |  | 822 |  |  | 706 |  |  | 763 |  |  | 784 |  |  | 676 |  |  | 664 |  |  | 631 |  |  | 690.5 |  |  | 733.5 |  |  | 745 |  |  | 741.5 |  |  | 691.5 |  |  | 676 |  |  | 647 |  |  | 758 |  |  | 722.5 |  |  | 724.5 |  |  | 710 |  |  | 775 |  |  | 666 |  |  | 644 |  |  | 762 |  |  | 698 |  |  | 806 |  |  | 739.5 |  |  | 790 |  |  | 681 |  |  | 790 |  |  | 692 |  |  | 694 |  |  | 711.5 |  |  | 808.5 |  |  | 655.5 |  |  | 692 |  |  | 698 |  |  | 696.5 |  |  | 816.5 |  |  | 699.5 |  |  | 742 |  |  | 760.5 |  |  | 732.5 |  |  | 689 |  |  | 645.5 |  |  | 746.5 |  |  | 720 |  |  | 687 |  |  | 696 |  |  | 715 |  |  | 762 |  |  | 679 |  |  | 758 |  |  | 786 |  |  | 637 |  |  | 691 |  |  | 725.5 |  |  | 734 |  |  | 784 |  |  | 632 |  |  | 755.5 |  |  | 784 |  |  | 708.5 |  |  | 717 |  |  | 716 |  |  | 709 |  |  | 688 |  |  | 766.5 |  |  | 737 |  |  | 669 |  |  | 819.5 |  |  | 759 |  |  | 708 |  |  | 685.5 |  |  | 742.5 |  |  | 771 |  |  | 701.5 |  |  | 710 |  |  | 710.5 |  |  | 724 |  |  | 724 |  |  | 741.5 |  |  | 770.5 |  |  | 748 |  |  | 733 |  |  | 778 |  |  | 773 |  |  | 638 |  |  | 738 |  |  | 688 |  |  | 703 |  |  | 745.5 |  |  | 682 |  |  | 769.5 |  |  | 732 |  |  | 777.5 |  |  | 734.5 |  |  | 729 |  |  | 758 |  |  | 760.5 |  |  | 750 |  |  | 714 |  |  | 758 |  |  | 720.5 |  |  | 754 |  |  | 689.5 |  |  | 755 |  |  | 731 |  |  | 737 |  |  | 729 |  |  | 769.5 |  |  | 670 |  |  | 717 |  |  | 740 |  |  | 662.5 |  |  | 799 |  |  | 704 |  |  | 707 |  |  | 702 |  |  | 774.5 |  |  | 665.5 |  |  | 733 |  |  | 686 |  |  | 791 |  |  | 726.5 |  |  | 761 |  |  | 653 |  |  | 657 |  |  | 762.5 |  |  | 718.5 |  |  | 741.5 |  |  | 701 |  |  | 776 |  |  | 750 |  |  | 701.5 |  |  | 747 |  |  | 704.5 |  |  | 655 |  |  | 682 |  |  | 752 |  |  | 684.5 |  |  | 751.5 |  |  | 716 |  |  | 684 |  |  | 744.5 |  |  | 660 |  |  | 749 |  |  | 756.5 |  |  | 707 |  |  | 721 |  |  | 721.5 |  |  | 605 |  |  | 790 |  |  | 709.5 |  |  | 725 |  |  | 751.5 |  |  | 767 |  |  | 637.5 |  |  | 736.5 |  |  | 628 |  |  | 757 |  |  | 733.5 |  |  | 716.5 |  |  | 723 |  |  | 706 |  |  | 778 |  |  | 705.5 |  |  | 750 |  |  | 681 |  |  | 747 |  |  | 774.5 |  |  | 687.5 |  |  | 714 |  |  | 783 |  |  | 743 |  |  | 743 |  |  | 762 |  |  | 708 |  |  | 733 |  |  | 691.5 |  |  | 701.5 |  |  | 693.5 |  |  | 710 |  |  | 692.5 |  |  | 707 |  |  | 686 |  |  | 762.5 |  |  | 692.5 |  |  | 619 |  |  | 746 |  |  | 609.5 |  |  | 707 |  |  | 757 |  |  | 685.5 |  |  | 701.5 |  |  | 768 |  |  | 760 |  |  | 744 |  |  | 670.5 |  |  | 663 |  |  | 645 |  |  | 710 |  |  | 676 |  |  | 751 |  |  | 727.5 |  |  | 693 |  |  | 671 |  |  | 613 |  |  | 755.5 |  |  | 830 |  |  | 743.5 |  |  | 745.5 |  |  | 715 |  |  | 699 |  |  | 693.5 |  |  | 655.5 |  |  | 713.5 |  |  | 694.5 |  |  | 779.5 |  |  | 808 |  |  | 699 |  |  | 767.5 |  |  | 725.5 |  |  | 730 |  |  | 665 |  |  | 739.5 |  |  | 698 |  |  | 727 |  |  | 689 |  |  | 722.5 |  |  | 723 |  |  | 692.5 |  |  | 698 |  |  | 707.5 |  |  | 770.5 |  |  | 777.5 |  |  | 731 |  |  | 665 |  |  | 734.5 |  |  | 742.5 |  |  | 728 |  |  | 679 |  |  | 668.5 |  |  | 720 |  |  | 661.5 |  |  | 750.5 |  |  | 730 |  |  | 732 |  |  | 686.5 |  |  | 736.5 |  |  | 675 |  |  | 728.5 |  |  | 744.5 |  |  | 707 |  |  | 748 |  |  | 747 |  |  | 717.5 |  |  | 716 |  |  | 687 |  |  | 699 |  |  | 717 |  |  | 785 |  |  | 686 |  |  | 782.5 |  |  | 691.5 |  |  | 689 |  |  | 649 |  |  | 727 |  |  | 720.5 |  |  | 732 |  |  | 765 |  |  | 700.5 |  |  | 701.5 |  |  | 677 |  |  | 730.5 |  |  | 747 |  |  | 712 |  |  | 705 |  |  | 762.5 |  |  | 803 |  |  | 701.5 |  |  | 658.5 |  |  | 682 |  |  | 728.5 |  |  | 668.5 |  |  | 637 |  |  | 654 |  |  | 749 |  |  | 696.5 |  |  | 709 |  |  | 720.5 |  |  | 726.5 |  |  | 755 |  |  | 678.5 |  |  | 698 |  |  | 746 |  |  | 711 |  |  | 699 |  |  | 680 |  |  | 763.5 |  |  | 747 |  |  | 758 |  |  | 705 |  |  | 774 |  |  | 669.5 |  |  | 801.5 |  |  | 712 |  |  | 692 |  |  | 726 |  |  | 701 |  |  | 705 |  |  | 725.5 |  |  | 769 |  |  | 714.5 |  |  | 802 |  |  | 691 |  |  | 757 |  |  | 686 |  |  | 695.5 |  |  | 744 |  |  | 721.5 |  |  | 654 |  |  | 716 |  |  | 744 |  |  | 706.5 |  |  | 767 |  |  | 710 |  |  | 666 |  |  | 828 |  |  | 749 |  |  | 727.5 |  |  | 692.5 |  |  | 668 |  |  | 691.5 |  |  | 685 |  |  | 704.5 |  |  | 737.5 |  |  | 699.5 |  |  | 681.5 |  |  | 686 |  |  | 760 |  |  | 730 |  |  | 696 |  |  | 736 |  |  | 688 |  |  | 710.5 |  |  | 689.5 |  |  | 718.5 |  |  | 737 |  |  | 717.5 |  |  | 766.5 |  |  | 753.5 |  |  | 760.5 |  |  | 706 |  |  | 678.5 |  |  | 700.5 |  |  | 736 |  |  | 777.5 |  |  | 699.5 |  |  | 771.5 |  |  | 756 |  |  | 752.5 |  |  | 730 |  |  | 672 |  |  | 700.5 |  |  | 751.5 |  |  | 738 |  |  | 742 |  |  | 681.5 |  |  | 637.5 |  |  | 744.5 |  |  | 740 |  |  | 698 |  |  | 720 |  |  | 732.5 |  |  | 736.5 |  |  | 720 |  |  | 712.5 |  |  | 701 |  |  | 678 |  |  | 714.5 |  |  | 654.5 |  |  | 713 |  |  | 731.5 |  |  | 765 |  |  | 692.5 |  |  | 765.5 |  |  | 729 |  |  | 730.5 |  |  | 698 |  |  | 737.5 |  |  | 728 |  |  | 793 |  |  | 765 |  |  | 733.5 |  |  | 674.5 |  |  | 766 |  |  | 686 |  |  | 637 |  |  | 707.5 |  |  | 680.5 |  |  | 708 |  |  | 736.5 |  |  | 682 |  |  | 717.5 |  |  | 706.5 |  |  | 678 |  |  | 738 |  |  | 711 |  |  | 714.5 |  |  | 639 |  |  | 706.5 |  |  | 656 |  |  | 730.5 |  |  | 756 |  |  | 685.5 |  |  | 710 |  |  | 677.5 |  |  | 712.5 |  |  | 705 |  |  | 697 |  |  | 704 |  |  | 725 |  |  | 714.5 |  |  | 647 |  |  | 683.5 |  |  | 641 |  |  | 749 |  |  | 737 |  |  | 771 |  |  | 765 |  |  | 697 |  |  | 680 |  |  | 727.5 |  |  | 716 |  |  | 745
28 |  | 822.5 |  |  | 736 |  |  | 755.5 |  |  | 776 |  |  | 758.5 |  |  | 760 |  |  | 726 |  |  | 761 |  |  | 767.5 |  |  | 736 |  |  | 773 |  |  | 830 |  |  | 783 |  |  | 794 |  |  | 758.5 |  |  | 762.5 |  |  | 714 |  |  | 750 |  |  | 797 |  |  | 645.5 |  |  | 764 |  |  | 791 |  |  | 800 |  |  | 785 |  |  | 695.5 |  |  | 770 |  |  | 808 |  |  | 729 |  |  | 784 |  |  | 772 |  |  | 733 |  |  | 744.5 |  |  | 857.5 |  |  | 722.5 |  |  | 724 |  |  | 736.5 |  |  | 752.5 |  |  | 710.5 |  |  | 768 |  |  | 807 |  |  | 670.5 |  |  | 720 |  |  | 803.5 |  |  | 772.5 |  |  | 807.5 |  |  | 773.5 |  |  | 760.5 |  |  | 747 |  |  | 687 |  |  | 691.5 |  |  | 771 |  |  | 796.5 |  |  | 679.5 |  |  | 805 |  |  | 709 |  |  | 712 |  |  | 799 |  |  | 811 |  |  | 752 |  |  | 764.5 |  |  | 846.5 |  |  | 784.5 |  |  | 710 |  |  | 763 |  |  | 667 |  |  | 698.5 |  |  | 789 |  |  | 790.5 |  |  | 768.5 |  |  | 752.5 |  |  | 736 |  |  | 766 |  |  | 724 |  |  | 731.5 |  |  | 799.5 |  |  | 713.5 |  |  | 759.5 |  |  | 776.5 |  |  | 772.5 |  |  | 746.5 |  |  | 771.5 |  |  | 762 |  |  | 717 |  |  | 764 |  |  | 779.5 |  |  | 725 |  |  | 685.5 |  |  | 739 |  |  | 700 |  |  | 768.5 |  |  | 773.5 |  |  | 787 |  |  | 887 |  |  | 752.5 |  |  | 746 |  |  | 733.5 |  |  | 760.5 |  |  | 758.5 |  |  | 733.5 |  |  | 718.5 |  |  | 744 |  |  | 685 |  |  | 745 |  |  | 762.5 |  |  | 733.5 |  |  | 739.5 |  |  | 740.5 |  |  | 745 |  |  | 787 |  |  | 760.5 |  |  | 729 |  |  | 746.5 |  |  | 770 |  |  | 763 |  |  | 735.5 |  |  | 731 |  |  | 788 |  |  | 728 |  |  | 729 |  |  | 787.5 |  |  | 810.5 |  |  | 692.5 |  |  | 802 |  |  | 685 |  |  | 675 |  |  | 783 |  |  | 772.5 |  |  | 772 |  |  | 714.5 |  |  | 795 |  |  | 756 |  |  | 822.5 |  |  | 672.5 |  |  | 674 |  |  | 719.5 |  |  | 746 |  |  | 782 |  |  | 790 |  |  | 762 |  |  | 756 |  |  | 723 |  |  | 733 |  |  | 726 |  |  | 720 |  |  | 718.5 |  |  | 728 |  |  | 686 |  |  | 742 |  |  | 783 |  |  | 690 |  |  | 694 |  |  | 763 |  |  | 744.5 |  |  | 784 |  |  | 761.5 |  |  | 763 |  |  | 681 |  |  | 760.5 |  |  | 715 |  |  | 839.5 |  |  | 774 |  |  | 707 |  |  | 762.5 |  |  | 694 |  |  | 723.5 |  |  | 710 |  |  | 723 |  |  | 688.5 |  |  | 744.5 |  |  | 759 |  |  | 698.5 |  |  | 715.5 |  |  | 742 |  |  | 755 |  |  | 763.5 |  |  | 731.5 |  |  | 701.5 |  |  | 774 |  |  | 814 |  |  | 723 |  |  | 778 |  |  | 810 |  |  | 773.5 |  |  | 699 |  |  | 724.5 |  |  | 816.5 |  |  | 762 |  |  | 727 |  |  | 762.5 |  |  | 698.5 |  |  | 702 |  |  | 771.5 |  |  | 808.5 |  |  | 726 |  |  | 712 |  |  | 737 |  |  | 694.5 |  |  | 760 |  |  | 776.5 |  |  | 744.5 |  |  | 739 |  |  | 770.5 |  |  | 734 |  |  | 742 |  |  | 811 |  |  | 789 |  |  | 721 |  |  | 767 |  |  | 793 |  |  | 786 |  |  | 814 |  |  | 723 |  |  | 734.5 |  |  | 769.5 |  |  | 755 |  |  | 676 |  |  | 770 |  |  | 751.5 |  |  | 745.5 |  |  | 800.5 |  |  | 690 |  |  | 765 |  |  | 770.5 |  |  | 726.5 |  |  | 653.5 |  |  | 792 |  |  | 803 |  |  | 758 |  |  | 744 |  |  | 760 |  |  | 720.5 |  |  | 693.5 |  |  | 778 |  |  | 753 |  |  | 750 |  |  | 756 |  |  | 674 |  |  | 708.5 |  |  | 692 |  |  | 828 |  |  | 773 |  |  | 786 |  |  | 709.5 |  |  | 808 |  |  | 774 |  |  | 666 |  |  | 807 |  |  | 825.5 |  |  | 777 |  |  | 736 |  |  | 693 |  |  | 781.5 |  |  | 788.5 |  |  | 767.5 |  |  | 801 |  |  | 677 |  |  | 698 |  |  | 792 |  |  | 744 |  |  | 737.5 |  |  | 810 |  |  | 727.5 |  |  | 722.5 |  |  | 797.5 |  |  | 729 |  |  | 785.5 |  |  | 759 |  |  | 725 |  |  | 710.5 |  |  | 764.5 |  |  | 808 |  |  | 842.5 |  |  | 816.5 |  |  | 762 |  |  | 802 |  |  | 739.5 |  |  | 687.5 |  |  | 746 |  |  | 672.5 |  |  | 810 |  |  | 717 |  |  | 768.5 |  |  | 775 |  |  | 676 |  |  | 785.5 |  |  | 757 |  |  | 782.5 |  |  | 725 |  |  | 800 |  |  | 753 |  |  | 681 |  |  | 815.5 |  |  | 780 |  |  | 754.5 |  |  | 769.5 |  |  | 756.5 |  |  | 811 |  |  | 766.5 |  |  | 846 |  |  | 753 |  |  | 734.5 |  |  | 771.5 |  |  | 743 |  |  | 748.5 |  |  | 740 |  |  | 753 |  |  | 854.5 |  |  | 747 |  |  | 735.5 |  |  | 745.5 |  |  | 822.5 |  |  | 738 |  |  | 672 |  |  | 814 |  |  | 717.5 |  |  | 737 |  |  | 767.5 |  |  | 762 |  |  | 711 |  |  | 706 |  |  | 733 |  |  | 814 |  |  | 740 |  |  | 747 |  |  | 754 |  |  | 717 |  |  | 762.5 |  |  | 782 |  |  | 675 |  |  | 834.5 |  |  | 712.5 |  |  | 811.5 |  |  | 844.5 |  |  | 764 |  |  | 824 |  |  | 698.5 |  |  | 814.5 |  |  | 812.5 |  |  | 817 |  |  | 720 |  |  | 733 |  |  | 746 |  |  | 718 |  |  | 731 |  |  | 723 |  |  | 724.5 |  |  | 725.5 |  |  | 759 |  |  | 799.5 |  |  | 784.5 |  |  | 718 |  |  | 781 |  |  | 768 |  |  | 752 |  |  | 716.5 |  |  | 690.5 |  |  | 742.5 |  |  | 743 |  |  | 781.5 |  |  | 730 |  |  | 722 |  |  | 718 |  |  | 710.5 |  |  | 832 |  |  | 711 |  |  | 739.5 |  |  | 778 |  |  | 775.5 |  |  | 807 |  |  | 769.5 |  |  | 705 |  |  | 662.5 |  |  | 761.5 |  |  | 810 |  |  | 693 |  |  | 688 |  |  | 722 |  |  | 739.5 |  |  | 711 |  |  | 754 |  |  | 732.5 |  |  | 811.5 |  |  | 746.5 |  |  | 748 |  |  | 717.5 |  |  | 770.5 |  |  | 769.5 |  |  | 792 |  |  | 790 |  |  | 718.5 |  |  | 698 |  |  | 813 |  |  | 720.5 |  |  | 743 |  |  | 768 |  |  | 746 |  |  | 684 |  |  | 740.5 |  |  | 758.5 |  |  | 710 |  |  | 819 |  |  | 752 |  |  | 731 |  |  | 719 |  |  | 733.5 |  |  | 686.5 |  |  | 740 |  |  | 854 |  |  | 797 |  |  | 732.5 |  |  | 774.5 |  |  | 739 |  |  | 726 |  |  | 771 |  |  | 762.5 |  |  | 799.5 |  |  | 758 |  |  | 684 |  |  | 789 |  |  | 761 |  |  | 739 |  |  | 803 |  |  | 716 |  |  | 771.5 |  |  | 679 |  |  | 803 |  |  | 762 |  |  | 795.5 |  |  | 789 |  |  | 709 |  |  | 667 |  |  | 787 |  |  | 807 |  |  | 762 |  |  | 727 |  |  | 689.5 |  |  | 788.5 |  |  | 709.5 |  |  | 772 |  |  | 786 |  |  | 790.5 |  |  | 710 |  |  | 746.5 |  |  | 770.5 |  |  | 690 |  |  | 727 |  |  | 849.5 |  |  | 773 |  |  | 792 |  |  | 816 |  |  | 741 |  |  | 729 |  |  | 749 |  |  | 744 |  |  | 839.5 |  |  | 732 |  |  | 719 |  |  | 742 |  |  | 732 |  |  | 789 |  |  | 697 |  |  | 819 |  |  | 827 |  |  | 809 |  |  | 771.5 |  |  | 737.5 |  |  | 684.5 |  |  | 783.5 |  |  | 782 |  |  | 732 |  |  | 787.5 |  |  | 714 |  |  | 735 |  |  | 752.5 |  |  | 768.5 |  |  | 785 |  |  | 714.5 |  |  | 739.5 |  |  | 706 |  |  | 780 |  |  | 716 |  |  | 783 |  |  | 781.5 |  |  | 715 |  |  | 768.5 |  |  | 754.5 |  |  | 712 |  |  | 782 |  |  | 717.5 |  |  | 731 |  |  | 768.5 |  |  | 696 |  |  | 741.5 |  |  | 711.5 |  |  | 750.5 |  |  | 770.5 |  |  | 762.5 |  |  | 741 |  |  | 782 |  |  | 843.5 |  |  | 767 |  |  | 707 |  |  | 762 |  |  | 773 |  |  | 779.5 |  |  | 764 |  |  | 733 |  |  | 735 |  |  | 756.5 |  |  | 726 |  |  | 717 |  |  | 750 |  |  | 829.5 |  |  | 801 |  |  | 645 |  |  | 741 |  |  | 751 |  |  | 825.5 |  |  | 730 |  |  | 702.5 |  |  | 776 |  |  | 800 |  |  | 837.5 |  |  | 809 |  |  | 719 |  |  | 692.5 |  |  | 759 |  |  | 725 |  |  | 808 |  |  | 737.5 |  |  | 724.5 |  |  | 760 |  |  | 726 |  |  | 757.5 |  |  | 751.5 |  |  | 691 |  |  | 804 |  |  | 773.5 |  |  | 766.5 |  |  | 730.5 |  |  | 695.5 |  |  | 823.5 |  |  | 793 |  |  | 742.5 |  |  | 764 |  |  | 740 |  |  | 725 |  |  | 790 |  |  | 753.5 |  |  | 705 |  |  | 720 |  |  | 758.5 |  |  | 709.5 |  |  | 701 |  |  | 700.5 |  |  | 752.5 |  |  | 807 |  |  | 717 |  |  | 755 |  |  | 714.5 |  |  | 768 |  |  | 774.5 |  |  | 733 |  |  | 803 |  |  | 804.5 |  |  | 759 |  |  | 861 |  |  | 727 |  |  | 787 |  |  | 805 |  |  | 715 |  |  | 688 |  |  | 670 |  |  | 711.5 |  |  | 748.5 |  |  | 766 |  |  | 788.5 |  |  | 715.5 |  |  | 700 |  |  | 668 |  |  | 784 |  |  | 761.5 |  |  | 739.5 |  |  | 749 |  |  | 822 |  |  | 681 |  |  | 668 |  |  | 791 |  |  | 722 |  |  | 827 |  |  | 760.5 |  |  | 814 |  |  | 720 |  |  | 819 |  |  | 718 |  |  | 720 |  |  | 758.5 |  |  | 847.5 |  |  | 670.5 |  |  | 713 |  |  | 737 |  |  | 720.5 |  |  | 837.5 |  |  | 746.5 |  |  | 781 |  |  | 789.5 |  |  | 756.5 |  |  | 718 |  |  | 692.5 |  |  | 785.5 |  |  | 749 |  |  | 713 |  |  | 720 |  |  | 739 |  |  | 801 |  |  | 708 |  |  | 782 |  |  | 815 |  |  | 661 |  |  | 706 |  |  | 764.5 |  |  | 760 |  |  | 823 |  |  | 671 |  |  | 779.5 |  |  | 813 |  |  | 747.5 |  |  | 764 |  |  | 755 |  |  | 738 |  |  | 712 |  |  | 805.5 |  |  | 763 |  |  | 684 |  |  | 848.5 |  |  | 780 |  |  | 734 |  |  | 711.5 |  |  | 768.5 |  |  | 810 |  |  | 725.5 |  |  | 739 |  |  | 739.5 |  |  | 745 |  |  | 753 |  |  | 780.5 |  |  | 809.5 |  |  | 787 |  |  | 757 |  |  | 799 |  |  | 799 |  |  | 664 |  |  | 785 |  |  | 703 |  |  | 718 |  |  | 784.5 |  |  | 697 |  |  | 808.5 |  |  | 779 |  |  | 792.5 |  |  | 749.5 |  |  | 755 |  |  | 782 |  |  | 786.5 |  |  | 797 |  |  | 738 |  |  | 787 |  |  | 746.5 |  |  | 793 |  |  | 710.5 |  |  | 770 |  |  | 755 |  |  | 766 |  |  | 768 |  |  | 795.5 |  |  | 699 |  |  | 756 |  |  | 764 |  |  | 683.5 |  |  | 838 |  |  | 730 |  |  | 754 |  |  | 741 |  |  | 795.5 |  |  | 704.5 |  |  | 772 |  |  | 725 |  |  | 820 |  |  | 773.5 |  |  | 785 |  |  | 700 |  |  | 683 |  |  | 788.5 |  |  | 742.5 |  |  | 762.5 |  |  | 725 |  |  | 802 |  |  | 765 |  |  | 740.5 |  |  | 794 |  |  | 733.5 |  |  | 684 |  |  | 697 |  |  | 767 |  |  | 731.5 |  |  | 798.5 |  |  | 745 |  |  | 705 |  |  | 768.5 |  |  | 689 |  |  | 764 |  |  | 771.5 |  |  | 746 |  |  | 760 |  |  | 760.5 |  |  | 634 |  |  | 829 |  |  | 735.5 |  |  | 754 |  |  | 772.5 |  |  | 796 |  |  | 661.5 |  |  | 751.5 |  |  | 657 |  |  | 804 |  |  | 780.5 |  |  | 731.5 |  |  | 744 |  |  | 727 |  |  | 799 |  |  | 744.5 |  |  | 797 |  |  | 720 |  |  | 773 |  |  | 803.5 |  |  | 713.5 |  |  | 740 |  |  | 822 |  |  | 790 |  |  | 767 |  |  | 801 |  |  | 729 |  |  | 772 |  |  | 712.5 |  |  | 716.5 |  |  | 740.5 |  |  | 739 |  |  | 739.5 |  |  | 722 |  |  | 715 |  |  | 777.5 |  |  | 707.5 |  |  | 648 |  |  | 785 |  |  | 635.5 |  |  | 736 |  |  | 772 |  |  | 700.5 |  |  | 725.5 |  |  | 807 |  |  | 786 |  |  | 770 |  |  | 685.5 |  |  | 678 |  |  | 674 |  |  | 731 |  |  | 705 |  |  | 772 |  |  | 756.5 |  |  | 732 |  |  | 692 |  |  | 637 |  |  | 794.5 |  |  | 845 |  |  | 790.5 |  |  | 792.5 |  |  | 754 |  |  | 725 |  |  | 740.5 |  |  | 676.5 |  |  | 742.5 |  |  | 741.5 |  |  | 794.5 |  |  | 847 |  |  | 738 |  |  | 793.5 |  |  | 740.5 |  |  | 769 |  |  | 689 |  |  | 778.5 |  |  | 713 |  |  | 756 |  |  | 736 |  |  | 769.5 |  |  | 744 |  |  | 731.5 |  |  | 745 |  |  | 746.5 |  |  | 796.5 |  |  | 801.5 |  |  | 770 |  |  | 704 |  |  | 763.5 |  |  | 768.5 |  |  | 754 |  |  | 726 |  |  | 694.5 |  |  | 759 |  |  | 700.5 |  |  | 771.5 |  |  | 745 |  |  | 756 |  |  | 715.5 |  |  | 760.5 |  |  | 704 |  |  | 743.5 |  |  | 783.5 |  |  | 746 |  |  | 774 |  |  | 786 |  |  | 756.5 |  |  | 745 |  |  | 716 |  |  | 738 |  |  | 738 |  |  | 814 |  |  | 707 |  |  | 821.5 |  |  | 738.5 |  |  | 715 |  |  | 688 |  |  | 751 |  |  | 749.5 |  |  | 771 |  |  | 791 |  |  | 739.5 |  |  | 727.5 |  |  | 698 |  |  | 769.5 |  |  | 768 |  |  | 727 |  |  | 752 |  |  | 809.5 |  |  | 832 |  |  | 740.5 |  |  | 679.5 |  |  | 697 |  |  | 749.5 |  |  | 707.5 |  |  | 684 |  |  | 693 |  |  | 770 |  |  | 711.5 |  |  | 748 |  |  | 735.5 |  |  | 765.5 |  |  | 781 |  |  | 702.5 |  |  | 722 |  |  | 767 |  |  | 732 |  |  | 720 |  |  | 701 |  |  | 802.5 |  |  | 786 |  |  | 784 |  |  | 720 |  |  | 813 |  |  | 698.5 |  |  | 848.5 |  |  | 736 |  |  | 721 |  |  | 750 |  |  | 727 |  |  | 744 |  |  | 740.5 |  |  | 808 |  |  | 740.5 |  |  | 826 |  |  | 730 |  |  | 772 |  |  | 725 |  |  | 710.5 |  |  | 768 |  |  | 747.5 |  |  | 675 |  |  | 755 |  |  | 783 |  |  | 735.5 |  |  | 782 |  |  | 734 |  |  | 690 |  |  | 867 |  |  | 796 |  |  | 751.5 |  |  | 731.5 |  |  | 692 |  |  | 717.5 |  |  | 709 |  |  | 728.5 |  |  | 776.5 |  |  | 714.5 |  |  | 720.5 |  |  | 701 |  |  | 799 |  |  | 756 |  |  | 711 |  |  | 783 |  |  | 727 |  |  | 734.5 |  |  | 710.5 |  |  | 747.5 |  |  | 784 |  |  | 741.5 |  |  | 805.5 |  |  | 800.5 |  |  | 784.5 |  |  | 721 |  |  | 717.5 |  |  | 724.5 |  |  | 775 |  |  | 803.5 |  |  | 720.5 |  |  | 797.5 |  |  | 795 |  |  | 778.5 |  |  | 754 |  |  | 719 |  |  | 729.5 |  |  | 777.5 |  |  | 767 |  |  | 781 |  |  | 720.5 |  |  | 676.5 |  |  | 783.5 |  |  | 779 |  |  | 745 |  |  | 749 |  |  | 771.5 |  |  | 762.5 |  |  | 767 |  |  | 733.5 |  |  | 748 |  |  | 717 |  |  | 738.5 |  |  | 680.5 |  |  | 752 |  |  | 746.5 |  |  | 791 |  |  | 707.5 |  |  | 791.5 |  |  | 758 |  |  | 756.5 |  |  | 745 |  |  | 766.5 |  |  | 743 |  |  | 819 |  |  | 786 |  |  | 748.5 |  |  | 689.5 |  |  | 813 |  |  | 725 |  |  | 684 |  |  | 746.5 |  |  | 719.5 |  |  | 729 |  |  | 751.5 |  |  | 729 |  |  | 746.5 |  |  | 732.5 |  |  | 707 |  |  | 785 |  |  | 732 |  |  | 729.5 |  |  | 678 |  |  | 745.5 |  |  | 695 |  |  | 756.5 |  |  | 803 |  |  | 724.5 |  |  | 734 |  |  | 698.5 |  |  | 733.5 |  |  | 729 |  |  | 718 |  |  | 728 |  |  | 764 |  |  | 738.5 |  |  | 686 |  |  | 698.5 |  |  | 680 |  |  | 788 |  |  | 776 |  |  | 818 |  |  | 804 |  |  | 726 |  |  | 695 |  |  | 766.5 |  |  | 742 |  |  | 760
29 |  | 861.5 |  |  | 762 |  |  | 781.5 |  |  | 823 |  |  | 773.5 |  |  | 786 |  |  | 773 |  |  | 782 |  |  | 806.5 |  |  | 775 |  |  | 812 |  |  | 869 |  |  | 812 |  |  | 833 |  |  | 773.5 |  |  | 791.5 |  |  | 743 |  |  | 765 |  |  | 836 |  |  | 660.5 |  |  | 803 |  |  | 815 |  |  | 826 |  |  | 824 |  |  | 734.5 |  |  | 799 |  |  | 847 |  |  | 750 |  |  | 810 |  |  | 811 |  |  | 748 |  |  | 773.5 |  |  | 896.5 |  |  | 761.5 |  |  | 739 |  |  | 762.5 |  |  | 767.5 |  |  | 725.5 |  |  | 815 |  |  | 833 |  |  | 709.5 |  |  | 749 |  |  | 824.5 |  |  | 793.5 |  |  | 828.5 |  |  | 802.5 |  |  | 789.5 |  |  | 776 |  |  | 711 |  |  | 720.5 |  |  | 810 |  |  | 817.5 |  |  | 705.5 |  |  | 829 |  |  | 756 |  |  | 751 |  |  | 828 |  |  | 835 |  |  | 778 |  |  | 790.5 |  |  | 893.5 |  |  | 805.5 |  |  | 739 |  |  | 784 |  |  | 706 |  |  | 713.5 |  |  | 810 |  |  | 837.5 |  |  | 792.5 |  |  | 781.5 |  |  | 775 |  |  | 781 |  |  | 763 |  |  | 752.5 |  |  | 823.5 |  |  | 752.5 |  |  | 788.5 |  |  | 823.5 |  |  | 796.5 |  |  | 767.5 |  |  | 800.5 |  |  | 788 |  |  | 743 |  |  | 811 |  |  | 803.5 |  |  | 740 |  |  | 700.5 |  |  | 778 |  |  | 739 |  |  | 815.5 |  |  | 802.5 |  |  | 816 |  |  | 934 |  |  | 773.5 |  |  | 785 |  |  | 748.5 |  |  | 799.5 |  |  | 797.5 |  |  | 759.5 |  |  | 739.5 |  |  | 783 |  |  | 724 |  |  | 760 |  |  | 809.5 |  |  | 772.5 |  |  | 778.5 |  |  | 787.5 |  |  | 769 |  |  | 813 |  |  | 799.5 |  |  | 753 |  |  | 770.5 |  |  | 817 |  |  | 789 |  |  | 761.5 |  |  | 778 |  |  | 814 |  |  | 743 |  |  | 750 |  |  | 826.5 |  |  | 849.5 |  |  | 731.5 |  |  | 841 |  |  | 732 |  |  | 699 |  |  | 822 |  |  | 819.5 |  |  | 793 |  |  | 753.5 |  |  | 819 |  |  | 795 |  |  | 846.5 |  |  | 711.5 |  |  | 700 |  |  | 740.5 |  |  | 785 |  |  | 803 |  |  | 816 |  |  | 809 |  |  | 795 |  |  | 762 |  |  | 762 |  |  | 752 |  |  | 759 |  |  | 733.5 |  |  | 757 |  |  | 712 |  |  | 781 |  |  | 822 |  |  | 714 |  |  | 733 |  |  | 792 |  |  | 765.5 |  |  | 810 |  |  | 800.5 |  |  | 784 |  |  | 705 |  |  | 786.5 |  |  | 741 |  |  | 868.5 |  |  | 795 |  |  | 722 |  |  | 788.5 |  |  | 733 |  |  | 762.5 |  |  | 731 |  |  | 738 |  |  | 712.5 |  |  | 783.5 |  |  | 780 |  |  | 737.5 |  |  | 754.5 |  |  | 768 |  |  | 781 |  |  | 802.5 |  |  | 757.5 |  |  | 748.5 |  |  | 789 |  |  | 853 |  |  | 738 |  |  | 825 |  |  | 839 |  |  | 820.5 |  |  | 720 |  |  | 763.5 |  |  | 863.5 |  |  | 809 |  |  | 753 |  |  | 786.5 |  |  | 719.5 |  |  | 726 |  |  | 800.5 |  |  | 834.5 |  |  | 765 |  |  | 751 |  |  | 784 |  |  | 733.5 |  |  | 786 |  |  | 802.5 |  |  | 759.5 |  |  | 768 |  |  | 817.5 |  |  | 773 |  |  | 781 |  |  | 835 |  |  | 836 |  |  | 750 |  |  | 788 |  |  | 808 |  |  | 810 |  |  | 829 |  |  | 762 |  |  | 773.5 |  |  | 808.5 |  |  | 776 |  |  | 702 |  |  | 799 |  |  | 790.5 |  |  | 766.5 |  |  | 839.5 |  |  | 737 |  |  | 794 |  |  | 799.5 |  |  | 765.5 |  |  | 682.5 |  |  | 818 |  |  | 818 |  |  | 797 |  |  | 773 |  |  | 786 |  |  | 735.5 |  |  | 708.5 |  |  | 817 |  |  | 777 |  |  | 779 |  |  | 782 |  |  | 689 |  |  | 729.5 |  |  | 739 |  |  | 843 |  |  | 802 |  |  | 810 |  |  | 735.5 |  |  | 847 |  |  | 813 |  |  | 705 |  |  | 833 |  |  | 846.5 |  |  | 824 |  |  | 762 |  |  | 719 |  |  | 807.5 |  |  | 827.5 |  |  | 793.5 |  |  | 848 |  |  | 716 |  |  | 745 |  |  | 818 |  |  | 791 |  |  | 766.5 |  |  | 839 |  |  | 766.5 |  |  | 746.5 |  |  | 826.5 |  |  | 776 |  |  | 824.5 |  |  | 785 |  |  | 740 |  |  | 725.5 |  |  | 803.5 |  |  | 847 |  |  | 863.5 |  |  | 837.5 |  |  | 786 |  |  | 849 |  |  | 778.5 |  |  | 726.5 |  |  | 761 |  |  | 719.5 |  |  | 849 |  |  | 746 |  |  | 807.5 |  |  | 822 |  |  | 700 |  |  | 800.5 |  |  | 778 |  |  | 821.5 |  |  | 764 |  |  | 839 |  |  | 768 |  |  | 720 |  |  | 841.5 |  |  | 819 |  |  | 775.5 |  |  | 795.5 |  |  | 771.5 |  |  | 850 |  |  | 792.5 |  |  | 893 |  |  | 774 |  |  | 773.5 |  |  | 797.5 |  |  | 758 |  |  | 769.5 |  |  | 764 |  |  | 774 |  |  | 883.5 |  |  | 776 |  |  | 782.5 |  |  | 784.5 |  |  | 837.5 |  |  | 777 |  |  | 711 |  |  | 838 |  |  | 732.5 |  |  | 766 |  |  | 796.5 |  |  | 788 |  |  | 750 |  |  | 721 |  |  | 772 |  |  | 838 |  |  | 766 |  |  | 786 |  |  | 801 |  |  | 756 |  |  | 777.5 |  |  | 811 |  |  | 714 |  |  | 860.5 |  |  | 738.5 |  |  | 826.5 |  |  | 859.5 |  |  | 803 |  |  | 863 |  |  | 737.5 |  |  | 829.5 |  |  | 851.5 |  |  | 832 |  |  | 759 |  |  | 780 |  |  | 793 |  |  | 742 |  |  | 778 |  |  | 749 |  |  | 763.5 |  |  | 749.5 |  |  | 785 |  |  | 828.5 |  |  | 823.5 |  |  | 747 |  |  | 810 |  |  | 783 |  |  | 778 |  |  | 755.5 |  |  | 729.5 |  |  | 781.5 |  |  | 769 |  |  | 796.5 |  |  | 759 |  |  | 761 |  |  | 744 |  |  | 734.5 |  |  | 871 |  |  | 740 |  |  | 778.5 |  |  | 799 |  |  | 796.5 |  |  | 831 |  |  | 784.5 |  |  | 731 |  |  | 701.5 |  |  | 808.5 |  |  | 849 |  |  | 732 |  |  | 714 |  |  | 769 |  |  | 754.5 |  |  | 750 |  |  | 801 |  |  | 747.5 |  |  | 837.5 |  |  | 772.5 |  |  | 787 |  |  | 741.5 |  |  | 799.5 |  |  | 793.5 |  |  | 813 |  |  | 829 |  |  | 744.5 |  |  | 727 |  |  | 828 |  |  | 744.5 |  |  | 758 |  |  | 792 |  |  | 793 |  |  | 705 |  |  | 761.5 |  |  | 797.5 |  |  | 749 |  |  | 858 |  |  | 767 |  |  | 755 |  |  | 748 |  |  | 772.5 |  |  | 733.5 |  |  | 766 |  |  | 875 |  |  | 836 |  |  | 756.5 |  |  | 813.5 |  |  | 768 |  |  | 752 |  |  | 792 |  |  | 786.5 |  |  | 846.5 |  |  | 779 |  |  | 699 |  |  | 810 |  |  | 800 |  |  | 763 |  |  | 827 |  |  | 755 |  |  | 800.5 |  |  | 705 |  |  | 842 |  |  | 801 |  |  | 824.5 |  |  | 836 |  |  | 730 |  |  | 696 |  |  | 808 |  |  | 836 |  |  | 786 |  |  | 751 |  |  | 704.5 |  |  | 827.5 |  |  | 735.5 |  |  | 798 |  |  | 833 |  |  | 816.5 |  |  | 749 |  |  | 772.5 |  |  | 791.5 |  |  | 719 |  |  | 753 |  |  | 878.5 |  |  | 797 |  |  | 816 |  |  | 845 |  |  | 780 |  |  | 750 |  |  | 778 |  |  | 783 |  |  | 868.5 |  |  | 771 |  |  | 740 |  |  | 757 |  |  | 761 |  |  | 828 |  |  | 723 |  |  | 843 |  |  | 866 |  |  | 835 |  |  | 810.5 |  |  | 784.5 |  |  | 710.5 |  |  | 812.5 |  |  | 797 |  |  | 758 |  |  | 834.5 |  |  | 740 |  |  | 756 |  |  | 773.5 |  |  | 783.5 |  |  | 824 |  |  | 753.5 |  |  | 768.5 |  |  | 735 |  |  | 801 |  |  | 755 |  |  | 822 |  |  | 820.5 |  |  | 762 |  |  | 792.5 |  |  | 778.5 |  |  | 741 |  |  | 811 |  |  | 741.5 |  |  | 757 |  |  | 807.5 |  |  | 717 |  |  | 780.5 |  |  | 726.5 |  |  | 771.5 |  |  | 817.5 |  |  | 809.5 |  |  | 780 |  |  | 821 |  |  | 882.5 |  |  | 814 |  |  | 746 |  |  | 801 |  |  | 802 |  |  | 818.5 |  |  | 779 |  |  | 754 |  |  | 774 |  |  | 795.5 |  |  | 773 |  |  | 743 |  |  | 797 |  |  | 844.5 |  |  | 840 |  |  | 684 |  |  | 780 |  |  | 790 |  |  | 851.5 |  |  | 769 |  |  | 749.5 |  |  | 797 |  |  | 839 |  |  | 863.5 |  |  | 824 |  |  | 748 |  |  | 716.5 |  |  | 785 |  |  | 740 |  |  | 823 |  |  | 784.5 |  |  | 745.5 |  |  | 786 |  |  | 741 |  |  | 804.5 |  |  | 790.5 |  |  | 730 |  |  | 843 |  |  | 812.5 |  |  | 795.5 |  |  | 745.5 |  |  | 724.5 |  |  | 838.5 |  |  | 832 |  |  | 781.5 |  |  | 788 |  |  | 766 |  |  | 740 |  |  | 814 |  |  | 792.5 |  |  | 734 |  |  | 744 |  |  | 805.5 |  |  | 738.5 |  |  | 716 |  |  | 747.5 |  |  | 781.5 |  |  | 828 |  |  | 756 |  |  | 770 |  |  | 729.5 |  |  | 789 |  |  | 813.5 |  |  | 772 |  |  | 842 |  |  | 833.5 |  |  | 785 |  |  | 900 |  |  | 756 |  |  | 808 |  |  | 826 |  |  | 730 |  |  | 727 |  |  | 717 |  |  | 735.5 |  |  | 795.5 |  |  | 813 |  |  | 814.5 |  |  | 736.5 |  |  | 747 |  |  | 683 |  |  | 808 |  |  | 785.5 |  |  | 778.5 |  |  | 764 |  |  | 869 |  |  | 710 |  |  | 694 |  |  | 806 |  |  | 737 |  |  | 853 |  |  | 781.5 |  |  | 829 |  |  | 759 |  |  | 858 |  |  | 744 |  |  | 749 |  |  | 787.5 |  |  | 876.5 |  |  | 699.5 |  |  | 728 |  |  | 766 |  |  | 746.5 |  |  | 852.5 |  |  | 775.5 |  |  | 810 |  |  | 810.5 |  |  | 803.5 |  |  | 733 |  |  | 716.5 |  |  | 824.5 |  |  | 778 |  |  | 752 |  |  | 735 |  |  | 765 |  |  | 830 |  |  | 723 |  |  | 808 |  |  | 862 |  |  | 700 |  |  | 730 |  |  | 803.5 |  |  | 775 |  |  | 852 |  |  | 710 |  |  | 818.5 |  |  | 828 |  |  | 776.5 |  |  | 803 |  |  | 776 |  |  | 777 |  |  | 751 |  |  | 829.5 |  |  | 789 |  |  | 710 |  |  | 887.5 |  |  | 827 |  |  | 773 |  |  | 726.5 |  |  | 794.5 |  |  | 839 |  |  | 749.5 |  |  | 760 |  |  | 778.5 |  |  | 792 |  |  | 777 |  |  | 819.5 |  |  | 848.5 |  |  | 826 |  |  | 786 |  |  | 820 |  |  | 814 |  |  | 688 |  |  | 824 |  |  | 742 |  |  | 739 |  |  | 799.5 |  |  | 723 |  |  | 834.5 |  |  | 803 |  |  | 807.5 |  |  | 773.5 |  |  | 781 |  |  | 821 |  |  | 825.5 |  |  | 826 |  |  | 767 |  |  | 808 |  |  | 785.5 |  |  | 832 |  |  | 736.5 |  |  | 796 |  |  | 794 |  |  | 792 |  |  | 794 |  |  | 842.5 |  |  | 728 |  |  | 795 |  |  | 788 |  |  | 704.5 |  |  | 877 |  |  | 754 |  |  | 780 |  |  | 762 |  |  | 819.5 |  |  | 730.5 |  |  | 796 |  |  | 751 |  |  | 841 |  |  | 799.5 |  |  | 814 |  |  | 724 |  |  | 712 |  |  | 827.5 |  |  | 781.5 |  |  | 801.5 |  |  | 751 |  |  | 828 |  |  | 804 |  |  | 787.5 |  |  | 815 |  |  | 759.5 |  |  | 705 |  |  | 744 |  |  | 782 |  |  | 778.5 |  |  | 822.5 |  |  | 771 |  |  | 726 |  |  | 794.5 |  |  | 715 |  |  | 779 |  |  | 795.5 |  |  | 761 |  |  | 786 |  |  | 799.5 |  |  | 658 |  |  | 844 |  |  | 750.5 |  |  | 769 |  |  | 793.5 |  |  | 835 |  |  | 708.5 |  |  | 790.5 |  |  | 704 |  |  | 843 |  |  | 806.5 |  |  | 770.5 |  |  | 770 |  |  | 774 |  |  | 814 |  |  | 768.5 |  |  | 836 |  |  | 744 |  |  | 788 |  |  | 818.5 |  |  | 752.5 |  |  | 779 |  |  | 869 |  |  | 829 |  |  | 796 |  |  | 827 |  |  | 768 |  |  | 811 |  |  | 751.5 |  |  | 755.5 |  |  | 761.5 |  |  | 754 |  |  | 778.5 |  |  | 769 |  |  | 744 |  |  | 824.5 |  |  | 722.5 |  |  | 663 |  |  | 824 |  |  | 656.5 |  |  | 765 |  |  | 787 |  |  | 715.5 |  |  | 764.5 |  |  | 833 |  |  | 807 |  |  | 817 |  |  | 709.5 |  |  | 704 |  |  | 713 |  |  | 757 |  |  | 720 |  |  | 796 |  |  | 785.5 |  |  | 771 |  |  | 731 |  |  | 684 |  |  | 809.5 |  |  | 871 |  |  | 814.5 |  |  | 813.5 |  |  | 775 |  |  | 772 |  |  | 787.5 |  |  | 715.5 |  |  | 781.5 |  |  | 780.5 |  |  | 818.5 |  |  | 862 |  |  | 777 |  |  | 814.5 |  |  | 779.5 |  |  | 793 |  |  | 713 |  |  | 793.5 |  |  | 752 |  |  | 771 |  |  | 765 |  |  | 784.5 |  |  | 773 |  |  | 755.5 |  |  | 784 |  |  | 793.5 |  |  | 825.5 |  |  | 830.5 |  |  | 796 |  |  | 743 |  |  | 802.5 |  |  | 783.5 |  |  | 778 |  |  | 765 |  |  | 741.5 |  |  | 785 |  |  | 739.5 |  |  | 810.5 |  |  | 784 |  |  | 771 |  |  | 741.5 |  |  | 799.5 |  |  | 730 |  |  | 782.5 |  |  | 809.5 |  |  | 770 |  |  | 795 |  |  | 833 |  |  | 795.5 |  |  | 784 |  |  | 755 |  |  | 764 |  |  | 777 |  |  | 835 |  |  | 736 |  |  | 847.5 |  |  | 785.5 |  |  | 754 |  |  | 709 |  |  | 775 |  |  | 788.5 |  |  | 792 |  |  | 830 |  |  | 763.5 |  |  | 766.5 |  |  | 727 |  |  | 795.5 |  |  | 807 |  |  | 756 |  |  | 799 |  |  | 830.5 |  |  | 871 |  |  | 769.5 |  |  | 726.5 |  |  | 723 |  |  | 788.5 |  |  | 731.5 |  |  | 713 |  |  | 732 |  |  | 796 |  |  | 750.5 |  |  | 769 |  |  | 756.5 |  |  | 804.5 |  |  | 810 |  |  | 731.5 |  |  | 769 |  |  | 782 |  |  | 753 |  |  | 735 |  |  | 740 |  |  | 826.5 |  |  | 815 |  |  | 813 |  |  | 744 |  |  | 860 |  |  | 727.5 |  |  | 874.5 |  |  | 765 |  |  | 736 |  |  | 776 |  |  | 753 |  |  | 783 |  |  | 779.5 |  |  | 837 |  |  | 779.5 |  |  | 865 |  |  | 751 |  |  | 787 |  |  | 754 |  |  | 736.5 |  |  | 797 |  |  | 768.5 |  |  | 699 |  |  | 781 |  |  | 822 |  |  | 764.5 |  |  | 797 |  |  | 760 |  |  | 705 |  |  | 906 |  |  | 843 |  |  | 766.5 |  |  | 770.5 |  |  | 718 |  |  | 738.5 |  |  | 735 |  |  | 743.5 |  |  | 815.5 |  |  | 753.5 |  |  | 759.5 |  |  | 740 |  |  | 823 |  |  | 771 |  |  | 737 |  |  | 809 |  |  | 774 |  |  | 763.5 |  |  | 757.5 |  |  | 773.5 |  |  | 823 |  |  | 788.5 |  |  | 844.5 |  |  | 821.5 |  |  | 805.5 |  |  | 745 |  |  | 746.5 |  |  | 750.5 |  |  | 790 |  |  | 829.5 |  |  | 759.5 |  |  | 823.5 |  |  | 816 |  |  | 817.5 |  |  | 780 |  |  | 758 |  |  | 768.5 |  |  | 816.5 |  |  | 782 |  |  | 796 |  |  | 735.5 |  |  | 715.5 |  |  | 830.5 |  |  | 808 |  |  | 766 |  |  | 778 |  |  | 786.5 |  |  | 791.5 |  |  | 782 |  |  | 772.5 |  |  | 763 |  |  | 756 |  |  | 767.5 |  |  | 727.5 |  |  | 776 |  |  | 785.5 |  |  | 817 |  |  | 731.5 |  |  | 815.5 |  |  | 787 |  |  | 771.5 |  |  | 792 |  |  | 805.5 |  |  | 767 |  |  | 848 |  |  | 801 |  |  | 774.5 |  |  | 736.5 |  |  | 828 |  |  | 749 |  |  | 723 |  |  | 772.5 |  |  | 734.5 |  |  | 753 |  |  | 780.5 |  |  | 768 |  |  | 761.5 |  |  | 771.5 |  |  | 722 |  |  | 800 |  |  | 771 |  |  | 753.5 |  |  | 702 |  |  | 792.5 |  |  | 742 |  |  | 785.5 |  |  | 818 |  |  | 748.5 |  |  | 755 |  |  | 719.5 |  |  | 757.5 |  |  | 768 |  |  | 757 |  |  | 752 |  |  | 779 |  |  | 767.5 |  |  | 733 |  |  | 722.5 |  |  | 709 |  |  | 814 |  |  | 800 |  |  | 839 |  |  | 828 |  |  | 773 |  |  | 734 |  |  | 790.5 |  |  | 757 |  |  | 807
30 |  | 885.5 |  |  | 786 |  |  | 820.5 |  |  | 844 |  |  | 788.5 |  |  | 812 |  |  | 797 |  |  | 821 |  |  | 845.5 |  |  | 814 |  |  | 836 |  |  | 895 |  |  | 841 |  |  | 862 |  |  | 794.5 |  |  | 830.5 |  |  | 782 |  |  | 789 |  |  | 857 |  |  | 707.5 |  |  | 832 |  |  | 854 |  |  | 852 |  |  | 848 |  |  | 760.5 |  |  | 825 |  |  | 894 |  |  | 776 |  |  | 834 |  |  | 840 |  |  | 763 |  |  | 799.5 |  |  | 935.5 |  |  | 787.5 |  |  | 786 |  |  | 777.5 |  |  | 788.5 |  |  | 764.5 |  |  | 854 |  |  | 848 |  |  | 748.5 |  |  | 788 |  |  | 863.5 |  |  | 817.5 |  |  | 867.5 |  |  | 826.5 |  |  | 815.5 |  |  | 800 |  |  | 758 |  |  | 735.5 |  |  | 857 |  |  | 838.5 |  |  | 720.5 |  |  | 876 |  |  | 780 |  |  | 766 |  |  | 867 |  |  | 882 |  |  | 804 |  |  | 819.5 |  |  | 932.5 |  |  | 826.5 |  |  | 760 |  |  | 810 |  |  | 745 |  |  | 742.5 |  |  | 825 |  |  | 884.5 |  |  | 807.5 |  |  | 820.5 |  |  | 801 |  |  | 820 |  |  | 778 |  |  | 767.5 |  |  | 852.5 |  |  | 799.5 |  |  | 814.5 |  |  | 849.5 |  |  | 820.5 |  |  | 814.5 |  |  | 839.5 |  |  | 827 |  |  | 758 |  |  | 858 |  |  | 829.5 |  |  | 779 |  |  | 747.5 |  |  | 817 |  |  | 763 |  |  | 854.5 |  |  | 826.5 |  |  | 837 |  |  | 963 |  |  | 799.5 |  |  | 824 |  |  | 787.5 |  |  | 828.5 |  |  | 823.5 |  |  | 780.5 |  |  | 768.5 |  |  | 822 |  |  | 763 |  |  | 789 |  |  | 838.5 |  |  | 787.5 |  |  | 807.5 |  |  | 816.5 |  |  | 795 |  |  | 837 |  |  | 814.5 |  |  | 774 |  |  | 796.5 |  |  | 841 |  |  | 836 |  |  | 790.5 |  |  | 817 |  |  | 843 |  |  | 782 |  |  | 776 |  |  | 850.5 |  |  | 873.5 |  |  | 755.5 |  |  | 867 |  |  | 756 |  |  | 725 |  |  | 837 |  |  | 840.5 |  |  | 832 |  |  | 800.5 |  |  | 848 |  |  | 819 |  |  | 867.5 |  |  | 737.5 |  |  | 721 |  |  | 766.5 |  |  | 824 |  |  | 818 |  |  | 845 |  |  | 848 |  |  | 810 |  |  | 788 |  |  | 786 |  |  | 778 |  |  | 780 |  |  | 780.5 |  |  | 772 |  |  | 751 |  |  | 802 |  |  | 837 |  |  | 743 |  |  | 780 |  |  | 839 |  |  | 804.5 |  |  | 849 |  |  | 824.5 |  |  | 823 |  |  | 726 |  |  | 825.5 |  |  | 767 |  |  | 892.5 |  |  | 816 |  |  | 743 |  |  | 814.5 |  |  | 748 |  |  | 786.5 |  |  | 752 |  |  | 785 |  |  | 733.5 |  |  | 812.5 |  |  | 827 |  |  | 784.5 |  |  | 783.5 |  |  | 794 |  |  | 810 |  |  | 828.5 |  |  | 796.5 |  |  | 769.5 |  |  | 810 |  |  | 879 |  |  | 762 |  |  | 854 |  |  | 854 |  |  | 867.5 |  |  | 767 |  |  | 784.5 |  |  | 889.5 |  |  | 848 |  |  | 782 |  |  | 812.5 |  |  | 740.5 |  |  | 752 |  |  | 821.5 |  |  | 855.5 |  |  | 812 |  |  | 798 |  |  | 823 |  |  | 748.5 |  |  | 833 |  |  | 841.5 |  |  | 798.5 |  |  | 797 |  |  | 838.5 |  |  | 802 |  |  | 828 |  |  | 856 |  |  | 860 |  |  | 789 |  |  | 817 |  |  | 855 |  |  | 849 |  |  | 868 |  |  | 801 |  |  | 820.5 |  |  | 834.5 |  |  | 791 |  |  | 717 |  |  | 846 |  |  | 829.5 |  |  | 813.5 |  |  | 860.5 |  |  | 766 |  |  | 815 |  |  | 838.5 |  |  | 786.5 |  |  | 711.5 |  |  | 842 |  |  | 865 |  |  | 818 |  |  | 812 |  |  | 810 |  |  | 761.5 |  |  | 729.5 |  |  | 843 |  |  | 816 |  |  | 808 |  |  | 811 |  |  | 736 |  |  | 758.5 |  |  | 778 |  |  | 882 |  |  | 826 |  |  | 834 |  |  | 756.5 |  |  | 871 |  |  | 852 |  |  | 744 |  |  | 862 |  |  | 885.5 |  |  | 863 |  |  | 783 |  |  | 740 |  |  | 846.5 |  |  | 856.5 |  |  | 817.5 |  |  | 895 |  |  | 763 |  |  | 774 |  |  | 865 |  |  | 817 |  |  | 792.5 |  |  | 878 |  |  | 795.5 |  |  | 785.5 |  |  | 865.5 |  |  | 802 |  |  | 853.5 |  |  | 824 |  |  | 779 |  |  | 764.5 |  |  | 842.5 |  |  | 886 |  |  | 902.5 |  |  | 884.5 |  |  | 815 |  |  | 873 |  |  | 804.5 |  |  | 773.5 |  |  | 808 |  |  | 766.5 |  |  | 888 |  |  | 772 |  |  | 854.5 |  |  | 837 |  |  | 724 |  |  | 839.5 |  |  | 799 |  |  | 868.5 |  |  | 803 |  |  | 865 |  |  | 807 |  |  | 741 |  |  | 862.5 |  |  | 858 |  |  | 822.5 |  |  | 834.5 |  |  | 810.5 |  |  | 871 |  |  | 831.5 |  |  | 932 |  |  | 821 |  |  | 788.5 |  |  | 836.5 |  |  | 805 |  |  | 784.5 |  |  | 803 |  |  | 821 |  |  | 904.5 |  |  | 791 |  |  | 803.5 |  |  | 823.5 |  |  | 863.5 |  |  | 816 |  |  | 735 |  |  | 877 |  |  | 753.5 |  |  | 813 |  |  | 825.5 |  |  | 809 |  |  | 771 |  |  | 742 |  |  | 798 |  |  | 864 |  |  | 795 |  |  | 801 |  |  | 848 |  |  | 795 |  |  | 792.5 |  |  | 835 |  |  | 738 |  |  | 899.5 |  |  | 767.5 |  |  | 841.5 |  |  | 888.5 |  |  | 829 |  |  | 878 |  |  | 758.5 |  |  | 876.5 |  |  | 872.5 |  |  | 871 |  |  | 780 |  |  | 819 |  |  | 832 |  |  | 771 |  |  | 817 |  |  | 788 |  |  | 787.5 |  |  | 788.5 |  |  | 824 |  |  | 852.5 |  |  | 838.5 |  |  | 794 |  |  | 849 |  |  | 822 |  |  | 799 |  |  | 781.5 |  |  | 753.5 |  |  | 810.5 |  |  | 784 |  |  | 822.5 |  |  | 806 |  |  | 808 |  |  | 773 |  |  | 758.5 |  |  | 895 |  |  | 755 |  |  | 807.5 |  |  | 820 |  |  | 825.5 |  |  | 857 |  |  | 823.5 |  |  | 770 |  |  | 722.5 |  |  | 837.5 |  |  | 878 |  |  | 771 |  |  | 735 |  |  | 793 |  |  | 793.5 |  |  | 771 |  |  | 840 |  |  | 768.5 |  |  | 876.5 |  |  | 798.5 |  |  | 826 |  |  | 780.5 |  |  | 846.5 |  |  | 822.5 |  |  | 852 |  |  | 850 |  |  | 783.5 |  |  | 756 |  |  | 867 |  |  | 783.5 |  |  | 773 |  |  | 831 |  |  | 817 |  |  | 720 |  |  | 785.5 |  |  | 844.5 |  |  | 778 |  |  | 882 |  |  | 791 |  |  | 784 |  |  | 769 |  |  | 796.5 |  |  | 772.5 |  |  | 813 |  |  | 904 |  |  | 851 |  |  | 780.5 |  |  | 860.5 |  |  | 807 |  |  | 773 |  |  | 807 |  |  | 807.5 |  |  | 875.5 |  |  | 800 |  |  | 746 |  |  | 834 |  |  | 847 |  |  | 792 |  |  | 851 |  |  | 794 |  |  | 824.5 |  |  | 726 |  |  | 881 |  |  | 848 |  |  | 839.5 |  |  | 883 |  |  | 754 |  |  | 722 |  |  | 832 |  |  | 862 |  |  | 815 |  |  | 775 |  |  | 743.5 |  |  | 842.5 |  |  | 759.5 |  |  | 822 |  |  | 862 |  |  | 863.5 |  |  | 788 |  |  | 811.5 |  |  | 806.5 |  |  | 745 |  |  | 779 |  |  | 899.5 |  |  | 812 |  |  | 840 |  |  | 871 |  |  | 795 |  |  | 789 |  |  | 807 |  |  | 812 |  |  | 889.5 |  |  | 818 |  |  | 779 |  |  | 796 |  |  | 782 |  |  | 843 |  |  | 749 |  |  | 872 |  |  | 905 |  |  | 850 |  |  | 849.5 |  |  | 799.5 |  |  | 731.5 |  |  | 851.5 |  |  | 836 |  |  | 782 |  |  | 858.5 |  |  | 769 |  |  | 782 |  |  | 812.5 |  |  | 812.5 |  |  | 863 |  |  | 792.5 |  |  | 797.5 |  |  | 774 |  |  | 822 |  |  | 781 |  |  | 861 |  |  | 849.5 |  |  | 783 |  |  | 816.5 |  |  | 807.5 |  |  | 767 |  |  | 850 |  |  | 788.5 |  |  | 786 |  |  | 846.5 |  |  | 756 |  |  | 809.5 |  |  | 765.5 |  |  | 818.5 |  |  | 856.5 |  |  | 824.5 |  |  | 827 |  |  | 847 |  |  | 921.5 |  |  | 861 |  |  | 793 |  |  | 840 |  |  | 828 |  |  | 847.5 |  |  | 808 |  |  | 769 |  |  | 798 |  |  | 824.5 |  |  | 797 |  |  | 790 |  |  | 823 |  |  | 865.5 |  |  | 855 |  |  | 708 |  |  | 804 |  |  | 814 |  |  | 890.5 |  |  | 808 |  |  | 775.5 |  |  | 821 |  |  | 860 |  |  | 892.5 |  |  | 839 |  |  | 769 |  |  | 737.5 |  |  | 814 |  |  | 764 |  |  | 838 |  |  | 813.5 |  |  | 771.5 |  |  | 825 |  |  | 767 |  |  | 819.5 |  |  | 819.5 |  |  | 759 |  |  | 858 |  |  | 836.5 |  |  | 834.5 |  |  | 774.5 |  |  | 750.5 |  |  | 885.5 |  |  | 858 |  |  | 805.5 |  |  | 809 |  |  | 792 |  |  | 779 |  |  | 853 |  |  | 839.5 |  |  | 758 |  |  | 770 |  |  | 829.5 |  |  | 762.5 |  |  | 742 |  |  | 762.5 |  |  | 802.5 |  |  | 849 |  |  | 785 |  |  | 809 |  |  | 758.5 |  |  | 828 |  |  | 839.5 |  |  | 811 |  |  | 871 |  |  | 859.5 |  |  | 814 |  |  | 921 |  |  | 795 |  |  | 847 |  |  | 865 |  |  | 769 |  |  | 748 |  |  | 756 |  |  | 750.5 |  |  | 821.5 |  |  | 842 |  |  | 853.5 |  |  | 751.5 |  |  | 776 |  |  | 707 |  |  | 823 |  |  | 832.5 |  |  | 802.5 |  |  | 803 |  |  | 890 |  |  | 749 |  |  | 715 |  |  | 835 |  |  | 761 |  |  | 877 |  |  | 820.5 |  |  | 850 |  |  | 798 |  |  | 897 |  |  | 783 |  |  | 788 |  |  | 826.5 |  |  | 900.5 |  |  | 738.5 |  |  | 757 |  |  | 792 |  |  | 775.5 |  |  | 873.5 |  |  | 814.5 |  |  | 831 |  |  | 849.5 |  |  | 827.5 |  |  | 762 |  |  | 737.5 |  |  | 863.5 |  |  | 799 |  |  | 776 |  |  | 774 |  |  | 812 |  |  | 845 |  |  | 752 |  |  | 837 |  |  | 877 |  |  | 739 |  |  | 751 |  |  | 842.5 |  |  | 814 |  |  | 881 |  |  | 749 |  |  | 842.5 |  |  | 867 |  |  | 797.5 |  |  | 832 |  |  | 815 |  |  | 816 |  |  | 798 |  |  | 844.5 |  |  | 810 |  |  | 757 |  |  | 926.5 |  |  | 851 |  |  | 799 |  |  | 747.5 |  |  | 833.5 |  |  | 886 |  |  | 770.5 |  |  | 799 |  |  | 825.5 |  |  | 818 |  |  | 798 |  |  | 843.5 |  |  | 887.5 |  |  | 873 |  |  | 812 |  |  | 846 |  |  | 838 |  |  | 717 |  |  | 848 |  |  | 763 |  |  | 763 |  |  | 838.5 |  |  | 744 |  |  | 860.5 |  |  | 818 |  |  | 833.5 |  |  | 802.5 |  |  | 807 |  |  | 850 |  |  | 872.5 |  |  | 873 |  |  | 782 |  |  | 823 |  |  | 824.5 |  |  | 861 |  |  | 762.5 |  |  | 825 |  |  | 833 |  |  | 831 |  |  | 833 |  |  | 871.5 |  |  | 767 |  |  | 834 |  |  | 814 |  |  | 751.5 |  |  | 916 |  |  | 783 |  |  | 827 |  |  | 791 |  |  | 843.5 |  |  | 756.5 |  |  | 820 |  |  | 798 |  |  | 870 |  |  | 838.5 |  |  | 835 |  |  | 763 |  |  | 727 |  |  | 856.5 |  |  | 796.5 |  |  | 830.5 |  |  | 780 |  |  | 867 |  |  | 825 |  |  | 816.5 |  |  | 839 |  |  | 806.5 |  |  | 720 |  |  | 783 |  |  | 829 |  |  | 793.5 |  |  | 851.5 |  |  | 795 |  |  | 741 |  |  | 841.5 |  |  | 754 |  |  | 805 |  |  | 842.5 |  |  | 808 |  |  | 801 |  |  | 846.5 |  |  | 705 |  |  | 870 |  |  | 774.5 |  |  | 790 |  |  | 808.5 |  |  | 874 |  |  | 732.5 |  |  | 829.5 |  |  | 743 |  |  | 872 |  |  | 830.5 |  |  | 817.5 |  |  | 809 |  |  | 813 |  |  | 853 |  |  | 807.5 |  |  | 862 |  |  | 765 |  |  | 812 |  |  | 857.5 |  |  | 791.5 |  |  | 803 |  |  | 908 |  |  | 850 |  |  | 835 |  |  | 848 |  |  | 807 |  |  | 837 |  |  | 790.5 |  |  | 794.5 |  |  | 800.5 |  |  | 793 |  |  | 799.5 |  |  | 793 |  |  | 770 |  |  | 839.5 |  |  | 746.5 |  |  | 687 |  |  | 845 |  |  | 682.5 |  |  | 791 |  |  | 808 |  |  | 739.5 |  |  | 790.5 |  |  | 880 |  |  | 854 |  |  | 838 |  |  | 738.5 |  |  | 730 |  |  | 760 |  |  | 783 |  |  | 749 |  |  | 825 |  |  | 824.5 |  |  | 797 |  |  | 752 |  |  | 713 |  |  | 848.5 |  |  | 910 |  |  | 861.5 |  |  | 834.5 |  |  | 790 |  |  | 796 |  |  | 826.5 |  |  | 744.5 |  |  | 820.5 |  |  | 804.5 |  |  | 839.5 |  |  | 888 |  |  | 816 |  |  | 861.5 |  |  | 808.5 |  |  | 832 |  |  | 728 |  |  | 840.5 |  |  | 781 |  |  | 795 |  |  | 789 |  |  | 823.5 |  |  | 812 |  |  | 784.5 |  |  | 808 |  |  | 819.5 |  |  | 840.5 |  |  | 869.5 |  |  | 811 |  |  | 772 |  |  | 826.5 |  |  | 830.5 |  |  | 817 |  |  | 812 |  |  | 770.5 |  |  | 832 |  |  | 768.5 |  |  | 836.5 |  |  | 799 |  |  | 797 |  |  | 780.5 |  |  | 838.5 |  |  | 777 |  |  | 806.5 |  |  | 848.5 |  |  | 794 |  |  | 824 |  |  | 872 |  |  | 821.5 |  |  | 808 |  |  | 781 |  |  | 793 |  |  | 803 |  |  | 874 |  |  | 762 |  |  | 871.5 |  |  | 832.5 |  |  | 778 |  |  | 748 |  |  | 804 |  |  | 827.5 |  |  | 807 |  |  | 869 |  |  | 778.5 |  |  | 805.5 |  |  | 756 |  |  | 816.5 |  |  | 828 |  |  | 771 |  |  | 828 |  |  | 859.5 |  |  | 910 |  |  | 795.5 |  |  | 773.5 |  |  | 747 |  |  | 827.5 |  |  | 746.5 |  |  | 737 |  |  | 747 |  |  | 835 |  |  | 789.5 |  |  | 795 |  |  | 777.5 |  |  | 851.5 |  |  | 831 |  |  | 770.5 |  |  | 816 |  |  | 808 |  |  | 782 |  |  | 761 |  |  | 755 |  |  | 865.5 |  |  | 854 |  |  | 837 |  |  | 759 |  |  | 899 |  |  | 774.5 |  |  | 921.5 |  |  | 794 |  |  | 783 |  |  | 815 |  |  | 774 |  |  | 809 |  |  | 794.5 |  |  | 863 |  |  | 803.5 |  |  | 904 |  |  | 775 |  |  | 816 |  |  | 793 |  |  | 775.5 |  |  | 826 |  |  | 815.5 |  |  | 714 |  |  | 807 |  |  | 846 |  |  | 779.5 |  |  | 812 |  |  | 799 |  |  | 734 |  |  | 953 |  |  | 867 |  |  | 813.5 |  |  | 809.5 |  |  | 765 |  |  | 764.5 |  |  | 774 |  |  | 767.5 |  |  | 844.5 |  |  | 792.5 |  |  | 780.5 |  |  | 755 |  |  | 862 |  |  | 795 |  |  | 758 |  |  | 848 |  |  | 798 |  |  | 789.5 |  |  | 772.5 |  |  | 797.5 |  |  | 838 |  |  | 814.5 |  |  | 873.5 |  |  | 850.5 |  |  | 826.5 |  |  | 784 |  |  | 785.5 |  |  | 789.5 |  |  | 819 |  |  | 853.5 |  |  | 806.5 |  |  | 844.5 |  |  | 863 |  |  | 832.5 |  |  | 819 |  |  | 779 |  |  | 789.5 |  |  | 831.5 |  |  | 811 |  |  | 822 |  |  | 759.5 |  |  | 741.5 |  |  | 877.5 |  |  | 847 |  |  | 813 |  |  | 825 |  |  | 812.5 |  |  | 806.5 |  |  | 797 |  |  | 801.5 |  |  | 792 |  |  | 803 |  |  | 814.5 |  |  | 751.5 |  |  | 815 |  |  | 800.5 |  |  | 841 |  |  | 757.5 |  |  | 836.5 |  |  | 816 |  |  | 800.5 |  |  | 813 |  |  | 829.5 |  |  | 796 |  |  | 874 |  |  | 848 |  |  | 789.5 |  |  | 751.5 |  |  | 852 |  |  | 775 |  |  | 738 |  |  | 811.5 |  |  | 749.5 |  |  | 779 |  |  | 819.5 |  |  | 815 |  |  | 800.5 |  |  | 795.5 |  |  | 746 |  |  | 847 |  |  | 818 |  |  | 792.5 |  |  | 741 |  |  | 839.5 |  |  | 789 |  |  | 800.5 |  |  | 842 |  |  | 763.5 |  |  | 794 |  |  | 758.5 |  |  | 778.5 |  |  | 792 |  |  | 778 |  |  | 778 |  |  | 803 |  |  | 814.5 |  |  | 762 |  |  | 737.5 |  |  | 748 |  |  | 843 |  |  | 826 |  |  | 878 |  |  | 875 |  |  | 820 |  |  | 760 |  |  | 805.5 |  |  | 786 |  |  | 836
31 |  | 924.5 |  |  | 812 |  |  | 846.5 |  |  | 868 |  |  | 814.5 |  |  | 838 |  |  | 844 |  |  | 868 |  |  | 884.5 |  |  | 835 |  |  | 865 |  |  | 919 |  |  | 865 |  |  | 901 |  |  | 841.5 |  |  | 869.5 |  |  | 821 |  |  | 836 |  |  | 886 |  |  | 731.5 |  |  | 856 |  |  | 875 |  |  | 878 |  |  | 895 |  |  | 789.5 |  |  | 872 |  |  | 923 |  |  | 815 |  |  | 849 |  |  | 866 |  |  | 810 |  |  | 846.5 |  |  | 974.5 |  |  | 813.5 |  |  | 815 |  |  | 792.5 |  |  | 835.5 |  |  | 788.5 |  |  | 869 |  |  | 869 |  |  | 787.5 |  |  | 817 |  |  | 902.5 |  |  | 838.5 |  |  | 893.5 |  |  | 873.5 |  |  | 854.5 |  |  | 829 |  |  | 797 |  |  | 750.5 |  |  | 896 |  |  | 853.5 |  |  | 759.5 |  |  | 897 |  |  | 809 |  |  | 792 |  |  | 891 |  |  | 908 |  |  | 828 |  |  | 848.5 |  |  | 971.5 |  |  | 865.5 |  |  | 789 |  |  | 849 |  |  | 784 |  |  | 763.5 |  |  | 864 |  |  | 905.5 |  |  | 833.5 |  |  | 867.5 |  |  | 816 |  |  | 859 |  |  | 807 |  |  | 806.5 |  |  | 891.5 |  |  | 846.5 |  |  | 853.5 |  |  | 888.5 |  |  | 867.5 |  |  | 835.5 |  |  | 854.5 |  |  | 842 |  |  | 797 |  |  | 884 |  |  | 868.5 |  |  | 818 |  |  | 786.5 |  |  | 846 |  |  | 802 |  |  | 880.5 |  |  | 841.5 |  |  | 884 |  |  | 1002 |  |  | 828.5 |  |  | 839 |  |  | 826.5 |  |  | 875.5 |  |  | 838.5 |  |  | 819.5 |  |  | 789.5 |  |  | 861 |  |  | 802 |  |  | 828 |  |  | 877.5 |  |  | 834.5 |  |  | 828.5 |  |  | 831.5 |  |  | 821 |  |  | 852 |  |  | 829.5 |  |  | 798 |  |  | 835.5 |  |  | 888 |  |  | 875 |  |  | 829.5 |  |  | 843 |  |  | 882 |  |  | 829 |  |  | 791 |  |  | 897.5 |  |  | 912.5 |  |  | 784.5 |  |  | 906 |  |  | 771 |  |  | 749 |  |  | 866 |  |  | 869.5 |  |  | 856 |  |  | 839.5 |  |  | 863 |  |  | 848 |  |  | 882.5 |  |  | 758.5 |  |  | 750 |  |  | 787.5 |  |  | 850 |  |  | 857 |  |  | 869 |  |  | 863 |  |  | 834 |  |  | 827 |  |  | 825 |  |  | 817 |  |  | 804 |  |  | 806.5 |  |  | 796 |  |  | 790 |  |  | 828 |  |  | 858 |  |  | 782 |  |  | 804 |  |  | 878 |  |  | 828.5 |  |  | 873 |  |  | 848.5 |  |  | 838 |  |  | 773 |  |  | 872.5 |  |  | 806 |  |  | 921.5 |  |  | 840 |  |  | 790 |  |  | 835.5 |  |  | 772 |  |  | 825.5 |  |  | 778 |  |  | 811 |  |  | 759.5 |  |  | 827.5 |  |  | 874 |  |  | 831.5 |  |  | 798.5 |  |  | 818 |  |  | 825 |  |  | 875.5 |  |  | 811.5 |  |  | 808.5 |  |  | 836 |  |  | 926 |  |  | 791 |  |  | 901 |  |  | 869 |  |  | 882.5 |  |  | 806 |  |  | 799.5 |  |  | 918.5 |  |  | 887 |  |  | 821 |  |  | 833.5 |  |  | 787.5 |  |  | 799 |  |  | 860.5 |  |  | 879.5 |  |  | 827 |  |  | 837 |  |  | 847 |  |  | 774.5 |  |  | 862 |  |  | 888.5 |  |  | 824.5 |  |  | 826 |  |  | 877.5 |  |  | 828 |  |  | 857 |  |  | 877 |  |  | 889 |  |  | 836 |  |  | 846 |  |  | 894 |  |  | 888 |  |  | 907 |  |  | 816 |  |  | 849.5 |  |  | 863.5 |  |  | 815 |  |  | 732 |  |  | 885 |  |  | 844.5 |  |  | 852.5 |  |  | 886.5 |  |  | 805 |  |  | 836 |  |  | 877.5 |  |  | 807.5 |  |  | 758.5 |  |  | 889 |  |  | 886 |  |  | 839 |  |  | 827 |  |  | 836 |  |  | 800.5 |  |  | 768.5 |  |  | 882 |  |  | 855 |  |  | 847 |  |  | 858 |  |  | 762 |  |  | 787.5 |  |  | 807 |  |  | 921 |  |  | 865 |  |  | 863 |  |  | 803.5 |  |  | 910 |  |  | 876 |  |  | 783 |  |  | 901 |  |  | 909.5 |  |  | 878 |  |  | 798 |  |  | 779 |  |  | 870.5 |  |  | 880.5 |  |  | 838.5 |  |  | 934 |  |  | 810 |  |  | 795 |  |  | 891 |  |  | 856 |  |  | 831.5 |  |  | 917 |  |  | 819.5 |  |  | 824.5 |  |  | 891.5 |  |  | 831 |  |  | 868.5 |  |  | 850 |  |  | 818 |  |  | 785.5 |  |  | 863.5 |  |  | 915 |  |  | 941.5 |  |  | 908.5 |  |  | 839 |  |  | 912 |  |  | 843.5 |  |  | 797.5 |  |  | 847 |  |  | 790.5 |  |  | 927 |  |  | 798 |  |  | 878.5 |  |  | 876 |  |  | 748 |  |  | 863.5 |  |  | 838 |  |  | 915.5 |  |  | 824 |  |  | 904 |  |  | 828 |  |  | 765 |  |  | 888.5 |  |  | 897 |  |  | 869.5 |  |  | 858.5 |  |  | 849.5 |  |  | 918 |  |  | 870.5 |  |  | 947 |  |  | 860 |  |  | 809.5 |  |  | 865.5 |  |  | 844 |  |  | 823.5 |  |  | 818 |  |  | 842 |  |  | 925.5 |  |  | 838 |  |  | 850.5 |  |  | 870.5 |  |  | 889.5 |  |  | 831 |  |  | 782 |  |  | 892 |  |  | 777.5 |  |  | 837 |  |  | 846.5 |  |  | 856 |  |  | 810 |  |  | 757 |  |  | 819 |  |  | 903 |  |  | 821 |  |  | 822 |  |  | 895 |  |  | 842 |  |  | 818.5 |  |  | 864 |  |  | 762 |  |  | 925.5 |  |  | 806.5 |  |  | 862.5 |  |  | 912.5 |  |  | 853 |  |  | 902 |  |  | 773.5 |  |  | 900.5 |  |  | 911.5 |  |  | 910 |  |  | 819 |  |  | 840 |  |  | 853 |  |  | 795 |  |  | 841 |  |  | 817 |  |  | 813.5 |  |  | 827.5 |  |  | 853 |  |  | 891.5 |  |  | 853.5 |  |  | 818 |  |  | 878 |  |  | 843 |  |  | 846 |  |  | 807.5 |  |  | 792.5 |  |  | 839.5 |  |  | 813 |  |  | 837.5 |  |  | 821 |  |  | 832 |  |  | 802 |  |  | 773.5 |  |  | 924 |  |  | 779 |  |  | 831.5 |  |  | 859 |  |  | 846.5 |  |  | 896 |  |  | 870.5 |  |  | 794 |  |  | 748.5 |  |  | 858.5 |  |  | 917 |  |  | 800 |  |  | 759 |  |  | 817 |  |  | 822.5 |  |  | 797 |  |  | 864 |  |  | 789.5 |  |  | 902.5 |  |  | 813.5 |  |  | 852 |  |  | 806.5 |  |  | 870.5 |  |  | 843.5 |  |  | 899 |  |  | 876 |  |  | 822.5 |  |  | 795 |  |  | 906 |  |  | 830.5 |  |  | 799 |  |  | 860 |  |  | 838 |  |  | 767 |  |  | 806.5 |  |  | 883.5 |  |  | 804 |  |  | 911 |  |  | 830 |  |  | 808 |  |  | 808 |  |  | 843.5 |  |  | 811.5 |  |  | 852 |  |  | 943 |  |  | 898 |  |  | 795.5 |  |  | 899.5 |  |  | 828 |  |  | 788 |  |  | 828 |  |  | 831.5 |  |  | 914.5 |  |  | 839 |  |  | 785 |  |  | 873 |  |  | 862 |  |  | 807 |  |  | 877 |  |  | 841 |  |  | 871.5 |  |  | 765 |  |  | 920 |  |  | 874 |  |  | 865.5 |  |  | 907 |  |  | 769 |  |  | 737 |  |  | 856 |  |  | 901 |  |  | 844 |  |  | 814 |  |  | 790.5 |  |  | 871.5 |  |  | 798.5 |  |  | 843 |  |  | 909 |  |  | 878.5 |  |  | 827 |  |  | 835.5 |  |  | 821.5 |  |  | 769 |  |  | 794 |  |  | 928.5 |  |  | 833 |  |  | 879 |  |  | 897 |  |  | 816 |  |  | 836 |  |  | 831 |  |  | 827 |  |  | 910.5 |  |  | 865 |  |  | 794 |  |  | 843 |  |  | 821 |  |  | 882 |  |  | 770 |  |  | 901 |  |  | 920 |  |  | 876 |  |  | 888.5 |  |  | 846.5 |  |  | 778.5 |  |  | 872.5 |  |  | 883 |  |  | 821 |  |  | 882.5 |  |  | 793 |  |  | 821 |  |  | 836.5 |  |  | 836.5 |  |  | 902 |  |  | 831.5 |  |  | 844.5 |  |  | 789 |  |  | 848 |  |  | 805 |  |  | 890 |  |  | 878.5 |  |  | 807 |  |  | 840.5 |  |  | 822.5 |  |  | 782 |  |  | 879 |  |  | 835.5 |  |  | 825 |  |  | 893.5 |  |  | 795 |  |  | 848.5 |  |  | 780.5 |  |  | 833.5 |  |  | 882.5 |  |  | 845.5 |  |  | 853 |  |  | 886 |  |  | 960.5 |  |  | 876 |  |  | 808 |  |  | 879 |  |  | 852 |  |  | 873.5 |  |  | 832 |  |  | 808 |  |  | 827 |  |  | 863.5 |  |  | 836 |  |  | 805 |  |  | 838 |  |  | 904.5 |  |  | 876 |  |  | 747 |  |  | 833 |  |  | 853 |  |  | 937.5 |  |  | 829 |  |  | 801.5 |  |  | 860 |  |  | 889 |  |  | 916.5 |  |  | 878 |  |  | 784 |  |  | 752.5 |  |  | 853 |  |  | 788 |  |  | 885 |  |  | 834.5 |  |  | 800.5 |  |  | 872 |  |  | 796 |  |  | 834.5 |  |  | 834.5 |  |  | 798 |  |  | 873 |  |  | 865.5 |  |  | 849.5 |  |  | 813.5 |  |  | 797.5 |  |  | 900.5 |  |  | 887 |  |  | 852.5 |  |  | 835 |  |  | 813 |  |  | 818 |  |  | 877 |  |  | 868.5 |  |  | 773 |  |  | 796 |  |  | 850.5 |  |  | 801.5 |  |  | 766 |  |  | 783.5 |  |  | 826.5 |  |  | 873 |  |  | 832 |  |  | 830 |  |  | 805.5 |  |  | 857 |  |  | 868.5 |  |  | 850 |  |  | 910 |  |  | 906.5 |  |  | 843 |  |  | 945 |  |  | 821 |  |  | 873 |  |  | 889 |  |  | 795 |  |  | 795 |  |  | 780 |  |  | 797.5 |  |  | 842.5 |  |  | 866 |  |  | 874.5 |  |  | 780.5 |  |  | 815 |  |  | 722 |  |  | 838 |  |  | 858.5 |  |  | 826.5 |  |  | 832 |  |  | 916 |  |  | 778 |  |  | 730 |  |  | 850 |  |  | 800 |  |  | 924 |  |  | 835.5 |  |  | 889 |  |  | 819 |  |  | 936 |  |  | 807 |  |  | 827 |  |  | 873.5 |  |  | 926.5 |  |  | 777.5 |  |  | 804 |  |  | 831 |  |  | 822.5 |  |  | 920.5 |  |  | 853.5 |  |  | 878 |  |  | 888.5 |  |  | 842.5 |  |  | 783 |  |  | 776.5 |  |  | 902.5 |  |  | 838 |  |  | 805 |  |  | 813 |  |  | 836 |  |  | 892 |  |  | 773 |  |  | 852 |  |  | 901 |  |  | 778 |  |  | 780 |  |  | 889.5 |  |  | 853 |  |  | 905 |  |  | 778 |  |  | 866.5 |  |  | 906 |  |  | 844.5 |  |  | 879 |  |  | 854 |  |  | 855 |  |  | 822 |  |  | 891.5 |  |  | 825 |  |  | 781 |  |  | 965.5 |  |  | 890 |  |  | 820 |  |  | 773.5 |  |  | 857.5 |  |  | 907 |  |  | 794.5 |  |  | 838 |  |  | 849.5 |  |  | 844 |  |  | 827 |  |  | 864.5 |  |  | 902.5 |  |  | 894 |  |  | 851 |  |  | 861 |  |  | 862 |  |  | 738 |  |  | 895 |  |  | 810 |  |  | 787 |  |  | 885.5 |  |  | 783 |  |  | 881.5 |  |  | 857 |  |  | 859.5 |  |  | 841.5 |  |  | 854 |  |  | 897 |  |  | 893.5 |  |  | 902 |  |  | 821 |  |  | 862 |  |  | 848.5 |  |  | 890 |  |  | 791.5 |  |  | 849 |  |  | 859 |  |  | 870 |  |  | 872 |  |  | 918.5 |  |  | 806 |  |  | 860 |  |  | 853 |  |  | 790.5 |  |  | 945 |  |  | 830 |  |  | 866 |  |  | 830 |  |  | 882.5 |  |  | 795.5 |  |  | 859 |  |  | 837 |  |  | 909 |  |  | 885.5 |  |  | 882 |  |  | 792 |  |  | 774 |  |  | 903.5 |  |  | 811.5 |  |  | 854.5 |  |  | 819 |  |  | 891 |  |  | 849 |  |  | 831.5 |  |  | 860 |  |  | 827.5 |  |  | 741 |  |  | 809 |  |  | 868 |  |  | 822.5 |  |  | 898.5 |  |  | 834 |  |  | 770 |  |  | 880.5 |  |  | 801 |  |  | 844 |  |  | 863.5 |  |  | 847 |  |  | 816 |  |  | 893.5 |  |  | 752 |  |  | 909 |  |  | 798.5 |  |  | 829 |  |  | 837.5 |  |  | 903 |  |  | 771.5 |  |  | 876.5 |  |  | 782 |  |  | 896 |  |  | 845.5 |  |  | 846.5 |  |  | 848 |  |  | 837 |  |  | 877 |  |  | 831.5 |  |  | 891 |  |  | 804 |  |  | 851 |  |  | 904.5 |  |  | 812.5 |  |  | 818 |  |  | 955 |  |  | 874 |  |  | 850 |  |  | 887 |  |  | 831 |  |  | 861 |  |  | 805.5 |  |  | 823.5 |  |  | 826.5 |  |  | 817 |  |  | 820.5 |  |  | 808 |  |  | 791 |  |  | 860.5 |  |  | 785.5 |  |  | 711 |  |  | 866 |  |  | 706.5 |  |  | 820 |  |  | 832 |  |  | 778.5 |  |  | 829.5 |  |  | 895 |  |  | 883 |  |  | 867 |  |  | 759.5 |  |  | 756 |  |  | 799 |  |  | 804 |  |  | 775 |  |  | 864 |  |  | 863.5 |  |  | 826 |  |  | 778 |  |  | 752 |  |  | 887.5 |  |  | 925 |  |  | 885.5 |  |  | 863.5 |  |  | 816 |  |  | 822 |  |  | 852.5 |  |  | 783.5 |  |  | 859.5 |  |  | 833.5 |  |  | 860.5 |  |  | 927 |  |  | 842 |  |  | 900.5 |  |  | 837.5 |  |  | 853 |  |  | 767 |  |  | 887.5 |  |  | 828 |  |  | 824 |  |  | 813 |  |  | 849.5 |  |  | 859 |  |  | 813.5 |  |  | 829 |  |  | 848.5 |  |  | 887.5 |  |  | 895.5 |  |  | 835 |  |  | 819 |  |  | 852.5 |  |  | 851.5 |  |  | 843 |  |  | 833 |  |  | 796.5 |  |  | 871 |  |  | 807.5 |  |  | 875.5 |  |  | 823 |  |  | 836 |  |  | 804.5 |  |  | 877.5 |  |  | 792 |  |  | 830.5 |  |  | 887.5 |  |  | 820 |  |  | 848 |  |  | 919 |  |  | 860.5 |  |  | 834 |  |  | 828 |  |  | 814 |  |  | 827 |  |  | 889 |  |  | 777 |  |  | 892.5 |  |  | 847.5 |  |  | 817 |  |  | 777 |  |  | 828 |  |  | 866.5 |  |  | 831 |  |  | 895 |  |  | 802.5 |  |  | 834.5 |  |  | 780 |  |  | 840.5 |  |  | 849 |  |  | 818 |  |  | 843 |  |  | 883.5 |  |  | 957 |  |  | 842.5 |  |  | 788.5 |  |  | 786 |  |  | 866.5 |  |  | 785.5 |  |  | 766 |  |  | 786 |  |  | 882 |  |  | 818.5 |  |  | 816 |  |  | 803.5 |  |  | 875.5 |  |  | 870 |  |  | 796.5 |  |  | 863 |  |  | 855 |  |  | 811 |  |  | 776 |  |  | 794 |  |  | 891.5 |  |  | 893 |  |  | 861 |  |  | 785 |  |  | 938 |  |  | 813.5 |  |  | 950.5 |  |  | 815 |  |  | 830 |  |  | 841 |  |  | 789 |  |  | 848 |  |  | 841.5 |  |  | 902 |  |  | 832.5 |  |  | 933 |  |  | 804 |  |  | 855 |  |  | 808 |  |  | 801.5 |  |  | 841 |  |  | 844.5 |  |  | 735 |  |  | 854 |  |  | 885 |  |  | 826.5 |  |  | 841 |  |  | 825 |  |  | 763 |  |  | 1000 |  |  | 906 |  |  | 834.5 |  |  | 856.5 |  |  | 804 |  |  | 785.5 |  |  | 803 |  |  | 791.5 |  |  | 883.5 |  |  | 831.5 |  |  | 801.5 |  |  | 794 |  |  | 888 |  |  | 810 |  |  | 784 |  |  | 895 |  |  | 827 |  |  | 804.5 |  |  | 801.5 |  |  | 836.5 |  |  | 877 |  |  | 853.5 |  |  | 888.5 |  |  | 865.5 |  |  | 852.5 |  |  | 823 |  |  | 809.5 |  |  | 810.5 |  |  | 866 |  |  | 877.5 |  |  | 832.5 |  |  | 865.5 |  |  | 902 |  |  | 853.5 |  |  | 845 |  |  | 803 |  |  | 836.5 |  |  | 852.5 |  |  | 840 |  |  | 861 |  |  | 798.5 |  |  | 765.5 |  |  | 916.5 |  |  | 868 |  |  | 842 |  |  | 854 |  |  | 851.5 |  |  | 832.5 |  |  | 818 |  |  | 848.5 |  |  | 818 |  |  | 832 |  |  | 853.5 |  |  | 772.5 |  |  | 830 |  |  | 824.5 |  |  | 870 |  |  | 772.5 |  |  | 875.5 |  |  | 845 |  |  | 824.5 |  |  | 837 |  |  | 868.5 |  |  | 811 |  |  | 900 |  |  | 869 |  |  | 828.5 |  |  | 790.5 |  |  | 899 |  |  | 796 |  |  | 777 |  |  | 850.5 |  |  | 788.5 |  |  | 826 |  |  | 858.5 |  |  | 839 |  |  | 826.5 |  |  | 819.5 |  |  | 761 |  |  | 871 |  |  | 847 |  |  | 821.5 |  |  | 780 |  |  | 860.5 |  |  | 836 |  |  | 821.5 |  |  | 889 |  |  | 784.5 |  |  | 815 |  |  | 805.5 |  |  | 804.5 |  |  | 831 |  |  | 825 |  |  | 825 |  |  | 850 |  |  | 840.5 |  |  | 788 |  |  | 776.5 |  |  | 787 |  |  | 890 |  |  | 865 |  |  | 917 |  |  | 890 |  |  | 835 |  |  | 799 |  |  | 834.5 |  |  | 801 |  |  | 875
32 |  | 945.5 |  |  | 859 |  |  | 885.5 |  |  | 883 |  |  | 838.5 |  |  | 864 |  |  | 865 |  |  | 894 |  |  | 905.5 |  |  | 864 |  |  | 886 |  |  | 958 |  |  | 886 |  |  | 940 |  |  | 867.5 |  |  | 895.5 |  |  | 842 |  |  | 860 |  |  | 910 |  |  | 770.5 |  |  | 877 |  |  | 899 |  |  | 917 |  |  | 916 |  |  | 804.5 |  |  | 896 |  |  | 947 |  |  | 844 |  |  | 864 |  |  | 905 |  |  | 839 |  |  | 875.5 |  |  | 1013.5 |  |  | 852.5 |  |  | 854 |  |  | 816.5 |  |  | 874.5 |  |  | 835.5 |  |  | 890 |  |  | 916 |  |  | 811.5 |  |  | 832 |  |  | 941.5 |  |  | 867.5 |  |  | 922.5 |  |  | 912.5 |  |  | 901.5 |  |  | 868 |  |  | 812 |  |  | 771.5 |  |  | 911 |  |  | 874.5 |  |  | 806.5 |  |  | 936 |  |  | 848 |  |  | 831 |  |  | 912 |  |  | 934 |  |  | 875 |  |  | 869.5 |  |  | 1018.5 |  |  | 886.5 |  |  | 804 |  |  | 896 |  |  | 799 |  |  | 789.5 |  |  | 903 |  |  | 931.5 |  |  | 857.5 |  |  | 914.5 |  |  | 842 |  |  | 888 |  |  | 846 |  |  | 845.5 |  |  | 906.5 |  |  | 867.5 |  |  | 892.5 |  |  | 912.5 |  |  | 906.5 |  |  | 882.5 |  |  | 893.5 |  |  | 881 |  |  | 823 |  |  | 913 |  |  | 915.5 |  |  | 857 |  |  | 801.5 |  |  | 861 |  |  | 841 |  |  | 919.5 |  |  | 888.5 |  |  | 905 |  |  | 1031 |  |  | 867.5 |  |  | 865 |  |  | 855.5 |  |  | 890.5 |  |  | 853.5 |  |  | 858.5 |  |  | 804.5 |  |  | 900 |  |  | 817 |  |  | 849 |  |  | 901.5 |  |  | 855.5 |  |  | 849.5 |  |  | 860.5 |  |  | 847 |  |  | 878 |  |  | 858.5 |  |  | 837 |  |  | 864.5 |  |  | 914 |  |  | 914 |  |  | 868.5 |  |  | 882 |  |  | 903 |  |  | 844 |  |  | 806 |  |  | 944.5 |  |  | 951.5 |  |  | 799.5 |  |  | 945 |  |  | 810 |  |  | 796 |  |  | 887 |  |  | 908.5 |  |  | 877 |  |  | 860.5 |  |  | 910 |  |  | 872 |  |  | 921.5 |  |  | 782.5 |  |  | 765 |  |  | 834.5 |  |  | 874 |  |  | 896 |  |  | 908 |  |  | 878 |  |  | 873 |  |  | 851 |  |  | 846 |  |  | 864 |  |  | 851 |  |  | 835.5 |  |  | 843 |  |  | 814 |  |  | 854 |  |  | 879 |  |  | 803 |  |  | 843 |  |  | 925 |  |  | 867.5 |  |  | 912 |  |  | 863.5 |  |  | 864 |  |  | 812 |  |  | 911.5 |  |  | 821 |  |  | 950.5 |  |  | 879 |  |  | 811 |  |  | 864.5 |  |  | 787 |  |  | 872.5 |  |  | 799 |  |  | 850 |  |  | 806.5 |  |  | 866.5 |  |  | 895 |  |  | 860.5 |  |  | 813.5 |  |  | 842 |  |  | 872 |  |  | 914.5 |  |  | 850.5 |  |  | 847.5 |  |  | 883 |  |  | 955 |  |  | 815 |  |  | 948 |  |  | 890 |  |  | 921.5 |  |  | 845 |  |  | 823.5 |  |  | 944.5 |  |  | 926 |  |  | 850 |  |  | 872.5 |  |  | 808.5 |  |  | 820 |  |  | 884.5 |  |  | 894.5 |  |  | 842 |  |  | 852 |  |  | 876 |  |  | 821.5 |  |  | 909 |  |  | 909.5 |  |  | 839.5 |  |  | 855 |  |  | 898.5 |  |  | 849 |  |  | 881 |  |  | 903 |  |  | 928 |  |  | 851 |  |  | 872 |  |  | 933 |  |  | 927 |  |  | 954 |  |  | 842 |  |  | 864.5 |  |  | 887.5 |  |  | 854 |  |  | 753 |  |  | 900 |  |  | 868.5 |  |  | 891.5 |  |  | 912.5 |  |  | 844 |  |  | 883 |  |  | 916.5 |  |  | 831.5 |  |  | 784.5 |  |  | 936 |  |  | 933 |  |  | 865 |  |  | 853 |  |  | 857 |  |  | 839.5 |  |  | 792.5 |  |  | 906 |  |  | 876 |  |  | 876 |  |  | 879 |  |  | 791 |  |  | 813.5 |  |  | 836 |  |  | 947 |  |  | 886 |  |  | 878 |  |  | 818.5 |  |  | 949 |  |  | 900 |  |  | 822 |  |  | 940 |  |  | 938.5 |  |  | 904 |  |  | 822 |  |  | 818 |  |  | 917.5 |  |  | 904.5 |  |  | 864.5 |  |  | 955 |  |  | 839 |  |  | 816 |  |  | 917 |  |  | 885 |  |  | 846.5 |  |  | 932 |  |  | 866.5 |  |  | 863.5 |  |  | 906.5 |  |  | 852 |  |  | 907.5 |  |  | 871 |  |  | 847 |  |  | 814.5 |  |  | 892.5 |  |  | 936 |  |  | 980.5 |  |  | 955.5 |  |  | 886 |  |  | 951 |  |  | 867.5 |  |  | 826.5 |  |  | 873 |  |  | 829.5 |  |  | 956 |  |  | 845 |  |  | 893.5 |  |  | 905 |  |  | 777 |  |  | 892.5 |  |  | 853 |  |  | 930.5 |  |  | 863 |  |  | 919 |  |  | 857 |  |  | 804 |  |  | 914.5 |  |  | 936 |  |  | 916.5 |  |  | 879.5 |  |  | 864.5 |  |  | 947 |  |  | 891.5 |  |  | 968 |  |  | 889 |  |  | 848.5 |  |  | 904.5 |  |  | 865 |  |  | 844.5 |  |  | 857 |  |  | 868 |  |  | 940.5 |  |  | 877 |  |  | 879.5 |  |  | 909.5 |  |  | 913.5 |  |  | 870 |  |  | 821 |  |  | 907 |  |  | 803.5 |  |  | 866 |  |  | 867.5 |  |  | 882 |  |  | 849 |  |  | 778 |  |  | 840 |  |  | 929 |  |  | 860 |  |  | 869 |  |  | 919 |  |  | 889 |  |  | 865.5 |  |  | 888 |  |  | 786 |  |  | 964.5 |  |  | 832.5 |  |  | 901.5 |  |  | 951.5 |  |  | 892 |  |  | 928 |  |  | 788.5 |  |  | 921.5 |  |  | 950.5 |  |  | 931 |  |  | 843 |  |  | 879 |  |  | 879 |  |  | 816 |  |  | 880 |  |  | 838 |  |  | 860.5 |  |  | 856.5 |  |  | 877 |  |  | 912.5 |  |  | 892.5 |  |  | 847 |  |  | 917 |  |  | 869 |  |  | 870 |  |  | 846.5 |  |  | 831.5 |  |  | 860.5 |  |  | 834 |  |  | 863.5 |  |  | 868 |  |  | 858 |  |  | 849 |  |  | 820.5 |  |  | 939 |  |  | 794 |  |  | 855.5 |  |  | 888 |  |  | 867.5 |  |  | 943 |  |  | 896.5 |  |  | 809 |  |  | 795.5 |  |  | 897.5 |  |  | 943 |  |  | 847 |  |  | 780 |  |  | 856 |  |  | 861.5 |  |  | 836 |  |  | 911 |  |  | 828.5 |  |  | 941.5 |  |  | 834.5 |  |  | 878 |  |  | 830.5 |  |  | 891.5 |  |  | 882.5 |  |  | 923 |  |  | 905 |  |  | 861.5 |  |  | 842 |  |  | 935 |  |  | 869.5 |  |  | 820 |  |  | 884 |  |  | 877 |  |  | 806 |  |  | 830.5 |  |  | 898.5 |  |  | 828 |  |  | 950 |  |  | 869 |  |  | 847 |  |  | 823 |  |  | 867.5 |  |  | 858.5 |  |  | 876 |  |  | 967 |  |  | 945 |  |  | 824.5 |  |  | 920.5 |  |  | 857 |  |  | 817 |  |  | 867 |  |  | 860.5 |  |  | 938.5 |  |  | 886 |  |  | 800 |  |  | 912 |  |  | 877 |  |  | 822 |  |  | 924 |  |  | 862 |  |  | 886.5 |  |  | 789 |  |  | 967 |  |  | 900 |  |  | 889.5 |  |  | 946 |  |  | 790 |  |  | 761 |  |  | 895 |  |  | 925 |  |  | 883 |  |  | 838 |  |  | 805.5 |  |  | 886.5 |  |  | 827.5 |  |  | 864 |  |  | 935 |  |  | 917.5 |  |  | 848 |  |  | 874.5 |  |  | 845.5 |  |  | 808 |  |  | 823 |  |  | 957.5 |  |  | 859 |  |  | 903 |  |  | 912 |  |  | 863 |  |  | 862 |  |  | 852 |  |  | 866 |  |  | 931.5 |  |  | 880 |  |  | 809 |  |  | 869 |  |  | 860 |  |  | 911 |  |  | 794 |  |  | 948 |  |  | 935 |  |  | 905 |  |  | 927.5 |  |  | 870.5 |  |  | 804.5 |  |  | 901.5 |  |  | 909 |  |  | 842 |  |  | 929.5 |  |  | 814 |  |  | 860 |  |  | 875.5 |  |  | 883.5 |  |  | 931 |  |  | 860.5 |  |  | 859.5 |  |  | 813 |  |  | 895 |  |  | 834 |  |  | 919 |  |  | 917.5 |  |  | 846 |  |  | 855.5 |  |  | 848.5 |  |  | 829 |  |  | 905 |  |  | 864.5 |  |  | 864 |  |  | 908.5 |  |  | 824 |  |  | 877.5 |  |  | 801.5 |  |  | 862.5 |  |  | 906.5 |  |  | 871.5 |  |  | 892 |  |  | 901 |  |  | 984.5 |  |  | 915 |  |  | 832 |  |  | 903 |  |  | 891 |  |  | 902.5 |  |  | 847 |  |  | 855 |  |  | 866 |  |  | 910.5 |  |  | 875 |  |  | 844 |  |  | 867 |  |  | 951.5 |  |  | 891 |  |  | 762 |  |  | 854 |  |  | 877 |  |  | 976.5 |  |  | 858 |  |  | 827.5 |  |  | 881 |  |  | 928 |  |  | 955.5 |  |  | 907 |  |  | 823 |  |  | 791.5 |  |  | 877 |  |  | 803 |  |  | 909 |  |  | 881.5 |  |  | 839.5 |  |  | 898 |  |  | 843 |  |  | 860.5 |  |  | 855.5 |  |  | 819 |  |  | 902 |  |  | 912.5 |  |  | 888.5 |  |  | 828.5 |  |  | 844.5 |  |  | 924.5 |  |  | 913 |  |  | 881.5 |  |  | 882 |  |  | 842 |  |  | 847 |  |  | 903 |  |  | 907.5 |  |  | 788 |  |  | 825 |  |  | 876.5 |  |  | 848.5 |  |  | 781 |  |  | 822.5 |  |  | 873.5 |  |  | 894 |  |  | 861 |  |  | 845 |  |  | 831.5 |  |  | 878 |  |  | 892.5 |  |  | 889 |  |  | 939 |  |  | 945.5 |  |  | 864 |  |  | 984 |  |  | 847 |  |  | 912 |  |  | 904 |  |  | 834 |  |  | 816 |  |  | 827 |  |  | 823.5 |  |  | 857.5 |  |  | 881 |  |  | 895.5 |  |  | 804.5 |  |  | 854 |  |  | 746 |  |  | 877 |  |  | 905.5 |  |  | 855.5 |  |  | 858 |  |  | 937 |  |  | 817 |  |  | 769 |  |  | 874 |  |  | 824 |  |  | 953 |  |  | 864.5 |  |  | 910 |  |  | 843 |  |  | 983 |  |  | 836 |  |  | 842 |  |  | 897.5 |  |  | 973.5 |  |  | 792.5 |  |  | 843 |  |  | 855 |  |  | 861.5 |  |  | 944.5 |  |  | 900.5 |  |  | 899 |  |  | 917.5 |  |  | 889.5 |  |  | 822 |  |  | 823.5 |  |  | 923.5 |  |  | 859 |  |  | 820 |  |  | 860 |  |  | 860 |  |  | 931 |  |  | 794 |  |  | 876 |  |  | 948 |  |  | 825 |  |  | 809 |  |  | 915.5 |  |  | 900 |  |  | 929 |  |  | 802 |  |  | 890.5 |  |  | 921 |  |  | 865.5 |  |  | 903 |  |  | 901 |  |  | 876 |  |  | 861 |  |  | 938.5 |  |  | 846 |  |  | 820 |  |  | 1004.5 |  |  | 914 |  |  | 846 |  |  | 812.5 |  |  | 886.5 |  |  | 954 |  |  | 823.5 |  |  | 885 |  |  | 888.5 |  |  | 868 |  |  | 856 |  |  | 879.5 |  |  | 941.5 |  |  | 941 |  |  | 890 |  |  | 900 |  |  | 877 |  |  | 759 |  |  | 921 |  |  | 839 |  |  | 816 |  |  | 932.5 |  |  | 804 |  |  | 902.5 |  |  | 896 |  |  | 906.5 |  |  | 888.5 |  |  | 883 |  |  | 923 |  |  | 908.5 |  |  | 941 |  |  | 845 |  |  | 901 |  |  | 863.5 |  |  | 905 |  |  | 817.5 |  |  | 875 |  |  | 874 |  |  | 917 |  |  | 919 |  |  | 939.5 |  |  | 853 |  |  | 907 |  |  | 868 |  |  | 837.5 |  |  | 992 |  |  | 877 |  |  | 890 |  |  | 856 |  |  | 921.5 |  |  | 842.5 |  |  | 880 |  |  | 884 |  |  | 924 |  |  | 911.5 |  |  | 908 |  |  | 818 |  |  | 795 |  |  | 918.5 |  |  | 837.5 |  |  | 893.5 |  |  | 845 |  |  | 938 |  |  | 888 |  |  | 870.5 |  |  | 881 |  |  | 866.5 |  |  | 756 |  |  | 848 |  |  | 883 |  |  | 843.5 |  |  | 937.5 |  |  | 873 |  |  | 809 |  |  | 906.5 |  |  | 830 |  |  | 891 |  |  | 910.5 |  |  | 876 |  |  | 863 |  |  | 922.5 |  |  | 791 |  |  | 938 |  |  | 845.5 |  |  | 850 |  |  | 876.5 |  |  | 929 |  |  | 786.5 |  |  | 915.5 |  |  | 797 |  |  | 922 |  |  | 884.5 |  |  | 867.5 |  |  | 895 |  |  | 861 |  |  | 892 |  |  | 870.5 |  |  | 917 |  |  | 843 |  |  | 890 |  |  | 943.5 |  |  | 851.5 |  |  | 857 |  |  | 979 |  |  | 903 |  |  | 871 |  |  | 913 |  |  | 852 |  |  | 908 |  |  | 829.5 |  |  | 862.5 |  |  | 850.5 |  |  | 864 |  |  | 841.5 |  |  | 855 |  |  | 817 |  |  | 899.5 |  |  | 824.5 |  |  | 740 |  |  | 892 |  |  | 727.5 |  |  | 835 |  |  | 856 |  |  | 825.5 |  |  | 850.5 |  |  | 921 |  |  | 922 |  |  | 888 |  |  | 798.5 |  |  | 795 |  |  | 828 |  |  | 851 |  |  | 799 |  |  | 911 |  |  | 887.5 |  |  | 850 |  |  | 807 |  |  | 776 |  |  | 934.5 |  |  | 954 |  |  | 909.5 |  |  | 884.5 |  |  | 855 |  |  | 848 |  |  | 878.5 |  |  | 809.5 |  |  | 880.5 |  |  | 848.5 |  |  | 884.5 |  |  | 953 |  |  | 863 |  |  | 924.5 |  |  | 863.5 |  |  | 900 |  |  | 806 |  |  | 911.5 |  |  | 849 |  |  | 863 |  |  | 837 |  |  | 875.5 |  |  | 885 |  |  | 842.5 |  |  | 844 |  |  | 887.5 |  |  | 916.5 |  |  | 934.5 |  |  | 874 |  |  | 848 |  |  | 878.5 |  |  | 890.5 |  |  | 890 |  |  | 848 |  |  | 822.5 |  |  | 910 |  |  | 846.5 |  |  | 896.5 |  |  | 852 |  |  | 857 |  |  | 843.5 |  |  | 916.5 |  |  | 831 |  |  | 856.5 |  |  | 913.5 |  |  | 841 |  |  | 877 |  |  | 934 |  |  | 899.5 |  |  | 873 |  |  | 867 |  |  | 843 |  |  | 866 |  |  | 928 |  |  | 798 |  |  | 916.5 |  |  | 871.5 |  |  | 856 |  |  | 801 |  |  | 843 |  |  | 905.5 |  |  | 878 |  |  | 934 |  |  | 823.5 |  |  | 860.5 |  |  | 827 |  |  | 864.5 |  |  | 870 |  |  | 842 |  |  | 872 |  |  | 898.5 |  |  | 1004 |  |  | 889.5 |  |  | 809.5 |  |  | 812 |  |  | 895.5 |  |  | 811.5 |  |  | 795 |  |  | 807 |  |  | 929 |  |  | 865.5 |  |  | 837 |  |  | 824.5 |  |  | 899.5 |  |  | 909 |  |  | 835.5 |  |  | 889 |  |  | 902 |  |  | 850 |  |  | 805 |  |  | 815 |  |  | 930.5 |  |  | 919 |  |  | 900 |  |  | 800 |  |  | 953 |  |  | 852.5 |  |  | 979.5 |  |  | 844 |  |  | 851 |  |  | 880 |  |  | 828 |  |  | 869 |  |  | 888.5 |  |  | 949 |  |  | 847.5 |  |  | 972 |  |  | 825 |  |  | 881 |  |  | 834 |  |  | 816.5 |  |  | 862 |  |  | 873.5 |  |  | 774 |  |  | 901 |  |  | 932 |  |  | 865.5 |  |  | 870 |  |  | 849 |  |  | 810 |  |  | 1047 |  |  | 927 |  |  | 863.5 |  |  | 871.5 |  |  | 851 |  |  | 811.5 |  |  | 829 |  |  | 830.5 |  |  | 909.5 |  |  | 846.5 |  |  | 827.5 |  |  | 833 |  |  | 914 |  |  | 839 |  |  | 810 |  |  | 919 |  |  | 848 |  |  | 833.5 |  |  | 830.5 |  |  | 862.5 |  |  | 916 |  |  | 868.5 |  |  | 909.5 |  |  | 904.5 |  |  | 878.5 |  |  | 852 |  |  | 838.5 |  |  | 849.5 |  |  | 895 |  |  | 924.5 |  |  | 871.5 |  |  | 889.5 |  |  | 931 |  |  | 874.5 |  |  | 884 |  |  | 824 |  |  | 875.5 |  |  | 867.5 |  |  | 866 |  |  | 900 |  |  | 819.5 |  |  | 780.5 |  |  | 940.5 |  |  | 897 |  |  | 889 |  |  | 878 |  |  | 872.5 |  |  | 856.5 |  |  | 857 |  |  | 895.5 |  |  | 842 |  |  | 856 |  |  | 900.5 |  |  | 801.5 |  |  | 859 |  |  | 850.5 |  |  | 894 |  |  | 811.5 |  |  | 914.5 |  |  | 884 |  |  | 850.5 |  |  | 876 |  |  | 889.5 |  |  | 832 |  |  | 947 |  |  | 916 |  |  | 849.5 |  |  | 805.5 |  |  | 914 |  |  | 820 |  |  | 803 |  |  | 876.5 |  |  | 835.5 |  |  | 852 |  |  | 905.5 |  |  | 868 |  |  | 865.5 |  |  | 840.5 |  |  | 776 |  |  | 910 |  |  | 871 |  |  | 850.5 |  |  | 819 |  |  | 899.5 |  |  | 862 |  |  | 842.5 |  |  | 928 |  |  | 810.5 |  |  | 854 |  |  | 820.5 |  |  | 851.5 |  |  | 846 |  |  | 854 |  |  | 846 |  |  | 876 |  |  | 855.5 |  |  | 827 |  |  | 797.5 |  |  | 826 |  |  | 929 |  |  | 904 |  |  | 938 |  |  | 914 |  |  | 882 |  |  | 814 |  |  | 873.5 |  |  | 822 |  |  | 914
33 |  | 974.5 |  |  | 885 |  |  | 909.5 |  |  | 909 |  |  | 859.5 |  |  | 893 |  |  | 889 |  |  | 920 |  |  | 934.5 |  |  | 893 |  |  | 910 |  |  | 979 |  |  | 901 |  |  | 987 |  |  | 896.5 |  |  | 934.5 |  |  | 866 |  |  | 907 |  |  | 939 |  |  | 794.5 |  |  | 916 |  |  | 914 |  |  | 941 |  |  | 940 |  |  | 843.5 |  |  | 943 |  |  | 971 |  |  | 868 |  |  | 893 |  |  | 934 |  |  | 854 |  |  | 914.5 |  |  | 1037.5 |  |  | 881.5 |  |  | 875 |  |  | 840.5 |  |  | 889.5 |  |  | 864.5 |  |  | 911 |  |  | 940 |  |  | 840.5 |  |  | 847 |  |  | 980.5 |  |  | 914.5 |  |  | 948.5 |  |  | 927.5 |  |  | 948.5 |  |  | 883 |  |  | 838 |  |  | 800.5 |  |  | 940 |  |  | 900.5 |  |  | 845.5 |  |  | 960 |  |  | 872 |  |  | 878 |  |  | 938 |  |  | 949 |  |  | 922 |  |  | 898.5 |  |  | 1033.5 |  |  | 933.5 |  |  | 843 |  |  | 920 |  |  | 820 |  |  | 810.5 |  |  | 932 |  |  | 955.5 |  |  | 883.5 |  |  | 929.5 |  |  | 857 |  |  | 912 |  |  | 885 |  |  | 884.5 |  |  | 953.5 |  |  | 888.5 |  |  | 931.5 |  |  | 951.5 |  |  | 935.5 |  |  | 929.5 |  |  | 932.5 |  |  | 920 |  |  | 870 |  |  | 939 |  |  | 944.5 |  |  | 881 |  |  | 830.5 |  |  | 885 |  |  | 856 |  |  | 940.5 |  |  | 917.5 |  |  | 944 |  |  | 1052 |  |  | 882.5 |  |  | 891 |  |  | 884.5 |  |  | 937.5 |  |  | 892.5 |  |  | 905.5 |  |  | 843.5 |  |  | 921 |  |  | 832 |  |  | 870 |  |  | 940.5 |  |  | 879.5 |  |  | 888.5 |  |  | 875.5 |  |  | 862 |  |  | 907 |  |  | 897.5 |  |  | 858 |  |  | 911.5 |  |  | 935 |  |  | 935 |  |  | 915.5 |  |  | 921 |  |  | 918 |  |  | 865 |  |  | 853 |  |  | 973.5 |  |  | 975.5 |  |  | 828.5 |  |  | 992 |  |  | 849 |  |  | 843 |  |  | 908 |  |  | 923.5 |  |  | 892 |  |  | 899.5 |  |  | 936 |  |  | 901 |  |  | 942.5 |  |  | 821.5 |  |  | 786 |  |  | 873.5 |  |  | 889 |  |  | 935 |  |  | 929 |  |  | 899 |  |  | 920 |  |  | 877 |  |  | 870 |  |  | 893 |  |  | 890 |  |  | 856.5 |  |  | 869 |  |  | 835 |  |  | 883 |  |  | 894 |  |  | 824 |  |  | 858 |  |  | 972 |  |  | 906.5 |  |  | 938 |  |  | 887.5 |  |  | 903 |  |  | 851 |  |  | 958.5 |  |  | 868 |  |  | 965.5 |  |  | 903 |  |  | 835 |  |  | 911.5 |  |  | 811 |  |  | 901.5 |  |  | 820 |  |  | 874 |  |  | 853.5 |  |  | 913.5 |  |  | 921 |  |  | 875.5 |  |  | 852.5 |  |  | 881 |  |  | 898 |  |  | 961.5 |  |  | 889.5 |  |  | 886.5 |  |  | 907 |  |  | 979 |  |  | 854 |  |  | 972 |  |  | 916 |  |  | 947.5 |  |  | 871 |  |  | 847.5 |  |  | 970.5 |  |  | 952 |  |  | 889 |  |  | 919.5 |  |  | 855.5 |  |  | 859 |  |  | 931.5 |  |  | 915.5 |  |  | 857 |  |  | 881 |  |  | 900 |  |  | 847.5 |  |  | 933 |  |  | 956.5 |  |  | 863.5 |  |  | 879 |  |  | 937.5 |  |  | 864 |  |  | 896 |  |  | 950 |  |  | 954 |  |  | 890 |  |  | 898 |  |  | 980 |  |  | 948 |  |  | 993 |  |  | 863 |  |  | 888.5 |  |  | 926.5 |  |  | 869 |  |  | 768 |  |  | 939 |  |  | 907.5 |  |  | 930.5 |  |  | 959.5 |  |  | 883 |  |  | 912 |  |  | 931.5 |  |  | 878.5 |  |  | 799.5 |  |  | 957 |  |  | 972 |  |  | 880 |  |  | 874 |  |  | 886 |  |  | 868.5 |  |  | 813.5 |  |  | 935 |  |  | 905 |  |  | 891 |  |  | 918 |  |  | 812 |  |  | 837.5 |  |  | 875 |  |  | 973 |  |  | 925 |  |  | 899 |  |  | 865.5 |  |  | 988 |  |  | 926 |  |  | 851 |  |  | 966 |  |  | 964.5 |  |  | 919 |  |  | 846 |  |  | 844 |  |  | 956.5 |  |  | 933.5 |  |  | 879.5 |  |  | 979 |  |  | 878 |  |  | 837 |  |  | 964 |  |  | 932 |  |  | 870.5 |  |  | 947 |  |  | 905.5 |  |  | 892.5 |  |  | 945.5 |  |  | 891 |  |  | 954.5 |  |  | 886 |  |  | 876 |  |  | 861.5 |  |  | 918.5 |  |  | 975 |  |  | 1019.5 |  |  | 984.5 |  |  | 907 |  |  | 966 |  |  | 906.5 |  |  | 865.5 |  |  | 888 |  |  | 853.5 |  |  | 982 |  |  | 866 |  |  | 908.5 |  |  | 926 |  |  | 792 |  |  | 931.5 |  |  | 874 |  |  | 945.5 |  |  | 902 |  |  | 958 |  |  | 896 |  |  | 828 |  |  | 961.5 |  |  | 962 |  |  | 945.5 |  |  | 900.5 |  |  | 903.5 |  |  | 986 |  |  | 930.5 |  |  | 1007 |  |  | 918 |  |  | 874.5 |  |  | 925.5 |  |  | 912 |  |  | 883.5 |  |  | 896 |  |  | 897 |  |  | 964.5 |  |  | 916 |  |  | 900.5 |  |  | 938.5 |  |  | 928.5 |  |  | 909 |  |  | 845 |  |  | 954 |  |  | 818.5 |  |  | 890 |  |  | 888.5 |  |  | 921 |  |  | 888 |  |  | 817 |  |  | 879 |  |  | 953 |  |  | 881 |  |  | 895 |  |  | 966 |  |  | 928 |  |  | 904.5 |  |  | 903 |  |  | 815 |  |  | 1011.5 |  |  | 847.5 |  |  | 925.5 |  |  | 980.5 |  |  | 907 |  |  | 967 |  |  | 827.5 |  |  | 947.5 |  |  | 989.5 |  |  | 970 |  |  | 864 |  |  | 918 |  |  | 900 |  |  | 845 |  |  | 919 |  |  | 864 |  |  | 884.5 |  |  | 871.5 |  |  | 892 |  |  | 951.5 |  |  | 913.5 |  |  | 876 |  |  | 941 |  |  | 890 |  |  | 917 |  |  | 885.5 |  |  | 855.5 |  |  | 881.5 |  |  | 873 |  |  | 878.5 |  |  | 907 |  |  | 897 |  |  | 888 |  |  | 867.5 |  |  | 968 |  |  | 833 |  |  | 879.5 |  |  | 914 |  |  | 914.5 |  |  | 969 |  |  | 935.5 |  |  | 848 |  |  | 824.5 |  |  | 936.5 |  |  | 972 |  |  | 862 |  |  | 806 |  |  | 871 |  |  | 885.5 |  |  | 865 |  |  | 935 |  |  | 857.5 |  |  | 980.5 |  |  | 873.5 |  |  | 925 |  |  | 851.5 |  |  | 917.5 |  |  | 911.5 |  |  | 970 |  |  | 944 |  |  | 900.5 |  |  | 881 |  |  | 950 |  |  | 893.5 |  |  | 844 |  |  | 923 |  |  | 916 |  |  | 845 |  |  | 854.5 |  |  | 945.5 |  |  | 875 |  |  | 989 |  |  | 908 |  |  | 886 |  |  | 862 |  |  | 888.5 |  |  | 887.5 |  |  | 915 |  |  | 988 |  |  | 974 |  |  | 850.5 |  |  | 949.5 |  |  | 881 |  |  | 864 |  |  | 882 |  |  | 899.5 |  |  | 964.5 |  |  | 912 |  |  | 839 |  |  | 951 |  |  | 901 |  |  | 861 |  |  | 971 |  |  | 901 |  |  | 925.5 |  |  | 810 |  |  | 1006 |  |  | 924 |  |  | 928.5 |  |  | 985 |  |  | 819 |  |  | 790 |  |  | 934 |  |  | 954 |  |  | 904 |  |  | 859 |  |  | 844.5 |  |  | 925.5 |  |  | 874.5 |  |  | 879 |  |  | 956 |  |  | 938.5 |  |  | 869 |  |  | 895.5 |  |  | 884.5 |  |  | 837 |  |  | 844 |  |  | 978.5 |  |  | 898 |  |  | 942 |  |  | 941 |  |  | 910 |  |  | 877 |  |  | 881 |  |  | 913 |  |  | 978.5 |  |  | 919 |  |  | 833 |  |  | 890 |  |  | 875 |  |  | 932 |  |  | 809 |  |  | 972 |  |  | 956 |  |  | 929 |  |  | 974.5 |  |  | 891.5 |  |  | 843.5 |  |  | 916.5 |  |  | 938 |  |  | 889 |  |  | 944.5 |  |  | 861 |  |  | 899 |  |  | 899.5 |  |  | 912.5 |  |  | 952 |  |  | 899.5 |  |  | 906.5 |  |  | 860 |  |  | 921 |  |  | 849 |  |  | 958 |  |  | 956.5 |  |  | 870 |  |  | 902.5 |  |  | 863.5 |  |  | 844 |  |  | 931 |  |  | 903.5 |  |  | 885 |  |  | 947.5 |  |  | 871 |  |  | 906.5 |  |  | 827.5 |  |  | 891.5 |  |  | 930.5 |  |  | 895.5 |  |  | 931 |  |  | 940 |  |  | 1023.5 |  |  | 954 |  |  | 847 |  |  | 932 |  |  | 920 |  |  | 941.5 |  |  | 868 |  |  | 894 |  |  | 905 |  |  | 939.5 |  |  | 890 |  |  | 883 |  |  | 906 |  |  | 990.5 |  |  | 938 |  |  | 786 |  |  | 883 |  |  | 916 |  |  | 1023.5 |  |  | 873 |  |  | 853.5 |  |  | 928 |  |  | 967 |  |  | 1002.5 |  |  | 922 |  |  | 862 |  |  | 812.5 |  |  | 892 |  |  | 832 |  |  | 938 |  |  | 920.5 |  |  | 868.5 |  |  | 922 |  |  | 882 |  |  | 907.5 |  |  | 884.5 |  |  | 858 |  |  | 931 |  |  | 927.5 |  |  | 914.5 |  |  | 854.5 |  |  | 870.5 |  |  | 939.5 |  |  | 960 |  |  | 920.5 |  |  | 897 |  |  | 889 |  |  | 894 |  |  | 924 |  |  | 936.5 |  |  | 827 |  |  | 846 |  |  | 897.5 |  |  | 887.5 |  |  | 828 |  |  | 861.5 |  |  | 888.5 |  |  | 941 |  |  | 890 |  |  | 874 |  |  | 857.5 |  |  | 907 |  |  | 939.5 |  |  | 915 |  |  | 986 |  |  | 966.5 |  |  | 885 |  |  | 1008 |  |  | 862 |  |  | 927 |  |  | 933 |  |  | 863 |  |  | 840 |  |  | 856 |  |  | 847.5 |  |  | 904.5 |  |  | 920 |  |  | 910.5 |  |  | 830.5 |  |  | 869 |  |  | 770 |  |  | 916 |  |  | 931.5 |  |  | 879.5 |  |  | 897 |  |  | 984 |  |  | 838 |  |  | 784 |  |  | 913 |  |  | 863 |  |  | 992 |  |  | 890.5 |  |  | 949 |  |  | 890 |  |  | 1022 |  |  | 851 |  |  | 889 |  |  | 912.5 |  |  | 997.5 |  |  | 807.5 |  |  | 869 |  |  | 870 |  |  | 908.5 |  |  | 983.5 |  |  | 924.5 |  |  | 928 |  |  | 956.5 |  |  | 928.5 |  |  | 837 |  |  | 852.5 |  |  | 947.5 |  |  | 883 |  |  | 846 |  |  | 889 |  |  | 884 |  |  | 955 |  |  | 841 |  |  | 923 |  |  | 977 |  |  | 849 |  |  | 830 |  |  | 936.5 |  |  | 947 |  |  | 953 |  |  | 823 |  |  | 916.5 |  |  | 936 |  |  | 880.5 |  |  | 927 |  |  | 925 |  |  | 891 |  |  | 876 |  |  | 953.5 |  |  | 893 |  |  | 841 |  |  | 1030.5 |  |  | 929 |  |  | 885 |  |  | 833.5 |  |  | 915.5 |  |  | 993 |  |  | 838.5 |  |  | 924 |  |  | 903.5 |  |  | 907 |  |  | 885 |  |  | 905.5 |  |  | 970.5 |  |  | 965 |  |  | 929 |  |  | 924 |  |  | 916 |  |  | 806 |  |  | 945 |  |  | 865 |  |  | 855 |  |  | 971.5 |  |  | 828 |  |  | 941.5 |  |  | 925 |  |  | 932.5 |  |  | 909.5 |  |  | 912 |  |  | 938 |  |  | 934.5 |  |  | 980 |  |  | 871 |  |  | 930 |  |  | 892.5 |  |  | 952 |  |  | 832.5 |  |  | 901 |  |  | 903 |  |  | 956 |  |  | 958 |  |  | 963.5 |  |  | 879 |  |  | 922 |  |  | 907 |  |  | 852.5 |  |  | 1039 |  |  | 906 |  |  | 916 |  |  | 871 |  |  | 950.5 |  |  | 857.5 |  |  | 909 |  |  | 905 |  |  | 948 |  |  | 926.5 |  |  | 934 |  |  | 865 |  |  | 824 |  |  | 965.5 |  |  | 866.5 |  |  | 932.5 |  |  | 860 |  |  | 977 |  |  | 909 |  |  | 909.5 |  |  | 920 |  |  | 890.5 |  |  | 780 |  |  | 863 |  |  | 930 |  |  | 867.5 |  |  | 966.5 |  |  | 902 |  |  | 848 |  |  | 945.5 |  |  | 869 |  |  | 917 |  |  | 949.5 |  |  | 915 |  |  | 887 |  |  | 961.5 |  |  | 806 |  |  | 953 |  |  | 892.5 |  |  | 889 |  |  | 902.5 |  |  | 944 |  |  | 825.5 |  |  | 954.5 |  |  | 821 |  |  | 937 |  |  | 899.5 |  |  | 888.5 |  |  | 942 |  |  | 876 |  |  | 931 |  |  | 894.5 |  |  | 938 |  |  | 882 |  |  | 937 |  |  | 972.5 |  |  | 877.5 |  |  | 872 |  |  | 1026 |  |  | 927 |  |  | 900 |  |  | 939 |  |  | 873 |  |  | 932 |  |  | 853.5 |  |  | 886.5 |  |  | 889.5 |  |  | 879 |  |  | 870.5 |  |  | 876 |  |  | 856 |  |  | 923.5 |  |  | 853.5 |  |  | 779 |  |  | 907 |  |  | 766.5 |  |  | 859 |  |  | 882 |  |  | 840.5 |  |  | 889.5 |  |  | 945 |  |  | 946 |  |  | 909 |  |  | 813.5 |  |  | 842 |  |  | 854 |  |  | 898 |  |  | 846 |  |  | 950 |  |  | 916.5 |  |  | 874 |  |  | 828 |  |  | 805 |  |  | 963.5 |  |  | 978 |  |  | 924.5 |  |  | 905.5 |  |  | 902 |  |  | 877 |  |  | 907.5 |  |  | 830.5 |  |  | 904.5 |  |  | 869.5 |  |  | 923.5 |  |  | 977 |  |  | 887 |  |  | 963.5 |  |  | 892.5 |  |  | 921 |  |  | 835 |  |  | 926.5 |  |  | 896 |  |  | 878 |  |  | 863 |  |  | 914.5 |  |  | 914 |  |  | 866.5 |  |  | 865 |  |  | 926.5 |  |  | 940.5 |  |  | 973.5 |  |  | 903 |  |  | 863 |  |  | 902.5 |  |  | 929.5 |  |  | 929 |  |  | 887 |  |  | 837.5 |  |  | 925 |  |  | 885.5 |  |  | 922.5 |  |  | 891 |  |  | 883 |  |  | 872.5 |  |  | 940.5 |  |  | 857 |  |  | 877.5 |  |  | 942.5 |  |  | 880 |  |  | 906 |  |  | 973 |  |  | 914.5 |  |  | 920 |  |  | 906 |  |  | 890 |  |  | 895 |  |  | 954 |  |  | 819 |  |  | 931.5 |  |  | 900.5 |  |  | 877 |  |  | 825 |  |  | 869 |  |  | 931.5 |  |  | 893 |  |  | 949 |  |  | 838.5 |  |  | 889.5 |  |  | 853 |  |  | 893.5 |  |  | 909 |  |  | 881 |  |  | 911 |  |  | 919.5 |  |  | 1019 |  |  | 918.5 |  |  | 833.5 |  |  | 851 |  |  | 934.5 |  |  | 832.5 |  |  | 816 |  |  | 836 |  |  | 968 |  |  | 880.5 |  |  | 858 |  |  | 863.5 |  |  | 920.5 |  |  | 930 |  |  | 861.5 |  |  | 904 |  |  | 941 |  |  | 889 |  |  | 829 |  |  | 841 |  |  | 954.5 |  |  | 940 |  |  | 947 |  |  | 839 |  |  | 992 |  |  | 876.5 |  |  | 1003.5 |  |  | 891 |  |  | 890 |  |  | 909 |  |  | 867 |  |  | 908 |  |  | 917.5 |  |  | 970 |  |  | 871.5 |  |  | 1011 |  |  | 849 |  |  | 905 |  |  | 863 |  |  | 863.5 |  |  | 891 |  |  | 899.5 |  |  | 821 |  |  | 948 |  |  | 971 |  |  | 886.5 |  |  | 909 |  |  | 878 |  |  | 834 |  |  | 1073 |  |  | 966 |  |  | 910.5 |  |  | 897.5 |  |  | 866 |  |  | 835.5 |  |  | 853 |  |  | 859.5 |  |  | 935.5 |  |  | 875.5 |  |  | 866.5 |  |  | 859 |  |  | 953 |  |  | 863 |  |  | 857 |  |  | 934 |  |  | 872 |  |  | 872.5 |  |  | 869.5 |  |  | 909.5 |  |  | 963 |  |  | 907.5 |  |  | 933.5 |  |  | 951.5 |  |  | 893.5 |  |  | 876 |  |  | 877.5 |  |  | 888.5 |  |  | 934 |  |  | 950.5 |  |  | 910.5 |  |  | 936.5 |  |  | 957 |  |  | 913.5 |  |  | 931 |  |  | 863 |  |  | 901.5 |  |  | 914.5 |  |  | 887 |  |  | 926 |  |  | 866.5 |  |  | 819.5 |  |  | 979.5 |  |  | 944 |  |  | 936 |  |  | 925 |  |  | 896.5 |  |  | 895.5 |  |  | 883 |  |  | 942.5 |  |  | 863 |  |  | 882 |  |  | 915.5 |  |  | 840.5 |  |  | 898 |  |  | 889.5 |  |  | 920 |  |  | 858.5 |  |  | 940.5 |  |  | 899 |  |  | 865.5 |  |  | 891 |  |  | 928.5 |  |  | 879 |  |  | 976 |  |  | 955 |  |  | 878.5 |  |  | 826.5 |  |  | 940 |  |  | 835 |  |  | 832 |  |  | 923.5 |  |  | 859.5 |  |  | 881 |  |  | 944.5 |  |  | 915 |  |  | 912.5 |  |  | 866.5 |  |  | 797 |  |  | 925 |  |  | 895 |  |  | 889.5 |  |  | 843 |  |  | 938.5 |  |  | 901 |  |  | 866.5 |  |  | 967 |  |  | 834.5 |  |  | 878 |  |  | 841.5 |  |  | 880.5 |  |  | 875 |  |  | 875 |  |  | 885 |  |  | 902 |  |  | 876.5 |  |  | 853 |  |  | 818.5 |  |  | 841 |  |  | 968 |  |  | 943 |  |  | 977 |  |  | 940 |  |  | 911 |  |  | 853 |  |  | 897.5 |  |  | 861 |  |  | 938
34 |  | 995.5 |  |  | 932 |  |  | 933.5 |  |  | 935 |  |  | 906.5 |  |  | 932 |  |  | 928 |  |  | 949 |  |  | 960.5 |  |  | 919 |  |  | 957 |  |  | 1018 |  |  | 930 |  |  | 1008 |  |  | 920.5 |  |  | 981.5 |  |  | 905 |  |  | 946 |  |  | 963 |  |  | 809.5 |  |  | 955 |  |  | 953 |  |  | 967 |  |  | 969 |  |  | 882.5 |  |  | 990 |  |  | 1010 |  |  | 907 |  |  | 914 |  |  | 949 |  |  | 875 |  |  | 943.5 |  |  | 1052.5 |  |  | 920.5 |  |  | 901 |  |  | 887.5 |  |  | 928.5 |  |  | 911.5 |  |  | 937 |  |  | 966 |  |  | 861.5 |  |  | 886 |  |  | 1019.5 |  |  | 943.5 |  |  | 969.5 |  |  | 974.5 |  |  | 972.5 |  |  | 909 |  |  | 853 |  |  | 824.5 |  |  | 964 |  |  | 915.5 |  |  | 884.5 |  |  | 1007 |  |  | 898 |  |  | 904 |  |  | 959 |  |  | 988 |  |  | 948 |  |  | 927.5 |  |  | 1054.5 |  |  | 972.5 |  |  | 858 |  |  | 949 |  |  | 849 |  |  | 857.5 |  |  | 947 |  |  | 976.5 |  |  | 922.5 |  |  | 976.5 |  |  | 896 |  |  | 951 |  |  | 924 |  |  | 905.5 |  |  | 974.5 |  |  | 909.5 |  |  | 960.5 |  |  | 966.5 |  |  | 974.5 |  |  | 950.5 |  |  | 958.5 |  |  | 946 |  |  | 899 |  |  | 954 |  |  | 965.5 |  |  | 907 |  |  | 845.5 |  |  | 909 |  |  | 895 |  |  | 987.5 |  |  | 964.5 |  |  | 959 |  |  | 1091 |  |  | 906.5 |  |  | 917 |  |  | 899.5 |  |  | 952.5 |  |  | 931.5 |  |  | 931.5 |  |  | 858.5 |  |  | 968 |  |  | 858 |  |  | 917 |  |  | 955.5 |  |  | 903.5 |  |  | 935.5 |  |  | 899.5 |  |  | 901 |  |  | 946 |  |  | 944.5 |  |  | 882 |  |  | 950.5 |  |  | 974 |  |  | 974 |  |  | 944.5 |  |  | 936 |  |  | 947 |  |  | 904 |  |  | 877 |  |  | 1012.5 |  |  | 1001.5 |  |  | 852.5 |  |  | 1016 |  |  | 875 |  |  | 872 |  |  | 923 |  |  | 949.5 |  |  | 907 |  |  | 920.5 |  |  | 962 |  |  | 916 |  |  | 989.5 |  |  | 836.5 |  |  | 807 |  |  | 912.5 |  |  | 928 |  |  | 982 |  |  | 950 |  |  | 946 |  |  | 935 |  |  | 898 |  |  | 899 |  |  | 940 |  |  | 905 |  |  | 882.5 |  |  | 884 |  |  | 874 |  |  | 907 |  |  | 923 |  |  | 871 |  |  | 884 |  |  | 987 |  |  | 935.5 |  |  | 964 |  |  | 926.5 |  |  | 927 |  |  | 890 |  |  | 987.5 |  |  | 897 |  |  | 1012.5 |  |  | 927 |  |  | 850 |  |  | 937.5 |  |  | 837 |  |  | 948.5 |  |  | 867 |  |  | 895 |  |  | 892.5 |  |  | 934.5 |  |  | 968 |  |  | 914.5 |  |  | 867.5 |  |  | 896 |  |  | 937 |  |  | 1000.5 |  |  | 928.5 |  |  | 925.5 |  |  | 922 |  |  | 1008 |  |  | 901 |  |  | 1011 |  |  | 945 |  |  | 962.5 |  |  | 900 |  |  | 876.5 |  |  | 994.5 |  |  | 981 |  |  | 904 |  |  | 948.5 |  |  | 876.5 |  |  | 888 |  |  | 957.5 |  |  | 930.5 |  |  | 896 |  |  | 920 |  |  | 921 |  |  | 871.5 |  |  | 980 |  |  | 980.5 |  |  | 892.5 |  |  | 903 |  |  | 984.5 |  |  | 903 |  |  | 943 |  |  | 974 |  |  | 1001 |  |  | 911 |  |  | 945 |  |  | 995 |  |  | 977 |  |  | 1032 |  |  | 887 |  |  | 935.5 |  |  | 952.5 |  |  | 898 |  |  | 792 |  |  | 960 |  |  | 931.5 |  |  | 969.5 |  |  | 985.5 |  |  | 898 |  |  | 938 |  |  | 978.5 |  |  | 893.5 |  |  | 838.5 |  |  | 986 |  |  | 1011 |  |  | 919 |  |  | 895 |  |  | 907 |  |  | 907.5 |  |  | 842.5 |  |  | 964 |  |  | 952 |  |  | 938 |  |  | 957 |  |  | 851 |  |  | 876.5 |  |  | 904 |  |  | 999 |  |  | 972 |  |  | 925 |  |  | 886.5 |  |  | 1014 |  |  | 947 |  |  | 898 |  |  | 1005 |  |  | 993.5 |  |  | 940 |  |  | 867 |  |  | 870 |  |  | 971.5 |  |  | 980.5 |  |  | 926.5 |  |  | 1008 |  |  | 893 |  |  | 884 |  |  | 988 |  |  | 958 |  |  | 917.5 |  |  | 973 |  |  | 934.5 |  |  | 939.5 |  |  | 974.5 |  |  | 920 |  |  | 993.5 |  |  | 910 |  |  | 902 |  |  | 900.5 |  |  | 942.5 |  |  | 1014 |  |  | 1048.5 |  |  | 1005.5 |  |  | 936 |  |  | 992 |  |  | 921.5 |  |  | 904.5 |  |  | 927 |  |  | 900.5 |  |  | 1006 |  |  | 887 |  |  | 932.5 |  |  | 955 |  |  | 839 |  |  | 955.5 |  |  | 921 |  |  | 984.5 |  |  | 941 |  |  | 997 |  |  | 911 |  |  | 852 |  |  | 976.5 |  |  | 988 |  |  | 960.5 |  |  | 921.5 |  |  | 929.5 |  |  | 1007 |  |  | 969.5 |  |  | 1033 |  |  | 957 |  |  | 900.5 |  |  | 946.5 |  |  | 951 |  |  | 907.5 |  |  | 922 |  |  | 944 |  |  | 1003.5 |  |  | 945 |  |  | 926.5 |  |  | 985.5 |  |  | 975.5 |  |  | 948 |  |  | 884 |  |  | 993 |  |  | 844.5 |  |  | 905 |  |  | 914.5 |  |  | 950 |  |  | 935 |  |  | 832 |  |  | 908 |  |  | 992 |  |  | 907 |  |  | 934 |  |  | 1013 |  |  | 975 |  |  | 951.5 |  |  | 927 |  |  | 844 |  |  | 1050.5 |  |  | 886.5 |  |  | 972.5 |  |  | 1006.5 |  |  | 933 |  |  | 988 |  |  | 842.5 |  |  | 973.5 |  |  | 1004.5 |  |  | 994 |  |  | 879 |  |  | 933 |  |  | 939 |  |  | 871 |  |  | 934 |  |  | 903 |  |  | 923.5 |  |  | 910.5 |  |  | 913 |  |  | 972.5 |  |  | 937.5 |  |  | 923 |  |  | 956 |  |  | 929 |  |  | 941 |  |  | 911.5 |  |  | 876.5 |  |  | 910.5 |  |  | 912 |  |  | 904.5 |  |  | 922 |  |  | 912 |  |  | 914 |  |  | 888.5 |  |  | 992 |  |  | 848 |  |  | 918.5 |  |  | 929 |  |  | 929.5 |  |  | 984 |  |  | 959.5 |  |  | 887 |  |  | 863.5 |  |  | 962.5 |  |  | 1001 |  |  | 883 |  |  | 845 |  |  | 910 |  |  | 932.5 |  |  | 891 |  |  | 974 |  |  | 896.5 |  |  | 1004.5 |  |  | 894.5 |  |  | 954 |  |  | 898.5 |  |  | 941.5 |  |  | 937.5 |  |  | 1017 |  |  | 959 |  |  | 915.5 |  |  | 905 |  |  | 971 |  |  | 908.5 |  |  | 865 |  |  | 947 |  |  | 940 |  |  | 874 |  |  | 893.5 |  |  | 974.5 |  |  | 890 |  |  | 1015 |  |  | 932 |  |  | 925 |  |  | 909 |  |  | 914.5 |  |  | 926.5 |  |  | 930 |  |  | 1027 |  |  | 1021 |  |  | 865.5 |  |  | 996.5 |  |  | 910 |  |  | 888 |  |  | 903 |  |  | 928.5 |  |  | 1003.5 |  |  | 959 |  |  | 886 |  |  | 975 |  |  | 940 |  |  | 885 |  |  | 986 |  |  | 925 |  |  | 940.5 |  |  | 825 |  |  | 1030 |  |  | 950 |  |  | 949.5 |  |  | 1024 |  |  | 848 |  |  | 819 |  |  | 981 |  |  | 978 |  |  | 928 |  |  | 885 |  |  | 891.5 |  |  | 949.5 |  |  | 889.5 |  |  | 918 |  |  | 995 |  |  | 964.5 |  |  | 908 |  |  | 924.5 |  |  | 923.5 |  |  | 852 |  |  | 865 |  |  | 1025.5 |  |  | 945 |  |  | 968 |  |  | 967 |  |  | 939 |  |  | 892 |  |  | 896 |  |  | 928 |  |  | 1017.5 |  |  | 945 |  |  | 872 |  |  | 937 |  |  | 896 |  |  | 953 |  |  | 835 |  |  | 996 |  |  | 971 |  |  | 950 |  |  | 1013.5 |  |  | 938.5 |  |  | 872.5 |  |  | 942.5 |  |  | 959 |  |  | 904 |  |  | 973.5 |  |  | 887 |  |  | 920 |  |  | 923.5 |  |  | 959.5 |  |  | 973 |  |  | 928.5 |  |  | 930.5 |  |  | 881 |  |  | 942 |  |  | 870 |  |  | 997 |  |  | 971.5 |  |  | 909 |  |  | 923.5 |  |  | 910.5 |  |  | 865 |  |  | 952 |  |  | 942.5 |  |  | 932 |  |  | 971.5 |  |  | 892 |  |  | 945.5 |  |  | 842.5 |  |  | 906.5 |  |  | 956.5 |  |  | 942.5 |  |  | 955 |  |  | 964 |  |  | 1062.5 |  |  | 975 |  |  | 873 |  |  | 958 |  |  | 959 |  |  | 970.5 |  |  | 883 |  |  | 923 |  |  | 952 |  |  | 960.5 |  |  | 914 |  |  | 922 |  |  | 953 |  |  | 1029.5 |  |  | 962 |  |  | 815 |  |  | 909 |  |  | 955 |  |  | 1038.5 |  |  | 912 |  |  | 877.5 |  |  | 967 |  |  | 996 |  |  | 1041.5 |  |  | 961 |  |  | 909 |  |  | 827.5 |  |  | 931 |  |  | 847 |  |  | 964 |  |  | 949.5 |  |  | 897.5 |  |  | 948 |  |  | 897 |  |  | 931.5 |  |  | 923.5 |  |  | 879 |  |  | 952 |  |  | 953.5 |  |  | 935.5 |  |  | 875.5 |  |  | 894.5 |  |  | 965.5 |  |  | 975 |  |  | 944.5 |  |  | 936 |  |  | 936 |  |  | 933 |  |  | 945 |  |  | 951.5 |  |  | 866 |  |  | 872 |  |  | 912.5 |  |  | 916.5 |  |  | 867 |  |  | 890.5 |  |  | 903.5 |  |  | 970 |  |  | 929 |  |  | 921 |  |  | 896.5 |  |  | 946 |  |  | 954.5 |  |  | 944 |  |  | 1007 |  |  | 1005.5 |  |  | 909 |  |  | 1037 |  |  | 909 |  |  | 953 |  |  | 972 |  |  | 910 |  |  | 855 |  |  | 895 |  |  | 886.5 |  |  | 951.5 |  |  | 941 |  |  | 949.5 |  |  | 854.5 |  |  | 893 |  |  | 817 |  |  | 945 |  |  | 970.5 |  |  | 903.5 |  |  | 918 |  |  | 1013 |  |  | 864 |  |  | 805 |  |  | 960 |  |  | 902 |  |  | 1031 |  |  | 937.5 |  |  | 973 |  |  | 911 |  |  | 1048 |  |  | 890 |  |  | 913 |  |  | 951.5 |  |  | 1023.5 |  |  | 822.5 |  |  | 893 |  |  | 891 |  |  | 932.5 |  |  | 998.5 |  |  | 948.5 |  |  | 943 |  |  | 995.5 |  |  | 952.5 |  |  | 876 |  |  | 873.5 |  |  | 973.5 |  |  | 922 |  |  | 893 |  |  | 936 |  |  | 910 |  |  | 970 |  |  | 888 |  |  | 949 |  |  | 1016 |  |  | 888 |  |  | 851 |  |  | 965.5 |  |  | 986 |  |  | 992 |  |  | 862 |  |  | 945.5 |  |  | 975 |  |  | 919.5 |  |  | 948 |  |  | 951 |  |  | 912 |  |  | 923 |  |  | 968.5 |  |  | 914 |  |  | 888 |  |  | 1051.5 |  |  | 958 |  |  | 900 |  |  | 862.5 |  |  | 930.5 |  |  | 1040 |  |  | 877.5 |  |  | 945 |  |  | 927.5 |  |  | 954 |  |  | 911 |  |  | 931.5 |  |  | 1009.5 |  |  | 989 |  |  | 944 |  |  | 963 |  |  | 940 |  |  | 853 |  |  | 966 |  |  | 889 |  |  | 881 |  |  | 1010.5 |  |  | 875 |  |  | 967.5 |  |  | 951 |  |  | 971.5 |  |  | 933.5 |  |  | 927 |  |  | 959 |  |  | 963.5 |  |  | 995 |  |  | 918 |  |  | 954 |  |  | 913.5 |  |  | 976 |  |  | 853.5 |  |  | 922 |  |  | 942 |  |  | 982 |  |  | 982 |  |  | 978.5 |  |  | 900 |  |  | 951 |  |  | 946 |  |  | 876.5 |  |  | 1065 |  |  | 945 |  |  | 955 |  |  | 886 |  |  | 974.5 |  |  | 896.5 |  |  | 938 |  |  | 929 |  |  | 972 |  |  | 947.5 |  |  | 955 |  |  | 889 |  |  | 871 |  |  | 1004.5 |  |  | 895.5 |  |  | 961.5 |  |  | 907 |  |  | 1016 |  |  | 948 |  |  | 935.5 |  |  | 941 |  |  | 929.5 |  |  | 804 |  |  | 892 |  |  | 969 |  |  | 891.5 |  |  | 992.5 |  |  | 931 |  |  | 863 |  |  | 984.5 |  |  | 895 |  |  | 964 |  |  | 970.5 |  |  | 962 |  |  | 902 |  |  | 987.5 |  |  | 827 |  |  | 1000 |  |  | 916.5 |  |  | 913 |  |  | 928.5 |  |  | 973 |  |  | 854.5 |  |  | 975.5 |  |  | 860 |  |  | 976 |  |  | 946.5 |  |  | 927.5 |  |  | 989 |  |  | 915 |  |  | 970 |  |  | 933.5 |  |  | 964 |  |  | 906 |  |  | 984 |  |  | 993.5 |  |  | 916.5 |  |  | 911 |  |  | 1047 |  |  | 953 |  |  | 939 |  |  | 968 |  |  | 899 |  |  | 958 |  |  | 882.5 |  |  | 915.5 |  |  | 915.5 |  |  | 908 |  |  | 891.5 |  |  | 915 |  |  | 880 |  |  | 962.5 |  |  | 879.5 |  |  | 805 |  |  | 946 |  |  | 805.5 |  |  | 880 |  |  | 921 |  |  | 855.5 |  |  | 913.5 |  |  | 974 |  |  | 993 |  |  | 948 |  |  | 842.5 |  |  | 881 |  |  | 878 |  |  | 913 |  |  | 872 |  |  | 997 |  |  | 963.5 |  |  | 895 |  |  | 852 |  |  | 820 |  |  | 992.5 |  |  | 993 |  |  | 939.5 |  |  | 944.5 |  |  | 941 |  |  | 924 |  |  | 946.5 |  |  | 851.5 |  |  | 919.5 |  |  | 884.5 |  |  | 949.5 |  |  | 1024 |  |  | 908 |  |  | 984.5 |  |  | 907.5 |  |  | 942 |  |  | 861 |  |  | 947.5 |  |  | 920 |  |  | 917 |  |  | 878 |  |  | 943.5 |  |  | 961 |  |  | 881.5 |  |  | 912 |  |  | 947.5 |  |  | 979.5 |  |  | 997.5 |  |  | 929 |  |  | 884 |  |  | 923.5 |  |  | 944.5 |  |  | 944 |  |  | 916 |  |  | 884.5 |  |  | 946 |  |  | 906.5 |  |  | 943.5 |  |  | 917 |  |  | 930 |  |  | 887.5 |  |  | 987.5 |  |  | 886 |  |  | 906.5 |  |  | 981.5 |  |  | 909 |  |  | 945 |  |  | 1012 |  |  | 953.5 |  |  | 967 |  |  | 921 |  |  | 916 |  |  | 934 |  |  | 993 |  |  | 845 |  |  | 970.5 |  |  | 924.5 |  |  | 892 |  |  | 854 |  |  | 908 |  |  | 946.5 |  |  | 917 |  |  | 964 |  |  | 864.5 |  |  | 928.5 |  |  | 879 |  |  | 914.5 |  |  | 924 |  |  | 920 |  |  | 926 |  |  | 958.5 |  |  | 1045 |  |  | 944.5 |  |  | 880.5 |  |  | 880 |  |  | 973.5 |  |  | 847.5 |  |  | 840 |  |  | 860 |  |  | 1007 |  |  | 895.5 |  |  | 873 |  |  | 910.5 |  |  | 967.5 |  |  | 977 |  |  | 890.5 |  |  | 933 |  |  | 962 |  |  | 928 |  |  | 853 |  |  | 880 |  |  | 993.5 |  |  | 969 |  |  | 968 |  |  | 878 |  |  | 1039 |  |  | 902.5 |  |  | 1032.5 |  |  | 915 |  |  | 905 |  |  | 938 |  |  | 896 |  |  | 947 |  |  | 946.5 |  |  | 1009 |  |  | 886.5 |  |  | 1035 |  |  | 870 |  |  | 934 |  |  | 902 |  |  | 889.5 |  |  | 906 |  |  | 920.5 |  |  | 850 |  |  | 995 |  |  | 986 |  |  | 925.5 |  |  | 948 |  |  | 904 |  |  | 873 |  |  | 1097 |  |  | 1013 |  |  | 936.5 |  |  | 936.5 |  |  | 890 |  |  | 882.5 |  |  | 868 |  |  | 888.5 |  |  | 974.5 |  |  | 922.5 |  |  | 913.5 |  |  | 883 |  |  | 992 |  |  | 902 |  |  | 872 |  |  | 963 |  |  | 887 |  |  | 896.5 |  |  | 895.5 |  |  | 935.5 |  |  | 1002 |  |  | 922.5 |  |  | 948.5 |  |  | 980.5 |  |  | 932.5 |  |  | 923 |  |  | 906.5 |  |  | 903.5 |  |  | 960 |  |  | 979.5 |  |  | 949.5 |  |  | 957.5 |  |  | 1004 |  |  | 952.5 |  |  | 955 |  |  | 902 |  |  | 940.5 |  |  | 938.5 |  |  | 934 |  |  | 965 |  |  | 887.5 |  |  | 843.5 |  |  | 1003.5 |  |  | 973 |  |  | 962 |  |  | 972 |  |  | 917.5 |  |  | 924.5 |  |  | 922 |  |  | 963.5 |  |  | 878 |  |  | 911 |  |  | 930.5 |  |  | 864.5 |  |  | 913 |  |  | 918.5 |  |  | 944 |  |  | 879.5 |  |  | 987.5 |  |  | 925 |  |  | 891.5 |  |  | 917 |  |  | 957.5 |  |  | 926 |  |  | 1002 |  |  | 994 |  |  | 907.5 |  |  | 865.5 |  |  | 969 |  |  | 861 |  |  | 853 |  |  | 944.5 |  |  | 883.5 |  |  | 907 |  |  | 965.5 |  |  | 941 |  |  | 951.5 |  |  | 913.5 |  |  | 823 |  |  | 964 |  |  | 919 |  |  | 904.5 |  |  | 890 |  |  | 967.5 |  |  | 948 |  |  | 905.5 |  |  | 982 |  |  | 860.5 |  |  | 917 |  |  | 888.5 |  |  | 927.5 |  |  | 901 |  |  | 914 |  |  | 932 |  |  | 923 |  |  | 923.5 |  |  | 892 |  |  | 844.5 |  |  | 880 |  |  | 992 |  |  | 972 |  |  | 992 |  |  | 979 |  |  | 940 |  |  | 879 |  |  | 921.5 |  |  | 882 |  |  | 977
35 |  | 1010.5 |  |  | 958 |  |  | 980.5 |  |  | 982 |  |  | 945.5 |  |  | 956 |  |  | 952 |  |  | 988 |  |  | 999.5 |  |  | 948 |  |  | 981 |  |  | 1044 |  |  | 951 |  |  | 1047 |  |  | 941.5 |  |  | 1020.5 |  |  | 926 |  |  | 975 |  |  | 1010 |  |  | 833.5 |  |  | 981 |  |  | 1000 |  |  | 993 |  |  | 993 |  |  | 921.5 |  |  | 1029 |  |  | 1031 |  |  | 933 |  |  | 953 |  |  | 996 |  |  | 914 |  |  | 958.5 |  |  | 1091.5 |  |  | 959.5 |  |  | 922 |  |  | 926.5 |  |  | 943.5 |  |  | 958.5 |  |  | 963 |  |  | 1005 |  |  | 890.5 |  |  | 925 |  |  | 1058.5 |  |  | 990.5 |  |  | 990.5 |  |  | 1003.5 |  |  | 996.5 |  |  | 956 |  |  | 868 |  |  | 863.5 |  |  | 979 |  |  | 936.5 |  |  | 923.5 |  |  | 1028 |  |  | 937 |  |  | 925 |  |  | 980 |  |  | 1035 |  |  | 987 |  |  | 948.5 |  |  | 1069.5 |  |  | 996.5 |  |  | 897 |  |  | 978 |  |  | 896 |  |  | 904.5 |  |  | 973 |  |  | 1023.5 |  |  | 937.5 |  |  | 1023.5 |  |  | 911 |  |  | 972 |  |  | 945 |  |  | 952.5 |  |  | 1003.5 |  |  | 930.5 |  |  | 986.5 |  |  | 1005.5 |  |  | 1000.5 |  |  | 979.5 |  |  | 997.5 |  |  | 967 |  |  | 920 |  |  | 980 |  |  | 1012.5 |  |  | 954 |  |  | 884.5 |  |  | 948 |  |  | 934 |  |  | 1016.5 |  |  | 979.5 |  |  | 998 |  |  | 1112 |  |  | 953.5 |  |  | 964 |  |  | 938.5 |  |  | 999.5 |  |  | 957.5 |  |  | 946.5 |  |  | 879.5 |  |  | 997 |  |  | 905 |  |  | 938 |  |  | 1002.5 |  |  | 932.5 |  |  | 964.5 |  |  | 938.5 |  |  | 948 |  |  | 972 |  |  | 983.5 |  |  | 921 |  |  | 989.5 |  |  | 998 |  |  | 1003 |  |  | 959.5 |  |  | 975 |  |  | 971 |  |  | 943 |  |  | 892 |  |  | 1041.5 |  |  | 1025.5 |  |  | 878.5 |  |  | 1040 |  |  | 901 |  |  | 901 |  |  | 952 |  |  | 996.5 |  |  | 954 |  |  | 946.5 |  |  | 977 |  |  | 931 |  |  | 1018.5 |  |  | 883.5 |  |  | 854 |  |  | 936.5 |  |  | 967 |  |  | 997 |  |  | 997 |  |  | 972 |  |  | 950 |  |  | 937 |  |  | 914 |  |  | 969 |  |  | 920 |  |  | 911.5 |  |  | 899 |  |  | 900 |  |  | 936 |  |  | 938 |  |  | 910 |  |  | 923 |  |  | 1016 |  |  | 950.5 |  |  | 985 |  |  | 952.5 |  |  | 948 |  |  | 905 |  |  | 1013.5 |  |  | 923 |  |  | 1051.5 |  |  | 966 |  |  | 871 |  |  | 963.5 |  |  | 861 |  |  | 987.5 |  |  | 882 |  |  | 934 |  |  | 907.5 |  |  | 949.5 |  |  | 989 |  |  | 938.5 |  |  | 893.5 |  |  | 943 |  |  | 961 |  |  | 1039.5 |  |  | 952.5 |  |  | 940.5 |  |  | 961 |  |  | 1034 |  |  | 925 |  |  | 1040 |  |  | 984 |  |  | 1001.5 |  |  | 939 |  |  | 905.5 |  |  | 1015.5 |  |  | 1020 |  |  | 933 |  |  | 995.5 |  |  | 891.5 |  |  | 927 |  |  | 983.5 |  |  | 969.5 |  |  | 943 |  |  | 935 |  |  | 950 |  |  | 910.5 |  |  | 995 |  |  | 1001.5 |  |  | 939.5 |  |  | 927 |  |  | 1031.5 |  |  | 942 |  |  | 972 |  |  | 995 |  |  | 1016 |  |  | 940 |  |  | 966 |  |  | 1019 |  |  | 992 |  |  | 1058 |  |  | 934 |  |  | 982.5 |  |  | 973.5 |  |  | 922 |  |  | 821 |  |  | 986 |  |  | 970.5 |  |  | 984.5 |  |  | 1024.5 |  |  | 937 |  |  | 962 |  |  | 999.5 |  |  | 914.5 |  |  | 862.5 |  |  | 1015 |  |  | 1058 |  |  | 940 |  |  | 921 |  |  | 936 |  |  | 931.5 |  |  | 881.5 |  |  | 988 |  |  | 991 |  |  | 985 |  |  | 981 |  |  | 872 |  |  | 923.5 |  |  | 925 |  |  | 1046 |  |  | 996 |  |  | 964 |  |  | 901.5 |  |  | 1043 |  |  | 986 |  |  | 937 |  |  | 1044 |  |  | 1019.5 |  |  | 979 |  |  | 906 |  |  | 885 |  |  | 1018.5 |  |  | 995.5 |  |  | 947.5 |  |  | 1037 |  |  | 940 |  |  | 923 |  |  | 1017 |  |  | 984 |  |  | 932.5 |  |  | 1012 |  |  | 960.5 |  |  | 960.5 |  |  | 1013.5 |  |  | 944 |  |  | 1014.5 |  |  | 931 |  |  | 931 |  |  | 947.5 |  |  | 981.5 |  |  | 1038 |  |  | 1063.5 |  |  | 1026.5 |  |  | 975 |  |  | 1016 |  |  | 960.5 |  |  | 943.5 |  |  | 966 |  |  | 924.5 |  |  | 1030 |  |  | 916 |  |  | 947.5 |  |  | 984 |  |  | 878 |  |  | 1002.5 |  |  | 942 |  |  | 1013.5 |  |  | 967 |  |  | 1026 |  |  | 958 |  |  | 878 |  |  | 1002.5 |  |  | 1027 |  |  | 989.5 |  |  | 945.5 |  |  | 976.5 |  |  | 1028 |  |  | 1008.5 |  |  | 1059 |  |  | 983 |  |  | 921.5 |  |  | 970.5 |  |  | 990 |  |  | 954.5 |  |  | 943 |  |  | 965 |  |  | 1050.5 |  |  | 971 |  |  | 952.5 |  |  | 1006.5 |  |  | 1014.5 |  |  | 995 |  |  | 905 |  |  | 1022 |  |  | 883.5 |  |  | 920 |  |  | 961.5 |  |  | 979 |  |  | 961 |  |  | 853 |  |  | 955 |  |  | 1031 |  |  | 922 |  |  | 955 |  |  | 1042 |  |  | 1014 |  |  | 980.5 |  |  | 951 |  |  | 859 |  |  | 1097.5 |  |  | 912.5 |  |  | 1019.5 |  |  | 1030.5 |  |  | 959 |  |  | 1012 |  |  | 881.5 |  |  | 994.5 |  |  | 1028.5 |  |  | 1020 |  |  | 926 |  |  | 959 |  |  | 965 |  |  | 886 |  |  | 955 |  |  | 924 |  |  | 944.5 |  |  | 949.5 |  |  | 942 |  |  | 993.5 |  |  | 961.5 |  |  | 944 |  |  | 980 |  |  | 968 |  |  | 965 |  |  | 950.5 |  |  | 902.5 |  |  | 925.5 |  |  | 951 |  |  | 943.5 |  |  | 961 |  |  | 933 |  |  | 929 |  |  | 927.5 |  |  | 1031 |  |  | 863 |  |  | 947.5 |  |  | 968 |  |  | 968.5 |  |  | 999 |  |  | 998.5 |  |  | 908 |  |  | 910.5 |  |  | 1001.5 |  |  | 1022 |  |  | 922 |  |  | 869 |  |  | 949 |  |  | 956.5 |  |  | 938 |  |  | 1013 |  |  | 943.5 |  |  | 1025.5 |  |  | 920.5 |  |  | 975 |  |  | 937.5 |  |  | 970.5 |  |  | 966.5 |  |  | 1046 |  |  | 980 |  |  | 944.5 |  |  | 952 |  |  | 1018 |  |  | 947.5 |  |  | 904 |  |  | 994 |  |  | 961 |  |  | 900 |  |  | 908.5 |  |  | 1003.5 |  |  | 916 |  |  | 1030 |  |  | 956 |  |  | 946 |  |  | 948 |  |  | 929.5 |  |  | 965.5 |  |  | 956 |  |  | 1066 |  |  | 1060 |  |  | 889.5 |  |  | 1020.5 |  |  | 925 |  |  | 903 |  |  | 924 |  |  | 967.5 |  |  | 1024.5 |  |  | 985 |  |  | 933 |  |  | 1022 |  |  | 964 |  |  | 906 |  |  | 1015 |  |  | 964 |  |  | 979.5 |  |  | 864 |  |  | 1054 |  |  | 976 |  |  | 988.5 |  |  | 1063 |  |  | 872 |  |  | 840 |  |  | 1010 |  |  | 1017 |  |  | 975 |  |  | 909 |  |  | 915.5 |  |  | 988.5 |  |  | 915.5 |  |  | 947 |  |  | 1034 |  |  | 1003.5 |  |  | 947 |  |  | 963.5 |  |  | 970.5 |  |  | 899 |  |  | 904 |  |  | 1051.5 |  |  | 984 |  |  | 989 |  |  | 993 |  |  | 960 |  |  | 939 |  |  | 943 |  |  | 975 |  |  | 1043.5 |  |  | 960 |  |  | 896 |  |  | 976 |  |  | 917 |  |  | 992 |  |  | 882 |  |  | 1025 |  |  | 1010 |  |  | 979 |  |  | 1052.5 |  |  | 977.5 |  |  | 911.5 |  |  | 957.5 |  |  | 998 |  |  | 928 |  |  | 1020.5 |  |  | 934 |  |  | 959 |  |  | 938.5 |  |  | 985.5 |  |  | 988 |  |  | 957.5 |  |  | 951.5 |  |  | 896 |  |  | 966 |  |  | 909 |  |  | 1023 |  |  | 992.5 |  |  | 924 |  |  | 962.5 |  |  | 931.5 |  |  | 891 |  |  | 973 |  |  | 957.5 |  |  | 956 |  |  | 1018.5 |  |  | 939 |  |  | 984.5 |  |  | 871.5 |  |  | 945.5 |  |  | 995.5 |  |  | 981.5 |  |  | 970 |  |  | 993 |  |  | 1077.5 |  |  | 1014 |  |  | 920 |  |  | 984 |  |  | 998 |  |  | 991.5 |  |  | 904 |  |  | 944 |  |  | 991 |  |  | 984.5 |  |  | 940 |  |  | 946 |  |  | 982 |  |  | 1050.5 |  |  | 1001 |  |  | 841 |  |  | 935 |  |  | 979 |  |  | 1085.5 |  |  | 951 |  |  | 898.5 |  |  | 982 |  |  | 1025 |  |  | 1088.5 |  |  | 1000 |  |  | 930 |  |  | 851.5 |  |  | 955 |  |  | 894 |  |  | 988 |  |  | 996.5 |  |  | 912.5 |  |  | 987 |  |  | 923 |  |  | 970.5 |  |  | 962.5 |  |  | 903 |  |  | 991 |  |  | 1000.5 |  |  | 964.5 |  |  | 896.5 |  |  | 923.5 |  |  | 989.5 |  |  | 1014 |  |  | 973.5 |  |  | 965 |  |  | 957 |  |  | 962 |  |  | 992 |  |  | 975.5 |  |  | 892 |  |  | 887 |  |  | 959.5 |  |  | 955.5 |  |  | 896 |  |  | 929.5 |  |  | 942.5 |  |  | 1017 |  |  | 976 |  |  | 950 |  |  | 935.5 |  |  | 967 |  |  | 980.5 |  |  | 973 |  |  | 1031 |  |  | 1044.5 |  |  | 948 |  |  | 1061 |  |  | 930 |  |  | 977 |  |  | 998 |  |  | 925 |  |  | 881 |  |  | 910 |  |  | 915.5 |  |  | 975.5 |  |  | 980 |  |  | 996.5 |  |  | 878.5 |  |  | 917 |  |  | 856 |  |  | 992 |  |  | 1017.5 |  |  | 942.5 |  |  | 957 |  |  | 1052 |  |  | 903 |  |  | 852 |  |  | 981 |  |  | 923 |  |  | 1055 |  |  | 961.5 |  |  | 999 |  |  | 958 |  |  | 1063 |  |  | 916 |  |  | 928 |  |  | 972.5 |  |  | 1044.5 |  |  | 861.5 |  |  | 932 |  |  | 920 |  |  | 953.5 |  |  | 1045.5 |  |  | 977.5 |  |  | 967 |  |  | 1019.5 |  |  | 976.5 |  |  | 905 |  |  | 912.5 |  |  | 997.5 |  |  | 946 |  |  | 914 |  |  | 957 |  |  | 957 |  |  | 999 |  |  | 912 |  |  | 988 |  |  | 1055 |  |  | 935 |  |  | 890 |  |  | 994.5 |  |  | 1007 |  |  | 1007 |  |  | 886 |  |  | 974.5 |  |  | 990 |  |  | 958.5 |  |  | 995 |  |  | 977 |  |  | 933 |  |  | 962 |  |  | 1015.5 |  |  | 938 |  |  | 927 |  |  | 1066.5 |  |  | 997 |  |  | 939 |  |  | 909.5 |  |  | 954.5 |  |  | 1055 |  |  | 916.5 |  |  | 984 |  |  | 956.5 |  |  | 993 |  |  | 958 |  |  | 970.5 |  |  | 1048.5 |  |  | 1028 |  |  | 983 |  |  | 1002 |  |  | 961 |  |  | 868 |  |  | 990 |  |  | 904 |  |  | 896 |  |  | 1049.5 |  |  | 922 |  |  | 988.5 |  |  | 966 |  |  | 1018.5 |  |  | 957.5 |  |  | 974 |  |  | 980 |  |  | 1010.5 |  |  | 1010 |  |  | 957 |  |  | 993 |  |  | 952.5 |  |  | 1005 |  |  | 892.5 |  |  | 937 |  |  | 966 |  |  | 1008 |  |  | 1011 |  |  | 1025.5 |  |  | 924 |  |  | 972 |  |  | 985 |  |  | 923.5 |  |  | 1104 |  |  | 974 |  |  | 979 |  |  | 907 |  |  | 989.5 |  |  | 917.5 |  |  | 977 |  |  | 976 |  |  | 996 |  |  | 976.5 |  |  | 981 |  |  | 936 |  |  | 892 |  |  | 1043.5 |  |  | 916.5 |  |  | 990.5 |  |  | 931 |  |  | 1031 |  |  | 977 |  |  | 959.5 |  |  | 965 |  |  | 953.5 |  |  | 825 |  |  | 907 |  |  | 1008 |  |  | 938.5 |  |  | 1007.5 |  |  | 970 |  |  | 892 |  |  | 1010.5 |  |  | 924 |  |  | 1003 |  |  | 994.5 |  |  | 1001 |  |  | 949 |  |  | 1011.5 |  |  | 856 |  |  | 1029 |  |  | 937.5 |  |  | 952 |  |  | 952.5 |  |  | 999 |  |  | 880.5 |  |  | 1001.5 |  |  | 899 |  |  | 1015 |  |  | 993.5 |  |  | 951.5 |  |  | 1010 |  |  | 944 |  |  | 1017 |  |  | 972.5 |  |  | 1011 |  |  | 935 |  |  | 1023 |  |  | 1008.5 |  |  | 940.5 |  |  | 940 |  |  | 1073 |  |  | 977 |  |  | 978 |  |  | 1015 |  |  | 925 |  |  | 997 |  |  | 929.5 |  |  | 930.5 |  |  | 936.5 |  |  | 932 |  |  | 930.5 |  |  | 936 |  |  | 909 |  |  | 977.5 |  |  | 900.5 |  |  | 829 |  |  | 967 |  |  | 834.5 |  |  | 909 |  |  | 945 |  |  | 894.5 |  |  | 937.5 |  |  | 995 |  |  | 1008 |  |  | 977 |  |  | 889.5 |  |  | 920 |  |  | 899 |  |  | 937 |  |  | 919 |  |  | 1036 |  |  | 989.5 |  |  | 934 |  |  | 873 |  |  | 835 |  |  | 1021.5 |  |  | 1040 |  |  | 968.5 |  |  | 959.5 |  |  | 988 |  |  | 939 |  |  | 993.5 |  |  | 875.5 |  |  | 940.5 |  |  | 923.5 |  |  | 996.5 |  |  | 1050 |  |  | 934 |  |  | 1023.5 |  |  | 936.5 |  |  | 989 |  |  | 908 |  |  | 962.5 |  |  | 967 |  |  | 964 |  |  | 902 |  |  | 982.5 |  |  | 1000 |  |  | 896.5 |  |  | 938 |  |  | 971.5 |  |  | 1003.5 |  |  | 1036.5 |  |  | 955 |  |  | 908 |  |  | 952.5 |  |  | 970.5 |  |  | 983 |  |  | 937 |  |  | 913.5 |  |  | 975 |  |  | 945.5 |  |  | 967.5 |  |  | 938 |  |  | 969 |  |  | 926.5 |  |  | 1008.5 |  |  | 915 |  |  | 921.5 |  |  | 1007.5 |  |  | 924 |  |  | 992 |  |  | 1051 |  |  | 974.5 |  |  | 1006 |  |  | 950 |  |  | 942 |  |  | 973 |  |  | 1014 |  |  | 884 |  |  | 1009.5 |  |  | 939.5 |  |  | 931 |  |  | 880 |  |  | 947 |  |  | 961.5 |  |  | 943 |  |  | 1003 |  |  | 903.5 |  |  | 949.5 |  |  | 903 |  |  | 943.5 |  |  | 939 |  |  | 959 |  |  | 965 |  |  | 1005.5 |  |  | 1060 |  |  | 968.5 |  |  | 909.5 |  |  | 919 |  |  | 1002.5 |  |  | 862.5 |  |  | 866 |  |  | 907 |  |  | 1054 |  |  | 916.5 |  |  | 899 |  |  | 936.5 |  |  | 1006.5 |  |  | 1024 |  |  | 919.5 |  |  | 957 |  |  | 1001 |  |  | 954 |  |  | 877 |  |  | 906 |  |  | 1040.5 |  |  | 1008 |  |  | 983 |  |  | 904 |  |  | 1086 |  |  | 926.5 |  |  | 1056.5 |  |  | 954 |  |  | 934 |  |  | 964 |  |  | 922 |  |  | 994 |  |  | 993.5 |  |  | 1030 |  |  | 925.5 |  |  | 1064 |  |  | 899 |  |  | 973 |  |  | 928 |  |  | 936.5 |  |  | 930 |  |  | 949.5 |  |  | 879 |  |  | 1034 |  |  | 1015 |  |  | 972.5 |  |  | 987 |  |  | 951 |  |  | 912 |  |  | 1121 |  |  | 1052 |  |  | 975.5 |  |  | 965.5 |  |  | 929 |  |  | 921.5 |  |  | 915 |  |  | 912.5 |  |  | 1000.5 |  |  | 937.5 |  |  | 934.5 |  |  | 898 |  |  | 1039 |  |  | 923 |  |  | 887 |  |  | 1002 |  |  | 911 |  |  | 935.5 |  |  | 910.5 |  |  | 982.5 |  |  | 1041 |  |  | 937.5 |  |  | 972.5 |  |  | 1004.5 |  |  | 953.5 |  |  | 962 |  |  | 921.5 |  |  | 918.5 |  |  | 1007 |  |  | 994.5 |  |  | 975.5 |  |  | 1004.5 |  |  | 1051 |  |  | 999.5 |  |  | 979 |  |  | 917 |  |  | 961.5 |  |  | 977.5 |  |  | 973 |  |  | 1004 |  |  | 916.5 |  |  | 882.5 |  |  | 1027.5 |  |  | 999 |  |  | 983 |  |  | 987 |  |  | 946.5 |  |  | 971.5 |  |  | 946 |  |  | 984.5 |  |  | 917 |  |  | 935 |  |  | 951.5 |  |  | 888.5 |  |  | 952 |  |  | 947.5 |  |  | 968 |  |  | 908.5 |  |  | 1026.5 |  |  | 951 |  |  | 917.5 |  |  | 938 |  |  | 983.5 |  |  | 955 |  |  | 1028 |  |  | 1009 |  |  | 954.5 |  |  | 904.5 |  |  | 990 |  |  | 876 |  |  | 882 |  |  | 965.5 |  |  | 912.5 |  |  | 936 |  |  | 991.5 |  |  | 956 |  |  | 990.5 |  |  | 952.5 |  |  | 862 |  |  | 979 |  |  | 940 |  |  | 933.5 |  |  | 929 |  |  | 1006.5 |  |  | 987 |  |  | 944.5 |  |  | 1021 |  |  | 875.5 |  |  | 956 |  |  | 909.5 |  |  | 951.5 |  |  | 948 |  |  | 940 |  |  | 971 |  |  | 970 |  |  | 938.5 |  |  | 918 |  |  | 891.5 |  |  | 901 |  |  | 1016 |  |  | 1001 |  |  | 1018 |  |  | 1000 |  |  | 966 |  |  | 926 |  |  | 945.5 |  |  | 903 |  |  | 1016
36 |  | 1031.5 |  |  | 997 |  |  | 995.5 |  |  | 997 |  |  | 974.5 |  |  | 971 |  |  | 991 |  |  | 1017 |  |  | 1023.5 |  |  | 977 |  |  | 996 |  |  | 1091 |  |  | 977 |  |  | 1076 |  |  | 980.5 |  |  | 1059.5 |  |  | 973 |  |  | 1022 |  |  | 1036 |  |  | 872.5 |  |  | 1002 |  |  | 1039 |  |  | 1008 |  |  | 1032 |  |  | 960.5 |  |  | 1053 |  |  | 1046 |  |  | 957 |  |  | 992 |  |  | 1035 |  |  | 961 |  |  | 973.5 |  |  | 1138.5 |  |  | 985.5 |  |  | 946 |  |  | 965.5 |  |  | 969.5 |  |  | 1005.5 |  |  | 987 |  |  | 1029 |  |  | 929.5 |  |  | 951 |  |  | 1084.5 |  |  | 1019.5 |  |  | 1029.5 |  |  | 1042.5 |  |  | 1035.5 |  |  | 1003 |  |  | 883 |  |  | 910.5 |  |  | 1005 |  |  | 975.5 |  |  | 949.5 |  |  | 1054 |  |  | 952 |  |  | 972 |  |  | 1004 |  |  | 1050 |  |  | 1002 |  |  | 963.5 |  |  | 1108.5 |  |  | 1035.5 |  |  | 936 |  |  | 1025 |  |  | 911 |  |  | 951.5 |  |  | 1002 |  |  | 1047.5 |  |  | 976.5 |  |  | 1062.5 |  |  | 950 |  |  | 996 |  |  | 984 |  |  | 967.5 |  |  | 1042.5 |  |  | 951.5 |  |  | 1015.5 |  |  | 1029.5 |  |  | 1024.5 |  |  | 1018.5 |  |  | 1036.5 |  |  | 982 |  |  | 967 |  |  | 1006 |  |  | 1059.5 |  |  | 993 |  |  | 923.5 |  |  | 974 |  |  | 949 |  |  | 1031.5 |  |  | 1026.5 |  |  | 1024 |  |  | 1151 |  |  | 974.5 |  |  | 1003 |  |  | 962.5 |  |  | 1020.5 |  |  | 978.5 |  |  | 985.5 |  |  | 918.5 |  |  | 1044 |  |  | 952 |  |  | 959 |  |  | 1017.5 |  |  | 961.5 |  |  | 979.5 |  |  | 967.5 |  |  | 987 |  |  | 1011 |  |  | 1030.5 |  |  | 936 |  |  | 1028.5 |  |  | 1027 |  |  | 1050 |  |  | 974.5 |  |  | 1014 |  |  | 1010 |  |  | 958 |  |  | 931 |  |  | 1062.5 |  |  | 1040.5 |  |  | 904.5 |  |  | 1061 |  |  | 916 |  |  | 930 |  |  | 978 |  |  | 1011.5 |  |  | 975 |  |  | 993.5 |  |  | 1016 |  |  | 978 |  |  | 1033.5 |  |  | 922.5 |  |  | 878 |  |  | 965.5 |  |  | 1006 |  |  | 1023 |  |  | 1012 |  |  | 998 |  |  | 976 |  |  | 961 |  |  | 938 |  |  | 1008 |  |  | 946 |  |  | 950.5 |  |  | 946 |  |  | 939 |  |  | 975 |  |  | 977 |  |  | 931 |  |  | 949 |  |  | 1042 |  |  | 971.5 |  |  | 1014 |  |  | 991.5 |  |  | 963 |  |  | 944 |  |  | 1037.5 |  |  | 949 |  |  | 1072.5 |  |  | 1005 |  |  | 892 |  |  | 984.5 |  |  | 908 |  |  | 1008.5 |  |  | 929 |  |  | 981 |  |  | 954.5 |  |  | 996.5 |  |  | 1015 |  |  | 964.5 |  |  | 908.5 |  |  | 967 |  |  | 982 |  |  | 1086.5 |  |  | 976.5 |  |  | 964.5 |  |  | 985 |  |  | 1073 |  |  | 964 |  |  | 1069 |  |  | 1023 |  |  | 1022.5 |  |  | 968 |  |  | 920.5 |  |  | 1054.5 |  |  | 1035 |  |  | 959 |  |  | 1034.5 |  |  | 915.5 |  |  | 953 |  |  | 1009.5 |  |  | 1008.5 |  |  | 990 |  |  | 964 |  |  | 976 |  |  | 925.5 |  |  | 1019 |  |  | 1025.5 |  |  | 965.5 |  |  | 948 |  |  | 1052.5 |  |  | 966 |  |  | 987 |  |  | 1034 |  |  | 1031 |  |  | 979 |  |  | 987 |  |  | 1066 |  |  | 1018 |  |  | 1082 |  |  | 973 |  |  | 1003.5 |  |  | 1012.5 |  |  | 943 |  |  | 860 |  |  | 1025 |  |  | 1009.5 |  |  | 999.5 |  |  | 1039.5 |  |  | 976 |  |  | 1009 |  |  | 1038.5 |  |  | 943.5 |  |  | 886.5 |  |  | 1062 |  |  | 1087 |  |  | 979 |  |  | 950 |  |  | 962 |  |  | 978.5 |  |  | 920.5 |  |  | 1014 |  |  | 1017 |  |  | 1000 |  |  | 1020 |  |  | 911 |  |  | 962.5 |  |  | 954 |  |  | 1070 |  |  | 1011 |  |  | 1011 |  |  | 925.5 |  |  | 1090 |  |  | 1025 |  |  | 976 |  |  | 1091 |  |  | 1034.5 |  |  | 1018 |  |  | 945 |  |  | 911 |  |  | 1057.5 |  |  | 1016.5 |  |  | 994.5 |  |  | 1066 |  |  | 987 |  |  | 952 |  |  | 1043 |  |  | 1023 |  |  | 958.5 |  |  | 1051 |  |  | 981.5 |  |  | 1007.5 |  |  | 1028.5 |  |  | 959 |  |  | 1035.5 |  |  | 955 |  |  | 970 |  |  | 976.5 |  |  | 1028.5 |  |  | 1077 |  |  | 1087.5 |  |  | 1052.5 |  |  | 996 |  |  | 1037 |  |  | 999.5 |  |  | 969.5 |  |  | 995 |  |  | 948.5 |  |  | 1059 |  |  | 942 |  |  | 994.5 |  |  | 1010 |  |  | 902 |  |  | 1026.5 |  |  | 966 |  |  | 1034.5 |  |  | 988 |  |  | 1065 |  |  | 997 |  |  | 925 |  |  | 1028.5 |  |  | 1066 |  |  | 1028.5 |  |  | 969.5 |  |  | 1015.5 |  |  | 1054 |  |  | 1047.5 |  |  | 1083 |  |  | 1030 |  |  | 936.5 |  |  | 996.5 |  |  | 1037 |  |  | 1001.5 |  |  | 990 |  |  | 980 |  |  | 1089.5 |  |  | 995 |  |  | 978.5 |  |  | 1021.5 |  |  | 1040.5 |  |  | 1024 |  |  | 934 |  |  | 1061 |  |  | 907.5 |  |  | 967 |  |  | 1000.5 |  |  | 1026 |  |  | 1000 |  |  | 882 |  |  | 981 |  |  | 1070 |  |  | 969 |  |  | 970 |  |  | 1089 |  |  | 1040 |  |  | 1004.5 |  |  | 998 |  |  | 906 |  |  | 1118.5 |  |  | 927.5 |  |  | 1058.5 |  |  | 1059.5 |  |  | 998 |  |  | 1036 |  |  | 896.5 |  |  | 1015.5 |  |  | 1067.5 |  |  | 1049 |  |  | 950 |  |  | 983 |  |  | 980 |  |  | 910 |  |  | 976 |  |  | 971 |  |  | 959.5 |  |  | 973.5 |  |  | 989 |  |  | 1032.5 |  |  | 985.5 |  |  | 973 |  |  | 1009 |  |  | 983 |  |  | 1004 |  |  | 997.5 |  |  | 917.5 |  |  | 949.5 |  |  | 966 |  |  | 982.5 |  |  | 987 |  |  | 962 |  |  | 950 |  |  | 942.5 |  |  | 1060 |  |  | 887 |  |  | 968.5 |  |  | 983 |  |  | 994.5 |  |  | 1028 |  |  | 1022.5 |  |  | 934 |  |  | 949.5 |  |  | 1025.5 |  |  | 1061 |  |  | 946 |  |  | 908 |  |  | 973 |  |  | 1003.5 |  |  | 959 |  |  | 1028 |  |  | 958.5 |  |  | 1064.5 |  |  | 949.5 |  |  | 999 |  |  | 976.5 |  |  | 1009.5 |  |  | 1005.5 |  |  | 1085 |  |  | 1001 |  |  | 983.5 |  |  | 999 |  |  | 1057 |  |  | 968.5 |  |  | 943 |  |  | 1018 |  |  | 1000 |  |  | 947 |  |  | 934.5 |  |  | 1050.5 |  |  | 942 |  |  | 1051 |  |  | 1003 |  |  | 967 |  |  | 987 |  |  | 950.5 |  |  | 1004.5 |  |  | 980 |  |  | 1105 |  |  | 1075 |  |  | 918.5 |  |  | 1067.5 |  |  | 946 |  |  | 942 |  |  | 945 |  |  | 1006.5 |  |  | 1050.5 |  |  | 1011 |  |  | 957 |  |  | 1051 |  |  | 988 |  |  | 945 |  |  | 1039 |  |  | 988 |  |  | 1018.5 |  |  | 911 |  |  | 1101 |  |  | 991 |  |  | 1012.5 |  |  | 1089 |  |  | 898 |  |  | 887 |  |  | 1049 |  |  | 1041 |  |  | 1004 |  |  | 948 |  |  | 936.5 |  |  | 1012.5 |  |  | 939.5 |  |  | 976 |  |  | 1058 |  |  | 1029.5 |  |  | 986 |  |  | 1002.5 |  |  | 985.5 |  |  | 938 |  |  | 928 |  |  | 1080.5 |  |  | 1013 |  |  | 1015 |  |  | 1014 |  |  | 989 |  |  | 965 |  |  | 982 |  |  | 996 |  |  | 1064.5 |  |  | 975 |  |  | 935 |  |  | 1005 |  |  | 956 |  |  | 1007 |  |  | 903 |  |  | 1051 |  |  | 1057 |  |  | 1003 |  |  | 1081.5 |  |  | 1016.5 |  |  | 950.5 |  |  | 972.5 |  |  | 1022 |  |  | 949 |  |  | 1041.5 |  |  | 973 |  |  | 983 |  |  | 977.5 |  |  | 1032.5 |  |  | 1017 |  |  | 986.5 |  |  | 977.5 |  |  | 925 |  |  | 992 |  |  | 930 |  |  | 1049 |  |  | 1013.5 |  |  | 939 |  |  | 1009.5 |  |  | 952.5 |  |  | 906 |  |  | 988 |  |  | 981.5 |  |  | 1003 |  |  | 1044.5 |  |  | 960 |  |  | 1013.5 |  |  | 895.5 |  |  | 984.5 |  |  | 1024.5 |  |  | 1005.5 |  |  | 985 |  |  | 1014 |  |  | 1116.5 |  |  | 1038 |  |  | 959 |  |  | 999 |  |  | 1013 |  |  | 1012.5 |  |  | 925 |  |  | 983 |  |  | 1012 |  |  | 1005.5 |  |  | 964 |  |  | 975 |  |  | 1011 |  |  | 1076.5 |  |  | 1048 |  |  | 880 |  |  | 974 |  |  | 1018 |  |  | 1106.5 |  |  | 980 |  |  | 919.5 |  |  | 1021 |  |  | 1064 |  |  | 1112.5 |  |  | 1039 |  |  | 959 |  |  | 872.5 |  |  | 1002 |  |  | 918 |  |  | 1027 |  |  | 1011.5 |  |  | 951.5 |  |  | 1008 |  |  | 944 |  |  | 996.5 |  |  | 1001.5 |  |  | 942 |  |  | 1030 |  |  | 1021.5 |  |  | 993.5 |  |  | 922.5 |  |  | 952.5 |  |  | 1004.5 |  |  | 1029 |  |  | 1002.5 |  |  | 991 |  |  | 983 |  |  | 1001 |  |  | 1013 |  |  | 1004.5 |  |  | 931 |  |  | 911 |  |  | 1006.5 |  |  | 994.5 |  |  | 922 |  |  | 968.5 |  |  | 981.5 |  |  | 1046 |  |  | 1005 |  |  | 974 |  |  | 974.5 |  |  | 1006 |  |  | 995.5 |  |  | 994 |  |  | 1057 |  |  | 1073.5 |  |  | 987 |  |  | 1100 |  |  | 969 |  |  | 1003 |  |  | 1045 |  |  | 949 |  |  | 910 |  |  | 939 |  |  | 936.5 |  |  | 1004.5 |  |  | 1009 |  |  | 1025.5 |  |  | 893.5 |  |  | 956 |  |  | 882 |  |  | 1031 |  |  | 1056.5 |  |  | 989.5 |  |  | 972 |  |  | 1067 |  |  | 924 |  |  | 891 |  |  | 1020 |  |  | 949 |  |  | 1094 |  |  | 985.5 |  |  | 1014 |  |  | 1005 |  |  | 1087 |  |  | 937 |  |  | 949 |  |  | 1019.5 |  |  | 1091.5 |  |  | 900.5 |  |  | 953 |  |  | 935 |  |  | 968.5 |  |  | 1066.5 |  |  | 1003.5 |  |  | 993 |  |  | 1066.5 |  |  | 1015.5 |  |  | 952 |  |  | 938.5 |  |  | 1021.5 |  |  | 975 |  |  | 940 |  |  | 986 |  |  | 978 |  |  | 1025 |  |  | 933 |  |  | 1027 |  |  | 1084 |  |  | 974 |  |  | 914 |  |  | 1033.5 |  |  | 1022 |  |  | 1022 |  |  | 933 |  |  | 989.5 |  |  | 1016 |  |  | 979.5 |  |  | 1042 |  |  | 1016 |  |  | 972 |  |  | 986 |  |  | 1044.5 |  |  | 964 |  |  | 951 |  |  | 1081.5 |  |  | 1026 |  |  | 965 |  |  | 938.5 |  |  | 978.5 |  |  | 1094 |  |  | 942.5 |  |  | 1023 |  |  | 971.5 |  |  | 1032 |  |  | 997 |  |  | 996.5 |  |  | 1087.5 |  |  | 1043 |  |  | 1004 |  |  | 1023 |  |  | 1000 |  |  | 894 |  |  | 1029 |  |  | 919 |  |  | 925 |  |  | 1078.5 |  |  | 961 |  |  | 1014.5 |  |  | 992 |  |  | 1044.5 |  |  | 978.5 |  |  | 989 |  |  | 1027 |  |  | 1049.5 |  |  | 1049 |  |  | 981 |  |  | 1032 |  |  | 981.5 |  |  | 1052 |  |  | 931.5 |  |  | 952 |  |  | 990 |  |  | 1023 |  |  | 1058 |  |  | 1049.5 |  |  | 948 |  |  | 1001 |  |  | 1011 |  |  | 947.5 |  |  | 1133 |  |  | 1021 |  |  | 1026 |  |  | 946 |  |  | 1013.5 |  |  | 946.5 |  |  | 1016 |  |  | 1002 |  |  | 1017 |  |  | 1005.5 |  |  | 1005 |  |  | 960 |  |  | 931 |  |  | 1067.5 |  |  | 963.5 |  |  | 1029.5 |  |  | 960 |  |  | 1070 |  |  | 998 |  |  | 998.5 |  |  | 991 |  |  | 1000.5 |  |  | 872 |  |  | 946 |  |  | 1055 |  |  | 962.5 |  |  | 1031.5 |  |  | 991 |  |  | 921 |  |  | 1057.5 |  |  | 953 |  |  | 1032 |  |  | 1033.5 |  |  | 1016 |  |  | 973 |  |  | 1040.5 |  |  | 871 |  |  | 1053 |  |  | 976.5 |  |  | 981 |  |  | 976.5 |  |  | 1025 |  |  | 909.5 |  |  | 1027.5 |  |  | 914 |  |  | 1041 |  |  | 1032.5 |  |  | 980.5 |  |  | 1057 |  |  | 991 |  |  | 1056 |  |  | 987.5 |  |  | 1026 |  |  | 959 |  |  | 1062 |  |  | 1047.5 |  |  | 979.5 |  |  | 979 |  |  | 1097 |  |  | 992 |  |  | 1002 |  |  | 1054 |  |  | 954 |  |  | 1026 |  |  | 958.5 |  |  | 969.5 |  |  | 962.5 |  |  | 961 |  |  | 954.5 |  |  | 983 |  |  | 924 |  |  | 1003.5 |  |  | 929.5 |  |  | 855 |  |  | 993 |  |  | 858.5 |  |  | 956 |  |  | 960 |  |  | 933.5 |  |  | 963.5 |  |  | 1016 |  |  | 1029 |  |  | 1003 |  |  | 918.5 |  |  | 946 |  |  | 928 |  |  | 976 |  |  | 958 |  |  | 1075 |  |  | 1015.5 |  |  | 963 |  |  | 920 |  |  | 861 |  |  | 1060.5 |  |  | 1079 |  |  | 994.5 |  |  | 974.5 |  |  | 1009 |  |  | 954 |  |  | 1008.5 |  |  | 899.5 |  |  | 961.5 |  |  | 962.5 |  |  | 1043.5 |  |  | 1089 |  |  | 949 |  |  | 1044.5 |  |  | 960.5 |  |  | 1015 |  |  | 955 |  |  | 986.5 |  |  | 1006 |  |  | 993 |  |  | 926 |  |  | 1021.5 |  |  | 1029 |  |  | 943.5 |  |  | 953 |  |  | 1000.5 |  |  | 1042.5 |  |  | 1057.5 |  |  | 981 |  |  | 929 |  |  | 991.5 |  |  | 985.5 |  |  | 1009 |  |  | 976 |  |  | 952.5 |  |  | 1004 |  |  | 992.5 |  |  | 996.5 |  |  | 959 |  |  | 990 |  |  | 950.5 |  |  | 1055.5 |  |  | 954 |  |  | 945.5 |  |  | 1022.5 |  |  | 950 |  |  | 1039 |  |  | 1080 |  |  | 998.5 |  |  | 1035 |  |  | 976 |  |  | 981 |  |  | 994 |  |  | 1035 |  |  | 910 |  |  | 1048.5 |  |  | 960.5 |  |  | 952 |  |  | 909 |  |  | 986 |  |  | 1000.5 |  |  | 972 |  |  | 1032 |  |  | 927.5 |  |  | 973.5 |  |  | 942 |  |  | 964.5 |  |  | 978 |  |  | 974 |  |  | 991 |  |  | 1044.5 |  |  | 1084 |  |  | 983.5 |  |  | 935.5 |  |  | 934 |  |  | 1023.5 |  |  | 901.5 |  |  | 905 |  |  | 931 |  |  | 1101 |  |  | 945.5 |  |  | 923 |  |  | 951.5 |  |  | 1027.5 |  |  | 1063 |  |  | 966.5 |  |  | 986 |  |  | 1040 |  |  | 980 |  |  | 903 |  |  | 927 |  |  | 1064.5 |  |  | 1023 |  |  | 1022 |  |  | 928 |  |  | 1107 |  |  | 950.5 |  |  | 1071.5 |  |  | 983 |  |  | 960 |  |  | 979 |  |  | 948 |  |  | 1033 |  |  | 1022.5 |  |  | 1059 |  |  | 964.5 |  |  | 1085 |  |  | 914 |  |  | 988 |  |  | 954 |  |  | 965.5 |  |  | 969 |  |  | 964.5 |  |  | 894 |  |  | 1063 |  |  | 1036 |  |  | 996.5 |  |  | 1008 |  |  | 975 |  |  | 941 |  |  | 1136 |  |  | 1067 |  |  | 999.5 |  |  | 1004.5 |  |  | 944 |  |  | 960.5 |  |  | 944 |  |  | 927.5 |  |  | 1015.5 |  |  | 952.5 |  |  | 958.5 |  |  | 913 |  |  | 1078 |  |  | 952 |  |  | 926 |  |  | 1026 |  |  | 935 |  |  | 964.5 |  |  | 931.5 |  |  | 1008.5 |  |  | 1080 |  |  | 984.5 |  |  | 1011.5 |  |  | 1019.5 |  |  | 992.5 |  |  | 991 |  |  | 968.5 |  |  | 939.5 |  |  | 1033 |  |  | 1009.5 |  |  | 1022.5 |  |  | 1030.5 |  |  | 1077 |  |  | 1038.5 |  |  | 994 |  |  | 964 |  |  | 1008.5 |  |  | 1003.5 |  |  | 1012 |  |  | 1028 |  |  | 955.5 |  |  | 929.5 |  |  | 1042.5 |  |  | 1046 |  |  | 1004 |  |  | 1002 |  |  | 961.5 |  |  | 986.5 |  |  | 972 |  |  | 999.5 |  |  | 956 |  |  | 956 |  |  | 998.5 |  |  | 909.5 |  |  | 978 |  |  | 962.5 |  |  | 992 |  |  | 937.5 |  |  | 1073.5 |  |  | 975 |  |  | 941.5 |  |  | 977 |  |  | 998.5 |  |  | 1002 |  |  | 1052 |  |  | 1035 |  |  | 983.5 |  |  | 919.5 |  |  | 1016 |  |  | 915 |  |  | 929 |  |  | 1004.5 |  |  | 959.5 |  |  | 975 |  |  | 1012.5 |  |  | 985 |  |  | 1016.5 |  |  | 973.5 |  |  | 888 |  |  | 1018 |  |  | 966 |  |  | 972.5 |  |  | 944 |  |  | 1045.5 |  |  | 1026 |  |  | 968.5 |  |  | 1068 |  |  | 890.5 |  |  | 995 |  |  | 924.5 |  |  | 975.5 |  |  | 977 |  |  | 955 |  |  | 1000 |  |  | 994 |  |  | 977.5 |  |  | 957 |  |  | 920.5 |  |  | 925 |  |  | 1037 |  |  | 1030 |  |  | 1039 |  |  | 1047 |  |  | 1013 |  |  | 955 |  |  | 984.5 |  |  | 932 |  |  | 1045
37 |  | 1055.5 |  |  | 1036 |  |  | 1021.5 |  |  | 1044 |  |  | 1003.5 |  |  | 997 |  |  | 1038 |  |  | 1038 |  |  | 1047.5 |  |  | 1006 |  |  | 1020 |  |  | 1130 |  |  | 1024 |  |  | 1100 |  |  | 1027.5 |  |  | 1088.5 |  |  | 999 |  |  | 1061 |  |  | 1075 |  |  | 887.5 |  |  | 1041 |  |  | 1086 |  |  | 1055 |  |  | 1071 |  |  | 999.5 |  |  | 1100 |  |  | 1085 |  |  | 996 |  |  | 1031 |  |  | 1061 |  |  | 990 |  |  | 994.5 |  |  | 1167.5 |  |  | 1006.5 |  |  | 972 |  |  | 986.5 |  |  | 990.5 |  |  | 1034.5 |  |  | 1013 |  |  | 1058 |  |  | 955.5 |  |  | 990 |  |  | 1131.5 |  |  | 1043.5 |  |  | 1053.5 |  |  | 1081.5 |  |  | 1082.5 |  |  | 1018 |  |  | 909 |  |  | 939.5 |  |  | 1026 |  |  | 990.5 |  |  | 996.5 |  |  | 1093 |  |  | 991 |  |  | 1011 |  |  | 1025 |  |  | 1089 |  |  | 1049 |  |  | 1002.5 |  |  | 1129.5 |  |  | 1074.5 |  |  | 951 |  |  | 1072 |  |  | 935 |  |  | 990.5 |  |  | 1041 |  |  | 1094.5 |  |  | 1015.5 |  |  | 1077.5 |  |  | 965 |  |  | 1025 |  |  | 1013 |  |  | 991.5 |  |  | 1063.5 |  |  | 966.5 |  |  | 1030.5 |  |  | 1050.5 |  |  | 1063.5 |  |  | 1047.5 |  |  | 1062.5 |  |  | 1008 |  |  | 1006 |  |  | 1045 |  |  | 1074.5 |  |  | 1014 |  |  | 962.5 |  |  | 995 |  |  | 996 |  |  | 1052.5 |  |  | 1065.5 |  |  | 1039 |  |  | 1172 |  |  | 1000.5 |  |  | 1032 |  |  | 977.5 |  |  | 1046.5 |  |  | 1025.5 |  |  | 1006.5 |  |  | 957.5 |  |  | 1083 |  |  | 976 |  |  | 983 |  |  | 1064.5 |  |  | 990.5 |  |  | 1008.5 |  |  | 982.5 |  |  | 1026 |  |  | 1032 |  |  | 1051.5 |  |  | 957 |  |  | 1067.5 |  |  | 1042 |  |  | 1089 |  |  | 995.5 |  |  | 1038 |  |  | 1034 |  |  | 987 |  |  | 978 |  |  | 1083.5 |  |  | 1061.5 |  |  | 925.5 |  |  | 1087 |  |  | 963 |  |  | 945 |  |  | 1004 |  |  | 1032.5 |  |  | 1004 |  |  | 1032.5 |  |  | 1042 |  |  | 993 |  |  | 1048.5 |  |  | 961.5 |  |  | 904 |  |  | 980.5 |  |  | 1021 |  |  | 1062 |  |  | 1051 |  |  | 1019 |  |  | 1015 |  |  | 976 |  |  | 967 |  |  | 1034 |  |  | 985 |  |  | 974.5 |  |  | 985 |  |  | 968 |  |  | 1014 |  |  | 1006 |  |  | 946 |  |  | 978 |  |  | 1066 |  |  | 997.5 |  |  | 1038 |  |  | 1030.5 |  |  | 1010 |  |  | 970 |  |  | 1076.5 |  |  | 973 |  |  | 1101.5 |  |  | 1044 |  |  | 939 |  |  | 1023.5 |  |  | 937 |  |  | 1047.5 |  |  | 944 |  |  | 1020 |  |  | 978.5 |  |  | 1043.5 |  |  | 1041 |  |  | 979.5 |  |  | 929.5 |  |  | 1006 |  |  | 1029 |  |  | 1125.5 |  |  | 1002.5 |  |  | 1003.5 |  |  | 1006 |  |  | 1102 |  |  | 993 |  |  | 1090 |  |  | 1047 |  |  | 1069.5 |  |  | 1015 |  |  | 935.5 |  |  | 1075.5 |  |  | 1059 |  |  | 998 |  |  | 1081.5 |  |  | 930.5 |  |  | 968 |  |  | 1038.5 |  |  | 1037.5 |  |  | 1016 |  |  | 993 |  |  | 1015 |  |  | 940.5 |  |  | 1066 |  |  | 1054.5 |  |  | 1004.5 |  |  | 963 |  |  | 1073.5 |  |  | 990 |  |  | 1011 |  |  | 1063 |  |  | 1055 |  |  | 994 |  |  | 1026 |  |  | 1113 |  |  | 1042 |  |  | 1108 |  |  | 1002 |  |  | 1032.5 |  |  | 1041.5 |  |  | 964 |  |  | 884 |  |  | 1049 |  |  | 1024.5 |  |  | 1046.5 |  |  | 1078.5 |  |  | 991 |  |  | 1048 |  |  | 1067.5 |  |  | 964.5 |  |  | 925.5 |  |  | 1091 |  |  | 1113 |  |  | 1000 |  |  | 971 |  |  | 983 |  |  | 1002.5 |  |  | 946.5 |  |  | 1038 |  |  | 1041 |  |  | 1026 |  |  | 1046 |  |  | 926 |  |  | 977.5 |  |  | 993 |  |  | 1094 |  |  | 1032 |  |  | 1040 |  |  | 949.5 |  |  | 1119 |  |  | 1072 |  |  | 1002 |  |  | 1112 |  |  | 1058.5 |  |  | 1065 |  |  | 971 |  |  | 932 |  |  | 1086.5 |  |  | 1045.5 |  |  | 1041.5 |  |  | 1081 |  |  | 1002 |  |  | 991 |  |  | 1082 |  |  | 1049 |  |  | 1005.5 |  |  | 1090 |  |  | 996.5 |  |  | 1046.5 |  |  | 1049.5 |  |  | 988 |  |  | 1050.5 |  |  | 970 |  |  | 985 |  |  | 1000.5 |  |  | 1049.5 |  |  | 1101 |  |  | 1134.5 |  |  | 1078.5 |  |  | 1035 |  |  | 1076 |  |  | 1020.5 |  |  | 984.5 |  |  | 1034 |  |  | 995.5 |  |  | 1083 |  |  | 966 |  |  | 1033.5 |  |  | 1039 |  |  | 923 |  |  | 1050.5 |  |  | 992 |  |  | 1055.5 |  |  | 1012 |  |  | 1104 |  |  | 1036 |  |  | 951 |  |  | 1075.5 |  |  | 1113 |  |  | 1057.5 |  |  | 998.5 |  |  | 1054.5 |  |  | 1080 |  |  | 1076.5 |  |  | 1109 |  |  | 1077 |  |  | 962.5 |  |  | 1017.5 |  |  | 1052 |  |  | 1025.5 |  |  | 1029 |  |  | 1006 |  |  | 1115.5 |  |  | 1010 |  |  | 1002.5 |  |  | 1042.5 |  |  | 1055.5 |  |  | 1045 |  |  | 955 |  |  | 1090 |  |  | 933.5 |  |  | 1006 |  |  | 1039.5 |  |  | 1050 |  |  | 1047 |  |  | 906 |  |  | 1005 |  |  | 1109 |  |  | 998 |  |  | 996 |  |  | 1128 |  |  | 1055 |  |  | 1043.5 |  |  | 1019 |  |  | 930 |  |  | 1139.5 |  |  | 948.5 |  |  | 1097.5 |  |  | 1080.5 |  |  | 1019 |  |  | 1075 |  |  | 935.5 |  |  | 1054.5 |  |  | 1106.5 |  |  | 1073 |  |  | 979 |  |  | 1009 |  |  | 1009 |  |  | 957 |  |  | 1015 |  |  | 1010 |  |  | 980.5 |  |  | 1020.5 |  |  | 1015 |  |  | 1058.5 |  |  | 1032.5 |  |  | 1012 |  |  | 1048 |  |  | 1022 |  |  | 1033 |  |  | 1012.5 |  |  | 964.5 |  |  | 973.5 |  |  | 981 |  |  | 1011.5 |  |  | 1013 |  |  | 1001 |  |  | 976 |  |  | 957.5 |  |  | 1084 |  |  | 913 |  |  | 1015.5 |  |  | 1004 |  |  | 1020.5 |  |  | 1054 |  |  | 1051.5 |  |  | 949 |  |  | 970.5 |  |  | 1072.5 |  |  | 1076 |  |  | 972 |  |  | 934 |  |  | 997 |  |  | 1027.5 |  |  | 983 |  |  | 1052 |  |  | 997.5 |  |  | 1085.5 |  |  | 964.5 |  |  | 1023 |  |  | 1000.5 |  |  | 1024.5 |  |  | 1034.5 |  |  | 1114 |  |  | 1027 |  |  | 1022.5 |  |  | 1023 |  |  | 1083 |  |  | 992.5 |  |  | 990 |  |  | 1065 |  |  | 1024 |  |  | 973 |  |  | 973.5 |  |  | 1089.5 |  |  | 963 |  |  | 1098 |  |  | 1050 |  |  | 993 |  |  | 1016 |  |  | 979.5 |  |  | 1043.5 |  |  | 1006 |  |  | 1144 |  |  | 1101 |  |  | 957.5 |  |  | 1082.5 |  |  | 972 |  |  | 971 |  |  | 974 |  |  | 1030.5 |  |  | 1097.5 |  |  | 1050 |  |  | 981 |  |  | 1098 |  |  | 1027 |  |  | 984 |  |  | 1054 |  |  | 1009 |  |  | 1065.5 |  |  | 926 |  |  | 1122 |  |  | 1017 |  |  | 1059.5 |  |  | 1136 |  |  | 913 |  |  | 902 |  |  | 1064 |  |  | 1056 |  |  | 1028 |  |  | 995 |  |  | 983.5 |  |  | 1041.5 |  |  | 978.5 |  |  | 991 |  |  | 1082 |  |  | 1055.5 |  |  | 1001 |  |  | 1026.5 |  |  | 1009.5 |  |  | 967 |  |  | 967 |  |  | 1127.5 |  |  | 1060 |  |  | 1041 |  |  | 1038 |  |  | 1028 |  |  | 980 |  |  | 1021 |  |  | 1020 |  |  | 1103.5 |  |  | 999 |  |  | 961 |  |  | 1031 |  |  | 980 |  |  | 1054 |  |  | 929 |  |  | 1090 |  |  | 1078 |  |  | 1042 |  |  | 1128.5 |  |  | 1042.5 |  |  | 974.5 |  |  | 987.5 |  |  | 1069 |  |  | 973 |  |  | 1065.5 |  |  | 988 |  |  | 1030 |  |  | 1006.5 |  |  | 1071.5 |  |  | 1043 |  |  | 1025.5 |  |  | 1001.5 |  |  | 940 |  |  | 1031 |  |  | 969 |  |  | 1064 |  |  | 1037.5 |  |  | 954 |  |  | 1024.5 |  |  | 981.5 |  |  | 932 |  |  | 1017 |  |  | 1002.5 |  |  | 1032 |  |  | 1068.5 |  |  | 981 |  |  | 1037.5 |  |  | 942.5 |  |  | 999.5 |  |  | 1063.5 |  |  | 1044.5 |  |  | 1006 |  |  | 1043 |  |  | 1131.5 |  |  | 1064 |  |  | 988 |  |  | 1038 |  |  | 1034 |  |  | 1059.5 |  |  | 946 |  |  | 998 |  |  | 1059 |  |  | 1020.5 |  |  | 993 |  |  | 990 |  |  | 1026 |  |  | 1115.5 |  |  | 1063 |  |  | 906 |  |  | 1000 |  |  | 1057 |  |  | 1121.5 |  |  | 1019 |  |  | 958.5 |  |  | 1047 |  |  | 1090 |  |  | 1127.5 |  |  | 1078 |  |  | 985 |  |  | 896.5 |  |  | 1049 |  |  | 947 |  |  | 1066 |  |  | 1050.5 |  |  | 972.5 |  |  | 1034 |  |  | 973 |  |  | 1022.5 |  |  | 1022.5 |  |  | 981 |  |  | 1059 |  |  | 1068.5 |  |  | 1040.5 |  |  | 948.5 |  |  | 999.5 |  |  | 1043.5 |  |  | 1068 |  |  | 1031.5 |  |  | 1020 |  |  | 1012 |  |  | 1027 |  |  | 1037 |  |  | 1043.5 |  |  | 957 |  |  | 950 |  |  | 1021.5 |  |  | 1009.5 |  |  | 951 |  |  | 1007.5 |  |  | 1020.5 |  |  | 1085 |  |  | 1026 |  |  | 1003 |  |  | 1000.5 |  |  | 1045 |  |  | 1034.5 |  |  | 1020 |  |  | 1096 |  |  | 1088.5 |  |  | 1013 |  |  | 1124 |  |  | 993 |  |  | 1042 |  |  | 1060 |  |  | 996 |  |  | 949 |  |  | 978 |  |  | 951.5 |  |  | 1030.5 |  |  | 1048 |  |  | 1072.5 |  |  | 908.5 |  |  | 995 |  |  | 906 |  |  | 1057 |  |  | 1082.5 |  |  | 1013.5 |  |  | 998 |  |  | 1096 |  |  | 963 |  |  | 920 |  |  | 1059 |  |  | 988 |  |  | 1115 |  |  | 1006.5 |  |  | 1061 |  |  | 1052 |  |  | 1126 |  |  | 963 |  |  | 964 |  |  | 1048.5 |  |  | 1117.5 |  |  | 939.5 |  |  | 977 |  |  | 950 |  |  | 989.5 |  |  | 1105.5 |  |  | 1024.5 |  |  | 1008 |  |  | 1087.5 |  |  | 1041.5 |  |  | 967 |  |  | 985.5 |  |  | 1047.5 |  |  | 999 |  |  | 955 |  |  | 1012 |  |  | 1017 |  |  | 1046 |  |  | 972 |  |  | 1048 |  |  | 1110 |  |  | 989 |  |  | 940 |  |  | 1057.5 |  |  | 1046 |  |  | 1043 |  |  | 954 |  |  | 1036.5 |  |  | 1055 |  |  | 1018.5 |  |  | 1063 |  |  | 1055 |  |  | 1019 |  |  | 1012 |  |  | 1073.5 |  |  | 1003 |  |  | 990 |  |  | 1110.5 |  |  | 1073 |  |  | 989 |  |  | 967.5 |  |  | 1007.5 |  |  | 1133 |  |  | 963.5 |  |  | 1062 |  |  | 1010.5 |  |  | 1056 |  |  | 1036 |  |  | 1035.5 |  |  | 1126.5 |  |  | 1082 |  |  | 1033 |  |  | 1070 |  |  | 1026 |  |  | 923 |  |  | 1068 |  |  | 958 |  |  | 940 |  |  | 1117.5 |  |  | 976 |  |  | 1043.5 |  |  | 1031 |  |  | 1068.5 |  |  | 1007.5 |  |  | 1018 |  |  | 1066 |  |  | 1073.5 |  |  | 1073 |  |  | 996 |  |  | 1056 |  |  | 1020.5 |  |  | 1067 |  |  | 960.5 |  |  | 991 |  |  | 1011 |  |  | 1047 |  |  | 1097 |  |  | 1064.5 |  |  | 977 |  |  | 1048 |  |  | 1050 |  |  | 968.5 |  |  | 1154 |  |  | 1036 |  |  | 1052 |  |  | 961 |  |  | 1060.5 |  |  | 985.5 |  |  | 1042 |  |  | 1049 |  |  | 1046 |  |  | 1034.5 |  |  | 1020 |  |  | 981 |  |  | 970 |  |  | 1106.5 |  |  | 1010.5 |  |  | 1068.5 |  |  | 975 |  |  | 1109 |  |  | 1019 |  |  | 1037.5 |  |  | 1015 |  |  | 1039.5 |  |  | 898 |  |  | 961 |  |  | 1081 |  |  | 1001.5 |  |  | 1052.5 |  |  | 1006 |  |  | 960 |  |  | 1086.5 |  |  | 992 |  |  | 1071 |  |  | 1048.5 |  |  | 1042 |  |  | 999 |  |  | 1069.5 |  |  | 900 |  |  | 1092 |  |  | 1005.5 |  |  | 1020 |  |  | 1015.5 |  |  | 1064 |  |  | 948.5 |  |  | 1051.5 |  |  | 935 |  |  | 1088 |  |  | 1058.5 |  |  | 1019.5 |  |  | 1083 |  |  | 1012 |  |  | 1082 |  |  | 1011.5 |  |  | 1041 |  |  | 998 |  |  | 1083 |  |  | 1086.5 |  |  | 1018.5 |  |  | 1003 |  |  | 1123 |  |  | 1013 |  |  | 1017 |  |  | 1093 |  |  | 980 |  |  | 1041 |  |  | 984.5 |  |  | 998.5 |  |  | 986.5 |  |  | 990 |  |  | 980.5 |  |  | 1012 |  |  | 939 |  |  | 1029.5 |  |  | 944.5 |  |  | 879 |  |  | 1014 |  |  | 897.5 |  |  | 1003 |  |  | 1007 |  |  | 959.5 |  |  | 984.5 |  |  | 1040 |  |  | 1068 |  |  | 1032 |  |  | 965.5 |  |  | 961 |  |  | 949 |  |  | 1005 |  |  | 982 |  |  | 1114 |  |  | 1041.5 |  |  | 1002 |  |  | 946 |  |  | 887 |  |  | 1089.5 |  |  | 1100 |  |  | 1018.5 |  |  | 995.5 |  |  | 1030 |  |  | 993 |  |  | 1023.5 |  |  | 946.5 |  |  | 987.5 |  |  | 1001.5 |  |  | 1072.5 |  |  | 1115 |  |  | 988 |  |  | 1083.5 |  |  | 1007.5 |  |  | 1030 |  |  | 979 |  |  | 1007.5 |  |  | 1027 |  |  | 1032 |  |  | 947 |  |  | 1060.5 |  |  | 1050 |  |  | 990.5 |  |  | 968 |  |  | 1039.5 |  |  | 1057.5 |  |  | 1096.5 |  |  | 996 |  |  | 968 |  |  | 1030.5 |  |  | 1000.5 |  |  | 1056 |  |  | 1000 |  |  | 991.5 |  |  | 1028 |  |  | 1021.5 |  |  | 1043.5 |  |  | 980 |  |  | 1029 |  |  | 989.5 |  |  | 1081.5 |  |  | 980 |  |  | 960.5 |  |  | 1046.5 |  |  | 971 |  |  | 1063 |  |  | 1106 |  |  | 1024.5 |  |  | 1074 |  |  | 1000 |  |  | 1028 |  |  | 1020 |  |  | 1059 |  |  | 957 |  |  | 1063.5 |  |  | 975.5 |  |  | 991 |  |  | 948 |  |  | 1012 |  |  | 1047.5 |  |  | 998 |  |  | 1071 |  |  | 942.5 |  |  | 1012.5 |  |  | 981 |  |  | 1011.5 |  |  | 1017 |  |  | 995 |  |  | 1006 |  |  | 1070.5 |  |  | 1113 |  |  | 998.5 |  |  | 950.5 |  |  | 981 |  |  | 1044.5 |  |  | 927.5 |  |  | 944 |  |  | 960 |  |  | 1130 |  |  | 960.5 |  |  | 947 |  |  | 990.5 |  |  | 1042.5 |  |  | 1102 |  |  | 990.5 |  |  | 1007 |  |  | 1066 |  |  | 1019 |  |  | 950 |  |  | 953 |  |  | 1090.5 |  |  | 1047 |  |  | 1046 |  |  | 957 |  |  | 1131 |  |  | 965.5 |  |  | 1110.5 |  |  | 1012 |  |  | 975 |  |  | 994 |  |  | 974 |  |  | 1048 |  |  | 1069.5 |  |  | 1088 |  |  | 1011.5 |  |  | 1106 |  |  | 943 |  |  | 1003 |  |  | 1001 |  |  | 991.5 |  |  | 984 |  |  | 990.5 |  |  | 909 |  |  | 1110 |  |  | 1075 |  |  | 1025.5 |  |  | 1029 |  |  | 999 |  |  | 956 |  |  | 1175 |  |  | 1091 |  |  | 1025.5 |  |  | 1028.5 |  |  | 973 |  |  | 984.5 |  |  | 991 |  |  | 951.5 |  |  | 1030.5 |  |  | 973.5 |  |  | 997.5 |  |  | 939 |  |  | 1104 |  |  | 976 |  |  | 950 |  |  | 1052 |  |  | 959 |  |  | 993.5 |  |  | 960.5 |  |  | 1055.5 |  |  | 1104 |  |  | 999.5 |  |  | 1032.5 |  |  | 1043.5 |  |  | 1016.5 |  |  | 1020 |  |  | 1007.5 |  |  | 986.5 |  |  | 1072 |  |  | 1056.5 |  |  | 1037.5 |  |  | 1051.5 |  |  | 1098 |  |  | 1059.5 |  |  | 1041 |  |  | 993 |  |  | 1047.5 |  |  | 1027.5 |  |  | 1059 |  |  | 1054 |  |  | 976.5 |  |  | 968.5 |  |  | 1081.5 |  |  | 1085 |  |  | 1030 |  |  | 1017 |  |  | 987.5 |  |  | 1007.5 |  |  | 1019 |  |  | 1046.5 |  |  | 982 |  |  | 980 |  |  | 1022.5 |  |  | 933.5 |  |  | 1007 |  |  | 1009.5 |  |  | 1013 |  |  | 958.5 |  |  | 1112.5 |  |  | 1022 |  |  | 956.5 |  |  | 1003 |  |  | 1045.5 |  |  | 1031 |  |  | 1067 |  |  | 1082 |  |  | 998.5 |  |  | 940.5 |  |  | 1031 |  |  | 939 |  |  | 968 |  |  | 1043.5 |  |  | 974.5 |  |  | 1014 |  |  | 1033.5 |  |  | 1000 |  |  | 1037.5 |  |  | 999.5 |  |  | 935 |  |  | 1044 |  |  | 1005 |  |  | 1011.5 |  |  | 983 |  |  | 1092.5 |  |  | 1050 |  |  | 1007.5 |  |  | 1092 |  |  | 911.5 |  |  | 1019 |  |  | 971.5 |  |  | 1014.5 |  |  | 1016 |  |  | 994 |  |  | 1015 |  |  | 1033 |  |  | 1016.5 |  |  | 981 |  |  | 959.5 |  |  | 949 |  |  | 1076 |  |  | 1069 |  |  | 1063 |  |  | 1094 |  |  | 1028 |  |  | 1002 |  |  | 1008.5 |  |  | 947 |  |  | 1092
38 |  | 1081.5 |  |  | 1083 |  |  | 1047.5 |  |  | 1068 |  |  | 1042.5 |  |  | 1036 |  |  | 1053 |  |  | 1085 |  |  | 1071.5 |  |  | 1032 |  |  | 1049 |  |  | 1154 |  |  | 1071 |  |  | 1129 |  |  | 1048.5 |  |  | 1109.5 |  |  | 1020 |  |  | 1087 |  |  | 1101 |  |  | 926.5 |  |  | 1080 |  |  | 1110 |  |  | 1070 |  |  | 1118 |  |  | 1025.5 |  |  | 1126 |  |  | 1114 |  |  | 1025 |  |  | 1070 |  |  | 1087 |  |  | 1016 |  |  | 1015.5 |  |  | 1193.5 |  |  | 1027.5 |  |  | 1011 |  |  | 1007.5 |  |  | 1019.5 |  |  | 1073.5 |  |  | 1052 |  |  | 1084 |  |  | 979.5 |  |  | 1011 |  |  | 1178.5 |  |  | 1082.5 |  |  | 1092.5 |  |  | 1096.5 |  |  | 1111.5 |  |  | 1044 |  |  | 956 |  |  | 978.5 |  |  | 1073 |  |  | 1005.5 |  |  | 1017.5 |  |  | 1108 |  |  | 1006 |  |  | 1037 |  |  | 1040 |  |  | 1136 |  |  | 1073 |  |  | 1026.5 |  |  | 1158.5 |  |  | 1121.5 |  |  | 990 |  |  | 1096 |  |  | 964 |  |  | 1029.5 |  |  | 1067 |  |  | 1115.5 |  |  | 1036.5 |  |  | 1103.5 |  |  | 994 |  |  | 1040 |  |  | 1042 |  |  | 1038.5 |  |  | 1092.5 |  |  | 995.5 |  |  | 1077.5 |  |  | 1065.5 |  |  | 1084.5 |  |  | 1076.5 |  |  | 1091.5 |  |  | 1029 |  |  | 1045 |  |  | 1060 |  |  | 1113.5 |  |  | 1053 |  |  | 1001.5 |  |  | 1019 |  |  | 1035 |  |  | 1099.5 |  |  | 1104.5 |  |  | 1065 |  |  | 1211 |  |  | 1024.5 |  |  | 1061 |  |  | 1001.5 |  |  | 1085.5 |  |  | 1046.5 |  |  | 1045.5 |  |  | 1004.5 |  |  | 1130 |  |  | 1015 |  |  | 1022 |  |  | 1103.5 |  |  | 1029.5 |  |  | 1037.5 |  |  | 1021.5 |  |  | 1065 |  |  | 1047 |  |  | 1075.5 |  |  | 996 |  |  | 1106.5 |  |  | 1063 |  |  | 1110 |  |  | 1016.5 |  |  | 1077 |  |  | 1055 |  |  | 1034 |  |  | 1025 |  |  | 1104.5 |  |  | 1090.5 |  |  | 964.5 |  |  | 1134 |  |  | 978 |  |  | 992 |  |  | 1051 |  |  | 1061.5 |  |  | 1025 |  |  | 1058.5 |  |  | 1068 |  |  | 1019 |  |  | 1095.5 |  |  | 976.5 |  |  | 928 |  |  | 1009.5 |  |  | 1045 |  |  | 1088 |  |  | 1098 |  |  | 1034 |  |  | 1054 |  |  | 1002 |  |  | 982 |  |  | 1081 |  |  | 1014 |  |  | 1013.5 |  |  | 1011 |  |  | 997 |  |  | 1053 |  |  | 1045 |  |  | 961 |  |  | 1007 |  |  | 1095 |  |  | 1026.5 |  |  | 1059 |  |  | 1069.5 |  |  | 1057 |  |  | 1009 |  |  | 1100.5 |  |  | 1020 |  |  | 1140.5 |  |  | 1070 |  |  | 968 |  |  | 1047.5 |  |  | 984 |  |  | 1073.5 |  |  | 983 |  |  | 1046 |  |  | 999.5 |  |  | 1072.5 |  |  | 1062 |  |  | 1005.5 |  |  | 968.5 |  |  | 1027 |  |  | 1068 |  |  | 1164.5 |  |  | 1041.5 |  |  | 1042.5 |  |  | 1045 |  |  | 1149 |  |  | 1017 |  |  | 1129 |  |  | 1073 |  |  | 1093.5 |  |  | 1030 |  |  | 974.5 |  |  | 1096.5 |  |  | 1106 |  |  | 1045 |  |  | 1120.5 |  |  | 969.5 |  |  | 1015 |  |  | 1085.5 |  |  | 1052.5 |  |  | 1055 |  |  | 1014 |  |  | 1041 |  |  | 979.5 |  |  | 1113 |  |  | 1075.5 |  |  | 1025.5 |  |  | 989 |  |  | 1094.5 |  |  | 1005 |  |  | 1058 |  |  | 1087 |  |  | 1076 |  |  | 1018 |  |  | 1055 |  |  | 1142 |  |  | 1066 |  |  | 1129 |  |  | 1023 |  |  | 1053.5 |  |  | 1088.5 |  |  | 988 |  |  | 931 |  |  | 1096 |  |  | 1045.5 |  |  | 1085.5 |  |  | 1117.5 |  |  | 1020 |  |  | 1087 |  |  | 1114.5 |  |  | 1003.5 |  |  | 949.5 |  |  | 1106 |  |  | 1142 |  |  | 1047 |  |  | 997 |  |  | 1022 |  |  | 1023.5 |  |  | 985.5 |  |  | 1085 |  |  | 1056 |  |  | 1065 |  |  | 1075 |  |  | 965 |  |  | 1016.5 |  |  | 1032 |  |  | 1109 |  |  | 1053 |  |  | 1061 |  |  | 964.5 |  |  | 1166 |  |  | 1098 |  |  | 1028 |  |  | 1141 |  |  | 1087.5 |  |  | 1089 |  |  | 1010 |  |  | 956 |  |  | 1107.5 |  |  | 1092.5 |  |  | 1062.5 |  |  | 1102 |  |  | 1017 |  |  | 1030 |  |  | 1108 |  |  | 1088 |  |  | 1020.5 |  |  | 1129 |  |  | 1025.5 |  |  | 1072.5 |  |  | 1078.5 |  |  | 1012 |  |  | 1097.5 |  |  | 999 |  |  | 1014 |  |  | 1021.5 |  |  | 1064.5 |  |  | 1140 |  |  | 1173.5 |  |  | 1117.5 |  |  | 1059 |  |  | 1123 |  |  | 1046.5 |  |  | 1013.5 |  |  | 1073 |  |  | 1021.5 |  |  | 1098 |  |  | 1013 |  |  | 1054.5 |  |  | 1065 |  |  | 970 |  |  | 1074.5 |  |  | 1039 |  |  | 1081.5 |  |  | 1051 |  |  | 1130 |  |  | 1057 |  |  | 975 |  |  | 1114.5 |  |  | 1160 |  |  | 1096.5 |  |  | 1027.5 |  |  | 1083.5 |  |  | 1119 |  |  | 1115.5 |  |  | 1148 |  |  | 1101 |  |  | 977.5 |  |  | 1038.5 |  |  | 1067 |  |  | 1072.5 |  |  | 1058 |  |  | 1030 |  |  | 1141.5 |  |  | 1049 |  |  | 1031.5 |  |  | 1063.5 |  |  | 1079.5 |  |  | 1060 |  |  | 976 |  |  | 1105 |  |  | 954.5 |  |  | 1027 |  |  | 1078.5 |  |  | 1079 |  |  | 1076 |  |  | 953 |  |  | 1044 |  |  | 1135 |  |  | 1045 |  |  | 1017 |  |  | 1167 |  |  | 1084 |  |  | 1082.5 |  |  | 1043 |  |  | 977 |  |  | 1178.5 |  |  | 977.5 |  |  | 1118.5 |  |  | 1119.5 |  |  | 1034 |  |  | 1114 |  |  | 956.5 |  |  | 1078.5 |  |  | 1145.5 |  |  | 1120 |  |  | 1026 |  |  | 1035 |  |  | 1048 |  |  | 978 |  |  | 1054 |  |  | 1057 |  |  | 1019.5 |  |  | 1049.5 |  |  | 1044 |  |  | 1087.5 |  |  | 1079.5 |  |  | 1027 |  |  | 1087 |  |  | 1037 |  |  | 1072 |  |  | 1027.5 |  |  | 990.5 |  |  | 1020.5 |  |  | 1020 |  |  | 1035.5 |  |  | 1052 |  |  | 1030 |  |  | 1023 |  |  | 972.5 |  |  | 1113 |  |  | 942 |  |  | 1062.5 |  |  | 1025 |  |  | 1067.5 |  |  | 1101 |  |  | 1080.5 |  |  | 970 |  |  | 1009.5 |  |  | 1111.5 |  |  | 1115 |  |  | 996 |  |  | 958 |  |  | 1036 |  |  | 1048.5 |  |  | 1022 |  |  | 1076 |  |  | 1018.5 |  |  | 1124.5 |  |  | 988.5 |  |  | 1047 |  |  | 1021.5 |  |  | 1050.5 |  |  | 1049.5 |  |  | 1138 |  |  | 1066 |  |  | 1037.5 |  |  | 1070 |  |  | 1104 |  |  | 1031.5 |  |  | 1037 |  |  | 1091 |  |  | 1045 |  |  | 988 |  |  | 1012.5 |  |  | 1115.5 |  |  | 1002 |  |  | 1113 |  |  | 1074 |  |  | 1022 |  |  | 1045 |  |  | 1003.5 |  |  | 1082.5 |  |  | 1021 |  |  | 1183 |  |  | 1140 |  |  | 983.5 |  |  | 1121.5 |  |  | 1011 |  |  | 992 |  |  | 989 |  |  | 1051.5 |  |  | 1144.5 |  |  | 1065 |  |  | 1010 |  |  | 1137 |  |  | 1066 |  |  | 1005 |  |  | 1080 |  |  | 1048 |  |  | 1112.5 |  |  | 947 |  |  | 1143 |  |  | 1056 |  |  | 1098.5 |  |  | 1175 |  |  | 952 |  |  | 941 |  |  | 1085 |  |  | 1080 |  |  | 1052 |  |  | 1034 |  |  | 1030.5 |  |  | 1056.5 |  |  | 1007.5 |  |  | 1038 |  |  | 1103 |  |  | 1094.5 |  |  | 1030 |  |  | 1065.5 |  |  | 1048.5 |  |  | 988 |  |  | 1014 |  |  | 1156.5 |  |  | 1084 |  |  | 1065 |  |  | 1064 |  |  | 1054 |  |  | 1009 |  |  | 1042 |  |  | 1046 |  |  | 1142.5 |  |  | 1028 |  |  | 1008 |  |  | 1078 |  |  | 1019 |  |  | 1101 |  |  | 953 |  |  | 1129 |  |  | 1107 |  |  | 1071 |  |  | 1175.5 |  |  | 1066.5 |  |  | 1003.5 |  |  | 1013.5 |  |  | 1098 |  |  | 999 |  |  | 1104.5 |  |  | 1027 |  |  | 1077 |  |  | 1053.5 |  |  | 1110.5 |  |  | 1082 |  |  | 1049.5 |  |  | 1040.5 |  |  | 969 |  |  | 1070 |  |  | 984 |  |  | 1103 |  |  | 1084.5 |  |  | 993 |  |  | 1071.5 |  |  | 1010.5 |  |  | 971 |  |  | 1043 |  |  | 1017.5 |  |  | 1071 |  |  | 1115.5 |  |  | 1020 |  |  | 1066.5 |  |  | 963.5 |  |  | 1038.5 |  |  | 1084.5 |  |  | 1070.5 |  |  | 1053 |  |  | 1082 |  |  | 1170.5 |  |  | 1093 |  |  | 1017 |  |  | 1062 |  |  | 1081 |  |  | 1083.5 |  |  | 972 |  |  | 1027 |  |  | 1083 |  |  | 1059.5 |  |  | 1032 |  |  | 1019 |  |  | 1052 |  |  | 1154.5 |  |  | 1078 |  |  | 921 |  |  | 1024 |  |  | 1081 |  |  | 1168.5 |  |  | 1058 |  |  | 1005.5 |  |  | 1068 |  |  | 1105 |  |  | 1174.5 |  |  | 1117 |  |  | 1014 |  |  | 935.5 |  |  | 1070 |  |  | 976 |  |  | 1081 |  |  | 1097.5 |  |  | 998.5 |  |  | 1063 |  |  | 994 |  |  | 1069.5 |  |  | 1043.5 |  |  | 1020 |  |  | 1098 |  |  | 1107.5 |  |  | 1079.5 |  |  | 987.5 |  |  | 1020.5 |  |  | 1090.5 |  |  | 1107 |  |  | 1070.5 |  |  | 1067 |  |  | 1059 |  |  | 1066 |  |  | 1076 |  |  | 1090.5 |  |  | 983 |  |  | 976 |  |  | 1036.5 |  |  | 1024.5 |  |  | 975 |  |  | 1031.5 |  |  | 1035.5 |  |  | 1114 |  |  | 1041 |  |  | 1042 |  |  | 1047.5 |  |  | 1060 |  |  | 1055.5 |  |  | 1049 |  |  | 1135 |  |  | 1127.5 |  |  | 1034 |  |  | 1171 |  |  | 1017 |  |  | 1063 |  |  | 1089 |  |  | 1020 |  |  | 996 |  |  | 1017 |  |  | 990.5 |  |  | 1051.5 |  |  | 1095 |  |  | 1098.5 |  |  | 929.5 |  |  | 1034 |  |  | 945 |  |  | 1078 |  |  | 1097.5 |  |  | 1042.5 |  |  | 1013 |  |  | 1135 |  |  | 1002 |  |  | 941 |  |  | 1083 |  |  | 1014 |  |  | 1136 |  |  | 1045.5 |  |  | 1076 |  |  | 1091 |  |  | 1141 |  |  | 1002 |  |  | 990 |  |  | 1077.5 |  |  | 1164.5 |  |  | 978.5 |  |  | 1016 |  |  | 971 |  |  | 1010.5 |  |  | 1134.5 |  |  | 1063.5 |  |  | 1032 |  |  | 1116.5 |  |  | 1070.5 |  |  | 1014 |  |  | 1032.5 |  |  | 1086.5 |  |  | 1038 |  |  | 984 |  |  | 1051 |  |  | 1056 |  |  | 1067 |  |  | 987 |  |  | 1095 |  |  | 1149 |  |  | 1028 |  |  | 987 |  |  | 1078.5 |  |  | 1061 |  |  | 1090 |  |  | 969 |  |  | 1051.5 |  |  | 1079 |  |  | 1057.5 |  |  | 1102 |  |  | 1081 |  |  | 1066 |  |  | 1036 |  |  | 1099.5 |  |  | 1029 |  |  | 1011 |  |  | 1136.5 |  |  | 1088 |  |  | 1013 |  |  | 993.5 |  |  | 1022.5 |  |  | 1159 |  |  | 1002.5 |  |  | 1083 |  |  | 1049.5 |  |  | 1071 |  |  | 1083 |  |  | 1074.5 |  |  | 1173.5 |  |  | 1103 |  |  | 1054 |  |  | 1085 |  |  | 1055 |  |  | 962 |  |  | 1115 |  |  | 982 |  |  | 979 |  |  | 1156.5 |  |  | 1015 |  |  | 1090.5 |  |  | 1055 |  |  | 1089.5 |  |  | 1031.5 |  |  | 1042 |  |  | 1105 |  |  | 1102.5 |  |  | 1099 |  |  | 1035 |  |  | 1103 |  |  | 1035.5 |  |  | 1093 |  |  | 986.5 |  |  | 1020 |  |  | 1040 |  |  | 1086 |  |  | 1136 |  |  | 1090.5 |  |  | 1003 |  |  | 1095 |  |  | 1065 |  |  | 1007.5 |  |  | 1169 |  |  | 1075 |  |  | 1091 |  |  | 1000 |  |  | 1075.5 |  |  | 1009.5 |  |  | 1063 |  |  | 1088 |  |  | 1093 |  |  | 1081.5 |  |  | 1046 |  |  | 1020 |  |  | 1009 |  |  | 1153.5 |  |  | 1057.5 |  |  | 1092.5 |  |  | 1014 |  |  | 1124 |  |  | 1040 |  |  | 1058.5 |  |  | 1044 |  |  | 1054.5 |  |  | 919 |  |  | 987 |  |  | 1105 |  |  | 1016.5 |  |  | 1076.5 |  |  | 1035 |  |  | 1007 |  |  | 1107.5 |  |  | 1013 |  |  | 1092 |  |  | 1074.5 |  |  | 1063 |  |  | 1014 |  |  | 1093.5 |  |  | 947 |  |  | 1118 |  |  | 1052.5 |  |  | 1059 |  |  | 1041.5 |  |  | 1085 |  |  | 995.5 |  |  | 1072.5 |  |  | 959 |  |  | 1135 |  |  | 1097.5 |  |  | 1058.5 |  |  | 1112 |  |  | 1027 |  |  | 1121 |  |  | 1037.5 |  |  | 1080 |  |  | 1024 |  |  | 1098 |  |  | 1125.5 |  |  | 1057.5 |  |  | 1032 |  |  | 1138 |  |  | 1028 |  |  | 1056 |  |  | 1132 |  |  | 1004 |  |  | 1067 |  |  | 1023.5 |  |  | 1022.5 |  |  | 1015.5 |  |  | 1037 |  |  | 1027.5 |  |  | 1051 |  |  | 978 |  |  | 1068.5 |  |  | 983.5 |  |  | 894 |  |  | 1043 |  |  | 936.5 |  |  | 1027 |  |  | 1031 |  |  | 998.5 |  |  | 1010.5 |  |  | 1079 |  |  | 1094 |  |  | 1079 |  |  | 980.5 |  |  | 1000 |  |  | 996 |  |  | 1044 |  |  | 997 |  |  | 1138 |  |  | 1088.5 |  |  | 1041 |  |  | 993 |  |  | 902 |  |  | 1113.5 |  |  | 1139 |  |  | 1042.5 |  |  | 1010.5 |  |  | 1051 |  |  | 1017 |  |  | 1062.5 |  |  | 985.5 |  |  | 1002.5 |  |  | 1048.5 |  |  | 1087.5 |  |  | 1130 |  |  | 1027 |  |  | 1122.5 |  |  | 1022.5 |  |  | 1059 |  |  | 1026 |  |  | 1046.5 |  |  | 1048 |  |  | 1071 |  |  | 962 |  |  | 1089.5 |  |  | 1079 |  |  | 1016.5 |  |  | 1015 |  |  | 1054.5 |  |  | 1081.5 |  |  | 1125.5 |  |  | 1035 |  |  | 1015 |  |  | 1077.5 |  |  | 1021.5 |  |  | 1077 |  |  | 1047 |  |  | 1030.5 |  |  | 1052 |  |  | 1068.5 |  |  | 1058.5 |  |  | 1027 |  |  | 1050 |  |  | 1010.5 |  |  | 1105.5 |  |  | 1001 |  |  | 986.5 |  |  | 1085.5 |  |  | 992 |  |  | 1110 |  |  | 1135 |  |  | 1039.5 |  |  | 1089 |  |  | 1024 |  |  | 1049 |  |  | 1059 |  |  | 1098 |  |  | 996 |  |  | 1092.5 |  |  | 1001.5 |  |  | 1006 |  |  | 974 |  |  | 1059 |  |  | 1086.5 |  |  | 1037 |  |  | 1118 |  |  | 981.5 |  |  | 1033.5 |  |  | 1020 |  |  | 1026.5 |  |  | 1046 |  |  | 1010 |  |  | 1045 |  |  | 1109.5 |  |  | 1139 |  |  | 1024.5 |  |  | 989.5 |  |  | 996 |  |  | 1059.5 |  |  | 953.5 |  |  | 959 |  |  | 999 |  |  | 1154 |  |  | 1007.5 |  |  | 971 |  |  | 1037.5 |  |  | 1068.5 |  |  | 1141 |  |  | 1011.5 |  |  | 1036 |  |  | 1092 |  |  | 1045 |  |  | 976 |  |  | 992 |  |  | 1129.5 |  |  | 1068 |  |  | 1070 |  |  | 1004 |  |  | 1146 |  |  | 1004.5 |  |  | 1134.5 |  |  | 1038 |  |  | 1014 |  |  | 1015 |  |  | 1003 |  |  | 1095 |  |  | 1090.5 |  |  | 1117 |  |  | 1040.5 |  |  | 1145 |  |  | 964 |  |  | 1027 |  |  | 1016 |  |  | 1015.5 |  |  | 1010 |  |  | 1037.5 |  |  | 948 |  |  | 1136 |  |  | 1099 |  |  | 1064.5 |  |  | 1050 |  |  | 1028 |  |  | 982 |  |  | 1204 |  |  | 1120 |  |  | 1040.5 |  |  | 1067.5 |  |  | 1012 |  |  | 1010.5 |  |  | 1012 |  |  | 990.5 |  |  | 1056.5 |  |  | 1012.5 |  |  | 1044.5 |  |  | 954 |  |  | 1125 |  |  | 991 |  |  | 989 |  |  | 1091 |  |  | 998 |  |  | 1032.5 |  |  | 989.5 |  |  | 1070.5 |  |  | 1125 |  |  | 1028.5 |  |  | 1071.5 |  |  | 1082.5 |  |  | 1045.5 |  |  | 1059 |  |  | 1033.5 |  |  | 1010.5 |  |  | 1111 |  |  | 1095.5 |  |  | 1066.5 |  |  | 1075.5 |  |  | 1127 |  |  | 1106.5 |  |  | 1067 |  |  | 1022 |  |  | 1086.5 |  |  | 1066.5 |  |  | 1088 |  |  | 1080 |  |  | 1005.5 |  |  | 989.5 |  |  | 1110.5 |  |  | 1111 |  |  | 1054 |  |  | 1041 |  |  | 1026.5 |  |  | 1031.5 |  |  | 1048 |  |  | 1072.5 |  |  | 1003 |  |  | 1027 |  |  | 1046.5 |  |  | 957.5 |  |  | 1036 |  |  | 1048.5 |  |  | 1034 |  |  | 982.5 |  |  | 1141.5 |  |  | 1046 |  |  | 971.5 |  |  | 1029 |  |  | 1092.5 |  |  | 1057 |  |  | 1096 |  |  | 1097 |  |  | 1037.5 |  |  | 964.5 |  |  | 1070 |  |  | 960 |  |  | 992 |  |  | 1072.5 |  |  | 1003.5 |  |  | 1029 |  |  | 1057.5 |  |  | 1026 |  |  | 1058.5 |  |  | 1038.5 |  |  | 974 |  |  | 1065 |  |  | 1044 |  |  | 1035.5 |  |  | 1012 |  |  | 1116.5 |  |  | 1089 |  |  | 1028.5 |  |  | 1116 |  |  | 935.5 |  |  | 1066 |  |  | 1010.5 |  |  | 1053.5 |  |  | 1055 |  |  | 1033 |  |  | 1062 |  |  | 1057 |  |  | 1055.5 |  |  | 1002 |  |  | 998.5 |  |  | 973 |  |  | 1091 |  |  | 1090 |  |  | 1110 |  |  | 1120 |  |  | 1052 |  |  | 1026 |  |  | 1055.5 |  |  | 973 |  |  | 1139
39 |  | 1105.5 |  |  | 1112 |  |  | 1073.5 |  |  | 1094 |  |  | 1089.5 |  |  | 1065 |  |  | 1082 |  |  | 1132 |  |  | 1092.5 |  |  | 1061 |  |  | 1088 |  |  | 1178 |  |  | 1092 |  |  | 1158 |  |  | 1063.5 |  |  | 1148.5 |  |  | 1035 |  |  | 1116 |  |  | 1130 |  |  | 973.5 |  |  | 1106 |  |  | 1125 |  |  | 1096 |  |  | 1147 |  |  | 1051.5 |  |  | 1173 |  |  | 1129 |  |  | 1064 |  |  | 1109 |  |  | 1102 |  |  | 1037 |  |  | 1054.5 |  |  | 1222.5 |  |  | 1066.5 |  |  | 1050 |  |  | 1022.5 |  |  | 1034.5 |  |  | 1120.5 |  |  | 1067 |  |  | 1113 |  |  | 1026.5 |  |  | 1026 |  |  | 1202.5 |  |  | 1103.5 |  |  | 1131.5 |  |  | 1135.5 |  |  | 1150.5 |  |  | 1073 |  |  | 985 |  |  | 1025.5 |  |  | 1120 |  |  | 1031.5 |  |  | 1056.5 |  |  | 1147 |  |  | 1027 |  |  | 1066 |  |  | 1069 |  |  | 1151 |  |  | 1112 |  |  | 1047.5 |  |  | 1173.5 |  |  | 1147.5 |  |  | 1019 |  |  | 1122 |  |  | 988 |  |  | 1053.5 |  |  | 1088 |  |  | 1154.5 |  |  | 1083.5 |  |  | 1150.5 |  |  | 1015 |  |  | 1061 |  |  | 1057 |  |  | 1064.5 |  |  | 1121.5 |  |  | 1034.5 |  |  | 1098.5 |  |  | 1089.5 |  |  | 1123.5 |  |  | 1097.5 |  |  | 1138.5 |  |  | 1068 |  |  | 1066 |  |  | 1081 |  |  | 1152.5 |  |  | 1079 |  |  | 1030.5 |  |  | 1034 |  |  | 1074 |  |  | 1123.5 |  |  | 1119.5 |  |  | 1094 |  |  | 1258 |  |  | 1063.5 |  |  | 1090 |  |  | 1030.5 |  |  | 1132.5 |  |  | 1093.5 |  |  | 1074.5 |  |  | 1028.5 |  |  | 1154 |  |  | 1036 |  |  | 1037 |  |  | 1127.5 |  |  | 1058.5 |  |  | 1076.5 |  |  | 1068.5 |  |  | 1089 |  |  | 1086 |  |  | 1090.5 |  |  | 1020 |  |  | 1145.5 |  |  | 1089 |  |  | 1125 |  |  | 1031.5 |  |  | 1116 |  |  | 1094 |  |  | 1081 |  |  | 1049 |  |  | 1143.5 |  |  | 1105.5 |  |  | 1003.5 |  |  | 1173 |  |  | 1017 |  |  | 1021 |  |  | 1080 |  |  | 1085.5 |  |  | 1051 |  |  | 1087.5 |  |  | 1115 |  |  | 1043 |  |  | 1119.5 |  |  | 997.5 |  |  | 954 |  |  | 1024.5 |  |  | 1060 |  |  | 1127 |  |  | 1137 |  |  | 1073 |  |  | 1075 |  |  | 1026 |  |  | 997 |  |  | 1120 |  |  | 1038 |  |  | 1037.5 |  |  | 1035 |  |  | 1012 |  |  | 1068 |  |  | 1066 |  |  | 1000 |  |  | 1046 |  |  | 1121 |  |  | 1047.5 |  |  | 1106 |  |  | 1108.5 |  |  | 1096 |  |  | 1048 |  |  | 1139.5 |  |  | 1046 |  |  | 1179.5 |  |  | 1109 |  |  | 1007 |  |  | 1094.5 |  |  | 1023 |  |  | 1088.5 |  |  | 1022 |  |  | 1085 |  |  | 1038.5 |  |  | 1093.5 |  |  | 1088 |  |  | 1020.5 |  |  | 1007.5 |  |  | 1048 |  |  | 1107 |  |  | 1211.5 |  |  | 1065.5 |  |  | 1063.5 |  |  | 1066 |  |  | 1175 |  |  | 1038 |  |  | 1158 |  |  | 1120 |  |  | 1140.5 |  |  | 1045 |  |  | 995.5 |  |  | 1125.5 |  |  | 1153 |  |  | 1092 |  |  | 1149.5 |  |  | 995.5 |  |  | 1036 |  |  | 1100.5 |  |  | 1076.5 |  |  | 1070 |  |  | 1040 |  |  | 1056 |  |  | 1018.5 |  |  | 1160 |  |  | 1090.5 |  |  | 1064.5 |  |  | 1015 |  |  | 1115.5 |  |  | 1020 |  |  | 1105 |  |  | 1102 |  |  | 1100 |  |  | 1033 |  |  | 1094 |  |  | 1181 |  |  | 1113 |  |  | 1176 |  |  | 1049 |  |  | 1074.5 |  |  | 1135.5 |  |  | 1014 |  |  | 970 |  |  | 1125 |  |  | 1071.5 |  |  | 1111.5 |  |  | 1164.5 |  |  | 1059 |  |  | 1126 |  |  | 1161.5 |  |  | 1032.5 |  |  | 973.5 |  |  | 1153 |  |  | 1168 |  |  | 1073 |  |  | 1021 |  |  | 1043 |  |  | 1062.5 |  |  | 1014.5 |  |  | 1109 |  |  | 1085 |  |  | 1091 |  |  | 1122 |  |  | 1012 |  |  | 1042.5 |  |  | 1053 |  |  | 1156 |  |  | 1068 |  |  | 1087 |  |  | 988.5 |  |  | 1213 |  |  | 1137 |  |  | 1052 |  |  | 1156 |  |  | 1126.5 |  |  | 1113 |  |  | 1031 |  |  | 985 |  |  | 1154.5 |  |  | 1116.5 |  |  | 1101.5 |  |  | 1149 |  |  | 1056 |  |  | 1069 |  |  | 1147 |  |  | 1112 |  |  | 1044.5 |  |  | 1176 |  |  | 1064.5 |  |  | 1111.5 |  |  | 1125.5 |  |  | 1027 |  |  | 1123.5 |  |  | 1038 |  |  | 1035 |  |  | 1060.5 |  |  | 1085.5 |  |  | 1166 |  |  | 1188.5 |  |  | 1138.5 |  |  | 1098 |  |  | 1138 |  |  | 1072.5 |  |  | 1052.5 |  |  | 1088 |  |  | 1068.5 |  |  | 1137 |  |  | 1037 |  |  | 1093.5 |  |  | 1094 |  |  | 1017 |  |  | 1100.5 |  |  | 1068 |  |  | 1128.5 |  |  | 1066 |  |  | 1159 |  |  | 1083 |  |  | 1014 |  |  | 1138.5 |  |  | 1199 |  |  | 1125.5 |  |  | 1051.5 |  |  | 1104.5 |  |  | 1166 |  |  | 1154.5 |  |  | 1187 |  |  | 1125 |  |  | 992.5 |  |  | 1067.5 |  |  | 1106 |  |  | 1096.5 |  |  | 1105 |  |  | 1077 |  |  | 1167.5 |  |  | 1070 |  |  | 1055.5 |  |  | 1089.5 |  |  | 1103.5 |  |  | 1081 |  |  | 1000 |  |  | 1144 |  |  | 1001.5 |  |  | 1042 |  |  | 1117.5 |  |  | 1105 |  |  | 1091 |  |  | 1000 |  |  | 1091 |  |  | 1150 |  |  | 1092 |  |  | 1056 |  |  | 1193 |  |  | 1110 |  |  | 1097.5 |  |  | 1058 |  |  | 998 |  |  | 1225.5 |  |  | 992.5 |  |  | 1133.5 |  |  | 1158.5 |  |  | 1055 |  |  | 1161 |  |  | 985.5 |  |  | 1117.5 |  |  | 1169.5 |  |  | 1149 |  |  | 1073 |  |  | 1082 |  |  | 1074 |  |  | 1017 |  |  | 1078 |  |  | 1083 |  |  | 1058.5 |  |  | 1064.5 |  |  | 1083 |  |  | 1116.5 |  |  | 1118.5 |  |  | 1042 |  |  | 1116 |  |  | 1084 |  |  | 1087 |  |  | 1074.5 |  |  | 1019.5 |  |  | 1067.5 |  |  | 1046 |  |  | 1074.5 |  |  | 1091 |  |  | 1056 |  |  | 1049 |  |  | 1011.5 |  |  | 1134 |  |  | 968 |  |  | 1077.5 |  |  | 1040 |  |  | 1106.5 |  |  | 1130 |  |  | 1104.5 |  |  | 991 |  |  | 1038.5 |  |  | 1135.5 |  |  | 1139 |  |  | 1043 |  |  | 987 |  |  | 1075 |  |  | 1063.5 |  |  | 1051 |  |  | 1102 |  |  | 1033.5 |  |  | 1153.5 |  |  | 1009.5 |  |  | 1086 |  |  | 1068.5 |  |  | 1089.5 |  |  | 1075.5 |  |  | 1177 |  |  | 1095 |  |  | 1061.5 |  |  | 1099 |  |  | 1143 |  |  | 1052.5 |  |  | 1076 |  |  | 1112 |  |  | 1074 |  |  | 1014 |  |  | 1036.5 |  |  | 1154.5 |  |  | 1017 |  |  | 1139 |  |  | 1113 |  |  | 1069 |  |  | 1066 |  |  | 1042.5 |  |  | 1111.5 |  |  | 1068 |  |  | 1230 |  |  | 1161 |  |  | 998.5 |  |  | 1150.5 |  |  | 1050 |  |  | 1007 |  |  | 1010 |  |  | 1075.5 |  |  | 1170.5 |  |  | 1104 |  |  | 1034 |  |  | 1158 |  |  | 1092 |  |  | 1034 |  |  | 1127 |  |  | 1063 |  |  | 1138.5 |  |  | 986 |  |  | 1169 |  |  | 1077 |  |  | 1137.5 |  |  | 1196 |  |  | 978 |  |  | 980 |  |  | 1132 |  |  | 1119 |  |  | 1081 |  |  | 1055 |  |  | 1059.5 |  |  | 1082.5 |  |  | 1046.5 |  |  | 1085 |  |  | 1118 |  |  | 1133.5 |  |  | 1051 |  |  | 1086.5 |  |  | 1074.5 |  |  | 1017 |  |  | 1029 |  |  | 1195.5 |  |  | 1123 |  |  | 1089 |  |  | 1093 |  |  | 1075 |  |  | 1035 |  |  | 1057 |  |  | 1072 |  |  | 1181.5 |  |  | 1067 |  |  | 1023 |  |  | 1117 |  |  | 1045 |  |  | 1148 |  |  | 992 |  |  | 1176 |  |  | 1136 |  |  | 1097 |  |  | 1214.5 |  |  | 1092.5 |  |  | 1042.5 |  |  | 1052.5 |  |  | 1127 |  |  | 1020 |  |  | 1143.5 |  |  | 1074 |  |  | 1103 |  |  | 1092.5 |  |  | 1149.5 |  |  | 1121 |  |  | 1073.5 |  |  | 1079.5 |  |  | 984 |  |  | 1096 |  |  | 1008 |  |  | 1118 |  |  | 1110.5 |  |  | 1032 |  |  | 1110.5 |  |  | 1034.5 |  |  | 1000 |  |  | 1082 |  |  | 1043.5 |  |  | 1095 |  |  | 1130.5 |  |  | 1044 |  |  | 1105.5 |  |  | 1002.5 |  |  | 1062.5 |  |  | 1113.5 |  |  | 1117.5 |  |  | 1092 |  |  | 1097 |  |  | 1209.5 |  |  | 1132 |  |  | 1046 |  |  | 1077 |  |  | 1120 |  |  | 1122.5 |  |  | 993 |  |  | 1042 |  |  | 1122 |  |  | 1080.5 |  |  | 1071 |  |  | 1040 |  |  | 1091 |  |  | 1180.5 |  |  | 1093 |  |  | 945 |  |  | 1039 |  |  | 1128 |  |  | 1207.5 |  |  | 1073 |  |  | 1029.5 |  |  | 1092 |  |  | 1134 |  |  | 1203.5 |  |  | 1132 |  |  | 1038 |  |  | 959.5 |  |  | 1091 |  |  | 1015 |  |  | 1110 |  |  | 1136.5 |  |  | 1022.5 |  |  | 1078 |  |  | 1018 |  |  | 1093.5 |  |  | 1082.5 |  |  | 1046 |  |  | 1137 |  |  | 1131.5 |  |  | 1118.5 |  |  | 1026.5 |  |  | 1041.5 |  |  | 1137.5 |  |  | 1154 |  |  | 1091.5 |  |  | 1093 |  |  | 1088 |  |  | 1113 |  |  | 1115 |  |  | 1114.5 |  |  | 1012 |  |  | 991 |  |  | 1083.5 |  |  | 1048.5 |  |  | 1014 |  |  | 1078.5 |  |  | 1059.5 |  |  | 1135 |  |  | 1062 |  |  | 1081 |  |  | 1076.5 |  |  | 1089 |  |  | 1070.5 |  |  | 1070 |  |  | 1161 |  |  | 1148.5 |  |  | 1049 |  |  | 1218 |  |  | 1056 |  |  | 1089 |  |  | 1128 |  |  | 1049 |  |  | 1035 |  |  | 1056 |  |  | 1019.5 |  |  | 1072.5 |  |  | 1134 |  |  | 1113.5 |  |  | 944.5 |  |  | 1049 |  |  | 971 |  |  | 1093 |  |  | 1136.5 |  |  | 1057.5 |  |  | 1037 |  |  | 1161 |  |  | 1026 |  |  | 965 |  |  | 1104 |  |  | 1029 |  |  | 1183 |  |  | 1092.5 |  |  | 1100 |  |  | 1130 |  |  | 1188 |  |  | 1049 |  |  | 1011 |  |  | 1106.5 |  |  | 1185.5 |  |  | 1002.5 |  |  | 1042 |  |  | 1010 |  |  | 1025.5 |  |  | 1149.5 |  |  | 1078.5 |  |  | 1061 |  |  | 1142.5 |  |  | 1085.5 |  |  | 1061 |  |  | 1047.5 |  |  | 1110.5 |  |  | 1077 |  |  | 999 |  |  | 1090 |  |  | 1095 |  |  | 1082 |  |  | 1008 |  |  | 1121 |  |  | 1188 |  |  | 1057 |  |  | 1002 |  |  | 1099.5 |  |  | 1082 |  |  | 1137 |  |  | 1008 |  |  | 1072.5 |  |  | 1105 |  |  | 1086.5 |  |  | 1126 |  |  | 1107 |  |  | 1090 |  |  | 1083 |  |  | 1114.5 |  |  | 1058 |  |  | 1037 |  |  | 1157.5 |  |  | 1127 |  |  | 1042 |  |  | 1019.5 |  |  | 1061.5 |  |  | 1180 |  |  | 1026.5 |  |  | 1122 |  |  | 1075.5 |  |  | 1110 |  |  | 1098 |  |  | 1113.5 |  |  | 1194.5 |  |  | 1127 |  |  | 1083 |  |  | 1100 |  |  | 1102 |  |  | 988 |  |  | 1154 |  |  | 1021 |  |  | 1018 |  |  | 1203.5 |  |  | 1039 |  |  | 1137.5 |  |  | 1094 |  |  | 1104.5 |  |  | 1052.5 |  |  | 1071 |  |  | 1152 |  |  | 1123.5 |  |  | 1138 |  |  | 1050 |  |  | 1118 |  |  | 1074.5 |  |  | 1117 |  |  | 1025.5 |  |  | 1046 |  |  | 1066 |  |  | 1110 |  |  | 1151 |  |  | 1137.5 |  |  | 1018 |  |  | 1110 |  |  | 1094 |  |  | 1036.5 |  |  | 1184 |  |  | 1099 |  |  | 1130 |  |  | 1039 |  |  | 1104.5 |  |  | 1056.5 |  |  | 1102 |  |  | 1135 |  |  | 1114 |  |  | 1107.5 |  |  | 1072 |  |  | 1059 |  |  | 1024 |  |  | 1182.5 |  |  | 1083.5 |  |  | 1139.5 |  |  | 1053 |  |  | 1148 |  |  | 1069 |  |  | 1105.5 |  |  | 1083 |  |  | 1080.5 |  |  | 958 |  |  | 1013 |  |  | 1126 |  |  | 1045.5 |  |  | 1100.5 |  |  | 1064 |  |  | 1028 |  |  | 1131.5 |  |  | 1052 |  |  | 1139 |  |  | 1113.5 |  |  | 1092 |  |  | 1029 |  |  | 1132.5 |  |  | 994 |  |  | 1139 |  |  | 1099.5 |  |  | 1080 |  |  | 1088.5 |  |  | 1124 |  |  | 1016.5 |  |  | 1119.5 |  |  | 980 |  |  | 1164 |  |  | 1126.5 |  |  | 1097.5 |  |  | 1151 |  |  | 1056 |  |  | 1145 |  |  | 1066.5 |  |  | 1106 |  |  | 1039 |  |  | 1122 |  |  | 1172.5 |  |  | 1104.5 |  |  | 1071 |  |  | 1177 |  |  | 1067 |  |  | 1085 |  |  | 1153 |  |  | 1043 |  |  | 1114 |  |  | 1044.5 |  |  | 1051.5 |  |  | 1030.5 |  |  | 1076 |  |  | 1048.5 |  |  | 1090 |  |  | 999 |  |  | 1089.5 |  |  | 1030.5 |  |  | 933 |  |  | 1069 |  |  | 962.5 |  |  | 1051 |  |  | 1046 |  |  | 1027.5 |  |  | 1031.5 |  |  | 1100 |  |  | 1109 |  |  | 1126 |  |  | 1001.5 |  |  | 1015 |  |  | 1011 |  |  | 1073 |  |  | 1036 |  |  | 1177 |  |  | 1127.5 |  |  | 1088 |  |  | 1022 |  |  | 949 |  |  | 1142.5 |  |  | 1160 |  |  | 1057.5 |  |  | 1057.5 |  |  | 1098 |  |  | 1043 |  |  | 1083.5 |  |  | 1024.5 |  |  | 1031.5 |  |  | 1074.5 |  |  | 1111.5 |  |  | 1169 |  |  | 1066 |  |  | 1161.5 |  |  | 1061.5 |  |  | 1085 |  |  | 1052 |  |  | 1070.5 |  |  | 1069 |  |  | 1086 |  |  | 986 |  |  | 1113.5 |  |  | 1118 |  |  | 1042.5 |  |  | 1041 |  |  | 1083.5 |  |  | 1105.5 |  |  | 1154.5 |  |  | 1050 |  |  | 1039 |  |  | 1124.5 |  |  | 1050.5 |  |  | 1116 |  |  | 1071 |  |  | 1054.5 |  |  | 1073 |  |  | 1107.5 |  |  | 1082.5 |  |  | 1066 |  |  | 1065 |  |  | 1049.5 |  |  | 1152.5 |  |  | 1025 |  |  | 1025.5 |  |  | 1132.5 |  |  | 1021 |  |  | 1139 |  |  | 1174 |  |  | 1078.5 |  |  | 1128 |  |  | 1039 |  |  | 1064 |  |  | 1106 |  |  | 1137 |  |  | 1020 |  |  | 1139.5 |  |  | 1040.5 |  |  | 1030 |  |  | 998 |  |  | 1088 |  |  | 1101.5 |  |  | 1076 |  |  | 1165 |  |  | 1028.5 |  |  | 1072.5 |  |  | 1067 |  |  | 1055.5 |  |  | 1061 |  |  | 1039 |  |  | 1069 |  |  | 1148.5 |  |  | 1186 |  |  | 1053.5 |  |  | 1036.5 |  |  | 1022 |  |  | 1085.5 |  |  | 982.5 |  |  | 983 |  |  | 1038 |  |  | 1193 |  |  | 1028.5 |  |  | 1010 |  |  | 1076.5 |  |  | 1094.5 |  |  | 1170 |  |  | 1026.5 |  |  | 1051 |  |  | 1121 |  |  | 1066 |  |  | 1015 |  |  | 1039 |  |  | 1153.5 |  |  | 1107 |  |  | 1096 |  |  | 1030 |  |  | 1175 |  |  | 1028.5 |  |  | 1155.5 |  |  | 1067 |  |  | 1053 |  |  | 1039 |  |  | 1042 |  |  | 1134 |  |  | 1116.5 |  |  | 1138 |  |  | 1066.5 |  |  | 1169 |  |  | 1003 |  |  | 1066 |  |  | 1042 |  |  | 1036.5 |  |  | 1057 |  |  | 1061.5 |  |  | 987 |  |  | 1165 |  |  | 1123 |  |  | 1090.5 |  |  | 1089 |  |  | 1043 |  |  | 1011 |  |  | 1219 |  |  | 1146 |  |  | 1079.5 |  |  | 1106.5 |  |  | 1059 |  |  | 1031.5 |  |  | 1038 |  |  | 1016.5 |  |  | 1080.5 |  |  | 1051.5 |  |  | 1091.5 |  |  | 969 |  |  | 1172 |  |  | 1012 |  |  | 1018 |  |  | 1130 |  |  | 1019 |  |  | 1071.5 |  |  | 1028.5 |  |  | 1099.5 |  |  | 1164 |  |  | 1067.5 |  |  | 1097.5 |  |  | 1129.5 |  |  | 1071.5 |  |  | 1083 |  |  | 1080.5 |  |  | 1049.5 |  |  | 1135 |  |  | 1121.5 |  |  | 1087.5 |  |  | 1101.5 |  |  | 1151 |  |  | 1121.5 |  |  | 1114 |  |  | 1051 |  |  | 1112.5 |  |  | 1092.5 |  |  | 1117 |  |  | 1109 |  |  | 1044.5 |  |  | 1028.5 |  |  | 1139.5 |  |  | 1140 |  |  | 1078 |  |  | 1056 |  |  | 1050.5 |  |  | 1078.5 |  |  | 1072 |  |  | 1119.5 |  |  | 1024 |  |  | 1042 |  |  | 1085.5 |  |  | 996.5 |  |  | 1057 |  |  | 1087.5 |  |  | 1049 |  |  | 1029.5 |  |  | 1188.5 |  |  | 1070 |  |  | 986.5 |  |  | 1058 |  |  | 1116.5 |  |  | 1086 |  |  | 1122 |  |  | 1136 |  |  | 1061.5 |  |  | 979.5 |  |  | 1117 |  |  | 1007 |  |  | 1031 |  |  | 1111.5 |  |  | 1042.5 |  |  | 1068 |  |  | 1081.5 |  |  | 1073 |  |  | 1082.5 |  |  | 1077.5 |  |  | 1000 |  |  | 1080 |  |  | 1068 |  |  | 1074.5 |  |  | 1036 |  |  | 1163.5 |  |  | 1128 |  |  | 1067.5 |  |  | 1163 |  |  | 950.5 |  |  | 1087 |  |  | 1025.5 |  |  | 1092.5 |  |  | 1079 |  |  | 1062 |  |  | 1101 |  |  | 1096 |  |  | 1094.5 |  |  | 1017 |  |  | 1024.5 |  |  | 1012 |  |  | 1130 |  |  | 1116 |  |  | 1139 |  |  | 1144 |  |  | 1076 |  |  | 1055 |  |  | 1094.5 |  |  | 988 |  |  | 1168
40 |  | 1129.5 |  |  | 1151 |  |  | 1088.5 |  |  | 1123 |  |  | 1128.5 |  |  | 1094 |  |  | 1129 |  |  | 1156 |  |  | 1107.5 |  |  | 1108 |  |  | 1112 |  |  | 1207 |  |  | 1139 |  |  | 1187 |  |  | 1087.5 |  |  | 1174.5 |  |  | 1059 |  |  | 1155 |  |  | 1177 |  |  | 1002.5 |  |  | 1132 |  |  | 1140 |  |  | 1117 |  |  | 1168 |  |  | 1090.5 |  |  | 1197 |  |  | 1168 |  |  | 1085 |  |  | 1135 |  |  | 1123 |  |  | 1052 |  |  | 1093.5 |  |  | 1246.5 |  |  | 1092.5 |  |  | 1076 |  |  | 1061.5 |  |  | 1055.5 |  |  | 1159.5 |  |  | 1082 |  |  | 1128 |  |  | 1041.5 |  |  | 1047 |  |  | 1217.5 |  |  | 1118.5 |  |  | 1170.5 |  |  | 1161.5 |  |  | 1174.5 |  |  | 1097 |  |  | 1009 |  |  | 1064.5 |  |  | 1135 |  |  | 1055.5 |  |  | 1077.5 |  |  | 1171 |  |  | 1051 |  |  | 1081 |  |  | 1108 |  |  | 1190 |  |  | 1141 |  |  | 1071.5 |  |  | 1194.5 |  |  | 1176.5 |  |  | 1045 |  |  | 1151 |  |  | 1027 |  |  | 1092.5 |  |  | 1114 |  |  | 1175.5 |  |  | 1122.5 |  |  | 1179.5 |  |  | 1054 |  |  | 1090 |  |  | 1081 |  |  | 1079.5 |  |  | 1160.5 |  |  | 1073.5 |  |  | 1124.5 |  |  | 1128.5 |  |  | 1152.5 |  |  | 1144.5 |  |  | 1177.5 |  |  | 1089 |  |  | 1105 |  |  | 1120 |  |  | 1167.5 |  |  | 1118 |  |  | 1056.5 |  |  | 1049 |  |  | 1113 |  |  | 1147.5 |  |  | 1143.5 |  |  | 1118 |  |  | 1305 |  |  | 1089.5 |  |  | 1119 |  |  | 1059.5 |  |  | 1147.5 |  |  | 1132.5 |  |  | 1103.5 |  |  | 1043.5 |  |  | 1180 |  |  | 1075 |  |  | 1061 |  |  | 1166.5 |  |  | 1073.5 |  |  | 1100.5 |  |  | 1107.5 |  |  | 1118 |  |  | 1125 |  |  | 1111.5 |  |  | 1059 |  |  | 1171.5 |  |  | 1136 |  |  | 1146 |  |  | 1055.5 |  |  | 1155 |  |  | 1109 |  |  | 1107 |  |  | 1070 |  |  | 1158.5 |  |  | 1129.5 |  |  | 1050.5 |  |  | 1194 |  |  | 1043 |  |  | 1042 |  |  | 1095 |  |  | 1132.5 |  |  | 1090 |  |  | 1126.5 |  |  | 1154 |  |  | 1064 |  |  | 1140.5 |  |  | 1018.5 |  |  | 980 |  |  | 1053.5 |  |  | 1084 |  |  | 1148 |  |  | 1152 |  |  | 1120 |  |  | 1096 |  |  | 1065 |  |  | 1018 |  |  | 1144 |  |  | 1062 |  |  | 1058.5 |  |  | 1050 |  |  | 1036 |  |  | 1092 |  |  | 1113 |  |  | 1026 |  |  | 1085 |  |  | 1136 |  |  | 1086.5 |  |  | 1153 |  |  | 1155.5 |  |  | 1135 |  |  | 1087 |  |  | 1160.5 |  |  | 1085 |  |  | 1218.5 |  |  | 1130 |  |  | 1036 |  |  | 1133.5 |  |  | 1062 |  |  | 1109.5 |  |  | 1037 |  |  | 1109 |  |  | 1077.5 |  |  | 1108.5 |  |  | 1127 |  |  | 1059.5 |  |  | 1022.5 |  |  | 1087 |  |  | 1146 |  |  | 1250.5 |  |  | 1080.5 |  |  | 1078.5 |  |  | 1090 |  |  | 1214 |  |  | 1062 |  |  | 1197 |  |  | 1159 |  |  | 1166.5 |  |  | 1066 |  |  | 1042.5 |  |  | 1146.5 |  |  | 1179 |  |  | 1139 |  |  | 1188.5 |  |  | 1016.5 |  |  | 1065 |  |  | 1147.5 |  |  | 1091.5 |  |  | 1094 |  |  | 1055 |  |  | 1082 |  |  | 1047.5 |  |  | 1184 |  |  | 1111.5 |  |  | 1085.5 |  |  | 1044 |  |  | 1130.5 |  |  | 1041 |  |  | 1144 |  |  | 1128 |  |  | 1139 |  |  | 1072 |  |  | 1133 |  |  | 1210 |  |  | 1160 |  |  | 1215 |  |  | 1064 |  |  | 1100.5 |  |  | 1182.5 |  |  | 1053 |  |  | 1009 |  |  | 1172 |  |  | 1095.5 |  |  | 1150.5 |  |  | 1211.5 |  |  | 1074 |  |  | 1173 |  |  | 1208.5 |  |  | 1061.5 |  |  | 997.5 |  |  | 1179 |  |  | 1189 |  |  | 1094 |  |  | 1045 |  |  | 1082 |  |  | 1077.5 |  |  | 1043.5 |  |  | 1156 |  |  | 1132 |  |  | 1106 |  |  | 1151 |  |  | 1041 |  |  | 1089.5 |  |  | 1092 |  |  | 1203 |  |  | 1115 |  |  | 1111 |  |  | 1012.5 |  |  | 1252 |  |  | 1158 |  |  | 1076 |  |  | 1185 |  |  | 1165.5 |  |  | 1160 |  |  | 1055 |  |  | 1014 |  |  | 1180.5 |  |  | 1142.5 |  |  | 1140.5 |  |  | 1175 |  |  | 1095 |  |  | 1093 |  |  | 1168 |  |  | 1159 |  |  | 1068.5 |  |  | 1202 |  |  | 1085.5 |  |  | 1150.5 |  |  | 1146.5 |  |  | 1066 |  |  | 1138.5 |  |  | 1067 |  |  | 1056 |  |  | 1107.5 |  |  | 1111.5 |  |  | 1190 |  |  | 1227.5 |  |  | 1164.5 |  |  | 1122 |  |  | 1153 |  |  | 1101.5 |  |  | 1076.5 |  |  | 1127 |  |  | 1094.5 |  |  | 1158 |  |  | 1052 |  |  | 1117.5 |  |  | 1123 |  |  | 1038 |  |  | 1129.5 |  |  | 1107 |  |  | 1154.5 |  |  | 1090 |  |  | 1198 |  |  | 1098 |  |  | 1043 |  |  | 1185.5 |  |  | 1228 |  |  | 1164.5 |  |  | 1090.5 |  |  | 1128.5 |  |  | 1205 |  |  | 1178.5 |  |  | 1208 |  |  | 1164 |  |  | 1031.5 |  |  | 1091.5 |  |  | 1135 |  |  | 1122.5 |  |  | 1126 |  |  | 1101 |  |  | 1193.5 |  |  | 1109 |  |  | 1081.5 |  |  | 1113.5 |  |  | 1150.5 |  |  | 1120 |  |  | 1039 |  |  | 1165 |  |  | 1040.5 |  |  | 1063 |  |  | 1156.5 |  |  | 1126 |  |  | 1115 |  |  | 1039 |  |  | 1130 |  |  | 1179 |  |  | 1116 |  |  | 1080 |  |  | 1222 |  |  | 1131 |  |  | 1123.5 |  |  | 1097 |  |  | 1037 |  |  | 1264.5 |  |  | 1007.5 |  |  | 1159.5 |  |  | 1187.5 |  |  | 1102 |  |  | 1208 |  |  | 1024.5 |  |  | 1132.5 |  |  | 1198.5 |  |  | 1170 |  |  | 1112 |  |  | 1097 |  |  | 1098 |  |  | 1064 |  |  | 1107 |  |  | 1122 |  |  | 1097.5 |  |  | 1085.5 |  |  | 1122 |  |  | 1140.5 |  |  | 1157.5 |  |  | 1063 |  |  | 1137 |  |  | 1105 |  |  | 1116 |  |  | 1100.5 |  |  | 1034.5 |  |  | 1088.5 |  |  | 1085 |  |  | 1098.5 |  |  | 1120 |  |  | 1080 |  |  | 1088 |  |  | 1026.5 |  |  | 1160 |  |  | 992 |  |  | 1103.5 |  |  | 1069 |  |  | 1135.5 |  |  | 1177 |  |  | 1125.5 |  |  | 1038 |  |  | 1059.5 |  |  | 1156.5 |  |  | 1165 |  |  | 1082 |  |  | 1013 |  |  | 1099 |  |  | 1092.5 |  |  | 1072 |  |  | 1123 |  |  | 1072.5 |  |  | 1168.5 |  |  | 1035.5 |  |  | 1112 |  |  | 1092.5 |  |  | 1104.5 |  |  | 1122.5 |  |  | 1192 |  |  | 1110 |  |  | 1090.5 |  |  | 1138 |  |  | 1182 |  |  | 1076.5 |  |  | 1102 |  |  | 1136 |  |  | 1113 |  |  | 1053 |  |  | 1065.5 |  |  | 1183.5 |  |  | 1038 |  |  | 1165 |  |  | 1128 |  |  | 1084 |  |  | 1095 |  |  | 1089.5 |  |  | 1135.5 |  |  | 1115 |  |  | 1245 |  |  | 1176 |  |  | 1027.5 |  |  | 1165.5 |  |  | 1097 |  |  | 1054 |  |  | 1049 |  |  | 1114.5 |  |  | 1209.5 |  |  | 1143 |  |  | 1058 |  |  | 1197 |  |  | 1107 |  |  | 1063 |  |  | 1166 |  |  | 1092 |  |  | 1185.5 |  |  | 1010 |  |  | 1216 |  |  | 1092 |  |  | 1161.5 |  |  | 1217 |  |  | 993 |  |  | 1001 |  |  | 1156 |  |  | 1148 |  |  | 1102 |  |  | 1094 |  |  | 1088.5 |  |  | 1106.5 |  |  | 1070.5 |  |  | 1111 |  |  | 1133 |  |  | 1172.5 |  |  | 1066 |  |  | 1110.5 |  |  | 1095.5 |  |  | 1043 |  |  | 1055 |  |  | 1219.5 |  |  | 1162 |  |  | 1128 |  |  | 1114 |  |  | 1096 |  |  | 1050 |  |  | 1081 |  |  | 1111 |  |  | 1220.5 |  |  | 1096 |  |  | 1052 |  |  | 1141 |  |  | 1069 |  |  | 1174 |  |  | 1031 |  |  | 1223 |  |  | 1162 |  |  | 1112 |  |  | 1253.5 |  |  | 1116.5 |  |  | 1081.5 |  |  | 1091.5 |  |  | 1151 |  |  | 1049 |  |  | 1190.5 |  |  | 1121 |  |  | 1132 |  |  | 1113.5 |  |  | 1196.5 |  |  | 1147 |  |  | 1094.5 |  |  | 1108.5 |  |  | 1013 |  |  | 1120 |  |  | 1034 |  |  | 1142 |  |  | 1149.5 |  |  | 1056 |  |  | 1139.5 |  |  | 1058.5 |  |  | 1039 |  |  | 1108 |  |  | 1082.5 |  |  | 1116 |  |  | 1177.5 |  |  | 1083 |  |  | 1129.5 |  |  | 1017.5 |  |  | 1101.5 |  |  | 1137.5 |  |  | 1138.5 |  |  | 1118 |  |  | 1123 |  |  | 1238.5 |  |  | 1156 |  |  | 1075 |  |  | 1092 |  |  | 1159 |  |  | 1161.5 |  |  | 1032 |  |  | 1089 |  |  | 1148 |  |  | 1119.5 |  |  | 1095 |  |  | 1066 |  |  | 1130 |  |  | 1219.5 |  |  | 1132 |  |  | 974 |  |  | 1065 |  |  | 1167 |  |  | 1254.5 |  |  | 1102 |  |  | 1068.5 |  |  | 1121 |  |  | 1155 |  |  | 1250.5 |  |  | 1161 |  |  | 1067 |  |  | 998.5 |  |  | 1117 |  |  | 1044 |  |  | 1149 |  |  | 1151.5 |  |  | 1046.5 |  |  | 1099 |  |  | 1057 |  |  | 1117.5 |  |  | 1129.5 |  |  | 1085 |  |  | 1166 |  |  | 1155.5 |  |  | 1147.5 |  |  | 1041.5 |  |  | 1067.5 |  |  | 1158.5 |  |  | 1193 |  |  | 1130.5 |  |  | 1132 |  |  | 1103 |  |  | 1152 |  |  | 1136 |  |  | 1153.5 |  |  | 1051 |  |  | 1017 |  |  | 1109.5 |  |  | 1087.5 |  |  | 1040 |  |  | 1107.5 |  |  | 1106.5 |  |  | 1164 |  |  | 1088 |  |  | 1110 |  |  | 1100.5 |  |  | 1128 |  |  | 1094.5 |  |  | 1109 |  |  | 1176 |  |  | 1187.5 |  |  | 1096 |  |  | 1247 |  |  | 1071 |  |  | 1128 |  |  | 1143 |  |  | 1096 |  |  | 1074 |  |  | 1085 |  |  | 1034.5 |  |  | 1111.5 |  |  | 1149 |  |  | 1137.5 |  |  | 983.5 |  |  | 1073 |  |  | 995 |  |  | 1140 |  |  | 1157.5 |  |  | 1096.5 |  |  | 1066 |  |  | 1190 |  |  | 1065 |  |  | 1004 |  |  | 1130 |  |  | 1076 |  |  | 1222 |  |  | 1107.5 |  |  | 1115 |  |  | 1159 |  |  | 1227 |  |  | 1073 |  |  | 1050 |  |  | 1130.5 |  |  | 1224.5 |  |  | 1028.5 |  |  | 1066 |  |  | 1025 |  |  | 1054.5 |  |  | 1188.5 |  |  | 1125.5 |  |  | 1100 |  |  | 1171.5 |  |  | 1106.5 |  |  | 1082 |  |  | 1062.5 |  |  | 1157.5 |  |  | 1092 |  |  | 1020 |  |  | 1129 |  |  | 1124 |  |  | 1103 |  |  | 1034 |  |  | 1147 |  |  | 1217 |  |  | 1081 |  |  | 1031 |  |  | 1120.5 |  |  | 1103 |  |  | 1161 |  |  | 1047 |  |  | 1087.5 |  |  | 1131 |  |  | 1133.5 |  |  | 1173 |  |  | 1136 |  |  | 1114 |  |  | 1107 |  |  | 1153.5 |  |  | 1097 |  |  | 1052 |  |  | 1196.5 |  |  | 1142 |  |  | 1066 |  |  | 1045.5 |  |  | 1100.5 |  |  | 1195 |  |  | 1050.5 |  |  | 1161 |  |  | 1101.5 |  |  | 1149 |  |  | 1113 |  |  | 1137.5 |  |  | 1223.5 |  |  | 1156 |  |  | 1098 |  |  | 1147 |  |  | 1149 |  |  | 1003 |  |  | 1175 |  |  | 1036 |  |  | 1065 |  |  | 1224.5 |  |  | 1063 |  |  | 1161.5 |  |  | 1133 |  |  | 1119.5 |  |  | 1091.5 |  |  | 1095 |  |  | 1181 |  |  | 1152.5 |  |  | 1153 |  |  | 1089 |  |  | 1165 |  |  | 1113.5 |  |  | 1156 |  |  | 1040.5 |  |  | 1075 |  |  | 1113 |  |  | 1131 |  |  | 1180 |  |  | 1161.5 |  |  | 1057 |  |  | 1136 |  |  | 1141 |  |  | 1060.5 |  |  | 1199 |  |  | 1146 |  |  | 1159 |  |  | 1060 |  |  | 1130.5 |  |  | 1085.5 |  |  | 1149 |  |  | 1174 |  |  | 1153 |  |  | 1154.5 |  |  | 1087 |  |  | 1088 |  |  | 1045 |  |  | 1197.5 |  |  | 1122.5 |  |  | 1178.5 |  |  | 1079 |  |  | 1163 |  |  | 1084 |  |  | 1120.5 |  |  | 1107 |  |  | 1109.5 |  |  | 979 |  |  | 1052 |  |  | 1147 |  |  | 1084.5 |  |  | 1139.5 |  |  | 1088 |  |  | 1049 |  |  | 1170.5 |  |  | 1099 |  |  | 1178 |  |  | 1142.5 |  |  | 1116 |  |  | 1068 |  |  | 1171.5 |  |  | 1033 |  |  | 1160 |  |  | 1120.5 |  |  | 1127 |  |  | 1127.5 |  |  | 1163 |  |  | 1040.5 |  |  | 1148.5 |  |  | 1027 |  |  | 1185 |  |  | 1141.5 |  |  | 1126.5 |  |  | 1190 |  |  | 1095 |  |  | 1160 |  |  | 1113.5 |  |  | 1135 |  |  | 1063 |  |  | 1143 |  |  | 1196.5 |  |  | 1128.5 |  |  | 1118 |  |  | 1192 |  |  | 1088 |  |  | 1124 |  |  | 1182 |  |  | 1069 |  |  | 1129 |  |  | 1059.5 |  |  | 1090.5 |  |  | 1045.5 |  |  | 1115 |  |  | 1074.5 |  |  | 1129 |  |  | 1023 |  |  | 1136.5 |  |  | 1051.5 |  |  | 962 |  |  | 1108 |  |  | 986.5 |  |  | 1090 |  |  | 1085 |  |  | 1053.5 |  |  | 1057.5 |  |  | 1139 |  |  | 1148 |  |  | 1173 |  |  | 1030.5 |  |  | 1036 |  |  | 1058 |  |  | 1112 |  |  | 1065 |  |  | 1192 |  |  | 1148.5 |  |  | 1135 |  |  | 1046 |  |  | 964 |  |  | 1189.5 |  |  | 1189 |  |  | 1081.5 |  |  | 1096.5 |  |  | 1124 |  |  | 1090 |  |  | 1122.5 |  |  | 1048.5 |  |  | 1057.5 |  |  | 1113.5 |  |  | 1150.5 |  |  | 1195 |  |  | 1092 |  |  | 1182.5 |  |  | 1100.5 |  |  | 1106 |  |  | 1076 |  |  | 1099.5 |  |  | 1108 |  |  | 1112 |  |  | 1033 |  |  | 1152.5 |  |  | 1157 |  |  | 1057.5 |  |  | 1062 |  |  | 1104.5 |  |  | 1126.5 |  |  | 1193.5 |  |  | 1065 |  |  | 1054 |  |  | 1171.5 |  |  | 1089.5 |  |  | 1131 |  |  | 1086 |  |  | 1078.5 |  |  | 1112 |  |  | 1128.5 |  |  | 1103.5 |  |  | 1087 |  |  | 1104 |  |  | 1078.5 |  |  | 1173.5 |  |  | 1064 |  |  | 1064.5 |  |  | 1171.5 |  |  | 1045 |  |  | 1178 |  |  | 1198 |  |  | 1107.5 |  |  | 1157 |  |  | 1078 |  |  | 1103 |  |  | 1127 |  |  | 1176 |  |  | 1044 |  |  | 1160.5 |  |  | 1064.5 |  |  | 1069 |  |  | 1037 |  |  | 1103 |  |  | 1116.5 |  |  | 1091 |  |  | 1204 |  |  | 1043.5 |  |  | 1098.5 |  |  | 1096 |  |  | 1070.5 |  |  | 1108 |  |  | 1078 |  |  | 1116 |  |  | 1187.5 |  |  | 1225 |  |  | 1074.5 |  |  | 1060.5 |  |  | 1037 |  |  | 1124.5 |  |  | 1003.5 |  |  | 1007 |  |  | 1077 |  |  | 1240 |  |  | 1067.5 |  |  | 1049 |  |  | 1115.5 |  |  | 1115.5 |  |  | 1191 |  |  | 1041.5 |  |  | 1090 |  |  | 1160 |  |  | 1105 |  |  | 1039 |  |  | 1065 |  |  | 1174.5 |  |  | 1122 |  |  | 1135 |  |  | 1054 |  |  | 1199 |  |  | 1067.5 |  |  | 1194.5 |  |  | 1106 |  |  | 1068 |  |  | 1063 |  |  | 1068 |  |  | 1149 |  |  | 1155.5 |  |  | 1164 |  |  | 1113.5 |  |  | 1198 |  |  | 1042 |  |  | 1087 |  |  | 1081 |  |  | 1057.5 |  |  | 1072 |  |  | 1076.5 |  |  | 1026 |  |  | 1194 |  |  | 1162 |  |  | 1105.5 |  |  | 1115 |  |  | 1067 |  |  | 1032 |  |  | 1248 |  |  | 1185 |  |  | 1118.5 |  |  | 1145.5 |  |  | 1098 |  |  | 1070.5 |  |  | 1059 |  |  | 1055.5 |  |  | 1101.5 |  |  | 1075.5 |  |  | 1130.5 |  |  | 990 |  |  | 1211 |  |  | 1051 |  |  | 1042 |  |  | 1169 |  |  | 1034 |  |  | 1092.5 |  |  | 1054.5 |  |  | 1125.5 |  |  | 1203 |  |  | 1082.5 |  |  | 1144.5 |  |  | 1158.5 |  |  | 1086.5 |  |  | 1109 |  |  | 1119.5 |  |  | 1078.5 |  |  | 1182 |  |  | 1145.5 |  |  | 1126.5 |  |  | 1130.5 |  |  | 1166 |  |  | 1145.5 |  |  | 1161 |  |  | 1098 |  |  | 1138.5 |  |  | 1121.5 |  |  | 1156 |  |  | 1148 |  |  | 1070.5 |  |  | 1057.5 |  |  | 1178.5 |  |  | 1166 |  |  | 1107 |  |  | 1085 |  |  | 1076.5 |  |  | 1125.5 |  |  | 1111 |  |  | 1158.5 |  |  | 1045 |  |  | 1081 |  |  | 1124.5 |  |  | 1011.5 |  |  | 1078 |  |  | 1126.5 |  |  | 1075 |  |  | 1050.5 |  |  | 1214.5 |  |  | 1117 |  |  | 1025.5 |  |  | 1097 |  |  | 1163.5 |  |  | 1101 |  |  | 1161 |  |  | 1151 |  |  | 1108.5 |  |  | 1005.5 |  |  | 1141 |  |  | 1031 |  |  | 1046 |  |  | 1126.5 |  |  | 1057.5 |  |  | 1107 |  |  | 1105.5 |  |  | 1112 |  |  | 1103.5 |  |  | 1116.5 |  |  | 1039 |  |  | 1119 |  |  | 1092 |  |  | 1113.5 |  |  | 1083 |  |  | 1202.5 |  |  | 1167 |  |  | 1106.5 |  |  | 1202 |  |  | 979.5 |  |  | 1116 |  |  | 1072.5 |  |  | 1118.5 |  |  | 1108 |  |  | 1077 |  |  | 1116 |  |  | 1120 |  |  | 1141.5 |  |  | 1041 |  |  | 1063.5 |  |  | 1038 |  |  | 1154 |  |  | 1131 |  |  | 1178 |  |  | 1183 |  |  | 1091 |  |  | 1076 |  |  | 1120.5 |  |  | 1003 |  |  | 1207
41 |  | 1168.5 |  |  | 1190 |  |  | 1103.5 |  |  | 1144 |  |  | 1154.5 |  |  | 1133 |  |  | 1168 |  |  | 1195 |  |  | 1122.5 |  |  | 1134 |  |  | 1133 |  |  | 1231 |  |  | 1168 |  |  | 1216 |  |  | 1108.5 |  |  | 1195.5 |  |  | 1083 |  |  | 1202 |  |  | 1203 |  |  | 1026.5 |  |  | 1171 |  |  | 1187 |  |  | 1132 |  |  | 1183 |  |  | 1105.5 |  |  | 1236 |  |  | 1183 |  |  | 1109 |  |  | 1182 |  |  | 1147 |  |  | 1067 |  |  | 1132.5 |  |  | 1261.5 |  |  | 1121.5 |  |  | 1102 |  |  | 1108.5 |  |  | 1081.5 |  |  | 1185.5 |  |  | 1129 |  |  | 1149 |  |  | 1062.5 |  |  | 1076 |  |  | 1238.5 |  |  | 1165.5 |  |  | 1209.5 |  |  | 1176.5 |  |  | 1203.5 |  |  | 1126 |  |  | 1030 |  |  | 1079.5 |  |  | 1161 |  |  | 1094.5 |  |  | 1116.5 |  |  | 1195 |  |  | 1090 |  |  | 1110 |  |  | 1137 |  |  | 1216 |  |  | 1180 |  |  | 1110.5 |  |  | 1215.5 |  |  | 1205.5 |  |  | 1060 |  |  | 1198 |  |  | 1042 |  |  | 1118.5 |  |  | 1161 |  |  | 1201.5 |  |  | 1143.5 |  |  | 1226.5 |  |  | 1069 |  |  | 1129 |  |  | 1120 |  |  | 1126.5 |  |  | 1175.5 |  |  | 1097.5 |  |  | 1171.5 |  |  | 1149.5 |  |  | 1191.5 |  |  | 1173.5 |  |  | 1192.5 |  |  | 1115 |  |  | 1144 |  |  | 1141 |  |  | 1191.5 |  |  | 1157 |  |  | 1071.5 |  |  | 1088 |  |  | 1139 |  |  | 1176.5 |  |  | 1169.5 |  |  | 1139 |  |  | 1344 |  |  | 1110.5 |  |  | 1158 |  |  | 1080.5 |  |  | 1173.5 |  |  | 1171.5 |  |  | 1142.5 |  |  | 1067.5 |  |  | 1201 |  |  | 1101 |  |  | 1082 |  |  | 1205.5 |  |  | 1099.5 |  |  | 1126.5 |  |  | 1136.5 |  |  | 1165 |  |  | 1149 |  |  | 1126.5 |  |  | 1074 |  |  | 1195.5 |  |  | 1165 |  |  | 1161 |  |  | 1070.5 |  |  | 1176 |  |  | 1124 |  |  | 1146 |  |  | 1117 |  |  | 1182.5 |  |  | 1153.5 |  |  | 1076.5 |  |  | 1241 |  |  | 1069 |  |  | 1063 |  |  | 1110 |  |  | 1156.5 |  |  | 1114 |  |  | 1165.5 |  |  | 1175 |  |  | 1088 |  |  | 1179.5 |  |  | 1057.5 |  |  | 1019 |  |  | 1100.5 |  |  | 1099 |  |  | 1172 |  |  | 1199 |  |  | 1146 |  |  | 1120 |  |  | 1091 |  |  | 1057 |  |  | 1183 |  |  | 1077 |  |  | 1105.5 |  |  | 1079 |  |  | 1065 |  |  | 1113 |  |  | 1139 |  |  | 1041 |  |  | 1106 |  |  | 1165 |  |  | 1115.5 |  |  | 1174 |  |  | 1176.5 |  |  | 1182 |  |  | 1126 |  |  | 1199.5 |  |  | 1124 |  |  | 1265.5 |  |  | 1156 |  |  | 1060 |  |  | 1180.5 |  |  | 1101 |  |  | 1135.5 |  |  | 1076 |  |  | 1148 |  |  | 1124.5 |  |  | 1132.5 |  |  | 1156 |  |  | 1074.5 |  |  | 1069.5 |  |  | 1113 |  |  | 1170 |  |  | 1289.5 |  |  | 1119.5 |  |  | 1117.5 |  |  | 1137 |  |  | 1229 |  |  | 1101 |  |  | 1218 |  |  | 1198 |  |  | 1192.5 |  |  | 1105 |  |  | 1081.5 |  |  | 1175.5 |  |  | 1205 |  |  | 1186 |  |  | 1214.5 |  |  | 1042.5 |  |  | 1104 |  |  | 1168.5 |  |  | 1106.5 |  |  | 1141 |  |  | 1076 |  |  | 1129 |  |  | 1086.5 |  |  | 1205 |  |  | 1132.5 |  |  | 1100.5 |  |  | 1070 |  |  | 1154.5 |  |  | 1062 |  |  | 1183 |  |  | 1167 |  |  | 1160 |  |  | 1111 |  |  | 1157 |  |  | 1249 |  |  | 1199 |  |  | 1241 |  |  | 1093 |  |  | 1129.5 |  |  | 1221.5 |  |  | 1074 |  |  | 1048 |  |  | 1201 |  |  | 1142.5 |  |  | 1176.5 |  |  | 1226.5 |  |  | 1095 |  |  | 1194 |  |  | 1223.5 |  |  | 1108.5 |  |  | 1026.5 |  |  | 1218 |  |  | 1228 |  |  | 1141 |  |  | 1092 |  |  | 1103 |  |  | 1124.5 |  |  | 1067.5 |  |  | 1182 |  |  | 1171 |  |  | 1130 |  |  | 1190 |  |  | 1067 |  |  | 1128.5 |  |  | 1131 |  |  | 1242 |  |  | 1136 |  |  | 1126 |  |  | 1041.5 |  |  | 1267 |  |  | 1187 |  |  | 1123 |  |  | 1206 |  |  | 1189.5 |  |  | 1199 |  |  | 1079 |  |  | 1053 |  |  | 1209.5 |  |  | 1163.5 |  |  | 1166.5 |  |  | 1214 |  |  | 1121 |  |  | 1114 |  |  | 1192 |  |  | 1174 |  |  | 1107.5 |  |  | 1226 |  |  | 1124.5 |  |  | 1176.5 |  |  | 1172.5 |  |  | 1113 |  |  | 1164.5 |  |  | 1091 |  |  | 1082 |  |  | 1146.5 |  |  | 1150.5 |  |  | 1211 |  |  | 1256.5 |  |  | 1179.5 |  |  | 1137 |  |  | 1200 |  |  | 1148.5 |  |  | 1091.5 |  |  | 1142 |  |  | 1120.5 |  |  | 1173 |  |  | 1067 |  |  | 1146.5 |  |  | 1162 |  |  | 1085 |  |  | 1155.5 |  |  | 1136 |  |  | 1178.5 |  |  | 1129 |  |  | 1237 |  |  | 1137 |  |  | 1090 |  |  | 1224.5 |  |  | 1254 |  |  | 1179.5 |  |  | 1116.5 |  |  | 1149.5 |  |  | 1252 |  |  | 1225.5 |  |  | 1234 |  |  | 1193 |  |  | 1046.5 |  |  | 1130.5 |  |  | 1164 |  |  | 1148.5 |  |  | 1165 |  |  | 1125 |  |  | 1240.5 |  |  | 1138 |  |  | 1120.5 |  |  | 1137.5 |  |  | 1174.5 |  |  | 1167 |  |  | 1086 |  |  | 1180 |  |  | 1055.5 |  |  | 1087 |  |  | 1195.5 |  |  | 1150 |  |  | 1162 |  |  | 1060 |  |  | 1177 |  |  | 1200 |  |  | 1140 |  |  | 1095 |  |  | 1248 |  |  | 1155 |  |  | 1147.5 |  |  | 1123 |  |  | 1084 |  |  | 1293.5 |  |  | 1046.5 |  |  | 1174.5 |  |  | 1208.5 |  |  | 1131 |  |  | 1247 |  |  | 1050.5 |  |  | 1171.5 |  |  | 1219.5 |  |  | 1199 |  |  | 1141 |  |  | 1144 |  |  | 1124 |  |  | 1079 |  |  | 1154 |  |  | 1161 |  |  | 1126.5 |  |  | 1111.5 |  |  | 1161 |  |  | 1164.5 |  |  | 1183.5 |  |  | 1084 |  |  | 1158 |  |  | 1131 |  |  | 1155 |  |  | 1129.5 |  |  | 1081.5 |  |  | 1114.5 |  |  | 1124 |  |  | 1124.5 |  |  | 1135 |  |  | 1106 |  |  | 1127 |  |  | 1065.5 |  |  | 1181 |  |  | 1031 |  |  | 1142.5 |  |  | 1116 |  |  | 1159.5 |  |  | 1216 |  |  | 1151.5 |  |  | 1067 |  |  | 1098.5 |  |  | 1180.5 |  |  | 1204 |  |  | 1108 |  |  | 1039 |  |  | 1123 |  |  | 1113.5 |  |  | 1101 |  |  | 1170 |  |  | 1093.5 |  |  | 1183.5 |  |  | 1059.5 |  |  | 1151 |  |  | 1131.5 |  |  | 1125.5 |  |  | 1151.5 |  |  | 1231 |  |  | 1125 |  |  | 1105.5 |  |  | 1177 |  |  | 1203 |  |  | 1102.5 |  |  | 1128 |  |  | 1183 |  |  | 1139 |  |  | 1079 |  |  | 1080.5 |  |  | 1212.5 |  |  | 1062 |  |  | 1191 |  |  | 1175 |  |  | 1110 |  |  | 1110 |  |  | 1113.5 |  |  | 1182.5 |  |  | 1136 |  |  | 1292 |  |  | 1200 |  |  | 1053.5 |  |  | 1189.5 |  |  | 1123 |  |  | 1101 |  |  | 1096 |  |  | 1140.5 |  |  | 1256.5 |  |  | 1164 |  |  | 1105 |  |  | 1212 |  |  | 1146 |  |  | 1089 |  |  | 1195 |  |  | 1107 |  |  | 1214.5 |  |  | 1036 |  |  | 1263 |  |  | 1116 |  |  | 1200.5 |  |  | 1241 |  |  | 1019 |  |  | 1022 |  |  | 1195 |  |  | 1169 |  |  | 1141 |  |  | 1115 |  |  | 1117.5 |  |  | 1127.5 |  |  | 1117.5 |  |  | 1150 |  |  | 1154 |  |  | 1211.5 |  |  | 1090 |  |  | 1131.5 |  |  | 1110.5 |  |  | 1067 |  |  | 1084 |  |  | 1234.5 |  |  | 1183 |  |  | 1149 |  |  | 1153 |  |  | 1120 |  |  | 1097 |  |  | 1120 |  |  | 1135 |  |  | 1235.5 |  |  | 1111 |  |  | 1091 |  |  | 1188 |  |  | 1116 |  |  | 1203 |  |  | 1057 |  |  | 1262 |  |  | 1209 |  |  | 1151 |  |  | 1279.5 |  |  | 1137.5 |  |  | 1120.5 |  |  | 1130.5 |  |  | 1190 |  |  | 1088 |  |  | 1214.5 |  |  | 1136 |  |  | 1158 |  |  | 1152.5 |  |  | 1220.5 |  |  | 1186 |  |  | 1141.5 |  |  | 1129.5 |  |  | 1052 |  |  | 1167 |  |  | 1081 |  |  | 1157 |  |  | 1196.5 |  |  | 1077 |  |  | 1163.5 |  |  | 1079.5 |  |  | 1086 |  |  | 1123 |  |  | 1121.5 |  |  | 1137 |  |  | 1216.5 |  |  | 1098 |  |  | 1153.5 |  |  | 1056.5 |  |  | 1116.5 |  |  | 1163.5 |  |  | 1159.5 |  |  | 1147 |  |  | 1144 |  |  | 1264.5 |  |  | 1185 |  |  | 1090 |  |  | 1118 |  |  | 1180 |  |  | 1187.5 |  |  | 1061 |  |  | 1104 |  |  | 1195 |  |  | 1140.5 |  |  | 1142 |  |  | 1105 |  |  | 1177 |  |  | 1258.5 |  |  | 1156 |  |  | 1000 |  |  | 1094 |  |  | 1188 |  |  | 1293.5 |  |  | 1149 |  |  | 1097.5 |  |  | 1142 |  |  | 1181 |  |  | 1289.5 |  |  | 1187 |  |  | 1096 |  |  | 1027.5 |  |  | 1143 |  |  | 1091 |  |  | 1170 |  |  | 1180.5 |  |  | 1085.5 |  |  | 1138 |  |  | 1072 |  |  | 1156.5 |  |  | 1168.5 |  |  | 1106 |  |  | 1195 |  |  | 1194.5 |  |  | 1162.5 |  |  | 1070.5 |  |  | 1114.5 |  |  | 1179.5 |  |  | 1232 |  |  | 1169.5 |  |  | 1171 |  |  | 1124 |  |  | 1176 |  |  | 1160 |  |  | 1200.5 |  |  | 1098 |  |  | 1064 |  |  | 1135.5 |  |  | 1111.5 |  |  | 1055 |  |  | 1122.5 |  |  | 1153.5 |  |  | 1190 |  |  | 1127 |  |  | 1157 |  |  | 1121.5 |  |  | 1157 |  |  | 1120.5 |  |  | 1138 |  |  | 1191 |  |  | 1226.5 |  |  | 1135 |  |  | 1276 |  |  | 1100 |  |  | 1152 |  |  | 1182 |  |  | 1143 |  |  | 1113 |  |  | 1109 |  |  | 1063.5 |  |  | 1126.5 |  |  | 1188 |  |  | 1161.5 |  |  | 1007.5 |  |  | 1102 |  |  | 1019 |  |  | 1164 |  |  | 1196.5 |  |  | 1120.5 |  |  | 1092 |  |  | 1229 |  |  | 1086 |  |  | 1043 |  |  | 1145 |  |  | 1115 |  |  | 1261 |  |  | 1128.5 |  |  | 1136 |  |  | 1198 |  |  | 1248 |  |  | 1097 |  |  | 1065 |  |  | 1156.5 |  |  | 1271.5 |  |  | 1043.5 |  |  | 1081 |  |  | 1040 |  |  | 1069.5 |  |  | 1209.5 |  |  | 1172.5 |  |  | 1129 |  |  | 1210.5 |  |  | 1130.5 |  |  | 1121 |  |  | 1083.5 |  |  | 1181.5 |  |  | 1131 |  |  | 1059 |  |  | 1155 |  |  | 1148 |  |  | 1127 |  |  | 1055 |  |  | 1176 |  |  | 1232 |  |  | 1128 |  |  | 1078 |  |  | 1159.5 |  |  | 1132 |  |  | 1200 |  |  | 1062 |  |  | 1113.5 |  |  | 1178 |  |  | 1180.5 |  |  | 1197 |  |  | 1165 |  |  | 1140 |  |  | 1128 |  |  | 1179.5 |  |  | 1136 |  |  | 1078 |  |  | 1243.5 |  |  | 1166 |  |  | 1095 |  |  | 1071.5 |  |  | 1124.5 |  |  | 1221 |  |  | 1097.5 |  |  | 1187 |  |  | 1148.5 |  |  | 1188 |  |  | 1128 |  |  | 1152.5 |  |  | 1247.5 |  |  | 1185 |  |  | 1145 |  |  | 1176 |  |  | 1196 |  |  | 1032 |  |  | 1199 |  |  | 1057 |  |  | 1104 |  |  | 1239.5 |  |  | 1089 |  |  | 1208.5 |  |  | 1162 |  |  | 1148.5 |  |  | 1130.5 |  |  | 1121 |  |  | 1228 |  |  | 1173.5 |  |  | 1182 |  |  | 1136 |  |  | 1180 |  |  | 1142.5 |  |  | 1185 |  |  | 1061.5 |  |  | 1114 |  |  | 1142 |  |  | 1160 |  |  | 1195 |  |  | 1200.5 |  |  | 1086 |  |  | 1162 |  |  | 1167 |  |  | 1086.5 |  |  | 1214 |  |  | 1161 |  |  | 1185 |  |  | 1086 |  |  | 1156.5 |  |  | 1100.5 |  |  | 1164 |  |  | 1195 |  |  | 1174 |  |  | 1169.5 |  |  | 1126 |  |  | 1114 |  |  | 1066 |  |  | 1226.5 |  |  | 1137.5 |  |  | 1202.5 |  |  | 1118 |  |  | 1210 |  |  | 1108 |  |  | 1144.5 |  |  | 1146 |  |  | 1133.5 |  |  | 1026 |  |  | 1073 |  |  | 1168 |  |  | 1113.5 |  |  | 1178.5 |  |  | 1135 |  |  | 1073 |  |  | 1185.5 |  |  | 1146 |  |  | 1193 |  |  | 1171.5 |  |  | 1140 |  |  | 1097 |  |  | 1200.5 |  |  | 1072 |  |  | 1207 |  |  | 1159.5 |  |  | 1166 |  |  | 1153.5 |  |  | 1189 |  |  | 1061.5 |  |  | 1177.5 |  |  | 1056 |  |  | 1224 |  |  | 1180.5 |  |  | 1165.5 |  |  | 1229 |  |  | 1134 |  |  | 1181 |  |  | 1137.5 |  |  | 1161 |  |  | 1102 |  |  | 1182 |  |  | 1211.5 |  |  | 1143.5 |  |  | 1139 |  |  | 1231 |  |  | 1103 |  |  | 1145 |  |  | 1211 |  |  | 1108 |  |  | 1153 |  |  | 1085.5 |  |  | 1129.5 |  |  | 1092.5 |  |  | 1154 |  |  | 1100.5 |  |  | 1158 |  |  | 1038 |  |  | 1157.5 |  |  | 1090.5 |  |  | 977 |  |  | 1147 |  |  | 1012.5 |  |  | 1129 |  |  | 1106 |  |  | 1092.5 |  |  | 1072.5 |  |  | 1178 |  |  | 1163 |  |  | 1212 |  |  | 1051.5 |  |  | 1075 |  |  | 1073 |  |  | 1127 |  |  | 1091 |  |  | 1218 |  |  | 1172.5 |  |  | 1164 |  |  | 1085 |  |  | 1011 |  |  | 1236.5 |  |  | 1204 |  |  | 1128.5 |  |  | 1111.5 |  |  | 1163 |  |  | 1116 |  |  | 1148.5 |  |  | 1074.5 |  |  | 1086.5 |  |  | 1142.5 |  |  | 1171.5 |  |  | 1210 |  |  | 1131 |  |  | 1197.5 |  |  | 1126.5 |  |  | 1132 |  |  | 1123 |  |  | 1120.5 |  |  | 1132 |  |  | 1159 |  |  | 1072 |  |  | 1199.5 |  |  | 1196 |  |  | 1072.5 |  |  | 1101 |  |  | 1143.5 |  |  | 1147.5 |  |  | 1217.5 |  |  | 1104 |  |  | 1093 |  |  | 1200.5 |  |  | 1118.5 |  |  | 1152 |  |  | 1133 |  |  | 1102.5 |  |  | 1141 |  |  | 1152.5 |  |  | 1124.5 |  |  | 1134 |  |  | 1125 |  |  | 1125.5 |  |  | 1197.5 |  |  | 1111 |  |  | 1085.5 |  |  | 1195.5 |  |  | 1084 |  |  | 1225 |  |  | 1237 |  |  | 1122.5 |  |  | 1178 |  |  | 1125 |  |  | 1118 |  |  | 1142 |  |  | 1200 |  |  | 1073 |  |  | 1184.5 |  |  | 1085.5 |  |  | 1108 |  |  | 1076 |  |  | 1132 |  |  | 1145.5 |  |  | 1115 |  |  | 1225 |  |  | 1064.5 |  |  | 1122.5 |  |  | 1135 |  |  | 1117.5 |  |  | 1137 |  |  | 1117 |  |  | 1145 |  |  | 1226.5 |  |  | 1264 |  |  | 1100.5 |  |  | 1099.5 |  |  | 1084 |  |  | 1153.5 |  |  | 1024.5 |  |  | 1028 |  |  | 1103 |  |  | 1287 |  |  | 1106.5 |  |  | 1078 |  |  | 1139.5 |  |  | 1144.5 |  |  | 1215 |  |  | 1067.5 |  |  | 1105 |  |  | 1184 |  |  | 1129 |  |  | 1054 |  |  | 1091 |  |  | 1195.5 |  |  | 1143 |  |  | 1164 |  |  | 1069 |  |  | 1214 |  |  | 1096.5 |  |  | 1209.5 |  |  | 1135 |  |  | 1115 |  |  | 1084 |  |  | 1092 |  |  | 1173 |  |  | 1176.5 |  |  | 1190 |  |  | 1134.5 |  |  | 1224 |  |  | 1081 |  |  | 1126 |  |  | 1120 |  |  | 1081.5 |  |  | 1087 |  |  | 1115.5 |  |  | 1065 |  |  | 1220 |  |  | 1201 |  |  | 1131.5 |  |  | 1130 |  |  | 1096 |  |  | 1071 |  |  | 1287 |  |  | 1214 |  |  | 1139.5 |  |  | 1166.5 |  |  | 1127 |  |  | 1117.5 |  |  | 1080 |  |  | 1081.5 |  |  | 1140.5 |  |  | 1099.5 |  |  | 1177.5 |  |  | 1016 |  |  | 1232 |  |  | 1066 |  |  | 1081 |  |  | 1198 |  |  | 1081 |  |  | 1131.5 |  |  | 1093.5 |  |  | 1172.5 |  |  | 1232 |  |  | 1121.5 |  |  | 1183.5 |  |  | 1187.5 |  |  | 1115.5 |  |  | 1124 |  |  | 1140.5 |  |  | 1102.5 |  |  | 1203 |  |  | 1171.5 |  |  | 1165.5 |  |  | 1154.5 |  |  | 1187 |  |  | 1169.5 |  |  | 1185 |  |  | 1127 |  |  | 1185.5 |  |  | 1150.5 |  |  | 1177 |  |  | 1195 |  |  | 1091.5 |  |  | 1072.5 |  |  | 1204.5 |  |  | 1187 |  |  | 1128 |  |  | 1109 |  |  | 1105.5 |  |  | 1149.5 |  |  | 1150 |  |  | 1182.5 |  |  | 1069 |  |  | 1128 |  |  | 1145.5 |  |  | 1037.5 |  |  | 1125 |  |  | 1147.5 |  |  | 1104 |  |  | 1079.5 |  |  | 1240.5 |  |  | 1156 |  |  | 1046.5 |  |  | 1121 |  |  | 1189.5 |  |  | 1125 |  |  | 1187 |  |  | 1190 |  |  | 1147.5 |  |  | 1044.5 |  |  | 1156 |  |  | 1070 |  |  | 1070 |  |  | 1147.5 |  |  | 1072.5 |  |  | 1146 |  |  | 1129.5 |  |  | 1141 |  |  | 1127.5 |  |  | 1155.5 |  |  | 1063 |  |  | 1148 |  |  | 1131 |  |  | 1142.5 |  |  | 1122 |  |  | 1226.5 |  |  | 1193 |  |  | 1121.5 |  |  | 1228 |  |  | 1026.5 |  |  | 1137 |  |  | 1111.5 |  |  | 1139.5 |  |  | 1147 |  |  | 1106 |  |  | 1142 |  |  | 1159 |  |  | 1156.5 |  |  | 1070 |  |  | 1102.5 |  |  | 1059 |  |  | 1193 |  |  | 1155 |  |  | 1202 |  |  | 1198 |  |  | 1120 |  |  | 1102 |  |  | 1167.5 |  |  | 1024 |  |  | 1231
42 |  | 1207.5 |  |  | 1214 |  |  | 1142.5 |  |  | 1183 |  |  | 1169.5 |  |  | 1148 |  |  | 1207 |  |  | 1234 |  |  | 1161.5 |  |  | 1173 |  |  | 1157 |  |  | 1270 |  |  | 1183 |  |  | 1255 |  |  | 1155.5 |  |  | 1210.5 |  |  | 1122 |  |  | 1226 |  |  | 1250 |  |  | 1073.5 |  |  | 1210 |  |  | 1208 |  |  | 1158 |  |  | 1212 |  |  | 1134.5 |  |  | 1265 |  |  | 1222 |  |  | 1148 |  |  | 1203 |  |  | 1171 |  |  | 1088 |  |  | 1171.5 |  |  | 1287.5 |  |  | 1136.5 |  |  | 1126 |  |  | 1132.5 |  |  | 1096.5 |  |  | 1214.5 |  |  | 1168 |  |  | 1178 |  |  | 1083.5 |  |  | 1102 |  |  | 1259.5 |  |  | 1191.5 |  |  | 1224.5 |  |  | 1205.5 |  |  | 1250.5 |  |  | 1150 |  |  | 1045 |  |  | 1094.5 |  |  | 1200 |  |  | 1118.5 |  |  | 1145.5 |  |  | 1219 |  |  | 1129 |  |  | 1139 |  |  | 1158 |  |  | 1255 |  |  | 1209 |  |  | 1157.5 |  |  | 1239.5 |  |  | 1220.5 |  |  | 1081 |  |  | 1224 |  |  | 1081 |  |  | 1147.5 |  |  | 1187 |  |  | 1222.5 |  |  | 1169.5 |  |  | 1265.5 |  |  | 1108 |  |  | 1168 |  |  | 1149 |  |  | 1150.5 |  |  | 1214.5 |  |  | 1144.5 |  |  | 1210.5 |  |  | 1188.5 |  |  | 1220.5 |  |  | 1188.5 |  |  | 1221.5 |  |  | 1154 |  |  | 1165 |  |  | 1165 |  |  | 1212.5 |  |  | 1186 |  |  | 1110.5 |  |  | 1127 |  |  | 1178 |  |  | 1191.5 |  |  | 1195.5 |  |  | 1168 |  |  | 1383 |  |  | 1149.5 |  |  | 1197 |  |  | 1106.5 |  |  | 1220.5 |  |  | 1218.5 |  |  | 1171.5 |  |  | 1088.5 |  |  | 1216 |  |  | 1122 |  |  | 1106 |  |  | 1234.5 |  |  | 1125.5 |  |  | 1165.5 |  |  | 1160.5 |  |  | 1204 |  |  | 1164 |  |  | 1173.5 |  |  | 1089 |  |  | 1234.5 |  |  | 1191 |  |  | 1182 |  |  | 1117.5 |  |  | 1191 |  |  | 1139 |  |  | 1161 |  |  | 1146 |  |  | 1229.5 |  |  | 1182.5 |  |  | 1091.5 |  |  | 1280 |  |  | 1116 |  |  | 1092 |  |  | 1131 |  |  | 1171.5 |  |  | 1153 |  |  | 1212.5 |  |  | 1196 |  |  | 1127 |  |  | 1218.5 |  |  | 1072.5 |  |  | 1048 |  |  | 1139.5 |  |  | 1146 |  |  | 1201 |  |  | 1214 |  |  | 1167 |  |  | 1159 |  |  | 1120 |  |  | 1081 |  |  | 1207 |  |  | 1116 |  |  | 1126.5 |  |  | 1094 |  |  | 1094 |  |  | 1152 |  |  | 1165 |  |  | 1088 |  |  | 1153 |  |  | 1180 |  |  | 1141.5 |  |  | 1195 |  |  | 1215.5 |  |  | 1229 |  |  | 1155 |  |  | 1246.5 |  |  | 1153 |  |  | 1304.5 |  |  | 1180 |  |  | 1089 |  |  | 1209.5 |  |  | 1122 |  |  | 1161.5 |  |  | 1091 |  |  | 1174 |  |  | 1145.5 |  |  | 1171.5 |  |  | 1195 |  |  | 1100.5 |  |  | 1116.5 |  |  | 1139 |  |  | 1196 |  |  | 1315.5 |  |  | 1140.5 |  |  | 1141.5 |  |  | 1161 |  |  | 1250 |  |  | 1122 |  |  | 1233 |  |  | 1237 |  |  | 1213.5 |  |  | 1131 |  |  | 1105.5 |  |  | 1201.5 |  |  | 1231 |  |  | 1215 |  |  | 1243.5 |  |  | 1081.5 |  |  | 1143 |  |  | 1194.5 |  |  | 1135.5 |  |  | 1170 |  |  | 1100 |  |  | 1153 |  |  | 1125.5 |  |  | 1244 |  |  | 1147.5 |  |  | 1147.5 |  |  | 1117 |  |  | 1169.5 |  |  | 1091 |  |  | 1198 |  |  | 1188 |  |  | 1199 |  |  | 1126 |  |  | 1204 |  |  | 1278 |  |  | 1228 |  |  | 1262 |  |  | 1140 |  |  | 1155.5 |  |  | 1260.5 |  |  | 1100 |  |  | 1095 |  |  | 1240 |  |  | 1189.5 |  |  | 1223.5 |  |  | 1252.5 |  |  | 1124 |  |  | 1223 |  |  | 1252.5 |  |  | 1132.5 |  |  | 1041.5 |  |  | 1247 |  |  | 1275 |  |  | 1170 |  |  | 1131 |  |  | 1142 |  |  | 1163.5 |  |  | 1106.5 |  |  | 1221 |  |  | 1218 |  |  | 1159 |  |  | 1216 |  |  | 1106 |  |  | 1149.5 |  |  | 1146 |  |  | 1266 |  |  | 1157 |  |  | 1152 |  |  | 1080.5 |  |  | 1306 |  |  | 1226 |  |  | 1144 |  |  | 1232 |  |  | 1218.5 |  |  | 1238 |  |  | 1118 |  |  | 1074 |  |  | 1230.5 |  |  | 1202.5 |  |  | 1205.5 |  |  | 1253 |  |  | 1160 |  |  | 1153 |  |  | 1221 |  |  | 1221 |  |  | 1133.5 |  |  | 1250 |  |  | 1150.5 |  |  | 1202.5 |  |  | 1193.5 |  |  | 1152 |  |  | 1211.5 |  |  | 1112 |  |  | 1106 |  |  | 1175.5 |  |  | 1197.5 |  |  | 1250 |  |  | 1295.5 |  |  | 1226.5 |  |  | 1163 |  |  | 1224 |  |  | 1174.5 |  |  | 1130.5 |  |  | 1166 |  |  | 1135.5 |  |  | 1188 |  |  | 1093 |  |  | 1175.5 |  |  | 1183 |  |  | 1124 |  |  | 1194.5 |  |  | 1151 |  |  | 1207.5 |  |  | 1144 |  |  | 1263 |  |  | 1176 |  |  | 1111 |  |  | 1271.5 |  |  | 1293 |  |  | 1218.5 |  |  | 1155.5 |  |  | 1175.5 |  |  | 1278 |  |  | 1264.5 |  |  | 1273 |  |  | 1232 |  |  | 1075.5 |  |  | 1151.5 |  |  | 1190 |  |  | 1174.5 |  |  | 1212 |  |  | 1151 |  |  | 1266.5 |  |  | 1185 |  |  | 1144.5 |  |  | 1184.5 |  |  | 1203.5 |  |  | 1206 |  |  | 1112 |  |  | 1195 |  |  | 1094.5 |  |  | 1111 |  |  | 1242.5 |  |  | 1197 |  |  | 1188 |  |  | 1099 |  |  | 1201 |  |  | 1226 |  |  | 1166 |  |  | 1142 |  |  | 1277 |  |  | 1202 |  |  | 1162.5 |  |  | 1152 |  |  | 1123 |  |  | 1314.5 |  |  | 1061.5 |  |  | 1221.5 |  |  | 1255.5 |  |  | 1157 |  |  | 1294 |  |  | 1074.5 |  |  | 1186.5 |  |  | 1248.5 |  |  | 1228 |  |  | 1170 |  |  | 1159 |  |  | 1148 |  |  | 1108 |  |  | 1175 |  |  | 1208 |  |  | 1165.5 |  |  | 1140.5 |  |  | 1176 |  |  | 1188.5 |  |  | 1222.5 |  |  | 1099 |  |  | 1182 |  |  | 1170 |  |  | 1170 |  |  | 1144.5 |  |  | 1107.5 |  |  | 1161.5 |  |  | 1163 |  |  | 1150.5 |  |  | 1174 |  |  | 1132 |  |  | 1148 |  |  | 1086.5 |  |  | 1220 |  |  | 1057 |  |  | 1171.5 |  |  | 1155 |  |  | 1174.5 |  |  | 1263 |  |  | 1177.5 |  |  | 1091 |  |  | 1145.5 |  |  | 1209.5 |  |  | 1230 |  |  | 1137 |  |  | 1078 |  |  | 1152 |  |  | 1128.5 |  |  | 1127 |  |  | 1209 |  |  | 1132.5 |  |  | 1207.5 |  |  | 1098.5 |  |  | 1177 |  |  | 1157.5 |  |  | 1149.5 |  |  | 1190.5 |  |  | 1252 |  |  | 1172 |  |  | 1126.5 |  |  | 1216 |  |  | 1242 |  |  | 1149.5 |  |  | 1143 |  |  | 1230 |  |  | 1163 |  |  | 1103 |  |  | 1119.5 |  |  | 1251.5 |  |  | 1088 |  |  | 1217 |  |  | 1196 |  |  | 1134 |  |  | 1136 |  |  | 1142.5 |  |  | 1197.5 |  |  | 1175 |  |  | 1313 |  |  | 1239 |  |  | 1074.5 |  |  | 1215.5 |  |  | 1170 |  |  | 1116 |  |  | 1111 |  |  | 1187.5 |  |  | 1280.5 |  |  | 1188 |  |  | 1152 |  |  | 1233 |  |  | 1193 |  |  | 1136 |  |  | 1234 |  |  | 1154 |  |  | 1240.5 |  |  | 1075 |  |  | 1302 |  |  | 1140 |  |  | 1215.5 |  |  | 1262 |  |  | 1034 |  |  | 1043 |  |  | 1216 |  |  | 1184 |  |  | 1156 |  |  | 1154 |  |  | 1156.5 |  |  | 1166.5 |  |  | 1143.5 |  |  | 1189 |  |  | 1175 |  |  | 1226.5 |  |  | 1114 |  |  | 1155.5 |  |  | 1149.5 |  |  | 1106 |  |  | 1123 |  |  | 1263.5 |  |  | 1198 |  |  | 1170 |  |  | 1192 |  |  | 1144 |  |  | 1121 |  |  | 1167 |  |  | 1164 |  |  | 1274.5 |  |  | 1158 |  |  | 1130 |  |  | 1227 |  |  | 1155 |  |  | 1229 |  |  | 1078 |  |  | 1309 |  |  | 1256 |  |  | 1190 |  |  | 1303.5 |  |  | 1166.5 |  |  | 1141.5 |  |  | 1169.5 |  |  | 1214 |  |  | 1127 |  |  | 1238.5 |  |  | 1162 |  |  | 1184 |  |  | 1173.5 |  |  | 1244.5 |  |  | 1225 |  |  | 1165.5 |  |  | 1144.5 |  |  | 1073 |  |  | 1214 |  |  | 1120 |  |  | 1196 |  |  | 1225.5 |  |  | 1116 |  |  | 1192.5 |  |  | 1108.5 |  |  | 1112 |  |  | 1162 |  |  | 1168.5 |  |  | 1161 |  |  | 1242.5 |  |  | 1124 |  |  | 1192.5 |  |  | 1103.5 |  |  | 1137.5 |  |  | 1189.5 |  |  | 1198.5 |  |  | 1168 |  |  | 1173 |  |  | 1303.5 |  |  | 1206 |  |  | 1119 |  |  | 1157 |  |  | 1219 |  |  | 1234.5 |  |  | 1082 |  |  | 1128 |  |  | 1234 |  |  | 1187.5 |  |  | 1181 |  |  | 1134 |  |  | 1192 |  |  | 1297.5 |  |  | 1180 |  |  | 1039 |  |  | 1133 |  |  | 1227 |  |  | 1332.5 |  |  | 1188 |  |  | 1123.5 |  |  | 1181 |  |  | 1220 |  |  | 1315.5 |  |  | 1226 |  |  | 1143 |  |  | 1066.5 |  |  | 1182 |  |  | 1130 |  |  | 1217 |  |  | 1206.5 |  |  | 1109.5 |  |  | 1162 |  |  | 1096 |  |  | 1180.5 |  |  | 1207.5 |  |  | 1121 |  |  | 1234 |  |  | 1220.5 |  |  | 1201.5 |  |  | 1096.5 |  |  | 1161.5 |  |  | 1203.5 |  |  | 1271 |  |  | 1184.5 |  |  | 1195 |  |  | 1163 |  |  | 1223 |  |  | 1189 |  |  | 1247.5 |  |  | 1145 |  |  | 1090 |  |  | 1174.5 |  |  | 1150.5 |  |  | 1102 |  |  | 1161.5 |  |  | 1177.5 |  |  | 1214 |  |  | 1156 |  |  | 1181 |  |  | 1142.5 |  |  | 1181 |  |  | 1149.5 |  |  | 1185 |  |  | 1238 |  |  | 1265.5 |  |  | 1164 |  |  | 1305 |  |  | 1124 |  |  | 1176 |  |  | 1221 |  |  | 1167 |  |  | 1137 |  |  | 1124 |  |  | 1102.5 |  |  | 1173.5 |  |  | 1209 |  |  | 1190.5 |  |  | 1031.5 |  |  | 1149 |  |  | 1043 |  |  | 1211 |  |  | 1225.5 |  |  | 1135.5 |  |  | 1131 |  |  | 1244 |  |  | 1110 |  |  | 1082 |  |  | 1171 |  |  | 1154 |  |  | 1308 |  |  | 1149.5 |  |  | 1165 |  |  | 1227 |  |  | 1263 |  |  | 1118 |  |  | 1104 |  |  | 1203.5 |  |  | 1310.5 |  |  | 1067.5 |  |  | 1110 |  |  | 1079 |  |  | 1084.5 |  |  | 1235.5 |  |  | 1219.5 |  |  | 1153 |  |  | 1231.5 |  |  | 1154.5 |  |  | 1145 |  |  | 1122.5 |  |  | 1210.5 |  |  | 1170 |  |  | 1074 |  |  | 1194 |  |  | 1177 |  |  | 1142 |  |  | 1076 |  |  | 1197 |  |  | 1258 |  |  | 1149 |  |  | 1099 |  |  | 1206.5 |  |  | 1179 |  |  | 1215 |  |  | 1101 |  |  | 1134.5 |  |  | 1217 |  |  | 1195.5 |  |  | 1223 |  |  | 1189 |  |  | 1161 |  |  | 1154 |  |  | 1218.5 |  |  | 1183 |  |  | 1107 |  |  | 1290.5 |  |  | 1187 |  |  | 1119 |  |  | 1086.5 |  |  | 1148.5 |  |  | 1245 |  |  | 1136.5 |  |  | 1202 |  |  | 1177.5 |  |  | 1227 |  |  | 1175 |  |  | 1181.5 |  |  | 1286.5 |  |  | 1200 |  |  | 1192 |  |  | 1205 |  |  | 1235 |  |  | 1056 |  |  | 1225 |  |  | 1072 |  |  | 1143 |  |  | 1278.5 |  |  | 1118 |  |  | 1247.5 |  |  | 1201 |  |  | 1172.5 |  |  | 1145.5 |  |  | 1142 |  |  | 1254 |  |  | 1188.5 |  |  | 1208 |  |  | 1162 |  |  | 1201 |  |  | 1157.5 |  |  | 1224 |  |  | 1082.5 |  |  | 1140 |  |  | 1157 |  |  | 1199 |  |  | 1216 |  |  | 1239.5 |  |  | 1110 |  |  | 1188 |  |  | 1193 |  |  | 1133.5 |  |  | 1261 |  |  | 1190 |  |  | 1224 |  |  | 1110 |  |  | 1195.5 |  |  | 1139.5 |  |  | 1203 |  |  | 1224 |  |  | 1221 |  |  | 1216.5 |  |  | 1165 |  |  | 1140 |  |  | 1090 |  |  | 1273.5 |  |  | 1176.5 |  |  | 1231.5 |  |  | 1165 |  |  | 1231 |  |  | 1134 |  |  | 1170.5 |  |  | 1185 |  |  | 1172.5 |  |  | 1055 |  |  | 1120 |  |  | 1189 |  |  | 1139.5 |  |  | 1217.5 |  |  | 1174 |  |  | 1102 |  |  | 1209.5 |  |  | 1161 |  |  | 1232 |  |  | 1210.5 |  |  | 1187 |  |  | 1126 |  |  | 1239.5 |  |  | 1098 |  |  | 1246 |  |  | 1185.5 |  |  | 1205 |  |  | 1177.5 |  |  | 1215 |  |  | 1076.5 |  |  | 1201.5 |  |  | 1103 |  |  | 1271 |  |  | 1195.5 |  |  | 1186.5 |  |  | 1255 |  |  | 1163 |  |  | 1220 |  |  | 1152.5 |  |  | 1176 |  |  | 1123 |  |  | 1211 |  |  | 1232.5 |  |  | 1190.5 |  |  | 1178 |  |  | 1260 |  |  | 1142 |  |  | 1192 |  |  | 1250 |  |  | 1129 |  |  | 1182 |  |  | 1124.5 |  |  | 1168.5 |  |  | 1131.5 |  |  | 1201 |  |  | 1129.5 |  |  | 1187 |  |  | 1067 |  |  | 1178.5 |  |  | 1111.5 |  |  | 1016 |  |  | 1173 |  |  | 1059.5 |  |  | 1150 |  |  | 1145 |  |  | 1116.5 |  |  | 1096.5 |  |  | 1204 |  |  | 1178 |  |  | 1251 |  |  | 1077.5 |  |  | 1104 |  |  | 1097 |  |  | 1156 |  |  | 1106 |  |  | 1239 |  |  | 1187.5 |  |  | 1211 |  |  | 1100 |  |  | 1058 |  |  | 1275.5 |  |  | 1225 |  |  | 1143.5 |  |  | 1126.5 |  |  | 1210 |  |  | 1137 |  |  | 1163.5 |  |  | 1098.5 |  |  | 1107.5 |  |  | 1181.5 |  |  | 1197.5 |  |  | 1225 |  |  | 1146 |  |  | 1236.5 |  |  | 1155.5 |  |  | 1179 |  |  | 1149 |  |  | 1159.5 |  |  | 1158 |  |  | 1198 |  |  | 1101 |  |  | 1228.5 |  |  | 1243 |  |  | 1098.5 |  |  | 1125 |  |  | 1182.5 |  |  | 1186.5 |  |  | 1264.5 |  |  | 1133 |  |  | 1140 |  |  | 1226.5 |  |  | 1157.5 |  |  | 1191 |  |  | 1180 |  |  | 1131.5 |  |  | 1162 |  |  | 1173.5 |  |  | 1171.5 |  |  | 1158 |  |  | 1154 |  |  | 1151.5 |  |  | 1244.5 |  |  | 1137 |  |  | 1132.5 |  |  | 1242.5 |  |  | 1099 |  |  | 1264 |  |  | 1276 |  |  | 1137.5 |  |  | 1193 |  |  | 1154 |  |  | 1157 |  |  | 1163 |  |  | 1229 |  |  | 1112 |  |  | 1223.5 |  |  | 1106.5 |  |  | 1134 |  |  | 1102 |  |  | 1153 |  |  | 1184.5 |  |  | 1162 |  |  | 1264 |  |  | 1103.5 |  |  | 1169.5 |  |  | 1156 |  |  | 1138.5 |  |  | 1176 |  |  | 1141 |  |  | 1166 |  |  | 1265.5 |  |  | 1290 |  |  | 1121.5 |  |  | 1120.5 |  |  | 1123 |  |  | 1200.5 |  |  | 1045.5 |  |  | 1054 |  |  | 1127 |  |  | 1302 |  |  | 1127.5 |  |  | 1117 |  |  | 1178.5 |  |  | 1165.5 |  |  | 1254 |  |  | 1106.5 |  |  | 1131 |  |  | 1199 |  |  | 1150 |  |  | 1101 |  |  | 1130 |  |  | 1234.5 |  |  | 1169 |  |  | 1211 |  |  | 1095 |  |  | 1243 |  |  | 1143.5 |  |  | 1224.5 |  |  | 1150 |  |  | 1136 |  |  | 1131 |  |  | 1116 |  |  | 1194 |  |  | 1200.5 |  |  | 1214 |  |  | 1149.5 |  |  | 1245 |  |  | 1105 |  |  | 1173 |  |  | 1159 |  |  | 1107.5 |  |  | 1116 |  |  | 1130.5 |  |  | 1080 |  |  | 1259 |  |  | 1216 |  |  | 1170.5 |  |  | 1159 |  |  | 1135 |  |  | 1095 |  |  | 1316 |  |  | 1238 |  |  | 1165.5 |  |  | 1205.5 |  |  | 1148 |  |  | 1141.5 |  |  | 1095 |  |  | 1110.5 |  |  | 1179.5 |  |  | 1146.5 |  |  | 1192.5 |  |  | 1055 |  |  | 1261 |  |  | 1090 |  |  | 1102 |  |  | 1222 |  |  | 1107 |  |  | 1146.5 |  |  | 1140.5 |  |  | 1187.5 |  |  | 1261 |  |  | 1160.5 |  |  | 1222.5 |  |  | 1213.5 |  |  | 1139.5 |  |  | 1139 |  |  | 1179.5 |  |  | 1131.5 |  |  | 1224 |  |  | 1192.5 |  |  | 1194.5 |  |  | 1183.5 |  |  | 1211 |  |  | 1208.5 |  |  | 1200 |  |  | 1148 |  |  | 1211.5 |  |  | 1179.5 |  |  | 1198 |  |  | 1224 |  |  | 1106.5 |  |  | 1119.5 |  |  | 1228.5 |  |  | 1211 |  |  | 1157 |  |  | 1135 |  |  | 1144.5 |  |  | 1196.5 |  |  | 1176 |  |  | 1206.5 |  |  | 1093 |  |  | 1154 |  |  | 1171.5 |  |  | 1061.5 |  |  | 1146 |  |  | 1162.5 |  |  | 1133 |  |  | 1108.5 |  |  | 1264.5 |  |  | 1195 |  |  | 1072.5 |  |  | 1150 |  |  | 1204.5 |  |  | 1164 |  |  | 1202 |  |  | 1229 |  |  | 1186.5 |  |  | 1073.5 |  |  | 1177 |  |  | 1096 |  |  | 1099 |  |  | 1176.5 |  |  | 1119.5 |  |  | 1185 |  |  | 1155.5 |  |  | 1170 |  |  | 1148.5 |  |  | 1181.5 |  |  | 1092 |  |  | 1177 |  |  | 1160 |  |  | 1171.5 |  |  | 1161 |  |  | 1265.5 |  |  | 1240 |  |  | 1147.5 |  |  | 1257 |  |  | 1065.5 |  |  | 1158 |  |  | 1132.5 |  |  | 1165.5 |  |  | 1176 |  |  | 1145 |  |  | 1181 |  |  | 1188 |  |  | 1195.5 |  |  | 1117 |  |  | 1149.5 |  |  | 1098 |  |  | 1208 |  |  | 1176 |  |  | 1228 |  |  | 1245 |  |  | 1135 |  |  | 1141 |  |  | 1214.5 |  |  | 1063 |  |  | 1260
43 |  | 1222.5 |  |  | 1238 |  |  | 1189.5 |  |  | 1230 |  |  | 1195.5 |  |  | 1169 |  |  | 1228 |  |  | 1258 |  |  | 1176.5 |  |  | 1212 |  |  | 1181 |  |  | 1309 |  |  | 1212 |  |  | 1279 |  |  | 1194.5 |  |  | 1234.5 |  |  | 1146 |  |  | 1250 |  |  | 1297 |  |  | 1097.5 |  |  | 1257 |  |  | 1229 |  |  | 1182 |  |  | 1227 |  |  | 1160.5 |  |  | 1304 |  |  | 1248 |  |  | 1187 |  |  | 1224 |  |  | 1192 |  |  | 1114 |  |  | 1218.5 |  |  | 1326.5 |  |  | 1151.5 |  |  | 1155 |  |  | 1161.5 |  |  | 1125.5 |  |  | 1253.5 |  |  | 1183 |  |  | 1204 |  |  | 1098.5 |  |  | 1131 |  |  | 1306.5 |  |  | 1230.5 |  |  | 1239.5 |  |  | 1244.5 |  |  | 1289.5 |  |  | 1179 |  |  | 1066 |  |  | 1123.5 |  |  | 1215 |  |  | 1139.5 |  |  | 1166.5 |  |  | 1245 |  |  | 1158 |  |  | 1168 |  |  | 1197 |  |  | 1284 |  |  | 1233 |  |  | 1196.5 |  |  | 1286.5 |  |  | 1259.5 |  |  | 1102 |  |  | 1250 |  |  | 1110 |  |  | 1168.5 |  |  | 1213 |  |  | 1261.5 |  |  | 1190.5 |  |  | 1291.5 |  |  | 1123 |  |  | 1192 |  |  | 1188 |  |  | 1174.5 |  |  | 1253.5 |  |  | 1191.5 |  |  | 1236.5 |  |  | 1227.5 |  |  | 1259.5 |  |  | 1227.5 |  |  | 1242.5 |  |  | 1169 |  |  | 1191 |  |  | 1212 |  |  | 1241.5 |  |  | 1225 |  |  | 1134.5 |  |  | 1148 |  |  | 1225 |  |  | 1230.5 |  |  | 1242.5 |  |  | 1189 |  |  | 1404 |  |  | 1188.5 |  |  | 1221 |  |  | 1121.5 |  |  | 1246.5 |  |  | 1233.5 |  |  | 1210.5 |  |  | 1114.5 |  |  | 1255 |  |  | 1161 |  |  | 1135 |  |  | 1273.5 |  |  | 1172.5 |  |  | 1189.5 |  |  | 1186.5 |  |  | 1228 |  |  | 1185 |  |  | 1202.5 |  |  | 1110 |  |  | 1258.5 |  |  | 1217 |  |  | 1221 |  |  | 1138.5 |  |  | 1230 |  |  | 1160 |  |  | 1200 |  |  | 1175 |  |  | 1268.5 |  |  | 1203.5 |  |  | 1112.5 |  |  | 1327 |  |  | 1131 |  |  | 1107 |  |  | 1157 |  |  | 1192.5 |  |  | 1174 |  |  | 1251.5 |  |  | 1211 |  |  | 1174 |  |  | 1242.5 |  |  | 1111.5 |  |  | 1087 |  |  | 1160.5 |  |  | 1161 |  |  | 1225 |  |  | 1240 |  |  | 1193 |  |  | 1198 |  |  | 1149 |  |  | 1120 |  |  | 1228 |  |  | 1131 |  |  | 1165.5 |  |  | 1133 |  |  | 1118 |  |  | 1191 |  |  | 1180 |  |  | 1127 |  |  | 1168 |  |  | 1195 |  |  | 1165.5 |  |  | 1221 |  |  | 1241.5 |  |  | 1276 |  |  | 1181 |  |  | 1285.5 |  |  | 1168 |  |  | 1319.5 |  |  | 1201 |  |  | 1110 |  |  | 1238.5 |  |  | 1169 |  |  | 1200.5 |  |  | 1117 |  |  | 1189 |  |  | 1184.5 |  |  | 1192.5 |  |  | 1210 |  |  | 1147.5 |  |  | 1155.5 |  |  | 1178 |  |  | 1243 |  |  | 1339.5 |  |  | 1169.5 |  |  | 1162.5 |  |  | 1190 |  |  | 1265 |  |  | 1148 |  |  | 1272 |  |  | 1266 |  |  | 1239.5 |  |  | 1178 |  |  | 1144.5 |  |  | 1216.5 |  |  | 1278 |  |  | 1241 |  |  | 1272.5 |  |  | 1120.5 |  |  | 1169 |  |  | 1233.5 |  |  | 1159.5 |  |  | 1196 |  |  | 1129 |  |  | 1200 |  |  | 1140.5 |  |  | 1270 |  |  | 1173.5 |  |  | 1173.5 |  |  | 1132 |  |  | 1198.5 |  |  | 1120 |  |  | 1222 |  |  | 1209 |  |  | 1223 |  |  | 1150 |  |  | 1251 |  |  | 1302 |  |  | 1243 |  |  | 1291 |  |  | 1169 |  |  | 1202.5 |  |  | 1299.5 |  |  | 1139 |  |  | 1124 |  |  | 1264 |  |  | 1228.5 |  |  | 1244.5 |  |  | 1291.5 |  |  | 1150 |  |  | 1247 |  |  | 1281.5 |  |  | 1158.5 |  |  | 1080.5 |  |  | 1294 |  |  | 1290 |  |  | 1194 |  |  | 1146 |  |  | 1168 |  |  | 1178.5 |  |  | 1145.5 |  |  | 1268 |  |  | 1257 |  |  | 1198 |  |  | 1263 |  |  | 1135 |  |  | 1170.5 |  |  | 1172 |  |  | 1281 |  |  | 1172 |  |  | 1173 |  |  | 1109.5 |  |  | 1335 |  |  | 1265 |  |  | 1191 |  |  | 1258 |  |  | 1244.5 |  |  | 1277 |  |  | 1139 |  |  | 1121 |  |  | 1269.5 |  |  | 1217.5 |  |  | 1252.5 |  |  | 1292 |  |  | 1207 |  |  | 1182 |  |  | 1268 |  |  | 1236 |  |  | 1157.5 |  |  | 1289 |  |  | 1171.5 |  |  | 1241.5 |  |  | 1232.5 |  |  | 1191 |  |  | 1258.5 |  |  | 1133 |  |  | 1153 |  |  | 1196.5 |  |  | 1223.5 |  |  | 1289 |  |  | 1334.5 |  |  | 1247.5 |  |  | 1184 |  |  | 1253 |  |  | 1198.5 |  |  | 1177.5 |  |  | 1195 |  |  | 1182.5 |  |  | 1235 |  |  | 1140 |  |  | 1190.5 |  |  | 1222 |  |  | 1163 |  |  | 1220.5 |  |  | 1172 |  |  | 1236.5 |  |  | 1168 |  |  | 1302 |  |  | 1197 |  |  | 1132 |  |  | 1286.5 |  |  | 1332 |  |  | 1257.5 |  |  | 1170.5 |  |  | 1214.5 |  |  | 1302 |  |  | 1311.5 |  |  | 1312 |  |  | 1247 |  |  | 1096.5 |  |  | 1198.5 |  |  | 1216 |  |  | 1195.5 |  |  | 1251 |  |  | 1198 |  |  | 1305.5 |  |  | 1214 |  |  | 1183.5 |  |  | 1199.5 |  |  | 1250.5 |  |  | 1230 |  |  | 1136 |  |  | 1219 |  |  | 1109.5 |  |  | 1158 |  |  | 1266.5 |  |  | 1226 |  |  | 1203 |  |  | 1138 |  |  | 1225 |  |  | 1265 |  |  | 1190 |  |  | 1168 |  |  | 1301 |  |  | 1241 |  |  | 1186.5 |  |  | 1191 |  |  | 1162 |  |  | 1353.5 |  |  | 1108.5 |  |  | 1247.5 |  |  | 1284.5 |  |  | 1181 |  |  | 1333 |  |  | 1103.5 |  |  | 1225.5 |  |  | 1295.5 |  |  | 1243 |  |  | 1185 |  |  | 1188 |  |  | 1187 |  |  | 1134 |  |  | 1196 |  |  | 1229 |  |  | 1194.5 |  |  | 1169.5 |  |  | 1215 |  |  | 1212.5 |  |  | 1237.5 |  |  | 1120 |  |  | 1229 |  |  | 1191 |  |  | 1199 |  |  | 1170.5 |  |  | 1122.5 |  |  | 1182.5 |  |  | 1187 |  |  | 1165.5 |  |  | 1221 |  |  | 1158 |  |  | 1195 |  |  | 1112.5 |  |  | 1259 |  |  | 1081 |  |  | 1210.5 |  |  | 1184 |  |  | 1213.5 |  |  | 1287 |  |  | 1203.5 |  |  | 1106 |  |  | 1184.5 |  |  | 1224.5 |  |  | 1251 |  |  | 1176 |  |  | 1102 |  |  | 1176 |  |  | 1154.5 |  |  | 1142 |  |  | 1248 |  |  | 1161.5 |  |  | 1246.5 |  |  | 1137.5 |  |  | 1206 |  |  | 1186.5 |  |  | 1173.5 |  |  | 1214.5 |  |  | 1267 |  |  | 1211 |  |  | 1173.5 |  |  | 1245 |  |  | 1289 |  |  | 1170.5 |  |  | 1182 |  |  | 1259 |  |  | 1189 |  |  | 1124 |  |  | 1134.5 |  |  | 1275.5 |  |  | 1103 |  |  | 1238 |  |  | 1222 |  |  | 1160 |  |  | 1175 |  |  | 1163.5 |  |  | 1244.5 |  |  | 1199 |  |  | 1360 |  |  | 1286 |  |  | 1103.5 |  |  | 1262.5 |  |  | 1209 |  |  | 1145 |  |  | 1126 |  |  | 1211.5 |  |  | 1295.5 |  |  | 1217 |  |  | 1173 |  |  | 1254 |  |  | 1214 |  |  | 1151 |  |  | 1273 |  |  | 1183 |  |  | 1264.5 |  |  | 1114 |  |  | 1341 |  |  | 1179 |  |  | 1236.5 |  |  | 1291 |  |  | 1073 |  |  | 1082 |  |  | 1231 |  |  | 1223 |  |  | 1203 |  |  | 1180 |  |  | 1171.5 |  |  | 1181.5 |  |  | 1167.5 |  |  | 1210 |  |  | 1204 |  |  | 1247.5 |  |  | 1140 |  |  | 1176.5 |  |  | 1164.5 |  |  | 1121 |  |  | 1162 |  |  | 1278.5 |  |  | 1213 |  |  | 1209 |  |  | 1216 |  |  | 1191 |  |  | 1168 |  |  | 1196 |  |  | 1188 |  |  | 1313.5 |  |  | 1197 |  |  | 1151 |  |  | 1266 |  |  | 1181 |  |  | 1255 |  |  | 1117 |  |  | 1356 |  |  | 1280 |  |  | 1205 |  |  | 1327.5 |  |  | 1192.5 |  |  | 1170.5 |  |  | 1198.5 |  |  | 1235 |  |  | 1148 |  |  | 1277.5 |  |  | 1209 |  |  | 1210 |  |  | 1188.5 |  |  | 1270.5 |  |  | 1264 |  |  | 1204.5 |  |  | 1159.5 |  |  | 1120 |  |  | 1253 |  |  | 1167 |  |  | 1211 |  |  | 1251.5 |  |  | 1155 |  |  | 1207.5 |  |  | 1147.5 |  |  | 1151 |  |  | 1177 |  |  | 1192.5 |  |  | 1200 |  |  | 1257.5 |  |  | 1163 |  |  | 1207.5 |  |  | 1118.5 |  |  | 1161.5 |  |  | 1236.5 |  |  | 1227.5 |  |  | 1183 |  |  | 1202 |  |  | 1342.5 |  |  | 1245 |  |  | 1158 |  |  | 1181 |  |  | 1243 |  |  | 1249.5 |  |  | 1108 |  |  | 1157 |  |  | 1263 |  |  | 1234.5 |  |  | 1220 |  |  | 1160 |  |  | 1231 |  |  | 1321.5 |  |  | 1195 |  |  | 1068 |  |  | 1172 |  |  | 1242 |  |  | 1379.5 |  |  | 1217 |  |  | 1162.5 |  |  | 1202 |  |  | 1259 |  |  | 1339.5 |  |  | 1250 |  |  | 1158 |  |  | 1105.5 |  |  | 1203 |  |  | 1159 |  |  | 1256 |  |  | 1235.5 |  |  | 1156.5 |  |  | 1201 |  |  | 1125 |  |  | 1219.5 |  |  | 1231.5 |  |  | 1160 |  |  | 1273 |  |  | 1267.5 |  |  | 1248.5 |  |  | 1143.5 |  |  | 1185.5 |  |  | 1229.5 |  |  | 1318 |  |  | 1223.5 |  |  | 1210 |  |  | 1202 |  |  | 1238 |  |  | 1236 |  |  | 1273.5 |  |  | 1192 |  |  | 1137 |  |  | 1189.5 |  |  | 1174.5 |  |  | 1131 |  |  | 1176.5 |  |  | 1203.5 |  |  | 1238 |  |  | 1180 |  |  | 1210 |  |  | 1189.5 |  |  | 1220 |  |  | 1170.5 |  |  | 1211 |  |  | 1267 |  |  | 1304.5 |  |  | 1185 |  |  | 1344 |  |  | 1163 |  |  | 1197 |  |  | 1242 |  |  | 1206 |  |  | 1184 |  |  | 1163 |  |  | 1141.5 |  |  | 1212.5 |  |  | 1233 |  |  | 1214.5 |  |  | 1052.5 |  |  | 1164 |  |  | 1090 |  |  | 1240 |  |  | 1264.5 |  |  | 1174.5 |  |  | 1170 |  |  | 1283 |  |  | 1134 |  |  | 1106 |  |  | 1195 |  |  | 1178 |  |  | 1347 |  |  | 1175.5 |  |  | 1212 |  |  | 1248 |  |  | 1310 |  |  | 1139 |  |  | 1128 |  |  | 1229.5 |  |  | 1349.5 |  |  | 1082.5 |  |  | 1136 |  |  | 1118 |  |  | 1099.5 |  |  | 1274.5 |  |  | 1234.5 |  |  | 1200 |  |  | 1255.5 |  |  | 1201.5 |  |  | 1174 |  |  | 1161.5 |  |  | 1239.5 |  |  | 1209 |  |  | 1113 |  |  | 1233 |  |  | 1203 |  |  | 1163 |  |  | 1097 |  |  | 1226 |  |  | 1305 |  |  | 1188 |  |  | 1138 |  |  | 1253.5 |  |  | 1203 |  |  | 1254 |  |  | 1116 |  |  | 1173.5 |  |  | 1264 |  |  | 1219.5 |  |  | 1262 |  |  | 1213 |  |  | 1200 |  |  | 1201 |  |  | 1247.5 |  |  | 1222 |  |  | 1122 |  |  | 1319.5 |  |  | 1211 |  |  | 1158 |  |  | 1125.5 |  |  | 1187.5 |  |  | 1274 |  |  | 1165.5 |  |  | 1241 |  |  | 1203.5 |  |  | 1274 |  |  | 1214 |  |  | 1202.5 |  |  | 1310.5 |  |  | 1224 |  |  | 1239 |  |  | 1220 |  |  | 1274 |  |  | 1095 |  |  | 1251 |  |  | 1093 |  |  | 1167 |  |  | 1299.5 |  |  | 1142 |  |  | 1294.5 |  |  | 1222 |  |  | 1219.5 |  |  | 1166.5 |  |  | 1171 |  |  | 1293 |  |  | 1214.5 |  |  | 1255 |  |  | 1188 |  |  | 1225 |  |  | 1178.5 |  |  | 1271 |  |  | 1108.5 |  |  | 1169 |  |  | 1178 |  |  | 1223 |  |  | 1242 |  |  | 1265.5 |  |  | 1139 |  |  | 1203 |  |  | 1232 |  |  | 1157.5 |  |  | 1300 |  |  | 1237 |  |  | 1248 |  |  | 1149 |  |  | 1234.5 |  |  | 1154.5 |  |  | 1242 |  |  | 1245 |  |  | 1242 |  |  | 1240.5 |  |  | 1194 |  |  | 1179 |  |  | 1129 |  |  | 1312.5 |  |  | 1205.5 |  |  | 1278.5 |  |  | 1186 |  |  | 1270 |  |  | 1160 |  |  | 1185.5 |  |  | 1211 |  |  | 1198.5 |  |  | 1102 |  |  | 1135 |  |  | 1228 |  |  | 1163.5 |  |  | 1238.5 |  |  | 1213 |  |  | 1123 |  |  | 1230.5 |  |  | 1200 |  |  | 1247 |  |  | 1225.5 |  |  | 1208 |  |  | 1173 |  |  | 1286.5 |  |  | 1137 |  |  | 1267 |  |  | 1211.5 |  |  | 1252 |  |  | 1192.5 |  |  | 1254 |  |  | 1105.5 |  |  | 1225.5 |  |  | 1142 |  |  | 1310 |  |  | 1216.5 |  |  | 1201.5 |  |  | 1294 |  |  | 1187 |  |  | 1259 |  |  | 1176.5 |  |  | 1215 |  |  | 1138 |  |  | 1250 |  |  | 1261.5 |  |  | 1219.5 |  |  | 1217 |  |  | 1275 |  |  | 1168 |  |  | 1207 |  |  | 1265 |  |  | 1168 |  |  | 1208 |  |  | 1150.5 |  |  | 1189.5 |  |  | 1157.5 |  |  | 1230 |  |  | 1168.5 |  |  | 1234 |  |  | 1114 |  |  | 1217.5 |  |  | 1135.5 |  |  | 1055 |  |  | 1212 |  |  | 1085.5 |  |  | 1179 |  |  | 1184 |  |  | 1140.5 |  |  | 1122.5 |  |  | 1228 |  |  | 1217 |  |  | 1280 |  |  | 1116.5 |  |  | 1119 |  |  | 1112 |  |  | 1203 |  |  | 1153 |  |  | 1286 |  |  | 1213.5 |  |  | 1250 |  |  | 1139 |  |  | 1079 |  |  | 1304.5 |  |  | 1246 |  |  | 1169.5 |  |  | 1141.5 |  |  | 1225 |  |  | 1166 |  |  | 1192.5 |  |  | 1113.5 |  |  | 1131.5 |  |  | 1210.5 |  |  | 1226.5 |  |  | 1251 |  |  | 1161 |  |  | 1275.5 |  |  | 1202.5 |  |  | 1203 |  |  | 1170 |  |  | 1206.5 |  |  | 1205 |  |  | 1219 |  |  | 1125 |  |  | 1243.5 |  |  | 1290 |  |  | 1119.5 |  |  | 1164 |  |  | 1229.5 |  |  | 1210.5 |  |  | 1311.5 |  |  | 1180 |  |  | 1166 |  |  | 1247.5 |  |  | 1186.5 |  |  | 1230 |  |  | 1209 |  |  | 1170.5 |  |  | 1201 |  |  | 1197.5 |  |  | 1186.5 |  |  | 1197 |  |  | 1178 |  |  | 1190.5 |  |  | 1268.5 |  |  | 1158 |  |  | 1161.5 |  |  | 1266.5 |  |  | 1120 |  |  | 1303 |  |  | 1302 |  |  | 1158.5 |  |  | 1232 |  |  | 1201 |  |  | 1196 |  |  | 1178 |  |  | 1250 |  |  | 1141 |  |  | 1262.5 |  |  | 1145.5 |  |  | 1173 |  |  | 1123 |  |  | 1200 |  |  | 1205.5 |  |  | 1186 |  |  | 1279 |  |  | 1142.5 |  |  | 1216.5 |  |  | 1195 |  |  | 1185.5 |  |  | 1215 |  |  | 1167 |  |  | 1205 |  |  | 1304.5 |  |  | 1314 |  |  | 1142.5 |  |  | 1141.5 |  |  | 1147 |  |  | 1247.5 |  |  | 1084.5 |  |  | 1093 |  |  | 1142 |  |  | 1331 |  |  | 1151.5 |  |  | 1141 |  |  | 1199.5 |  |  | 1180.5 |  |  | 1275 |  |  | 1145.5 |  |  | 1170 |  |  | 1228 |  |  | 1179 |  |  | 1140 |  |  | 1151 |  |  | 1281.5 |  |  | 1208 |  |  | 1250 |  |  | 1142 |  |  | 1282 |  |  | 1167.5 |  |  | 1263.5 |  |  | 1171 |  |  | 1162 |  |  | 1170 |  |  | 1137 |  |  | 1220 |  |  | 1229.5 |  |  | 1253 |  |  | 1178.5 |  |  | 1274 |  |  | 1129 |  |  | 1199 |  |  | 1174 |  |  | 1131.5 |  |  | 1145 |  |  | 1169.5 |  |  | 1101 |  |  | 1280 |  |  | 1245 |  |  | 1191.5 |  |  | 1188 |  |  | 1174 |  |  | 1116 |  |  | 1345 |  |  | 1277 |  |  | 1189.5 |  |  | 1231.5 |  |  | 1187 |  |  | 1165.5 |  |  | 1110 |  |  | 1125.5 |  |  | 1218.5 |  |  | 1175.5 |  |  | 1221.5 |  |  | 1094 |  |  | 1285 |  |  | 1129 |  |  | 1131 |  |  | 1248 |  |  | 1133 |  |  | 1170.5 |  |  | 1187.5 |  |  | 1202.5 |  |  | 1282 |  |  | 1207.5 |  |  | 1246.5 |  |  | 1239.5 |  |  | 1160.5 |  |  | 1178 |  |  | 1218.5 |  |  | 1170.5 |  |  | 1245 |  |  | 1221.5 |  |  | 1241.5 |  |  | 1207.5 |  |  | 1226 |  |  | 1247.5 |  |  | 1221 |  |  | 1187 |  |  | 1240.5 |  |  | 1194.5 |  |  | 1227 |  |  | 1245 |  |  | 1145.5 |  |  | 1145.5 |  |  | 1243.5 |  |  | 1235 |  |  | 1172 |  |  | 1150 |  |  | 1191.5 |  |  | 1235.5 |  |  | 1223 |  |  | 1221.5 |  |  | 1114 |  |  | 1180 |  |  | 1210.5 |  |  | 1076.5 |  |  | 1172 |  |  | 1201.5 |  |  | 1172 |  |  | 1137.5 |  |  | 1290.5 |  |  | 1221 |  |  | 1111.5 |  |  | 1197 |  |  | 1219.5 |  |  | 1211 |  |  | 1241 |  |  | 1250 |  |  | 1201.5 |  |  | 1112.5 |  |  | 1216 |  |  | 1135 |  |  | 1146 |  |  | 1197.5 |  |  | 1158.5 |  |  | 1224 |  |  | 1170.5 |  |  | 1185 |  |  | 1174.5 |  |  | 1210.5 |  |  | 1131 |  |  | 1192 |  |  | 1199 |  |  | 1195.5 |  |  | 1187 |  |  | 1280.5 |  |  | 1255 |  |  | 1176.5 |  |  | 1286 |  |  | 1104.5 |  |  | 1179 |  |  | 1156.5 |  |  | 1204.5 |  |  | 1191 |  |  | 1166 |  |  | 1228 |  |  | 1209 |  |  | 1210.5 |  |  | 1143 |  |  | 1170.5 |  |  | 1127 |  |  | 1223 |  |  | 1223 |  |  | 1252 |  |  | 1284 |  |  | 1159 |  |  | 1180 |  |  | 1253.5 |  |  | 1102 |  |  | 1299
44 |  | 1251.5 |  |  | 1277 |  |  | 1228.5 |  |  | 1245 |  |  | 1221.5 |  |  | 1190 |  |  | 1257 |  |  | 1297 |  |  | 1223.5 |  |  | 1241 |  |  | 1205 |  |  | 1356 |  |  | 1241 |  |  | 1305 |  |  | 1215.5 |  |  | 1260.5 |  |  | 1161 |  |  | 1289 |  |  | 1336 |  |  | 1136.5 |  |  | 1283 |  |  | 1276 |  |  | 1208 |  |  | 1251 |  |  | 1189.5 |  |  | 1351 |  |  | 1263 |  |  | 1208 |  |  | 1245 |  |  | 1207 |  |  | 1135 |  |  | 1244.5 |  |  | 1352.5 |  |  | 1198.5 |  |  | 1179 |  |  | 1185.5 |  |  | 1164.5 |  |  | 1279.5 |  |  | 1222 |  |  | 1219 |  |  | 1137.5 |  |  | 1178 |  |  | 1321.5 |  |  | 1269.5 |  |  | 1263.5 |  |  | 1291.5 |  |  | 1336.5 |  |  | 1203 |  |  | 1105 |  |  | 1149.5 |  |  | 1244 |  |  | 1178.5 |  |  | 1195.5 |  |  | 1274 |  |  | 1182 |  |  | 1197 |  |  | 1221 |  |  | 1299 |  |  | 1272 |  |  | 1220.5 |  |  | 1325.5 |  |  | 1274.5 |  |  | 1123 |  |  | 1289 |  |  | 1136 |  |  | 1189.5 |  |  | 1228 |  |  | 1290.5 |  |  | 1211.5 |  |  | 1317.5 |  |  | 1147 |  |  | 1239 |  |  | 1209 |  |  | 1195.5 |  |  | 1277.5 |  |  | 1238.5 |  |  | 1275.5 |  |  | 1266.5 |  |  | 1283.5 |  |  | 1256.5 |  |  | 1257.5 |  |  | 1190 |  |  | 1206 |  |  | 1236 |  |  | 1256.5 |  |  | 1272 |  |  | 1155.5 |  |  | 1172 |  |  | 1240 |  |  | 1259.5 |  |  | 1281.5 |  |  | 1218 |  |  | 1443 |  |  | 1217.5 |  |  | 1268 |  |  | 1168.5 |  |  | 1272.5 |  |  | 1248.5 |  |  | 1231.5 |  |  | 1138.5 |  |  | 1284 |  |  | 1208 |  |  | 1150 |  |  | 1320.5 |  |  | 1219.5 |  |  | 1236.5 |  |  | 1215.5 |  |  | 1254 |  |  | 1224 |  |  | 1217.5 |  |  | 1149 |  |  | 1282.5 |  |  | 1238 |  |  | 1250 |  |  | 1167.5 |  |  | 1254 |  |  | 1181 |  |  | 1226 |  |  | 1222 |  |  | 1297.5 |  |  | 1242.5 |  |  | 1136.5 |  |  | 1366 |  |  | 1157 |  |  | 1146 |  |  | 1204 |  |  | 1213.5 |  |  | 1213 |  |  | 1298.5 |  |  | 1232 |  |  | 1189 |  |  | 1281.5 |  |  | 1137.5 |  |  | 1126 |  |  | 1175.5 |  |  | 1185 |  |  | 1240 |  |  | 1261 |  |  | 1217 |  |  | 1213 |  |  | 1170 |  |  | 1144 |  |  | 1267 |  |  | 1178 |  |  | 1180.5 |  |  | 1159 |  |  | 1139 |  |  | 1230 |  |  | 1195 |  |  | 1153 |  |  | 1183 |  |  | 1242 |  |  | 1194.5 |  |  | 1250 |  |  | 1265.5 |  |  | 1302 |  |  | 1210 |  |  | 1300.5 |  |  | 1194 |  |  | 1366.5 |  |  | 1216 |  |  | 1131 |  |  | 1253.5 |  |  | 1198 |  |  | 1247.5 |  |  | 1156 |  |  | 1213 |  |  | 1208.5 |  |  | 1213.5 |  |  | 1236 |  |  | 1162.5 |  |  | 1194.5 |  |  | 1217 |  |  | 1258 |  |  | 1386.5 |  |  | 1208.5 |  |  | 1201.5 |  |  | 1205 |  |  | 1304 |  |  | 1177 |  |  | 1287 |  |  | 1290 |  |  | 1268.5 |  |  | 1193 |  |  | 1159.5 |  |  | 1242.5 |  |  | 1307 |  |  | 1288 |  |  | 1296.5 |  |  | 1141.5 |  |  | 1193 |  |  | 1259.5 |  |  | 1198.5 |  |  | 1243 |  |  | 1155 |  |  | 1221 |  |  | 1187.5 |  |  | 1299 |  |  | 1197.5 |  |  | 1197.5 |  |  | 1147 |  |  | 1224.5 |  |  | 1135 |  |  | 1261 |  |  | 1256 |  |  | 1238 |  |  | 1174 |  |  | 1277 |  |  | 1349 |  |  | 1272 |  |  | 1330 |  |  | 1184 |  |  | 1223.5 |  |  | 1346.5 |  |  | 1186 |  |  | 1150 |  |  | 1285 |  |  | 1275.5 |  |  | 1268.5 |  |  | 1315.5 |  |  | 1176 |  |  | 1276 |  |  | 1310.5 |  |  | 1197.5 |  |  | 1119.5 |  |  | 1323 |  |  | 1329 |  |  | 1209 |  |  | 1161 |  |  | 1189 |  |  | 1217.5 |  |  | 1192.5 |  |  | 1315 |  |  | 1296 |  |  | 1213 |  |  | 1284 |  |  | 1174 |  |  | 1199.5 |  |  | 1187 |  |  | 1302 |  |  | 1193 |  |  | 1220 |  |  | 1148.5 |  |  | 1356 |  |  | 1294 |  |  | 1230 |  |  | 1305 |  |  | 1273.5 |  |  | 1303 |  |  | 1186 |  |  | 1168 |  |  | 1295.5 |  |  | 1232.5 |  |  | 1281.5 |  |  | 1313 |  |  | 1246 |  |  | 1211 |  |  | 1307 |  |  | 1275 |  |  | 1196.5 |  |  | 1304 |  |  | 1200.5 |  |  | 1270.5 |  |  | 1261.5 |  |  | 1238 |  |  | 1284.5 |  |  | 1180 |  |  | 1200 |  |  | 1217.5 |  |  | 1244.5 |  |  | 1328 |  |  | 1373.5 |  |  | 1271.5 |  |  | 1208 |  |  | 1282 |  |  | 1237.5 |  |  | 1216.5 |  |  | 1234 |  |  | 1221.5 |  |  | 1264 |  |  | 1179 |  |  | 1205.5 |  |  | 1243 |  |  | 1202 |  |  | 1241.5 |  |  | 1198 |  |  | 1251.5 |  |  | 1215 |  |  | 1328 |  |  | 1212 |  |  | 1171 |  |  | 1307.5 |  |  | 1356 |  |  | 1272.5 |  |  | 1185.5 |  |  | 1261.5 |  |  | 1328 |  |  | 1337.5 |  |  | 1338 |  |  | 1271 |  |  | 1125.5 |  |  | 1237.5 |  |  | 1240 |  |  | 1221.5 |  |  | 1290 |  |  | 1222 |  |  | 1352.5 |  |  | 1253 |  |  | 1198.5 |  |  | 1238.5 |  |  | 1279.5 |  |  | 1269 |  |  | 1175 |  |  | 1240 |  |  | 1135.5 |  |  | 1205 |  |  | 1287.5 |  |  | 1250 |  |  | 1250 |  |  | 1167 |  |  | 1240 |  |  | 1286 |  |  | 1229 |  |  | 1192 |  |  | 1327 |  |  | 1262 |  |  | 1225.5 |  |  | 1230 |  |  | 1201 |  |  | 1379.5 |  |  | 1129.5 |  |  | 1271.5 |  |  | 1310.5 |  |  | 1220 |  |  | 1348 |  |  | 1132.5 |  |  | 1249.5 |  |  | 1334.5 |  |  | 1267 |  |  | 1209 |  |  | 1235 |  |  | 1216 |  |  | 1158 |  |  | 1211 |  |  | 1250 |  |  | 1218.5 |  |  | 1190.5 |  |  | 1254 |  |  | 1233.5 |  |  | 1284.5 |  |  | 1141 |  |  | 1255 |  |  | 1212 |  |  | 1225 |  |  | 1196.5 |  |  | 1146.5 |  |  | 1221.5 |  |  | 1216 |  |  | 1212.5 |  |  | 1247 |  |  | 1182 |  |  | 1234 |  |  | 1151.5 |  |  | 1285 |  |  | 1096 |  |  | 1239.5 |  |  | 1210 |  |  | 1252.5 |  |  | 1326 |  |  | 1232.5 |  |  | 1127 |  |  | 1223.5 |  |  | 1245.5 |  |  | 1277 |  |  | 1223 |  |  | 1123 |  |  | 1202 |  |  | 1183.5 |  |  | 1171 |  |  | 1272 |  |  | 1208.5 |  |  | 1285.5 |  |  | 1163.5 |  |  | 1227 |  |  | 1225.5 |  |  | 1194.5 |  |  | 1240.5 |  |  | 1306 |  |  | 1237 |  |  | 1194.5 |  |  | 1274 |  |  | 1318 |  |  | 1209.5 |  |  | 1197 |  |  | 1285 |  |  | 1228 |  |  | 1148 |  |  | 1173.5 |  |  | 1322.5 |  |  | 1150 |  |  | 1262 |  |  | 1261 |  |  | 1189 |  |  | 1201 |  |  | 1202.5 |  |  | 1283.5 |  |  | 1225 |  |  | 1381 |  |  | 1333 |  |  | 1124.5 |  |  | 1288.5 |  |  | 1238 |  |  | 1184 |  |  | 1165 |  |  | 1232.5 |  |  | 1321.5 |  |  | 1241 |  |  | 1188 |  |  | 1301 |  |  | 1240 |  |  | 1190 |  |  | 1302 |  |  | 1230 |  |  | 1303.5 |  |  | 1153 |  |  | 1367 |  |  | 1226 |  |  | 1275.5 |  |  | 1320 |  |  | 1102 |  |  | 1129 |  |  | 1260 |  |  | 1249 |  |  | 1232 |  |  | 1219 |  |  | 1200.5 |  |  | 1202.5 |  |  | 1182.5 |  |  | 1257 |  |  | 1230 |  |  | 1262.5 |  |  | 1166 |  |  | 1202.5 |  |  | 1185.5 |  |  | 1168 |  |  | 1188 |  |  | 1293.5 |  |  | 1242 |  |  | 1238 |  |  | 1255 |  |  | 1217 |  |  | 1189 |  |  | 1211 |  |  | 1212 |  |  | 1328.5 |  |  | 1226 |  |  | 1180 |  |  | 1290 |  |  | 1205 |  |  | 1294 |  |  | 1156 |  |  | 1377 |  |  | 1304 |  |  | 1234 |  |  | 1342.5 |  |  | 1218.5 |  |  | 1209.5 |  |  | 1245.5 |  |  | 1256 |  |  | 1163 |  |  | 1316.5 |  |  | 1224 |  |  | 1249 |  |  | 1203.5 |  |  | 1309.5 |  |  | 1288 |  |  | 1251.5 |  |  | 1183.5 |  |  | 1144 |  |  | 1282 |  |  | 1193 |  |  | 1250 |  |  | 1290.5 |  |  | 1202 |  |  | 1231.5 |  |  | 1168.5 |  |  | 1166 |  |  | 1216 |  |  | 1221.5 |  |  | 1224 |  |  | 1278.5 |  |  | 1192 |  |  | 1222.5 |  |  | 1165.5 |  |  | 1200.5 |  |  | 1265.5 |  |  | 1242.5 |  |  | 1212 |  |  | 1223 |  |  | 1363.5 |  |  | 1274 |  |  | 1182 |  |  | 1196 |  |  | 1264 |  |  | 1296.5 |  |  | 1129 |  |  | 1204 |  |  | 1289 |  |  | 1281.5 |  |  | 1259 |  |  | 1199 |  |  | 1270 |  |  | 1360.5 |  |  | 1224 |  |  | 1107 |  |  | 1219 |  |  | 1289 |  |  | 1426.5 |  |  | 1246 |  |  | 1183.5 |  |  | 1231 |  |  | 1274 |  |  | 1354.5 |  |  | 1289 |  |  | 1182 |  |  | 1152.5 |  |  | 1242 |  |  | 1185 |  |  | 1271 |  |  | 1274.5 |  |  | 1203.5 |  |  | 1240 |  |  | 1154 |  |  | 1234.5 |  |  | 1278.5 |  |  | 1186 |  |  | 1294 |  |  | 1314.5 |  |  | 1274.5 |  |  | 1182.5 |  |  | 1224.5 |  |  | 1268.5 |  |  | 1357 |  |  | 1270.5 |  |  | 1234 |  |  | 1241 |  |  | 1267 |  |  | 1260 |  |  | 1297.5 |  |  | 1239 |  |  | 1161 |  |  | 1204.5 |  |  | 1195.5 |  |  | 1152 |  |  | 1215.5 |  |  | 1224.5 |  |  | 1277 |  |  | 1201 |  |  | 1231 |  |  | 1210.5 |  |  | 1244 |  |  | 1194.5 |  |  | 1250 |  |  | 1314 |  |  | 1351.5 |  |  | 1206 |  |  | 1391 |  |  | 1192 |  |  | 1244 |  |  | 1257 |  |  | 1227 |  |  | 1213 |  |  | 1184 |  |  | 1167.5 |  |  | 1259.5 |  |  | 1280 |  |  | 1235.5 |  |  | 1091.5 |  |  | 1188 |  |  | 1114 |  |  | 1279 |  |  | 1303.5 |  |  | 1213.5 |  |  | 1209 |  |  | 1312 |  |  | 1155 |  |  | 1145 |  |  | 1216 |  |  | 1199 |  |  | 1362 |  |  | 1222.5 |  |  | 1259 |  |  | 1263 |  |  | 1349 |  |  | 1163 |  |  | 1175 |  |  | 1268.5 |  |  | 1364.5 |  |  | 1097.5 |  |  | 1183 |  |  | 1142 |  |  | 1125.5 |  |  | 1298.5 |  |  | 1249.5 |  |  | 1239 |  |  | 1279.5 |  |  | 1216.5 |  |  | 1195 |  |  | 1200.5 |  |  | 1286.5 |  |  | 1230 |  |  | 1142 |  |  | 1280 |  |  | 1232 |  |  | 1192 |  |  | 1136 |  |  | 1273 |  |  | 1344 |  |  | 1235 |  |  | 1177 |  |  | 1279.5 |  |  | 1224 |  |  | 1280 |  |  | 1137 |  |  | 1194.5 |  |  | 1290 |  |  | 1248.5 |  |  | 1277 |  |  | 1228 |  |  | 1239 |  |  | 1240 |  |  | 1286.5 |  |  | 1237 |  |  | 1151 |  |  | 1358.5 |  |  | 1258 |  |  | 1197 |  |  | 1164.5 |  |  | 1226.5 |  |  | 1321 |  |  | 1180.5 |  |  | 1288 |  |  | 1224.5 |  |  | 1321 |  |  | 1253 |  |  | 1226.5 |  |  | 1349.5 |  |  | 1245 |  |  | 1265 |  |  | 1246 |  |  | 1289 |  |  | 1142 |  |  | 1298 |  |  | 1117 |  |  | 1193 |  |  | 1346.5 |  |  | 1157 |  |  | 1341.5 |  |  | 1237 |  |  | 1258.5 |  |  | 1187.5 |  |  | 1218 |  |  | 1322 |  |  | 1229.5 |  |  | 1270 |  |  | 1235 |  |  | 1264 |  |  | 1207.5 |  |  | 1297 |  |  | 1129.5 |  |  | 1193 |  |  | 1199 |  |  | 1249 |  |  | 1266 |  |  | 1312.5 |  |  | 1178 |  |  | 1218 |  |  | 1256 |  |  | 1181.5 |  |  | 1339 |  |  | 1284 |  |  | 1274 |  |  | 1196 |  |  | 1249.5 |  |  | 1193.5 |  |  | 1263 |  |  | 1266 |  |  | 1271 |  |  | 1269.5 |  |  | 1233 |  |  | 1218 |  |  | 1168 |  |  | 1351.5 |  |  | 1226.5 |  |  | 1293.5 |  |  | 1225 |  |  | 1296 |  |  | 1199 |  |  | 1214.5 |  |  | 1250 |  |  | 1227.5 |  |  | 1117 |  |  | 1182 |  |  | 1254 |  |  | 1189.5 |  |  | 1262.5 |  |  | 1237 |  |  | 1170 |  |  | 1251.5 |  |  | 1215 |  |  | 1294 |  |  | 1264.5 |  |  | 1229 |  |  | 1202 |  |  | 1315.5 |  |  | 1158 |  |  | 1293 |  |  | 1240.5 |  |  | 1299 |  |  | 1216.5 |  |  | 1278 |  |  | 1134.5 |  |  | 1246.5 |  |  | 1189 |  |  | 1334 |  |  | 1242.5 |  |  | 1240.5 |  |  | 1341 |  |  | 1213 |  |  | 1280 |  |  | 1200.5 |  |  | 1236 |  |  | 1162 |  |  | 1274 |  |  | 1308.5 |  |  | 1234.5 |  |  | 1256 |  |  | 1290 |  |  | 1192 |  |  | 1228 |  |  | 1289 |  |  | 1189 |  |  | 1237 |  |  | 1171.5 |  |  | 1236.5 |  |  | 1186.5 |  |  | 1245 |  |  | 1189.5 |  |  | 1249 |  |  | 1153 |  |  | 1238.5 |  |  | 1164.5 |  |  | 1094 |  |  | 1236 |  |  | 1124.5 |  |  | 1205 |  |  | 1213 |  |  | 1169.5 |  |  | 1146.5 |  |  | 1252 |  |  | 1243 |  |  | 1327 |  |  | 1163.5 |  |  | 1140 |  |  | 1133 |  |  | 1229 |  |  | 1192 |  |  | 1325 |  |  | 1228.5 |  |  | 1297 |  |  | 1165 |  |  | 1108 |  |  | 1330.5 |  |  | 1285 |  |  | 1198.5 |  |  | 1167.5 |  |  | 1240 |  |  | 1192 |  |  | 1221.5 |  |  | 1160.5 |  |  | 1170.5 |  |  | 1225.5 |  |  | 1265.5 |  |  | 1290 |  |  | 1200 |  |  | 1296.5 |  |  | 1217.5 |  |  | 1224 |  |  | 1185 |  |  | 1245.5 |  |  | 1234 |  |  | 1234 |  |  | 1154 |  |  | 1258.5 |  |  | 1329 |  |  | 1145.5 |  |  | 1179 |  |  | 1255.5 |  |  | 1236.5 |  |  | 1332.5 |  |  | 1227 |  |  | 1205 |  |  | 1294.5 |  |  | 1201.5 |  |  | 1254 |  |  | 1230 |  |  | 1199.5 |  |  | 1216 |  |  | 1218.5 |  |  | 1201.5 |  |  | 1236 |  |  | 1204 |  |  | 1229.5 |  |  | 1292.5 |  |  | 1187 |  |  | 1200.5 |  |  | 1305.5 |  |  | 1159 |  |  | 1342 |  |  | 1331 |  |  | 1205.5 |  |  | 1256 |  |  | 1227 |  |  | 1235 |  |  | 1217 |  |  | 1279 |  |  | 1167 |  |  | 1309.5 |  |  | 1166.5 |  |  | 1212 |  |  | 1144 |  |  | 1224 |  |  | 1229.5 |  |  | 1225 |  |  | 1326 |  |  | 1168.5 |  |  | 1245.5 |  |  | 1242 |  |  | 1214.5 |  |  | 1241 |  |  | 1188 |  |  | 1252 |  |  | 1351.5 |  |  | 1340 |  |  | 1157.5 |  |  | 1170.5 |  |  | 1186 |  |  | 1286.5 |  |  | 1110.5 |  |  | 1140 |  |  | 1166 |  |  | 1346 |  |  | 1172.5 |  |  | 1156 |  |  | 1225.5 |  |  | 1206.5 |  |  | 1314 |  |  | 1184.5 |  |  | 1191 |  |  | 1275 |  |  | 1205 |  |  | 1164 |  |  | 1177 |  |  | 1296.5 |  |  | 1237 |  |  | 1276 |  |  | 1168 |  |  | 1297 |  |  | 1191.5 |  |  | 1284.5 |  |  | 1200 |  |  | 1201 |  |  | 1191 |  |  | 1166 |  |  | 1259 |  |  | 1255.5 |  |  | 1279 |  |  | 1217.5 |  |  | 1303 |  |  | 1144 |  |  | 1220 |  |  | 1203 |  |  | 1170.5 |  |  | 1171 |  |  | 1195.5 |  |  | 1148 |  |  | 1309 |  |  | 1274 |  |  | 1215.5 |  |  | 1212 |  |  | 1213 |  |  | 1140 |  |  | 1374 |  |  | 1316 |  |  | 1228.5 |  |  | 1270.5 |  |  | 1216 |  |  | 1212.5 |  |  | 1125 |  |  | 1140.5 |  |  | 1239.5 |  |  | 1190.5 |  |  | 1242.5 |  |  | 1133 |  |  | 1311 |  |  | 1144 |  |  | 1170 |  |  | 1263 |  |  | 1180 |  |  | 1209.5 |  |  | 1208.5 |  |  | 1241.5 |  |  | 1303 |  |  | 1246.5 |  |  | 1261.5 |  |  | 1265.5 |  |  | 1199.5 |  |  | 1199 |  |  | 1239.5 |  |  | 1217.5 |  |  | 1284 |  |  | 1245.5 |  |  | 1262.5 |  |  | 1236.5 |  |  | 1250 |  |  | 1286.5 |  |  | 1242 |  |  | 1226 |  |  | 1264.5 |  |  | 1220.5 |  |  | 1274 |  |  | 1269 |  |  | 1160.5 |  |  | 1174.5 |  |  | 1258.5 |  |  | 1264 |  |  | 1187 |  |  | 1171 |  |  | 1230.5 |  |  | 1282.5 |  |  | 1262 |  |  | 1247.5 |  |  | 1140 |  |  | 1219 |  |  | 1249.5 |  |  | 1115.5 |  |  | 1196 |  |  | 1222.5 |  |  | 1211 |  |  | 1161.5 |  |  | 1311.5 |  |  | 1250 |  |  | 1137.5 |  |  | 1236 |  |  | 1258.5 |  |  | 1232 |  |  | 1256 |  |  | 1271 |  |  | 1240.5 |  |  | 1133.5 |  |  | 1255 |  |  | 1159 |  |  | 1170 |  |  | 1244.5 |  |  | 1184.5 |  |  | 1263 |  |  | 1196.5 |  |  | 1211 |  |  | 1213.5 |  |  | 1234.5 |  |  | 1178 |  |  | 1218 |  |  | 1225 |  |  | 1234.5 |  |  | 1211 |  |  | 1306.5 |  |  | 1276 |  |  | 1215.5 |  |  | 1301 |  |  | 1125.5 |  |  | 1200 |  |  | 1195.5 |  |  | 1230.5 |  |  | 1215 |  |  | 1181 |  |  | 1257 |  |  | 1235 |  |  | 1257.5 |  |  | 1158 |  |  | 1185.5 |  |  | 1156 |  |  | 1249 |  |  | 1247 |  |  | 1267 |  |  | 1308 |  |  | 1206 |  |  | 1204 |  |  | 1277.5 |  |  | 1131 |  |  | 1320
45 |  | 1298.5 |  |  | 1316 |  |  | 1254.5 |  |  | 1292 |  |  | 1260.5 |  |  | 1237 |  |  | 1283 |  |  | 1336 |  |  | 1238.5 |  |  | 1288 |  |  | 1231 |  |  | 1380 |  |  | 1267 |  |  | 1320 |  |  | 1244.5 |  |  | 1307.5 |  |  | 1185 |  |  | 1336 |  |  | 1375 |  |  | 1162.5 |  |  | 1304 |  |  | 1305 |  |  | 1247 |  |  | 1275 |  |  | 1218.5 |  |  | 1366 |  |  | 1287 |  |  | 1234 |  |  | 1271 |  |  | 1236 |  |  | 1182 |  |  | 1283.5 |  |  | 1391.5 |  |  | 1224.5 |  |  | 1194 |  |  | 1200.5 |  |  | 1190.5 |  |  | 1305.5 |  |  | 1269 |  |  | 1243 |  |  | 1161.5 |  |  | 1199 |  |  | 1360.5 |  |  | 1293.5 |  |  | 1278.5 |  |  | 1330.5 |  |  | 1365.5 |  |  | 1227 |  |  | 1134 |  |  | 1170.5 |  |  | 1270 |  |  | 1193.5 |  |  | 1224.5 |  |  | 1300 |  |  | 1206 |  |  | 1221 |  |  | 1247 |  |  | 1323 |  |  | 1319 |  |  | 1241.5 |  |  | 1354.5 |  |  | 1289.5 |  |  | 1147 |  |  | 1310 |  |  | 1175 |  |  | 1204.5 |  |  | 1267 |  |  | 1305.5 |  |  | 1258.5 |  |  | 1343.5 |  |  | 1173 |  |  | 1278 |  |  | 1248 |  |  | 1216.5 |  |  | 1316.5 |  |  | 1253.5 |  |  | 1314.5 |  |  | 1295.5 |  |  | 1312.5 |  |  | 1271.5 |  |  | 1296.5 |  |  | 1211 |  |  | 1232 |  |  | 1265 |  |  | 1295.5 |  |  | 1311 |  |  | 1194.5 |  |  | 1211 |  |  | 1269 |  |  | 1306.5 |  |  | 1328.5 |  |  | 1239 |  |  | 1464 |  |  | 1241.5 |  |  | 1315 |  |  | 1207.5 |  |  | 1296.5 |  |  | 1263.5 |  |  | 1252.5 |  |  | 1164.5 |  |  | 1308 |  |  | 1247 |  |  | 1174 |  |  | 1359.5 |  |  | 1245.5 |  |  | 1283.5 |  |  | 1236.5 |  |  | 1280 |  |  | 1263 |  |  | 1238.5 |  |  | 1178 |  |  | 1297.5 |  |  | 1277 |  |  | 1289 |  |  | 1188.5 |  |  | 1275 |  |  | 1196 |  |  | 1247 |  |  | 1243 |  |  | 1336.5 |  |  | 1266.5 |  |  | 1183.5 |  |  | 1387 |  |  | 1196 |  |  | 1172 |  |  | 1219 |  |  | 1239.5 |  |  | 1252 |  |  | 1327.5 |  |  | 1279 |  |  | 1213 |  |  | 1305.5 |  |  | 1176.5 |  |  | 1165 |  |  | 1199.5 |  |  | 1211 |  |  | 1269 |  |  | 1290 |  |  | 1232 |  |  | 1234 |  |  | 1196 |  |  | 1159 |  |  | 1306 |  |  | 1207 |  |  | 1204.5 |  |  | 1206 |  |  | 1165 |  |  | 1245 |  |  | 1234 |  |  | 1179 |  |  | 1212 |  |  | 1263 |  |  | 1233.5 |  |  | 1289 |  |  | 1280.5 |  |  | 1341 |  |  | 1236 |  |  | 1324.5 |  |  | 1241 |  |  | 1405.5 |  |  | 1263 |  |  | 1170 |  |  | 1268.5 |  |  | 1222 |  |  | 1286.5 |  |  | 1195 |  |  | 1239 |  |  | 1229.5 |  |  | 1252.5 |  |  | 1283 |  |  | 1201.5 |  |  | 1209.5 |  |  | 1264 |  |  | 1279 |  |  | 1433.5 |  |  | 1247.5 |  |  | 1222.5 |  |  | 1252 |  |  | 1330 |  |  | 1192 |  |  | 1308 |  |  | 1314 |  |  | 1289.5 |  |  | 1240 |  |  | 1185.5 |  |  | 1266.5 |  |  | 1346 |  |  | 1335 |  |  | 1325.5 |  |  | 1180.5 |  |  | 1217 |  |  | 1274.5 |  |  | 1224.5 |  |  | 1282 |  |  | 1194 |  |  | 1247 |  |  | 1208.5 |  |  | 1338 |  |  | 1223.5 |  |  | 1244.5 |  |  | 1171 |  |  | 1250.5 |  |  | 1164 |  |  | 1300 |  |  | 1285 |  |  | 1259 |  |  | 1195 |  |  | 1324 |  |  | 1378 |  |  | 1311 |  |  | 1354 |  |  | 1223 |  |  | 1249.5 |  |  | 1370.5 |  |  | 1215 |  |  | 1174 |  |  | 1332 |  |  | 1314.5 |  |  | 1292.5 |  |  | 1362.5 |  |  | 1205 |  |  | 1300 |  |  | 1349.5 |  |  | 1223.5 |  |  | 1148.5 |  |  | 1349 |  |  | 1355 |  |  | 1248 |  |  | 1200 |  |  | 1228 |  |  | 1241.5 |  |  | 1231.5 |  |  | 1341 |  |  | 1320 |  |  | 1260 |  |  | 1310 |  |  | 1213 |  |  | 1214.5 |  |  | 1211 |  |  | 1341 |  |  | 1240 |  |  | 1235 |  |  | 1169.5 |  |  | 1385 |  |  | 1309 |  |  | 1277 |  |  | 1329 |  |  | 1299.5 |  |  | 1350 |  |  | 1225 |  |  | 1207 |  |  | 1324.5 |  |  | 1261.5 |  |  | 1302.5 |  |  | 1339 |  |  | 1275 |  |  | 1232 |  |  | 1331 |  |  | 1299 |  |  | 1225.5 |  |  | 1325 |  |  | 1215.5 |  |  | 1294.5 |  |  | 1300.5 |  |  | 1285 |  |  | 1323.5 |  |  | 1206 |  |  | 1215 |  |  | 1243.5 |  |  | 1291.5 |  |  | 1375 |  |  | 1394.5 |  |  | 1300.5 |  |  | 1247 |  |  | 1321 |  |  | 1276.5 |  |  | 1240.5 |  |  | 1273 |  |  | 1245.5 |  |  | 1288 |  |  | 1218 |  |  | 1244.5 |  |  | 1282 |  |  | 1228 |  |  | 1265.5 |  |  | 1224 |  |  | 1275.5 |  |  | 1236 |  |  | 1367 |  |  | 1251 |  |  | 1200 |  |  | 1346.5 |  |  | 1371 |  |  | 1311.5 |  |  | 1206.5 |  |  | 1300.5 |  |  | 1354 |  |  | 1384.5 |  |  | 1362 |  |  | 1286 |  |  | 1151.5 |  |  | 1261.5 |  |  | 1287 |  |  | 1236.5 |  |  | 1311 |  |  | 1251 |  |  | 1381.5 |  |  | 1274 |  |  | 1219.5 |  |  | 1262.5 |  |  | 1300.5 |  |  | 1316 |  |  | 1214 |  |  | 1255 |  |  | 1156.5 |  |  | 1220 |  |  | 1334.5 |  |  | 1289 |  |  | 1289 |  |  | 1214 |  |  | 1279 |  |  | 1312 |  |  | 1258 |  |  | 1221 |  |  | 1356 |  |  | 1277 |  |  | 1249.5 |  |  | 1254 |  |  | 1240 |  |  | 1426.5 |  |  | 1158.5 |  |  | 1318.5 |  |  | 1336.5 |  |  | 1259 |  |  | 1387 |  |  | 1161.5 |  |  | 1275.5 |  |  | 1349.5 |  |  | 1296 |  |  | 1256 |  |  | 1274 |  |  | 1255 |  |  | 1205 |  |  | 1232 |  |  | 1265 |  |  | 1242.5 |  |  | 1229.5 |  |  | 1293 |  |  | 1272.5 |  |  | 1310.5 |  |  | 1170 |  |  | 1281 |  |  | 1227 |  |  | 1264 |  |  | 1211.5 |  |  | 1170.5 |  |  | 1247.5 |  |  | 1240 |  |  | 1241.5 |  |  | 1262 |  |  | 1211 |  |  | 1273 |  |  | 1175.5 |  |  | 1300 |  |  | 1135 |  |  | 1268.5 |  |  | 1234 |  |  | 1278.5 |  |  | 1355 |  |  | 1279.5 |  |  | 1142 |  |  | 1262.5 |  |  | 1260.5 |  |  | 1324 |  |  | 1270 |  |  | 1162 |  |  | 1228 |  |  | 1198.5 |  |  | 1210 |  |  | 1296 |  |  | 1229.5 |  |  | 1324.5 |  |  | 1202.5 |  |  | 1253 |  |  | 1272.5 |  |  | 1233.5 |  |  | 1264.5 |  |  | 1330 |  |  | 1276 |  |  | 1209.5 |  |  | 1303 |  |  | 1333 |  |  | 1238.5 |  |  | 1244 |  |  | 1324 |  |  | 1243 |  |  | 1187 |  |  | 1188.5 |  |  | 1361.5 |  |  | 1179 |  |  | 1291 |  |  | 1276 |  |  | 1215 |  |  | 1222 |  |  | 1223.5 |  |  | 1307.5 |  |  | 1264 |  |  | 1410 |  |  | 1359 |  |  | 1145.5 |  |  | 1335.5 |  |  | 1259 |  |  | 1213 |  |  | 1204 |  |  | 1256.5 |  |  | 1336.5 |  |  | 1262 |  |  | 1209 |  |  | 1316 |  |  | 1279 |  |  | 1229 |  |  | 1331 |  |  | 1251 |  |  | 1350.5 |  |  | 1192 |  |  | 1388 |  |  | 1265 |  |  | 1304.5 |  |  | 1359 |  |  | 1141 |  |  | 1153 |  |  | 1275 |  |  | 1264 |  |  | 1256 |  |  | 1258 |  |  | 1215.5 |  |  | 1241.5 |  |  | 1229.5 |  |  | 1272 |  |  | 1269 |  |  | 1277.5 |  |  | 1181 |  |  | 1241.5 |  |  | 1214.5 |  |  | 1194 |  |  | 1214 |  |  | 1319.5 |  |  | 1268 |  |  | 1285 |  |  | 1302 |  |  | 1238 |  |  | 1236 |  |  | 1250 |  |  | 1251 |  |  | 1354.5 |  |  | 1241 |  |  | 1219 |  |  | 1337 |  |  | 1231 |  |  | 1315 |  |  | 1185 |  |  | 1416 |  |  | 1343 |  |  | 1260 |  |  | 1366.5 |  |  | 1244.5 |  |  | 1230.5 |  |  | 1271.5 |  |  | 1280 |  |  | 1202 |  |  | 1342.5 |  |  | 1253 |  |  | 1264 |  |  | 1250.5 |  |  | 1324.5 |  |  | 1303 |  |  | 1272.5 |  |  | 1230.5 |  |  | 1173 |  |  | 1321 |  |  | 1232 |  |  | 1265 |  |  | 1314.5 |  |  | 1241 |  |  | 1246.5 |  |  | 1183.5 |  |  | 1181 |  |  | 1245 |  |  | 1268.5 |  |  | 1253 |  |  | 1325.5 |  |  | 1213 |  |  | 1237.5 |  |  | 1212.5 |  |  | 1215.5 |  |  | 1286.5 |  |  | 1281.5 |  |  | 1227 |  |  | 1238 |  |  | 1378.5 |  |  | 1298 |  |  | 1221 |  |  | 1235 |  |  | 1285 |  |  | 1335.5 |  |  | 1144 |  |  | 1233 |  |  | 1328 |  |  | 1328.5 |  |  | 1283 |  |  | 1225 |  |  | 1294 |  |  | 1389.5 |  |  | 1239 |  |  | 1146 |  |  | 1258 |  |  | 1310 |  |  | 1473.5 |  |  | 1285 |  |  | 1198.5 |  |  | 1270 |  |  | 1295 |  |  | 1393.5 |  |  | 1318 |  |  | 1211 |  |  | 1176.5 |  |  | 1289 |  |  | 1224 |  |  | 1310 |  |  | 1313.5 |  |  | 1229.5 |  |  | 1269 |  |  | 1193 |  |  | 1260.5 |  |  | 1325.5 |  |  | 1207 |  |  | 1333 |  |  | 1361.5 |  |  | 1303.5 |  |  | 1203.5 |  |  | 1250.5 |  |  | 1292.5 |  |  | 1386 |  |  | 1309.5 |  |  | 1273 |  |  | 1265 |  |  | 1296 |  |  | 1289 |  |  | 1336.5 |  |  | 1265 |  |  | 1187 |  |  | 1225.5 |  |  | 1221.5 |  |  | 1176 |  |  | 1254.5 |  |  | 1271.5 |  |  | 1324 |  |  | 1240 |  |  | 1246 |  |  | 1257.5 |  |  | 1259 |  |  | 1241.5 |  |  | 1279 |  |  | 1340 |  |  | 1398.5 |  |  | 1235 |  |  | 1415 |  |  | 1218 |  |  | 1270 |  |  | 1296 |  |  | 1253 |  |  | 1260 |  |  | 1231 |  |  | 1214.5 |  |  | 1306.5 |  |  | 1304 |  |  | 1259.5 |  |  | 1138.5 |  |  | 1217 |  |  | 1161 |  |  | 1318 |  |  | 1324.5 |  |  | 1239.5 |  |  | 1224 |  |  | 1359 |  |  | 1202 |  |  | 1184 |  |  | 1263 |  |  | 1238 |  |  | 1401 |  |  | 1269.5 |  |  | 1274 |  |  | 1287 |  |  | 1370 |  |  | 1210 |  |  | 1190 |  |  | 1289.5 |  |  | 1411.5 |  |  | 1136.5 |  |  | 1212 |  |  | 1189 |  |  | 1146.5 |  |  | 1322.5 |  |  | 1288.5 |  |  | 1268 |  |  | 1294.5 |  |  | 1237.5 |  |  | 1234 |  |  | 1247.5 |  |  | 1315.5 |  |  | 1245 |  |  | 1181 |  |  | 1319 |  |  | 1279 |  |  | 1231 |  |  | 1165 |  |  | 1288 |  |  | 1365 |  |  | 1256 |  |  | 1216 |  |  | 1318.5 |  |  | 1253 |  |  | 1301 |  |  | 1158 |  |  | 1233.5 |  |  | 1329 |  |  | 1269.5 |  |  | 1306 |  |  | 1252 |  |  | 1265 |  |  | 1279 |  |  | 1325.5 |  |  | 1252 |  |  | 1166 |  |  | 1384.5 |  |  | 1297 |  |  | 1218 |  |  | 1211.5 |  |  | 1247.5 |  |  | 1345 |  |  | 1195.5 |  |  | 1317 |  |  | 1250.5 |  |  | 1342 |  |  | 1277 |  |  | 1247.5 |  |  | 1388.5 |  |  | 1260 |  |  | 1312 |  |  | 1285 |  |  | 1315 |  |  | 1163 |  |  | 1313 |  |  | 1143 |  |  | 1222 |  |  | 1385.5 |  |  | 1172 |  |  | 1362.5 |  |  | 1258 |  |  | 1282.5 |  |  | 1202.5 |  |  | 1239 |  |  | 1351 |  |  | 1253.5 |  |  | 1294 |  |  | 1274 |  |  | 1293 |  |  | 1246.5 |  |  | 1344 |  |  | 1150.5 |  |  | 1208 |  |  | 1246 |  |  | 1264 |  |  | 1313 |  |  | 1351.5 |  |  | 1199 |  |  | 1257 |  |  | 1271 |  |  | 1196.5 |  |  | 1354 |  |  | 1305 |  |  | 1313 |  |  | 1235 |  |  | 1270.5 |  |  | 1208.5 |  |  | 1284 |  |  | 1287 |  |  | 1310 |  |  | 1316.5 |  |  | 1272 |  |  | 1247 |  |  | 1189 |  |  | 1398.5 |  |  | 1250.5 |  |  | 1332.5 |  |  | 1249 |  |  | 1317 |  |  | 1228 |  |  | 1243.5 |  |  | 1276 |  |  | 1253.5 |  |  | 1156 |  |  | 1211 |  |  | 1269 |  |  | 1215.5 |  |  | 1283.5 |  |  | 1276 |  |  | 1196 |  |  | 1298.5 |  |  | 1239 |  |  | 1320 |  |  | 1311.5 |  |  | 1258 |  |  | 1228 |  |  | 1344.5 |  |  | 1205 |  |  | 1314 |  |  | 1264.5 |  |  | 1328 |  |  | 1240.5 |  |  | 1302 |  |  | 1181.5 |  |  | 1285.5 |  |  | 1213 |  |  | 1360 |  |  | 1268.5 |  |  | 1287.5 |  |  | 1367 |  |  | 1239 |  |  | 1327 |  |  | 1224.5 |  |  | 1260 |  |  | 1201 |  |  | 1300 |  |  | 1347.5 |  |  | 1281.5 |  |  | 1303 |  |  | 1329 |  |  | 1213 |  |  | 1243 |  |  | 1318 |  |  | 1218 |  |  | 1263 |  |  | 1195.5 |  |  | 1260.5 |  |  | 1233.5 |  |  | 1274 |  |  | 1210.5 |  |  | 1288 |  |  | 1192 |  |  | 1277.5 |  |  | 1190.5 |  |  | 1120 |  |  | 1265 |  |  | 1163.5 |  |  | 1229 |  |  | 1260 |  |  | 1208.5 |  |  | 1193.5 |  |  | 1281 |  |  | 1290 |  |  | 1353 |  |  | 1192.5 |  |  | 1187 |  |  | 1157 |  |  | 1276 |  |  | 1239 |  |  | 1364 |  |  | 1267.5 |  |  | 1318 |  |  | 1204 |  |  | 1123 |  |  | 1359.5 |  |  | 1309 |  |  | 1237.5 |  |  | 1188.5 |  |  | 1255 |  |  | 1216 |  |  | 1242.5 |  |  | 1199.5 |  |  | 1194.5 |  |  | 1240.5 |  |  | 1304.5 |  |  | 1329 |  |  | 1215 |  |  | 1311.5 |  |  | 1256.5 |  |  | 1263 |  |  | 1200 |  |  | 1274.5 |  |  | 1281 |  |  | 1258 |  |  | 1169 |  |  | 1297.5 |  |  | 1358 |  |  | 1166.5 |  |  | 1200 |  |  | 1281.5 |  |  | 1275.5 |  |  | 1379.5 |  |  | 1256 |  |  | 1231 |  |  | 1315.5 |  |  | 1240.5 |  |  | 1283 |  |  | 1277 |  |  | 1246.5 |  |  | 1245 |  |  | 1244.5 |  |  | 1240.5 |  |  | 1275 |  |  | 1251 |  |  | 1250.5 |  |  | 1331.5 |  |  | 1234 |  |  | 1224.5 |  |  | 1334.5 |  |  | 1198 |  |  | 1357 |  |  | 1378 |  |  | 1244.5 |  |  | 1295 |  |  | 1248 |  |  | 1261 |  |  | 1238 |  |  | 1308 |  |  | 1191 |  |  | 1348.5 |  |  | 1205.5 |  |  | 1236 |  |  | 1168 |  |  | 1245 |  |  | 1250.5 |  |  | 1251 |  |  | 1365 |  |  | 1207.5 |  |  | 1271.5 |  |  | 1289 |  |  | 1229.5 |  |  | 1262 |  |  | 1203 |  |  | 1299 |  |  | 1380.5 |  |  | 1379 |  |  | 1186.5 |  |  | 1199.5 |  |  | 1212 |  |  | 1333.5 |  |  | 1149.5 |  |  | 1179 |  |  | 1205 |  |  | 1393 |  |  | 1211.5 |  |  | 1180 |  |  | 1272.5 |  |  | 1230.5 |  |  | 1343 |  |  | 1213.5 |  |  | 1215 |  |  | 1290 |  |  | 1252 |  |  | 1211 |  |  | 1192 |  |  | 1343.5 |  |  | 1284 |  |  | 1297 |  |  | 1207 |  |  | 1321 |  |  | 1215.5 |  |  | 1305.5 |  |  | 1226 |  |  | 1240 |  |  | 1230 |  |  | 1190 |  |  | 1298 |  |  | 1281.5 |  |  | 1300 |  |  | 1238.5 |  |  | 1327 |  |  | 1159 |  |  | 1246 |  |  | 1227 |  |  | 1209.5 |  |  | 1195 |  |  | 1242.5 |  |  | 1195 |  |  | 1335 |  |  | 1313 |  |  | 1236.5 |  |  | 1238 |  |  | 1234 |  |  | 1155 |  |  | 1389 |  |  | 1331 |  |  | 1275.5 |  |  | 1291.5 |  |  | 1263 |  |  | 1233.5 |  |  | 1172 |  |  | 1155.5 |  |  | 1278.5 |  |  | 1229.5 |  |  | 1257.5 |  |  | 1162 |  |  | 1358 |  |  | 1173 |  |  | 1185 |  |  | 1302 |  |  | 1227 |  |  | 1238.5 |  |  | 1223.5 |  |  | 1267.5 |  |  | 1350 |  |  | 1275.5 |  |  | 1287.5 |  |  | 1304.5 |  |  | 1220.5 |  |  | 1223 |  |  | 1263.5 |  |  | 1256.5 |  |  | 1308 |  |  | 1260.5 |  |  | 1286.5 |  |  | 1265.5 |  |  | 1289 |  |  | 1325.5 |  |  | 1266 |  |  | 1252 |  |  | 1290.5 |  |  | 1259.5 |  |  | 1313 |  |  | 1290 |  |  | 1175.5 |  |  | 1221.5 |  |  | 1287.5 |  |  | 1290 |  |  | 1216 |  |  | 1192 |  |  | 1269.5 |  |  | 1306.5 |  |  | 1291 |  |  | 1271.5 |  |  | 1169 |  |  | 1245 |  |  | 1296.5 |  |  | 1139.5 |  |  | 1243 |  |  | 1269.5 |  |  | 1240 |  |  | 1187.5 |  |  | 1350.5 |  |  | 1289 |  |  | 1176.5 |  |  | 1262 |  |  | 1297.5 |  |  | 1258 |  |  | 1277 |  |  | 1318 |  |  | 1264.5 |  |  | 1154.5 |  |  | 1294 |  |  | 1183 |  |  | 1217 |  |  | 1283.5 |  |  | 1213.5 |  |  | 1302 |  |  | 1235.5 |  |  | 1226 |  |  | 1228.5 |  |  | 1273.5 |  |  | 1217 |  |  | 1239 |  |  | 1264 |  |  | 1263.5 |  |  | 1258 |  |  | 1335.5 |  |  | 1297 |  |  | 1241.5 |  |  | 1348 |  |  | 1146.5 |  |  | 1215 |  |  | 1234.5 |  |  | 1256.5 |  |  | 1236 |  |  | 1220 |  |  | 1283 |  |  | 1282 |  |  | 1296.5 |  |  | 1197 |  |  | 1209.5 |  |  | 1182 |  |  | 1270 |  |  | 1268 |  |  | 1314 |  |  | 1334 |  |  | 1245 |  |  | 1243 |  |  | 1298.5 |  |  | 1178 |  |  | 1346
46 |  | 1337.5 |  |  | 1355 |  |  | 1293.5 |  |  | 1316 |  |  | 1286.5 |  |  | 1261 |  |  | 1304 |  |  | 1351 |  |  | 1277.5 |  |  | 1303 |  |  | 1246 |  |  | 1395 |  |  | 1291 |  |  | 1367 |  |  | 1273.5 |  |  | 1322.5 |  |  | 1224 |  |  | 1362 |  |  | 1390 |  |  | 1186.5 |  |  | 1351 |  |  | 1352 |  |  | 1268 |  |  | 1314 |  |  | 1247.5 |  |  | 1413 |  |  | 1326 |  |  | 1258 |  |  | 1310 |  |  | 1265 |  |  | 1206 |  |  | 1309.5 |  |  | 1430.5 |  |  | 1271.5 |  |  | 1209 |  |  | 1229.5 |  |  | 1229.5 |  |  | 1326.5 |  |  | 1316 |  |  | 1269 |  |  | 1185.5 |  |  | 1214 |  |  | 1384.5 |  |  | 1332.5 |  |  | 1317.5 |  |  | 1377.5 |  |  | 1386.5 |  |  | 1266 |  |  | 1149 |  |  | 1194.5 |  |  | 1296 |  |  | 1208.5 |  |  | 1239.5 |  |  | 1324 |  |  | 1230 |  |  | 1260 |  |  | 1276 |  |  | 1362 |  |  | 1334 |  |  | 1280.5 |  |  | 1383.5 |  |  | 1318.5 |  |  | 1186 |  |  | 1334 |  |  | 1201 |  |  | 1225.5 |  |  | 1293 |  |  | 1334.5 |  |  | 1279.5 |  |  | 1390.5 |  |  | 1220 |  |  | 1307 |  |  | 1287 |  |  | 1255.5 |  |  | 1363.5 |  |  | 1282.5 |  |  | 1340.5 |  |  | 1324.5 |  |  | 1338.5 |  |  | 1295.5 |  |  | 1322.5 |  |  | 1232 |  |  | 1279 |  |  | 1291 |  |  | 1342.5 |  |  | 1340 |  |  | 1218.5 |  |  | 1250 |  |  | 1298 |  |  | 1332.5 |  |  | 1367.5 |  |  | 1286 |  |  | 1479 |  |  | 1265.5 |  |  | 1354 |  |  | 1233.5 |  |  | 1325.5 |  |  | 1284.5 |  |  | 1273.5 |  |  | 1203.5 |  |  | 1332 |  |  | 1271 |  |  | 1189 |  |  | 1374.5 |  |  | 1271.5 |  |  | 1298.5 |  |  | 1283.5 |  |  | 1319 |  |  | 1289 |  |  | 1277.5 |  |  | 1202 |  |  | 1312.5 |  |  | 1316 |  |  | 1318 |  |  | 1203.5 |  |  | 1314 |  |  | 1225 |  |  | 1268 |  |  | 1272 |  |  | 1362.5 |  |  | 1292.5 |  |  | 1230.5 |  |  | 1426 |  |  | 1217 |  |  | 1201 |  |  | 1234 |  |  | 1278.5 |  |  | 1276 |  |  | 1366.5 |  |  | 1300 |  |  | 1252 |  |  | 1326.5 |  |  | 1202.5 |  |  | 1212 |  |  | 1246.5 |  |  | 1237 |  |  | 1295 |  |  | 1314 |  |  | 1271 |  |  | 1273 |  |  | 1235 |  |  | 1198 |  |  | 1327 |  |  | 1231 |  |  | 1219.5 |  |  | 1245 |  |  | 1189 |  |  | 1292 |  |  | 1258 |  |  | 1203 |  |  | 1259 |  |  | 1284 |  |  | 1259.5 |  |  | 1315 |  |  | 1319.5 |  |  | 1362 |  |  | 1257 |  |  | 1363.5 |  |  | 1265 |  |  | 1434.5 |  |  | 1287 |  |  | 1185 |  |  | 1292.5 |  |  | 1243 |  |  | 1333.5 |  |  | 1242 |  |  | 1265 |  |  | 1276.5 |  |  | 1299.5 |  |  | 1322 |  |  | 1240.5 |  |  | 1256.5 |  |  | 1303 |  |  | 1308 |  |  | 1448.5 |  |  | 1271.5 |  |  | 1243.5 |  |  | 1281 |  |  | 1354 |  |  | 1231 |  |  | 1355 |  |  | 1335 |  |  | 1328.5 |  |  | 1264 |  |  | 1209.5 |  |  | 1295.5 |  |  | 1372 |  |  | 1364 |  |  | 1364.5 |  |  | 1219.5 |  |  | 1241 |  |  | 1313.5 |  |  | 1250.5 |  |  | 1321 |  |  | 1223 |  |  | 1286 |  |  | 1247.5 |  |  | 1385 |  |  | 1270.5 |  |  | 1283.5 |  |  | 1210 |  |  | 1279.5 |  |  | 1193 |  |  | 1315 |  |  | 1300 |  |  | 1280 |  |  | 1216 |  |  | 1363 |  |  | 1399 |  |  | 1335 |  |  | 1383 |  |  | 1244 |  |  | 1275.5 |  |  | 1385.5 |  |  | 1262 |  |  | 1203 |  |  | 1361 |  |  | 1335.5 |  |  | 1339.5 |  |  | 1383.5 |  |  | 1252 |  |  | 1321 |  |  | 1364.5 |  |  | 1252.5 |  |  | 1177.5 |  |  | 1370 |  |  | 1376 |  |  | 1274 |  |  | 1247 |  |  | 1275 |  |  | 1262.5 |  |  | 1278.5 |  |  | 1380 |  |  | 1349 |  |  | 1275 |  |  | 1349 |  |  | 1252 |  |  | 1253.5 |  |  | 1250 |  |  | 1367 |  |  | 1269 |  |  | 1264 |  |  | 1216.5 |  |  | 1424 |  |  | 1338 |  |  | 1301 |  |  | 1350 |  |  | 1328.5 |  |  | 1397 |  |  | 1264 |  |  | 1233 |  |  | 1348.5 |  |  | 1300.5 |  |  | 1317.5 |  |  | 1386 |  |  | 1296 |  |  | 1253 |  |  | 1357 |  |  | 1338 |  |  | 1240.5 |  |  | 1351 |  |  | 1236.5 |  |  | 1341.5 |  |  | 1339.5 |  |  | 1300 |  |  | 1370.5 |  |  | 1221 |  |  | 1230 |  |  | 1269.5 |  |  | 1315.5 |  |  | 1396 |  |  | 1420.5 |  |  | 1321.5 |  |  | 1276 |  |  | 1368 |  |  | 1291.5 |  |  | 1264.5 |  |  | 1320 |  |  | 1284.5 |  |  | 1317 |  |  | 1242 |  |  | 1265.5 |  |  | 1308 |  |  | 1252 |  |  | 1280.5 |  |  | 1245 |  |  | 1322.5 |  |  | 1275 |  |  | 1406 |  |  | 1275 |  |  | 1221 |  |  | 1375.5 |  |  | 1410 |  |  | 1340.5 |  |  | 1227.5 |  |  | 1321.5 |  |  | 1393 |  |  | 1423.5 |  |  | 1401 |  |  | 1312 |  |  | 1190.5 |  |  | 1300.5 |  |  | 1316 |  |  | 1275.5 |  |  | 1335 |  |  | 1272 |  |  | 1428.5 |  |  | 1313 |  |  | 1258.5 |  |  | 1309.5 |  |  | 1339.5 |  |  | 1340 |  |  | 1229 |  |  | 1279 |  |  | 1185.5 |  |  | 1244 |  |  | 1363.5 |  |  | 1328 |  |  | 1313 |  |  | 1240 |  |  | 1300 |  |  | 1338 |  |  | 1305 |  |  | 1247 |  |  | 1403 |  |  | 1324 |  |  | 1288.5 |  |  | 1301 |  |  | 1287 |  |  | 1455.5 |  |  | 1197.5 |  |  | 1333.5 |  |  | 1383.5 |  |  | 1298 |  |  | 1426 |  |  | 1200.5 |  |  | 1290.5 |  |  | 1373.5 |  |  | 1322 |  |  | 1295 |  |  | 1313 |  |  | 1276 |  |  | 1220 |  |  | 1258 |  |  | 1291 |  |  | 1281.5 |  |  | 1255.5 |  |  | 1317 |  |  | 1298.5 |  |  | 1349.5 |  |  | 1217 |  |  | 1328 |  |  | 1253 |  |  | 1290 |  |  | 1235.5 |  |  | 1209.5 |  |  | 1286.5 |  |  | 1287 |  |  | 1256.5 |  |  | 1283 |  |  | 1250 |  |  | 1299 |  |  | 1201.5 |  |  | 1339 |  |  | 1182 |  |  | 1289.5 |  |  | 1249 |  |  | 1299.5 |  |  | 1384 |  |  | 1300.5 |  |  | 1163 |  |  | 1283.5 |  |  | 1299.5 |  |  | 1353 |  |  | 1317 |  |  | 1201 |  |  | 1267 |  |  | 1219.5 |  |  | 1257 |  |  | 1335 |  |  | 1250.5 |  |  | 1371.5 |  |  | 1249.5 |  |  | 1274 |  |  | 1311.5 |  |  | 1257.5 |  |  | 1279.5 |  |  | 1356 |  |  | 1323 |  |  | 1233.5 |  |  | 1329 |  |  | 1380 |  |  | 1277.5 |  |  | 1283 |  |  | 1363 |  |  | 1282 |  |  | 1208 |  |  | 1203.5 |  |  | 1376.5 |  |  | 1218 |  |  | 1338 |  |  | 1323 |  |  | 1254 |  |  | 1237 |  |  | 1247.5 |  |  | 1322.5 |  |  | 1288 |  |  | 1439 |  |  | 1398 |  |  | 1169.5 |  |  | 1356.5 |  |  | 1283 |  |  | 1252 |  |  | 1230 |  |  | 1303.5 |  |  | 1383.5 |  |  | 1277 |  |  | 1238 |  |  | 1345 |  |  | 1326 |  |  | 1250 |  |  | 1370 |  |  | 1266 |  |  | 1374.5 |  |  | 1207 |  |  | 1417 |  |  | 1289 |  |  | 1325.5 |  |  | 1385 |  |  | 1165 |  |  | 1192 |  |  | 1299 |  |  | 1279 |  |  | 1271 |  |  | 1287 |  |  | 1254.5 |  |  | 1288.5 |  |  | 1268.5 |  |  | 1311 |  |  | 1290 |  |  | 1292.5 |  |  | 1202 |  |  | 1262.5 |  |  | 1240.5 |  |  | 1220 |  |  | 1261 |  |  | 1366.5 |  |  | 1283 |  |  | 1314 |  |  | 1349 |  |  | 1277 |  |  | 1275 |  |  | 1265 |  |  | 1272 |  |  | 1393.5 |  |  | 1288 |  |  | 1266 |  |  | 1384 |  |  | 1257 |  |  | 1344 |  |  | 1224 |  |  | 1455 |  |  | 1364 |  |  | 1299 |  |  | 1413.5 |  |  | 1283.5 |  |  | 1245.5 |  |  | 1295.5 |  |  | 1304 |  |  | 1217 |  |  | 1389.5 |  |  | 1279 |  |  | 1285 |  |  | 1276.5 |  |  | 1363.5 |  |  | 1342 |  |  | 1287.5 |  |  | 1254.5 |  |  | 1202 |  |  | 1368 |  |  | 1271 |  |  | 1294 |  |  | 1335.5 |  |  | 1256 |  |  | 1285.5 |  |  | 1207.5 |  |  | 1205 |  |  | 1266 |  |  | 1307.5 |  |  | 1277 |  |  | 1340.5 |  |  | 1234 |  |  | 1263.5 |  |  | 1251.5 |  |  | 1239.5 |  |  | 1333.5 |  |  | 1307.5 |  |  | 1251 |  |  | 1259 |  |  | 1399.5 |  |  | 1322 |  |  | 1260 |  |  | 1259 |  |  | 1324 |  |  | 1350.5 |  |  | 1165 |  |  | 1257 |  |  | 1349 |  |  | 1352.5 |  |  | 1312 |  |  | 1240 |  |  | 1333 |  |  | 1436.5 |  |  | 1265 |  |  | 1172 |  |  | 1284 |  |  | 1336 |  |  | 1520.5 |  |  | 1309 |  |  | 1245.5 |  |  | 1285 |  |  | 1321 |  |  | 1432.5 |  |  | 1333 |  |  | 1237 |  |  | 1197.5 |  |  | 1328 |  |  | 1263 |  |  | 1334 |  |  | 1352.5 |  |  | 1276.5 |  |  | 1298 |  |  | 1232 |  |  | 1307.5 |  |  | 1349.5 |  |  | 1231 |  |  | 1359 |  |  | 1408.5 |  |  | 1332.5 |  |  | 1227.5 |  |  | 1289.5 |  |  | 1313.5 |  |  | 1433 |  |  | 1324.5 |  |  | 1288 |  |  | 1294 |  |  | 1343 |  |  | 1310 |  |  | 1365.5 |  |  | 1312 |  |  | 1213 |  |  | 1264.5 |  |  | 1247.5 |  |  | 1223 |  |  | 1293.5 |  |  | 1292.5 |  |  | 1363 |  |  | 1279 |  |  | 1285 |  |  | 1304.5 |  |  | 1288 |  |  | 1288.5 |  |  | 1326 |  |  | 1364 |  |  | 1437.5 |  |  | 1256 |  |  | 1430 |  |  | 1265 |  |  | 1309 |  |  | 1335 |  |  | 1292 |  |  | 1281 |  |  | 1278 |  |  | 1229.5 |  |  | 1345.5 |  |  | 1343 |  |  | 1274.5 |  |  | 1167.5 |  |  | 1243 |  |  | 1187 |  |  | 1342 |  |  | 1363.5 |  |  | 1265.5 |  |  | 1263 |  |  | 1388 |  |  | 1223 |  |  | 1199 |  |  | 1287 |  |  | 1264 |  |  | 1440 |  |  | 1316.5 |  |  | 1321 |  |  | 1326 |  |  | 1409 |  |  | 1257 |  |  | 1205 |  |  | 1310.5 |  |  | 1426.5 |  |  | 1162.5 |  |  | 1233 |  |  | 1236 |  |  | 1185.5 |  |  | 1361.5 |  |  | 1327.5 |  |  | 1307 |  |  | 1323.5 |  |  | 1258.5 |  |  | 1263 |  |  | 1276.5 |  |  | 1354.5 |  |  | 1271 |  |  | 1220 |  |  | 1334 |  |  | 1318 |  |  | 1257 |  |  | 1180 |  |  | 1317 |  |  | 1389 |  |  | 1295 |  |  | 1240 |  |  | 1357.5 |  |  | 1268 |  |  | 1322 |  |  | 1179 |  |  | 1257.5 |  |  | 1344 |  |  | 1295.5 |  |  | 1353 |  |  | 1291 |  |  | 1289 |  |  | 1318 |  |  | 1364.5 |  |  | 1291 |  |  | 1213 |  |  | 1399.5 |  |  | 1312 |  |  | 1242 |  |  | 1250.5 |  |  | 1273.5 |  |  | 1366 |  |  | 1216.5 |  |  | 1356 |  |  | 1271.5 |  |  | 1371 |  |  | 1316 |  |  | 1294.5 |  |  | 1412.5 |  |  | 1281 |  |  | 1341 |  |  | 1324 |  |  | 1354 |  |  | 1210 |  |  | 1352 |  |  | 1158 |  |  | 1261 |  |  | 1409.5 |  |  | 1198 |  |  | 1391.5 |  |  | 1284 |  |  | 1329.5 |  |  | 1241.5 |  |  | 1260 |  |  | 1372 |  |  | 1282.5 |  |  | 1323 |  |  | 1300 |  |  | 1314 |  |  | 1272.5 |  |  | 1383 |  |  | 1165.5 |  |  | 1232 |  |  | 1270 |  |  | 1303 |  |  | 1339 |  |  | 1398.5 |  |  | 1228 |  |  | 1278 |  |  | 1292 |  |  | 1243.5 |  |  | 1393 |  |  | 1320 |  |  | 1337 |  |  | 1274 |  |  | 1285.5 |  |  | 1229.5 |  |  | 1313 |  |  | 1326 |  |  | 1325 |  |  | 1337.5 |  |  | 1319 |  |  | 1276 |  |  | 1204 |  |  | 1413.5 |  |  | 1297.5 |  |  | 1371.5 |  |  | 1278 |  |  | 1364 |  |  | 1254 |  |  | 1264.5 |  |  | 1323 |  |  | 1274.5 |  |  | 1171 |  |  | 1240 |  |  | 1316 |  |  | 1239.5 |  |  | 1309.5 |  |  | 1323 |  |  | 1235 |  |  | 1337.5 |  |  | 1286 |  |  | 1349 |  |  | 1350.5 |  |  | 1279 |  |  | 1267 |  |  | 1370.5 |  |  | 1244 |  |  | 1335 |  |  | 1279.5 |  |  | 1367 |  |  | 1255.5 |  |  | 1317 |  |  | 1220.5 |  |  | 1324.5 |  |  | 1228 |  |  | 1375 |  |  | 1307.5 |  |  | 1311.5 |  |  | 1406 |  |  | 1278 |  |  | 1374 |  |  | 1263.5 |  |  | 1299 |  |  | 1216 |  |  | 1339 |  |  | 1376.5 |  |  | 1320.5 |  |  | 1329 |  |  | 1344 |  |  | 1242 |  |  | 1267 |  |  | 1357 |  |  | 1247 |  |  | 1292 |  |  | 1234.5 |  |  | 1281.5 |  |  | 1254.5 |  |  | 1300 |  |  | 1249.5 |  |  | 1312 |  |  | 1231 |  |  | 1303.5 |  |  | 1229.5 |  |  | 1141 |  |  | 1291 |  |  | 1210.5 |  |  | 1250 |  |  | 1299 |  |  | 1234.5 |  |  | 1240.5 |  |  | 1320 |  |  | 1311 |  |  | 1382 |  |  | 1239.5 |  |  | 1226 |  |  | 1186 |  |  | 1291 |  |  | 1286 |  |  | 1411 |  |  | 1282.5 |  |  | 1365 |  |  | 1243 |  |  | 1144 |  |  | 1398.5 |  |  | 1333 |  |  | 1258.5 |  |  | 1203.5 |  |  | 1284 |  |  | 1255 |  |  | 1266.5 |  |  | 1238.5 |  |  | 1233.5 |  |  | 1287.5 |  |  | 1343.5 |  |  | 1344 |  |  | 1254 |  |  | 1350.5 |  |  | 1295.5 |  |  | 1302 |  |  | 1224 |  |  | 1295.5 |  |  | 1320 |  |  | 1284 |  |  | 1208 |  |  | 1312.5 |  |  | 1397 |  |  | 1213.5 |  |  | 1224 |  |  | 1296.5 |  |  | 1322.5 |  |  | 1418.5 |  |  | 1271 |  |  | 1255 |  |  | 1354.5 |  |  | 1261.5 |  |  | 1322 |  |  | 1301 |  |  | 1285.5 |  |  | 1269 |  |  | 1291.5 |  |  | 1266.5 |  |  | 1314 |  |  | 1272 |  |  | 1271.5 |  |  | 1370.5 |  |  | 1258 |  |  | 1245.5 |  |  | 1349.5 |  |  | 1237 |  |  | 1378 |  |  | 1407 |  |  | 1291.5 |  |  | 1324 |  |  | 1277 |  |  | 1282 |  |  | 1259 |  |  | 1332 |  |  | 1238 |  |  | 1372.5 |  |  | 1226.5 |  |  | 1251 |  |  | 1207 |  |  | 1274 |  |  | 1276.5 |  |  | 1290 |  |  | 1394 |  |  | 1236.5 |  |  | 1295.5 |  |  | 1315 |  |  | 1250.5 |  |  | 1288 |  |  | 1242 |  |  | 1338 |  |  | 1419.5 |  |  | 1400 |  |  | 1212.5 |  |  | 1246.5 |  |  | 1238 |  |  | 1354.5 |  |  | 1164.5 |  |  | 1218 |  |  | 1229 |  |  | 1422 |  |  | 1232.5 |  |  | 1204 |  |  | 1301.5 |  |  | 1269.5 |  |  | 1372 |  |  | 1234.5 |  |  | 1236 |  |  | 1305 |  |  | 1281 |  |  | 1232 |  |  | 1239 |  |  | 1364.5 |  |  | 1310 |  |  | 1326 |  |  | 1236 |  |  | 1368 |  |  | 1239.5 |  |  | 1344.5 |  |  | 1255 |  |  | 1287 |  |  | 1256 |  |  | 1229 |  |  | 1322 |  |  | 1328.5 |  |  | 1339 |  |  | 1277.5 |  |  | 1374 |  |  | 1198 |  |  | 1285 |  |  | 1266 |  |  | 1248.5 |  |  | 1234 |  |  | 1263.5 |  |  | 1221 |  |  | 1374 |  |  | 1337 |  |  | 1251.5 |  |  | 1264 |  |  | 1263 |  |  | 1179 |  |  | 1436 |  |  | 1370 |  |  | 1290.5 |  |  | 1315.5 |  |  | 1292 |  |  | 1254.5 |  |  | 1187 |  |  | 1179.5 |  |  | 1299.5 |  |  | 1268.5 |  |  | 1304.5 |  |  | 1191 |  |  | 1373 |  |  | 1220 |  |  | 1232 |  |  | 1317 |  |  | 1266 |  |  | 1253.5 |  |  | 1262.5 |  |  | 1282.5 |  |  | 1376 |  |  | 1314.5 |  |  | 1326.5 |  |  | 1333.5 |  |  | 1267.5 |  |  | 1249 |  |  | 1284.5 |  |  | 1271.5 |  |  | 1332 |  |  | 1275.5 |  |  | 1307.5 |  |  | 1294.5 |  |  | 1328 |  |  | 1340.5 |  |  | 1281 |  |  | 1273 |  |  | 1314.5 |  |  | 1283.5 |  |  | 1334 |  |  | 1329 |  |  | 1204.5 |  |  | 1242.5 |  |  | 1311.5 |  |  | 1314 |  |  | 1255 |  |  | 1231 |  |  | 1316.5 |  |  | 1330.5 |  |  | 1315 |  |  | 1295.5 |  |  | 1193 |  |  | 1292 |  |  | 1343.5 |  |  | 1154.5 |  |  | 1258 |  |  | 1298.5 |  |  | 1269 |  |  | 1213.5 |  |  | 1371.5 |  |  | 1336 |  |  | 1215.5 |  |  | 1301 |  |  | 1318.5 |  |  | 1287 |  |  | 1303 |  |  | 1357 |  |  | 1279.5 |  |  | 1201.5 |  |  | 1323 |  |  | 1222 |  |  | 1246 |  |  | 1309.5 |  |  | 1252.5 |  |  | 1317 |  |  | 1264.5 |  |  | 1250 |  |  | 1243.5 |  |  | 1288.5 |  |  | 1246 |  |  | 1254 |  |  | 1290 |  |  | 1302.5 |  |  | 1279 |  |  | 1374.5 |  |  | 1321 |  |  | 1267.5 |  |  | 1387 |  |  | 1167.5 |  |  | 1262 |  |  | 1249.5 |  |  | 1280.5 |  |  | 1275 |  |  | 1249 |  |  | 1312 |  |  | 1297 |  |  | 1320.5 |  |  | 1226 |  |  | 1248.5 |  |  | 1211 |  |  | 1294 |  |  | 1283 |  |  | 1353 |  |  | 1381 |  |  | 1269 |  |  | 1290 |  |  | 1337.5 |  |  | 1217 |  |  | 1361
47 |  | 1376.5 |  |  | 1370 |  |  | 1319.5 |  |  | 1340 |  |  | 1315.5 |  |  | 1308 |  |  | 1333 |  |  | 1398 |  |  | 1298.5 |  |  | 1332 |  |  | 1270 |  |  | 1434 |  |  | 1315 |  |  | 1393 |  |  | 1288.5 |  |  | 1351.5 |  |  | 1271 |  |  | 1386 |  |  | 1419 |  |  | 1225.5 |  |  | 1390 |  |  | 1381 |  |  | 1315 |  |  | 1340 |  |  | 1268.5 |  |  | 1437 |  |  | 1365 |  |  | 1273 |  |  | 1349 |  |  | 1289 |  |  | 1245 |  |  | 1348.5 |  |  | 1459.5 |  |  | 1295.5 |  |  | 1224 |  |  | 1253.5 |  |  | 1258.5 |  |  | 1350.5 |  |  | 1331 |  |  | 1290 |  |  | 1224.5 |  |  | 1253 |  |  | 1423.5 |  |  | 1347.5 |  |  | 1364.5 |  |  | 1424.5 |  |  | 1415.5 |  |  | 1305 |  |  | 1196 |  |  | 1241.5 |  |  | 1322 |  |  | 1234.5 |  |  | 1286.5 |  |  | 1353 |  |  | 1269 |  |  | 1299 |  |  | 1300 |  |  | 1386 |  |  | 1373 |  |  | 1295.5 |  |  | 1404.5 |  |  | 1365.5 |  |  | 1201 |  |  | 1355 |  |  | 1240 |  |  | 1264.5 |  |  | 1332 |  |  | 1360.5 |  |  | 1318.5 |  |  | 1437.5 |  |  | 1259 |  |  | 1328 |  |  | 1311 |  |  | 1294.5 |  |  | 1387.5 |  |  | 1297.5 |  |  | 1379.5 |  |  | 1353.5 |  |  | 1364.5 |  |  | 1342.5 |  |  | 1351.5 |  |  | 1279 |  |  | 1305 |  |  | 1330 |  |  | 1389.5 |  |  | 1379 |  |  | 1239.5 |  |  | 1297 |  |  | 1327 |  |  | 1347.5 |  |  | 1391.5 |  |  | 1307 |  |  | 1508 |  |  | 1294.5 |  |  | 1375 |  |  | 1262.5 |  |  | 1340.5 |  |  | 1313.5 |  |  | 1299.5 |  |  | 1250.5 |  |  | 1371 |  |  | 1300 |  |  | 1218 |  |  | 1400.5 |  |  | 1300.5 |  |  | 1324.5 |  |  | 1307.5 |  |  | 1340 |  |  | 1315 |  |  | 1324.5 |  |  | 1231 |  |  | 1341.5 |  |  | 1355 |  |  | 1357 |  |  | 1242.5 |  |  | 1338 |  |  | 1272 |  |  | 1297 |  |  | 1293 |  |  | 1386.5 |  |  | 1307.5 |  |  | 1259.5 |  |  | 1452 |  |  | 1243 |  |  | 1240 |  |  | 1249 |  |  | 1293.5 |  |  | 1315 |  |  | 1381.5 |  |  | 1347 |  |  | 1291 |  |  | 1347.5 |  |  | 1228.5 |  |  | 1236 |  |  | 1285.5 |  |  | 1258 |  |  | 1342 |  |  | 1329 |  |  | 1292 |  |  | 1312 |  |  | 1259 |  |  | 1237 |  |  | 1342 |  |  | 1270 |  |  | 1248.5 |  |  | 1284 |  |  | 1218 |  |  | 1321 |  |  | 1305 |  |  | 1232 |  |  | 1298 |  |  | 1310 |  |  | 1306.5 |  |  | 1341 |  |  | 1348.5 |  |  | 1377 |  |  | 1283 |  |  | 1392.5 |  |  | 1304 |  |  | 1460.5 |  |  | 1334 |  |  | 1211 |  |  | 1331.5 |  |  | 1282 |  |  | 1372.5 |  |  | 1271 |  |  | 1280 |  |  | 1315.5 |  |  | 1320.5 |  |  | 1361 |  |  | 1255.5 |  |  | 1295.5 |  |  | 1342 |  |  | 1347 |  |  | 1474.5 |  |  | 1286.5 |  |  | 1269.5 |  |  | 1307 |  |  | 1369 |  |  | 1270 |  |  | 1379 |  |  | 1350 |  |  | 1357.5 |  |  | 1285 |  |  | 1238.5 |  |  | 1324.5 |  |  | 1398 |  |  | 1403 |  |  | 1390.5 |  |  | 1258.5 |  |  | 1267 |  |  | 1339.5 |  |  | 1279.5 |  |  | 1360 |  |  | 1262 |  |  | 1333 |  |  | 1262.5 |  |  | 1409 |  |  | 1294.5 |  |  | 1307.5 |  |  | 1257 |  |  | 1294.5 |  |  | 1232 |  |  | 1339 |  |  | 1339 |  |  | 1319 |  |  | 1240 |  |  | 1387 |  |  | 1420 |  |  | 1350 |  |  | 1412 |  |  | 1283 |  |  | 1296.5 |  |  | 1409.5 |  |  | 1277 |  |  | 1227 |  |  | 1387 |  |  | 1359.5 |  |  | 1378.5 |  |  | 1422.5 |  |  | 1291 |  |  | 1345 |  |  | 1411.5 |  |  | 1281.5 |  |  | 1201.5 |  |  | 1394 |  |  | 1415 |  |  | 1313 |  |  | 1262 |  |  | 1314 |  |  | 1301.5 |  |  | 1304.5 |  |  | 1395 |  |  | 1364 |  |  | 1296 |  |  | 1375 |  |  | 1291 |  |  | 1300.5 |  |  | 1297 |  |  | 1388 |  |  | 1316 |  |  | 1293 |  |  | 1255.5 |  |  | 1445 |  |  | 1364 |  |  | 1327 |  |  | 1374 |  |  | 1357.5 |  |  | 1436 |  |  | 1288 |  |  | 1248 |  |  | 1395.5 |  |  | 1321.5 |  |  | 1364.5 |  |  | 1425 |  |  | 1335 |  |  | 1282 |  |  | 1372 |  |  | 1359 |  |  | 1255.5 |  |  | 1375 |  |  | 1251.5 |  |  | 1380.5 |  |  | 1378.5 |  |  | 1339 |  |  | 1394.5 |  |  | 1268 |  |  | 1251 |  |  | 1284.5 |  |  | 1344.5 |  |  | 1411 |  |  | 1446.5 |  |  | 1360.5 |  |  | 1315 |  |  | 1407 |  |  | 1317.5 |  |  | 1285.5 |  |  | 1367 |  |  | 1331.5 |  |  | 1356 |  |  | 1271 |  |  | 1291.5 |  |  | 1347 |  |  | 1267 |  |  | 1309.5 |  |  | 1269 |  |  | 1361.5 |  |  | 1322 |  |  | 1445 |  |  | 1314 |  |  | 1247 |  |  | 1399.5 |  |  | 1439 |  |  | 1364.5 |  |  | 1248.5 |  |  | 1342.5 |  |  | 1432 |  |  | 1452.5 |  |  | 1440 |  |  | 1333 |  |  | 1229.5 |  |  | 1321.5 |  |  | 1345 |  |  | 1314.5 |  |  | 1361 |  |  | 1296 |  |  | 1467.5 |  |  | 1337 |  |  | 1305.5 |  |  | 1356.5 |  |  | 1368.5 |  |  | 1364 |  |  | 1268 |  |  | 1326 |  |  | 1200.5 |  |  | 1291 |  |  | 1389.5 |  |  | 1352 |  |  | 1360 |  |  | 1279 |  |  | 1347 |  |  | 1359 |  |  | 1344 |  |  | 1271 |  |  | 1432 |  |  | 1363 |  |  | 1312.5 |  |  | 1330 |  |  | 1334 |  |  | 1494.5 |  |  | 1218.5 |  |  | 1359.5 |  |  | 1398.5 |  |  | 1324 |  |  | 1452 |  |  | 1239.5 |  |  | 1337.5 |  |  | 1394.5 |  |  | 1348 |  |  | 1324 |  |  | 1352 |  |  | 1291 |  |  | 1259 |  |  | 1305 |  |  | 1315 |  |  | 1296.5 |  |  | 1294.5 |  |  | 1343 |  |  | 1327.5 |  |  | 1370.5 |  |  | 1232 |  |  | 1375 |  |  | 1268 |  |  | 1305 |  |  | 1264.5 |  |  | 1233.5 |  |  | 1307.5 |  |  | 1326 |  |  | 1295.5 |  |  | 1304 |  |  | 1274 |  |  | 1338 |  |  | 1222.5 |  |  | 1354 |  |  | 1221 |  |  | 1318.5 |  |  | 1288 |  |  | 1328.5 |  |  | 1408 |  |  | 1324.5 |  |  | 1210 |  |  | 1307.5 |  |  | 1346.5 |  |  | 1392 |  |  | 1332 |  |  | 1230 |  |  | 1314 |  |  | 1266.5 |  |  | 1286 |  |  | 1356 |  |  | 1274.5 |  |  | 1395.5 |  |  | 1275.5 |  |  | 1303 |  |  | 1326.5 |  |  | 1283.5 |  |  | 1326.5 |  |  | 1395 |  |  | 1349 |  |  | 1272.5 |  |  | 1355 |  |  | 1404 |  |  | 1306.5 |  |  | 1312 |  |  | 1402 |  |  | 1311 |  |  | 1229 |  |  | 1224.5 |  |  | 1423.5 |  |  | 1265 |  |  | 1362 |  |  | 1349 |  |  | 1283 |  |  | 1258 |  |  | 1271.5 |  |  | 1361.5 |  |  | 1303 |  |  | 1478 |  |  | 1424 |  |  | 1193.5 |  |  | 1395.5 |  |  | 1304 |  |  | 1299 |  |  | 1245 |  |  | 1329.5 |  |  | 1404.5 |  |  | 1316 |  |  | 1264 |  |  | 1360 |  |  | 1350 |  |  | 1279 |  |  | 1409 |  |  | 1313 |  |  | 1403.5 |  |  | 1228 |  |  | 1456 |  |  | 1315 |  |  | 1349.5 |  |  | 1414 |  |  | 1212 |  |  | 1218 |  |  | 1325 |  |  | 1305 |  |  | 1310 |  |  | 1316 |  |  | 1293.5 |  |  | 1314.5 |  |  | 1289.5 |  |  | 1350 |  |  | 1314 |  |  | 1331.5 |  |  | 1223 |  |  | 1291.5 |  |  | 1279.5 |  |  | 1235 |  |  | 1290 |  |  | 1405.5 |  |  | 1304 |  |  | 1353 |  |  | 1373 |  |  | 1316 |  |  | 1314 |  |  | 1291 |  |  | 1301 |  |  | 1440.5 |  |  | 1335 |  |  | 1305 |  |  | 1423 |  |  | 1296 |  |  | 1383 |  |  | 1248 |  |  | 1476 |  |  | 1393 |  |  | 1325 |  |  | 1460.5 |  |  | 1309.5 |  |  | 1266.5 |  |  | 1334.5 |  |  | 1351 |  |  | 1243 |  |  | 1428.5 |  |  | 1326 |  |  | 1309 |  |  | 1291.5 |  |  | 1392.5 |  |  | 1363 |  |  | 1326.5 |  |  | 1283.5 |  |  | 1241 |  |  | 1383 |  |  | 1318 |  |  | 1309 |  |  | 1374.5 |  |  | 1280 |  |  | 1311.5 |  |  | 1246.5 |  |  | 1229 |  |  | 1281 |  |  | 1328.5 |  |  | 1292 |  |  | 1364.5 |  |  | 1281 |  |  | 1292.5 |  |  | 1266.5 |  |  | 1268.5 |  |  | 1357.5 |  |  | 1346.5 |  |  | 1266 |  |  | 1280 |  |  | 1425.5 |  |  | 1343 |  |  | 1307 |  |  | 1283 |  |  | 1371 |  |  | 1376.5 |  |  | 1189 |  |  | 1283 |  |  | 1373 |  |  | 1378.5 |  |  | 1351 |  |  | 1279 |  |  | 1354 |  |  | 1475.5 |  |  | 1289 |  |  | 1187 |  |  | 1323 |  |  | 1362 |  |  | 1546.5 |  |  | 1338 |  |  | 1260.5 |  |  | 1306 |  |  | 1342 |  |  | 1471.5 |  |  | 1380 |  |  | 1258 |  |  | 1236.5 |  |  | 1357 |  |  | 1302 |  |  | 1355 |  |  | 1391.5 |  |  | 1315.5 |  |  | 1345 |  |  | 1271 |  |  | 1346.5 |  |  | 1375.5 |  |  | 1252 |  |  | 1398 |  |  | 1423.5 |  |  | 1371.5 |  |  | 1242.5 |  |  | 1315.5 |  |  | 1339.5 |  |  | 1472 |  |  | 1345.5 |  |  | 1317 |  |  | 1318 |  |  | 1364 |  |  | 1336 |  |  | 1404.5 |  |  | 1341 |  |  | 1260 |  |  | 1303.5 |  |  | 1273.5 |  |  | 1249 |  |  | 1340.5 |  |  | 1321.5 |  |  | 1378 |  |  | 1308 |  |  | 1306 |  |  | 1333.5 |  |  | 1327 |  |  | 1314.5 |  |  | 1355 |  |  | 1379 |  |  | 1476.5 |  |  | 1295 |  |  | 1469 |  |  | 1291 |  |  | 1335 |  |  | 1382 |  |  | 1331 |  |  | 1302 |  |  | 1317 |  |  | 1244.5 |  |  | 1360.5 |  |  | 1382 |  |  | 1313.5 |  |  | 1206.5 |  |  | 1282 |  |  | 1216 |  |  | 1357 |  |  | 1389.5 |  |  | 1291.5 |  |  | 1284 |  |  | 1417 |  |  | 1262 |  |  | 1214 |  |  | 1334 |  |  | 1279 |  |  | 1469 |  |  | 1342.5 |  |  | 1368 |  |  | 1347 |  |  | 1448 |  |  | 1278 |  |  | 1226 |  |  | 1325.5 |  |  | 1465.5 |  |  | 1209.5 |  |  | 1272 |  |  | 1265 |  |  | 1209.5 |  |  | 1400.5 |  |  | 1353.5 |  |  | 1333 |  |  | 1362.5 |  |  | 1305.5 |  |  | 1310 |  |  | 1315.5 |  |  | 1375.5 |  |  | 1292 |  |  | 1267 |  |  | 1355 |  |  | 1333 |  |  | 1286 |  |  | 1201 |  |  | 1356 |  |  | 1404 |  |  | 1321 |  |  | 1264 |  |  | 1381.5 |  |  | 1307 |  |  | 1361 |  |  | 1208 |  |  | 1278.5 |  |  | 1365 |  |  | 1319.5 |  |  | 1400 |  |  | 1338 |  |  | 1328 |  |  | 1344 |  |  | 1411.5 |  |  | 1317 |  |  | 1252 |  |  | 1428.5 |  |  | 1351 |  |  | 1281 |  |  | 1279.5 |  |  | 1302.5 |  |  | 1381 |  |  | 1255.5 |  |  | 1403 |  |  | 1300.5 |  |  | 1410 |  |  | 1340 |  |  | 1309.5 |  |  | 1433.5 |  |  | 1305 |  |  | 1370 |  |  | 1339 |  |  | 1393 |  |  | 1225 |  |  | 1391 |  |  | 1205 |  |  | 1287 |  |  | 1430.5 |  |  | 1237 |  |  | 1406.5 |  |  | 1305 |  |  | 1353.5 |  |  | 1280.5 |  |  | 1275 |  |  | 1396 |  |  | 1329.5 |  |  | 1349 |  |  | 1339 |  |  | 1361 |  |  | 1296.5 |  |  | 1412 |  |  | 1212.5 |  |  | 1261 |  |  | 1285 |  |  | 1318 |  |  | 1378 |  |  | 1437.5 |  |  | 1275 |  |  | 1307 |  |  | 1318 |  |  | 1282.5 |  |  | 1432 |  |  | 1359 |  |  | 1363 |  |  | 1298 |  |  | 1311.5 |  |  | 1268.5 |  |  | 1360 |  |  | 1365 |  |  | 1346 |  |  | 1363.5 |  |  | 1358 |  |  | 1305 |  |  | 1225 |  |  | 1452.5 |  |  | 1323.5 |  |  | 1397.5 |  |  | 1293 |  |  | 1388 |  |  | 1278 |  |  | 1303.5 |  |  | 1349 |  |  | 1313.5 |  |  | 1195 |  |  | 1279 |  |  | 1355 |  |  | 1260.5 |  |  | 1335.5 |  |  | 1352 |  |  | 1274 |  |  | 1361.5 |  |  | 1312 |  |  | 1364 |  |  | 1397.5 |  |  | 1303 |  |  | 1291 |  |  | 1391.5 |  |  | 1283 |  |  | 1350 |  |  | 1294.5 |  |  | 1391 |  |  | 1276.5 |  |  | 1364 |  |  | 1241.5 |  |  | 1348.5 |  |  | 1267 |  |  | 1414 |  |  | 1346.5 |  |  | 1350.5 |  |  | 1453 |  |  | 1299 |  |  | 1413 |  |  | 1292.5 |  |  | 1314 |  |  | 1245 |  |  | 1365 |  |  | 1423.5 |  |  | 1341.5 |  |  | 1376 |  |  | 1383 |  |  | 1263 |  |  | 1282 |  |  | 1396 |  |  | 1294 |  |  | 1307 |  |  | 1273.5 |  |  | 1305.5 |  |  | 1269.5 |  |  | 1329 |  |  | 1264.5 |  |  | 1338 |  |  | 1278 |  |  | 1342.5 |  |  | 1253.5 |  |  | 1170 |  |  | 1338 |  |  | 1249.5 |  |  | 1276 |  |  | 1325 |  |  | 1263.5 |  |  | 1261.5 |  |  | 1344 |  |  | 1350 |  |  | 1411 |  |  | 1265.5 |  |  | 1265 |  |  | 1210 |  |  | 1330 |  |  | 1310 |  |  | 1426 |  |  | 1306.5 |  |  | 1404 |  |  | 1290 |  |  | 1173 |  |  | 1427.5 |  |  | 1354 |  |  | 1282.5 |  |  | 1224.5 |  |  | 1310 |  |  | 1302 |  |  | 1287.5 |  |  | 1267.5 |  |  | 1259.5 |  |  | 1311.5 |  |  | 1369.5 |  |  | 1368 |  |  | 1283 |  |  | 1376.5 |  |  | 1324.5 |  |  | 1328 |  |  | 1271 |  |  | 1316.5 |  |  | 1359 |  |  | 1299 |  |  | 1229 |  |  | 1333.5 |  |  | 1418 |  |  | 1242.5 |  |  | 1245 |  |  | 1320.5 |  |  | 1369.5 |  |  | 1457.5 |  |  | 1310 |  |  | 1270 |  |  | 1401.5 |  |  | 1285.5 |  |  | 1361 |  |  | 1340 |  |  | 1300.5 |  |  | 1316 |  |  | 1330.5 |  |  | 1295.5 |  |  | 1353 |  |  | 1311 |  |  | 1297.5 |  |  | 1396.5 |  |  | 1297 |  |  | 1284.5 |  |  | 1378.5 |  |  | 1276 |  |  | 1407 |  |  | 1436 |  |  | 1306.5 |  |  | 1371 |  |  | 1292 |  |  | 1321 |  |  | 1288 |  |  | 1371 |  |  | 1262 |  |  | 1393.5 |  |  | 1241.5 |  |  | 1280 |  |  | 1233 |  |  | 1313 |  |  | 1305.5 |  |  | 1319 |  |  | 1409 |  |  | 1275.5 |  |  | 1334.5 |  |  | 1336 |  |  | 1297.5 |  |  | 1327 |  |  | 1271 |  |  | 1362 |  |  | 1434.5 |  |  | 1429 |  |  | 1227.5 |  |  | 1261.5 |  |  | 1264 |  |  | 1378.5 |  |  | 1190.5 |  |  | 1233 |  |  | 1268 |  |  | 1461 |  |  | 1247.5 |  |  | 1251 |  |  | 1316.5 |  |  | 1284.5 |  |  | 1396 |  |  | 1273.5 |  |  | 1260 |  |  | 1320 |  |  | 1302 |  |  | 1253 |  |  | 1260 |  |  | 1390.5 |  |  | 1331 |  |  | 1373 |  |  | 1257 |  |  | 1415 |  |  | 1278.5 |  |  | 1383.5 |  |  | 1279 |  |  | 1334 |  |  | 1295 |  |  | 1276 |  |  | 1361 |  |  | 1367.5 |  |  | 1354 |  |  | 1316.5 |  |  | 1403 |  |  | 1227 |  |  | 1324 |  |  | 1287 |  |  | 1295.5 |  |  | 1273 |  |  | 1278.5 |  |  | 1236 |  |  | 1398 |  |  | 1376 |  |  | 1266.5 |  |  | 1303 |  |  | 1289 |  |  | 1218 |  |  | 1451 |  |  | 1396 |  |  | 1316.5 |  |  | 1344.5 |  |  | 1313 |  |  | 1283.5 |  |  | 1208 |  |  | 1218.5 |  |  | 1323.5 |  |  | 1297.5 |  |  | 1333.5 |  |  | 1215 |  |  | 1394 |  |  | 1259 |  |  | 1258 |  |  | 1356 |  |  | 1290 |  |  | 1274.5 |  |  | 1301.5 |  |  | 1308.5 |  |  | 1415 |  |  | 1329.5 |  |  | 1341.5 |  |  | 1348.5 |  |  | 1288.5 |  |  | 1296 |  |  | 1323.5 |  |  | 1297.5 |  |  | 1361 |  |  | 1290.5 |  |  | 1354.5 |  |  | 1333.5 |  |  | 1375 |  |  | 1355.5 |  |  | 1302 |  |  | 1312 |  |  | 1353.5 |  |  | 1330.5 |  |  | 1360 |  |  | 1344 |  |  | 1243.5 |  |  | 1271.5 |  |  | 1332.5 |  |  | 1343 |  |  | 1294 |  |  | 1270 |  |  | 1342.5 |  |  | 1354.5 |  |  | 1354 |  |  | 1334.5 |  |  | 1232 |  |  | 1307 |  |  | 1367.5 |  |  | 1193.5 |  |  | 1305 |  |  | 1322.5 |  |  | 1290 |  |  | 1239.5 |  |  | 1418.5 |  |  | 1360 |  |  | 1241.5 |  |  | 1348 |  |  | 1342.5 |  |  | 1326 |  |  | 1329 |  |  | 1396 |  |  | 1294.5 |  |  | 1225.5 |  |  | 1347 |  |  | 1261 |  |  | 1272 |  |  | 1330.5 |  |  | 1276.5 |  |  | 1364 |  |  | 1285.5 |  |  | 1279 |  |  | 1272.5 |  |  | 1327.5 |  |  | 1261 |  |  | 1278 |  |  | 1311 |  |  | 1328.5 |  |  | 1305 |  |  | 1400.5 |  |  | 1360 |  |  | 1314.5 |  |  | 1434 |  |  | 1196.5 |  |  | 1309 |  |  | 1273.5 |  |  | 1309.5 |  |  | 1299 |  |  | 1270 |  |  | 1338 |  |  | 1318 |  |  | 1341.5 |  |  | 1273 |  |  | 1277.5 |  |  | 1232 |  |  | 1309 |  |  | 1322 |  |  | 1374 |  |  | 1410 |  |  | 1293 |  |  | 1305 |  |  | 1376.5 |  |  | 1241 |  |  | 1382
48 |  | 1415.5 |  |  | 1409 |  |  | 1358.5 |  |  | 1355 |  |  | 1354.5 |  |  | 1334 |  |  | 1359 |  |  | 1445 |  |  | 1313.5 |  |  | 1358 |  |  | 1291 |  |  | 1463 |  |  | 1354 |  |  | 1408 |  |  | 1309.5 |  |  | 1390.5 |  |  | 1300 |  |  | 1412 |  |  | 1458 |  |  | 1249.5 |  |  | 1429 |  |  | 1396 |  |  | 1336 |  |  | 1379 |  |  | 1315.5 |  |  | 1463 |  |  | 1404 |  |  | 1288 |  |  | 1364 |  |  | 1310 |  |  | 1284 |  |  | 1377.5 |  |  | 1485.5 |  |  | 1319.5 |  |  | 1248 |  |  | 1279.5 |  |  | 1287.5 |  |  | 1389.5 |  |  | 1370 |  |  | 1311 |  |  | 1245.5 |  |  | 1268 |  |  | 1444.5 |  |  | 1394.5 |  |  | 1388.5 |  |  | 1453.5 |  |  | 1436.5 |  |  | 1334 |  |  | 1235 |  |  | 1280.5 |  |  | 1348 |  |  | 1281.5 |  |  | 1315.5 |  |  | 1374 |  |  | 1295 |  |  | 1323 |  |  | 1321 |  |  | 1415 |  |  | 1412 |  |  | 1342.5 |  |  | 1443.5 |  |  | 1386.5 |  |  | 1225 |  |  | 1384 |  |  | 1255 |  |  | 1303.5 |  |  | 1347 |  |  | 1381.5 |  |  | 1357.5 |  |  | 1463.5 |  |  | 1280 |  |  | 1367 |  |  | 1350 |  |  | 1315.5 |  |  | 1426.5 |  |  | 1336.5 |  |  | 1405.5 |  |  | 1377.5 |  |  | 1385.5 |  |  | 1363.5 |  |  | 1372.5 |  |  | 1308 |  |  | 1344 |  |  | 1351 |  |  | 1415.5 |  |  | 1394 |  |  | 1268.5 |  |  | 1312 |  |  | 1348 |  |  | 1371.5 |  |  | 1406.5 |  |  | 1336 |  |  | 1537 |  |  | 1309.5 |  |  | 1396 |  |  | 1309.5 |  |  | 1355.5 |  |  | 1342.5 |  |  | 1323.5 |  |  | 1297.5 |  |  | 1386 |  |  | 1324 |  |  | 1257 |  |  | 1421.5 |  |  | 1326.5 |  |  | 1350.5 |  |  | 1322.5 |  |  | 1369 |  |  | 1330 |  |  | 1345.5 |  |  | 1270 |  |  | 1365.5 |  |  | 1394 |  |  | 1396 |  |  | 1268.5 |  |  | 1353 |  |  | 1311 |  |  | 1318 |  |  | 1332 |  |  | 1433.5 |  |  | 1322.5 |  |  | 1306.5 |  |  | 1476 |  |  | 1282 |  |  | 1261 |  |  | 1275 |  |  | 1319.5 |  |  | 1362 |  |  | 1410.5 |  |  | 1386 |  |  | 1320 |  |  | 1386.5 |  |  | 1267.5 |  |  | 1262 |  |  | 1324.5 |  |  | 1305 |  |  | 1389 |  |  | 1353 |  |  | 1313 |  |  | 1336 |  |  | 1274 |  |  | 1266 |  |  | 1368 |  |  | 1285 |  |  | 1263.5 |  |  | 1323 |  |  | 1265 |  |  | 1342 |  |  | 1344 |  |  | 1256 |  |  | 1324 |  |  | 1331 |  |  | 1345.5 |  |  | 1362 |  |  | 1377.5 |  |  | 1401 |  |  | 1322 |  |  | 1413.5 |  |  | 1330 |  |  | 1481.5 |  |  | 1373 |  |  | 1250 |  |  | 1355.5 |  |  | 1329 |  |  | 1401.5 |  |  | 1310 |  |  | 1304 |  |  | 1330.5 |  |  | 1335.5 |  |  | 1387 |  |  | 1294.5 |  |  | 1334.5 |  |  | 1381 |  |  | 1373 |  |  | 1498.5 |  |  | 1333.5 |  |  | 1316.5 |  |  | 1336 |  |  | 1393 |  |  | 1299 |  |  | 1394 |  |  | 1397 |  |  | 1396.5 |  |  | 1324 |  |  | 1267.5 |  |  | 1363.5 |  |  | 1424 |  |  | 1427 |  |  | 1429.5 |  |  | 1282.5 |  |  | 1314 |  |  | 1363.5 |  |  | 1318.5 |  |  | 1399 |  |  | 1288 |  |  | 1362 |  |  | 1277.5 |  |  | 1456 |  |  | 1315.5 |  |  | 1336.5 |  |  | 1286 |  |  | 1341.5 |  |  | 1253 |  |  | 1368 |  |  | 1368 |  |  | 1358 |  |  | 1266 |  |  | 1408 |  |  | 1459 |  |  | 1397 |  |  | 1459 |  |  | 1330 |  |  | 1335.5 |  |  | 1456.5 |  |  | 1316 |  |  | 1256 |  |  | 1413 |  |  | 1383.5 |  |  | 1417.5 |  |  | 1448.5 |  |  | 1312 |  |  | 1374 |  |  | 1426.5 |  |  | 1307.5 |  |  | 1240.5 |  |  | 1433 |  |  | 1430 |  |  | 1342 |  |  | 1286 |  |  | 1335 |  |  | 1316.5 |  |  | 1351.5 |  |  | 1416 |  |  | 1411 |  |  | 1322 |  |  | 1414 |  |  | 1330 |  |  | 1339.5 |  |  | 1326 |  |  | 1412 |  |  | 1363 |  |  | 1332 |  |  | 1284.5 |  |  | 1484 |  |  | 1390 |  |  | 1374 |  |  | 1413 |  |  | 1383.5 |  |  | 1457 |  |  | 1303 |  |  | 1272 |  |  | 1421.5 |  |  | 1345.5 |  |  | 1390.5 |  |  | 1446 |  |  | 1359 |  |  | 1297 |  |  | 1411 |  |  | 1374 |  |  | 1302.5 |  |  | 1396 |  |  | 1280.5 |  |  | 1395.5 |  |  | 1407.5 |  |  | 1360 |  |  | 1415.5 |  |  | 1315 |  |  | 1280 |  |  | 1310.5 |  |  | 1383.5 |  |  | 1426 |  |  | 1485.5 |  |  | 1384.5 |  |  | 1354 |  |  | 1431 |  |  | 1356.5 |  |  | 1332.5 |  |  | 1393 |  |  | 1370.5 |  |  | 1382 |  |  | 1295 |  |  | 1306.5 |  |  | 1371 |  |  | 1306 |  |  | 1333.5 |  |  | 1290 |  |  | 1400.5 |  |  | 1348 |  |  | 1484 |  |  | 1343 |  |  | 1276 |  |  | 1420.5 |  |  | 1478 |  |  | 1411.5 |  |  | 1287.5 |  |  | 1389.5 |  |  | 1461 |  |  | 1473.5 |  |  | 1464 |  |  | 1359 |  |  | 1258.5 |  |  | 1336.5 |  |  | 1366 |  |  | 1353.5 |  |  | 1376 |  |  | 1311 |  |  | 1496.5 |  |  | 1361 |  |  | 1329.5 |  |  | 1395.5 |  |  | 1389.5 |  |  | 1385 |  |  | 1307 |  |  | 1347 |  |  | 1221.5 |  |  | 1315 |  |  | 1436.5 |  |  | 1381 |  |  | 1375 |  |  | 1294 |  |  | 1394 |  |  | 1406 |  |  | 1368 |  |  | 1318 |  |  | 1458 |  |  | 1410 |  |  | 1351.5 |  |  | 1359 |  |  | 1349 |  |  | 1509.5 |  |  | 1265.5 |  |  | 1383.5 |  |  | 1427.5 |  |  | 1345 |  |  | 1478 |  |  | 1260.5 |  |  | 1384.5 |  |  | 1409.5 |  |  | 1377 |  |  | 1350 |  |  | 1367 |  |  | 1317 |  |  | 1280 |  |  | 1326 |  |  | 1354 |  |  | 1311.5 |  |  | 1333.5 |  |  | 1364 |  |  | 1366.5 |  |  | 1396.5 |  |  | 1256 |  |  | 1396 |  |  | 1307 |  |  | 1329 |  |  | 1290.5 |  |  | 1262.5 |  |  | 1336.5 |  |  | 1347 |  |  | 1310.5 |  |  | 1351 |  |  | 1321 |  |  | 1377 |  |  | 1261.5 |  |  | 1383 |  |  | 1236 |  |  | 1342.5 |  |  | 1327 |  |  | 1354.5 |  |  | 1447 |  |  | 1348.5 |  |  | 1234 |  |  | 1346.5 |  |  | 1372.5 |  |  | 1421 |  |  | 1347 |  |  | 1269 |  |  | 1338 |  |  | 1287.5 |  |  | 1325 |  |  | 1371 |  |  | 1298.5 |  |  | 1416.5 |  |  | 1290.5 |  |  | 1318 |  |  | 1365.5 |  |  | 1309.5 |  |  | 1341.5 |  |  | 1424 |  |  | 1375 |  |  | 1311.5 |  |  | 1394 |  |  | 1428 |  |  | 1353.5 |  |  | 1341 |  |  | 1441 |  |  | 1332 |  |  | 1250 |  |  | 1239.5 |  |  | 1452.5 |  |  | 1304 |  |  | 1383 |  |  | 1375 |  |  | 1322 |  |  | 1297 |  |  | 1310.5 |  |  | 1376.5 |  |  | 1332 |  |  | 1525 |  |  | 1453 |  |  | 1240.5 |  |  | 1434.5 |  |  | 1333 |  |  | 1325 |  |  | 1269 |  |  | 1368.5 |  |  | 1433.5 |  |  | 1342 |  |  | 1303 |  |  | 1381 |  |  | 1376 |  |  | 1326 |  |  | 1448 |  |  | 1334 |  |  | 1450.5 |  |  | 1249 |  |  | 1495 |  |  | 1336 |  |  | 1373.5 |  |  | 1453 |  |  | 1238 |  |  | 1233 |  |  | 1354 |  |  | 1352 |  |  | 1334 |  |  | 1340 |  |  | 1332.5 |  |  | 1343.5 |  |  | 1313.5 |  |  | 1365 |  |  | 1340 |  |  | 1370.5 |  |  | 1247 |  |  | 1315.5 |  |  | 1305.5 |  |  | 1259 |  |  | 1337 |  |  | 1434.5 |  |  | 1328 |  |  | 1392 |  |  | 1412 |  |  | 1345 |  |  | 1338 |  |  | 1315 |  |  | 1340 |  |  | 1464.5 |  |  | 1364 |  |  | 1320 |  |  | 1444 |  |  | 1335 |  |  | 1409 |  |  | 1263 |  |  | 1502 |  |  | 1414 |  |  | 1340 |  |  | 1499.5 |  |  | 1356.5 |  |  | 1295.5 |  |  | 1355.5 |  |  | 1375 |  |  | 1269 |  |  | 1467.5 |  |  | 1373 |  |  | 1348 |  |  | 1312.5 |  |  | 1418.5 |  |  | 1389 |  |  | 1341.5 |  |  | 1312.5 |  |  | 1267 |  |  | 1430 |  |  | 1365 |  |  | 1324 |  |  | 1400.5 |  |  | 1301 |  |  | 1332.5 |  |  | 1261.5 |  |  | 1253 |  |  | 1305 |  |  | 1354.5 |  |  | 1313 |  |  | 1379.5 |  |  | 1320 |  |  | 1331.5 |  |  | 1287.5 |  |  | 1297.5 |  |  | 1372.5 |  |  | 1367.5 |  |  | 1281 |  |  | 1304 |  |  | 1454.5 |  |  | 1390 |  |  | 1322 |  |  | 1304 |  |  | 1392 |  |  | 1415.5 |  |  | 1204 |  |  | 1298 |  |  | 1388 |  |  | 1393.5 |  |  | 1390 |  |  | 1300 |  |  | 1369 |  |  | 1501.5 |  |  | 1336 |  |  | 1226 |  |  | 1362 |  |  | 1388 |  |  | 1585.5 |  |  | 1377 |  |  | 1299.5 |  |  | 1353 |  |  | 1357 |  |  | 1518.5 |  |  | 1395 |  |  | 1284 |  |  | 1283.5 |  |  | 1396 |  |  | 1326 |  |  | 1370 |  |  | 1417.5 |  |  | 1354.5 |  |  | 1371 |  |  | 1310 |  |  | 1361.5 |  |  | 1414.5 |  |  | 1291 |  |  | 1437 |  |  | 1438.5 |  |  | 1410.5 |  |  | 1289.5 |  |  | 1341.5 |  |  | 1354.5 |  |  | 1496 |  |  | 1360.5 |  |  | 1343 |  |  | 1339 |  |  | 1388 |  |  | 1362 |  |  | 1443.5 |  |  | 1356 |  |  | 1299 |  |  | 1342.5 |  |  | 1299.5 |  |  | 1288 |  |  | 1379.5 |  |  | 1350.5 |  |  | 1407 |  |  | 1323 |  |  | 1345 |  |  | 1372.5 |  |  | 1353 |  |  | 1340.5 |  |  | 1379 |  |  | 1403 |  |  | 1515.5 |  |  | 1334 |  |  | 1498 |  |  | 1317 |  |  | 1364 |  |  | 1397 |  |  | 1357 |  |  | 1331 |  |  | 1338 |  |  | 1273.5 |  |  | 1399.5 |  |  | 1411 |  |  | 1339.5 |  |  | 1245.5 |  |  | 1303 |  |  | 1231 |  |  | 1396 |  |  | 1428.5 |  |  | 1315.5 |  |  | 1323 |  |  | 1432 |  |  | 1286 |  |  | 1240 |  |  | 1349 |  |  | 1300 |  |  | 1495 |  |  | 1366.5 |  |  | 1389 |  |  | 1371 |  |  | 1487 |  |  | 1299 |  |  | 1252 |  |  | 1364.5 |  |  | 1491.5 |  |  | 1256.5 |  |  | 1298 |  |  | 1286 |  |  | 1235.5 |  |  | 1447.5 |  |  | 1400.5 |  |  | 1348 |  |  | 1401.5 |  |  | 1326.5 |  |  | 1336 |  |  | 1341.5 |  |  | 1414.5 |  |  | 1321 |  |  | 1293 |  |  | 1370 |  |  | 1357 |  |  | 1307 |  |  | 1240 |  |  | 1377 |  |  | 1451 |  |  | 1345 |  |  | 1288 |  |  | 1420.5 |  |  | 1328 |  |  | 1400 |  |  | 1247 |  |  | 1317.5 |  |  | 1391 |  |  | 1358.5 |  |  | 1424 |  |  | 1367 |  |  | 1367 |  |  | 1370 |  |  | 1437.5 |  |  | 1332 |  |  | 1276 |  |  | 1449.5 |  |  | 1390 |  |  | 1320 |  |  | 1303.5 |  |  | 1341.5 |  |  | 1396 |  |  | 1279.5 |  |  | 1432 |  |  | 1347.5 |  |  | 1457 |  |  | 1379 |  |  | 1333.5 |  |  | 1462.5 |  |  | 1320 |  |  | 1385 |  |  | 1354 |  |  | 1432 |  |  | 1251 |  |  | 1406 |  |  | 1244 |  |  | 1313 |  |  | 1477.5 |  |  | 1252 |  |  | 1453.5 |  |  | 1326 |  |  | 1400.5 |  |  | 1306.5 |  |  | 1314 |  |  | 1411 |  |  | 1368.5 |  |  | 1378 |  |  | 1386 |  |  | 1400 |  |  | 1325.5 |  |  | 1438 |  |  | 1251.5 |  |  | 1276 |  |  | 1309 |  |  | 1342 |  |  | 1404 |  |  | 1476.5 |  |  | 1296 |  |  | 1346 |  |  | 1365 |  |  | 1303.5 |  |  | 1461 |  |  | 1406 |  |  | 1402 |  |  | 1337 |  |  | 1326.5 |  |  | 1297.5 |  |  | 1399 |  |  | 1404 |  |  | 1385 |  |  | 1392.5 |  |  | 1384 |  |  | 1344 |  |  | 1272 |  |  | 1481.5 |  |  | 1362.5 |  |  | 1412.5 |  |  | 1340 |  |  | 1414 |  |  | 1317 |  |  | 1329.5 |  |  | 1375 |  |  | 1352.5 |  |  | 1210 |  |  | 1294 |  |  | 1376 |  |  | 1307.5 |  |  | 1359.5 |  |  | 1381 |  |  | 1300 |  |  | 1376.5 |  |  | 1341 |  |  | 1393 |  |  | 1436.5 |  |  | 1329 |  |  | 1320 |  |  | 1406.5 |  |  | 1304 |  |  | 1389 |  |  | 1333.5 |  |  | 1420 |  |  | 1300.5 |  |  | 1403 |  |  | 1267.5 |  |  | 1377.5 |  |  | 1293 |  |  | 1453 |  |  | 1385.5 |  |  | 1374.5 |  |  | 1477 |  |  | 1346 |  |  | 1452 |  |  | 1331.5 |  |  | 1361 |  |  | 1260 |  |  | 1380 |  |  | 1444.5 |  |  | 1380.5 |  |  | 1402 |  |  | 1412 |  |  | 1287 |  |  | 1306 |  |  | 1425 |  |  | 1333 |  |  | 1354 |  |  | 1302.5 |  |  | 1352.5 |  |  | 1284.5 |  |  | 1355 |  |  | 1303.5 |  |  | 1377 |  |  | 1317 |  |  | 1357.5 |  |  | 1279.5 |  |  | 1185 |  |  | 1364 |  |  | 1296.5 |  |  | 1323 |  |  | 1364 |  |  | 1292.5 |  |  | 1300.5 |  |  | 1359 |  |  | 1374 |  |  | 1432 |  |  | 1280.5 |  |  | 1312 |  |  | 1234 |  |  | 1359 |  |  | 1349 |  |  | 1450 |  |  | 1335.5 |  |  | 1419 |  |  | 1319 |  |  | 1220 |  |  | 1466.5 |  |  | 1375 |  |  | 1329.5 |  |  | 1253.5 |  |  | 1339 |  |  | 1326 |  |  | 1334.5 |  |  | 1282.5 |  |  | 1306.5 |  |  | 1337.5 |  |  | 1393.5 |  |  | 1383 |  |  | 1330 |  |  | 1400.5 |  |  | 1348.5 |  |  | 1367 |  |  | 1295 |  |  | 1345.5 |  |  | 1398 |  |  | 1320 |  |  | 1253 |  |  | 1372.5 |  |  | 1444 |  |  | 1281.5 |  |  | 1260 |  |  | 1344.5 |  |  | 1398.5 |  |  | 1483.5 |  |  | 1336 |  |  | 1294 |  |  | 1430.5 |  |  | 1300.5 |  |  | 1387 |  |  | 1387 |  |  | 1321.5 |  |  | 1355 |  |  | 1369.5 |  |  | 1342.5 |  |  | 1400 |  |  | 1350 |  |  | 1326.5 |  |  | 1443.5 |  |  | 1326 |  |  | 1313.5 |  |  | 1404.5 |  |  | 1315 |  |  | 1433 |  |  | 1483 |  |  | 1332.5 |  |  | 1418 |  |  | 1321 |  |  | 1350 |  |  | 1335 |  |  | 1395 |  |  | 1301 |  |  | 1432.5 |  |  | 1288.5 |  |  | 1301 |  |  | 1259 |  |  | 1352 |  |  | 1344.5 |  |  | 1366 |  |  | 1438 |  |  | 1304.5 |  |  | 1363.5 |  |  | 1351 |  |  | 1318.5 |  |  | 1366 |  |  | 1295 |  |  | 1383 |  |  | 1481.5 |  |  | 1455 |  |  | 1266.5 |  |  | 1285.5 |  |  | 1293 |  |  | 1417.5 |  |  | 1237.5 |  |  | 1280 |  |  | 1292 |  |  | 1490 |  |  | 1286.5 |  |  | 1266 |  |  | 1340.5 |  |  | 1310.5 |  |  | 1411 |  |  | 1297.5 |  |  | 1307 |  |  | 1349 |  |  | 1326 |  |  | 1274 |  |  | 1275 |  |  | 1429.5 |  |  | 1378 |  |  | 1420 |  |  | 1281 |  |  | 1439 |  |  | 1317.5 |  |  | 1422.5 |  |  | 1318 |  |  | 1360 |  |  | 1334 |  |  | 1297 |  |  | 1390 |  |  | 1382.5 |  |  | 1375 |  |  | 1355.5 |  |  | 1442 |  |  | 1266 |  |  | 1339 |  |  | 1313 |  |  | 1310.5 |  |  | 1297 |  |  | 1304.5 |  |  | 1275 |  |  | 1413 |  |  | 1400 |  |  | 1281.5 |  |  | 1324 |  |  | 1304 |  |  | 1244 |  |  | 1490 |  |  | 1443 |  |  | 1337.5 |  |  | 1383.5 |  |  | 1328 |  |  | 1322.5 |  |  | 1247 |  |  | 1239.5 |  |  | 1352.5 |  |  | 1323.5 |  |  | 1372.5 |  |  | 1262 |  |  | 1420 |  |  | 1298 |  |  | 1305 |  |  | 1382 |  |  | 1337 |  |  | 1321.5 |  |  | 1316.5 |  |  | 1355.5 |  |  | 1441 |  |  | 1368.5 |  |  | 1367.5 |  |  | 1372.5 |  |  | 1317.5 |  |  | 1325 |  |  | 1370.5 |  |  | 1336.5 |  |  | 1385 |  |  | 1311.5 |  |  | 1383.5 |  |  | 1380.5 |  |  | 1399 |  |  | 1379.5 |  |  | 1349 |  |  | 1351 |  |  | 1368.5 |  |  | 1369.5 |  |  | 1386 |  |  | 1383 |  |  | 1258.5 |  |  | 1292.5 |  |  | 1361.5 |  |  | 1369 |  |  | 1333 |  |  | 1296 |  |  | 1366.5 |  |  | 1369.5 |  |  | 1383 |  |  | 1373.5 |  |  | 1279 |  |  | 1328 |  |  | 1393.5 |  |  | 1222.5 |  |  | 1344 |  |  | 1346.5 |  |  | 1314 |  |  | 1265.5 |  |  | 1465.5 |  |  | 1375 |  |  | 1280.5 |  |  | 1377 |  |  | 1366.5 |  |  | 1341 |  |  | 1368 |  |  | 1435 |  |  | 1323.5 |  |  | 1240.5 |  |  | 1394 |  |  | 1300 |  |  | 1301 |  |  | 1351.5 |  |  | 1305.5 |  |  | 1411 |  |  | 1309.5 |  |  | 1318 |  |  | 1293.5 |  |  | 1356.5 |  |  | 1285 |  |  | 1293 |  |  | 1358 |  |  | 1367.5 |  |  | 1344 |  |  | 1429.5 |  |  | 1399 |  |  | 1338.5 |  |  | 1473 |  |  | 1220.5 |  |  | 1338 |  |  | 1302.5 |  |  | 1338.5 |  |  | 1338 |  |  | 1296 |  |  | 1362 |  |  | 1342 |  |  | 1370.5 |  |  | 1297 |  |  | 1306.5 |  |  | 1253 |  |  | 1324 |  |  | 1346 |  |  | 1400 |  |  | 1425 |  |  | 1340 |  |  | 1334 |  |  | 1397.5 |  |  | 1256 |  |  | 1429
49 |  | 1462.5 |  |  | 1435 |  |  | 1397.5 |  |  | 1384 |  |  | 1393.5 |  |  | 1373 |  |  | 1388 |  |  | 1484 |  |  | 1352.5 |  |  | 1397 |  |  | 1317 |  |  | 1502 |  |  | 1393 |  |  | 1447 |  |  | 1335.5 |  |  | 1405.5 |  |  | 1339 |  |  | 1436 |  |  | 1497 |  |  | 1296.5 |  |  | 1450 |  |  | 1425 |  |  | 1375 |  |  | 1418 |  |  | 1362.5 |  |  | 1502 |  |  | 1425 |  |  | 1312 |  |  | 1393 |  |  | 1336 |  |  | 1310 |  |  | 1416.5 |  |  | 1506.5 |  |  | 1358.5 |  |  | 1277 |  |  | 1303.5 |  |  | 1326.5 |  |  | 1428.5 |  |  | 1399 |  |  | 1340 |  |  | 1269.5 |  |  | 1289 |  |  | 1468.5 |  |  | 1418.5 |  |  | 1435.5 |  |  | 1492.5 |  |  | 1465.5 |  |  | 1381 |  |  | 1261 |  |  | 1309.5 |  |  | 1363 |  |  | 1305.5 |  |  | 1336.5 |  |  | 1403 |  |  | 1316 |  |  | 1370 |  |  | 1360 |  |  | 1454 |  |  | 1433 |  |  | 1363.5 |  |  | 1472.5 |  |  | 1410.5 |  |  | 1251 |  |  | 1431 |  |  | 1276 |  |  | 1332.5 |  |  | 1368 |  |  | 1410.5 |  |  | 1378.5 |  |  | 1489.5 |  |  | 1304 |  |  | 1406 |  |  | 1389 |  |  | 1362.5 |  |  | 1447.5 |  |  | 1362.5 |  |  | 1452.5 |  |  | 1398.5 |  |  | 1411.5 |  |  | 1389.5 |  |  | 1387.5 |  |  | 1332 |  |  | 1391 |  |  | 1390 |  |  | 1454.5 |  |  | 1420 |  |  | 1292.5 |  |  | 1341 |  |  | 1387 |  |  | 1392.5 |  |  | 1427.5 |  |  | 1360 |  |  | 1576 |  |  | 1348.5 |  |  | 1443 |  |  | 1330.5 |  |  | 1370.5 |  |  | 1381.5 |  |  | 1362.5 |  |  | 1336.5 |  |  | 1433 |  |  | 1350 |  |  | 1296 |  |  | 1460.5 |  |  | 1350.5 |  |  | 1389.5 |  |  | 1361.5 |  |  | 1416 |  |  | 1351 |  |  | 1384.5 |  |  | 1309 |  |  | 1391.5 |  |  | 1409 |  |  | 1411 |  |  | 1307.5 |  |  | 1368 |  |  | 1335 |  |  | 1342 |  |  | 1347 |  |  | 1462.5 |  |  | 1348.5 |  |  | 1327.5 |  |  | 1497 |  |  | 1321 |  |  | 1287 |  |  | 1314 |  |  | 1348.5 |  |  | 1391 |  |  | 1436.5 |  |  | 1410 |  |  | 1341 |  |  | 1412.5 |  |  | 1293.5 |  |  | 1277 |  |  | 1350.5 |  |  | 1329 |  |  | 1410 |  |  | 1379 |  |  | 1352 |  |  | 1375 |  |  | 1303 |  |  | 1313 |  |  | 1392 |  |  | 1324 |  |  | 1302.5 |  |  | 1370 |  |  | 1280 |  |  | 1368 |  |  | 1373 |  |  | 1295 |  |  | 1363 |  |  | 1346 |  |  | 1384.5 |  |  | 1388 |  |  | 1403.5 |  |  | 1440 |  |  | 1348 |  |  | 1439.5 |  |  | 1359 |  |  | 1520.5 |  |  | 1399 |  |  | 1274 |  |  | 1379.5 |  |  | 1368 |  |  | 1416.5 |  |  | 1349 |  |  | 1333 |  |  | 1351.5 |  |  | 1364.5 |  |  | 1426 |  |  | 1320.5 |  |  | 1381.5 |  |  | 1396 |  |  | 1394 |  |  | 1545.5 |  |  | 1348.5 |  |  | 1331.5 |  |  | 1362 |  |  | 1432 |  |  | 1338 |  |  | 1418 |  |  | 1426 |  |  | 1417.5 |  |  | 1350 |  |  | 1282.5 |  |  | 1387.5 |  |  | 1450 |  |  | 1442 |  |  | 1468.5 |  |  | 1306.5 |  |  | 1338 |  |  | 1389.5 |  |  | 1342.5 |  |  | 1446 |  |  | 1312 |  |  | 1383 |  |  | 1298.5 |  |  | 1485 |  |  | 1344.5 |  |  | 1375.5 |  |  | 1325 |  |  | 1367.5 |  |  | 1277 |  |  | 1392 |  |  | 1383 |  |  | 1379 |  |  | 1295 |  |  | 1447 |  |  | 1485 |  |  | 1423 |  |  | 1506 |  |  | 1356 |  |  | 1350.5 |  |  | 1477.5 |  |  | 1340 |  |  | 1295 |  |  | 1460 |  |  | 1398.5 |  |  | 1438.5 |  |  | 1463.5 |  |  | 1333 |  |  | 1400 |  |  | 1452.5 |  |  | 1328.5 |  |  | 1266.5 |  |  | 1472 |  |  | 1456 |  |  | 1371 |  |  | 1325 |  |  | 1361 |  |  | 1340.5 |  |  | 1380.5 |  |  | 1445 |  |  | 1450 |  |  | 1343 |  |  | 1438 |  |  | 1345 |  |  | 1365.5 |  |  | 1365 |  |  | 1459 |  |  | 1410 |  |  | 1356 |  |  | 1331.5 |  |  | 1531 |  |  | 1416 |  |  | 1389 |  |  | 1439 |  |  | 1430.5 |  |  | 1504 |  |  | 1332 |  |  | 1287 |  |  | 1460.5 |  |  | 1374.5 |  |  | 1414.5 |  |  | 1475 |  |  | 1374 |  |  | 1326 |  |  | 1426 |  |  | 1395 |  |  | 1341.5 |  |  | 1420 |  |  | 1319.5 |  |  | 1421.5 |  |  | 1446.5 |  |  | 1375 |  |  | 1430.5 |  |  | 1354 |  |  | 1319 |  |  | 1349.5 |  |  | 1404.5 |  |  | 1452 |  |  | 1509.5 |  |  | 1431.5 |  |  | 1393 |  |  | 1470 |  |  | 1395.5 |  |  | 1347.5 |  |  | 1417 |  |  | 1396.5 |  |  | 1408 |  |  | 1319 |  |  | 1345.5 |  |  | 1410 |  |  | 1335 |  |  | 1380.5 |  |  | 1329 |  |  | 1439.5 |  |  | 1374 |  |  | 1513 |  |  | 1369 |  |  | 1302 |  |  | 1444.5 |  |  | 1507 |  |  | 1440.5 |  |  | 1311.5 |  |  | 1418.5 |  |  | 1476 |  |  | 1488.5 |  |  | 1511 |  |  | 1385 |  |  | 1287.5 |  |  | 1375.5 |  |  | 1381 |  |  | 1379.5 |  |  | 1405 |  |  | 1358 |  |  | 1511.5 |  |  | 1385 |  |  | 1358.5 |  |  | 1416.5 |  |  | 1413.5 |  |  | 1400 |  |  | 1336 |  |  | 1386 |  |  | 1242.5 |  |  | 1354 |  |  | 1451.5 |  |  | 1410 |  |  | 1404 |  |  | 1309 |  |  | 1418 |  |  | 1453 |  |  | 1407 |  |  | 1344 |  |  | 1505 |  |  | 1425 |  |  | 1398.5 |  |  | 1374 |  |  | 1396 |  |  | 1538.5 |  |  | 1304.5 |  |  | 1404.5 |  |  | 1448.5 |  |  | 1369 |  |  | 1499 |  |  | 1299.5 |  |  | 1431.5 |  |  | 1433.5 |  |  | 1416 |  |  | 1379 |  |  | 1414 |  |  | 1356 |  |  | 1309 |  |  | 1355 |  |  | 1401 |  |  | 1350.5 |  |  | 1359.5 |  |  | 1393 |  |  | 1405.5 |  |  | 1420.5 |  |  | 1295 |  |  | 1417 |  |  | 1331 |  |  | 1344 |  |  | 1337.5 |  |  | 1301.5 |  |  | 1375.5 |  |  | 1386 |  |  | 1349.5 |  |  | 1372 |  |  | 1336 |  |  | 1398 |  |  | 1282.5 |  |  | 1398 |  |  | 1275 |  |  | 1381.5 |  |  | 1353 |  |  | 1401.5 |  |  | 1476 |  |  | 1363.5 |  |  | 1281 |  |  | 1385.5 |  |  | 1411.5 |  |  | 1442 |  |  | 1376 |  |  | 1290 |  |  | 1353 |  |  | 1302.5 |  |  | 1340 |  |  | 1400 |  |  | 1322.5 |  |  | 1463.5 |  |  | 1319.5 |  |  | 1333 |  |  | 1389.5 |  |  | 1335.5 |  |  | 1356.5 |  |  | 1463 |  |  | 1396 |  |  | 1358.5 |  |  | 1433 |  |  | 1452 |  |  | 1368.5 |  |  | 1367 |  |  | 1462 |  |  | 1379 |  |  | 1289 |  |  | 1278.5 |  |  | 1478.5 |  |  | 1325 |  |  | 1409 |  |  | 1414 |  |  | 1361 |  |  | 1323 |  |  | 1349.5 |  |  | 1397.5 |  |  | 1358 |  |  | 1540 |  |  | 1492 |  |  | 1255.5 |  |  | 1449.5 |  |  | 1348 |  |  | 1349 |  |  | 1293 |  |  | 1397.5 |  |  | 1472.5 |  |  | 1389 |  |  | 1332 |  |  | 1420 |  |  | 1400 |  |  | 1355 |  |  | 1463 |  |  | 1360 |  |  | 1479.5 |  |  | 1264 |  |  | 1519 |  |  | 1375 |  |  | 1420.5 |  |  | 1468 |  |  | 1259 |  |  | 1248 |  |  | 1369 |  |  | 1399 |  |  | 1373 |  |  | 1366 |  |  | 1353.5 |  |  | 1382.5 |  |  | 1328.5 |  |  | 1386 |  |  | 1379 |  |  | 1391.5 |  |  | 1262 |  |  | 1330.5 |  |  | 1326.5 |  |  | 1298 |  |  | 1376 |  |  | 1458.5 |  |  | 1357 |  |  | 1431 |  |  | 1441 |  |  | 1392 |  |  | 1359 |  |  | 1336 |  |  | 1361 |  |  | 1490.5 |  |  | 1403 |  |  | 1367 |  |  | 1483 |  |  | 1350 |  |  | 1433 |  |  | 1278 |  |  | 1517 |  |  | 1440 |  |  | 1379 |  |  | 1514.5 |  |  | 1403.5 |  |  | 1334.5 |  |  | 1376.5 |  |  | 1401 |  |  | 1298 |  |  | 1496.5 |  |  | 1412 |  |  | 1377 |  |  | 1359.5 |  |  | 1433.5 |  |  | 1410 |  |  | 1365.5 |  |  | 1338.5 |  |  | 1291 |  |  | 1451 |  |  | 1394 |  |  | 1348 |  |  | 1424.5 |  |  | 1340 |  |  | 1356.5 |  |  | 1308.5 |  |  | 1300 |  |  | 1326 |  |  | 1393.5 |  |  | 1352 |  |  | 1418.5 |  |  | 1367 |  |  | 1355.5 |  |  | 1316.5 |  |  | 1336.5 |  |  | 1396.5 |  |  | 1393.5 |  |  | 1296 |  |  | 1319 |  |  | 1480.5 |  |  | 1429 |  |  | 1361 |  |  | 1351 |  |  | 1431 |  |  | 1462.5 |  |  | 1230 |  |  | 1345 |  |  | 1409 |  |  | 1414.5 |  |  | 1405 |  |  | 1347 |  |  | 1408 |  |  | 1525.5 |  |  | 1365 |  |  | 1265 |  |  | 1401 |  |  | 1427 |  |  | 1614.5 |  |  | 1401 |  |  | 1338.5 |  |  | 1368 |  |  | 1396 |  |  | 1565.5 |  |  | 1442 |  |  | 1313 |  |  | 1304.5 |  |  | 1417 |  |  | 1365 |  |  | 1385 |  |  | 1446.5 |  |  | 1378.5 |  |  | 1395 |  |  | 1336 |  |  | 1382.5 |  |  | 1440.5 |  |  | 1315 |  |  | 1484 |  |  | 1477.5 |  |  | 1449.5 |  |  | 1310.5 |  |  | 1367.5 |  |  | 1378.5 |  |  | 1535 |  |  | 1399.5 |  |  | 1382 |  |  | 1368 |  |  | 1427 |  |  | 1401 |  |  | 1458.5 |  |  | 1395 |  |  | 1338 |  |  | 1368.5 |  |  | 1323.5 |  |  | 1327 |  |  | 1405.5 |  |  | 1389.5 |  |  | 1446 |  |  | 1338 |  |  | 1384 |  |  | 1401.5 |  |  | 1379 |  |  | 1379.5 |  |  | 1403 |  |  | 1429 |  |  | 1562.5 |  |  | 1373 |  |  | 1537 |  |  | 1346 |  |  | 1385 |  |  | 1436 |  |  | 1396 |  |  | 1357 |  |  | 1362 |  |  | 1302.5 |  |  | 1414.5 |  |  | 1426 |  |  | 1378.5 |  |  | 1266.5 |  |  | 1324 |  |  | 1255 |  |  | 1422 |  |  | 1467.5 |  |  | 1330.5 |  |  | 1370 |  |  | 1456 |  |  | 1310 |  |  | 1269 |  |  | 1388 |  |  | 1339 |  |  | 1534 |  |  | 1381.5 |  |  | 1428 |  |  | 1410 |  |  | 1508 |  |  | 1346 |  |  | 1281 |  |  | 1411.5 |  |  | 1530.5 |  |  | 1280.5 |  |  | 1319 |  |  | 1333 |  |  | 1261.5 |  |  | 1473.5 |  |  | 1447.5 |  |  | 1372 |  |  | 1422.5 |  |  | 1373.5 |  |  | 1383 |  |  | 1356.5 |  |  | 1440.5 |  |  | 1345 |  |  | 1340 |  |  | 1409 |  |  | 1396 |  |  | 1346 |  |  | 1287 |  |  | 1403 |  |  | 1466 |  |  | 1366 |  |  | 1314 |  |  | 1459.5 |  |  | 1349 |  |  | 1439 |  |  | 1262 |  |  | 1341.5 |  |  | 1412 |  |  | 1384.5 |  |  | 1450 |  |  | 1406 |  |  | 1382 |  |  | 1394 |  |  | 1476.5 |  |  | 1347 |  |  | 1305 |  |  | 1473.5 |  |  | 1429 |  |  | 1367 |  |  | 1327.5 |  |  | 1380.5 |  |  | 1417 |  |  | 1308.5 |  |  | 1471 |  |  | 1368.5 |  |  | 1478 |  |  | 1426 |  |  | 1372.5 |  |  | 1477.5 |  |  | 1367 |  |  | 1424 |  |  | 1393 |  |  | 1447 |  |  | 1275 |  |  | 1421 |  |  | 1259 |  |  | 1328 |  |  | 1506.5 |  |  | 1267 |  |  | 1474.5 |  |  | 1350 |  |  | 1439.5 |  |  | 1345.5 |  |  | 1329 |  |  | 1432 |  |  | 1407.5 |  |  | 1417 |  |  | 1433 |  |  | 1424 |  |  | 1364.5 |  |  | 1467 |  |  | 1266.5 |  |  | 1291 |  |  | 1338 |  |  | 1357 |  |  | 1451 |  |  | 1515.5 |  |  | 1335 |  |  | 1385 |  |  | 1389 |  |  | 1329.5 |  |  | 1482 |  |  | 1421 |  |  | 1431 |  |  | 1352 |  |  | 1373.5 |  |  | 1336.5 |  |  | 1414 |  |  | 1451 |  |  | 1411 |  |  | 1431.5 |  |  | 1410 |  |  | 1359 |  |  | 1287 |  |  | 1502.5 |  |  | 1377.5 |  |  | 1427.5 |  |  | 1369 |  |  | 1461 |  |  | 1356 |  |  | 1344.5 |  |  | 1404 |  |  | 1367.5 |  |  | 1234 |  |  | 1320 |  |  | 1405 |  |  | 1354.5 |  |  | 1388.5 |  |  | 1410 |  |  | 1339 |  |  | 1423.5 |  |  | 1365 |  |  | 1417 |  |  | 1462.5 |  |  | 1355 |  |  | 1349 |  |  | 1421.5 |  |  | 1330 |  |  | 1415 |  |  | 1380.5 |  |  | 1441 |  |  | 1315.5 |  |  | 1429 |  |  | 1306.5 |  |  | 1424.5 |  |  | 1308 |  |  | 1479 |  |  | 1414.5 |  |  | 1395.5 |  |  | 1501 |  |  | 1367 |  |  | 1476 |  |  | 1355.5 |  |  | 1387 |  |  | 1275 |  |  | 1406 |  |  | 1470.5 |  |  | 1419.5 |  |  | 1423 |  |  | 1459 |  |  | 1326 |  |  | 1321 |  |  | 1464 |  |  | 1380 |  |  | 1393 |  |  | 1341.5 |  |  | 1391.5 |  |  | 1308.5 |  |  | 1384 |  |  | 1332.5 |  |  | 1403 |  |  | 1332 |  |  | 1396.5 |  |  | 1305.5 |  |  | 1224 |  |  | 1393 |  |  | 1322.5 |  |  | 1362 |  |  | 1403 |  |  | 1307.5 |  |  | 1339.5 |  |  | 1374 |  |  | 1389 |  |  | 1453 |  |  | 1295.5 |  |  | 1351 |  |  | 1263 |  |  | 1388 |  |  | 1375 |  |  | 1479 |  |  | 1361.5 |  |  | 1458 |  |  | 1348 |  |  | 1246 |  |  | 1513.5 |  |  | 1396 |  |  | 1368.5 |  |  | 1300.5 |  |  | 1363 |  |  | 1373 |  |  | 1373.5 |  |  | 1329.5 |  |  | 1345.5 |  |  | 1361.5 |  |  | 1422.5 |  |  | 1422 |  |  | 1351 |  |  | 1415.5 |  |  | 1372.5 |  |  | 1393 |  |  | 1324 |  |  | 1360.5 |  |  | 1437 |  |  | 1367 |  |  | 1277 |  |  | 1387.5 |  |  | 1491 |  |  | 1320.5 |  |  | 1286 |  |  | 1383.5 |  |  | 1437.5 |  |  | 1504.5 |  |  | 1383 |  |  | 1333 |  |  | 1456.5 |  |  | 1321.5 |  |  | 1426 |  |  | 1413 |  |  | 1360.5 |  |  | 1384 |  |  | 1393.5 |  |  | 1363.5 |  |  | 1415 |  |  | 1379 |  |  | 1350.5 |  |  | 1482.5 |  |  | 1341 |  |  | 1342.5 |  |  | 1430.5 |  |  | 1336 |  |  | 1472 |  |  | 1498 |  |  | 1371.5 |  |  | 1442 |  |  | 1368 |  |  | 1397 |  |  | 1374 |  |  | 1416 |  |  | 1330 |  |  | 1471.5 |  |  | 1327.5 |  |  | 1348 |  |  | 1285 |  |  | 1399 |  |  | 1391.5 |  |  | 1390 |  |  | 1467 |  |  | 1351.5 |  |  | 1378.5 |  |  | 1377 |  |  | 1347.5 |  |  | 1390 |  |  | 1310 |  |  | 1404 |  |  | 1520.5 |  |  | 1484 |  |  | 1281.5 |  |  | 1324.5 |  |  | 1308 |  |  | 1441.5 |  |  | 1263.5 |  |  | 1319 |  |  | 1313 |  |  | 1511 |  |  | 1301.5 |  |  | 1290 |  |  | 1364.5 |  |  | 1349.5 |  |  | 1440 |  |  | 1336.5 |  |  | 1322 |  |  | 1388 |  |  | 1341 |  |  | 1303 |  |  | 1322 |  |  | 1468.5 |  |  | 1417 |  |  | 1459 |  |  | 1320 |  |  | 1460 |  |  | 1356.5 |  |  | 1448.5 |  |  | 1333 |  |  | 1375 |  |  | 1355 |  |  | 1326 |  |  | 1429 |  |  | 1406.5 |  |  | 1414 |  |  | 1381.5 |  |  | 1481 |  |  | 1290 |  |  | 1365 |  |  | 1328 |  |  | 1336.5 |  |  | 1323 |  |  | 1351.5 |  |  | 1314 |  |  | 1452 |  |  | 1426 |  |  | 1320.5 |  |  | 1339 |  |  | 1325 |  |  | 1273 |  |  | 1529 |  |  | 1464 |  |  | 1384.5 |  |  | 1412.5 |  |  | 1357 |  |  | 1348.5 |  |  | 1276 |  |  | 1278.5 |  |  | 1378.5 |  |  | 1347.5 |  |  | 1411.5 |  |  | 1301 |  |  | 1444 |  |  | 1324 |  |  | 1326 |  |  | 1406 |  |  | 1352 |  |  | 1336.5 |  |  | 1355.5 |  |  | 1384.5 |  |  | 1456 |  |  | 1389.5 |  |  | 1391.5 |  |  | 1401.5 |  |  | 1356.5 |  |  | 1346 |  |  | 1385.5 |  |  | 1351.5 |  |  | 1414 |  |  | 1326.5 |  |  | 1412.5 |  |  | 1419.5 |  |  | 1420 |  |  | 1408.5 |  |  | 1370 |  |  | 1398 |  |  | 1389.5 |  |  | 1393.5 |  |  | 1425 |  |  | 1409 |  |  | 1282.5 |  |  | 1316.5 |  |  | 1408.5 |  |  | 1384 |  |  | 1357 |  |  | 1322 |  |  | 1405.5 |  |  | 1416.5 |  |  | 1398 |  |  | 1412.5 |  |  | 1294 |  |  | 1349 |  |  | 1417.5 |  |  | 1269.5 |  |  | 1368 |  |  | 1375.5 |  |  | 1340 |  |  | 1294.5 |  |  | 1486.5 |  |  | 1414 |  |  | 1295.5 |  |  | 1401 |  |  | 1387.5 |  |  | 1370 |  |  | 1397 |  |  | 1464 |  |  | 1347.5 |  |  | 1279.5 |  |  | 1409 |  |  | 1329 |  |  | 1325 |  |  | 1366.5 |  |  | 1344.5 |  |  | 1432 |  |  | 1348.5 |  |  | 1342 |  |  | 1314.5 |  |  | 1403.5 |  |  | 1332 |  |  | 1317 |  |  | 1384 |  |  | 1396.5 |  |  | 1359 |  |  | 1455.5 |  |  | 1438 |  |  | 1364.5 |  |  | 1512 |  |  | 1241.5 |  |  | 1364 |  |  | 1328.5 |  |  | 1377.5 |  |  | 1377 |  |  | 1343 |  |  | 1409 |  |  | 1366 |  |  | 1417.5 |  |  | 1323 |  |  | 1353.5 |  |  | 1300 |  |  | 1339 |  |  | 1361 |  |  | 1421 |  |  | 1464 |  |  | 1379 |  |  | 1349 |  |  | 1436.5 |  |  | 1285 |  |  | 1444
50 |  | 1501.5 |  |  | 1482 |  |  | 1436.5 |  |  | 1408 |  |  | 1417.5 |  |  | 1420 |  |  | 1417 |  |  | 1513 |  |  | 1367.5 |  |  | 1412 |  |  | 1364 |  |  | 1523 |  |  | 1432 |  |  | 1471 |  |  | 1356.5 |  |  | 1452.5 |  |  | 1365 |  |  | 1475 |  |  | 1526 |  |  | 1335.5 |  |  | 1474 |  |  | 1454 |  |  | 1390 |  |  | 1457 |  |  | 1401.5 |  |  | 1528 |  |  | 1454 |  |  | 1341 |  |  | 1432 |  |  | 1357 |  |  | 1339 |  |  | 1437.5 |  |  | 1532.5 |  |  | 1397.5 |  |  | 1316 |  |  | 1324.5 |  |  | 1365.5 |  |  | 1457.5 |  |  | 1438 |  |  | 1364 |  |  | 1316.5 |  |  | 1313 |  |  | 1492.5 |  |  | 1439.5 |  |  | 1459.5 |  |  | 1531.5 |  |  | 1512.5 |  |  | 1396 |  |  | 1290 |  |  | 1335.5 |  |  | 1389 |  |  | 1344.5 |  |  | 1351.5 |  |  | 1450 |  |  | 1355 |  |  | 1396 |  |  | 1375 |  |  | 1483 |  |  | 1457 |  |  | 1384.5 |  |  | 1501.5 |  |  | 1449.5 |  |  | 1277 |  |  | 1452 |  |  | 1302 |  |  | 1347.5 |  |  | 1397 |  |  | 1439.5 |  |  | 1404.5 |  |  | 1513.5 |  |  | 1343 |  |  | 1445 |  |  | 1428 |  |  | 1391.5 |  |  | 1462.5 |  |  | 1383.5 |  |  | 1491.5 |  |  | 1437.5 |  |  | 1458.5 |  |  | 1436.5 |  |  | 1408.5 |  |  | 1347 |  |  | 1415 |  |  | 1416 |  |  | 1501.5 |  |  | 1459 |  |  | 1331.5 |  |  | 1367 |  |  | 1411 |  |  | 1407.5 |  |  | 1456.5 |  |  | 1386 |  |  | 1623 |  |  | 1374.5 |  |  | 1490 |  |  | 1356.5 |  |  | 1396.5 |  |  | 1407.5 |  |  | 1383.5 |  |  | 1351.5 |  |  | 1454 |  |  | 1376 |  |  | 1325 |  |  | 1484.5 |  |  | 1379.5 |  |  | 1428.5 |  |  | 1390.5 |  |  | 1455 |  |  | 1375 |  |  | 1423.5 |  |  | 1324 |  |  | 1415.5 |  |  | 1448 |  |  | 1437 |  |  | 1333.5 |  |  | 1394 |  |  | 1361 |  |  | 1389 |  |  | 1373 |  |  | 1486.5 |  |  | 1387.5 |  |  | 1366.5 |  |  | 1544 |  |  | 1347 |  |  | 1334 |  |  | 1353 |  |  | 1369.5 |  |  | 1417 |  |  | 1460.5 |  |  | 1436 |  |  | 1367 |  |  | 1436.5 |  |  | 1322.5 |  |  | 1303 |  |  | 1371.5 |  |  | 1376 |  |  | 1436 |  |  | 1426 |  |  | 1391 |  |  | 1390 |  |  | 1324 |  |  | 1360 |  |  | 1431 |  |  | 1353 |  |  | 1328.5 |  |  | 1385 |  |  | 1301 |  |  | 1407 |  |  | 1420 |  |  | 1321 |  |  | 1378 |  |  | 1370 |  |  | 1423.5 |  |  | 1417 |  |  | 1427.5 |  |  | 1464 |  |  | 1372 |  |  | 1454.5 |  |  | 1388 |  |  | 1559.5 |  |  | 1438 |  |  | 1313 |  |  | 1426.5 |  |  | 1415 |  |  | 1463.5 |  |  | 1388 |  |  | 1354 |  |  | 1375.5 |  |  | 1385.5 |  |  | 1452 |  |  | 1346.5 |  |  | 1420.5 |  |  | 1435 |  |  | 1409 |  |  | 1571.5 |  |  | 1374.5 |  |  | 1357.5 |  |  | 1409 |  |  | 1471 |  |  | 1377 |  |  | 1447 |  |  | 1450 |  |  | 1446.5 |  |  | 1374 |  |  | 1297.5 |  |  | 1434.5 |  |  | 1476 |  |  | 1481 |  |  | 1497.5 |  |  | 1330.5 |  |  | 1377 |  |  | 1410.5 |  |  | 1366.5 |  |  | 1467 |  |  | 1333 |  |  | 1409 |  |  | 1324.5 |  |  | 1514 |  |  | 1383.5 |  |  | 1390.5 |  |  | 1351 |  |  | 1382.5 |  |  | 1292 |  |  | 1418 |  |  | 1422 |  |  | 1400 |  |  | 1342 |  |  | 1473 |  |  | 1506 |  |  | 1449 |  |  | 1521 |  |  | 1395 |  |  | 1389.5 |  |  | 1516.5 |  |  | 1387 |  |  | 1319 |  |  | 1475 |  |  | 1437.5 |  |  | 1467.5 |  |  | 1478.5 |  |  | 1372 |  |  | 1439 |  |  | 1491.5 |  |  | 1367.5 |  |  | 1287.5 |  |  | 1511 |  |  | 1495 |  |  | 1410 |  |  | 1351 |  |  | 1387 |  |  | 1379.5 |  |  | 1401.5 |  |  | 1492 |  |  | 1465 |  |  | 1364 |  |  | 1477 |  |  | 1369 |  |  | 1391.5 |  |  | 1394 |  |  | 1480 |  |  | 1434 |  |  | 1403 |  |  | 1378.5 |  |  | 1557 |  |  | 1463 |  |  | 1413 |  |  | 1478 |  |  | 1459.5 |  |  | 1543 |  |  | 1371 |  |  | 1326 |  |  | 1475.5 |  |  | 1421.5 |  |  | 1440.5 |  |  | 1522 |  |  | 1395 |  |  | 1350 |  |  | 1465 |  |  | 1424 |  |  | 1356.5 |  |  | 1459 |  |  | 1334.5 |  |  | 1468.5 |  |  | 1493.5 |  |  | 1399 |  |  | 1469.5 |  |  | 1383 |  |  | 1334 |  |  | 1370.5 |  |  | 1419.5 |  |  | 1467 |  |  | 1535.5 |  |  | 1457.5 |  |  | 1419 |  |  | 1496 |  |  | 1421.5 |  |  | 1371.5 |  |  | 1438 |  |  | 1435.5 |  |  | 1437 |  |  | 1345 |  |  | 1374.5 |  |  | 1436 |  |  | 1382 |  |  | 1419.5 |  |  | 1358 |  |  | 1468.5 |  |  | 1398 |  |  | 1552 |  |  | 1390 |  |  | 1341 |  |  | 1468.5 |  |  | 1546 |  |  | 1479.5 |  |  | 1337.5 |  |  | 1457.5 |  |  | 1523 |  |  | 1535.5 |  |  | 1535 |  |  | 1424 |  |  | 1311.5 |  |  | 1414.5 |  |  | 1428 |  |  | 1403.5 |  |  | 1444 |  |  | 1405 |  |  | 1558.5 |  |  | 1414 |  |  | 1405.5 |  |  | 1463.5 |  |  | 1452.5 |  |  | 1415 |  |  | 1375 |  |  | 1425 |  |  | 1257.5 |  |  | 1369 |  |  | 1477.5 |  |  | 1436 |  |  | 1428 |  |  | 1348 |  |  | 1433 |  |  | 1482 |  |  | 1436 |  |  | 1383 |  |  | 1544 |  |  | 1440 |  |  | 1419.5 |  |  | 1400 |  |  | 1420 |  |  | 1559.5 |  |  | 1330.5 |  |  | 1425.5 |  |  | 1469.5 |  |  | 1390 |  |  | 1525 |  |  | 1328.5 |  |  | 1470.5 |  |  | 1448.5 |  |  | 1445 |  |  | 1408 |  |  | 1429 |  |  | 1382 |  |  | 1333 |  |  | 1394 |  |  | 1427 |  |  | 1397.5 |  |  | 1388.5 |  |  | 1417 |  |  | 1426.5 |  |  | 1441.5 |  |  | 1319 |  |  | 1464 |  |  | 1352 |  |  | 1383 |  |  | 1366.5 |  |  | 1327.5 |  |  | 1422.5 |  |  | 1412 |  |  | 1373.5 |  |  | 1411 |  |  | 1357 |  |  | 1437 |  |  | 1297.5 |  |  | 1419 |  |  | 1314 |  |  | 1420.5 |  |  | 1368 |  |  | 1448.5 |  |  | 1500 |  |  | 1384.5 |  |  | 1305 |  |  | 1406.5 |  |  | 1450.5 |  |  | 1481 |  |  | 1415 |  |  | 1329 |  |  | 1368 |  |  | 1328.5 |  |  | 1364 |  |  | 1447 |  |  | 1351.5 |  |  | 1484.5 |  |  | 1358.5 |  |  | 1372 |  |  | 1428.5 |  |  | 1374.5 |  |  | 1371.5 |  |  | 1478 |  |  | 1411 |  |  | 1397.5 |  |  | 1448 |  |  | 1478 |  |  | 1389.5 |  |  | 1382 |  |  | 1486 |  |  | 1408 |  |  | 1328 |  |  | 1293.5 |  |  | 1525.5 |  |  | 1340 |  |  | 1430 |  |  | 1438 |  |  | 1382 |  |  | 1370 |  |  | 1378.5 |  |  | 1412.5 |  |  | 1379 |  |  | 1579 |  |  | 1521 |  |  | 1270.5 |  |  | 1488.5 |  |  | 1377 |  |  | 1370 |  |  | 1332 |  |  | 1444.5 |  |  | 1493.5 |  |  | 1410 |  |  | 1356 |  |  | 1467 |  |  | 1424 |  |  | 1379 |  |  | 1510 |  |  | 1386 |  |  | 1505.5 |  |  | 1311 |  |  | 1558 |  |  | 1414 |  |  | 1459.5 |  |  | 1494 |  |  | 1283 |  |  | 1263 |  |  | 1393 |  |  | 1423 |  |  | 1420 |  |  | 1405 |  |  | 1368.5 |  |  | 1403.5 |  |  | 1349.5 |  |  | 1415 |  |  | 1403 |  |  | 1420.5 |  |  | 1277 |  |  | 1356.5 |  |  | 1347.5 |  |  | 1345 |  |  | 1402 |  |  | 1473.5 |  |  | 1378 |  |  | 1446 |  |  | 1470 |  |  | 1413 |  |  | 1406 |  |  | 1360 |  |  | 1390 |  |  | 1514.5 |  |  | 1432 |  |  | 1406 |  |  | 1498 |  |  | 1389 |  |  | 1457 |  |  | 1302 |  |  | 1546 |  |  | 1464 |  |  | 1418 |  |  | 1538.5 |  |  | 1432.5 |  |  | 1349.5 |  |  | 1415.5 |  |  | 1440 |  |  | 1322 |  |  | 1535.5 |  |  | 1438 |  |  | 1392 |  |  | 1406.5 |  |  | 1472.5 |  |  | 1436 |  |  | 1389.5 |  |  | 1353.5 |  |  | 1338 |  |  | 1490 |  |  | 1433 |  |  | 1374 |  |  | 1439.5 |  |  | 1369 |  |  | 1380.5 |  |  | 1355.5 |  |  | 1321 |  |  | 1347 |  |  | 1422.5 |  |  | 1378 |  |  | 1439.5 |  |  | 1393 |  |  | 1394.5 |  |  | 1340.5 |  |  | 1383.5 |  |  | 1435.5 |  |  | 1419.5 |  |  | 1320 |  |  | 1334 |  |  | 1504.5 |  |  | 1453 |  |  | 1376 |  |  | 1377 |  |  | 1470 |  |  | 1491.5 |  |  | 1251 |  |  | 1392 |  |  | 1438 |  |  | 1435.5 |  |  | 1431 |  |  | 1362 |  |  | 1429 |  |  | 1572.5 |  |  | 1412 |  |  | 1294 |  |  | 1422 |  |  | 1451 |  |  | 1661.5 |  |  | 1440 |  |  | 1353.5 |  |  | 1415 |  |  | 1435 |  |  | 1594.5 |  |  | 1481 |  |  | 1339 |  |  | 1328.5 |  |  | 1441 |  |  | 1404 |  |  | 1411 |  |  | 1467.5 |  |  | 1393.5 |  |  | 1442 |  |  | 1362 |  |  | 1421.5 |  |  | 1479.5 |  |  | 1341 |  |  | 1499 |  |  | 1492.5 |  |  | 1464.5 |  |  | 1349.5 |  |  | 1414.5 |  |  | 1393.5 |  |  | 1574 |  |  | 1428.5 |  |  | 1403 |  |  | 1397 |  |  | 1466 |  |  | 1448 |  |  | 1479.5 |  |  | 1424 |  |  | 1362 |  |  | 1415.5 |  |  | 1362.5 |  |  | 1356 |  |  | 1444.5 |  |  | 1413.5 |  |  | 1467 |  |  | 1359 |  |  | 1413 |  |  | 1440.5 |  |  | 1405 |  |  | 1418.5 |  |  | 1442 |  |  | 1458 |  |  | 1601.5 |  |  | 1412 |  |  | 1584 |  |  | 1385 |  |  | 1400 |  |  | 1462 |  |  | 1420 |  |  | 1404 |  |  | 1409 |  |  | 1331.5 |  |  | 1429.5 |  |  | 1447 |  |  | 1417.5 |  |  | 1290.5 |  |  | 1371 |  |  | 1281 |  |  | 1461 |  |  | 1491.5 |  |  | 1354.5 |  |  | 1396 |  |  | 1480 |  |  | 1325 |  |  | 1298 |  |  | 1412 |  |  | 1378 |  |  | 1581 |  |  | 1410.5 |  |  | 1475 |  |  | 1436 |  |  | 1534 |  |  | 1393 |  |  | 1296 |  |  | 1440.5 |  |  | 1556.5 |  |  | 1306.5 |  |  | 1348 |  |  | 1357 |  |  | 1300.5 |  |  | 1499.5 |  |  | 1471.5 |  |  | 1398 |  |  | 1461.5 |  |  | 1388.5 |  |  | 1422 |  |  | 1380.5 |  |  | 1479.5 |  |  | 1392 |  |  | 1379 |  |  | 1424 |  |  | 1422 |  |  | 1385 |  |  | 1316 |  |  | 1424 |  |  | 1513 |  |  | 1405 |  |  | 1335 |  |  | 1485.5 |  |  | 1375 |  |  | 1454 |  |  | 1309 |  |  | 1380.5 |  |  | 1436 |  |  | 1413.5 |  |  | 1465 |  |  | 1445 |  |  | 1411 |  |  | 1415 |  |  | 1515.5 |  |  | 1371 |  |  | 1320 |  |  | 1499.5 |  |  | 1458 |  |  | 1406 |  |  | 1356.5 |  |  | 1409.5 |  |  | 1456 |  |  | 1355.5 |  |  | 1510 |  |  | 1389.5 |  |  | 1517 |  |  | 1473 |  |  | 1401.5 |  |  | 1516.5 |  |  | 1391 |  |  | 1439 |  |  | 1432 |  |  | 1462 |  |  | 1299 |  |  | 1436 |  |  | 1298 |  |  | 1354 |  |  | 1521.5 |  |  | 1306 |  |  | 1521.5 |  |  | 1365 |  |  | 1460.5 |  |  | 1360.5 |  |  | 1355 |  |  | 1456 |  |  | 1446.5 |  |  | 1464 |  |  | 1472 |  |  | 1448 |  |  | 1393.5 |  |  | 1496 |  |  | 1313.5 |  |  | 1315 |  |  | 1377 |  |  | 1383 |  |  | 1490 |  |  | 1554.5 |  |  | 1356 |  |  | 1400 |  |  | 1410 |  |  | 1368.5 |  |  | 1506 |  |  | 1450 |  |  | 1446 |  |  | 1391 |  |  | 1399.5 |  |  | 1365.5 |  |  | 1429 |  |  | 1475 |  |  | 1426 |  |  | 1455.5 |  |  | 1449 |  |  | 1380 |  |  | 1334 |  |  | 1541.5 |  |  | 1403.5 |  |  | 1466.5 |  |  | 1398 |  |  | 1476 |  |  | 1371 |  |  | 1373.5 |  |  | 1428 |  |  | 1406.5 |  |  | 1263 |  |  | 1346 |  |  | 1431 |  |  | 1369.5 |  |  | 1414.5 |  |  | 1457 |  |  | 1360 |  |  | 1462.5 |  |  | 1391 |  |  | 1441 |  |  | 1509.5 |  |  | 1381 |  |  | 1364 |  |  | 1445.5 |  |  | 1356 |  |  | 1441 |  |  | 1401.5 |  |  | 1470 |  |  | 1354.5 |  |  | 1455 |  |  | 1345.5 |  |  | 1450.5 |  |  | 1329 |  |  | 1505 |  |  | 1438.5 |  |  | 1434.5 |  |  | 1522 |  |  | 1393 |  |  | 1500 |  |  | 1376.5 |  |  | 1426 |  |  | 1296 |  |  | 1445 |  |  | 1496.5 |  |  | 1443.5 |  |  | 1452 |  |  | 1483 |  |  | 1341 |  |  | 1336 |  |  | 1511 |  |  | 1419 |  |  | 1408 |  |  | 1365.5 |  |  | 1430.5 |  |  | 1355.5 |  |  | 1423 |  |  | 1347.5 |  |  | 1450 |  |  | 1347 |  |  | 1435.5 |  |  | 1344.5 |  |  | 1263 |  |  | 1422 |  |  | 1369.5 |  |  | 1401 |  |  | 1450 |  |  | 1336.5 |  |  | 1378.5 |  |  | 1389 |  |  | 1415 |  |  | 1500 |  |  | 1310.5 |  |  | 1398 |  |  | 1278 |  |  | 1427 |  |  | 1390 |  |  | 1500 |  |  | 1387.5 |  |  | 1497 |  |  | 1369 |  |  | 1275 |  |  | 1528.5 |  |  | 1420 |  |  | 1392.5 |  |  | 1324.5 |  |  | 1387 |  |  | 1412 |  |  | 1402.5 |  |  | 1353.5 |  |  | 1392.5 |  |  | 1400.5 |  |  | 1446.5 |  |  | 1437 |  |  | 1372 |  |  | 1430.5 |  |  | 1411.5 |  |  | 1432 |  |  | 1371 |  |  | 1399.5 |  |  | 1452 |  |  | 1414 |  |  | 1301 |  |  | 1426.5 |  |  | 1515 |  |  | 1349.5 |  |  | 1307 |  |  | 1404.5 |  |  | 1476.5 |  |  | 1551.5 |  |  | 1412 |  |  | 1372 |  |  | 1485.5 |  |  | 1368.5 |  |  | 1452 |  |  | 1452 |  |  | 1389.5 |  |  | 1413 |  |  | 1432.5 |  |  | 1387.5 |  |  | 1441 |  |  | 1405 |  |  | 1376.5 |  |  | 1508.5 |  |  | 1370 |  |  | 1389.5 |  |  | 1445.5 |  |  | 1383 |  |  | 1498 |  |  | 1527 |  |  | 1418.5 |  |  | 1463 |  |  | 1407 |  |  | 1426 |  |  | 1395 |  |  | 1442 |  |  | 1369 |  |  | 1492.5 |  |  | 1366.5 |  |  | 1377 |  |  | 1324 |  |  | 1438 |  |  | 1417.5 |  |  | 1411 |  |  | 1514 |  |  | 1375.5 |  |  | 1404.5 |  |  | 1416 |  |  | 1376.5 |  |  | 1429 |  |  | 1331 |  |  | 1451 |  |  | 1559.5 |  |  | 1508 |  |  | 1305.5 |  |  | 1363.5 |  |  | 1337 |  |  | 1488.5 |  |  | 1292.5 |  |  | 1358 |  |  | 1337 |  |  | 1558 |  |  | 1316.5 |  |  | 1337 |  |  | 1385.5 |  |  | 1388.5 |  |  | 1455 |  |  | 1357.5 |  |  | 1348 |  |  | 1427 |  |  | 1370 |  |  | 1327 |  |  | 1337 |  |  | 1497.5 |  |  | 1456 |  |  | 1498 |  |  | 1359 |  |  | 1484 |  |  | 1377.5 |  |  | 1477.5 |  |  | 1362 |  |  | 1414 |  |  | 1381 |  |  | 1352 |  |  | 1468 |  |  | 1435.5 |  |  | 1461 |  |  | 1420.5 |  |  | 1505 |  |  | 1305 |  |  | 1404 |  |  | 1352 |  |  | 1375.5 |  |  | 1362 |  |  | 1372.5 |  |  | 1329 |  |  | 1478 |  |  | 1447 |  |  | 1346.5 |  |  | 1360 |  |  | 1346 |  |  | 1312 |  |  | 1555 |  |  | 1503 |  |  | 1399.5 |  |  | 1441.5 |  |  | 1396 |  |  | 1372.5 |  |  | 1315 |  |  | 1293.5 |  |  | 1425.5 |  |  | 1368.5 |  |  | 1440.5 |  |  | 1316 |  |  | 1470 |  |  | 1371 |  |  | 1347 |  |  | 1453 |  |  | 1373 |  |  | 1375.5 |  |  | 1402.5 |  |  | 1423.5 |  |  | 1495 |  |  | 1436.5 |  |  | 1415.5 |  |  | 1448.5 |  |  | 1382.5 |  |  | 1372 |  |  | 1414.5 |  |  | 1398.5 |  |  | 1440 |  |  | 1365.5 |  |  | 1451.5 |  |  | 1443.5 |  |  | 1459 |  |  | 1437.5 |  |  | 1409 |  |  | 1445 |  |  | 1410.5 |  |  | 1432.5 |  |  | 1454 |  |  | 1430 |  |  | 1311.5 |  |  | 1342.5 |  |  | 1434.5 |  |  | 1399 |  |  | 1383 |  |  | 1348 |  |  | 1434.5 |  |  | 1455.5 |  |  | 1445 |  |  | 1438.5 |  |  | 1315 |  |  | 1388 |  |  | 1432.5 |  |  | 1316.5 |  |  | 1392 |  |  | 1401.5 |  |  | 1361 |  |  | 1323.5 |  |  | 1510.5 |  |  | 1461 |  |  | 1342.5 |  |  | 1427 |  |  | 1426.5 |  |  | 1391 |  |  | 1436 |  |  | 1493 |  |  | 1373.5 |  |  | 1308.5 |  |  | 1448 |  |  | 1353 |  |  | 1349 |  |  | 1413.5 |  |  | 1383.5 |  |  | 1458 |  |  | 1387.5 |  |  | 1381 |  |  | 1353.5 |  |  | 1432.5 |  |  | 1347 |  |  | 1332 |  |  | 1423 |  |  | 1411.5 |  |  | 1380 |  |  | 1479.5 |  |  | 1453 |  |  | 1403.5 |  |  | 1559 |  |  | 1267.5 |  |  | 1388 |  |  | 1375.5 |  |  | 1406.5 |  |  | 1392 |  |  | 1364 |  |  | 1435 |  |  | 1405 |  |  | 1456.5 |  |  | 1344 |  |  | 1377.5 |  |  | 1326 |  |  | 1365 |  |  | 1387 |  |  | 1468 |  |  | 1490 |  |  | 1403 |  |  | 1396 |  |  | 1460.5 |  |  | 1332 |  |  | 1470
51 |  | 1516.5 |  |  | 1506 |  |  | 1465.5 |  |  | 1429 |  |  | 1464.5 |  |  | 1444 |  |  | 1441 |  |  | 1528 |  |  | 1396.5 |  |  | 1436 |  |  | 1393 |  |  | 1562 |  |  | 1471 |  |  | 1510 |  |  | 1385.5 |  |  | 1491.5 |  |  | 1386 |  |  | 1514 |  |  | 1565 |  |  | 1356.5 |  |  | 1503 |  |  | 1501 |  |  | 1411 |  |  | 1486 |  |  | 1427.5 |  |  | 1575 |  |  | 1501 |  |  | 1362 |  |  | 1471 |  |  | 1381 |  |  | 1378 |  |  | 1463.5 |  |  | 1547.5 |  |  | 1426.5 |  |  | 1342 |  |  | 1363.5 |  |  | 1404.5 |  |  | 1472.5 |  |  | 1453 |  |  | 1403 |  |  | 1363.5 |  |  | 1328 |  |  | 1513.5 |  |  | 1463.5 |  |  | 1506.5 |  |  | 1552.5 |  |  | 1536.5 |  |  | 1420 |  |  | 1316 |  |  | 1356.5 |  |  | 1413 |  |  | 1368.5 |  |  | 1398.5 |  |  | 1497 |  |  | 1376 |  |  | 1422 |  |  | 1414 |  |  | 1509 |  |  | 1504 |  |  | 1399.5 |  |  | 1516.5 |  |  | 1475.5 |  |  | 1324 |  |  | 1499 |  |  | 1349 |  |  | 1386.5 |  |  | 1418 |  |  | 1465.5 |  |  | 1443.5 |  |  | 1542.5 |  |  | 1369 |  |  | 1471 |  |  | 1475 |  |  | 1415.5 |  |  | 1509.5 |  |  | 1422.5 |  |  | 1520.5 |  |  | 1466.5 |  |  | 1487.5 |  |  | 1460.5 |  |  | 1423.5 |  |  | 1368 |  |  | 1454 |  |  | 1442 |  |  | 1522.5 |  |  | 1480 |  |  | 1360.5 |  |  | 1406 |  |  | 1458 |  |  | 1446.5 |  |  | 1495.5 |  |  | 1433 |  |  | 1670 |  |  | 1389.5 |  |  | 1511 |  |  | 1403.5 |  |  | 1443.5 |  |  | 1422.5 |  |  | 1407.5 |  |  | 1372.5 |  |  | 1483 |  |  | 1405 |  |  | 1354 |  |  | 1499.5 |  |  | 1403.5 |  |  | 1467.5 |  |  | 1419.5 |  |  | 1470 |  |  | 1390 |  |  | 1462.5 |  |  | 1350 |  |  | 1444.5 |  |  | 1487 |  |  | 1452 |  |  | 1348.5 |  |  | 1420 |  |  | 1400 |  |  | 1415 |  |  | 1412 |  |  | 1507.5 |  |  | 1426.5 |  |  | 1381.5 |  |  | 1565 |  |  | 1386 |  |  | 1358 |  |  | 1379 |  |  | 1393.5 |  |  | 1456 |  |  | 1486.5 |  |  | 1465 |  |  | 1396 |  |  | 1460.5 |  |  | 1343.5 |  |  | 1329 |  |  | 1397.5 |  |  | 1405 |  |  | 1451 |  |  | 1450 |  |  | 1430 |  |  | 1405 |  |  | 1339 |  |  | 1384 |  |  | 1457 |  |  | 1392 |  |  | 1357.5 |  |  | 1424 |  |  | 1322 |  |  | 1446 |  |  | 1459 |  |  | 1345 |  |  | 1399 |  |  | 1394 |  |  | 1462.5 |  |  | 1443 |  |  | 1456.5 |  |  | 1503 |  |  | 1396 |  |  | 1480.5 |  |  | 1412 |  |  | 1598.5 |  |  | 1453 |  |  | 1328 |  |  | 1473.5 |  |  | 1441 |  |  | 1489.5 |  |  | 1427 |  |  | 1380 |  |  | 1414.5 |  |  | 1424.5 |  |  | 1491 |  |  | 1385.5 |  |  | 1459.5 |  |  | 1450 |  |  | 1456 |  |  | 1618.5 |  |  | 1398.5 |  |  | 1372.5 |  |  | 1438 |  |  | 1500 |  |  | 1401 |  |  | 1476 |  |  | 1479 |  |  | 1461.5 |  |  | 1395 |  |  | 1312.5 |  |  | 1460.5 |  |  | 1500 |  |  | 1510 |  |  | 1544.5 |  |  | 1354.5 |  |  | 1403 |  |  | 1431.5 |  |  | 1392.5 |  |  | 1506 |  |  | 1359 |  |  | 1435 |  |  | 1363.5 |  |  | 1553 |  |  | 1407.5 |  |  | 1411.5 |  |  | 1380 |  |  | 1421.5 |  |  | 1316 |  |  | 1465 |  |  | 1451 |  |  | 1421 |  |  | 1381 |  |  | 1488 |  |  | 1530 |  |  | 1475 |  |  | 1542 |  |  | 1424 |  |  | 1428.5 |  |  | 1545.5 |  |  | 1426 |  |  | 1334 |  |  | 1522 |  |  | 1476.5 |  |  | 1493.5 |  |  | 1504.5 |  |  | 1419 |  |  | 1460 |  |  | 1520.5 |  |  | 1396.5 |  |  | 1326.5 |  |  | 1550 |  |  | 1516 |  |  | 1436 |  |  | 1390 |  |  | 1434 |  |  | 1394.5 |  |  | 1427.5 |  |  | 1531 |  |  | 1486 |  |  | 1390 |  |  | 1516 |  |  | 1416 |  |  | 1417.5 |  |  | 1433 |  |  | 1504 |  |  | 1449 |  |  | 1450 |  |  | 1425.5 |  |  | 1572 |  |  | 1478 |  |  | 1428 |  |  | 1507 |  |  | 1488.5 |  |  | 1558 |  |  | 1400 |  |  | 1365 |  |  | 1514.5 |  |  | 1445.5 |  |  | 1464.5 |  |  | 1543 |  |  | 1421 |  |  | 1379 |  |  | 1504 |  |  | 1463 |  |  | 1377.5 |  |  | 1483 |  |  | 1373.5 |  |  | 1507.5 |  |  | 1522.5 |  |  | 1438 |  |  | 1508.5 |  |  | 1409 |  |  | 1373 |  |  | 1409.5 |  |  | 1434.5 |  |  | 1491 |  |  | 1559.5 |  |  | 1496.5 |  |  | 1458 |  |  | 1525 |  |  | 1445.5 |  |  | 1386.5 |  |  | 1477 |  |  | 1474.5 |  |  | 1458 |  |  | 1392 |  |  | 1421.5 |  |  | 1483 |  |  | 1406 |  |  | 1458.5 |  |  | 1405 |  |  | 1515.5 |  |  | 1437 |  |  | 1578 |  |  | 1414 |  |  | 1356 |  |  | 1515.5 |  |  | 1575 |  |  | 1508.5 |  |  | 1384.5 |  |  | 1478.5 |  |  | 1547 |  |  | 1582.5 |  |  | 1559 |  |  | 1463 |  |  | 1337.5 |  |  | 1438.5 |  |  | 1457 |  |  | 1427.5 |  |  | 1470 |  |  | 1429 |  |  | 1584.5 |  |  | 1435 |  |  | 1420.5 |  |  | 1478.5 |  |  | 1478.5 |  |  | 1439 |  |  | 1399 |  |  | 1454 |  |  | 1281.5 |  |  | 1395 |  |  | 1524.5 |  |  | 1475 |  |  | 1443 |  |  | 1374 |  |  | 1448 |  |  | 1521 |  |  | 1483 |  |  | 1407 |  |  | 1565 |  |  | 1461 |  |  | 1445.5 |  |  | 1439 |  |  | 1459 |  |  | 1580.5 |  |  | 1356.5 |  |  | 1440.5 |  |  | 1498.5 |  |  | 1405 |  |  | 1546 |  |  | 1354.5 |  |  | 1509.5 |  |  | 1469.5 |  |  | 1466 |  |  | 1455 |  |  | 1455 |  |  | 1429 |  |  | 1348 |  |  | 1441 |  |  | 1456 |  |  | 1426.5 |  |  | 1427.5 |  |  | 1446 |  |  | 1455.5 |  |  | 1467.5 |  |  | 1340 |  |  | 1493 |  |  | 1378 |  |  | 1422 |  |  | 1381.5 |  |  | 1374.5 |  |  | 1451.5 |  |  | 1438 |  |  | 1394.5 |  |  | 1450 |  |  | 1381 |  |  | 1466 |  |  | 1323.5 |  |  | 1443 |  |  | 1335 |  |  | 1449.5 |  |  | 1397 |  |  | 1477.5 |  |  | 1547 |  |  | 1399.5 |  |  | 1344 |  |  | 1427.5 |  |  | 1489.5 |  |  | 1502 |  |  | 1436 |  |  | 1344 |  |  | 1407 |  |  | 1375.5 |  |  | 1403 |  |  | 1494 |  |  | 1372.5 |  |  | 1510.5 |  |  | 1397.5 |  |  | 1396 |  |  | 1467.5 |  |  | 1389.5 |  |  | 1418.5 |  |  | 1504 |  |  | 1432 |  |  | 1426.5 |  |  | 1474 |  |  | 1502 |  |  | 1415.5 |  |  | 1406 |  |  | 1525 |  |  | 1429 |  |  | 1357 |  |  | 1317.5 |  |  | 1551.5 |  |  | 1364 |  |  | 1469 |  |  | 1477 |  |  | 1421 |  |  | 1396 |  |  | 1393.5 |  |  | 1436.5 |  |  | 1418 |  |  | 1594 |  |  | 1560 |  |  | 1317.5 |  |  | 1535.5 |  |  | 1398 |  |  | 1409 |  |  | 1347 |  |  | 1459.5 |  |  | 1532.5 |  |  | 1449 |  |  | 1403 |  |  | 1493 |  |  | 1450 |  |  | 1400 |  |  | 1525 |  |  | 1412 |  |  | 1552.5 |  |  | 1358 |  |  | 1579 |  |  | 1461 |  |  | 1474.5 |  |  | 1533 |  |  | 1307 |  |  | 1284 |  |  | 1432 |  |  | 1470 |  |  | 1441 |  |  | 1452 |  |  | 1394.5 |  |  | 1450.5 |  |  | 1378.5 |  |  | 1454 |  |  | 1442 |  |  | 1449.5 |  |  | 1292 |  |  | 1371.5 |  |  | 1373.5 |  |  | 1384 |  |  | 1428 |  |  | 1488.5 |  |  | 1399 |  |  | 1493 |  |  | 1509 |  |  | 1452 |  |  | 1427 |  |  | 1375 |  |  | 1414 |  |  | 1553.5 |  |  | 1453 |  |  | 1445 |  |  | 1527 |  |  | 1410 |  |  | 1483 |  |  | 1341 |  |  | 1585 |  |  | 1485 |  |  | 1457 |  |  | 1577.5 |  |  | 1447.5 |  |  | 1378.5 |  |  | 1454.5 |  |  | 1464 |  |  | 1343 |  |  | 1582.5 |  |  | 1464 |  |  | 1418 |  |  | 1432.5 |  |  | 1498.5 |  |  | 1475 |  |  | 1410.5 |  |  | 1379.5 |  |  | 1362 |  |  | 1505 |  |  | 1448 |  |  | 1400 |  |  | 1486.5 |  |  | 1408 |  |  | 1395.5 |  |  | 1370.5 |  |  | 1360 |  |  | 1386 |  |  | 1443.5 |  |  | 1393 |  |  | 1454.5 |  |  | 1422 |  |  | 1420.5 |  |  | 1369.5 |  |  | 1412.5 |  |  | 1461.5 |  |  | 1434.5 |  |  | 1341 |  |  | 1349 |  |  | 1530.5 |  |  | 1482 |  |  | 1391 |  |  | 1416 |  |  | 1517 |  |  | 1538.5 |  |  | 1298 |  |  | 1421 |  |  | 1467 |  |  | 1474.5 |  |  | 1470 |  |  | 1391 |  |  | 1458 |  |  | 1587.5 |  |  | 1459 |  |  | 1333 |  |  | 1437 |  |  | 1498 |  |  | 1700.5 |  |  | 1466 |  |  | 1400.5 |  |  | 1436 |  |  | 1459 |  |  | 1609.5 |  |  | 1496 |  |  | 1360 |  |  | 1375.5 |  |  | 1462 |  |  | 1433 |  |  | 1432 |  |  | 1514.5 |  |  | 1414.5 |  |  | 1466 |  |  | 1401 |  |  | 1447.5 |  |  | 1508.5 |  |  | 1380 |  |  | 1523 |  |  | 1513.5 |  |  | 1511.5 |  |  | 1364.5 |  |  | 1453.5 |  |  | 1417.5 |  |  | 1595 |  |  | 1454.5 |  |  | 1418 |  |  | 1423 |  |  | 1505 |  |  | 1487 |  |  | 1494.5 |  |  | 1448 |  |  | 1401 |  |  | 1462.5 |  |  | 1409.5 |  |  | 1382 |  |  | 1483.5 |  |  | 1460.5 |  |  | 1496 |  |  | 1398 |  |  | 1452 |  |  | 1469.5 |  |  | 1434 |  |  | 1465.5 |  |  | 1466 |  |  | 1473 |  |  | 1640.5 |  |  | 1441 |  |  | 1605 |  |  | 1409 |  |  | 1439 |  |  | 1501 |  |  | 1441 |  |  | 1443 |  |  | 1424 |  |  | 1352.5 |  |  | 1450.5 |  |  | 1476 |  |  | 1456.5 |  |  | 1319.5 |  |  | 1400 |  |  | 1328 |  |  | 1487 |  |  | 1517.5 |  |  | 1378.5 |  |  | 1435 |  |  | 1504 |  |  | 1364 |  |  | 1322 |  |  | 1427 |  |  | 1402 |  |  | 1607 |  |  | 1449.5 |  |  | 1514 |  |  | 1483 |  |  | 1560 |  |  | 1414 |  |  | 1311 |  |  | 1464.5 |  |  | 1577.5 |  |  | 1345.5 |  |  | 1377 |  |  | 1396 |  |  | 1347.5 |  |  | 1538.5 |  |  | 1500.5 |  |  | 1413 |  |  | 1500.5 |  |  | 1427.5 |  |  | 1446 |  |  | 1395.5 |  |  | 1500.5 |  |  | 1431 |  |  | 1418 |  |  | 1463 |  |  | 1469 |  |  | 1414 |  |  | 1355 |  |  | 1463 |  |  | 1560 |  |  | 1426 |  |  | 1361 |  |  | 1524.5 |  |  | 1401 |  |  | 1483 |  |  | 1333 |  |  | 1404.5 |  |  | 1457 |  |  | 1452.5 |  |  | 1512 |  |  | 1474 |  |  | 1437 |  |  | 1454 |  |  | 1541.5 |  |  | 1410 |  |  | 1346 |  |  | 1525.5 |  |  | 1505 |  |  | 1421 |  |  | 1395.5 |  |  | 1448.5 |  |  | 1495 |  |  | 1384.5 |  |  | 1549 |  |  | 1428.5 |  |  | 1541 |  |  | 1502 |  |  | 1425.5 |  |  | 1537.5 |  |  | 1420 |  |  | 1478 |  |  | 1456 |  |  | 1501 |  |  | 1328 |  |  | 1475 |  |  | 1327 |  |  | 1369 |  |  | 1568.5 |  |  | 1335 |  |  | 1536.5 |  |  | 1404 |  |  | 1481.5 |  |  | 1399.5 |  |  | 1379 |  |  | 1482 |  |  | 1485.5 |  |  | 1503 |  |  | 1498 |  |  | 1463 |  |  | 1422.5 |  |  | 1522 |  |  | 1360.5 |  |  | 1330 |  |  | 1403 |  |  | 1409 |  |  | 1505 |  |  | 1593.5 |  |  | 1380 |  |  | 1421 |  |  | 1439 |  |  | 1407.5 |  |  | 1530 |  |  | 1476 |  |  | 1461 |  |  | 1430 |  |  | 1438.5 |  |  | 1386.5 |  |  | 1468 |  |  | 1496 |  |  | 1441 |  |  | 1470.5 |  |  | 1488 |  |  | 1419 |  |  | 1373 |  |  | 1567.5 |  |  | 1427.5 |  |  | 1490.5 |  |  | 1424 |  |  | 1515 |  |  | 1410 |  |  | 1388.5 |  |  | 1452 |  |  | 1430.5 |  |  | 1287 |  |  | 1370 |  |  | 1460 |  |  | 1408.5 |  |  | 1443.5 |  |  | 1481 |  |  | 1384 |  |  | 1477.5 |  |  | 1430 |  |  | 1470 |  |  | 1538.5 |  |  | 1420 |  |  | 1411 |  |  | 1460.5 |  |  | 1371 |  |  | 1465 |  |  | 1440.5 |  |  | 1485 |  |  | 1383.5 |  |  | 1481 |  |  | 1371.5 |  |  | 1465.5 |  |  | 1368 |  |  | 1520 |  |  | 1464.5 |  |  | 1460.5 |  |  | 1561 |  |  | 1432 |  |  | 1539 |  |  | 1415.5 |  |  | 1450 |  |  | 1311 |  |  | 1460 |  |  | 1543.5 |  |  | 1482.5 |  |  | 1473 |  |  | 1509 |  |  | 1362 |  |  | 1360 |  |  | 1535 |  |  | 1440 |  |  | 1432 |  |  | 1404.5 |  |  | 1477.5 |  |  | 1381.5 |  |  | 1462 |  |  | 1373.5 |  |  | 1465 |  |  | 1362 |  |  | 1459.5 |  |  | 1373.5 |  |  | 1289 |  |  | 1446 |  |  | 1408.5 |  |  | 1430 |  |  | 1471 |  |  | 1375.5 |  |  | 1417.5 |  |  | 1428 |  |  | 1441 |  |  | 1539 |  |  | 1331.5 |  |  | 1424 |  |  | 1317 |  |  | 1466 |  |  | 1429 |  |  | 1521 |  |  | 1426.5 |  |  | 1536 |  |  | 1395 |  |  | 1296 |  |  | 1567.5 |  |  | 1449 |  |  | 1416.5 |  |  | 1350.5 |  |  | 1416 |  |  | 1441 |  |  | 1441.5 |  |  | 1392.5 |  |  | 1416.5 |  |  | 1439.5 |  |  | 1467.5 |  |  | 1458 |  |  | 1419 |  |  | 1459.5 |  |  | 1435.5 |  |  | 1458 |  |  | 1400 |  |  | 1438.5 |  |  | 1481 |  |  | 1438 |  |  | 1327 |  |  | 1455.5 |  |  | 1554 |  |  | 1373.5 |  |  | 1328 |  |  | 1443.5 |  |  | 1497.5 |  |  | 1575.5 |  |  | 1459 |  |  | 1411 |  |  | 1500.5 |  |  | 1389.5 |  |  | 1473 |  |  | 1491 |  |  | 1428.5 |  |  | 1439 |  |  | 1456.5 |  |  | 1434.5 |  |  | 1467 |  |  | 1431 |  |  | 1391.5 |  |  | 1534.5 |  |  | 1394 |  |  | 1404.5 |  |  | 1460.5 |  |  | 1422 |  |  | 1519 |  |  | 1556 |  |  | 1465.5 |  |  | 1478 |  |  | 1431 |  |  | 1455 |  |  | 1416 |  |  | 1481 |  |  | 1395 |  |  | 1531.5 |  |  | 1381.5 |  |  | 1416 |  |  | 1371 |  |  | 1464 |  |  | 1464.5 |  |  | 1458 |  |  | 1529 |  |  | 1399.5 |  |  | 1443.5 |  |  | 1437 |  |  | 1402.5 |  |  | 1468 |  |  | 1352 |  |  | 1466 |  |  | 1574.5 |  |  | 1534 |  |  | 1344.5 |  |  | 1378.5 |  |  | 1363 |  |  | 1509.5 |  |  | 1331.5 |  |  | 1379 |  |  | 1361 |  |  | 1582 |  |  | 1355.5 |  |  | 1352 |  |  | 1414.5 |  |  | 1427.5 |  |  | 1481 |  |  | 1378.5 |  |  | 1374 |  |  | 1466 |  |  | 1409 |  |  | 1374 |  |  | 1352 |  |  | 1536.5 |  |  | 1477 |  |  | 1519 |  |  | 1374 |  |  | 1508 |  |  | 1416.5 |  |  | 1506.5 |  |  | 1401 |  |  | 1453 |  |  | 1420 |  |  | 1373 |  |  | 1507 |  |  | 1450.5 |  |  | 1490 |  |  | 1467.5 |  |  | 1544 |  |  | 1334 |  |  | 1443 |  |  | 1373 |  |  | 1401.5 |  |  | 1409 |  |  | 1396.5 |  |  | 1350 |  |  | 1502 |  |  | 1486 |  |  | 1372.5 |  |  | 1375 |  |  | 1367 |  |  | 1338 |  |  | 1584 |  |  | 1529 |  |  | 1428.5 |  |  | 1488.5 |  |  | 1422 |  |  | 1419.5 |  |  | 1341 |  |  | 1317.5 |  |  | 1440.5 |  |  | 1389.5 |  |  | 1479.5 |  |  | 1355 |  |  | 1509 |  |  | 1410 |  |  | 1368 |  |  | 1474 |  |  | 1397 |  |  | 1401.5 |  |  | 1417.5 |  |  | 1462.5 |  |  | 1516 |  |  | 1483.5 |  |  | 1439.5 |  |  | 1474.5 |  |  | 1411.5 |  |  | 1401 |  |  | 1453.5 |  |  | 1437.5 |  |  | 1479 |  |  | 1391.5 |  |  | 1490.5 |  |  | 1482.5 |  |  | 1488 |  |  | 1458.5 |  |  | 1448 |  |  | 1469 |  |  | 1457.5 |  |  | 1471.5 |  |  | 1480 |  |  | 1451 |  |  | 1326.5 |  |  | 1363.5 |  |  | 1463.5 |  |  | 1438 |  |  | 1404 |  |  | 1369 |  |  | 1473.5 |  |  | 1494.5 |  |  | 1492 |  |  | 1459.5 |  |  | 1354 |  |  | 1409 |  |  | 1471.5 |  |  | 1363.5 |  |  | 1413 |  |  | 1422.5 |  |  | 1376 |  |  | 1362.5 |  |  | 1557.5 |  |  | 1500 |  |  | 1357.5 |  |  | 1474 |  |  | 1455.5 |  |  | 1430 |  |  | 1460 |  |  | 1514 |  |  | 1388.5 |  |  | 1332.5 |  |  | 1495 |  |  | 1382 |  |  | 1396 |  |  | 1437.5 |  |  | 1422.5 |  |  | 1497 |  |  | 1426.5 |  |  | 1405 |  |  | 1392.5 |  |  | 1479.5 |  |  | 1386 |  |  | 1371 |  |  | 1452 |  |  | 1437.5 |  |  | 1427 |  |  | 1518.5 |  |  | 1479 |  |  | 1418.5 |  |  | 1598 |  |  | 1293.5 |  |  | 1414 |  |  | 1399.5 |  |  | 1421.5 |  |  | 1421 |  |  | 1379 |  |  | 1482 |  |  | 1452 |  |  | 1495.5 |  |  | 1373 |  |  | 1403.5 |  |  | 1350 |  |  | 1391 |  |  | 1411 |  |  | 1483 |  |  | 1511 |  |  | 1450 |  |  | 1443 |  |  | 1499.5 |  |  | 1358 |  |  | 1499
52 |  | 1545.5 |  |  | 1545 |  |  | 1489.5 |  |  | 1453 |  |  | 1493.5 |  |  | 1473 |  |  | 1470 |  |  | 1557 |  |  | 1425.5 |  |  | 1475 |  |  | 1408 |  |  | 1586 |  |  | 1497 |  |  | 1549 |  |  | 1411.5 |  |  | 1538.5 |  |  | 1401 |  |  | 1543 |  |  | 1604 |  |  | 1395.5 |  |  | 1524 |  |  | 1548 |  |  | 1437 |  |  | 1515 |  |  | 1466.5 |  |  | 1601 |  |  | 1525 |  |  | 1391 |  |  | 1500 |  |  | 1407 |  |  | 1425 |  |  | 1484.5 |  |  | 1586.5 |  |  | 1452.5 |  |  | 1363 |  |  | 1402.5 |  |  | 1443.5 |  |  | 1501.5 |  |  | 1500 |  |  | 1450 |  |  | 1389.5 |  |  | 1367 |  |  | 1552.5 |  |  | 1487.5 |  |  | 1530.5 |  |  | 1573.5 |  |  | 1557.5 |  |  | 1459 |  |  | 1342 |  |  | 1380.5 |  |  | 1460 |  |  | 1415.5 |  |  | 1413.5 |  |  | 1526 |  |  | 1391 |  |  | 1448 |  |  | 1435 |  |  | 1538 |  |  | 1530 |  |  | 1446.5 |  |  | 1555.5 |  |  | 1496.5 |  |  | 1339 |  |  | 1538 |  |  | 1370 |  |  | 1410.5 |  |  | 1442 |  |  | 1504.5 |  |  | 1482.5 |  |  | 1571.5 |  |  | 1408 |  |  | 1495 |  |  | 1514 |  |  | 1454.5 |  |  | 1530.5 |  |  | 1448.5 |  |  | 1559.5 |  |  | 1513.5 |  |  | 1516.5 |  |  | 1507.5 |  |  | 1462.5 |  |  | 1415 |  |  | 1469 |  |  | 1466 |  |  | 1551.5 |  |  | 1527 |  |  | 1375.5 |  |  | 1453 |  |  | 1497 |  |  | 1493.5 |  |  | 1534.5 |  |  | 1472 |  |  | 1699 |  |  | 1418.5 |  |  | 1550 |  |  | 1450.5 |  |  | 1482.5 |  |  | 1446.5 |  |  | 1436.5 |  |  | 1396.5 |  |  | 1507 |  |  | 1434 |  |  | 1378 |  |  | 1520.5 |  |  | 1424.5 |  |  | 1491.5 |  |  | 1458.5 |  |  | 1496 |  |  | 1429 |  |  | 1486.5 |  |  | 1379 |  |  | 1483.5 |  |  | 1513 |  |  | 1491 |  |  | 1387.5 |  |  | 1435 |  |  | 1421 |  |  | 1462 |  |  | 1436 |  |  | 1531.5 |  |  | 1455.5 |  |  | 1420.5 |  |  | 1612 |  |  | 1433 |  |  | 1382 |  |  | 1418 |  |  | 1422.5 |  |  | 1477 |  |  | 1525.5 |  |  | 1512 |  |  | 1422 |  |  | 1499.5 |  |  | 1390.5 |  |  | 1376 |  |  | 1426.5 |  |  | 1431 |  |  | 1472 |  |  | 1476 |  |  | 1477 |  |  | 1452 |  |  | 1365 |  |  | 1423 |  |  | 1483 |  |  | 1413 |  |  | 1383.5 |  |  | 1450 |  |  | 1361 |  |  | 1485 |  |  | 1474 |  |  | 1384 |  |  | 1438 |  |  | 1420 |  |  | 1509.5 |  |  | 1467 |  |  | 1480.5 |  |  | 1524 |  |  | 1425 |  |  | 1506.5 |  |  | 1438 |  |  | 1627.5 |  |  | 1477 |  |  | 1354 |  |  | 1512.5 |  |  | 1480 |  |  | 1513.5 |  |  | 1453 |  |  | 1406 |  |  | 1440.5 |  |  | 1471.5 |  |  | 1512 |  |  | 1424.5 |  |  | 1488.5 |  |  | 1471 |  |  | 1471 |  |  | 1657.5 |  |  | 1424.5 |  |  | 1398.5 |  |  | 1477 |  |  | 1524 |  |  | 1440 |  |  | 1515 |  |  | 1505 |  |  | 1487.5 |  |  | 1442 |  |  | 1327.5 |  |  | 1489.5 |  |  | 1529 |  |  | 1557 |  |  | 1591.5 |  |  | 1375.5 |  |  | 1442 |  |  | 1478.5 |  |  | 1416.5 |  |  | 1527 |  |  | 1380 |  |  | 1450 |  |  | 1392.5 |  |  | 1592 |  |  | 1446.5 |  |  | 1432.5 |  |  | 1404 |  |  | 1460.5 |  |  | 1355 |  |  | 1486 |  |  | 1472 |  |  | 1460 |  |  | 1396 |  |  | 1527 |  |  | 1556 |  |  | 1514 |  |  | 1571 |  |  | 1471 |  |  | 1467.5 |  |  | 1560.5 |  |  | 1473 |  |  | 1363 |  |  | 1543 |  |  | 1502.5 |  |  | 1517.5 |  |  | 1519.5 |  |  | 1466 |  |  | 1484 |  |  | 1544.5 |  |  | 1425.5 |  |  | 1373.5 |  |  | 1565 |  |  | 1555 |  |  | 1483 |  |  | 1429 |  |  | 1473 |  |  | 1433.5 |  |  | 1453.5 |  |  | 1570 |  |  | 1510 |  |  | 1429 |  |  | 1563 |  |  | 1455 |  |  | 1432.5 |  |  | 1462 |  |  | 1519 |  |  | 1475 |  |  | 1489 |  |  | 1449.5 |  |  | 1601 |  |  | 1517 |  |  | 1467 |  |  | 1531 |  |  | 1527.5 |  |  | 1587 |  |  | 1429 |  |  | 1391 |  |  | 1535.5 |  |  | 1492.5 |  |  | 1493.5 |  |  | 1558 |  |  | 1468 |  |  | 1394 |  |  | 1551 |  |  | 1502 |  |  | 1401.5 |  |  | 1522 |  |  | 1394.5 |  |  | 1522.5 |  |  | 1561.5 |  |  | 1477 |  |  | 1547.5 |  |  | 1433 |  |  | 1412 |  |  | 1424.5 |  |  | 1460.5 |  |  | 1538 |  |  | 1585.5 |  |  | 1511.5 |  |  | 1487 |  |  | 1551 |  |  | 1492.5 |  |  | 1401.5 |  |  | 1524 |  |  | 1513.5 |  |  | 1479 |  |  | 1421 |  |  | 1445.5 |  |  | 1507 |  |  | 1430 |  |  | 1497.5 |  |  | 1420 |  |  | 1530.5 |  |  | 1466 |  |  | 1625 |  |  | 1440 |  |  | 1371 |  |  | 1544.5 |  |  | 1596 |  |  | 1529.5 |  |  | 1423.5 |  |  | 1517.5 |  |  | 1568 |  |  | 1597.5 |  |  | 1583 |  |  | 1502 |  |  | 1361.5 |  |  | 1459.5 |  |  | 1478 |  |  | 1474.5 |  |  | 1517 |  |  | 1444 |  |  | 1605.5 |  |  | 1474 |  |  | 1444.5 |  |  | 1499.5 |  |  | 1499.5 |  |  | 1463 |  |  | 1425 |  |  | 1469 |  |  | 1305.5 |  |  | 1421 |  |  | 1553.5 |  |  | 1499 |  |  | 1472 |  |  | 1421 |  |  | 1487 |  |  | 1547 |  |  | 1522 |  |  | 1446 |  |  | 1612 |  |  | 1490 |  |  | 1466.5 |  |  | 1478 |  |  | 1480 |  |  | 1619.5 |  |  | 1395.5 |  |  | 1479.5 |  |  | 1524.5 |  |  | 1429 |  |  | 1575 |  |  | 1378.5 |  |  | 1530.5 |  |  | 1508.5 |  |  | 1513 |  |  | 1484 |  |  | 1484 |  |  | 1458 |  |  | 1395 |  |  | 1480 |  |  | 1485 |  |  | 1452.5 |  |  | 1456.5 |  |  | 1475 |  |  | 1476.5 |  |  | 1482.5 |  |  | 1379 |  |  | 1508 |  |  | 1417 |  |  | 1451 |  |  | 1420.5 |  |  | 1389.5 |  |  | 1466.5 |  |  | 1485 |  |  | 1433.5 |  |  | 1489 |  |  | 1428 |  |  | 1495 |  |  | 1352.5 |  |  | 1464 |  |  | 1361 |  |  | 1470.5 |  |  | 1421 |  |  | 1524.5 |  |  | 1594 |  |  | 1425.5 |  |  | 1383 |  |  | 1456.5 |  |  | 1504.5 |  |  | 1528 |  |  | 1475 |  |  | 1368 |  |  | 1446 |  |  | 1396.5 |  |  | 1442 |  |  | 1515 |  |  | 1401.5 |  |  | 1531.5 |  |  | 1412.5 |  |  | 1422 |  |  | 1506.5 |  |  | 1418.5 |  |  | 1439.5 |  |  | 1543 |  |  | 1447 |  |  | 1450.5 |  |  | 1521 |  |  | 1528 |  |  | 1439.5 |  |  | 1421 |  |  | 1546 |  |  | 1450 |  |  | 1396 |  |  | 1346.5 |  |  | 1566.5 |  |  | 1403 |  |  | 1516 |  |  | 1492 |  |  | 1450 |  |  | 1411 |  |  | 1414.5 |  |  | 1465.5 |  |  | 1465 |  |  | 1618 |  |  | 1575 |  |  | 1346.5 |  |  | 1574.5 |  |  | 1413 |  |  | 1456 |  |  | 1386 |  |  | 1483.5 |  |  | 1579.5 |  |  | 1478 |  |  | 1432 |  |  | 1514 |  |  | 1489 |  |  | 1439 |  |  | 1564 |  |  | 1433 |  |  | 1567.5 |  |  | 1382 |  |  | 1626 |  |  | 1482 |  |  | 1500.5 |  |  | 1580 |  |  | 1333 |  |  | 1331 |  |  | 1447 |  |  | 1517 |  |  | 1480 |  |  | 1478 |  |  | 1418.5 |  |  | 1465.5 |  |  | 1404.5 |  |  | 1493 |  |  | 1468 |  |  | 1464.5 |  |  | 1339 |  |  | 1400.5 |  |  | 1420.5 |  |  | 1410 |  |  | 1467 |  |  | 1512.5 |  |  | 1428 |  |  | 1532 |  |  | 1533 |  |  | 1491 |  |  | 1456 |  |  | 1414 |  |  | 1440 |  |  | 1592.5 |  |  | 1474 |  |  | 1484 |  |  | 1542 |  |  | 1425 |  |  | 1522 |  |  | 1380 |  |  | 1632 |  |  | 1532 |  |  | 1483 |  |  | 1606.5 |  |  | 1494.5 |  |  | 1425.5 |  |  | 1483.5 |  |  | 1503 |  |  | 1382 |  |  | 1603.5 |  |  | 1479 |  |  | 1444 |  |  | 1456.5 |  |  | 1527.5 |  |  | 1514 |  |  | 1457.5 |  |  | 1426.5 |  |  | 1388 |  |  | 1529 |  |  | 1472 |  |  | 1421 |  |  | 1515.5 |  |  | 1437 |  |  | 1434.5 |  |  | 1391.5 |  |  | 1386 |  |  | 1407 |  |  | 1490.5 |  |  | 1419 |  |  | 1469.5 |  |  | 1437 |  |  | 1467.5 |  |  | 1393.5 |  |  | 1427.5 |  |  | 1508.5 |  |  | 1460.5 |  |  | 1370 |  |  | 1375 |  |  | 1551.5 |  |  | 1506 |  |  | 1430 |  |  | 1437 |  |  | 1564 |  |  | 1585.5 |  |  | 1337 |  |  | 1445 |  |  | 1482 |  |  | 1498.5 |  |  | 1517 |  |  | 1406 |  |  | 1482 |  |  | 1626.5 |  |  | 1506 |  |  | 1354 |  |  | 1452 |  |  | 1537 |  |  | 1715.5 |  |  | 1487 |  |  | 1426.5 |  |  | 1457 |  |  | 1506 |  |  | 1635.5 |  |  | 1520 |  |  | 1381 |  |  | 1401.5 |  |  | 1509 |  |  | 1472 |  |  | 1471 |  |  | 1553.5 |  |  | 1461.5 |  |  | 1505 |  |  | 1440 |  |  | 1476.5 |  |  | 1529.5 |  |  | 1404 |  |  | 1549 |  |  | 1542.5 |  |  | 1558.5 |  |  | 1388.5 |  |  | 1482.5 |  |  | 1443.5 |  |  | 1642 |  |  | 1478.5 |  |  | 1447 |  |  | 1462 |  |  | 1552 |  |  | 1526 |  |  | 1509.5 |  |  | 1487 |  |  | 1422 |  |  | 1501.5 |  |  | 1448.5 |  |  | 1421 |  |  | 1522.5 |  |  | 1499.5 |  |  | 1525 |  |  | 1424 |  |  | 1481 |  |  | 1516.5 |  |  | 1481 |  |  | 1504.5 |  |  | 1495 |  |  | 1488 |  |  | 1655.5 |  |  | 1480 |  |  | 1634 |  |  | 1438 |  |  | 1478 |  |  | 1516 |  |  | 1470 |  |  | 1458 |  |  | 1463 |  |  | 1391.5 |  |  | 1489.5 |  |  | 1502 |  |  | 1480.5 |  |  | 1334.5 |  |  | 1415 |  |  | 1357 |  |  | 1534 |  |  | 1546.5 |  |  | 1407.5 |  |  | 1450 |  |  | 1543 |  |  | 1393 |  |  | 1361 |  |  | 1466 |  |  | 1423 |  |  | 1631 |  |  | 1464.5 |  |  | 1535 |  |  | 1498 |  |  | 1581 |  |  | 1438 |  |  | 1326 |  |  | 1479.5 |  |  | 1616.5 |  |  | 1369.5 |  |  | 1416 |  |  | 1420 |  |  | 1386.5 |  |  | 1585.5 |  |  | 1529.5 |  |  | 1437 |  |  | 1515.5 |  |  | 1474.5 |  |  | 1485 |  |  | 1434.5 |  |  | 1529.5 |  |  | 1478 |  |  | 1433 |  |  | 1484 |  |  | 1498 |  |  | 1435 |  |  | 1379 |  |  | 1492 |  |  | 1589 |  |  | 1441 |  |  | 1400 |  |  | 1571.5 |  |  | 1427 |  |  | 1512 |  |  | 1362 |  |  | 1419.5 |  |  | 1486 |  |  | 1491.5 |  |  | 1559 |  |  | 1489 |  |  | 1461 |  |  | 1501 |  |  | 1556.5 |  |  | 1439 |  |  | 1367 |  |  | 1540.5 |  |  | 1526 |  |  | 1460 |  |  | 1442.5 |  |  | 1474.5 |  |  | 1510 |  |  | 1423.5 |  |  | 1570 |  |  | 1467.5 |  |  | 1565 |  |  | 1523 |  |  | 1449.5 |  |  | 1561.5 |  |  | 1459 |  |  | 1517 |  |  | 1471 |  |  | 1527 |  |  | 1367 |  |  | 1514 |  |  | 1348 |  |  | 1393 |  |  | 1615.5 |  |  | 1350 |  |  | 1560.5 |  |  | 1419 |  |  | 1505.5 |  |  | 1428.5 |  |  | 1426 |  |  | 1511 |  |  | 1524.5 |  |  | 1529 |  |  | 1524 |  |  | 1484 |  |  | 1437.5 |  |  | 1561 |  |  | 1399.5 |  |  | 1345 |  |  | 1442 |  |  | 1456 |  |  | 1544 |  |  | 1640.5 |  |  | 1419 |  |  | 1445 |  |  | 1463 |  |  | 1436.5 |  |  | 1569 |  |  | 1500 |  |  | 1482 |  |  | 1456 |  |  | 1464.5 |  |  | 1410.5 |  |  | 1483 |  |  | 1525 |  |  | 1480 |  |  | 1499.5 |  |  | 1514 |  |  | 1440 |  |  | 1412 |  |  | 1614.5 |  |  | 1466.5 |  |  | 1516.5 |  |  | 1471 |  |  | 1541 |  |  | 1449 |  |  | 1409.5 |  |  | 1499 |  |  | 1477.5 |  |  | 1334 |  |  | 1391 |  |  | 1489 |  |  | 1432.5 |  |  | 1482.5 |  |  | 1528 |  |  | 1410 |  |  | 1524.5 |  |  | 1459 |  |  | 1494 |  |  | 1577.5 |  |  | 1444 |  |  | 1450 |  |  | 1489.5 |  |  | 1410 |  |  | 1486 |  |  | 1487.5 |  |  | 1524 |  |  | 1398.5 |  |  | 1510 |  |  | 1397.5 |  |  | 1512.5 |  |  | 1394 |  |  | 1544 |  |  | 1511.5 |  |  | 1507.5 |  |  | 1576 |  |  | 1447 |  |  | 1560 |  |  | 1436.5 |  |  | 1489 |  |  | 1332 |  |  | 1484 |  |  | 1590.5 |  |  | 1506.5 |  |  | 1494 |  |  | 1533 |  |  | 1409 |  |  | 1375 |  |  | 1582 |  |  | 1466 |  |  | 1447 |  |  | 1428.5 |  |  | 1516.5 |  |  | 1396.5 |  |  | 1501 |  |  | 1402.5 |  |  | 1512 |  |  | 1401 |  |  | 1506.5 |  |  | 1394.5 |  |  | 1310 |  |  | 1485 |  |  | 1429.5 |  |  | 1469 |  |  | 1518 |  |  | 1399.5 |  |  | 1438.5 |  |  | 1475 |  |  | 1480 |  |  | 1568 |  |  | 1378.5 |  |  | 1439 |  |  | 1356 |  |  | 1490 |  |  | 1476 |  |  | 1547 |  |  | 1450.5 |  |  | 1560 |  |  | 1419 |  |  | 1311 |  |  | 1614.5 |  |  | 1464 |  |  | 1437.5 |  |  | 1376.5 |  |  | 1463 |  |  | 1467 |  |  | 1470.5 |  |  | 1421.5 |  |  | 1431.5 |  |  | 1478.5 |  |  | 1488.5 |  |  | 1484 |  |  | 1440 |  |  | 1498.5 |  |  | 1450.5 |  |  | 1487 |  |  | 1447 |  |  | 1464.5 |  |  | 1505 |  |  | 1453 |  |  | 1356 |  |  | 1484.5 |  |  | 1575 |  |  | 1399.5 |  |  | 1367 |  |  | 1472.5 |  |  | 1536.5 |  |  | 1599.5 |  |  | 1498 |  |  | 1440 |  |  | 1515.5 |  |  | 1404.5 |  |  | 1488 |  |  | 1512 |  |  | 1452.5 |  |  | 1478 |  |  | 1495.5 |  |  | 1473.5 |  |  | 1514 |  |  | 1455 |  |  | 1420.5 |  |  | 1573.5 |  |  | 1441 |  |  | 1428.5 |  |  | 1481.5 |  |  | 1437 |  |  | 1548 |  |  | 1577 |  |  | 1504.5 |  |  | 1517 |  |  | 1452 |  |  | 1470 |  |  | 1455 |  |  | 1502 |  |  | 1434 |  |  | 1557.5 |  |  | 1420.5 |  |  | 1445 |  |  | 1395 |  |  | 1493 |  |  | 1503.5 |  |  | 1484 |  |  | 1568 |  |  | 1414.5 |  |  | 1467.5 |  |  | 1452 |  |  | 1423.5 |  |  | 1497 |  |  | 1373 |  |  | 1513 |  |  | 1603.5 |  |  | 1581 |  |  | 1370.5 |  |  | 1417.5 |  |  | 1389 |  |  | 1524.5 |  |  | 1355.5 |  |  | 1418 |  |  | 1390 |  |  | 1606 |  |  | 1370.5 |  |  | 1391 |  |  | 1435.5 |  |  | 1451.5 |  |  | 1520 |  |  | 1417.5 |  |  | 1413 |  |  | 1487 |  |  | 1424 |  |  | 1413 |  |  | 1367 |  |  | 1557.5 |  |  | 1516 |  |  | 1540 |  |  | 1403 |  |  | 1547 |  |  | 1442.5 |  |  | 1521.5 |  |  | 1416 |  |  | 1479 |  |  | 1459 |  |  | 1397 |  |  | 1536 |  |  | 1497.5 |  |  | 1514 |  |  | 1482.5 |  |  | 1568 |  |  | 1381 |  |  | 1482 |  |  | 1412 |  |  | 1440.5 |  |  | 1435 |  |  | 1435.5 |  |  | 1389 |  |  | 1541 |  |  | 1512 |  |  | 1411.5 |  |  | 1414 |  |  | 1382 |  |  | 1377 |  |  | 1613 |  |  | 1568 |  |  | 1443.5 |  |  | 1535.5 |  |  | 1448 |  |  | 1434.5 |  |  | 1362 |  |  | 1356.5 |  |  | 1479.5 |  |  | 1404.5 |  |  | 1518.5 |  |  | 1384 |  |  | 1535 |  |  | 1449 |  |  | 1407 |  |  | 1489 |  |  | 1421 |  |  | 1430.5 |  |  | 1441.5 |  |  | 1488.5 |  |  | 1531 |  |  | 1507.5 |  |  | 1465.5 |  |  | 1521.5 |  |  | 1432.5 |  |  | 1427 |  |  | 1468.5 |  |  | 1466.5 |  |  | 1518 |  |  | 1430.5 |  |  | 1505.5 |  |  | 1521.5 |  |  | 1517 |  |  | 1479.5 |  |  | 1487 |  |  | 1508 |  |  | 1483.5 |  |  | 1510.5 |  |  | 1519 |  |  | 1477 |  |  | 1347.5 |  |  | 1387.5 |  |  | 1478.5 |  |  | 1485 |  |  | 1443 |  |  | 1416 |  |  | 1497.5 |  |  | 1520.5 |  |  | 1531 |  |  | 1506.5 |  |  | 1378 |  |  | 1448 |  |  | 1495.5 |  |  | 1410.5 |  |  | 1434 |  |  | 1461.5 |  |  | 1415 |  |  | 1377.5 |  |  | 1583.5 |  |  | 1524 |  |  | 1396.5 |  |  | 1521 |  |  | 1481.5 |  |  | 1469 |  |  | 1499 |  |  | 1538 |  |  | 1409.5 |  |  | 1353.5 |  |  | 1519 |  |  | 1403 |  |  | 1435 |  |  | 1466.5 |  |  | 1461.5 |  |  | 1518 |  |  | 1450.5 |  |  | 1434 |  |  | 1413.5 |  |  | 1503.5 |  |  | 1425 |  |  | 1418 |  |  | 1478 |  |  | 1452.5 |  |  | 1474 |  |  | 1542.5 |  |  | 1494 |  |  | 1457.5 |  |  | 1645 |  |  | 1317.5 |  |  | 1443 |  |  | 1425.5 |  |  | 1450.5 |  |  | 1436 |  |  | 1400 |  |  | 1529 |  |  | 1467 |  |  | 1534.5 |  |  | 1399 |  |  | 1432.5 |  |  | 1371 |  |  | 1412 |  |  | 1450 |  |  | 1509 |  |  | 1550 |  |  | 1465 |  |  | 1467 |  |  | 1538.5 |  |  | 1397 |  |  | 1525
53 |  | 1584.5 |  |  | 1574 |  |  | 1513.5 |  |  | 1500 |  |  | 1517.5 |  |  | 1520 |  |  | 1499 |  |  | 1581 |  |  | 1440.5 |  |  | 1504 |  |  | 1447 |  |  | 1625 |  |  | 1512 |  |  | 1596 |  |  | 1426.5 |  |  | 1553.5 |  |  | 1422 |  |  | 1582 |  |  | 1619 |  |  | 1434.5 |  |  | 1550 |  |  | 1574 |  |  | 1463 |  |  | 1554 |  |  | 1513.5 |  |  | 1640 |  |  | 1551 |  |  | 1430 |  |  | 1539 |  |  | 1446 |  |  | 1464 |  |  | 1523.5 |  |  | 1607.5 |  |  | 1491.5 |  |  | 1384 |  |  | 1441.5 |  |  | 1469.5 |  |  | 1530.5 |  |  | 1529 |  |  | 1474 |  |  | 1415.5 |  |  | 1388 |  |  | 1567.5 |  |  | 1516.5 |  |  | 1551.5 |  |  | 1602.5 |  |  | 1596.5 |  |  | 1498 |  |  | 1363 |  |  | 1395.5 |  |  | 1499 |  |  | 1454.5 |  |  | 1434.5 |  |  | 1555 |  |  | 1430 |  |  | 1487 |  |  | 1450 |  |  | 1577 |  |  | 1551 |  |  | 1485.5 |  |  | 1570.5 |  |  | 1543.5 |  |  | 1378 |  |  | 1567 |  |  | 1409 |  |  | 1431.5 |  |  | 1481 |  |  | 1528.5 |  |  | 1508.5 |  |  | 1595.5 |  |  | 1429 |  |  | 1510 |  |  | 1538 |  |  | 1493.5 |  |  | 1556.5 |  |  | 1474.5 |  |  | 1588.5 |  |  | 1552.5 |  |  | 1555.5 |  |  | 1528.5 |  |  | 1488.5 |  |  | 1454 |  |  | 1495 |  |  | 1487 |  |  | 1566.5 |  |  | 1566 |  |  | 1414.5 |  |  | 1492 |  |  | 1536 |  |  | 1519.5 |  |  | 1560.5 |  |  | 1496 |  |  | 1720 |  |  | 1442.5 |  |  | 1565 |  |  | 1474.5 |  |  | 1508.5 |  |  | 1467.5 |  |  | 1462.5 |  |  | 1411.5 |  |  | 1546 |  |  | 1481 |  |  | 1417 |  |  | 1535.5 |  |  | 1471.5 |  |  | 1530.5 |  |  | 1487.5 |  |  | 1520 |  |  | 1476 |  |  | 1501.5 |  |  | 1394 |  |  | 1530.5 |  |  | 1552 |  |  | 1520 |  |  | 1426.5 |  |  | 1459 |  |  | 1468 |  |  | 1486 |  |  | 1475 |  |  | 1555.5 |  |  | 1494.5 |  |  | 1459.5 |  |  | 1651 |  |  | 1457 |  |  | 1397 |  |  | 1465 |  |  | 1461.5 |  |  | 1492 |  |  | 1540.5 |  |  | 1551 |  |  | 1437 |  |  | 1538.5 |  |  | 1414.5 |  |  | 1391 |  |  | 1450.5 |  |  | 1470 |  |  | 1493 |  |  | 1500 |  |  | 1516 |  |  | 1476 |  |  | 1404 |  |  | 1470 |  |  | 1522 |  |  | 1437 |  |  | 1409.5 |  |  | 1471 |  |  | 1400 |  |  | 1514 |  |  | 1498 |  |  | 1410 |  |  | 1453 |  |  | 1467 |  |  | 1548.5 |  |  | 1506 |  |  | 1504.5 |  |  | 1545 |  |  | 1449 |  |  | 1532.5 |  |  | 1485 |  |  | 1653.5 |  |  | 1503 |  |  | 1383 |  |  | 1541.5 |  |  | 1506 |  |  | 1560.5 |  |  | 1482 |  |  | 1427 |  |  | 1487.5 |  |  | 1510.5 |  |  | 1551 |  |  | 1445.5 |  |  | 1517.5 |  |  | 1500 |  |  | 1510 |  |  | 1672.5 |  |  | 1463.5 |  |  | 1437.5 |  |  | 1524 |  |  | 1553 |  |  | 1479 |  |  | 1562 |  |  | 1544 |  |  | 1508.5 |  |  | 1489 |  |  | 1356.5 |  |  | 1510.5 |  |  | 1544 |  |  | 1596 |  |  | 1630.5 |  |  | 1399.5 |  |  | 1463 |  |  | 1525.5 |  |  | 1455.5 |  |  | 1556 |  |  | 1404 |  |  | 1479 |  |  | 1431.5 |  |  | 1618 |  |  | 1485.5 |  |  | 1458.5 |  |  | 1433 |  |  | 1489.5 |  |  | 1394 |  |  | 1533 |  |  | 1496 |  |  | 1486 |  |  | 1417 |  |  | 1553 |  |  | 1571 |  |  | 1561 |  |  | 1600 |  |  | 1486 |  |  | 1493.5 |  |  | 1599.5 |  |  | 1512 |  |  | 1402 |  |  | 1590 |  |  | 1523.5 |  |  | 1541.5 |  |  | 1534.5 |  |  | 1495 |  |  | 1523 |  |  | 1573.5 |  |  | 1464.5 |  |  | 1397.5 |  |  | 1594 |  |  | 1584 |  |  | 1509 |  |  | 1455 |  |  | 1512 |  |  | 1454.5 |  |  | 1479.5 |  |  | 1599 |  |  | 1531 |  |  | 1458 |  |  | 1610 |  |  | 1481 |  |  | 1479.5 |  |  | 1501 |  |  | 1558 |  |  | 1499 |  |  | 1510 |  |  | 1478.5 |  |  | 1630 |  |  | 1543 |  |  | 1506 |  |  | 1578 |  |  | 1566.5 |  |  | 1602 |  |  | 1455 |  |  | 1417 |  |  | 1556.5 |  |  | 1507.5 |  |  | 1540.5 |  |  | 1605 |  |  | 1489 |  |  | 1433 |  |  | 1598 |  |  | 1549 |  |  | 1427.5 |  |  | 1569 |  |  | 1415.5 |  |  | 1543.5 |  |  | 1576.5 |  |  | 1524 |  |  | 1594.5 |  |  | 1472 |  |  | 1441 |  |  | 1445.5 |  |  | 1499.5 |  |  | 1567 |  |  | 1632.5 |  |  | 1550.5 |  |  | 1534 |  |  | 1590 |  |  | 1516.5 |  |  | 1427.5 |  |  | 1571 |  |  | 1539.5 |  |  | 1503 |  |  | 1460 |  |  | 1474.5 |  |  | 1546 |  |  | 1477 |  |  | 1518.5 |  |  | 1467 |  |  | 1569.5 |  |  | 1481 |  |  | 1646 |  |  | 1487 |  |  | 1400 |  |  | 1583.5 |  |  | 1635 |  |  | 1553.5 |  |  | 1462.5 |  |  | 1556.5 |  |  | 1607 |  |  | 1636.5 |  |  | 1612 |  |  | 1541 |  |  | 1400.5 |  |  | 1498.5 |  |  | 1517 |  |  | 1521.5 |  |  | 1556 |  |  | 1491 |  |  | 1629.5 |  |  | 1489 |  |  | 1491.5 |  |  | 1525.5 |  |  | 1528.5 |  |  | 1502 |  |  | 1449 |  |  | 1490 |  |  | 1352.5 |  |  | 1442 |  |  | 1592.5 |  |  | 1525 |  |  | 1498 |  |  | 1442 |  |  | 1502 |  |  | 1586 |  |  | 1561 |  |  | 1461 |  |  | 1636 |  |  | 1519 |  |  | 1492.5 |  |  | 1502 |  |  | 1495 |  |  | 1648.5 |  |  | 1410.5 |  |  | 1518.5 |  |  | 1563.5 |  |  | 1458 |  |  | 1622 |  |  | 1417.5 |  |  | 1556.5 |  |  | 1537.5 |  |  | 1537 |  |  | 1499 |  |  | 1499 |  |  | 1497 |  |  | 1434 |  |  | 1504 |  |  | 1511 |  |  | 1476.5 |  |  | 1480.5 |  |  | 1499 |  |  | 1497.5 |  |  | 1511.5 |  |  | 1403 |  |  | 1529 |  |  | 1441 |  |  | 1466 |  |  | 1449.5 |  |  | 1415.5 |  |  | 1505.5 |  |  | 1511 |  |  | 1462.5 |  |  | 1536 |  |  | 1467 |  |  | 1524 |  |  | 1391.5 |  |  | 1493 |  |  | 1400 |  |  | 1517.5 |  |  | 1460 |  |  | 1550.5 |  |  | 1615 |  |  | 1440.5 |  |  | 1430 |  |  | 1482.5 |  |  | 1528.5 |  |  | 1549 |  |  | 1504 |  |  | 1392 |  |  | 1470 |  |  | 1425.5 |  |  | 1481 |  |  | 1541 |  |  | 1440.5 |  |  | 1578.5 |  |  | 1459.5 |  |  | 1446 |  |  | 1521.5 |  |  | 1465.5 |  |  | 1454.5 |  |  | 1564 |  |  | 1462 |  |  | 1465.5 |  |  | 1560 |  |  | 1575 |  |  | 1463.5 |  |  | 1447 |  |  | 1593 |  |  | 1479 |  |  | 1435 |  |  | 1372.5 |  |  | 1590.5 |  |  | 1442 |  |  | 1545 |  |  | 1507 |  |  | 1474 |  |  | 1450 |  |  | 1440.5 |  |  | 1494.5 |  |  | 1504 |  |  | 1633 |  |  | 1601 |  |  | 1375.5 |  |  | 1621.5 |  |  | 1460 |  |  | 1480 |  |  | 1425 |  |  | 1509.5 |  |  | 1605.5 |  |  | 1499 |  |  | 1447 |  |  | 1561 |  |  | 1528 |  |  | 1468 |  |  | 1603 |  |  | 1448 |  |  | 1614.5 |  |  | 1408 |  |  | 1647 |  |  | 1497 |  |  | 1524.5 |  |  | 1609 |  |  | 1354 |  |  | 1357 |  |  | 1473 |  |  | 1543 |  |  | 1509 |  |  | 1504 |  |  | 1457.5 |  |  | 1491.5 |  |  | 1451.5 |  |  | 1532 |  |  | 1489 |  |  | 1503.5 |  |  | 1378 |  |  | 1415.5 |  |  | 1467.5 |  |  | 1431 |  |  | 1493 |  |  | 1551.5 |  |  | 1443 |  |  | 1553 |  |  | 1557 |  |  | 1506 |  |  | 1471 |  |  | 1429 |  |  | 1455 |  |  | 1621.5 |  |  | 1495 |  |  | 1508 |  |  | 1568 |  |  | 1454 |  |  | 1561 |  |  | 1419 |  |  | 1656 |  |  | 1556 |  |  | 1522 |  |  | 1630.5 |  |  | 1533.5 |  |  | 1449.5 |  |  | 1507.5 |  |  | 1524 |  |  | 1403 |  |  | 1618.5 |  |  | 1503 |  |  | 1473 |  |  | 1477.5 |  |  | 1566.5 |  |  | 1540 |  |  | 1478.5 |  |  | 1447.5 |  |  | 1435 |  |  | 1558 |  |  | 1487 |  |  | 1460 |  |  | 1554.5 |  |  | 1461 |  |  | 1458.5 |  |  | 1406.5 |  |  | 1425 |  |  | 1454 |  |  | 1529.5 |  |  | 1443 |  |  | 1498.5 |  |  | 1476 |  |  | 1506.5 |  |  | 1419.5 |  |  | 1466.5 |  |  | 1529.5 |  |  | 1507.5 |  |  | 1391 |  |  | 1390 |  |  | 1590.5 |  |  | 1545 |  |  | 1459 |  |  | 1484 |  |  | 1611 |  |  | 1611.5 |  |  | 1358 |  |  | 1474 |  |  | 1529 |  |  | 1527.5 |  |  | 1538 |  |  | 1430 |  |  | 1506 |  |  | 1665.5 |  |  | 1553 |  |  | 1378 |  |  | 1499 |  |  | 1576 |  |  | 1730.5 |  |  | 1513 |  |  | 1447.5 |  |  | 1486 |  |  | 1530 |  |  | 1664.5 |  |  | 1549 |  |  | 1420 |  |  | 1440.5 |  |  | 1533 |  |  | 1493 |  |  | 1518 |  |  | 1592.5 |  |  | 1487.5 |  |  | 1552 |  |  | 1464 |  |  | 1515.5 |  |  | 1544.5 |  |  | 1451 |  |  | 1564 |  |  | 1568.5 |  |  | 1587.5 |  |  | 1409.5 |  |  | 1521.5 |  |  | 1467.5 |  |  | 1663 |  |  | 1507.5 |  |  | 1471 |  |  | 1491 |  |  | 1567 |  |  | 1573 |  |  | 1538.5 |  |  | 1526 |  |  | 1446 |  |  | 1525.5 |  |  | 1472.5 |  |  | 1442 |  |  | 1548.5 |  |  | 1538.5 |  |  | 1564 |  |  | 1463 |  |  | 1502 |  |  | 1563.5 |  |  | 1496 |  |  | 1519.5 |  |  | 1524 |  |  | 1503 |  |  | 1694.5 |  |  | 1495 |  |  | 1663 |  |  | 1464 |  |  | 1517 |  |  | 1555 |  |  | 1509 |  |  | 1505 |  |  | 1489 |  |  | 1406.5 |  |  | 1536.5 |  |  | 1531 |  |  | 1504.5 |  |  | 1381.5 |  |  | 1441 |  |  | 1396 |  |  | 1558 |  |  | 1570.5 |  |  | 1446.5 |  |  | 1489 |  |  | 1582 |  |  | 1417 |  |  | 1400 |  |  | 1481 |  |  | 1470 |  |  | 1660 |  |  | 1485.5 |  |  | 1574 |  |  | 1537 |  |  | 1620 |  |  | 1464 |  |  | 1347 |  |  | 1500.5 |  |  | 1663.5 |  |  | 1384.5 |  |  | 1442 |  |  | 1449 |  |  | 1412.5 |  |  | 1600.5 |  |  | 1576.5 |  |  | 1461 |  |  | 1554.5 |  |  | 1521.5 |  |  | 1532 |  |  | 1463.5 |  |  | 1555.5 |  |  | 1493 |  |  | 1457 |  |  | 1510 |  |  | 1537 |  |  | 1456 |  |  | 1418 |  |  | 1521 |  |  | 1618 |  |  | 1480 |  |  | 1439 |  |  | 1597.5 |  |  | 1466 |  |  | 1527 |  |  | 1401 |  |  | 1458.5 |  |  | 1515 |  |  | 1538.5 |  |  | 1574 |  |  | 1528 |  |  | 1485 |  |  | 1516 |  |  | 1585.5 |  |  | 1463 |  |  | 1396 |  |  | 1587.5 |  |  | 1547 |  |  | 1475 |  |  | 1471.5 |  |  | 1500.5 |  |  | 1549 |  |  | 1438.5 |  |  | 1609 |  |  | 1488.5 |  |  | 1604 |  |  | 1570 |  |  | 1488.5 |  |  | 1576.5 |  |  | 1498 |  |  | 1556 |  |  | 1495 |  |  | 1566 |  |  | 1393 |  |  | 1553 |  |  | 1387 |  |  | 1419 |  |  | 1654.5 |  |  | 1374 |  |  | 1586.5 |  |  | 1448 |  |  | 1544.5 |  |  | 1457.5 |  |  | 1473 |  |  | 1540 |  |  | 1553.5 |  |  | 1568 |  |  | 1548 |  |  | 1523 |  |  | 1452.5 |  |  | 1600 |  |  | 1428.5 |  |  | 1392 |  |  | 1457 |  |  | 1503 |  |  | 1568 |  |  | 1664.5 |  |  | 1466 |  |  | 1460 |  |  | 1502 |  |  | 1465.5 |  |  | 1593 |  |  | 1526 |  |  | 1508 |  |  | 1477 |  |  | 1493.5 |  |  | 1449.5 |  |  | 1504 |  |  | 1564 |  |  | 1509 |  |  | 1538.5 |  |  | 1529 |  |  | 1464 |  |  | 1433 |  |  | 1629.5 |  |  | 1513.5 |  |  | 1531.5 |  |  | 1497 |  |  | 1562 |  |  | 1488 |  |  | 1430.5 |  |  | 1528 |  |  | 1506.5 |  |  | 1381 |  |  | 1438 |  |  | 1513 |  |  | 1471.5 |  |  | 1529.5 |  |  | 1543 |  |  | 1449 |  |  | 1571.5 |  |  | 1488 |  |  | 1509 |  |  | 1592.5 |  |  | 1459 |  |  | 1476 |  |  | 1515.5 |  |  | 1457 |  |  | 1515 |  |  | 1516.5 |  |  | 1563 |  |  | 1427.5 |  |  | 1534 |  |  | 1412.5 |  |  | 1536.5 |  |  | 1418 |  |  | 1559 |  |  | 1550.5 |  |  | 1546.5 |  |  | 1605 |  |  | 1494 |  |  | 1584 |  |  | 1483.5 |  |  | 1528 |  |  | 1356 |  |  | 1513 |  |  | 1605.5 |  |  | 1530.5 |  |  | 1515 |  |  | 1557 |  |  | 1435 |  |  | 1399 |  |  | 1621 |  |  | 1490 |  |  | 1462 |  |  | 1475.5 |  |  | 1537.5 |  |  | 1435.5 |  |  | 1540 |  |  | 1426.5 |  |  | 1551 |  |  | 1430 |  |  | 1521.5 |  |  | 1441.5 |  |  | 1331 |  |  | 1514 |  |  | 1450.5 |  |  | 1498 |  |  | 1533 |  |  | 1438.5 |  |  | 1462.5 |  |  | 1504 |  |  | 1504 |  |  | 1589 |  |  | 1417.5 |  |  | 1478 |  |  | 1382 |  |  | 1537 |  |  | 1523 |  |  | 1568 |  |  | 1474.5 |  |  | 1607 |  |  | 1458 |  |  | 1326 |  |  | 1629.5 |  |  | 1511 |  |  | 1476.5 |  |  | 1391.5 |  |  | 1489 |  |  | 1506 |  |  | 1496.5 |  |  | 1447.5 |  |  | 1452.5 |  |  | 1499.5 |  |  | 1535.5 |  |  | 1499 |  |  | 1479 |  |  | 1537.5 |  |  | 1497.5 |  |  | 1534 |  |  | 1476 |  |  | 1493.5 |  |  | 1544 |  |  | 1500 |  |  | 1377 |  |  | 1499.5 |  |  | 1596 |  |  | 1420.5 |  |  | 1414 |  |  | 1498.5 |  |  | 1575.5 |  |  | 1646.5 |  |  | 1545 |  |  | 1464 |  |  | 1530.5 |  |  | 1430.5 |  |  | 1514 |  |  | 1538 |  |  | 1478.5 |  |  | 1525 |  |  | 1524.5 |  |  | 1497.5 |  |  | 1540 |  |  | 1470 |  |  | 1435.5 |  |  | 1599.5 |  |  | 1462 |  |  | 1467.5 |  |  | 1496.5 |  |  | 1484 |  |  | 1572 |  |  | 1601 |  |  | 1530.5 |  |  | 1564 |  |  | 1467 |  |  | 1509 |  |  | 1479 |  |  | 1541 |  |  | 1473 |  |  | 1578.5 |  |  | 1459.5 |  |  | 1469 |  |  | 1434 |  |  | 1540 |  |  | 1529.5 |  |  | 1510 |  |  | 1592 |  |  | 1435.5 |  |  | 1506.5 |  |  | 1476 |  |  | 1444.5 |  |  | 1521 |  |  | 1388 |  |  | 1534 |  |  | 1632.5 |  |  | 1607 |  |  | 1417.5 |  |  | 1456.5 |  |  | 1428 |  |  | 1553.5 |  |  | 1379.5 |  |  | 1447 |  |  | 1405 |  |  | 1621 |  |  | 1399.5 |  |  | 1417 |  |  | 1464.5 |  |  | 1472.5 |  |  | 1546 |  |  | 1456.5 |  |  | 1460 |  |  | 1511 |  |  | 1463 |  |  | 1452 |  |  | 1393 |  |  | 1586.5 |  |  | 1542 |  |  | 1579 |  |  | 1418 |  |  | 1576 |  |  | 1489.5 |  |  | 1560.5 |  |  | 1455 |  |  | 1503 |  |  | 1498 |  |  | 1418 |  |  | 1560 |  |  | 1523.5 |  |  | 1553 |  |  | 1521.5 |  |  | 1594 |  |  | 1410 |  |  | 1503 |  |  | 1441 |  |  | 1469.5 |  |  | 1461 |  |  | 1459.5 |  |  | 1436 |  |  | 1588 |  |  | 1551 |  |  | 1435.5 |  |  | 1435 |  |  | 1421 |  |  | 1403 |  |  | 1637 |  |  | 1589 |  |  | 1467.5 |  |  | 1559.5 |  |  | 1469 |  |  | 1481.5 |  |  | 1388 |  |  | 1377.5 |  |  | 1503.5 |  |  | 1419.5 |  |  | 1533.5 |  |  | 1423 |  |  | 1550 |  |  | 1475 |  |  | 1446 |  |  | 1528 |  |  | 1445 |  |  | 1456.5 |  |  | 1462.5 |  |  | 1527.5 |  |  | 1570 |  |  | 1546.5 |  |  | 1512.5 |  |  | 1542.5 |  |  | 1456.5 |  |  | 1456 |  |  | 1507.5 |  |  | 1481.5 |  |  | 1547 |  |  | 1477.5 |  |  | 1531.5 |  |  | 1542.5 |  |  | 1556 |  |  | 1503.5 |  |  | 1502 |  |  | 1547 |  |  | 1530.5 |  |  | 1525.5 |  |  | 1545 |  |  | 1516 |  |  | 1371.5 |  |  | 1411.5 |  |  | 1499.5 |  |  | 1514 |  |  | 1472 |  |  | 1455 |  |  | 1512.5 |  |  | 1549.5 |  |  | 1578 |  |  | 1545.5 |  |  | 1404 |  |  | 1472 |  |  | 1534.5 |  |  | 1439.5 |  |  | 1455 |  |  | 1500.5 |  |  | 1462 |  |  | 1406.5 |  |  | 1607.5 |  |  | 1539 |  |  | 1422.5 |  |  | 1550 |  |  | 1507.5 |  |  | 1508 |  |  | 1546 |  |  | 1562 |  |  | 1424.5 |  |  | 1392.5 |  |  | 1558 |  |  | 1427 |  |  | 1461 |  |  | 1492.5 |  |  | 1482.5 |  |  | 1539 |  |  | 1471.5 |  |  | 1458 |  |  | 1437.5 |  |  | 1527.5 |  |  | 1440 |  |  | 1433 |  |  | 1493 |  |  | 1473.5 |  |  | 1498 |  |  | 1571.5 |  |  | 1533 |  |  | 1504.5 |  |  | 1692 |  |  | 1332.5 |  |  | 1464 |  |  | 1454.5 |  |  | 1465.5 |  |  | 1475 |  |  | 1447 |  |  | 1568 |  |  | 1496 |  |  | 1563.5 |  |  | 1425 |  |  | 1461.5 |  |  | 1395 |  |  | 1459 |  |  | 1471 |  |  | 1538 |  |  | 1565 |  |  | 1486 |  |  | 1488 |  |  | 1577.5 |  |  | 1436 |  |  | 1564
54 |  | 1608.5 |  |  | 1595 |  |  | 1560.5 |  |  | 1524 |  |  | 1532.5 |  |  | 1559 |  |  | 1525 |  |  | 1605 |  |  | 1487.5 |  |  | 1525 |  |  | 1494 |  |  | 1651 |  |  | 1559 |  |  | 1635 |  |  | 1447.5 |  |  | 1592.5 |  |  | 1469 |  |  | 1621 |  |  | 1658 |  |  | 1455.5 |  |  | 1565 |  |  | 1589 |  |  | 1478 |  |  | 1569 |  |  | 1537.5 |  |  | 1655 |  |  | 1566 |  |  | 1477 |  |  | 1578 |  |  | 1475 |  |  | 1503 |  |  | 1547.5 |  |  | 1622.5 |  |  | 1538.5 |  |  | 1413 |  |  | 1480.5 |  |  | 1516.5 |  |  | 1545.5 |  |  | 1568 |  |  | 1513 |  |  | 1436.5 |  |  | 1409 |  |  | 1596.5 |  |  | 1531.5 |  |  | 1590.5 |  |  | 1631.5 |  |  | 1643.5 |  |  | 1519 |  |  | 1389 |  |  | 1434.5 |  |  | 1523 |  |  | 1475.5 |  |  | 1473.5 |  |  | 1594 |  |  | 1477 |  |  | 1511 |  |  | 1489 |  |  | 1616 |  |  | 1572 |  |  | 1509.5 |  |  | 1599.5 |  |  | 1564.5 |  |  | 1393 |  |  | 1588 |  |  | 1448 |  |  | 1457.5 |  |  | 1496 |  |  | 1549.5 |  |  | 1547.5 |  |  | 1634.5 |  |  | 1468 |  |  | 1557 |  |  | 1564 |  |  | 1540.5 |  |  | 1577.5 |  |  | 1495.5 |  |  | 1603.5 |  |  | 1576.5 |  |  | 1570.5 |  |  | 1543.5 |  |  | 1503.5 |  |  | 1478 |  |  | 1521 |  |  | 1513 |  |  | 1605.5 |  |  | 1613 |  |  | 1429.5 |  |  | 1531 |  |  | 1575 |  |  | 1566.5 |  |  | 1599.5 |  |  | 1520 |  |  | 1749 |  |  | 1471.5 |  |  | 1604 |  |  | 1489.5 |  |  | 1547.5 |  |  | 1506.5 |  |  | 1483.5 |  |  | 1435.5 |  |  | 1572 |  |  | 1507 |  |  | 1456 |  |  | 1561.5 |  |  | 1510.5 |  |  | 1551.5 |  |  | 1511.5 |  |  | 1535 |  |  | 1515 |  |  | 1525.5 |  |  | 1420 |  |  | 1556.5 |  |  | 1581 |  |  | 1541 |  |  | 1473.5 |  |  | 1498 |  |  | 1497 |  |  | 1501 |  |  | 1522 |  |  | 1594.5 |  |  | 1520.5 |  |  | 1488.5 |  |  | 1690 |  |  | 1483 |  |  | 1418 |  |  | 1486 |  |  | 1490.5 |  |  | 1513 |  |  | 1555.5 |  |  | 1598 |  |  | 1452 |  |  | 1564.5 |  |  | 1443.5 |  |  | 1430 |  |  | 1476.5 |  |  | 1494 |  |  | 1517 |  |  | 1524 |  |  | 1537 |  |  | 1505 |  |  | 1425 |  |  | 1499 |  |  | 1546 |  |  | 1452 |  |  | 1435.5 |  |  | 1492 |  |  | 1421 |  |  | 1553 |  |  | 1522 |  |  | 1457 |  |  | 1479 |  |  | 1488 |  |  | 1569.5 |  |  | 1553 |  |  | 1519.5 |  |  | 1584 |  |  | 1470 |  |  | 1571.5 |  |  | 1506 |  |  | 1679.5 |  |  | 1529 |  |  | 1422 |  |  | 1567.5 |  |  | 1553 |  |  | 1586.5 |  |  | 1511 |  |  | 1466 |  |  | 1534.5 |  |  | 1557.5 |  |  | 1590 |  |  | 1474.5 |  |  | 1546.5 |  |  | 1515 |  |  | 1549 |  |  | 1711.5 |  |  | 1489.5 |  |  | 1484.5 |  |  | 1571 |  |  | 1592 |  |  | 1500 |  |  | 1601 |  |  | 1591 |  |  | 1555.5 |  |  | 1510 |  |  | 1395.5 |  |  | 1525.5 |  |  | 1568 |  |  | 1635 |  |  | 1669.5 |  |  | 1425.5 |  |  | 1487 |  |  | 1572.5 |  |  | 1470.5 |  |  | 1571 |  |  | 1433 |  |  | 1518 |  |  | 1455.5 |  |  | 1657 |  |  | 1532.5 |  |  | 1497.5 |  |  | 1472 |  |  | 1528.5 |  |  | 1433 |  |  | 1548 |  |  | 1517 |  |  | 1533 |  |  | 1441 |  |  | 1600 |  |  | 1597 |  |  | 1587 |  |  | 1639 |  |  | 1510 |  |  | 1532.5 |  |  | 1638.5 |  |  | 1527 |  |  | 1441 |  |  | 1629 |  |  | 1570.5 |  |  | 1588.5 |  |  | 1563.5 |  |  | 1519 |  |  | 1552 |  |  | 1612.5 |  |  | 1503.5 |  |  | 1418.5 |  |  | 1620 |  |  | 1605 |  |  | 1530 |  |  | 1502 |  |  | 1538 |  |  | 1483.5 |  |  | 1505.5 |  |  | 1628 |  |  | 1546 |  |  | 1484 |  |  | 1631 |  |  | 1520 |  |  | 1505.5 |  |  | 1548 |  |  | 1573 |  |  | 1514 |  |  | 1525 |  |  | 1502.5 |  |  | 1669 |  |  | 1582 |  |  | 1527 |  |  | 1607 |  |  | 1592.5 |  |  | 1631 |  |  | 1481 |  |  | 1432 |  |  | 1577.5 |  |  | 1546.5 |  |  | 1587.5 |  |  | 1620 |  |  | 1504 |  |  | 1457 |  |  | 1645 |  |  | 1564 |  |  | 1474.5 |  |  | 1598 |  |  | 1441.5 |  |  | 1567.5 |  |  | 1591.5 |  |  | 1545 |  |  | 1633.5 |  |  | 1511 |  |  | 1467 |  |  | 1474.5 |  |  | 1538.5 |  |  | 1596 |  |  | 1647.5 |  |  | 1597.5 |  |  | 1573 |  |  | 1619 |  |  | 1542.5 |  |  | 1442.5 |  |  | 1618 |  |  | 1565.5 |  |  | 1532 |  |  | 1481 |  |  | 1500.5 |  |  | 1593 |  |  | 1503 |  |  | 1539.5 |  |  | 1496 |  |  | 1616.5 |  |  | 1502 |  |  | 1685 |  |  | 1526 |  |  | 1421 |  |  | 1622.5 |  |  | 1674 |  |  | 1600.5 |  |  | 1491.5 |  |  | 1595.5 |  |  | 1636 |  |  | 1660.5 |  |  | 1659 |  |  | 1580 |  |  | 1415.5 |  |  | 1524.5 |  |  | 1556 |  |  | 1545.5 |  |  | 1595 |  |  | 1515 |  |  | 1644.5 |  |  | 1528 |  |  | 1515.5 |  |  | 1540.5 |  |  | 1575.5 |  |  | 1528 |  |  | 1478 |  |  | 1511 |  |  | 1399.5 |  |  | 1481 |  |  | 1639.5 |  |  | 1549 |  |  | 1522 |  |  | 1471 |  |  | 1528 |  |  | 1633 |  |  | 1582 |  |  | 1500 |  |  | 1675 |  |  | 1543 |  |  | 1531.5 |  |  | 1541 |  |  | 1510 |  |  | 1695.5 |  |  | 1449.5 |  |  | 1533.5 |  |  | 1610.5 |  |  | 1505 |  |  | 1637 |  |  | 1443.5 |  |  | 1582.5 |  |  | 1576.5 |  |  | 1561 |  |  | 1520 |  |  | 1523 |  |  | 1521 |  |  | 1449 |  |  | 1525 |  |  | 1558 |  |  | 1515.5 |  |  | 1527.5 |  |  | 1514 |  |  | 1518.5 |  |  | 1540.5 |  |  | 1442 |  |  | 1576 |  |  | 1480 |  |  | 1487 |  |  | 1464.5 |  |  | 1439.5 |  |  | 1544.5 |  |  | 1526 |  |  | 1501.5 |  |  | 1560 |  |  | 1496 |  |  | 1571 |  |  | 1420.5 |  |  | 1532 |  |  | 1415 |  |  | 1564.5 |  |  | 1475 |  |  | 1574.5 |  |  | 1662 |  |  | 1469.5 |  |  | 1454 |  |  | 1521.5 |  |  | 1549.5 |  |  | 1570 |  |  | 1543 |  |  | 1413 |  |  | 1499 |  |  | 1440.5 |  |  | 1496 |  |  | 1567 |  |  | 1479.5 |  |  | 1625.5 |  |  | 1480.5 |  |  | 1470 |  |  | 1536.5 |  |  | 1504.5 |  |  | 1501.5 |  |  | 1585 |  |  | 1501 |  |  | 1480.5 |  |  | 1589 |  |  | 1601 |  |  | 1510.5 |  |  | 1473 |  |  | 1614 |  |  | 1526 |  |  | 1456 |  |  | 1411.5 |  |  | 1629.5 |  |  | 1468 |  |  | 1569 |  |  | 1546 |  |  | 1500 |  |  | 1479 |  |  | 1455.5 |  |  | 1515.5 |  |  | 1530 |  |  | 1654 |  |  | 1640 |  |  | 1414.5 |  |  | 1668.5 |  |  | 1481 |  |  | 1519 |  |  | 1464 |  |  | 1538.5 |  |  | 1652.5 |  |  | 1546 |  |  | 1476 |  |  | 1576 |  |  | 1554 |  |  | 1515 |  |  | 1642 |  |  | 1487 |  |  | 1653.5 |  |  | 1434 |  |  | 1668 |  |  | 1523 |  |  | 1571.5 |  |  | 1638 |  |  | 1393 |  |  | 1378 |  |  | 1512 |  |  | 1572 |  |  | 1535 |  |  | 1525 |  |  | 1486.5 |  |  | 1512.5 |  |  | 1472.5 |  |  | 1561 |  |  | 1518 |  |  | 1532.5 |  |  | 1393 |  |  | 1454.5 |  |  | 1491.5 |  |  | 1478 |  |  | 1532 |  |  | 1566.5 |  |  | 1467 |  |  | 1592 |  |  | 1586 |  |  | 1545 |  |  | 1518 |  |  | 1468 |  |  | 1484 |  |  | 1660.5 |  |  | 1534 |  |  | 1537 |  |  | 1615 |  |  | 1480 |  |  | 1585 |  |  | 1445 |  |  | 1703 |  |  | 1582 |  |  | 1551 |  |  | 1651.5 |  |  | 1562.5 |  |  | 1478.5 |  |  | 1546.5 |  |  | 1548 |  |  | 1442 |  |  | 1642.5 |  |  | 1532 |  |  | 1520 |  |  | 1492.5 |  |  | 1592.5 |  |  | 1561 |  |  | 1517.5 |  |  | 1462.5 |  |  | 1474 |  |  | 1597 |  |  | 1513 |  |  | 1486 |  |  | 1569.5 |  |  | 1500 |  |  | 1484.5 |  |  | 1432.5 |  |  | 1446 |  |  | 1483 |  |  | 1553.5 |  |  | 1458 |  |  | 1513.5 |  |  | 1523 |  |  | 1535.5 |  |  | 1434.5 |  |  | 1487.5 |  |  | 1544.5 |  |  | 1554.5 |  |  | 1420 |  |  | 1411 |  |  | 1619.5 |  |  | 1560 |  |  | 1474 |  |  | 1510 |  |  | 1650 |  |  | 1637.5 |  |  | 1387 |  |  | 1503 |  |  | 1568 |  |  | 1556.5 |  |  | 1567 |  |  | 1445 |  |  | 1527 |  |  | 1704.5 |  |  | 1592 |  |  | 1417 |  |  | 1523 |  |  | 1591 |  |  | 1756.5 |  |  | 1539 |  |  | 1486.5 |  |  | 1525 |  |  | 1569 |  |  | 1690.5 |  |  | 1575 |  |  | 1459 |  |  | 1469.5 |  |  | 1572 |  |  | 1508 |  |  | 1565 |  |  | 1631.5 |  |  | 1513.5 |  |  | 1567 |  |  | 1488 |  |  | 1562.5 |  |  | 1570.5 |  |  | 1475 |  |  | 1579 |  |  | 1592.5 |  |  | 1634.5 |  |  | 1430.5 |  |  | 1542.5 |  |  | 1493.5 |  |  | 1710 |  |  | 1533.5 |  |  | 1510 |  |  | 1517 |  |  | 1596 |  |  | 1597 |  |  | 1553.5 |  |  | 1547 |  |  | 1485 |  |  | 1540.5 |  |  | 1493.5 |  |  | 1481 |  |  | 1574.5 |  |  | 1564.5 |  |  | 1603 |  |  | 1487 |  |  | 1517 |  |  | 1584.5 |  |  | 1517 |  |  | 1558.5 |  |  | 1571 |  |  | 1542 |  |  | 1709.5 |  |  | 1534 |  |  | 1692 |  |  | 1503 |  |  | 1543 |  |  | 1584 |  |  | 1524 |  |  | 1544 |  |  | 1515 |  |  | 1445.5 |  |  | 1565.5 |  |  | 1557 |  |  | 1543.5 |  |  | 1410.5 |  |  | 1465 |  |  | 1435 |  |  | 1597 |  |  | 1609.5 |  |  | 1485.5 |  |  | 1528 |  |  | 1629 |  |  | 1443 |  |  | 1429 |  |  | 1507 |  |  | 1509 |  |  | 1675 |  |  | 1524.5 |  |  | 1600 |  |  | 1584 |  |  | 1644 |  |  | 1479 |  |  | 1386 |  |  | 1515.5 |  |  | 1702.5 |  |  | 1410.5 |  |  | 1457 |  |  | 1464 |  |  | 1451.5 |  |  | 1629.5 |  |  | 1602.5 |  |  | 1508 |  |  | 1601.5 |  |  | 1547.5 |  |  | 1579 |  |  | 1487.5 |  |  | 1584.5 |  |  | 1540 |  |  | 1486 |  |  | 1539 |  |  | 1558 |  |  | 1480 |  |  | 1439 |  |  | 1542 |  |  | 1639 |  |  | 1504 |  |  | 1460 |  |  | 1618.5 |  |  | 1492 |  |  | 1566 |  |  | 1440 |  |  | 1484.5 |  |  | 1554 |  |  | 1562.5 |  |  | 1613 |  |  | 1554 |  |  | 1524 |  |  | 1531 |  |  | 1614.5 |  |  | 1502 |  |  | 1422 |  |  | 1626.5 |  |  | 1586 |  |  | 1490 |  |  | 1518.5 |  |  | 1547.5 |  |  | 1575 |  |  | 1464.5 |  |  | 1624 |  |  | 1512.5 |  |  | 1625 |  |  | 1599 |  |  | 1527.5 |  |  | 1623.5 |  |  | 1522 |  |  | 1595 |  |  | 1519 |  |  | 1590 |  |  | 1440 |  |  | 1579 |  |  | 1402 |  |  | 1445 |  |  | 1701.5 |  |  | 1398 |  |  | 1610.5 |  |  | 1463 |  |  | 1583.5 |  |  | 1483.5 |  |  | 1499 |  |  | 1555 |  |  | 1582.5 |  |  | 1615 |  |  | 1587 |  |  | 1562 |  |  | 1499.5 |  |  | 1615 |  |  | 1452.5 |  |  | 1407 |  |  | 1483 |  |  | 1542 |  |  | 1592 |  |  | 1690.5 |  |  | 1495 |  |  | 1475 |  |  | 1549 |  |  | 1489.5 |  |  | 1632 |  |  | 1552 |  |  | 1532 |  |  | 1506 |  |  | 1519.5 |  |  | 1496.5 |  |  | 1543 |  |  | 1603 |  |  | 1533 |  |  | 1562.5 |  |  | 1558 |  |  | 1488 |  |  | 1472 |  |  | 1658.5 |  |  | 1537.5 |  |  | 1552.5 |  |  | 1544 |  |  | 1609 |  |  | 1503 |  |  | 1454.5 |  |  | 1567 |  |  | 1553.5 |  |  | 1420 |  |  | 1477 |  |  | 1528 |  |  | 1518.5 |  |  | 1568.5 |  |  | 1590 |  |  | 1488 |  |  | 1618.5 |  |  | 1514 |  |  | 1530 |  |  | 1631.5 |  |  | 1506 |  |  | 1515 |  |  | 1544.5 |  |  | 1486 |  |  | 1530 |  |  | 1537.5 |  |  | 1610 |  |  | 1466.5 |  |  | 1573 |  |  | 1433.5 |  |  | 1562.5 |  |  | 1442 |  |  | 1606 |  |  | 1597.5 |  |  | 1585.5 |  |  | 1652 |  |  | 1541 |  |  | 1631 |  |  | 1507.5 |  |  | 1575 |  |  | 1380 |  |  | 1537 |  |  | 1644.5 |  |  | 1545.5 |  |  | 1554 |  |  | 1586 |  |  | 1482 |  |  | 1423 |  |  | 1645 |  |  | 1514 |  |  | 1486 |  |  | 1504.5 |  |  | 1584.5 |  |  | 1464.5 |  |  | 1579 |  |  | 1473.5 |  |  | 1566 |  |  | 1477 |  |  | 1547.5 |  |  | 1467.5 |  |  | 1355 |  |  | 1553 |  |  | 1497.5 |  |  | 1522 |  |  | 1562 |  |  | 1485.5 |  |  | 1501.5 |  |  | 1528 |  |  | 1519 |  |  | 1618 |  |  | 1456.5 |  |  | 1507 |  |  | 1421 |  |  | 1566 |  |  | 1570 |  |  | 1589 |  |  | 1498.5 |  |  | 1654 |  |  | 1479 |  |  | 1352 |  |  | 1650.5 |  |  | 1550 |  |  | 1500.5 |  |  | 1430.5 |  |  | 1513 |  |  | 1545 |  |  | 1522.5 |  |  | 1473.5 |  |  | 1467.5 |  |  | 1546.5 |  |  | 1582.5 |  |  | 1528 |  |  | 1494 |  |  | 1561.5 |  |  | 1512.5 |  |  | 1555 |  |  | 1505 |  |  | 1517.5 |  |  | 1591 |  |  | 1526 |  |  | 1416 |  |  | 1538.5 |  |  | 1617 |  |  | 1459.5 |  |  | 1429 |  |  | 1524.5 |  |  | 1622.5 |  |  | 1672.5 |  |  | 1592 |  |  | 1488 |  |  | 1554.5 |  |  | 1454.5 |  |  | 1553 |  |  | 1562 |  |  | 1517.5 |  |  | 1554 |  |  | 1550.5 |  |  | 1523.5 |  |  | 1564 |  |  | 1517 |  |  | 1461.5 |  |  | 1623.5 |  |  | 1491 |  |  | 1491.5 |  |  | 1520.5 |  |  | 1531 |  |  | 1611 |  |  | 1627 |  |  | 1554.5 |  |  | 1579 |  |  | 1506 |  |  | 1538 |  |  | 1500 |  |  | 1556 |  |  | 1512 |  |  | 1599.5 |  |  | 1498.5 |  |  | 1516 |  |  | 1460 |  |  | 1561 |  |  | 1550.5 |  |  | 1531 |  |  | 1616 |  |  | 1456.5 |  |  | 1532.5 |  |  | 1515 |  |  | 1473.5 |  |  | 1550 |  |  | 1412 |  |  | 1549 |  |  | 1656.5 |  |  | 1646 |  |  | 1443.5 |  |  | 1495.5 |  |  | 1457 |  |  | 1574.5 |  |  | 1426.5 |  |  | 1476 |  |  | 1452 |  |  | 1647 |  |  | 1428.5 |  |  | 1432 |  |  | 1488.5 |  |  | 1501.5 |  |  | 1575 |  |  | 1471.5 |  |  | 1484 |  |  | 1540 |  |  | 1502 |  |  | 1499 |  |  | 1432 |  |  | 1610.5 |  |  | 1581 |  |  | 1626 |  |  | 1439 |  |  | 1591 |  |  | 1504.5 |  |  | 1599.5 |  |  | 1502 |  |  | 1527 |  |  | 1522 |  |  | 1465 |  |  | 1581 |  |  | 1538.5 |  |  | 1568 |  |  | 1545.5 |  |  | 1641 |  |  | 1425 |  |  | 1542 |  |  | 1470 |  |  | 1516.5 |  |  | 1500 |  |  | 1498.5 |  |  | 1460 |  |  | 1635 |  |  | 1598 |  |  | 1474.5 |  |  | 1456 |  |  | 1442 |  |  | 1424 |  |  | 1658 |  |  | 1628 |  |  | 1506.5 |  |  | 1598.5 |  |  | 1498 |  |  | 1496.5 |  |  | 1427 |  |  | 1406.5 |  |  | 1550.5 |  |  | 1445.5 |  |  | 1580.5 |  |  | 1444 |  |  | 1579 |  |  | 1501 |  |  | 1493 |  |  | 1557 |  |  | 1492 |  |  | 1482.5 |  |  | 1483.5 |  |  | 1574.5 |  |  | 1599 |  |  | 1575.5 |  |  | 1541.5 |  |  | 1589.5 |  |  | 1495.5 |  |  | 1482 |  |  | 1522.5 |  |  | 1528.5 |  |  | 1586 |  |  | 1492.5 |  |  | 1570.5 |  |  | 1571.5 |  |  | 1595 |  |  | 1542.5 |  |  | 1549 |  |  | 1573 |  |  | 1569.5 |  |  | 1564.5 |  |  | 1584 |  |  | 1531 |  |  | 1418.5 |  |  | 1458.5 |  |  | 1525.5 |  |  | 1561 |  |  | 1493 |  |  | 1476 |  |  | 1536.5 |  |  | 1588.5 |  |  | 1607 |  |  | 1584.5 |  |  | 1451 |  |  | 1519 |  |  | 1573.5 |  |  | 1486.5 |  |  | 1476 |  |  | 1539.5 |  |  | 1483 |  |  | 1430.5 |  |  | 1646.5 |  |  | 1578 |  |  | 1461.5 |  |  | 1571 |  |  | 1533.5 |  |  | 1555 |  |  | 1567 |  |  | 1601 |  |  | 1453.5 |  |  | 1416.5 |  |  | 1587 |  |  | 1451 |  |  | 1508 |  |  | 1521.5 |  |  | 1521.5 |  |  | 1578 |  |  | 1510.5 |  |  | 1487 |  |  | 1458.5 |  |  | 1556.5 |  |  | 1487 |  |  | 1472 |  |  | 1519 |  |  | 1494.5 |  |  | 1527 |  |  | 1595.5 |  |  | 1554 |  |  | 1543.5 |  |  | 1731 |  |  | 1347.5 |  |  | 1511 |  |  | 1483.5 |  |  | 1504.5 |  |  | 1490 |  |  | 1486 |  |  | 1607 |  |  | 1535 |  |  | 1602.5 |  |  | 1446 |  |  | 1508.5 |  |  | 1416 |  |  | 1483 |  |  | 1497 |  |  | 1577 |  |  | 1580 |  |  | 1525 |  |  | 1527 |  |  | 1592.5 |  |  | 1460 |  |  | 1579
55 |  | 1634.5 |  |  | 1642 |  |  | 1581.5 |  |  | 1539 |  |  | 1561.5 |  |  | 1606 |  |  | 1564 |  |  | 1631 |  |  | 1508.5 |  |  | 1551 |  |  | 1541 |  |  | 1666 |  |  | 1588 |  |  | 1682 |  |  | 1462.5 |  |  | 1631.5 |  |  | 1498 |  |  | 1668 |  |  | 1705 |  |  | 1494.5 |  |  | 1594 |  |  | 1628 |  |  | 1499 |  |  | 1608 |  |  | 1552.5 |  |  | 1694 |  |  | 1581 |  |  | 1503 |  |  | 1599 |  |  | 1499 |  |  | 1527 |  |  | 1576.5 |  |  | 1643.5 |  |  | 1562.5 |  |  | 1452 |  |  | 1506.5 |  |  | 1540.5 |  |  | 1574.5 |  |  | 1594 |  |  | 1560 |  |  | 1475.5 |  |  | 1456 |  |  | 1625.5 |  |  | 1546.5 |  |  | 1619.5 |  |  | 1678.5 |  |  | 1690.5 |  |  | 1566 |  |  | 1428 |  |  | 1458.5 |  |  | 1538 |  |  | 1514.5 |  |  | 1494.5 |  |  | 1618 |  |  | 1516 |  |  | 1535 |  |  | 1504 |  |  | 1637 |  |  | 1619 |  |  | 1548.5 |  |  | 1638.5 |  |  | 1603.5 |  |  | 1432 |  |  | 1614 |  |  | 1463 |  |  | 1496.5 |  |  | 1543 |  |  | 1570.5 |  |  | 1571.5 |  |  | 1673.5 |  |  | 1507 |  |  | 1596 |  |  | 1579 |  |  | 1566.5 |  |  | 1606.5 |  |  | 1516.5 |  |  | 1629.5 |  |  | 1591.5 |  |  | 1594.5 |  |  | 1572.5 |  |  | 1527.5 |  |  | 1504 |  |  | 1545 |  |  | 1537 |  |  | 1652.5 |  |  | 1634 |  |  | 1444.5 |  |  | 1546 |  |  | 1614 |  |  | 1605.5 |  |  | 1628.5 |  |  | 1541 |  |  | 1775 |  |  | 1510.5 |  |  | 1630 |  |  | 1513.5 |  |  | 1573.5 |  |  | 1545.5 |  |  | 1504.5 |  |  | 1464.5 |  |  | 1598 |  |  | 1546 |  |  | 1471 |  |  | 1608.5 |  |  | 1549.5 |  |  | 1598.5 |  |  | 1550.5 |  |  | 1559 |  |  | 1554 |  |  | 1564.5 |  |  | 1459 |  |  | 1582.5 |  |  | 1596 |  |  | 1567 |  |  | 1499.5 |  |  | 1537 |  |  | 1536 |  |  | 1540 |  |  | 1561 |  |  | 1620.5 |  |  | 1559.5 |  |  | 1527.5 |  |  | 1711 |  |  | 1512 |  |  | 1457 |  |  | 1515 |  |  | 1537.5 |  |  | 1539 |  |  | 1576.5 |  |  | 1624 |  |  | 1473 |  |  | 1611.5 |  |  | 1490.5 |  |  | 1451 |  |  | 1500.5 |  |  | 1515 |  |  | 1556 |  |  | 1563 |  |  | 1584 |  |  | 1520 |  |  | 1472 |  |  | 1528 |  |  | 1567 |  |  | 1467 |  |  | 1456.5 |  |  | 1513 |  |  | 1450 |  |  | 1579 |  |  | 1561 |  |  | 1496 |  |  | 1494 |  |  | 1535 |  |  | 1616.5 |  |  | 1582 |  |  | 1540.5 |  |  | 1623 |  |  | 1509 |  |  | 1618.5 |  |  | 1553 |  |  | 1700.5 |  |  | 1568 |  |  | 1448 |  |  | 1582.5 |  |  | 1568 |  |  | 1610.5 |  |  | 1537 |  |  | 1505 |  |  | 1573.5 |  |  | 1581.5 |  |  | 1605 |  |  | 1500.5 |  |  | 1570.5 |  |  | 1562 |  |  | 1588 |  |  | 1740.5 |  |  | 1504.5 |  |  | 1531.5 |  |  | 1592 |  |  | 1613 |  |  | 1526 |  |  | 1648 |  |  | 1612 |  |  | 1594.5 |  |  | 1549 |  |  | 1434.5 |  |  | 1564.5 |  |  | 1607 |  |  | 1664 |  |  | 1693.5 |  |  | 1451.5 |  |  | 1508 |  |  | 1611.5 |  |  | 1494.5 |  |  | 1592 |  |  | 1448 |  |  | 1539 |  |  | 1484.5 |  |  | 1696 |  |  | 1553.5 |  |  | 1523.5 |  |  | 1487 |  |  | 1554.5 |  |  | 1480 |  |  | 1572 |  |  | 1556 |  |  | 1557 |  |  | 1456 |  |  | 1621 |  |  | 1636 |  |  | 1626 |  |  | 1668 |  |  | 1525 |  |  | 1571.5 |  |  | 1677.5 |  |  | 1551 |  |  | 1480 |  |  | 1668 |  |  | 1591.5 |  |  | 1617.5 |  |  | 1584.5 |  |  | 1566 |  |  | 1581 |  |  | 1636.5 |  |  | 1542.5 |  |  | 1457.5 |  |  | 1635 |  |  | 1634 |  |  | 1554 |  |  | 1531 |  |  | 1585 |  |  | 1512.5 |  |  | 1529.5 |  |  | 1652 |  |  | 1572 |  |  | 1499 |  |  | 1652 |  |  | 1544 |  |  | 1526.5 |  |  | 1563 |  |  | 1602 |  |  | 1543 |  |  | 1554 |  |  | 1541.5 |  |  | 1684 |  |  | 1606 |  |  | 1556 |  |  | 1631 |  |  | 1631.5 |  |  | 1678 |  |  | 1507 |  |  | 1461 |  |  | 1592.5 |  |  | 1570.5 |  |  | 1626.5 |  |  | 1659 |  |  | 1528 |  |  | 1472 |  |  | 1669 |  |  | 1585 |  |  | 1513.5 |  |  | 1624 |  |  | 1480.5 |  |  | 1606.5 |  |  | 1606.5 |  |  | 1592 |  |  | 1672.5 |  |  | 1535 |  |  | 1493 |  |  | 1503.5 |  |  | 1577.5 |  |  | 1625 |  |  | 1686.5 |  |  | 1644.5 |  |  | 1594 |  |  | 1658 |  |  | 1581.5 |  |  | 1481.5 |  |  | 1639 |  |  | 1591.5 |  |  | 1579 |  |  | 1505 |  |  | 1524.5 |  |  | 1608 |  |  | 1518 |  |  | 1586.5 |  |  | 1525 |  |  | 1637.5 |  |  | 1541 |  |  | 1711 |  |  | 1565 |  |  | 1468 |  |  | 1643.5 |  |  | 1703 |  |  | 1629.5 |  |  | 1506.5 |  |  | 1610.5 |  |  | 1665 |  |  | 1686.5 |  |  | 1706 |  |  | 1601 |  |  | 1441.5 |  |  | 1550.5 |  |  | 1582 |  |  | 1560.5 |  |  | 1621 |  |  | 1544 |  |  | 1670.5 |  |  | 1557 |  |  | 1536.5 |  |  | 1579.5 |  |  | 1604.5 |  |  | 1554 |  |  | 1504 |  |  | 1558 |  |  | 1446.5 |  |  | 1528 |  |  | 1686.5 |  |  | 1570 |  |  | 1551 |  |  | 1492 |  |  | 1549 |  |  | 1654 |  |  | 1597 |  |  | 1529 |  |  | 1714 |  |  | 1567 |  |  | 1546.5 |  |  | 1562 |  |  | 1531 |  |  | 1716.5 |  |  | 1470.5 |  |  | 1572.5 |  |  | 1625.5 |  |  | 1529 |  |  | 1661 |  |  | 1469.5 |  |  | 1621.5 |  |  | 1591.5 |  |  | 1585 |  |  | 1559 |  |  | 1544 |  |  | 1550 |  |  | 1470 |  |  | 1564 |  |  | 1582 |  |  | 1554.5 |  |  | 1551.5 |  |  | 1529 |  |  | 1539.5 |  |  | 1564.5 |  |  | 1466 |  |  | 1605 |  |  | 1495 |  |  | 1502 |  |  | 1488.5 |  |  | 1468.5 |  |  | 1573.5 |  |  | 1550 |  |  | 1540.5 |  |  | 1581 |  |  | 1525 |  |  | 1610 |  |  | 1441.5 |  |  | 1553 |  |  | 1462 |  |  | 1593.5 |  |  | 1514 |  |  | 1603.5 |  |  | 1701 |  |  | 1493.5 |  |  | 1475 |  |  | 1545.5 |  |  | 1596.5 |  |  | 1585 |  |  | 1582 |  |  | 1439 |  |  | 1528 |  |  | 1464.5 |  |  | 1525 |  |  | 1614 |  |  | 1508.5 |  |  | 1640.5 |  |  | 1509.5 |  |  | 1517 |  |  | 1575.5 |  |  | 1543.5 |  |  | 1530.5 |  |  | 1632 |  |  | 1540 |  |  | 1519.5 |  |  | 1615 |  |  | 1648 |  |  | 1549.5 |  |  | 1488 |  |  | 1638 |  |  | 1565 |  |  | 1503 |  |  | 1450.5 |  |  | 1655.5 |  |  | 1507 |  |  | 1608 |  |  | 1575 |  |  | 1539 |  |  | 1503 |  |  | 1476.5 |  |  | 1554.5 |  |  | 1569 |  |  | 1693 |  |  | 1669 |  |  | 1443.5 |  |  | 1707.5 |  |  | 1507 |  |  | 1545 |  |  | 1490 |  |  | 1553.5 |  |  | 1673.5 |  |  | 1572 |  |  | 1497 |  |  | 1615 |  |  | 1575 |  |  | 1541 |  |  | 1668 |  |  | 1516 |  |  | 1668.5 |  |  | 1458 |  |  | 1692 |  |  | 1552 |  |  | 1600.5 |  |  | 1659 |  |  | 1440 |  |  | 1399 |  |  | 1559 |  |  | 1611 |  |  | 1556 |  |  | 1554 |  |  | 1515.5 |  |  | 1538.5 |  |  | 1487.5 |  |  | 1608 |  |  | 1547 |  |  | 1579.5 |  |  | 1419 |  |  | 1483.5 |  |  | 1538.5 |  |  | 1517 |  |  | 1571 |  |  | 1595.5 |  |  | 1506 |  |  | 1621 |  |  | 1615 |  |  | 1584 |  |  | 1557 |  |  | 1515 |  |  | 1510 |  |  | 1675.5 |  |  | 1555 |  |  | 1576 |  |  | 1654 |  |  | 1504 |  |  | 1624 |  |  | 1492 |  |  | 1718 |  |  | 1611 |  |  | 1572 |  |  | 1690.5 |  |  | 1586.5 |  |  | 1517.5 |  |  | 1585.5 |  |  | 1587 |  |  | 1481 |  |  | 1663.5 |  |  | 1556 |  |  | 1559 |  |  | 1539.5 |  |  | 1618.5 |  |  | 1587 |  |  | 1543.5 |  |  | 1483.5 |  |  | 1498 |  |  | 1636 |  |  | 1539 |  |  | 1533 |  |  | 1598.5 |  |  | 1524 |  |  | 1510.5 |  |  | 1447.5 |  |  | 1461 |  |  | 1509 |  |  | 1582.5 |  |  | 1479 |  |  | 1560.5 |  |  | 1549 |  |  | 1574.5 |  |  | 1473.5 |  |  | 1511.5 |  |  | 1583.5 |  |  | 1569.5 |  |  | 1459 |  |  | 1432 |  |  | 1658.5 |  |  | 1599 |  |  | 1503 |  |  | 1531 |  |  | 1676 |  |  | 1684.5 |  |  | 1408 |  |  | 1524 |  |  | 1589 |  |  | 1585.5 |  |  | 1582 |  |  | 1466 |  |  | 1548 |  |  | 1719.5 |  |  | 1613 |  |  | 1443 |  |  | 1552 |  |  | 1638 |  |  | 1795.5 |  |  | 1586 |  |  | 1510.5 |  |  | 1554 |  |  | 1590 |  |  | 1729.5 |  |  | 1614 |  |  | 1480 |  |  | 1508.5 |  |  | 1593 |  |  | 1523 |  |  | 1586 |  |  | 1678.5 |  |  | 1534.5 |  |  | 1614 |  |  | 1527 |  |  | 1601.5 |  |  | 1609.5 |  |  | 1514 |  |  | 1626 |  |  | 1621.5 |  |  | 1681.5 |  |  | 1451.5 |  |  | 1589.5 |  |  | 1519.5 |  |  | 1734 |  |  | 1554.5 |  |  | 1557 |  |  | 1538 |  |  | 1622 |  |  | 1621 |  |  | 1577.5 |  |  | 1576 |  |  | 1500 |  |  | 1566.5 |  |  | 1540.5 |  |  | 1510 |  |  | 1595.5 |  |  | 1579.5 |  |  | 1642 |  |  | 1526 |  |  | 1532 |  |  | 1610.5 |  |  | 1564 |  |  | 1597.5 |  |  | 1610 |  |  | 1581 |  |  | 1724.5 |  |  | 1549 |  |  | 1731 |  |  | 1524 |  |  | 1590 |  |  | 1605 |  |  | 1563 |  |  | 1559 |  |  | 1541 |  |  | 1474.5 |  |  | 1612.5 |  |  | 1572 |  |  | 1590.5 |  |  | 1439.5 |  |  | 1494 |  |  | 1464 |  |  | 1621 |  |  | 1648.5 |  |  | 1511.5 |  |  | 1543 |  |  | 1676 |  |  | 1467 |  |  | 1450 |  |  | 1546 |  |  | 1548 |  |  | 1696 |  |  | 1539.5 |  |  | 1626 |  |  | 1610 |  |  | 1670 |  |  | 1526 |  |  | 1412 |  |  | 1554.5 |  |  | 1741.5 |  |  | 1434.5 |  |  | 1478 |  |  | 1511 |  |  | 1472.5 |  |  | 1650.5 |  |  | 1617.5 |  |  | 1555 |  |  | 1625.5 |  |  | 1586.5 |  |  | 1626 |  |  | 1526.5 |  |  | 1610.5 |  |  | 1566 |  |  | 1510 |  |  | 1568 |  |  | 1605 |  |  | 1527 |  |  | 1478 |  |  | 1557 |  |  | 1678 |  |  | 1525 |  |  | 1481 |  |  | 1657.5 |  |  | 1531 |  |  | 1605 |  |  | 1461 |  |  | 1508.5 |  |  | 1578 |  |  | 1609.5 |  |  | 1660 |  |  | 1569 |  |  | 1548 |  |  | 1570 |  |  | 1640.5 |  |  | 1517 |  |  | 1446 |  |  | 1652.5 |  |  | 1601 |  |  | 1514 |  |  | 1539.5 |  |  | 1571.5 |  |  | 1614 |  |  | 1503.5 |  |  | 1639 |  |  | 1551.5 |  |  | 1664 |  |  | 1638 |  |  | 1566.5 |  |  | 1662.5 |  |  | 1551 |  |  | 1634 |  |  | 1566 |  |  | 1614 |  |  | 1461 |  |  | 1600 |  |  | 1417 |  |  | 1466 |  |  | 1730.5 |  |  | 1413 |  |  | 1649.5 |  |  | 1502 |  |  | 1598.5 |  |  | 1504.5 |  |  | 1520 |  |  | 1576 |  |  | 1606.5 |  |  | 1636 |  |  | 1602 |  |  | 1601 |  |  | 1546.5 |  |  | 1630 |  |  | 1473.5 |  |  | 1422 |  |  | 1512 |  |  | 1571 |  |  | 1631 |  |  | 1714.5 |  |  | 1521 |  |  | 1499 |  |  | 1570 |  |  | 1513.5 |  |  | 1679 |  |  | 1581 |  |  | 1558 |  |  | 1545 |  |  | 1543.5 |  |  | 1511.5 |  |  | 1582 |  |  | 1627 |  |  | 1572 |  |  | 1601.5 |  |  | 1584 |  |  | 1535 |  |  | 1511 |  |  | 1687.5 |  |  | 1552.5 |  |  | 1591.5 |  |  | 1568 |  |  | 1638 |  |  | 1550 |  |  | 1483.5 |  |  | 1591 |  |  | 1568.5 |  |  | 1444 |  |  | 1516 |  |  | 1552 |  |  | 1557.5 |  |  | 1597.5 |  |  | 1605 |  |  | 1512 |  |  | 1657.5 |  |  | 1535 |  |  | 1545 |  |  | 1646.5 |  |  | 1532 |  |  | 1530 |  |  | 1583.5 |  |  | 1515 |  |  | 1577 |  |  | 1558.5 |  |  | 1649 |  |  | 1505.5 |  |  | 1594 |  |  | 1480.5 |  |  | 1601.5 |  |  | 1471 |  |  | 1635 |  |  | 1612.5 |  |  | 1600.5 |  |  | 1678 |  |  | 1562 |  |  | 1657 |  |  | 1546.5 |  |  | 1614 |  |  | 1401 |  |  | 1552 |  |  | 1673.5 |  |  | 1584.5 |  |  | 1601 |  |  | 1601 |  |  | 1503 |  |  | 1438 |  |  | 1671 |  |  | 1553 |  |  | 1507 |  |  | 1543.5 |  |  | 1631.5 |  |  | 1479.5 |  |  | 1594 |  |  | 1520.5 |  |  | 1613 |  |  | 1506 |  |  | 1576.5 |  |  | 1482.5 |  |  | 1381 |  |  | 1582 |  |  | 1544.5 |  |  | 1546 |  |  | 1601 |  |  | 1500.5 |  |  | 1548.5 |  |  | 1557 |  |  | 1548 |  |  | 1639 |  |  | 1477.5 |  |  | 1522 |  |  | 1436 |  |  | 1590 |  |  | 1594 |  |  | 1636 |  |  | 1519.5 |  |  | 1683 |  |  | 1503 |  |  | 1378 |  |  | 1697.5 |  |  | 1574 |  |  | 1524.5 |  |  | 1445.5 |  |  | 1552 |  |  | 1592 |  |  | 1569.5 |  |  | 1499.5 |  |  | 1514.5 |  |  | 1575.5 |  |  | 1608.5 |  |  | 1552 |  |  | 1518 |  |  | 1582.5 |  |  | 1551.5 |  |  | 1579 |  |  | 1531 |  |  | 1541.5 |  |  | 1630 |  |  | 1547 |  |  | 1455 |  |  | 1577.5 |  |  | 1664 |  |  | 1474.5 |  |  | 1444 |  |  | 1563.5 |  |  | 1648.5 |  |  | 1698.5 |  |  | 1618 |  |  | 1503 |  |  | 1580.5 |  |  | 1493.5 |  |  | 1582 |  |  | 1591 |  |  | 1556.5 |  |  | 1601 |  |  | 1576.5 |  |  | 1562.5 |  |  | 1590 |  |  | 1564 |  |  | 1490.5 |  |  | 1670.5 |  |  | 1530 |  |  | 1530.5 |  |  | 1535.5 |  |  | 1570 |  |  | 1635 |  |  | 1666 |  |  | 1593.5 |  |  | 1618 |  |  | 1535 |  |  | 1585 |  |  | 1539 |  |  | 1582 |  |  | 1551 |  |  | 1638.5 |  |  | 1524.5 |  |  | 1563 |  |  | 1481 |  |  | 1576 |  |  | 1565.5 |  |  | 1570 |  |  | 1655 |  |  | 1485.5 |  |  | 1571.5 |  |  | 1554 |  |  | 1502.5 |  |  | 1597 |  |  | 1433 |  |  | 1575 |  |  | 1680.5 |  |  | 1685 |  |  | 1469.5 |  |  | 1542.5 |  |  | 1483 |  |  | 1613.5 |  |  | 1473.5 |  |  | 1502 |  |  | 1467 |  |  | 1694 |  |  | 1467.5 |  |  | 1456 |  |  | 1509.5 |  |  | 1516.5 |  |  | 1596 |  |  | 1495.5 |  |  | 1499 |  |  | 1566 |  |  | 1549 |  |  | 1520 |  |  | 1456 |  |  | 1649.5 |  |  | 1610 |  |  | 1650 |  |  | 1478 |  |  | 1617 |  |  | 1525.5 |  |  | 1628.5 |  |  | 1526 |  |  | 1566 |  |  | 1561 |  |  | 1491 |  |  | 1610 |  |  | 1559.5 |  |  | 1583 |  |  | 1560.5 |  |  | 1680 |  |  | 1449 |  |  | 1557 |  |  | 1517 |  |  | 1537.5 |  |  | 1529 |  |  | 1537.5 |  |  | 1484 |  |  | 1682 |  |  | 1637 |  |  | 1513.5 |  |  | 1495 |  |  | 1466 |  |  | 1450 |  |  | 1673 |  |  | 1654 |  |  | 1545.5 |  |  | 1622.5 |  |  | 1522 |  |  | 1511.5 |  |  | 1474 |  |  | 1445.5 |  |  | 1571.5 |  |  | 1484.5 |  |  | 1619.5 |  |  | 1465 |  |  | 1618 |  |  | 1516 |  |  | 1517 |  |  | 1572 |  |  | 1521 |  |  | 1511.5 |  |  | 1512.5 |  |  | 1603.5 |  |  | 1638 |  |  | 1596.5 |  |  | 1556.5 |  |  | 1615.5 |  |  | 1534.5 |  |  | 1521 |  |  | 1537.5 |  |  | 1567.5 |  |  | 1607 |  |  | 1513.5 |  |  | 1599.5 |  |  | 1610.5 |  |  | 1634 |  |  | 1557.5 |  |  | 1588 |  |  | 1602 |  |  | 1584.5 |  |  | 1603.5 |  |  | 1613 |  |  | 1546 |  |  | 1457.5 |  |  | 1473.5 |  |  | 1572.5 |  |  | 1600 |  |  | 1532 |  |  | 1515 |  |  | 1575.5 |  |  | 1627.5 |  |  | 1633 |  |  | 1599.5 |  |  | 1477 |  |  | 1534 |  |  | 1602.5 |  |  | 1507.5 |  |  | 1515 |  |  | 1578.5 |  |  | 1522 |  |  | 1445.5 |  |  | 1685.5 |  |  | 1604 |  |  | 1508.5 |  |  | 1597 |  |  | 1559.5 |  |  | 1570 |  |  | 1614 |  |  | 1627 |  |  | 1482.5 |  |  | 1463.5 |  |  | 1602 |  |  | 1466 |  |  | 1547 |  |  | 1547.5 |  |  | 1560.5 |  |  | 1593 |  |  | 1549.5 |  |  | 1513 |  |  | 1479.5 |  |  | 1571.5 |  |  | 1516 |  |  | 1511 |  |  | 1540 |  |  | 1541.5 |  |  | 1556 |  |  | 1634.5 |  |  | 1583 |  |  | 1567.5 |  |  | 1757 |  |  | 1386.5 |  |  | 1535 |  |  | 1509.5 |  |  | 1551.5 |  |  | 1505 |  |  | 1525 |  |  | 1646 |  |  | 1582 |  |  | 1628.5 |  |  | 1461 |  |  | 1532.5 |  |  | 1455 |  |  | 1512 |  |  | 1518 |  |  | 1616 |  |  | 1606 |  |  | 1564 |  |  | 1556 |  |  | 1631.5 |  |  | 1486 |  |  | 1618
56 |  | 1673.5 |  |  | 1668 |  |  | 1605.5 |  |  | 1565 |  |  | 1587.5 |  |  | 1630 |  |  | 1588 |  |  | 1657 |  |  | 1534.5 |  |  | 1575 |  |  | 1580 |  |  | 1705 |  |  | 1612 |  |  | 1697 |  |  | 1509.5 |  |  | 1655.5 |  |  | 1545 |  |  | 1689 |  |  | 1734 |  |  | 1533.5 |  |  | 1609 |  |  | 1649 |  |  | 1514 |  |  | 1623 |  |  | 1591.5 |  |  | 1741 |  |  | 1607 |  |  | 1527 |  |  | 1638 |  |  | 1538 |  |  | 1574 |  |  | 1600.5 |  |  | 1682.5 |  |  | 1577.5 |  |  | 1476 |  |  | 1535.5 |  |  | 1555.5 |  |  | 1613.5 |  |  | 1618 |  |  | 1607 |  |  | 1501.5 |  |  | 1495 |  |  | 1640.5 |  |  | 1585.5 |  |  | 1658.5 |  |  | 1704.5 |  |  | 1729.5 |  |  | 1590 |  |  | 1467 |  |  | 1497.5 |  |  | 1559 |  |  | 1529.5 |  |  | 1533.5 |  |  | 1633 |  |  | 1555 |  |  | 1561 |  |  | 1519 |  |  | 1684 |  |  | 1645 |  |  | 1577.5 |  |  | 1664.5 |  |  | 1632.5 |  |  | 1471 |  |  | 1638 |  |  | 1484 |  |  | 1535.5 |  |  | 1582 |  |  | 1599.5 |  |  | 1618.5 |  |  | 1694.5 |  |  | 1554 |  |  | 1611 |  |  | 1618 |  |  | 1605.5 |  |  | 1632.5 |  |  | 1563.5 |  |  | 1655.5 |  |  | 1612.5 |  |  | 1633.5 |  |  | 1598.5 |  |  | 1553.5 |  |  | 1519 |  |  | 1584 |  |  | 1576 |  |  | 1667.5 |  |  | 1663 |  |  | 1483.5 |  |  | 1585 |  |  | 1640 |  |  | 1652.5 |  |  | 1675.5 |  |  | 1567 |  |  | 1814 |  |  | 1549.5 |  |  | 1656 |  |  | 1552.5 |  |  | 1612.5 |  |  | 1569.5 |  |  | 1533.5 |  |  | 1503.5 |  |  | 1645 |  |  | 1593 |  |  | 1495 |  |  | 1632.5 |  |  | 1588.5 |  |  | 1622.5 |  |  | 1571.5 |  |  | 1580 |  |  | 1593 |  |  | 1611.5 |  |  | 1480 |  |  | 1606.5 |  |  | 1620 |  |  | 1588 |  |  | 1523.5 |  |  | 1552 |  |  | 1575 |  |  | 1555 |  |  | 1608 |  |  | 1659.5 |  |  | 1574.5 |  |  | 1566.5 |  |  | 1726 |  |  | 1533 |  |  | 1496 |  |  | 1539 |  |  | 1552.5 |  |  | 1578 |  |  | 1602.5 |  |  | 1648 |  |  | 1497 |  |  | 1635.5 |  |  | 1537.5 |  |  | 1472 |  |  | 1524.5 |  |  | 1554 |  |  | 1603 |  |  | 1602 |  |  | 1613 |  |  | 1549 |  |  | 1496 |  |  | 1552 |  |  | 1606 |  |  | 1496 |  |  | 1482.5 |  |  | 1542 |  |  | 1465 |  |  | 1605 |  |  | 1587 |  |  | 1543 |  |  | 1515 |  |  | 1574 |  |  | 1645.5 |  |  | 1608 |  |  | 1555.5 |  |  | 1652 |  |  | 1533 |  |  | 1642.5 |  |  | 1574 |  |  | 1721.5 |  |  | 1607 |  |  | 1477 |  |  | 1597.5 |  |  | 1615 |  |  | 1639.5 |  |  | 1561 |  |  | 1534 |  |  | 1594.5 |  |  | 1607.5 |  |  | 1634 |  |  | 1539.5 |  |  | 1617.5 |  |  | 1601 |  |  | 1617 |  |  | 1779.5 |  |  | 1528.5 |  |  | 1570.5 |  |  | 1639 |  |  | 1652 |  |  | 1547 |  |  | 1674 |  |  | 1659 |  |  | 1620.5 |  |  | 1578 |  |  | 1473.5 |  |  | 1611.5 |  |  | 1622 |  |  | 1693 |  |  | 1740.5 |  |  | 1480.5 |  |  | 1532 |  |  | 1640.5 |  |  | 1515.5 |  |  | 1613 |  |  | 1487 |  |  | 1554 |  |  | 1531.5 |  |  | 1711 |  |  | 1568.5 |  |  | 1544.5 |  |  | 1508 |  |  | 1580.5 |  |  | 1519 |  |  | 1619 |  |  | 1582 |  |  | 1596 |  |  | 1471 |  |  | 1668 |  |  | 1665 |  |  | 1665 |  |  | 1683 |  |  | 1564 |  |  | 1592.5 |  |  | 1692.5 |  |  | 1577 |  |  | 1501 |  |  | 1697 |  |  | 1617.5 |  |  | 1643.5 |  |  | 1599.5 |  |  | 1587 |  |  | 1610 |  |  | 1675.5 |  |  | 1589.5 |  |  | 1483.5 |  |  | 1661 |  |  | 1681 |  |  | 1575 |  |  | 1570 |  |  | 1600 |  |  | 1559.5 |  |  | 1576.5 |  |  | 1667 |  |  | 1596 |  |  | 1538 |  |  | 1699 |  |  | 1565 |  |  | 1565.5 |  |  | 1584 |  |  | 1623 |  |  | 1564 |  |  | 1601 |  |  | 1570.5 |  |  | 1710 |  |  | 1632 |  |  | 1571 |  |  | 1678 |  |  | 1660.5 |  |  | 1693 |  |  | 1522 |  |  | 1508 |  |  | 1631.5 |  |  | 1596.5 |  |  | 1665.5 |  |  | 1680 |  |  | 1575 |  |  | 1493 |  |  | 1716 |  |  | 1600 |  |  | 1542.5 |  |  | 1663 |  |  | 1519.5 |  |  | 1621.5 |  |  | 1645.5 |  |  | 1639 |  |  | 1719.5 |  |  | 1582 |  |  | 1508 |  |  | 1550.5 |  |  | 1601.5 |  |  | 1640 |  |  | 1701.5 |  |  | 1670.5 |  |  | 1609 |  |  | 1679 |  |  | 1596.5 |  |  | 1510.5 |  |  | 1686 |  |  | 1638.5 |  |  | 1605 |  |  | 1552 |  |  | 1571.5 |  |  | 1655 |  |  | 1544 |  |  | 1625.5 |  |  | 1549 |  |  | 1684.5 |  |  | 1580 |  |  | 1735 |  |  | 1591 |  |  | 1507 |  |  | 1682.5 |  |  | 1750 |  |  | 1668.5 |  |  | 1553.5 |  |  | 1639.5 |  |  | 1694 |  |  | 1701.5 |  |  | 1735 |  |  | 1616 |  |  | 1480.5 |  |  | 1574.5 |  |  | 1606 |  |  | 1584.5 |  |  | 1645 |  |  | 1568 |  |  | 1717.5 |  |  | 1578 |  |  | 1575.5 |  |  | 1626.5 |  |  | 1625.5 |  |  | 1580 |  |  | 1525 |  |  | 1582 |  |  | 1493.5 |  |  | 1567 |  |  | 1707.5 |  |  | 1585 |  |  | 1580 |  |  | 1539 |  |  | 1575 |  |  | 1669 |  |  | 1612 |  |  | 1558 |  |  | 1740 |  |  | 1593 |  |  | 1572.5 |  |  | 1601 |  |  | 1570 |  |  | 1740.5 |  |  | 1499.5 |  |  | 1593.5 |  |  | 1640.5 |  |  | 1553 |  |  | 1700 |  |  | 1484.5 |  |  | 1660.5 |  |  | 1606.5 |  |  | 1611 |  |  | 1580 |  |  | 1568 |  |  | 1589 |  |  | 1494 |  |  | 1590 |  |  | 1603 |  |  | 1578.5 |  |  | 1590.5 |  |  | 1568 |  |  | 1560.5 |  |  | 1603.5 |  |  | 1490 |  |  | 1644 |  |  | 1534 |  |  | 1549 |  |  | 1527.5 |  |  | 1497.5 |  |  | 1599.5 |  |  | 1579 |  |  | 1566.5 |  |  | 1610 |  |  | 1564 |  |  | 1649 |  |  | 1456.5 |  |  | 1592 |  |  | 1486 |  |  | 1614.5 |  |  | 1553 |  |  | 1627.5 |  |  | 1748 |  |  | 1522.5 |  |  | 1522 |  |  | 1584.5 |  |  | 1617.5 |  |  | 1632 |  |  | 1621 |  |  | 1463 |  |  | 1575 |  |  | 1490.5 |  |  | 1549 |  |  | 1653 |  |  | 1555.5 |  |  | 1679.5 |  |  | 1530.5 |  |  | 1532 |  |  | 1604.5 |  |  | 1582.5 |  |  | 1545.5 |  |  | 1653 |  |  | 1564 |  |  | 1566.5 |  |  | 1644 |  |  | 1687 |  |  | 1575.5 |  |  | 1527 |  |  | 1677 |  |  | 1580 |  |  | 1532 |  |  | 1465.5 |  |  | 1681.5 |  |  | 1522 |  |  | 1629 |  |  | 1601 |  |  | 1578 |  |  | 1542 |  |  | 1497.5 |  |  | 1593.5 |  |  | 1616 |  |  | 1719 |  |  | 1698 |  |  | 1482.5 |  |  | 1746.5 |  |  | 1531 |  |  | 1584 |  |  | 1505 |  |  | 1592.5 |  |  | 1712.5 |  |  | 1611 |  |  | 1518 |  |  | 1639 |  |  | 1596 |  |  | 1580 |  |  | 1692 |  |  | 1537 |  |  | 1697.5 |  |  | 1505 |  |  | 1721 |  |  | 1591 |  |  | 1626.5 |  |  | 1680 |  |  | 1479 |  |  | 1425 |  |  | 1588 |  |  | 1632 |  |  | 1582 |  |  | 1583 |  |  | 1562.5 |  |  | 1577.5 |  |  | 1502.5 |  |  | 1637 |  |  | 1571 |  |  | 1626.5 |  |  | 1466 |  |  | 1504.5 |  |  | 1585.5 |  |  | 1564 |  |  | 1597 |  |  | 1621.5 |  |  | 1530 |  |  | 1642 |  |  | 1630 |  |  | 1631 |  |  | 1572 |  |  | 1536 |  |  | 1525 |  |  | 1696.5 |  |  | 1594 |  |  | 1615 |  |  | 1683 |  |  | 1533 |  |  | 1650 |  |  | 1531 |  |  | 1733 |  |  | 1637 |  |  | 1619 |  |  | 1716.5 |  |  | 1610.5 |  |  | 1564.5 |  |  | 1606.5 |  |  | 1608 |  |  | 1505 |  |  | 1702.5 |  |  | 1577 |  |  | 1583 |  |  | 1578.5 |  |  | 1642.5 |  |  | 1611 |  |  | 1569.5 |  |  | 1530.5 |  |  | 1527 |  |  | 1675 |  |  | 1563 |  |  | 1580 |  |  | 1624.5 |  |  | 1550 |  |  | 1539.5 |  |  | 1471.5 |  |  | 1508 |  |  | 1535 |  |  | 1603.5 |  |  | 1508 |  |  | 1589.5 |  |  | 1588 |  |  | 1613.5 |  |  | 1488.5 |  |  | 1532.5 |  |  | 1622.5 |  |  | 1616.5 |  |  | 1483 |  |  | 1447 |  |  | 1679.5 |  |  | 1638 |  |  | 1542 |  |  | 1570 |  |  | 1691 |  |  | 1731.5 |  |  | 1423 |  |  | 1553 |  |  | 1613 |  |  | 1624.5 |  |  | 1606 |  |  | 1513 |  |  | 1563 |  |  | 1745.5 |  |  | 1639 |  |  | 1467 |  |  | 1578 |  |  | 1677 |  |  | 1810.5 |  |  | 1612 |  |  | 1539.5 |  |  | 1569 |  |  | 1637 |  |  | 1768.5 |  |  | 1629 |  |  | 1519 |  |  | 1534.5 |  |  | 1614 |  |  | 1538 |  |  | 1612 |  |  | 1717.5 |  |  | 1549.5 |  |  | 1629 |  |  | 1548 |  |  | 1630.5 |  |  | 1648.5 |  |  | 1538 |  |  | 1652 |  |  | 1642.5 |  |  | 1707.5 |  |  | 1490.5 |  |  | 1610.5 |  |  | 1543.5 |  |  | 1773 |  |  | 1593.5 |  |  | 1604 |  |  | 1562 |  |  | 1661 |  |  | 1650 |  |  | 1603.5 |  |  | 1597 |  |  | 1539 |  |  | 1605.5 |  |  | 1587.5 |  |  | 1534 |  |  | 1619.5 |  |  | 1603.5 |  |  | 1671 |  |  | 1547 |  |  | 1556 |  |  | 1636.5 |  |  | 1585 |  |  | 1618.5 |  |  | 1625 |  |  | 1596 |  |  | 1739.5 |  |  | 1570 |  |  | 1757 |  |  | 1545 |  |  | 1637 |  |  | 1652 |  |  | 1602 |  |  | 1580 |  |  | 1567 |  |  | 1495.5 |  |  | 1633.5 |  |  | 1598 |  |  | 1637.5 |  |  | 1468.5 |  |  | 1515 |  |  | 1488 |  |  | 1660 |  |  | 1677.5 |  |  | 1550.5 |  |  | 1569 |  |  | 1715 |  |  | 1506 |  |  | 1474 |  |  | 1570 |  |  | 1577 |  |  | 1720 |  |  | 1568.5 |  |  | 1673 |  |  | 1625 |  |  | 1709 |  |  | 1565 |  |  | 1438 |  |  | 1593.5 |  |  | 1762.5 |  |  | 1458.5 |  |  | 1517 |  |  | 1550 |  |  | 1511.5 |  |  | 1689.5 |  |  | 1656.5 |  |  | 1581 |  |  | 1664.5 |  |  | 1601.5 |  |  | 1665 |  |  | 1573.5 |  |  | 1634.5 |  |  | 1587 |  |  | 1549 |  |  | 1583 |  |  | 1652 |  |  | 1553 |  |  | 1493 |  |  | 1578 |  |  | 1693 |  |  | 1540 |  |  | 1505 |  |  | 1683.5 |  |  | 1578 |  |  | 1644 |  |  | 1500 |  |  | 1532.5 |  |  | 1602 |  |  | 1624.5 |  |  | 1684 |  |  | 1608 |  |  | 1577 |  |  | 1609 |  |  | 1661.5 |  |  | 1538 |  |  | 1493 |  |  | 1673.5 |  |  | 1630 |  |  | 1535 |  |  | 1563.5 |  |  | 1592.5 |  |  | 1635 |  |  | 1542.5 |  |  | 1654 |  |  | 1572.5 |  |  | 1703 |  |  | 1653 |  |  | 1592.5 |  |  | 1701.5 |  |  | 1575 |  |  | 1660 |  |  | 1595 |  |  | 1638 |  |  | 1487 |  |  | 1615 |  |  | 1456 |  |  | 1492 |  |  | 1751.5 |  |  | 1428 |  |  | 1678.5 |  |  | 1549 |  |  | 1645.5 |  |  | 1543.5 |  |  | 1535 |  |  | 1623 |  |  | 1645.5 |  |  | 1657 |  |  | 1623 |  |  | 1640 |  |  | 1561.5 |  |  | 1645 |  |  | 1499.5 |  |  | 1437 |  |  | 1551 |  |  | 1586 |  |  | 1678 |  |  | 1729.5 |  |  | 1542 |  |  | 1528 |  |  | 1585 |  |  | 1528.5 |  |  | 1694 |  |  | 1602 |  |  | 1605 |  |  | 1574 |  |  | 1582.5 |  |  | 1526.5 |  |  | 1629 |  |  | 1656 |  |  | 1611 |  |  | 1627.5 |  |  | 1599 |  |  | 1574 |  |  | 1558 |  |  | 1711.5 |  |  | 1591.5 |  |  | 1612.5 |  |  | 1597 |  |  | 1662 |  |  | 1597 |  |  | 1530.5 |  |  | 1617 |  |  | 1594.5 |  |  | 1468 |  |  | 1555 |  |  | 1573 |  |  | 1581.5 |  |  | 1644.5 |  |  | 1652 |  |  | 1536 |  |  | 1678.5 |  |  | 1561 |  |  | 1574 |  |  | 1667.5 |  |  | 1579 |  |  | 1556 |  |  | 1598.5 |  |  | 1562 |  |  | 1592 |  |  | 1573.5 |  |  | 1696 |  |  | 1529.5 |  |  | 1633 |  |  | 1509.5 |  |  | 1640.5 |  |  | 1486 |  |  | 1674 |  |  | 1651.5 |  |  | 1615.5 |  |  | 1707 |  |  | 1601 |  |  | 1672 |  |  | 1575.5 |  |  | 1638 |  |  | 1427 |  |  | 1599 |  |  | 1697.5 |  |  | 1623.5 |  |  | 1622 |  |  | 1640 |  |  | 1550 |  |  | 1485 |  |  | 1686 |  |  | 1574 |  |  | 1528 |  |  | 1572.5 |  |  | 1678.5 |  |  | 1526.5 |  |  | 1615 |  |  | 1544.5 |  |  | 1637 |  |  | 1530 |  |  | 1615.5 |  |  | 1497.5 |  |  | 1428 |  |  | 1611 |  |  | 1583.5 |  |  | 1593 |  |  | 1625 |  |  | 1524.5 |  |  | 1595.5 |  |  | 1604 |  |  | 1577 |  |  | 1668 |  |  | 1498.5 |  |  | 1537 |  |  | 1462 |  |  | 1614 |  |  | 1633 |  |  | 1665 |  |  | 1543.5 |  |  | 1722 |  |  | 1542 |  |  | 1417 |  |  | 1723.5 |  |  | 1621 |  |  | 1563.5 |  |  | 1492.5 |  |  | 1567 |  |  | 1631 |  |  | 1593.5 |  |  | 1538.5 |  |  | 1529.5 |  |  | 1622.5 |  |  | 1623.5 |  |  | 1591 |  |  | 1542 |  |  | 1603.5 |  |  | 1590.5 |  |  | 1603 |  |  | 1570 |  |  | 1556.5 |  |  | 1656 |  |  | 1562 |  |  | 1479 |  |  | 1616.5 |  |  | 1703 |  |  | 1513.5 |  |  | 1465 |  |  | 1610.5 |  |  | 1695.5 |  |  | 1713.5 |  |  | 1642 |  |  | 1550 |  |  | 1601.5 |  |  | 1532.5 |  |  | 1621 |  |  | 1620 |  |  | 1595.5 |  |  | 1622 |  |  | 1615.5 |  |  | 1583.5 |  |  | 1629 |  |  | 1603 |  |  | 1529.5 |  |  | 1691.5 |  |  | 1577 |  |  | 1556.5 |  |  | 1556.5 |  |  | 1596 |  |  | 1650 |  |  | 1687 |  |  | 1608.5 |  |  | 1642 |  |  | 1559 |  |  | 1614 |  |  | 1578 |  |  | 1611 |  |  | 1575 |  |  | 1667.5 |  |  | 1550.5 |  |  | 1589 |  |  | 1528 |  |  | 1591 |  |  | 1604.5 |  |  | 1609 |  |  | 1702 |  |  | 1514.5 |  |  | 1586.5 |  |  | 1578 |  |  | 1526.5 |  |  | 1636 |  |  | 1459 |  |  | 1614 |  |  | 1719.5 |  |  | 1724 |  |  | 1508.5 |  |  | 1568.5 |  |  | 1507 |  |  | 1639.5 |  |  | 1488.5 |  |  | 1517 |  |  | 1482 |  |  | 1733 |  |  | 1493.5 |  |  | 1482 |  |  | 1535.5 |  |  | 1545.5 |  |  | 1625 |  |  | 1510.5 |  |  | 1546 |  |  | 1605 |  |  | 1564 |  |  | 1535 |  |  | 1482 |  |  | 1673.5 |  |  | 1625 |  |  | 1676 |  |  | 1499 |  |  | 1656 |  |  | 1554.5 |  |  | 1649.5 |  |  | 1565 |  |  | 1587 |  |  | 1590 |  |  | 1530 |  |  | 1631 |  |  | 1588.5 |  |  | 1604 |  |  | 1607.5 |  |  | 1719 |  |  | 1478 |  |  | 1572 |  |  | 1538 |  |  | 1576.5 |  |  | 1568 |  |  | 1561.5 |  |  | 1523 |  |  | 1697 |  |  | 1661 |  |  | 1560.5 |  |  | 1510 |  |  | 1490 |  |  | 1489 |  |  | 1702 |  |  | 1693 |  |  | 1584.5 |  |  | 1637.5 |  |  | 1569 |  |  | 1540.5 |  |  | 1500 |  |  | 1474.5 |  |  | 1586.5 |  |  | 1505.5 |  |  | 1640.5 |  |  | 1504 |  |  | 1647 |  |  | 1531 |  |  | 1564 |  |  | 1611 |  |  | 1568 |  |  | 1526.5 |  |  | 1527.5 |  |  | 1624.5 |  |  | 1662 |  |  | 1622.5 |  |  | 1595.5 |  |  | 1654.5 |  |  | 1581.5 |  |  | 1568 |  |  | 1566.5 |  |  | 1588.5 |  |  | 1622 |  |  | 1552.5 |  |  | 1646.5 |  |  | 1634.5 |  |  | 1673 |  |  | 1604.5 |  |  | 1614 |  |  | 1628 |  |  | 1599.5 |  |  | 1642.5 |  |  | 1652 |  |  | 1593 |  |  | 1504.5 |  |  | 1512.5 |  |  | 1587.5 |  |  | 1647 |  |  | 1558 |  |  | 1536 |  |  | 1622.5 |  |  | 1648.5 |  |  | 1680 |  |  | 1638.5 |  |  | 1516 |  |  | 1563 |  |  | 1641.5 |  |  | 1546.5 |  |  | 1544 |  |  | 1593.5 |  |  | 1569 |  |  | 1466.5 |  |  | 1732.5 |  |  | 1633 |  |  | 1523.5 |  |  | 1636 |  |  | 1606.5 |  |  | 1596 |  |  | 1653 |  |  | 1651 |  |  | 1529.5 |  |  | 1489.5 |  |  | 1626 |  |  | 1505 |  |  | 1562 |  |  | 1571.5 |  |  | 1599.5 |  |  | 1622 |  |  | 1570.5 |  |  | 1560 |  |  | 1494.5 |  |  | 1592.5 |  |  | 1555 |  |  | 1532 |  |  | 1566 |  |  | 1570.5 |  |  | 1580 |  |  | 1655.5 |  |  | 1622 |  |  | 1596.5 |  |  | 1781 |  |  | 1412.5 |  |  | 1574 |  |  | 1530.5 |  |  | 1566.5 |  |  | 1520 |  |  | 1564 |  |  | 1693 |  |  | 1621 |  |  | 1667.5 |  |  | 1482 |  |  | 1558.5 |  |  | 1494 |  |  | 1527 |  |  | 1557 |  |  | 1655 |  |  | 1621 |  |  | 1579 |  |  | 1595 |  |  | 1646.5 |  |  | 1512 |  |  | 1665
57 |  | 1720.5 |  |  | 1707 |  |  | 1644.5 |  |  | 1580 |  |  | 1613.5 |  |  | 1645 |  |  | 1603 |  |  | 1686 |  |  | 1558.5 |  |  | 1601 |  |  | 1604 |  |  | 1726 |  |  | 1651 |  |  | 1736 |  |  | 1556.5 |  |  | 1702.5 |  |  | 1566 |  |  | 1710 |  |  | 1749 |  |  | 1559.5 |  |  | 1635 |  |  | 1673 |  |  | 1535 |  |  | 1644 |  |  | 1630.5 |  |  | 1762 |  |  | 1636 |  |  | 1566 |  |  | 1659 |  |  | 1562 |  |  | 1589 |  |  | 1629.5 |  |  | 1729.5 |  |  | 1598.5 |  |  | 1505 |  |  | 1561.5 |  |  | 1594.5 |  |  | 1637.5 |  |  | 1644 |  |  | 1631 |  |  | 1522.5 |  |  | 1542 |  |  | 1664.5 |  |  | 1614.5 |  |  | 1673.5 |  |  | 1743.5 |  |  | 1776.5 |  |  | 1614 |  |  | 1496 |  |  | 1526.5 |  |  | 1598 |  |  | 1544.5 |  |  | 1572.5 |  |  | 1662 |  |  | 1581 |  |  | 1585 |  |  | 1543 |  |  | 1699 |  |  | 1666 |  |  | 1616.5 |  |  | 1690.5 |  |  | 1647.5 |  |  | 1510 |  |  | 1659 |  |  | 1523 |  |  | 1550.5 |  |  | 1608 |  |  | 1623.5 |  |  | 1657.5 |  |  | 1718.5 |  |  | 1593 |  |  | 1637 |  |  | 1644 |  |  | 1634.5 |  |  | 1658.5 |  |  | 1578.5 |  |  | 1681.5 |  |  | 1627.5 |  |  | 1662.5 |  |  | 1637.5 |  |  | 1579.5 |  |  | 1543 |  |  | 1613 |  |  | 1605 |  |  | 1714.5 |  |  | 1689 |  |  | 1530.5 |  |  | 1614 |  |  | 1666 |  |  | 1691.5 |  |  | 1701.5 |  |  | 1591 |  |  | 1835 |  |  | 1578.5 |  |  | 1703 |  |  | 1591.5 |  |  | 1638.5 |  |  | 1616.5 |  |  | 1572.5 |  |  | 1524.5 |  |  | 1674 |  |  | 1617 |  |  | 1519 |  |  | 1679.5 |  |  | 1614.5 |  |  | 1669.5 |  |  | 1597.5 |  |  | 1619 |  |  | 1622 |  |  | 1640.5 |  |  | 1519 |  |  | 1635.5 |  |  | 1659 |  |  | 1614 |  |  | 1544.5 |  |  | 1591 |  |  | 1622 |  |  | 1576 |  |  | 1634 |  |  | 1680.5 |  |  | 1621.5 |  |  | 1581.5 |  |  | 1741 |  |  | 1548 |  |  | 1517 |  |  | 1563 |  |  | 1581.5 |  |  | 1617 |  |  | 1617.5 |  |  | 1669 |  |  | 1536 |  |  | 1656.5 |  |  | 1552.5 |  |  | 1519 |  |  | 1571.5 |  |  | 1601 |  |  | 1624 |  |  | 1623 |  |  | 1660 |  |  | 1575 |  |  | 1543 |  |  | 1567 |  |  | 1635 |  |  | 1535 |  |  | 1529.5 |  |  | 1557 |  |  | 1489 |  |  | 1626 |  |  | 1613 |  |  | 1582 |  |  | 1541 |  |  | 1600 |  |  | 1669.5 |  |  | 1647 |  |  | 1602.5 |  |  | 1691 |  |  | 1562 |  |  | 1681.5 |  |  | 1589 |  |  | 1760.5 |  |  | 1646 |  |  | 1498 |  |  | 1636.5 |  |  | 1654 |  |  | 1678.5 |  |  | 1608 |  |  | 1555 |  |  | 1633.5 |  |  | 1628.5 |  |  | 1660 |  |  | 1578.5 |  |  | 1664.5 |  |  | 1648 |  |  | 1632 |  |  | 1818.5 |  |  | 1557.5 |  |  | 1617.5 |  |  | 1660 |  |  | 1681 |  |  | 1586 |  |  | 1689 |  |  | 1680 |  |  | 1644.5 |  |  | 1617 |  |  | 1520.5 |  |  | 1626.5 |  |  | 1643 |  |  | 1708 |  |  | 1755.5 |  |  | 1506.5 |  |  | 1571 |  |  | 1669.5 |  |  | 1562.5 |  |  | 1628 |  |  | 1511 |  |  | 1575 |  |  | 1578.5 |  |  | 1735 |  |  | 1607.5 |  |  | 1565.5 |  |  | 1534 |  |  | 1595.5 |  |  | 1566 |  |  | 1658 |  |  | 1629 |  |  | 1635 |  |  | 1492 |  |  | 1707 |  |  | 1686 |  |  | 1680 |  |  | 1704 |  |  | 1603 |  |  | 1616.5 |  |  | 1739.5 |  |  | 1601 |  |  | 1540 |  |  | 1721 |  |  | 1641.5 |  |  | 1667.5 |  |  | 1646.5 |  |  | 1616 |  |  | 1636 |  |  | 1714.5 |  |  | 1604.5 |  |  | 1504.5 |  |  | 1708 |  |  | 1720 |  |  | 1622 |  |  | 1609 |  |  | 1639 |  |  | 1585.5 |  |  | 1597.5 |  |  | 1696 |  |  | 1622 |  |  | 1585 |  |  | 1746 |  |  | 1604 |  |  | 1612.5 |  |  | 1605 |  |  | 1652 |  |  | 1590 |  |  | 1627 |  |  | 1591.5 |  |  | 1757 |  |  | 1671 |  |  | 1586 |  |  | 1702 |  |  | 1699.5 |  |  | 1708 |  |  | 1537 |  |  | 1555 |  |  | 1657.5 |  |  | 1625.5 |  |  | 1689.5 |  |  | 1727 |  |  | 1604 |  |  | 1532 |  |  | 1763 |  |  | 1621 |  |  | 1571.5 |  |  | 1702 |  |  | 1566.5 |  |  | 1660.5 |  |  | 1674.5 |  |  | 1663 |  |  | 1734.5 |  |  | 1621 |  |  | 1547 |  |  | 1579.5 |  |  | 1640.5 |  |  | 1664 |  |  | 1716.5 |  |  | 1694.5 |  |  | 1635 |  |  | 1708 |  |  | 1620.5 |  |  | 1557.5 |  |  | 1712 |  |  | 1653.5 |  |  | 1634 |  |  | 1573 |  |  | 1586.5 |  |  | 1694 |  |  | 1573 |  |  | 1654.5 |  |  | 1588 |  |  | 1710.5 |  |  | 1619 |  |  | 1774 |  |  | 1630 |  |  | 1554 |  |  | 1721.5 |  |  | 1774 |  |  | 1697.5 |  |  | 1579.5 |  |  | 1668.5 |  |  | 1720 |  |  | 1740.5 |  |  | 1782 |  |  | 1655 |  |  | 1504.5 |  |  | 1598.5 |  |  | 1627 |  |  | 1605.5 |  |  | 1666 |  |  | 1589 |  |  | 1743.5 |  |  | 1625 |  |  | 1604.5 |  |  | 1655.5 |  |  | 1640.5 |  |  | 1595 |  |  | 1564 |  |  | 1606 |  |  | 1508.5 |  |  | 1591 |  |  | 1722.5 |  |  | 1632 |  |  | 1595 |  |  | 1568 |  |  | 1604 |  |  | 1708 |  |  | 1638 |  |  | 1582 |  |  | 1779 |  |  | 1640 |  |  | 1593.5 |  |  | 1616 |  |  | 1617 |  |  | 1755.5 |  |  | 1514.5 |  |  | 1640.5 |  |  | 1669.5 |  |  | 1582 |  |  | 1724 |  |  | 1513.5 |  |  | 1681.5 |  |  | 1621.5 |  |  | 1650 |  |  | 1627 |  |  | 1592 |  |  | 1613 |  |  | 1509 |  |  | 1611 |  |  | 1642 |  |  | 1617.5 |  |  | 1616.5 |  |  | 1607 |  |  | 1575.5 |  |  | 1618.5 |  |  | 1516 |  |  | 1659 |  |  | 1581 |  |  | 1588 |  |  | 1551.5 |  |  | 1512.5 |  |  | 1620.5 |  |  | 1600 |  |  | 1587.5 |  |  | 1631 |  |  | 1611 |  |  | 1673 |  |  | 1482.5 |  |  | 1607 |  |  | 1525 |  |  | 1643.5 |  |  | 1582 |  |  | 1674.5 |  |  | 1772 |  |  | 1561.5 |  |  | 1569 |  |  | 1605.5 |  |  | 1641.5 |  |  | 1647 |  |  | 1636 |  |  | 1478 |  |  | 1622 |  |  | 1529.5 |  |  | 1578 |  |  | 1700 |  |  | 1581.5 |  |  | 1718.5 |  |  | 1569.5 |  |  | 1556 |  |  | 1619.5 |  |  | 1606.5 |  |  | 1569.5 |  |  | 1692 |  |  | 1611 |  |  | 1595.5 |  |  | 1683 |  |  | 1734 |  |  | 1599.5 |  |  | 1566 |  |  | 1716 |  |  | 1609 |  |  | 1571 |  |  | 1480.5 |  |  | 1702.5 |  |  | 1551 |  |  | 1668 |  |  | 1640 |  |  | 1599 |  |  | 1589 |  |  | 1536.5 |  |  | 1622.5 |  |  | 1631 |  |  | 1734 |  |  | 1737 |  |  | 1521.5 |  |  | 1775.5 |  |  | 1557 |  |  | 1610 |  |  | 1544 |  |  | 1613.5 |  |  | 1759.5 |  |  | 1637 |  |  | 1533 |  |  | 1660 |  |  | 1635 |  |  | 1595 |  |  | 1713 |  |  | 1576 |  |  | 1744.5 |  |  | 1552 |  |  | 1760 |  |  | 1638 |  |  | 1652.5 |  |  | 1719 |  |  | 1526 |  |  | 1454 |  |  | 1617 |  |  | 1658 |  |  | 1603 |  |  | 1630 |  |  | 1601.5 |  |  | 1598.5 |  |  | 1531.5 |  |  | 1676 |  |  | 1600 |  |  | 1665.5 |  |  | 1487 |  |  | 1525.5 |  |  | 1624.5 |  |  | 1603 |  |  | 1644 |  |  | 1650.5 |  |  | 1569 |  |  | 1657 |  |  | 1651 |  |  | 1670 |  |  | 1619 |  |  | 1557 |  |  | 1549 |  |  | 1720.5 |  |  | 1620 |  |  | 1662 |  |  | 1698 |  |  | 1572 |  |  | 1665 |  |  | 1570 |  |  | 1772 |  |  | 1652 |  |  | 1658 |  |  | 1742.5 |  |  | 1657.5 |  |  | 1603.5 |  |  | 1645.5 |  |  | 1647 |  |  | 1534 |  |  | 1731.5 |  |  | 1606 |  |  | 1622 |  |  | 1599.5 |  |  | 1681.5 |  |  | 1658 |  |  | 1584.5 |  |  | 1556.5 |  |  | 1542 |  |  | 1696 |  |  | 1602 |  |  | 1604 |  |  | 1663.5 |  |  | 1589 |  |  | 1563.5 |  |  | 1495.5 |  |  | 1547 |  |  | 1561 |  |  | 1642.5 |  |  | 1534 |  |  | 1604.5 |  |  | 1609 |  |  | 1642.5 |  |  | 1527.5 |  |  | 1553.5 |  |  | 1646.5 |  |  | 1637.5 |  |  | 1509 |  |  | 1476 |  |  | 1718.5 |  |  | 1662 |  |  | 1566 |  |  | 1599 |  |  | 1720 |  |  | 1755.5 |  |  | 1447 |  |  | 1592 |  |  | 1639 |  |  | 1645.5 |  |  | 1621 |  |  | 1552 |  |  | 1584 |  |  | 1784.5 |  |  | 1686 |  |  | 1506 |  |  | 1602 |  |  | 1716 |  |  | 1857.5 |  |  | 1633 |  |  | 1586.5 |  |  | 1616 |  |  | 1661 |  |  | 1783.5 |  |  | 1676 |  |  | 1543 |  |  | 1581.5 |  |  | 1640 |  |  | 1562 |  |  | 1641 |  |  | 1756.5 |  |  | 1588.5 |  |  | 1658 |  |  | 1587 |  |  | 1645.5 |  |  | 1672.5 |  |  | 1577 |  |  | 1667 |  |  | 1666.5 |  |  | 1736.5 |  |  | 1516.5 |  |  | 1625.5 |  |  | 1582.5 |  |  | 1799 |  |  | 1619.5 |  |  | 1633 |  |  | 1583 |  |  | 1700 |  |  | 1676 |  |  | 1642.5 |  |  | 1636 |  |  | 1560 |  |  | 1620.5 |  |  | 1626.5 |  |  | 1573 |  |  | 1666.5 |  |  | 1629.5 |  |  | 1710 |  |  | 1568 |  |  | 1595 |  |  | 1675.5 |  |  | 1624 |  |  | 1642.5 |  |  | 1672 |  |  | 1635 |  |  | 1760.5 |  |  | 1609 |  |  | 1783 |  |  | 1571 |  |  | 1676 |  |  | 1667 |  |  | 1623 |  |  | 1609 |  |  | 1591 |  |  | 1521.5 |  |  | 1654.5 |  |  | 1627 |  |  | 1676.5 |  |  | 1489.5 |  |  | 1541 |  |  | 1535 |  |  | 1689 |  |  | 1706.5 |  |  | 1576.5 |  |  | 1616 |  |  | 1741 |  |  | 1545 |  |  | 1500 |  |  | 1596 |  |  | 1601 |  |  | 1735 |  |  | 1583.5 |  |  | 1712 |  |  | 1640 |  |  | 1730 |  |  | 1604 |  |  | 1477 |  |  | 1608.5 |  |  | 1801.5 |  |  | 1482.5 |  |  | 1556 |  |  | 1565 |  |  | 1550.5 |  |  | 1736.5 |  |  | 1677.5 |  |  | 1602 |  |  | 1703.5 |  |  | 1648.5 |  |  | 1712 |  |  | 1612.5 |  |  | 1658.5 |  |  | 1616 |  |  | 1564 |  |  | 1622 |  |  | 1691 |  |  | 1600 |  |  | 1522 |  |  | 1617 |  |  | 1732 |  |  | 1566 |  |  | 1531 |  |  | 1707.5 |  |  | 1617 |  |  | 1668 |  |  | 1547 |  |  | 1558.5 |  |  | 1641 |  |  | 1663.5 |  |  | 1723 |  |  | 1655 |  |  | 1616 |  |  | 1624 |  |  | 1700.5 |  |  | 1559 |  |  | 1532 |  |  | 1720.5 |  |  | 1669 |  |  | 1582 |  |  | 1584.5 |  |  | 1616.5 |  |  | 1664 |  |  | 1568.5 |  |  | 1680 |  |  | 1611.5 |  |  | 1742 |  |  | 1692 |  |  | 1607.5 |  |  | 1725.5 |  |  | 1614 |  |  | 1699 |  |  | 1619 |  |  | 1662 |  |  | 1513 |  |  | 1654 |  |  | 1482 |  |  | 1521 |  |  | 1790.5 |  |  | 1452 |  |  | 1717.5 |  |  | 1564 |  |  | 1666.5 |  |  | 1567.5 |  |  | 1574 |  |  | 1652 |  |  | 1684.5 |  |  | 1672 |  |  | 1649 |  |  | 1664 |  |  | 1585.5 |  |  | 1674 |  |  | 1520.5 |  |  | 1463 |  |  | 1590 |  |  | 1633 |  |  | 1702 |  |  | 1744.5 |  |  | 1581 |  |  | 1567 |  |  | 1632 |  |  | 1552.5 |  |  | 1715 |  |  | 1628 |  |  | 1620 |  |  | 1621 |  |  | 1603.5 |  |  | 1541.5 |  |  | 1676 |  |  | 1695 |  |  | 1626 |  |  | 1666.5 |  |  | 1628 |  |  | 1600 |  |  | 1597 |  |  | 1737.5 |  |  | 1630.5 |  |  | 1627.5 |  |  | 1621 |  |  | 1688 |  |  | 1626 |  |  | 1556.5 |  |  | 1643 |  |  | 1618.5 |  |  | 1492 |  |  | 1576 |  |  | 1620 |  |  | 1605.5 |  |  | 1659.5 |  |  | 1681 |  |  | 1557 |  |  | 1717.5 |  |  | 1600 |  |  | 1595 |  |  | 1714.5 |  |  | 1603 |  |  | 1577 |  |  | 1627.5 |  |  | 1588 |  |  | 1607 |  |  | 1594.5 |  |  | 1735 |  |  | 1558.5 |  |  | 1654 |  |  | 1533.5 |  |  | 1666.5 |  |  | 1510 |  |  | 1713 |  |  | 1666.5 |  |  | 1636.5 |  |  | 1736 |  |  | 1648 |  |  | 1701 |  |  | 1614.5 |  |  | 1677 |  |  | 1451 |  |  | 1623 |  |  | 1736.5 |  |  | 1662.5 |  |  | 1661 |  |  | 1655 |  |  | 1574 |  |  | 1532 |  |  | 1725 |  |  | 1603 |  |  | 1549 |  |  | 1596.5 |  |  | 1725.5 |  |  | 1550.5 |  |  | 1654 |  |  | 1559.5 |  |  | 1676 |  |  | 1554 |  |  | 1644.5 |  |  | 1544.5 |  |  | 1467 |  |  | 1658 |  |  | 1622.5 |  |  | 1632 |  |  | 1664 |  |  | 1563.5 |  |  | 1642.5 |  |  | 1625 |  |  | 1592 |  |  | 1707 |  |  | 1545.5 |  |  | 1576 |  |  | 1483 |  |  | 1629 |  |  | 1672 |  |  | 1704 |  |  | 1582.5 |  |  | 1743 |  |  | 1557 |  |  | 1443 |  |  | 1749.5 |  |  | 1642 |  |  | 1592.5 |  |  | 1518.5 |  |  | 1582 |  |  | 1678 |  |  | 1622.5 |  |  | 1564.5 |  |  | 1555.5 |  |  | 1661.5 |  |  | 1649.5 |  |  | 1630 |  |  | 1581 |  |  | 1618.5 |  |  | 1616.5 |  |  | 1642 |  |  | 1594 |  |  | 1595.5 |  |  | 1695 |  |  | 1577 |  |  | 1494 |  |  | 1655.5 |  |  | 1724 |  |  | 1534.5 |  |  | 1512 |  |  | 1636.5 |  |  | 1719.5 |  |  | 1752.5 |  |  | 1681 |  |  | 1597 |  |  | 1640.5 |  |  | 1556.5 |  |  | 1668 |  |  | 1635 |  |  | 1634.5 |  |  | 1648 |  |  | 1636.5 |  |  | 1630.5 |  |  | 1676 |  |  | 1629 |  |  | 1576.5 |  |  | 1717.5 |  |  | 1616 |  |  | 1603.5 |  |  | 1595.5 |  |  | 1635 |  |  | 1689 |  |  | 1716 |  |  | 1637.5 |  |  | 1671 |  |  | 1583 |  |  | 1661 |  |  | 1599 |  |  | 1650 |  |  | 1590 |  |  | 1714.5 |  |  | 1589.5 |  |  | 1636 |  |  | 1575 |  |  | 1638 |  |  | 1628.5 |  |  | 1624 |  |  | 1749 |  |  | 1561.5 |  |  | 1610.5 |  |  | 1607 |  |  | 1550.5 |  |  | 1657 |  |  | 1506 |  |  | 1653 |  |  | 1758.5 |  |  | 1771 |  |  | 1532.5 |  |  | 1615.5 |  |  | 1528 |  |  | 1678.5 |  |  | 1509.5 |  |  | 1564 |  |  | 1503 |  |  | 1772 |  |  | 1519.5 |  |  | 1506 |  |  | 1556.5 |  |  | 1569.5 |  |  | 1672 |  |  | 1539.5 |  |  | 1575 |  |  | 1626 |  |  | 1603 |  |  | 1556 |  |  | 1497 |  |  | 1712.5 |  |  | 1649 |  |  | 1697 |  |  | 1538 |  |  | 1680 |  |  | 1601.5 |  |  | 1696.5 |  |  | 1580 |  |  | 1608 |  |  | 1614 |  |  | 1577 |  |  | 1660 |  |  | 1617.5 |  |  | 1643 |  |  | 1633.5 |  |  | 1745 |  |  | 1502 |  |  | 1593 |  |  | 1585 |  |  | 1605.5 |  |  | 1607 |  |  | 1590.5 |  |  | 1562 |  |  | 1718 |  |  | 1682 |  |  | 1599.5 |  |  | 1525 |  |  | 1529 |  |  | 1513 |  |  | 1749 |  |  | 1732 |  |  | 1608.5 |  |  | 1652.5 |  |  | 1584 |  |  | 1566.5 |  |  | 1539 |  |  | 1513.5 |  |  | 1610.5 |  |  | 1529.5 |  |  | 1661.5 |  |  | 1533 |  |  | 1694 |  |  | 1578 |  |  | 1593 |  |  | 1650 |  |  | 1615 |  |  | 1555.5 |  |  | 1566.5 |  |  | 1650.5 |  |  | 1677 |  |  | 1637.5 |  |  | 1634.5 |  |  | 1701.5 |  |  | 1607.5 |  |  | 1592 |  |  | 1590.5 |  |  | 1635.5 |  |  | 1661 |  |  | 1591.5 |  |  | 1685.5 |  |  | 1673.5 |  |  | 1688 |  |  | 1643.5 |  |  | 1653 |  |  | 1657 |  |  | 1625.5 |  |  | 1681.5 |  |  | 1676 |  |  | 1622 |  |  | 1525.5 |  |  | 1533.5 |  |  | 1613.5 |  |  | 1686 |  |  | 1584 |  |  | 1551 |  |  | 1648.5 |  |  | 1663.5 |  |  | 1704 |  |  | 1664.5 |  |  | 1531 |  |  | 1602 |  |  | 1656.5 |  |  | 1567.5 |  |  | 1583 |  |  | 1617.5 |  |  | 1616 |  |  | 1492.5 |  |  | 1753.5 |  |  | 1662 |  |  | 1570.5 |  |  | 1683 |  |  | 1645.5 |  |  | 1620 |  |  | 1674 |  |  | 1666 |  |  | 1568.5 |  |  | 1528.5 |  |  | 1665 |  |  | 1544 |  |  | 1588 |  |  | 1595.5 |  |  | 1614.5 |  |  | 1661 |  |  | 1617.5 |  |  | 1586 |  |  | 1523.5 |  |  | 1613.5 |  |  | 1594 |  |  | 1571 |  |  | 1605 |  |  | 1585.5 |  |  | 1595 |  |  | 1676.5 |  |  | 1661 |  |  | 1617.5 |  |  | 1807 |  |  | 1438.5 |  |  | 1603 |  |  | 1556.5 |  |  | 1592.5 |  |  | 1567 |  |  | 1588 |  |  | 1732 |  |  | 1636 |  |  | 1688.5 |  |  | 1506 |  |  | 1605.5 |  |  | 1520 |  |  | 1553 |  |  | 1583 |  |  | 1684 |  |  | 1647 |  |  | 1605 |  |  | 1634 |  |  | 1672.5 |  |  | 1527 |  |  | 1694
58 |  | 1767.5 |  |  | 1736 |  |  | 1683.5 |  |  | 1627 |  |  | 1634.5 |  |  | 1660 |  |  | 1632 |  |  | 1707 |  |  | 1587.5 |  |  | 1630 |  |  | 1630 |  |  | 1773 |  |  | 1675 |  |  | 1775 |  |  | 1571.5 |  |  | 1728.5 |  |  | 1581 |  |  | 1736 |  |  | 1773 |  |  | 1580.5 |  |  | 1659 |  |  | 1712 |  |  | 1550 |  |  | 1683 |  |  | 1669.5 |  |  | 1791 |  |  | 1662 |  |  | 1613 |  |  | 1688 |  |  | 1583 |  |  | 1628 |  |  | 1653.5 |  |  | 1753.5 |  |  | 1627.5 |  |  | 1529 |  |  | 1587.5 |  |  | 1633.5 |  |  | 1676.5 |  |  | 1683 |  |  | 1657 |  |  | 1569.5 |  |  | 1566 |  |  | 1690.5 |  |  | 1629.5 |  |  | 1699.5 |  |  | 1782.5 |  |  | 1823.5 |  |  | 1640 |  |  | 1522 |  |  | 1555.5 |  |  | 1613 |  |  | 1559.5 |  |  | 1598.5 |  |  | 1683 |  |  | 1605 |  |  | 1606 |  |  | 1582 |  |  | 1738 |  |  | 1705 |  |  | 1637.5 |  |  | 1719.5 |  |  | 1662.5 |  |  | 1557 |  |  | 1688 |  |  | 1547 |  |  | 1576.5 |  |  | 1623 |  |  | 1647.5 |  |  | 1686.5 |  |  | 1757.5 |  |  | 1640 |  |  | 1684 |  |  | 1691 |  |  | 1663.5 |  |  | 1697.5 |  |  | 1625.5 |  |  | 1707.5 |  |  | 1648.5 |  |  | 1701.5 |  |  | 1661.5 |  |  | 1618.5 |  |  | 1572 |  |  | 1660 |  |  | 1644 |  |  | 1761.5 |  |  | 1736 |  |  | 1569.5 |  |  | 1661 |  |  | 1690 |  |  | 1706.5 |  |  | 1722.5 |  |  | 1638 |  |  | 1856 |  |  | 1602.5 |  |  | 1729 |  |  | 1620.5 |  |  | 1677.5 |  |  | 1655.5 |  |  | 1611.5 |  |  | 1553.5 |  |  | 1689 |  |  | 1643 |  |  | 1548 |  |  | 1700.5 |  |  | 1629.5 |  |  | 1708.5 |  |  | 1626.5 |  |  | 1658 |  |  | 1669 |  |  | 1679.5 |  |  | 1540 |  |  | 1661.5 |  |  | 1680 |  |  | 1629 |  |  | 1570.5 |  |  | 1630 |  |  | 1637 |  |  | 1597 |  |  | 1658 |  |  | 1704.5 |  |  | 1645.5 |  |  | 1607.5 |  |  | 1788 |  |  | 1587 |  |  | 1546 |  |  | 1589 |  |  | 1610.5 |  |  | 1641 |  |  | 1632.5 |  |  | 1693 |  |  | 1583 |  |  | 1695.5 |  |  | 1581.5 |  |  | 1540 |  |  | 1618.5 |  |  | 1622 |  |  | 1639 |  |  | 1638 |  |  | 1681 |  |  | 1614 |  |  | 1590 |  |  | 1591 |  |  | 1674 |  |  | 1550 |  |  | 1568.5 |  |  | 1596 |  |  | 1518 |  |  | 1665 |  |  | 1652 |  |  | 1629 |  |  | 1567 |  |  | 1629 |  |  | 1708.5 |  |  | 1676 |  |  | 1641.5 |  |  | 1717 |  |  | 1577 |  |  | 1702.5 |  |  | 1636 |  |  | 1807.5 |  |  | 1661 |  |  | 1545 |  |  | 1660.5 |  |  | 1680 |  |  | 1717.5 |  |  | 1632 |  |  | 1581 |  |  | 1659.5 |  |  | 1643.5 |  |  | 1699 |  |  | 1602.5 |  |  | 1679.5 |  |  | 1687 |  |  | 1661 |  |  | 1833.5 |  |  | 1586.5 |  |  | 1632.5 |  |  | 1699 |  |  | 1707 |  |  | 1607 |  |  | 1736 |  |  | 1704 |  |  | 1683.5 |  |  | 1638 |  |  | 1567.5 |  |  | 1652.5 |  |  | 1664 |  |  | 1732 |  |  | 1794.5 |  |  | 1535.5 |  |  | 1592 |  |  | 1695.5 |  |  | 1591.5 |  |  | 1667 |  |  | 1526 |  |  | 1614 |  |  | 1599.5 |  |  | 1774 |  |  | 1646.5 |  |  | 1604.5 |  |  | 1563 |  |  | 1610.5 |  |  | 1595 |  |  | 1684 |  |  | 1676 |  |  | 1650 |  |  | 1507 |  |  | 1733 |  |  | 1707 |  |  | 1695 |  |  | 1719 |  |  | 1642 |  |  | 1655.5 |  |  | 1765.5 |  |  | 1630 |  |  | 1555 |  |  | 1745 |  |  | 1662.5 |  |  | 1714.5 |  |  | 1685.5 |  |  | 1645 |  |  | 1651 |  |  | 1743.5 |  |  | 1643.5 |  |  | 1551.5 |  |  | 1729 |  |  | 1749 |  |  | 1661 |  |  | 1656 |  |  | 1668 |  |  | 1624.5 |  |  | 1612.5 |  |  | 1743 |  |  | 1643 |  |  | 1600 |  |  | 1785 |  |  | 1651 |  |  | 1659.5 |  |  | 1631 |  |  | 1691 |  |  | 1629 |  |  | 1653 |  |  | 1617.5 |  |  | 1796 |  |  | 1686 |  |  | 1607 |  |  | 1726 |  |  | 1714.5 |  |  | 1747 |  |  | 1566 |  |  | 1594 |  |  | 1683.5 |  |  | 1651.5 |  |  | 1736.5 |  |  | 1774 |  |  | 1630 |  |  | 1561 |  |  | 1778 |  |  | 1642 |  |  | 1592.5 |  |  | 1741 |  |  | 1613.5 |  |  | 1686.5 |  |  | 1695.5 |  |  | 1702 |  |  | 1773.5 |  |  | 1660 |  |  | 1594 |  |  | 1603.5 |  |  | 1679.5 |  |  | 1711 |  |  | 1737.5 |  |  | 1723.5 |  |  | 1674 |  |  | 1723 |  |  | 1649.5 |  |  | 1578.5 |  |  | 1751 |  |  | 1679.5 |  |  | 1673 |  |  | 1620 |  |  | 1625.5 |  |  | 1733 |  |  | 1594 |  |  | 1701.5 |  |  | 1614 |  |  | 1736.5 |  |  | 1643 |  |  | 1813 |  |  | 1659 |  |  | 1593 |  |  | 1736.5 |  |  | 1803 |  |  | 1721.5 |  |  | 1594.5 |  |  | 1692.5 |  |  | 1749 |  |  | 1764.5 |  |  | 1821 |  |  | 1684 |  |  | 1525.5 |  |  | 1637.5 |  |  | 1674 |  |  | 1634.5 |  |  | 1705 |  |  | 1628 |  |  | 1772.5 |  |  | 1646 |  |  | 1643.5 |  |  | 1694.5 |  |  | 1679.5 |  |  | 1619 |  |  | 1593 |  |  | 1627 |  |  | 1523.5 |  |  | 1620 |  |  | 1748.5 |  |  | 1679 |  |  | 1642 |  |  | 1583 |  |  | 1651 |  |  | 1723 |  |  | 1685 |  |  | 1621 |  |  | 1800 |  |  | 1679 |  |  | 1608.5 |  |  | 1655 |  |  | 1632 |  |  | 1802.5 |  |  | 1553.5 |  |  | 1661.5 |  |  | 1708.5 |  |  | 1608 |  |  | 1745 |  |  | 1560.5 |  |  | 1702.5 |  |  | 1650.5 |  |  | 1674 |  |  | 1653 |  |  | 1613 |  |  | 1652 |  |  | 1535 |  |  | 1635 |  |  | 1681 |  |  | 1656.5 |  |  | 1655.5 |  |  | 1636 |  |  | 1614.5 |  |  | 1657.5 |  |  | 1537 |  |  | 1685 |  |  | 1596 |  |  | 1627 |  |  | 1577.5 |  |  | 1533.5 |  |  | 1667.5 |  |  | 1639 |  |  | 1608.5 |  |  | 1660 |  |  | 1650 |  |  | 1712 |  |  | 1508.5 |  |  | 1654 |  |  | 1546 |  |  | 1664.5 |  |  | 1621 |  |  | 1700.5 |  |  | 1801 |  |  | 1600.5 |  |  | 1598 |  |  | 1652.5 |  |  | 1670.5 |  |  | 1694 |  |  | 1657 |  |  | 1502 |  |  | 1661 |  |  | 1544.5 |  |  | 1625 |  |  | 1724 |  |  | 1596.5 |  |  | 1739.5 |  |  | 1595.5 |  |  | 1577 |  |  | 1634.5 |  |  | 1627.5 |  |  | 1593.5 |  |  | 1731 |  |  | 1650 |  |  | 1624.5 |  |  | 1707 |  |  | 1763 |  |  | 1646.5 |  |  | 1613 |  |  | 1755 |  |  | 1648 |  |  | 1600 |  |  | 1504.5 |  |  | 1717.5 |  |  | 1580 |  |  | 1715 |  |  | 1669 |  |  | 1638 |  |  | 1636 |  |  | 1575.5 |  |  | 1643.5 |  |  | 1657 |  |  | 1773 |  |  | 1766 |  |  | 1542.5 |  |  | 1796.5 |  |  | 1586 |  |  | 1649 |  |  | 1559 |  |  | 1637.5 |  |  | 1798.5 |  |  | 1666 |  |  | 1572 |  |  | 1699 |  |  | 1664 |  |  | 1642 |  |  | 1728 |  |  | 1602 |  |  | 1759.5 |  |  | 1567 |  |  | 1786 |  |  | 1677 |  |  | 1678.5 |  |  | 1734 |  |  | 1547 |  |  | 1493 |  |  | 1656 |  |  | 1705 |  |  | 1650 |  |  | 1669 |  |  | 1640.5 |  |  | 1619.5 |  |  | 1555.5 |  |  | 1715 |  |  | 1647 |  |  | 1691.5 |  |  | 1513 |  |  | 1551.5 |  |  | 1650.5 |  |  | 1632 |  |  | 1659 |  |  | 1689.5 |  |  | 1616 |  |  | 1681 |  |  | 1672 |  |  | 1709 |  |  | 1640 |  |  | 1581 |  |  | 1578 |  |  | 1767.5 |  |  | 1667 |  |  | 1686 |  |  | 1727 |  |  | 1587 |  |  | 1686 |  |  | 1617 |  |  | 1801 |  |  | 1673 |  |  | 1697 |  |  | 1789.5 |  |  | 1704.5 |  |  | 1629.5 |  |  | 1669.5 |  |  | 1686 |  |  | 1549 |  |  | 1755.5 |  |  | 1627 |  |  | 1637 |  |  | 1620.5 |  |  | 1728.5 |  |  | 1687 |  |  | 1631.5 |  |  | 1582.5 |  |  | 1568 |  |  | 1743 |  |  | 1641 |  |  | 1619 |  |  | 1689.5 |  |  | 1618 |  |  | 1589.5 |  |  | 1542.5 |  |  | 1571 |  |  | 1600 |  |  | 1671.5 |  |  | 1560 |  |  | 1625.5 |  |  | 1648 |  |  | 1671.5 |  |  | 1553.5 |  |  | 1574.5 |  |  | 1672.5 |  |  | 1658.5 |  |  | 1548 |  |  | 1523 |  |  | 1757.5 |  |  | 1677 |  |  | 1581 |  |  | 1638 |  |  | 1744 |  |  | 1794.5 |  |  | 1494 |  |  | 1616 |  |  | 1660 |  |  | 1671.5 |  |  | 1645 |  |  | 1578 |  |  | 1610 |  |  | 1805.5 |  |  | 1701 |  |  | 1545 |  |  | 1631 |  |  | 1763 |  |  | 1886.5 |  |  | 1659 |  |  | 1612.5 |  |  | 1640 |  |  | 1700 |  |  | 1830.5 |  |  | 1715 |  |  | 1582 |  |  | 1620.5 |  |  | 1679 |  |  | 1586 |  |  | 1665 |  |  | 1780.5 |  |  | 1614.5 |  |  | 1679 |  |  | 1613 |  |  | 1660.5 |  |  | 1719.5 |  |  | 1598 |  |  | 1682 |  |  | 1692.5 |  |  | 1751.5 |  |  | 1555.5 |  |  | 1672.5 |  |  | 1611.5 |  |  | 1846 |  |  | 1645.5 |  |  | 1680 |  |  | 1630 |  |  | 1729 |  |  | 1697 |  |  | 1681.5 |  |  | 1657 |  |  | 1584 |  |  | 1667.5 |  |  | 1647.5 |  |  | 1620 |  |  | 1692.5 |  |  | 1653.5 |  |  | 1757 |  |  | 1592 |  |  | 1634 |  |  | 1722.5 |  |  | 1663 |  |  | 1663.5 |  |  | 1693 |  |  | 1674 |  |  | 1799.5 |  |  | 1624 |  |  | 1812 |  |  | 1618 |  |  | 1715 |  |  | 1706 |  |  | 1638 |  |  | 1656 |  |  | 1638 |  |  | 1560.5 |  |  | 1675.5 |  |  | 1651 |  |  | 1697.5 |  |  | 1510.5 |  |  | 1556 |  |  | 1556 |  |  | 1736 |  |  | 1727.5 |  |  | 1602.5 |  |  | 1663 |  |  | 1770 |  |  | 1560 |  |  | 1526 |  |  | 1643 |  |  | 1640 |  |  | 1761 |  |  | 1607.5 |  |  | 1759 |  |  | 1679 |  |  | 1777 |  |  | 1619 |  |  | 1516 |  |  | 1655.5 |  |  | 1816.5 |  |  | 1497.5 |  |  | 1571 |  |  | 1594 |  |  | 1565.5 |  |  | 1775.5 |  |  | 1703.5 |  |  | 1617 |  |  | 1727.5 |  |  | 1677.5 |  |  | 1741 |  |  | 1659.5 |  |  | 1684.5 |  |  | 1645 |  |  | 1588 |  |  | 1637 |  |  | 1715 |  |  | 1615 |  |  | 1569 |  |  | 1664 |  |  | 1771 |  |  | 1595 |  |  | 1570 |  |  | 1746.5 |  |  | 1656 |  |  | 1683 |  |  | 1594 |  |  | 1587.5 |  |  | 1670 |  |  | 1678.5 |  |  | 1770 |  |  | 1684 |  |  | 1640 |  |  | 1653 |  |  | 1715.5 |  |  | 1598 |  |  | 1579 |  |  | 1746.5 |  |  | 1693 |  |  | 1629 |  |  | 1608.5 |  |  | 1637.5 |  |  | 1690 |  |  | 1592.5 |  |  | 1701 |  |  | 1658.5 |  |  | 1771 |  |  | 1731 |  |  | 1654.5 |  |  | 1740.5 |  |  | 1638 |  |  | 1720 |  |  | 1640 |  |  | 1701 |  |  | 1560 |  |  | 1669 |  |  | 1508 |  |  | 1560 |  |  | 1811.5 |  |  | 1481 |  |  | 1741.5 |  |  | 1588 |  |  | 1705.5 |  |  | 1614.5 |  |  | 1595 |  |  | 1673 |  |  | 1731.5 |  |  | 1711 |  |  | 1675 |  |  | 1711 |  |  | 1624.5 |  |  | 1721 |  |  | 1544.5 |  |  | 1502 |  |  | 1629 |  |  | 1672 |  |  | 1723 |  |  | 1765.5 |  |  | 1620 |  |  | 1606 |  |  | 1671 |  |  | 1567.5 |  |  | 1741 |  |  | 1667 |  |  | 1646 |  |  | 1660 |  |  | 1624.5 |  |  | 1580.5 |  |  | 1705 |  |  | 1721 |  |  | 1650 |  |  | 1690.5 |  |  | 1667 |  |  | 1629 |  |  | 1636 |  |  | 1763.5 |  |  | 1669.5 |  |  | 1651.5 |  |  | 1645 |  |  | 1727 |  |  | 1665 |  |  | 1571.5 |  |  | 1690 |  |  | 1657.5 |  |  | 1516 |  |  | 1602 |  |  | 1667 |  |  | 1634.5 |  |  | 1674.5 |  |  | 1696 |  |  | 1596 |  |  | 1764.5 |  |  | 1624 |  |  | 1634 |  |  | 1738.5 |  |  | 1629 |  |  | 1598 |  |  | 1674.5 |  |  | 1603 |  |  | 1646 |  |  | 1615.5 |  |  | 1782 |  |  | 1587.5 |  |  | 1693 |  |  | 1548.5 |  |  | 1705.5 |  |  | 1549 |  |  | 1734 |  |  | 1692.5 |  |  | 1665.5 |  |  | 1762 |  |  | 1672 |  |  | 1716 |  |  | 1653.5 |  |  | 1692 |  |  | 1498 |  |  | 1652 |  |  | 1760.5 |  |  | 1709.5 |  |  | 1685 |  |  | 1702 |  |  | 1598 |  |  | 1571 |  |  | 1764 |  |  | 1627 |  |  | 1578 |  |  | 1620.5 |  |  | 1740.5 |  |  | 1576.5 |  |  | 1680 |  |  | 1598.5 |  |  | 1705 |  |  | 1578 |  |  | 1665.5 |  |  | 1565.5 |  |  | 1493 |  |  | 1673 |  |  | 1651.5 |  |  | 1653 |  |  | 1688 |  |  | 1589.5 |  |  | 1668.5 |  |  | 1651 |  |  | 1618 |  |  | 1728 |  |  | 1560.5 |  |  | 1600 |  |  | 1522 |  |  | 1655 |  |  | 1701 |  |  | 1728 |  |  | 1597.5 |  |  | 1767 |  |  | 1578 |  |  | 1472 |  |  | 1778.5 |  |  | 1681 |  |  | 1618.5 |  |  | 1565.5 |  |  | 1629 |  |  | 1704 |  |  | 1651.5 |  |  | 1579.5 |  |  | 1602.5 |  |  | 1687.5 |  |  | 1673.5 |  |  | 1651 |  |  | 1620 |  |  | 1665.5 |  |  | 1642.5 |  |  | 1671 |  |  | 1609 |  |  | 1621.5 |  |  | 1742 |  |  | 1616 |  |  | 1518 |  |  | 1679.5 |  |  | 1745 |  |  | 1560.5 |  |  | 1536 |  |  | 1651.5 |  |  | 1748.5 |  |  | 1799.5 |  |  | 1705 |  |  | 1636 |  |  | 1661.5 |  |  | 1603.5 |  |  | 1683 |  |  | 1674 |  |  | 1663.5 |  |  | 1695 |  |  | 1660.5 |  |  | 1659.5 |  |  | 1715 |  |  | 1668 |  |  | 1591.5 |  |  | 1764.5 |  |  | 1640 |  |  | 1642.5 |  |  | 1610.5 |  |  | 1674 |  |  | 1718 |  |  | 1763 |  |  | 1684.5 |  |  | 1710 |  |  | 1622 |  |  | 1700 |  |  | 1625 |  |  | 1665 |  |  | 1611 |  |  | 1743.5 |  |  | 1618.5 |  |  | 1675 |  |  | 1604 |  |  | 1653 |  |  | 1675.5 |  |  | 1653 |  |  | 1778 |  |  | 1600.5 |  |  | 1649.5 |  |  | 1622 |  |  | 1576.5 |  |  | 1681 |  |  | 1532 |  |  | 1682 |  |  | 1773.5 |  |  | 1792 |  |  | 1547.5 |  |  | 1630.5 |  |  | 1575 |  |  | 1699.5 |  |  | 1524.5 |  |  | 1588 |  |  | 1542 |  |  | 1787 |  |  | 1545.5 |  |  | 1527 |  |  | 1595.5 |  |  | 1616.5 |  |  | 1701 |  |  | 1578.5 |  |  | 1622 |  |  | 1647 |  |  | 1624 |  |  | 1585 |  |  | 1536 |  |  | 1751.5 |  |  | 1664 |  |  | 1744 |  |  | 1577 |  |  | 1695 |  |  | 1640.5 |  |  | 1735.5 |  |  | 1619 |  |  | 1655 |  |  | 1643 |  |  | 1598 |  |  | 1684 |  |  | 1638.5 |  |  | 1658 |  |  | 1672.5 |  |  | 1784 |  |  | 1528 |  |  | 1632 |  |  | 1624 |  |  | 1620.5 |  |  | 1633 |  |  | 1629.5 |  |  | 1609 |  |  | 1747 |  |  | 1711 |  |  | 1646.5 |  |  | 1564 |  |  | 1555 |  |  | 1552 |  |  | 1764 |  |  | 1779 |  |  | 1647.5 |  |  | 1681.5 |  |  | 1599 |  |  | 1605.5 |  |  | 1578 |  |  | 1552.5 |  |  | 1639.5 |  |  | 1576.5 |  |  | 1690.5 |  |  | 1548 |  |  | 1733 |  |  | 1602 |  |  | 1608 |  |  | 1665 |  |  | 1644 |  |  | 1581.5 |  |  | 1595.5 |  |  | 1689.5 |  |  | 1698 |  |  | 1684.5 |  |  | 1673.5 |  |  | 1727.5 |  |  | 1631.5 |  |  | 1631 |  |  | 1629.5 |  |  | 1650.5 |  |  | 1700 |  |  | 1620.5 |  |  | 1724.5 |  |  | 1697.5 |  |  | 1735 |  |  | 1682.5 |  |  | 1679 |  |  | 1672 |  |  | 1654.5 |  |  | 1720.5 |  |  | 1700 |  |  | 1648 |  |  | 1540.5 |  |  | 1554.5 |  |  | 1642.5 |  |  | 1725 |  |  | 1623 |  |  | 1580 |  |  | 1663.5 |  |  | 1702.5 |  |  | 1728 |  |  | 1711.5 |  |  | 1555 |  |  | 1623 |  |  | 1695.5 |  |  | 1591.5 |  |  | 1604 |  |  | 1646.5 |  |  | 1640 |  |  | 1518.5 |  |  | 1768.5 |  |  | 1691 |  |  | 1617.5 |  |  | 1722 |  |  | 1684.5 |  |  | 1635 |  |  | 1721 |  |  | 1692 |  |  | 1583.5 |  |  | 1575.5 |  |  | 1704 |  |  | 1583 |  |  | 1614 |  |  | 1642.5 |  |  | 1653.5 |  |  | 1690 |  |  | 1646.5 |  |  | 1615 |  |  | 1570.5 |  |  | 1652.5 |  |  | 1623 |  |  | 1618 |  |  | 1629 |  |  | 1609.5 |  |  | 1634 |  |  | 1715.5 |  |  | 1700 |  |  | 1664.5 |  |  | 1831 |  |  | 1464.5 |  |  | 1627 |  |  | 1582.5 |  |  | 1613.5 |  |  | 1606 |  |  | 1609 |  |  | 1771 |  |  | 1662 |  |  | 1703.5 |  |  | 1527 |  |  | 1620.5 |  |  | 1535 |  |  | 1592 |  |  | 1612 |  |  | 1710 |  |  | 1668 |  |  | 1644 |  |  | 1660 |  |  | 1687.5 |  |  | 1553 |  |  | 1715
59 |  | 1814.5 |  |  | 1783 |  |  | 1722.5 |  |  | 1656 |  |  | 1681.5 |  |  | 1684 |  |  | 1671 |  |  | 1731 |  |  | 1626.5 |  |  | 1645 |  |  | 1645 |  |  | 1797 |  |  | 1714 |  |  | 1822 |  |  | 1586.5 |  |  | 1749.5 |  |  | 1620 |  |  | 1765 |  |  | 1802 |  |  | 1619.5 |  |  | 1698 |  |  | 1751 |  |  | 1597 |  |  | 1712 |  |  | 1695.5 |  |  | 1812 |  |  | 1686 |  |  | 1642 |  |  | 1703 |  |  | 1604 |  |  | 1667 |  |  | 1674.5 |  |  | 1792.5 |  |  | 1674.5 |  |  | 1555 |  |  | 1602.5 |  |  | 1654.5 |  |  | 1723.5 |  |  | 1704 |  |  | 1686 |  |  | 1593.5 |  |  | 1605 |  |  | 1729.5 |  |  | 1668.5 |  |  | 1720.5 |  |  | 1821.5 |  |  | 1847.5 |  |  | 1687 |  |  | 1551 |  |  | 1602.5 |  |  | 1642 |  |  | 1583.5 |  |  | 1627.5 |  |  | 1722 |  |  | 1652 |  |  | 1632 |  |  | 1608 |  |  | 1777 |  |  | 1752 |  |  | 1658.5 |  |  | 1740.5 |  |  | 1677.5 |  |  | 1586 |  |  | 1717 |  |  | 1562 |  |  | 1600.5 |  |  | 1649 |  |  | 1673.5 |  |  | 1710.5 |  |  | 1804.5 |  |  | 1669 |  |  | 1731 |  |  | 1715 |  |  | 1689.5 |  |  | 1723.5 |  |  | 1640.5 |  |  | 1736.5 |  |  | 1677.5 |  |  | 1748.5 |  |  | 1700.5 |  |  | 1644.5 |  |  | 1598 |  |  | 1686 |  |  | 1673 |  |  | 1790.5 |  |  | 1775 |  |  | 1598.5 |  |  | 1682 |  |  | 1729 |  |  | 1745.5 |  |  | 1761.5 |  |  | 1662 |  |  | 1882 |  |  | 1617.5 |  |  | 1758 |  |  | 1649.5 |  |  | 1703.5 |  |  | 1679.5 |  |  | 1658.5 |  |  | 1568.5 |  |  | 1713 |  |  | 1682 |  |  | 1587 |  |  | 1721.5 |  |  | 1658.5 |  |  | 1729.5 |  |  | 1673.5 |  |  | 1673 |  |  | 1684 |  |  | 1718.5 |  |  | 1561 |  |  | 1685.5 |  |  | 1701 |  |  | 1644 |  |  | 1609.5 |  |  | 1669 |  |  | 1661 |  |  | 1621 |  |  | 1697 |  |  | 1725.5 |  |  | 1669.5 |  |  | 1631.5 |  |  | 1803 |  |  | 1616 |  |  | 1572 |  |  | 1628 |  |  | 1649.5 |  |  | 1662 |  |  | 1671.5 |  |  | 1740 |  |  | 1630 |  |  | 1719.5 |  |  | 1628.5 |  |  | 1564 |  |  | 1642.5 |  |  | 1648 |  |  | 1678 |  |  | 1667 |  |  | 1710 |  |  | 1635 |  |  | 1605 |  |  | 1630 |  |  | 1695 |  |  | 1579 |  |  | 1592.5 |  |  | 1635 |  |  | 1539 |  |  | 1694 |  |  | 1691 |  |  | 1653 |  |  | 1606 |  |  | 1653 |  |  | 1729.5 |  |  | 1702 |  |  | 1680.5 |  |  | 1738 |  |  | 1601 |  |  | 1717.5 |  |  | 1675 |  |  | 1836.5 |  |  | 1676 |  |  | 1560 |  |  | 1681.5 |  |  | 1706 |  |  | 1756.5 |  |  | 1661 |  |  | 1610 |  |  | 1706.5 |  |  | 1690.5 |  |  | 1714 |  |  | 1626.5 |  |  | 1694.5 |  |  | 1702 |  |  | 1708 |  |  | 1872.5 |  |  | 1601.5 |  |  | 1661.5 |  |  | 1714 |  |  | 1728 |  |  | 1646 |  |  | 1775 |  |  | 1728 |  |  | 1709.5 |  |  | 1677 |  |  | 1591.5 |  |  | 1691.5 |  |  | 1703 |  |  | 1758 |  |  | 1818.5 |  |  | 1559.5 |  |  | 1639 |  |  | 1724.5 |  |  | 1606.5 |  |  | 1691 |  |  | 1555 |  |  | 1638 |  |  | 1625.5 |  |  | 1795 |  |  | 1670.5 |  |  | 1643.5 |  |  | 1602 |  |  | 1634.5 |  |  | 1634 |  |  | 1699 |  |  | 1700 |  |  | 1697 |  |  | 1533 |  |  | 1772 |  |  | 1746 |  |  | 1724 |  |  | 1766 |  |  | 1657 |  |  | 1670.5 |  |  | 1780.5 |  |  | 1656 |  |  | 1602 |  |  | 1766 |  |  | 1691.5 |  |  | 1740.5 |  |  | 1714.5 |  |  | 1684 |  |  | 1675 |  |  | 1782.5 |  |  | 1664.5 |  |  | 1580.5 |  |  | 1753 |  |  | 1788 |  |  | 1700 |  |  | 1703 |  |  | 1692 |  |  | 1653.5 |  |  | 1627.5 |  |  | 1769 |  |  | 1669 |  |  | 1639 |  |  | 1811 |  |  | 1690 |  |  | 1698.5 |  |  | 1660 |  |  | 1717 |  |  | 1676 |  |  | 1692 |  |  | 1638.5 |  |  | 1811 |  |  | 1712 |  |  | 1654 |  |  | 1765 |  |  | 1753.5 |  |  | 1768 |  |  | 1590 |  |  | 1633 |  |  | 1730.5 |  |  | 1675.5 |  |  | 1762.5 |  |  | 1800 |  |  | 1645 |  |  | 1600 |  |  | 1817 |  |  | 1668 |  |  | 1621.5 |  |  | 1765 |  |  | 1634.5 |  |  | 1725.5 |  |  | 1719.5 |  |  | 1749 |  |  | 1820.5 |  |  | 1684 |  |  | 1623 |  |  | 1642.5 |  |  | 1694.5 |  |  | 1750 |  |  | 1761.5 |  |  | 1749.5 |  |  | 1698 |  |  | 1762 |  |  | 1670.5 |  |  | 1602.5 |  |  | 1790 |  |  | 1705.5 |  |  | 1702 |  |  | 1659 |  |  | 1664.5 |  |  | 1748 |  |  | 1641 |  |  | 1722.5 |  |  | 1638 |  |  | 1751.5 |  |  | 1664 |  |  | 1852 |  |  | 1706 |  |  | 1632 |  |  | 1775.5 |  |  | 1832 |  |  | 1742.5 |  |  | 1615.5 |  |  | 1721.5 |  |  | 1775 |  |  | 1779.5 |  |  | 1860 |  |  | 1723 |  |  | 1554.5 |  |  | 1666.5 |  |  | 1713 |  |  | 1655.5 |  |  | 1731 |  |  | 1675 |  |  | 1811.5 |  |  | 1685 |  |  | 1690.5 |  |  | 1733.5 |  |  | 1718.5 |  |  | 1648 |  |  | 1608 |  |  | 1666 |  |  | 1570.5 |  |  | 1649 |  |  | 1787.5 |  |  | 1718 |  |  | 1668 |  |  | 1622 |  |  | 1675 |  |  | 1744 |  |  | 1706 |  |  | 1650 |  |  | 1815 |  |  | 1718 |  |  | 1637.5 |  |  | 1681 |  |  | 1656 |  |  | 1831.5 |  |  | 1568.5 |  |  | 1687.5 |  |  | 1729.5 |  |  | 1647 |  |  | 1792 |  |  | 1589.5 |  |  | 1726.5 |  |  | 1697.5 |  |  | 1713 |  |  | 1679 |  |  | 1642 |  |  | 1673 |  |  | 1556 |  |  | 1661 |  |  | 1696 |  |  | 1685.5 |  |  | 1694.5 |  |  | 1651 |  |  | 1653.5 |  |  | 1696.5 |  |  | 1561 |  |  | 1700 |  |  | 1635 |  |  | 1653 |  |  | 1624.5 |  |  | 1580.5 |  |  | 1714.5 |  |  | 1686 |  |  | 1623.5 |  |  | 1707 |  |  | 1689 |  |  | 1759 |  |  | 1547.5 |  |  | 1675 |  |  | 1585 |  |  | 1685.5 |  |  | 1668 |  |  | 1739.5 |  |  | 1830 |  |  | 1639.5 |  |  | 1627 |  |  | 1676.5 |  |  | 1685.5 |  |  | 1718 |  |  | 1672 |  |  | 1528 |  |  | 1682 |  |  | 1573.5 |  |  | 1664 |  |  | 1753 |  |  | 1620.5 |  |  | 1768.5 |  |  | 1634.5 |  |  | 1601 |  |  | 1673.5 |  |  | 1666.5 |  |  | 1614.5 |  |  | 1770 |  |  | 1689 |  |  | 1671.5 |  |  | 1733 |  |  | 1810 |  |  | 1693.5 |  |  | 1652 |  |  | 1770 |  |  | 1695 |  |  | 1624 |  |  | 1525.5 |  |  | 1756.5 |  |  | 1595 |  |  | 1736 |  |  | 1708 |  |  | 1659 |  |  | 1675 |  |  | 1614.5 |  |  | 1669.5 |  |  | 1686 |  |  | 1812 |  |  | 1790 |  |  | 1563.5 |  |  | 1835.5 |  |  | 1625 |  |  | 1678 |  |  | 1598 |  |  | 1676.5 |  |  | 1845.5 |  |  | 1705 |  |  | 1593 |  |  | 1723 |  |  | 1693 |  |  | 1666 |  |  | 1767 |  |  | 1628 |  |  | 1785.5 |  |  | 1596 |  |  | 1810 |  |  | 1716 |  |  | 1717.5 |  |  | 1773 |  |  | 1568 |  |  | 1517 |  |  | 1677 |  |  | 1744 |  |  | 1697 |  |  | 1716 |  |  | 1655.5 |  |  | 1648.5 |  |  | 1570.5 |  |  | 1730 |  |  | 1662 |  |  | 1720.5 |  |  | 1534 |  |  | 1590.5 |  |  | 1676.5 |  |  | 1671 |  |  | 1674 |  |  | 1704.5 |  |  | 1637 |  |  | 1707 |  |  | 1687 |  |  | 1730 |  |  | 1687 |  |  | 1620 |  |  | 1625 |  |  | 1796.5 |  |  | 1691 |  |  | 1725 |  |  | 1766 |  |  | 1616 |  |  | 1712 |  |  | 1656 |  |  | 1830 |  |  | 1702 |  |  | 1712 |  |  | 1804.5 |  |  | 1728.5 |  |  | 1653.5 |  |  | 1698.5 |  |  | 1710 |  |  | 1573 |  |  | 1784.5 |  |  | 1653 |  |  | 1661 |  |  | 1641.5 |  |  | 1749.5 |  |  | 1711 |  |  | 1646.5 |  |  | 1629.5 |  |  | 1594 |  |  | 1764 |  |  | 1662 |  |  | 1645 |  |  | 1715.5 |  |  | 1665 |  |  | 1615.5 |  |  | 1581.5 |  |  | 1592 |  |  | 1639 |  |  | 1686.5 |  |  | 1575 |  |  | 1672.5 |  |  | 1669 |  |  | 1710.5 |  |  | 1574.5 |  |  | 1589.5 |  |  | 1701.5 |  |  | 1697.5 |  |  | 1574 |  |  | 1552 |  |  | 1796.5 |  |  | 1716 |  |  | 1620 |  |  | 1685 |  |  | 1783 |  |  | 1815.5 |  |  | 1533 |  |  | 1655 |  |  | 1707 |  |  | 1695.5 |  |  | 1669 |  |  | 1617 |  |  | 1636 |  |  | 1844.5 |  |  | 1740 |  |  | 1566 |  |  | 1670 |  |  | 1787 |  |  | 1933.5 |  |  | 1698 |  |  | 1638.5 |  |  | 1666 |  |  | 1739 |  |  | 1869.5 |  |  | 1754 |  |  | 1611 |  |  | 1659.5 |  |  | 1703 |  |  | 1615 |  |  | 1689 |  |  | 1819.5 |  |  | 1653.5 |  |  | 1718 |  |  | 1637 |  |  | 1686.5 |  |  | 1740.5 |  |  | 1645 |  |  | 1721 |  |  | 1718.5 |  |  | 1777.5 |  |  | 1570.5 |  |  | 1711.5 |  |  | 1650.5 |  |  | 1872 |  |  | 1660.5 |  |  | 1706 |  |  | 1669 |  |  | 1750 |  |  | 1723 |  |  | 1707.5 |  |  | 1683 |  |  | 1613 |  |  | 1688.5 |  |  | 1686.5 |  |  | 1641 |  |  | 1731.5 |  |  | 1679.5 |  |  | 1796 |  |  | 1613 |  |  | 1658 |  |  | 1743.5 |  |  | 1710 |  |  | 1678.5 |  |  | 1732 |  |  | 1689 |  |  | 1825.5 |  |  | 1663 |  |  | 1827 |  |  | 1657 |  |  | 1736 |  |  | 1735 |  |  | 1677 |  |  | 1695 |  |  | 1662 |  |  | 1607.5 |  |  | 1701.5 |  |  | 1675 |  |  | 1721.5 |  |  | 1536.5 |  |  | 1595 |  |  | 1595 |  |  | 1751 |  |  | 1756.5 |  |  | 1617.5 |  |  | 1710 |  |  | 1794 |  |  | 1575 |  |  | 1555 |  |  | 1672 |  |  | 1687 |  |  | 1800 |  |  | 1622.5 |  |  | 1798 |  |  | 1694 |  |  | 1801 |  |  | 1658 |  |  | 1555 |  |  | 1684.5 |  |  | 1863.5 |  |  | 1523.5 |  |  | 1610 |  |  | 1609 |  |  | 1604.5 |  |  | 1814.5 |  |  | 1718.5 |  |  | 1638 |  |  | 1742.5 |  |  | 1692.5 |  |  | 1780 |  |  | 1698.5 |  |  | 1731.5 |  |  | 1666 |  |  | 1627 |  |  | 1652 |  |  | 1736 |  |  | 1644 |  |  | 1584 |  |  | 1703 |  |  | 1810 |  |  | 1624 |  |  | 1594 |  |  | 1785.5 |  |  | 1677 |  |  | 1707 |  |  | 1618 |  |  | 1616.5 |  |  | 1694 |  |  | 1704.5 |  |  | 1794 |  |  | 1713 |  |  | 1666 |  |  | 1679 |  |  | 1762.5 |  |  | 1645 |  |  | 1608 |  |  | 1770.5 |  |  | 1717 |  |  | 1653 |  |  | 1637.5 |  |  | 1676.5 |  |  | 1714 |  |  | 1613.5 |  |  | 1725 |  |  | 1687.5 |  |  | 1800 |  |  | 1755 |  |  | 1669.5 |  |  | 1761.5 |  |  | 1677 |  |  | 1749 |  |  | 1664 |  |  | 1716 |  |  | 1581 |  |  | 1693 |  |  | 1547 |  |  | 1586 |  |  | 1840.5 |  |  | 1520 |  |  | 1788.5 |  |  | 1635 |  |  | 1729.5 |  |  | 1653.5 |  |  | 1610 |  |  | 1688 |  |  | 1760.5 |  |  | 1737 |  |  | 1690 |  |  | 1737 |  |  | 1645.5 |  |  | 1760 |  |  | 1565.5 |  |  | 1541 |  |  | 1644 |  |  | 1696 |  |  | 1762 |  |  | 1812.5 |  |  | 1644 |  |  | 1635 |  |  | 1718 |  |  | 1588.5 |  |  | 1780 |  |  | 1714 |  |  | 1693 |  |  | 1707 |  |  | 1663.5 |  |  | 1609.5 |  |  | 1726 |  |  | 1768 |  |  | 1676 |  |  | 1711.5 |  |  | 1706 |  |  | 1644 |  |  | 1683 |  |  | 1802.5 |  |  | 1684.5 |  |  | 1666.5 |  |  | 1660 |  |  | 1748 |  |  | 1691 |  |  | 1610.5 |  |  | 1714 |  |  | 1696.5 |  |  | 1531 |  |  | 1641 |  |  | 1682 |  |  | 1673.5 |  |  | 1713.5 |  |  | 1711 |  |  | 1635 |  |  | 1788.5 |  |  | 1671 |  |  | 1649 |  |  | 1777.5 |  |  | 1653 |  |  | 1645 |  |  | 1695.5 |  |  | 1618 |  |  | 1685 |  |  | 1654.5 |  |  | 1829 |  |  | 1611.5 |  |  | 1719 |  |  | 1569.5 |  |  | 1731.5 |  |  | 1564 |  |  | 1760 |  |  | 1716.5 |  |  | 1689.5 |  |  | 1801 |  |  | 1687 |  |  | 1755 |  |  | 1674.5 |  |  | 1716 |  |  | 1527 |  |  | 1678 |  |  | 1799.5 |  |  | 1730.5 |  |  | 1732 |  |  | 1749 |  |  | 1619 |  |  | 1586 |  |  | 1785 |  |  | 1674 |  |  | 1604 |  |  | 1641.5 |  |  | 1779.5 |  |  | 1591.5 |  |  | 1695 |  |  | 1645.5 |  |  | 1752 |  |  | 1617 |  |  | 1704.5 |  |  | 1580.5 |  |  | 1522 |  |  | 1712 |  |  | 1672.5 |  |  | 1679 |  |  | 1735 |  |  | 1613.5 |  |  | 1694.5 |  |  | 1677 |  |  | 1647 |  |  | 1749 |  |  | 1599.5 |  |  | 1639 |  |  | 1569 |  |  | 1702 |  |  | 1722 |  |  | 1767 |  |  | 1621.5 |  |  | 1814 |  |  | 1599 |  |  | 1511 |  |  | 1793.5 |  |  | 1707 |  |  | 1633.5 |  |  | 1589.5 |  |  | 1650 |  |  | 1725 |  |  | 1672.5 |  |  | 1603.5 |  |  | 1617.5 |  |  | 1702.5 |  |  | 1697.5 |  |  | 1690 |  |  | 1667 |  |  | 1694.5 |  |  | 1668.5 |  |  | 1695 |  |  | 1624 |  |  | 1642.5 |  |  | 1789 |  |  | 1655 |  |  | 1557 |  |  | 1705.5 |  |  | 1760 |  |  | 1599.5 |  |  | 1575 |  |  | 1680.5 |  |  | 1795.5 |  |  | 1838.5 |  |  | 1734 |  |  | 1675 |  |  | 1700.5 |  |  | 1650.5 |  |  | 1704 |  |  | 1713 |  |  | 1684.5 |  |  | 1734 |  |  | 1684.5 |  |  | 1683.5 |  |  | 1754 |  |  | 1707 |  |  | 1606.5 |  |  | 1811.5 |  |  | 1664 |  |  | 1681.5 |  |  | 1657.5 |  |  | 1700 |  |  | 1744 |  |  | 1784 |  |  | 1705.5 |  |  | 1739 |  |  | 1669 |  |  | 1715 |  |  | 1646 |  |  | 1680 |  |  | 1635 |  |  | 1782.5 |  |  | 1657.5 |  |  | 1701 |  |  | 1651 |  |  | 1692 |  |  | 1714.5 |  |  | 1674 |  |  | 1807 |  |  | 1639.5 |  |  | 1696.5 |  |  | 1661 |  |  | 1605.5 |  |  | 1705 |  |  | 1547 |  |  | 1721 |  |  | 1797.5 |  |  | 1839 |  |  | 1571.5 |  |  | 1659.5 |  |  | 1604 |  |  | 1714.5 |  |  | 1539.5 |  |  | 1603 |  |  | 1557 |  |  | 1802 |  |  | 1571.5 |  |  | 1548 |  |  | 1634.5 |  |  | 1631.5 |  |  | 1722 |  |  | 1617.5 |  |  | 1646 |  |  | 1686 |  |  | 1663 |  |  | 1609 |  |  | 1560 |  |  | 1777.5 |  |  | 1679 |  |  | 1765 |  |  | 1624 |  |  | 1710 |  |  | 1666.5 |  |  | 1774.5 |  |  | 1658 |  |  | 1702 |  |  | 1690 |  |  | 1624 |  |  | 1731 |  |  | 1662.5 |  |  | 1682 |  |  | 1693.5 |  |  | 1805 |  |  | 1543 |  |  | 1679 |  |  | 1648 |  |  | 1659.5 |  |  | 1659 |  |  | 1658.5 |  |  | 1633 |  |  | 1771 |  |  | 1750 |  |  | 1693.5 |  |  | 1611 |  |  | 1581 |  |  | 1578 |  |  | 1803 |  |  | 1818 |  |  | 1671.5 |  |  | 1702.5 |  |  | 1638 |  |  | 1634.5 |  |  | 1599 |  |  | 1599.5 |  |  | 1686.5 |  |  | 1605.5 |  |  | 1705.5 |  |  | 1563 |  |  | 1780 |  |  | 1631 |  |  | 1634 |  |  | 1689 |  |  | 1673 |  |  | 1602.5 |  |  | 1619.5 |  |  | 1728.5 |  |  | 1737 |  |  | 1699.5 |  |  | 1699.5 |  |  | 1756.5 |  |  | 1646.5 |  |  | 1655 |  |  | 1653.5 |  |  | 1689.5 |  |  | 1729 |  |  | 1635.5 |  |  | 1771.5 |  |  | 1736.5 |  |  | 1761 |  |  | 1706.5 |  |  | 1718 |  |  | 1693 |  |  | 1683.5 |  |  | 1741.5 |  |  | 1726 |  |  | 1695 |  |  | 1566.5 |  |  | 1593.5 |  |  | 1681.5 |  |  | 1772 |  |  | 1638 |  |  | 1627 |  |  | 1710.5 |  |  | 1749.5 |  |  | 1749 |  |  | 1758.5 |  |  | 1584 |  |  | 1662 |  |  | 1716.5 |  |  | 1638.5 |  |  | 1633 |  |  | 1675.5 |  |  | 1664 |  |  | 1542.5 |  |  | 1815.5 |  |  | 1738 |  |  | 1656.5 |  |  | 1737 |  |  | 1731.5 |  |  | 1650 |  |  | 1747 |  |  | 1731 |  |  | 1607.5 |  |  | 1599.5 |  |  | 1719 |  |  | 1622 |  |  | 1643 |  |  | 1666.5 |  |  | 1682.5 |  |  | 1719 |  |  | 1672.5 |  |  | 1644 |  |  | 1596.5 |  |  | 1691.5 |  |  | 1662 |  |  | 1665 |  |  | 1653 |  |  | 1638.5 |  |  | 1649 |  |  | 1736.5 |  |  | 1721 |  |  | 1693.5 |  |  | 1846 |  |  | 1503.5 |  |  | 1666 |  |  | 1629.5 |  |  | 1660.5 |  |  | 1635 |  |  | 1638 |  |  | 1818 |  |  | 1683 |  |  | 1727.5 |  |  | 1548 |  |  | 1667.5 |  |  | 1574 |  |  | 1631 |  |  | 1627 |  |  | 1757 |  |  | 1694 |  |  | 1673 |  |  | 1689 |  |  | 1702.5 |  |  | 1600 |  |  | 1739
60 |  | 1840.5 |  |  | 1809 |  |  | 1769.5 |  |  | 1680 |  |  | 1720.5 |  |  | 1723 |  |  | 1718 |  |  | 1752 |  |  | 1641.5 |  |  | 1669 |  |  | 1684 |  |  | 1812 |  |  | 1753 |  |  | 1861 |  |  | 1633.5 |  |  | 1778.5 |  |  | 1646 |  |  | 1786 |  |  | 1817 |  |  | 1640.5 |  |  | 1737 |  |  | 1775 |  |  | 1636 |  |  | 1751 |  |  | 1710.5 |  |  | 1851 |  |  | 1710 |  |  | 1681 |  |  | 1724 |  |  | 1643 |  |  | 1706 |  |  | 1689.5 |  |  | 1831.5 |  |  | 1703.5 |  |  | 1602 |  |  | 1641.5 |  |  | 1693.5 |  |  | 1770.5 |  |  | 1743 |  |  | 1715 |  |  | 1622.5 |  |  | 1652 |  |  | 1776.5 |  |  | 1697.5 |  |  | 1749.5 |  |  | 1868.5 |  |  | 1886.5 |  |  | 1726 |  |  | 1572 |  |  | 1641.5 |  |  | 1689 |  |  | 1630.5 |  |  | 1666.5 |  |  | 1769 |  |  | 1691 |  |  | 1653 |  |  | 1634 |  |  | 1798 |  |  | 1791 |  |  | 1679.5 |  |  | 1755.5 |  |  | 1692.5 |  |  | 1607 |  |  | 1746 |  |  | 1586 |  |  | 1629.5 |  |  | 1696 |  |  | 1694.5 |  |  | 1757.5 |  |  | 1843.5 |  |  | 1716 |  |  | 1770 |  |  | 1754 |  |  | 1713.5 |  |  | 1762.5 |  |  | 1655.5 |  |  | 1762.5 |  |  | 1703.5 |  |  | 1774.5 |  |  | 1724.5 |  |  | 1673.5 |  |  | 1645 |  |  | 1733 |  |  | 1697 |  |  | 1814.5 |  |  | 1822 |  |  | 1622.5 |  |  | 1721 |  |  | 1755 |  |  | 1774.5 |  |  | 1808.5 |  |  | 1709 |  |  | 1906 |  |  | 1638.5 |  |  | 1784 |  |  | 1673.5 |  |  | 1724.5 |  |  | 1718.5 |  |  | 1697.5 |  |  | 1594.5 |  |  | 1752 |  |  | 1729 |  |  | 1616 |  |  | 1747.5 |  |  | 1679.5 |  |  | 1744.5 |  |  | 1697.5 |  |  | 1699 |  |  | 1708 |  |  | 1742.5 |  |  | 1585 |  |  | 1724.5 |  |  | 1740 |  |  | 1673 |  |  | 1624.5 |  |  | 1698 |  |  | 1700 |  |  | 1642 |  |  | 1736 |  |  | 1746.5 |  |  | 1708.5 |  |  | 1678.5 |  |  | 1829 |  |  | 1640 |  |  | 1601 |  |  | 1652 |  |  | 1673.5 |  |  | 1691 |  |  | 1718.5 |  |  | 1761 |  |  | 1669 |  |  | 1748.5 |  |  | 1649.5 |  |  | 1579 |  |  | 1671.5 |  |  | 1663 |  |  | 1725 |  |  | 1682 |  |  | 1749 |  |  | 1656 |  |  | 1631 |  |  | 1651 |  |  | 1721 |  |  | 1594 |  |  | 1607.5 |  |  | 1659 |  |  | 1554 |  |  | 1733 |  |  | 1738 |  |  | 1679 |  |  | 1635 |  |  | 1674 |  |  | 1753.5 |  |  | 1741 |  |  | 1704.5 |  |  | 1753 |  |  | 1640 |  |  | 1756.5 |  |  | 1714 |  |  | 1875.5 |  |  | 1705 |  |  | 1575 |  |  | 1728.5 |  |  | 1732 |  |  | 1780.5 |  |  | 1700 |  |  | 1631 |  |  | 1753.5 |  |  | 1716.5 |  |  | 1743 |  |  | 1652.5 |  |  | 1720.5 |  |  | 1726 |  |  | 1737 |  |  | 1919.5 |  |  | 1616.5 |  |  | 1708.5 |  |  | 1743 |  |  | 1767 |  |  | 1685 |  |  | 1790 |  |  | 1743 |  |  | 1724.5 |  |  | 1703 |  |  | 1606.5 |  |  | 1720.5 |  |  | 1742 |  |  | 1784 |  |  | 1865.5 |  |  | 1585.5 |  |  | 1686 |  |  | 1771.5 |  |  | 1630.5 |  |  | 1738 |  |  | 1594 |  |  | 1685 |  |  | 1664.5 |  |  | 1816 |  |  | 1685.5 |  |  | 1690.5 |  |  | 1628 |  |  | 1649.5 |  |  | 1658 |  |  | 1714 |  |  | 1747 |  |  | 1721 |  |  | 1562 |  |  | 1787 |  |  | 1775 |  |  | 1753 |  |  | 1781 |  |  | 1672 |  |  | 1709.5 |  |  | 1819.5 |  |  | 1677 |  |  | 1626 |  |  | 1781 |  |  | 1738.5 |  |  | 1787.5 |  |  | 1761.5 |  |  | 1713 |  |  | 1690 |  |  | 1829.5 |  |  | 1688.5 |  |  | 1595.5 |  |  | 1779 |  |  | 1827 |  |  | 1721 |  |  | 1729 |  |  | 1739 |  |  | 1677.5 |  |  | 1653.5 |  |  | 1795 |  |  | 1695 |  |  | 1678 |  |  | 1837 |  |  | 1729 |  |  | 1737.5 |  |  | 1675 |  |  | 1756 |  |  | 1723 |  |  | 1721 |  |  | 1662.5 |  |  | 1850 |  |  | 1736 |  |  | 1683 |  |  | 1804 |  |  | 1792.5 |  |  | 1789 |  |  | 1605 |  |  | 1672 |  |  | 1777.5 |  |  | 1722.5 |  |  | 1809.5 |  |  | 1815 |  |  | 1660 |  |  | 1615 |  |  | 1841 |  |  | 1692 |  |  | 1645.5 |  |  | 1789 |  |  | 1673.5 |  |  | 1746.5 |  |  | 1766.5 |  |  | 1770 |  |  | 1844.5 |  |  | 1699 |  |  | 1662 |  |  | 1689.5 |  |  | 1709.5 |  |  | 1779 |  |  | 1782.5 |  |  | 1796.5 |  |  | 1713 |  |  | 1777 |  |  | 1709.5 |  |  | 1626.5 |  |  | 1829 |  |  | 1726.5 |  |  | 1728 |  |  | 1698 |  |  | 1703.5 |  |  | 1777 |  |  | 1680 |  |  | 1751.5 |  |  | 1685 |  |  | 1798.5 |  |  | 1688 |  |  | 1867 |  |  | 1721 |  |  | 1658 |  |  | 1790.5 |  |  | 1861 |  |  | 1781.5 |  |  | 1636.5 |  |  | 1760.5 |  |  | 1796 |  |  | 1808.5 |  |  | 1886 |  |  | 1770 |  |  | 1575.5 |  |  | 1692.5 |  |  | 1752 |  |  | 1681.5 |  |  | 1755 |  |  | 1704 |  |  | 1835.5 |  |  | 1706 |  |  | 1705.5 |  |  | 1754.5 |  |  | 1744.5 |  |  | 1672 |  |  | 1632 |  |  | 1705 |  |  | 1599.5 |  |  | 1688 |  |  | 1826.5 |  |  | 1742 |  |  | 1715 |  |  | 1661 |  |  | 1704 |  |  | 1783 |  |  | 1730 |  |  | 1689 |  |  | 1839 |  |  | 1733 |  |  | 1658.5 |  |  | 1728 |  |  | 1695 |  |  | 1860.5 |  |  | 1597.5 |  |  | 1716.5 |  |  | 1768.5 |  |  | 1673 |  |  | 1839 |  |  | 1604.5 |  |  | 1765.5 |  |  | 1721.5 |  |  | 1728 |  |  | 1708 |  |  | 1671 |  |  | 1694 |  |  | 1595 |  |  | 1708 |  |  | 1743 |  |  | 1706.5 |  |  | 1741.5 |  |  | 1666 |  |  | 1700.5 |  |  | 1743.5 |  |  | 1576 |  |  | 1739 |  |  | 1656 |  |  | 1692 |  |  | 1645.5 |  |  | 1609.5 |  |  | 1761.5 |  |  | 1707 |  |  | 1662.5 |  |  | 1746 |  |  | 1710 |  |  | 1785 |  |  | 1576.5 |  |  | 1704 |  |  | 1606 |  |  | 1724.5 |  |  | 1692 |  |  | 1768.5 |  |  | 1877 |  |  | 1678.5 |  |  | 1642 |  |  | 1697.5 |  |  | 1724.5 |  |  | 1742 |  |  | 1719 |  |  | 1549 |  |  | 1708 |  |  | 1599.5 |  |  | 1690 |  |  | 1800 |  |  | 1635.5 |  |  | 1789.5 |  |  | 1673.5 |  |  | 1640 |  |  | 1712.5 |  |  | 1692.5 |  |  | 1629.5 |  |  | 1809 |  |  | 1728 |  |  | 1686.5 |  |  | 1748 |  |  | 1834 |  |  | 1717.5 |  |  | 1673 |  |  | 1791 |  |  | 1721 |  |  | 1645 |  |  | 1564.5 |  |  | 1785.5 |  |  | 1634 |  |  | 1765 |  |  | 1747 |  |  | 1698 |  |  | 1699 |  |  | 1629.5 |  |  | 1684.5 |  |  | 1725 |  |  | 1836 |  |  | 1829 |  |  | 1610.5 |  |  | 1874.5 |  |  | 1651 |  |  | 1725 |  |  | 1645 |  |  | 1700.5 |  |  | 1874.5 |  |  | 1729 |  |  | 1614 |  |  | 1744 |  |  | 1717 |  |  | 1692 |  |  | 1814 |  |  | 1649 |  |  | 1811.5 |  |  | 1635 |  |  | 1839 |  |  | 1742 |  |  | 1764.5 |  |  | 1794 |  |  | 1607 |  |  | 1546 |  |  | 1701 |  |  | 1768 |  |  | 1723 |  |  | 1737 |  |  | 1676.5 |  |  | 1663.5 |  |  | 1591.5 |  |  | 1745 |  |  | 1691 |  |  | 1749.5 |  |  | 1563 |  |  | 1616.5 |  |  | 1702.5 |  |  | 1686 |  |  | 1713 |  |  | 1730.5 |  |  | 1676 |  |  | 1746 |  |  | 1726 |  |  | 1756 |  |  | 1734 |  |  | 1646 |  |  | 1654 |  |  | 1835.5 |  |  | 1730 |  |  | 1749 |  |  | 1790 |  |  | 1655 |  |  | 1727 |  |  | 1703 |  |  | 1859 |  |  | 1726 |  |  | 1738 |  |  | 1825.5 |  |  | 1767.5 |  |  | 1692.5 |  |  | 1737.5 |  |  | 1749 |  |  | 1588 |  |  | 1810.5 |  |  | 1692 |  |  | 1700 |  |  | 1656.5 |  |  | 1788.5 |  |  | 1758 |  |  | 1685.5 |  |  | 1653.5 |  |  | 1641 |  |  | 1803 |  |  | 1709 |  |  | 1684 |  |  | 1741.5 |  |  | 1691 |  |  | 1630.5 |  |  | 1602.5 |  |  | 1616 |  |  | 1686 |  |  | 1707.5 |  |  | 1601 |  |  | 1687.5 |  |  | 1693 |  |  | 1731.5 |  |  | 1613.5 |  |  | 1628.5 |  |  | 1727.5 |  |  | 1721.5 |  |  | 1598 |  |  | 1591 |  |  | 1820.5 |  |  | 1763 |  |  | 1659 |  |  | 1714 |  |  | 1812 |  |  | 1830.5 |  |  | 1572 |  |  | 1670 |  |  | 1746 |  |  | 1719.5 |  |  | 1695 |  |  | 1643 |  |  | 1651 |  |  | 1873.5 |  |  | 1766 |  |  | 1595 |  |  | 1696 |  |  | 1802 |  |  | 1962.5 |  |  | 1737 |  |  | 1677.5 |  |  | 1687 |  |  | 1754 |  |  | 1890.5 |  |  | 1769 |  |  | 1640 |  |  | 1685.5 |  |  | 1727 |  |  | 1662 |  |  | 1728 |  |  | 1848.5 |  |  | 1692.5 |  |  | 1757 |  |  | 1658 |  |  | 1707.5 |  |  | 1761.5 |  |  | 1684 |  |  | 1745 |  |  | 1765.5 |  |  | 1824.5 |  |  | 1599.5 |  |  | 1750.5 |  |  | 1679.5 |  |  | 1887 |  |  | 1686.5 |  |  | 1732 |  |  | 1695 |  |  | 1774 |  |  | 1762 |  |  | 1728.5 |  |  | 1730 |  |  | 1637 |  |  | 1714.5 |  |  | 1707.5 |  |  | 1656 |  |  | 1757.5 |  |  | 1705.5 |  |  | 1835 |  |  | 1628 |  |  | 1697 |  |  | 1772.5 |  |  | 1731 |  |  | 1704.5 |  |  | 1761 |  |  | 1728 |  |  | 1872.5 |  |  | 1687 |  |  | 1874 |  |  | 1678 |  |  | 1765 |  |  | 1756 |  |  | 1698 |  |  | 1742 |  |  | 1691 |  |  | 1654.5 |  |  | 1722.5 |  |  | 1690 |  |  | 1768.5 |  |  | 1575.5 |  |  | 1634 |  |  | 1642 |  |  | 1798 |  |  | 1785.5 |  |  | 1641.5 |  |  | 1736 |  |  | 1833 |  |  | 1596 |  |  | 1576 |  |  | 1687 |  |  | 1713 |  |  | 1839 |  |  | 1637.5 |  |  | 1822 |  |  | 1741 |  |  | 1840 |  |  | 1684 |  |  | 1584 |  |  | 1723.5 |  |  | 1902.5 |  |  | 1570.5 |  |  | 1649 |  |  | 1638 |  |  | 1628.5 |  |  | 1829.5 |  |  | 1757.5 |  |  | 1685 |  |  | 1768.5 |  |  | 1739.5 |  |  | 1827 |  |  | 1727.5 |  |  | 1760.5 |  |  | 1690 |  |  | 1651 |  |  | 1673 |  |  | 1765 |  |  | 1683 |  |  | 1623 |  |  | 1732 |  |  | 1849 |  |  | 1663 |  |  | 1641 |  |  | 1824.5 |  |  | 1701 |  |  | 1728 |  |  | 1633 |  |  | 1663.5 |  |  | 1709 |  |  | 1733.5 |  |  | 1815 |  |  | 1742 |  |  | 1692 |  |  | 1705 |  |  | 1801.5 |  |  | 1666 |  |  | 1629 |  |  | 1809.5 |  |  | 1741 |  |  | 1679 |  |  | 1676.5 |  |  | 1715.5 |  |  | 1761 |  |  | 1637.5 |  |  | 1746 |  |  | 1702.5 |  |  | 1847 |  |  | 1779 |  |  | 1684.5 |  |  | 1787.5 |  |  | 1692 |  |  | 1788 |  |  | 1703 |  |  | 1755 |  |  | 1610 |  |  | 1740 |  |  | 1586 |  |  | 1612 |  |  | 1861.5 |  |  | 1549 |  |  | 1809.5 |  |  | 1661 |  |  | 1755.5 |  |  | 1692.5 |  |  | 1649 |  |  | 1727 |  |  | 1799.5 |  |  | 1763 |  |  | 1737 |  |  | 1766 |  |  | 1660.5 |  |  | 1781 |  |  | 1580.5 |  |  | 1565 |  |  | 1659 |  |  | 1711 |  |  | 1791 |  |  | 1838.5 |  |  | 1665 |  |  | 1664 |  |  | 1733 |  |  | 1627.5 |  |  | 1819 |  |  | 1753 |  |  | 1722 |  |  | 1733 |  |  | 1678.5 |  |  | 1656.5 |  |  | 1773 |  |  | 1807 |  |  | 1723 |  |  | 1737.5 |  |  | 1732 |  |  | 1665 |  |  | 1698 |  |  | 1841.5 |  |  | 1710.5 |  |  | 1705.5 |  |  | 1699 |  |  | 1777 |  |  | 1738 |  |  | 1639.5 |  |  | 1740 |  |  | 1743.5 |  |  | 1570 |  |  | 1680 |  |  | 1711 |  |  | 1688.5 |  |  | 1752.5 |  |  | 1750 |  |  | 1650 |  |  | 1827.5 |  |  | 1692 |  |  | 1673 |  |  | 1806.5 |  |  | 1679 |  |  | 1674 |  |  | 1716.5 |  |  | 1639 |  |  | 1724 |  |  | 1693.5 |  |  | 1868 |  |  | 1640.5 |  |  | 1766 |  |  | 1608.5 |  |  | 1760.5 |  |  | 1579 |  |  | 1807 |  |  | 1745.5 |  |  | 1736.5 |  |  | 1840 |  |  | 1726 |  |  | 1781 |  |  | 1698.5 |  |  | 1742 |  |  | 1542 |  |  | 1717 |  |  | 1838.5 |  |  | 1745.5 |  |  | 1747 |  |  | 1775 |  |  | 1640 |  |  | 1625 |  |  | 1809 |  |  | 1695 |  |  | 1651 |  |  | 1665.5 |  |  | 1808.5 |  |  | 1615.5 |  |  | 1716 |  |  | 1684.5 |  |  | 1778 |  |  | 1641 |  |  | 1743.5 |  |  | 1604.5 |  |  | 1561 |  |  | 1738 |  |  | 1698.5 |  |  | 1718 |  |  | 1761 |  |  | 1660.5 |  |  | 1718.5 |  |  | 1692 |  |  | 1671 |  |  | 1770 |  |  | 1646.5 |  |  | 1686 |  |  | 1595 |  |  | 1723 |  |  | 1769 |  |  | 1806 |  |  | 1650.5 |  |  | 1853 |  |  | 1638 |  |  | 1537 |  |  | 1819.5 |  |  | 1722 |  |  | 1672.5 |  |  | 1628.5 |  |  | 1689 |  |  | 1764 |  |  | 1711.5 |  |  | 1632.5 |  |  | 1646.5 |  |  | 1717.5 |  |  | 1744.5 |  |  | 1705 |  |  | 1682 |  |  | 1733.5 |  |  | 1707.5 |  |  | 1716 |  |  | 1663 |  |  | 1671.5 |  |  | 1828 |  |  | 1679 |  |  | 1583 |  |  | 1744.5 |  |  | 1807 |  |  | 1614.5 |  |  | 1614 |  |  | 1709.5 |  |  | 1810.5 |  |  | 1853.5 |  |  | 1773 |  |  | 1699 |  |  | 1726.5 |  |  | 1689.5 |  |  | 1730 |  |  | 1742 |  |  | 1723.5 |  |  | 1773 |  |  | 1713.5 |  |  | 1712.5 |  |  | 1778 |  |  | 1733 |  |  | 1621.5 |  |  | 1826.5 |  |  | 1711 |  |  | 1696.5 |  |  | 1696.5 |  |  | 1715 |  |  | 1783 |  |  | 1813 |  |  | 1744.5 |  |  | 1760 |  |  | 1708 |  |  | 1736 |  |  | 1685 |  |  | 1719 |  |  | 1664 |  |  | 1806.5 |  |  | 1683.5 |  |  | 1727 |  |  | 1680 |  |  | 1721 |  |  | 1743.5 |  |  | 1698 |  |  | 1831 |  |  | 1654.5 |  |  | 1725.5 |  |  | 1676 |  |  | 1652.5 |  |  | 1726 |  |  | 1586 |  |  | 1736 |  |  | 1844.5 |  |  | 1863 |  |  | 1610.5 |  |  | 1674.5 |  |  | 1630 |  |  | 1738.5 |  |  | 1578.5 |  |  | 1642 |  |  | 1578 |  |  | 1849 |  |  | 1586.5 |  |  | 1563 |  |  | 1660.5 |  |  | 1678.5 |  |  | 1761 |  |  | 1641.5 |  |  | 1661 |  |  | 1725 |  |  | 1692 |  |  | 1656 |  |  | 1586 |  |  | 1801.5 |  |  | 1700 |  |  | 1780 |  |  | 1653 |  |  | 1757 |  |  | 1687.5 |  |  | 1800.5 |  |  | 1684 |  |  | 1741 |  |  | 1729 |  |  | 1650 |  |  | 1778 |  |  | 1677.5 |  |  | 1721 |  |  | 1719.5 |  |  | 1820 |  |  | 1582 |  |  | 1694 |  |  | 1677 |  |  | 1706.5 |  |  | 1698 |  |  | 1697.5 |  |  | 1680 |  |  | 1818 |  |  | 1771 |  |  | 1708.5 |  |  | 1640 |  |  | 1602 |  |  | 1617 |  |  | 1827 |  |  | 1857 |  |  | 1710.5 |  |  | 1728.5 |  |  | 1659 |  |  | 1660.5 |  |  | 1625 |  |  | 1628.5 |  |  | 1715.5 |  |  | 1631.5 |  |  | 1720.5 |  |  | 1592 |  |  | 1827 |  |  | 1660 |  |  | 1649 |  |  | 1728 |  |  | 1702 |  |  | 1626.5 |  |  | 1645.5 |  |  | 1767.5 |  |  | 1761 |  |  | 1728.5 |  |  | 1720.5 |  |  | 1795.5 |  |  | 1685.5 |  |  | 1679 |  |  | 1682.5 |  |  | 1710.5 |  |  | 1768 |  |  | 1674.5 |  |  | 1810.5 |  |  | 1751.5 |  |  | 1808 |  |  | 1732.5 |  |  | 1733 |  |  | 1717 |  |  | 1698.5 |  |  | 1762.5 |  |  | 1741 |  |  | 1724 |  |  | 1590.5 |  |  | 1608.5 |  |  | 1702.5 |  |  | 1796 |  |  | 1659 |  |  | 1656 |  |  | 1749.5 |  |  | 1775.5 |  |  | 1778 |  |  | 1797.5 |  |  | 1623 |  |  | 1683 |  |  | 1740.5 |  |  | 1653.5 |  |  | 1657 |  |  | 1714.5 |  |  | 1703 |  |  | 1571.5 |  |  | 1844.5 |  |  | 1759 |  |  | 1685.5 |  |  | 1761 |  |  | 1778.5 |  |  | 1697 |  |  | 1794 |  |  | 1752 |  |  | 1654.5 |  |  | 1614.5 |  |  | 1758 |  |  | 1643 |  |  | 1682 |  |  | 1692.5 |  |  | 1721.5 |  |  | 1743 |  |  | 1696.5 |  |  | 1668 |  |  | 1620.5 |  |  | 1717.5 |  |  | 1677 |  |  | 1704 |  |  | 1668 |  |  | 1677.5 |  |  | 1678 |  |  | 1762.5 |  |  | 1760 |  |  | 1717.5 |  |  | 1893 |  |  | 1542.5 |  |  | 1705 |  |  | 1676.5 |  |  | 1675.5 |  |  | 1664 |  |  | 1667 |  |  | 1857 |  |  | 1709 |  |  | 1766.5 |  |  | 1577 |  |  | 1688.5 |  |  | 1589 |  |  | 1660 |  |  | 1648 |  |  | 1796 |  |  | 1720 |  |  | 1712 |  |  | 1736 |  |  | 1723.5 |  |  | 1621 |  |  | 1778
61 |  | 1887.5 |  |  | 1856 |  |  | 1808.5 |  |  | 1719 |  |  | 1741.5 |  |  | 1744 |  |  | 1765 |  |  | 1776 |  |  | 1680.5 |  |  | 1695 |  |  | 1723 |  |  | 1838 |  |  | 1779 |  |  | 1900 |  |  | 1659.5 |  |  | 1793.5 |  |  | 1693 |  |  | 1812 |  |  | 1856 |  |  | 1679.5 |  |  | 1776 |  |  | 1804 |  |  | 1662 |  |  | 1790 |  |  | 1757.5 |  |  | 1875 |  |  | 1736 |  |  | 1720 |  |  | 1763 |  |  | 1682 |  |  | 1730 |  |  | 1718.5 |  |  | 1860.5 |  |  | 1727.5 |  |  | 1623 |  |  | 1680.5 |  |  | 1717.5 |  |  | 1809.5 |  |  | 1772 |  |  | 1741 |  |  | 1651.5 |  |  | 1676 |  |  | 1815.5 |  |  | 1726.5 |  |  | 1778.5 |  |  | 1915.5 |  |  | 1915.5 |  |  | 1741 |  |  | 1598 |  |  | 1667.5 |  |  | 1718 |  |  | 1654.5 |  |  | 1687.5 |  |  | 1808 |  |  | 1730 |  |  | 1692 |  |  | 1663 |  |  | 1824 |  |  | 1812 |  |  | 1703.5 |  |  | 1802.5 |  |  | 1716.5 |  |  | 1628 |  |  | 1767 |  |  | 1625 |  |  | 1655.5 |  |  | 1725 |  |  | 1741.5 |  |  | 1796.5 |  |  | 1890.5 |  |  | 1731 |  |  | 1809 |  |  | 1775 |  |  | 1752.5 |  |  | 1777.5 |  |  | 1694.5 |  |  | 1809.5 |  |  | 1742.5 |  |  | 1803.5 |  |  | 1750.5 |  |  | 1712.5 |  |  | 1660 |  |  | 1772 |  |  | 1726 |  |  | 1853.5 |  |  | 1869 |  |  | 1643.5 |  |  | 1747 |  |  | 1784 |  |  | 1803.5 |  |  | 1847.5 |  |  | 1733 |  |  | 1927 |  |  | 1659.5 |  |  | 1799 |  |  | 1702.5 |  |  | 1748.5 |  |  | 1747.5 |  |  | 1721.5 |  |  | 1618.5 |  |  | 1773 |  |  | 1776 |  |  | 1645 |  |  | 1762.5 |  |  | 1708.5 |  |  | 1783.5 |  |  | 1721.5 |  |  | 1728 |  |  | 1729 |  |  | 1781.5 |  |  | 1614 |  |  | 1763.5 |  |  | 1779 |  |  | 1694 |  |  | 1639.5 |  |  | 1713 |  |  | 1747 |  |  | 1663 |  |  | 1760 |  |  | 1785.5 |  |  | 1732.5 |  |  | 1717.5 |  |  | 1844 |  |  | 1655 |  |  | 1640 |  |  | 1681 |  |  | 1699.5 |  |  | 1706 |  |  | 1742.5 |  |  | 1790 |  |  | 1698 |  |  | 1787.5 |  |  | 1670.5 |  |  | 1626 |  |  | 1710.5 |  |  | 1687 |  |  | 1751 |  |  | 1721 |  |  | 1788 |  |  | 1680 |  |  | 1652 |  |  | 1680 |  |  | 1745 |  |  | 1633 |  |  | 1646.5 |  |  | 1680 |  |  | 1593 |  |  | 1759 |  |  | 1762 |  |  | 1718 |  |  | 1659 |  |  | 1700 |  |  | 1768.5 |  |  | 1770 |  |  | 1751.5 |  |  | 1768 |  |  | 1679 |  |  | 1782.5 |  |  | 1761 |  |  | 1890.5 |  |  | 1731 |  |  | 1596 |  |  | 1749.5 |  |  | 1771 |  |  | 1801.5 |  |  | 1739 |  |  | 1670 |  |  | 1800.5 |  |  | 1755.5 |  |  | 1782 |  |  | 1699.5 |  |  | 1746.5 |  |  | 1750 |  |  | 1761 |  |  | 1943.5 |  |  | 1645.5 |  |  | 1755.5 |  |  | 1782 |  |  | 1814 |  |  | 1700 |  |  | 1816 |  |  | 1782 |  |  | 1739.5 |  |  | 1718 |  |  | 1653.5 |  |  | 1746.5 |  |  | 1757 |  |  | 1831 |  |  | 1904.5 |  |  | 1624.5 |  |  | 1725 |  |  | 1792.5 |  |  | 1656.5 |  |  | 1762 |  |  | 1609 |  |  | 1706 |  |  | 1679.5 |  |  | 1831 |  |  | 1724.5 |  |  | 1729.5 |  |  | 1652 |  |  | 1688.5 |  |  | 1705 |  |  | 1761 |  |  | 1771 |  |  | 1736 |  |  | 1577 |  |  | 1816 |  |  | 1814 |  |  | 1774 |  |  | 1810 |  |  | 1693 |  |  | 1738.5 |  |  | 1848.5 |  |  | 1701 |  |  | 1673 |  |  | 1820 |  |  | 1767.5 |  |  | 1816.5 |  |  | 1790.5 |  |  | 1739 |  |  | 1711 |  |  | 1868.5 |  |  | 1714.5 |  |  | 1624.5 |  |  | 1800 |  |  | 1866 |  |  | 1736 |  |  | 1750 |  |  | 1778 |  |  | 1724.5 |  |  | 1679.5 |  |  | 1810 |  |  | 1734 |  |  | 1693 |  |  | 1863 |  |  | 1755 |  |  | 1776.5 |  |  | 1714 |  |  | 1771 |  |  | 1744 |  |  | 1742 |  |  | 1709.5 |  |  | 1871 |  |  | 1751 |  |  | 1704 |  |  | 1843 |  |  | 1816.5 |  |  | 1818 |  |  | 1626 |  |  | 1711 |  |  | 1816.5 |  |  | 1748.5 |  |  | 1824.5 |  |  | 1854 |  |  | 1707 |  |  | 1654 |  |  | 1880 |  |  | 1739 |  |  | 1660.5 |  |  | 1813 |  |  | 1720.5 |  |  | 1785.5 |  |  | 1813.5 |  |  | 1809 |  |  | 1883.5 |  |  | 1720 |  |  | 1709 |  |  | 1718.5 |  |  | 1733.5 |  |  | 1818 |  |  | 1808.5 |  |  | 1835.5 |  |  | 1734 |  |  | 1801 |  |  | 1735.5 |  |  | 1665.5 |  |  | 1858 |  |  | 1750.5 |  |  | 1767 |  |  | 1737 |  |  | 1724.5 |  |  | 1801 |  |  | 1706 |  |  | 1766.5 |  |  | 1714 |  |  | 1845.5 |  |  | 1712 |  |  | 1906 |  |  | 1742 |  |  | 1682 |  |  | 1837.5 |  |  | 1900 |  |  | 1828.5 |  |  | 1651.5 |  |  | 1799.5 |  |  | 1811 |  |  | 1847.5 |  |  | 1915 |  |  | 1796 |  |  | 1601.5 |  |  | 1731.5 |  |  | 1767 |  |  | 1702.5 |  |  | 1794 |  |  | 1725 |  |  | 1861.5 |  |  | 1745 |  |  | 1744.5 |  |  | 1775.5 |  |  | 1768.5 |  |  | 1701 |  |  | 1658 |  |  | 1720 |  |  | 1628.5 |  |  | 1727 |  |  | 1852.5 |  |  | 1781 |  |  | 1741 |  |  | 1700 |  |  | 1751 |  |  | 1809 |  |  | 1759 |  |  | 1704 |  |  | 1863 |  |  | 1759 |  |  | 1697.5 |  |  | 1767 |  |  | 1710 |  |  | 1875.5 |  |  | 1636.5 |  |  | 1763.5 |  |  | 1792.5 |  |  | 1702 |  |  | 1863 |  |  | 1651.5 |  |  | 1780.5 |  |  | 1747.5 |  |  | 1754 |  |  | 1747 |  |  | 1700 |  |  | 1733 |  |  | 1642 |  |  | 1737 |  |  | 1767 |  |  | 1732.5 |  |  | 1780.5 |  |  | 1681 |  |  | 1739.5 |  |  | 1769.5 |  |  | 1615 |  |  | 1786 |  |  | 1682 |  |  | 1718 |  |  | 1671.5 |  |  | 1648.5 |  |  | 1785.5 |  |  | 1733 |  |  | 1691.5 |  |  | 1775 |  |  | 1725 |  |  | 1811 |  |  | 1615.5 |  |  | 1730 |  |  | 1653 |  |  | 1748.5 |  |  | 1707 |  |  | 1789.5 |  |  | 1892 |  |  | 1699.5 |  |  | 1681 |  |  | 1736.5 |  |  | 1748.5 |  |  | 1781 |  |  | 1745 |  |  | 1588 |  |  | 1729 |  |  | 1638.5 |  |  | 1716 |  |  | 1847 |  |  | 1664.5 |  |  | 1810.5 |  |  | 1702.5 |  |  | 1687 |  |  | 1759.5 |  |  | 1731.5 |  |  | 1658.5 |  |  | 1824 |  |  | 1752 |  |  | 1733.5 |  |  | 1777 |  |  | 1881 |  |  | 1738.5 |  |  | 1699 |  |  | 1830 |  |  | 1745 |  |  | 1674 |  |  | 1588.5 |  |  | 1824.5 |  |  | 1649 |  |  | 1780 |  |  | 1768 |  |  | 1722 |  |  | 1723 |  |  | 1658.5 |  |  | 1723.5 |  |  | 1772 |  |  | 1883 |  |  | 1876 |  |  | 1657.5 |  |  | 1913.5 |  |  | 1690 |  |  | 1754 |  |  | 1692 |  |  | 1747.5 |  |  | 1913.5 |  |  | 1768 |  |  | 1640 |  |  | 1773 |  |  | 1741 |  |  | 1721 |  |  | 1829 |  |  | 1688 |  |  | 1826.5 |  |  | 1650 |  |  | 1868 |  |  | 1757 |  |  | 1790.5 |  |  | 1818 |  |  | 1636 |  |  | 1570 |  |  | 1722 |  |  | 1783 |  |  | 1770 |  |  | 1776 |  |  | 1715.5 |  |  | 1692.5 |  |  | 1617.5 |  |  | 1784 |  |  | 1730 |  |  | 1788.5 |  |  | 1602 |  |  | 1655.5 |  |  | 1741.5 |  |  | 1712 |  |  | 1752 |  |  | 1751.5 |  |  | 1705 |  |  | 1767 |  |  | 1747 |  |  | 1785 |  |  | 1749 |  |  | 1693 |  |  | 1683 |  |  | 1850.5 |  |  | 1751 |  |  | 1778 |  |  | 1811 |  |  | 1694 |  |  | 1751 |  |  | 1742 |  |  | 1880 |  |  | 1752 |  |  | 1753 |  |  | 1872.5 |  |  | 1788.5 |  |  | 1731.5 |  |  | 1784.5 |  |  | 1778 |  |  | 1617 |  |  | 1849.5 |  |  | 1707 |  |  | 1739 |  |  | 1677.5 |  |  | 1835.5 |  |  | 1784 |  |  | 1724.5 |  |  | 1700.5 |  |  | 1670 |  |  | 1842 |  |  | 1724 |  |  | 1708 |  |  | 1770.5 |  |  | 1712 |  |  | 1645.5 |  |  | 1626.5 |  |  | 1663 |  |  | 1707 |  |  | 1746.5 |  |  | 1648 |  |  | 1726.5 |  |  | 1717 |  |  | 1770.5 |  |  | 1652.5 |  |  | 1649.5 |  |  | 1766.5 |  |  | 1760.5 |  |  | 1627 |  |  | 1612 |  |  | 1859.5 |  |  | 1787 |  |  | 1688 |  |  | 1738 |  |  | 1838 |  |  | 1845.5 |  |  | 1598 |  |  | 1696 |  |  | 1785 |  |  | 1734.5 |  |  | 1721 |  |  | 1682 |  |  | 1698 |  |  | 1899.5 |  |  | 1787 |  |  | 1610 |  |  | 1722 |  |  | 1831 |  |  | 1991.5 |  |  | 1776 |  |  | 1701.5 |  |  | 1716 |  |  | 1783 |  |  | 1937.5 |  |  | 1808 |  |  | 1679 |  |  | 1711.5 |  |  | 1766 |  |  | 1677 |  |  | 1752 |  |  | 1895.5 |  |  | 1739.5 |  |  | 1781 |  |  | 1687 |  |  | 1728.5 |  |  | 1782.5 |  |  | 1705 |  |  | 1769 |  |  | 1789.5 |  |  | 1863.5 |  |  | 1646.5 |  |  | 1776.5 |  |  | 1703.5 |  |  | 1934 |  |  | 1725.5 |  |  | 1771 |  |  | 1716 |  |  | 1803 |  |  | 1777 |  |  | 1775.5 |  |  | 1751 |  |  | 1658 |  |  | 1753.5 |  |  | 1733.5 |  |  | 1685 |  |  | 1772.5 |  |  | 1720.5 |  |  | 1864 |  |  | 1652 |  |  | 1726 |  |  | 1787.5 |  |  | 1746 |  |  | 1743.5 |  |  | 1782 |  |  | 1752 |  |  | 1911.5 |  |  | 1711 |  |  | 1898 |  |  | 1693 |  |  | 1804 |  |  | 1771 |  |  | 1713 |  |  | 1768 |  |  | 1738 |  |  | 1669.5 |  |  | 1737.5 |  |  | 1711 |  |  | 1789.5 |  |  | 1596.5 |  |  | 1658 |  |  | 1671 |  |  | 1824 |  |  | 1814.5 |  |  | 1670.5 |  |  | 1783 |  |  | 1857 |  |  | 1635 |  |  | 1597 |  |  | 1708 |  |  | 1739 |  |  | 1878 |  |  | 1658.5 |  |  | 1848 |  |  | 1788 |  |  | 1866 |  |  | 1723 |  |  | 1623 |  |  | 1738.5 |  |  | 1926.5 |  |  | 1594.5 |  |  | 1664 |  |  | 1664 |  |  | 1667.5 |  |  | 1868.5 |  |  | 1772.5 |  |  | 1700 |  |  | 1797.5 |  |  | 1778.5 |  |  | 1866 |  |  | 1774.5 |  |  | 1789.5 |  |  | 1729 |  |  | 1666 |  |  | 1697 |  |  | 1804 |  |  | 1722 |  |  | 1638 |  |  | 1771 |  |  | 1864 |  |  | 1689 |  |  | 1665 |  |  | 1850.5 |  |  | 1725 |  |  | 1749 |  |  | 1648 |  |  | 1710.5 |  |  | 1724 |  |  | 1762.5 |  |  | 1862 |  |  | 1789 |  |  | 1713 |  |  | 1744 |  |  | 1816.5 |  |  | 1692 |  |  | 1653 |  |  | 1824.5 |  |  | 1765 |  |  | 1718 |  |  | 1715.5 |  |  | 1736.5 |  |  | 1785 |  |  | 1652.5 |  |  | 1793 |  |  | 1741.5 |  |  | 1862 |  |  | 1805 |  |  | 1705.5 |  |  | 1826.5 |  |  | 1731 |  |  | 1817 |  |  | 1742 |  |  | 1779 |  |  | 1625 |  |  | 1764 |  |  | 1601 |  |  | 1651 |  |  | 1908.5 |  |  | 1588 |  |  | 1824.5 |  |  | 1690 |  |  | 1770.5 |  |  | 1707.5 |  |  | 1678 |  |  | 1756 |  |  | 1823.5 |  |  | 1792 |  |  | 1766 |  |  | 1813 |  |  | 1684.5 |  |  | 1802 |  |  | 1627.5 |  |  | 1586 |  |  | 1683 |  |  | 1758 |  |  | 1815 |  |  | 1862.5 |  |  | 1680 |  |  | 1711 |  |  | 1772 |  |  | 1656.5 |  |  | 1858 |  |  | 1792 |  |  | 1751 |  |  | 1759 |  |  | 1707.5 |  |  | 1680.5 |  |  | 1794 |  |  | 1854 |  |  | 1770 |  |  | 1766.5 |  |  | 1758 |  |  | 1691 |  |  | 1722 |  |  | 1888.5 |  |  | 1749.5 |  |  | 1729.5 |  |  | 1723 |  |  | 1816 |  |  | 1767 |  |  | 1660.5 |  |  | 1761 |  |  | 1758.5 |  |  | 1609 |  |  | 1701 |  |  | 1740 |  |  | 1735.5 |  |  | 1773.5 |  |  | 1765 |  |  | 1665 |  |  | 1866.5 |  |  | 1731 |  |  | 1702 |  |  | 1830.5 |  |  | 1694 |  |  | 1698 |  |  | 1737.5 |  |  | 1678 |  |  | 1753 |  |  | 1708.5 |  |  | 1907 |  |  | 1679.5 |  |  | 1792 |  |  | 1623.5 |  |  | 1781.5 |  |  | 1605 |  |  | 1846 |  |  | 1792.5 |  |  | 1762.5 |  |  | 1887 |  |  | 1752 |  |  | 1810 |  |  | 1724.5 |  |  | 1768 |  |  | 1581 |  |  | 1746 |  |  | 1867.5 |  |  | 1769.5 |  |  | 1768 |  |  | 1822 |  |  | 1666 |  |  | 1654 |  |  | 1848 |  |  | 1710 |  |  | 1680 |  |  | 1689.5 |  |  | 1855.5 |  |  | 1639.5 |  |  | 1755 |  |  | 1723.5 |  |  | 1799 |  |  | 1667 |  |  | 1782.5 |  |  | 1651.5 |  |  | 1590 |  |  | 1785 |  |  | 1719.5 |  |  | 1742 |  |  | 1790 |  |  | 1689.5 |  |  | 1744.5 |  |  | 1716 |  |  | 1710 |  |  | 1796 |  |  | 1675.5 |  |  | 1725 |  |  | 1619 |  |  | 1749 |  |  | 1795 |  |  | 1845 |  |  | 1689.5 |  |  | 1882 |  |  | 1659 |  |  | 1584 |  |  | 1848.5 |  |  | 1743 |  |  | 1711.5 |  |  | 1675.5 |  |  | 1710 |  |  | 1793 |  |  | 1726.5 |  |  | 1671.5 |  |  | 1667.5 |  |  | 1738.5 |  |  | 1773.5 |  |  | 1744 |  |  | 1711 |  |  | 1754.5 |  |  | 1736.5 |  |  | 1755 |  |  | 1702 |  |  | 1710.5 |  |  | 1875 |  |  | 1718 |  |  | 1604 |  |  | 1765.5 |  |  | 1833 |  |  | 1643.5 |  |  | 1638 |  |  | 1756.5 |  |  | 1831.5 |  |  | 1874.5 |  |  | 1788 |  |  | 1723 |  |  | 1747.5 |  |  | 1715.5 |  |  | 1769 |  |  | 1763 |  |  | 1738.5 |  |  | 1812 |  |  | 1739.5 |  |  | 1736.5 |  |  | 1817 |  |  | 1772 |  |  | 1636.5 |  |  | 1841.5 |  |  | 1740 |  |  | 1717.5 |  |  | 1725.5 |  |  | 1754 |  |  | 1798 |  |  | 1842 |  |  | 1759.5 |  |  | 1807 |  |  | 1732 |  |  | 1762 |  |  | 1724 |  |  | 1740 |  |  | 1688 |  |  | 1830.5 |  |  | 1712.5 |  |  | 1748 |  |  | 1695 |  |  | 1760 |  |  | 1769.5 |  |  | 1713 |  |  | 1860 |  |  | 1678.5 |  |  | 1751.5 |  |  | 1697 |  |  | 1667.5 |  |  | 1750 |  |  | 1612 |  |  | 1751 |  |  | 1859.5 |  |  | 1878 |  |  | 1649.5 |  |  | 1695.5 |  |  | 1669 |  |  | 1762.5 |  |  | 1604.5 |  |  | 1657 |  |  | 1625 |  |  | 1875 |  |  | 1633.5 |  |  | 1584 |  |  | 1707.5 |  |  | 1717.5 |  |  | 1785 |  |  | 1665.5 |  |  | 1687 |  |  | 1746 |  |  | 1731 |  |  | 1695 |  |  | 1607 |  |  | 1816.5 |  |  | 1729 |  |  | 1827 |  |  | 1677 |  |  | 1804 |  |  | 1726.5 |  |  | 1824.5 |  |  | 1708 |  |  | 1770 |  |  | 1776 |  |  | 1679 |  |  | 1802 |  |  | 1698.5 |  |  | 1745 |  |  | 1766.5 |  |  | 1841 |  |  | 1608 |  |  | 1733 |  |  | 1706 |  |  | 1745.5 |  |  | 1737 |  |  | 1736.5 |  |  | 1695 |  |  | 1833 |  |  | 1818 |  |  | 1734.5 |  |  | 1666 |  |  | 1617 |  |  | 1638 |  |  | 1874 |  |  | 1881 |  |  | 1736.5 |  |  | 1767.5 |  |  | 1685 |  |  | 1684.5 |  |  | 1646 |  |  | 1643.5 |  |  | 1741.5 |  |  | 1646.5 |  |  | 1741.5 |  |  | 1631 |  |  | 1851 |  |  | 1675 |  |  | 1664 |  |  | 1743 |  |  | 1741 |  |  | 1665.5 |  |  | 1684.5 |  |  | 1791.5 |  |  | 1776 |  |  | 1775.5 |  |  | 1741.5 |  |  | 1842.5 |  |  | 1700.5 |  |  | 1694 |  |  | 1703.5 |  |  | 1749.5 |  |  | 1815 |  |  | 1695.5 |  |  | 1857.5 |  |  | 1777.5 |  |  | 1837 |  |  | 1771.5 |  |  | 1759 |  |  | 1756 |  |  | 1724.5 |  |  | 1788.5 |  |  | 1780 |  |  | 1753 |  |  | 1614.5 |  |  | 1647.5 |  |  | 1741.5 |  |  | 1822 |  |  | 1698 |  |  | 1685 |  |  | 1788.5 |  |  | 1790.5 |  |  | 1799 |  |  | 1836.5 |  |  | 1647 |  |  | 1730 |  |  | 1755.5 |  |  | 1692.5 |  |  | 1681 |  |  | 1735.5 |  |  | 1742 |  |  | 1610.5 |  |  | 1870.5 |  |  | 1806 |  |  | 1724.5 |  |  | 1790 |  |  | 1807.5 |  |  | 1712 |  |  | 1820 |  |  | 1791 |  |  | 1675.5 |  |  | 1635.5 |  |  | 1805 |  |  | 1664 |  |  | 1721 |  |  | 1731.5 |  |  | 1750.5 |  |  | 1769 |  |  | 1735.5 |  |  | 1715 |  |  | 1644.5 |  |  | 1732.5 |  |  | 1716 |  |  | 1725 |  |  | 1707 |  |  | 1716.5 |  |  | 1699 |  |  | 1801.5 |  |  | 1789 |  |  | 1738.5 |  |  | 1908 |  |  | 1581.5 |  |  | 1720 |  |  | 1700.5 |  |  | 1722.5 |  |  | 1693 |  |  | 1714 |  |  | 1904 |  |  | 1735 |  |  | 1790.5 |  |  | 1601 |  |  | 1735.5 |  |  | 1615 |  |  | 1684 |  |  | 1663 |  |  | 1817 |  |  | 1759 |  |  | 1751 |  |  | 1775 |  |  | 1762.5 |  |  | 1645 |  |  | 1817
62 |  | 1913.5 |  |  | 1895 |  |  | 1832.5 |  |  | 1758 |  |  | 1770.5 |  |  | 1768 |  |  | 1791 |  |  | 1823 |  |  | 1695.5 |  |  | 1710 |  |  | 1762 |  |  | 1862 |  |  | 1818 |  |  | 1939 |  |  | 1698.5 |  |  | 1817.5 |  |  | 1719 |  |  | 1827 |  |  | 1882 |  |  | 1705.5 |  |  | 1815 |  |  | 1828 |  |  | 1686 |  |  | 1805 |  |  | 1781.5 |  |  | 1914 |  |  | 1762 |  |  | 1759 |  |  | 1810 |  |  | 1706 |  |  | 1751 |  |  | 1757.5 |  |  | 1886.5 |  |  | 1742.5 |  |  | 1649 |  |  | 1727.5 |  |  | 1743.5 |  |  | 1835.5 |  |  | 1796 |  |  | 1780 |  |  | 1698.5 |  |  | 1723 |  |  | 1839.5 |  |  | 1755.5 |  |  | 1793.5 |  |  | 1941.5 |  |  | 1962.5 |  |  | 1780 |  |  | 1613 |  |  | 1696.5 |  |  | 1757 |  |  | 1680.5 |  |  | 1708.5 |  |  | 1834 |  |  | 1745 |  |  | 1721 |  |  | 1687 |  |  | 1850 |  |  | 1851 |  |  | 1729.5 |  |  | 1817.5 |  |  | 1742.5 |  |  | 1675 |  |  | 1788 |  |  | 1651 |  |  | 1681.5 |  |  | 1746 |  |  | 1780.5 |  |  | 1817.5 |  |  | 1905.5 |  |  | 1746 |  |  | 1856 |  |  | 1822 |  |  | 1773.5 |  |  | 1824.5 |  |  | 1733.5 |  |  | 1833.5 |  |  | 1768.5 |  |  | 1824.5 |  |  | 1771.5 |  |  | 1751.5 |  |  | 1699 |  |  | 1819 |  |  | 1765 |  |  | 1868.5 |  |  | 1908 |  |  | 1672.5 |  |  | 1786 |  |  | 1810 |  |  | 1827.5 |  |  | 1886.5 |  |  | 1759 |  |  | 1948 |  |  | 1680.5 |  |  | 1820 |  |  | 1723.5 |  |  | 1774.5 |  |  | 1773.5 |  |  | 1736.5 |  |  | 1665.5 |  |  | 1812 |  |  | 1791 |  |  | 1671 |  |  | 1801.5 |  |  | 1729.5 |  |  | 1812.5 |  |  | 1768.5 |  |  | 1767 |  |  | 1755 |  |  | 1807.5 |  |  | 1653 |  |  | 1802.5 |  |  | 1803 |  |  | 1709 |  |  | 1665.5 |  |  | 1752 |  |  | 1794 |  |  | 1692 |  |  | 1799 |  |  | 1811.5 |  |  | 1771.5 |  |  | 1743.5 |  |  | 1891 |  |  | 1694 |  |  | 1669 |  |  | 1728 |  |  | 1728.5 |  |  | 1745 |  |  | 1781.5 |  |  | 1819 |  |  | 1722 |  |  | 1811.5 |  |  | 1717.5 |  |  | 1665 |  |  | 1725.5 |  |  | 1726 |  |  | 1777 |  |  | 1742 |  |  | 1835 |  |  | 1695 |  |  | 1691 |  |  | 1719 |  |  | 1774 |  |  | 1654 |  |  | 1693.5 |  |  | 1727 |  |  | 1617 |  |  | 1806 |  |  | 1777 |  |  | 1757 |  |  | 1706 |  |  | 1721 |  |  | 1797.5 |  |  | 1791 |  |  | 1790.5 |  |  | 1815 |  |  | 1694 |  |  | 1829.5 |  |  | 1800 |  |  | 1937.5 |  |  | 1746 |  |  | 1643 |  |  | 1764.5 |  |  | 1786 |  |  | 1825.5 |  |  | 1786 |  |  | 1694 |  |  | 1824.5 |  |  | 1770.5 |  |  | 1821 |  |  | 1738.5 |  |  | 1761.5 |  |  | 1771 |  |  | 1776 |  |  | 1964.5 |  |  | 1660.5 |  |  | 1779.5 |  |  | 1811 |  |  | 1840 |  |  | 1747 |  |  | 1837 |  |  | 1811 |  |  | 1786.5 |  |  | 1739 |  |  | 1668.5 |  |  | 1772.5 |  |  | 1796 |  |  | 1846 |  |  | 1951.5 |  |  | 1663.5 |  |  | 1746 |  |  | 1807.5 |  |  | 1682.5 |  |  | 1809 |  |  | 1656 |  |  | 1753 |  |  | 1700.5 |  |  | 1852 |  |  | 1745.5 |  |  | 1768.5 |  |  | 1691 |  |  | 1727.5 |  |  | 1752 |  |  | 1800 |  |  | 1797 |  |  | 1762 |  |  | 1603 |  |  | 1840 |  |  | 1853 |  |  | 1803 |  |  | 1857 |  |  | 1732 |  |  | 1764.5 |  |  | 1895.5 |  |  | 1740 |  |  | 1720 |  |  | 1835 |  |  | 1796.5 |  |  | 1863.5 |  |  | 1829.5 |  |  | 1778 |  |  | 1750 |  |  | 1907.5 |  |  | 1743.5 |  |  | 1653.5 |  |  | 1847 |  |  | 1881 |  |  | 1765 |  |  | 1779 |  |  | 1817 |  |  | 1763.5 |  |  | 1703.5 |  |  | 1849 |  |  | 1749 |  |  | 1708 |  |  | 1902 |  |  | 1784 |  |  | 1815.5 |  |  | 1761 |  |  | 1797 |  |  | 1770 |  |  | 1763 |  |  | 1730.5 |  |  | 1895 |  |  | 1766 |  |  | 1730 |  |  | 1869 |  |  | 1842.5 |  |  | 1857 |  |  | 1665 |  |  | 1750 |  |  | 1855.5 |  |  | 1769.5 |  |  | 1863.5 |  |  | 1880 |  |  | 1731 |  |  | 1675 |  |  | 1909 |  |  | 1768 |  |  | 1675.5 |  |  | 1837 |  |  | 1735.5 |  |  | 1809.5 |  |  | 1839.5 |  |  | 1830 |  |  | 1909.5 |  |  | 1735 |  |  | 1738 |  |  | 1757.5 |  |  | 1772.5 |  |  | 1842 |  |  | 1855.5 |  |  | 1882.5 |  |  | 1763 |  |  | 1825 |  |  | 1750.5 |  |  | 1680.5 |  |  | 1884 |  |  | 1776.5 |  |  | 1814 |  |  | 1776 |  |  | 1763.5 |  |  | 1830 |  |  | 1735 |  |  | 1792.5 |  |  | 1743 |  |  | 1884.5 |  |  | 1733 |  |  | 1953 |  |  | 1771 |  |  | 1697 |  |  | 1861.5 |  |  | 1947 |  |  | 1875.5 |  |  | 1666.5 |  |  | 1838.5 |  |  | 1835 |  |  | 1862.5 |  |  | 1962 |  |  | 1811 |  |  | 1627.5 |  |  | 1760.5 |  |  | 1806 |  |  | 1723.5 |  |  | 1841 |  |  | 1772 |  |  | 1900.5 |  |  | 1760 |  |  | 1765.5 |  |  | 1801.5 |  |  | 1797.5 |  |  | 1725 |  |  | 1682 |  |  | 1735 |  |  | 1675.5 |  |  | 1766 |  |  | 1891.5 |  |  | 1810 |  |  | 1770 |  |  | 1715 |  |  | 1766 |  |  | 1848 |  |  | 1798 |  |  | 1719 |  |  | 1889 |  |  | 1798 |  |  | 1721.5 |  |  | 1793 |  |  | 1736 |  |  | 1896.5 |  |  | 1662.5 |  |  | 1802.5 |  |  | 1818.5 |  |  | 1731 |  |  | 1892 |  |  | 1672.5 |  |  | 1804.5 |  |  | 1794.5 |  |  | 1775 |  |  | 1773 |  |  | 1729 |  |  | 1772 |  |  | 1666 |  |  | 1776 |  |  | 1796 |  |  | 1753.5 |  |  | 1801.5 |  |  | 1707 |  |  | 1754.5 |  |  | 1793.5 |  |  | 1641 |  |  | 1807 |  |  | 1721 |  |  | 1747 |  |  | 1697.5 |  |  | 1695.5 |  |  | 1824.5 |  |  | 1762 |  |  | 1712.5 |  |  | 1799 |  |  | 1754 |  |  | 1850 |  |  | 1654.5 |  |  | 1769 |  |  | 1677 |  |  | 1763.5 |  |  | 1733 |  |  | 1813.5 |  |  | 1939 |  |  | 1738.5 |  |  | 1702 |  |  | 1760.5 |  |  | 1787.5 |  |  | 1820 |  |  | 1769 |  |  | 1635 |  |  | 1776 |  |  | 1664.5 |  |  | 1742 |  |  | 1886 |  |  | 1685.5 |  |  | 1825.5 |  |  | 1726.5 |  |  | 1713 |  |  | 1798.5 |  |  | 1770.5 |  |  | 1697.5 |  |  | 1845 |  |  | 1781 |  |  | 1772.5 |  |  | 1803 |  |  | 1902 |  |  | 1785.5 |  |  | 1720 |  |  | 1877 |  |  | 1771 |  |  | 1700 |  |  | 1603.5 |  |  | 1848.5 |  |  | 1664 |  |  | 1819 |  |  | 1815 |  |  | 1751 |  |  | 1744 |  |  | 1697.5 |  |  | 1770.5 |  |  | 1787 |  |  | 1922 |  |  | 1902 |  |  | 1678.5 |  |  | 1928.5 |  |  | 1737 |  |  | 1801 |  |  | 1731 |  |  | 1794.5 |  |  | 1952.5 |  |  | 1783 |  |  | 1664 |  |  | 1812 |  |  | 1770 |  |  | 1750 |  |  | 1876 |  |  | 1709 |  |  | 1873.5 |  |  | 1671 |  |  | 1889 |  |  | 1804 |  |  | 1811.5 |  |  | 1844 |  |  | 1675 |  |  | 1596 |  |  | 1761 |  |  | 1804 |  |  | 1794 |  |  | 1805 |  |  | 1754.5 |  |  | 1739.5 |  |  | 1632.5 |  |  | 1805 |  |  | 1759 |  |  | 1803.5 |  |  | 1623 |  |  | 1702.5 |  |  | 1780.5 |  |  | 1759 |  |  | 1773 |  |  | 1772.5 |  |  | 1744 |  |  | 1796 |  |  | 1776 |  |  | 1824 |  |  | 1788 |  |  | 1732 |  |  | 1704 |  |  | 1871.5 |  |  | 1790 |  |  | 1793 |  |  | 1850 |  |  | 1718 |  |  | 1775 |  |  | 1768 |  |  | 1927 |  |  | 1791 |  |  | 1768 |  |  | 1893.5 |  |  | 1812.5 |  |  | 1770.5 |  |  | 1805.5 |  |  | 1825 |  |  | 1632 |  |  | 1888.5 |  |  | 1731 |  |  | 1760 |  |  | 1703.5 |  |  | 1864.5 |  |  | 1823 |  |  | 1763.5 |  |  | 1747.5 |  |  | 1699 |  |  | 1871 |  |  | 1739 |  |  | 1732 |  |  | 1791.5 |  |  | 1733 |  |  | 1692.5 |  |  | 1641.5 |  |  | 1702 |  |  | 1736 |  |  | 1793.5 |  |  | 1677 |  |  | 1765.5 |  |  | 1764 |  |  | 1817.5 |  |  | 1691.5 |  |  | 1670.5 |  |  | 1805.5 |  |  | 1775.5 |  |  | 1642 |  |  | 1638 |  |  | 1906.5 |  |  | 1811 |  |  | 1703 |  |  | 1759 |  |  | 1877 |  |  | 1866.5 |  |  | 1637 |  |  | 1717 |  |  | 1806 |  |  | 1749.5 |  |  | 1750 |  |  | 1711 |  |  | 1745 |  |  | 1938.5 |  |  | 1802 |  |  | 1631 |  |  | 1761 |  |  | 1857 |  |  | 2030.5 |  |  | 1815 |  |  | 1727.5 |  |  | 1763 |  |  | 1812 |  |  | 1958.5 |  |  | 1832 |  |  | 1694 |  |  | 1750.5 |  |  | 1787 |  |  | 1716 |  |  | 1776 |  |  | 1934.5 |  |  | 1778.5 |  |  | 1802 |  |  | 1716 |  |  | 1767.5 |  |  | 1797.5 |  |  | 1744 |  |  | 1808 |  |  | 1828.5 |  |  | 1910.5 |  |  | 1672.5 |  |  | 1815.5 |  |  | 1729.5 |  |  | 1955 |  |  | 1746.5 |  |  | 1795 |  |  | 1737 |  |  | 1829 |  |  | 1816 |  |  | 1790.5 |  |  | 1777 |  |  | 1697 |  |  | 1779.5 |  |  | 1754.5 |  |  | 1724 |  |  | 1819.5 |  |  | 1741.5 |  |  | 1879 |  |  | 1678 |  |  | 1752 |  |  | 1834.5 |  |  | 1793 |  |  | 1769.5 |  |  | 1797 |  |  | 1767 |  |  | 1932.5 |  |  | 1740 |  |  | 1924 |  |  | 1719 |  |  | 1819 |  |  | 1792 |  |  | 1760 |  |  | 1794 |  |  | 1785 |  |  | 1708.5 |  |  | 1784.5 |  |  | 1735 |  |  | 1804.5 |  |  | 1635.5 |  |  | 1697 |  |  | 1697 |  |  | 1853 |  |  | 1853.5 |  |  | 1709.5 |  |  | 1822 |  |  | 1883 |  |  | 1682 |  |  | 1621 |  |  | 1755 |  |  | 1768 |  |  | 1904 |  |  | 1682.5 |  |  | 1869 |  |  | 1809 |  |  | 1895 |  |  | 1749 |  |  | 1649 |  |  | 1753.5 |  |  | 1965.5 |  |  | 1623.5 |  |  | 1703 |  |  | 1693 |  |  | 1691.5 |  |  | 1889.5 |  |  | 1798.5 |  |  | 1715 |  |  | 1818.5 |  |  | 1793.5 |  |  | 1887 |  |  | 1803.5 |  |  | 1815.5 |  |  | 1755 |  |  | 1681 |  |  | 1736 |  |  | 1825 |  |  | 1737 |  |  | 1662 |  |  | 1818 |  |  | 1903 |  |  | 1728 |  |  | 1691 |  |  | 1889.5 |  |  | 1749 |  |  | 1778 |  |  | 1672 |  |  | 1736.5 |  |  | 1763 |  |  | 1791.5 |  |  | 1883 |  |  | 1804 |  |  | 1734 |  |  | 1773 |  |  | 1840.5 |  |  | 1731 |  |  | 1682 |  |  | 1845.5 |  |  | 1780 |  |  | 1742 |  |  | 1739.5 |  |  | 1762.5 |  |  | 1814 |  |  | 1691.5 |  |  | 1840 |  |  | 1788.5 |  |  | 1901 |  |  | 1844 |  |  | 1734.5 |  |  | 1852.5 |  |  | 1755 |  |  | 1843 |  |  | 1789 |  |  | 1800 |  |  | 1664 |  |  | 1793 |  |  | 1640 |  |  | 1672 |  |  | 1937.5 |  |  | 1635 |  |  | 1850.5 |  |  | 1729 |  |  | 1791.5 |  |  | 1746.5 |  |  | 1717 |  |  | 1782 |  |  | 1838.5 |  |  | 1807 |  |  | 1781 |  |  | 1834 |  |  | 1705.5 |  |  | 1828 |  |  | 1674.5 |  |  | 1612 |  |  | 1730 |  |  | 1779 |  |  | 1839 |  |  | 1886.5 |  |  | 1704 |  |  | 1750 |  |  | 1798 |  |  | 1677.5 |  |  | 1882 |  |  | 1821 |  |  | 1775 |  |  | 1788 |  |  | 1728.5 |  |  | 1701.5 |  |  | 1818 |  |  | 1880 |  |  | 1799 |  |  | 1805.5 |  |  | 1773 |  |  | 1712 |  |  | 1769 |  |  | 1909.5 |  |  | 1796.5 |  |  | 1768.5 |  |  | 1749 |  |  | 1831 |  |  | 1806 |  |  | 1675.5 |  |  | 1787 |  |  | 1784.5 |  |  | 1638 |  |  | 1722 |  |  | 1769 |  |  | 1750.5 |  |  | 1788.5 |  |  | 1791 |  |  | 1704 |  |  | 1881.5 |  |  | 1752 |  |  | 1731 |  |  | 1851.5 |  |  | 1709 |  |  | 1745 |  |  | 1752.5 |  |  | 1699 |  |  | 1779 |  |  | 1732.5 |  |  | 1933 |  |  | 1705.5 |  |  | 1816 |  |  | 1670.5 |  |  | 1807.5 |  |  | 1631 |  |  | 1885 |  |  | 1831.5 |  |  | 1801.5 |  |  | 1934 |  |  | 1776 |  |  | 1836 |  |  | 1745.5 |  |  | 1794 |  |  | 1628 |  |  | 1785 |  |  | 1896.5 |  |  | 1784.5 |  |  | 1792 |  |  | 1843 |  |  | 1692 |  |  | 1683 |  |  | 1874 |  |  | 1725 |  |  | 1719 |  |  | 1728.5 |  |  | 1881.5 |  |  | 1678.5 |  |  | 1802 |  |  | 1749.5 |  |  | 1828 |  |  | 1706 |  |  | 1808.5 |  |  | 1690.5 |  |  | 1629 |  |  | 1824 |  |  | 1740.5 |  |  | 1781 |  |  | 1829 |  |  | 1728.5 |  |  | 1773.5 |  |  | 1737 |  |  | 1749 |  |  | 1825 |  |  | 1690.5 |  |  | 1740 |  |  | 1645 |  |  | 1773 |  |  | 1824 |  |  | 1871 |  |  | 1728.5 |  |  | 1911 |  |  | 1698 |  |  | 1623 |  |  | 1872.5 |  |  | 1782 |  |  | 1737.5 |  |  | 1714.5 |  |  | 1725 |  |  | 1817 |  |  | 1773.5 |  |  | 1710.5 |  |  | 1691.5 |  |  | 1753.5 |  |  | 1802.5 |  |  | 1783 |  |  | 1737 |  |  | 1775.5 |  |  | 1751.5 |  |  | 1802 |  |  | 1728 |  |  | 1731.5 |  |  | 1901 |  |  | 1744 |  |  | 1630 |  |  | 1804.5 |  |  | 1862 |  |  | 1690.5 |  |  | 1667 |  |  | 1795.5 |  |  | 1870.5 |  |  | 1903.5 |  |  | 1814 |  |  | 1749 |  |  | 1786.5 |  |  | 1744.5 |  |  | 1798 |  |  | 1810 |  |  | 1777.5 |  |  | 1838 |  |  | 1763.5 |  |  | 1757.5 |  |  | 1841 |  |  | 1801 |  |  | 1651.5 |  |  | 1856.5 |  |  | 1761 |  |  | 1738.5 |  |  | 1746.5 |  |  | 1793 |  |  | 1837 |  |  | 1889 |  |  | 1774.5 |  |  | 1836 |  |  | 1756 |  |  | 1786 |  |  | 1745 |  |  | 1779 |  |  | 1717 |  |  | 1859.5 |  |  | 1751.5 |  |  | 1769 |  |  | 1719 |  |  | 1799 |  |  | 1784.5 |  |  | 1734 |  |  | 1881 |  |  | 1725.5 |  |  | 1790.5 |  |  | 1736 |  |  | 1696.5 |  |  | 1797 |  |  | 1659 |  |  | 1766 |  |  | 1898.5 |  |  | 1904 |  |  | 1673.5 |  |  | 1724.5 |  |  | 1690 |  |  | 1791.5 |  |  | 1625.5 |  |  | 1678 |  |  | 1640 |  |  | 1890 |  |  | 1672.5 |  |  | 1599 |  |  | 1728.5 |  |  | 1756.5 |  |  | 1814 |  |  | 1689.5 |  |  | 1716 |  |  | 1793 |  |  | 1755 |  |  | 1716 |  |  | 1628 |  |  | 1842.5 |  |  | 1750 |  |  | 1866 |  |  | 1724 |  |  | 1843 |  |  | 1755.5 |  |  | 1839.5 |  |  | 1723 |  |  | 1799 |  |  | 1802 |  |  | 1726 |  |  | 1841 |  |  | 1713.5 |  |  | 1784 |  |  | 1787.5 |  |  | 1867 |  |  | 1647 |  |  | 1759 |  |  | 1745 |  |  | 1769.5 |  |  | 1763 |  |  | 1783.5 |  |  | 1734 |  |  | 1880 |  |  | 1833 |  |  | 1758.5 |  |  | 1695 |  |  | 1641 |  |  | 1677 |  |  | 1913 |  |  | 1920 |  |  | 1775.5 |  |  | 1796.5 |  |  | 1700 |  |  | 1705.5 |  |  | 1693 |  |  | 1664.5 |  |  | 1770.5 |  |  | 1670.5 |  |  | 1767.5 |  |  | 1670 |  |  | 1890 |  |  | 1704 |  |  | 1685 |  |  | 1782 |  |  | 1780 |  |  | 1686.5 |  |  | 1699.5 |  |  | 1838.5 |  |  | 1802 |  |  | 1801.5 |  |  | 1756.5 |  |  | 1857.5 |  |  | 1729.5 |  |  | 1741 |  |  | 1729.5 |  |  | 1788.5 |  |  | 1841 |  |  | 1724.5 |  |  | 1896.5 |  |  | 1806.5 |  |  | 1884 |  |  | 1786.5 |  |  | 1806 |  |  | 1782 |  |  | 1750.5 |  |  | 1803.5 |  |  | 1827 |  |  | 1774 |  |  | 1653.5 |  |  | 1673.5 |  |  | 1756.5 |  |  | 1846 |  |  | 1727 |  |  | 1724 |  |  | 1812.5 |  |  | 1829.5 |  |  | 1825 |  |  | 1883.5 |  |  | 1686 |  |  | 1769 |  |  | 1794.5 |  |  | 1739.5 |  |  | 1720 |  |  | 1761.5 |  |  | 1781 |  |  | 1649.5 |  |  | 1896.5 |  |  | 1845 |  |  | 1745.5 |  |  | 1816 |  |  | 1846.5 |  |  | 1759 |  |  | 1846 |  |  | 1815 |  |  | 1699.5 |  |  | 1659.5 |  |  | 1820 |  |  | 1693 |  |  | 1742 |  |  | 1770.5 |  |  | 1774.5 |  |  | 1816 |  |  | 1782.5 |  |  | 1754 |  |  | 1670.5 |  |  | 1758.5 |  |  | 1740 |  |  | 1751 |  |  | 1736 |  |  | 1742.5 |  |  | 1723 |  |  | 1827.5 |  |  | 1836 |  |  | 1785.5 |  |  | 1947 |  |  | 1607.5 |  |  | 1741 |  |  | 1721.5 |  |  | 1746.5 |  |  | 1740 |  |  | 1743 |  |  | 1925 |  |  | 1764 |  |  | 1814.5 |  |  | 1630 |  |  | 1756.5 |  |  | 1639 |  |  | 1723 |  |  | 1684 |  |  | 1841 |  |  | 1788 |  |  | 1777 |  |  | 1814 |  |  | 1786.5 |  |  | 1692 |  |  | 1864
63 |  | 1952.5 |  |  | 1921 |  |  | 1858.5 |  |  | 1779 |  |  | 1799.5 |  |  | 1807 |  |  | 1815 |  |  | 1862 |  |  | 1710.5 |  |  | 1739 |  |  | 1788 |  |  | 1909 |  |  | 1865 |  |  | 1968 |  |  | 1722.5 |  |  | 1832.5 |  |  | 1748 |  |  | 1842 |  |  | 1921 |  |  | 1729.5 |  |  | 1839 |  |  | 1867 |  |  | 1712 |  |  | 1831 |  |  | 1796.5 |  |  | 1929 |  |  | 1801 |  |  | 1788 |  |  | 1834 |  |  | 1721 |  |  | 1798 |  |  | 1778.5 |  |  | 1925.5 |  |  | 1781.5 |  |  | 1678 |  |  | 1756.5 |  |  | 1764.5 |  |  | 1874.5 |  |  | 1843 |  |  | 1827 |  |  | 1727.5 |  |  | 1770 |  |  | 1878.5 |  |  | 1770.5 |  |  | 1819.5 |  |  | 1980.5 |  |  | 1983.5 |  |  | 1819 |  |  | 1637 |  |  | 1722.5 |  |  | 1781 |  |  | 1719.5 |  |  | 1723.5 |  |  | 1855 |  |  | 1771 |  |  | 1750 |  |  | 1734 |  |  | 1874 |  |  | 1872 |  |  | 1768.5 |  |  | 1843.5 |  |  | 1781.5 |  |  | 1714 |  |  | 1812 |  |  | 1675 |  |  | 1705.5 |  |  | 1775 |  |  | 1795.5 |  |  | 1832.5 |  |  | 1952.5 |  |  | 1772 |  |  | 1903 |  |  | 1846 |  |  | 1812.5 |  |  | 1839.5 |  |  | 1780.5 |  |  | 1854.5 |  |  | 1797.5 |  |  | 1839.5 |  |  | 1797.5 |  |  | 1790.5 |  |  | 1720 |  |  | 1866 |  |  | 1804 |  |  | 1889.5 |  |  | 1932 |  |  | 1711.5 |  |  | 1833 |  |  | 1849 |  |  | 1874.5 |  |  | 1933.5 |  |  | 1785 |  |  | 1977 |  |  | 1719.5 |  |  | 1867 |  |  | 1738.5 |  |  | 1803.5 |  |  | 1788.5 |  |  | 1760.5 |  |  | 1691.5 |  |  | 1836 |  |  | 1838 |  |  | 1697 |  |  | 1816.5 |  |  | 1744.5 |  |  | 1836.5 |  |  | 1789.5 |  |  | 1814 |  |  | 1770 |  |  | 1828.5 |  |  | 1682 |  |  | 1826.5 |  |  | 1824 |  |  | 1735 |  |  | 1704.5 |  |  | 1781 |  |  | 1818 |  |  | 1721 |  |  | 1838 |  |  | 1832.5 |  |  | 1800.5 |  |  | 1772.5 |  |  | 1915 |  |  | 1733 |  |  | 1708 |  |  | 1767 |  |  | 1775.5 |  |  | 1771 |  |  | 1820.5 |  |  | 1848 |  |  | 1746 |  |  | 1826.5 |  |  | 1743.5 |  |  | 1689 |  |  | 1749.5 |  |  | 1773 |  |  | 1801 |  |  | 1757 |  |  | 1874 |  |  | 1716 |  |  | 1712 |  |  | 1743 |  |  | 1803 |  |  | 1701 |  |  | 1740.5 |  |  | 1774 |  |  | 1656 |  |  | 1821 |  |  | 1798 |  |  | 1804 |  |  | 1721 |  |  | 1760 |  |  | 1818.5 |  |  | 1838 |  |  | 1819.5 |  |  | 1854 |  |  | 1741 |  |  | 1850.5 |  |  | 1815 |  |  | 1963.5 |  |  | 1767 |  |  | 1664 |  |  | 1811.5 |  |  | 1825 |  |  | 1864.5 |  |  | 1833 |  |  | 1723 |  |  | 1863.5 |  |  | 1796.5 |  |  | 1836 |  |  | 1777.5 |  |  | 1800.5 |  |  | 1786 |  |  | 1815 |  |  | 1993.5 |  |  | 1675.5 |  |  | 1800.5 |  |  | 1850 |  |  | 1879 |  |  | 1762 |  |  | 1884 |  |  | 1850 |  |  | 1801.5 |  |  | 1763 |  |  | 1692.5 |  |  | 1801.5 |  |  | 1817 |  |  | 1885 |  |  | 1998.5 |  |  | 1689.5 |  |  | 1772 |  |  | 1831.5 |  |  | 1721.5 |  |  | 1833 |  |  | 1703 |  |  | 1774 |  |  | 1726.5 |  |  | 1891 |  |  | 1771.5 |  |  | 1792.5 |  |  | 1712 |  |  | 1766.5 |  |  | 1791 |  |  | 1839 |  |  | 1823 |  |  | 1809 |  |  | 1627 |  |  | 1879 |  |  | 1877 |  |  | 1842 |  |  | 1878 |  |  | 1753 |  |  | 1779.5 |  |  | 1924.5 |  |  | 1769 |  |  | 1749 |  |  | 1882 |  |  | 1825.5 |  |  | 1889.5 |  |  | 1850.5 |  |  | 1793 |  |  | 1776 |  |  | 1954.5 |  |  | 1782.5 |  |  | 1700.5 |  |  | 1886 |  |  | 1905 |  |  | 1804 |  |  | 1818 |  |  | 1856 |  |  | 1784.5 |  |  | 1742.5 |  |  | 1870 |  |  | 1773 |  |  | 1732 |  |  | 1941 |  |  | 1813 |  |  | 1836.5 |  |  | 1800 |  |  | 1844 |  |  | 1796 |  |  | 1784 |  |  | 1769.5 |  |  | 1934 |  |  | 1805 |  |  | 1754 |  |  | 1908 |  |  | 1881.5 |  |  | 1883 |  |  | 1680 |  |  | 1771 |  |  | 1902.5 |  |  | 1795.5 |  |  | 1887.5 |  |  | 1906 |  |  | 1755 |  |  | 1714 |  |  | 1930 |  |  | 1792 |  |  | 1699.5 |  |  | 1876 |  |  | 1782.5 |  |  | 1835.5 |  |  | 1854.5 |  |  | 1859 |  |  | 1924.5 |  |  | 1750 |  |  | 1762 |  |  | 1772.5 |  |  | 1819.5 |  |  | 1881 |  |  | 1876.5 |  |  | 1921.5 |  |  | 1787 |  |  | 1840 |  |  | 1779.5 |  |  | 1695.5 |  |  | 1923 |  |  | 1823.5 |  |  | 1853 |  |  | 1815 |  |  | 1784.5 |  |  | 1877 |  |  | 1759 |  |  | 1818.5 |  |  | 1767 |  |  | 1931.5 |  |  | 1754 |  |  | 1982 |  |  | 1797 |  |  | 1726 |  |  | 1900.5 |  |  | 1968 |  |  | 1901.5 |  |  | 1705.5 |  |  | 1877.5 |  |  | 1850 |  |  | 1901.5 |  |  | 1991 |  |  | 1858 |  |  | 1648.5 |  |  | 1786.5 |  |  | 1832 |  |  | 1770.5 |  |  | 1888 |  |  | 1801 |  |  | 1947.5 |  |  | 1784 |  |  | 1786.5 |  |  | 1827.5 |  |  | 1844.5 |  |  | 1751 |  |  | 1703 |  |  | 1761 |  |  | 1699.5 |  |  | 1805 |  |  | 1930.5 |  |  | 1825 |  |  | 1799 |  |  | 1744 |  |  | 1790 |  |  | 1863 |  |  | 1845 |  |  | 1748 |  |  | 1918 |  |  | 1824 |  |  | 1750.5 |  |  | 1840 |  |  | 1751 |  |  | 1917.5 |  |  | 1709.5 |  |  | 1841.5 |  |  | 1844.5 |  |  | 1778 |  |  | 1931 |  |  | 1687.5 |  |  | 1851.5 |  |  | 1823.5 |  |  | 1801 |  |  | 1794 |  |  | 1744 |  |  | 1811 |  |  | 1681 |  |  | 1800 |  |  | 1820 |  |  | 1768.5 |  |  | 1848.5 |  |  | 1728 |  |  | 1775.5 |  |  | 1840.5 |  |  | 1688 |  |  | 1854 |  |  | 1747 |  |  | 1776 |  |  | 1726.5 |  |  | 1724.5 |  |  | 1871.5 |  |  | 1801 |  |  | 1759.5 |  |  | 1828 |  |  | 1769 |  |  | 1871 |  |  | 1693.5 |  |  | 1784 |  |  | 1698 |  |  | 1792.5 |  |  | 1780 |  |  | 1842.5 |  |  | 1968 |  |  | 1762.5 |  |  | 1728 |  |  | 1799.5 |  |  | 1816.5 |  |  | 1859 |  |  | 1784 |  |  | 1650 |  |  | 1791 |  |  | 1688.5 |  |  | 1766 |  |  | 1933 |  |  | 1706.5 |  |  | 1872.5 |  |  | 1750.5 |  |  | 1752 |  |  | 1819.5 |  |  | 1791.5 |  |  | 1736.5 |  |  | 1866 |  |  | 1828 |  |  | 1793.5 |  |  | 1842 |  |  | 1923 |  |  | 1824.5 |  |  | 1744 |  |  | 1916 |  |  | 1818 |  |  | 1715 |  |  | 1642.5 |  |  | 1877.5 |  |  | 1693 |  |  | 1858 |  |  | 1839 |  |  | 1777 |  |  | 1783 |  |  | 1736.5 |  |  | 1785.5 |  |  | 1834 |  |  | 1948 |  |  | 1926 |  |  | 1717.5 |  |  | 1957.5 |  |  | 1766 |  |  | 1816 |  |  | 1752 |  |  | 1833.5 |  |  | 1991.5 |  |  | 1822 |  |  | 1685 |  |  | 1841 |  |  | 1799 |  |  | 1789 |  |  | 1915 |  |  | 1724 |  |  | 1912.5 |  |  | 1710 |  |  | 1913 |  |  | 1833 |  |  | 1832.5 |  |  | 1865 |  |  | 1722 |  |  | 1625 |  |  | 1808 |  |  | 1825 |  |  | 1815 |  |  | 1834 |  |  | 1769.5 |  |  | 1760.5 |  |  | 1656.5 |  |  | 1852 |  |  | 1783 |  |  | 1842.5 |  |  | 1652 |  |  | 1717.5 |  |  | 1827.5 |  |  | 1788 |  |  | 1820 |  |  | 1811.5 |  |  | 1783 |  |  | 1817 |  |  | 1800 |  |  | 1839 |  |  | 1812 |  |  | 1758 |  |  | 1743 |  |  | 1900.5 |  |  | 1829 |  |  | 1832 |  |  | 1874 |  |  | 1757 |  |  | 1796 |  |  | 1792 |  |  | 1974 |  |  | 1815 |  |  | 1789 |  |  | 1917.5 |  |  | 1851.5 |  |  | 1791.5 |  |  | 1852.5 |  |  | 1849 |  |  | 1679 |  |  | 1927.5 |  |  | 1770 |  |  | 1786 |  |  | 1742.5 |  |  | 1911.5 |  |  | 1862 |  |  | 1792.5 |  |  | 1768.5 |  |  | 1725 |  |  | 1910 |  |  | 1768 |  |  | 1747 |  |  | 1812.5 |  |  | 1780 |  |  | 1716.5 |  |  | 1665.5 |  |  | 1731 |  |  | 1757 |  |  | 1840.5 |  |  | 1724 |  |  | 1804.5 |  |  | 1803 |  |  | 1856.5 |  |  | 1715.5 |  |  | 1685.5 |  |  | 1829.5 |  |  | 1801.5 |  |  | 1668 |  |  | 1685 |  |  | 1927.5 |  |  | 1858 |  |  | 1724 |  |  | 1780 |  |  | 1901 |  |  | 1895.5 |  |  | 1652 |  |  | 1732 |  |  | 1832 |  |  | 1764.5 |  |  | 1789 |  |  | 1750 |  |  | 1771 |  |  | 1959.5 |  |  | 1831 |  |  | 1646 |  |  | 1808 |  |  | 1881 |  |  | 2054.5 |  |  | 1854 |  |  | 1748.5 |  |  | 1778 |  |  | 1836 |  |  | 1997.5 |  |  | 1879 |  |  | 1733 |  |  | 1779.5 |  |  | 1808 |  |  | 1763 |  |  | 1802 |  |  | 1963.5 |  |  | 1825.5 |  |  | 1831 |  |  | 1731 |  |  | 1788.5 |  |  | 1812.5 |  |  | 1768 |  |  | 1847 |  |  | 1854.5 |  |  | 1957.5 |  |  | 1698.5 |  |  | 1844.5 |  |  | 1768.5 |  |  | 1976 |  |  | 1772.5 |  |  | 1834 |  |  | 1758 |  |  | 1858 |  |  | 1855 |  |  | 1819.5 |  |  | 1803 |  |  | 1721 |  |  | 1826.5 |  |  | 1793.5 |  |  | 1748 |  |  | 1845.5 |  |  | 1767.5 |  |  | 1900 |  |  | 1704 |  |  | 1791 |  |  | 1849.5 |  |  | 1832 |  |  | 1808.5 |  |  | 1844 |  |  | 1791 |  |  | 1947.5 |  |  | 1764 |  |  | 1939 |  |  | 1758 |  |  | 1840 |  |  | 1839 |  |  | 1789 |  |  | 1833 |  |  | 1832 |  |  | 1729.5 |  |  | 1813.5 |  |  | 1761 |  |  | 1843.5 |  |  | 1664.5 |  |  | 1744 |  |  | 1726 |  |  | 1879 |  |  | 1900.5 |  |  | 1735.5 |  |  | 1837 |  |  | 1922 |  |  | 1703 |  |  | 1668 |  |  | 1776 |  |  | 1794 |  |  | 1930 |  |  | 1721.5 |  |  | 1884 |  |  | 1833 |  |  | 1916 |  |  | 1788 |  |  | 1678 |  |  | 1792.5 |  |  | 2004.5 |  |  | 1644.5 |  |  | 1718 |  |  | 1732 |  |  | 1717.5 |  |  | 1913.5 |  |  | 1845.5 |  |  | 1744 |  |  | 1844.5 |  |  | 1814.5 |  |  | 1913 |  |  | 1842.5 |  |  | 1854.5 |  |  | 1779 |  |  | 1707 |  |  | 1775 |  |  | 1864 |  |  | 1766 |  |  | 1677 |  |  | 1833 |  |  | 1918 |  |  | 1743 |  |  | 1738 |  |  | 1913.5 |  |  | 1796 |  |  | 1825 |  |  | 1696 |  |  | 1783.5 |  |  | 1789 |  |  | 1817.5 |  |  | 1922 |  |  | 1825 |  |  | 1773 |  |  | 1812 |  |  | 1879.5 |  |  | 1760 |  |  | 1721 |  |  | 1884.5 |  |  | 1819 |  |  | 1781 |  |  | 1754.5 |  |  | 1783.5 |  |  | 1853 |  |  | 1730.5 |  |  | 1866 |  |  | 1809.5 |  |  | 1940 |  |  | 1859 |  |  | 1749.5 |  |  | 1891.5 |  |  | 1776 |  |  | 1882 |  |  | 1828 |  |  | 1826 |  |  | 1679 |  |  | 1832 |  |  | 1664 |  |  | 1698 |  |  | 1958.5 |  |  | 1661 |  |  | 1865.5 |  |  | 1768 |  |  | 1830.5 |  |  | 1785.5 |  |  | 1764 |  |  | 1829 |  |  | 1877.5 |  |  | 1831 |  |  | 1820 |  |  | 1860 |  |  | 1752.5 |  |  | 1857 |  |  | 1689.5 |  |  | 1651 |  |  | 1751 |  |  | 1818 |  |  | 1865 |  |  | 1925.5 |  |  | 1725 |  |  | 1776 |  |  | 1837 |  |  | 1698.5 |  |  | 1921 |  |  | 1868 |  |  | 1796 |  |  | 1817 |  |  | 1775.5 |  |  | 1730.5 |  |  | 1842 |  |  | 1906 |  |  | 1838 |  |  | 1826.5 |  |  | 1788 |  |  | 1741 |  |  | 1798 |  |  | 1948.5 |  |  | 1825.5 |  |  | 1807.5 |  |  | 1788 |  |  | 1846 |  |  | 1830 |  |  | 1722.5 |  |  | 1826 |  |  | 1799.5 |  |  | 1685 |  |  | 1748 |  |  | 1808 |  |  | 1789.5 |  |  | 1835.5 |  |  | 1812 |  |  | 1725 |  |  | 1910.5 |  |  | 1778 |  |  | 1760 |  |  | 1875.5 |  |  | 1733 |  |  | 1792 |  |  | 1791.5 |  |  | 1738 |  |  | 1794 |  |  | 1761.5 |  |  | 1954 |  |  | 1734.5 |  |  | 1831 |  |  | 1696.5 |  |  | 1854.5 |  |  | 1670 |  |  | 1906 |  |  | 1870.5 |  |  | 1840.5 |  |  | 1958 |  |  | 1815 |  |  | 1862 |  |  | 1784.5 |  |  | 1823 |  |  | 1667 |  |  | 1800 |  |  | 1925.5 |  |  | 1799.5 |  |  | 1839 |  |  | 1869 |  |  | 1721 |  |  | 1709 |  |  | 1903 |  |  | 1746 |  |  | 1758 |  |  | 1749.5 |  |  | 1928.5 |  |  | 1717.5 |  |  | 1817 |  |  | 1770.5 |  |  | 1857 |  |  | 1745 |  |  | 1823.5 |  |  | 1711.5 |  |  | 1668 |  |  | 1839 |  |  | 1787.5 |  |  | 1810 |  |  | 1850 |  |  | 1754.5 |  |  | 1812.5 |  |  | 1784 |  |  | 1764 |  |  | 1849 |  |  | 1714.5 |  |  | 1755 |  |  | 1669 |  |  | 1799 |  |  | 1848 |  |  | 1897 |  |  | 1743.5 |  |  | 1940 |  |  | 1727 |  |  | 1670 |  |  | 1896.5 |  |  | 1797 |  |  | 1761.5 |  |  | 1735.5 |  |  | 1749 |  |  | 1846 |  |  | 1788.5 |  |  | 1757.5 |  |  | 1717.5 |  |  | 1777.5 |  |  | 1817.5 |  |  | 1830 |  |  | 1776 |  |  | 1801.5 |  |  | 1772.5 |  |  | 1817 |  |  | 1775 |  |  | 1770.5 |  |  | 1948 |  |  | 1770 |  |  | 1651 |  |  | 1851.5 |  |  | 1877 |  |  | 1716.5 |  |  | 1682 |  |  | 1834.5 |  |  | 1909.5 |  |  | 1942.5 |  |  | 1835 |  |  | 1788 |  |  | 1801.5 |  |  | 1791.5 |  |  | 1822 |  |  | 1849 |  |  | 1803.5 |  |  | 1885 |  |  | 1792.5 |  |  | 1778.5 |  |  | 1888 |  |  | 1840 |  |  | 1675.5 |  |  | 1877.5 |  |  | 1776 |  |  | 1767.5 |  |  | 1785.5 |  |  | 1832 |  |  | 1876 |  |  | 1918 |  |  | 1821.5 |  |  | 1875 |  |  | 1780 |  |  | 1810 |  |  | 1766 |  |  | 1800 |  |  | 1738 |  |  | 1888.5 |  |  | 1775.5 |  |  | 1784 |  |  | 1740 |  |  | 1846 |  |  | 1810.5 |  |  | 1760 |  |  | 1928 |  |  | 1749.5 |  |  | 1811.5 |  |  | 1760 |  |  | 1725.5 |  |  | 1823 |  |  | 1698 |  |  | 1781 |  |  | 1937.5 |  |  | 1933 |  |  | 1712.5 |  |  | 1739.5 |  |  | 1714 |  |  | 1815.5 |  |  | 1646.5 |  |  | 1704 |  |  | 1655 |  |  | 1919 |  |  | 1696.5 |  |  | 1628 |  |  | 1767.5 |  |  | 1785.5 |  |  | 1861 |  |  | 1728.5 |  |  | 1731 |  |  | 1832 |  |  | 1770 |  |  | 1742 |  |  | 1667 |  |  | 1881.5 |  |  | 1789 |  |  | 1895 |  |  | 1753 |  |  | 1882 |  |  | 1781.5 |  |  | 1854.5 |  |  | 1762 |  |  | 1838 |  |  | 1831 |  |  | 1773 |  |  | 1870 |  |  | 1728.5 |  |  | 1823 |  |  | 1816.5 |  |  | 1906 |  |  | 1673 |  |  | 1783 |  |  | 1769 |  |  | 1795.5 |  |  | 1789 |  |  | 1830.5 |  |  | 1749 |  |  | 1919 |  |  | 1872 |  |  | 1773.5 |  |  | 1734 |  |  | 1670 |  |  | 1716 |  |  | 1952 |  |  | 1959 |  |  | 1796.5 |  |  | 1835.5 |  |  | 1747 |  |  | 1729.5 |  |  | 1740 |  |  | 1690.5 |  |  | 1785.5 |  |  | 1717.5 |  |  | 1788.5 |  |  | 1709 |  |  | 1919 |  |  | 1719 |  |  | 1732 |  |  | 1821 |  |  | 1827 |  |  | 1725.5 |  |  | 1714.5 |  |  | 1867.5 |  |  | 1849 |  |  | 1840.5 |  |  | 1785.5 |  |  | 1872.5 |  |  | 1753.5 |  |  | 1788 |  |  | 1776.5 |  |  | 1812.5 |  |  | 1862 |  |  | 1763.5 |  |  | 1935.5 |  |  | 1832.5 |  |  | 1931 |  |  | 1812.5 |  |  | 1845 |  |  | 1797 |  |  | 1776.5 |  |  | 1850.5 |  |  | 1866 |  |  | 1813 |  |  | 1677.5 |  |  | 1688.5 |  |  | 1795.5 |  |  | 1867 |  |  | 1766 |  |  | 1745 |  |  | 1859.5 |  |  | 1844.5 |  |  | 1864 |  |  | 1907.5 |  |  | 1710 |  |  | 1808 |  |  | 1841.5 |  |  | 1765.5 |  |  | 1767 |  |  | 1800.5 |  |  | 1805 |  |  | 1688.5 |  |  | 1925.5 |  |  | 1871 |  |  | 1771.5 |  |  | 1855 |  |  | 1861.5 |  |  | 1780 |  |  | 1872 |  |  | 1839 |  |  | 1723.5 |  |  | 1674.5 |  |  | 1859 |  |  | 1722 |  |  | 1757 |  |  | 1785.5 |  |  | 1813.5 |  |  | 1855 |  |  | 1821.5 |  |  | 1801 |  |  | 1696.5 |  |  | 1805.5 |  |  | 1755 |  |  | 1790 |  |  | 1783 |  |  | 1789.5 |  |  | 1770 |  |  | 1866.5 |  |  | 1862 |  |  | 1809.5 |  |  | 1973 |  |  | 1622.5 |  |  | 1767 |  |  | 1768.5 |  |  | 1785.5 |  |  | 1769 |  |  | 1782 |  |  | 1972 |  |  | 1790 |  |  | 1861.5 |  |  | 1677 |  |  | 1785.5 |  |  | 1678 |  |  | 1762 |  |  | 1710 |  |  | 1880 |  |  | 1827 |  |  | 1798 |  |  | 1861 |  |  | 1810.5 |  |  | 1739 |  |  | 1885
64 |  | 1991.5 |  |  | 1960 |  |  | 1882.5 |  |  | 1818 |  |  | 1823.5 |  |  | 1846 |  |  | 1839 |  |  | 1886 |  |  | 1725.5 |  |  | 1768 |  |  | 1809 |  |  | 1933 |  |  | 1904 |  |  | 2015 |  |  | 1761.5 |  |  | 1871.5 |  |  | 1777 |  |  | 1868 |  |  | 1947 |  |  | 1753.5 |  |  | 1878 |  |  | 1882 |  |  | 1751 |  |  | 1846 |  |  | 1820.5 |  |  | 1968 |  |  | 1840 |  |  | 1827 |  |  | 1873 |  |  | 1760 |  |  | 1845 |  |  | 1802.5 |  |  | 1954.5 |  |  | 1820.5 |  |  | 1725 |  |  | 1771.5 |  |  | 1779.5 |  |  | 1889.5 |  |  | 1890 |  |  | 1842 |  |  | 1748.5 |  |  | 1785 |  |  | 1904.5 |  |  | 1796.5 |  |  | 1866.5 |  |  | 2001.5 |  |  | 2012.5 |  |  | 1834 |  |  | 1684 |  |  | 1761.5 |  |  | 1820 |  |  | 1740.5 |  |  | 1752.5 |  |  | 1870 |  |  | 1786 |  |  | 1789 |  |  | 1755 |  |  | 1895 |  |  | 1898 |  |  | 1797.5 |  |  | 1867.5 |  |  | 1802.5 |  |  | 1743 |  |  | 1841 |  |  | 1704 |  |  | 1720.5 |  |  | 1814 |  |  | 1842.5 |  |  | 1871.5 |  |  | 1991.5 |  |  | 1801 |  |  | 1950 |  |  | 1870 |  |  | 1833.5 |  |  | 1878.5 |  |  | 1804.5 |  |  | 1883.5 |  |  | 1836.5 |  |  | 1865.5 |  |  | 1826.5 |  |  | 1814.5 |  |  | 1735 |  |  | 1913 |  |  | 1828 |  |  | 1915.5 |  |  | 1958 |  |  | 1750.5 |  |  | 1848 |  |  | 1878 |  |  | 1913.5 |  |  | 1962.5 |  |  | 1800 |  |  | 2003 |  |  | 1766.5 |  |  | 1891 |  |  | 1753.5 |  |  | 1842.5 |  |  | 1827.5 |  |  | 1781.5 |  |  | 1730.5 |  |  | 1875 |  |  | 1859 |  |  | 1718 |  |  | 1831.5 |  |  | 1765.5 |  |  | 1875.5 |  |  | 1815.5 |  |  | 1838 |  |  | 1794 |  |  | 1867.5 |  |  | 1706 |  |  | 1847.5 |  |  | 1848 |  |  | 1750 |  |  | 1743.5 |  |  | 1805 |  |  | 1857 |  |  | 1736 |  |  | 1877 |  |  | 1856.5 |  |  | 1847.5 |  |  | 1787.5 |  |  | 1944 |  |  | 1762 |  |  | 1737 |  |  | 1791 |  |  | 1814.5 |  |  | 1810 |  |  | 1844.5 |  |  | 1872 |  |  | 1767 |  |  | 1852.5 |  |  | 1769.5 |  |  | 1728 |  |  | 1788.5 |  |  | 1799 |  |  | 1848 |  |  | 1786 |  |  | 1898 |  |  | 1740 |  |  | 1759 |  |  | 1767 |  |  | 1829 |  |  | 1740 |  |  | 1761.5 |  |  | 1803 |  |  | 1685 |  |  | 1847 |  |  | 1837 |  |  | 1819 |  |  | 1760 |  |  | 1786 |  |  | 1847.5 |  |  | 1859 |  |  | 1834.5 |  |  | 1893 |  |  | 1780 |  |  | 1874.5 |  |  | 1854 |  |  | 1987.5 |  |  | 1796 |  |  | 1685 |  |  | 1835.5 |  |  | 1872 |  |  | 1911.5 |  |  | 1848 |  |  | 1749 |  |  | 1884.5 |  |  | 1822.5 |  |  | 1860 |  |  | 1824.5 |  |  | 1829.5 |  |  | 1801 |  |  | 1844 |  |  | 2008.5 |  |  | 1704.5 |  |  | 1839.5 |  |  | 1897 |  |  | 1903 |  |  | 1801 |  |  | 1923 |  |  | 1897 |  |  | 1840.5 |  |  | 1810 |  |  | 1721.5 |  |  | 1848.5 |  |  | 1846 |  |  | 1911 |  |  | 2024.5 |  |  | 1715.5 |  |  | 1819 |  |  | 1878.5 |  |  | 1747.5 |  |  | 1880 |  |  | 1727 |  |  | 1803 |  |  | 1765.5 |  |  | 1930 |  |  | 1797.5 |  |  | 1831.5 |  |  | 1733 |  |  | 1781.5 |  |  | 1830 |  |  | 1854 |  |  | 1844 |  |  | 1833 |  |  | 1674 |  |  | 1926 |  |  | 1924 |  |  | 1866 |  |  | 1925 |  |  | 1777 |  |  | 1794.5 |  |  | 1945.5 |  |  | 1790 |  |  | 1775 |  |  | 1929 |  |  | 1864.5 |  |  | 1910.5 |  |  | 1897.5 |  |  | 1817 |  |  | 1815 |  |  | 1969.5 |  |  | 1829.5 |  |  | 1739.5 |  |  | 1925 |  |  | 1934 |  |  | 1825 |  |  | 1842 |  |  | 1895 |  |  | 1808.5 |  |  | 1766.5 |  |  | 1891 |  |  | 1812 |  |  | 1771 |  |  | 1967 |  |  | 1839 |  |  | 1883.5 |  |  | 1847 |  |  | 1883 |  |  | 1843 |  |  | 1799 |  |  | 1808.5 |  |  | 1958 |  |  | 1844 |  |  | 1778 |  |  | 1929 |  |  | 1907.5 |  |  | 1909 |  |  | 1709 |  |  | 1797 |  |  | 1931.5 |  |  | 1816.5 |  |  | 1916.5 |  |  | 1953 |  |  | 1794 |  |  | 1753 |  |  | 1951 |  |  | 1816 |  |  | 1725.5 |  |  | 1915 |  |  | 1821.5 |  |  | 1861.5 |  |  | 1869.5 |  |  | 1888 |  |  | 1948.5 |  |  | 1779 |  |  | 1783 |  |  | 1798.5 |  |  | 1858.5 |  |  | 1907 |  |  | 1900.5 |  |  | 1968.5 |  |  | 1826 |  |  | 1879 |  |  | 1800.5 |  |  | 1742.5 |  |  | 1962 |  |  | 1852.5 |  |  | 1892 |  |  | 1830 |  |  | 1805.5 |  |  | 1892 |  |  | 1780 |  |  | 1842.5 |  |  | 1793 |  |  | 1978.5 |  |  | 1780 |  |  | 2021 |  |  | 1836 |  |  | 1750 |  |  | 1921.5 |  |  | 1992 |  |  | 1916.5 |  |  | 1726.5 |  |  | 1906.5 |  |  | 1874 |  |  | 1930.5 |  |  | 2038 |  |  | 1873 |  |  | 1674.5 |  |  | 1815.5 |  |  | 1871 |  |  | 1796.5 |  |  | 1903 |  |  | 1827 |  |  | 1962.5 |  |  | 1799 |  |  | 1801.5 |  |  | 1851.5 |  |  | 1870.5 |  |  | 1798 |  |  | 1724 |  |  | 1782 |  |  | 1738.5 |  |  | 1844 |  |  | 1977.5 |  |  | 1872 |  |  | 1825 |  |  | 1768 |  |  | 1829 |  |  | 1902 |  |  | 1871 |  |  | 1787 |  |  | 1947 |  |  | 1863 |  |  | 1779.5 |  |  | 1879 |  |  | 1790 |  |  | 1941.5 |  |  | 1748.5 |  |  | 1856.5 |  |  | 1865.5 |  |  | 1804 |  |  | 1955 |  |  | 1713.5 |  |  | 1898.5 |  |  | 1849.5 |  |  | 1827 |  |  | 1833 |  |  | 1783 |  |  | 1832 |  |  | 1707 |  |  | 1829 |  |  | 1844 |  |  | 1797.5 |  |  | 1877.5 |  |  | 1767 |  |  | 1801.5 |  |  | 1866.5 |  |  | 1727 |  |  | 1880 |  |  | 1786 |  |  | 1802 |  |  | 1741.5 |  |  | 1763.5 |  |  | 1892.5 |  |  | 1827 |  |  | 1780.5 |  |  | 1857 |  |  | 1790 |  |  | 1918 |  |  | 1732.5 |  |  | 1805 |  |  | 1724 |  |  | 1807.5 |  |  | 1809 |  |  | 1866.5 |  |  | 1983 |  |  | 1809.5 |  |  | 1767 |  |  | 1838.5 |  |  | 1840.5 |  |  | 1874 |  |  | 1799 |  |  | 1674 |  |  | 1838 |  |  | 1717.5 |  |  | 1781 |  |  | 1948 |  |  | 1721.5 |  |  | 1919.5 |  |  | 1797.5 |  |  | 1773 |  |  | 1866.5 |  |  | 1817.5 |  |  | 1757.5 |  |  | 1913 |  |  | 1849 |  |  | 1840.5 |  |  | 1868 |  |  | 1962 |  |  | 1848.5 |  |  | 1791 |  |  | 1937 |  |  | 1857 |  |  | 1741 |  |  | 1657.5 |  |  | 1916.5 |  |  | 1714 |  |  | 1897 |  |  | 1865 |  |  | 1801 |  |  | 1812 |  |  | 1775.5 |  |  | 1809.5 |  |  | 1863 |  |  | 1963 |  |  | 1950 |  |  | 1746.5 |  |  | 1972.5 |  |  | 1792 |  |  | 1831 |  |  | 1767 |  |  | 1862.5 |  |  | 2020.5 |  |  | 1861 |  |  | 1724 |  |  | 1865 |  |  | 1838 |  |  | 1828 |  |  | 1936 |  |  | 1745 |  |  | 1951.5 |  |  | 1757 |  |  | 1934 |  |  | 1859 |  |  | 1858.5 |  |  | 1891 |  |  | 1751 |  |  | 1640 |  |  | 1837 |  |  | 1849 |  |  | 1854 |  |  | 1881 |  |  | 1790.5 |  |  | 1799.5 |  |  | 1682.5 |  |  | 1891 |  |  | 1809 |  |  | 1863.5 |  |  | 1691 |  |  | 1732.5 |  |  | 1856.5 |  |  | 1803 |  |  | 1841 |  |  | 1826.5 |  |  | 1822 |  |  | 1856 |  |  | 1826 |  |  | 1854 |  |  | 1836 |  |  | 1784 |  |  | 1790 |  |  | 1915.5 |  |  | 1853 |  |  | 1871 |  |  | 1913 |  |  | 1781 |  |  | 1817 |  |  | 1831 |  |  | 2013 |  |  | 1854 |  |  | 1836 |  |  | 1932.5 |  |  | 1866.5 |  |  | 1806.5 |  |  | 1881.5 |  |  | 1870 |  |  | 1694 |  |  | 1948.5 |  |  | 1796 |  |  | 1825 |  |  | 1766.5 |  |  | 1950.5 |  |  | 1901 |  |  | 1839.5 |  |  | 1797.5 |  |  | 1751 |  |  | 1939 |  |  | 1807 |  |  | 1768 |  |  | 1841.5 |  |  | 1827 |  |  | 1763.5 |  |  | 1704.5 |  |  | 1770 |  |  | 1781 |  |  | 1864.5 |  |  | 1750 |  |  | 1843.5 |  |  | 1827 |  |  | 1871.5 |  |  | 1730.5 |  |  | 1706.5 |  |  | 1868.5 |  |  | 1840.5 |  |  | 1692 |  |  | 1711 |  |  | 1942.5 |  |  | 1873 |  |  | 1763 |  |  | 1827 |  |  | 1948 |  |  | 1910.5 |  |  | 1681 |  |  | 1761 |  |  | 1861 |  |  | 1803.5 |  |  | 1836 |  |  | 1771 |  |  | 1810 |  |  | 1988.5 |  |  | 1857 |  |  | 1672 |  |  | 1832 |  |  | 1928 |  |  | 2078.5 |  |  | 1893 |  |  | 1763.5 |  |  | 1807 |  |  | 1865 |  |  | 2026.5 |  |  | 1908 |  |  | 1780 |  |  | 1794.5 |  |  | 1855 |  |  | 1787 |  |  | 1817 |  |  | 2010.5 |  |  | 1864.5 |  |  | 1860 |  |  | 1755 |  |  | 1812.5 |  |  | 1841.5 |  |  | 1789 |  |  | 1894 |  |  | 1875.5 |  |  | 1986.5 |  |  | 1745.5 |  |  | 1883.5 |  |  | 1807.5 |  |  | 2015 |  |  | 1801.5 |  |  | 1858 |  |  | 1805 |  |  | 1884 |  |  | 1894 |  |  | 1848.5 |  |  | 1827 |  |  | 1742 |  |  | 1865.5 |  |  | 1822.5 |  |  | 1763 |  |  | 1892.5 |  |  | 1806.5 |  |  | 1939 |  |  | 1733 |  |  | 1806 |  |  | 1864.5 |  |  | 1858 |  |  | 1855.5 |  |  | 1883 |  |  | 1817 |  |  | 1986.5 |  |  | 1803 |  |  | 1954 |  |  | 1787 |  |  | 1887 |  |  | 1860 |  |  | 1828 |  |  | 1848 |  |  | 1858 |  |  | 1755.5 |  |  | 1837.5 |  |  | 1782 |  |  | 1869.5 |  |  | 1688.5 |  |  | 1768 |  |  | 1765 |  |  | 1918 |  |  | 1926.5 |  |  | 1756.5 |  |  | 1863 |  |  | 1937 |  |  | 1742 |  |  | 1689 |  |  | 1815 |  |  | 1809 |  |  | 1951 |  |  | 1742.5 |  |  | 1923 |  |  | 1872 |  |  | 1931 |  |  | 1809 |  |  | 1702 |  |  | 1821.5 |  |  | 2025.5 |  |  | 1670.5 |  |  | 1739 |  |  | 1753 |  |  | 1756.5 |  |  | 1952.5 |  |  | 1892.5 |  |  | 1783 |  |  | 1891.5 |  |  | 1838.5 |  |  | 1960 |  |  | 1871.5 |  |  | 1893.5 |  |  | 1803 |  |  | 1754 |  |  | 1790 |  |  | 1903 |  |  | 1787 |  |  | 1698 |  |  | 1854 |  |  | 1944 |  |  | 1769 |  |  | 1764 |  |  | 1960.5 |  |  | 1843 |  |  | 1849 |  |  | 1722 |  |  | 1822.5 |  |  | 1818 |  |  | 1856.5 |  |  | 1943 |  |  | 1854 |  |  | 1797 |  |  | 1859 |  |  | 1905.5 |  |  | 1789 |  |  | 1736 |  |  | 1923.5 |  |  | 1858 |  |  | 1805 |  |  | 1775.5 |  |  | 1812.5 |  |  | 1868 |  |  | 1754.5 |  |  | 1913 |  |  | 1838.5 |  |  | 1964 |  |  | 1874 |  |  | 1764.5 |  |  | 1920.5 |  |  | 1815 |  |  | 1906 |  |  | 1854 |  |  | 1855 |  |  | 1718 |  |  | 1858 |  |  | 1690 |  |  | 1737 |  |  | 2005.5 |  |  | 1690 |  |  | 1904.5 |  |  | 1807 |  |  | 1877.5 |  |  | 1814.5 |  |  | 1779 |  |  | 1868 |  |  | 1898.5 |  |  | 1855 |  |  | 1859 |  |  | 1884 |  |  | 1791.5 |  |  | 1881 |  |  | 1713.5 |  |  | 1666 |  |  | 1775 |  |  | 1847 |  |  | 1891 |  |  | 1964.5 |  |  | 1754 |  |  | 1823 |  |  | 1861 |  |  | 1727.5 |  |  | 1950 |  |  | 1897 |  |  | 1835 |  |  | 1832 |  |  | 1796.5 |  |  | 1759.5 |  |  | 1868 |  |  | 1930 |  |  | 1853 |  |  | 1873.5 |  |  | 1827 |  |  | 1780 |  |  | 1822 |  |  | 1963.5 |  |  | 1840.5 |  |  | 1833.5 |  |  | 1835 |  |  | 1893 |  |  | 1869 |  |  | 1761.5 |  |  | 1852 |  |  | 1814.5 |  |  | 1714 |  |  | 1763 |  |  | 1823 |  |  | 1810.5 |  |  | 1850.5 |  |  | 1841 |  |  | 1754 |  |  | 1949.5 |  |  | 1793 |  |  | 1807 |  |  | 1914.5 |  |  | 1748 |  |  | 1821 |  |  | 1838.5 |  |  | 1762 |  |  | 1833 |  |  | 1790.5 |  |  | 1993 |  |  | 1755.5 |  |  | 1852 |  |  | 1722.5 |  |  | 1901.5 |  |  | 1709 |  |  | 1930 |  |  | 1917.5 |  |  | 1864.5 |  |  | 1973 |  |  | 1844 |  |  | 1877 |  |  | 1823.5 |  |  | 1838 |  |  | 1682 |  |  | 1826 |  |  | 1949.5 |  |  | 1828.5 |  |  | 1865 |  |  | 1908 |  |  | 1760 |  |  | 1735 |  |  | 1942 |  |  | 1761 |  |  | 1773 |  |  | 1788.5 |  |  | 1967.5 |  |  | 1764.5 |  |  | 1838 |  |  | 1785.5 |  |  | 1886 |  |  | 1766 |  |  | 1844.5 |  |  | 1750.5 |  |  | 1715 |  |  | 1868 |  |  | 1813.5 |  |  | 1831 |  |  | 1874 |  |  | 1775.5 |  |  | 1841.5 |  |  | 1805 |  |  | 1793 |  |  | 1888 |  |  | 1743.5 |  |  | 1779 |  |  | 1695 |  |  | 1814 |  |  | 1887 |  |  | 1926 |  |  | 1764.5 |  |  | 1955 |  |  | 1748 |  |  | 1717 |  |  | 1943.5 |  |  | 1823 |  |  | 1790.5 |  |  | 1764.5 |  |  | 1788 |  |  | 1885 |  |  | 1812.5 |  |  | 1786.5 |  |  | 1756.5 |  |  | 1792.5 |  |  | 1846.5 |  |  | 1845 |  |  | 1815 |  |  | 1830.5 |  |  | 1798.5 |  |  | 1846 |  |  | 1799 |  |  | 1809.5 |  |  | 1963 |  |  | 1809 |  |  | 1666 |  |  | 1890.5 |  |  | 1916 |  |  | 1763.5 |  |  | 1697 |  |  | 1855.5 |  |  | 1924.5 |  |  | 1963.5 |  |  | 1859 |  |  | 1827 |  |  | 1822.5 |  |  | 1820.5 |  |  | 1851 |  |  | 1888 |  |  | 1842.5 |  |  | 1909 |  |  | 1831.5 |  |  | 1799.5 |  |  | 1927 |  |  | 1861 |  |  | 1696.5 |  |  | 1903.5 |  |  | 1815 |  |  | 1814.5 |  |  | 1811.5 |  |  | 1879 |  |  | 1891 |  |  | 1944 |  |  | 1842.5 |  |  | 1922 |  |  | 1809 |  |  | 1849 |  |  | 1805 |  |  | 1821 |  |  | 1777 |  |  | 1912.5 |  |  | 1796.5 |  |  | 1831 |  |  | 1769 |  |  | 1885 |  |  | 1834.5 |  |  | 1786 |  |  | 1952 |  |  | 1770.5 |  |  | 1850.5 |  |  | 1799 |  |  | 1751.5 |  |  | 1862 |  |  | 1713 |  |  | 1805 |  |  | 1966.5 |  |  | 1962 |  |  | 1738.5 |  |  | 1765.5 |  |  | 1729 |  |  | 1854.5 |  |  | 1667.5 |  |  | 1730 |  |  | 1676 |  |  | 1948 |  |  | 1720.5 |  |  | 1654 |  |  | 1806.5 |  |  | 1814.5 |  |  | 1908 |  |  | 1752.5 |  |  | 1778 |  |  | 1861 |  |  | 1817 |  |  | 1763 |  |  | 1706 |  |  | 1902.5 |  |  | 1810 |  |  | 1921 |  |  | 1792 |  |  | 1921 |  |  | 1828.5 |  |  | 1893.5 |  |  | 1809 |  |  | 1864 |  |  | 1870 |  |  | 1820 |  |  | 1899 |  |  | 1752.5 |  |  | 1847 |  |  | 1863.5 |  |  | 1945 |  |  | 1697 |  |  | 1812 |  |  | 1795 |  |  | 1834.5 |  |  | 1818 |  |  | 1869.5 |  |  | 1778 |  |  | 1966 |  |  | 1911 |  |  | 1797.5 |  |  | 1749 |  |  | 1717 |  |  | 1755 |  |  | 1991 |  |  | 1988 |  |  | 1811.5 |  |  | 1874.5 |  |  | 1776 |  |  | 1768.5 |  |  | 1766 |  |  | 1719.5 |  |  | 1800.5 |  |  | 1738.5 |  |  | 1803.5 |  |  | 1724 |  |  | 1966 |  |  | 1740 |  |  | 1747 |  |  | 1836 |  |  | 1874 |  |  | 1772.5 |  |  | 1753.5 |  |  | 1882.5 |  |  | 1864 |  |  | 1887.5 |  |  | 1806.5 |  |  | 1893.5 |  |  | 1782.5 |  |  | 1803 |  |  | 1802.5 |  |  | 1851.5 |  |  | 1909 |  |  | 1778.5 |  |  | 1959.5 |  |  | 1871.5 |  |  | 1960 |  |  | 1836.5 |  |  | 1869 |  |  | 1836 |  |  | 1815.5 |  |  | 1889.5 |  |  | 1913 |  |  | 1842 |  |  | 1698.5 |  |  | 1714.5 |  |  | 1842.5 |  |  | 1914 |  |  | 1813 |  |  | 1784 |  |  | 1883.5 |  |  | 1873.5 |  |  | 1888 |  |  | 1933.5 |  |  | 1757 |  |  | 1837 |  |  | 1867.5 |  |  | 1791.5 |  |  | 1793 |  |  | 1847.5 |  |  | 1829 |  |  | 1727.5 |  |  | 1946.5 |  |  | 1895 |  |  | 1786.5 |  |  | 1894 |  |  | 1876.5 |  |  | 1809 |  |  | 1893 |  |  | 1878 |  |  | 1762.5 |  |  | 1713.5 |  |  | 1883 |  |  | 1746 |  |  | 1772 |  |  | 1806.5 |  |  | 1834.5 |  |  | 1894 |  |  | 1860.5 |  |  | 1822 |  |  | 1720.5 |  |  | 1826.5 |  |  | 1770 |  |  | 1829 |  |  | 1798 |  |  | 1804.5 |  |  | 1809 |  |  | 1895.5 |  |  | 1886 |  |  | 1833.5 |  |  | 2020 |  |  | 1669.5 |  |  | 1782 |  |  | 1815.5 |  |  | 1824.5 |  |  | 1798 |  |  | 1821 |  |  | 2011 |  |  | 1814 |  |  | 1900.5 |  |  | 1701 |  |  | 1811.5 |  |  | 1693 |  |  | 1788 |  |  | 1757 |  |  | 1927 |  |  | 1848 |  |  | 1813 |  |  | 1900 |  |  | 1825.5 |  |  | 1754 |  |  | 1924
65 |  | 2030.5 |  |  | 1981 |  |  | 1921.5 |  |  | 1857 |  |  | 1847.5 |  |  | 1885 |  |  | 1863 |  |  | 1925 |  |  | 1740.5 |  |  | 1797 |  |  | 1824 |  |  | 1957 |  |  | 1951 |  |  | 2054 |  |  | 1800.5 |  |  | 1897.5 |  |  | 1816 |  |  | 1907 |  |  | 1986 |  |  | 1792.5 |  |  | 1904 |  |  | 1911 |  |  | 1777 |  |  | 1885 |  |  | 1835.5 |  |  | 1992 |  |  | 1866 |  |  | 1856 |  |  | 1920 |  |  | 1781 |  |  | 1884 |  |  | 1841.5 |  |  | 1969.5 |  |  | 1867.5 |  |  | 1764 |  |  | 1800.5 |  |  | 1803.5 |  |  | 1910.5 |  |  | 1919 |  |  | 1871 |  |  | 1769.5 |  |  | 1806 |  |  | 1928.5 |  |  | 1835.5 |  |  | 1905.5 |  |  | 2040.5 |  |  | 2059.5 |  |  | 1858 |  |  | 1731 |  |  | 1800.5 |  |  | 1844 |  |  | 1766.5 |  |  | 1767.5 |  |  | 1885 |  |  | 1815 |  |  | 1818 |  |  | 1779 |  |  | 1942 |  |  | 1937 |  |  | 1823.5 |  |  | 1888.5 |  |  | 1831.5 |  |  | 1782 |  |  | 1862 |  |  | 1743 |  |  | 1759.5 |  |  | 1835 |  |  | 1866.5 |  |  | 1910.5 |  |  | 2012.5 |  |  | 1825 |  |  | 1979 |  |  | 1909 |  |  | 1872.5 |  |  | 1917.5 |  |  | 1833.5 |  |  | 1904.5 |  |  | 1851.5 |  |  | 1894.5 |  |  | 1852.5 |  |  | 1829.5 |  |  | 1774 |  |  | 1937 |  |  | 1843 |  |  | 1930.5 |  |  | 1984 |  |  | 1797.5 |  |  | 1863 |  |  | 1904 |  |  | 1952.5 |  |  | 1983.5 |  |  | 1847 |  |  | 2024 |  |  | 1787.5 |  |  | 1920 |  |  | 1792.5 |  |  | 1863.5 |  |  | 1874.5 |  |  | 1805.5 |  |  | 1745.5 |  |  | 1899 |  |  | 1874 |  |  | 1733 |  |  | 1857.5 |  |  | 1794.5 |  |  | 1914.5 |  |  | 1830.5 |  |  | 1862 |  |  | 1815 |  |  | 1882.5 |  |  | 1721 |  |  | 1871.5 |  |  | 1887 |  |  | 1797 |  |  | 1758.5 |  |  | 1829 |  |  | 1896 |  |  | 1760 |  |  | 1903 |  |  | 1877.5 |  |  | 1873.5 |  |  | 1813.5 |  |  | 1965 |  |  | 1801 |  |  | 1758 |  |  | 1830 |  |  | 1829.5 |  |  | 1831 |  |  | 1891.5 |  |  | 1901 |  |  | 1788 |  |  | 1876.5 |  |  | 1808.5 |  |  | 1767 |  |  | 1803.5 |  |  | 1838 |  |  | 1887 |  |  | 1815 |  |  | 1919 |  |  | 1764 |  |  | 1783 |  |  | 1806 |  |  | 1876 |  |  | 1766 |  |  | 1787.5 |  |  | 1842 |  |  | 1709 |  |  | 1886 |  |  | 1858 |  |  | 1848 |  |  | 1784 |  |  | 1815 |  |  | 1886.5 |  |  | 1874 |  |  | 1881.5 |  |  | 1914 |  |  | 1804 |  |  | 1913.5 |  |  | 1883 |  |  | 2011.5 |  |  | 1811 |  |  | 1700 |  |  | 1850.5 |  |  | 1893 |  |  | 1937.5 |  |  | 1887 |  |  | 1770 |  |  | 1923.5 |  |  | 1846.5 |  |  | 1875 |  |  | 1853.5 |  |  | 1868.5 |  |  | 1840 |  |  | 1883 |  |  | 2023.5 |  |  | 1751.5 |  |  | 1886.5 |  |  | 1926 |  |  | 1950 |  |  | 1840 |  |  | 1947 |  |  | 1912 |  |  | 1879.5 |  |  | 1831 |  |  | 1768.5 |  |  | 1887.5 |  |  | 1893 |  |  | 1958 |  |  | 2048.5 |  |  | 1736.5 |  |  | 1840 |  |  | 1902.5 |  |  | 1762.5 |  |  | 1909 |  |  | 1742 |  |  | 1827 |  |  | 1804.5 |  |  | 1954 |  |  | 1836.5 |  |  | 1846.5 |  |  | 1780 |  |  | 1807.5 |  |  | 1851 |  |  | 1893 |  |  | 1868 |  |  | 1862 |  |  | 1689 |  |  | 1965 |  |  | 1963 |  |  | 1905 |  |  | 1964 |  |  | 1792 |  |  | 1833.5 |  |  | 1984.5 |  |  | 1819 |  |  | 1814 |  |  | 1958 |  |  | 1911.5 |  |  | 1931.5 |  |  | 1912.5 |  |  | 1843 |  |  | 1854 |  |  | 1995.5 |  |  | 1876.5 |  |  | 1765.5 |  |  | 1951 |  |  | 1973 |  |  | 1849 |  |  | 1881 |  |  | 1924 |  |  | 1834.5 |  |  | 1781.5 |  |  | 1930 |  |  | 1851 |  |  | 1818 |  |  | 1988 |  |  | 1878 |  |  | 1904.5 |  |  | 1873 |  |  | 1898 |  |  | 1867 |  |  | 1823 |  |  | 1847.5 |  |  | 1987 |  |  | 1883 |  |  | 1817 |  |  | 1968 |  |  | 1946.5 |  |  | 1933 |  |  | 1748 |  |  | 1818 |  |  | 1955.5 |  |  | 1845.5 |  |  | 1955.5 |  |  | 1968 |  |  | 1818 |  |  | 1782 |  |  | 1998 |  |  | 1863 |  |  | 1764.5 |  |  | 1939 |  |  | 1860.5 |  |  | 1887.5 |  |  | 1908.5 |  |  | 1903 |  |  | 1995.5 |  |  | 1794 |  |  | 1809 |  |  | 1837.5 |  |  | 1879.5 |  |  | 1931 |  |  | 1929.5 |  |  | 1992.5 |  |  | 1865 |  |  | 1918 |  |  | 1824.5 |  |  | 1781.5 |  |  | 1986 |  |  | 1891.5 |  |  | 1913 |  |  | 1854 |  |  | 1826.5 |  |  | 1931 |  |  | 1804 |  |  | 1868.5 |  |  | 1822 |  |  | 2025.5 |  |  | 1819 |  |  | 2060 |  |  | 1851 |  |  | 1797 |  |  | 1945.5 |  |  | 2013 |  |  | 1955.5 |  |  | 1755.5 |  |  | 1953.5 |  |  | 1921 |  |  | 1951.5 |  |  | 2067 |  |  | 1920 |  |  | 1703.5 |  |  | 1862.5 |  |  | 1900 |  |  | 1825.5 |  |  | 1924 |  |  | 1842 |  |  | 2001.5 |  |  | 1828 |  |  | 1825.5 |  |  | 1875.5 |  |  | 1894.5 |  |  | 1822 |  |  | 1745 |  |  | 1797 |  |  | 1785.5 |  |  | 1859 |  |  | 2016.5 |  |  | 1893 |  |  | 1849 |  |  | 1807 |  |  | 1868 |  |  | 1931 |  |  | 1900 |  |  | 1811 |  |  | 1994 |  |  | 1887 |  |  | 1818.5 |  |  | 1894 |  |  | 1816 |  |  | 1967.5 |  |  | 1772.5 |  |  | 1903.5 |  |  | 1912.5 |  |  | 1828 |  |  | 1979 |  |  | 1737.5 |  |  | 1945.5 |  |  | 1888.5 |  |  | 1853 |  |  | 1854 |  |  | 1804 |  |  | 1856 |  |  | 1746 |  |  | 1844 |  |  | 1873 |  |  | 1823.5 |  |  | 1898.5 |  |  | 1814 |  |  | 1822.5 |  |  | 1881.5 |  |  | 1753 |  |  | 1909 |  |  | 1833 |  |  | 1823 |  |  | 1756.5 |  |  | 1778.5 |  |  | 1939.5 |  |  | 1842 |  |  | 1804.5 |  |  | 1896 |  |  | 1837 |  |  | 1957 |  |  | 1771.5 |  |  | 1831 |  |  | 1771 |  |  | 1833.5 |  |  | 1848 |  |  | 1892.5 |  |  | 2030 |  |  | 1830.5 |  |  | 1796 |  |  | 1877.5 |  |  | 1861.5 |  |  | 1913 |  |  | 1838 |  |  | 1700 |  |  | 1877 |  |  | 1738.5 |  |  | 1807 |  |  | 1995 |  |  | 1747.5 |  |  | 1934.5 |  |  | 1812.5 |  |  | 1812 |  |  | 1895.5 |  |  | 1856.5 |  |  | 1781.5 |  |  | 1952 |  |  | 1873 |  |  | 1879.5 |  |  | 1897 |  |  | 1988 |  |  | 1887.5 |  |  | 1838 |  |  | 1958 |  |  | 1896 |  |  | 1756 |  |  | 1686.5 |  |  | 1955.5 |  |  | 1740 |  |  | 1912 |  |  | 1894 |  |  | 1816 |  |  | 1827 |  |  | 1814.5 |  |  | 1833.5 |  |  | 1889 |  |  | 1984 |  |  | 1979 |  |  | 1785.5 |  |  | 2019.5 |  |  | 1821 |  |  | 1870 |  |  | 1791 |  |  | 1901.5 |  |  | 2059.5 |  |  | 1890 |  |  | 1753 |  |  | 1891 |  |  | 1867 |  |  | 1867 |  |  | 1983 |  |  | 1769 |  |  | 1990.5 |  |  | 1796 |  |  | 1973 |  |  | 1898 |  |  | 1905.5 |  |  | 1917 |  |  | 1766 |  |  | 1666 |  |  | 1876 |  |  | 1888 |  |  | 1893 |  |  | 1928 |  |  | 1816.5 |  |  | 1828.5 |  |  | 1697.5 |  |  | 1930 |  |  | 1848 |  |  | 1878.5 |  |  | 1730 |  |  | 1771.5 |  |  | 1880.5 |  |  | 1832 |  |  | 1880 |  |  | 1865.5 |  |  | 1851 |  |  | 1885 |  |  | 1865 |  |  | 1901 |  |  | 1875 |  |  | 1810 |  |  | 1819 |  |  | 1941.5 |  |  | 1868 |  |  | 1918 |  |  | 1928 |  |  | 1828 |  |  | 1856 |  |  | 1870 |  |  | 2052 |  |  | 1878 |  |  | 1857 |  |  | 1958.5 |  |  | 1892.5 |  |  | 1853.5 |  |  | 1920.5 |  |  | 1894 |  |  | 1709 |  |  | 1969.5 |  |  | 1811 |  |  | 1840 |  |  | 1790.5 |  |  | 1989.5 |  |  | 1925 |  |  | 1863.5 |  |  | 1844.5 |  |  | 1777 |  |  | 1978 |  |  | 1822 |  |  | 1815 |  |  | 1880.5 |  |  | 1866 |  |  | 1789.5 |  |  | 1728.5 |  |  | 1796 |  |  | 1802 |  |  | 1911.5 |  |  | 1797 |  |  | 1872.5 |  |  | 1874 |  |  | 1918.5 |  |  | 1759.5 |  |  | 1753.5 |  |  | 1892.5 |  |  | 1879.5 |  |  | 1731 |  |  | 1740 |  |  | 1963.5 |  |  | 1888 |  |  | 1792 |  |  | 1856 |  |  | 1972 |  |  | 1949.5 |  |  | 1728 |  |  | 1776 |  |  | 1900 |  |  | 1818.5 |  |  | 1883 |  |  | 1797 |  |  | 1839 |  |  | 2027.5 |  |  | 1896 |  |  | 1687 |  |  | 1858 |  |  | 1957 |  |  | 2117.5 |  |  | 1932 |  |  | 1792.5 |  |  | 1836 |  |  | 1886 |  |  | 2073.5 |  |  | 1937 |  |  | 1806 |  |  | 1841.5 |  |  | 1884 |  |  | 1834 |  |  | 1864 |  |  | 2039.5 |  |  | 1911.5 |  |  | 1875 |  |  | 1779 |  |  | 1851.5 |  |  | 1880.5 |  |  | 1828 |  |  | 1923 |  |  | 1922.5 |  |  | 2001.5 |  |  | 1766.5 |  |  | 1922.5 |  |  | 1833.5 |  |  | 2044 |  |  | 1816.5 |  |  | 1879 |  |  | 1852 |  |  | 1905 |  |  | 1941 |  |  | 1877.5 |  |  | 1866 |  |  | 1766 |  |  | 1886.5 |  |  | 1869.5 |  |  | 1778 |  |  | 1916.5 |  |  | 1835.5 |  |  | 1965 |  |  | 1762 |  |  | 1845 |  |  | 1911.5 |  |  | 1897 |  |  | 1902.5 |  |  | 1904 |  |  | 1841 |  |  | 2033.5 |  |  | 1842 |  |  | 1980 |  |  | 1813 |  |  | 1913 |  |  | 1875 |  |  | 1843 |  |  | 1895 |  |  | 1879 |  |  | 1781.5 |  |  | 1858.5 |  |  | 1806 |  |  | 1898.5 |  |  | 1709.5 |  |  | 1783 |  |  | 1794 |  |  | 1942 |  |  | 1947.5 |  |  | 1777.5 |  |  | 1910 |  |  | 1952 |  |  | 1763 |  |  | 1736 |  |  | 1830 |  |  | 1835 |  |  | 1990 |  |  | 1781.5 |  |  | 1962 |  |  | 1887 |  |  | 1946 |  |  | 1830 |  |  | 1741 |  |  | 1842.5 |  |  | 2040.5 |  |  | 1699.5 |  |  | 1765 |  |  | 1792 |  |  | 1771.5 |  |  | 1976.5 |  |  | 1916.5 |  |  | 1804 |  |  | 1930.5 |  |  | 1885.5 |  |  | 1999 |  |  | 1892.5 |  |  | 1917.5 |  |  | 1827 |  |  | 1775 |  |  | 1837 |  |  | 1942 |  |  | 1826 |  |  | 1719 |  |  | 1869 |  |  | 1983 |  |  | 1784 |  |  | 1790 |  |  | 1981.5 |  |  | 1872 |  |  | 1864 |  |  | 1769 |  |  | 1843.5 |  |  | 1844 |  |  | 1885.5 |  |  | 1964 |  |  | 1901 |  |  | 1812 |  |  | 1898 |  |  | 1944.5 |  |  | 1810 |  |  | 1775 |  |  | 1938.5 |  |  | 1887 |  |  | 1844 |  |  | 1814.5 |  |  | 1859.5 |  |  | 1894 |  |  | 1775.5 |  |  | 1939 |  |  | 1859.5 |  |  | 1988 |  |  | 1898 |  |  | 1788.5 |  |  | 1941.5 |  |  | 1839 |  |  | 1945 |  |  | 1880 |  |  | 1879 |  |  | 1742 |  |  | 1897 |  |  | 1729 |  |  | 1752 |  |  | 2029.5 |  |  | 1729 |  |  | 1919.5 |  |  | 1846 |  |  | 1892.5 |  |  | 1843.5 |  |  | 1803 |  |  | 1897 |  |  | 1937.5 |  |  | 1876 |  |  | 1898 |  |  | 1923 |  |  | 1815.5 |  |  | 1907 |  |  | 1752.5 |  |  | 1695 |  |  | 1814 |  |  | 1894 |  |  | 1906 |  |  | 1990.5 |  |  | 1778 |  |  | 1847 |  |  | 1876 |  |  | 1742.5 |  |  | 1976 |  |  | 1936 |  |  | 1864 |  |  | 1858 |  |  | 1825.5 |  |  | 1798.5 |  |  | 1894 |  |  | 1977 |  |  | 1892 |  |  | 1902.5 |  |  | 1866 |  |  | 1801 |  |  | 1861 |  |  | 2010.5 |  |  | 1866.5 |  |  | 1848.5 |  |  | 1864 |  |  | 1932 |  |  | 1908 |  |  | 1808.5 |  |  | 1876 |  |  | 1840.5 |  |  | 1743 |  |  | 1778 |  |  | 1852 |  |  | 1834.5 |  |  | 1874.5 |  |  | 1867 |  |  | 1778 |  |  | 1973.5 |  |  | 1817 |  |  | 1846 |  |  | 1961.5 |  |  | 1795 |  |  | 1868 |  |  | 1862.5 |  |  | 1809 |  |  | 1859 |  |  | 1837.5 |  |  | 2019 |  |  | 1779.5 |  |  | 1881 |  |  | 1748.5 |  |  | 1948.5 |  |  | 1724 |  |  | 1951 |  |  | 1938.5 |  |  | 1911.5 |  |  | 2012 |  |  | 1859 |  |  | 1906 |  |  | 1844.5 |  |  | 1862 |  |  | 1697 |  |  | 1850 |  |  | 1996.5 |  |  | 1875.5 |  |  | 1891 |  |  | 1947 |  |  | 1781 |  |  | 1761 |  |  | 1966 |  |  | 1785 |  |  | 1820 |  |  | 1814.5 |  |  | 1991.5 |  |  | 1785.5 |  |  | 1862 |  |  | 1806.5 |  |  | 1912 |  |  | 1805 |  |  | 1873.5 |  |  | 1765.5 |  |  | 1741 |  |  | 1883 |  |  | 1837.5 |  |  | 1878 |  |  | 1895 |  |  | 1801.5 |  |  | 1862.5 |  |  | 1829 |  |  | 1808 |  |  | 1912 |  |  | 1782.5 |  |  | 1794 |  |  | 1734 |  |  | 1843 |  |  | 1902 |  |  | 1947 |  |  | 1793.5 |  |  | 1979 |  |  | 1795 |  |  | 1743 |  |  | 1990.5 |  |  | 1849 |  |  | 1829.5 |  |  | 1779.5 |  |  | 1812 |  |  | 1924 |  |  | 1827.5 |  |  | 1807.5 |  |  | 1780.5 |  |  | 1821.5 |  |  | 1870.5 |  |  | 1871 |  |  | 1844 |  |  | 1859.5 |  |  | 1827.5 |  |  | 1885 |  |  | 1814 |  |  | 1848.5 |  |  | 1989 |  |  | 1848 |  |  | 1705 |  |  | 1916.5 |  |  | 1955 |  |  | 1778.5 |  |  | 1721 |  |  | 1876.5 |  |  | 1963.5 |  |  | 2002.5 |  |  | 1906 |  |  | 1853 |  |  | 1848.5 |  |  | 1835.5 |  |  | 1890 |  |  | 1917 |  |  | 1881.5 |  |  | 1948 |  |  | 1846.5 |  |  | 1823.5 |  |  | 1966 |  |  | 1900 |  |  | 1735.5 |  |  | 1918.5 |  |  | 1862 |  |  | 1829.5 |  |  | 1837.5 |  |  | 1905 |  |  | 1938 |  |  | 1983 |  |  | 1863.5 |  |  | 1943 |  |  | 1833 |  |  | 1878 |  |  | 1834 |  |  | 1845 |  |  | 1792 |  |  | 1933.5 |  |  | 1822.5 |  |  | 1857 |  |  | 1784 |  |  | 1900 |  |  | 1873.5 |  |  | 1833 |  |  | 1967 |  |  | 1799.5 |  |  | 1874.5 |  |  | 1823 |  |  | 1772.5 |  |  | 1883 |  |  | 1752 |  |  | 1831 |  |  | 1992.5 |  |  | 1991 |  |  | 1759.5 |  |  | 1804.5 |  |  | 1755 |  |  | 1893.5 |  |  | 1693.5 |  |  | 1769 |  |  | 1715 |  |  | 1972 |  |  | 1767.5 |  |  | 1701 |  |  | 1835.5 |  |  | 1843.5 |  |  | 1923 |  |  | 1778.5 |  |  | 1802 |  |  | 1887 |  |  | 1843 |  |  | 1778 |  |  | 1735 |  |  | 1941.5 |  |  | 1831 |  |  | 1942 |  |  | 1818 |  |  | 1960 |  |  | 1854.5 |  |  | 1932.5 |  |  | 1848 |  |  | 1893 |  |  | 1899 |  |  | 1841 |  |  | 1946 |  |  | 1778.5 |  |  | 1862 |  |  | 1892.5 |  |  | 1992 |  |  | 1718 |  |  | 1838 |  |  | 1821 |  |  | 1881.5 |  |  | 1857 |  |  | 1884.5 |  |  | 1817 |  |  | 2005 |  |  | 1937 |  |  | 1836.5 |  |  | 1764 |  |  | 1732 |  |  | 1781 |  |  | 2030 |  |  | 2035 |  |  | 1840.5 |  |  | 1903.5 |  |  | 1791 |  |  | 1815.5 |  |  | 1813 |  |  | 1758.5 |  |  | 1821.5 |  |  | 1762.5 |  |  | 1842.5 |  |  | 1763 |  |  | 2005 |  |  | 1755 |  |  | 1794 |  |  | 1860 |  |  | 1921 |  |  | 1787.5 |  |  | 1782.5 |  |  | 1903.5 |  |  | 1893 |  |  | 1934.5 |  |  | 1830.5 |  |  | 1922.5 |  |  | 1803.5 |  |  | 1850 |  |  | 1841.5 |  |  | 1877.5 |  |  | 1924 |  |  | 1793.5 |  |  | 2006.5 |  |  | 1895.5 |  |  | 1989 |  |  | 1851.5 |  |  | 1884 |  |  | 1875 |  |  | 1862.5 |  |  | 1918.5 |  |  | 1928 |  |  | 1889 |  |  | 1737.5 |  |  | 1735.5 |  |  | 1866.5 |  |  | 1940 |  |  | 1837 |  |  | 1831 |  |  | 1922.5 |  |  | 1902.5 |  |  | 1912 |  |  | 1948.5 |  |  | 1778 |  |  | 1863 |  |  | 1914.5 |  |  | 1830.5 |  |  | 1814 |  |  | 1894.5 |  |  | 1855 |  |  | 1756.5 |  |  | 1993.5 |  |  | 1921 |  |  | 1833.5 |  |  | 1941 |  |  | 1900.5 |  |  | 1824 |  |  | 1932 |  |  | 1917 |  |  | 1791.5 |  |  | 1752.5 |  |  | 1909 |  |  | 1793 |  |  | 1787 |  |  | 1845.5 |  |  | 1858.5 |  |  | 1915 |  |  | 1886.5 |  |  | 1843 |  |  | 1746.5 |  |  | 1850.5 |  |  | 1794 |  |  | 1868 |  |  | 1845 |  |  | 1825.5 |  |  | 1830 |  |  | 1916.5 |  |  | 1925 |  |  | 1880.5 |  |  | 2041 |  |  | 1716.5 |  |  | 1821 |  |  | 1844.5 |  |  | 1863.5 |  |  | 1827 |  |  | 1847 |  |  | 2040 |  |  | 1838 |  |  | 1929.5 |  |  | 1740 |  |  | 1826.5 |  |  | 1708 |  |  | 1803 |  |  | 1786 |  |  | 1951 |  |  | 1872 |  |  | 1837 |  |  | 1924 |  |  | 1854.5 |  |  | 1780 |  |  | 1939
66 |  | 2077.5 |  |  | 2020 |  |  | 1960.5 |  |  | 1881 |  |  | 1871.5 |  |  | 1924 |  |  | 1878 |  |  | 1940 |  |  | 1755.5 |  |  | 1826 |  |  | 1848 |  |  | 2004 |  |  | 1977 |  |  | 2083 |  |  | 1829.5 |  |  | 1923.5 |  |  | 1831 |  |  | 1933 |  |  | 2015 |  |  | 1818.5 |  |  | 1928 |  |  | 1935 |  |  | 1792 |  |  | 1911 |  |  | 1861.5 |  |  | 2031 |  |  | 1905 |  |  | 1871 |  |  | 1935 |  |  | 1820 |  |  | 1923 |  |  | 1856.5 |  |  | 1993.5 |  |  | 1882.5 |  |  | 1788 |  |  | 1839.5 |  |  | 1832.5 |  |  | 1957.5 |  |  | 1945 |  |  | 1895 |  |  | 1784.5 |  |  | 1845 |  |  | 1957.5 |  |  | 1882.5 |  |  | 1944.5 |  |  | 2079.5 |  |  | 2080.5 |  |  | 1897 |  |  | 1770 |  |  | 1821.5 |  |  | 1868 |  |  | 1787.5 |  |  | 1806.5 |  |  | 1909 |  |  | 1862 |  |  | 1857 |  |  | 1818 |  |  | 1989 |  |  | 1966 |  |  | 1862.5 |  |  | 1903.5 |  |  | 1878.5 |  |  | 1811 |  |  | 1891 |  |  | 1764 |  |  | 1783.5 |  |  | 1864 |  |  | 1890.5 |  |  | 1925.5 |  |  | 2038.5 |  |  | 1846 |  |  | 2018 |  |  | 1938 |  |  | 1911.5 |  |  | 1946.5 |  |  | 1848.5 |  |  | 1943.5 |  |  | 1890.5 |  |  | 1918.5 |  |  | 1891.5 |  |  | 1868.5 |  |  | 1821 |  |  | 1952 |  |  | 1858 |  |  | 1951.5 |  |  | 2013 |  |  | 1836.5 |  |  | 1910 |  |  | 1930 |  |  | 1973.5 |  |  | 2012.5 |  |  | 1873 |  |  | 2063 |  |  | 1813.5 |  |  | 1949 |  |  | 1818.5 |  |  | 1902.5 |  |  | 1889.5 |  |  | 1829.5 |  |  | 1784.5 |  |  | 1914 |  |  | 1900 |  |  | 1762 |  |  | 1886.5 |  |  | 1833.5 |  |  | 1940.5 |  |  | 1856.5 |  |  | 1891 |  |  | 1841 |  |  | 1921.5 |  |  | 1736 |  |  | 1910.5 |  |  | 1908 |  |  | 1826 |  |  | 1782.5 |  |  | 1853 |  |  | 1911 |  |  | 1799 |  |  | 1932 |  |  | 1901.5 |  |  | 1888.5 |  |  | 1834.5 |  |  | 1989 |  |  | 1827 |  |  | 1797 |  |  | 1854 |  |  | 1855.5 |  |  | 1846 |  |  | 1938.5 |  |  | 1922 |  |  | 1817 |  |  | 1915.5 |  |  | 1855.5 |  |  | 1806 |  |  | 1824.5 |  |  | 1853 |  |  | 1908 |  |  | 1839 |  |  | 1966 |  |  | 1779 |  |  | 1830 |  |  | 1832 |  |  | 1923 |  |  | 1792 |  |  | 1802.5 |  |  | 1868 |  |  | 1756 |  |  | 1925 |  |  | 1905 |  |  | 1872 |  |  | 1808 |  |  | 1839 |  |  | 1912.5 |  |  | 1895 |  |  | 1902.5 |  |  | 1953 |  |  | 1830 |  |  | 1960.5 |  |  | 1909 |  |  | 2050.5 |  |  | 1858 |  |  | 1721 |  |  | 1865.5 |  |  | 1908 |  |  | 1958.5 |  |  | 1926 |  |  | 1796 |  |  | 1952.5 |  |  | 1870.5 |  |  | 1914 |  |  | 1900.5 |  |  | 1897.5 |  |  | 1861 |  |  | 1930 |  |  | 2062.5 |  |  | 1798.5 |  |  | 1912.5 |  |  | 1955 |  |  | 1989 |  |  | 1869 |  |  | 1968 |  |  | 1941 |  |  | 1905.5 |  |  | 1846 |  |  | 1807.5 |  |  | 1934.5 |  |  | 1932 |  |  | 1982 |  |  | 2087.5 |  |  | 1783.5 |  |  | 1879 |  |  | 1941.5 |  |  | 1809.5 |  |  | 1933 |  |  | 1771 |  |  | 1851 |  |  | 1825.5 |  |  | 2001 |  |  | 1860.5 |  |  | 1875.5 |  |  | 1827 |  |  | 1822.5 |  |  | 1866 |  |  | 1917 |  |  | 1915 |  |  | 1877 |  |  | 1728 |  |  | 1991 |  |  | 2002 |  |  | 1920 |  |  | 2003 |  |  | 1831 |  |  | 1859.5 |  |  | 1999.5 |  |  | 1848 |  |  | 1840 |  |  | 2005 |  |  | 1937.5 |  |  | 1952.5 |  |  | 1951.5 |  |  | 1858 |  |  | 1901 |  |  | 2019.5 |  |  | 1900.5 |  |  | 1791.5 |  |  | 1990 |  |  | 2020 |  |  | 1873 |  |  | 1920 |  |  | 1945 |  |  | 1873.5 |  |  | 1820.5 |  |  | 1945 |  |  | 1875 |  |  | 1844 |  |  | 2003 |  |  | 1893 |  |  | 1951.5 |  |  | 1912 |  |  | 1913 |  |  | 1906 |  |  | 1849 |  |  | 1876.5 |  |  | 2026 |  |  | 1907 |  |  | 1846 |  |  | 2007 |  |  | 1975.5 |  |  | 1959 |  |  | 1787 |  |  | 1857 |  |  | 1976.5 |  |  | 1884.5 |  |  | 1970.5 |  |  | 1989 |  |  | 1857 |  |  | 1806 |  |  | 2022 |  |  | 1884 |  |  | 1785.5 |  |  | 1960 |  |  | 1886.5 |  |  | 1916.5 |  |  | 1947.5 |  |  | 1927 |  |  | 2024.5 |  |  | 1818 |  |  | 1833 |  |  | 1884.5 |  |  | 1908.5 |  |  | 1957 |  |  | 1976.5 |  |  | 2007.5 |  |  | 1886 |  |  | 1947 |  |  | 1863.5 |  |  | 1820.5 |  |  | 2001 |  |  | 1930.5 |  |  | 1942 |  |  | 1869 |  |  | 1847.5 |  |  | 1955 |  |  | 1828 |  |  | 1907.5 |  |  | 1869 |  |  | 2054.5 |  |  | 1845 |  |  | 2099 |  |  | 1890 |  |  | 1836 |  |  | 1984.5 |  |  | 2034 |  |  | 2002.5 |  |  | 1781.5 |  |  | 1992.5 |  |  | 1945 |  |  | 1977.5 |  |  | 2106 |  |  | 1944 |  |  | 1742.5 |  |  | 1883.5 |  |  | 1947 |  |  | 1864.5 |  |  | 1963 |  |  | 1881 |  |  | 2025.5 |  |  | 1852 |  |  | 1849.5 |  |  | 1914.5 |  |  | 1915.5 |  |  | 1848 |  |  | 1766 |  |  | 1818 |  |  | 1832.5 |  |  | 1874 |  |  | 2040.5 |  |  | 1940 |  |  | 1878 |  |  | 1831 |  |  | 1915 |  |  | 1970 |  |  | 1939 |  |  | 1850 |  |  | 2020 |  |  | 1911 |  |  | 1857.5 |  |  | 1920 |  |  | 1855 |  |  | 1996.5 |  |  | 1801.5 |  |  | 1942.5 |  |  | 1951.5 |  |  | 1867 |  |  | 2003 |  |  | 1776.5 |  |  | 1992.5 |  |  | 1927.5 |  |  | 1892 |  |  | 1893 |  |  | 1833 |  |  | 1882 |  |  | 1770 |  |  | 1883 |  |  | 1902 |  |  | 1862.5 |  |  | 1927.5 |  |  | 1838 |  |  | 1848.5 |  |  | 1905.5 |  |  | 1779 |  |  | 1948 |  |  | 1854 |  |  | 1870 |  |  | 1795.5 |  |  | 1793.5 |  |  | 1954.5 |  |  | 1881 |  |  | 1843.5 |  |  | 1935 |  |  | 1876 |  |  | 1996 |  |  | 1810.5 |  |  | 1870 |  |  | 1795 |  |  | 1872.5 |  |  | 1863 |  |  | 1939.5 |  |  | 2051 |  |  | 1869.5 |  |  | 1835 |  |  | 1898.5 |  |  | 1908.5 |  |  | 1960 |  |  | 1862 |  |  | 1724 |  |  | 1924 |  |  | 1762.5 |  |  | 1846 |  |  | 2019 |  |  | 1776.5 |  |  | 1955.5 |  |  | 1836.5 |  |  | 1836 |  |  | 1934.5 |  |  | 1895.5 |  |  | 1802.5 |  |  | 1991 |  |  | 1902 |  |  | 1918.5 |  |  | 1918 |  |  | 2027 |  |  | 1916.5 |  |  | 1877 |  |  | 1984 |  |  | 1943 |  |  | 1785 |  |  | 1725.5 |  |  | 1979.5 |  |  | 1761 |  |  | 1959 |  |  | 1941 |  |  | 1831 |  |  | 1848 |  |  | 1840.5 |  |  | 1848.5 |  |  | 1915 |  |  | 1999 |  |  | 2018 |  |  | 1824.5 |  |  | 2058.5 |  |  | 1847 |  |  | 1899 |  |  | 1806 |  |  | 1940.5 |  |  | 2085.5 |  |  | 1929 |  |  | 1774 |  |  | 1930 |  |  | 1906 |  |  | 1896 |  |  | 2022 |  |  | 1798 |  |  | 2016.5 |  |  | 1817 |  |  | 1988 |  |  | 1927 |  |  | 1952.5 |  |  | 1964 |  |  | 1813 |  |  | 1690 |  |  | 1902 |  |  | 1903 |  |  | 1917 |  |  | 1957 |  |  | 1842.5 |  |  | 1867.5 |  |  | 1723.5 |  |  | 1954 |  |  | 1869 |  |  | 1902.5 |  |  | 1754 |  |  | 1795.5 |  |  | 1906.5 |  |  | 1853 |  |  | 1919 |  |  | 1891.5 |  |  | 1898 |  |  | 1900 |  |  | 1889 |  |  | 1925 |  |  | 1896 |  |  | 1849 |  |  | 1845 |  |  | 1962.5 |  |  | 1892 |  |  | 1942 |  |  | 1943 |  |  | 1867 |  |  | 1895 |  |  | 1896 |  |  | 2078 |  |  | 1917 |  |  | 1896 |  |  | 2005.5 |  |  | 1931.5 |  |  | 1892.5 |  |  | 1949.5 |  |  | 1933 |  |  | 1735 |  |  | 2008.5 |  |  | 1832 |  |  | 1887 |  |  | 1837.5 |  |  | 2036.5 |  |  | 1972 |  |  | 1902.5 |  |  | 1883.5 |  |  | 1792 |  |  | 1993 |  |  | 1837 |  |  | 1854 |  |  | 1904.5 |  |  | 1887 |  |  | 1828.5 |  |  | 1754.5 |  |  | 1843 |  |  | 1817 |  |  | 1932.5 |  |  | 1826 |  |  | 1898.5 |  |  | 1913 |  |  | 1939.5 |  |  | 1774.5 |  |  | 1768.5 |  |  | 1916.5 |  |  | 1918.5 |  |  | 1746 |  |  | 1761 |  |  | 2002.5 |  |  | 1912 |  |  | 1831 |  |  | 1895 |  |  | 1993 |  |  | 1988.5 |  |  | 1757 |  |  | 1815 |  |  | 1939 |  |  | 1842.5 |  |  | 1898 |  |  | 1812 |  |  | 1863 |  |  | 2066.5 |  |  | 1935 |  |  | 1708 |  |  | 1905 |  |  | 2004 |  |  | 2164.5 |  |  | 1961 |  |  | 1818.5 |  |  | 1875 |  |  | 1912 |  |  | 2094.5 |  |  | 1966 |  |  | 1845 |  |  | 1888.5 |  |  | 1931 |  |  | 1849 |  |  | 1888 |  |  | 2063.5 |  |  | 1932.5 |  |  | 1890 |  |  | 1805 |  |  | 1875.5 |  |  | 1904.5 |  |  | 1875 |  |  | 1970 |  |  | 1951.5 |  |  | 2016.5 |  |  | 1813.5 |  |  | 1943.5 |  |  | 1857.5 |  |  | 2068 |  |  | 1831.5 |  |  | 1918 |  |  | 1891 |  |  | 1929 |  |  | 1988 |  |  | 1916.5 |  |  | 1890 |  |  | 1795 |  |  | 1910.5 |  |  | 1898.5 |  |  | 1825 |  |  | 1940.5 |  |  | 1874.5 |  |  | 1991 |  |  | 1786 |  |  | 1866 |  |  | 1940.5 |  |  | 1923 |  |  | 1941.5 |  |  | 1943 |  |  | 1867 |  |  | 2072.5 |  |  | 1881 |  |  | 1995 |  |  | 1828 |  |  | 1934 |  |  | 1914 |  |  | 1882 |  |  | 1942 |  |  | 1918 |  |  | 1796.5 |  |  | 1882.5 |  |  | 1845 |  |  | 1924.5 |  |  | 1735.5 |  |  | 1822 |  |  | 1833 |  |  | 1981 |  |  | 1986.5 |  |  | 1816.5 |  |  | 1949 |  |  | 1967 |  |  | 1810 |  |  | 1775 |  |  | 1856 |  |  | 1864 |  |  | 2011 |  |  | 1820.5 |  |  | 2009 |  |  | 1913 |  |  | 1993 |  |  | 1845 |  |  | 1765 |  |  | 1857.5 |  |  | 2069.5 |  |  | 1738.5 |  |  | 1804 |  |  | 1807 |  |  | 1810.5 |  |  | 1991.5 |  |  | 1931.5 |  |  | 1819 |  |  | 1951.5 |  |  | 1911.5 |  |  | 2046 |  |  | 1939.5 |  |  | 1938.5 |  |  | 1866 |  |  | 1814 |  |  | 1863 |  |  | 1968 |  |  | 1855 |  |  | 1734 |  |  | 1908 |  |  | 2007 |  |  | 1799 |  |  | 1819 |  |  | 2020.5 |  |  | 1898 |  |  | 1911 |  |  | 1793 |  |  | 1882.5 |  |  | 1870 |  |  | 1911.5 |  |  | 2003 |  |  | 1948 |  |  | 1851 |  |  | 1913 |  |  | 1991.5 |  |  | 1836 |  |  | 1814 |  |  | 1962.5 |  |  | 1926 |  |  | 1883 |  |  | 1829.5 |  |  | 1880.5 |  |  | 1918 |  |  | 1796.5 |  |  | 1986 |  |  | 1885.5 |  |  | 2027 |  |  | 1924 |  |  | 1817.5 |  |  | 1988.5 |  |  | 1878 |  |  | 1971 |  |  | 1904 |  |  | 1926 |  |  | 1781 |  |  | 1936 |  |  | 1758 |  |  | 1776 |  |  | 2055.5 |  |  | 1768 |  |  | 1966.5 |  |  | 1893 |  |  | 1931.5 |  |  | 1858.5 |  |  | 1842 |  |  | 1918 |  |  | 1966.5 |  |  | 1897 |  |  | 1937 |  |  | 1962 |  |  | 1839.5 |  |  | 1954 |  |  | 1791.5 |  |  | 1710 |  |  | 1843 |  |  | 1909 |  |  | 1921 |  |  | 2011.5 |  |  | 1802 |  |  | 1862 |  |  | 1915 |  |  | 1781.5 |  |  | 2015 |  |  | 1965 |  |  | 1893 |  |  | 1873 |  |  | 1864.5 |  |  | 1824.5 |  |  | 1933 |  |  | 2001 |  |  | 1916 |  |  | 1928.5 |  |  | 1881 |  |  | 1830 |  |  | 1876 |  |  | 2031.5 |  |  | 1887.5 |  |  | 1872.5 |  |  | 1903 |  |  | 1953 |  |  | 1937 |  |  | 1837.5 |  |  | 1915 |  |  | 1879.5 |  |  | 1767 |  |  | 1793 |  |  | 1881 |  |  | 1873.5 |  |  | 1921.5 |  |  | 1896 |  |  | 1817 |  |  | 1999.5 |  |  | 1864 |  |  | 1885 |  |  | 1985.5 |  |  | 1821 |  |  | 1889 |  |  | 1901.5 |  |  | 1824 |  |  | 1888 |  |  | 1876.5 |  |  | 2058 |  |  | 1818.5 |  |  | 1910 |  |  | 1772.5 |  |  | 1963.5 |  |  | 1750 |  |  | 1998 |  |  | 1977.5 |  |  | 1932.5 |  |  | 2038 |  |  | 1898 |  |  | 1945 |  |  | 1868.5 |  |  | 1877 |  |  | 1726 |  |  | 1871 |  |  | 2017.5 |  |  | 1914.5 |  |  | 1930 |  |  | 1973 |  |  | 1820 |  |  | 1800 |  |  | 1990 |  |  | 1800 |  |  | 1835 |  |  | 1861.5 |  |  | 2038.5 |  |  | 1811.5 |  |  | 1888 |  |  | 1845.5 |  |  | 1927 |  |  | 1831 |  |  | 1912.5 |  |  | 1794.5 |  |  | 1756 |  |  | 1930 |  |  | 1852.5 |  |  | 1907 |  |  | 1934 |  |  | 1822.5 |  |  | 1909.5 |  |  | 1853 |  |  | 1855 |  |  | 1933 |  |  | 1806.5 |  |  | 1815 |  |  | 1781 |  |  | 1890 |  |  | 1928 |  |  | 1971 |  |  | 1832.5 |  |  | 2005 |  |  | 1824 |  |  | 1769 |  |  | 2029.5 |  |  | 1864 |  |  | 1850.5 |  |  | 1800.5 |  |  | 1859 |  |  | 1939 |  |  | 1848.5 |  |  | 1831.5 |  |  | 1801.5 |  |  | 1860.5 |  |  | 1885.5 |  |  | 1918 |  |  | 1883 |  |  | 1888.5 |  |  | 1842.5 |  |  | 1900 |  |  | 1843 |  |  | 1863.5 |  |  | 2010 |  |  | 1874 |  |  | 1734 |  |  | 1945.5 |  |  | 1994 |  |  | 1807.5 |  |  | 1750 |  |  | 1915.5 |  |  | 2010.5 |  |  | 2049.5 |  |  | 1953 |  |  | 1892 |  |  | 1887.5 |  |  | 1864.5 |  |  | 1905 |  |  | 1938 |  |  | 1907.5 |  |  | 1969 |  |  | 1885.5 |  |  | 1838.5 |  |  | 1981 |  |  | 1939 |  |  | 1759.5 |  |  | 1957.5 |  |  | 1883 |  |  | 1853.5 |  |  | 1884.5 |  |  | 1920 |  |  | 1977 |  |  | 2012 |  |  | 1884.5 |  |  | 1982 |  |  | 1857 |  |  | 1899 |  |  | 1855 |  |  | 1874 |  |  | 1818 |  |  | 1980.5 |  |  | 1861.5 |  |  | 1878 |  |  | 1813 |  |  | 1939 |  |  | 1920.5 |  |  | 1859 |  |  | 2006 |  |  | 1828.5 |  |  | 1903.5 |  |  | 1849 |  |  | 1801.5 |  |  | 1912 |  |  | 1781 |  |  | 1878 |  |  | 2021.5 |  |  | 2015 |  |  | 1783.5 |  |  | 1830.5 |  |  | 1770 |  |  | 1917.5 |  |  | 1719.5 |  |  | 1784 |  |  | 1744 |  |  | 1996 |  |  | 1782.5 |  |  | 1725 |  |  | 1882.5 |  |  | 1890.5 |  |  | 1947 |  |  | 1807.5 |  |  | 1817 |  |  | 1916 |  |  | 1882 |  |  | 1799 |  |  | 1774 |  |  | 1980.5 |  |  | 1860 |  |  | 1971 |  |  | 1833 |  |  | 1986 |  |  | 1878.5 |  |  | 1953.5 |  |  | 1869 |  |  | 1908 |  |  | 1923 |  |  | 1880 |  |  | 1993 |  |  | 1825.5 |  |  | 1901 |  |  | 1939.5 |  |  | 2007 |  |  | 1765 |  |  | 1864 |  |  | 1860 |  |  | 1920.5 |  |  | 1878 |  |  | 1931.5 |  |  | 1838 |  |  | 2052 |  |  | 1958 |  |  | 1875.5 |  |  | 1811 |  |  | 1747 |  |  | 1807 |  |  | 2051 |  |  | 2061 |  |  | 1866.5 |  |  | 1942.5 |  |  | 1817 |  |  | 1844.5 |  |  | 1842 |  |  | 1782.5 |  |  | 1860.5 |  |  | 1809.5 |  |  | 1857.5 |  |  | 1792 |  |  | 2020 |  |  | 1794 |  |  | 1820 |  |  | 1889 |  |  | 1968 |  |  | 1802.5 |  |  | 1821.5 |  |  | 1942.5 |  |  | 1922 |  |  | 1955.5 |  |  | 1856.5 |  |  | 1961.5 |  |  | 1827.5 |  |  | 1889 |  |  | 1880.5 |  |  | 1906.5 |  |  | 1963 |  |  | 1822.5 |  |  | 2030.5 |  |  | 1910.5 |  |  | 2015 |  |  | 1890.5 |  |  | 1908 |  |  | 1914 |  |  | 1877.5 |  |  | 1957.5 |  |  | 1949 |  |  | 1928 |  |  | 1761.5 |  |  | 1750.5 |  |  | 1887.5 |  |  | 1955 |  |  | 1858 |  |  | 1878 |  |  | 1943.5 |  |  | 1941.5 |  |  | 1927 |  |  | 1963.5 |  |  | 1799 |  |  | 1902 |  |  | 1940.5 |  |  | 1845.5 |  |  | 1853 |  |  | 1915.5 |  |  | 1902 |  |  | 1777.5 |  |  | 2014.5 |  |  | 1947 |  |  | 1857.5 |  |  | 1965 |  |  | 1926.5 |  |  | 1863 |  |  | 1947 |  |  | 1938 |  |  | 1838.5 |  |  | 1778.5 |  |  | 1948 |  |  | 1817 |  |  | 1802 |  |  | 1874.5 |  |  | 1884.5 |  |  | 1954 |  |  | 1925.5 |  |  | 1882 |  |  | 1793.5 |  |  | 1874.5 |  |  | 1809 |  |  | 1889 |  |  | 1866 |  |  | 1851.5 |  |  | 1845 |  |  | 1945.5 |  |  | 1964 |  |  | 1901.5 |  |  | 2065 |  |  | 1755.5 |  |  | 1860 |  |  | 1873.5 |  |  | 1892.5 |  |  | 1856 |  |  | 1886 |  |  | 2079 |  |  | 1877 |  |  | 1958.5 |  |  | 1787 |  |  | 1841.5 |  |  | 1747 |  |  | 1829 |  |  | 1807 |  |  | 1990 |  |  | 1919 |  |  | 1866 |  |  | 1963 |  |  | 1883.5 |  |  | 1809 |  |  | 1960
67 |  | 2106.5 |  |  | 2044 |  |  | 1989.5 |  |  | 1907 |  |  | 1886.5 |  |  | 1963 |  |  | 1917 |  |  | 1966 |  |  | 1802.5 |  |  | 1873 |  |  | 1863 |  |  | 2033 |  |  | 2016 |  |  | 2104 |  |  | 1868.5 |  |  | 1949.5 |  |  | 1846 |  |  | 1962 |  |  | 2054 |  |  | 1847.5 |  |  | 1957 |  |  | 1982 |  |  | 1816 |  |  | 1926 |  |  | 1885.5 |  |  | 2046 |  |  | 1929 |  |  | 1900 |  |  | 1974 |  |  | 1849 |  |  | 1962 |  |  | 1895.5 |  |  | 2014.5 |  |  | 1929.5 |  |  | 1812 |  |  | 1863.5 |  |  | 1879.5 |  |  | 2004.5 |  |  | 1984 |  |  | 1924 |  |  | 1823.5 |  |  | 1874 |  |  | 1996.5 |  |  | 1897.5 |  |  | 1965.5 |  |  | 2118.5 |  |  | 2104.5 |  |  | 1926 |  |  | 1799 |  |  | 1850.5 |  |  | 1889 |  |  | 1834.5 |  |  | 1827.5 |  |  | 1956 |  |  | 1883 |  |  | 1881 |  |  | 1857 |  |  | 2028 |  |  | 1987 |  |  | 1883.5 |  |  | 1927.5 |  |  | 1917.5 |  |  | 1835 |  |  | 1917 |  |  | 1788 |  |  | 1812.5 |  |  | 1890 |  |  | 1911.5 |  |  | 1964.5 |  |  | 2077.5 |  |  | 1861 |  |  | 2042 |  |  | 1985 |  |  | 1950.5 |  |  | 1985.5 |  |  | 1887.5 |  |  | 1958.5 |  |  | 1911.5 |  |  | 1944.5 |  |  | 1906.5 |  |  | 1889.5 |  |  | 1845 |  |  | 1973 |  |  | 1905 |  |  | 1980.5 |  |  | 2052 |  |  | 1883.5 |  |  | 1936 |  |  | 1969 |  |  | 2002.5 |  |  | 2041.5 |  |  | 1888 |  |  | 2102 |  |  | 1852.5 |  |  | 1973 |  |  | 1865.5 |  |  | 1941.5 |  |  | 1928.5 |  |  | 1858.5 |  |  | 1823.5 |  |  | 1940 |  |  | 1921 |  |  | 1801 |  |  | 1925.5 |  |  | 1857.5 |  |  | 1979.5 |  |  | 1895.5 |  |  | 1917 |  |  | 1880 |  |  | 1936.5 |  |  | 1757 |  |  | 1949.5 |  |  | 1947 |  |  | 1847 |  |  | 1803.5 |  |  | 1868 |  |  | 1950 |  |  | 1814 |  |  | 1971 |  |  | 1927.5 |  |  | 1912.5 |  |  | 1858.5 |  |  | 2004 |  |  | 1874 |  |  | 1836 |  |  | 1893 |  |  | 1876.5 |  |  | 1875 |  |  | 1977.5 |  |  | 1937 |  |  | 1864 |  |  | 1941.5 |  |  | 1876.5 |  |  | 1827 |  |  | 1848.5 |  |  | 1868 |  |  | 1947 |  |  | 1865 |  |  | 2013 |  |  | 1826 |  |  | 1859 |  |  | 1871 |  |  | 1944 |  |  | 1821 |  |  | 1817.5 |  |  | 1915 |  |  | 1795 |  |  | 1951 |  |  | 1952 |  |  | 1919 |  |  | 1847 |  |  | 1878 |  |  | 1941.5 |  |  | 1921 |  |  | 1941.5 |  |  | 1974 |  |  | 1859 |  |  | 1999.5 |  |  | 1948 |  |  | 2076.5 |  |  | 1873 |  |  | 1742 |  |  | 1889.5 |  |  | 1955 |  |  | 1982.5 |  |  | 1941 |  |  | 1820 |  |  | 1991.5 |  |  | 1909.5 |  |  | 1943 |  |  | 1926.5 |  |  | 1923.5 |  |  | 1890 |  |  | 1956 |  |  | 2088.5 |  |  | 1837.5 |  |  | 1959.5 |  |  | 1981 |  |  | 2018 |  |  | 1893 |  |  | 1997 |  |  | 1980 |  |  | 1929.5 |  |  | 1870 |  |  | 1836.5 |  |  | 1949.5 |  |  | 1958 |  |  | 2008 |  |  | 2102.5 |  |  | 1822.5 |  |  | 1900 |  |  | 1956.5 |  |  | 1848.5 |  |  | 1957 |  |  | 1795 |  |  | 1866 |  |  | 1851.5 |  |  | 2016 |  |  | 1907.5 |  |  | 1914.5 |  |  | 1848 |  |  | 1861.5 |  |  | 1890 |  |  | 1943 |  |  | 1954 |  |  | 1901 |  |  | 1743 |  |  | 2038 |  |  | 2041 |  |  | 1946 |  |  | 2042 |  |  | 1855 |  |  | 1906.5 |  |  | 2046.5 |  |  | 1895 |  |  | 1869 |  |  | 2029 |  |  | 1976.5 |  |  | 1991.5 |  |  | 1975.5 |  |  | 1884 |  |  | 1916 |  |  | 2043.5 |  |  | 1939.5 |  |  | 1815.5 |  |  | 2019 |  |  | 2041 |  |  | 1888 |  |  | 1959 |  |  | 1960 |  |  | 1920.5 |  |  | 1846.5 |  |  | 1984 |  |  | 1896 |  |  | 1868 |  |  | 2029 |  |  | 1908 |  |  | 1972.5 |  |  | 1936 |  |  | 1937 |  |  | 1921 |  |  | 1870 |  |  | 1891.5 |  |  | 2055 |  |  | 1931 |  |  | 1893 |  |  | 2033 |  |  | 2022.5 |  |  | 1988 |  |  | 1826 |  |  | 1904 |  |  | 2015.5 |  |  | 1910.5 |  |  | 1996.5 |  |  | 2015 |  |  | 1872 |  |  | 1853 |  |  | 2061 |  |  | 1931 |  |  | 1824.5 |  |  | 1981 |  |  | 1907.5 |  |  | 1963.5 |  |  | 1968.5 |  |  | 1951 |  |  | 2071.5 |  |  | 1844 |  |  | 1862 |  |  | 1913.5 |  |  | 1947.5 |  |  | 1996 |  |  | 1997.5 |  |  | 2046.5 |  |  | 1901 |  |  | 1976 |  |  | 1892.5 |  |  | 1859.5 |  |  | 2048 |  |  | 1951.5 |  |  | 1989 |  |  | 1890 |  |  | 1886.5 |  |  | 1994 |  |  | 1857 |  |  | 1936.5 |  |  | 1916 |  |  | 2093.5 |  |  | 1874 |  |  | 2120 |  |  | 1905 |  |  | 1860 |  |  | 2023.5 |  |  | 2058 |  |  | 2031.5 |  |  | 1810.5 |  |  | 2018.5 |  |  | 1966 |  |  | 2006.5 |  |  | 2132 |  |  | 1983 |  |  | 1763.5 |  |  | 1930.5 |  |  | 1968 |  |  | 1885.5 |  |  | 2002 |  |  | 1902 |  |  | 2064.5 |  |  | 1878 |  |  | 1870.5 |  |  | 1943.5 |  |  | 1936.5 |  |  | 1872 |  |  | 1795 |  |  | 1842 |  |  | 1879.5 |  |  | 1921 |  |  | 2079.5 |  |  | 1964 |  |  | 1902 |  |  | 1870 |  |  | 1936 |  |  | 1985 |  |  | 1960 |  |  | 1879 |  |  | 2067 |  |  | 1932 |  |  | 1881.5 |  |  | 1946 |  |  | 1881 |  |  | 2035.5 |  |  | 1830.5 |  |  | 1968.5 |  |  | 1980.5 |  |  | 1896 |  |  | 2042 |  |  | 1823.5 |  |  | 2016.5 |  |  | 1942.5 |  |  | 1921 |  |  | 1919 |  |  | 1859 |  |  | 1921 |  |  | 1791 |  |  | 1909 |  |  | 1931 |  |  | 1901.5 |  |  | 1966.5 |  |  | 1859 |  |  | 1872.5 |  |  | 1929.5 |  |  | 1818 |  |  | 1995 |  |  | 1875 |  |  | 1909 |  |  | 1819.5 |  |  | 1817.5 |  |  | 1969.5 |  |  | 1928 |  |  | 1864.5 |  |  | 1974 |  |  | 1915 |  |  | 2025 |  |  | 1831.5 |  |  | 1894 |  |  | 1834 |  |  | 1898.5 |  |  | 1892 |  |  | 1965.5 |  |  | 2090 |  |  | 1890.5 |  |  | 1859 |  |  | 1913.5 |  |  | 1937.5 |  |  | 1986 |  |  | 1883 |  |  | 1771 |  |  | 1953 |  |  | 1783.5 |  |  | 1867 |  |  | 2045 |  |  | 1815.5 |  |  | 1994.5 |  |  | 1875.5 |  |  | 1862 |  |  | 1973.5 |  |  | 1916.5 |  |  | 1817.5 |  |  | 2012 |  |  | 1941 |  |  | 1965.5 |  |  | 1965 |  |  | 2048 |  |  | 1945.5 |  |  | 1906 |  |  | 2010 |  |  | 1964 |  |  | 1806 |  |  | 1764.5 |  |  | 1994.5 |  |  | 1808 |  |  | 1983 |  |  | 1970 |  |  | 1860 |  |  | 1887 |  |  | 1879.5 |  |  | 1872.5 |  |  | 1954 |  |  | 2038 |  |  | 2057 |  |  | 1871.5 |  |  | 2097.5 |  |  | 1886 |  |  | 1920 |  |  | 1827 |  |  | 1955.5 |  |  | 2100.5 |  |  | 1950 |  |  | 1803 |  |  | 1969 |  |  | 1953 |  |  | 1925 |  |  | 2048 |  |  | 1822 |  |  | 2040.5 |  |  | 1856 |  |  | 2027 |  |  | 1948 |  |  | 1978.5 |  |  | 2003 |  |  | 1860 |  |  | 1729 |  |  | 1931 |  |  | 1918 |  |  | 1956 |  |  | 1983 |  |  | 1857.5 |  |  | 1893.5 |  |  | 1738.5 |  |  | 2001 |  |  | 1895 |  |  | 1917.5 |  |  | 1778 |  |  | 1816.5 |  |  | 1932.5 |  |  | 1877 |  |  | 1958 |  |  | 1920.5 |  |  | 1945 |  |  | 1947 |  |  | 1913 |  |  | 1946 |  |  | 1920 |  |  | 1888 |  |  | 1860 |  |  | 1986.5 |  |  | 1931 |  |  | 1963 |  |  | 1972 |  |  | 1891 |  |  | 1910 |  |  | 1920 |  |  | 2102 |  |  | 1943 |  |  | 1922 |  |  | 2044.5 |  |  | 1946.5 |  |  | 1913.5 |  |  | 1988.5 |  |  | 1954 |  |  | 1774 |  |  | 2032.5 |  |  | 1861 |  |  | 1908 |  |  | 1858.5 |  |  | 2060.5 |  |  | 1993 |  |  | 1949.5 |  |  | 1898.5 |  |  | 1807 |  |  | 2017 |  |  | 1876 |  |  | 1883 |  |  | 1928.5 |  |  | 1913 |  |  | 1857.5 |  |  | 1801.5 |  |  | 1890 |  |  | 1856 |  |  | 1971.5 |  |  | 1873 |  |  | 1945.5 |  |  | 1960 |  |  | 1963.5 |  |  | 1813.5 |  |  | 1783.5 |  |  | 1942.5 |  |  | 1944.5 |  |  | 1767 |  |  | 1800 |  |  | 2028.5 |  |  | 1951 |  |  | 1857 |  |  | 1916 |  |  | 2014 |  |  | 2017.5 |  |  | 1796 |  |  | 1862 |  |  | 1978 |  |  | 1866.5 |  |  | 1919 |  |  | 1841 |  |  | 1910 |  |  | 2092.5 |  |  | 1956 |  |  | 1747 |  |  | 1952 |  |  | 2019 |  |  | 2190.5 |  |  | 1990 |  |  | 1839.5 |  |  | 1896 |  |  | 1951 |  |  | 2133.5 |  |  | 1981 |  |  | 1866 |  |  | 1909.5 |  |  | 1955 |  |  | 1896 |  |  | 1909 |  |  | 2084.5 |  |  | 1947.5 |  |  | 1929 |  |  | 1829 |  |  | 1914.5 |  |  | 1933.5 |  |  | 1914 |  |  | 1996 |  |  | 1972.5 |  |  | 2063.5 |  |  | 1828.5 |  |  | 1964.5 |  |  | 1878.5 |  |  | 2089 |  |  | 1878.5 |  |  | 1947 |  |  | 1930 |  |  | 1953 |  |  | 2027 |  |  | 1945.5 |  |  | 1929 |  |  | 1824 |  |  | 1957.5 |  |  | 1945.5 |  |  | 1849 |  |  | 1987.5 |  |  | 1913.5 |  |  | 2030 |  |  | 1815 |  |  | 1913 |  |  | 1969.5 |  |  | 1962 |  |  | 1980.5 |  |  | 1972 |  |  | 1906 |  |  | 2119.5 |  |  | 1905 |  |  | 2019 |  |  | 1854 |  |  | 1981 |  |  | 1961 |  |  | 1929 |  |  | 1981 |  |  | 1942 |  |  | 1811.5 |  |  | 1921.5 |  |  | 1869 |  |  | 1963.5 |  |  | 1764.5 |  |  | 1846 |  |  | 1859 |  |  | 2002 |  |  | 2025.5 |  |  | 1842.5 |  |  | 1988 |  |  | 1988 |  |  | 1825 |  |  | 1814 |  |  | 1880 |  |  | 1879 |  |  | 2032 |  |  | 1867.5 |  |  | 2033 |  |  | 1937 |  |  | 2040 |  |  | 1869 |  |  | 1791 |  |  | 1896.5 |  |  | 2108.5 |  |  | 1767.5 |  |  | 1833 |  |  | 1846 |  |  | 1834.5 |  |  | 2030.5 |  |  | 1952.5 |  |  | 1866 |  |  | 1990.5 |  |  | 1958.5 |  |  | 2085 |  |  | 1978.5 |  |  | 1953.5 |  |  | 1905 |  |  | 1843 |  |  | 1902 |  |  | 1994 |  |  | 1894 |  |  | 1773 |  |  | 1955 |  |  | 2054 |  |  | 1823 |  |  | 1848 |  |  | 2046.5 |  |  | 1913 |  |  | 1958 |  |  | 1819 |  |  | 1903.5 |  |  | 1909 |  |  | 1935.5 |  |  | 2042 |  |  | 1977 |  |  | 1898 |  |  | 1952 |  |  | 2030.5 |  |  | 1865 |  |  | 1853 |  |  | 1977.5 |  |  | 1950 |  |  | 1909 |  |  | 1858.5 |  |  | 1895.5 |  |  | 1939 |  |  | 1835.5 |  |  | 2025 |  |  | 1900.5 |  |  | 2048 |  |  | 1963 |  |  | 1856.5 |  |  | 2027.5 |  |  | 1899 |  |  | 2018 |  |  | 1919 |  |  | 1952 |  |  | 1820 |  |  | 1975 |  |  | 1784 |  |  | 1805 |  |  | 2070.5 |  |  | 1815 |  |  | 2005.5 |  |  | 1919 |  |  | 1970.5 |  |  | 1884.5 |  |  | 1866 |  |  | 1957 |  |  | 1995.5 |  |  | 1926 |  |  | 1958 |  |  | 2001 |  |  | 1878.5 |  |  | 1969 |  |  | 1815.5 |  |  | 1731 |  |  | 1872 |  |  | 1933 |  |  | 1936 |  |  | 2026.5 |  |  | 1841 |  |  | 1909 |  |  | 1930 |  |  | 1820.5 |  |  | 2030 |  |  | 1994 |  |  | 1932 |  |  | 1912 |  |  | 1888.5 |  |  | 1853.5 |  |  | 1954 |  |  | 2030 |  |  | 1940 |  |  | 1957.5 |  |  | 1928 |  |  | 1845 |  |  | 1897 |  |  | 2060.5 |  |  | 1911.5 |  |  | 1901.5 |  |  | 1942 |  |  | 1992 |  |  | 1976 |  |  | 1884.5 |  |  | 1962 |  |  | 1918.5 |  |  | 1793 |  |  | 1808 |  |  | 1902 |  |  | 1894.5 |  |  | 1945.5 |  |  | 1920 |  |  | 1856 |  |  | 2038.5 |  |  | 1903 |  |  | 1924 |  |  | 2000.5 |  |  | 1860 |  |  | 1913 |  |  | 1948.5 |  |  | 1863 |  |  | 1909 |  |  | 1891.5 |  |  | 2082 |  |  | 1839.5 |  |  | 1931 |  |  | 1787.5 |  |  | 2002.5 |  |  | 1776 |  |  | 2037 |  |  | 1992.5 |  |  | 1947.5 |  |  | 2077 |  |  | 1927 |  |  | 1960 |  |  | 1892.5 |  |  | 1916 |  |  | 1741 |  |  | 1895 |  |  | 2041.5 |  |  | 1953.5 |  |  | 1969 |  |  | 1999 |  |  | 1859 |  |  | 1815 |  |  | 2005 |  |  | 1839 |  |  | 1874 |  |  | 1900.5 |  |  | 2077.5 |  |  | 1850.5 |  |  | 1914 |  |  | 1874.5 |  |  | 1953 |  |  | 1860 |  |  | 1951.5 |  |  | 1809.5 |  |  | 1785 |  |  | 1959 |  |  | 1891.5 |  |  | 1946 |  |  | 1963 |  |  | 1843.5 |  |  | 1956.5 |  |  | 1879 |  |  | 1879 |  |  | 1948 |  |  | 1830.5 |  |  | 1841 |  |  | 1807 |  |  | 1937 |  |  | 1943 |  |  | 2018 |  |  | 1871.5 |  |  | 2044 |  |  | 1845 |  |  | 1795 |  |  | 2058.5 |  |  | 1890 |  |  | 1871.5 |  |  | 1839.5 |  |  | 1906 |  |  | 1960 |  |  | 1877.5 |  |  | 1857.5 |  |  | 1830.5 |  |  | 1899.5 |  |  | 1906.5 |  |  | 1939 |  |  | 1904 |  |  | 1903.5 |  |  | 1881.5 |  |  | 1929 |  |  | 1864 |  |  | 1892.5 |  |  | 2057 |  |  | 1903 |  |  | 1758 |  |  | 1971.5 |  |  | 2033 |  |  | 1831.5 |  |  | 1797 |  |  | 1944.5 |  |  | 2057.5 |  |  | 2078.5 |  |  | 1992 |  |  | 1931 |  |  | 1913.5 |  |  | 1888.5 |  |  | 1944 |  |  | 1953 |  |  | 1946.5 |  |  | 2016 |  |  | 1924.5 |  |  | 1859.5 |  |  | 1996 |  |  | 1968 |  |  | 1774.5 |  |  | 1996.5 |  |  | 1907 |  |  | 1882.5 |  |  | 1923.5 |  |  | 1967 |  |  | 1998 |  |  | 2038 |  |  | 1899.5 |  |  | 2011 |  |  | 1878 |  |  | 1938 |  |  | 1870 |  |  | 1889 |  |  | 1847 |  |  | 2019.5 |  |  | 1885.5 |  |  | 1899 |  |  | 1860 |  |  | 1965 |  |  | 1946.5 |  |  | 1888 |  |  | 2045 |  |  | 1843.5 |  |  | 1942.5 |  |  | 1888 |  |  | 1840.5 |  |  | 1951 |  |  | 1796 |  |  | 1917 |  |  | 2045.5 |  |  | 2044 |  |  | 1807.5 |  |  | 1877.5 |  |  | 1785 |  |  | 1943.5 |  |  | 1734.5 |  |  | 1810 |  |  | 1791 |  |  | 2011 |  |  | 1811.5 |  |  | 1772 |  |  | 1921.5 |  |  | 1905.5 |  |  | 1968 |  |  | 1822.5 |  |  | 1843 |  |  | 1942 |  |  | 1897 |  |  | 1820 |  |  | 1803 |  |  | 1995.5 |  |  | 1899 |  |  | 2000 |  |  | 1857 |  |  | 2001 |  |  | 1925.5 |  |  | 1977.5 |  |  | 1890 |  |  | 1937 |  |  | 1962 |  |  | 1904 |  |  | 2019 |  |  | 1864.5 |  |  | 1922 |  |  | 1986.5 |  |  | 2046 |  |  | 1804 |  |  | 1888 |  |  | 1899 |  |  | 1967.5 |  |  | 1917 |  |  | 1970.5 |  |  | 1867 |  |  | 2067 |  |  | 1997 |  |  | 1914.5 |  |  | 1858 |  |  | 1773 |  |  | 1822 |  |  | 2066 |  |  | 2100 |  |  | 1881.5 |  |  | 1957.5 |  |  | 1864 |  |  | 1868.5 |  |  | 1866 |  |  | 1829.5 |  |  | 1881.5 |  |  | 1833.5 |  |  | 1881.5 |  |  | 1821 |  |  | 2067 |  |  | 1818 |  |  | 1841 |  |  | 1928 |  |  | 2015 |  |  | 1841.5 |  |  | 1860.5 |  |  | 1981.5 |  |  | 1961 |  |  | 1976.5 |  |  | 1882.5 |  |  | 1982.5 |  |  | 1851.5 |  |  | 1904 |  |  | 1919.5 |  |  | 1921.5 |  |  | 1992 |  |  | 1861.5 |  |  | 2069.5 |  |  | 1949.5 |  |  | 2062 |  |  | 1929.5 |  |  | 1934 |  |  | 1938 |  |  | 1892.5 |  |  | 1981.5 |  |  | 1970 |  |  | 1949 |  |  | 1790.5 |  |  | 1771.5 |  |  | 1916.5 |  |  | 1984 |  |  | 1882 |  |  | 1917 |  |  | 1982.5 |  |  | 1965.5 |  |  | 1956 |  |  | 1989.5 |  |  | 1814 |  |  | 1941 |  |  | 1961.5 |  |  | 1892.5 |  |  | 1868 |  |  | 1944.5 |  |  | 1941 |  |  | 1816.5 |  |  | 2035.5 |  |  | 1971 |  |  | 1904.5 |  |  | 2004 |  |  | 1950.5 |  |  | 1884 |  |  | 1962 |  |  | 1959 |  |  | 1885.5 |  |  | 1793.5 |  |  | 1987 |  |  | 1856 |  |  | 1828 |  |  | 1900.5 |  |  | 1905.5 |  |  | 1983 |  |  | 1951.5 |  |  | 1903 |  |  | 1817.5 |  |  | 1921.5 |  |  | 1848 |  |  | 1915 |  |  | 1887 |  |  | 1872.5 |  |  | 1884 |  |  | 1971.5 |  |  | 1993 |  |  | 1916.5 |  |  | 2091 |  |  | 1781.5 |  |  | 1907 |  |  | 1912.5 |  |  | 1939.5 |  |  | 1885 |  |  | 1901 |  |  | 2103 |  |  | 1901 |  |  | 2005.5 |  |  | 1826 |  |  | 1865.5 |  |  | 1776 |  |  | 1850 |  |  | 1822 |  |  | 2005 |  |  | 1943 |  |  | 1890 |  |  | 2002 |  |  | 1898.5 |  |  | 1848 |  |  | 1984
68 |  | 2121.5 |  |  | 2070 |  |  | 2004.5 |  |  | 1933 |  |  | 1901.5 |  |  | 2010 |  |  | 1956 |  |  | 2005 |  |  | 1826.5 |  |  | 1894 |  |  | 1902 |  |  | 2062 |  |  | 2037 |  |  | 2125 |  |  | 1907.5 |  |  | 1996.5 |  |  | 1870 |  |  | 1977 |  |  | 2075 |  |  | 1886.5 |  |  | 1983 |  |  | 2011 |  |  | 1837 |  |  | 1973 |  |  | 1932.5 |  |  | 2072 |  |  | 1968 |  |  | 1939 |  |  | 2013 |  |  | 1896 |  |  | 2001 |  |  | 1921.5 |  |  | 2053.5 |  |  | 1958.5 |  |  | 1851 |  |  | 1878.5 |  |  | 1918.5 |  |  | 2028.5 |  |  | 2023 |  |  | 1971 |  |  | 1847.5 |  |  | 1900 |  |  | 2025.5 |  |  | 1912.5 |  |  | 2004.5 |  |  | 2165.5 |  |  | 2130.5 |  |  | 1941 |  |  | 1838 |  |  | 1889.5 |  |  | 1915 |  |  | 1863.5 |  |  | 1842.5 |  |  | 1985 |  |  | 1922 |  |  | 1920 |  |  | 1896 |  |  | 2067 |  |  | 2008 |  |  | 1909.5 |  |  | 1966.5 |  |  | 1932.5 |  |  | 1859 |  |  | 1956 |  |  | 1814 |  |  | 1859.5 |  |  | 1914 |  |  | 1932.5 |  |  | 1993.5 |  |  | 2116.5 |  |  | 1908 |  |  | 2081 |  |  | 2032 |  |  | 1989.5 |  |  | 2000.5 |  |  | 1916.5 |  |  | 1997.5 |  |  | 1932.5 |  |  | 1973.5 |  |  | 1930.5 |  |  | 1913.5 |  |  | 1866 |  |  | 1994 |  |  | 1926 |  |  | 2019.5 |  |  | 2099 |  |  | 1909.5 |  |  | 1957 |  |  | 1990 |  |  | 2026.5 |  |  | 2080.5 |  |  | 1935 |  |  | 2128 |  |  | 1899.5 |  |  | 2020 |  |  | 1894.5 |  |  | 1956.5 |  |  | 1975.5 |  |  | 1879.5 |  |  | 1870.5 |  |  | 1955 |  |  | 1947 |  |  | 1816 |  |  | 1954.5 |  |  | 1896.5 |  |  | 2018.5 |  |  | 1924.5 |  |  | 1946 |  |  | 1919 |  |  | 1965.5 |  |  | 1783 |  |  | 1988.5 |  |  | 1968 |  |  | 1886 |  |  | 1832.5 |  |  | 1907 |  |  | 1976 |  |  | 1853 |  |  | 1995 |  |  | 1942.5 |  |  | 1938.5 |  |  | 1897.5 |  |  | 2033 |  |  | 1903 |  |  | 1860 |  |  | 1919 |  |  | 1900.5 |  |  | 1904 |  |  | 1992.5 |  |  | 1952 |  |  | 1903 |  |  | 1956.5 |  |  | 1915.5 |  |  | 1856 |  |  | 1863.5 |  |  | 1907 |  |  | 1986 |  |  | 1889 |  |  | 2052 |  |  | 1852 |  |  | 1874 |  |  | 1918 |  |  | 1965 |  |  | 1847 |  |  | 1838.5 |  |  | 1930 |  |  | 1819 |  |  | 1998 |  |  | 1991 |  |  | 1948 |  |  | 1871 |  |  | 1899 |  |  | 1988.5 |  |  | 1945 |  |  | 1980.5 |  |  | 1995 |  |  | 1898 |  |  | 2028.5 |  |  | 1974 |  |  | 2100.5 |  |  | 1912 |  |  | 1757 |  |  | 1913.5 |  |  | 1994 |  |  | 2021.5 |  |  | 1956 |  |  | 1846 |  |  | 2030.5 |  |  | 1948.5 |  |  | 1972 |  |  | 1941.5 |  |  | 1938.5 |  |  | 1914 |  |  | 1971 |  |  | 2127.5 |  |  | 1852.5 |  |  | 1980.5 |  |  | 2020 |  |  | 2039 |  |  | 1917 |  |  | 2023 |  |  | 1995 |  |  | 1958.5 |  |  | 1891 |  |  | 1857.5 |  |  | 1964.5 |  |  | 1973 |  |  | 2037 |  |  | 2141.5 |  |  | 1837.5 |  |  | 1915 |  |  | 1995.5 |  |  | 1887.5 |  |  | 1983 |  |  | 1834 |  |  | 1881 |  |  | 1898.5 |  |  | 2042 |  |  | 1933.5 |  |  | 1938.5 |  |  | 1877 |  |  | 1876.5 |  |  | 1919 |  |  | 1972 |  |  | 1980 |  |  | 1940 |  |  | 1782 |  |  | 2053 |  |  | 2056 |  |  | 1975 |  |  | 2081 |  |  | 1894 |  |  | 1945.5 |  |  | 2067.5 |  |  | 1934 |  |  | 1898 |  |  | 2044 |  |  | 2005.5 |  |  | 2020.5 |  |  | 2022.5 |  |  | 1899 |  |  | 1945 |  |  | 2072.5 |  |  | 1963.5 |  |  | 1830.5 |  |  | 2048 |  |  | 2067 |  |  | 1935 |  |  | 1983 |  |  | 2007 |  |  | 1944.5 |  |  | 1885.5 |  |  | 2010 |  |  | 1911 |  |  | 1894 |  |  | 2050 |  |  | 1932 |  |  | 2001.5 |  |  | 1962 |  |  | 1952 |  |  | 1960 |  |  | 1896 |  |  | 1938.5 |  |  | 2070 |  |  | 1952 |  |  | 1914 |  |  | 2072 |  |  | 2048.5 |  |  | 2003 |  |  | 1873 |  |  | 1925 |  |  | 2030.5 |  |  | 1934.5 |  |  | 2043.5 |  |  | 2062 |  |  | 1919 |  |  | 1879 |  |  | 2082 |  |  | 1970 |  |  | 1850.5 |  |  | 2020 |  |  | 1936.5 |  |  | 1987.5 |  |  | 1983.5 |  |  | 1990 |  |  | 2110.5 |  |  | 1865 |  |  | 1886 |  |  | 1939.5 |  |  | 1968.5 |  |  | 2022 |  |  | 2036.5 |  |  | 2075.5 |  |  | 1927 |  |  | 2015 |  |  | 1921.5 |  |  | 1880.5 |  |  | 2074 |  |  | 1972.5 |  |  | 2018 |  |  | 1916 |  |  | 1907.5 |  |  | 2033 |  |  | 1896 |  |  | 1960.5 |  |  | 1942 |  |  | 2117.5 |  |  | 1913 |  |  | 2146 |  |  | 1952 |  |  | 1899 |  |  | 2062.5 |  |  | 2082 |  |  | 2070.5 |  |  | 1834.5 |  |  | 2039.5 |  |  | 2005 |  |  | 2045.5 |  |  | 2161 |  |  | 2022 |  |  | 1789.5 |  |  | 1954.5 |  |  | 2007 |  |  | 1906.5 |  |  | 2041 |  |  | 1928 |  |  | 2085.5 |  |  | 1917 |  |  | 1891.5 |  |  | 1972.5 |  |  | 1975.5 |  |  | 1887 |  |  | 1810 |  |  | 1866 |  |  | 1900.5 |  |  | 1945 |  |  | 2108.5 |  |  | 1990 |  |  | 1928 |  |  | 1891 |  |  | 1975 |  |  | 2000 |  |  | 1986 |  |  | 1918 |  |  | 2093 |  |  | 1971 |  |  | 1910.5 |  |  | 1975 |  |  | 1920 |  |  | 2050.5 |  |  | 1845.5 |  |  | 1983.5 |  |  | 2004.5 |  |  | 1935 |  |  | 2081 |  |  | 1852.5 |  |  | 2045.5 |  |  | 1957.5 |  |  | 1936 |  |  | 1940 |  |  | 1880 |  |  | 1950 |  |  | 1806 |  |  | 1930 |  |  | 1978 |  |  | 1948.5 |  |  | 1990.5 |  |  | 1880 |  |  | 1898.5 |  |  | 1955.5 |  |  | 1844 |  |  | 2016 |  |  | 1904 |  |  | 1956 |  |  | 1858.5 |  |  | 1856.5 |  |  | 2008.5 |  |  | 1975 |  |  | 1911.5 |  |  | 1998 |  |  | 1954 |  |  | 2064 |  |  | 1870.5 |  |  | 1933 |  |  | 1849 |  |  | 1927.5 |  |  | 1907 |  |  | 2004.5 |  |  | 2116 |  |  | 1937.5 |  |  | 1898 |  |  | 1939.5 |  |  | 1984.5 |  |  | 2015 |  |  | 1922 |  |  | 1810 |  |  | 2000 |  |  | 1822.5 |  |  | 1896 |  |  | 2074 |  |  | 1854.5 |  |  | 2041.5 |  |  | 1899.5 |  |  | 1883 |  |  | 2012.5 |  |  | 1955.5 |  |  | 1843.5 |  |  | 2041 |  |  | 1980 |  |  | 2004.5 |  |  | 2004 |  |  | 2087 |  |  | 1966.5 |  |  | 1930 |  |  | 2049 |  |  | 1988 |  |  | 1821 |  |  | 1788.5 |  |  | 2020.5 |  |  | 1829 |  |  | 2012 |  |  | 1985 |  |  | 1899 |  |  | 1913 |  |  | 1905.5 |  |  | 1901.5 |  |  | 2001 |  |  | 2067 |  |  | 2096 |  |  | 1892.5 |  |  | 2123.5 |  |  | 1933 |  |  | 1944 |  |  | 1848 |  |  | 1976.5 |  |  | 2126.5 |  |  | 1997 |  |  | 1832 |  |  | 1990 |  |  | 1968 |  |  | 1951 |  |  | 2087 |  |  | 1869 |  |  | 2061.5 |  |  | 1885 |  |  | 2053 |  |  | 1995 |  |  | 1999.5 |  |  | 2029 |  |  | 1881 |  |  | 1776 |  |  | 1955 |  |  | 1944 |  |  | 1995 |  |  | 2004 |  |  | 1886.5 |  |  | 1940.5 |  |  | 1777.5 |  |  | 2027 |  |  | 1921 |  |  | 1938.5 |  |  | 1807 |  |  | 1840.5 |  |  | 1961.5 |  |  | 1916 |  |  | 1982 |  |  | 1935.5 |  |  | 1992 |  |  | 1976 |  |  | 1939 |  |  | 1967 |  |  | 1959 |  |  | 1927 |  |  | 1907 |  |  | 2001.5 |  |  | 1952 |  |  | 1984 |  |  | 1987 |  |  | 1938 |  |  | 1957 |  |  | 1959 |  |  | 2123 |  |  | 1958 |  |  | 1961 |  |  | 2059.5 |  |  | 1967.5 |  |  | 1952.5 |  |  | 2035.5 |  |  | 1978 |  |  | 1803 |  |  | 2071.5 |  |  | 1900 |  |  | 1947 |  |  | 1873.5 |  |  | 2089.5 |  |  | 2032 |  |  | 1964.5 |  |  | 1919.5 |  |  | 1831 |  |  | 2032 |  |  | 1905 |  |  | 1907 |  |  | 1952.5 |  |  | 1960 |  |  | 1872.5 |  |  | 1825.5 |  |  | 1929 |  |  | 1885 |  |  | 2018.5 |  |  | 1902 |  |  | 1960.5 |  |  | 1999 |  |  | 1978.5 |  |  | 1837.5 |  |  | 1807.5 |  |  | 1989.5 |  |  | 1983.5 |  |  | 1791 |  |  | 1847 |  |  | 2075.5 |  |  | 1990 |  |  | 1872 |  |  | 1937 |  |  | 2029 |  |  | 2064.5 |  |  | 1820 |  |  | 1883 |  |  | 1993 |  |  | 1905.5 |  |  | 1966 |  |  | 1856 |  |  | 1931 |  |  | 2113.5 |  |  | 2003 |  |  | 1768 |  |  | 1973 |  |  | 2066 |  |  | 2205.5 |  |  | 2011 |  |  | 1865.5 |  |  | 1935 |  |  | 1990 |  |  | 2154.5 |  |  | 2005 |  |  | 1887 |  |  | 1933.5 |  |  | 2002 |  |  | 1917 |  |  | 1933 |  |  | 2123.5 |  |  | 1976.5 |  |  | 1968 |  |  | 1868 |  |  | 1935.5 |  |  | 1972.5 |  |  | 1943 |  |  | 2020 |  |  | 1998.5 |  |  | 2110.5 |  |  | 1849.5 |  |  | 1985.5 |  |  | 1917.5 |  |  | 2136 |  |  | 1917.5 |  |  | 1971 |  |  | 1945 |  |  | 1992 |  |  | 2051 |  |  | 1974.5 |  |  | 1968 |  |  | 1848 |  |  | 2004.5 |  |  | 1960.5 |  |  | 1878 |  |  | 2026.5 |  |  | 1952.5 |  |  | 2077 |  |  | 1841 |  |  | 1942 |  |  | 2008.5 |  |  | 1991 |  |  | 2027.5 |  |  | 2011 |  |  | 1927 |  |  | 2158.5 |  |  | 1920 |  |  | 2058 |  |  | 1878 |  |  | 2010 |  |  | 1987 |  |  | 1958 |  |  | 2002 |  |  | 1971 |  |  | 1850.5 |  |  | 1936.5 |  |  | 1884 |  |  | 1978.5 |  |  | 1803.5 |  |  | 1872 |  |  | 1880 |  |  | 2017 |  |  | 2064.5 |  |  | 1881.5 |  |  | 2017 |  |  | 2014 |  |  | 1849 |  |  | 1861 |  |  | 1919 |  |  | 1903 |  |  | 2056 |  |  | 1893.5 |  |  | 2054 |  |  | 1976 |  |  | 2061 |  |  | 1895 |  |  | 1812 |  |  | 1922.5 |  |  | 2123.5 |  |  | 1796.5 |  |  | 1857 |  |  | 1893 |  |  | 1863.5 |  |  | 2069.5 |  |  | 1978.5 |  |  | 1890 |  |  | 2037.5 |  |  | 1984.5 |  |  | 2109 |  |  | 2007.5 |  |  | 1974.5 |  |  | 1929 |  |  | 1864 |  |  | 1931 |  |  | 2020 |  |  | 1933 |  |  | 1788 |  |  | 2002 |  |  | 2093 |  |  | 1844 |  |  | 1895 |  |  | 2075.5 |  |  | 1934 |  |  | 1979 |  |  | 1858 |  |  | 1927.5 |  |  | 1930 |  |  | 1956.5 |  |  | 2068 |  |  | 2016 |  |  | 1922 |  |  | 1981 |  |  | 2056.5 |  |  | 1912 |  |  | 1874 |  |  | 2001.5 |  |  | 1989 |  |  | 1924 |  |  | 1873.5 |  |  | 1921.5 |  |  | 1963 |  |  | 1874.5 |  |  | 2064 |  |  | 1915.5 |  |  | 2063 |  |  | 2002 |  |  | 1877.5 |  |  | 2053.5 |  |  | 1938 |  |  | 2057 |  |  | 1966 |  |  | 1991 |  |  | 1841 |  |  | 1999 |  |  | 1799 |  |  | 1820 |  |  | 2085.5 |  |  | 1830 |  |  | 2044.5 |  |  | 1943 |  |  | 1994.5 |  |  | 1913.5 |  |  | 1913 |  |  | 1972 |  |  | 2021.5 |  |  | 1947 |  |  | 1987 |  |  | 2016 |  |  | 1902.5 |  |  | 2008 |  |  | 1839.5 |  |  | 1770 |  |  | 1901 |  |  | 1972 |  |  | 1965 |  |  | 2055.5 |  |  | 1880 |  |  | 1924 |  |  | 1969 |  |  | 1841.5 |  |  | 2077 |  |  | 2041 |  |  | 1956 |  |  | 1938 |  |  | 1914.5 |  |  | 1868.5 |  |  | 1975 |  |  | 2069 |  |  | 1969 |  |  | 1996.5 |  |  | 1954 |  |  | 1871 |  |  | 1926 |  |  | 2099.5 |  |  | 1932.5 |  |  | 1930.5 |  |  | 1981 |  |  | 2016 |  |  | 2005 |  |  | 1910.5 |  |  | 2001 |  |  | 1947.5 |  |  | 1832 |  |  | 1855 |  |  | 1941 |  |  | 1920.5 |  |  | 1992.5 |  |  | 1941 |  |  | 1880 |  |  | 2064.5 |  |  | 1950 |  |  | 1950 |  |  | 2015.5 |  |  | 1886 |  |  | 1928 |  |  | 1987.5 |  |  | 1887 |  |  | 1956 |  |  | 1938.5 |  |  | 2121 |  |  | 1886.5 |  |  | 1955 |  |  | 1802.5 |  |  | 2031.5 |  |  | 1797 |  |  | 2076 |  |  | 2007.5 |  |  | 1973.5 |  |  | 2098 |  |  | 1942 |  |  | 1984 |  |  | 1931.5 |  |  | 1955 |  |  | 1756 |  |  | 1910 |  |  | 2065.5 |  |  | 1982.5 |  |  | 1998 |  |  | 2046 |  |  | 1898 |  |  | 1844 |  |  | 2044 |  |  | 1878 |  |  | 1913 |  |  | 1947.5 |  |  | 2124.5 |  |  | 1876.5 |  |  | 1961 |  |  | 1913.5 |  |  | 1982 |  |  | 1899 |  |  | 1990.5 |  |  | 1848.5 |  |  | 1809 |  |  | 1988 |  |  | 1917.5 |  |  | 1967 |  |  | 2002 |  |  | 1882.5 |  |  | 1995.5 |  |  | 1908 |  |  | 1905 |  |  | 1963 |  |  | 1854.5 |  |  | 1865 |  |  | 1854 |  |  | 1966 |  |  | 1967 |  |  | 2039 |  |  | 1897.5 |  |  | 2083 |  |  | 1892 |  |  | 1842 |  |  | 2084.5 |  |  | 1937 |  |  | 1918.5 |  |  | 1854.5 |  |  | 1953 |  |  | 1999 |  |  | 1898.5 |  |  | 1878.5 |  |  | 1869.5 |  |  | 1938.5 |  |  | 1932.5 |  |  | 1978 |  |  | 1951 |  |  | 1942.5 |  |  | 1905.5 |  |  | 1955 |  |  | 1903 |  |  | 1913.5 |  |  | 2072 |  |  | 1927 |  |  | 1787 |  |  | 2000.5 |  |  | 2072 |  |  | 1870.5 |  |  | 1826 |  |  | 1968.5 |  |  | 2078.5 |  |  | 2099.5 |  |  | 2031 |  |  | 1970 |  |  | 1952.5 |  |  | 1927.5 |  |  | 1991 |  |  | 1982 |  |  | 1993.5 |  |  | 2063 |  |  | 1971.5 |  |  | 1906.5 |  |  | 2025 |  |  | 1992 |  |  | 1800.5 |  |  | 2043.5 |  |  | 1946 |  |  | 1911.5 |  |  | 1970.5 |  |  | 1993 |  |  | 2022 |  |  | 2085 |  |  | 1920.5 |  |  | 2050 |  |  | 1902 |  |  | 1977 |  |  | 1891 |  |  | 1910 |  |  | 1871 |  |  | 2034.5 |  |  | 1900.5 |  |  | 1938 |  |  | 1907 |  |  | 2004 |  |  | 1961.5 |  |  | 1927 |  |  | 2074 |  |  | 1858.5 |  |  | 1989.5 |  |  | 1927 |  |  | 1887.5 |  |  | 1990 |  |  | 1835 |  |  | 1964 |  |  | 2084.5 |  |  | 2083 |  |  | 1822.5 |  |  | 1906.5 |  |  | 1832 |  |  | 1964.5 |  |  | 1758.5 |  |  | 1849 |  |  | 1815 |  |  | 2050 |  |  | 1850.5 |  |  | 1811 |  |  | 1942.5 |  |  | 1926.5 |  |  | 1992 |  |  | 1846.5 |  |  | 1872 |  |  | 1981 |  |  | 1923 |  |  | 1844 |  |  | 1842 |  |  | 2034.5 |  |  | 1938 |  |  | 2047 |  |  | 1883 |  |  | 2016 |  |  | 1951.5 |  |  | 1998.5 |  |  | 1919 |  |  | 1976 |  |  | 2001 |  |  | 1930 |  |  | 2034 |  |  | 1885.5 |  |  | 1969 |  |  | 2007.5 |  |  | 2061 |  |  | 1825 |  |  | 1909 |  |  | 1928 |  |  | 1982.5 |  |  | 1956 |  |  | 2009.5 |  |  | 1891 |  |  | 2093 |  |  | 2012 |  |  | 1953.5 |  |  | 1897 |  |  | 1794 |  |  | 1851 |  |  | 2081 |  |  | 2147 |  |  | 1902.5 |  |  | 1981.5 |  |  | 1888 |  |  | 1907.5 |  |  | 1905 |  |  | 1858.5 |  |  | 1907.5 |  |  | 1872.5 |  |  | 1910.5 |  |  | 1836 |  |  | 2088 |  |  | 1857 |  |  | 1880 |  |  | 1954 |  |  | 2030 |  |  | 1888.5 |  |  | 1884.5 |  |  | 2020.5 |  |  | 2000 |  |  | 2002.5 |  |  | 1897.5 |  |  | 2003.5 |  |  | 1880.5 |  |  | 1928 |  |  | 1948.5 |  |  | 1960.5 |  |  | 2031 |  |  | 1885.5 |  |  | 2098.5 |  |  | 1996.5 |  |  | 2101 |  |  | 1968.5 |  |  | 1973 |  |  | 1964 |  |  | 1918.5 |  |  | 2010.5 |  |  | 1996 |  |  | 1988 |  |  | 1829.5 |  |  | 1792.5 |  |  | 1940.5 |  |  | 2013 |  |  | 1897 |  |  | 1941 |  |  | 2006.5 |  |  | 2004.5 |  |  | 1977 |  |  | 2004.5 |  |  | 1835 |  |  | 1980 |  |  | 1985.5 |  |  | 1916.5 |  |  | 1907 |  |  | 1983.5 |  |  | 1965 |  |  | 1855.5 |  |  | 2074.5 |  |  | 2010 |  |  | 1919.5 |  |  | 2033 |  |  | 1965.5 |  |  | 1910 |  |  | 2009 |  |  | 1998 |  |  | 1924.5 |  |  | 1822.5 |  |  | 2008 |  |  | 1895 |  |  | 1867 |  |  | 1915.5 |  |  | 1934.5 |  |  | 2009 |  |  | 1972.5 |  |  | 1927 |  |  | 1838.5 |  |  | 1960.5 |  |  | 1869 |  |  | 1944 |  |  | 1926 |  |  | 1896.5 |  |  | 1908 |  |  | 2000.5 |  |  | 2014 |  |  | 1940.5 |  |  | 2115 |  |  | 1802.5 |  |  | 1922 |  |  | 1951.5 |  |  | 1960.5 |  |  | 1924 |  |  | 1940 |  |  | 2118 |  |  | 1916 |  |  | 2052.5 |  |  | 1850 |  |  | 1886.5 |  |  | 1797 |  |  | 1897 |  |  | 1861 |  |  | 2026 |  |  | 1969 |  |  | 1919 |  |  | 2041 |  |  | 1919.5 |  |  | 1872 |  |  | 2005
69 |  | 2168.5 |  |  | 2109 |  |  | 2043.5 |  |  | 1957 |  |  | 1916.5 |  |  | 2049 |  |  | 1980 |  |  | 2044 |  |  | 1850.5 |  |  | 1918 |  |  | 1931 |  |  | 2077 |  |  | 2076 |  |  | 2172 |  |  | 1946.5 |  |  | 2022.5 |  |  | 1896 |  |  | 1998 |  |  | 2096 |  |  | 1933.5 |  |  | 2022 |  |  | 2026 |  |  | 1876 |  |  | 1999 |  |  | 1956.5 |  |  | 2111 |  |  | 1983 |  |  | 1986 |  |  | 2052 |  |  | 1911 |  |  | 2016 |  |  | 1950.5 |  |  | 2079.5 |  |  | 1979.5 |  |  | 1890 |  |  | 1917.5 |  |  | 1947.5 |  |  | 2067.5 |  |  | 2044 |  |  | 1986 |  |  | 1871.5 |  |  | 1921 |  |  | 2040.5 |  |  | 1941.5 |  |  | 2043.5 |  |  | 2204.5 |  |  | 2151.5 |  |  | 1956 |  |  | 1859 |  |  | 1936.5 |  |  | 1962 |  |  | 1892.5 |  |  | 1866.5 |  |  | 2024 |  |  | 1969 |  |  | 1959 |  |  | 1917 |  |  | 2093 |  |  | 2037 |  |  | 1956.5 |  |  | 1992.5 |  |  | 1979.5 |  |  | 1898 |  |  | 1977 |  |  | 1853 |  |  | 1898.5 |  |  | 1943 |  |  | 1947.5 |  |  | 2014.5 |  |  | 2155.5 |  |  | 1955 |  |  | 2120 |  |  | 2071 |  |  | 2015.5 |  |  | 2039.5 |  |  | 1937.5 |  |  | 2036.5 |  |  | 1947.5 |  |  | 1988.5 |  |  | 1969.5 |  |  | 1928.5 |  |  | 1890 |  |  | 2023 |  |  | 1941 |  |  | 2058.5 |  |  | 2114 |  |  | 1948.5 |  |  | 2004 |  |  | 2029 |  |  | 2055.5 |  |  | 2119.5 |  |  | 1982 |  |  | 2143 |  |  | 1920.5 |  |  | 2044 |  |  | 1909.5 |  |  | 1980.5 |  |  | 2004.5 |  |  | 1900.5 |  |  | 1917.5 |  |  | 1981 |  |  | 1976 |  |  | 1831 |  |  | 1978.5 |  |  | 1935.5 |  |  | 2044.5 |  |  | 1945.5 |  |  | 1967 |  |  | 1948 |  |  | 1991.5 |  |  | 1807 |  |  | 2009.5 |  |  | 1994 |  |  | 1912 |  |  | 1847.5 |  |  | 1946 |  |  | 1991 |  |  | 1900 |  |  | 2010 |  |  | 1957.5 |  |  | 1964.5 |  |  | 1921.5 |  |  | 2054 |  |  | 1942 |  |  | 1889 |  |  | 1945 |  |  | 1939.5 |  |  | 1930 |  |  | 2018.5 |  |  | 1973 |  |  | 1932 |  |  | 1982.5 |  |  | 1954.5 |  |  | 1895 |  |  | 1902.5 |  |  | 1946 |  |  | 2025 |  |  | 1913 |  |  | 2099 |  |  | 1891 |  |  | 1913 |  |  | 1957 |  |  | 1994 |  |  | 1871 |  |  | 1877.5 |  |  | 1956 |  |  | 1845 |  |  | 2037 |  |  | 2006 |  |  | 1995 |  |  | 1895 |  |  | 1923 |  |  | 2014.5 |  |  | 1992 |  |  | 2019.5 |  |  | 2042 |  |  | 1913 |  |  | 2067.5 |  |  | 1998 |  |  | 2121.5 |  |  | 1941 |  |  | 1783 |  |  | 1952.5 |  |  | 2041 |  |  | 2068.5 |  |  | 1980 |  |  | 1875 |  |  | 2045.5 |  |  | 1995.5 |  |  | 2011 |  |  | 1970.5 |  |  | 1964.5 |  |  | 1938 |  |  | 2018 |  |  | 2156.5 |  |  | 1867.5 |  |  | 2009.5 |  |  | 2059 |  |  | 2060 |  |  | 1956 |  |  | 2052 |  |  | 2024 |  |  | 1982.5 |  |  | 1938 |  |  | 1883.5 |  |  | 1988.5 |  |  | 1988 |  |  | 2076 |  |  | 2165.5 |  |  | 1876.5 |  |  | 1954 |  |  | 2034.5 |  |  | 1908.5 |  |  | 1998 |  |  | 1873 |  |  | 1896 |  |  | 1945.5 |  |  | 2071 |  |  | 1948.5 |  |  | 1985.5 |  |  | 1903 |  |  | 1897.5 |  |  | 1948 |  |  | 1993 |  |  | 2019 |  |  | 1987 |  |  | 1797 |  |  | 2092 |  |  | 2082 |  |  | 1990 |  |  | 2102 |  |  | 1933 |  |  | 1971.5 |  |  | 2106.5 |  |  | 1963 |  |  | 1927 |  |  | 2091 |  |  | 2020.5 |  |  | 2041.5 |  |  | 2046.5 |  |  | 1925 |  |  | 1984 |  |  | 2101.5 |  |  | 2010.5 |  |  | 1856.5 |  |  | 2063 |  |  | 2082 |  |  | 1959 |  |  | 2004 |  |  | 2033 |  |  | 1965.5 |  |  | 1909.5 |  |  | 2049 |  |  | 1932 |  |  | 1918 |  |  | 2089 |  |  | 1956 |  |  | 2048.5 |  |  | 2001 |  |  | 1973 |  |  | 1986 |  |  | 1917 |  |  | 1962.5 |  |  | 2109 |  |  | 1981 |  |  | 1938 |  |  | 2087 |  |  | 2063.5 |  |  | 2032 |  |  | 1888 |  |  | 1940 |  |  | 2045.5 |  |  | 1981.5 |  |  | 2072.5 |  |  | 2101 |  |  | 1940 |  |  | 1894 |  |  | 2129 |  |  | 1996 |  |  | 1876.5 |  |  | 2067 |  |  | 1983.5 |  |  | 2034.5 |  |  | 2007.5 |  |  | 2016 |  |  | 2157.5 |  |  | 1889 |  |  | 1912 |  |  | 1968.5 |  |  | 2015.5 |  |  | 2046 |  |  | 2057.5 |  |  | 2122.5 |  |  | 1974 |  |  | 2030 |  |  | 1960.5 |  |  | 1919.5 |  |  | 2098 |  |  | 1987.5 |  |  | 2047 |  |  | 1942 |  |  | 1936.5 |  |  | 2054 |  |  | 1922 |  |  | 1989.5 |  |  | 1957 |  |  | 2164.5 |  |  | 1960 |  |  | 2193 |  |  | 1967 |  |  | 1920 |  |  | 2101.5 |  |  | 2121 |  |  | 2085.5 |  |  | 1873.5 |  |  | 2068.5 |  |  | 2052 |  |  | 2069.5 |  |  | 2185 |  |  | 2046 |  |  | 1804.5 |  |  | 1993.5 |  |  | 2046 |  |  | 1932.5 |  |  | 2080 |  |  | 1957 |  |  | 2132.5 |  |  | 1932 |  |  | 1938.5 |  |  | 2011.5 |  |  | 2014.5 |  |  | 1911 |  |  | 1825 |  |  | 1905 |  |  | 1947.5 |  |  | 1974 |  |  | 2137.5 |  |  | 2029 |  |  | 1954 |  |  | 1912 |  |  | 2014 |  |  | 2029 |  |  | 2007 |  |  | 1965 |  |  | 2140 |  |  | 2010 |  |  | 1939.5 |  |  | 1990 |  |  | 1959 |  |  | 2089.5 |  |  | 1866.5 |  |  | 2030.5 |  |  | 2019.5 |  |  | 1974 |  |  | 2105 |  |  | 1881.5 |  |  | 2071.5 |  |  | 1972.5 |  |  | 1975 |  |  | 1979 |  |  | 1906 |  |  | 1976 |  |  | 1853 |  |  | 1954 |  |  | 2017 |  |  | 1963.5 |  |  | 2014.5 |  |  | 1919 |  |  | 1919.5 |  |  | 1994.5 |  |  | 1891 |  |  | 2063 |  |  | 1919 |  |  | 1977 |  |  | 1873.5 |  |  | 1871.5 |  |  | 2047.5 |  |  | 2004 |  |  | 1926.5 |  |  | 2013 |  |  | 1993 |  |  | 2085 |  |  | 1894.5 |  |  | 1948 |  |  | 1878 |  |  | 1966.5 |  |  | 1931 |  |  | 2043.5 |  |  | 2142 |  |  | 1976.5 |  |  | 1913 |  |  | 1986.5 |  |  | 2008.5 |  |  | 2041 |  |  | 1946 |  |  | 1839 |  |  | 2026 |  |  | 1837.5 |  |  | 1925 |  |  | 2121 |  |  | 1901.5 |  |  | 2065.5 |  |  | 1920.5 |  |  | 1930 |  |  | 2059.5 |  |  | 1994.5 |  |  | 1882.5 |  |  | 2067 |  |  | 2006 |  |  | 2019.5 |  |  | 2051 |  |  | 2102 |  |  | 2013.5 |  |  | 1969 |  |  | 2088 |  |  | 2012 |  |  | 1842 |  |  | 1817.5 |  |  | 2041.5 |  |  | 1876 |  |  | 2059 |  |  | 2014 |  |  | 1946 |  |  | 1939 |  |  | 1929.5 |  |  | 1927.5 |  |  | 2030 |  |  | 2091 |  |  | 2135 |  |  | 1916.5 |  |  | 2147.5 |  |  | 1972 |  |  | 1983 |  |  | 1872 |  |  | 2005.5 |  |  | 2152.5 |  |  | 2026 |  |  | 1871 |  |  | 2014 |  |  | 1997 |  |  | 1980 |  |  | 2126 |  |  | 1908 |  |  | 2100.5 |  |  | 1914 |  |  | 2079 |  |  | 2021 |  |  | 2038.5 |  |  | 2044 |  |  | 1905 |  |  | 1797 |  |  | 1970 |  |  | 1965 |  |  | 2010 |  |  | 2019 |  |  | 1915.5 |  |  | 1966.5 |  |  | 1792.5 |  |  | 2074 |  |  | 1942 |  |  | 1977.5 |  |  | 1828 |  |  | 1869.5 |  |  | 1985.5 |  |  | 1955 |  |  | 2003 |  |  | 1974.5 |  |  | 2016 |  |  | 1997 |  |  | 1986 |  |  | 1991 |  |  | 1998 |  |  | 1966 |  |  | 1922 |  |  | 2030.5 |  |  | 1973 |  |  | 2023 |  |  | 2008 |  |  | 1964 |  |  | 1986 |  |  | 2006 |  |  | 2138 |  |  | 1997 |  |  | 1985 |  |  | 2098.5 |  |  | 2006.5 |  |  | 1981.5 |  |  | 2059.5 |  |  | 2007 |  |  | 1818 |  |  | 2097.5 |  |  | 1939 |  |  | 1971 |  |  | 1912.5 |  |  | 2136.5 |  |  | 2056 |  |  | 1979.5 |  |  | 1966.5 |  |  | 1855 |  |  | 2079 |  |  | 1952 |  |  | 1946 |  |  | 1967.5 |  |  | 1989 |  |  | 1896.5 |  |  | 1864.5 |  |  | 1958 |  |  | 1924 |  |  | 2057.5 |  |  | 1926 |  |  | 1989.5 |  |  | 2025 |  |  | 2002.5 |  |  | 1858.5 |  |  | 1836.5 |  |  | 2004.5 |  |  | 2009.5 |  |  | 1830 |  |  | 1886 |  |  | 2101.5 |  |  | 2029 |  |  | 1911 |  |  | 1963 |  |  | 2058 |  |  | 2111.5 |  |  | 1846 |  |  | 1930 |  |  | 2032 |  |  | 1929.5 |  |  | 1987 |  |  | 1882 |  |  | 1955 |  |  | 2160.5 |  |  | 2024 |  |  | 1789 |  |  | 1997 |  |  | 2095 |  |  | 2244.5 |  |  | 2035 |  |  | 1904.5 |  |  | 1964 |  |  | 2037 |  |  | 2201.5 |  |  | 2052 |  |  | 1926 |  |  | 1954.5 |  |  | 2017 |  |  | 1943 |  |  | 1948 |  |  | 2170.5 |  |  | 2015.5 |  |  | 2007 |  |  | 1889 |  |  | 1961.5 |  |  | 1987.5 |  |  | 1982 |  |  | 2041 |  |  | 2019.5 |  |  | 2157.5 |  |  | 1878.5 |  |  | 2011.5 |  |  | 1938.5 |  |  | 2160 |  |  | 1956.5 |  |  | 2018 |  |  | 1971 |  |  | 2018 |  |  | 2075 |  |  | 1998.5 |  |  | 2007 |  |  | 1872 |  |  | 2033.5 |  |  | 1984.5 |  |  | 1902 |  |  | 2055.5 |  |  | 1981.5 |  |  | 2092 |  |  | 1862 |  |  | 1971 |  |  | 2055.5 |  |  | 2030 |  |  | 2066.5 |  |  | 2050 |  |  | 1951 |  |  | 2197.5 |  |  | 1949 |  |  | 2079 |  |  | 1902 |  |  | 2025 |  |  | 2026 |  |  | 2005 |  |  | 2017 |  |  | 2010 |  |  | 1865.5 |  |  | 1957.5 |  |  | 1905 |  |  | 2002.5 |  |  | 1818.5 |  |  | 1896 |  |  | 1906 |  |  | 2056 |  |  | 2103.5 |  |  | 1920.5 |  |  | 2043 |  |  | 2035 |  |  | 1878 |  |  | 1887 |  |  | 1958 |  |  | 1929 |  |  | 2071 |  |  | 1908.5 |  |  | 2083 |  |  | 2000 |  |  | 2100 |  |  | 1942 |  |  | 1851 |  |  | 1961.5 |  |  | 2149.5 |  |  | 1822.5 |  |  | 1886 |  |  | 1914 |  |  | 1878.5 |  |  | 2098.5 |  |  | 2017.5 |  |  | 1919 |  |  | 2066.5 |  |  | 2008.5 |  |  | 2148 |  |  | 2054.5 |  |  | 2000.5 |  |  | 1976 |  |  | 1879 |  |  | 1952 |  |  | 2059 |  |  | 1957 |  |  | 1814 |  |  | 2023 |  |  | 2122 |  |  | 1891 |  |  | 1942 |  |  | 2090.5 |  |  | 1960 |  |  | 2000 |  |  | 1882 |  |  | 1956.5 |  |  | 1945 |  |  | 1995.5 |  |  | 2107 |  |  | 2045 |  |  | 1969 |  |  | 2010 |  |  | 2095.5 |  |  | 1933 |  |  | 1895 |  |  | 2048.5 |  |  | 2028 |  |  | 1945 |  |  | 1912.5 |  |  | 1936.5 |  |  | 1978 |  |  | 1913.5 |  |  | 2111 |  |  | 1939.5 |  |  | 2102 |  |  | 2026 |  |  | 1903.5 |  |  | 2092.5 |  |  | 1967 |  |  | 2081 |  |  | 2013 |  |  | 2015 |  |  | 1870 |  |  | 2014 |  |  | 1814 |  |  | 1859 |  |  | 2100.5 |  |  | 1869 |  |  | 2059.5 |  |  | 1964 |  |  | 2033.5 |  |  | 1934.5 |  |  | 1942 |  |  | 1987 |  |  | 2050.5 |  |  | 1973 |  |  | 2026 |  |  | 2040 |  |  | 1949.5 |  |  | 2034 |  |  | 1886.5 |  |  | 1799 |  |  | 1940 |  |  | 1987 |  |  | 2012 |  |  | 2079.5 |  |  | 1919 |  |  | 1963 |  |  | 2016 |  |  | 1867.5 |  |  | 2106 |  |  | 2080 |  |  | 1985 |  |  | 1967 |  |  | 1961.5 |  |  | 1894.5 |  |  | 2014 |  |  | 2108 |  |  | 1984 |  |  | 2035.5 |  |  | 1993 |  |  | 1886 |  |  | 1965 |  |  | 2120.5 |  |  | 1956.5 |  |  | 1959.5 |  |  | 1996 |  |  | 2040 |  |  | 2034 |  |  | 1931.5 |  |  | 2027 |  |  | 1962.5 |  |  | 1847 |  |  | 1884 |  |  | 1962 |  |  | 1946.5 |  |  | 2018.5 |  |  | 1988 |  |  | 1919 |  |  | 2090.5 |  |  | 1997 |  |  | 1979 |  |  | 2036.5 |  |  | 1933 |  |  | 1943 |  |  | 2013.5 |  |  | 1913 |  |  | 2003 |  |  | 1967.5 |  |  | 2136 |  |  | 1925.5 |  |  | 1994 |  |  | 1823.5 |  |  | 2055.5 |  |  | 1812 |  |  | 2097 |  |  | 2031.5 |  |  | 1994.5 |  |  | 2119 |  |  | 1981 |  |  | 2023 |  |  | 1970.5 |  |  | 2002 |  |  | 1771 |  |  | 1934 |  |  | 2089.5 |  |  | 2029.5 |  |  | 2019 |  |  | 2067 |  |  | 1937 |  |  | 1883 |  |  | 2068 |  |  | 1925 |  |  | 1937 |  |  | 1986.5 |  |  | 2139.5 |  |  | 1915.5 |  |  | 1985 |  |  | 1960.5 |  |  | 2006 |  |  | 1946 |  |  | 2029.5 |  |  | 1895.5 |  |  | 1856 |  |  | 2009 |  |  | 1941.5 |  |  | 2014 |  |  | 2041 |  |  | 1897.5 |  |  | 2042.5 |  |  | 1955 |  |  | 1934 |  |  | 2002 |  |  | 1875.5 |  |  | 1904 |  |  | 1883 |  |  | 2005 |  |  | 2006 |  |  | 2086 |  |  | 1918.5 |  |  | 2104 |  |  | 1921 |  |  | 1881 |  |  | 2099.5 |  |  | 1984 |  |  | 1942.5 |  |  | 1901.5 |  |  | 1979 |  |  | 2046 |  |  | 1937.5 |  |  | 1925.5 |  |  | 1884.5 |  |  | 1967.5 |  |  | 1971.5 |  |  | 2025 |  |  | 1980 |  |  | 1981.5 |  |  | 1920.5 |  |  | 1976 |  |  | 1929 |  |  | 1942.5 |  |  | 2111 |  |  | 1956 |  |  | 1813 |  |  | 2029.5 |  |  | 2093 |  |  | 1917.5 |  |  | 1841 |  |  | 1983.5 |  |  | 2117.5 |  |  | 2128.5 |  |  | 2078 |  |  | 1996 |  |  | 1976.5 |  |  | 1948.5 |  |  | 2015 |  |  | 2008 |  |  | 2014.5 |  |  | 2092 |  |  | 1995.5 |  |  | 1930.5 |  |  | 2072 |  |  | 2007 |  |  | 1839.5 |  |  | 2082.5 |  |  | 1961 |  |  | 1926.5 |  |  | 1996.5 |  |  | 2040 |  |  | 2061 |  |  | 2100 |  |  | 1949.5 |  |  | 2089 |  |  | 1923 |  |  | 2016 |  |  | 1917 |  |  | 1957 |  |  | 1918 |  |  | 2073.5 |  |  | 1947.5 |  |  | 1959 |  |  | 1936 |  |  | 2019 |  |  | 1976.5 |  |  | 1951 |  |  | 2103 |  |  | 1897.5 |  |  | 2028.5 |  |  | 1948 |  |  | 1926.5 |  |  | 2029 |  |  | 1850 |  |  | 1988 |  |  | 2108.5 |  |  | 2109 |  |  | 1861.5 |  |  | 1945.5 |  |  | 1871 |  |  | 2011.5 |  |  | 1805.5 |  |  | 1896 |  |  | 1854 |  |  | 2089 |  |  | 1897.5 |  |  | 1850 |  |  | 1957.5 |  |  | 1965.5 |  |  | 2039 |  |  | 1867.5 |  |  | 1896 |  |  | 2005 |  |  | 1952 |  |  | 1873 |  |  | 1881 |  |  | 2081.5 |  |  | 1977 |  |  | 2068 |  |  | 1907 |  |  | 2055 |  |  | 1972.5 |  |  | 2013.5 |  |  | 1966 |  |  | 2023 |  |  | 2030 |  |  | 1959 |  |  | 2060 |  |  | 1914.5 |  |  | 1998 |  |  | 2031.5 |  |  | 2082 |  |  | 1854 |  |  | 1933 |  |  | 1952 |  |  | 2021.5 |  |  | 2003 |  |  | 2024.5 |  |  | 1930 |  |  | 2119 |  |  | 2051 |  |  | 1982.5 |  |  | 1912 |  |  | 1833 |  |  | 1875 |  |  | 2128 |  |  | 2194 |  |  | 1923.5 |  |  | 2020.5 |  |  | 1927 |  |  | 1946.5 |  |  | 1934 |  |  | 1905.5 |  |  | 1931.5 |  |  | 1911.5 |  |  | 1931.5 |  |  | 1875 |  |  | 2127 |  |  | 1872 |  |  | 1904 |  |  | 1969 |  |  | 2069 |  |  | 1917.5 |  |  | 1910.5 |  |  | 2049.5 |  |  | 2024 |  |  | 2041.5 |  |  | 1921.5 |  |  | 2024.5 |  |  | 1906.5 |  |  | 1954 |  |  | 1987.5 |  |  | 1989.5 |  |  | 2078 |  |  | 1911.5 |  |  | 2119.5 |  |  | 2043.5 |  |  | 2140 |  |  | 1994.5 |  |  | 2002 |  |  | 2003 |  |  | 1944.5 |  |  | 2039.5 |  |  | 2020 |  |  | 2027 |  |  | 1855.5 |  |  | 1839.5 |  |  | 1966.5 |  |  | 2052 |  |  | 1918 |  |  | 1962 |  |  | 2045.5 |  |  | 2043.5 |  |  | 2006 |  |  | 2028.5 |  |  | 1850 |  |  | 2004 |  |  | 2009.5 |  |  | 1942.5 |  |  | 1936 |  |  | 2007.5 |  |  | 2012 |  |  | 1881.5 |  |  | 2100.5 |  |  | 2049 |  |  | 1934.5 |  |  | 2062 |  |  | 1991.5 |  |  | 1957 |  |  | 2038 |  |  | 2037 |  |  | 1963.5 |  |  | 1869.5 |  |  | 2029 |  |  | 1934 |  |  | 1882 |  |  | 1954.5 |  |  | 1981.5 |  |  | 2030 |  |  | 2019.5 |  |  | 1956 |  |  | 1877.5 |  |  | 2007.5 |  |  | 1890 |  |  | 1965 |  |  | 1965 |  |  | 1935.5 |  |  | 1937 |  |  | 2024.5 |  |  | 2061 |  |  | 1966.5 |  |  | 2141 |  |  | 1817.5 |  |  | 1969 |  |  | 1975.5 |  |  | 1986.5 |  |  | 1953 |  |  | 1987 |  |  | 2142 |  |  | 1945 |  |  | 2076.5 |  |  | 1879 |  |  | 1907.5 |  |  | 1812 |  |  | 1912 |  |  | 1908 |  |  | 2065 |  |  | 2008 |  |  | 1958 |  |  | 2065 |  |  | 1934.5 |  |  | 1911 |  |  | 2034
70 |  | 2192.5 |  |  | 2135 |  |  | 2072.5 |  |  | 1996 |  |  | 1955.5 |  |  | 2064 |  |  | 2019 |  |  | 2065 |  |  | 1876.5 |  |  | 1939 |  |  | 1970 |  |  | 2124 |  |  | 2115 |  |  | 2211 |  |  | 1972.5 |  |  | 2046.5 |  |  | 1911 |  |  | 2024 |  |  | 2111 |  |  | 1948.5 |  |  | 2043 |  |  | 2065 |  |  | 1923 |  |  | 2014 |  |  | 1995.5 |  |  | 2132 |  |  | 2004 |  |  | 2025 |  |  | 2067 |  |  | 1935 |  |  | 2031 |  |  | 1989.5 |  |  | 2103.5 |  |  | 1994.5 |  |  | 1919 |  |  | 1956.5 |  |  | 1986.5 |  |  | 2096.5 |  |  | 2091 |  |  | 2007 |  |  | 1895.5 |  |  | 1968 |  |  | 2069.5 |  |  | 1988.5 |  |  | 2082.5 |  |  | 2228.5 |  |  | 2177.5 |  |  | 1977 |  |  | 1898 |  |  | 1962.5 |  |  | 2001 |  |  | 1931.5 |  |  | 1881.5 |  |  | 2039 |  |  | 2016 |  |  | 1974 |  |  | 1932 |  |  | 2117 |  |  | 2076 |  |  | 2003.5 |  |  | 2013.5 |  |  | 2018.5 |  |  | 1937 |  |  | 2016 |  |  | 1874 |  |  | 1927.5 |  |  | 1967 |  |  | 1986.5 |  |  | 2061.5 |  |  | 2194.5 |  |  | 2002 |  |  | 2159 |  |  | 2100 |  |  | 2030.5 |  |  | 2078.5 |  |  | 1984.5 |  |  | 2083.5 |  |  | 1986.5 |  |  | 2035.5 |  |  | 1984.5 |  |  | 1943.5 |  |  | 1919 |  |  | 2070 |  |  | 1980 |  |  | 2097.5 |  |  | 2153 |  |  | 1987.5 |  |  | 2025 |  |  | 2044 |  |  | 2076.5 |  |  | 2140.5 |  |  | 2008 |  |  | 2164 |  |  | 1944.5 |  |  | 2073 |  |  | 1938.5 |  |  | 2019.5 |  |  | 2043.5 |  |  | 1947.5 |  |  | 1956.5 |  |  | 2020 |  |  | 2023 |  |  | 1860 |  |  | 1993.5 |  |  | 1950.5 |  |  | 2068.5 |  |  | 1966.5 |  |  | 1982 |  |  | 1977 |  |  | 2015.5 |  |  | 1854 |  |  | 2035.5 |  |  | 2023 |  |  | 1951 |  |  | 1886.5 |  |  | 1967 |  |  | 2020 |  |  | 1939 |  |  | 2039 |  |  | 1972.5 |  |  | 2003.5 |  |  | 1960.5 |  |  | 2101 |  |  | 1971 |  |  | 1918 |  |  | 1960 |  |  | 1960.5 |  |  | 1969 |  |  | 2033.5 |  |  | 2012 |  |  | 1971 |  |  | 2006.5 |  |  | 1983.5 |  |  | 1910 |  |  | 1926.5 |  |  | 1970 |  |  | 2064 |  |  | 1952 |  |  | 2123 |  |  | 1938 |  |  | 1942 |  |  | 1972 |  |  | 2020 |  |  | 1918 |  |  | 1903.5 |  |  | 2003 |  |  | 1869 |  |  | 2076 |  |  | 2027 |  |  | 2034 |  |  | 1910 |  |  | 1952 |  |  | 2029.5 |  |  | 2039 |  |  | 2048.5 |  |  | 2063 |  |  | 1960 |  |  | 2093.5 |  |  | 2013 |  |  | 2136.5 |  |  | 1956 |  |  | 1822 |  |  | 1967.5 |  |  | 2070 |  |  | 2107.5 |  |  | 2004 |  |  | 1901 |  |  | 2071.5 |  |  | 2019.5 |  |  | 2050 |  |  | 1996.5 |  |  | 2003.5 |  |  | 1977 |  |  | 2057 |  |  | 2180.5 |  |  | 1893.5 |  |  | 2048.5 |  |  | 2080 |  |  | 2099 |  |  | 1971 |  |  | 2091 |  |  | 2063 |  |  | 2029.5 |  |  | 1962 |  |  | 1922.5 |  |  | 2027.5 |  |  | 2009 |  |  | 2105 |  |  | 2186.5 |  |  | 1905.5 |  |  | 1975 |  |  | 2049.5 |  |  | 1932.5 |  |  | 2037 |  |  | 1897 |  |  | 1911 |  |  | 1960.5 |  |  | 2097 |  |  | 1995.5 |  |  | 2000.5 |  |  | 1929 |  |  | 1918.5 |  |  | 1972 |  |  | 2019 |  |  | 2040 |  |  | 2026 |  |  | 1812 |  |  | 2116 |  |  | 2121 |  |  | 2014 |  |  | 2117 |  |  | 1959 |  |  | 2010.5 |  |  | 2153.5 |  |  | 1992 |  |  | 1942 |  |  | 2138 |  |  | 2059.5 |  |  | 2080.5 |  |  | 2072.5 |  |  | 1940 |  |  | 2031 |  |  | 2148.5 |  |  | 2039.5 |  |  | 1880.5 |  |  | 2089 |  |  | 2129 |  |  | 1998 |  |  | 2043 |  |  | 2054 |  |  | 2004.5 |  |  | 1935.5 |  |  | 2073 |  |  | 1971 |  |  | 1957 |  |  | 2118 |  |  | 1977 |  |  | 2095.5 |  |  | 2040 |  |  | 2012 |  |  | 2012 |  |  | 1964 |  |  | 1983.5 |  |  | 2130 |  |  | 2007 |  |  | 1967 |  |  | 2111 |  |  | 2087.5 |  |  | 2058 |  |  | 1927 |  |  | 1955 |  |  | 2084.5 |  |  | 2005.5 |  |  | 2119.5 |  |  | 2140 |  |  | 1979 |  |  | 1909 |  |  | 2168 |  |  | 2017 |  |  | 1902.5 |  |  | 2088 |  |  | 2022.5 |  |  | 2081.5 |  |  | 2028.5 |  |  | 2031 |  |  | 2181.5 |  |  | 1915 |  |  | 1938 |  |  | 2015.5 |  |  | 2030.5 |  |  | 2061 |  |  | 2081.5 |  |  | 2151.5 |  |  | 2003 |  |  | 2056 |  |  | 1981.5 |  |  | 1945.5 |  |  | 2137 |  |  | 2011.5 |  |  | 2094 |  |  | 1971 |  |  | 1951.5 |  |  | 2069 |  |  | 1937 |  |  | 2018.5 |  |  | 1972 |  |  | 2193.5 |  |  | 1984 |  |  | 2240 |  |  | 1988 |  |  | 1949 |  |  | 2140.5 |  |  | 2160 |  |  | 2124.5 |  |  | 1894.5 |  |  | 2092.5 |  |  | 2067 |  |  | 2090.5 |  |  | 2211 |  |  | 2067 |  |  | 1851.5 |  |  | 2022.5 |  |  | 2070 |  |  | 1956.5 |  |  | 2104 |  |  | 1986 |  |  | 2153.5 |  |  | 1956 |  |  | 1959.5 |  |  | 2050.5 |  |  | 2053.5 |  |  | 1958 |  |  | 1851 |  |  | 1944 |  |  | 1986.5 |  |  | 1989 |  |  | 2176.5 |  |  | 2044 |  |  | 1978 |  |  | 1933 |  |  | 2029 |  |  | 2068 |  |  | 2046 |  |  | 1980 |  |  | 2155 |  |  | 2057 |  |  | 1978.5 |  |  | 2005 |  |  | 1998 |  |  | 2128.5 |  |  | 1887.5 |  |  | 2056.5 |  |  | 2034.5 |  |  | 2013 |  |  | 2126 |  |  | 1910.5 |  |  | 2118.5 |  |  | 2011.5 |  |  | 2014 |  |  | 2008 |  |  | 1927 |  |  | 1991 |  |  | 1877 |  |  | 1975 |  |  | 2046 |  |  | 2010.5 |  |  | 2035.5 |  |  | 1966 |  |  | 1943.5 |  |  | 2033.5 |  |  | 1930 |  |  | 2084 |  |  | 1948 |  |  | 2001 |  |  | 1920.5 |  |  | 1892.5 |  |  | 2062.5 |  |  | 2025 |  |  | 1952.5 |  |  | 2042 |  |  | 2022 |  |  | 2111 |  |  | 1923.5 |  |  | 1987 |  |  | 1904 |  |  | 1990.5 |  |  | 1957 |  |  | 2090.5 |  |  | 2157 |  |  | 1997.5 |  |  | 1942 |  |  | 2025.5 |  |  | 2029.5 |  |  | 2062 |  |  | 1985 |  |  | 1863 |  |  | 2052 |  |  | 1861.5 |  |  | 1964 |  |  | 2150 |  |  | 1940.5 |  |  | 2104.5 |  |  | 1935.5 |  |  | 1945 |  |  | 2098.5 |  |  | 2041.5 |  |  | 1906.5 |  |  | 2096 |  |  | 2045 |  |  | 2058.5 |  |  | 2077 |  |  | 2126 |  |  | 2060.5 |  |  | 2008 |  |  | 2109 |  |  | 2027 |  |  | 1863 |  |  | 1846.5 |  |  | 2088.5 |  |  | 1915 |  |  | 2080 |  |  | 2040 |  |  | 1972 |  |  | 1954 |  |  | 1958.5 |  |  | 1956.5 |  |  | 2051 |  |  | 2117 |  |  | 2164 |  |  | 1937.5 |  |  | 2173.5 |  |  | 1998 |  |  | 2022 |  |  | 1911 |  |  | 2031.5 |  |  | 2178.5 |  |  | 2041 |  |  | 1900 |  |  | 2035 |  |  | 2044 |  |  | 2006 |  |  | 2141 |  |  | 1947 |  |  | 2139.5 |  |  | 1943 |  |  | 2118 |  |  | 2060 |  |  | 2077.5 |  |  | 2073 |  |  | 1934 |  |  | 1812 |  |  | 1996 |  |  | 1980 |  |  | 2049 |  |  | 2043 |  |  | 1936.5 |  |  | 1990.5 |  |  | 1821.5 |  |  | 2089 |  |  | 1963 |  |  | 1998.5 |  |  | 1849 |  |  | 1916.5 |  |  | 2006.5 |  |  | 1981 |  |  | 2042 |  |  | 1995.5 |  |  | 2037 |  |  | 2026 |  |  | 2001 |  |  | 2030 |  |  | 2045 |  |  | 1990 |  |  | 1961 |  |  | 2077.5 |  |  | 1994 |  |  | 2062 |  |  | 2029 |  |  | 2011 |  |  | 2001 |  |  | 2030 |  |  | 2159 |  |  | 2026 |  |  | 2024 |  |  | 2127.5 |  |  | 2021.5 |  |  | 2020.5 |  |  | 2074.5 |  |  | 2033 |  |  | 1857 |  |  | 2126.5 |  |  | 1954 |  |  | 1986 |  |  | 1941.5 |  |  | 2157.5 |  |  | 2071 |  |  | 2026.5 |  |  | 1981.5 |  |  | 1876 |  |  | 2126 |  |  | 1991 |  |  | 1972 |  |  | 1996.5 |  |  | 2018 |  |  | 1920.5 |  |  | 1890.5 |  |  | 1973 |  |  | 1963 |  |  | 2096.5 |  |  | 1965 |  |  | 2028.5 |  |  | 2064 |  |  | 2049.5 |  |  | 1897.5 |  |  | 1857.5 |  |  | 2043.5 |  |  | 2048.5 |  |  | 1854 |  |  | 1901 |  |  | 2130.5 |  |  | 2058 |  |  | 1926 |  |  | 1984 |  |  | 2082 |  |  | 2132.5 |  |  | 1870 |  |  | 1956 |  |  | 2056 |  |  | 1968.5 |  |  | 2026 |  |  | 1903 |  |  | 1979 |  |  | 2181.5 |  |  | 2071 |  |  | 1818 |  |  | 2021 |  |  | 2142 |  |  | 2273.5 |  |  | 2059 |  |  | 1951.5 |  |  | 1993 |  |  | 2061 |  |  | 2248.5 |  |  | 2076 |  |  | 1955 |  |  | 1983.5 |  |  | 2043 |  |  | 1969 |  |  | 1995 |  |  | 2196.5 |  |  | 2044.5 |  |  | 2054 |  |  | 1904 |  |  | 1987.5 |  |  | 2002.5 |  |  | 1997 |  |  | 2070 |  |  | 2066.5 |  |  | 2186.5 |  |  | 1902.5 |  |  | 2032.5 |  |  | 1967.5 |  |  | 2189 |  |  | 1982.5 |  |  | 2065 |  |  | 2018 |  |  | 2039 |  |  | 2122 |  |  | 2037.5 |  |  | 2033 |  |  | 1896 |  |  | 2062.5 |  |  | 2008.5 |  |  | 1917 |  |  | 2094.5 |  |  | 2010.5 |  |  | 2121 |  |  | 1909 |  |  | 2010 |  |  | 2076.5 |  |  | 2054 |  |  | 2105.5 |  |  | 2076 |  |  | 1977 |  |  | 2226.5 |  |  | 1978 |  |  | 2108 |  |  | 1941 |  |  | 2072 |  |  | 2047 |  |  | 2034 |  |  | 2046 |  |  | 2025 |  |  | 1886.5 |  |  | 1983.5 |  |  | 1934 |  |  | 2049.5 |  |  | 1847.5 |  |  | 1917 |  |  | 1953 |  |  | 2095 |  |  | 2118.5 |  |  | 1949.5 |  |  | 2082 |  |  | 2056 |  |  | 1907 |  |  | 1916 |  |  | 1987 |  |  | 1958 |  |  | 2086 |  |  | 1923.5 |  |  | 2122 |  |  | 2015 |  |  | 2139 |  |  | 1971 |  |  | 1890 |  |  | 2000.5 |  |  | 2188.5 |  |  | 1837.5 |  |  | 1925 |  |  | 1938 |  |  | 1925.5 |  |  | 2113.5 |  |  | 2041.5 |  |  | 1940 |  |  | 2092.5 |  |  | 2023.5 |  |  | 2187 |  |  | 2078.5 |  |  | 2015.5 |  |  | 2015 |  |  | 1908 |  |  | 1976 |  |  | 2106 |  |  | 1983 |  |  | 1829 |  |  | 2049 |  |  | 2148 |  |  | 1915 |  |  | 1989 |  |  | 2129.5 |  |  | 2007 |  |  | 2039 |  |  | 1921 |  |  | 2003.5 |  |  | 1960 |  |  | 2034.5 |  |  | 2154 |  |  | 2069 |  |  | 1998 |  |  | 2025 |  |  | 2134.5 |  |  | 1962 |  |  | 1934 |  |  | 2087.5 |  |  | 2043 |  |  | 1971 |  |  | 1951.5 |  |  | 1957.5 |  |  | 2007 |  |  | 1939.5 |  |  | 2150 |  |  | 1954.5 |  |  | 2128 |  |  | 2055 |  |  | 1942.5 |  |  | 2107.5 |  |  | 1982 |  |  | 2105 |  |  | 2028 |  |  | 2036 |  |  | 1894 |  |  | 2029 |  |  | 1838 |  |  | 1883 |  |  | 2129.5 |  |  | 1908 |  |  | 2088.5 |  |  | 1988 |  |  | 2080.5 |  |  | 1955.5 |  |  | 1957 |  |  | 2013 |  |  | 2089.5 |  |  | 1997 |  |  | 2052 |  |  | 2087 |  |  | 1975.5 |  |  | 2055 |  |  | 1912.5 |  |  | 1820 |  |  | 1964 |  |  | 2011 |  |  | 2027 |  |  | 2094.5 |  |  | 1945 |  |  | 2002 |  |  | 2031 |  |  | 1893.5 |  |  | 2127 |  |  | 2101 |  |  | 2024 |  |  | 1988 |  |  | 2008.5 |  |  | 1941.5 |  |  | 2053 |  |  | 2129 |  |  | 2008 |  |  | 2059.5 |  |  | 2017 |  |  | 1925 |  |  | 2004 |  |  | 2149.5 |  |  | 1971.5 |  |  | 1974.5 |  |  | 2011 |  |  | 2087 |  |  | 2081 |  |  | 1960.5 |  |  | 2056 |  |  | 1977.5 |  |  | 1886 |  |  | 1905 |  |  | 1977 |  |  | 1985.5 |  |  | 2065.5 |  |  | 2014 |  |  | 1958 |  |  | 2129.5 |  |  | 2036 |  |  | 2003 |  |  | 2075.5 |  |  | 1959 |  |  | 1964 |  |  | 2042.5 |  |  | 1934 |  |  | 2018 |  |  | 1993.5 |  |  | 2157 |  |  | 1964.5 |  |  | 2033 |  |  | 1847.5 |  |  | 2070.5 |  |  | 1851 |  |  | 2118 |  |  | 2070.5 |  |  | 2018.5 |  |  | 2145 |  |  | 2005 |  |  | 2062 |  |  | 2009.5 |  |  | 2041 |  |  | 1818 |  |  | 1973 |  |  | 2110.5 |  |  | 2044.5 |  |  | 2040 |  |  | 2106 |  |  | 1966 |  |  | 1922 |  |  | 2107 |  |  | 1951 |  |  | 1976 |  |  | 2007.5 |  |  | 2168.5 |  |  | 1930.5 |  |  | 2014 |  |  | 2007.5 |  |  | 2021 |  |  | 1985 |  |  | 2058.5 |  |  | 1919.5 |  |  | 1903 |  |  | 2048 |  |  | 1970.5 |  |  | 2029 |  |  | 2062 |  |  | 1912.5 |  |  | 2063.5 |  |  | 1976 |  |  | 1949 |  |  | 2028 |  |  | 1914.5 |  |  | 1919 |  |  | 1898 |  |  | 2044 |  |  | 2045 |  |  | 2110 |  |  | 1944.5 |  |  | 2125 |  |  | 1947 |  |  | 1896 |  |  | 2138.5 |  |  | 2005 |  |  | 1963.5 |  |  | 1940.5 |  |  | 2008 |  |  | 2085 |  |  | 1963.5 |  |  | 1954.5 |  |  | 1910.5 |  |  | 1982.5 |  |  | 1986.5 |  |  | 2046 |  |  | 2027 |  |  | 2020.5 |  |  | 1944.5 |  |  | 2000 |  |  | 1968 |  |  | 1981.5 |  |  | 2137 |  |  | 1982 |  |  | 1839 |  |  | 2050.5 |  |  | 2132 |  |  | 1932.5 |  |  | 1880 |  |  | 2022.5 |  |  | 2164.5 |  |  | 2167.5 |  |  | 2117 |  |  | 2025 |  |  | 2015.5 |  |  | 1987.5 |  |  | 2041 |  |  | 2023 |  |  | 2053.5 |  |  | 2139 |  |  | 2019.5 |  |  | 1977.5 |  |  | 2096 |  |  | 2028 |  |  | 1854.5 |  |  | 2103.5 |  |  | 1990 |  |  | 1941.5 |  |  | 2043.5 |  |  | 2066 |  |  | 2085 |  |  | 2115 |  |  | 1964.5 |  |  | 2118 |  |  | 1952 |  |  | 2055 |  |  | 1956 |  |  | 1983 |  |  | 1965 |  |  | 2120.5 |  |  | 1976.5 |  |  | 1985 |  |  | 1975 |  |  | 2045 |  |  | 1997.5 |  |  | 1966 |  |  | 2129 |  |  | 1923.5 |  |  | 2075.5 |  |  | 1987 |  |  | 1965.5 |  |  | 2050 |  |  | 1889 |  |  | 2012 |  |  | 2137.5 |  |  | 2156 |  |  | 1882.5 |  |  | 1984.5 |  |  | 1910 |  |  | 2050.5 |  |  | 1829.5 |  |  | 1943 |  |  | 1901 |  |  | 2118 |  |  | 1921.5 |  |  | 1897 |  |  | 1981.5 |  |  | 2004.5 |  |  | 2068 |  |  | 1893.5 |  |  | 1925 |  |  | 2031 |  |  | 1973 |  |  | 1894 |  |  | 1896 |  |  | 2102.5 |  |  | 2016 |  |  | 2094 |  |  | 1922 |  |  | 2070 |  |  | 2001.5 |  |  | 2028.5 |  |  | 2005 |  |  | 2062 |  |  | 2045 |  |  | 1998 |  |  | 2084 |  |  | 1943.5 |  |  | 2019 |  |  | 2070.5 |  |  | 2111 |  |  | 1883 |  |  | 1972 |  |  | 1978 |  |  | 2050.5 |  |  | 2027 |  |  | 2039.5 |  |  | 1945 |  |  | 2158 |  |  | 2066 |  |  | 2021.5 |  |  | 1936 |  |  | 1872 |  |  | 1896 |  |  | 2152 |  |  | 2220 |  |  | 1947.5 |  |  | 2059.5 |  |  | 1966 |  |  | 1985.5 |  |  | 1958 |  |  | 1929.5 |  |  | 1957.5 |  |  | 1935.5 |  |  | 1952.5 |  |  | 1890 |  |  | 2166 |  |  | 1898 |  |  | 1930 |  |  | 1995 |  |  | 2095 |  |  | 1956.5 |  |  | 1957.5 |  |  | 2096.5 |  |  | 2071 |  |  | 2080.5 |  |  | 1968.5 |  |  | 2063.5 |  |  | 1927.5 |  |  | 2001 |  |  | 2026.5 |  |  | 2013.5 |  |  | 2102 |  |  | 1937.5 |  |  | 2166.5 |  |  | 2082.5 |  |  | 2179 |  |  | 2041.5 |  |  | 2031 |  |  | 2024 |  |  | 1991.5 |  |  | 2078.5 |  |  | 2059 |  |  | 2056 |  |  | 1884.5 |  |  | 1860.5 |  |  | 1987.5 |  |  | 2076 |  |  | 1965 |  |  | 1988 |  |  | 2071.5 |  |  | 2067.5 |  |  | 2045 |  |  | 2052.5 |  |  | 1871 |  |  | 2028 |  |  | 2056.5 |  |  | 1963.5 |  |  | 1975 |  |  | 2033.5 |  |  | 2051 |  |  | 1928.5 |  |  | 2147.5 |  |  | 2070 |  |  | 1981.5 |  |  | 2091 |  |  | 2038.5 |  |  | 1996 |  |  | 2077 |  |  | 2061 |  |  | 1989.5 |  |  | 1890.5 |  |  | 2050 |  |  | 1973 |  |  | 1903 |  |  | 1969.5 |  |  | 2005.5 |  |  | 2069 |  |  | 2040.5 |  |  | 1980 |  |  | 1916.5 |  |  | 2031.5 |  |  | 1937 |  |  | 1986 |  |  | 2012 |  |  | 1974.5 |  |  | 1976 |  |  | 2053.5 |  |  | 2076 |  |  | 2005.5 |  |  | 2156 |  |  | 1864.5 |  |  | 2008 |  |  | 2014.5 |  |  | 2007.5 |  |  | 1974 |  |  | 2011 |  |  | 2181 |  |  | 1984 |  |  | 2097.5 |  |  | 1905 |  |  | 1946.5 |  |  | 1859 |  |  | 1933 |  |  | 1947 |  |  | 2104 |  |  | 2029 |  |  | 1984 |  |  | 2094 |  |  | 1981.5 |  |  | 1932 |  |  | 2055
71 |  | 2231.5 |  |  | 2182 |  |  | 2096.5 |  |  | 2043 |  |  | 1970.5 |  |  | 2090 |  |  | 2058 |  |  | 2091 |  |  | 1923.5 |  |  | 1960 |  |  | 2009 |  |  | 2139 |  |  | 2130 |  |  | 2237 |  |  | 2011.5 |  |  | 2085.5 |  |  | 1940 |  |  | 2053 |  |  | 2135 |  |  | 1963.5 |  |  | 2069 |  |  | 2086 |  |  | 1962 |  |  | 2053 |  |  | 2034.5 |  |  | 2171 |  |  | 2030 |  |  | 2051 |  |  | 2093 |  |  | 1964 |  |  | 2078 |  |  | 2010.5 |  |  | 2142.5 |  |  | 2033.5 |  |  | 1966 |  |  | 1995.5 |  |  | 2025.5 |  |  | 2143.5 |  |  | 2106 |  |  | 2046 |  |  | 1934.5 |  |  | 2007 |  |  | 2090.5 |  |  | 2014.5 |  |  | 2103.5 |  |  | 2249.5 |  |  | 2198.5 |  |  | 2024 |  |  | 1913 |  |  | 2001.5 |  |  | 2027 |  |  | 1970.5 |  |  | 1902.5 |  |  | 2054 |  |  | 2031 |  |  | 1995 |  |  | 1947 |  |  | 2146 |  |  | 2100 |  |  | 2050.5 |  |  | 2034.5 |  |  | 2057.5 |  |  | 1958 |  |  | 2037 |  |  | 1889 |  |  | 1951.5 |  |  | 2006 |  |  | 2033.5 |  |  | 2100.5 |  |  | 2223.5 |  |  | 2041 |  |  | 2198 |  |  | 2147 |  |  | 2045.5 |  |  | 2125.5 |  |  | 2031.5 |  |  | 2130.5 |  |  | 2010.5 |  |  | 2074.5 |  |  | 2005.5 |  |  | 1990.5 |  |  | 1934 |  |  | 2096 |  |  | 2004 |  |  | 2121.5 |  |  | 2182 |  |  | 2002.5 |  |  | 2064 |  |  | 2083 |  |  | 2097.5 |  |  | 2179.5 |  |  | 2055 |  |  | 2188 |  |  | 1968.5 |  |  | 2120 |  |  | 1964.5 |  |  | 2058.5 |  |  | 2072.5 |  |  | 1962.5 |  |  | 1977.5 |  |  | 2041 |  |  | 2047 |  |  | 1889 |  |  | 2032.5 |  |  | 1965.5 |  |  | 2107.5 |  |  | 1981.5 |  |  | 1997 |  |  | 1992 |  |  | 2062.5 |  |  | 1893 |  |  | 2074.5 |  |  | 2044 |  |  | 1980 |  |  | 1901.5 |  |  | 2014 |  |  | 2044 |  |  | 1963 |  |  | 2065 |  |  | 1996.5 |  |  | 2027.5 |  |  | 2007.5 |  |  | 2148 |  |  | 1997 |  |  | 1944 |  |  | 1986 |  |  | 1981.5 |  |  | 1998 |  |  | 2048.5 |  |  | 2041 |  |  | 1995 |  |  | 2032.5 |  |  | 2009.5 |  |  | 1949 |  |  | 1973.5 |  |  | 1991 |  |  | 2103 |  |  | 1999 |  |  | 2152 |  |  | 1962 |  |  | 1963 |  |  | 2019 |  |  | 2044 |  |  | 1939 |  |  | 1924.5 |  |  | 2024 |  |  | 1890 |  |  | 2115 |  |  | 2066 |  |  | 2073 |  |  | 1939 |  |  | 1976 |  |  | 2068.5 |  |  | 2065 |  |  | 2074.5 |  |  | 2087 |  |  | 1984 |  |  | 2117.5 |  |  | 2028 |  |  | 2160.5 |  |  | 1985 |  |  | 1861 |  |  | 2014.5 |  |  | 2117 |  |  | 2122.5 |  |  | 2051 |  |  | 1940 |  |  | 2118.5 |  |  | 2058.5 |  |  | 2097 |  |  | 2011.5 |  |  | 2024.5 |  |  | 2024 |  |  | 2078 |  |  | 2201.5 |  |  | 1922.5 |  |  | 2069.5 |  |  | 2109 |  |  | 2120 |  |  | 1997 |  |  | 2138 |  |  | 2102 |  |  | 2068.5 |  |  | 1986 |  |  | 1943.5 |  |  | 2051.5 |  |  | 2056 |  |  | 2144 |  |  | 2225.5 |  |  | 1944.5 |  |  | 1996 |  |  | 2064.5 |  |  | 1961.5 |  |  | 2066 |  |  | 1912 |  |  | 1958 |  |  | 1981.5 |  |  | 2136 |  |  | 2016.5 |  |  | 2026.5 |  |  | 1955 |  |  | 1939.5 |  |  | 1996 |  |  | 2034 |  |  | 2061 |  |  | 2073 |  |  | 1851 |  |  | 2131 |  |  | 2145 |  |  | 2040 |  |  | 2141 |  |  | 1998 |  |  | 2036.5 |  |  | 2168.5 |  |  | 2031 |  |  | 1968 |  |  | 2164 |  |  | 2080.5 |  |  | 2101.5 |  |  | 2119.5 |  |  | 1969 |  |  | 2057 |  |  | 2187.5 |  |  | 2054.5 |  |  | 1906.5 |  |  | 2136 |  |  | 2168 |  |  | 2019 |  |  | 2082 |  |  | 2093 |  |  | 2028.5 |  |  | 1982.5 |  |  | 2094 |  |  | 2010 |  |  | 1986 |  |  | 2142 |  |  | 1992 |  |  | 2119.5 |  |  | 2087 |  |  | 2051 |  |  | 2038 |  |  | 1988 |  |  | 2030.5 |  |  | 2156 |  |  | 2046 |  |  | 1993 |  |  | 2135 |  |  | 2126.5 |  |  | 2079 |  |  | 1974 |  |  | 1976 |  |  | 2123.5 |  |  | 2044.5 |  |  | 2158.5 |  |  | 2164 |  |  | 2005 |  |  | 1938 |  |  | 2192 |  |  | 2056 |  |  | 1949.5 |  |  | 2135 |  |  | 2037.5 |  |  | 2110.5 |  |  | 2067.5 |  |  | 2070 |  |  | 2207.5 |  |  | 1936 |  |  | 1967 |  |  | 2030.5 |  |  | 2054.5 |  |  | 2108 |  |  | 2102.5 |  |  | 2180.5 |  |  | 2027 |  |  | 2071 |  |  | 2020.5 |  |  | 1971.5 |  |  | 2176 |  |  | 2037.5 |  |  | 2133 |  |  | 2010 |  |  | 1977.5 |  |  | 2108 |  |  | 1958 |  |  | 2033.5 |  |  | 2001 |  |  | 2232.5 |  |  | 2023 |  |  | 2266 |  |  | 2027 |  |  | 1970 |  |  | 2169.5 |  |  | 2199 |  |  | 2139.5 |  |  | 1915.5 |  |  | 2139.5 |  |  | 2093 |  |  | 2114.5 |  |  | 2240 |  |  | 2091 |  |  | 1877.5 |  |  | 2046.5 |  |  | 2109 |  |  | 1995.5 |  |  | 2143 |  |  | 2001 |  |  | 2174.5 |  |  | 1982 |  |  | 1998.5 |  |  | 2074.5 |  |  | 2079.5 |  |  | 2005 |  |  | 1880 |  |  | 1991 |  |  | 2010.5 |  |  | 2004 |  |  | 2202.5 |  |  | 2068 |  |  | 2025 |  |  | 1980 |  |  | 2050 |  |  | 2092 |  |  | 2085 |  |  | 2001 |  |  | 2202 |  |  | 2096 |  |  | 2025.5 |  |  | 2044 |  |  | 2037 |  |  | 2143.5 |  |  | 1926.5 |  |  | 2077.5 |  |  | 2073.5 |  |  | 2052 |  |  | 2147 |  |  | 1939.5 |  |  | 2157.5 |  |  | 2026.5 |  |  | 2043 |  |  | 2034 |  |  | 1966 |  |  | 2006 |  |  | 1903 |  |  | 2014 |  |  | 2070 |  |  | 2039.5 |  |  | 2061.5 |  |  | 1992 |  |  | 1969.5 |  |  | 2072.5 |  |  | 1969 |  |  | 2105 |  |  | 1963 |  |  | 2040 |  |  | 1959.5 |  |  | 1916.5 |  |  | 2077.5 |  |  | 2046 |  |  | 1991.5 |  |  | 2089 |  |  | 2061 |  |  | 2150 |  |  | 1952.5 |  |  | 2026 |  |  | 1925 |  |  | 2029.5 |  |  | 1978 |  |  | 2114.5 |  |  | 2181 |  |  | 2036.5 |  |  | 1957 |  |  | 2049.5 |  |  | 2055.5 |  |  | 2091 |  |  | 2024 |  |  | 1887 |  |  | 2081 |  |  | 1885.5 |  |  | 1988 |  |  | 2197 |  |  | 1955.5 |  |  | 2130.5 |  |  | 1959.5 |  |  | 1992 |  |  | 2145.5 |  |  | 2080.5 |  |  | 1921.5 |  |  | 2135 |  |  | 2069 |  |  | 2082.5 |  |  | 2116 |  |  | 2141 |  |  | 2107.5 |  |  | 2034 |  |  | 2138 |  |  | 2053 |  |  | 1892 |  |  | 1875.5 |  |  | 2127.5 |  |  | 1941 |  |  | 2119 |  |  | 2079 |  |  | 1987 |  |  | 1978 |  |  | 1997.5 |  |  | 1977.5 |  |  | 2072 |  |  | 2156 |  |  | 2203 |  |  | 1976.5 |  |  | 2220.5 |  |  | 2022 |  |  | 2037 |  |  | 1926 |  |  | 2055.5 |  |  | 2225.5 |  |  | 2067 |  |  | 1926 |  |  | 2064 |  |  | 2059 |  |  | 2032 |  |  | 2188 |  |  | 1962 |  |  | 2168.5 |  |  | 1964 |  |  | 2142 |  |  | 2081 |  |  | 2092.5 |  |  | 2094 |  |  | 1963 |  |  | 1851 |  |  | 2025 |  |  | 2004 |  |  | 2073 |  |  | 2058 |  |  | 1975.5 |  |  | 2014.5 |  |  | 1836.5 |  |  | 2128 |  |  | 2010 |  |  | 2037.5 |  |  | 1870 |  |  | 1955.5 |  |  | 2035.5 |  |  | 2010 |  |  | 2089 |  |  | 2019.5 |  |  | 2076 |  |  | 2050 |  |  | 2040 |  |  | 2051 |  |  | 2084 |  |  | 2005 |  |  | 2000 |  |  | 2092.5 |  |  | 2033 |  |  | 2086 |  |  | 2068 |  |  | 2040 |  |  | 2040 |  |  | 2054 |  |  | 2183 |  |  | 2065 |  |  | 2053 |  |  | 2142.5 |  |  | 2050.5 |  |  | 2044.5 |  |  | 2095.5 |  |  | 2080 |  |  | 1896 |  |  | 2152.5 |  |  | 1978 |  |  | 2025 |  |  | 1980.5 |  |  | 2196.5 |  |  | 2110 |  |  | 2041.5 |  |  | 2028.5 |  |  | 1905 |  |  | 2147 |  |  | 2012 |  |  | 2019 |  |  | 2017.5 |  |  | 2044 |  |  | 1935.5 |  |  | 1929.5 |  |  | 2012 |  |  | 1978 |  |  | 2143.5 |  |  | 1986 |  |  | 2049.5 |  |  | 2093 |  |  | 2088.5 |  |  | 1923.5 |  |  | 1872.5 |  |  | 2090.5 |  |  | 2074.5 |  |  | 1901 |  |  | 1916 |  |  | 2156.5 |  |  | 2082 |  |  | 1952 |  |  | 2013 |  |  | 2129 |  |  | 2171.5 |  |  | 1899 |  |  | 1985 |  |  | 2103 |  |  | 1994.5 |  |  | 2065 |  |  | 1942 |  |  | 2000 |  |  | 2207.5 |  |  | 2095 |  |  | 1844 |  |  | 2036 |  |  | 2163 |  |  | 2288.5 |  |  | 2080 |  |  | 1972.5 |  |  | 2008 |  |  | 2100 |  |  | 2263.5 |  |  | 2091 |  |  | 1979 |  |  | 2022.5 |  |  | 2064 |  |  | 1998 |  |  | 2021 |  |  | 2243.5 |  |  | 2073.5 |  |  | 2069 |  |  | 1933 |  |  | 2026.5 |  |  | 2031.5 |  |  | 2023 |  |  | 2085 |  |  | 2105.5 |  |  | 2225.5 |  |  | 1917.5 |  |  | 2071.5 |  |  | 2006.5 |  |  | 2204 |  |  | 2003.5 |  |  | 2112 |  |  | 2047 |  |  | 2054 |  |  | 2161 |  |  | 2076.5 |  |  | 2048 |  |  | 1943 |  |  | 2077.5 |  |  | 2032.5 |  |  | 1938 |  |  | 2109.5 |  |  | 2036.5 |  |  | 2168 |  |  | 1956 |  |  | 2036 |  |  | 2102.5 |  |  | 2093 |  |  | 2126.5 |  |  | 2105 |  |  | 2016 |  |  | 2273.5 |  |  | 1993 |  |  | 2147 |  |  | 1962 |  |  | 2119 |  |  | 2071 |  |  | 2063 |  |  | 2085 |  |  | 2049 |  |  | 1925.5 |  |  | 1998.5 |  |  | 1973 |  |  | 2073.5 |  |  | 1868.5 |  |  | 1943 |  |  | 1977 |  |  | 2134 |  |  | 2139.5 |  |  | 1988.5 |  |  | 2121 |  |  | 2080 |  |  | 1954 |  |  | 1942 |  |  | 2026 |  |  | 1982 |  |  | 2107 |  |  | 1947.5 |  |  | 2137 |  |  | 2062 |  |  | 2154 |  |  | 2010 |  |  | 1905 |  |  | 2039.5 |  |  | 2212.5 |  |  | 1876.5 |  |  | 1946 |  |  | 1953 |  |  | 1972.5 |  |  | 2152.5 |  |  | 2080.5 |  |  | 1961 |  |  | 2121.5 |  |  | 2070.5 |  |  | 2216 |  |  | 2117.5 |  |  | 2062.5 |  |  | 2054 |  |  | 1932 |  |  | 1997 |  |  | 2135 |  |  | 2004 |  |  | 1855 |  |  | 2088 |  |  | 2187 |  |  | 1930 |  |  | 2036 |  |  | 2150.5 |  |  | 2028 |  |  | 2063 |  |  | 1942 |  |  | 2018.5 |  |  | 1986 |  |  | 2058.5 |  |  | 2201 |  |  | 2093 |  |  | 2027 |  |  | 2049 |  |  | 2155.5 |  |  | 2001 |  |  | 1958 |  |  | 2134.5 |  |  | 2072 |  |  | 1992 |  |  | 1966.5 |  |  | 1996.5 |  |  | 2022 |  |  | 1963.5 |  |  | 2176 |  |  | 1969.5 |  |  | 2149 |  |  | 2079 |  |  | 1989.5 |  |  | 2133.5 |  |  | 2006 |  |  | 2134 |  |  | 2049 |  |  | 2057 |  |  | 1918 |  |  | 2053 |  |  | 1885 |  |  | 1930 |  |  | 2158.5 |  |  | 1923 |  |  | 2135.5 |  |  | 2009 |  |  | 2119.5 |  |  | 1981.5 |  |  | 1983 |  |  | 2039 |  |  | 2136.5 |  |  | 2036 |  |  | 2091 |  |  | 2116 |  |  | 2022.5 |  |  | 2084 |  |  | 1951.5 |  |  | 1859 |  |  | 1993 |  |  | 2040 |  |  | 2053 |  |  | 2118.5 |  |  | 1984 |  |  | 2026 |  |  | 2078 |  |  | 1919.5 |  |  | 2166 |  |  | 2116 |  |  | 2063 |  |  | 2003 |  |  | 2023.5 |  |  | 1965.5 |  |  | 2092 |  |  | 2168 |  |  | 2034 |  |  | 2106.5 |  |  | 2038 |  |  | 1964 |  |  | 2025 |  |  | 2164.5 |  |  | 2018.5 |  |  | 1998.5 |  |  | 2058 |  |  | 2113 |  |  | 2110 |  |  | 1989.5 |  |  | 2080 |  |  | 2006.5 |  |  | 1901 |  |  | 1952 |  |  | 2001 |  |  | 2032.5 |  |  | 2104.5 |  |  | 2043 |  |  | 2005 |  |  | 2168.5 |  |  | 2060 |  |  | 2024 |  |  | 2096.5 |  |  | 1974 |  |  | 1979 |  |  | 2068.5 |  |  | 1973 |  |  | 2057 |  |  | 2014.5 |  |  | 2178 |  |  | 1979.5 |  |  | 2062 |  |  | 1876.5 |  |  | 2109.5 |  |  | 1898 |  |  | 2142 |  |  | 2091.5 |  |  | 2033.5 |  |  | 2184 |  |  | 2044 |  |  | 2083 |  |  | 2048.5 |  |  | 2065 |  |  | 1844 |  |  | 1988 |  |  | 2131.5 |  |  | 2083.5 |  |  | 2069 |  |  | 2145 |  |  | 1992 |  |  | 1951 |  |  | 2136 |  |  | 1980 |  |  | 1997 |  |  | 2022.5 |  |  | 2215.5 |  |  | 1954.5 |  |  | 2040 |  |  | 2046.5 |  |  | 2050 |  |  | 2006 |  |  | 2084.5 |  |  | 1934.5 |  |  | 1927 |  |  | 2074 |  |  | 1994.5 |  |  | 2044 |  |  | 2101 |  |  | 1936.5 |  |  | 2092.5 |  |  | 2005 |  |  | 1970 |  |  | 2067 |  |  | 1953.5 |  |  | 1958 |  |  | 1913 |  |  | 2059 |  |  | 2084 |  |  | 2157 |  |  | 1970.5 |  |  | 2146 |  |  | 1968 |  |  | 1922 |  |  | 2185.5 |  |  | 2044 |  |  | 1987.5 |  |  | 1969.5 |  |  | 2032 |  |  | 2124 |  |  | 2002.5 |  |  | 1993.5 |  |  | 1931.5 |  |  | 2021.5 |  |  | 2025.5 |  |  | 2061 |  |  | 2066 |  |  | 2059.5 |  |  | 1968.5 |  |  | 2039 |  |  | 2007 |  |  | 2002.5 |  |  | 2176 |  |  | 2011 |  |  | 1886 |  |  | 2076.5 |  |  | 2179 |  |  | 1961.5 |  |  | 1919 |  |  | 2061.5 |  |  | 2203.5 |  |  | 2182.5 |  |  | 2156 |  |  | 2072 |  |  | 2039.5 |  |  | 2026.5 |  |  | 2067 |  |  | 2038 |  |  | 2100.5 |  |  | 2163 |  |  | 2058.5 |  |  | 2006.5 |  |  | 2111 |  |  | 2054 |  |  | 1878.5 |  |  | 2124.5 |  |  | 2029 |  |  | 1980.5 |  |  | 2072.5 |  |  | 2105 |  |  | 2124 |  |  | 2139 |  |  | 2003.5 |  |  | 2144 |  |  | 1967 |  |  | 2076 |  |  | 1977 |  |  | 2004 |  |  | 1989 |  |  | 2167.5 |  |  | 2002.5 |  |  | 2009 |  |  | 2014 |  |  | 2071 |  |  | 2012.5 |  |  | 1995 |  |  | 2168 |  |  | 1962.5 |  |  | 2122.5 |  |  | 2016 |  |  | 1989.5 |  |  | 2089 |  |  | 1910 |  |  | 2033 |  |  | 2161.5 |  |  | 2195 |  |  | 1908.5 |  |  | 2023.5 |  |  | 1949 |  |  | 2071.5 |  |  | 1858.5 |  |  | 1982 |  |  | 1930 |  |  | 2133 |  |  | 1947.5 |  |  | 1921 |  |  | 2005.5 |  |  | 2043.5 |  |  | 2107 |  |  | 1932.5 |  |  | 1940 |  |  | 2046 |  |  | 1999 |  |  | 1941 |  |  | 1917 |  |  | 2128.5 |  |  | 2042 |  |  | 2109 |  |  | 1961 |  |  | 2109 |  |  | 2025.5 |  |  | 2054.5 |  |  | 2029 |  |  | 2109 |  |  | 2060 |  |  | 2037 |  |  | 2105 |  |  | 1964.5 |  |  | 2040 |  |  | 2109.5 |  |  | 2126 |  |  | 1907 |  |  | 1996 |  |  | 2017 |  |  | 2089.5 |  |  | 2048 |  |  | 2054.5 |  |  | 1984 |  |  | 2184 |  |  | 2113 |  |  | 2045.5 |  |  | 1983 |  |  | 1911 |  |  | 1943 |  |  | 2181 |  |  | 2241 |  |  | 1994.5 |  |  | 2098.5 |  |  | 1990 |  |  | 2032.5 |  |  | 1997 |  |  | 1958.5 |  |  | 1996.5 |  |  | 1974.5 |  |  | 1973.5 |  |  | 1919 |  |  | 2195 |  |  | 1937 |  |  | 1956 |  |  | 2024 |  |  | 2116 |  |  | 1995.5 |  |  | 1978.5 |  |  | 2143.5 |  |  | 2095 |  |  | 2095.5 |  |  | 2015.5 |  |  | 2102.5 |  |  | 1951.5 |  |  | 2040 |  |  | 2073.5 |  |  | 2052.5 |  |  | 2131 |  |  | 1963.5 |  |  | 2192.5 |  |  | 2106.5 |  |  | 2194 |  |  | 2067.5 |  |  | 2046 |  |  | 2053 |  |  | 2012.5 |  |  | 2104.5 |  |  | 2088 |  |  | 2103 |  |  | 1908.5 |  |  | 1889.5 |  |  | 2013.5 |  |  | 2115 |  |  | 1980 |  |  | 2012 |  |  | 2118.5 |  |  | 2106.5 |  |  | 2084 |  |  | 2073.5 |  |  | 1900 |  |  | 2049 |  |  | 2077.5 |  |  | 2002.5 |  |  | 1996 |  |  | 2057.5 |  |  | 2077 |  |  | 1954.5 |  |  | 2171.5 |  |  | 2117 |  |  | 2020.5 |  |  | 2130 |  |  | 2064.5 |  |  | 2025 |  |  | 2124 |  |  | 2076 |  |  | 2013.5 |  |  | 1911.5 |  |  | 2074 |  |  | 1997 |  |  | 1942 |  |  | 2008.5 |  |  | 2020.5 |  |  | 2116 |  |  | 2079.5 |  |  | 2027 |  |  | 1931.5 |  |  | 2070.5 |  |  | 1963 |  |  | 2033 |  |  | 2027 |  |  | 2013.5 |  |  | 1991 |  |  | 2068.5 |  |  | 2115 |  |  | 2034.5 |  |  | 2182 |  |  | 1879.5 |  |  | 2023 |  |  | 2053.5 |  |  | 2036.5 |  |  | 1995 |  |  | 2035 |  |  | 2228 |  |  | 2005 |  |  | 2112.5 |  |  | 1920 |  |  | 1985.5 |  |  | 1883 |  |  | 1957 |  |  | 1962 |  |  | 2151 |  |  | 2053 |  |  | 2013 |  |  | 2120 |  |  | 2020.5 |  |  | 1971 |  |  | 2094
72 |  | 2255.5 |  |  | 2208 |  |  | 2135.5 |  |  | 2067 |  |  | 2017.5 |  |  | 2105 |  |  | 2082 |  |  | 2115 |  |  | 1962.5 |  |  | 1999 |  |  | 2048 |  |  | 2178 |  |  | 2156 |  |  | 2252 |  |  | 2040.5 |  |  | 2114.5 |  |  | 1969 |  |  | 2082 |  |  | 2156 |  |  | 1992.5 |  |  | 2098 |  |  | 2125 |  |  | 1977 |  |  | 2092 |  |  | 2058.5 |  |  | 2192 |  |  | 2051 |  |  | 2080 |  |  | 2132 |  |  | 1993 |  |  | 2117 |  |  | 2049.5 |  |  | 2157.5 |  |  | 2057.5 |  |  | 2005 |  |  | 2016.5 |  |  | 2064.5 |  |  | 2182.5 |  |  | 2130 |  |  | 2070 |  |  | 1963.5 |  |  | 2022 |  |  | 2119.5 |  |  | 2043.5 |  |  | 2124.5 |  |  | 2288.5 |  |  | 2224.5 |  |  | 2045 |  |  | 1942 |  |  | 2048.5 |  |  | 2048 |  |  | 2009.5 |  |  | 1941.5 |  |  | 2075 |  |  | 2057 |  |  | 2021 |  |  | 1976 |  |  | 2167 |  |  | 2124 |  |  | 2065.5 |  |  | 2055.5 |  |  | 2086.5 |  |  | 1997 |  |  | 2084 |  |  | 1918 |  |  | 1977.5 |  |  | 2027 |  |  | 2048.5 |  |  | 2124.5 |  |  | 2244.5 |  |  | 2065 |  |  | 2219 |  |  | 2168 |  |  | 2060.5 |  |  | 2164.5 |  |  | 2070.5 |  |  | 2169.5 |  |  | 2031.5 |  |  | 2089.5 |  |  | 2052.5 |  |  | 2011.5 |  |  | 1949 |  |  | 2122 |  |  | 2028 |  |  | 2168.5 |  |  | 2229 |  |  | 2017.5 |  |  | 2079 |  |  | 2098 |  |  | 2121.5 |  |  | 2200.5 |  |  | 2070 |  |  | 2209 |  |  | 2007.5 |  |  | 2167 |  |  | 2011.5 |  |  | 2084.5 |  |  | 2119.5 |  |  | 1977.5 |  |  | 2006.5 |  |  | 2056 |  |  | 2071 |  |  | 1928 |  |  | 2047.5 |  |  | 2012.5 |  |  | 2128.5 |  |  | 2028.5 |  |  | 2044 |  |  | 2031 |  |  | 2091.5 |  |  | 1922 |  |  | 2113.5 |  |  | 2083 |  |  | 2019 |  |  | 1930.5 |  |  | 2053 |  |  | 2073 |  |  | 2010 |  |  | 2089 |  |  | 2025.5 |  |  | 2066.5 |  |  | 2022.5 |  |  | 2163 |  |  | 2018 |  |  | 1991 |  |  | 2001 |  |  | 2005.5 |  |  | 2019 |  |  | 2077.5 |  |  | 2065 |  |  | 2019 |  |  | 2058.5 |  |  | 2024.5 |  |  | 1975 |  |  | 1997.5 |  |  | 2030 |  |  | 2150 |  |  | 2020 |  |  | 2191 |  |  | 1991 |  |  | 1978 |  |  | 2034 |  |  | 2070 |  |  | 1968 |  |  | 1963.5 |  |  | 2039 |  |  | 1905 |  |  | 2139 |  |  | 2087 |  |  | 2120 |  |  | 1960 |  |  | 2015 |  |  | 2083.5 |  |  | 2080 |  |  | 2098.5 |  |  | 2113 |  |  | 2010 |  |  | 2132.5 |  |  | 2054 |  |  | 2186.5 |  |  | 2024 |  |  | 1882 |  |  | 2035.5 |  |  | 2132 |  |  | 2148.5 |  |  | 2098 |  |  | 1961 |  |  | 2165.5 |  |  | 2097.5 |  |  | 2112 |  |  | 2058.5 |  |  | 2063.5 |  |  | 2050 |  |  | 2093 |  |  | 2240.5 |  |  | 1961.5 |  |  | 2093.5 |  |  | 2130 |  |  | 2146 |  |  | 2012 |  |  | 2159 |  |  | 2123 |  |  | 2115.5 |  |  | 2033 |  |  | 1964.5 |  |  | 2090.5 |  |  | 2077 |  |  | 2170 |  |  | 2251.5 |  |  | 1983.5 |  |  | 2035 |  |  | 2093.5 |  |  | 1987.5 |  |  | 2105 |  |  | 1951 |  |  | 1979 |  |  | 2010.5 |  |  | 2175 |  |  | 2063.5 |  |  | 2065.5 |  |  | 1994 |  |  | 1986.5 |  |  | 2017 |  |  | 2058 |  |  | 2100 |  |  | 2120 |  |  | 1890 |  |  | 2155 |  |  | 2171 |  |  | 2061 |  |  | 2188 |  |  | 2037 |  |  | 2051.5 |  |  | 2183.5 |  |  | 2052 |  |  | 1997 |  |  | 2211 |  |  | 2104.5 |  |  | 2148.5 |  |  | 2166.5 |  |  | 1993 |  |  | 2078 |  |  | 2208.5 |  |  | 2080.5 |  |  | 1921.5 |  |  | 2157 |  |  | 2194 |  |  | 2040 |  |  | 2108 |  |  | 2114 |  |  | 2049.5 |  |  | 2011.5 |  |  | 2141 |  |  | 2025 |  |  | 2025 |  |  | 2166 |  |  | 2021 |  |  | 2166.5 |  |  | 2108 |  |  | 2072 |  |  | 2059 |  |  | 2012 |  |  | 2059.5 |  |  | 2177 |  |  | 2085 |  |  | 2022 |  |  | 2159 |  |  | 2173.5 |  |  | 2105 |  |  | 2021 |  |  | 1997 |  |  | 2162.5 |  |  | 2068.5 |  |  | 2184.5 |  |  | 2190 |  |  | 2044 |  |  | 1959 |  |  | 2207 |  |  | 2103 |  |  | 1996.5 |  |  | 2174 |  |  | 2066.5 |  |  | 2131.5 |  |  | 2114.5 |  |  | 2109 |  |  | 2233.5 |  |  | 1983 |  |  | 2014 |  |  | 2056.5 |  |  | 2078.5 |  |  | 2129 |  |  | 2141.5 |  |  | 2201.5 |  |  | 2048 |  |  | 2118 |  |  | 2035.5 |  |  | 2018.5 |  |  | 2215 |  |  | 2063.5 |  |  | 2172 |  |  | 2049 |  |  | 2024.5 |  |  | 2134 |  |  | 1997 |  |  | 2062.5 |  |  | 2048 |  |  | 2261.5 |  |  | 2070 |  |  | 2287 |  |  | 2066 |  |  | 1996 |  |  | 2193.5 |  |  | 2238 |  |  | 2168.5 |  |  | 1930.5 |  |  | 2168.5 |  |  | 2117 |  |  | 2129.5 |  |  | 2255 |  |  | 2117 |  |  | 1906.5 |  |  | 2085.5 |  |  | 2130 |  |  | 2019.5 |  |  | 2158 |  |  | 2030 |  |  | 2200.5 |  |  | 2006 |  |  | 2022.5 |  |  | 2095.5 |  |  | 2094.5 |  |  | 2052 |  |  | 1919 |  |  | 2030 |  |  | 2049.5 |  |  | 2030 |  |  | 2231.5 |  |  | 2083 |  |  | 2046 |  |  | 2009 |  |  | 2089 |  |  | 2131 |  |  | 2111 |  |  | 2040 |  |  | 2217 |  |  | 2122 |  |  | 2049.5 |  |  | 2083 |  |  | 2058 |  |  | 2182.5 |  |  | 1965.5 |  |  | 2098.5 |  |  | 2120.5 |  |  | 2091 |  |  | 2173 |  |  | 1954.5 |  |  | 2196.5 |  |  | 2055.5 |  |  | 2067 |  |  | 2055 |  |  | 2005 |  |  | 2035 |  |  | 1927 |  |  | 2053 |  |  | 2091 |  |  | 2054.5 |  |  | 2108.5 |  |  | 2007 |  |  | 2008.5 |  |  | 2087.5 |  |  | 2008 |  |  | 2129 |  |  | 1992 |  |  | 2079 |  |  | 1998.5 |  |  | 1942.5 |  |  | 2116.5 |  |  | 2061 |  |  | 2015.5 |  |  | 2110 |  |  | 2082 |  |  | 2197 |  |  | 1967.5 |  |  | 2073 |  |  | 1964 |  |  | 2076.5 |  |  | 2002 |  |  | 2153.5 |  |  | 2220 |  |  | 2051.5 |  |  | 1996 |  |  | 2064.5 |  |  | 2076.5 |  |  | 2130 |  |  | 2063 |  |  | 1902 |  |  | 2107 |  |  | 1900.5 |  |  | 2012 |  |  | 2236 |  |  | 1979.5 |  |  | 2177.5 |  |  | 1985.5 |  |  | 2013 |  |  | 2184.5 |  |  | 2127.5 |  |  | 1968.5 |  |  | 2174 |  |  | 2116 |  |  | 2108.5 |  |  | 2145 |  |  | 2170 |  |  | 2133.5 |  |  | 2073 |  |  | 2167 |  |  | 2077 |  |  | 1907 |  |  | 1922.5 |  |  | 2148.5 |  |  | 1980 |  |  | 2158 |  |  | 2126 |  |  | 2026 |  |  | 1993 |  |  | 2026.5 |  |  | 2016.5 |  |  | 2093 |  |  | 2203 |  |  | 2242 |  |  | 2000.5 |  |  | 2267.5 |  |  | 2048 |  |  | 2061 |  |  | 1952 |  |  | 2102.5 |  |  | 2251.5 |  |  | 2093 |  |  | 1955 |  |  | 2088 |  |  | 2098 |  |  | 2047 |  |  | 2203 |  |  | 2001 |  |  | 2192.5 |  |  | 2003 |  |  | 2171 |  |  | 2110 |  |  | 2116.5 |  |  | 2109 |  |  | 1989 |  |  | 1872 |  |  | 2051 |  |  | 2043 |  |  | 2094 |  |  | 2105 |  |  | 2014.5 |  |  | 2061.5 |  |  | 1851.5 |  |  | 2167 |  |  | 2031 |  |  | 2052.5 |  |  | 1894 |  |  | 1981.5 |  |  | 2059.5 |  |  | 2034 |  |  | 2118 |  |  | 2066.5 |  |  | 2097 |  |  | 2071 |  |  | 2087 |  |  | 2090 |  |  | 2123 |  |  | 2044 |  |  | 2026 |  |  | 2107.5 |  |  | 2059 |  |  | 2125 |  |  | 2097 |  |  | 2069 |  |  | 2061 |  |  | 2093 |  |  | 2198 |  |  | 2086 |  |  | 2100 |  |  | 2171.5 |  |  | 2071.5 |  |  | 2083.5 |  |  | 2116.5 |  |  | 2104 |  |  | 1935 |  |  | 2181.5 |  |  | 2017 |  |  | 2051 |  |  | 2006.5 |  |  | 2211.5 |  |  | 2139 |  |  | 2056.5 |  |  | 2057.5 |  |  | 1944 |  |  | 2194 |  |  | 2036 |  |  | 2048 |  |  | 2056.5 |  |  | 2091 |  |  | 1956.5 |  |  | 1976.5 |  |  | 2051 |  |  | 2017 |  |  | 2182.5 |  |  | 2033 |  |  | 2078.5 |  |  | 2117 |  |  | 2103.5 |  |  | 1970.5 |  |  | 1896.5 |  |  | 2119.5 |  |  | 2121.5 |  |  | 1927 |  |  | 1963 |  |  | 2185.5 |  |  | 2121 |  |  | 1981 |  |  | 2039 |  |  | 2168 |  |  | 2210.5 |  |  | 1946 |  |  | 2006 |  |  | 2124 |  |  | 2018.5 |  |  | 2104 |  |  | 1966 |  |  | 2047 |  |  | 2236.5 |  |  | 2110 |  |  | 1873 |  |  | 2075 |  |  | 2189 |  |  | 2309.5 |  |  | 2106 |  |  | 1998.5 |  |  | 2047 |  |  | 2147 |  |  | 2302.5 |  |  | 2112 |  |  | 2018 |  |  | 2046.5 |  |  | 2103 |  |  | 2027 |  |  | 2045 |  |  | 2282.5 |  |  | 2120.5 |  |  | 2116 |  |  | 1962 |  |  | 2052.5 |  |  | 2052.5 |  |  | 2044 |  |  | 2114 |  |  | 2134.5 |  |  | 2264.5 |  |  | 1932.5 |  |  | 2086.5 |  |  | 2053.5 |  |  | 2243 |  |  | 2027.5 |  |  | 2159 |  |  | 2068 |  |  | 2101 |  |  | 2176 |  |  | 2097.5 |  |  | 2072 |  |  | 1972 |  |  | 2101.5 |  |  | 2071.5 |  |  | 1977 |  |  | 2148.5 |  |  | 2075.5 |  |  | 2194 |  |  | 1995 |  |  | 2051 |  |  | 2117.5 |  |  | 2132 |  |  | 2152.5 |  |  | 2152 |  |  | 2042 |  |  | 2312.5 |  |  | 2022 |  |  | 2162 |  |  | 1983 |  |  | 2158 |  |  | 2118 |  |  | 2102 |  |  | 2100 |  |  | 2088 |  |  | 1940.5 |  |  | 2027.5 |  |  | 2012 |  |  | 2088.5 |  |  | 1915.5 |  |  | 1967 |  |  | 2001 |  |  | 2149 |  |  | 2168.5 |  |  | 2003.5 |  |  | 2145 |  |  | 2127 |  |  | 1969 |  |  | 1981 |  |  | 2050 |  |  | 2029 |  |  | 2128 |  |  | 1986.5 |  |  | 2161 |  |  | 2088 |  |  | 2193 |  |  | 2034 |  |  | 1944 |  |  | 2086.5 |  |  | 2238.5 |  |  | 1900.5 |  |  | 1985 |  |  | 1979 |  |  | 1987.5 |  |  | 2191.5 |  |  | 2119.5 |  |  | 1990 |  |  | 2150.5 |  |  | 2109.5 |  |  | 2240 |  |  | 2146.5 |  |  | 2088.5 |  |  | 2075 |  |  | 1961 |  |  | 2026 |  |  | 2182 |  |  | 2025 |  |  | 1881 |  |  | 2112 |  |  | 2208 |  |  | 1959 |  |  | 2075 |  |  | 2179.5 |  |  | 2075 |  |  | 2102 |  |  | 1989 |  |  | 2033.5 |  |  | 2015 |  |  | 2105.5 |  |  | 2230 |  |  | 2114 |  |  | 2066 |  |  | 2075 |  |  | 2202.5 |  |  | 2022 |  |  | 1997 |  |  | 2155.5 |  |  | 2111 |  |  | 2013 |  |  | 2013.5 |  |  | 2025.5 |  |  | 2061 |  |  | 1984.5 |  |  | 2200 |  |  | 2008.5 |  |  | 2188 |  |  | 2094 |  |  | 2015.5 |  |  | 2159.5 |  |  | 2045 |  |  | 2149 |  |  | 2070 |  |  | 2083 |  |  | 1947 |  |  | 2068 |  |  | 1932 |  |  | 1956 |  |  | 2173.5 |  |  | 1952 |  |  | 2174.5 |  |  | 2030 |  |  | 2143.5 |  |  | 2007.5 |  |  | 1998 |  |  | 2060 |  |  | 2160.5 |  |  | 2065 |  |  | 2138 |  |  | 2155 |  |  | 2061.5 |  |  | 2108 |  |  | 1977.5 |  |  | 1888 |  |  | 2017 |  |  | 2079 |  |  | 2100 |  |  | 2157.5 |  |  | 2013 |  |  | 2065 |  |  | 2104 |  |  | 1948.5 |  |  | 2195 |  |  | 2142 |  |  | 2092 |  |  | 2027 |  |  | 2070.5 |  |  | 1980.5 |  |  | 2107 |  |  | 2194 |  |  | 2081 |  |  | 2153.5 |  |  | 2053 |  |  | 1979 |  |  | 2040 |  |  | 2203.5 |  |  | 2044.5 |  |  | 2019.5 |  |  | 2073 |  |  | 2134 |  |  | 2139 |  |  | 2013.5 |  |  | 2104 |  |  | 2027.5 |  |  | 1927 |  |  | 1973 |  |  | 2048 |  |  | 2058.5 |  |  | 2119.5 |  |  | 2064 |  |  | 2044 |  |  | 2192.5 |  |  | 2084 |  |  | 2048 |  |  | 2125.5 |  |  | 1995 |  |  | 2026 |  |  | 2107.5 |  |  | 2002 |  |  | 2104 |  |  | 2035.5 |  |  | 2193 |  |  | 1994.5 |  |  | 2086 |  |  | 1915.5 |  |  | 2124.5 |  |  | 1945 |  |  | 2181 |  |  | 2130.5 |  |  | 2054.5 |  |  | 2199 |  |  | 2070 |  |  | 2107 |  |  | 2077.5 |  |  | 2086 |  |  | 1873 |  |  | 2009 |  |  | 2146.5 |  |  | 2122.5 |  |  | 2108 |  |  | 2184 |  |  | 2013 |  |  | 1990 |  |  | 2165 |  |  | 2019 |  |  | 2026 |  |  | 2048.5 |  |  | 2244.5 |  |  | 1993.5 |  |  | 2066 |  |  | 2061.5 |  |  | 2071 |  |  | 2027 |  |  | 2105.5 |  |  | 1958.5 |  |  | 1951 |  |  | 2113 |  |  | 2015.5 |  |  | 2070 |  |  | 2127 |  |  | 1957.5 |  |  | 2139.5 |  |  | 2052 |  |  | 2009 |  |  | 2093 |  |  | 1968.5 |  |  | 1979 |  |  | 1952 |  |  | 2085 |  |  | 2123 |  |  | 2196 |  |  | 1991.5 |  |  | 2185 |  |  | 1992 |  |  | 1969 |  |  | 2214.5 |  |  | 2083 |  |  | 2016.5 |  |  | 1993.5 |  |  | 2061 |  |  | 2139 |  |  | 2031.5 |  |  | 2019.5 |  |  | 1960.5 |  |  | 2045.5 |  |  | 2064.5 |  |  | 2108 |  |  | 2081 |  |  | 2085.5 |  |  | 2015.5 |  |  | 2065 |  |  | 2022 |  |  | 2041.5 |  |  | 2215 |  |  | 2026 |  |  | 1910 |  |  | 2102.5 |  |  | 2203 |  |  | 2000.5 |  |  | 1958 |  |  | 2082.5 |  |  | 2250.5 |  |  | 2203.5 |  |  | 2203 |  |  | 2111 |  |  | 2078.5 |  |  | 2055.5 |  |  | 2114 |  |  | 2067 |  |  | 2126.5 |  |  | 2187 |  |  | 2105.5 |  |  | 2030.5 |  |  | 2150 |  |  | 2069 |  |  | 1917.5 |  |  | 2139.5 |  |  | 2068 |  |  | 2019.5 |  |  | 2111.5 |  |  | 2126 |  |  | 2145 |  |  | 2160 |  |  | 2042.5 |  |  | 2165 |  |  | 2006 |  |  | 2100 |  |  | 2006 |  |  | 2043 |  |  | 2028 |  |  | 2206.5 |  |  | 2028.5 |  |  | 2048 |  |  | 2040 |  |  | 2097 |  |  | 2041.5 |  |  | 2024 |  |  | 2207 |  |  | 1986.5 |  |  | 2161.5 |  |  | 2063 |  |  | 2028.5 |  |  | 2136 |  |  | 1957 |  |  | 2080 |  |  | 2187.5 |  |  | 2219 |  |  | 1955.5 |  |  | 2047.5 |  |  | 1975 |  |  | 2100.5 |  |  | 1873.5 |  |  | 2021 |  |  | 1977 |  |  | 2148 |  |  | 1976.5 |  |  | 1950 |  |  | 2029.5 |  |  | 2064.5 |  |  | 2154 |  |  | 1971.5 |  |  | 1955 |  |  | 2061 |  |  | 2025 |  |  | 1970 |  |  | 1946 |  |  | 2149.5 |  |  | 2071 |  |  | 2135 |  |  | 1985 |  |  | 2133 |  |  | 2072.5 |  |  | 2093.5 |  |  | 2044 |  |  | 2148 |  |  | 2081 |  |  | 2058 |  |  | 2120 |  |  | 1990.5 |  |  | 2055 |  |  | 2124.5 |  |  | 2165 |  |  | 1922 |  |  | 2020 |  |  | 2064 |  |  | 2115.5 |  |  | 2069 |  |  | 2083.5 |  |  | 2031 |  |  | 2205 |  |  | 2137 |  |  | 2084.5 |  |  | 1998 |  |  | 1950 |  |  | 1990 |  |  | 2210 |  |  | 2280 |  |  | 2009.5 |  |  | 2127.5 |  |  | 2014 |  |  | 2058.5 |  |  | 2012 |  |  | 1984.5 |  |  | 2043.5 |  |  | 2021.5 |  |  | 2012.5 |  |  | 1934 |  |  | 2224 |  |  | 1952 |  |  | 1980 |  |  | 2053 |  |  | 2155 |  |  | 2019.5 |  |  | 2002.5 |  |  | 2169.5 |  |  | 2121 |  |  | 2134.5 |  |  | 2030.5 |  |  | 2141.5 |  |  | 1972.5 |  |  | 2061 |  |  | 2097.5 |  |  | 2073.5 |  |  | 2160 |  |  | 1984.5 |  |  | 2213.5 |  |  | 2135.5 |  |  | 2241 |  |  | 2091.5 |  |  | 2085 |  |  | 2077 |  |  | 2036.5 |  |  | 2130.5 |  |  | 2103 |  |  | 2124 |  |  | 1934.5 |  |  | 1928.5 |  |  | 2052.5 |  |  | 2141 |  |  | 2004 |  |  | 2059 |  |  | 2157.5 |  |  | 2135.5 |  |  | 2108 |  |  | 2120.5 |  |  | 1915 |  |  | 2070 |  |  | 2098.5 |  |  | 2026.5 |  |  | 2035 |  |  | 2083.5 |  |  | 2124 |  |  | 2001.5 |  |  | 2197.5 |  |  | 2138 |  |  | 2059.5 |  |  | 2159 |  |  | 2079.5 |  |  | 2064 |  |  | 2145 |  |  | 2115 |  |  | 2034.5 |  |  | 1950.5 |  |  | 2121 |  |  | 2044 |  |  | 1971 |  |  | 2047.5 |  |  | 2067.5 |  |  | 2142 |  |  | 2103.5 |  |  | 2053 |  |  | 1946.5 |  |  | 2096.5 |  |  | 1992 |  |  | 2072 |  |  | 2066 |  |  | 2042.5 |  |  | 2012 |  |  | 2107.5 |  |  | 2162 |  |  | 2060.5 |  |  | 2221 |  |  | 1905.5 |  |  | 2038 |  |  | 2068.5 |  |  | 2060.5 |  |  | 2010 |  |  | 2064 |  |  | 2275 |  |  | 2052 |  |  | 2141.5 |  |  | 1949 |  |  | 2009.5 |  |  | 1898 |  |  | 1986 |  |  | 2001 |  |  | 2190 |  |  | 2092 |  |  | 2042 |  |  | 2135 |  |  | 2041.5 |  |  | 2010 |  |  | 2133
73 |  | 2284.5 |  |  | 2229 |  |  | 2174.5 |  |  | 2106 |  |  | 2038.5 |  |  | 2129 |  |  | 2121 |  |  | 2144 |  |  | 1991.5 |  |  | 2023 |  |  | 2077 |  |  | 2204 |  |  | 2185 |  |  | 2291 |  |  | 2079.5 |  |  | 2135.5 |  |  | 2016 |  |  | 2103 |  |  | 2180 |  |  | 2013.5 |  |  | 2145 |  |  | 2146 |  |  | 2003 |  |  | 2116 |  |  | 2105.5 |  |  | 2207 |  |  | 2066 |  |  | 2095 |  |  | 2179 |  |  | 2022 |  |  | 2146 |  |  | 2073.5 |  |  | 2204.5 |  |  | 2104.5 |  |  | 2034 |  |  | 2042.5 |  |  | 2103.5 |  |  | 2203.5 |  |  | 2169 |  |  | 2109 |  |  | 2002.5 |  |  | 2048 |  |  | 2140.5 |  |  | 2090.5 |  |  | 2163.5 |  |  | 2303.5 |  |  | 2253.5 |  |  | 2069 |  |  | 1957 |  |  | 2069.5 |  |  | 2069 |  |  | 2056.5 |  |  | 1980.5 |  |  | 2104 |  |  | 2081 |  |  | 2050 |  |  | 2000 |  |  | 2206 |  |  | 2148 |  |  | 2089.5 |  |  | 2084.5 |  |  | 2101.5 |  |  | 2023 |  |  | 2131 |  |  | 1939 |  |  | 2016.5 |  |  | 2074 |  |  | 2063.5 |  |  | 2145.5 |  |  | 2268.5 |  |  | 2104 |  |  | 2258 |  |  | 2197 |  |  | 2084.5 |  |  | 2211.5 |  |  | 2091.5 |  |  | 2198.5 |  |  | 2078.5 |  |  | 2110.5 |  |  | 2091.5 |  |  | 2058.5 |  |  | 1996 |  |  | 2161 |  |  | 2043 |  |  | 2207.5 |  |  | 2244 |  |  | 2038.5 |  |  | 2118 |  |  | 2124 |  |  | 2147.5 |  |  | 2224.5 |  |  | 2085 |  |  | 2233 |  |  | 2022.5 |  |  | 2214 |  |  | 2032.5 |  |  | 2123.5 |  |  | 2158.5 |  |  | 2016.5 |  |  | 2053.5 |  |  | 2077 |  |  | 2097 |  |  | 1954 |  |  | 2086.5 |  |  | 2033.5 |  |  | 2167.5 |  |  | 2067.5 |  |  | 2091 |  |  | 2057 |  |  | 2117.5 |  |  | 1948 |  |  | 2128.5 |  |  | 2130 |  |  | 2066 |  |  | 1951.5 |  |  | 2074 |  |  | 2097 |  |  | 2036 |  |  | 2118 |  |  | 2064.5 |  |  | 2092.5 |  |  | 2051.5 |  |  | 2210 |  |  | 2065 |  |  | 2012 |  |  | 2022 |  |  | 2044.5 |  |  | 2043 |  |  | 2103.5 |  |  | 2104 |  |  | 2045 |  |  | 2097.5 |  |  | 2039.5 |  |  | 2022 |  |  | 2023.5 |  |  | 2045 |  |  | 2176 |  |  | 2059 |  |  | 2230 |  |  | 2030 |  |  | 2017 |  |  | 2055 |  |  | 2109 |  |  | 2015 |  |  | 1987.5 |  |  | 2063 |  |  | 1944 |  |  | 2186 |  |  | 2111 |  |  | 2149 |  |  | 1981 |  |  | 2041 |  |  | 2122.5 |  |  | 2119 |  |  | 2137.5 |  |  | 2128 |  |  | 2034 |  |  | 2171.5 |  |  | 2080 |  |  | 2210.5 |  |  | 2039 |  |  | 1911 |  |  | 2061.5 |  |  | 2156 |  |  | 2195.5 |  |  | 2137 |  |  | 1976 |  |  | 2204.5 |  |  | 2136.5 |  |  | 2138 |  |  | 2079.5 |  |  | 2102.5 |  |  | 2071 |  |  | 2108 |  |  | 2266.5 |  |  | 1982.5 |  |  | 2122.5 |  |  | 2154 |  |  | 2175 |  |  | 2051 |  |  | 2198 |  |  | 2162 |  |  | 2162.5 |  |  | 2059 |  |  | 2003.5 |  |  | 2119.5 |  |  | 2116 |  |  | 2185 |  |  | 2298.5 |  |  | 2012.5 |  |  | 2074 |  |  | 2132.5 |  |  | 2002.5 |  |  | 2126 |  |  | 1980 |  |  | 2000 |  |  | 2049.5 |  |  | 2201 |  |  | 2092.5 |  |  | 2104.5 |  |  | 2015 |  |  | 2033.5 |  |  | 2032 |  |  | 2084 |  |  | 2124 |  |  | 2159 |  |  | 1905 |  |  | 2181 |  |  | 2197 |  |  | 2087 |  |  | 2227 |  |  | 2058 |  |  | 2090.5 |  |  | 2198.5 |  |  | 2076 |  |  | 2012 |  |  | 2237 |  |  | 2125.5 |  |  | 2187.5 |  |  | 2190.5 |  |  | 2008 |  |  | 2125 |  |  | 2255.5 |  |  | 2127.5 |  |  | 1960.5 |  |  | 2186 |  |  | 2215 |  |  | 2069 |  |  | 2123 |  |  | 2138 |  |  | 2064.5 |  |  | 2032.5 |  |  | 2188 |  |  | 2064 |  |  | 2046 |  |  | 2205 |  |  | 2068 |  |  | 2205.5 |  |  | 2123 |  |  | 2093 |  |  | 2098 |  |  | 2033 |  |  | 2080.5 |  |  | 2198 |  |  | 2100 |  |  | 2048 |  |  | 2198 |  |  | 2194.5 |  |  | 2152 |  |  | 2047 |  |  | 2044 |  |  | 2183.5 |  |  | 2115.5 |  |  | 2205.5 |  |  | 2229 |  |  | 2065 |  |  | 1983 |  |  | 2246 |  |  | 2129 |  |  | 2035.5 |  |  | 2200 |  |  | 2092.5 |  |  | 2152.5 |  |  | 2129.5 |  |  | 2133 |  |  | 2254.5 |  |  | 1998 |  |  | 2029 |  |  | 2080.5 |  |  | 2102.5 |  |  | 2153 |  |  | 2180.5 |  |  | 2240.5 |  |  | 2095 |  |  | 2142 |  |  | 2074.5 |  |  | 2065.5 |  |  | 2236 |  |  | 2110.5 |  |  | 2211 |  |  | 2088 |  |  | 2039.5 |  |  | 2160 |  |  | 2012 |  |  | 2101.5 |  |  | 2087 |  |  | 2282.5 |  |  | 2099 |  |  | 2308 |  |  | 2105 |  |  | 2043 |  |  | 2232.5 |  |  | 2253 |  |  | 2192.5 |  |  | 1969.5 |  |  | 2192.5 |  |  | 2141 |  |  | 2144.5 |  |  | 2284 |  |  | 2143 |  |  | 1935.5 |  |  | 2106.5 |  |  | 2177 |  |  | 2045.5 |  |  | 2197 |  |  | 2054 |  |  | 2247.5 |  |  | 2021 |  |  | 2051.5 |  |  | 2134.5 |  |  | 2120.5 |  |  | 2099 |  |  | 1940 |  |  | 2045 |  |  | 2078.5 |  |  | 2054 |  |  | 2255.5 |  |  | 2122 |  |  | 2070 |  |  | 2035 |  |  | 2118 |  |  | 2178 |  |  | 2137 |  |  | 2087 |  |  | 2256 |  |  | 2143 |  |  | 2096.5 |  |  | 2104 |  |  | 2097 |  |  | 2211.5 |  |  | 2012.5 |  |  | 2124.5 |  |  | 2146.5 |  |  | 2112 |  |  | 2212 |  |  | 1983.5 |  |  | 2220.5 |  |  | 2081.5 |  |  | 2114 |  |  | 2070 |  |  | 2029 |  |  | 2082 |  |  | 1953 |  |  | 2092 |  |  | 2112 |  |  | 2101.5 |  |  | 2129.5 |  |  | 2033 |  |  | 2034.5 |  |  | 2126.5 |  |  | 2029 |  |  | 2144 |  |  | 2021 |  |  | 2118 |  |  | 2045.5 |  |  | 1968.5 |  |  | 2163.5 |  |  | 2085 |  |  | 2036.5 |  |  | 2134 |  |  | 2097 |  |  | 2236 |  |  | 1996.5 |  |  | 2097 |  |  | 2003 |  |  | 2091.5 |  |  | 2041 |  |  | 2182.5 |  |  | 2249 |  |  | 2075.5 |  |  | 2043 |  |  | 2093.5 |  |  | 2102.5 |  |  | 2156 |  |  | 2102 |  |  | 1923 |  |  | 2128 |  |  | 1947.5 |  |  | 2036 |  |  | 2257 |  |  | 2018.5 |  |  | 2224.5 |  |  | 2000.5 |  |  | 2034 |  |  | 2213.5 |  |  | 2153.5 |  |  | 2015.5 |  |  | 2198 |  |  | 2137 |  |  | 2147.5 |  |  | 2184 |  |  | 2217 |  |  | 2162.5 |  |  | 2099 |  |  | 2191 |  |  | 2098 |  |  | 1933 |  |  | 1948.5 |  |  | 2172.5 |  |  | 2027 |  |  | 2205 |  |  | 2165 |  |  | 2052 |  |  | 2040 |  |  | 2050.5 |  |  | 2055.5 |  |  | 2108 |  |  | 2227 |  |  | 2281 |  |  | 2029.5 |  |  | 2306.5 |  |  | 2074 |  |  | 2100 |  |  | 1973 |  |  | 2117.5 |  |  | 2280.5 |  |  | 2108 |  |  | 1970 |  |  | 2135 |  |  | 2124 |  |  | 2076 |  |  | 2218 |  |  | 2025 |  |  | 2221.5 |  |  | 2029 |  |  | 2210 |  |  | 2136 |  |  | 2163.5 |  |  | 2124 |  |  | 2004 |  |  | 1901 |  |  | 2075 |  |  | 2064 |  |  | 2133 |  |  | 2134 |  |  | 2040.5 |  |  | 2076.5 |  |  | 1890.5 |  |  | 2214 |  |  | 2055 |  |  | 2099.5 |  |  | 1933 |  |  | 1996.5 |  |  | 2080.5 |  |  | 2063 |  |  | 2147 |  |  | 2090.5 |  |  | 2118 |  |  | 2110 |  |  | 2111 |  |  | 2116 |  |  | 2170 |  |  | 2070 |  |  | 2073 |  |  | 2146.5 |  |  | 2098 |  |  | 2140 |  |  | 2144 |  |  | 2084 |  |  | 2085 |  |  | 2122 |  |  | 2224 |  |  | 2125 |  |  | 2121 |  |  | 2197.5 |  |  | 2086.5 |  |  | 2098.5 |  |  | 2155.5 |  |  | 2119 |  |  | 1974 |  |  | 2196.5 |  |  | 2064 |  |  | 2098 |  |  | 2021.5 |  |  | 2250.5 |  |  | 2163 |  |  | 2103.5 |  |  | 2078.5 |  |  | 1973 |  |  | 2220 |  |  | 2062 |  |  | 2095 |  |  | 2071.5 |  |  | 2130 |  |  | 2003.5 |  |  | 2015.5 |  |  | 2072 |  |  | 2056 |  |  | 2203.5 |  |  | 2080 |  |  | 2117.5 |  |  | 2132 |  |  | 2127.5 |  |  | 1996.5 |  |  | 1943.5 |  |  | 2166.5 |  |  | 2145.5 |  |  | 1948 |  |  | 2002 |  |  | 2224.5 |  |  | 2147 |  |  | 2020 |  |  | 2078 |  |  | 2215 |  |  | 2231.5 |  |  | 1961 |  |  | 2030 |  |  | 2150 |  |  | 2047.5 |  |  | 2133 |  |  | 1987 |  |  | 2073 |  |  | 2260.5 |  |  | 2149 |  |  | 1912 |  |  | 2122 |  |  | 2213 |  |  | 2348.5 |  |  | 2132 |  |  | 2013.5 |  |  | 2086 |  |  | 2173 |  |  | 2341.5 |  |  | 2151 |  |  | 2042 |  |  | 2072.5 |  |  | 2129 |  |  | 2048 |  |  | 2060 |  |  | 2329.5 |  |  | 2159.5 |  |  | 2140 |  |  | 2001 |  |  | 2091.5 |  |  | 2067.5 |  |  | 2068 |  |  | 2138 |  |  | 2160.5 |  |  | 2288.5 |  |  | 1961.5 |  |  | 2110.5 |  |  | 2079.5 |  |  | 2282 |  |  | 2056.5 |  |  | 2198 |  |  | 2097 |  |  | 2148 |  |  | 2197 |  |  | 2144.5 |  |  | 2098 |  |  | 2001 |  |  | 2125.5 |  |  | 2110.5 |  |  | 2016 |  |  | 2174.5 |  |  | 2099.5 |  |  | 2209 |  |  | 2016 |  |  | 2066 |  |  | 2143.5 |  |  | 2153 |  |  | 2173.5 |  |  | 2176 |  |  | 2081 |  |  | 2327.5 |  |  | 2061 |  |  | 2186 |  |  | 2007 |  |  | 2197 |  |  | 2144 |  |  | 2123 |  |  | 2115 |  |  | 2109 |  |  | 1979.5 |  |  | 2056.5 |  |  | 2059 |  |  | 2127.5 |  |  | 1936.5 |  |  | 2006 |  |  | 2030 |  |  | 2175 |  |  | 2194.5 |  |  | 2018.5 |  |  | 2184 |  |  | 2151 |  |  | 1993 |  |  | 2010 |  |  | 2071 |  |  | 2050 |  |  | 2143 |  |  | 2007.5 |  |  | 2200 |  |  | 2127 |  |  | 2208 |  |  | 2055 |  |  | 1965 |  |  | 2107.5 |  |  | 2264.5 |  |  | 1939.5 |  |  | 2011 |  |  | 2018 |  |  | 2026.5 |  |  | 2215.5 |  |  | 2166.5 |  |  | 2014 |  |  | 2189.5 |  |  | 2135.5 |  |  | 2261 |  |  | 2185.5 |  |  | 2117.5 |  |  | 2099 |  |  | 1987 |  |  | 2065 |  |  | 2206 |  |  | 2072 |  |  | 1920 |  |  | 2151 |  |  | 2229 |  |  | 1998 |  |  | 2096 |  |  | 2205.5 |  |  | 2096 |  |  | 2117 |  |  | 2036 |  |  | 2062.5 |  |  | 2054 |  |  | 2120.5 |  |  | 2256 |  |  | 2138 |  |  | 2087 |  |  | 2114 |  |  | 2217.5 |  |  | 2061 |  |  | 2012 |  |  | 2184.5 |  |  | 2140 |  |  | 2042 |  |  | 2052.5 |  |  | 2064.5 |  |  | 2108 |  |  | 2013.5 |  |  | 2229 |  |  | 2037.5 |  |  | 2209 |  |  | 2115 |  |  | 2041.5 |  |  | 2174.5 |  |  | 2060 |  |  | 2175 |  |  | 2085 |  |  | 2104 |  |  | 1986 |  |  | 2092 |  |  | 1947 |  |  | 1980 |  |  | 2188.5 |  |  | 1973 |  |  | 2221.5 |  |  | 2054 |  |  | 2167.5 |  |  | 2046.5 |  |  | 2037 |  |  | 2099 |  |  | 2199.5 |  |  | 2086 |  |  | 2164 |  |  | 2179 |  |  | 2082.5 |  |  | 2132 |  |  | 2003.5 |  |  | 1912 |  |  | 2064 |  |  | 2094 |  |  | 2129 |  |  | 2183.5 |  |  | 2052 |  |  | 2080 |  |  | 2133 |  |  | 1977.5 |  |  | 2234 |  |  | 2166 |  |  | 2113 |  |  | 2048 |  |  | 2094.5 |  |  | 2001.5 |  |  | 2146 |  |  | 2209 |  |  | 2120 |  |  | 2200.5 |  |  | 2092 |  |  | 2003 |  |  | 2061 |  |  | 2250.5 |  |  | 2068.5 |  |  | 2066.5 |  |  | 2112 |  |  | 2163 |  |  | 2154 |  |  | 2034.5 |  |  | 2130 |  |  | 2066.5 |  |  | 1966 |  |  | 1994 |  |  | 2069 |  |  | 2087.5 |  |  | 2134.5 |  |  | 2088 |  |  | 2059 |  |  | 2207.5 |  |  | 2123 |  |  | 2074 |  |  | 2151.5 |  |  | 2010 |  |  | 2041 |  |  | 2128.5 |  |  | 2041 |  |  | 2143 |  |  | 2064.5 |  |  | 2240 |  |  | 2018.5 |  |  | 2112 |  |  | 1944.5 |  |  | 2139.5 |  |  | 1971 |  |  | 2228 |  |  | 2169.5 |  |  | 2083.5 |  |  | 2225 |  |  | 2109 |  |  | 2122 |  |  | 2098.5 |  |  | 2133 |  |  | 1912 |  |  | 2033 |  |  | 2175.5 |  |  | 2161.5 |  |  | 2123 |  |  | 2213 |  |  | 2039 |  |  | 2029 |  |  | 2194 |  |  | 2058 |  |  | 2073 |  |  | 2072.5 |  |  | 2268.5 |  |  | 2022.5 |  |  | 2087 |  |  | 2076.5 |  |  | 2118 |  |  | 2074 |  |  | 2131.5 |  |  | 1997.5 |  |  | 1998 |  |  | 2152 |  |  | 2054.5 |  |  | 2096 |  |  | 2151 |  |  | 1972.5 |  |  | 2168.5 |  |  | 2067 |  |  | 2048 |  |  | 2132 |  |  | 1983.5 |  |  | 2018 |  |  | 1991 |  |  | 2106 |  |  | 2170 |  |  | 2235 |  |  | 2030.5 |  |  | 2214 |  |  | 2018 |  |  | 1990 |  |  | 2238.5 |  |  | 2104 |  |  | 2045.5 |  |  | 2019.5 |  |  | 2087 |  |  | 2186 |  |  | 2057.5 |  |  | 2045.5 |  |  | 1981.5 |  |  | 2071.5 |  |  | 2111.5 |  |  | 2137 |  |  | 2102 |  |  | 2111.5 |  |  | 2054.5 |  |  | 2091 |  |  | 2037 |  |  | 2088.5 |  |  | 2230 |  |  | 2073 |  |  | 1957 |  |  | 2149.5 |  |  | 2232 |  |  | 2026.5 |  |  | 1982 |  |  | 2129.5 |  |  | 2276.5 |  |  | 2227.5 |  |  | 2242 |  |  | 2140 |  |  | 2107.5 |  |  | 2084.5 |  |  | 2135 |  |  | 2088 |  |  | 2147.5 |  |  | 2226 |  |  | 2120.5 |  |  | 2045.5 |  |  | 2171 |  |  | 2090 |  |  | 1956.5 |  |  | 2178.5 |  |  | 2107 |  |  | 2034.5 |  |  | 2135.5 |  |  | 2141 |  |  | 2184 |  |  | 2199 |  |  | 2066.5 |  |  | 2186 |  |  | 2053 |  |  | 2121 |  |  | 2053 |  |  | 2090 |  |  | 2057 |  |  | 2221.5 |  |  | 2067.5 |  |  | 2074 |  |  | 2055 |  |  | 2118 |  |  | 2070.5 |  |  | 2045 |  |  | 2246 |  |  | 2025.5 |  |  | 2200.5 |  |  | 2092 |  |  | 2075.5 |  |  | 2175 |  |  | 1986 |  |  | 2101 |  |  | 2216.5 |  |  | 2240 |  |  | 1994.5 |  |  | 2086.5 |  |  | 1999 |  |  | 2115.5 |  |  | 1912.5 |  |  | 2060 |  |  | 2001 |  |  | 2195 |  |  | 2000.5 |  |  | 1974 |  |  | 2055.5 |  |  | 2093.5 |  |  | 2193 |  |  | 1992.5 |  |  | 1994 |  |  | 2108 |  |  | 2054 |  |  | 2017 |  |  | 1985 |  |  | 2196.5 |  |  | 2086 |  |  | 2161 |  |  | 2024 |  |  | 2154 |  |  | 2096.5 |  |  | 2132.5 |  |  | 2065 |  |  | 2169 |  |  | 2096 |  |  | 2105 |  |  | 2135 |  |  | 2016.5 |  |  | 2070 |  |  | 2153.5 |  |  | 2191 |  |  | 1948 |  |  | 2059 |  |  | 2079 |  |  | 2162.5 |  |  | 2116 |  |  | 2122.5 |  |  | 2052 |  |  | 2252 |  |  | 2161 |  |  | 2105.5 |  |  | 2022 |  |  | 1976 |  |  | 2014 |  |  | 2234 |  |  | 2304 |  |  | 2048.5 |  |  | 2166.5 |  |  | 2038 |  |  | 2073.5 |  |  | 2033 |  |  | 1999.5 |  |  | 2069.5 |  |  | 2045.5 |  |  | 2033.5 |  |  | 1973 |  |  | 2248 |  |  | 1991 |  |  | 2001 |  |  | 2077 |  |  | 2181 |  |  | 2043.5 |  |  | 2041.5 |  |  | 2184.5 |  |  | 2136 |  |  | 2173.5 |  |  | 2045.5 |  |  | 2188.5 |  |  | 1998.5 |  |  | 2100 |  |  | 2121.5 |  |  | 2102.5 |  |  | 2181 |  |  | 1999.5 |  |  | 2239.5 |  |  | 2164.5 |  |  | 2262 |  |  | 2130.5 |  |  | 2100 |  |  | 2106 |  |  | 2060.5 |  |  | 2154.5 |  |  | 2118 |  |  | 2163 |  |  | 1958.5 |  |  | 1957.5 |  |  | 2073.5 |  |  | 2180 |  |  | 2019 |  |  | 2085 |  |  | 2183.5 |  |  | 2182.5 |  |  | 2155 |  |  | 2141.5 |  |  | 1944 |  |  | 2091 |  |  | 2124.5 |  |  | 2041.5 |  |  | 2064 |  |  | 2109.5 |  |  | 2145 |  |  | 2027.5 |  |  | 2221.5 |  |  | 2167 |  |  | 2088.5 |  |  | 2188 |  |  | 2100.5 |  |  | 2085 |  |  | 2160 |  |  | 2136 |  |  | 2081.5 |  |  | 1965.5 |  |  | 2136 |  |  | 2083 |  |  | 2010 |  |  | 2062.5 |  |  | 2082.5 |  |  | 2189 |  |  | 2118.5 |  |  | 2082 |  |  | 1985.5 |  |  | 2125.5 |  |  | 2016 |  |  | 2087 |  |  | 2087 |  |  | 2081.5 |  |  | 2027 |  |  | 2131.5 |  |  | 2177 |  |  | 2084.5 |  |  | 2250 |  |  | 1934.5 |  |  | 2059 |  |  | 2107.5 |  |  | 2089.5 |  |  | 2036 |  |  | 2090 |  |  | 2314 |  |  | 2099 |  |  | 2180.5 |  |  | 1996 |  |  | 2056.5 |  |  | 1919 |  |  | 2025 |  |  | 2040 |  |  | 2219 |  |  | 2139 |  |  | 2057 |  |  | 2174 |  |  | 2062.5 |  |  | 2025 |  |  | 2162
74 |  | 2313.5 |  |  | 2253 |  |  | 2203.5 |  |  | 2121 |  |  | 2064.5 |  |  | 2168 |  |  | 2168 |  |  | 2183 |  |  | 2017.5 |  |  | 2047 |  |  | 2103 |  |  | 2251 |  |  | 2214 |  |  | 2330 |  |  | 2103.5 |  |  | 2161.5 |  |  | 2040 |  |  | 2142 |  |  | 2227 |  |  | 2042.5 |  |  | 2184 |  |  | 2175 |  |  | 2050 |  |  | 2155 |  |  | 2120.5 |  |  | 2254 |  |  | 2105 |  |  | 2134 |  |  | 2194 |  |  | 2051 |  |  | 2175 |  |  | 2088.5 |  |  | 2228.5 |  |  | 2125.5 |  |  | 2073 |  |  | 2081.5 |  |  | 2132.5 |  |  | 2232.5 |  |  | 2208 |  |  | 2148 |  |  | 2028.5 |  |  | 2077 |  |  | 2155.5 |  |  | 2137.5 |  |  | 2184.5 |  |  | 2329.5 |  |  | 2300.5 |  |  | 2090 |  |  | 1981 |  |  | 2108.5 |  |  | 2108 |  |  | 2082.5 |  |  | 2019.5 |  |  | 2130 |  |  | 2096 |  |  | 2097 |  |  | 2039 |  |  | 2235 |  |  | 2163 |  |  | 2128.5 |  |  | 2108.5 |  |  | 2116.5 |  |  | 2052 |  |  | 2178 |  |  | 1960 |  |  | 2031.5 |  |  | 2100 |  |  | 2102.5 |  |  | 2160.5 |  |  | 2292.5 |  |  | 2130 |  |  | 2297 |  |  | 2226 |  |  | 2123.5 |  |  | 2235.5 |  |  | 2138.5 |  |  | 2227.5 |  |  | 2125.5 |  |  | 2149.5 |  |  | 2106.5 |  |  | 2073.5 |  |  | 2035 |  |  | 2176 |  |  | 2064 |  |  | 2228.5 |  |  | 2283 |  |  | 2077.5 |  |  | 2157 |  |  | 2163 |  |  | 2186.5 |  |  | 2263.5 |  |  | 2106 |  |  | 2248 |  |  | 2061.5 |  |  | 2253 |  |  | 2079.5 |  |  | 2138.5 |  |  | 2173.5 |  |  | 2040.5 |  |  | 2079.5 |  |  | 2098 |  |  | 2144 |  |  | 1980 |  |  | 2101.5 |  |  | 2059.5 |  |  | 2182.5 |  |  | 2082.5 |  |  | 2130 |  |  | 2086 |  |  | 2146.5 |  |  | 1974 |  |  | 2167.5 |  |  | 2159 |  |  | 2090 |  |  | 1998.5 |  |  | 2098 |  |  | 2136 |  |  | 2065 |  |  | 2144 |  |  | 2090.5 |  |  | 2139.5 |  |  | 2080.5 |  |  | 2239 |  |  | 2104 |  |  | 2051 |  |  | 2043 |  |  | 2070.5 |  |  | 2067 |  |  | 2142.5 |  |  | 2133 |  |  | 2074 |  |  | 2126.5 |  |  | 2054.5 |  |  | 2061 |  |  | 2047.5 |  |  | 2074 |  |  | 2200 |  |  | 2085 |  |  | 2259 |  |  | 2045 |  |  | 2056 |  |  | 2094 |  |  | 2156 |  |  | 2041 |  |  | 2008.5 |  |  | 2102 |  |  | 1983 |  |  | 2233 |  |  | 2150 |  |  | 2173 |  |  | 2020 |  |  | 2080 |  |  | 2137.5 |  |  | 2143 |  |  | 2176.5 |  |  | 2149 |  |  | 2060 |  |  | 2195.5 |  |  | 2119 |  |  | 2225.5 |  |  | 2063 |  |  | 1958 |  |  | 2108.5 |  |  | 2182 |  |  | 2221.5 |  |  | 2161 |  |  | 2000 |  |  | 2219.5 |  |  | 2175.5 |  |  | 2177 |  |  | 2100.5 |  |  | 2128.5 |  |  | 2118 |  |  | 2132 |  |  | 2313.5 |  |  | 2003.5 |  |  | 2161.5 |  |  | 2193 |  |  | 2199 |  |  | 2072 |  |  | 2237 |  |  | 2201 |  |  | 2177.5 |  |  | 2083 |  |  | 2042.5 |  |  | 2143.5 |  |  | 2140 |  |  | 2214 |  |  | 2327.5 |  |  | 2041.5 |  |  | 2098 |  |  | 2171.5 |  |  | 2017.5 |  |  | 2150 |  |  | 2009 |  |  | 2047 |  |  | 2073.5 |  |  | 2216 |  |  | 2107.5 |  |  | 2151.5 |  |  | 2054 |  |  | 2062.5 |  |  | 2047 |  |  | 2110 |  |  | 2150 |  |  | 2188 |  |  | 1920 |  |  | 2202 |  |  | 2218 |  |  | 2134 |  |  | 2253 |  |  | 2097 |  |  | 2129.5 |  |  | 2245.5 |  |  | 2091 |  |  | 2051 |  |  | 2276 |  |  | 2164.5 |  |  | 2208.5 |  |  | 2229.5 |  |  | 2047 |  |  | 2164 |  |  | 2276.5 |  |  | 2148.5 |  |  | 1986.5 |  |  | 2225 |  |  | 2254 |  |  | 2093 |  |  | 2170 |  |  | 2153 |  |  | 2090.5 |  |  | 2053.5 |  |  | 2203 |  |  | 2088 |  |  | 2085 |  |  | 2220 |  |  | 2089 |  |  | 2244.5 |  |  | 2147 |  |  | 2132 |  |  | 2113 |  |  | 2080 |  |  | 2119.5 |  |  | 2237 |  |  | 2129 |  |  | 2095 |  |  | 2237 |  |  | 2233.5 |  |  | 2173 |  |  | 2073 |  |  | 2059 |  |  | 2209.5 |  |  | 2136.5 |  |  | 2252.5 |  |  | 2253 |  |  | 2089 |  |  | 1998 |  |  | 2293 |  |  | 2155 |  |  | 2074.5 |  |  | 2215 |  |  | 2107.5 |  |  | 2167.5 |  |  | 2168.5 |  |  | 2172 |  |  | 2283.5 |  |  | 2024 |  |  | 2050 |  |  | 2104.5 |  |  | 2141.5 |  |  | 2168 |  |  | 2219.5 |  |  | 2264.5 |  |  | 2124 |  |  | 2171 |  |  | 2089.5 |  |  | 2104.5 |  |  | 2262 |  |  | 2125.5 |  |  | 2232 |  |  | 2127 |  |  | 2063.5 |  |  | 2189 |  |  | 2051 |  |  | 2127.5 |  |  | 2108 |  |  | 2297.5 |  |  | 2138 |  |  | 2334 |  |  | 2152 |  |  | 2082 |  |  | 2258.5 |  |  | 2292 |  |  | 2216.5 |  |  | 1990.5 |  |  | 2239.5 |  |  | 2180 |  |  | 2173.5 |  |  | 2323 |  |  | 2169 |  |  | 1950.5 |  |  | 2135.5 |  |  | 2224 |  |  | 2071.5 |  |  | 2226 |  |  | 2075 |  |  | 2273.5 |  |  | 2060 |  |  | 2090.5 |  |  | 2149.5 |  |  | 2149.5 |  |  | 2123 |  |  | 1966 |  |  | 2071 |  |  | 2107.5 |  |  | 2078 |  |  | 2276.5 |  |  | 2143 |  |  | 2109 |  |  | 2056 |  |  | 2133 |  |  | 2199 |  |  | 2184 |  |  | 2134 |  |  | 2303 |  |  | 2182 |  |  | 2135.5 |  |  | 2151 |  |  | 2123 |  |  | 2250.5 |  |  | 2036.5 |  |  | 2145.5 |  |  | 2167.5 |  |  | 2133 |  |  | 2251 |  |  | 1998.5 |  |  | 2249.5 |  |  | 2107.5 |  |  | 2161 |  |  | 2099 |  |  | 2068 |  |  | 2121 |  |  | 1968 |  |  | 2121 |  |  | 2159 |  |  | 2148.5 |  |  | 2168.5 |  |  | 2080 |  |  | 2073.5 |  |  | 2173.5 |  |  | 2053 |  |  | 2168 |  |  | 2060 |  |  | 2144 |  |  | 2060.5 |  |  | 1992.5 |  |  | 2178.5 |  |  | 2106 |  |  | 2051.5 |  |  | 2155 |  |  | 2118 |  |  | 2262 |  |  | 2043.5 |  |  | 2112 |  |  | 2018 |  |  | 2130.5 |  |  | 2056 |  |  | 2229.5 |  |  | 2273 |  |  | 2104.5 |  |  | 2067 |  |  | 2122.5 |  |  | 2149.5 |  |  | 2195 |  |  | 2126 |  |  | 1952 |  |  | 2167 |  |  | 1971.5 |  |  | 2075 |  |  | 2286 |  |  | 2057.5 |  |  | 2271.5 |  |  | 2024.5 |  |  | 2063 |  |  | 2239.5 |  |  | 2174.5 |  |  | 2054.5 |  |  | 2219 |  |  | 2158 |  |  | 2186.5 |  |  | 2210 |  |  | 2256 |  |  | 2209.5 |  |  | 2128 |  |  | 2230 |  |  | 2122 |  |  | 1980 |  |  | 1969.5 |  |  | 2193.5 |  |  | 2051 |  |  | 2229 |  |  | 2204 |  |  | 2091 |  |  | 2069 |  |  | 2071.5 |  |  | 2081.5 |  |  | 2137 |  |  | 2266 |  |  | 2302 |  |  | 2068.5 |  |  | 2335.5 |  |  | 2100 |  |  | 2126 |  |  | 1988 |  |  | 2138.5 |  |  | 2295.5 |  |  | 2123 |  |  | 1985 |  |  | 2174 |  |  | 2150 |  |  | 2115 |  |  | 2257 |  |  | 2054 |  |  | 2260.5 |  |  | 2058 |  |  | 2225 |  |  | 2151 |  |  | 2192.5 |  |  | 2163 |  |  | 2043 |  |  | 1940 |  |  | 2101 |  |  | 2090 |  |  | 2172 |  |  | 2181 |  |  | 2069.5 |  |  | 2102.5 |  |  | 1937.5 |  |  | 2243 |  |  | 2094 |  |  | 2138.5 |  |  | 1954 |  |  | 2017.5 |  |  | 2104.5 |  |  | 2089 |  |  | 2186 |  |  | 2129.5 |  |  | 2157 |  |  | 2157 |  |  | 2158 |  |  | 2155 |  |  | 2209 |  |  | 2091 |  |  | 2088 |  |  | 2161.5 |  |  | 2127 |  |  | 2164 |  |  | 2191 |  |  | 2108 |  |  | 2109 |  |  | 2146 |  |  | 2253 |  |  | 2164 |  |  | 2142 |  |  | 2226.5 |  |  | 2125.5 |  |  | 2127.5 |  |  | 2194.5 |  |  | 2140 |  |  | 1989 |  |  | 2222.5 |  |  | 2093 |  |  | 2124 |  |  | 2042.5 |  |  | 2279.5 |  |  | 2189 |  |  | 2150.5 |  |  | 2093.5 |  |  | 2012 |  |  | 2241 |  |  | 2077 |  |  | 2121 |  |  | 2110.5 |  |  | 2145 |  |  | 2029.5 |  |  | 2039.5 |  |  | 2098 |  |  | 2095 |  |  | 2250.5 |  |  | 2106 |  |  | 2132.5 |  |  | 2153 |  |  | 2142.5 |  |  | 2035.5 |  |  | 1972.5 |  |  | 2205.5 |  |  | 2160.5 |  |  | 1969 |  |  | 2049 |  |  | 2250.5 |  |  | 2171 |  |  | 2041 |  |  | 2099 |  |  | 2254 |  |  | 2252.5 |  |  | 2000 |  |  | 2069 |  |  | 2179 |  |  | 2086.5 |  |  | 2148 |  |  | 2011 |  |  | 2088 |  |  | 2286.5 |  |  | 2170 |  |  | 1938 |  |  | 2146 |  |  | 2239 |  |  | 2395.5 |  |  | 2179 |  |  | 2037.5 |  |  | 2107 |  |  | 2188 |  |  | 2367.5 |  |  | 2198 |  |  | 2081 |  |  | 2096.5 |  |  | 2144 |  |  | 2087 |  |  | 2075 |  |  | 2368.5 |  |  | 2188.5 |  |  | 2187 |  |  | 2022 |  |  | 2130.5 |  |  | 2106.5 |  |  | 2107 |  |  | 2185 |  |  | 2184.5 |  |  | 2327.5 |  |  | 2000.5 |  |  | 2149.5 |  |  | 2118.5 |  |  | 2311 |  |  | 2103.5 |  |  | 2227 |  |  | 2118 |  |  | 2187 |  |  | 2226 |  |  | 2165.5 |  |  | 2124 |  |  | 2048 |  |  | 2151.5 |  |  | 2131.5 |  |  | 2055 |  |  | 2213.5 |  |  | 2125.5 |  |  | 2224 |  |  | 2063 |  |  | 2092 |  |  | 2164.5 |  |  | 2179 |  |  | 2212.5 |  |  | 2197 |  |  | 2120 |  |  | 2353.5 |  |  | 2100 |  |  | 2215 |  |  | 2046 |  |  | 2221 |  |  | 2191 |  |  | 2149 |  |  | 2162 |  |  | 2148 |  |  | 2003.5 |  |  | 2095.5 |  |  | 2106 |  |  | 2142.5 |  |  | 1962.5 |  |  | 2045 |  |  | 2059 |  |  | 2204 |  |  | 2218.5 |  |  | 2047.5 |  |  | 2223 |  |  | 2198 |  |  | 2014 |  |  | 2031 |  |  | 2110 |  |  | 2089 |  |  | 2182 |  |  | 2033.5 |  |  | 2239 |  |  | 2151 |  |  | 2232 |  |  | 2070 |  |  | 1991 |  |  | 2122.5 |  |  | 2290.5 |  |  | 1965.5 |  |  | 2032 |  |  | 2057 |  |  | 2065.5 |  |  | 2241.5 |  |  | 2205.5 |  |  | 2053 |  |  | 2213.5 |  |  | 2161.5 |  |  | 2287 |  |  | 2211.5 |  |  | 2156.5 |  |  | 2146 |  |  | 2026 |  |  | 2091 |  |  | 2230 |  |  | 2098 |  |  | 1967 |  |  | 2177 |  |  | 2276 |  |  | 2022 |  |  | 2111 |  |  | 2229.5 |  |  | 2111 |  |  | 2138 |  |  | 2083 |  |  | 2086.5 |  |  | 2075 |  |  | 2144.5 |  |  | 2303 |  |  | 2185 |  |  | 2113 |  |  | 2143 |  |  | 2246.5 |  |  | 2100 |  |  | 2036 |  |  | 2223.5 |  |  | 2164 |  |  | 2068 |  |  | 2081.5 |  |  | 2103.5 |  |  | 2134 |  |  | 2037.5 |  |  | 2255 |  |  | 2084.5 |  |  | 2235 |  |  | 2162 |  |  | 2080.5 |  |  | 2198.5 |  |  | 2099 |  |  | 2214 |  |  | 2132 |  |  | 2133 |  |  | 2025 |  |  | 2118 |  |  | 1986 |  |  | 2009 |  |  | 2203.5 |  |  | 1988 |  |  | 2260.5 |  |  | 2075 |  |  | 2188.5 |  |  | 2085.5 |  |  | 2058 |  |  | 2146 |  |  | 2238.5 |  |  | 2112 |  |  | 2190 |  |  | 2200 |  |  | 2129.5 |  |  | 2158 |  |  | 2024.5 |  |  | 1938 |  |  | 2093 |  |  | 2133 |  |  | 2168 |  |  | 2204.5 |  |  | 2073 |  |  | 2104 |  |  | 2172 |  |  | 2016.5 |  |  | 2258 |  |  | 2187 |  |  | 2152 |  |  | 2087 |  |  | 2109.5 |  |  | 2027.5 |  |  | 2185 |  |  | 2235 |  |  | 2149 |  |  | 2226.5 |  |  | 2121 |  |  | 2027 |  |  | 2076 |  |  | 2297.5 |  |  | 2089.5 |  |  | 2105.5 |  |  | 2159 |  |  | 2187 |  |  | 2175 |  |  | 2055.5 |  |  | 2169 |  |  | 2087.5 |  |  | 2005 |  |  | 2020 |  |  | 2116 |  |  | 2108.5 |  |  | 2181.5 |  |  | 2117 |  |  | 2080 |  |  | 2246.5 |  |  | 2162 |  |  | 2100 |  |  | 2166.5 |  |  | 2031 |  |  | 2062 |  |  | 2154.5 |  |  | 2080 |  |  | 2169 |  |  | 2093.5 |  |  | 2269 |  |  | 2039.5 |  |  | 2136 |  |  | 1983.5 |  |  | 2186.5 |  |  | 2018 |  |  | 2249 |  |  | 2184.5 |  |  | 2107.5 |  |  | 2264 |  |  | 2130 |  |  | 2143 |  |  | 2127.5 |  |  | 2157 |  |  | 1933 |  |  | 2072 |  |  | 2204.5 |  |  | 2200.5 |  |  | 2138 |  |  | 2228 |  |  | 2078 |  |  | 2050 |  |  | 2233 |  |  | 2082 |  |  | 2094 |  |  | 2111.5 |  |  | 2315.5 |  |  | 2061.5 |  |  | 2116 |  |  | 2097.5 |  |  | 2139 |  |  | 2098 |  |  | 2152.5 |  |  | 2021.5 |  |  | 2037 |  |  | 2181 |  |  | 2083.5 |  |  | 2120 |  |  | 2172 |  |  | 1998.5 |  |  | 2215.5 |  |  | 2096 |  |  | 2087 |  |  | 2171 |  |  | 2022.5 |  |  | 2047 |  |  | 2038 |  |  | 2145 |  |  | 2194 |  |  | 2274 |  |  | 2051.5 |  |  | 2235 |  |  | 2039 |  |  | 2019 |  |  | 2277.5 |  |  | 2128 |  |  | 2066.5 |  |  | 2043.5 |  |  | 2108 |  |  | 2207 |  |  | 2083.5 |  |  | 2069.5 |  |  | 2005.5 |  |  | 2095.5 |  |  | 2126.5 |  |  | 2158 |  |  | 2128 |  |  | 2150.5 |  |  | 2080.5 |  |  | 2120 |  |  | 2058 |  |  | 2114.5 |  |  | 2269 |  |  | 2088 |  |  | 1996 |  |  | 2178.5 |  |  | 2256 |  |  | 2050.5 |  |  | 2021 |  |  | 2176.5 |  |  | 2315.5 |  |  | 2256.5 |  |  | 2281 |  |  | 2169 |  |  | 2154.5 |  |  | 2110.5 |  |  | 2156 |  |  | 2127 |  |  | 2168.5 |  |  | 2252 |  |  | 2141.5 |  |  | 2074.5 |  |  | 2192 |  |  | 2129 |  |  | 1995.5 |  |  | 2207.5 |  |  | 2133 |  |  | 2073.5 |  |  | 2164.5 |  |  | 2162 |  |  | 2205 |  |  | 2214 |  |  | 2113.5 |  |  | 2210 |  |  | 2068 |  |  | 2168 |  |  | 2068 |  |  | 2119 |  |  | 2104 |  |  | 2260.5 |  |  | 2114.5 |  |  | 2100 |  |  | 2094 |  |  | 2157 |  |  | 2109.5 |  |  | 2060 |  |  | 2285 |  |  | 2072.5 |  |  | 2215.5 |  |  | 2116 |  |  | 2101.5 |  |  | 2222 |  |  | 2015 |  |  | 2148 |  |  | 2231.5 |  |  | 2264 |  |  | 2023.5 |  |  | 2115.5 |  |  | 2023 |  |  | 2139.5 |  |  | 1951.5 |  |  | 2089 |  |  | 2040 |  |  | 2234 |  |  | 2039.5 |  |  | 1998 |  |  | 2084.5 |  |  | 2117.5 |  |  | 2208 |  |  | 2021.5 |  |  | 2033 |  |  | 2134 |  |  | 2101 |  |  | 2056 |  |  | 2011 |  |  | 2211.5 |  |  | 2112 |  |  | 2185 |  |  | 2048 |  |  | 2183 |  |  | 2143.5 |  |  | 2147.5 |  |  | 2080 |  |  | 2184 |  |  | 2122 |  |  | 2120 |  |  | 2164 |  |  | 2045.5 |  |  | 2094 |  |  | 2192.5 |  |  | 2206 |  |  | 1987 |  |  | 2098 |  |  | 2118 |  |  | 2177.5 |  |  | 2131 |  |  | 2151.5 |  |  | 2078 |  |  | 2281 |  |  | 2182 |  |  | 2126.5 |  |  | 2037 |  |  | 2015 |  |  | 2029 |  |  | 2258 |  |  | 2325 |  |  | 2077.5 |  |  | 2205.5 |  |  | 2059 |  |  | 2112.5 |  |  | 2080 |  |  | 2020.5 |  |  | 2116.5 |  |  | 2060.5 |  |  | 2062.5 |  |  | 1997 |  |  | 2263 |  |  | 2038 |  |  | 2027 |  |  | 2101 |  |  | 2207 |  |  | 2082.5 |  |  | 2080.5 |  |  | 2231.5 |  |  | 2157 |  |  | 2220.5 |  |  | 2074.5 |  |  | 2212.5 |  |  | 2045.5 |  |  | 2126 |  |  | 2147.5 |  |  | 2141.5 |  |  | 2228 |  |  | 2025.5 |  |  | 2268.5 |  |  | 2203.5 |  |  | 2291 |  |  | 2156.5 |  |  | 2147 |  |  | 2132 |  |  | 2089.5 |  |  | 2183.5 |  |  | 2165 |  |  | 2189 |  |  | 1973.5 |  |  | 1996.5 |  |  | 2088.5 |  |  | 2204 |  |  | 2066 |  |  | 2124 |  |  | 2207.5 |  |  | 2197.5 |  |  | 2181 |  |  | 2156.5 |  |  | 1968 |  |  | 2120 |  |  | 2163.5 |  |  | 2065.5 |  |  | 2103 |  |  | 2148.5 |  |  | 2184 |  |  | 2066.5 |  |  | 2250.5 |  |  | 2196 |  |  | 2117.5 |  |  | 2209 |  |  | 2129.5 |  |  | 2109 |  |  | 2207 |  |  | 2162 |  |  | 2120.5 |  |  | 2012.5 |  |  | 2162 |  |  | 2112 |  |  | 2034 |  |  | 2083.5 |  |  | 2121.5 |  |  | 2215 |  |  | 2139.5 |  |  | 2121 |  |  | 2000.5 |  |  | 2151.5 |  |  | 2037 |  |  | 2108 |  |  | 2111 |  |  | 2096.5 |  |  | 2066 |  |  | 2170.5 |  |  | 2203 |  |  | 2123.5 |  |  | 2297 |  |  | 1973.5 |  |  | 2080 |  |  | 2154.5 |  |  | 2128.5 |  |  | 2057 |  |  | 2114 |  |  | 2338 |  |  | 2125 |  |  | 2201.5 |  |  | 2022 |  |  | 2095.5 |  |  | 1966 |  |  | 2049 |  |  | 2079 |  |  | 2266 |  |  | 2163 |  |  | 2096 |  |  | 2203 |  |  | 2091.5 |  |  | 2049 |  |  | 2177
75 |  | 2334.5 |  |  | 2268 |  |  | 2242.5 |  |  | 2160 |  |  | 2090.5 |  |  | 2207 |  |  | 2207 |  |  | 2198 |  |  | 2032.5 |  |  | 2062 |  |  | 2118 |  |  | 2277 |  |  | 2235 |  |  | 2356 |  |  | 2124.5 |  |  | 2208.5 |  |  | 2087 |  |  | 2171 |  |  | 2274 |  |  | 2066.5 |  |  | 2223 |  |  | 2214 |  |  | 2076 |  |  | 2179 |  |  | 2159.5 |  |  | 2283 |  |  | 2152 |  |  | 2173 |  |  | 2223 |  |  | 2075 |  |  | 2190 |  |  | 2103.5 |  |  | 2249.5 |  |  | 2154.5 |  |  | 2120 |  |  | 2128.5 |  |  | 2161.5 |  |  | 2258.5 |  |  | 2229 |  |  | 2163 |  |  | 2049.5 |  |  | 2116 |  |  | 2202.5 |  |  | 2166.5 |  |  | 2210.5 |  |  | 2355.5 |  |  | 2326.5 |  |  | 2105 |  |  | 2028 |  |  | 2129.5 |  |  | 2134 |  |  | 2129.5 |  |  | 2040.5 |  |  | 2169 |  |  | 2111 |  |  | 2112 |  |  | 2054 |  |  | 2250 |  |  | 2202 |  |  | 2167.5 |  |  | 2123.5 |  |  | 2131.5 |  |  | 2091 |  |  | 2225 |  |  | 1986 |  |  | 2070.5 |  |  | 2121 |  |  | 2131.5 |  |  | 2184.5 |  |  | 2307.5 |  |  | 2151 |  |  | 2323 |  |  | 2241 |  |  | 2147.5 |  |  | 2274.5 |  |  | 2164.5 |  |  | 2253.5 |  |  | 2146.5 |  |  | 2188.5 |  |  | 2153.5 |  |  | 2094.5 |  |  | 2064 |  |  | 2202 |  |  | 2079 |  |  | 2275.5 |  |  | 2304 |  |  | 2116.5 |  |  | 2196 |  |  | 2202 |  |  | 2215.5 |  |  | 2310.5 |  |  | 2153 |  |  | 2287 |  |  | 2085.5 |  |  | 2282 |  |  | 2103.5 |  |  | 2162.5 |  |  | 2197.5 |  |  | 2066.5 |  |  | 2105.5 |  |  | 2113 |  |  | 2159 |  |  | 2001 |  |  | 2140.5 |  |  | 2106.5 |  |  | 2221.5 |  |  | 2103.5 |  |  | 2156 |  |  | 2115 |  |  | 2193.5 |  |  | 2021 |  |  | 2206.5 |  |  | 2174 |  |  | 2129 |  |  | 2013.5 |  |  | 2137 |  |  | 2151 |  |  | 2094 |  |  | 2183 |  |  | 2129.5 |  |  | 2168.5 |  |  | 2119.5 |  |  | 2254 |  |  | 2128 |  |  | 2080 |  |  | 2082 |  |  | 2085.5 |  |  | 2096 |  |  | 2181.5 |  |  | 2157 |  |  | 2098 |  |  | 2150.5 |  |  | 2069.5 |  |  | 2082 |  |  | 2073.5 |  |  | 2103 |  |  | 2239 |  |  | 2124 |  |  | 2285 |  |  | 2084 |  |  | 2085 |  |  | 2133 |  |  | 2185 |  |  | 2062 |  |  | 2029.5 |  |  | 2126 |  |  | 2022 |  |  | 2262 |  |  | 2165 |  |  | 2188 |  |  | 2059 |  |  | 2106 |  |  | 2152.5 |  |  | 2167 |  |  | 2205.5 |  |  | 2173 |  |  | 2089 |  |  | 2234.5 |  |  | 2148 |  |  | 2251.5 |  |  | 2087 |  |  | 1997 |  |  | 2155.5 |  |  | 2229 |  |  | 2260.5 |  |  | 2200 |  |  | 2026 |  |  | 2234.5 |  |  | 2222.5 |  |  | 2206 |  |  | 2121.5 |  |  | 2149.5 |  |  | 2133 |  |  | 2171 |  |  | 2352.5 |  |  | 2042.5 |  |  | 2190.5 |  |  | 2217 |  |  | 2225 |  |  | 2087 |  |  | 2284 |  |  | 2222 |  |  | 2201.5 |  |  | 2112 |  |  | 2068.5 |  |  | 2167.5 |  |  | 2166 |  |  | 2243 |  |  | 2374.5 |  |  | 2067.5 |  |  | 2119 |  |  | 2192.5 |  |  | 2064.5 |  |  | 2171 |  |  | 2035 |  |  | 2076 |  |  | 2097.5 |  |  | 2255 |  |  | 2128.5 |  |  | 2190.5 |  |  | 2080 |  |  | 2086.5 |  |  | 2068 |  |  | 2136 |  |  | 2176 |  |  | 2227 |  |  | 1959 |  |  | 2241 |  |  | 2247 |  |  | 2158 |  |  | 2292 |  |  | 2126 |  |  | 2153.5 |  |  | 2266.5 |  |  | 2130 |  |  | 2072 |  |  | 2315 |  |  | 2188.5 |  |  | 2247.5 |  |  | 2255.5 |  |  | 2068 |  |  | 2193 |  |  | 2300.5 |  |  | 2163.5 |  |  | 2025.5 |  |  | 2246 |  |  | 2269 |  |  | 2132 |  |  | 2185 |  |  | 2174 |  |  | 2129.5 |  |  | 2100.5 |  |  | 2242 |  |  | 2109 |  |  | 2106 |  |  | 2249 |  |  | 2104 |  |  | 2273.5 |  |  | 2194 |  |  | 2156 |  |  | 2139 |  |  | 2095 |  |  | 2140.5 |  |  | 2263 |  |  | 2144 |  |  | 2116 |  |  | 2261 |  |  | 2257.5 |  |  | 2199 |  |  | 2097 |  |  | 2106 |  |  | 2224.5 |  |  | 2183.5 |  |  | 2276.5 |  |  | 2279 |  |  | 2115 |  |  | 2013 |  |  | 2322 |  |  | 2176 |  |  | 2103.5 |  |  | 2241 |  |  | 2136.5 |  |  | 2191.5 |  |  | 2215.5 |  |  | 2187 |  |  | 2298.5 |  |  | 2048 |  |  | 2079 |  |  | 2128.5 |  |  | 2156.5 |  |  | 2194 |  |  | 2240.5 |  |  | 2285.5 |  |  | 2148 |  |  | 2200 |  |  | 2110.5 |  |  | 2125.5 |  |  | 2288 |  |  | 2164.5 |  |  | 2271 |  |  | 2142 |  |  | 2078.5 |  |  | 2215 |  |  | 2075 |  |  | 2166.5 |  |  | 2155 |  |  | 2318.5 |  |  | 2177 |  |  | 2358 |  |  | 2191 |  |  | 2106 |  |  | 2284.5 |  |  | 2321 |  |  | 2237.5 |  |  | 2029.5 |  |  | 2278.5 |  |  | 2201 |  |  | 2212.5 |  |  | 2362 |  |  | 2193 |  |  | 1965.5 |  |  | 2156.5 |  |  | 2239 |  |  | 2110.5 |  |  | 2273 |  |  | 2114 |  |  | 2288.5 |  |  | 2099 |  |  | 2105.5 |  |  | 2170.5 |  |  | 2175.5 |  |  | 2170 |  |  | 1981 |  |  | 2110 |  |  | 2133.5 |  |  | 2093 |  |  | 2323.5 |  |  | 2164 |  |  | 2135 |  |  | 2095 |  |  | 2162 |  |  | 2238 |  |  | 2223 |  |  | 2160 |  |  | 2332 |  |  | 2208 |  |  | 2182.5 |  |  | 2190 |  |  | 2162 |  |  | 2271.5 |  |  | 2062.5 |  |  | 2192.5 |  |  | 2214.5 |  |  | 2172 |  |  | 2272 |  |  | 2022.5 |  |  | 2288.5 |  |  | 2136.5 |  |  | 2187 |  |  | 2138 |  |  | 2107 |  |  | 2145 |  |  | 2007 |  |  | 2147 |  |  | 2180 |  |  | 2187.5 |  |  | 2192.5 |  |  | 2119 |  |  | 2094.5 |  |  | 2212.5 |  |  | 2092 |  |  | 2189 |  |  | 2099 |  |  | 2191 |  |  | 2081.5 |  |  | 2018.5 |  |  | 2217.5 |  |  | 2145 |  |  | 2098.5 |  |  | 2194 |  |  | 2157 |  |  | 2291 |  |  | 2064.5 |  |  | 2138 |  |  | 2044 |  |  | 2156.5 |  |  | 2071 |  |  | 2244.5 |  |  | 2312 |  |  | 2143.5 |  |  | 2093 |  |  | 2146.5 |  |  | 2173.5 |  |  | 2221 |  |  | 2155 |  |  | 1978 |  |  | 2193 |  |  | 1986.5 |  |  | 2101 |  |  | 2307 |  |  | 2081.5 |  |  | 2297.5 |  |  | 2053.5 |  |  | 2084 |  |  | 2278.5 |  |  | 2213.5 |  |  | 2080.5 |  |  | 2245 |  |  | 2179 |  |  | 2233.5 |  |  | 2225 |  |  | 2295 |  |  | 2248.5 |  |  | 2152 |  |  | 2254 |  |  | 2151 |  |  | 2027 |  |  | 1984.5 |  |  | 2232.5 |  |  | 2090 |  |  | 2253 |  |  | 2230 |  |  | 2130 |  |  | 2093 |  |  | 2100.5 |  |  | 2120.5 |  |  | 2176 |  |  | 2290 |  |  | 2326 |  |  | 2107.5 |  |  | 2374.5 |  |  | 2115 |  |  | 2147 |  |  | 2009 |  |  | 2159.5 |  |  | 2319.5 |  |  | 2149 |  |  | 2024 |  |  | 2213 |  |  | 2174 |  |  | 2162 |  |  | 2272 |  |  | 2101 |  |  | 2281.5 |  |  | 2079 |  |  | 2246 |  |  | 2172 |  |  | 2221.5 |  |  | 2189 |  |  | 2082 |  |  | 1979 |  |  | 2122 |  |  | 2137 |  |  | 2198 |  |  | 2202 |  |  | 2116.5 |  |  | 2128.5 |  |  | 1963.5 |  |  | 2282 |  |  | 2133 |  |  | 2177.5 |  |  | 1980 |  |  | 2056.5 |  |  | 2151.5 |  |  | 2104 |  |  | 2215 |  |  | 2168.5 |  |  | 2186 |  |  | 2204 |  |  | 2187 |  |  | 2181 |  |  | 2238 |  |  | 2106 |  |  | 2114 |  |  | 2200.5 |  |  | 2166 |  |  | 2203 |  |  | 2206 |  |  | 2147 |  |  | 2124 |  |  | 2161 |  |  | 2277 |  |  | 2190 |  |  | 2166 |  |  | 2250.5 |  |  | 2172.5 |  |  | 2142.5 |  |  | 2220.5 |  |  | 2166 |  |  | 2010 |  |  | 2261.5 |  |  | 2114 |  |  | 2139 |  |  | 2071.5 |  |  | 2303.5 |  |  | 2218 |  |  | 2189.5 |  |  | 2132.5 |  |  | 2041 |  |  | 2280 |  |  | 2101 |  |  | 2160 |  |  | 2125.5 |  |  | 2171 |  |  | 2076.5 |  |  | 2078.5 |  |  | 2127 |  |  | 2116 |  |  | 2276.5 |  |  | 2145 |  |  | 2161.5 |  |  | 2174 |  |  | 2168.5 |  |  | 2061.5 |  |  | 1998.5 |  |  | 2234.5 |  |  | 2175.5 |  |  | 2008 |  |  | 2073 |  |  | 2276.5 |  |  | 2192 |  |  | 2080 |  |  | 2128 |  |  | 2280 |  |  | 2278.5 |  |  | 2015 |  |  | 2108 |  |  | 2208 |  |  | 2112.5 |  |  | 2174 |  |  | 2035 |  |  | 2127 |  |  | 2312.5 |  |  | 2191 |  |  | 1962 |  |  | 2175 |  |  | 2260 |  |  | 2416.5 |  |  | 2203 |  |  | 2076.5 |  |  | 2146 |  |  | 2212 |  |  | 2396.5 |  |  | 2213 |  |  | 2120 |  |  | 2122.5 |  |  | 2183 |  |  | 2108 |  |  | 2114 |  |  | 2389.5 |  |  | 2235.5 |  |  | 2213 |  |  | 2061 |  |  | 2177.5 |  |  | 2130.5 |  |  | 2128 |  |  | 2224 |  |  | 2208.5 |  |  | 2366.5 |  |  | 2039.5 |  |  | 2173.5 |  |  | 2139.5 |  |  | 2340 |  |  | 2118.5 |  |  | 2242 |  |  | 2157 |  |  | 2234 |  |  | 2273 |  |  | 2180.5 |  |  | 2163 |  |  | 2074 |  |  | 2190.5 |  |  | 2170.5 |  |  | 2079 |  |  | 2234.5 |  |  | 2146.5 |  |  | 2263 |  |  | 2078 |  |  | 2107 |  |  | 2188.5 |  |  | 2226 |  |  | 2251.5 |  |  | 2218 |  |  | 2167 |  |  | 2392.5 |  |  | 2115 |  |  | 2236 |  |  | 2075 |  |  | 2236 |  |  | 2230 |  |  | 2178 |  |  | 2177 |  |  | 2174 |  |  | 2042.5 |  |  | 2116.5 |  |  | 2121 |  |  | 2168.5 |  |  | 2001.5 |  |  | 2066 |  |  | 2080 |  |  | 2251 |  |  | 2239.5 |  |  | 2073.5 |  |  | 2238 |  |  | 2213 |  |  | 2035 |  |  | 2057 |  |  | 2136 |  |  | 2104 |  |  | 2203 |  |  | 2054.5 |  |  | 2254 |  |  | 2177 |  |  | 2256 |  |  | 2094 |  |  | 2017 |  |  | 2143.5 |  |  | 2305.5 |  |  | 1991.5 |  |  | 2061 |  |  | 2081 |  |  | 2091.5 |  |  | 2267.5 |  |  | 2231.5 |  |  | 2077 |  |  | 2252.5 |  |  | 2208.5 |  |  | 2308 |  |  | 2226.5 |  |  | 2171.5 |  |  | 2185 |  |  | 2050 |  |  | 2115 |  |  | 2251 |  |  | 2113 |  |  | 2014 |  |  | 2216 |  |  | 2300 |  |  | 2046 |  |  | 2137 |  |  | 2253.5 |  |  | 2135 |  |  | 2162 |  |  | 2098 |  |  | 2125.5 |  |  | 2090 |  |  | 2173.5 |  |  | 2324 |  |  | 2214 |  |  | 2152 |  |  | 2158 |  |  | 2261.5 |  |  | 2124 |  |  | 2075 |  |  | 2249.5 |  |  | 2185 |  |  | 2083 |  |  | 2120.5 |  |  | 2129.5 |  |  | 2158 |  |  | 2063.5 |  |  | 2294 |  |  | 2099.5 |  |  | 2256 |  |  | 2201 |  |  | 2104.5 |  |  | 2245.5 |  |  | 2138 |  |  | 2261 |  |  | 2161 |  |  | 2172 |  |  | 2072 |  |  | 2142 |  |  | 2015 |  |  | 2035 |  |  | 2229.5 |  |  | 2009 |  |  | 2284.5 |  |  | 2099 |  |  | 2235.5 |  |  | 2124.5 |  |  | 2084 |  |  | 2193 |  |  | 2262.5 |  |  | 2138 |  |  | 2214 |  |  | 2221 |  |  | 2176.5 |  |  | 2197 |  |  | 2050.5 |  |  | 1967 |  |  | 2132 |  |  | 2148 |  |  | 2183 |  |  | 2228.5 |  |  | 2102 |  |  | 2143 |  |  | 2196 |  |  | 2037.5 |  |  | 2273 |  |  | 2234 |  |  | 2191 |  |  | 2126 |  |  | 2156.5 |  |  | 2042.5 |  |  | 2232 |  |  | 2261 |  |  | 2178 |  |  | 2247.5 |  |  | 2147 |  |  | 2051 |  |  | 2105 |  |  | 2326.5 |  |  | 2115.5 |  |  | 2131.5 |  |  | 2198 |  |  | 2226 |  |  | 2190 |  |  | 2079.5 |  |  | 2193 |  |  | 2116.5 |  |  | 2052 |  |  | 2046 |  |  | 2137 |  |  | 2137.5 |  |  | 2202.5 |  |  | 2164 |  |  | 2119 |  |  | 2275.5 |  |  | 2209 |  |  | 2126 |  |  | 2213.5 |  |  | 2052 |  |  | 2091 |  |  | 2193.5 |  |  | 2109 |  |  | 2208 |  |  | 2122.5 |  |  | 2295 |  |  | 2086.5 |  |  | 2183 |  |  | 2022.5 |  |  | 2225.5 |  |  | 2047 |  |  | 2273 |  |  | 2213.5 |  |  | 2122.5 |  |  | 2288 |  |  | 2177 |  |  | 2164 |  |  | 2174.5 |  |  | 2196 |  |  | 1948 |  |  | 2093 |  |  | 2230.5 |  |  | 2239.5 |  |  | 2167 |  |  | 2254 |  |  | 2125 |  |  | 2076 |  |  | 2248 |  |  | 2097 |  |  | 2141 |  |  | 2150.5 |  |  | 2330.5 |  |  | 2090.5 |  |  | 2131 |  |  | 2136.5 |  |  | 2165 |  |  | 2122 |  |  | 2178.5 |  |  | 2047.5 |  |  | 2084 |  |  | 2207 |  |  | 2122.5 |  |  | 2146 |  |  | 2211 |  |  | 2037.5 |  |  | 2236.5 |  |  | 2125 |  |  | 2126 |  |  | 2186 |  |  | 2048.5 |  |  | 2076 |  |  | 2077 |  |  | 2174 |  |  | 2233 |  |  | 2295 |  |  | 2075.5 |  |  | 2282 |  |  | 2086 |  |  | 2048 |  |  | 2298.5 |  |  | 2152 |  |  | 2087.5 |  |  | 2082.5 |  |  | 2123 |  |  | 2236 |  |  | 2122.5 |  |  | 2098.5 |  |  | 2052.5 |  |  | 2110.5 |  |  | 2155.5 |  |  | 2187 |  |  | 2157 |  |  | 2165.5 |  |  | 2106.5 |  |  | 2141 |  |  | 2097 |  |  | 2153.5 |  |  | 2308 |  |  | 2109 |  |  | 2022 |  |  | 2199.5 |  |  | 2280 |  |  | 2089.5 |  |  | 2036 |  |  | 2215.5 |  |  | 2354.5 |  |  | 2295.5 |  |  | 2302 |  |  | 2208 |  |  | 2169.5 |  |  | 2157.5 |  |  | 2203 |  |  | 2156 |  |  | 2189.5 |  |  | 2291 |  |  | 2170.5 |  |  | 2121.5 |  |  | 2213 |  |  | 2155 |  |  | 2021.5 |  |  | 2233.5 |  |  | 2162 |  |  | 2102.5 |  |  | 2185.5 |  |  | 2188 |  |  | 2252 |  |  | 2238 |  |  | 2160.5 |  |  | 2249 |  |  | 2094 |  |  | 2192 |  |  | 2115 |  |  | 2158 |  |  | 2125 |  |  | 2307.5 |  |  | 2140.5 |  |  | 2121 |  |  | 2118 |  |  | 2204 |  |  | 2148.5 |  |  | 2086 |  |  | 2324 |  |  | 2111.5 |  |  | 2239.5 |  |  | 2137 |  |  | 2140.5 |  |  | 2237 |  |  | 2030 |  |  | 2163 |  |  | 2270.5 |  |  | 2293 |  |  | 2052.5 |  |  | 2141.5 |  |  | 2038 |  |  | 2154.5 |  |  | 1980.5 |  |  | 2115 |  |  | 2087 |  |  | 2263 |  |  | 2086.5 |  |  | 2013 |  |  | 2099.5 |  |  | 2146.5 |  |  | 2229 |  |  | 2047.5 |  |  | 2057 |  |  | 2155 |  |  | 2140 |  |  | 2103 |  |  | 2032 |  |  | 2235.5 |  |  | 2141 |  |  | 2200 |  |  | 2087 |  |  | 2222 |  |  | 2169.5 |  |  | 2194.5 |  |  | 2119 |  |  | 2213 |  |  | 2151 |  |  | 2144 |  |  | 2185 |  |  | 2084.5 |  |  | 2133 |  |  | 2239.5 |  |  | 2253 |  |  | 2008 |  |  | 2137 |  |  | 2139 |  |  | 2192.5 |  |  | 2178 |  |  | 2180.5 |  |  | 2099 |  |  | 2320 |  |  | 2197 |  |  | 2150.5 |  |  | 2076 |  |  | 2041 |  |  | 2055 |  |  | 2297 |  |  | 2364 |  |  | 2116.5 |  |  | 2244.5 |  |  | 2080 |  |  | 2141.5 |  |  | 2095 |  |  | 2067.5 |  |  | 2155.5 |  |  | 2099.5 |  |  | 2086.5 |  |  | 2023 |  |  | 2284 |  |  | 2067 |  |  | 2056 |  |  | 2122 |  |  | 2246 |  |  | 2129.5 |  |  | 2119.5 |  |  | 2260.5 |  |  | 2196 |  |  | 2235.5 |  |  | 2098.5 |  |  | 2236.5 |  |  | 2069.5 |  |  | 2152 |  |  | 2168.5 |  |  | 2180.5 |  |  | 2243 |  |  | 2046.5 |  |  | 2307.5 |  |  | 2218.5 |  |  | 2338 |  |  | 2180.5 |  |  | 2186 |  |  | 2171 |  |  | 2110.5 |  |  | 2212.5 |  |  | 2191 |  |  | 2228 |  |  | 2012.5 |  |  | 2017.5 |  |  | 2109.5 |  |  | 2228 |  |  | 2095 |  |  | 2145 |  |  | 2236.5 |  |  | 2218.5 |  |  | 2207 |  |  | 2185.5 |  |  | 2007 |  |  | 2141 |  |  | 2202.5 |  |  | 2089.5 |  |  | 2124 |  |  | 2172.5 |  |  | 2213 |  |  | 2095.5 |  |  | 2271.5 |  |  | 2243 |  |  | 2156.5 |  |  | 2256 |  |  | 2150.5 |  |  | 2135 |  |  | 2246 |  |  | 2201 |  |  | 2146.5 |  |  | 2059.5 |  |  | 2186 |  |  | 2136 |  |  | 2055 |  |  | 2122.5 |  |  | 2160.5 |  |  | 2239 |  |  | 2165.5 |  |  | 2145 |  |  | 2047.5 |  |  | 2198.5 |  |  | 2076 |  |  | 2129 |  |  | 2158 |  |  | 2135.5 |  |  | 2087 |  |  | 2199.5 |  |  | 2229 |  |  | 2138.5 |  |  | 2336 |  |  | 1994.5 |  |  | 2104 |  |  | 2169.5 |  |  | 2157.5 |  |  | 2083 |  |  | 2153 |  |  | 2377 |  |  | 2140 |  |  | 2240.5 |  |  | 2051 |  |  | 2134.5 |  |  | 2013 |  |  | 2078 |  |  | 2118 |  |  | 2305 |  |  | 2202 |  |  | 2120 |  |  | 2224 |  |  | 2138.5 |  |  | 2064 |  |  | 2206
76 |  | 2360.5 |  |  | 2297 |  |  | 2263.5 |  |  | 2207 |  |  | 2105.5 |  |  | 2246 |  |  | 2246 |  |  | 2222 |  |  | 2061.5 |  |  | 2077 |  |  | 2142 |  |  | 2301 |  |  | 2282 |  |  | 2403 |  |  | 2145.5 |  |  | 2229.5 |  |  | 2134 |  |  | 2197 |  |  | 2313 |  |  | 2092.5 |  |  | 2247 |  |  | 2253 |  |  | 2115 |  |  | 2203 |  |  | 2188.5 |  |  | 2312 |  |  | 2167 |  |  | 2194 |  |  | 2252 |  |  | 2096 |  |  | 2229 |  |  | 2118.5 |  |  | 2275.5 |  |  | 2178.5 |  |  | 2167 |  |  | 2167.5 |  |  | 2200.5 |  |  | 2287.5 |  |  | 2253 |  |  | 2202 |  |  | 2075.5 |  |  | 2145 |  |  | 2226.5 |  |  | 2181.5 |  |  | 2239.5 |  |  | 2402.5 |  |  | 2365.5 |  |  | 2144 |  |  | 2049 |  |  | 2176.5 |  |  | 2160 |  |  | 2155.5 |  |  | 2087.5 |  |  | 2198 |  |  | 2150 |  |  | 2159 |  |  | 2101 |  |  | 2265 |  |  | 2241 |  |  | 2188.5 |  |  | 2170.5 |  |  | 2155.5 |  |  | 2115 |  |  | 2249 |  |  | 2033 |  |  | 2085.5 |  |  | 2160 |  |  | 2160.5 |  |  | 2223.5 |  |  | 2331.5 |  |  | 2190 |  |  | 2344 |  |  | 2267 |  |  | 2186.5 |  |  | 2300.5 |  |  | 2193.5 |  |  | 2300.5 |  |  | 2193.5 |  |  | 2227.5 |  |  | 2192.5 |  |  | 2133.5 |  |  | 2085 |  |  | 2249 |  |  | 2094 |  |  | 2304.5 |  |  | 2328 |  |  | 2137.5 |  |  | 2243 |  |  | 2217 |  |  | 2230.5 |  |  | 2334.5 |  |  | 2177 |  |  | 2326 |  |  | 2109.5 |  |  | 2321 |  |  | 2124.5 |  |  | 2191.5 |  |  | 2236.5 |  |  | 2090.5 |  |  | 2131.5 |  |  | 2139 |  |  | 2183 |  |  | 2048 |  |  | 2164.5 |  |  | 2153.5 |  |  | 2245.5 |  |  | 2118.5 |  |  | 2182 |  |  | 2139 |  |  | 2217.5 |  |  | 2060 |  |  | 2232.5 |  |  | 2213 |  |  | 2150 |  |  | 2060.5 |  |  | 2176 |  |  | 2172 |  |  | 2115 |  |  | 2198 |  |  | 2158.5 |  |  | 2189.5 |  |  | 2143.5 |  |  | 2269 |  |  | 2167 |  |  | 2119 |  |  | 2121 |  |  | 2124.5 |  |  | 2143 |  |  | 2207.5 |  |  | 2172 |  |  | 2119 |  |  | 2189.5 |  |  | 2108.5 |  |  | 2108 |  |  | 2088.5 |  |  | 2132 |  |  | 2278 |  |  | 2163 |  |  | 2314 |  |  | 2108 |  |  | 2109 |  |  | 2157 |  |  | 2200 |  |  | 2088 |  |  | 2050.5 |  |  | 2165 |  |  | 2048 |  |  | 2288 |  |  | 2189 |  |  | 2214 |  |  | 2088 |  |  | 2153 |  |  | 2199.5 |  |  | 2188 |  |  | 2244.5 |  |  | 2194 |  |  | 2128 |  |  | 2255.5 |  |  | 2187 |  |  | 2290.5 |  |  | 2116 |  |  | 2044 |  |  | 2170.5 |  |  | 2276 |  |  | 2299.5 |  |  | 2221 |  |  | 2050 |  |  | 2255.5 |  |  | 2261.5 |  |  | 2235 |  |  | 2147.5 |  |  | 2170.5 |  |  | 2162 |  |  | 2210 |  |  | 2378.5 |  |  | 2081.5 |  |  | 2237.5 |  |  | 2232 |  |  | 2272 |  |  | 2126 |  |  | 2323 |  |  | 2269 |  |  | 2222.5 |  |  | 2159 |  |  | 2094.5 |  |  | 2193.5 |  |  | 2195 |  |  | 2258 |  |  | 2421.5 |  |  | 2082.5 |  |  | 2145 |  |  | 2231.5 |  |  | 2085.5 |  |  | 2210 |  |  | 2050 |  |  | 2105 |  |  | 2144.5 |  |  | 2294 |  |  | 2154.5 |  |  | 2205.5 |  |  | 2109 |  |  | 2101.5 |  |  | 2092 |  |  | 2162 |  |  | 2215 |  |  | 2253 |  |  | 1998 |  |  | 2280 |  |  | 2286 |  |  | 2205 |  |  | 2307 |  |  | 2152 |  |  | 2182.5 |  |  | 2290.5 |  |  | 2145 |  |  | 2087 |  |  | 2339 |  |  | 2209.5 |  |  | 2268.5 |  |  | 2294.5 |  |  | 2115 |  |  | 2214 |  |  | 2321.5 |  |  | 2187.5 |  |  | 2064.5 |  |  | 2272 |  |  | 2298 |  |  | 2158 |  |  | 2232 |  |  | 2200 |  |  | 2168.5 |  |  | 2124.5 |  |  | 2281 |  |  | 2133 |  |  | 2153 |  |  | 2288 |  |  | 2143 |  |  | 2312.5 |  |  | 2233 |  |  | 2185 |  |  | 2163 |  |  | 2134 |  |  | 2187.5 |  |  | 2302 |  |  | 2191 |  |  | 2155 |  |  | 2282 |  |  | 2296.5 |  |  | 2246 |  |  | 2136 |  |  | 2145 |  |  | 2239.5 |  |  | 2204.5 |  |  | 2302.5 |  |  | 2318 |  |  | 2162 |  |  | 2060 |  |  | 2348 |  |  | 2202 |  |  | 2142.5 |  |  | 2256 |  |  | 2165.5 |  |  | 2217.5 |  |  | 2236.5 |  |  | 2213 |  |  | 2337.5 |  |  | 2069 |  |  | 2094 |  |  | 2143.5 |  |  | 2203.5 |  |  | 2241 |  |  | 2287.5 |  |  | 2306.5 |  |  | 2187 |  |  | 2247 |  |  | 2149.5 |  |  | 2149.5 |  |  | 2335 |  |  | 2190.5 |  |  | 2310 |  |  | 2166 |  |  | 2107.5 |  |  | 2254 |  |  | 2096 |  |  | 2205.5 |  |  | 2179 |  |  | 2357.5 |  |  | 2192 |  |  | 2382 |  |  | 2212 |  |  | 2145 |  |  | 2323.5 |  |  | 2350 |  |  | 2276.5 |  |  | 2050.5 |  |  | 2307.5 |  |  | 2222 |  |  | 2251.5 |  |  | 2377 |  |  | 2222 |  |  | 2012.5 |  |  | 2180.5 |  |  | 2278 |  |  | 2125.5 |  |  | 2299 |  |  | 2143 |  |  | 2309.5 |  |  | 2128 |  |  | 2129.5 |  |  | 2199.5 |  |  | 2190.5 |  |  | 2185 |  |  | 2020 |  |  | 2134 |  |  | 2148.5 |  |  | 2119 |  |  | 2352.5 |  |  | 2188 |  |  | 2174 |  |  | 2134 |  |  | 2191 |  |  | 2277 |  |  | 2238 |  |  | 2199 |  |  | 2356 |  |  | 2232 |  |  | 2197.5 |  |  | 2237 |  |  | 2177 |  |  | 2295.5 |  |  | 2083.5 |  |  | 2231.5 |  |  | 2235.5 |  |  | 2219 |  |  | 2301 |  |  | 2037.5 |  |  | 2327.5 |  |  | 2151.5 |  |  | 2211 |  |  | 2167 |  |  | 2122 |  |  | 2192 |  |  | 2028 |  |  | 2194 |  |  | 2219 |  |  | 2202.5 |  |  | 2213.5 |  |  | 2140 |  |  | 2133.5 |  |  | 2236.5 |  |  | 2107 |  |  | 2218 |  |  | 2123 |  |  | 2230 |  |  | 2120.5 |  |  | 2057.5 |  |  | 2238.5 |  |  | 2160 |  |  | 2127.5 |  |  | 2218 |  |  | 2196 |  |  | 2312 |  |  | 2103.5 |  |  | 2162 |  |  | 2070 |  |  | 2185.5 |  |  | 2110 |  |  | 2270.5 |  |  | 2351 |  |  | 2190.5 |  |  | 2114 |  |  | 2170.5 |  |  | 2220.5 |  |  | 2236 |  |  | 2194 |  |  | 2017 |  |  | 2232 |  |  | 2025.5 |  |  | 2127 |  |  | 2346 |  |  | 2120.5 |  |  | 2323.5 |  |  | 2082.5 |  |  | 2099 |  |  | 2317.5 |  |  | 2242.5 |  |  | 2104.5 |  |  | 2260 |  |  | 2200 |  |  | 2257.5 |  |  | 2251 |  |  | 2316 |  |  | 2287.5 |  |  | 2181 |  |  | 2269 |  |  | 2166 |  |  | 2074 |  |  | 2031.5 |  |  | 2253.5 |  |  | 2111 |  |  | 2292 |  |  | 2256 |  |  | 2154 |  |  | 2132 |  |  | 2139.5 |  |  | 2144.5 |  |  | 2215 |  |  | 2329 |  |  | 2350 |  |  | 2122.5 |  |  | 2403.5 |  |  | 2141 |  |  | 2171 |  |  | 2030 |  |  | 2183.5 |  |  | 2366.5 |  |  | 2178 |  |  | 2063 |  |  | 2237 |  |  | 2221 |  |  | 2183 |  |  | 2319 |  |  | 2116 |  |  | 2310.5 |  |  | 2118 |  |  | 2270 |  |  | 2198 |  |  | 2242.5 |  |  | 2204 |  |  | 2121 |  |  | 2005 |  |  | 2169 |  |  | 2163 |  |  | 2245 |  |  | 2223 |  |  | 2163.5 |  |  | 2143.5 |  |  | 1984.5 |  |  | 2329 |  |  | 2154 |  |  | 2203.5 |  |  | 2027 |  |  | 2080.5 |  |  | 2198.5 |  |  | 2125 |  |  | 2241 |  |  | 2194.5 |  |  | 2210 |  |  | 2251 |  |  | 2226 |  |  | 2220 |  |  | 2253 |  |  | 2121 |  |  | 2143 |  |  | 2215.5 |  |  | 2181 |  |  | 2218 |  |  | 2245 |  |  | 2176 |  |  | 2148 |  |  | 2185 |  |  | 2306 |  |  | 2237 |  |  | 2213 |  |  | 2289.5 |  |  | 2193.5 |  |  | 2181.5 |  |  | 2235.5 |  |  | 2205 |  |  | 2036 |  |  | 2282.5 |  |  | 2140 |  |  | 2165 |  |  | 2100.5 |  |  | 2342.5 |  |  | 2257 |  |  | 2213.5 |  |  | 2171.5 |  |  | 2056 |  |  | 2295 |  |  | 2125 |  |  | 2184 |  |  | 2151.5 |  |  | 2192 |  |  | 2100.5 |  |  | 2104.5 |  |  | 2174 |  |  | 2155 |  |  | 2291.5 |  |  | 2171 |  |  | 2190.5 |  |  | 2195 |  |  | 2194.5 |  |  | 2082.5 |  |  | 2022.5 |  |  | 2281.5 |  |  | 2214.5 |  |  | 2029 |  |  | 2112 |  |  | 2297.5 |  |  | 2216 |  |  | 2119 |  |  | 2167 |  |  | 2319 |  |  | 2299.5 |  |  | 2044 |  |  | 2134 |  |  | 2229 |  |  | 2141.5 |  |  | 2221 |  |  | 2050 |  |  | 2151 |  |  | 2351.5 |  |  | 2217 |  |  | 2001 |  |  | 2199 |  |  | 2299 |  |  | 2437.5 |  |  | 2218 |  |  | 2100.5 |  |  | 2161 |  |  | 2251 |  |  | 2411.5 |  |  | 2228 |  |  | 2149 |  |  | 2137.5 |  |  | 2222 |  |  | 2129 |  |  | 2153 |  |  | 2436.5 |  |  | 2259.5 |  |  | 2242 |  |  | 2100 |  |  | 2198.5 |  |  | 2159.5 |  |  | 2167 |  |  | 2239 |  |  | 2247.5 |  |  | 2381.5 |  |  | 2086.5 |  |  | 2212.5 |  |  | 2163.5 |  |  | 2366 |  |  | 2142.5 |  |  | 2268 |  |  | 2172 |  |  | 2263 |  |  | 2294 |  |  | 2227.5 |  |  | 2192 |  |  | 2095 |  |  | 2219.5 |  |  | 2217.5 |  |  | 2100 |  |  | 2273.5 |  |  | 2170.5 |  |  | 2284 |  |  | 2107 |  |  | 2154 |  |  | 2212.5 |  |  | 2265 |  |  | 2290.5 |  |  | 2244 |  |  | 2214 |  |  | 2407.5 |  |  | 2144 |  |  | 2275 |  |  | 2114 |  |  | 2262 |  |  | 2277 |  |  | 2199 |  |  | 2216 |  |  | 2198 |  |  | 2081.5 |  |  | 2140.5 |  |  | 2168 |  |  | 2207.5 |  |  | 2025.5 |  |  | 2087 |  |  | 2119 |  |  | 2298 |  |  | 2265.5 |  |  | 2102.5 |  |  | 2277 |  |  | 2234 |  |  | 2074 |  |  | 2078 |  |  | 2157 |  |  | 2143 |  |  | 2218 |  |  | 2078.5 |  |  | 2301 |  |  | 2216 |  |  | 2295 |  |  | 2115 |  |  | 2056 |  |  | 2158.5 |  |  | 2331.5 |  |  | 2012.5 |  |  | 2082 |  |  | 2110 |  |  | 2130.5 |  |  | 2282.5 |  |  | 2270.5 |  |  | 2106 |  |  | 2291.5 |  |  | 2229.5 |  |  | 2337 |  |  | 2250.5 |  |  | 2192.5 |  |  | 2206 |  |  | 2065 |  |  | 2144 |  |  | 2298 |  |  | 2152 |  |  | 2043 |  |  | 2263 |  |  | 2324 |  |  | 2072 |  |  | 2176 |  |  | 2277.5 |  |  | 2159 |  |  | 2188 |  |  | 2113 |  |  | 2146.5 |  |  | 2129 |  |  | 2212.5 |  |  | 2345 |  |  | 2238 |  |  | 2191 |  |  | 2182 |  |  | 2308.5 |  |  | 2163 |  |  | 2104 |  |  | 2273.5 |  |  | 2224 |  |  | 2130 |  |  | 2146.5 |  |  | 2176.5 |  |  | 2173 |  |  | 2102.5 |  |  | 2315 |  |  | 2114.5 |  |  | 2295 |  |  | 2227 |  |  | 2125.5 |  |  | 2266.5 |  |  | 2177 |  |  | 2276 |  |  | 2182 |  |  | 2198 |  |  | 2096 |  |  | 2157 |  |  | 2062 |  |  | 2061 |  |  | 2244.5 |  |  | 2038 |  |  | 2308.5 |  |  | 2123 |  |  | 2264.5 |  |  | 2150.5 |  |  | 2123 |  |  | 2208 |  |  | 2309.5 |  |  | 2177 |  |  | 2229 |  |  | 2250 |  |  | 2197.5 |  |  | 2244 |  |  | 2074.5 |  |  | 1982 |  |  | 2158 |  |  | 2163 |  |  | 2207 |  |  | 2243.5 |  |  | 2141 |  |  | 2169 |  |  | 2220 |  |  | 2066.5 |  |  | 2320 |  |  | 2273 |  |  | 2212 |  |  | 2141 |  |  | 2180.5 |  |  | 2089.5 |  |  | 2271 |  |  | 2308 |  |  | 2217 |  |  | 2271.5 |  |  | 2194 |  |  | 2066 |  |  | 2126 |  |  | 2350.5 |  |  | 2144.5 |  |  | 2178.5 |  |  | 2237 |  |  | 2252 |  |  | 2205 |  |  | 2105.5 |  |  | 2240 |  |  | 2140.5 |  |  | 2076 |  |  | 2085 |  |  | 2166 |  |  | 2158.5 |  |  | 2241.5 |  |  | 2190 |  |  | 2166 |  |  | 2296.5 |  |  | 2238 |  |  | 2147 |  |  | 2239.5 |  |  | 2081 |  |  | 2106 |  |  | 2214.5 |  |  | 2130 |  |  | 2247 |  |  | 2151.5 |  |  | 2342 |  |  | 2133.5 |  |  | 2207 |  |  | 2051.5 |  |  | 2246.5 |  |  | 2062 |  |  | 2288 |  |  | 2252.5 |  |  | 2161.5 |  |  | 2317 |  |  | 2201 |  |  | 2188 |  |  | 2200.5 |  |  | 2243 |  |  | 1987 |  |  | 2122 |  |  | 2269.5 |  |  | 2265.5 |  |  | 2206 |  |  | 2280 |  |  | 2151 |  |  | 2115 |  |  | 2295 |  |  | 2144 |  |  | 2170 |  |  | 2179.5 |  |  | 2369.5 |  |  | 2105.5 |  |  | 2160 |  |  | 2151.5 |  |  | 2189 |  |  | 2146 |  |  | 2207.5 |  |  | 2086.5 |  |  | 2131 |  |  | 2231 |  |  | 2137.5 |  |  | 2170 |  |  | 2240 |  |  | 2052.5 |  |  | 2265.5 |  |  | 2154 |  |  | 2165 |  |  | 2201 |  |  | 2072.5 |  |  | 2100 |  |  | 2103 |  |  | 2198 |  |  | 2248 |  |  | 2316 |  |  | 2104.5 |  |  | 2321 |  |  | 2133 |  |  | 2069 |  |  | 2327.5 |  |  | 2191 |  |  | 2111.5 |  |  | 2121.5 |  |  | 2138 |  |  | 2283 |  |  | 2161.5 |  |  | 2124.5 |  |  | 2091.5 |  |  | 2157.5 |  |  | 2194.5 |  |  | 2216 |  |  | 2172 |  |  | 2194.5 |  |  | 2130.5 |  |  | 2188 |  |  | 2123 |  |  | 2192.5 |  |  | 2347 |  |  | 2156 |  |  | 2069 |  |  | 2238.5 |  |  | 2319 |  |  | 2128.5 |  |  | 2075 |  |  | 2254.5 |  |  | 2401.5 |  |  | 2319.5 |  |  | 2317 |  |  | 2247 |  |  | 2184.5 |  |  | 2186.5 |  |  | 2242 |  |  | 2180 |  |  | 2236.5 |  |  | 2330 |  |  | 2199.5 |  |  | 2160.5 |  |  | 2252 |  |  | 2194 |  |  | 2036.5 |  |  | 2272.5 |  |  | 2191 |  |  | 2141.5 |  |  | 2206.5 |  |  | 2235 |  |  | 2273 |  |  | 2259 |  |  | 2199.5 |  |  | 2264 |  |  | 2115 |  |  | 2231 |  |  | 2136 |  |  | 2173 |  |  | 2149 |  |  | 2333.5 |  |  | 2164.5 |  |  | 2147 |  |  | 2165 |  |  | 2233 |  |  | 2187.5 |  |  | 2101 |  |  | 2345 |  |  | 2158.5 |  |  | 2278.5 |  |  | 2176 |  |  | 2179.5 |  |  | 2276 |  |  | 2069 |  |  | 2210 |  |  | 2309.5 |  |  | 2319 |  |  | 2081.5 |  |  | 2156.5 |  |  | 2062 |  |  | 2193.5 |  |  | 2001.5 |  |  | 2162 |  |  | 2134 |  |  | 2302 |  |  | 2107.5 |  |  | 2037 |  |  | 2120.5 |  |  | 2185.5 |  |  | 2268 |  |  | 2071.5 |  |  | 2096 |  |  | 2179 |  |  | 2161 |  |  | 2129 |  |  | 2071 |  |  | 2250.5 |  |  | 2170 |  |  | 2247 |  |  | 2102 |  |  | 2261 |  |  | 2208.5 |  |  | 2233.5 |  |  | 2166 |  |  | 2252 |  |  | 2190 |  |  | 2170 |  |  | 2209 |  |  | 2108.5 |  |  | 2172 |  |  | 2265.5 |  |  | 2282 |  |  | 2023 |  |  | 2152 |  |  | 2186 |  |  | 2239.5 |  |  | 2193 |  |  | 2195.5 |  |  | 2114 |  |  | 2349 |  |  | 2226 |  |  | 2189.5 |  |  | 2100 |  |  | 2070 |  |  | 2102 |  |  | 2318 |  |  | 2403 |  |  | 2142.5 |  |  | 2268.5 |  |  | 2106 |  |  | 2156.5 |  |  | 2110 |  |  | 2114.5 |  |  | 2179.5 |  |  | 2125.5 |  |  | 2101.5 |  |  | 2062 |  |  | 2323 |  |  | 2096 |  |  | 2071 |  |  | 2161 |  |  | 2272 |  |  | 2176.5 |  |  | 2158.5 |  |  | 2299.5 |  |  | 2211 |  |  | 2261.5 |  |  | 2122.5 |  |  | 2260.5 |  |  | 2108.5 |  |  | 2181 |  |  | 2207.5 |  |  | 2206.5 |  |  | 2267 |  |  | 2085.5 |  |  | 2322.5 |  |  | 2239.5 |  |  | 2367 |  |  | 2219.5 |  |  | 2225 |  |  | 2186 |  |  | 2149.5 |  |  | 2241.5 |  |  | 2206 |  |  | 2252 |  |  | 2027.5 |  |  | 2056.5 |  |  | 2130.5 |  |  | 2249 |  |  | 2119 |  |  | 2184 |  |  | 2265.5 |  |  | 2257.5 |  |  | 2233 |  |  | 2209.5 |  |  | 2028 |  |  | 2156 |  |  | 2217.5 |  |  | 2128.5 |  |  | 2163 |  |  | 2219.5 |  |  | 2242 |  |  | 2116.5 |  |  | 2295.5 |  |  | 2264 |  |  | 2195.5 |  |  | 2277 |  |  | 2165.5 |  |  | 2174 |  |  | 2270 |  |  | 2240 |  |  | 2170.5 |  |  | 2085.5 |  |  | 2225 |  |  | 2160 |  |  | 2094 |  |  | 2146.5 |  |  | 2175.5 |  |  | 2278 |  |  | 2212.5 |  |  | 2169 |  |  | 2076.5 |  |  | 2224.5 |  |  | 2097 |  |  | 2155 |  |  | 2173 |  |  | 2150.5 |  |  | 2113 |  |  | 2238.5 |  |  | 2255 |  |  | 2153.5 |  |  | 2362 |  |  | 2015.5 |  |  | 2133 |  |  | 2216.5 |  |  | 2178.5 |  |  | 2122 |  |  | 2192 |  |  | 2398 |  |  | 2166 |  |  | 2264.5 |  |  | 2080 |  |  | 2155.5 |  |  | 2037 |  |  | 2099 |  |  | 2133 |  |  | 2352 |  |  | 2217 |  |  | 2135 |  |  | 2239 |  |  | 2159.5 |  |  | 2093 |  |  | 2235
77 |  | 2399.5 |  |  | 2336 |  |  | 2310.5 |  |  | 2233 |  |  | 2126.5 |  |  | 2272 |  |  | 2285 |  |  | 2246 |  |  | 2100.5 |  |  | 2101 |  |  | 2181 |  |  | 2348 |  |  | 2321 |  |  | 2418 |  |  | 2184.5 |  |  | 2244.5 |  |  | 2181 |  |  | 2223 |  |  | 2339 |  |  | 2131.5 |  |  | 2268 |  |  | 2268 |  |  | 2130 |  |  | 2250 |  |  | 2227.5 |  |  | 2336 |  |  | 2182 |  |  | 2241 |  |  | 2278 |  |  | 2111 |  |  | 2258 |  |  | 2139.5 |  |  | 2290.5 |  |  | 2217.5 |  |  | 2206 |  |  | 2182.5 |  |  | 2239.5 |  |  | 2326.5 |  |  | 2277 |  |  | 2217 |  |  | 2104.5 |  |  | 2160 |  |  | 2247.5 |  |  | 2207.5 |  |  | 2278.5 |  |  | 2431.5 |  |  | 2412.5 |  |  | 2183 |  |  | 2088 |  |  | 2191.5 |  |  | 2199 |  |  | 2176.5 |  |  | 2113.5 |  |  | 2227 |  |  | 2197 |  |  | 2206 |  |  | 2140 |  |  | 2312 |  |  | 2256 |  |  | 2209.5 |  |  | 2185.5 |  |  | 2194.5 |  |  | 2130 |  |  | 2278 |  |  | 2048 |  |  | 2109.5 |  |  | 2181 |  |  | 2199.5 |  |  | 2252.5 |  |  | 2352.5 |  |  | 2229 |  |  | 2373 |  |  | 2306 |  |  | 2225.5 |  |  | 2315.5 |  |  | 2217.5 |  |  | 2329.5 |  |  | 2232.5 |  |  | 2242.5 |  |  | 2218.5 |  |  | 2162.5 |  |  | 2100 |  |  | 2278 |  |  | 2133 |  |  | 2351.5 |  |  | 2349 |  |  | 2176.5 |  |  | 2282 |  |  | 2232 |  |  | 2254.5 |  |  | 2349.5 |  |  | 2198 |  |  | 2352 |  |  | 2138.5 |  |  | 2360 |  |  | 2163.5 |  |  | 2230.5 |  |  | 2257.5 |  |  | 2129.5 |  |  | 2146.5 |  |  | 2186 |  |  | 2207 |  |  | 2077 |  |  | 2190.5 |  |  | 2168.5 |  |  | 2260.5 |  |  | 2142.5 |  |  | 2197 |  |  | 2163 |  |  | 2243.5 |  |  | 2099 |  |  | 2261.5 |  |  | 2237 |  |  | 2179 |  |  | 2099.5 |  |  | 2215 |  |  | 2198 |  |  | 2141 |  |  | 2237 |  |  | 2187.5 |  |  | 2215.5 |  |  | 2167.5 |  |  | 2308 |  |  | 2206 |  |  | 2140 |  |  | 2145 |  |  | 2148.5 |  |  | 2182 |  |  | 2254.5 |  |  | 2187 |  |  | 2134 |  |  | 2204.5 |  |  | 2129.5 |  |  | 2123 |  |  | 2127.5 |  |  | 2179 |  |  | 2304 |  |  | 2178 |  |  | 2329 |  |  | 2123 |  |  | 2148 |  |  | 2172 |  |  | 2239 |  |  | 2103 |  |  | 2074.5 |  |  | 2186 |  |  | 2072 |  |  | 2327 |  |  | 2213 |  |  | 2235 |  |  | 2127 |  |  | 2200 |  |  | 2228.5 |  |  | 2235 |  |  | 2283.5 |  |  | 2233 |  |  | 2154 |  |  | 2284.5 |  |  | 2226 |  |  | 2314.5 |  |  | 2163 |  |  | 2068 |  |  | 2194.5 |  |  | 2300 |  |  | 2328.5 |  |  | 2268 |  |  | 2089 |  |  | 2284.5 |  |  | 2282.5 |  |  | 2274 |  |  | 2186.5 |  |  | 2185.5 |  |  | 2188 |  |  | 2257 |  |  | 2393.5 |  |  | 2128.5 |  |  | 2261.5 |  |  | 2261 |  |  | 2311 |  |  | 2173 |  |  | 2338 |  |  | 2293 |  |  | 2251.5 |  |  | 2188 |  |  | 2123.5 |  |  | 2240.5 |  |  | 2224 |  |  | 2273 |  |  | 2442.5 |  |  | 2121.5 |  |  | 2160 |  |  | 2257.5 |  |  | 2100.5 |  |  | 2249 |  |  | 2076 |  |  | 2144 |  |  | 2183.5 |  |  | 2315 |  |  | 2175.5 |  |  | 2244.5 |  |  | 2148 |  |  | 2148.5 |  |  | 2118 |  |  | 2191 |  |  | 2254 |  |  | 2282 |  |  | 2037 |  |  | 2304 |  |  | 2333 |  |  | 2231 |  |  | 2346 |  |  | 2178 |  |  | 2208.5 |  |  | 2329.5 |  |  | 2174 |  |  | 2126 |  |  | 2363 |  |  | 2224.5 |  |  | 2297.5 |  |  | 2341.5 |  |  | 2141 |  |  | 2253 |  |  | 2368.5 |  |  | 2226.5 |  |  | 2088.5 |  |  | 2296 |  |  | 2345 |  |  | 2197 |  |  | 2256 |  |  | 2226 |  |  | 2197.5 |  |  | 2153.5 |  |  | 2320 |  |  | 2157 |  |  | 2168 |  |  | 2327 |  |  | 2169 |  |  | 2359.5 |  |  | 2280 |  |  | 2224 |  |  | 2178 |  |  | 2181 |  |  | 2213.5 |  |  | 2349 |  |  | 2206 |  |  | 2194 |  |  | 2311 |  |  | 2320.5 |  |  | 2272 |  |  | 2162 |  |  | 2166 |  |  | 2265.5 |  |  | 2219.5 |  |  | 2326.5 |  |  | 2339 |  |  | 2201 |  |  | 2099 |  |  | 2369 |  |  | 2223 |  |  | 2166.5 |  |  | 2295 |  |  | 2186.5 |  |  | 2256.5 |  |  | 2251.5 |  |  | 2234 |  |  | 2376.5 |  |  | 2116 |  |  | 2123 |  |  | 2167.5 |  |  | 2224.5 |  |  | 2280 |  |  | 2326.5 |  |  | 2332.5 |  |  | 2202 |  |  | 2262 |  |  | 2164.5 |  |  | 2188.5 |  |  | 2374 |  |  | 2237.5 |  |  | 2334 |  |  | 2187 |  |  | 2133.5 |  |  | 2275 |  |  | 2135 |  |  | 2220.5 |  |  | 2226 |  |  | 2396.5 |  |  | 2207 |  |  | 2411 |  |  | 2241 |  |  | 2184 |  |  | 2352.5 |  |  | 2379 |  |  | 2305.5 |  |  | 2071.5 |  |  | 2328.5 |  |  | 2243 |  |  | 2266.5 |  |  | 2398 |  |  | 2261 |  |  | 2051.5 |  |  | 2201.5 |  |  | 2302 |  |  | 2172.5 |  |  | 2338 |  |  | 2164 |  |  | 2338.5 |  |  | 2149 |  |  | 2176.5 |  |  | 2225.5 |  |  | 2216.5 |  |  | 2214 |  |  | 2059 |  |  | 2155 |  |  | 2169.5 |  |  | 2158 |  |  | 2373.5 |  |  | 2209 |  |  | 2200 |  |  | 2158 |  |  | 2230 |  |  | 2292 |  |  | 2277 |  |  | 2238 |  |  | 2395 |  |  | 2256 |  |  | 2212.5 |  |  | 2252 |  |  | 2206 |  |  | 2310.5 |  |  | 2122.5 |  |  | 2260.5 |  |  | 2250.5 |  |  | 2258 |  |  | 2340 |  |  | 2063.5 |  |  | 2366.5 |  |  | 2190.5 |  |  | 2237 |  |  | 2182 |  |  | 2137 |  |  | 2207 |  |  | 2054 |  |  | 2220 |  |  | 2240 |  |  | 2226.5 |  |  | 2237.5 |  |  | 2179 |  |  | 2157.5 |  |  | 2251.5 |  |  | 2146 |  |  | 2257 |  |  | 2152 |  |  | 2256 |  |  | 2144.5 |  |  | 2096.5 |  |  | 2259.5 |  |  | 2181 |  |  | 2174.5 |  |  | 2242 |  |  | 2211 |  |  | 2336 |  |  | 2127.5 |  |  | 2177 |  |  | 2094 |  |  | 2224.5 |  |  | 2136 |  |  | 2296.5 |  |  | 2390 |  |  | 2229.5 |  |  | 2161 |  |  | 2209.5 |  |  | 2235.5 |  |  | 2262 |  |  | 2233 |  |  | 2056 |  |  | 2256 |  |  | 2049.5 |  |  | 2174 |  |  | 2367 |  |  | 2149.5 |  |  | 2338.5 |  |  | 2108.5 |  |  | 2128 |  |  | 2343.5 |  |  | 2271.5 |  |  | 2125.5 |  |  | 2307 |  |  | 2226 |  |  | 2283.5 |  |  | 2290 |  |  | 2355 |  |  | 2311.5 |  |  | 2220 |  |  | 2308 |  |  | 2205 |  |  | 2098 |  |  | 2060.5 |  |  | 2274.5 |  |  | 2126 |  |  | 2316 |  |  | 2271 |  |  | 2183 |  |  | 2171 |  |  | 2154.5 |  |  | 2159.5 |  |  | 2241 |  |  | 2358 |  |  | 2397 |  |  | 2148.5 |  |  | 2442.5 |  |  | 2156 |  |  | 2210 |  |  | 2054 |  |  | 2222.5 |  |  | 2392.5 |  |  | 2202 |  |  | 2092 |  |  | 2276 |  |  | 2247 |  |  | 2198 |  |  | 2343 |  |  | 2163 |  |  | 2357.5 |  |  | 2147 |  |  | 2309 |  |  | 2237 |  |  | 2268.5 |  |  | 2243 |  |  | 2160 |  |  | 2029 |  |  | 2190 |  |  | 2202 |  |  | 2269 |  |  | 2249 |  |  | 2187.5 |  |  | 2182.5 |  |  | 2023.5 |  |  | 2368 |  |  | 2178 |  |  | 2224.5 |  |  | 2066 |  |  | 2119.5 |  |  | 2245.5 |  |  | 2164 |  |  | 2280 |  |  | 2241.5 |  |  | 2234 |  |  | 2266 |  |  | 2255 |  |  | 2246 |  |  | 2292 |  |  | 2142 |  |  | 2182 |  |  | 2244.5 |  |  | 2220 |  |  | 2257 |  |  | 2284 |  |  | 2202 |  |  | 2187 |  |  | 2232 |  |  | 2327 |  |  | 2263 |  |  | 2228 |  |  | 2328.5 |  |  | 2208.5 |  |  | 2220.5 |  |  | 2264.5 |  |  | 2244 |  |  | 2057 |  |  | 2311.5 |  |  | 2155 |  |  | 2194 |  |  | 2115.5 |  |  | 2368.5 |  |  | 2296 |  |  | 2228.5 |  |  | 2218.5 |  |  | 2080 |  |  | 2342 |  |  | 2154 |  |  | 2231 |  |  | 2190.5 |  |  | 2239 |  |  | 2139.5 |  |  | 2151.5 |  |  | 2213 |  |  | 2179 |  |  | 2317.5 |  |  | 2197 |  |  | 2219.5 |  |  | 2234 |  |  | 2233.5 |  |  | 2111.5 |  |  | 2051.5 |  |  | 2328.5 |  |  | 2229.5 |  |  | 2053 |  |  | 2138 |  |  | 2318.5 |  |  | 2240 |  |  | 2134 |  |  | 2214 |  |  | 2345 |  |  | 2320.5 |  |  | 2070 |  |  | 2160 |  |  | 2268 |  |  | 2188.5 |  |  | 2247 |  |  | 2089 |  |  | 2166 |  |  | 2390.5 |  |  | 2256 |  |  | 2048 |  |  | 2223 |  |  | 2346 |  |  | 2476.5 |  |  | 2247 |  |  | 2139.5 |  |  | 2200 |  |  | 2290 |  |  | 2426.5 |  |  | 2249 |  |  | 2196 |  |  | 2158.5 |  |  | 2243 |  |  | 2168 |  |  | 2192 |  |  | 2465.5 |  |  | 2283.5 |  |  | 2266 |  |  | 2126 |  |  | 2224.5 |  |  | 2198.5 |  |  | 2206 |  |  | 2268 |  |  | 2273.5 |  |  | 2428.5 |  |  | 2115.5 |  |  | 2241.5 |  |  | 2189.5 |  |  | 2405 |  |  | 2163.5 |  |  | 2307 |  |  | 2211 |  |  | 2310 |  |  | 2341 |  |  | 2253.5 |  |  | 2239 |  |  | 2142 |  |  | 2243.5 |  |  | 2264.5 |  |  | 2124 |  |  | 2297.5 |  |  | 2196.5 |  |  | 2310 |  |  | 2131 |  |  | 2169 |  |  | 2236.5 |  |  | 2312 |  |  | 2319.5 |  |  | 2283 |  |  | 2253 |  |  | 2446.5 |  |  | 2165 |  |  | 2290 |  |  | 2153 |  |  | 2301 |  |  | 2306 |  |  | 2238 |  |  | 2255 |  |  | 2222 |  |  | 2107.5 |  |  | 2179.5 |  |  | 2194 |  |  | 2233.5 |  |  | 2054.5 |  |  | 2116 |  |  | 2166 |  |  | 2322 |  |  | 2304.5 |  |  | 2123.5 |  |  | 2292 |  |  | 2281 |  |  | 2121 |  |  | 2125 |  |  | 2196 |  |  | 2167 |  |  | 2244 |  |  | 2099.5 |  |  | 2322 |  |  | 2255 |  |  | 2324 |  |  | 2130 |  |  | 2095 |  |  | 2187.5 |  |  | 2352.5 |  |  | 2051.5 |  |  | 2121 |  |  | 2131 |  |  | 2145.5 |  |  | 2311.5 |  |  | 2291.5 |  |  | 2145 |  |  | 2330.5 |  |  | 2258.5 |  |  | 2361 |  |  | 2271.5 |  |  | 2231.5 |  |  | 2230 |  |  | 2091 |  |  | 2183 |  |  | 2327 |  |  | 2167 |  |  | 2072 |  |  | 2278 |  |  | 2348 |  |  | 2098 |  |  | 2202 |  |  | 2298.5 |  |  | 2198 |  |  | 2227 |  |  | 2134 |  |  | 2161.5 |  |  | 2155 |  |  | 2238.5 |  |  | 2384 |  |  | 2285 |  |  | 2206 |  |  | 2206 |  |  | 2323.5 |  |  | 2192 |  |  | 2128 |  |  | 2294.5 |  |  | 2248 |  |  | 2145 |  |  | 2170.5 |  |  | 2205.5 |  |  | 2220 |  |  | 2117.5 |  |  | 2354 |  |  | 2135.5 |  |  | 2321 |  |  | 2256 |  |  | 2149.5 |  |  | 2281.5 |  |  | 2216 |  |  | 2315 |  |  | 2197 |  |  | 2237 |  |  | 2122 |  |  | 2196 |  |  | 2091 |  |  | 2100 |  |  | 2268.5 |  |  | 2077 |  |  | 2334.5 |  |  | 2162 |  |  | 2279.5 |  |  | 2189.5 |  |  | 2170 |  |  | 2247 |  |  | 2338.5 |  |  | 2203 |  |  | 2276 |  |  | 2289 |  |  | 2223.5 |  |  | 2291 |  |  | 2113.5 |  |  | 2003 |  |  | 2179 |  |  | 2187 |  |  | 2231 |  |  | 2282.5 |  |  | 2156 |  |  | 2208 |  |  | 2259 |  |  | 2087.5 |  |  | 2359 |  |  | 2288 |  |  | 2251 |  |  | 2162 |  |  | 2209.5 |  |  | 2128.5 |  |  | 2310 |  |  | 2329 |  |  | 2241 |  |  | 2300.5 |  |  | 2223 |  |  | 2092 |  |  | 2152 |  |  | 2389.5 |  |  | 2170.5 |  |  | 2204.5 |  |  | 2263 |  |  | 2281 |  |  | 2252 |  |  | 2129.5 |  |  | 2279 |  |  | 2164.5 |  |  | 2100 |  |  | 2100 |  |  | 2205 |  |  | 2197.5 |  |  | 2256.5 |  |  | 2229 |  |  | 2187 |  |  | 2311.5 |  |  | 2259 |  |  | 2162 |  |  | 2265.5 |  |  | 2096 |  |  | 2121 |  |  | 2243.5 |  |  | 2154 |  |  | 2268 |  |  | 2177.5 |  |  | 2366 |  |  | 2159.5 |  |  | 2228 |  |  | 2090.5 |  |  | 2272.5 |  |  | 2091 |  |  | 2303 |  |  | 2291.5 |  |  | 2185.5 |  |  | 2341 |  |  | 2227 |  |  | 2214 |  |  | 2229.5 |  |  | 2290 |  |  | 2008 |  |  | 2148 |  |  | 2316.5 |  |  | 2294.5 |  |  | 2232 |  |  | 2304 |  |  | 2190 |  |  | 2144 |  |  | 2324 |  |  | 2170 |  |  | 2199 |  |  | 2205.5 |  |  | 2416.5 |  |  | 2129.5 |  |  | 2184 |  |  | 2172.5 |  |  | 2204 |  |  | 2185 |  |  | 2233.5 |  |  | 2112.5 |  |  | 2160 |  |  | 2252 |  |  | 2163.5 |  |  | 2199 |  |  | 2264 |  |  | 2078.5 |  |  | 2280.5 |  |  | 2175 |  |  | 2204 |  |  | 2230 |  |  | 2093.5 |  |  | 2139 |  |  | 2127 |  |  | 2227 |  |  | 2287 |  |  | 2340 |  |  | 2125.5 |  |  | 2360 |  |  | 2180 |  |  | 2098 |  |  | 2342.5 |  |  | 2215 |  |  | 2150.5 |  |  | 2136.5 |  |  | 2162 |  |  | 2304 |  |  | 2182.5 |  |  | 2139.5 |  |  | 2106.5 |  |  | 2204.5 |  |  | 2233.5 |  |  | 2240 |  |  | 2211 |  |  | 2233.5 |  |  | 2159.5 |  |  | 2203 |  |  | 2152 |  |  | 2231.5 |  |  | 2373 |  |  | 2180 |  |  | 2108 |  |  | 2277.5 |  |  | 2334 |  |  | 2154.5 |  |  | 2099 |  |  | 2275.5 |  |  | 2430.5 |  |  | 2366.5 |  |  | 2364 |  |  | 2271 |  |  | 2223.5 |  |  | 2210.5 |  |  | 2289 |  |  | 2219 |  |  | 2260.5 |  |  | 2369 |  |  | 2214.5 |  |  | 2207.5 |  |  | 2276 |  |  | 2233 |  |  | 2065.5 |  |  | 2311.5 |  |  | 2238 |  |  | 2156.5 |  |  | 2253.5 |  |  | 2264 |  |  | 2288 |  |  | 2285 |  |  | 2228.5 |  |  | 2279 |  |  | 2154 |  |  | 2270 |  |  | 2160 |  |  | 2220 |  |  | 2178 |  |  | 2372.5 |  |  | 2193.5 |  |  | 2186 |  |  | 2180 |  |  | 2272 |  |  | 2202.5 |  |  | 2122 |  |  | 2392 |  |  | 2197.5 |  |  | 2317.5 |  |  | 2200 |  |  | 2203.5 |  |  | 2300 |  |  | 2090 |  |  | 2249 |  |  | 2333.5 |  |  | 2340 |  |  | 2110.5 |  |  | 2195.5 |  |  | 2086 |  |  | 2214.5 |  |  | 2022.5 |  |  | 2183 |  |  | 2160 |  |  | 2331 |  |  | 2122.5 |  |  | 2076 |  |  | 2144.5 |  |  | 2232.5 |  |  | 2307 |  |  | 2092.5 |  |  | 2122 |  |  | 2205 |  |  | 2185 |  |  | 2158 |  |  | 2097 |  |  | 2289.5 |  |  | 2196 |  |  | 2294 |  |  | 2117 |  |  | 2308 |  |  | 2255.5 |  |  | 2272.5 |  |  | 2190 |  |  | 2267 |  |  | 2205 |  |  | 2209 |  |  | 2248 |  |  | 2129.5 |  |  | 2211 |  |  | 2294.5 |  |  | 2321 |  |  | 2049 |  |  | 2191 |  |  | 2225 |  |  | 2278.5 |  |  | 2208 |  |  | 2234.5 |  |  | 2153 |  |  | 2375 |  |  | 2255 |  |  | 2236.5 |  |  | 2126 |  |  | 2117 |  |  | 2149 |  |  | 2357 |  |  | 2429 |  |  | 2181.5 |  |  | 2315.5 |  |  | 2130 |  |  | 2171.5 |  |  | 2134 |  |  | 2143.5 |  |  | 2203.5 |  |  | 2164.5 |  |  | 2125.5 |  |  | 2083 |  |  | 2362 |  |  | 2125 |  |  | 2118 |  |  | 2200 |  |  | 2287 |  |  | 2215.5 |  |  | 2197.5 |  |  | 2325.5 |  |  | 2250 |  |  | 2300.5 |  |  | 2161.5 |  |  | 2289.5 |  |  | 2134.5 |  |  | 2196 |  |  | 2246.5 |  |  | 2245.5 |  |  | 2306 |  |  | 2100.5 |  |  | 2348.5 |  |  | 2263.5 |  |  | 2414 |  |  | 2234.5 |  |  | 2264 |  |  | 2212 |  |  | 2178.5 |  |  | 2280.5 |  |  | 2235 |  |  | 2281 |  |  | 2066.5 |  |  | 2103.5 |  |  | 2154.5 |  |  | 2278 |  |  | 2158 |  |  | 2199 |  |  | 2312.5 |  |  | 2304.5 |  |  | 2262 |  |  | 2248.5 |  |  | 2067 |  |  | 2177 |  |  | 2256.5 |  |  | 2167.5 |  |  | 2210 |  |  | 2248.5 |  |  | 2266 |  |  | 2155.5 |  |  | 2319.5 |  |  | 2293 |  |  | 2224.5 |  |  | 2303 |  |  | 2204.5 |  |  | 2213 |  |  | 2299 |  |  | 2279 |  |  | 2199.5 |  |  | 2114.5 |  |  | 2264 |  |  | 2199 |  |  | 2115 |  |  | 2172.5 |  |  | 2199.5 |  |  | 2325 |  |  | 2236.5 |  |  | 2195 |  |  | 2105.5 |  |  | 2263.5 |  |  | 2126 |  |  | 2176 |  |  | 2199 |  |  | 2179.5 |  |  | 2160 |  |  | 2262.5 |  |  | 2270 |  |  | 2168.5 |  |  | 2388 |  |  | 2041.5 |  |  | 2180 |  |  | 2245.5 |  |  | 2193.5 |  |  | 2161 |  |  | 2207 |  |  | 2437 |  |  | 2181 |  |  | 2293.5 |  |  | 2106 |  |  | 2179.5 |  |  | 2084 |  |  | 2125 |  |  | 2180 |  |  | 2381 |  |  | 2238 |  |  | 2174 |  |  | 2260 |  |  | 2198.5 |  |  | 2117 |  |  | 2250
78 |  | 2420.5 |  |  | 2365 |  |  | 2339.5 |  |  | 2272 |  |  | 2155.5 |  |  | 2319 |  |  | 2324 |  |  | 2267 |  |  | 2129.5 |  |  | 2140 |  |  | 2220 |  |  | 2369 |  |  | 2336 |  |  | 2433 |  |  | 2199.5 |  |  | 2283.5 |  |  | 2210 |  |  | 2262 |  |  | 2368 |  |  | 2160.5 |  |  | 2297 |  |  | 2307 |  |  | 2156 |  |  | 2274 |  |  | 2253.5 |  |  | 2362 |  |  | 2203 |  |  | 2280 |  |  | 2317 |  |  | 2132 |  |  | 2282 |  |  | 2186.5 |  |  | 2329.5 |  |  | 2246.5 |  |  | 2227 |  |  | 2208.5 |  |  | 2278.5 |  |  | 2365.5 |  |  | 2306 |  |  | 2256 |  |  | 2125.5 |  |  | 2186 |  |  | 2271.5 |  |  | 2233.5 |  |  | 2304.5 |  |  | 2446.5 |  |  | 2433.5 |  |  | 2212 |  |  | 2127 |  |  | 2230.5 |  |  | 2238 |  |  | 2202.5 |  |  | 2152.5 |  |  | 2242 |  |  | 2244 |  |  | 2230 |  |  | 2161 |  |  | 2351 |  |  | 2295 |  |  | 2238.5 |  |  | 2214.5 |  |  | 2209.5 |  |  | 2169 |  |  | 2293 |  |  | 2074 |  |  | 2148.5 |  |  | 2205 |  |  | 2228.5 |  |  | 2291.5 |  |  | 2376.5 |  |  | 2255 |  |  | 2402 |  |  | 2332 |  |  | 2251.5 |  |  | 2354.5 |  |  | 2243.5 |  |  | 2368.5 |  |  | 2271.5 |  |  | 2281.5 |  |  | 2233.5 |  |  | 2186.5 |  |  | 2115 |  |  | 2317 |  |  | 2159 |  |  | 2372.5 |  |  | 2396 |  |  | 2191.5 |  |  | 2311 |  |  | 2261 |  |  | 2275.5 |  |  | 2364.5 |  |  | 2213 |  |  | 2373 |  |  | 2167.5 |  |  | 2407 |  |  | 2202.5 |  |  | 2277.5 |  |  | 2286.5 |  |  | 2168.5 |  |  | 2161.5 |  |  | 2207 |  |  | 2231 |  |  | 2106 |  |  | 2205.5 |  |  | 2207.5 |  |  | 2275.5 |  |  | 2171.5 |  |  | 2223 |  |  | 2202 |  |  | 2282.5 |  |  | 2146 |  |  | 2285.5 |  |  | 2263 |  |  | 2200 |  |  | 2138.5 |  |  | 2254 |  |  | 2224 |  |  | 2170 |  |  | 2276 |  |  | 2213.5 |  |  | 2230.5 |  |  | 2188.5 |  |  | 2347 |  |  | 2221 |  |  | 2179 |  |  | 2184 |  |  | 2163.5 |  |  | 2229 |  |  | 2280.5 |  |  | 2234 |  |  | 2155 |  |  | 2230.5 |  |  | 2153.5 |  |  | 2149 |  |  | 2151.5 |  |  | 2226 |  |  | 2351 |  |  | 2193 |  |  | 2353 |  |  | 2147 |  |  | 2169 |  |  | 2187 |  |  | 2278 |  |  | 2142 |  |  | 2100.5 |  |  | 2207 |  |  | 2111 |  |  | 2366 |  |  | 2260 |  |  | 2259 |  |  | 2142 |  |  | 2224 |  |  | 2249.5 |  |  | 2274 |  |  | 2309.5 |  |  | 2257 |  |  | 2178 |  |  | 2310.5 |  |  | 2252 |  |  | 2338.5 |  |  | 2192 |  |  | 2097 |  |  | 2233.5 |  |  | 2339 |  |  | 2367.5 |  |  | 2315 |  |  | 2118 |  |  | 2323.5 |  |  | 2308.5 |  |  | 2300 |  |  | 2233.5 |  |  | 2211.5 |  |  | 2217 |  |  | 2296 |  |  | 2422.5 |  |  | 2143.5 |  |  | 2300.5 |  |  | 2285 |  |  | 2337 |  |  | 2202 |  |  | 2362 |  |  | 2322 |  |  | 2272.5 |  |  | 2235 |  |  | 2138.5 |  |  | 2255.5 |  |  | 2250 |  |  | 2294 |  |  | 2466.5 |  |  | 2150.5 |  |  | 2186 |  |  | 2281.5 |  |  | 2139.5 |  |  | 2275 |  |  | 2123 |  |  | 2191 |  |  | 2222.5 |  |  | 2344 |  |  | 2222.5 |  |  | 2291.5 |  |  | 2169 |  |  | 2177.5 |  |  | 2144 |  |  | 2217 |  |  | 2301 |  |  | 2321 |  |  | 2066 |  |  | 2351 |  |  | 2372 |  |  | 2257 |  |  | 2385 |  |  | 2204 |  |  | 2255.5 |  |  | 2358.5 |  |  | 2213 |  |  | 2155 |  |  | 2384 |  |  | 2263.5 |  |  | 2344.5 |  |  | 2365.5 |  |  | 2167 |  |  | 2268 |  |  | 2407.5 |  |  | 2247.5 |  |  | 2103.5 |  |  | 2320 |  |  | 2374 |  |  | 2236 |  |  | 2285 |  |  | 2247 |  |  | 2221.5 |  |  | 2174.5 |  |  | 2367 |  |  | 2183 |  |  | 2194 |  |  | 2374 |  |  | 2208 |  |  | 2388.5 |  |  | 2295 |  |  | 2239 |  |  | 2193 |  |  | 2196 |  |  | 2260.5 |  |  | 2388 |  |  | 2230 |  |  | 2215 |  |  | 2332 |  |  | 2346.5 |  |  | 2287 |  |  | 2209 |  |  | 2192 |  |  | 2304.5 |  |  | 2258.5 |  |  | 2373.5 |  |  | 2360 |  |  | 2216 |  |  | 2138 |  |  | 2384 |  |  | 2247 |  |  | 2192.5 |  |  | 2334 |  |  | 2207.5 |  |  | 2280.5 |  |  | 2272.5 |  |  | 2281 |  |  | 2397.5 |  |  | 2131 |  |  | 2149 |  |  | 2206.5 |  |  | 2271.5 |  |  | 2306 |  |  | 2365.5 |  |  | 2361.5 |  |  | 2217 |  |  | 2309 |  |  | 2179.5 |  |  | 2227.5 |  |  | 2413 |  |  | 2276.5 |  |  | 2381 |  |  | 2211 |  |  | 2172.5 |  |  | 2296 |  |  | 2164 |  |  | 2259.5 |  |  | 2265 |  |  | 2422.5 |  |  | 2246 |  |  | 2432 |  |  | 2280 |  |  | 2208 |  |  | 2399.5 |  |  | 2394 |  |  | 2344.5 |  |  | 2086.5 |  |  | 2367.5 |  |  | 2269 |  |  | 2313.5 |  |  | 2413 |  |  | 2285 |  |  | 2072.5 |  |  | 2240.5 |  |  | 2323 |  |  | 2201.5 |  |  | 2377 |  |  | 2188 |  |  | 2385.5 |  |  | 2170 |  |  | 2202.5 |  |  | 2251.5 |  |  | 2263.5 |  |  | 2253 |  |  | 2106 |  |  | 2181 |  |  | 2190.5 |  |  | 2182 |  |  | 2412.5 |  |  | 2256 |  |  | 2239 |  |  | 2187 |  |  | 2256 |  |  | 2331 |  |  | 2298 |  |  | 2267 |  |  | 2416 |  |  | 2280 |  |  | 2251.5 |  |  | 2291 |  |  | 2227 |  |  | 2349.5 |  |  | 2137.5 |  |  | 2275.5 |  |  | 2279.5 |  |  | 2279 |  |  | 2379 |  |  | 2078.5 |  |  | 2392.5 |  |  | 2211.5 |  |  | 2276 |  |  | 2206 |  |  | 2152 |  |  | 2231 |  |  | 2075 |  |  | 2267 |  |  | 2279 |  |  | 2265.5 |  |  | 2276.5 |  |  | 2218 |  |  | 2196.5 |  |  | 2266.5 |  |  | 2170 |  |  | 2281 |  |  | 2173 |  |  | 2295 |  |  | 2173.5 |  |  | 2125.5 |  |  | 2283.5 |  |  | 2202 |  |  | 2195.5 |  |  | 2289 |  |  | 2235 |  |  | 2362 |  |  | 2156.5 |  |  | 2201 |  |  | 2123 |  |  | 2263.5 |  |  | 2160 |  |  | 2317.5 |  |  | 2416 |  |  | 2258.5 |  |  | 2200 |  |  | 2224.5 |  |  | 2274.5 |  |  | 2309 |  |  | 2272 |  |  | 2080 |  |  | 2277 |  |  | 2070.5 |  |  | 2198 |  |  | 2388 |  |  | 2188.5 |  |  | 2377.5 |  |  | 2129.5 |  |  | 2154 |  |  | 2390.5 |  |  | 2292.5 |  |  | 2151.5 |  |  | 2328 |  |  | 2265 |  |  | 2322.5 |  |  | 2305 |  |  | 2394 |  |  | 2326.5 |  |  | 2259 |  |  | 2332 |  |  | 2231 |  |  | 2119 |  |  | 2099.5 |  |  | 2298.5 |  |  | 2173 |  |  | 2363 |  |  | 2310 |  |  | 2209 |  |  | 2200 |  |  | 2193.5 |  |  | 2206.5 |  |  | 2256 |  |  | 2384 |  |  | 2426 |  |  | 2172.5 |  |  | 2481.5 |  |  | 2171 |  |  | 2225 |  |  | 2093 |  |  | 2246.5 |  |  | 2416.5 |  |  | 2228 |  |  | 2131 |  |  | 2302 |  |  | 2273 |  |  | 2237 |  |  | 2372 |  |  | 2184 |  |  | 2404.5 |  |  | 2176 |  |  | 2348 |  |  | 2266 |  |  | 2315.5 |  |  | 2264 |  |  | 2199 |  |  | 2055 |  |  | 2214 |  |  | 2223 |  |  | 2293 |  |  | 2264 |  |  | 2208.5 |  |  | 2221.5 |  |  | 2049.5 |  |  | 2397 |  |  | 2199 |  |  | 2239.5 |  |  | 2081 |  |  | 2166.5 |  |  | 2271.5 |  |  | 2188 |  |  | 2304 |  |  | 2262.5 |  |  | 2273 |  |  | 2305 |  |  | 2281 |  |  | 2293 |  |  | 2318 |  |  | 2189 |  |  | 2211 |  |  | 2270.5 |  |  | 2246 |  |  | 2304 |  |  | 2299 |  |  | 2231 |  |  | 2213 |  |  | 2247 |  |  | 2366 |  |  | 2287 |  |  | 2249 |  |  | 2349.5 |  |  | 2237.5 |  |  | 2267.5 |  |  | 2293.5 |  |  | 2283 |  |  | 2072 |  |  | 2340.5 |  |  | 2176 |  |  | 2215 |  |  | 2154.5 |  |  | 2392.5 |  |  | 2325 |  |  | 2267.5 |  |  | 2257.5 |  |  | 2106 |  |  | 2381 |  |  | 2193 |  |  | 2255 |  |  | 2219.5 |  |  | 2263 |  |  | 2178.5 |  |  | 2190.5 |  |  | 2234 |  |  | 2218 |  |  | 2346.5 |  |  | 2223 |  |  | 2245.5 |  |  | 2260 |  |  | 2259.5 |  |  | 2132.5 |  |  | 2077.5 |  |  | 2349.5 |  |  | 2244.5 |  |  | 2092 |  |  | 2167 |  |  | 2333.5 |  |  | 2255 |  |  | 2158 |  |  | 2238 |  |  | 2392 |  |  | 2335.5 |  |  | 2096 |  |  | 2181 |  |  | 2283 |  |  | 2235.5 |  |  | 2262 |  |  | 2115 |  |  | 2213 |  |  | 2437.5 |  |  | 2303 |  |  | 2087 |  |  | 2270 |  |  | 2372 |  |  | 2502.5 |  |  | 2276 |  |  | 2178.5 |  |  | 2247 |  |  | 2305 |  |  | 2465.5 |  |  | 2288 |  |  | 2243 |  |  | 2187.5 |  |  | 2269 |  |  | 2189 |  |  | 2218 |  |  | 2504.5 |  |  | 2307.5 |  |  | 2305 |  |  | 2165 |  |  | 2253.5 |  |  | 2245.5 |  |  | 2245 |  |  | 2289 |  |  | 2299.5 |  |  | 2452.5 |  |  | 2154.5 |  |  | 2288.5 |  |  | 2213.5 |  |  | 2434 |  |  | 2189.5 |  |  | 2354 |  |  | 2258 |  |  | 2357 |  |  | 2367 |  |  | 2277.5 |  |  | 2260 |  |  | 2171 |  |  | 2264.5 |  |  | 2311.5 |  |  | 2139 |  |  | 2321.5 |  |  | 2211.5 |  |  | 2331 |  |  | 2178 |  |  | 2208 |  |  | 2251.5 |  |  | 2333 |  |  | 2348.5 |  |  | 2309 |  |  | 2277 |  |  | 2493.5 |  |  | 2189 |  |  | 2311 |  |  | 2192 |  |  | 2322 |  |  | 2332 |  |  | 2277 |  |  | 2302 |  |  | 2248 |  |  | 2154.5 |  |  | 2218.5 |  |  | 2215 |  |  | 2254.5 |  |  | 2093.5 |  |  | 2163 |  |  | 2181 |  |  | 2337 |  |  | 2333.5 |  |  | 2138.5 |  |  | 2316 |  |  | 2302 |  |  | 2160 |  |  | 2149 |  |  | 2225 |  |  | 2206 |  |  | 2291 |  |  | 2114.5 |  |  | 2361 |  |  | 2294 |  |  | 2363 |  |  | 2156 |  |  | 2134 |  |  | 2208.5 |  |  | 2391.5 |  |  | 2090.5 |  |  | 2160 |  |  | 2160 |  |  | 2169.5 |  |  | 2337.5 |  |  | 2315.5 |  |  | 2171 |  |  | 2359.5 |  |  | 2279.5 |  |  | 2376 |  |  | 2310.5 |  |  | 2270.5 |  |  | 2251 |  |  | 2115 |  |  | 2222 |  |  | 2351 |  |  | 2182 |  |  | 2098 |  |  | 2304 |  |  | 2372 |  |  | 2122 |  |  | 2228 |  |  | 2327.5 |  |  | 2213 |  |  | 2256 |  |  | 2158 |  |  | 2176.5 |  |  | 2202 |  |  | 2262.5 |  |  | 2408 |  |  | 2314 |  |  | 2245 |  |  | 2245 |  |  | 2362.5 |  |  | 2216 |  |  | 2143 |  |  | 2309.5 |  |  | 2274 |  |  | 2171 |  |  | 2217.5 |  |  | 2234.5 |  |  | 2235 |  |  | 2141.5 |  |  | 2369 |  |  | 2159.5 |  |  | 2347 |  |  | 2303 |  |  | 2164.5 |  |  | 2305.5 |  |  | 2263 |  |  | 2341 |  |  | 2212 |  |  | 2276 |  |  | 2161 |  |  | 2211 |  |  | 2112 |  |  | 2126 |  |  | 2297.5 |  |  | 2116 |  |  | 2355.5 |  |  | 2188 |  |  | 2294.5 |  |  | 2213.5 |  |  | 2209 |  |  | 2273 |  |  | 2353.5 |  |  | 2229 |  |  | 2302 |  |  | 2336 |  |  | 2247.5 |  |  | 2312 |  |  | 2139.5 |  |  | 2050 |  |  | 2203 |  |  | 2213 |  |  | 2260 |  |  | 2321.5 |  |  | 2195 |  |  | 2232 |  |  | 2288 |  |  | 2126.5 |  |  | 2398 |  |  | 2335 |  |  | 2298 |  |  | 2209 |  |  | 2230.5 |  |  | 2157.5 |  |  | 2339 |  |  | 2355 |  |  | 2256 |  |  | 2339.5 |  |  | 2247 |  |  | 2118 |  |  | 2181 |  |  | 2404.5 |  |  | 2217.5 |  |  | 2243.5 |  |  | 2278 |  |  | 2310 |  |  | 2276 |  |  | 2176.5 |  |  | 2326 |  |  | 2193.5 |  |  | 2124 |  |  | 2139 |  |  | 2252 |  |  | 2236.5 |  |  | 2295.5 |  |  | 2268 |  |  | 2211 |  |  | 2340.5 |  |  | 2274 |  |  | 2201 |  |  | 2294.5 |  |  | 2120 |  |  | 2136 |  |  | 2290.5 |  |  | 2178 |  |  | 2289 |  |  | 2201.5 |  |  | 2405 |  |  | 2185.5 |  |  | 2252 |  |  | 2105.5 |  |  | 2311.5 |  |  | 2112 |  |  | 2318 |  |  | 2330.5 |  |  | 2211.5 |  |  | 2365 |  |  | 2266 |  |  | 2235 |  |  | 2268.5 |  |  | 2329 |  |  | 2055 |  |  | 2177 |  |  | 2345.5 |  |  | 2320.5 |  |  | 2271 |  |  | 2325 |  |  | 2229 |  |  | 2170 |  |  | 2348 |  |  | 2209 |  |  | 2225 |  |  | 2226.5 |  |  | 2442.5 |  |  | 2168.5 |  |  | 2213 |  |  | 2219.5 |  |  | 2243 |  |  | 2232 |  |  | 2272.5 |  |  | 2138.5 |  |  | 2207 |  |  | 2291 |  |  | 2210.5 |  |  | 2214 |  |  | 2279 |  |  | 2117.5 |  |  | 2327.5 |  |  | 2204 |  |  | 2228 |  |  | 2254 |  |  | 2114.5 |  |  | 2160 |  |  | 2153 |  |  | 2251 |  |  | 2311 |  |  | 2387 |  |  | 2146.5 |  |  | 2381 |  |  | 2219 |  |  | 2122 |  |  | 2357.5 |  |  | 2262 |  |  | 2165.5 |  |  | 2162.5 |  |  | 2186 |  |  | 2325 |  |  | 2229.5 |  |  | 2154.5 |  |  | 2145.5 |  |  | 2225.5 |  |  | 2254.5 |  |  | 2266 |  |  | 2232 |  |  | 2254.5 |  |  | 2180.5 |  |  | 2242 |  |  | 2173 |  |  | 2278.5 |  |  | 2420 |  |  | 2209 |  |  | 2132 |  |  | 2306.5 |  |  | 2360 |  |  | 2183.5 |  |  | 2128 |  |  | 2301.5 |  |  | 2459.5 |  |  | 2390.5 |  |  | 2393 |  |  | 2292 |  |  | 2262.5 |  |  | 2249.5 |  |  | 2315 |  |  | 2266 |  |  | 2281.5 |  |  | 2416 |  |  | 2253.5 |  |  | 2222.5 |  |  | 2291 |  |  | 2262 |  |  | 2094.5 |  |  | 2350.5 |  |  | 2264 |  |  | 2195.5 |  |  | 2282.5 |  |  | 2285 |  |  | 2335 |  |  | 2314 |  |  | 2254.5 |  |  | 2318 |  |  | 2193 |  |  | 2291 |  |  | 2189 |  |  | 2259 |  |  | 2204 |  |  | 2398.5 |  |  | 2232.5 |  |  | 2225 |  |  | 2209 |  |  | 2293 |  |  | 2217.5 |  |  | 2151 |  |  | 2413 |  |  | 2244.5 |  |  | 2338.5 |  |  | 2221 |  |  | 2229.5 |  |  | 2339 |  |  | 2119 |  |  | 2270 |  |  | 2348.5 |  |  | 2355 |  |  | 2139.5 |  |  | 2221.5 |  |  | 2115 |  |  | 2243.5 |  |  | 2043.5 |  |  | 2230 |  |  | 2175 |  |  | 2352 |  |  | 2146.5 |  |  | 2115 |  |  | 2168.5 |  |  | 2271.5 |  |  | 2354 |  |  | 2118.5 |  |  | 2151 |  |  | 2226 |  |  | 2206 |  |  | 2187 |  |  | 2126 |  |  | 2328.5 |  |  | 2222 |  |  | 2333 |  |  | 2156 |  |  | 2334 |  |  | 2294.5 |  |  | 2296.5 |  |  | 2237 |  |  | 2306 |  |  | 2244 |  |  | 2248 |  |  | 2269 |  |  | 2168.5 |  |  | 2237 |  |  | 2323.5 |  |  | 2360 |  |  | 2078 |  |  | 2230 |  |  | 2240 |  |  | 2325.5 |  |  | 2229 |  |  | 2258.5 |  |  | 2192 |  |  | 2396 |  |  | 2294 |  |  | 2283.5 |  |  | 2152 |  |  | 2156 |  |  | 2178 |  |  | 2378 |  |  | 2450 |  |  | 2220.5 |  |  | 2354.5 |  |  | 2169 |  |  | 2210.5 |  |  | 2173 |  |  | 2182.5 |  |  | 2224.5 |  |  | 2211.5 |  |  | 2149.5 |  |  | 2104 |  |  | 2409 |  |  | 2151 |  |  | 2147 |  |  | 2224 |  |  | 2334 |  |  | 2236.5 |  |  | 2236.5 |  |  | 2372.5 |  |  | 2265 |  |  | 2315.5 |  |  | 2176.5 |  |  | 2328.5 |  |  | 2181.5 |  |  | 2211 |  |  | 2272.5 |  |  | 2284.5 |  |  | 2353 |  |  | 2126.5 |  |  | 2387.5 |  |  | 2302.5 |  |  | 2443 |  |  | 2260.5 |  |  | 2303 |  |  | 2259 |  |  | 2199.5 |  |  | 2304.5 |  |  | 2282 |  |  | 2305 |  |  | 2105.5 |  |  | 2142.5 |  |  | 2178.5 |  |  | 2317 |  |  | 2173 |  |  | 2246 |  |  | 2333.5 |  |  | 2351.5 |  |  | 2288 |  |  | 2277.5 |  |  | 2106 |  |  | 2216 |  |  | 2280.5 |  |  | 2182.5 |  |  | 2225 |  |  | 2272.5 |  |  | 2305 |  |  | 2179.5 |  |  | 2345.5 |  |  | 2319 |  |  | 2263.5 |  |  | 2342 |  |  | 2228.5 |  |  | 2237 |  |  | 2325 |  |  | 2318 |  |  | 2220.5 |  |  | 2140.5 |  |  | 2311 |  |  | 2223 |  |  | 2162 |  |  | 2193.5 |  |  | 2246.5 |  |  | 2364 |  |  | 2275.5 |  |  | 2219 |  |  | 2126.5 |  |  | 2302.5 |  |  | 2150 |  |  | 2200 |  |  | 2228 |  |  | 2226.5 |  |  | 2181 |  |  | 2288.5 |  |  | 2291 |  |  | 2194.5 |  |  | 2414 |  |  | 2070.5 |  |  | 2227 |  |  | 2266.5 |  |  | 2232.5 |  |  | 2190 |  |  | 2222 |  |  | 2463 |  |  | 2228 |  |  | 2308.5 |  |  | 2145 |  |  | 2218.5 |  |  | 2110 |  |  | 2140 |  |  | 2219 |  |  | 2428 |  |  | 2277 |  |  | 2213 |  |  | 2299 |  |  | 2222.5 |  |  | 2143 |  |  | 2289
79 |  | 2446.5 |  |  | 2391 |  |  | 2378.5 |  |  | 2296 |  |  | 2176.5 |  |  | 2345 |  |  | 2350 |  |  | 2282 |  |  | 2168.5 |  |  | 2169 |  |  | 2235 |  |  | 2393 |  |  | 2375 |  |  | 2454 |  |  | 2220.5 |  |  | 2307.5 |  |  | 2239 |  |  | 2291 |  |  | 2397 |  |  | 2207.5 |  |  | 2336 |  |  | 2354 |  |  | 2180 |  |  | 2298 |  |  | 2279.5 |  |  | 2391 |  |  | 2227 |  |  | 2327 |  |  | 2356 |  |  | 2171 |  |  | 2308 |  |  | 2207.5 |  |  | 2368.5 |  |  | 2270.5 |  |  | 2266 |  |  | 2247.5 |  |  | 2325.5 |  |  | 2386.5 |  |  | 2353 |  |  | 2303 |  |  | 2151.5 |  |  | 2212 |  |  | 2318.5 |  |  | 2248.5 |  |  | 2351.5 |  |  | 2461.5 |  |  | 2448.5 |  |  | 2251 |  |  | 2142 |  |  | 2245.5 |  |  | 2262 |  |  | 2241.5 |  |  | 2199.5 |  |  | 2289 |  |  | 2283 |  |  | 2259 |  |  | 2200 |  |  | 2390 |  |  | 2324 |  |  | 2277.5 |  |  | 2243.5 |  |  | 2248.5 |  |  | 2190 |  |  | 2319 |  |  | 2113 |  |  | 2187.5 |  |  | 2220 |  |  | 2252.5 |  |  | 2338.5 |  |  | 2405.5 |  |  | 2294 |  |  | 2417 |  |  | 2356 |  |  | 2290.5 |  |  | 2380.5 |  |  | 2269.5 |  |  | 2397.5 |  |  | 2318.5 |  |  | 2305.5 |  |  | 2280.5 |  |  | 2212.5 |  |  | 2130 |  |  | 2356 |  |  | 2198 |  |  | 2396.5 |  |  | 2411 |  |  | 2217.5 |  |  | 2358 |  |  | 2287 |  |  | 2296.5 |  |  | 2411.5 |  |  | 2228 |  |  | 2420 |  |  | 2206.5 |  |  | 2446 |  |  | 2249.5 |  |  | 2316.5 |  |  | 2307.5 |  |  | 2194.5 |  |  | 2182.5 |  |  | 2233 |  |  | 2260 |  |  | 2121 |  |  | 2244.5 |  |  | 2254.5 |  |  | 2304.5 |  |  | 2186.5 |  |  | 2244 |  |  | 2223 |  |  | 2297.5 |  |  | 2185 |  |  | 2332.5 |  |  | 2284 |  |  | 2239 |  |  | 2164.5 |  |  | 2275 |  |  | 2263 |  |  | 2185 |  |  | 2305 |  |  | 2237.5 |  |  | 2251.5 |  |  | 2217.5 |  |  | 2373 |  |  | 2260 |  |  | 2205 |  |  | 2231 |  |  | 2189.5 |  |  | 2268 |  |  | 2319.5 |  |  | 2281 |  |  | 2184 |  |  | 2251.5 |  |  | 2192.5 |  |  | 2188 |  |  | 2190.5 |  |  | 2273 |  |  | 2377 |  |  | 2232 |  |  | 2382 |  |  | 2171 |  |  | 2216 |  |  | 2216 |  |  | 2302 |  |  | 2163 |  |  | 2139.5 |  |  | 2231 |  |  | 2158 |  |  | 2405 |  |  | 2307 |  |  | 2283 |  |  | 2157 |  |  | 2248 |  |  | 2288.5 |  |  | 2303 |  |  | 2335.5 |  |  | 2286 |  |  | 2217 |  |  | 2349.5 |  |  | 2276 |  |  | 2377.5 |  |  | 2218 |  |  | 2121 |  |  | 2259.5 |  |  | 2368 |  |  | 2396.5 |  |  | 2362 |  |  | 2139 |  |  | 2338.5 |  |  | 2337.5 |  |  | 2347 |  |  | 2272.5 |  |  | 2235.5 |  |  | 2243 |  |  | 2311 |  |  | 2461.5 |  |  | 2172.5 |  |  | 2347.5 |  |  | 2306 |  |  | 2366 |  |  | 2241 |  |  | 2388 |  |  | 2351 |  |  | 2287.5 |  |  | 2259 |  |  | 2153.5 |  |  | 2302.5 |  |  | 2289 |  |  | 2320 |  |  | 2492.5 |  |  | 2176.5 |  |  | 2225 |  |  | 2320.5 |  |  | 2154.5 |  |  | 2290 |  |  | 2138 |  |  | 2217 |  |  | 2261.5 |  |  | 2373 |  |  | 2248.5 |  |  | 2320.5 |  |  | 2198 |  |  | 2203.5 |  |  | 2183 |  |  | 2256 |  |  | 2327 |  |  | 2360 |  |  | 2105 |  |  | 2377 |  |  | 2401 |  |  | 2278 |  |  | 2409 |  |  | 2225 |  |  | 2281.5 |  |  | 2397.5 |  |  | 2239 |  |  | 2194 |  |  | 2399 |  |  | 2287.5 |  |  | 2383.5 |  |  | 2391.5 |  |  | 2214 |  |  | 2297 |  |  | 2431.5 |  |  | 2294.5 |  |  | 2142.5 |  |  | 2359 |  |  | 2389 |  |  | 2275 |  |  | 2324 |  |  | 2262 |  |  | 2268.5 |  |  | 2203.5 |  |  | 2406 |  |  | 2198 |  |  | 2218 |  |  | 2413 |  |  | 2232 |  |  | 2427.5 |  |  | 2324 |  |  | 2268 |  |  | 2214 |  |  | 2235 |  |  | 2275.5 |  |  | 2409 |  |  | 2245 |  |  | 2230 |  |  | 2371 |  |  | 2361.5 |  |  | 2326 |  |  | 2235 |  |  | 2216 |  |  | 2343.5 |  |  | 2297.5 |  |  | 2402.5 |  |  | 2399 |  |  | 2255 |  |  | 2164 |  |  | 2410 |  |  | 2271 |  |  | 2216.5 |  |  | 2363 |  |  | 2236.5 |  |  | 2295.5 |  |  | 2301.5 |  |  | 2320 |  |  | 2421.5 |  |  | 2157 |  |  | 2188 |  |  | 2232.5 |  |  | 2292.5 |  |  | 2353 |  |  | 2391.5 |  |  | 2382.5 |  |  | 2243 |  |  | 2330 |  |  | 2194.5 |  |  | 2256.5 |  |  | 2428 |  |  | 2297.5 |  |  | 2402 |  |  | 2258 |  |  | 2219.5 |  |  | 2317 |  |  | 2203 |  |  | 2288.5 |  |  | 2286 |  |  | 2443.5 |  |  | 2293 |  |  | 2458 |  |  | 2327 |  |  | 2247 |  |  | 2420.5 |  |  | 2433 |  |  | 2368.5 |  |  | 2125.5 |  |  | 2414.5 |  |  | 2316 |  |  | 2352.5 |  |  | 2428 |  |  | 2324 |  |  | 2101.5 |  |  | 2287.5 |  |  | 2347 |  |  | 2227.5 |  |  | 2424 |  |  | 2203 |  |  | 2411.5 |  |  | 2194 |  |  | 2228.5 |  |  | 2280.5 |  |  | 2310.5 |  |  | 2292 |  |  | 2145 |  |  | 2220 |  |  | 2211.5 |  |  | 2206 |  |  | 2459.5 |  |  | 2295 |  |  | 2286 |  |  | 2211 |  |  | 2303 |  |  | 2370 |  |  | 2313 |  |  | 2282 |  |  | 2455 |  |  | 2319 |  |  | 2275.5 |  |  | 2338 |  |  | 2274 |  |  | 2370.5 |  |  | 2163.5 |  |  | 2290.5 |  |  | 2294.5 |  |  | 2294 |  |  | 2405 |  |  | 2117.5 |  |  | 2431.5 |  |  | 2237.5 |  |  | 2315 |  |  | 2245 |  |  | 2181 |  |  | 2270 |  |  | 2101 |  |  | 2314 |  |  | 2326 |  |  | 2286.5 |  |  | 2302.5 |  |  | 2239 |  |  | 2220.5 |  |  | 2305.5 |  |  | 2217 |  |  | 2310 |  |  | 2212 |  |  | 2321 |  |  | 2212.5 |  |  | 2172.5 |  |  | 2322.5 |  |  | 2223 |  |  | 2219.5 |  |  | 2336 |  |  | 2264 |  |  | 2391 |  |  | 2195.5 |  |  | 2230 |  |  | 2138 |  |  | 2289.5 |  |  | 2181 |  |  | 2356.5 |  |  | 2442 |  |  | 2305.5 |  |  | 2226 |  |  | 2245.5 |  |  | 2300.5 |  |  | 2338 |  |  | 2311 |  |  | 2109 |  |  | 2306 |  |  | 2096.5 |  |  | 2237 |  |  | 2427 |  |  | 2209.5 |  |  | 2401.5 |  |  | 2144.5 |  |  | 2180 |  |  | 2429.5 |  |  | 2307.5 |  |  | 2190.5 |  |  | 2367 |  |  | 2304 |  |  | 2343.5 |  |  | 2329 |  |  | 2441 |  |  | 2341.5 |  |  | 2298 |  |  | 2379 |  |  | 2270 |  |  | 2145 |  |  | 2125.5 |  |  | 2327.5 |  |  | 2212 |  |  | 2384 |  |  | 2334 |  |  | 2238 |  |  | 2239 |  |  | 2232.5 |  |  | 2221.5 |  |  | 2295 |  |  | 2423 |  |  | 2447 |  |  | 2193.5 |  |  | 2520.5 |  |  | 2210 |  |  | 2272 |  |  | 2117 |  |  | 2285.5 |  |  | 2437.5 |  |  | 2249 |  |  | 2157 |  |  | 2331 |  |  | 2299 |  |  | 2252 |  |  | 2411 |  |  | 2223 |  |  | 2443.5 |  |  | 2215 |  |  | 2372 |  |  | 2290 |  |  | 2362.5 |  |  | 2311 |  |  | 2246 |  |  | 2094 |  |  | 2240 |  |  | 2247 |  |  | 2319 |  |  | 2279 |  |  | 2247.5 |  |  | 2245.5 |  |  | 2070.5 |  |  | 2444 |  |  | 2246 |  |  | 2268.5 |  |  | 2110 |  |  | 2213.5 |  |  | 2297.5 |  |  | 2227 |  |  | 2328 |  |  | 2301.5 |  |  | 2312 |  |  | 2352 |  |  | 2328 |  |  | 2314 |  |  | 2342 |  |  | 2218 |  |  | 2235 |  |  | 2285.5 |  |  | 2272 |  |  | 2343 |  |  | 2325 |  |  | 2255 |  |  | 2228 |  |  | 2268 |  |  | 2390 |  |  | 2326 |  |  | 2288 |  |  | 2388.5 |  |  | 2263.5 |  |  | 2314.5 |  |  | 2317.5 |  |  | 2304 |  |  | 2111 |  |  | 2366.5 |  |  | 2205 |  |  | 2241 |  |  | 2175.5 |  |  | 2416.5 |  |  | 2349 |  |  | 2291.5 |  |  | 2286.5 |  |  | 2127 |  |  | 2420 |  |  | 2214 |  |  | 2302 |  |  | 2240.5 |  |  | 2310 |  |  | 2193.5 |  |  | 2214.5 |  |  | 2273 |  |  | 2247 |  |  | 2393.5 |  |  | 2262 |  |  | 2284.5 |  |  | 2289 |  |  | 2298.5 |  |  | 2158.5 |  |  | 2101.5 |  |  | 2388.5 |  |  | 2283.5 |  |  | 2131 |  |  | 2196 |  |  | 2372.5 |  |  | 2294 |  |  | 2184 |  |  | 2267 |  |  | 2431 |  |  | 2374.5 |  |  | 2117 |  |  | 2220 |  |  | 2307 |  |  | 2261.5 |  |  | 2301 |  |  | 2162 |  |  | 2242 |  |  | 2476.5 |  |  | 2332 |  |  | 2108 |  |  | 2309 |  |  | 2398 |  |  | 2517.5 |  |  | 2291 |  |  | 2199.5 |  |  | 2276 |  |  | 2331 |  |  | 2491.5 |  |  | 2314 |  |  | 2264 |  |  | 2213.5 |  |  | 2293 |  |  | 2228 |  |  | 2244 |  |  | 2551.5 |  |  | 2354.5 |  |  | 2326 |  |  | 2191 |  |  | 2274.5 |  |  | 2274.5 |  |  | 2274 |  |  | 2315 |  |  | 2325.5 |  |  | 2478.5 |  |  | 2180.5 |  |  | 2335.5 |  |  | 2242.5 |  |  | 2481 |  |  | 2215.5 |  |  | 2393 |  |  | 2282 |  |  | 2404 |  |  | 2406 |  |  | 2292.5 |  |  | 2284 |  |  | 2218 |  |  | 2311.5 |  |  | 2335.5 |  |  | 2186 |  |  | 2342.5 |  |  | 2250.5 |  |  | 2378 |  |  | 2202 |  |  | 2255 |  |  | 2272.5 |  |  | 2359 |  |  | 2387.5 |  |  | 2356 |  |  | 2301 |  |  | 2532.5 |  |  | 2215 |  |  | 2350 |  |  | 2218 |  |  | 2361 |  |  | 2371 |  |  | 2316 |  |  | 2331 |  |  | 2295 |  |  | 2201.5 |  |  | 2257.5 |  |  | 2230 |  |  | 2293.5 |  |  | 2108.5 |  |  | 2202 |  |  | 2220 |  |  | 2376 |  |  | 2372.5 |  |  | 2153.5 |  |  | 2340 |  |  | 2326 |  |  | 2175 |  |  | 2170 |  |  | 2254 |  |  | 2227 |  |  | 2306 |  |  | 2153.5 |  |  | 2382 |  |  | 2333 |  |  | 2384 |  |  | 2171 |  |  | 2155 |  |  | 2255.5 |  |  | 2430.5 |  |  | 2111.5 |  |  | 2189 |  |  | 2181 |  |  | 2198.5 |  |  | 2363.5 |  |  | 2339.5 |  |  | 2186 |  |  | 2383.5 |  |  | 2326.5 |  |  | 2400 |  |  | 2336.5 |  |  | 2309.5 |  |  | 2266 |  |  | 2162 |  |  | 2246 |  |  | 2366 |  |  | 2206 |  |  | 2127 |  |  | 2330 |  |  | 2419 |  |  | 2161 |  |  | 2252 |  |  | 2356.5 |  |  | 2228 |  |  | 2282 |  |  | 2205 |  |  | 2197.5 |  |  | 2217 |  |  | 2291.5 |  |  | 2423 |  |  | 2353 |  |  | 2274 |  |  | 2292 |  |  | 2388.5 |  |  | 2245 |  |  | 2169 |  |  | 2348.5 |  |  | 2313 |  |  | 2195 |  |  | 2232.5 |  |  | 2258.5 |  |  | 2256 |  |  | 2167.5 |  |  | 2395 |  |  | 2185.5 |  |  | 2394 |  |  | 2342 |  |  | 2179.5 |  |  | 2344.5 |  |  | 2287 |  |  | 2367 |  |  | 2259 |  |  | 2315 |  |  | 2200 |  |  | 2250 |  |  | 2127 |  |  | 2155 |  |  | 2344.5 |  |  | 2137 |  |  | 2384.5 |  |  | 2212 |  |  | 2323.5 |  |  | 2239.5 |  |  | 2248 |  |  | 2320 |  |  | 2368.5 |  |  | 2276 |  |  | 2326 |  |  | 2365 |  |  | 2262.5 |  |  | 2327 |  |  | 2178.5 |  |  | 2097 |  |  | 2218 |  |  | 2234 |  |  | 2281 |  |  | 2360.5 |  |  | 2224 |  |  | 2271 |  |  | 2335 |  |  | 2165.5 |  |  | 2437 |  |  | 2382 |  |  | 2327 |  |  | 2248 |  |  | 2259.5 |  |  | 2172.5 |  |  | 2386 |  |  | 2402 |  |  | 2285 |  |  | 2354.5 |  |  | 2268 |  |  | 2147 |  |  | 2202 |  |  | 2451.5 |  |  | 2232.5 |  |  | 2264.5 |  |  | 2293 |  |  | 2357 |  |  | 2315 |  |  | 2191.5 |  |  | 2365 |  |  | 2222.5 |  |  | 2150 |  |  | 2178 |  |  | 2291 |  |  | 2260.5 |  |  | 2324.5 |  |  | 2297 |  |  | 2240 |  |  | 2387.5 |  |  | 2313 |  |  | 2227 |  |  | 2333.5 |  |  | 2149 |  |  | 2175 |  |  | 2319.5 |  |  | 2193 |  |  | 2304 |  |  | 2216.5 |  |  | 2420 |  |  | 2206.5 |  |  | 2281 |  |  | 2120.5 |  |  | 2335.5 |  |  | 2151 |  |  | 2347 |  |  | 2369.5 |  |  | 2235.5 |  |  | 2380 |  |  | 2290 |  |  | 2274 |  |  | 2315.5 |  |  | 2358 |  |  | 2094 |  |  | 2206 |  |  | 2371.5 |  |  | 2335.5 |  |  | 2310 |  |  | 2354 |  |  | 2255 |  |  | 2217 |  |  | 2395 |  |  | 2256 |  |  | 2246 |  |  | 2252.5 |  |  | 2463.5 |  |  | 2215.5 |  |  | 2228 |  |  | 2248.5 |  |  | 2282 |  |  | 2253 |  |  | 2311.5 |  |  | 2153.5 |  |  | 2236 |  |  | 2330 |  |  | 2225.5 |  |  | 2238 |  |  | 2318 |  |  | 2143.5 |  |  | 2366.5 |  |  | 2228 |  |  | 2252 |  |  | 2269 |  |  | 2153.5 |  |  | 2181 |  |  | 2179 |  |  | 2275 |  |  | 2332 |  |  | 2402 |  |  | 2193.5 |  |  | 2420 |  |  | 2248 |  |  | 2148 |  |  | 2378.5 |  |  | 2301 |  |  | 2212.5 |  |  | 2177.5 |  |  | 2212 |  |  | 2346 |  |  | 2255.5 |  |  | 2193.5 |  |  | 2184.5 |  |  | 2249.5 |  |  | 2280.5 |  |  | 2305 |  |  | 2261 |  |  | 2293.5 |  |  | 2227.5 |  |  | 2268 |  |  | 2199 |  |  | 2299.5 |  |  | 2467 |  |  | 2238 |  |  | 2171 |  |  | 2353.5 |  |  | 2386 |  |  | 2204.5 |  |  | 2167 |  |  | 2325.5 |  |  | 2485.5 |  |  | 2414.5 |  |  | 2417 |  |  | 2313 |  |  | 2277.5 |  |  | 2275.5 |  |  | 2339 |  |  | 2313 |  |  | 2307.5 |  |  | 2455 |  |  | 2279.5 |  |  | 2248.5 |  |  | 2317 |  |  | 2277 |  |  | 2133.5 |  |  | 2365.5 |  |  | 2303 |  |  | 2234.5 |  |  | 2306.5 |  |  | 2309 |  |  | 2356 |  |  | 2340 |  |  | 2301.5 |  |  | 2365 |  |  | 2222 |  |  | 2315 |  |  | 2228 |  |  | 2298 |  |  | 2251 |  |  | 2427.5 |  |  | 2271.5 |  |  | 2272 |  |  | 2230 |  |  | 2308 |  |  | 2232.5 |  |  | 2198 |  |  | 2428 |  |  | 2270.5 |  |  | 2359.5 |  |  | 2260 |  |  | 2268.5 |  |  | 2365 |  |  | 2140 |  |  | 2291 |  |  | 2372.5 |  |  | 2381 |  |  | 2186.5 |  |  | 2250.5 |  |  | 2139 |  |  | 2282.5 |  |  | 2067.5 |  |  | 2277 |  |  | 2199 |  |  | 2373 |  |  | 2161.5 |  |  | 2162 |  |  | 2197.5 |  |  | 2310.5 |  |  | 2378 |  |  | 2157.5 |  |  | 2180 |  |  | 2255 |  |  | 2245 |  |  | 2208 |  |  | 2141 |  |  | 2367.5 |  |  | 2243 |  |  | 2380 |  |  | 2195 |  |  | 2358 |  |  | 2315.5 |  |  | 2322.5 |  |  | 2266 |  |  | 2353 |  |  | 2265 |  |  | 2277 |  |  | 2316 |  |  | 2189.5 |  |  | 2276 |  |  | 2347.5 |  |  | 2399 |  |  | 2102 |  |  | 2245 |  |  | 2279 |  |  | 2349.5 |  |  | 2258 |  |  | 2279.5 |  |  | 2218 |  |  | 2422 |  |  | 2333 |  |  | 2312.5 |  |  | 2173 |  |  | 2177 |  |  | 2217 |  |  | 2425 |  |  | 2489 |  |  | 2267.5 |  |  | 2375.5 |  |  | 2190 |  |  | 2234.5 |  |  | 2220 |  |  | 2206.5 |  |  | 2253.5 |  |  | 2235.5 |  |  | 2188.5 |  |  | 2143 |  |  | 2430 |  |  | 2198 |  |  | 2176 |  |  | 2263 |  |  | 2349 |  |  | 2275.5 |  |  | 2257.5 |  |  | 2411.5 |  |  | 2289 |  |  | 2354.5 |  |  | 2223.5 |  |  | 2367.5 |  |  | 2196.5 |  |  | 2258 |  |  | 2298.5 |  |  | 2323.5 |  |  | 2400 |  |  | 2155.5 |  |  | 2426.5 |  |  | 2317.5 |  |  | 2464 |  |  | 2307.5 |  |  | 2350 |  |  | 2283 |  |  | 2223.5 |  |  | 2328.5 |  |  | 2321 |  |  | 2352 |  |  | 2131.5 |  |  | 2166.5 |  |  | 2217.5 |  |  | 2346 |  |  | 2202 |  |  | 2272 |  |  | 2362.5 |  |  | 2380.5 |  |  | 2309 |  |  | 2316.5 |  |  | 2121 |  |  | 2242 |  |  | 2319.5 |  |  | 2197.5 |  |  | 2249 |  |  | 2287.5 |  |  | 2352 |  |  | 2205.5 |  |  | 2366.5 |  |  | 2340 |  |  | 2287.5 |  |  | 2366 |  |  | 2267.5 |  |  | 2263 |  |  | 2340 |  |  | 2342 |  |  | 2244.5 |  |  | 2179.5 |  |  | 2332 |  |  | 2238 |  |  | 2188 |  |  | 2214.5 |  |  | 2285.5 |  |  | 2403 |  |  | 2301.5 |  |  | 2245 |  |  | 2147.5 |  |  | 2323.5 |  |  | 2176 |  |  | 2226 |  |  | 2275 |  |  | 2265.5 |  |  | 2202 |  |  | 2317.5 |  |  | 2312 |  |  | 2220.5 |  |  | 2461 |  |  | 2109.5 |  |  | 2251 |  |  | 2305.5 |  |  | 2253.5 |  |  | 2229 |  |  | 2261 |  |  | 2492 |  |  | 2249 |  |  | 2347.5 |  |  | 2184 |  |  | 2233.5 |  |  | 2149 |  |  | 2155 |  |  | 2258 |  |  | 2454 |  |  | 2306 |  |  | 2260 |  |  | 2346 |  |  | 2251.5 |  |  | 2190 |  |  | 2336
80 |  | 2475.5 |  |  | 2412 |  |  | 2399.5 |  |  | 2343 |  |  | 2205.5 |  |  | 2392 |  |  | 2389 |  |  | 2311 |  |  | 2189.5 |  |  | 2193 |  |  | 2256 |  |  | 2440 |  |  | 2414 |  |  | 2501 |  |  | 2235.5 |  |  | 2346.5 |  |  | 2268 |  |  | 2330 |  |  | 2444 |  |  | 2222.5 |  |  | 2375 |  |  | 2380 |  |  | 2206 |  |  | 2324 |  |  | 2318.5 |  |  | 2406 |  |  | 2242 |  |  | 2348 |  |  | 2403 |  |  | 2186 |  |  | 2334 |  |  | 2246.5 |  |  | 2392.5 |  |  | 2294.5 |  |  | 2281 |  |  | 2286.5 |  |  | 2351.5 |  |  | 2401.5 |  |  | 2400 |  |  | 2329 |  |  | 2175.5 |  |  | 2241 |  |  | 2339.5 |  |  | 2269.5 |  |  | 2390.5 |  |  | 2485.5 |  |  | 2474.5 |  |  | 2275 |  |  | 2163 |  |  | 2260.5 |  |  | 2277 |  |  | 2267.5 |  |  | 2223.5 |  |  | 2313 |  |  | 2304 |  |  | 2280 |  |  | 2224 |  |  | 2416 |  |  | 2363 |  |  | 2306.5 |  |  | 2282.5 |  |  | 2277.5 |  |  | 2214 |  |  | 2343 |  |  | 2142 |  |  | 2226.5 |  |  | 2259 |  |  | 2267.5 |  |  | 2385.5 |  |  | 2434.5 |  |  | 2320 |  |  | 2443 |  |  | 2385 |  |  | 2311.5 |  |  | 2406.5 |  |  | 2308.5 |  |  | 2436.5 |  |  | 2347.5 |  |  | 2344.5 |  |  | 2319.5 |  |  | 2233.5 |  |  | 2156 |  |  | 2403 |  |  | 2245 |  |  | 2411.5 |  |  | 2435 |  |  | 2241.5 |  |  | 2379 |  |  | 2316 |  |  | 2311.5 |  |  | 2437.5 |  |  | 2257 |  |  | 2441 |  |  | 2235.5 |  |  | 2470 |  |  | 2264.5 |  |  | 2337.5 |  |  | 2346.5 |  |  | 2233.5 |  |  | 2211.5 |  |  | 2280 |  |  | 2299 |  |  | 2160 |  |  | 2291.5 |  |  | 2301.5 |  |  | 2325.5 |  |  | 2207.5 |  |  | 2291 |  |  | 2262 |  |  | 2344.5 |  |  | 2232 |  |  | 2356.5 |  |  | 2323 |  |  | 2260 |  |  | 2203.5 |  |  | 2314 |  |  | 2310 |  |  | 2214 |  |  | 2344 |  |  | 2284.5 |  |  | 2290.5 |  |  | 2243.5 |  |  | 2412 |  |  | 2299 |  |  | 2226 |  |  | 2278 |  |  | 2236.5 |  |  | 2294 |  |  | 2343.5 |  |  | 2307 |  |  | 2205 |  |  | 2290.5 |  |  | 2239.5 |  |  | 2212 |  |  | 2229.5 |  |  | 2294 |  |  | 2401 |  |  | 2258 |  |  | 2421 |  |  | 2210 |  |  | 2242 |  |  | 2237 |  |  | 2323 |  |  | 2202 |  |  | 2186.5 |  |  | 2252 |  |  | 2197 |  |  | 2434 |  |  | 2333 |  |  | 2298 |  |  | 2181 |  |  | 2272 |  |  | 2312.5 |  |  | 2327 |  |  | 2350.5 |  |  | 2333 |  |  | 2238 |  |  | 2375.5 |  |  | 2323 |  |  | 2403.5 |  |  | 2257 |  |  | 2145 |  |  | 2283.5 |  |  | 2392 |  |  | 2417.5 |  |  | 2388 |  |  | 2186 |  |  | 2362.5 |  |  | 2366.5 |  |  | 2368 |  |  | 2319.5 |  |  | 2274.5 |  |  | 2264 |  |  | 2326 |  |  | 2482.5 |  |  | 2187.5 |  |  | 2386.5 |  |  | 2332 |  |  | 2387 |  |  | 2280 |  |  | 2414 |  |  | 2390 |  |  | 2302.5 |  |  | 2285 |  |  | 2192.5 |  |  | 2326.5 |  |  | 2304 |  |  | 2359 |  |  | 2539.5 |  |  | 2202.5 |  |  | 2272 |  |  | 2341.5 |  |  | 2193.5 |  |  | 2314 |  |  | 2167 |  |  | 2246 |  |  | 2276.5 |  |  | 2397 |  |  | 2287.5 |  |  | 2367.5 |  |  | 2219 |  |  | 2250.5 |  |  | 2212 |  |  | 2271 |  |  | 2366 |  |  | 2381 |  |  | 2126 |  |  | 2406 |  |  | 2425 |  |  | 2299 |  |  | 2435 |  |  | 2249 |  |  | 2296.5 |  |  | 2444.5 |  |  | 2263 |  |  | 2220 |  |  | 2428 |  |  | 2326.5 |  |  | 2398.5 |  |  | 2430.5 |  |  | 2238 |  |  | 2323 |  |  | 2446.5 |  |  | 2341.5 |  |  | 2168.5 |  |  | 2383 |  |  | 2404 |  |  | 2314 |  |  | 2371 |  |  | 2291 |  |  | 2297.5 |  |  | 2229.5 |  |  | 2430 |  |  | 2237 |  |  | 2233 |  |  | 2434 |  |  | 2256 |  |  | 2442.5 |  |  | 2363 |  |  | 2289 |  |  | 2235 |  |  | 2282 |  |  | 2299.5 |  |  | 2435 |  |  | 2292 |  |  | 2245 |  |  | 2395 |  |  | 2376.5 |  |  | 2355 |  |  | 2274 |  |  | 2255 |  |  | 2372.5 |  |  | 2318.5 |  |  | 2426.5 |  |  | 2420 |  |  | 2270 |  |  | 2193 |  |  | 2449 |  |  | 2300 |  |  | 2237.5 |  |  | 2389 |  |  | 2262.5 |  |  | 2342.5 |  |  | 2340.5 |  |  | 2349 |  |  | 2436.5 |  |  | 2181 |  |  | 2217 |  |  | 2271.5 |  |  | 2331.5 |  |  | 2392 |  |  | 2406.5 |  |  | 2421.5 |  |  | 2264 |  |  | 2354 |  |  | 2241.5 |  |  | 2277.5 |  |  | 2449 |  |  | 2344.5 |  |  | 2426 |  |  | 2297 |  |  | 2243.5 |  |  | 2343 |  |  | 2242 |  |  | 2317.5 |  |  | 2315 |  |  | 2482.5 |  |  | 2308 |  |  | 2497 |  |  | 2356 |  |  | 2276 |  |  | 2446.5 |  |  | 2454 |  |  | 2407.5 |  |  | 2172.5 |  |  | 2435.5 |  |  | 2363 |  |  | 2373.5 |  |  | 2449 |  |  | 2363 |  |  | 2148.5 |  |  | 2308.5 |  |  | 2371 |  |  | 2274.5 |  |  | 2450 |  |  | 2224 |  |  | 2450.5 |  |  | 2233 |  |  | 2275.5 |  |  | 2327.5 |  |  | 2336.5 |  |  | 2316 |  |  | 2169 |  |  | 2235 |  |  | 2235.5 |  |  | 2245 |  |  | 2483.5 |  |  | 2321 |  |  | 2315 |  |  | 2232 |  |  | 2350 |  |  | 2409 |  |  | 2334 |  |  | 2306 |  |  | 2476 |  |  | 2340 |  |  | 2314.5 |  |  | 2385 |  |  | 2298 |  |  | 2394.5 |  |  | 2202.5 |  |  | 2314.5 |  |  | 2315.5 |  |  | 2333 |  |  | 2444 |  |  | 2132.5 |  |  | 2470.5 |  |  | 2252.5 |  |  | 2336 |  |  | 2284 |  |  | 2196 |  |  | 2299 |  |  | 2140 |  |  | 2353 |  |  | 2341 |  |  | 2333.5 |  |  | 2349.5 |  |  | 2260 |  |  | 2244.5 |  |  | 2352.5 |  |  | 2264 |  |  | 2334 |  |  | 2251 |  |  | 2368 |  |  | 2233.5 |  |  | 2211.5 |  |  | 2346.5 |  |  | 2244 |  |  | 2266.5 |  |  | 2383 |  |  | 2285 |  |  | 2420 |  |  | 2216.5 |  |  | 2269 |  |  | 2167 |  |  | 2328.5 |  |  | 2202 |  |  | 2395.5 |  |  | 2468 |  |  | 2334.5 |  |  | 2255 |  |  | 2271.5 |  |  | 2339.5 |  |  | 2377 |  |  | 2332 |  |  | 2130 |  |  | 2327 |  |  | 2135.5 |  |  | 2263 |  |  | 2453 |  |  | 2233.5 |  |  | 2425.5 |  |  | 2168.5 |  |  | 2219 |  |  | 2450.5 |  |  | 2354.5 |  |  | 2237.5 |  |  | 2396 |  |  | 2343 |  |  | 2390.5 |  |  | 2350 |  |  | 2480 |  |  | 2356.5 |  |  | 2322 |  |  | 2418 |  |  | 2291 |  |  | 2192 |  |  | 2146.5 |  |  | 2353.5 |  |  | 2251 |  |  | 2431 |  |  | 2355 |  |  | 2253 |  |  | 2278 |  |  | 2256.5 |  |  | 2236.5 |  |  | 2324 |  |  | 2447 |  |  | 2494 |  |  | 2232.5 |  |  | 2546.5 |  |  | 2239 |  |  | 2301 |  |  | 2132 |  |  | 2324.5 |  |  | 2458.5 |  |  | 2288 |  |  | 2178 |  |  | 2352 |  |  | 2325 |  |  | 2291 |  |  | 2437 |  |  | 2270 |  |  | 2472.5 |  |  | 2262 |  |  | 2411 |  |  | 2337 |  |  | 2391.5 |  |  | 2350 |  |  | 2267 |  |  | 2123 |  |  | 2255 |  |  | 2286 |  |  | 2340 |  |  | 2305 |  |  | 2268.5 |  |  | 2266.5 |  |  | 2109.5 |  |  | 2483 |  |  | 2267 |  |  | 2307.5 |  |  | 2134 |  |  | 2228.5 |  |  | 2326.5 |  |  | 2274 |  |  | 2352 |  |  | 2340.5 |  |  | 2327 |  |  | 2381 |  |  | 2367 |  |  | 2329 |  |  | 2389 |  |  | 2247 |  |  | 2261 |  |  | 2314.5 |  |  | 2301 |  |  | 2372 |  |  | 2364 |  |  | 2281 |  |  | 2275 |  |  | 2297 |  |  | 2416 |  |  | 2352 |  |  | 2314 |  |  | 2427.5 |  |  | 2310.5 |  |  | 2335.5 |  |  | 2341.5 |  |  | 2351 |  |  | 2140 |  |  | 2413.5 |  |  | 2226 |  |  | 2280 |  |  | 2204.5 |  |  | 2437.5 |  |  | 2370 |  |  | 2320.5 |  |  | 2325.5 |  |  | 2174 |  |  | 2446 |  |  | 2253 |  |  | 2331 |  |  | 2279.5 |  |  | 2357 |  |  | 2240.5 |  |  | 2253.5 |  |  | 2297 |  |  | 2286 |  |  | 2417.5 |  |  | 2283 |  |  | 2323.5 |  |  | 2328 |  |  | 2319.5 |  |  | 2179.5 |  |  | 2140.5 |  |  | 2435.5 |  |  | 2330.5 |  |  | 2157 |  |  | 2235 |  |  | 2387.5 |  |  | 2318 |  |  | 2208 |  |  | 2306 |  |  | 2460 |  |  | 2413.5 |  |  | 2138 |  |  | 2249 |  |  | 2354 |  |  | 2282.5 |  |  | 2322 |  |  | 2201 |  |  | 2281 |  |  | 2500.5 |  |  | 2371 |  |  | 2123 |  |  | 2356 |  |  | 2424 |  |  | 2541.5 |  |  | 2320 |  |  | 2220.5 |  |  | 2300 |  |  | 2352 |  |  | 2515.5 |  |  | 2340 |  |  | 2285 |  |  | 2252.5 |  |  | 2314 |  |  | 2243 |  |  | 2270 |  |  | 2598.5 |  |  | 2380.5 |  |  | 2365 |  |  | 2230 |  |  | 2298.5 |  |  | 2313.5 |  |  | 2303 |  |  | 2354 |  |  | 2364.5 |  |  | 2502.5 |  |  | 2227.5 |  |  | 2356.5 |  |  | 2281.5 |  |  | 2505 |  |  | 2241.5 |  |  | 2432 |  |  | 2297 |  |  | 2430 |  |  | 2435 |  |  | 2331.5 |  |  | 2313 |  |  | 2247 |  |  | 2326.5 |  |  | 2382.5 |  |  | 2215 |  |  | 2371.5 |  |  | 2279.5 |  |  | 2393 |  |  | 2228 |  |  | 2284 |  |  | 2311.5 |  |  | 2380 |  |  | 2411.5 |  |  | 2395 |  |  | 2340 |  |  | 2571.5 |  |  | 2241 |  |  | 2376 |  |  | 2244 |  |  | 2382 |  |  | 2418 |  |  | 2340 |  |  | 2360 |  |  | 2316 |  |  | 2227.5 |  |  | 2272.5 |  |  | 2259 |  |  | 2332.5 |  |  | 2134.5 |  |  | 2217 |  |  | 2259 |  |  | 2405 |  |  | 2419.5 |  |  | 2200.5 |  |  | 2387 |  |  | 2355 |  |  | 2214 |  |  | 2209 |  |  | 2293 |  |  | 2242 |  |  | 2345 |  |  | 2200.5 |  |  | 2397 |  |  | 2372 |  |  | 2405 |  |  | 2218 |  |  | 2202 |  |  | 2281.5 |  |  | 2477.5 |  |  | 2140.5 |  |  | 2218 |  |  | 2196 |  |  | 2224.5 |  |  | 2378.5 |  |  | 2386.5 |  |  | 2201 |  |  | 2404.5 |  |  | 2365.5 |  |  | 2415 |  |  | 2351.5 |  |  | 2356.5 |  |  | 2281 |  |  | 2186 |  |  | 2270 |  |  | 2387 |  |  | 2227 |  |  | 2151 |  |  | 2369 |  |  | 2440 |  |  | 2176 |  |  | 2299 |  |  | 2395.5 |  |  | 2254 |  |  | 2303 |  |  | 2244 |  |  | 2212.5 |  |  | 2243 |  |  | 2317.5 |  |  | 2462 |  |  | 2382 |  |  | 2300 |  |  | 2331 |  |  | 2435.5 |  |  | 2284 |  |  | 2190 |  |  | 2377.5 |  |  | 2334 |  |  | 2219 |  |  | 2256.5 |  |  | 2284.5 |  |  | 2277 |  |  | 2196.5 |  |  | 2410 |  |  | 2224.5 |  |  | 2423 |  |  | 2363 |  |  | 2226.5 |  |  | 2383.5 |  |  | 2313 |  |  | 2391 |  |  | 2306 |  |  | 2336 |  |  | 2239 |  |  | 2279 |  |  | 2166 |  |  | 2170 |  |  | 2373.5 |  |  | 2184 |  |  | 2423.5 |  |  | 2233 |  |  | 2344.5 |  |  | 2254.5 |  |  | 2274 |  |  | 2349 |  |  | 2397.5 |  |  | 2297 |  |  | 2347 |  |  | 2404 |  |  | 2301.5 |  |  | 2348 |  |  | 2204.5 |  |  | 2126 |  |  | 2233 |  |  | 2255 |  |  | 2307 |  |  | 2381.5 |  |  | 2263 |  |  | 2292 |  |  | 2374 |  |  | 2204.5 |  |  | 2463 |  |  | 2408 |  |  | 2353 |  |  | 2287 |  |  | 2298.5 |  |  | 2187.5 |  |  | 2433 |  |  | 2449 |  |  | 2324 |  |  | 2378.5 |  |  | 2307 |  |  | 2171 |  |  | 2226 |  |  | 2490.5 |  |  | 2279.5 |  |  | 2303.5 |  |  | 2332 |  |  | 2386 |  |  | 2354 |  |  | 2230.5 |  |  | 2404 |  |  | 2269.5 |  |  | 2176 |  |  | 2217 |  |  | 2315 |  |  | 2275.5 |  |  | 2371.5 |  |  | 2344 |  |  | 2279 |  |  | 2408.5 |  |  | 2334 |  |  | 2253 |  |  | 2357.5 |  |  | 2175 |  |  | 2199 |  |  | 2345.5 |  |  | 2208 |  |  | 2343 |  |  | 2255.5 |  |  | 2441 |  |  | 2221.5 |  |  | 2320 |  |  | 2141.5 |  |  | 2382.5 |  |  | 2172 |  |  | 2376 |  |  | 2408.5 |  |  | 2274.5 |  |  | 2406 |  |  | 2316 |  |  | 2289 |  |  | 2354.5 |  |  | 2387 |  |  | 2120 |  |  | 2230 |  |  | 2392.5 |  |  | 2364.5 |  |  | 2336 |  |  | 2375 |  |  | 2281 |  |  | 2256 |  |  | 2424 |  |  | 2282 |  |  | 2293 |  |  | 2299.5 |  |  | 2487.5 |  |  | 2236.5 |  |  | 2254 |  |  | 2263.5 |  |  | 2321 |  |  | 2279 |  |  | 2326.5 |  |  | 2192.5 |  |  | 2262 |  |  | 2351 |  |  | 2272.5 |  |  | 2259 |  |  | 2347 |  |  | 2169.5 |  |  | 2390.5 |  |  | 2275 |  |  | 2276 |  |  | 2308 |  |  | 2168.5 |  |  | 2220 |  |  | 2200 |  |  | 2290 |  |  | 2356 |  |  | 2441 |  |  | 2217.5 |  |  | 2435 |  |  | 2272 |  |  | 2195 |  |  | 2417.5 |  |  | 2340 |  |  | 2227.5 |  |  | 2216.5 |  |  | 2251 |  |  | 2385 |  |  | 2302.5 |  |  | 2217.5 |  |  | 2199.5 |  |  | 2278.5 |  |  | 2304.5 |  |  | 2331 |  |  | 2287 |  |  | 2314.5 |  |  | 2248.5 |  |  | 2294 |  |  | 2238 |  |  | 2328.5 |  |  | 2488 |  |  | 2267 |  |  | 2210 |  |  | 2379.5 |  |  | 2415 |  |  | 2243.5 |  |  | 2196 |  |  | 2354.5 |  |  | 2511.5 |  |  | 2438.5 |  |  | 2443 |  |  | 2339 |  |  | 2316.5 |  |  | 2296.5 |  |  | 2363 |  |  | 2339 |  |  | 2354.5 |  |  | 2484 |  |  | 2326.5 |  |  | 2295.5 |  |  | 2332 |  |  | 2306 |  |  | 2172.5 |  |  | 2380.5 |  |  | 2332 |  |  | 2273.5 |  |  | 2345.5 |  |  | 2338 |  |  | 2377 |  |  | 2379 |  |  | 2316.5 |  |  | 2386 |  |  | 2237 |  |  | 2341 |  |  | 2257 |  |  | 2337 |  |  | 2272 |  |  | 2474.5 |  |  | 2310.5 |  |  | 2311 |  |  | 2251 |  |  | 2347 |  |  | 2258.5 |  |  | 2237 |  |  | 2443 |  |  | 2294.5 |  |  | 2398.5 |  |  | 2275 |  |  | 2292.5 |  |  | 2404 |  |  | 2155 |  |  | 2338 |  |  | 2401.5 |  |  | 2420 |  |  | 2207.5 |  |  | 2276.5 |  |  | 2160 |  |  | 2306.5 |  |  | 2093.5 |  |  | 2316 |  |  | 2214 |  |  | 2394 |  |  | 2200.5 |  |  | 2191 |  |  | 2236.5 |  |  | 2349.5 |  |  | 2417 |  |  | 2178.5 |  |  | 2209 |  |  | 2270 |  |  | 2260 |  |  | 2247 |  |  | 2167 |  |  | 2388.5 |  |  | 2272 |  |  | 2427 |  |  | 2242 |  |  | 2405 |  |  | 2336.5 |  |  | 2351.5 |  |  | 2295 |  |  | 2400 |  |  | 2304 |  |  | 2306 |  |  | 2331 |  |  | 2204.5 |  |  | 2297 |  |  | 2386.5 |  |  | 2438 |  |  | 2149 |  |  | 2284 |  |  | 2308 |  |  | 2364.5 |  |  | 2273 |  |  | 2326.5 |  |  | 2242 |  |  | 2448 |  |  | 2348 |  |  | 2341.5 |  |  | 2197 |  |  | 2198 |  |  | 2264 |  |  | 2449 |  |  | 2536 |  |  | 2291.5 |  |  | 2401.5 |  |  | 2229 |  |  | 2260.5 |  |  | 2259 |  |  | 2232.5 |  |  | 2292.5 |  |  | 2274.5 |  |  | 2214.5 |  |  | 2182 |  |  | 2459 |  |  | 2237 |  |  | 2205 |  |  | 2289 |  |  | 2388 |  |  | 2290.5 |  |  | 2278.5 |  |  | 2450.5 |  |  | 2304 |  |  | 2401.5 |  |  | 2238.5 |  |  | 2406.5 |  |  | 2225.5 |  |  | 2305 |  |  | 2337.5 |  |  | 2347.5 |  |  | 2429 |  |  | 2176.5 |  |  | 2473.5 |  |  | 2343.5 |  |  | 2479 |  |  | 2331.5 |  |  | 2389 |  |  | 2312 |  |  | 2262.5 |  |  | 2357.5 |  |  | 2345 |  |  | 2391 |  |  | 2146.5 |  |  | 2187.5 |  |  | 2264.5 |  |  | 2361 |  |  | 2231 |  |  | 2311 |  |  | 2401.5 |  |  | 2419.5 |  |  | 2338 |  |  | 2355.5 |  |  | 2136 |  |  | 2263 |  |  | 2340.5 |  |  | 2218.5 |  |  | 2264 |  |  | 2302.5 |  |  | 2391 |  |  | 2220.5 |  |  | 2413.5 |  |  | 2379 |  |  | 2326.5 |  |  | 2395 |  |  | 2282.5 |  |  | 2302 |  |  | 2366 |  |  | 2381 |  |  | 2270.5 |  |  | 2194.5 |  |  | 2361 |  |  | 2259 |  |  | 2227 |  |  | 2253.5 |  |  | 2324.5 |  |  | 2427 |  |  | 2340.5 |  |  | 2284 |  |  | 2186.5 |  |  | 2344.5 |  |  | 2223 |  |  | 2250 |  |  | 2290 |  |  | 2312.5 |  |  | 2228 |  |  | 2341.5 |  |  | 2341 |  |  | 2249.5 |  |  | 2490 |  |  | 2156.5 |  |  | 2266 |  |  | 2344.5 |  |  | 2277.5 |  |  | 2253 |  |  | 2290 |  |  | 2516 |  |  | 2296 |  |  | 2376.5 |  |  | 2223 |  |  | 2257.5 |  |  | 2188 |  |  | 2194 |  |  | 2297 |  |  | 2469 |  |  | 2335 |  |  | 2281 |  |  | 2361 |  |  | 2272.5 |  |  | 2229 |  |  | 2375
81 |  | 2514.5 |  |  | 2427 |  |  | 2420.5 |  |  | 2390 |  |  | 2244.5 |  |  | 2431 |  |  | 2436 |  |  | 2350 |  |  | 2228.5 |  |  | 2214 |  |  | 2271 |  |  | 2479 |  |  | 2429 |  |  | 2527 |  |  | 2261.5 |  |  | 2385.5 |  |  | 2307 |  |  | 2369 |  |  | 2468 |  |  | 2261.5 |  |  | 2414 |  |  | 2409 |  |  | 2245 |  |  | 2339 |  |  | 2344.5 |  |  | 2445 |  |  | 2281 |  |  | 2387 |  |  | 2442 |  |  | 2201 |  |  | 2349 |  |  | 2267.5 |  |  | 2416.5 |  |  | 2341.5 |  |  | 2320 |  |  | 2325.5 |  |  | 2377.5 |  |  | 2422.5 |  |  | 2429 |  |  | 2368 |  |  | 2199.5 |  |  | 2280 |  |  | 2365.5 |  |  | 2295.5 |  |  | 2405.5 |  |  | 2511.5 |  |  | 2498.5 |  |  | 2299 |  |  | 2178 |  |  | 2286.5 |  |  | 2292 |  |  | 2296.5 |  |  | 2247.5 |  |  | 2334 |  |  | 2333 |  |  | 2295 |  |  | 2245 |  |  | 2431 |  |  | 2387 |  |  | 2345.5 |  |  | 2308.5 |  |  | 2316.5 |  |  | 2229 |  |  | 2369 |  |  | 2181 |  |  | 2255.5 |  |  | 2298 |  |  | 2293.5 |  |  | 2432.5 |  |  | 2473.5 |  |  | 2359 |  |  | 2464 |  |  | 2432 |  |  | 2358.5 |  |  | 2445.5 |  |  | 2332.5 |  |  | 2457.5 |  |  | 2371.5 |  |  | 2368.5 |  |  | 2366.5 |  |  | 2254.5 |  |  | 2182 |  |  | 2442 |  |  | 2284 |  |  | 2432.5 |  |  | 2474 |  |  | 2280.5 |  |  | 2426 |  |  | 2355 |  |  | 2332.5 |  |  | 2463.5 |  |  | 2283 |  |  | 2456 |  |  | 2274.5 |  |  | 2517 |  |  | 2303.5 |  |  | 2363.5 |  |  | 2375.5 |  |  | 2272.5 |  |  | 2240.5 |  |  | 2295 |  |  | 2323 |  |  | 2175 |  |  | 2315.5 |  |  | 2330.5 |  |  | 2340.5 |  |  | 2231.5 |  |  | 2320 |  |  | 2283 |  |  | 2383.5 |  |  | 2279 |  |  | 2395.5 |  |  | 2370 |  |  | 2299 |  |  | 2242.5 |  |  | 2338 |  |  | 2349 |  |  | 2235 |  |  | 2383 |  |  | 2308.5 |  |  | 2337.5 |  |  | 2282.5 |  |  | 2433 |  |  | 2325 |  |  | 2265 |  |  | 2304 |  |  | 2283.5 |  |  | 2320 |  |  | 2369.5 |  |  | 2346 |  |  | 2226 |  |  | 2337.5 |  |  | 2265.5 |  |  | 2233 |  |  | 2255.5 |  |  | 2333 |  |  | 2416 |  |  | 2279 |  |  | 2447 |  |  | 2225 |  |  | 2289 |  |  | 2266 |  |  | 2362 |  |  | 2228 |  |  | 2225.5 |  |  | 2273 |  |  | 2244 |  |  | 2449 |  |  | 2372 |  |  | 2322 |  |  | 2228 |  |  | 2319 |  |  | 2351.5 |  |  | 2351 |  |  | 2365.5 |  |  | 2354 |  |  | 2277 |  |  | 2414.5 |  |  | 2362 |  |  | 2432.5 |  |  | 2296 |  |  | 2169 |  |  | 2322.5 |  |  | 2418 |  |  | 2446.5 |  |  | 2409 |  |  | 2210 |  |  | 2388.5 |  |  | 2395.5 |  |  | 2383 |  |  | 2345.5 |  |  | 2303.5 |  |  | 2303 |  |  | 2365 |  |  | 2497.5 |  |  | 2211.5 |  |  | 2415.5 |  |  | 2379 |  |  | 2408 |  |  | 2327 |  |  | 2435 |  |  | 2429 |  |  | 2331.5 |  |  | 2311 |  |  | 2213.5 |  |  | 2350.5 |  |  | 2328 |  |  | 2398 |  |  | 2565.5 |  |  | 2228.5 |  |  | 2319 |  |  | 2380.5 |  |  | 2214.5 |  |  | 2353 |  |  | 2193 |  |  | 2270 |  |  | 2302.5 |  |  | 2426 |  |  | 2316.5 |  |  | 2414.5 |  |  | 2258 |  |  | 2265.5 |  |  | 2259 |  |  | 2292 |  |  | 2395 |  |  | 2428 |  |  | 2155 |  |  | 2435 |  |  | 2464 |  |  | 2314 |  |  | 2474 |  |  | 2288 |  |  | 2335.5 |  |  | 2473.5 |  |  | 2289 |  |  | 2246 |  |  | 2449 |  |  | 2341.5 |  |  | 2437.5 |  |  | 2469.5 |  |  | 2253 |  |  | 2347 |  |  | 2472.5 |  |  | 2388.5 |  |  | 2189.5 |  |  | 2404 |  |  | 2443 |  |  | 2343 |  |  | 2410 |  |  | 2315 |  |  | 2344.5 |  |  | 2253.5 |  |  | 2459 |  |  | 2261 |  |  | 2272 |  |  | 2460 |  |  | 2285 |  |  | 2468.5 |  |  | 2387 |  |  | 2310 |  |  | 2250 |  |  | 2306 |  |  | 2323.5 |  |  | 2464 |  |  | 2331 |  |  | 2292 |  |  | 2421 |  |  | 2415.5 |  |  | 2394 |  |  | 2303 |  |  | 2270 |  |  | 2396.5 |  |  | 2357.5 |  |  | 2465.5 |  |  | 2441 |  |  | 2309 |  |  | 2217 |  |  | 2496 |  |  | 2324 |  |  | 2276.5 |  |  | 2428 |  |  | 2309.5 |  |  | 2371.5 |  |  | 2379.5 |  |  | 2378 |  |  | 2483.5 |  |  | 2220 |  |  | 2232 |  |  | 2310.5 |  |  | 2378.5 |  |  | 2439 |  |  | 2430.5 |  |  | 2460.5 |  |  | 2290 |  |  | 2393 |  |  | 2262.5 |  |  | 2316.5 |  |  | 2496 |  |  | 2383.5 |  |  | 2455 |  |  | 2344 |  |  | 2282.5 |  |  | 2390 |  |  | 2266 |  |  | 2343.5 |  |  | 2339 |  |  | 2511.5 |  |  | 2337 |  |  | 2521 |  |  | 2382 |  |  | 2323 |  |  | 2467.5 |  |  | 2480 |  |  | 2446.5 |  |  | 2211.5 |  |  | 2464.5 |  |  | 2389 |  |  | 2399.5 |  |  | 2488 |  |  | 2384 |  |  | 2187.5 |  |  | 2332.5 |  |  | 2400 |  |  | 2300.5 |  |  | 2497 |  |  | 2253 |  |  | 2497.5 |  |  | 2280 |  |  | 2296.5 |  |  | 2342.5 |  |  | 2383.5 |  |  | 2355 |  |  | 2193 |  |  | 2274 |  |  | 2274.5 |  |  | 2284 |  |  | 2509.5 |  |  | 2368 |  |  | 2339 |  |  | 2271 |  |  | 2371 |  |  | 2435 |  |  | 2360 |  |  | 2330 |  |  | 2523 |  |  | 2366 |  |  | 2340.5 |  |  | 2409 |  |  | 2327 |  |  | 2420.5 |  |  | 2241.5 |  |  | 2329.5 |  |  | 2336.5 |  |  | 2372 |  |  | 2459 |  |  | 2147.5 |  |  | 2517.5 |  |  | 2267.5 |  |  | 2351 |  |  | 2323 |  |  | 2243 |  |  | 2323 |  |  | 2187 |  |  | 2400 |  |  | 2362 |  |  | 2348.5 |  |  | 2370.5 |  |  | 2284 |  |  | 2270.5 |  |  | 2378.5 |  |  | 2293 |  |  | 2363 |  |  | 2272 |  |  | 2389 |  |  | 2272.5 |  |  | 2250.5 |  |  | 2385.5 |  |  | 2291 |  |  | 2281.5 |  |  | 2398 |  |  | 2311 |  |  | 2446 |  |  | 2263.5 |  |  | 2316 |  |  | 2206 |  |  | 2354.5 |  |  | 2249 |  |  | 2421.5 |  |  | 2489 |  |  | 2355.5 |  |  | 2294 |  |  | 2295.5 |  |  | 2378.5 |  |  | 2424 |  |  | 2371 |  |  | 2177 |  |  | 2348 |  |  | 2182.5 |  |  | 2302 |  |  | 2477 |  |  | 2248.5 |  |  | 2440.5 |  |  | 2194.5 |  |  | 2248 |  |  | 2471.5 |  |  | 2401.5 |  |  | 2252.5 |  |  | 2411 |  |  | 2367 |  |  | 2411.5 |  |  | 2371 |  |  | 2504 |  |  | 2403.5 |  |  | 2361 |  |  | 2433 |  |  | 2338 |  |  | 2216 |  |  | 2172.5 |  |  | 2377.5 |  |  | 2290 |  |  | 2470 |  |  | 2381 |  |  | 2277 |  |  | 2325 |  |  | 2285.5 |  |  | 2283.5 |  |  | 2345 |  |  | 2486 |  |  | 2515 |  |  | 2247.5 |  |  | 2575.5 |  |  | 2265 |  |  | 2327 |  |  | 2171 |  |  | 2363.5 |  |  | 2484.5 |  |  | 2327 |  |  | 2225 |  |  | 2381 |  |  | 2340 |  |  | 2306 |  |  | 2484 |  |  | 2291 |  |  | 2487.5 |  |  | 2291 |  |  | 2437 |  |  | 2376 |  |  | 2415.5 |  |  | 2397 |  |  | 2296 |  |  | 2162 |  |  | 2294 |  |  | 2307 |  |  | 2366 |  |  | 2352 |  |  | 2283.5 |  |  | 2295.5 |  |  | 2156.5 |  |  | 2507 |  |  | 2306 |  |  | 2346.5 |  |  | 2163 |  |  | 2257.5 |  |  | 2352.5 |  |  | 2289 |  |  | 2373 |  |  | 2379.5 |  |  | 2351 |  |  | 2405 |  |  | 2396 |  |  | 2344 |  |  | 2415 |  |  | 2271 |  |  | 2290 |  |  | 2361.5 |  |  | 2316 |  |  | 2396 |  |  | 2403 |  |  | 2320 |  |  | 2314 |  |  | 2336 |  |  | 2440 |  |  | 2391 |  |  | 2329 |  |  | 2448.5 |  |  | 2349.5 |  |  | 2374.5 |  |  | 2365.5 |  |  | 2366 |  |  | 2179 |  |  | 2442.5 |  |  | 2241 |  |  | 2309 |  |  | 2233.5 |  |  | 2484.5 |  |  | 2409 |  |  | 2349.5 |  |  | 2340.5 |  |  | 2200 |  |  | 2472 |  |  | 2268 |  |  | 2370 |  |  | 2300.5 |  |  | 2396 |  |  | 2269.5 |  |  | 2268.5 |  |  | 2336 |  |  | 2312 |  |  | 2438.5 |  |  | 2322 |  |  | 2347.5 |  |  | 2352 |  |  | 2366.5 |  |  | 2226.5 |  |  | 2161.5 |  |  | 2482.5 |  |  | 2356.5 |  |  | 2178 |  |  | 2282 |  |  | 2416.5 |  |  | 2339 |  |  | 2255 |  |  | 2321 |  |  | 2499 |  |  | 2434.5 |  |  | 2164 |  |  | 2270 |  |  | 2383 |  |  | 2321.5 |  |  | 2361 |  |  | 2240 |  |  | 2302 |  |  | 2526.5 |  |  | 2410 |  |  | 2152 |  |  | 2380 |  |  | 2439 |  |  | 2580.5 |  |  | 2335 |  |  | 2259.5 |  |  | 2329 |  |  | 2391 |  |  | 2554.5 |  |  | 2366 |  |  | 2311 |  |  | 2276.5 |  |  | 2338 |  |  | 2264 |  |  | 2309 |  |  | 2637.5 |  |  | 2401.5 |  |  | 2386 |  |  | 2259 |  |  | 2319.5 |  |  | 2352.5 |  |  | 2342 |  |  | 2401 |  |  | 2403.5 |  |  | 2541.5 |  |  | 2242.5 |  |  | 2385.5 |  |  | 2305.5 |  |  | 2544 |  |  | 2267.5 |  |  | 2479 |  |  | 2318 |  |  | 2477 |  |  | 2464 |  |  | 2352.5 |  |  | 2337 |  |  | 2276 |  |  | 2341.5 |  |  | 2397.5 |  |  | 2230 |  |  | 2397.5 |  |  | 2294.5 |  |  | 2432 |  |  | 2252 |  |  | 2323 |  |  | 2332.5 |  |  | 2419 |  |  | 2432.5 |  |  | 2421 |  |  | 2379 |  |  | 2600.5 |  |  | 2280 |  |  | 2415 |  |  | 2265 |  |  | 2429 |  |  | 2465 |  |  | 2369 |  |  | 2407 |  |  | 2363 |  |  | 2242.5 |  |  | 2296.5 |  |  | 2306 |  |  | 2347.5 |  |  | 2160.5 |  |  | 2243 |  |  | 2298 |  |  | 2429 |  |  | 2434.5 |  |  | 2226.5 |  |  | 2408 |  |  | 2376 |  |  | 2253 |  |  | 2230 |  |  | 2308 |  |  | 2257 |  |  | 2371 |  |  | 2247.5 |  |  | 2412 |  |  | 2401 |  |  | 2429 |  |  | 2244 |  |  | 2226 |  |  | 2296.5 |  |  | 2524.5 |  |  | 2187.5 |  |  | 2233 |  |  | 2235 |  |  | 2239.5 |  |  | 2404.5 |  |  | 2401.5 |  |  | 2230 |  |  | 2425.5 |  |  | 2404.5 |  |  | 2430 |  |  | 2375.5 |  |  | 2380.5 |  |  | 2320 |  |  | 2201 |  |  | 2299 |  |  | 2426 |  |  | 2274 |  |  | 2198 |  |  | 2416 |  |  | 2461 |  |  | 2215 |  |  | 2338 |  |  | 2434.5 |  |  | 2293 |  |  | 2342 |  |  | 2270 |  |  | 2236.5 |  |  | 2258 |  |  | 2356.5 |  |  | 2488 |  |  | 2421 |  |  | 2329 |  |  | 2370 |  |  | 2459.5 |  |  | 2323 |  |  | 2205 |  |  | 2406.5 |  |  | 2358 |  |  | 2258 |  |  | 2295.5 |  |  | 2305.5 |  |  | 2292 |  |  | 2235.5 |  |  | 2439 |  |  | 2253.5 |  |  | 2444 |  |  | 2389 |  |  | 2265.5 |  |  | 2422.5 |  |  | 2360 |  |  | 2417 |  |  | 2332 |  |  | 2383 |  |  | 2278 |  |  | 2294 |  |  | 2195 |  |  | 2217 |  |  | 2394.5 |  |  | 2205 |  |  | 2447.5 |  |  | 2257 |  |  | 2370.5 |  |  | 2275.5 |  |  | 2298 |  |  | 2364 |  |  | 2421.5 |  |  | 2336 |  |  | 2386 |  |  | 2428 |  |  | 2330.5 |  |  | 2395 |  |  | 2233.5 |  |  | 2141 |  |  | 2248 |  |  | 2284 |  |  | 2346 |  |  | 2410.5 |  |  | 2287 |  |  | 2321 |  |  | 2421 |  |  | 2228.5 |  |  | 2489 |  |  | 2437 |  |  | 2400 |  |  | 2313 |  |  | 2319.5 |  |  | 2211.5 |  |  | 2459 |  |  | 2478 |  |  | 2371 |  |  | 2402.5 |  |  | 2346 |  |  | 2218 |  |  | 2265 |  |  | 2516.5 |  |  | 2305.5 |  |  | 2327.5 |  |  | 2379 |  |  | 2410 |  |  | 2401 |  |  | 2269.5 |  |  | 2430 |  |  | 2295.5 |  |  | 2205 |  |  | 2241 |  |  | 2344 |  |  | 2314.5 |  |  | 2418.5 |  |  | 2383 |  |  | 2326 |  |  | 2423.5 |  |  | 2373 |  |  | 2274 |  |  | 2404.5 |  |  | 2201 |  |  | 2223 |  |  | 2384.5 |  |  | 2247 |  |  | 2364 |  |  | 2294.5 |  |  | 2470 |  |  | 2250.5 |  |  | 2341 |  |  | 2156.5 |  |  | 2403.5 |  |  | 2201 |  |  | 2397 |  |  | 2455.5 |  |  | 2321.5 |  |  | 2427 |  |  | 2337 |  |  | 2304 |  |  | 2393.5 |  |  | 2434 |  |  | 2144 |  |  | 2277 |  |  | 2416.5 |  |  | 2411.5 |  |  | 2362 |  |  | 2422 |  |  | 2320 |  |  | 2295 |  |  | 2453 |  |  | 2329 |  |  | 2322 |  |  | 2325.5 |  |  | 2526.5 |  |  | 2257.5 |  |  | 2269 |  |  | 2287.5 |  |  | 2360 |  |  | 2318 |  |  | 2347.5 |  |  | 2213.5 |  |  | 2283 |  |  | 2372 |  |  | 2296.5 |  |  | 2283 |  |  | 2373 |  |  | 2190.5 |  |  | 2437.5 |  |  | 2301 |  |  | 2302 |  |  | 2355 |  |  | 2194.5 |  |  | 2235 |  |  | 2221 |  |  | 2329 |  |  | 2371 |  |  | 2456 |  |  | 2243.5 |  |  | 2450 |  |  | 2319 |  |  | 2221 |  |  | 2438.5 |  |  | 2361 |  |  | 2242.5 |  |  | 2242.5 |  |  | 2290 |  |  | 2409 |  |  | 2341.5 |  |  | 2243.5 |  |  | 2246.5 |  |  | 2317.5 |  |  | 2343.5 |  |  | 2357 |  |  | 2313 |  |  | 2343.5 |  |  | 2272.5 |  |  | 2333 |  |  | 2259 |  |  | 2343.5 |  |  | 2509 |  |  | 2296 |  |  | 2231 |  |  | 2394.5 |  |  | 2462 |  |  | 2264.5 |  |  | 2211 |  |  | 2393.5 |  |  | 2537.5 |  |  | 2485.5 |  |  | 2467 |  |  | 2386 |  |  | 2355.5 |  |  | 2317.5 |  |  | 2384 |  |  | 2368 |  |  | 2375.5 |  |  | 2510 |  |  | 2365.5 |  |  | 2334.5 |  |  | 2347 |  |  | 2321 |  |  | 2187.5 |  |  | 2401.5 |  |  | 2379 |  |  | 2299.5 |  |  | 2374.5 |  |  | 2385 |  |  | 2403 |  |  | 2418 |  |  | 2363.5 |  |  | 2410 |  |  | 2252 |  |  | 2370 |  |  | 2283 |  |  | 2352 |  |  | 2293 |  |  | 2513.5 |  |  | 2325.5 |  |  | 2358 |  |  | 2290 |  |  | 2362 |  |  | 2287.5 |  |  | 2276 |  |  | 2469 |  |  | 2333.5 |  |  | 2437.5 |  |  | 2299 |  |  | 2321.5 |  |  | 2428 |  |  | 2202 |  |  | 2353 |  |  | 2422.5 |  |  | 2435 |  |  | 2246.5 |  |  | 2297.5 |  |  | 2175 |  |  | 2345.5 |  |  | 2114.5 |  |  | 2331 |  |  | 2240 |  |  | 2415 |  |  | 2226.5 |  |  | 2220 |  |  | 2283.5 |  |  | 2396.5 |  |  | 2441 |  |  | 2225.5 |  |  | 2248 |  |  | 2291 |  |  | 2275 |  |  | 2294 |  |  | 2206 |  |  | 2427.5 |  |  | 2287 |  |  | 2466 |  |  | 2289 |  |  | 2431 |  |  | 2360.5 |  |  | 2372.5 |  |  | 2334 |  |  | 2439 |  |  | 2328 |  |  | 2345 |  |  | 2378 |  |  | 2243.5 |  |  | 2336 |  |  | 2425.5 |  |  | 2453 |  |  | 2196 |  |  | 2299 |  |  | 2355 |  |  | 2403.5 |  |  | 2294 |  |  | 2355.5 |  |  | 2266 |  |  | 2477 |  |  | 2374 |  |  | 2370.5 |  |  | 2221 |  |  | 2219 |  |  | 2311 |  |  | 2470 |  |  | 2575 |  |  | 2317.5 |  |  | 2416.5 |  |  | 2258 |  |  | 2299.5 |  |  | 2280 |  |  | 2271.5 |  |  | 2318.5 |  |  | 2300.5 |  |  | 2253.5 |  |  | 2221 |  |  | 2506 |  |  | 2258 |  |  | 2229 |  |  | 2328 |  |  | 2435 |  |  | 2305.5 |  |  | 2317.5 |  |  | 2474.5 |  |  | 2319 |  |  | 2422.5 |  |  | 2262.5 |  |  | 2421.5 |  |  | 2246.5 |  |  | 2352 |  |  | 2366.5 |  |  | 2371.5 |  |  | 2468 |  |  | 2215.5 |  |  | 2512.5 |  |  | 2372.5 |  |  | 2503 |  |  | 2370.5 |  |  | 2410 |  |  | 2359 |  |  | 2309.5 |  |  | 2386.5 |  |  | 2384 |  |  | 2438 |  |  | 2170.5 |  |  | 2226.5 |  |  | 2303.5 |  |  | 2385 |  |  | 2257 |  |  | 2326 |  |  | 2422.5 |  |  | 2440.5 |  |  | 2364 |  |  | 2394.5 |  |  | 2175 |  |  | 2302 |  |  | 2355.5 |  |  | 2239.5 |  |  | 2293 |  |  | 2317.5 |  |  | 2415 |  |  | 2235.5 |  |  | 2452.5 |  |  | 2418 |  |  | 2373.5 |  |  | 2442 |  |  | 2297.5 |  |  | 2328 |  |  | 2387 |  |  | 2420 |  |  | 2285.5 |  |  | 2233.5 |  |  | 2376 |  |  | 2283 |  |  | 2253 |  |  | 2282.5 |  |  | 2345.5 |  |  | 2466 |  |  | 2361.5 |  |  | 2310 |  |  | 2207.5 |  |  | 2373.5 |  |  | 2252 |  |  | 2265 |  |  | 2314 |  |  | 2338.5 |  |  | 2252 |  |  | 2356.5 |  |  | 2362 |  |  | 2296.5 |  |  | 2537 |  |  | 2195.5 |  |  | 2292 |  |  | 2359.5 |  |  | 2306.5 |  |  | 2279 |  |  | 2311 |  |  | 2537 |  |  | 2311 |  |  | 2415.5 |  |  | 2270 |  |  | 2296.5 |  |  | 2214 |  |  | 2223 |  |  | 2336 |  |  | 2484 |  |  | 2350 |  |  | 2328 |  |  | 2400 |  |  | 2296.5 |  |  | 2268 |  |  | 2390
82 |  | 2529.5 |  |  | 2448 |  |  | 2467.5 |  |  | 2411 |  |  | 2268.5 |  |  | 2457 |  |  | 2460 |  |  | 2371 |  |  | 2252.5 |  |  | 2253 |  |  | 2300 |  |  | 2505 |  |  | 2444 |  |  | 2548 |  |  | 2282.5 |  |  | 2432.5 |  |  | 2346 |  |  | 2408 |  |  | 2497 |  |  | 2285.5 |  |  | 2429 |  |  | 2435 |  |  | 2266 |  |  | 2363 |  |  | 2359.5 |  |  | 2484 |  |  | 2310 |  |  | 2408 |  |  | 2457 |  |  | 2240 |  |  | 2378 |  |  | 2314.5 |  |  | 2431.5 |  |  | 2356.5 |  |  | 2367 |  |  | 2364.5 |  |  | 2392.5 |  |  | 2451.5 |  |  | 2468 |  |  | 2407 |  |  | 2223.5 |  |  | 2319 |  |  | 2386.5 |  |  | 2316.5 |  |  | 2431.5 |  |  | 2540.5 |  |  | 2513.5 |  |  | 2328 |  |  | 2204 |  |  | 2325.5 |  |  | 2313 |  |  | 2320.5 |  |  | 2271.5 |  |  | 2355 |  |  | 2362 |  |  | 2316 |  |  | 2284 |  |  | 2455 |  |  | 2416 |  |  | 2384.5 |  |  | 2347.5 |  |  | 2355.5 |  |  | 2276 |  |  | 2384 |  |  | 2207 |  |  | 2302.5 |  |  | 2337 |  |  | 2332.5 |  |  | 2471.5 |  |  | 2488.5 |  |  | 2380 |  |  | 2493 |  |  | 2471 |  |  | 2379.5 |  |  | 2460.5 |  |  | 2379.5 |  |  | 2504.5 |  |  | 2410.5 |  |  | 2407.5 |  |  | 2390.5 |  |  | 2301.5 |  |  | 2203 |  |  | 2481 |  |  | 2299 |  |  | 2471.5 |  |  | 2500 |  |  | 2327.5 |  |  | 2465 |  |  | 2402 |  |  | 2358.5 |  |  | 2510.5 |  |  | 2307 |  |  | 2471 |  |  | 2298.5 |  |  | 2546 |  |  | 2332.5 |  |  | 2378.5 |  |  | 2399.5 |  |  | 2319.5 |  |  | 2279.5 |  |  | 2321 |  |  | 2352 |  |  | 2190 |  |  | 2339.5 |  |  | 2369.5 |  |  | 2361.5 |  |  | 2278.5 |  |  | 2335 |  |  | 2298 |  |  | 2409.5 |  |  | 2303 |  |  | 2424.5 |  |  | 2391 |  |  | 2328 |  |  | 2263.5 |  |  | 2364 |  |  | 2373 |  |  | 2274 |  |  | 2422 |  |  | 2355.5 |  |  | 2376.5 |  |  | 2303.5 |  |  | 2480 |  |  | 2340 |  |  | 2294 |  |  | 2328 |  |  | 2322.5 |  |  | 2359 |  |  | 2393.5 |  |  | 2361 |  |  | 2247 |  |  | 2384.5 |  |  | 2286.5 |  |  | 2254 |  |  | 2276.5 |  |  | 2357 |  |  | 2442 |  |  | 2318 |  |  | 2473 |  |  | 2264 |  |  | 2310 |  |  | 2292 |  |  | 2409 |  |  | 2254 |  |  | 2264.5 |  |  | 2312 |  |  | 2283 |  |  | 2496 |  |  | 2387 |  |  | 2361 |  |  | 2257 |  |  | 2358 |  |  | 2398.5 |  |  | 2366 |  |  | 2386.5 |  |  | 2380 |  |  | 2298 |  |  | 2440.5 |  |  | 2377 |  |  | 2456.5 |  |  | 2320 |  |  | 2198 |  |  | 2343.5 |  |  | 2439 |  |  | 2461.5 |  |  | 2456 |  |  | 2249 |  |  | 2417.5 |  |  | 2416.5 |  |  | 2407 |  |  | 2374.5 |  |  | 2327.5 |  |  | 2350 |  |  | 2412 |  |  | 2526.5 |  |  | 2237.5 |  |  | 2441.5 |  |  | 2405 |  |  | 2423 |  |  | 2366 |  |  | 2461 |  |  | 2476 |  |  | 2378.5 |  |  | 2340 |  |  | 2252.5 |  |  | 2374.5 |  |  | 2352 |  |  | 2437 |  |  | 2589.5 |  |  | 2257.5 |  |  | 2340 |  |  | 2401.5 |  |  | 2261.5 |  |  | 2400 |  |  | 2232 |  |  | 2309 |  |  | 2328.5 |  |  | 2450 |  |  | 2355.5 |  |  | 2461.5 |  |  | 2305 |  |  | 2280.5 |  |  | 2298 |  |  | 2318 |  |  | 2424 |  |  | 2454 |  |  | 2176 |  |  | 2450 |  |  | 2479 |  |  | 2343 |  |  | 2489 |  |  | 2335 |  |  | 2364.5 |  |  | 2499.5 |  |  | 2328 |  |  | 2270 |  |  | 2470 |  |  | 2380.5 |  |  | 2463.5 |  |  | 2508.5 |  |  | 2292 |  |  | 2362 |  |  | 2501.5 |  |  | 2409.5 |  |  | 2210.5 |  |  | 2433 |  |  | 2482 |  |  | 2364 |  |  | 2434 |  |  | 2344 |  |  | 2373.5 |  |  | 2300.5 |  |  | 2485 |  |  | 2300 |  |  | 2287 |  |  | 2499 |  |  | 2324 |  |  | 2507.5 |  |  | 2411 |  |  | 2331 |  |  | 2297 |  |  | 2327 |  |  | 2344.5 |  |  | 2488 |  |  | 2357 |  |  | 2331 |  |  | 2460 |  |  | 2430.5 |  |  | 2409 |  |  | 2327 |  |  | 2296 |  |  | 2425.5 |  |  | 2383.5 |  |  | 2494.5 |  |  | 2465 |  |  | 2338 |  |  | 2232 |  |  | 2522 |  |  | 2350 |  |  | 2323.5 |  |  | 2443 |  |  | 2333.5 |  |  | 2410.5 |  |  | 2405.5 |  |  | 2404 |  |  | 2507.5 |  |  | 2244 |  |  | 2258 |  |  | 2331.5 |  |  | 2393.5 |  |  | 2454 |  |  | 2451.5 |  |  | 2507.5 |  |  | 2329 |  |  | 2417 |  |  | 2283.5 |  |  | 2342.5 |  |  | 2543 |  |  | 2422.5 |  |  | 2476 |  |  | 2373 |  |  | 2308.5 |  |  | 2437 |  |  | 2292 |  |  | 2382.5 |  |  | 2365 |  |  | 2537.5 |  |  | 2384 |  |  | 2545 |  |  | 2421 |  |  | 2349 |  |  | 2496.5 |  |  | 2495 |  |  | 2467.5 |  |  | 2237.5 |  |  | 2503.5 |  |  | 2428 |  |  | 2438.5 |  |  | 2527 |  |  | 2410 |  |  | 2213.5 |  |  | 2371.5 |  |  | 2415 |  |  | 2339.5 |  |  | 2536 |  |  | 2300 |  |  | 2526.5 |  |  | 2319 |  |  | 2335.5 |  |  | 2368.5 |  |  | 2422.5 |  |  | 2384 |  |  | 2214 |  |  | 2295 |  |  | 2321.5 |  |  | 2323 |  |  | 2535.5 |  |  | 2397 |  |  | 2354 |  |  | 2286 |  |  | 2392 |  |  | 2474 |  |  | 2399 |  |  | 2354 |  |  | 2562 |  |  | 2387 |  |  | 2379.5 |  |  | 2456 |  |  | 2366 |  |  | 2449.5 |  |  | 2267.5 |  |  | 2358.5 |  |  | 2351.5 |  |  | 2387 |  |  | 2483 |  |  | 2162.5 |  |  | 2556.5 |  |  | 2314.5 |  |  | 2380 |  |  | 2370 |  |  | 2264 |  |  | 2344 |  |  | 2208 |  |  | 2447 |  |  | 2401 |  |  | 2374.5 |  |  | 2409.5 |  |  | 2299 |  |  | 2309.5 |  |  | 2417.5 |  |  | 2317 |  |  | 2392 |  |  | 2311 |  |  | 2418 |  |  | 2311.5 |  |  | 2276.5 |  |  | 2406.5 |  |  | 2306 |  |  | 2310.5 |  |  | 2424 |  |  | 2337 |  |  | 2493 |  |  | 2310.5 |  |  | 2337 |  |  | 2245 |  |  | 2380.5 |  |  | 2264 |  |  | 2436.5 |  |  | 2518 |  |  | 2381.5 |  |  | 2341 |  |  | 2319.5 |  |  | 2402.5 |  |  | 2439 |  |  | 2397 |  |  | 2216 |  |  | 2363 |  |  | 2229.5 |  |  | 2341 |  |  | 2503 |  |  | 2277.5 |  |  | 2487.5 |  |  | 2220.5 |  |  | 2263 |  |  | 2486.5 |  |  | 2448.5 |  |  | 2291.5 |  |  | 2458 |  |  | 2391 |  |  | 2450.5 |  |  | 2410 |  |  | 2543 |  |  | 2432.5 |  |  | 2382 |  |  | 2457 |  |  | 2367 |  |  | 2240 |  |  | 2198.5 |  |  | 2398.5 |  |  | 2305 |  |  | 2494 |  |  | 2407 |  |  | 2316 |  |  | 2364 |  |  | 2332.5 |  |  | 2298.5 |  |  | 2392 |  |  | 2533 |  |  | 2530 |  |  | 2294.5 |  |  | 2590.5 |  |  | 2304 |  |  | 2374 |  |  | 2197 |  |  | 2402.5 |  |  | 2499.5 |  |  | 2366 |  |  | 2240 |  |  | 2420 |  |  | 2379 |  |  | 2321 |  |  | 2499 |  |  | 2330 |  |  | 2534.5 |  |  | 2330 |  |  | 2466 |  |  | 2402 |  |  | 2439.5 |  |  | 2444 |  |  | 2325 |  |  | 2209 |  |  | 2341 |  |  | 2336 |  |  | 2405 |  |  | 2399 |  |  | 2322.5 |  |  | 2324.5 |  |  | 2195.5 |  |  | 2522 |  |  | 2321 |  |  | 2367.5 |  |  | 2202 |  |  | 2281.5 |  |  | 2391.5 |  |  | 2315 |  |  | 2412 |  |  | 2403.5 |  |  | 2375 |  |  | 2434 |  |  | 2425 |  |  | 2365 |  |  | 2439 |  |  | 2300 |  |  | 2316 |  |  | 2408.5 |  |  | 2331 |  |  | 2435 |  |  | 2427 |  |  | 2367 |  |  | 2353 |  |  | 2365 |  |  | 2464 |  |  | 2430 |  |  | 2368 |  |  | 2463.5 |  |  | 2396.5 |  |  | 2389.5 |  |  | 2394.5 |  |  | 2387 |  |  | 2200 |  |  | 2489.5 |  |  | 2262 |  |  | 2348 |  |  | 2262.5 |  |  | 2513.5 |  |  | 2433 |  |  | 2364.5 |  |  | 2366.5 |  |  | 2226 |  |  | 2498 |  |  | 2307 |  |  | 2394 |  |  | 2324.5 |  |  | 2411 |  |  | 2295.5 |  |  | 2307.5 |  |  | 2362 |  |  | 2336 |  |  | 2462.5 |  |  | 2343 |  |  | 2362.5 |  |  | 2378 |  |  | 2405.5 |  |  | 2247.5 |  |  | 2200.5 |  |  | 2529.5 |  |  | 2380.5 |  |  | 2193 |  |  | 2308 |  |  | 2455.5 |  |  | 2368 |  |  | 2302 |  |  | 2368 |  |  | 2525 |  |  | 2473.5 |  |  | 2193 |  |  | 2291 |  |  | 2422 |  |  | 2347.5 |  |  | 2385 |  |  | 2279 |  |  | 2326 |  |  | 2552.5 |  |  | 2449 |  |  | 2178 |  |  | 2406 |  |  | 2478 |  |  | 2619.5 |  |  | 2361 |  |  | 2298.5 |  |  | 2368 |  |  | 2438 |  |  | 2593.5 |  |  | 2387 |  |  | 2332 |  |  | 2300.5 |  |  | 2359 |  |  | 2303 |  |  | 2324 |  |  | 2652.5 |  |  | 2448.5 |  |  | 2415 |  |  | 2298 |  |  | 2334.5 |  |  | 2391.5 |  |  | 2389 |  |  | 2416 |  |  | 2442.5 |  |  | 2562.5 |  |  | 2289.5 |  |  | 2414.5 |  |  | 2329.5 |  |  | 2583 |  |  | 2288.5 |  |  | 2500 |  |  | 2342 |  |  | 2492 |  |  | 2488 |  |  | 2391.5 |  |  | 2361 |  |  | 2300 |  |  | 2362.5 |  |  | 2421.5 |  |  | 2277 |  |  | 2436.5 |  |  | 2309.5 |  |  | 2458 |  |  | 2299 |  |  | 2349 |  |  | 2371.5 |  |  | 2434 |  |  | 2453.5 |  |  | 2460 |  |  | 2408 |  |  | 2629.5 |  |  | 2306 |  |  | 2462 |  |  | 2289 |  |  | 2476 |  |  | 2494 |  |  | 2393 |  |  | 2422 |  |  | 2378 |  |  | 2281.5 |  |  | 2325.5 |  |  | 2330 |  |  | 2376.5 |  |  | 2207.5 |  |  | 2290 |  |  | 2313 |  |  | 2444 |  |  | 2455.5 |  |  | 2273.5 |  |  | 2429 |  |  | 2391 |  |  | 2282 |  |  | 2269 |  |  | 2337 |  |  | 2281 |  |  | 2395 |  |  | 2276.5 |  |  | 2459 |  |  | 2440 |  |  | 2458 |  |  | 2270 |  |  | 2265 |  |  | 2311.5 |  |  | 2548.5 |  |  | 2208.5 |  |  | 2262 |  |  | 2274 |  |  | 2286.5 |  |  | 2430.5 |  |  | 2416.5 |  |  | 2269 |  |  | 2446.5 |  |  | 2433.5 |  |  | 2454 |  |  | 2390.5 |  |  | 2406.5 |  |  | 2335 |  |  | 2240 |  |  | 2338 |  |  | 2455 |  |  | 2295 |  |  | 2222 |  |  | 2440 |  |  | 2482 |  |  | 2230 |  |  | 2359 |  |  | 2481.5 |  |  | 2332 |  |  | 2368 |  |  | 2309 |  |  | 2251.5 |  |  | 2287 |  |  | 2377.5 |  |  | 2512 |  |  | 2450 |  |  | 2376 |  |  | 2399 |  |  | 2485.5 |  |  | 2362 |  |  | 2229 |  |  | 2421.5 |  |  | 2397 |  |  | 2305 |  |  | 2310.5 |  |  | 2329.5 |  |  | 2313 |  |  | 2250.5 |  |  | 2468 |  |  | 2300.5 |  |  | 2470 |  |  | 2418 |  |  | 2304.5 |  |  | 2448.5 |  |  | 2399 |  |  | 2446 |  |  | 2371 |  |  | 2407 |  |  | 2304 |  |  | 2320 |  |  | 2234 |  |  | 2256 |  |  | 2441.5 |  |  | 2226 |  |  | 2476.5 |  |  | 2283 |  |  | 2417.5 |  |  | 2314.5 |  |  | 2324 |  |  | 2411 |  |  | 2450.5 |  |  | 2351 |  |  | 2415 |  |  | 2467 |  |  | 2351.5 |  |  | 2424 |  |  | 2280.5 |  |  | 2162 |  |  | 2287 |  |  | 2308 |  |  | 2385 |  |  | 2457.5 |  |  | 2313 |  |  | 2368 |  |  | 2450 |  |  | 2275.5 |  |  | 2536 |  |  | 2476 |  |  | 2426 |  |  | 2360 |  |  | 2345.5 |  |  | 2226.5 |  |  | 2488 |  |  | 2493 |  |  | 2395 |  |  | 2441.5 |  |  | 2372 |  |  | 2239 |  |  | 2312 |  |  | 2555.5 |  |  | 2329.5 |  |  | 2351.5 |  |  | 2426 |  |  | 2439 |  |  | 2430 |  |  | 2298.5 |  |  | 2477 |  |  | 2324.5 |  |  | 2244 |  |  | 2256 |  |  | 2359 |  |  | 2329.5 |  |  | 2433.5 |  |  | 2398 |  |  | 2373 |  |  | 2449.5 |  |  | 2412 |  |  | 2300 |  |  | 2430.5 |  |  | 2222 |  |  | 2270 |  |  | 2431.5 |  |  | 2286 |  |  | 2403 |  |  | 2333.5 |  |  | 2499 |  |  | 2274.5 |  |  | 2380 |  |  | 2171.5 |  |  | 2442.5 |  |  | 2248 |  |  | 2421 |  |  | 2494.5 |  |  | 2342.5 |  |  | 2466 |  |  | 2384 |  |  | 2325 |  |  | 2414.5 |  |  | 2473 |  |  | 2165 |  |  | 2298 |  |  | 2455.5 |  |  | 2437.5 |  |  | 2401 |  |  | 2448 |  |  | 2341 |  |  | 2324 |  |  | 2479 |  |  | 2353 |  |  | 2361 |  |  | 2354.5 |  |  | 2552.5 |  |  | 2283.5 |  |  | 2308 |  |  | 2311.5 |  |  | 2407 |  |  | 2344 |  |  | 2376.5 |  |  | 2252.5 |  |  | 2307 |  |  | 2411 |  |  | 2325.5 |  |  | 2304 |  |  | 2412 |  |  | 2211.5 |  |  | 2461.5 |  |  | 2330 |  |  | 2317 |  |  | 2384 |  |  | 2233.5 |  |  | 2282 |  |  | 2242 |  |  | 2368 |  |  | 2392 |  |  | 2495 |  |  | 2282.5 |  |  | 2476 |  |  | 2358 |  |  | 2260 |  |  | 2459.5 |  |  | 2385 |  |  | 2263.5 |  |  | 2257.5 |  |  | 2329 |  |  | 2424 |  |  | 2367.5 |  |  | 2282.5 |  |  | 2293.5 |  |  | 2341.5 |  |  | 2390.5 |  |  | 2372 |  |  | 2339 |  |  | 2382.5 |  |  | 2319.5 |  |  | 2348 |  |  | 2274 |  |  | 2367.5 |  |  | 2548 |  |  | 2322 |  |  | 2270 |  |  | 2418.5 |  |  | 2501 |  |  | 2288.5 |  |  | 2250 |  |  | 2419.5 |  |  | 2584.5 |  |  | 2511.5 |  |  | 2493 |  |  | 2412 |  |  | 2379.5 |  |  | 2341.5 |  |  | 2423 |  |  | 2397 |  |  | 2399.5 |  |  | 2525 |  |  | 2389.5 |  |  | 2373.5 |  |  | 2362 |  |  | 2342 |  |  | 2234.5 |  |  | 2440.5 |  |  | 2394 |  |  | 2320.5 |  |  | 2413.5 |  |  | 2424 |  |  | 2427 |  |  | 2444 |  |  | 2402.5 |  |  | 2457 |  |  | 2281 |  |  | 2409 |  |  | 2298 |  |  | 2367 |  |  | 2332 |  |  | 2528.5 |  |  | 2340.5 |  |  | 2379 |  |  | 2305 |  |  | 2401 |  |  | 2308.5 |  |  | 2323 |  |  | 2508 |  |  | 2348.5 |  |  | 2458.5 |  |  | 2346 |  |  | 2345.5 |  |  | 2467 |  |  | 2223 |  |  | 2368 |  |  | 2469.5 |  |  | 2450 |  |  | 2285.5 |  |  | 2326.5 |  |  | 2222 |  |  | 2384.5 |  |  | 2138.5 |  |  | 2352 |  |  | 2287 |  |  | 2436 |  |  | 2265.5 |  |  | 2267 |  |  | 2307.5 |  |  | 2435.5 |  |  | 2488 |  |  | 2249.5 |  |  | 2269 |  |  | 2338 |  |  | 2322 |  |  | 2318 |  |  | 2232 |  |  | 2456.5 |  |  | 2313 |  |  | 2505 |  |  | 2328 |  |  | 2478 |  |  | 2381.5 |  |  | 2393.5 |  |  | 2373 |  |  | 2463 |  |  | 2352 |  |  | 2371 |  |  | 2399 |  |  | 2258.5 |  |  | 2375 |  |  | 2454.5 |  |  | 2492 |  |  | 2211 |  |  | 2338 |  |  | 2394 |  |  | 2442.5 |  |  | 2341 |  |  | 2394.5 |  |  | 2287 |  |  | 2506 |  |  | 2400 |  |  | 2396.5 |  |  | 2260 |  |  | 2248 |  |  | 2326 |  |  | 2509 |  |  | 2614 |  |  | 2346.5 |  |  | 2437.5 |  |  | 2287 |  |  | 2325.5 |  |  | 2295 |  |  | 2318.5 |  |  | 2342.5 |  |  | 2315.5 |  |  | 2292.5 |  |  | 2247 |  |  | 2545 |  |  | 2279 |  |  | 2255 |  |  | 2343 |  |  | 2464 |  |  | 2352.5 |  |  | 2346.5 |  |  | 2521.5 |  |  | 2348 |  |  | 2469.5 |  |  | 2291.5 |  |  | 2445.5 |  |  | 2261.5 |  |  | 2378 |  |  | 2392.5 |  |  | 2400.5 |  |  | 2494 |  |  | 2230.5 |  |  | 2527.5 |  |  | 2411.5 |  |  | 2542 |  |  | 2409.5 |  |  | 2434 |  |  | 2398 |  |  | 2348.5 |  |  | 2433.5 |  |  | 2431 |  |  | 2464 |  |  | 2196.5 |  |  | 2241.5 |  |  | 2329.5 |  |  | 2409 |  |  | 2296 |  |  | 2373 |  |  | 2451.5 |  |  | 2461.5 |  |  | 2393 |  |  | 2415.5 |  |  | 2222 |  |  | 2341 |  |  | 2379.5 |  |  | 2263.5 |  |  | 2317 |  |  | 2356.5 |  |  | 2441 |  |  | 2274.5 |  |  | 2478.5 |  |  | 2444 |  |  | 2412.5 |  |  | 2463 |  |  | 2326.5 |  |  | 2367 |  |  | 2408 |  |  | 2441 |  |  | 2300.5 |  |  | 2272.5 |  |  | 2397 |  |  | 2304 |  |  | 2274 |  |  | 2306.5 |  |  | 2384.5 |  |  | 2481 |  |  | 2390.5 |  |  | 2325 |  |  | 2222.5 |  |  | 2420.5 |  |  | 2291 |  |  | 2294 |  |  | 2340 |  |  | 2364.5 |  |  | 2291 |  |  | 2395.5 |  |  | 2401 |  |  | 2322.5 |  |  | 2558 |  |  | 2234.5 |  |  | 2331 |  |  | 2374.5 |  |  | 2345.5 |  |  | 2318 |  |  | 2340 |  |  | 2576 |  |  | 2350 |  |  | 2436.5 |  |  | 2291 |  |  | 2311.5 |  |  | 2240 |  |  | 2252 |  |  | 2351 |  |  | 2510 |  |  | 2397 |  |  | 2352 |  |  | 2439 |  |  | 2317.5 |  |  | 2307 |  |  | 2411
83 |  | 2544.5 |  |  | 2487 |  |  | 2514.5 |  |  | 2432 |  |  | 2283.5 |  |  | 2496 |  |  | 2486 |  |  | 2410 |  |  | 2273.5 |  |  | 2292 |  |  | 2347 |  |  | 2529 |  |  | 2468 |  |  | 2572 |  |  | 2311.5 |  |  | 2447.5 |  |  | 2385 |  |  | 2447 |  |  | 2518 |  |  | 2309.5 |  |  | 2455 |  |  | 2461 |  |  | 2281 |  |  | 2402 |  |  | 2398.5 |  |  | 2523 |  |  | 2349 |  |  | 2434 |  |  | 2496 |  |  | 2266 |  |  | 2399 |  |  | 2329.5 |  |  | 2470.5 |  |  | 2403.5 |  |  | 2388 |  |  | 2393.5 |  |  | 2418.5 |  |  | 2490.5 |  |  | 2515 |  |  | 2422 |  |  | 2244.5 |  |  | 2345 |  |  | 2401.5 |  |  | 2340.5 |  |  | 2457.5 |  |  | 2564.5 |  |  | 2560.5 |  |  | 2367 |  |  | 2230 |  |  | 2354.5 |  |  | 2360 |  |  | 2367.5 |  |  | 2292.5 |  |  | 2381 |  |  | 2386 |  |  | 2337 |  |  | 2299 |  |  | 2476 |  |  | 2445 |  |  | 2423.5 |  |  | 2376.5 |  |  | 2384.5 |  |  | 2315 |  |  | 2431 |  |  | 2233 |  |  | 2341.5 |  |  | 2384 |  |  | 2356.5 |  |  | 2497.5 |  |  | 2512.5 |  |  | 2419 |  |  | 2508 |  |  | 2510 |  |  | 2418.5 |  |  | 2475.5 |  |  | 2400.5 |  |  | 2530.5 |  |  | 2439.5 |  |  | 2446.5 |  |  | 2405.5 |  |  | 2330.5 |  |  | 2218 |  |  | 2528 |  |  | 2320 |  |  | 2500.5 |  |  | 2515 |  |  | 2366.5 |  |  | 2489 |  |  | 2426 |  |  | 2397.5 |  |  | 2539.5 |  |  | 2331 |  |  | 2486 |  |  | 2337.5 |  |  | 2570 |  |  | 2353.5 |  |  | 2417.5 |  |  | 2446.5 |  |  | 2334.5 |  |  | 2303.5 |  |  | 2350 |  |  | 2399 |  |  | 2229 |  |  | 2354.5 |  |  | 2393.5 |  |  | 2382.5 |  |  | 2307.5 |  |  | 2374 |  |  | 2337 |  |  | 2424.5 |  |  | 2342 |  |  | 2445.5 |  |  | 2412 |  |  | 2349 |  |  | 2310.5 |  |  | 2403 |  |  | 2388 |  |  | 2298 |  |  | 2451 |  |  | 2394.5 |  |  | 2400.5 |  |  | 2324.5 |  |  | 2495 |  |  | 2355 |  |  | 2318 |  |  | 2354 |  |  | 2337.5 |  |  | 2406 |  |  | 2440.5 |  |  | 2408 |  |  | 2262 |  |  | 2405.5 |  |  | 2315.5 |  |  | 2293 |  |  | 2315.5 |  |  | 2396 |  |  | 2489 |  |  | 2344 |  |  | 2499 |  |  | 2311 |  |  | 2325 |  |  | 2331 |  |  | 2433 |  |  | 2280 |  |  | 2279.5 |  |  | 2336 |  |  | 2322 |  |  | 2543 |  |  | 2426 |  |  | 2390 |  |  | 2286 |  |  | 2387 |  |  | 2413.5 |  |  | 2390 |  |  | 2407.5 |  |  | 2419 |  |  | 2337 |  |  | 2466.5 |  |  | 2398 |  |  | 2503.5 |  |  | 2359 |  |  | 2213 |  |  | 2372.5 |  |  | 2465 |  |  | 2500.5 |  |  | 2471 |  |  | 2264 |  |  | 2446.5 |  |  | 2455.5 |  |  | 2433 |  |  | 2413.5 |  |  | 2366.5 |  |  | 2389 |  |  | 2459 |  |  | 2547.5 |  |  | 2252.5 |  |  | 2467.5 |  |  | 2429 |  |  | 2470 |  |  | 2395 |  |  | 2485 |  |  | 2515 |  |  | 2393.5 |  |  | 2364 |  |  | 2281.5 |  |  | 2413.5 |  |  | 2391 |  |  | 2452 |  |  | 2628.5 |  |  | 2296.5 |  |  | 2361 |  |  | 2440.5 |  |  | 2308.5 |  |  | 2421 |  |  | 2279 |  |  | 2338 |  |  | 2352.5 |  |  | 2471 |  |  | 2379.5 |  |  | 2500.5 |  |  | 2352 |  |  | 2304.5 |  |  | 2345 |  |  | 2357 |  |  | 2448 |  |  | 2493 |  |  | 2191 |  |  | 2497 |  |  | 2518 |  |  | 2390 |  |  | 2504 |  |  | 2356 |  |  | 2403.5 |  |  | 2523.5 |  |  | 2343 |  |  | 2296 |  |  | 2494 |  |  | 2419.5 |  |  | 2510.5 |  |  | 2555.5 |  |  | 2331 |  |  | 2383 |  |  | 2540.5 |  |  | 2438.5 |  |  | 2257.5 |  |  | 2462 |  |  | 2521 |  |  | 2388 |  |  | 2458 |  |  | 2370 |  |  | 2420.5 |  |  | 2329.5 |  |  | 2509 |  |  | 2339 |  |  | 2334 |  |  | 2514 |  |  | 2348 |  |  | 2533.5 |  |  | 2432 |  |  | 2352 |  |  | 2312 |  |  | 2353 |  |  | 2383.5 |  |  | 2509 |  |  | 2383 |  |  | 2355 |  |  | 2499 |  |  | 2469.5 |  |  | 2430 |  |  | 2353 |  |  | 2317 |  |  | 2464.5 |  |  | 2422.5 |  |  | 2515.5 |  |  | 2504 |  |  | 2364 |  |  | 2261 |  |  | 2569 |  |  | 2376 |  |  | 2338.5 |  |  | 2490 |  |  | 2359.5 |  |  | 2434.5 |  |  | 2444.5 |  |  | 2430 |  |  | 2554.5 |  |  | 2291 |  |  | 2273 |  |  | 2360.5 |  |  | 2408.5 |  |  | 2469 |  |  | 2466.5 |  |  | 2533.5 |  |  | 2353 |  |  | 2464 |  |  | 2298.5 |  |  | 2371.5 |  |  | 2564 |  |  | 2461.5 |  |  | 2505 |  |  | 2420 |  |  | 2332.5 |  |  | 2463 |  |  | 2313 |  |  | 2429.5 |  |  | 2380 |  |  | 2552.5 |  |  | 2410 |  |  | 2574 |  |  | 2445 |  |  | 2364 |  |  | 2520.5 |  |  | 2521 |  |  | 2506.5 |  |  | 2261.5 |  |  | 2550.5 |  |  | 2475 |  |  | 2464.5 |  |  | 2566 |  |  | 2434 |  |  | 2234.5 |  |  | 2397.5 |  |  | 2462 |  |  | 2368.5 |  |  | 2565 |  |  | 2339 |  |  | 2573.5 |  |  | 2340 |  |  | 2361.5 |  |  | 2383.5 |  |  | 2461.5 |  |  | 2408 |  |  | 2240 |  |  | 2324 |  |  | 2360.5 |  |  | 2347 |  |  | 2574.5 |  |  | 2444 |  |  | 2401 |  |  | 2325 |  |  | 2407 |  |  | 2513 |  |  | 2414 |  |  | 2378 |  |  | 2588 |  |  | 2408 |  |  | 2400.5 |  |  | 2480 |  |  | 2392 |  |  | 2464.5 |  |  | 2306.5 |  |  | 2384.5 |  |  | 2372.5 |  |  | 2411 |  |  | 2504 |  |  | 2209.5 |  |  | 2603.5 |  |  | 2353.5 |  |  | 2406 |  |  | 2417 |  |  | 2303 |  |  | 2383 |  |  | 2234 |  |  | 2473 |  |  | 2440 |  |  | 2413.5 |  |  | 2448.5 |  |  | 2323 |  |  | 2324.5 |  |  | 2432.5 |  |  | 2338 |  |  | 2407 |  |  | 2337 |  |  | 2444 |  |  | 2350.5 |  |  | 2302.5 |  |  | 2445.5 |  |  | 2330 |  |  | 2336.5 |  |  | 2448 |  |  | 2376 |  |  | 2519 |  |  | 2349.5 |  |  | 2363 |  |  | 2266 |  |  | 2406.5 |  |  | 2311 |  |  | 2460.5 |  |  | 2544 |  |  | 2420.5 |  |  | 2370 |  |  | 2340.5 |  |  | 2441.5 |  |  | 2486 |  |  | 2423 |  |  | 2231 |  |  | 2389 |  |  | 2268.5 |  |  | 2367 |  |  | 2542 |  |  | 2324.5 |  |  | 2511.5 |  |  | 2246.5 |  |  | 2289 |  |  | 2501.5 |  |  | 2487.5 |  |  | 2306.5 |  |  | 2482 |  |  | 2412 |  |  | 2474.5 |  |  | 2457 |  |  | 2582 |  |  | 2461.5 |  |  | 2397 |  |  | 2478 |  |  | 2391 |  |  | 2261 |  |  | 2245.5 |  |  | 2427.5 |  |  | 2326 |  |  | 2533 |  |  | 2428 |  |  | 2363 |  |  | 2411 |  |  | 2379.5 |  |  | 2322.5 |  |  | 2439 |  |  | 2557 |  |  | 2545 |  |  | 2323.5 |  |  | 2619.5 |  |  | 2319 |  |  | 2403 |  |  | 2223 |  |  | 2441.5 |  |  | 2514.5 |  |  | 2395 |  |  | 2264 |  |  | 2459 |  |  | 2405 |  |  | 2360 |  |  | 2538 |  |  | 2377 |  |  | 2560.5 |  |  | 2359 |  |  | 2505 |  |  | 2423 |  |  | 2454.5 |  |  | 2483 |  |  | 2354 |  |  | 2224 |  |  | 2362 |  |  | 2360 |  |  | 2420 |  |  | 2423 |  |  | 2361.5 |  |  | 2350.5 |  |  | 2242.5 |  |  | 2537 |  |  | 2336 |  |  | 2396.5 |  |  | 2241 |  |  | 2320.5 |  |  | 2406.5 |  |  | 2354 |  |  | 2459 |  |  | 2432.5 |  |  | 2390 |  |  | 2460 |  |  | 2440 |  |  | 2380 |  |  | 2468 |  |  | 2339 |  |  | 2337 |  |  | 2432.5 |  |  | 2370 |  |  | 2464 |  |  | 2456 |  |  | 2414 |  |  | 2377 |  |  | 2404 |  |  | 2490 |  |  | 2477 |  |  | 2394 |  |  | 2484.5 |  |  | 2417.5 |  |  | 2404.5 |  |  | 2423.5 |  |  | 2413 |  |  | 2226 |  |  | 2504.5 |  |  | 2301 |  |  | 2387 |  |  | 2277.5 |  |  | 2534.5 |  |  | 2448 |  |  | 2403.5 |  |  | 2381.5 |  |  | 2241 |  |  | 2537 |  |  | 2333 |  |  | 2423 |  |  | 2371.5 |  |  | 2437 |  |  | 2319.5 |  |  | 2333.5 |  |  | 2401 |  |  | 2365 |  |  | 2486.5 |  |  | 2369 |  |  | 2401.5 |  |  | 2402 |  |  | 2434.5 |  |  | 2294.5 |  |  | 2221.5 |  |  | 2568.5 |  |  | 2419.5 |  |  | 2208 |  |  | 2334 |  |  | 2484.5 |  |  | 2383 |  |  | 2323 |  |  | 2383 |  |  | 2554 |  |  | 2497.5 |  |  | 2222 |  |  | 2306 |  |  | 2469 |  |  | 2368.5 |  |  | 2400 |  |  | 2300 |  |  | 2365 |  |  | 2578.5 |  |  | 2496 |  |  | 2207 |  |  | 2432 |  |  | 2502 |  |  | 2634.5 |  |  | 2390 |  |  | 2313.5 |  |  | 2407 |  |  | 2462 |  |  | 2617.5 |  |  | 2434 |  |  | 2353 |  |  | 2326.5 |  |  | 2406 |  |  | 2318 |  |  | 2350 |  |  | 2699.5 |  |  | 2463.5 |  |  | 2454 |  |  | 2324 |  |  | 2363.5 |  |  | 2420.5 |  |  | 2415 |  |  | 2455 |  |  | 2463.5 |  |  | 2609.5 |  |  | 2313.5 |  |  | 2461.5 |  |  | 2344.5 |  |  | 2622 |  |  | 2327.5 |  |  | 2529 |  |  | 2381 |  |  | 2518 |  |  | 2527 |  |  | 2415.5 |  |  | 2382 |  |  | 2347 |  |  | 2391.5 |  |  | 2447.5 |  |  | 2303 |  |  | 2465.5 |  |  | 2338.5 |  |  | 2473 |  |  | 2346 |  |  | 2396 |  |  | 2418.5 |  |  | 2473 |  |  | 2474.5 |  |  | 2486 |  |  | 2437 |  |  | 2653.5 |  |  | 2327 |  |  | 2509 |  |  | 2310 |  |  | 2505 |  |  | 2533 |  |  | 2419 |  |  | 2437 |  |  | 2402 |  |  | 2310.5 |  |  | 2346.5 |  |  | 2359 |  |  | 2400.5 |  |  | 2246.5 |  |  | 2319 |  |  | 2342 |  |  | 2465 |  |  | 2494.5 |  |  | 2320.5 |  |  | 2455 |  |  | 2417 |  |  | 2306 |  |  | 2298 |  |  | 2376 |  |  | 2296 |  |  | 2434 |  |  | 2315.5 |  |  | 2498 |  |  | 2479 |  |  | 2473 |  |  | 2309 |  |  | 2280 |  |  | 2350.5 |  |  | 2572.5 |  |  | 2234.5 |  |  | 2286 |  |  | 2289 |  |  | 2325.5 |  |  | 2469.5 |  |  | 2455.5 |  |  | 2295 |  |  | 2485.5 |  |  | 2457.5 |  |  | 2493 |  |  | 2429.5 |  |  | 2445.5 |  |  | 2374 |  |  | 2264 |  |  | 2367 |  |  | 2494 |  |  | 2342 |  |  | 2243 |  |  | 2479 |  |  | 2497 |  |  | 2256 |  |  | 2388 |  |  | 2510.5 |  |  | 2379 |  |  | 2392 |  |  | 2348 |  |  | 2266.5 |  |  | 2308 |  |  | 2398.5 |  |  | 2533 |  |  | 2465 |  |  | 2397 |  |  | 2420 |  |  | 2514.5 |  |  | 2391 |  |  | 2268 |  |  | 2447.5 |  |  | 2423 |  |  | 2329 |  |  | 2339.5 |  |  | 2355.5 |  |  | 2337 |  |  | 2297.5 |  |  | 2507 |  |  | 2329.5 |  |  | 2496 |  |  | 2465 |  |  | 2343.5 |  |  | 2463.5 |  |  | 2438 |  |  | 2470 |  |  | 2397 |  |  | 2422 |  |  | 2343 |  |  | 2367 |  |  | 2263 |  |  | 2282 |  |  | 2456.5 |  |  | 2250 |  |  | 2500.5 |  |  | 2330 |  |  | 2456.5 |  |  | 2353.5 |  |  | 2371 |  |  | 2450 |  |  | 2471.5 |  |  | 2390 |  |  | 2454 |  |  | 2482 |  |  | 2380.5 |  |  | 2450 |  |  | 2309.5 |  |  | 2201 |  |  | 2311 |  |  | 2347 |  |  | 2432 |  |  | 2496.5 |  |  | 2339 |  |  | 2383 |  |  | 2471 |  |  | 2301.5 |  |  | 2583 |  |  | 2500 |  |  | 2450 |  |  | 2375 |  |  | 2384.5 |  |  | 2265.5 |  |  | 2514 |  |  | 2532 |  |  | 2442 |  |  | 2480.5 |  |  | 2411 |  |  | 2265 |  |  | 2333 |  |  | 2581.5 |  |  | 2376.5 |  |  | 2398.5 |  |  | 2441 |  |  | 2468 |  |  | 2445 |  |  | 2327.5 |  |  | 2492 |  |  | 2345.5 |  |  | 2291 |  |  | 2285 |  |  | 2383 |  |  | 2350.5 |  |  | 2459.5 |  |  | 2413 |  |  | 2412 |  |  | 2464.5 |  |  | 2451 |  |  | 2326 |  |  | 2456.5 |  |  | 2243 |  |  | 2291 |  |  | 2457.5 |  |  | 2307 |  |  | 2442 |  |  | 2354.5 |  |  | 2520 |  |  | 2289.5 |  |  | 2419 |  |  | 2192.5 |  |  | 2481.5 |  |  | 2272 |  |  | 2445 |  |  | 2518.5 |  |  | 2357.5 |  |  | 2487 |  |  | 2431 |  |  | 2372 |  |  | 2443.5 |  |  | 2494 |  |  | 2204 |  |  | 2324 |  |  | 2476.5 |  |  | 2461.5 |  |  | 2440 |  |  | 2474 |  |  | 2380 |  |  | 2371 |  |  | 2494 |  |  | 2377 |  |  | 2390 |  |  | 2401.5 |  |  | 2581.5 |  |  | 2312.5 |  |  | 2347 |  |  | 2332.5 |  |  | 2433 |  |  | 2383 |  |  | 2423.5 |  |  | 2273.5 |  |  | 2336 |  |  | 2435 |  |  | 2349.5 |  |  | 2343 |  |  | 2438 |  |  | 2235.5 |  |  | 2508.5 |  |  | 2359 |  |  | 2364 |  |  | 2399 |  |  | 2272.5 |  |  | 2329 |  |  | 2281 |  |  | 2392 |  |  | 2418 |  |  | 2534 |  |  | 2303.5 |  |  | 2500 |  |  | 2397 |  |  | 2289 |  |  | 2506.5 |  |  | 2424 |  |  | 2302.5 |  |  | 2283.5 |  |  | 2355 |  |  | 2471 |  |  | 2406.5 |  |  | 2297.5 |  |  | 2340.5 |  |  | 2365.5 |  |  | 2411.5 |  |  | 2401 |  |  | 2368 |  |  | 2406.5 |  |  | 2358.5 |  |  | 2387 |  |  | 2303 |  |  | 2391.5 |  |  | 2587 |  |  | 2361 |  |  | 2309 |  |  | 2447.5 |  |  | 2530 |  |  | 2335.5 |  |  | 2265 |  |  | 2440.5 |  |  | 2623.5 |  |  | 2526.5 |  |  | 2532 |  |  | 2438 |  |  | 2394.5 |  |  | 2356.5 |  |  | 2470 |  |  | 2436 |  |  | 2438.5 |  |  | 2564 |  |  | 2410.5 |  |  | 2402.5 |  |  | 2388 |  |  | 2381 |  |  | 2260.5 |  |  | 2479.5 |  |  | 2433 |  |  | 2349.5 |  |  | 2442.5 |  |  | 2439 |  |  | 2474 |  |  | 2470 |  |  | 2417.5 |  |  | 2496 |  |  | 2302 |  |  | 2430 |  |  | 2313 |  |  | 2393 |  |  | 2356 |  |  | 2557.5 |  |  | 2379.5 |  |  | 2400 |  |  | 2329 |  |  | 2440 |  |  | 2329.5 |  |  | 2362 |  |  | 2523 |  |  | 2387.5 |  |  | 2482.5 |  |  | 2385 |  |  | 2369.5 |  |  | 2514 |  |  | 2252 |  |  | 2394 |  |  | 2493.5 |  |  | 2474 |  |  | 2300.5 |  |  | 2373.5 |  |  | 2243 |  |  | 2405.5 |  |  | 2185.5 |  |  | 2391 |  |  | 2302 |  |  | 2475 |  |  | 2304.5 |  |  | 2314 |  |  | 2333.5 |  |  | 2474.5 |  |  | 2509 |  |  | 2288.5 |  |  | 2298 |  |  | 2377 |  |  | 2361 |  |  | 2365 |  |  | 2261 |  |  | 2485.5 |  |  | 2352 |  |  | 2520 |  |  | 2343 |  |  | 2517 |  |  | 2420.5 |  |  | 2414.5 |  |  | 2412 |  |  | 2502 |  |  | 2391 |  |  | 2410 |  |  | 2438 |  |  | 2287.5 |  |  | 2401 |  |  | 2478.5 |  |  | 2518 |  |  | 2226 |  |  | 2385 |  |  | 2415 |  |  | 2468.5 |  |  | 2365 |  |  | 2433.5 |  |  | 2326 |  |  | 2545 |  |  | 2447 |  |  | 2422.5 |  |  | 2275 |  |  | 2272 |  |  | 2355 |  |  | 2538 |  |  | 2653 |  |  | 2367.5 |  |  | 2463.5 |  |  | 2311 |  |  | 2351.5 |  |  | 2324 |  |  | 2344.5 |  |  | 2357.5 |  |  | 2336.5 |  |  | 2321.5 |  |  | 2271 |  |  | 2571 |  |  | 2318 |  |  | 2302 |  |  | 2382 |  |  | 2488 |  |  | 2399.5 |  |  | 2375.5 |  |  | 2568.5 |  |  | 2387 |  |  | 2516.5 |  |  | 2312.5 |  |  | 2484.5 |  |  | 2285.5 |  |  | 2402 |  |  | 2431.5 |  |  | 2447.5 |  |  | 2520 |  |  | 2245.5 |  |  | 2542.5 |  |  | 2437.5 |  |  | 2557 |  |  | 2433.5 |  |  | 2473 |  |  | 2437 |  |  | 2387.5 |  |  | 2472.5 |  |  | 2457 |  |  | 2493 |  |  | 2235.5 |  |  | 2265.5 |  |  | 2350.5 |  |  | 2448 |  |  | 2335 |  |  | 2412 |  |  | 2498.5 |  |  | 2500.5 |  |  | 2432 |  |  | 2439.5 |  |  | 2246 |  |  | 2388 |  |  | 2418.5 |  |  | 2287.5 |  |  | 2341 |  |  | 2377.5 |  |  | 2488 |  |  | 2313.5 |  |  | 2493.5 |  |  | 2491 |  |  | 2451.5 |  |  | 2484 |  |  | 2365.5 |  |  | 2396 |  |  | 2437 |  |  | 2456 |  |  | 2339.5 |  |  | 2293.5 |  |  | 2436 |  |  | 2330 |  |  | 2303 |  |  | 2335.5 |  |  | 2431.5 |  |  | 2520 |  |  | 2419.5 |  |  | 2340 |  |  | 2251.5 |  |  | 2441.5 |  |  | 2315 |  |  | 2333 |  |  | 2355 |  |  | 2403.5 |  |  | 2315 |  |  | 2434.5 |  |  | 2416 |  |  | 2351.5 |  |  | 2597 |  |  | 2255.5 |  |  | 2370 |  |  | 2398.5 |  |  | 2392.5 |  |  | 2344 |  |  | 2361 |  |  | 2623 |  |  | 2397 |  |  | 2483.5 |  |  | 2338 |  |  | 2350.5 |  |  | 2279 |  |  | 2299 |  |  | 2366 |  |  | 2549 |  |  | 2444 |  |  | 2376 |  |  | 2478 |  |  | 2332.5 |  |  | 2333 |  |  | 2450
84 |  | 2568.5 |  |  | 2526 |  |  | 2543.5 |  |  | 2458 |  |  | 2312.5 |  |  | 2535 |  |  | 2525 |  |  | 2436 |  |  | 2312.5 |  |  | 2313 |  |  | 2394 |  |  | 2576 |  |  | 2507 |  |  | 2593 |  |  | 2335.5 |  |  | 2486.5 |  |  | 2400 |  |  | 2476 |  |  | 2565 |  |  | 2356.5 |  |  | 2479 |  |  | 2500 |  |  | 2320 |  |  | 2428 |  |  | 2427.5 |  |  | 2562 |  |  | 2364 |  |  | 2458 |  |  | 2525 |  |  | 2295 |  |  | 2438 |  |  | 2368.5 |  |  | 2509.5 |  |  | 2424.5 |  |  | 2414 |  |  | 2440.5 |  |  | 2457.5 |  |  | 2529.5 |  |  | 2554 |  |  | 2469 |  |  | 2273.5 |  |  | 2384 |  |  | 2440.5 |  |  | 2366.5 |  |  | 2486.5 |  |  | 2603.5 |  |  | 2599.5 |  |  | 2388 |  |  | 2256 |  |  | 2375.5 |  |  | 2399 |  |  | 2391.5 |  |  | 2331.5 |  |  | 2420 |  |  | 2410 |  |  | 2363 |  |  | 2323 |  |  | 2500 |  |  | 2466 |  |  | 2447.5 |  |  | 2423.5 |  |  | 2423.5 |  |  | 2354 |  |  | 2470 |  |  | 2254 |  |  | 2380.5 |  |  | 2423 |  |  | 2395.5 |  |  | 2544.5 |  |  | 2533.5 |  |  | 2458 |  |  | 2523 |  |  | 2536 |  |  | 2439.5 |  |  | 2514.5 |  |  | 2447.5 |  |  | 2545.5 |  |  | 2478.5 |  |  | 2493.5 |  |  | 2452.5 |  |  | 2351.5 |  |  | 2257 |  |  | 2567 |  |  | 2349 |  |  | 2515.5 |  |  | 2530 |  |  | 2387.5 |  |  | 2510 |  |  | 2447 |  |  | 2444.5 |  |  | 2578.5 |  |  | 2370 |  |  | 2507 |  |  | 2363.5 |  |  | 2609 |  |  | 2379.5 |  |  | 2443.5 |  |  | 2472.5 |  |  | 2373.5 |  |  | 2327.5 |  |  | 2379 |  |  | 2428 |  |  | 2268 |  |  | 2375.5 |  |  | 2422.5 |  |  | 2421.5 |  |  | 2328.5 |  |  | 2403 |  |  | 2376 |  |  | 2463.5 |  |  | 2381 |  |  | 2484.5 |  |  | 2459 |  |  | 2388 |  |  | 2357.5 |  |  | 2442 |  |  | 2417 |  |  | 2337 |  |  | 2475 |  |  | 2415.5 |  |  | 2429.5 |  |  | 2350.5 |  |  | 2542 |  |  | 2381 |  |  | 2347 |  |  | 2380 |  |  | 2358.5 |  |  | 2453 |  |  | 2469.5 |  |  | 2434 |  |  | 2277 |  |  | 2431.5 |  |  | 2336.5 |  |  | 2314 |  |  | 2339.5 |  |  | 2435 |  |  | 2528 |  |  | 2383 |  |  | 2546 |  |  | 2350 |  |  | 2364 |  |  | 2357 |  |  | 2459 |  |  | 2304 |  |  | 2318.5 |  |  | 2365 |  |  | 2361 |  |  | 2558 |  |  | 2465 |  |  | 2405 |  |  | 2301 |  |  | 2411 |  |  | 2437.5 |  |  | 2414 |  |  | 2428.5 |  |  | 2440 |  |  | 2376 |  |  | 2505.5 |  |  | 2437 |  |  | 2542.5 |  |  | 2388 |  |  | 2242 |  |  | 2398.5 |  |  | 2504 |  |  | 2539.5 |  |  | 2510 |  |  | 2303 |  |  | 2467.5 |  |  | 2494.5 |  |  | 2454 |  |  | 2437.5 |  |  | 2405.5 |  |  | 2404 |  |  | 2483 |  |  | 2571.5 |  |  | 2299.5 |  |  | 2488.5 |  |  | 2455 |  |  | 2496 |  |  | 2410 |  |  | 2524 |  |  | 2536 |  |  | 2408.5 |  |  | 2403 |  |  | 2320.5 |  |  | 2434.5 |  |  | 2415 |  |  | 2491 |  |  | 2649.5 |  |  | 2311.5 |  |  | 2387 |  |  | 2487.5 |  |  | 2323.5 |  |  | 2460 |  |  | 2326 |  |  | 2385 |  |  | 2367.5 |  |  | 2486 |  |  | 2418.5 |  |  | 2547.5 |  |  | 2378 |  |  | 2351.5 |  |  | 2384 |  |  | 2378 |  |  | 2495 |  |  | 2532 |  |  | 2230 |  |  | 2536 |  |  | 2565 |  |  | 2416 |  |  | 2519 |  |  | 2377 |  |  | 2427.5 |  |  | 2570.5 |  |  | 2358 |  |  | 2311 |  |  | 2533 |  |  | 2440.5 |  |  | 2525.5 |  |  | 2576.5 |  |  | 2352 |  |  | 2412 |  |  | 2561.5 |  |  | 2459.5 |  |  | 2278.5 |  |  | 2501 |  |  | 2547 |  |  | 2409 |  |  | 2482 |  |  | 2391 |  |  | 2441.5 |  |  | 2358.5 |  |  | 2535 |  |  | 2368 |  |  | 2363 |  |  | 2535 |  |  | 2369 |  |  | 2554.5 |  |  | 2479 |  |  | 2391 |  |  | 2333 |  |  | 2392 |  |  | 2430.5 |  |  | 2533 |  |  | 2430 |  |  | 2384 |  |  | 2523 |  |  | 2498.5 |  |  | 2451 |  |  | 2382 |  |  | 2343 |  |  | 2511.5 |  |  | 2443.5 |  |  | 2530.5 |  |  | 2530 |  |  | 2411 |  |  | 2282 |  |  | 2608 |  |  | 2400 |  |  | 2364.5 |  |  | 2529 |  |  | 2398.5 |  |  | 2481.5 |  |  | 2473.5 |  |  | 2454 |  |  | 2569.5 |  |  | 2330 |  |  | 2288 |  |  | 2384.5 |  |  | 2423.5 |  |  | 2493 |  |  | 2492.5 |  |  | 2580.5 |  |  | 2368 |  |  | 2503 |  |  | 2337.5 |  |  | 2410.5 |  |  | 2579 |  |  | 2500.5 |  |  | 2544 |  |  | 2446 |  |  | 2361.5 |  |  | 2487 |  |  | 2328 |  |  | 2458.5 |  |  | 2401 |  |  | 2581.5 |  |  | 2434 |  |  | 2613 |  |  | 2460 |  |  | 2403 |  |  | 2559.5 |  |  | 2550 |  |  | 2545.5 |  |  | 2308.5 |  |  | 2565.5 |  |  | 2490 |  |  | 2479.5 |  |  | 2605 |  |  | 2473 |  |  | 2263.5 |  |  | 2412.5 |  |  | 2488 |  |  | 2407.5 |  |  | 2612 |  |  | 2378 |  |  | 2588.5 |  |  | 2387 |  |  | 2400.5 |  |  | 2422.5 |  |  | 2482.5 |  |  | 2432 |  |  | 2279 |  |  | 2348 |  |  | 2399.5 |  |  | 2373 |  |  | 2598.5 |  |  | 2491 |  |  | 2430 |  |  | 2372 |  |  | 2446 |  |  | 2534 |  |  | 2435 |  |  | 2417 |  |  | 2635 |  |  | 2432 |  |  | 2426.5 |  |  | 2506 |  |  | 2431 |  |  | 2490.5 |  |  | 2345.5 |  |  | 2405.5 |  |  | 2398.5 |  |  | 2437 |  |  | 2543 |  |  | 2235.5 |  |  | 2627.5 |  |  | 2379.5 |  |  | 2445 |  |  | 2443 |  |  | 2342 |  |  | 2422 |  |  | 2273 |  |  | 2497 |  |  | 2466 |  |  | 2434.5 |  |  | 2472.5 |  |  | 2344 |  |  | 2345.5 |  |  | 2458.5 |  |  | 2377 |  |  | 2433 |  |  | 2376 |  |  | 2468 |  |  | 2374.5 |  |  | 2331.5 |  |  | 2469.5 |  |  | 2351 |  |  | 2360.5 |  |  | 2463 |  |  | 2402 |  |  | 2534 |  |  | 2388.5 |  |  | 2378 |  |  | 2313 |  |  | 2445.5 |  |  | 2340 |  |  | 2489.5 |  |  | 2583 |  |  | 2467.5 |  |  | 2399 |  |  | 2355.5 |  |  | 2456.5 |  |  | 2515 |  |  | 2447 |  |  | 2255 |  |  | 2415 |  |  | 2283.5 |  |  | 2382 |  |  | 2589 |  |  | 2345.5 |  |  | 2558.5 |  |  | 2285.5 |  |  | 2328 |  |  | 2522.5 |  |  | 2513.5 |  |  | 2327.5 |  |  | 2521 |  |  | 2451 |  |  | 2521.5 |  |  | 2486 |  |  | 2621 |  |  | 2476.5 |  |  | 2418 |  |  | 2504 |  |  | 2406 |  |  | 2308 |  |  | 2292.5 |  |  | 2466.5 |  |  | 2365 |  |  | 2548 |  |  | 2454 |  |  | 2402 |  |  | 2450 |  |  | 2418.5 |  |  | 2346.5 |  |  | 2468 |  |  | 2583 |  |  | 2571 |  |  | 2362.5 |  |  | 2640.5 |  |  | 2334 |  |  | 2450 |  |  | 2244 |  |  | 2465.5 |  |  | 2540.5 |  |  | 2442 |  |  | 2293 |  |  | 2485 |  |  | 2426 |  |  | 2375 |  |  | 2577 |  |  | 2401 |  |  | 2607.5 |  |  | 2398 |  |  | 2544 |  |  | 2438 |  |  | 2475.5 |  |  | 2507 |  |  | 2375 |  |  | 2271 |  |  | 2401 |  |  | 2386 |  |  | 2459 |  |  | 2452 |  |  | 2387.5 |  |  | 2397.5 |  |  | 2289.5 |  |  | 2552 |  |  | 2375 |  |  | 2435.5 |  |  | 2256 |  |  | 2346.5 |  |  | 2432.5 |  |  | 2393 |  |  | 2488 |  |  | 2456.5 |  |  | 2429 |  |  | 2489 |  |  | 2455 |  |  | 2419 |  |  | 2483 |  |  | 2378 |  |  | 2363 |  |  | 2458.5 |  |  | 2399 |  |  | 2503 |  |  | 2495 |  |  | 2453 |  |  | 2392 |  |  | 2419 |  |  | 2537 |  |  | 2516 |  |  | 2433 |  |  | 2505.5 |  |  | 2446.5 |  |  | 2433.5 |  |  | 2470.5 |  |  | 2460 |  |  | 2247 |  |  | 2530.5 |  |  | 2325 |  |  | 2416 |  |  | 2301.5 |  |  | 2563.5 |  |  | 2463 |  |  | 2418.5 |  |  | 2428.5 |  |  | 2262 |  |  | 2563 |  |  | 2348 |  |  | 2447 |  |  | 2392.5 |  |  | 2463 |  |  | 2358.5 |  |  | 2348.5 |  |  | 2427 |  |  | 2380 |  |  | 2510.5 |  |  | 2384 |  |  | 2416.5 |  |  | 2441 |  |  | 2460.5 |  |  | 2320.5 |  |  | 2236.5 |  |  | 2583.5 |  |  | 2443.5 |  |  | 2255 |  |  | 2373 |  |  | 2505.5 |  |  | 2430 |  |  | 2362 |  |  | 2422 |  |  | 2578 |  |  | 2521.5 |  |  | 2237 |  |  | 2321 |  |  | 2508 |  |  | 2392.5 |  |  | 2421 |  |  | 2324 |  |  | 2394 |  |  | 2617.5 |  |  | 2522 |  |  | 2246 |  |  | 2453 |  |  | 2541 |  |  | 2660.5 |  |  | 2419 |  |  | 2334.5 |  |  | 2433 |  |  | 2488 |  |  | 2656.5 |  |  | 2458 |  |  | 2392 |  |  | 2373.5 |  |  | 2445 |  |  | 2333 |  |  | 2376 |  |  | 2728.5 |  |  | 2489.5 |  |  | 2475 |  |  | 2353 |  |  | 2402.5 |  |  | 2444.5 |  |  | 2441 |  |  | 2484 |  |  | 2510.5 |  |  | 2630.5 |  |  | 2339.5 |  |  | 2508.5 |  |  | 2365.5 |  |  | 2637 |  |  | 2351.5 |  |  | 2568 |  |  | 2396 |  |  | 2547 |  |  | 2566 |  |  | 2454.5 |  |  | 2411 |  |  | 2362 |  |  | 2415.5 |  |  | 2462.5 |  |  | 2342 |  |  | 2504.5 |  |  | 2377.5 |  |  | 2512 |  |  | 2372 |  |  | 2417 |  |  | 2433.5 |  |  | 2488 |  |  | 2503.5 |  |  | 2507 |  |  | 2476 |  |  | 2692.5 |  |  | 2374 |  |  | 2548 |  |  | 2325 |  |  | 2531 |  |  | 2548 |  |  | 2440 |  |  | 2452 |  |  | 2417 |  |  | 2334.5 |  |  | 2370.5 |  |  | 2380 |  |  | 2439.5 |  |  | 2293.5 |  |  | 2348 |  |  | 2371 |  |  | 2489 |  |  | 2518.5 |  |  | 2346.5 |  |  | 2476 |  |  | 2441 |  |  | 2330 |  |  | 2327 |  |  | 2405 |  |  | 2311 |  |  | 2449 |  |  | 2362.5 |  |  | 2522 |  |  | 2526 |  |  | 2512 |  |  | 2324 |  |  | 2295 |  |  | 2365.5 |  |  | 2619.5 |  |  | 2281.5 |  |  | 2325 |  |  | 2328 |  |  | 2346.5 |  |  | 2490.5 |  |  | 2470.5 |  |  | 2316 |  |  | 2514.5 |  |  | 2496.5 |  |  | 2514 |  |  | 2453.5 |  |  | 2484.5 |  |  | 2413 |  |  | 2290 |  |  | 2391 |  |  | 2533 |  |  | 2363 |  |  | 2267 |  |  | 2500 |  |  | 2521 |  |  | 2295 |  |  | 2427 |  |  | 2534.5 |  |  | 2400 |  |  | 2413 |  |  | 2363 |  |  | 2295.5 |  |  | 2329 |  |  | 2445.5 |  |  | 2554 |  |  | 2504 |  |  | 2426 |  |  | 2449 |  |  | 2543.5 |  |  | 2406 |  |  | 2294 |  |  | 2486.5 |  |  | 2444 |  |  | 2368 |  |  | 2378.5 |  |  | 2376.5 |  |  | 2376 |  |  | 2336.5 |  |  | 2528 |  |  | 2350.5 |  |  | 2535 |  |  | 2480 |  |  | 2372.5 |  |  | 2489.5 |  |  | 2464 |  |  | 2491 |  |  | 2436 |  |  | 2448 |  |  | 2372 |  |  | 2393 |  |  | 2302 |  |  | 2329 |  |  | 2480.5 |  |  | 2265 |  |  | 2515.5 |  |  | 2345 |  |  | 2471.5 |  |  | 2392.5 |  |  | 2410 |  |  | 2497 |  |  | 2495.5 |  |  | 2437 |  |  | 2483 |  |  | 2529 |  |  | 2395.5 |  |  | 2479 |  |  | 2338.5 |  |  | 2222 |  |  | 2358 |  |  | 2362 |  |  | 2456 |  |  | 2517.5 |  |  | 2378 |  |  | 2422 |  |  | 2518 |  |  | 2348.5 |  |  | 2609 |  |  | 2529 |  |  | 2471 |  |  | 2422 |  |  | 2431.5 |  |  | 2291.5 |  |  | 2553 |  |  | 2558 |  |  | 2481 |  |  | 2519.5 |  |  | 2450 |  |  | 2304 |  |  | 2348 |  |  | 2620.5 |  |  | 2402.5 |  |  | 2419.5 |  |  | 2465 |  |  | 2483 |  |  | 2492 |  |  | 2366.5 |  |  | 2518 |  |  | 2360.5 |  |  | 2306 |  |  | 2324 |  |  | 2398 |  |  | 2389.5 |  |  | 2474.5 |  |  | 2452 |  |  | 2441 |  |  | 2511.5 |  |  | 2466 |  |  | 2350 |  |  | 2471.5 |  |  | 2269 |  |  | 2312 |  |  | 2481.5 |  |  | 2322 |  |  | 2489 |  |  | 2393.5 |  |  | 2549 |  |  | 2336.5 |  |  | 2448 |  |  | 2231.5 |  |  | 2507.5 |  |  | 2319 |  |  | 2484 |  |  | 2557.5 |  |  | 2372.5 |  |  | 2513 |  |  | 2457 |  |  | 2419 |  |  | 2469.5 |  |  | 2509 |  |  | 2228 |  |  | 2353 |  |  | 2515.5 |  |  | 2482.5 |  |  | 2466 |  |  | 2495 |  |  | 2406 |  |  | 2392 |  |  | 2509 |  |  | 2416 |  |  | 2414 |  |  | 2440.5 |  |  | 2605.5 |  |  | 2351.5 |  |  | 2373 |  |  | 2371.5 |  |  | 2454 |  |  | 2422 |  |  | 2438.5 |  |  | 2294.5 |  |  | 2365 |  |  | 2474 |  |  | 2375.5 |  |  | 2382 |  |  | 2485 |  |  | 2259.5 |  |  | 2537.5 |  |  | 2398 |  |  | 2403 |  |  | 2428 |  |  | 2298.5 |  |  | 2368 |  |  | 2305 |  |  | 2418 |  |  | 2465 |  |  | 2573 |  |  | 2342.5 |  |  | 2524 |  |  | 2444 |  |  | 2304 |  |  | 2527.5 |  |  | 2450 |  |  | 2317.5 |  |  | 2304.5 |  |  | 2394 |  |  | 2510 |  |  | 2430.5 |  |  | 2326.5 |  |  | 2369.5 |  |  | 2394.5 |  |  | 2435.5 |  |  | 2440 |  |  | 2407 |  |  | 2427.5 |  |  | 2397.5 |  |  | 2408 |  |  | 2332 |  |  | 2412.5 |  |  | 2626 |  |  | 2376 |  |  | 2324 |  |  | 2486.5 |  |  | 2577 |  |  | 2374.5 |  |  | 2286 |  |  | 2466.5 |  |  | 2638.5 |  |  | 2555.5 |  |  | 2553 |  |  | 2459 |  |  | 2441.5 |  |  | 2380.5 |  |  | 2509 |  |  | 2457 |  |  | 2485.5 |  |  | 2593 |  |  | 2439.5 |  |  | 2423.5 |  |  | 2409 |  |  | 2420 |  |  | 2299.5 |  |  | 2518.5 |  |  | 2459 |  |  | 2370.5 |  |  | 2463.5 |  |  | 2463 |  |  | 2503 |  |  | 2491 |  |  | 2443.5 |  |  | 2520 |  |  | 2341 |  |  | 2451 |  |  | 2334 |  |  | 2422 |  |  | 2395 |  |  | 2604.5 |  |  | 2405.5 |  |  | 2447 |  |  | 2358 |  |  | 2466 |  |  | 2368.5 |  |  | 2409 |  |  | 2562 |  |  | 2411.5 |  |  | 2521.5 |  |  | 2432 |  |  | 2384.5 |  |  | 2535 |  |  | 2299 |  |  | 2418 |  |  | 2532.5 |  |  | 2500 |  |  | 2315.5 |  |  | 2412.5 |  |  | 2282 |  |  | 2434.5 |  |  | 2206.5 |  |  | 2415 |  |  | 2341 |  |  | 2501 |  |  | 2343.5 |  |  | 2340 |  |  | 2359.5 |  |  | 2521.5 |  |  | 2524 |  |  | 2303.5 |  |  | 2322 |  |  | 2401 |  |  | 2408 |  |  | 2389 |  |  | 2282 |  |  | 2532.5 |  |  | 2399 |  |  | 2544 |  |  | 2372 |  |  | 2538 |  |  | 2459.5 |  |  | 2453.5 |  |  | 2451 |  |  | 2549 |  |  | 2406 |  |  | 2439 |  |  | 2467 |  |  | 2313.5 |  |  | 2425 |  |  | 2507.5 |  |  | 2533 |  |  | 2265 |  |  | 2424 |  |  | 2436 |  |  | 2483.5 |  |  | 2404 |  |  | 2480.5 |  |  | 2352 |  |  | 2560 |  |  | 2476 |  |  | 2437.5 |  |  | 2304 |  |  | 2287 |  |  | 2370 |  |  | 2585 |  |  | 2682 |  |  | 2382.5 |  |  | 2502.5 |  |  | 2350 |  |  | 2366.5 |  |  | 2363 |  |  | 2391.5 |  |  | 2372.5 |  |  | 2383.5 |  |  | 2360.5 |  |  | 2318 |  |  | 2610 |  |  | 2333 |  |  | 2326 |  |  | 2406 |  |  | 2514 |  |  | 2446.5 |  |  | 2401.5 |  |  | 2615.5 |  |  | 2416 |  |  | 2545.5 |  |  | 2351.5 |  |  | 2531.5 |  |  | 2306.5 |  |  | 2441 |  |  | 2455.5 |  |  | 2494.5 |  |  | 2546 |  |  | 2260.5 |  |  | 2581.5 |  |  | 2463.5 |  |  | 2586 |  |  | 2448.5 |  |  | 2497 |  |  | 2466 |  |  | 2411.5 |  |  | 2501.5 |  |  | 2478 |  |  | 2519 |  |  | 2282.5 |  |  | 2286.5 |  |  | 2389.5 |  |  | 2469 |  |  | 2361 |  |  | 2436 |  |  | 2537.5 |  |  | 2515.5 |  |  | 2453 |  |  | 2465.5 |  |  | 2293 |  |  | 2412 |  |  | 2465.5 |  |  | 2326.5 |  |  | 2356 |  |  | 2398.5 |  |  | 2509 |  |  | 2342.5 |  |  | 2517.5 |  |  | 2530 |  |  | 2472.5 |  |  | 2505 |  |  | 2404.5 |  |  | 2422 |  |  | 2476 |  |  | 2471 |  |  | 2378.5 |  |  | 2332.5 |  |  | 2451 |  |  | 2369 |  |  | 2318 |  |  | 2374.5 |  |  | 2446.5 |  |  | 2544 |  |  | 2445.5 |  |  | 2379 |  |  | 2272.5 |  |  | 2480.5 |  |  | 2344 |  |  | 2348 |  |  | 2376 |  |  | 2418.5 |  |  | 2336 |  |  | 2460.5 |  |  | 2455 |  |  | 2390.5 |  |  | 2621 |  |  | 2284.5 |  |  | 2385 |  |  | 2445.5 |  |  | 2431.5 |  |  | 2359 |  |  | 2387 |  |  | 2652 |  |  | 2444 |  |  | 2509.5 |  |  | 2367 |  |  | 2397.5 |  |  | 2300 |  |  | 2346 |  |  | 2413 |  |  | 2573 |  |  | 2483 |  |  | 2423 |  |  | 2507 |  |  | 2371.5 |  |  | 2357 |  |  | 2497
85 |  | 2589.5 |  |  | 2541 |  |  | 2582.5 |  |  | 2473 |  |  | 2336.5 |  |  | 2574 |  |  | 2554 |  |  | 2475 |  |  | 2338.5 |  |  | 2337 |  |  | 2423 |  |  | 2605 |  |  | 2546 |  |  | 2622 |  |  | 2359.5 |  |  | 2525.5 |  |  | 2429 |  |  | 2491 |  |  | 2580 |  |  | 2385.5 |  |  | 2518 |  |  | 2529 |  |  | 2359 |  |  | 2467 |  |  | 2466.5 |  |  | 2577 |  |  | 2403 |  |  | 2487 |  |  | 2572 |  |  | 2334 |  |  | 2453 |  |  | 2394.5 |  |  | 2533.5 |  |  | 2445.5 |  |  | 2429 |  |  | 2479.5 |  |  | 2504.5 |  |  | 2568.5 |  |  | 2569 |  |  | 2484 |  |  | 2312.5 |  |  | 2405 |  |  | 2464.5 |  |  | 2392.5 |  |  | 2507.5 |  |  | 2627.5 |  |  | 2614.5 |  |  | 2417 |  |  | 2285 |  |  | 2422.5 |  |  | 2423 |  |  | 2438.5 |  |  | 2346.5 |  |  | 2459 |  |  | 2425 |  |  | 2392 |  |  | 2344 |  |  | 2524 |  |  | 2481 |  |  | 2476.5 |  |  | 2470.5 |  |  | 2438.5 |  |  | 2375 |  |  | 2491 |  |  | 2293 |  |  | 2401.5 |  |  | 2470 |  |  | 2410.5 |  |  | 2565.5 |  |  | 2580.5 |  |  | 2497 |  |  | 2562 |  |  | 2557 |  |  | 2463.5 |  |  | 2540.5 |  |  | 2473.5 |  |  | 2584.5 |  |  | 2507.5 |  |  | 2522.5 |  |  | 2467.5 |  |  | 2366.5 |  |  | 2304 |  |  | 2588 |  |  | 2370 |  |  | 2539.5 |  |  | 2545 |  |  | 2434.5 |  |  | 2534 |  |  | 2468 |  |  | 2465.5 |  |  | 2602.5 |  |  | 2399 |  |  | 2522 |  |  | 2389.5 |  |  | 2656 |  |  | 2394.5 |  |  | 2490.5 |  |  | 2487.5 |  |  | 2412.5 |  |  | 2348.5 |  |  | 2400 |  |  | 2467 |  |  | 2315 |  |  | 2399.5 |  |  | 2437.5 |  |  | 2450.5 |  |  | 2354.5 |  |  | 2442 |  |  | 2391 |  |  | 2502.5 |  |  | 2396 |  |  | 2508.5 |  |  | 2480 |  |  | 2414 |  |  | 2404.5 |  |  | 2481 |  |  | 2464 |  |  | 2363 |  |  | 2514 |  |  | 2441.5 |  |  | 2468.5 |  |  | 2389.5 |  |  | 2568 |  |  | 2405 |  |  | 2376 |  |  | 2404 |  |  | 2397.5 |  |  | 2477 |  |  | 2490.5 |  |  | 2463 |  |  | 2306 |  |  | 2457.5 |  |  | 2383.5 |  |  | 2361 |  |  | 2365.5 |  |  | 2459 |  |  | 2543 |  |  | 2404 |  |  | 2585 |  |  | 2389 |  |  | 2379 |  |  | 2378 |  |  | 2474 |  |  | 2351 |  |  | 2357.5 |  |  | 2404 |  |  | 2382 |  |  | 2579 |  |  | 2504 |  |  | 2429 |  |  | 2330 |  |  | 2432 |  |  | 2466.5 |  |  | 2429 |  |  | 2467.5 |  |  | 2487 |  |  | 2405 |  |  | 2544.5 |  |  | 2476 |  |  | 2568.5 |  |  | 2412 |  |  | 2268 |  |  | 2422.5 |  |  | 2519 |  |  | 2560.5 |  |  | 2525 |  |  | 2327 |  |  | 2482.5 |  |  | 2520.5 |  |  | 2480 |  |  | 2458.5 |  |  | 2426.5 |  |  | 2451 |  |  | 2522 |  |  | 2586.5 |  |  | 2323.5 |  |  | 2517.5 |  |  | 2502 |  |  | 2535 |  |  | 2449 |  |  | 2563 |  |  | 2575 |  |  | 2447.5 |  |  | 2424 |  |  | 2349.5 |  |  | 2455.5 |  |  | 2436 |  |  | 2512 |  |  | 2675.5 |  |  | 2358.5 |  |  | 2402 |  |  | 2534.5 |  |  | 2352.5 |  |  | 2489 |  |  | 2365 |  |  | 2414 |  |  | 2388.5 |  |  | 2512 |  |  | 2465.5 |  |  | 2586.5 |  |  | 2425 |  |  | 2398.5 |  |  | 2399 |  |  | 2399 |  |  | 2534 |  |  | 2553 |  |  | 2269 |  |  | 2565 |  |  | 2594 |  |  | 2455 |  |  | 2548 |  |  | 2416 |  |  | 2466.5 |  |  | 2585.5 |  |  | 2397 |  |  | 2350 |  |  | 2562 |  |  | 2466.5 |  |  | 2551.5 |  |  | 2615.5 |  |  | 2376 |  |  | 2451 |  |  | 2587.5 |  |  | 2480.5 |  |  | 2307.5 |  |  | 2525 |  |  | 2562 |  |  | 2424 |  |  | 2508 |  |  | 2415 |  |  | 2465.5 |  |  | 2373.5 |  |  | 2574 |  |  | 2415 |  |  | 2402 |  |  | 2556 |  |  | 2393 |  |  | 2593.5 |  |  | 2505 |  |  | 2430 |  |  | 2348 |  |  | 2407 |  |  | 2451.5 |  |  | 2580 |  |  | 2451 |  |  | 2399 |  |  | 2552 |  |  | 2545.5 |  |  | 2490 |  |  | 2421 |  |  | 2367 |  |  | 2535.5 |  |  | 2467.5 |  |  | 2569.5 |  |  | 2569 |  |  | 2450 |  |  | 2297 |  |  | 2632 |  |  | 2426 |  |  | 2403.5 |  |  | 2544 |  |  | 2419.5 |  |  | 2520.5 |  |  | 2488.5 |  |  | 2475 |  |  | 2608.5 |  |  | 2345 |  |  | 2303 |  |  | 2423.5 |  |  | 2438.5 |  |  | 2532 |  |  | 2531.5 |  |  | 2604.5 |  |  | 2397 |  |  | 2527 |  |  | 2352.5 |  |  | 2431.5 |  |  | 2600 |  |  | 2547.5 |  |  | 2583 |  |  | 2461 |  |  | 2400.5 |  |  | 2511 |  |  | 2343 |  |  | 2482.5 |  |  | 2440 |  |  | 2596.5 |  |  | 2455 |  |  | 2634 |  |  | 2489 |  |  | 2427 |  |  | 2588.5 |  |  | 2571 |  |  | 2584.5 |  |  | 2347.5 |  |  | 2589.5 |  |  | 2511 |  |  | 2518.5 |  |  | 2644 |  |  | 2499 |  |  | 2284.5 |  |  | 2427.5 |  |  | 2514 |  |  | 2436.5 |  |  | 2651 |  |  | 2407 |  |  | 2627.5 |  |  | 2434 |  |  | 2424.5 |  |  | 2443.5 |  |  | 2497.5 |  |  | 2471 |  |  | 2318 |  |  | 2377 |  |  | 2446.5 |  |  | 2402 |  |  | 2637.5 |  |  | 2506 |  |  | 2456 |  |  | 2419 |  |  | 2467 |  |  | 2573 |  |  | 2450 |  |  | 2441 |  |  | 2661 |  |  | 2479 |  |  | 2465.5 |  |  | 2535 |  |  | 2460 |  |  | 2519.5 |  |  | 2371.5 |  |  | 2429.5 |  |  | 2445.5 |  |  | 2466 |  |  | 2564 |  |  | 2250.5 |  |  | 2656.5 |  |  | 2426.5 |  |  | 2471 |  |  | 2458 |  |  | 2366 |  |  | 2469 |  |  | 2302 |  |  | 2536 |  |  | 2505 |  |  | 2463.5 |  |  | 2493.5 |  |  | 2370 |  |  | 2366.5 |  |  | 2497.5 |  |  | 2401 |  |  | 2472 |  |  | 2405 |  |  | 2489 |  |  | 2400.5 |  |  | 2370.5 |  |  | 2498.5 |  |  | 2390 |  |  | 2407.5 |  |  | 2502 |  |  | 2441 |  |  | 2555 |  |  | 2403.5 |  |  | 2417 |  |  | 2339 |  |  | 2484.5 |  |  | 2387 |  |  | 2510.5 |  |  | 2612 |  |  | 2506.5 |  |  | 2423 |  |  | 2370.5 |  |  | 2495.5 |  |  | 2562 |  |  | 2486 |  |  | 2284 |  |  | 2462 |  |  | 2298.5 |  |  | 2411 |  |  | 2613 |  |  | 2369.5 |  |  | 2587.5 |  |  | 2306.5 |  |  | 2354 |  |  | 2551.5 |  |  | 2560.5 |  |  | 2353.5 |  |  | 2545 |  |  | 2475 |  |  | 2560.5 |  |  | 2510 |  |  | 2660 |  |  | 2491.5 |  |  | 2444 |  |  | 2530 |  |  | 2445 |  |  | 2334 |  |  | 2339.5 |  |  | 2490.5 |  |  | 2412 |  |  | 2572 |  |  | 2478 |  |  | 2428 |  |  | 2471 |  |  | 2433.5 |  |  | 2372.5 |  |  | 2492 |  |  | 2612 |  |  | 2592 |  |  | 2401.5 |  |  | 2669.5 |  |  | 2381 |  |  | 2476 |  |  | 2273 |  |  | 2480.5 |  |  | 2579.5 |  |  | 2463 |  |  | 2340 |  |  | 2500 |  |  | 2452 |  |  | 2422 |  |  | 2616 |  |  | 2430 |  |  | 2646.5 |  |  | 2422 |  |  | 2583 |  |  | 2467 |  |  | 2522.5 |  |  | 2531 |  |  | 2396 |  |  | 2318 |  |  | 2427 |  |  | 2407 |  |  | 2480 |  |  | 2467 |  |  | 2434.5 |  |  | 2418.5 |  |  | 2336.5 |  |  | 2567 |  |  | 2414 |  |  | 2474.5 |  |  | 2295 |  |  | 2370.5 |  |  | 2479.5 |  |  | 2432 |  |  | 2527 |  |  | 2495.5 |  |  | 2444 |  |  | 2513 |  |  | 2479 |  |  | 2466 |  |  | 2504 |  |  | 2393 |  |  | 2392 |  |  | 2487.5 |  |  | 2438 |  |  | 2550 |  |  | 2521 |  |  | 2477 |  |  | 2407 |  |  | 2466 |  |  | 2584 |  |  | 2542 |  |  | 2457 |  |  | 2544.5 |  |  | 2475.5 |  |  | 2454.5 |  |  | 2509.5 |  |  | 2489 |  |  | 2262 |  |  | 2577.5 |  |  | 2364 |  |  | 2442 |  |  | 2348.5 |  |  | 2592.5 |  |  | 2489 |  |  | 2457.5 |  |  | 2457.5 |  |  | 2309 |  |  | 2592 |  |  | 2372 |  |  | 2494 |  |  | 2431.5 |  |  | 2492 |  |  | 2405.5 |  |  | 2374.5 |  |  | 2442 |  |  | 2419 |  |  | 2549.5 |  |  | 2408 |  |  | 2442.5 |  |  | 2456 |  |  | 2489.5 |  |  | 2367.5 |  |  | 2260.5 |  |  | 2598.5 |  |  | 2482.5 |  |  | 2294 |  |  | 2397 |  |  | 2526.5 |  |  | 2454 |  |  | 2409 |  |  | 2448 |  |  | 2617 |  |  | 2560.5 |  |  | 2261 |  |  | 2368 |  |  | 2547 |  |  | 2416.5 |  |  | 2460 |  |  | 2339 |  |  | 2415 |  |  | 2664.5 |  |  | 2543 |  |  | 2293 |  |  | 2482 |  |  | 2580 |  |  | 2707.5 |  |  | 2458 |  |  | 2381.5 |  |  | 2457 |  |  | 2509 |  |  | 2682.5 |  |  | 2497 |  |  | 2418 |  |  | 2412.5 |  |  | 2469 |  |  | 2372 |  |  | 2391 |  |  | 2767.5 |  |  | 2504.5 |  |  | 2522 |  |  | 2374 |  |  | 2428.5 |  |  | 2468.5 |  |  | 2467 |  |  | 2531 |  |  | 2557.5 |  |  | 2656.5 |  |  | 2378.5 |  |  | 2523.5 |  |  | 2389.5 |  |  | 2666 |  |  | 2390.5 |  |  | 2583 |  |  | 2425 |  |  | 2586 |  |  | 2605 |  |  | 2475.5 |  |  | 2458 |  |  | 2383 |  |  | 2454.5 |  |  | 2491.5 |  |  | 2357 |  |  | 2551.5 |  |  | 2398.5 |  |  | 2541 |  |  | 2387 |  |  | 2438 |  |  | 2454.5 |  |  | 2517 |  |  | 2518.5 |  |  | 2536 |  |  | 2502 |  |  | 2721.5 |  |  | 2413 |  |  | 2569 |  |  | 2351 |  |  | 2570 |  |  | 2572 |  |  | 2469 |  |  | 2491 |  |  | 2456 |  |  | 2360.5 |  |  | 2396.5 |  |  | 2395 |  |  | 2478.5 |  |  | 2340.5 |  |  | 2387 |  |  | 2395 |  |  | 2515 |  |  | 2565.5 |  |  | 2367.5 |  |  | 2502 |  |  | 2480 |  |  | 2356 |  |  | 2374 |  |  | 2420 |  |  | 2350 |  |  | 2478 |  |  | 2391.5 |  |  | 2551 |  |  | 2565 |  |  | 2536 |  |  | 2350 |  |  | 2321 |  |  | 2412.5 |  |  | 2666.5 |  |  | 2305.5 |  |  | 2364 |  |  | 2367 |  |  | 2375.5 |  |  | 2519.5 |  |  | 2491.5 |  |  | 2340 |  |  | 2529.5 |  |  | 2535.5 |  |  | 2553 |  |  | 2492.5 |  |  | 2499.5 |  |  | 2434 |  |  | 2319 |  |  | 2412 |  |  | 2548 |  |  | 2402 |  |  | 2293 |  |  | 2539 |  |  | 2545 |  |  | 2319 |  |  | 2466 |  |  | 2581.5 |  |  | 2426 |  |  | 2452 |  |  | 2402 |  |  | 2334.5 |  |  | 2376 |  |  | 2466.5 |  |  | 2580 |  |  | 2551 |  |  | 2473 |  |  | 2475 |  |  | 2590.5 |  |  | 2445 |  |  | 2318 |  |  | 2533.5 |  |  | 2473 |  |  | 2389 |  |  | 2425.5 |  |  | 2400.5 |  |  | 2423 |  |  | 2383.5 |  |  | 2567 |  |  | 2397.5 |  |  | 2561 |  |  | 2509 |  |  | 2401.5 |  |  | 2504.5 |  |  | 2503 |  |  | 2530 |  |  | 2475 |  |  | 2463 |  |  | 2387 |  |  | 2419 |  |  | 2323 |  |  | 2368 |  |  | 2495.5 |  |  | 2294 |  |  | 2554.5 |  |  | 2366 |  |  | 2492.5 |  |  | 2413.5 |  |  | 2436 |  |  | 2536 |  |  | 2519.5 |  |  | 2476 |  |  | 2504 |  |  | 2555 |  |  | 2434.5 |  |  | 2518 |  |  | 2362.5 |  |  | 2246 |  |  | 2379 |  |  | 2401 |  |  | 2477 |  |  | 2538.5 |  |  | 2417 |  |  | 2443 |  |  | 2544 |  |  | 2363.5 |  |  | 2638 |  |  | 2550 |  |  | 2510 |  |  | 2448 |  |  | 2452.5 |  |  | 2317.5 |  |  | 2577 |  |  | 2584 |  |  | 2507 |  |  | 2534.5 |  |  | 2471 |  |  | 2333 |  |  | 2387 |  |  | 2635.5 |  |  | 2449.5 |  |  | 2466.5 |  |  | 2504 |  |  | 2507 |  |  | 2531 |  |  | 2387.5 |  |  | 2557 |  |  | 2386.5 |  |  | 2327 |  |  | 2371 |  |  | 2413 |  |  | 2413.5 |  |  | 2495.5 |  |  | 2473 |  |  | 2467 |  |  | 2532.5 |  |  | 2492 |  |  | 2371 |  |  | 2510.5 |  |  | 2293 |  |  | 2351 |  |  | 2507.5 |  |  | 2361 |  |  | 2504 |  |  | 2432.5 |  |  | 2573 |  |  | 2357.5 |  |  | 2463 |  |  | 2270.5 |  |  | 2522.5 |  |  | 2334 |  |  | 2508 |  |  | 2604.5 |  |  | 2387.5 |  |  | 2534 |  |  | 2483 |  |  | 2458 |  |  | 2508.5 |  |  | 2548 |  |  | 2252 |  |  | 2382 |  |  | 2544.5 |  |  | 2506.5 |  |  | 2487 |  |  | 2521 |  |  | 2453 |  |  | 2439 |  |  | 2530 |  |  | 2440 |  |  | 2438 |  |  | 2469.5 |  |  | 2631.5 |  |  | 2366.5 |  |  | 2388 |  |  | 2395.5 |  |  | 2475 |  |  | 2469 |  |  | 2453.5 |  |  | 2315.5 |  |  | 2391 |  |  | 2498 |  |  | 2404.5 |  |  | 2411 |  |  | 2514 |  |  | 2306.5 |  |  | 2558.5 |  |  | 2422 |  |  | 2427 |  |  | 2443 |  |  | 2324.5 |  |  | 2392 |  |  | 2344 |  |  | 2433 |  |  | 2504 |  |  | 2597 |  |  | 2357.5 |  |  | 2553 |  |  | 2465 |  |  | 2319 |  |  | 2551.5 |  |  | 2465 |  |  | 2346.5 |  |  | 2343.5 |  |  | 2409 |  |  | 2557 |  |  | 2454.5 |  |  | 2373.5 |  |  | 2390.5 |  |  | 2418.5 |  |  | 2464.5 |  |  | 2479 |  |  | 2436 |  |  | 2442.5 |  |  | 2421.5 |  |  | 2434 |  |  | 2353 |  |  | 2433.5 |  |  | 2665 |  |  | 2423 |  |  | 2353 |  |  | 2510.5 |  |  | 2606 |  |  | 2413.5 |  |  | 2310 |  |  | 2487.5 |  |  | 2653.5 |  |  | 2570.5 |  |  | 2592 |  |  | 2498 |  |  | 2480.5 |  |  | 2401.5 |  |  | 2524 |  |  | 2472 |  |  | 2506.5 |  |  | 2608 |  |  | 2463.5 |  |  | 2449.5 |  |  | 2433 |  |  | 2444 |  |  | 2314.5 |  |  | 2539.5 |  |  | 2506 |  |  | 2409.5 |  |  | 2492.5 |  |  | 2487 |  |  | 2542 |  |  | 2538 |  |  | 2472.5 |  |  | 2535 |  |  | 2370 |  |  | 2475 |  |  | 2373 |  |  | 2446 |  |  | 2419 |  |  | 2643.5 |  |  | 2444.5 |  |  | 2473 |  |  | 2397 |  |  | 2513 |  |  | 2392.5 |  |  | 2456 |  |  | 2586 |  |  | 2437.5 |  |  | 2568.5 |  |  | 2458 |  |  | 2410.5 |  |  | 2574 |  |  | 2346 |  |  | 2444 |  |  | 2558.5 |  |  | 2529 |  |  | 2330.5 |  |  | 2441.5 |  |  | 2311 |  |  | 2463.5 |  |  | 2253.5 |  |  | 2436 |  |  | 2370 |  |  | 2548 |  |  | 2382.5 |  |  | 2364 |  |  | 2374.5 |  |  | 2568.5 |  |  | 2548 |  |  | 2327.5 |  |  | 2361 |  |  | 2440 |  |  | 2434 |  |  | 2428 |  |  | 2311 |  |  | 2561.5 |  |  | 2423 |  |  | 2583 |  |  | 2401 |  |  | 2567 |  |  | 2483.5 |  |  | 2479.5 |  |  | 2490 |  |  | 2596 |  |  | 2427 |  |  | 2478 |  |  | 2482 |  |  | 2339.5 |  |  | 2440 |  |  | 2546.5 |  |  | 2548 |  |  | 2286 |  |  | 2463 |  |  | 2475 |  |  | 2522.5 |  |  | 2451 |  |  | 2519.5 |  |  | 2373 |  |  | 2599 |  |  | 2523 |  |  | 2484.5 |  |  | 2343 |  |  | 2311 |  |  | 2399 |  |  | 2611 |  |  | 2711 |  |  | 2429.5 |  |  | 2528.5 |  |  | 2371 |  |  | 2405.5 |  |  | 2402 |  |  | 2430.5 |  |  | 2401.5 |  |  | 2412.5 |  |  | 2407.5 |  |  | 2357 |  |  | 2649 |  |  | 2362 |  |  | 2347 |  |  | 2427 |  |  | 2529 |  |  | 2470.5 |  |  | 2422.5 |  |  | 2636.5 |  |  | 2455 |  |  | 2566.5 |  |  | 2366.5 |  |  | 2570.5 |  |  | 2335.5 |  |  | 2462 |  |  | 2484.5 |  |  | 2515.5 |  |  | 2567 |  |  | 2299.5 |  |  | 2620.5 |  |  | 2478.5 |  |  | 2612 |  |  | 2474.5 |  |  | 2544 |  |  | 2513 |  |  | 2440.5 |  |  | 2522.5 |  |  | 2502 |  |  | 2548 |  |  | 2321.5 |  |  | 2310.5 |  |  | 2410.5 |  |  | 2508 |  |  | 2376 |  |  | 2451 |  |  | 2576.5 |  |  | 2530.5 |  |  | 2474 |  |  | 2494.5 |  |  | 2332 |  |  | 2438 |  |  | 2480.5 |  |  | 2341.5 |  |  | 2395 |  |  | 2419.5 |  |  | 2548 |  |  | 2366.5 |  |  | 2556.5 |  |  | 2569 |  |  | 2487.5 |  |  | 2526 |  |  | 2451.5 |  |  | 2451 |  |  | 2491 |  |  | 2518 |  |  | 2417.5 |  |  | 2371.5 |  |  | 2466 |  |  | 2384 |  |  | 2357 |  |  | 2395.5 |  |  | 2472.5 |  |  | 2568 |  |  | 2484.5 |  |  | 2405 |  |  | 2301.5 |  |  | 2527.5 |  |  | 2359 |  |  | 2387 |  |  | 2397 |  |  | 2433.5 |  |  | 2362 |  |  | 2499.5 |  |  | 2476 |  |  | 2405.5 |  |  | 2636 |  |  | 2308.5 |  |  | 2406 |  |  | 2474.5 |  |  | 2470.5 |  |  | 2398 |  |  | 2402 |  |  | 2691 |  |  | 2465 |  |  | 2530.5 |  |  | 2388 |  |  | 2412.5 |  |  | 2339 |  |  | 2372 |  |  | 2452 |  |  | 2612 |  |  | 2522 |  |  | 2447 |  |  | 2536 |  |  | 2395.5 |  |  | 2404 |  |  | 2523
86 |  | 2628.5 |  |  | 2580 |  |  | 2621.5 |  |  | 2512 |  |  | 2357.5 |  |  | 2613 |  |  | 2575 |  |  | 2490 |  |  | 2367.5 |  |  | 2363 |  |  | 2438 |  |  | 2631 |  |  | 2567 |  |  | 2646 |  |  | 2398.5 |  |  | 2564.5 |  |  | 2476 |  |  | 2530 |  |  | 2619 |  |  | 2400.5 |  |  | 2565 |  |  | 2576 |  |  | 2398 |  |  | 2488 |  |  | 2505.5 |  |  | 2616 |  |  | 2418 |  |  | 2526 |  |  | 2601 |  |  | 2349 |  |  | 2477 |  |  | 2415.5 |  |  | 2572.5 |  |  | 2460.5 |  |  | 2450 |  |  | 2526.5 |  |  | 2543.5 |  |  | 2583.5 |  |  | 2593 |  |  | 2508 |  |  | 2338.5 |  |  | 2444 |  |  | 2490.5 |  |  | 2439.5 |  |  | 2531.5 |  |  | 2674.5 |  |  | 2635.5 |  |  | 2456 |  |  | 2324 |  |  | 2451.5 |  |  | 2449 |  |  | 2467.5 |  |  | 2385.5 |  |  | 2498 |  |  | 2451 |  |  | 2431 |  |  | 2373 |  |  | 2571 |  |  | 2496 |  |  | 2497.5 |  |  | 2485.5 |  |  | 2459.5 |  |  | 2414 |  |  | 2520 |  |  | 2319 |  |  | 2422.5 |  |  | 2496 |  |  | 2449.5 |  |  | 2586.5 |  |  | 2606.5 |  |  | 2526 |  |  | 2601 |  |  | 2596 |  |  | 2484.5 |  |  | 2579.5 |  |  | 2488.5 |  |  | 2623.5 |  |  | 2546.5 |  |  | 2551.5 |  |  | 2491.5 |  |  | 2392.5 |  |  | 2333 |  |  | 2617 |  |  | 2399 |  |  | 2563.5 |  |  | 2574 |  |  | 2449.5 |  |  | 2573 |  |  | 2492 |  |  | 2494.5 |  |  | 2631.5 |  |  | 2428 |  |  | 2543 |  |  | 2436.5 |  |  | 2677 |  |  | 2420.5 |  |  | 2514.5 |  |  | 2502.5 |  |  | 2433.5 |  |  | 2372.5 |  |  | 2424 |  |  | 2491 |  |  | 2336 |  |  | 2414.5 |  |  | 2476.5 |  |  | 2497.5 |  |  | 2393.5 |  |  | 2471 |  |  | 2415 |  |  | 2526.5 |  |  | 2420 |  |  | 2547.5 |  |  | 2501 |  |  | 2435 |  |  | 2433.5 |  |  | 2510 |  |  | 2488 |  |  | 2402 |  |  | 2538 |  |  | 2465.5 |  |  | 2483.5 |  |  | 2436.5 |  |  | 2583 |  |  | 2420 |  |  | 2415 |  |  | 2433 |  |  | 2436.5 |  |  | 2498 |  |  | 2511.5 |  |  | 2510 |  |  | 2335 |  |  | 2472.5 |  |  | 2412.5 |  |  | 2376 |  |  | 2394.5 |  |  | 2498 |  |  | 2567 |  |  | 2443 |  |  | 2624 |  |  | 2418 |  |  | 2426 |  |  | 2404 |  |  | 2498 |  |  | 2398 |  |  | 2396.5 |  |  | 2419 |  |  | 2397 |  |  | 2626 |  |  | 2528 |  |  | 2450 |  |  | 2356 |  |  | 2471 |  |  | 2481.5 |  |  | 2468 |  |  | 2506.5 |  |  | 2502 |  |  | 2434 |  |  | 2583.5 |  |  | 2515 |  |  | 2615.5 |  |  | 2427 |  |  | 2289 |  |  | 2461.5 |  |  | 2558 |  |  | 2575.5 |  |  | 2564 |  |  | 2342 |  |  | 2503.5 |  |  | 2544.5 |  |  | 2519 |  |  | 2497.5 |  |  | 2473.5 |  |  | 2477 |  |  | 2543 |  |  | 2625.5 |  |  | 2362.5 |  |  | 2543.5 |  |  | 2528 |  |  | 2561 |  |  | 2488 |  |  | 2589 |  |  | 2614 |  |  | 2462.5 |  |  | 2463 |  |  | 2388.5 |  |  | 2494.5 |  |  | 2457 |  |  | 2541 |  |  | 2699.5 |  |  | 2397.5 |  |  | 2417 |  |  | 2549.5 |  |  | 2367.5 |  |  | 2504 |  |  | 2404 |  |  | 2461 |  |  | 2414.5 |  |  | 2551 |  |  | 2504.5 |  |  | 2615.5 |  |  | 2472 |  |  | 2427.5 |  |  | 2446 |  |  | 2438 |  |  | 2549 |  |  | 2577 |  |  | 2295 |  |  | 2589 |  |  | 2609 |  |  | 2476 |  |  | 2587 |  |  | 2445 |  |  | 2505.5 |  |  | 2614.5 |  |  | 2444 |  |  | 2389 |  |  | 2601 |  |  | 2495.5 |  |  | 2590.5 |  |  | 2654.5 |  |  | 2400 |  |  | 2490 |  |  | 2611.5 |  |  | 2506.5 |  |  | 2354.5 |  |  | 2540 |  |  | 2586 |  |  | 2453 |  |  | 2534 |  |  | 2441 |  |  | 2504.5 |  |  | 2399.5 |  |  | 2613 |  |  | 2430 |  |  | 2431 |  |  | 2582 |  |  | 2414 |  |  | 2619.5 |  |  | 2544 |  |  | 2445 |  |  | 2387 |  |  | 2436 |  |  | 2490.5 |  |  | 2601 |  |  | 2475 |  |  | 2438 |  |  | 2581 |  |  | 2560.5 |  |  | 2514 |  |  | 2460 |  |  | 2406 |  |  | 2574.5 |  |  | 2514.5 |  |  | 2595.5 |  |  | 2590 |  |  | 2489 |  |  | 2336 |  |  | 2679 |  |  | 2447 |  |  | 2429.5 |  |  | 2565 |  |  | 2440.5 |  |  | 2559.5 |  |  | 2527.5 |  |  | 2501 |  |  | 2655.5 |  |  | 2374 |  |  | 2327 |  |  | 2447.5 |  |  | 2477.5 |  |  | 2561 |  |  | 2552.5 |  |  | 2651.5 |  |  | 2418 |  |  | 2553 |  |  | 2378.5 |  |  | 2457.5 |  |  | 2639 |  |  | 2562.5 |  |  | 2604 |  |  | 2500 |  |  | 2426.5 |  |  | 2558 |  |  | 2390 |  |  | 2521.5 |  |  | 2479 |  |  | 2622.5 |  |  | 2476 |  |  | 2663 |  |  | 2515 |  |  | 2451 |  |  | 2617.5 |  |  | 2586 |  |  | 2605.5 |  |  | 2394.5 |  |  | 2618.5 |  |  | 2537 |  |  | 2547.5 |  |  | 2668 |  |  | 2538 |  |  | 2310.5 |  |  | 2466.5 |  |  | 2553 |  |  | 2451.5 |  |  | 2666 |  |  | 2446 |  |  | 2666.5 |  |  | 2458 |  |  | 2463.5 |  |  | 2472.5 |  |  | 2521.5 |  |  | 2500 |  |  | 2365 |  |  | 2403 |  |  | 2472.5 |  |  | 2441 |  |  | 2652.5 |  |  | 2521 |  |  | 2477 |  |  | 2440 |  |  | 2491 |  |  | 2612 |  |  | 2471 |  |  | 2488 |  |  | 2676 |  |  | 2518 |  |  | 2480.5 |  |  | 2582 |  |  | 2475 |  |  | 2548.5 |  |  | 2386.5 |  |  | 2468.5 |  |  | 2460.5 |  |  | 2495 |  |  | 2590 |  |  | 2265.5 |  |  | 2680.5 |  |  | 2465.5 |  |  | 2518 |  |  | 2505 |  |  | 2405 |  |  | 2490 |  |  | 2341 |  |  | 2557 |  |  | 2552 |  |  | 2478.5 |  |  | 2532.5 |  |  | 2396 |  |  | 2395.5 |  |  | 2512.5 |  |  | 2427 |  |  | 2498 |  |  | 2452 |  |  | 2528 |  |  | 2439.5 |  |  | 2391.5 |  |  | 2537.5 |  |  | 2429 |  |  | 2454.5 |  |  | 2541 |  |  | 2467 |  |  | 2594 |  |  | 2418.5 |  |  | 2456 |  |  | 2365 |  |  | 2523.5 |  |  | 2413 |  |  | 2539.5 |  |  | 2627 |  |  | 2521.5 |  |  | 2462 |  |  | 2394.5 |  |  | 2516.5 |  |  | 2609 |  |  | 2515 |  |  | 2323 |  |  | 2501 |  |  | 2327.5 |  |  | 2458 |  |  | 2642 |  |  | 2408.5 |  |  | 2613.5 |  |  | 2335.5 |  |  | 2393 |  |  | 2590.5 |  |  | 2584.5 |  |  | 2392.5 |  |  | 2574 |  |  | 2496 |  |  | 2586.5 |  |  | 2549 |  |  | 2675 |  |  | 2512.5 |  |  | 2470 |  |  | 2569 |  |  | 2474 |  |  | 2355 |  |  | 2365.5 |  |  | 2529.5 |  |  | 2441 |  |  | 2619 |  |  | 2507 |  |  | 2475 |  |  | 2495 |  |  | 2454.5 |  |  | 2411.5 |  |  | 2507 |  |  | 2651 |  |  | 2639 |  |  | 2416.5 |  |  | 2708.5 |  |  | 2420 |  |  | 2502 |  |  | 2312 |  |  | 2527.5 |  |  | 2594.5 |  |  | 2492 |  |  | 2364 |  |  | 2539 |  |  | 2467 |  |  | 2437 |  |  | 2640 |  |  | 2456 |  |  | 2670.5 |  |  | 2461 |  |  | 2622 |  |  | 2496 |  |  | 2537.5 |  |  | 2560 |  |  | 2435 |  |  | 2357 |  |  | 2451 |  |  | 2422 |  |  | 2504 |  |  | 2506 |  |  | 2449.5 |  |  | 2444.5 |  |  | 2351.5 |  |  | 2588 |  |  | 2429 |  |  | 2489.5 |  |  | 2319 |  |  | 2409.5 |  |  | 2508.5 |  |  | 2458 |  |  | 2542 |  |  | 2534.5 |  |  | 2491 |  |  | 2534 |  |  | 2503 |  |  | 2513 |  |  | 2530 |  |  | 2432 |  |  | 2416 |  |  | 2534.5 |  |  | 2467 |  |  | 2589 |  |  | 2560 |  |  | 2492 |  |  | 2454 |  |  | 2505 |  |  | 2605 |  |  | 2566 |  |  | 2486 |  |  | 2573.5 |  |  | 2514.5 |  |  | 2475.5 |  |  | 2524.5 |  |  | 2528 |  |  | 2301 |  |  | 2606.5 |  |  | 2379 |  |  | 2489 |  |  | 2377.5 |  |  | 2616.5 |  |  | 2536 |  |  | 2483.5 |  |  | 2472.5 |  |  | 2335 |  |  | 2621 |  |  | 2411 |  |  | 2515 |  |  | 2470.5 |  |  | 2516 |  |  | 2444.5 |  |  | 2413.5 |  |  | 2466 |  |  | 2458 |  |  | 2573.5 |  |  | 2423 |  |  | 2471.5 |  |  | 2485 |  |  | 2536.5 |  |  | 2393.5 |  |  | 2281.5 |  |  | 2645.5 |  |  | 2508.5 |  |  | 2323 |  |  | 2423 |  |  | 2565.5 |  |  | 2493 |  |  | 2448 |  |  | 2487 |  |  | 2656 |  |  | 2589.5 |  |  | 2308 |  |  | 2389 |  |  | 2594 |  |  | 2445.5 |  |  | 2484 |  |  | 2354 |  |  | 2439 |  |  | 2685.5 |  |  | 2569 |  |  | 2319 |  |  | 2497 |  |  | 2606 |  |  | 2722.5 |  |  | 2482 |  |  | 2405.5 |  |  | 2496 |  |  | 2548 |  |  | 2703.5 |  |  | 2523 |  |  | 2439 |  |  | 2438.5 |  |  | 2495 |  |  | 2398 |  |  | 2406 |  |  | 2806.5 |  |  | 2525.5 |  |  | 2569 |  |  | 2413 |  |  | 2452.5 |  |  | 2489.5 |  |  | 2496 |  |  | 2555 |  |  | 2581.5 |  |  | 2680.5 |  |  | 2417.5 |  |  | 2562.5 |  |  | 2413.5 |  |  | 2705 |  |  | 2416.5 |  |  | 2604 |  |  | 2454 |  |  | 2612 |  |  | 2644 |  |  | 2496.5 |  |  | 2487 |  |  | 2398 |  |  | 2478.5 |  |  | 2506.5 |  |  | 2386 |  |  | 2580.5 |  |  | 2419.5 |  |  | 2565 |  |  | 2426 |  |  | 2485 |  |  | 2483.5 |  |  | 2532 |  |  | 2557.5 |  |  | 2565 |  |  | 2531 |  |  | 2742.5 |  |  | 2434 |  |  | 2584 |  |  | 2372 |  |  | 2599 |  |  | 2611 |  |  | 2498 |  |  | 2512 |  |  | 2471 |  |  | 2384.5 |  |  | 2411.5 |  |  | 2410 |  |  | 2507.5 |  |  | 2364.5 |  |  | 2402 |  |  | 2424 |  |  | 2541 |  |  | 2580.5 |  |  | 2388.5 |  |  | 2523 |  |  | 2519 |  |  | 2371 |  |  | 2403 |  |  | 2435 |  |  | 2397 |  |  | 2507 |  |  | 2412.5 |  |  | 2577 |  |  | 2604 |  |  | 2560 |  |  | 2365 |  |  | 2347 |  |  | 2459.5 |  |  | 2713.5 |  |  | 2329.5 |  |  | 2403 |  |  | 2414 |  |  | 2404.5 |  |  | 2540.5 |  |  | 2530.5 |  |  | 2369 |  |  | 2558.5 |  |  | 2574.5 |  |  | 2568 |  |  | 2513.5 |  |  | 2538.5 |  |  | 2463 |  |  | 2366 |  |  | 2438 |  |  | 2577 |  |  | 2423 |  |  | 2317 |  |  | 2568 |  |  | 2569 |  |  | 2366 |  |  | 2492 |  |  | 2620.5 |  |  | 2447 |  |  | 2481 |  |  | 2428 |  |  | 2358.5 |  |  | 2415 |  |  | 2505.5 |  |  | 2619 |  |  | 2590 |  |  | 2494 |  |  | 2514 |  |  | 2619.5 |  |  | 2484 |  |  | 2342 |  |  | 2554.5 |  |  | 2512 |  |  | 2404 |  |  | 2464.5 |  |  | 2447.5 |  |  | 2462 |  |  | 2398.5 |  |  | 2596 |  |  | 2444.5 |  |  | 2582 |  |  | 2535 |  |  | 2425.5 |  |  | 2551.5 |  |  | 2542 |  |  | 2556 |  |  | 2522 |  |  | 2478 |  |  | 2411 |  |  | 2448 |  |  | 2338 |  |  | 2415 |  |  | 2521.5 |  |  | 2320 |  |  | 2583.5 |  |  | 2387 |  |  | 2518.5 |  |  | 2439.5 |  |  | 2451 |  |  | 2562 |  |  | 2558.5 |  |  | 2497 |  |  | 2543 |  |  | 2576 |  |  | 2473.5 |  |  | 2557 |  |  | 2388.5 |  |  | 2270 |  |  | 2408 |  |  | 2416 |  |  | 2498 |  |  | 2577.5 |  |  | 2456 |  |  | 2472 |  |  | 2583 |  |  | 2384.5 |  |  | 2659 |  |  | 2565 |  |  | 2549 |  |  | 2477 |  |  | 2481.5 |  |  | 2343.5 |  |  | 2624 |  |  | 2610 |  |  | 2536 |  |  | 2558.5 |  |  | 2495 |  |  | 2372 |  |  | 2416 |  |  | 2656.5 |  |  | 2470.5 |  |  | 2481.5 |  |  | 2530 |  |  | 2554 |  |  | 2557 |  |  | 2416.5 |  |  | 2578 |  |  | 2412.5 |  |  | 2366 |  |  | 2392 |  |  | 2439 |  |  | 2428.5 |  |  | 2524.5 |  |  | 2512 |  |  | 2506 |  |  | 2556.5 |  |  | 2531 |  |  | 2400 |  |  | 2539.5 |  |  | 2319 |  |  | 2375 |  |  | 2546.5 |  |  | 2400 |  |  | 2543 |  |  | 2447.5 |  |  | 2599 |  |  | 2386.5 |  |  | 2478 |  |  | 2296.5 |  |  | 2569.5 |  |  | 2381 |  |  | 2529 |  |  | 2651.5 |  |  | 2413.5 |  |  | 2558 |  |  | 2504 |  |  | 2497 |  |  | 2547.5 |  |  | 2569 |  |  | 2291 |  |  | 2408 |  |  | 2591.5 |  |  | 2532.5 |  |  | 2511 |  |  | 2542 |  |  | 2500 |  |  | 2478 |  |  | 2569 |  |  | 2479 |  |  | 2485 |  |  | 2493.5 |  |  | 2655.5 |  |  | 2387.5 |  |  | 2409 |  |  | 2416.5 |  |  | 2522 |  |  | 2490 |  |  | 2500.5 |  |  | 2354.5 |  |  | 2417 |  |  | 2519 |  |  | 2451.5 |  |  | 2450 |  |  | 2535 |  |  | 2353.5 |  |  | 2587.5 |  |  | 2451 |  |  | 2448 |  |  | 2469 |  |  | 2350.5 |  |  | 2431 |  |  | 2365 |  |  | 2472 |  |  | 2543 |  |  | 2618 |  |  | 2372.5 |  |  | 2592 |  |  | 2494 |  |  | 2358 |  |  | 2577.5 |  |  | 2491 |  |  | 2375.5 |  |  | 2369.5 |  |  | 2433 |  |  | 2596 |  |  | 2483.5 |  |  | 2412.5 |  |  | 2416.5 |  |  | 2442.5 |  |  | 2493.5 |  |  | 2526 |  |  | 2475 |  |  | 2463.5 |  |  | 2468.5 |  |  | 2463 |  |  | 2400 |  |  | 2480.5 |  |  | 2689 |  |  | 2470 |  |  | 2374 |  |  | 2536.5 |  |  | 2653 |  |  | 2434.5 |  |  | 2339 |  |  | 2513.5 |  |  | 2668.5 |  |  | 2617.5 |  |  | 2618 |  |  | 2527 |  |  | 2509.5 |  |  | 2425.5 |  |  | 2563 |  |  | 2496 |  |  | 2545.5 |  |  | 2634 |  |  | 2489.5 |  |  | 2478.5 |  |  | 2454 |  |  | 2491 |  |  | 2361.5 |  |  | 2565.5 |  |  | 2553 |  |  | 2438.5 |  |  | 2513.5 |  |  | 2511 |  |  | 2589 |  |  | 2567 |  |  | 2487.5 |  |  | 2556 |  |  | 2399 |  |  | 2504 |  |  | 2402 |  |  | 2467 |  |  | 2458 |  |  | 2682.5 |  |  | 2470.5 |  |  | 2488 |  |  | 2423 |  |  | 2552 |  |  | 2407.5 |  |  | 2482 |  |  | 2612 |  |  | 2452.5 |  |  | 2607.5 |  |  | 2487 |  |  | 2425.5 |  |  | 2621 |  |  | 2367 |  |  | 2459 |  |  | 2579.5 |  |  | 2555 |  |  | 2356.5 |  |  | 2470.5 |  |  | 2350 |  |  | 2502.5 |  |  | 2292.5 |  |  | 2483 |  |  | 2385 |  |  | 2574 |  |  | 2429.5 |  |  | 2403 |  |  | 2421.5 |  |  | 2615.5 |  |  | 2587 |  |  | 2366.5 |  |  | 2387 |  |  | 2479 |  |  | 2449 |  |  | 2452 |  |  | 2350 |  |  | 2576.5 |  |  | 2470 |  |  | 2607 |  |  | 2425 |  |  | 2593 |  |  | 2522.5 |  |  | 2508.5 |  |  | 2511 |  |  | 2622 |  |  | 2474 |  |  | 2493 |  |  | 2521 |  |  | 2368.5 |  |  | 2455 |  |  | 2567.5 |  |  | 2569 |  |  | 2333 |  |  | 2510 |  |  | 2490 |  |  | 2543.5 |  |  | 2490 |  |  | 2558.5 |  |  | 2388 |  |  | 2625 |  |  | 2552 |  |  | 2523.5 |  |  | 2372 |  |  | 2358 |  |  | 2420 |  |  | 2640 |  |  | 2758 |  |  | 2468.5 |  |  | 2567.5 |  |  | 2395 |  |  | 2420.5 |  |  | 2449 |  |  | 2459.5 |  |  | 2448.5 |  |  | 2441.5 |  |  | 2422.5 |  |  | 2383 |  |  | 2673 |  |  | 2386 |  |  | 2362 |  |  | 2448 |  |  | 2555 |  |  | 2494.5 |  |  | 2443.5 |  |  | 2665.5 |  |  | 2479 |  |  | 2613.5 |  |  | 2390.5 |  |  | 2609.5 |  |  | 2356.5 |  |  | 2486 |  |  | 2499.5 |  |  | 2554.5 |  |  | 2593 |  |  | 2338.5 |  |  | 2644.5 |  |  | 2507.5 |  |  | 2651 |  |  | 2503.5 |  |  | 2568 |  |  | 2528 |  |  | 2455.5 |  |  | 2543.5 |  |  | 2528 |  |  | 2587 |  |  | 2336.5 |  |  | 2336.5 |  |  | 2439.5 |  |  | 2537 |  |  | 2405 |  |  | 2466 |  |  | 2615.5 |  |  | 2577.5 |  |  | 2498 |  |  | 2533.5 |  |  | 2371 |  |  | 2477 |  |  | 2504.5 |  |  | 2380.5 |  |  | 2410 |  |  | 2458.5 |  |  | 2595 |  |  | 2392.5 |  |  | 2595.5 |  |  | 2598 |  |  | 2508.5 |  |  | 2550 |  |  | 2472.5 |  |  | 2475 |  |  | 2515 |  |  | 2533 |  |  | 2464.5 |  |  | 2397.5 |  |  | 2513 |  |  | 2423 |  |  | 2378 |  |  | 2442.5 |  |  | 2496.5 |  |  | 2615 |  |  | 2499.5 |  |  | 2429 |  |  | 2316.5 |  |  | 2553.5 |  |  | 2383 |  |  | 2426 |  |  | 2436 |  |  | 2454.5 |  |  | 2401 |  |  | 2538.5 |  |  | 2523 |  |  | 2420.5 |  |  | 2662 |  |  | 2329.5 |  |  | 2453 |  |  | 2498.5 |  |  | 2494.5 |  |  | 2422 |  |  | 2441 |  |  | 2730 |  |  | 2494 |  |  | 2569.5 |  |  | 2427 |  |  | 2451.5 |  |  | 2378 |  |  | 2393 |  |  | 2481 |  |  | 2651 |  |  | 2546 |  |  | 2494 |  |  | 2575 |  |  | 2416.5 |  |  | 2451 |  |  | 2544
87 |  | 2649.5 |  |  | 2619 |  |  | 2642.5 |  |  | 2538 |  |  | 2404.5 |  |  | 2652 |  |  | 2614 |  |  | 2519 |  |  | 2388.5 |  |  | 2402 |  |  | 2464 |  |  | 2660 |  |  | 2606 |  |  | 2672 |  |  | 2413.5 |  |  | 2585.5 |  |  | 2491 |  |  | 2569 |  |  | 2658 |  |  | 2439.5 |  |  | 2604 |  |  | 2597 |  |  | 2437 |  |  | 2527 |  |  | 2544.5 |  |  | 2637 |  |  | 2447 |  |  | 2573 |  |  | 2640 |  |  | 2373 |  |  | 2524 |  |  | 2462.5 |  |  | 2598.5 |  |  | 2489.5 |  |  | 2471 |  |  | 2552.5 |  |  | 2567.5 |  |  | 2598.5 |  |  | 2622 |  |  | 2523 |  |  | 2377.5 |  |  | 2465 |  |  | 2505.5 |  |  | 2478.5 |  |  | 2555.5 |  |  | 2703.5 |  |  | 2650.5 |  |  | 2485 |  |  | 2345 |  |  | 2477.5 |  |  | 2464 |  |  | 2496.5 |  |  | 2424.5 |  |  | 2537 |  |  | 2477 |  |  | 2470 |  |  | 2399 |  |  | 2597 |  |  | 2511 |  |  | 2536.5 |  |  | 2524.5 |  |  | 2483.5 |  |  | 2453 |  |  | 2544 |  |  | 2345 |  |  | 2446.5 |  |  | 2543 |  |  | 2475.5 |  |  | 2625.5 |  |  | 2630.5 |  |  | 2565 |  |  | 2640 |  |  | 2625 |  |  | 2531.5 |  |  | 2618.5 |  |  | 2512.5 |  |  | 2649.5 |  |  | 2570.5 |  |  | 2577.5 |  |  | 2520.5 |  |  | 2431.5 |  |  | 2348 |  |  | 2632 |  |  | 2425 |  |  | 2587.5 |  |  | 2603 |  |  | 2464.5 |  |  | 2612 |  |  | 2518 |  |  | 2523.5 |  |  | 2655.5 |  |  | 2449 |  |  | 2590 |  |  | 2462.5 |  |  | 2703 |  |  | 2449.5 |  |  | 2535.5 |  |  | 2541.5 |  |  | 2472.5 |  |  | 2411.5 |  |  | 2463 |  |  | 2515 |  |  | 2383 |  |  | 2435.5 |  |  | 2491.5 |  |  | 2536.5 |  |  | 2432.5 |  |  | 2495 |  |  | 2436 |  |  | 2550.5 |  |  | 2449 |  |  | 2586.5 |  |  | 2530 |  |  | 2461 |  |  | 2457.5 |  |  | 2525 |  |  | 2512 |  |  | 2449 |  |  | 2577 |  |  | 2486.5 |  |  | 2530.5 |  |  | 2457.5 |  |  | 2609 |  |  | 2444 |  |  | 2444 |  |  | 2459 |  |  | 2483.5 |  |  | 2545 |  |  | 2550.5 |  |  | 2525 |  |  | 2374 |  |  | 2511.5 |  |  | 2438.5 |  |  | 2400 |  |  | 2433.5 |  |  | 2537 |  |  | 2582 |  |  | 2472 |  |  | 2645 |  |  | 2433 |  |  | 2455 |  |  | 2451 |  |  | 2524 |  |  | 2413 |  |  | 2422.5 |  |  | 2440 |  |  | 2426 |  |  | 2665 |  |  | 2575 |  |  | 2474 |  |  | 2395 |  |  | 2495 |  |  | 2505.5 |  |  | 2507 |  |  | 2535.5 |  |  | 2523 |  |  | 2473 |  |  | 2622.5 |  |  | 2554 |  |  | 2639.5 |  |  | 2442 |  |  | 2313 |  |  | 2476.5 |  |  | 2587 |  |  | 2601.5 |  |  | 2603 |  |  | 2381 |  |  | 2524.5 |  |  | 2591.5 |  |  | 2548 |  |  | 2523.5 |  |  | 2494.5 |  |  | 2516 |  |  | 2558 |  |  | 2651.5 |  |  | 2409.5 |  |  | 2582.5 |  |  | 2554 |  |  | 2576 |  |  | 2503 |  |  | 2613 |  |  | 2643 |  |  | 2501.5 |  |  | 2478 |  |  | 2427.5 |  |  | 2541.5 |  |  | 2472 |  |  | 2580 |  |  | 2728.5 |  |  | 2444.5 |  |  | 2446 |  |  | 2570.5 |  |  | 2393.5 |  |  | 2543 |  |  | 2430 |  |  | 2482 |  |  | 2438.5 |  |  | 2590 |  |  | 2530.5 |  |  | 2630.5 |  |  | 2519 |  |  | 2451.5 |  |  | 2475 |  |  | 2477 |  |  | 2588 |  |  | 2624 |  |  | 2319 |  |  | 2615 |  |  | 2638 |  |  | 2502 |  |  | 2608 |  |  | 2484 |  |  | 2544.5 |  |  | 2653.5 |  |  | 2473 |  |  | 2428 |  |  | 2640 |  |  | 2542.5 |  |  | 2629.5 |  |  | 2678.5 |  |  | 2421 |  |  | 2519 |  |  | 2635.5 |  |  | 2553.5 |  |  | 2383.5 |  |  | 2561 |  |  | 2610 |  |  | 2500 |  |  | 2581 |  |  | 2465 |  |  | 2543.5 |  |  | 2438.5 |  |  | 2642 |  |  | 2456 |  |  | 2470 |  |  | 2608 |  |  | 2443 |  |  | 2658.5 |  |  | 2565 |  |  | 2469 |  |  | 2416 |  |  | 2457 |  |  | 2505.5 |  |  | 2627 |  |  | 2514 |  |  | 2464 |  |  | 2596 |  |  | 2599.5 |  |  | 2540 |  |  | 2475 |  |  | 2430 |  |  | 2598.5 |  |  | 2553.5 |  |  | 2610.5 |  |  | 2605 |  |  | 2510 |  |  | 2375 |  |  | 2700 |  |  | 2468 |  |  | 2468.5 |  |  | 2580 |  |  | 2464.5 |  |  | 2606.5 |  |  | 2542.5 |  |  | 2540 |  |  | 2684.5 |  |  | 2395 |  |  | 2351 |  |  | 2476.5 |  |  | 2524.5 |  |  | 2608 |  |  | 2591.5 |  |  | 2680.5 |  |  | 2444 |  |  | 2592 |  |  | 2393.5 |  |  | 2486.5 |  |  | 2678 |  |  | 2601.5 |  |  | 2643 |  |  | 2529 |  |  | 2455.5 |  |  | 2597 |  |  | 2429 |  |  | 2568.5 |  |  | 2508 |  |  | 2643.5 |  |  | 2500 |  |  | 2689 |  |  | 2562 |  |  | 2490 |  |  | 2646.5 |  |  | 2612 |  |  | 2644.5 |  |  | 2418.5 |  |  | 2647.5 |  |  | 2563 |  |  | 2571.5 |  |  | 2715 |  |  | 2562 |  |  | 2334.5 |  |  | 2481.5 |  |  | 2574 |  |  | 2475.5 |  |  | 2690 |  |  | 2475 |  |  | 2713.5 |  |  | 2482 |  |  | 2487.5 |  |  | 2498.5 |  |  | 2560.5 |  |  | 2539 |  |  | 2386 |  |  | 2450 |  |  | 2487.5 |  |  | 2456 |  |  | 2681.5 |  |  | 2536 |  |  | 2506 |  |  | 2479 |  |  | 2538 |  |  | 2651 |  |  | 2495 |  |  | 2514 |  |  | 2702 |  |  | 2544 |  |  | 2501.5 |  |  | 2621 |  |  | 2496 |  |  | 2569.5 |  |  | 2425.5 |  |  | 2497.5 |  |  | 2484.5 |  |  | 2534 |  |  | 2611 |  |  | 2286.5 |  |  | 2719.5 |  |  | 2512.5 |  |  | 2533 |  |  | 2534 |  |  | 2420 |  |  | 2505 |  |  | 2367 |  |  | 2583 |  |  | 2591 |  |  | 2525.5 |  |  | 2558.5 |  |  | 2425 |  |  | 2424.5 |  |  | 2533.5 |  |  | 2456 |  |  | 2524 |  |  | 2491 |  |  | 2552 |  |  | 2468.5 |  |  | 2412.5 |  |  | 2558.5 |  |  | 2468 |  |  | 2493.5 |  |  | 2580 |  |  | 2493 |  |  | 2615 |  |  | 2439.5 |  |  | 2503 |  |  | 2389 |  |  | 2562.5 |  |  | 2452 |  |  | 2563.5 |  |  | 2666 |  |  | 2545.5 |  |  | 2501 |  |  | 2409.5 |  |  | 2542.5 |  |  | 2648 |  |  | 2554 |  |  | 2344 |  |  | 2516 |  |  | 2366.5 |  |  | 2497 |  |  | 2671 |  |  | 2437.5 |  |  | 2634.5 |  |  | 2350.5 |  |  | 2432 |  |  | 2614.5 |  |  | 2610.5 |  |  | 2439.5 |  |  | 2621 |  |  | 2525 |  |  | 2610.5 |  |  | 2575 |  |  | 2699 |  |  | 2527.5 |  |  | 2485 |  |  | 2616 |  |  | 2495 |  |  | 2381 |  |  | 2412.5 |  |  | 2555.5 |  |  | 2467 |  |  | 2643 |  |  | 2522 |  |  | 2499 |  |  | 2516 |  |  | 2475.5 |  |  | 2458.5 |  |  | 2531 |  |  | 2690 |  |  | 2665 |  |  | 2437.5 |  |  | 2747.5 |  |  | 2441 |  |  | 2541 |  |  | 2359 |  |  | 2566.5 |  |  | 2615.5 |  |  | 2513 |  |  | 2393 |  |  | 2586 |  |  | 2493 |  |  | 2461 |  |  | 2669 |  |  | 2477 |  |  | 2717.5 |  |  | 2508 |  |  | 2648 |  |  | 2517 |  |  | 2566.5 |  |  | 2599 |  |  | 2456 |  |  | 2396 |  |  | 2498 |  |  | 2461 |  |  | 2530 |  |  | 2545 |  |  | 2473.5 |  |  | 2491.5 |  |  | 2377.5 |  |  | 2612 |  |  | 2458 |  |  | 2515.5 |  |  | 2366 |  |  | 2424.5 |  |  | 2555.5 |  |  | 2497 |  |  | 2571 |  |  | 2560.5 |  |  | 2520 |  |  | 2573 |  |  | 2527 |  |  | 2560 |  |  | 2551 |  |  | 2458 |  |  | 2455 |  |  | 2560.5 |  |  | 2491 |  |  | 2628 |  |  | 2599 |  |  | 2521 |  |  | 2469 |  |  | 2552 |  |  | 2631 |  |  | 2613 |  |  | 2501 |  |  | 2588.5 |  |  | 2561.5 |  |  | 2522.5 |  |  | 2553.5 |  |  | 2552 |  |  | 2327 |  |  | 2627.5 |  |  | 2408 |  |  | 2536 |  |  | 2416.5 |  |  | 2640.5 |  |  | 2565 |  |  | 2507.5 |  |  | 2493.5 |  |  | 2350 |  |  | 2647 |  |  | 2450 |  |  | 2536 |  |  | 2491.5 |  |  | 2555 |  |  | 2470.5 |  |  | 2437.5 |  |  | 2505 |  |  | 2497 |  |  | 2599.5 |  |  | 2449 |  |  | 2510.5 |  |  | 2509 |  |  | 2575.5 |  |  | 2432.5 |  |  | 2296.5 |  |  | 2666.5 |  |  | 2547.5 |  |  | 2370 |  |  | 2462 |  |  | 2604.5 |  |  | 2540 |  |  | 2463 |  |  | 2516 |  |  | 2677 |  |  | 2613.5 |  |  | 2332 |  |  | 2436 |  |  | 2633 |  |  | 2484.5 |  |  | 2510 |  |  | 2378 |  |  | 2486 |  |  | 2706.5 |  |  | 2593 |  |  | 2348 |  |  | 2512 |  |  | 2653 |  |  | 2769.5 |  |  | 2521 |  |  | 2420.5 |  |  | 2520 |  |  | 2569 |  |  | 2750.5 |  |  | 2552 |  |  | 2463 |  |  | 2464.5 |  |  | 2524 |  |  | 2413 |  |  | 2430 |  |  | 2845.5 |  |  | 2554.5 |  |  | 2584 |  |  | 2428 |  |  | 2499.5 |  |  | 2536.5 |  |  | 2511 |  |  | 2594 |  |  | 2610.5 |  |  | 2719.5 |  |  | 2441.5 |  |  | 2591.5 |  |  | 2452.5 |  |  | 2744 |  |  | 2463.5 |  |  | 2633 |  |  | 2483 |  |  | 2633 |  |  | 2668 |  |  | 2520.5 |  |  | 2513 |  |  | 2424 |  |  | 2502.5 |  |  | 2545.5 |  |  | 2401 |  |  | 2606.5 |  |  | 2445.5 |  |  | 2589 |  |  | 2455 |  |  | 2524 |  |  | 2522.5 |  |  | 2579 |  |  | 2581.5 |  |  | 2594 |  |  | 2557 |  |  | 2781.5 |  |  | 2455 |  |  | 2623 |  |  | 2411 |  |  | 2620 |  |  | 2658 |  |  | 2545 |  |  | 2559 |  |  | 2510 |  |  | 2431.5 |  |  | 2426.5 |  |  | 2449 |  |  | 2554.5 |  |  | 2385.5 |  |  | 2423 |  |  | 2450 |  |  | 2580 |  |  | 2595.5 |  |  | 2427.5 |  |  | 2549 |  |  | 2558 |  |  | 2386 |  |  | 2432 |  |  | 2461 |  |  | 2423 |  |  | 2554 |  |  | 2451.5 |  |  | 2624 |  |  | 2643 |  |  | 2599 |  |  | 2412 |  |  | 2386 |  |  | 2488.5 |  |  | 2728.5 |  |  | 2358.5 |  |  | 2427 |  |  | 2453 |  |  | 2425.5 |  |  | 2579.5 |  |  | 2556.5 |  |  | 2393 |  |  | 2579.5 |  |  | 2621.5 |  |  | 2597 |  |  | 2528.5 |  |  | 2553.5 |  |  | 2502 |  |  | 2381 |  |  | 2453 |  |  | 2598 |  |  | 2470 |  |  | 2346 |  |  | 2607 |  |  | 2608 |  |  | 2405 |  |  | 2518 |  |  | 2641.5 |  |  | 2486 |  |  | 2496 |  |  | 2475 |  |  | 2397.5 |  |  | 2462 |  |  | 2544.5 |  |  | 2645 |  |  | 2629 |  |  | 2515 |  |  | 2553 |  |  | 2645.5 |  |  | 2505 |  |  | 2366 |  |  | 2580.5 |  |  | 2538 |  |  | 2430 |  |  | 2479.5 |  |  | 2476.5 |  |  | 2501 |  |  | 2445.5 |  |  | 2625 |  |  | 2459.5 |  |  | 2608 |  |  | 2550 |  |  | 2449.5 |  |  | 2580.5 |  |  | 2563 |  |  | 2582 |  |  | 2548 |  |  | 2517 |  |  | 2440 |  |  | 2474 |  |  | 2367 |  |  | 2441 |  |  | 2568.5 |  |  | 2344 |  |  | 2609.5 |  |  | 2426 |  |  | 2539.5 |  |  | 2454.5 |  |  | 2472 |  |  | 2609 |  |  | 2605.5 |  |  | 2536 |  |  | 2558 |  |  | 2597 |  |  | 2497.5 |  |  | 2596 |  |  | 2414.5 |  |  | 2299 |  |  | 2447 |  |  | 2445 |  |  | 2524 |  |  | 2592.5 |  |  | 2495 |  |  | 2511 |  |  | 2622 |  |  | 2410.5 |  |  | 2685 |  |  | 2586 |  |  | 2588 |  |  | 2516 |  |  | 2528.5 |  |  | 2382.5 |  |  | 2645 |  |  | 2657 |  |  | 2557 |  |  | 2584.5 |  |  | 2521 |  |  | 2398 |  |  | 2442 |  |  | 2677.5 |  |  | 2509.5 |  |  | 2505.5 |  |  | 2554 |  |  | 2601 |  |  | 2596 |  |  | 2455.5 |  |  | 2602 |  |  | 2433.5 |  |  | 2387 |  |  | 2431 |  |  | 2478 |  |  | 2457.5 |  |  | 2539.5 |  |  | 2533 |  |  | 2530 |  |  | 2577.5 |  |  | 2578 |  |  | 2439 |  |  | 2578.5 |  |  | 2345 |  |  | 2396 |  |  | 2570.5 |  |  | 2421 |  |  | 2569 |  |  | 2473.5 |  |  | 2620 |  |  | 2425.5 |  |  | 2504 |  |  | 2317.5 |  |  | 2598.5 |  |  | 2402 |  |  | 2553 |  |  | 2677.5 |  |  | 2434.5 |  |  | 2584 |  |  | 2543 |  |  | 2536 |  |  | 2568.5 |  |  | 2593 |  |  | 2320 |  |  | 2434 |  |  | 2620.5 |  |  | 2571.5 |  |  | 2558 |  |  | 2581 |  |  | 2524 |  |  | 2493 |  |  | 2584 |  |  | 2494 |  |  | 2524 |  |  | 2517.5 |  |  | 2670.5 |  |  | 2408.5 |  |  | 2448 |  |  | 2455.5 |  |  | 2569 |  |  | 2519 |  |  | 2539.5 |  |  | 2380.5 |  |  | 2438 |  |  | 2543 |  |  | 2475.5 |  |  | 2476 |  |  | 2550 |  |  | 2368.5 |  |  | 2613.5 |  |  | 2477 |  |  | 2477 |  |  | 2493 |  |  | 2374.5 |  |  | 2460 |  |  | 2391 |  |  | 2498 |  |  | 2558 |  |  | 2657 |  |  | 2396.5 |  |  | 2631 |  |  | 2523 |  |  | 2405 |  |  | 2616.5 |  |  | 2530 |  |  | 2399.5 |  |  | 2416.5 |  |  | 2454 |  |  | 2635 |  |  | 2522.5 |  |  | 2438.5 |  |  | 2463.5 |  |  | 2489.5 |  |  | 2532.5 |  |  | 2573 |  |  | 2501 |  |  | 2478.5 |  |  | 2494.5 |  |  | 2487 |  |  | 2426 |  |  | 2504.5 |  |  | 2736 |  |  | 2517 |  |  | 2395 |  |  | 2583.5 |  |  | 2692 |  |  | 2458.5 |  |  | 2368 |  |  | 2560.5 |  |  | 2707.5 |  |  | 2641.5 |  |  | 2633 |  |  | 2551 |  |  | 2535.5 |  |  | 2464.5 |  |  | 2592 |  |  | 2535 |  |  | 2569.5 |  |  | 2673 |  |  | 2504.5 |  |  | 2504.5 |  |  | 2469 |  |  | 2538 |  |  | 2376.5 |  |  | 2612.5 |  |  | 2579 |  |  | 2467.5 |  |  | 2552.5 |  |  | 2550 |  |  | 2628 |  |  | 2614 |  |  | 2526.5 |  |  | 2571 |  |  | 2423 |  |  | 2530 |  |  | 2449 |  |  | 2491 |  |  | 2497 |  |  | 2721.5 |  |  | 2517.5 |  |  | 2503 |  |  | 2462 |  |  | 2576 |  |  | 2422.5 |  |  | 2529 |  |  | 2651 |  |  | 2476.5 |  |  | 2654.5 |  |  | 2502 |  |  | 2464.5 |  |  | 2650 |  |  | 2382 |  |  | 2498 |  |  | 2605.5 |  |  | 2576 |  |  | 2403.5 |  |  | 2499.5 |  |  | 2376 |  |  | 2531.5 |  |  | 2331.5 |  |  | 2507 |  |  | 2424 |  |  | 2600 |  |  | 2476.5 |  |  | 2429 |  |  | 2460.5 |  |  | 2654.5 |  |  | 2611 |  |  | 2395.5 |  |  | 2411 |  |  | 2518 |  |  | 2488 |  |  | 2499 |  |  | 2389 |  |  | 2600.5 |  |  | 2509 |  |  | 2631 |  |  | 2464 |  |  | 2632 |  |  | 2546.5 |  |  | 2523.5 |  |  | 2558 |  |  | 2646 |  |  | 2495 |  |  | 2519 |  |  | 2550 |  |  | 2407.5 |  |  | 2484 |  |  | 2614.5 |  |  | 2608 |  |  | 2380 |  |  | 2549 |  |  | 2529 |  |  | 2590.5 |  |  | 2537 |  |  | 2573.5 |  |  | 2409 |  |  | 2664 |  |  | 2576 |  |  | 2547.5 |  |  | 2411 |  |  | 2405 |  |  | 2459 |  |  | 2669 |  |  | 2787 |  |  | 2492.5 |  |  | 2588.5 |  |  | 2424 |  |  | 2441.5 |  |  | 2470 |  |  | 2506.5 |  |  | 2469.5 |  |  | 2470.5 |  |  | 2469.5 |  |  | 2412 |  |  | 2697 |  |  | 2401 |  |  | 2383 |  |  | 2487 |  |  | 2602 |  |  | 2509.5 |  |  | 2482.5 |  |  | 2694.5 |  |  | 2494 |  |  | 2660.5 |  |  | 2414.5 |  |  | 2633.5 |  |  | 2403.5 |  |  | 2525 |  |  | 2520.5 |  |  | 2575.5 |  |  | 2632 |  |  | 2367.5 |  |  | 2659.5 |  |  | 2554.5 |  |  | 2666 |  |  | 2542.5 |  |  | 2589 |  |  | 2549 |  |  | 2494.5 |  |  | 2564.5 |  |  | 2549 |  |  | 2626 |  |  | 2360.5 |  |  | 2365.5 |  |  | 2468.5 |  |  | 2576 |  |  | 2426 |  |  | 2495 |  |  | 2641.5 |  |  | 2592.5 |  |  | 2519 |  |  | 2580.5 |  |  | 2386 |  |  | 2506 |  |  | 2551.5 |  |  | 2406.5 |  |  | 2449 |  |  | 2497.5 |  |  | 2624 |  |  | 2416.5 |  |  | 2616.5 |  |  | 2637 |  |  | 2555.5 |  |  | 2574 |  |  | 2496.5 |  |  | 2490 |  |  | 2530 |  |  | 2557 |  |  | 2479.5 |  |  | 2418.5 |  |  | 2539 |  |  | 2438 |  |  | 2417 |  |  | 2471.5 |  |  | 2535.5 |  |  | 2654 |  |  | 2523.5 |  |  | 2468 |  |  | 2331.5 |  |  | 2582.5 |  |  | 2409 |  |  | 2455 |  |  | 2462 |  |  | 2475.5 |  |  | 2416 |  |  | 2577.5 |  |  | 2538 |  |  | 2449.5 |  |  | 2688 |  |  | 2358.5 |  |  | 2477 |  |  | 2519.5 |  |  | 2541.5 |  |  | 2446 |  |  | 2488 |  |  | 2759 |  |  | 2541 |  |  | 2595.5 |  |  | 2466 |  |  | 2475.5 |  |  | 2425 |  |  | 2432 |  |  | 2502 |  |  | 2672 |  |  | 2585 |  |  | 2533 |  |  | 2590 |  |  | 2455.5 |  |  | 2490 |  |  | 2573
88 |  | 2673.5 |  |  | 2666 |  |  | 2689.5 |  |  | 2567 |  |  | 2428.5 |  |  | 2699 |  |  | 2635 |  |  | 2545 |  |  | 2427.5 |  |  | 2417 |  |  | 2503 |  |  | 2684 |  |  | 2632 |  |  | 2701 |  |  | 2452.5 |  |  | 2632.5 |  |  | 2530 |  |  | 2608 |  |  | 2705 |  |  | 2454.5 |  |  | 2643 |  |  | 2636 |  |  | 2476 |  |  | 2566 |  |  | 2565.5 |  |  | 2663 |  |  | 2486 |  |  | 2597 |  |  | 2679 |  |  | 2397 |  |  | 2548 |  |  | 2488.5 |  |  | 2627.5 |  |  | 2515.5 |  |  | 2518 |  |  | 2573.5 |  |  | 2593.5 |  |  | 2622.5 |  |  | 2637 |  |  | 2570 |  |  | 2424.5 |  |  | 2486 |  |  | 2534.5 |  |  | 2504.5 |  |  | 2579.5 |  |  | 2729.5 |  |  | 2674.5 |  |  | 2506 |  |  | 2371 |  |  | 2492.5 |  |  | 2479 |  |  | 2511.5 |  |  | 2471.5 |  |  | 2576 |  |  | 2524 |  |  | 2509 |  |  | 2423 |  |  | 2636 |  |  | 2537 |  |  | 2562.5 |  |  | 2571.5 |  |  | 2522.5 |  |  | 2479 |  |  | 2583 |  |  | 2374 |  |  | 2461.5 |  |  | 2582 |  |  | 2499.5 |  |  | 2651.5 |  |  | 2656.5 |  |  | 2580 |  |  | 2687 |  |  | 2646 |  |  | 2570.5 |  |  | 2633.5 |  |  | 2541.5 |  |  | 2673.5 |  |  | 2609.5 |  |  | 2592.5 |  |  | 2559.5 |  |  | 2470.5 |  |  | 2372 |  |  | 2658 |  |  | 2464 |  |  | 2634.5 |  |  | 2632 |  |  | 2493.5 |  |  | 2651 |  |  | 2544 |  |  | 2549.5 |  |  | 2681.5 |  |  | 2470 |  |  | 2619 |  |  | 2483.5 |  |  | 2724 |  |  | 2478.5 |  |  | 2582.5 |  |  | 2580.5 |  |  | 2511.5 |  |  | 2435.5 |  |  | 2502 |  |  | 2562 |  |  | 2407 |  |  | 2474.5 |  |  | 2517.5 |  |  | 2562.5 |  |  | 2456.5 |  |  | 2542 |  |  | 2475 |  |  | 2589.5 |  |  | 2475 |  |  | 2610.5 |  |  | 2554 |  |  | 2485 |  |  | 2504.5 |  |  | 2549 |  |  | 2533 |  |  | 2488 |  |  | 2601 |  |  | 2515.5 |  |  | 2545.5 |  |  | 2496.5 |  |  | 2638 |  |  | 2468 |  |  | 2470 |  |  | 2498 |  |  | 2504.5 |  |  | 2566 |  |  | 2597.5 |  |  | 2549 |  |  | 2395 |  |  | 2526.5 |  |  | 2477.5 |  |  | 2424 |  |  | 2462.5 |  |  | 2563 |  |  | 2629 |  |  | 2511 |  |  | 2660 |  |  | 2448 |  |  | 2476 |  |  | 2472 |  |  | 2563 |  |  | 2434 |  |  | 2446.5 |  |  | 2469 |  |  | 2450 |  |  | 2704 |  |  | 2604 |  |  | 2500 |  |  | 2434 |  |  | 2534 |  |  | 2552.5 |  |  | 2531 |  |  | 2559.5 |  |  | 2538 |  |  | 2499 |  |  | 2651.5 |  |  | 2578 |  |  | 2654.5 |  |  | 2471 |  |  | 2337 |  |  | 2523.5 |  |  | 2634 |  |  | 2627.5 |  |  | 2629 |  |  | 2410 |  |  | 2563.5 |  |  | 2630.5 |  |  | 2595 |  |  | 2562.5 |  |  | 2533.5 |  |  | 2563 |  |  | 2587 |  |  | 2690.5 |  |  | 2438.5 |  |  | 2629.5 |  |  | 2580 |  |  | 2605 |  |  | 2527 |  |  | 2652 |  |  | 2690 |  |  | 2540.5 |  |  | 2507 |  |  | 2466.5 |  |  | 2567.5 |  |  | 2493 |  |  | 2609 |  |  | 2754.5 |  |  | 2483.5 |  |  | 2485 |  |  | 2596.5 |  |  | 2432.5 |  |  | 2582 |  |  | 2456 |  |  | 2508 |  |  | 2485.5 |  |  | 2605 |  |  | 2556.5 |  |  | 2669.5 |  |  | 2558 |  |  | 2490.5 |  |  | 2514 |  |  | 2492 |  |  | 2627 |  |  | 2671 |  |  | 2366 |  |  | 2630 |  |  | 2677 |  |  | 2517 |  |  | 2634 |  |  | 2508 |  |  | 2573.5 |  |  | 2677.5 |  |  | 2512 |  |  | 2452 |  |  | 2679 |  |  | 2566.5 |  |  | 2644.5 |  |  | 2717.5 |  |  | 2445 |  |  | 2543 |  |  | 2656.5 |  |  | 2582.5 |  |  | 2409.5 |  |  | 2576 |  |  | 2649 |  |  | 2529 |  |  | 2596 |  |  | 2491 |  |  | 2564.5 |  |  | 2467.5 |  |  | 2663 |  |  | 2495 |  |  | 2491 |  |  | 2655 |  |  | 2482 |  |  | 2697.5 |  |  | 2589 |  |  | 2516 |  |  | 2431 |  |  | 2472 |  |  | 2544.5 |  |  | 2674 |  |  | 2535 |  |  | 2511 |  |  | 2611 |  |  | 2620.5 |  |  | 2561 |  |  | 2514 |  |  | 2445 |  |  | 2622.5 |  |  | 2568.5 |  |  | 2649.5 |  |  | 2631 |  |  | 2549 |  |  | 2404 |  |  | 2729 |  |  | 2497 |  |  | 2483.5 |  |  | 2601 |  |  | 2479.5 |  |  | 2630.5 |  |  | 2589.5 |  |  | 2579 |  |  | 2731.5 |  |  | 2421 |  |  | 2380 |  |  | 2497.5 |  |  | 2545.5 |  |  | 2637 |  |  | 2638.5 |  |  | 2704.5 |  |  | 2470 |  |  | 2631 |  |  | 2419.5 |  |  | 2512.5 |  |  | 2707 |  |  | 2625.5 |  |  | 2669 |  |  | 2544 |  |  | 2494.5 |  |  | 2618 |  |  | 2455 |  |  | 2589.5 |  |  | 2523 |  |  | 2658.5 |  |  | 2524 |  |  | 2728 |  |  | 2591 |  |  | 2511 |  |  | 2667.5 |  |  | 2659 |  |  | 2668.5 |  |  | 2433.5 |  |  | 2668.5 |  |  | 2610 |  |  | 2610.5 |  |  | 2736 |  |  | 2586 |  |  | 2360.5 |  |  | 2520.5 |  |  | 2621 |  |  | 2499.5 |  |  | 2711 |  |  | 2522 |  |  | 2739.5 |  |  | 2497 |  |  | 2502.5 |  |  | 2537.5 |  |  | 2581.5 |  |  | 2578 |  |  | 2412 |  |  | 2476 |  |  | 2502.5 |  |  | 2477 |  |  | 2702.5 |  |  | 2575 |  |  | 2521 |  |  | 2526 |  |  | 2585 |  |  | 2690 |  |  | 2519 |  |  | 2538 |  |  | 2723 |  |  | 2570 |  |  | 2548.5 |  |  | 2645 |  |  | 2525 |  |  | 2593.5 |  |  | 2464.5 |  |  | 2518.5 |  |  | 2523.5 |  |  | 2549 |  |  | 2640 |  |  | 2312.5 |  |  | 2758.5 |  |  | 2533.5 |  |  | 2562 |  |  | 2563 |  |  | 2435 |  |  | 2544 |  |  | 2406 |  |  | 2609 |  |  | 2620 |  |  | 2551.5 |  |  | 2582.5 |  |  | 2454 |  |  | 2471.5 |  |  | 2557.5 |  |  | 2503 |  |  | 2539 |  |  | 2538 |  |  | 2591 |  |  | 2515.5 |  |  | 2451.5 |  |  | 2587.5 |  |  | 2507 |  |  | 2532.5 |  |  | 2619 |  |  | 2532 |  |  | 2662 |  |  | 2463.5 |  |  | 2532 |  |  | 2415 |  |  | 2586.5 |  |  | 2491 |  |  | 2602.5 |  |  | 2690 |  |  | 2584.5 |  |  | 2516 |  |  | 2435.5 |  |  | 2571.5 |  |  | 2687 |  |  | 2575 |  |  | 2383 |  |  | 2542 |  |  | 2413.5 |  |  | 2521 |  |  | 2692 |  |  | 2466.5 |  |  | 2649.5 |  |  | 2389.5 |  |  | 2471 |  |  | 2635.5 |  |  | 2639.5 |  |  | 2454.5 |  |  | 2647 |  |  | 2551 |  |  | 2649.5 |  |  | 2590 |  |  | 2714 |  |  | 2542.5 |  |  | 2509 |  |  | 2642 |  |  | 2534 |  |  | 2428 |  |  | 2427.5 |  |  | 2602.5 |  |  | 2491 |  |  | 2667 |  |  | 2543 |  |  | 2538 |  |  | 2540 |  |  | 2499.5 |  |  | 2479.5 |  |  | 2557 |  |  | 2729 |  |  | 2694 |  |  | 2461.5 |  |  | 2773.5 |  |  | 2465 |  |  | 2562 |  |  | 2398 |  |  | 2581.5 |  |  | 2639.5 |  |  | 2542 |  |  | 2432 |  |  | 2625 |  |  | 2514 |  |  | 2500 |  |  | 2690 |  |  | 2524 |  |  | 2756.5 |  |  | 2534 |  |  | 2687 |  |  | 2532 |  |  | 2590.5 |  |  | 2646 |  |  | 2482 |  |  | 2425 |  |  | 2527 |  |  | 2500 |  |  | 2556 |  |  | 2574 |  |  | 2488.5 |  |  | 2517.5 |  |  | 2416.5 |  |  | 2651 |  |  | 2497 |  |  | 2544.5 |  |  | 2381 |  |  | 2453.5 |  |  | 2581.5 |  |  | 2521 |  |  | 2592 |  |  | 2589.5 |  |  | 2546 |  |  | 2599 |  |  | 2548 |  |  | 2584 |  |  | 2566 |  |  | 2473 |  |  | 2481 |  |  | 2589.5 |  |  | 2520 |  |  | 2649 |  |  | 2614 |  |  | 2536 |  |  | 2498 |  |  | 2578 |  |  | 2670 |  |  | 2652 |  |  | 2540 |  |  | 2617.5 |  |  | 2608.5 |  |  | 2537.5 |  |  | 2592.5 |  |  | 2573 |  |  | 2374 |  |  | 2666.5 |  |  | 2429 |  |  | 2583 |  |  | 2463.5 |  |  | 2661.5 |  |  | 2612 |  |  | 2522.5 |  |  | 2517.5 |  |  | 2374 |  |  | 2694 |  |  | 2497 |  |  | 2565 |  |  | 2515.5 |  |  | 2576 |  |  | 2491.5 |  |  | 2484.5 |  |  | 2544 |  |  | 2526 |  |  | 2638.5 |  |  | 2473 |  |  | 2549.5 |  |  | 2548 |  |  | 2604.5 |  |  | 2453.5 |  |  | 2322.5 |  |  | 2690.5 |  |  | 2586.5 |  |  | 2391 |  |  | 2501 |  |  | 2625.5 |  |  | 2587 |  |  | 2492 |  |  | 2537 |  |  | 2703 |  |  | 2660.5 |  |  | 2379 |  |  | 2475 |  |  | 2672 |  |  | 2508.5 |  |  | 2531 |  |  | 2404 |  |  | 2512 |  |  | 2730.5 |  |  | 2640 |  |  | 2374 |  |  | 2551 |  |  | 2668 |  |  | 2798.5 |  |  | 2536 |  |  | 2449.5 |  |  | 2559 |  |  | 2616 |  |  | 2779.5 |  |  | 2599 |  |  | 2489 |  |  | 2511.5 |  |  | 2563 |  |  | 2434 |  |  | 2445 |  |  | 2892.5 |  |  | 2601.5 |  |  | 2613 |  |  | 2452 |  |  | 2538.5 |  |  | 2562.5 |  |  | 2526 |  |  | 2620 |  |  | 2631.5 |  |  | 2758.5 |  |  | 2488.5 |  |  | 2620.5 |  |  | 2476.5 |  |  | 2765 |  |  | 2502.5 |  |  | 2672 |  |  | 2504 |  |  | 2662 |  |  | 2692 |  |  | 2567.5 |  |  | 2542 |  |  | 2471 |  |  | 2531.5 |  |  | 2571.5 |  |  | 2427 |  |  | 2632.5 |  |  | 2492.5 |  |  | 2615 |  |  | 2470 |  |  | 2550 |  |  | 2543.5 |  |  | 2626 |  |  | 2607.5 |  |  | 2618 |  |  | 2596 |  |  | 2820.5 |  |  | 2494 |  |  | 2670 |  |  | 2435 |  |  | 2646 |  |  | 2673 |  |  | 2571 |  |  | 2583 |  |  | 2531 |  |  | 2470.5 |  |  | 2441.5 |  |  | 2488 |  |  | 2583.5 |  |  | 2400.5 |  |  | 2449 |  |  | 2489 |  |  | 2606 |  |  | 2610.5 |  |  | 2474.5 |  |  | 2588 |  |  | 2579 |  |  | 2401 |  |  | 2471 |  |  | 2476 |  |  | 2447 |  |  | 2593 |  |  | 2475.5 |  |  | 2653 |  |  | 2672 |  |  | 2646 |  |  | 2451 |  |  | 2433 |  |  | 2527.5 |  |  | 2775.5 |  |  | 2397.5 |  |  | 2453 |  |  | 2479 |  |  | 2464.5 |  |  | 2594.5 |  |  | 2603.5 |  |  | 2419 |  |  | 2605.5 |  |  | 2645.5 |  |  | 2626 |  |  | 2554.5 |  |  | 2582.5 |  |  | 2531 |  |  | 2402 |  |  | 2500 |  |  | 2645 |  |  | 2496 |  |  | 2370 |  |  | 2654 |  |  | 2629 |  |  | 2434 |  |  | 2542 |  |  | 2688.5 |  |  | 2533 |  |  | 2517 |  |  | 2499 |  |  | 2421.5 |  |  | 2501 |  |  | 2583.5 |  |  | 2692 |  |  | 2653 |  |  | 2539 |  |  | 2600 |  |  | 2671.5 |  |  | 2544 |  |  | 2395 |  |  | 2604.5 |  |  | 2585 |  |  | 2456 |  |  | 2518.5 |  |  | 2500.5 |  |  | 2530 |  |  | 2460.5 |  |  | 2649 |  |  | 2474.5 |  |  | 2634 |  |  | 2597 |  |  | 2478.5 |  |  | 2601.5 |  |  | 2584 |  |  | 2611 |  |  | 2569 |  |  | 2538 |  |  | 2469 |  |  | 2521 |  |  | 2393 |  |  | 2456 |  |  | 2607.5 |  |  | 2373 |  |  | 2635.5 |  |  | 2465 |  |  | 2554.5 |  |  | 2501.5 |  |  | 2498 |  |  | 2638 |  |  | 2620.5 |  |  | 2575 |  |  | 2579 |  |  | 2626 |  |  | 2518.5 |  |  | 2617 |  |  | 2453.5 |  |  | 2314 |  |  | 2468 |  |  | 2484 |  |  | 2539 |  |  | 2613.5 |  |  | 2534 |  |  | 2526 |  |  | 2646 |  |  | 2436.5 |  |  | 2732 |  |  | 2610 |  |  | 2635 |  |  | 2531 |  |  | 2552.5 |  |  | 2406.5 |  |  | 2692 |  |  | 2696 |  |  | 2604 |  |  | 2623.5 |  |  | 2568 |  |  | 2437 |  |  | 2481 |  |  | 2724.5 |  |  | 2556.5 |  |  | 2529.5 |  |  | 2593 |  |  | 2616 |  |  | 2635 |  |  | 2476.5 |  |  | 2626 |  |  | 2462.5 |  |  | 2411 |  |  | 2470 |  |  | 2517 |  |  | 2478.5 |  |  | 2578.5 |  |  | 2554 |  |  | 2554 |  |  | 2616.5 |  |  | 2599 |  |  | 2465 |  |  | 2599.5 |  |  | 2392 |  |  | 2420 |  |  | 2594.5 |  |  | 2450 |  |  | 2584 |  |  | 2499.5 |  |  | 2659 |  |  | 2451.5 |  |  | 2528 |  |  | 2343.5 |  |  | 2622.5 |  |  | 2423 |  |  | 2568 |  |  | 2706.5 |  |  | 2463.5 |  |  | 2599 |  |  | 2558 |  |  | 2575 |  |  | 2583.5 |  |  | 2608 |  |  | 2359 |  |  | 2449 |  |  | 2644.5 |  |  | 2600.5 |  |  | 2605 |  |  | 2628 |  |  | 2563 |  |  | 2532 |  |  | 2608 |  |  | 2515 |  |  | 2548 |  |  | 2543.5 |  |  | 2717.5 |  |  | 2429.5 |  |  | 2477 |  |  | 2502.5 |  |  | 2608 |  |  | 2543 |  |  | 2565.5 |  |  | 2419.5 |  |  | 2453 |  |  | 2582 |  |  | 2490.5 |  |  | 2505 |  |  | 2571 |  |  | 2407.5 |  |  | 2642.5 |  |  | 2506 |  |  | 2506 |  |  | 2522 |  |  | 2421.5 |  |  | 2481 |  |  | 2420 |  |  | 2524 |  |  | 2597 |  |  | 2696 |  |  | 2422.5 |  |  | 2660 |  |  | 2570 |  |  | 2429 |  |  | 2640.5 |  |  | 2577 |  |  | 2414.5 |  |  | 2440.5 |  |  | 2478 |  |  | 2659 |  |  | 2551.5 |  |  | 2477.5 |  |  | 2478.5 |  |  | 2513.5 |  |  | 2556.5 |  |  | 2602 |  |  | 2522 |  |  | 2499.5 |  |  | 2518.5 |  |  | 2513 |  |  | 2465 |  |  | 2519.5 |  |  | 2760 |  |  | 2556 |  |  | 2410 |  |  | 2622.5 |  |  | 2707 |  |  | 2497.5 |  |  | 2407 |  |  | 2575.5 |  |  | 2728.5 |  |  | 2680.5 |  |  | 2659 |  |  | 2566 |  |  | 2559.5 |  |  | 2479.5 |  |  | 2631 |  |  | 2550 |  |  | 2608.5 |  |  | 2720 |  |  | 2543.5 |  |  | 2528.5 |  |  | 2495 |  |  | 2577 |  |  | 2400.5 |  |  | 2641.5 |  |  | 2594 |  |  | 2514.5 |  |  | 2576.5 |  |  | 2589 |  |  | 2643 |  |  | 2653 |  |  | 2573.5 |  |  | 2592 |  |  | 2438 |  |  | 2545 |  |  | 2470 |  |  | 2520 |  |  | 2523 |  |  | 2742.5 |  |  | 2556.5 |  |  | 2524 |  |  | 2501 |  |  | 2602 |  |  | 2448.5 |  |  | 2555 |  |  | 2680 |  |  | 2502.5 |  |  | 2693.5 |  |  | 2549 |  |  | 2493.5 |  |  | 2671 |  |  | 2429 |  |  | 2537 |  |  | 2652.5 |  |  | 2623 |  |  | 2429.5 |  |  | 2520.5 |  |  | 2402 |  |  | 2546.5 |  |  | 2357.5 |  |  | 2546 |  |  | 2450 |  |  | 2639 |  |  | 2515.5 |  |  | 2444 |  |  | 2486.5 |  |  | 2669.5 |  |  | 2632 |  |  | 2434.5 |  |  | 2437 |  |  | 2565 |  |  | 2514 |  |  | 2546 |  |  | 2415 |  |  | 2626.5 |  |  | 2556 |  |  | 2655 |  |  | 2503 |  |  | 2658 |  |  | 2570.5 |  |  | 2544.5 |  |  | 2573 |  |  | 2667 |  |  | 2534 |  |  | 2558 |  |  | 2574 |  |  | 2428.5 |  |  | 2508 |  |  | 2661.5 |  |  | 2632 |  |  | 2409 |  |  | 2578 |  |  | 2544 |  |  | 2605.5 |  |  | 2584 |  |  | 2620.5 |  |  | 2448 |  |  | 2679 |  |  | 2623 |  |  | 2562.5 |  |  | 2458 |  |  | 2420 |  |  | 2485 |  |  | 2708 |  |  | 2826 |  |  | 2507.5 |  |  | 2603.5 |  |  | 2439 |  |  | 2480.5 |  |  | 2491 |  |  | 2545.5 |  |  | 2490.5 |  |  | 2509.5 |  |  | 2516.5 |  |  | 2451 |  |  | 2736 |  |  | 2416 |  |  | 2404 |  |  | 2526 |  |  | 2628 |  |  | 2535.5 |  |  | 2529.5 |  |  | 2718.5 |  |  | 2523 |  |  | 2699.5 |  |  | 2453.5 |  |  | 2657.5 |  |  | 2424.5 |  |  | 2540 |  |  | 2544.5 |  |  | 2599.5 |  |  | 2671 |  |  | 2414.5 |  |  | 2688.5 |  |  | 2583.5 |  |  | 2705 |  |  | 2589.5 |  |  | 2628 |  |  | 2570 |  |  | 2523.5 |  |  | 2593.5 |  |  | 2588 |  |  | 2673 |  |  | 2375.5 |  |  | 2394.5 |  |  | 2507.5 |  |  | 2591 |  |  | 2441 |  |  | 2519 |  |  | 2662.5 |  |  | 2618.5 |  |  | 2558 |  |  | 2619.5 |  |  | 2401 |  |  | 2532 |  |  | 2580.5 |  |  | 2435.5 |  |  | 2464 |  |  | 2518.5 |  |  | 2663 |  |  | 2442.5 |  |  | 2645.5 |  |  | 2658 |  |  | 2576.5 |  |  | 2603 |  |  | 2517.5 |  |  | 2516 |  |  | 2569 |  |  | 2572 |  |  | 2518.5 |  |  | 2457.5 |  |  | 2565 |  |  | 2467 |  |  | 2456 |  |  | 2500.5 |  |  | 2561.5 |  |  | 2680 |  |  | 2562.5 |  |  | 2507 |  |  | 2352.5 |  |  | 2597.5 |  |  | 2430 |  |  | 2470 |  |  | 2486 |  |  | 2504.5 |  |  | 2437 |  |  | 2598.5 |  |  | 2559 |  |  | 2496.5 |  |  | 2727 |  |  | 2382.5 |  |  | 2516 |  |  | 2543.5 |  |  | 2567.5 |  |  | 2475 |  |  | 2509 |  |  | 2774 |  |  | 2570 |  |  | 2616.5 |  |  | 2490 |  |  | 2496.5 |  |  | 2449 |  |  | 2456 |  |  | 2517 |  |  | 2687 |  |  | 2611 |  |  | 2572 |  |  | 2629 |  |  | 2479.5 |  |  | 2514 |  |  | 2594
89 |  | 2697.5 |  |  | 2681 |  |  | 2718.5 |  |  | 2606 |  |  | 2467.5 |  |  | 2738 |  |  | 2650 |  |  | 2571 |  |  | 2451.5 |  |  | 2441 |  |  | 2542 |  |  | 2708 |  |  | 2653 |  |  | 2722 |  |  | 2476.5 |  |  | 2656.5 |  |  | 2556 |  |  | 2632 |  |  | 2744 |  |  | 2469.5 |  |  | 2682 |  |  | 2665 |  |  | 2505 |  |  | 2605 |  |  | 2604.5 |  |  | 2702 |  |  | 2525 |  |  | 2621 |  |  | 2708 |  |  | 2423 |  |  | 2595 |  |  | 2509.5 |  |  | 2656.5 |  |  | 2554.5 |  |  | 2557 |  |  | 2588.5 |  |  | 2608.5 |  |  | 2637.5 |  |  | 2658 |  |  | 2609 |  |  | 2453.5 |  |  | 2512 |  |  | 2558.5 |  |  | 2519.5 |  |  | 2600.5 |  |  | 2744.5 |  |  | 2695.5 |  |  | 2545 |  |  | 2418 |  |  | 2516.5 |  |  | 2503 |  |  | 2526.5 |  |  | 2510.5 |  |  | 2602 |  |  | 2545 |  |  | 2530 |  |  | 2470 |  |  | 2675 |  |  | 2566 |  |  | 2588.5 |  |  | 2586.5 |  |  | 2537.5 |  |  | 2508 |  |  | 2607 |  |  | 2395 |  |  | 2500.5 |  |  | 2608 |  |  | 2525.5 |  |  | 2690.5 |  |  | 2680.5 |  |  | 2606 |  |  | 2713 |  |  | 2675 |  |  | 2609.5 |  |  | 2672.5 |  |  | 2562.5 |  |  | 2688.5 |  |  | 2656.5 |  |  | 2613.5 |  |  | 2598.5 |  |  | 2509.5 |  |  | 2387 |  |  | 2687 |  |  | 2485 |  |  | 2658.5 |  |  | 2647 |  |  | 2532.5 |  |  | 2677 |  |  | 2573 |  |  | 2570.5 |  |  | 2728.5 |  |  | 2485 |  |  | 2666 |  |  | 2509.5 |  |  | 2771 |  |  | 2493.5 |  |  | 2629.5 |  |  | 2604.5 |  |  | 2540.5 |  |  | 2474.5 |  |  | 2531 |  |  | 2588 |  |  | 2422 |  |  | 2513.5 |  |  | 2556.5 |  |  | 2609.5 |  |  | 2495.5 |  |  | 2557 |  |  | 2490 |  |  | 2604.5 |  |  | 2514 |  |  | 2649.5 |  |  | 2593 |  |  | 2509 |  |  | 2533.5 |  |  | 2588 |  |  | 2557 |  |  | 2503 |  |  | 2622 |  |  | 2544.5 |  |  | 2592.5 |  |  | 2511.5 |  |  | 2685 |  |  | 2515 |  |  | 2491 |  |  | 2513 |  |  | 2543.5 |  |  | 2592 |  |  | 2618.5 |  |  | 2588 |  |  | 2434 |  |  | 2552.5 |  |  | 2503.5 |  |  | 2471 |  |  | 2486.5 |  |  | 2602 |  |  | 2676 |  |  | 2558 |  |  | 2699 |  |  | 2477 |  |  | 2491 |  |  | 2493 |  |  | 2578 |  |  | 2463 |  |  | 2485.5 |  |  | 2484 |  |  | 2476 |  |  | 2751 |  |  | 2619 |  |  | 2529 |  |  | 2460 |  |  | 2555 |  |  | 2573.5 |  |  | 2570 |  |  | 2606.5 |  |  | 2559 |  |  | 2538 |  |  | 2677.5 |  |  | 2625 |  |  | 2693.5 |  |  | 2492 |  |  | 2366 |  |  | 2547.5 |  |  | 2663 |  |  | 2653.5 |  |  | 2668 |  |  | 2449 |  |  | 2602.5 |  |  | 2645.5 |  |  | 2621 |  |  | 2583.5 |  |  | 2572.5 |  |  | 2610 |  |  | 2616 |  |  | 2729.5 |  |  | 2462.5 |  |  | 2668.5 |  |  | 2627 |  |  | 2631 |  |  | 2566 |  |  | 2681 |  |  | 2719 |  |  | 2564.5 |  |  | 2546 |  |  | 2490.5 |  |  | 2591.5 |  |  | 2522 |  |  | 2633 |  |  | 2783.5 |  |  | 2504.5 |  |  | 2506 |  |  | 2622.5 |  |  | 2447.5 |  |  | 2611 |  |  | 2503 |  |  | 2532 |  |  | 2514.5 |  |  | 2620 |  |  | 2585.5 |  |  | 2693.5 |  |  | 2582 |  |  | 2511.5 |  |  | 2543 |  |  | 2518 |  |  | 2656 |  |  | 2686 |  |  | 2395 |  |  | 2651 |  |  | 2706 |  |  | 2564 |  |  | 2663 |  |  | 2547 |  |  | 2588.5 |  |  | 2724.5 |  |  | 2538 |  |  | 2467 |  |  | 2726 |  |  | 2605.5 |  |  | 2673.5 |  |  | 2738.5 |  |  | 2466 |  |  | 2582 |  |  | 2677.5 |  |  | 2629.5 |  |  | 2435.5 |  |  | 2591 |  |  | 2664 |  |  | 2550 |  |  | 2635 |  |  | 2520 |  |  | 2585.5 |  |  | 2482.5 |  |  | 2702 |  |  | 2524 |  |  | 2515 |  |  | 2694 |  |  | 2521 |  |  | 2736.5 |  |  | 2628 |  |  | 2555 |  |  | 2470 |  |  | 2511 |  |  | 2583.5 |  |  | 2689 |  |  | 2556 |  |  | 2558 |  |  | 2650 |  |  | 2659.5 |  |  | 2585 |  |  | 2540 |  |  | 2484 |  |  | 2648.5 |  |  | 2607.5 |  |  | 2688.5 |  |  | 2660 |  |  | 2578 |  |  | 2443 |  |  | 2744 |  |  | 2518 |  |  | 2507.5 |  |  | 2622 |  |  | 2500.5 |  |  | 2645.5 |  |  | 2610.5 |  |  | 2626 |  |  | 2760.5 |  |  | 2450 |  |  | 2419 |  |  | 2526.5 |  |  | 2566.5 |  |  | 2684 |  |  | 2667.5 |  |  | 2719.5 |  |  | 2509 |  |  | 2652 |  |  | 2448.5 |  |  | 2538.5 |  |  | 2731 |  |  | 2649.5 |  |  | 2698 |  |  | 2583 |  |  | 2533.5 |  |  | 2633 |  |  | 2494 |  |  | 2615.5 |  |  | 2544 |  |  | 2684.5 |  |  | 2571 |  |  | 2749 |  |  | 2615 |  |  | 2535 |  |  | 2706.5 |  |  | 2685 |  |  | 2697.5 |  |  | 2457.5 |  |  | 2707.5 |  |  | 2657 |  |  | 2639.5 |  |  | 2760 |  |  | 2625 |  |  | 2399.5 |  |  | 2549.5 |  |  | 2650 |  |  | 2525.5 |  |  | 2750 |  |  | 2561 |  |  | 2778.5 |  |  | 2526 |  |  | 2531.5 |  |  | 2576.5 |  |  | 2620.5 |  |  | 2602 |  |  | 2433 |  |  | 2497 |  |  | 2541.5 |  |  | 2506 |  |  | 2741.5 |  |  | 2599 |  |  | 2545 |  |  | 2547 |  |  | 2614 |  |  | 2705 |  |  | 2540 |  |  | 2564 |  |  | 2770 |  |  | 2596 |  |  | 2587.5 |  |  | 2666 |  |  | 2564 |  |  | 2640.5 |  |  | 2479.5 |  |  | 2565.5 |  |  | 2552.5 |  |  | 2588 |  |  | 2679 |  |  | 2351.5 |  |  | 2773.5 |  |  | 2559.5 |  |  | 2588 |  |  | 2578 |  |  | 2461 |  |  | 2583 |  |  | 2445 |  |  | 2635 |  |  | 2667 |  |  | 2577.5 |  |  | 2629.5 |  |  | 2478 |  |  | 2486.5 |  |  | 2583.5 |  |  | 2527 |  |  | 2586 |  |  | 2577 |  |  | 2617 |  |  | 2539.5 |  |  | 2480.5 |  |  | 2602.5 |  |  | 2531 |  |  | 2558.5 |  |  | 2658 |  |  | 2561 |  |  | 2677 |  |  | 2489.5 |  |  | 2571 |  |  | 2454 |  |  | 2625.5 |  |  | 2512 |  |  | 2649.5 |  |  | 2716 |  |  | 2599.5 |  |  | 2537 |  |  | 2474.5 |  |  | 2592.5 |  |  | 2702 |  |  | 2604 |  |  | 2404 |  |  | 2581 |  |  | 2439.5 |  |  | 2542 |  |  | 2731 |  |  | 2513.5 |  |  | 2664.5 |  |  | 2410.5 |  |  | 2500 |  |  | 2674.5 |  |  | 2668.5 |  |  | 2493.5 |  |  | 2686 |  |  | 2598 |  |  | 2696.5 |  |  | 2605 |  |  | 2761 |  |  | 2568.5 |  |  | 2548 |  |  | 2681 |  |  | 2555 |  |  | 2467 |  |  | 2442.5 |  |  | 2623.5 |  |  | 2512 |  |  | 2691 |  |  | 2582 |  |  | 2559 |  |  | 2561 |  |  | 2514.5 |  |  | 2494.5 |  |  | 2578 |  |  | 2753 |  |  | 2741 |  |  | 2485.5 |  |  | 2797.5 |  |  | 2504 |  |  | 2577 |  |  | 2422 |  |  | 2605.5 |  |  | 2663.5 |  |  | 2566 |  |  | 2458 |  |  | 2646 |  |  | 2535 |  |  | 2547 |  |  | 2711 |  |  | 2563 |  |  | 2777.5 |  |  | 2555 |  |  | 2711 |  |  | 2571 |  |  | 2614.5 |  |  | 2670 |  |  | 2511 |  |  | 2440 |  |  | 2548 |  |  | 2521 |  |  | 2595 |  |  | 2621 |  |  | 2512.5 |  |  | 2556.5 |  |  | 2437.5 |  |  | 2677 |  |  | 2512 |  |  | 2570.5 |  |  | 2396 |  |  | 2479.5 |  |  | 2596.5 |  |  | 2542 |  |  | 2618 |  |  | 2615.5 |  |  | 2585 |  |  | 2638 |  |  | 2574 |  |  | 2605 |  |  | 2590 |  |  | 2512 |  |  | 2496 |  |  | 2613.5 |  |  | 2546 |  |  | 2688 |  |  | 2640 |  |  | 2560 |  |  | 2545 |  |  | 2607 |  |  | 2694 |  |  | 2667 |  |  | 2579 |  |  | 2643.5 |  |  | 2634.5 |  |  | 2558.5 |  |  | 2621.5 |  |  | 2594 |  |  | 2395 |  |  | 2695.5 |  |  | 2444 |  |  | 2598 |  |  | 2510.5 |  |  | 2687.5 |  |  | 2659 |  |  | 2551.5 |  |  | 2538.5 |  |  | 2395 |  |  | 2715 |  |  | 2544 |  |  | 2612 |  |  | 2541.5 |  |  | 2615 |  |  | 2517.5 |  |  | 2510.5 |  |  | 2583 |  |  | 2555 |  |  | 2664.5 |  |  | 2512 |  |  | 2573.5 |  |  | 2577 |  |  | 2628.5 |  |  | 2492.5 |  |  | 2348.5 |  |  | 2711.5 |  |  | 2612.5 |  |  | 2415 |  |  | 2525 |  |  | 2646.5 |  |  | 2611 |  |  | 2507 |  |  | 2566 |  |  | 2742 |  |  | 2699.5 |  |  | 2394 |  |  | 2504 |  |  | 2687 |  |  | 2532.5 |  |  | 2570 |  |  | 2430 |  |  | 2538 |  |  | 2754.5 |  |  | 2679 |  |  | 2413 |  |  | 2566 |  |  | 2694 |  |  | 2837.5 |  |  | 2560 |  |  | 2478.5 |  |  | 2580 |  |  | 2637 |  |  | 2826.5 |  |  | 2638 |  |  | 2528 |  |  | 2526.5 |  |  | 2592 |  |  | 2455 |  |  | 2460 |  |  | 2921.5 |  |  | 2616.5 |  |  | 2652 |  |  | 2481 |  |  | 2585.5 |  |  | 2601.5 |  |  | 2550 |  |  | 2667 |  |  | 2655.5 |  |  | 2797.5 |  |  | 2514.5 |  |  | 2649.5 |  |  | 2500.5 |  |  | 2812 |  |  | 2549.5 |  |  | 2696 |  |  | 2543 |  |  | 2686 |  |  | 2739 |  |  | 2591.5 |  |  | 2557 |  |  | 2497 |  |  | 2552.5 |  |  | 2595.5 |  |  | 2474 |  |  | 2658.5 |  |  | 2521.5 |  |  | 2654 |  |  | 2485 |  |  | 2597 |  |  | 2567.5 |  |  | 2650 |  |  | 2631.5 |  |  | 2647 |  |  | 2622 |  |  | 2859.5 |  |  | 2533 |  |  | 2699 |  |  | 2456 |  |  | 2667 |  |  | 2699 |  |  | 2595 |  |  | 2604 |  |  | 2546 |  |  | 2485.5 |  |  | 2470.5 |  |  | 2527 |  |  | 2609.5 |  |  | 2426.5 |  |  | 2464 |  |  | 2518 |  |  | 2621 |  |  | 2634.5 |  |  | 2495.5 |  |  | 2635 |  |  | 2618 |  |  | 2440 |  |  | 2510 |  |  | 2515 |  |  | 2486 |  |  | 2640 |  |  | 2522.5 |  |  | 2700 |  |  | 2711 |  |  | 2675 |  |  | 2466 |  |  | 2462 |  |  | 2574.5 |  |  | 2790.5 |  |  | 2412.5 |  |  | 2474 |  |  | 2518 |  |  | 2493.5 |  |  | 2633.5 |  |  | 2629.5 |  |  | 2458 |  |  | 2626.5 |  |  | 2692.5 |  |  | 2673 |  |  | 2583.5 |  |  | 2629.5 |  |  | 2552 |  |  | 2441 |  |  | 2529 |  |  | 2674 |  |  | 2535 |  |  | 2399 |  |  | 2680 |  |  | 2644 |  |  | 2473 |  |  | 2581 |  |  | 2735.5 |  |  | 2559 |  |  | 2546 |  |  | 2520 |  |  | 2436.5 |  |  | 2530 |  |  | 2612.5 |  |  | 2718 |  |  | 2674 |  |  | 2578 |  |  | 2647 |  |  | 2718.5 |  |  | 2570 |  |  | 2419 |  |  | 2628.5 |  |  | 2606 |  |  | 2482 |  |  | 2557.5 |  |  | 2547.5 |  |  | 2577 |  |  | 2489.5 |  |  | 2673 |  |  | 2503.5 |  |  | 2658 |  |  | 2612 |  |  | 2504.5 |  |  | 2616.5 |  |  | 2610 |  |  | 2650 |  |  | 2598 |  |  | 2567 |  |  | 2516 |  |  | 2550 |  |  | 2408 |  |  | 2503 |  |  | 2646.5 |  |  | 2399 |  |  | 2661.5 |  |  | 2486 |  |  | 2578.5 |  |  | 2540.5 |  |  | 2537 |  |  | 2659 |  |  | 2667.5 |  |  | 2599 |  |  | 2608 |  |  | 2641 |  |  | 2557.5 |  |  | 2664 |  |  | 2477.5 |  |  | 2335 |  |  | 2497 |  |  | 2523 |  |  | 2560 |  |  | 2634.5 |  |  | 2563 |  |  | 2550 |  |  | 2685 |  |  | 2483.5 |  |  | 2756 |  |  | 2649 |  |  | 2674 |  |  | 2578 |  |  | 2578.5 |  |  | 2421.5 |  |  | 2739 |  |  | 2735 |  |  | 2643 |  |  | 2652.5 |  |  | 2615 |  |  | 2458 |  |  | 2510 |  |  | 2748.5 |  |  | 2580.5 |  |  | 2576.5 |  |  | 2640 |  |  | 2655 |  |  | 2650 |  |  | 2491.5 |  |  | 2641 |  |  | 2486.5 |  |  | 2450 |  |  | 2496 |  |  | 2546 |  |  | 2499.5 |  |  | 2617.5 |  |  | 2583 |  |  | 2575 |  |  | 2631.5 |  |  | 2646 |  |  | 2512 |  |  | 2638.5 |  |  | 2439 |  |  | 2435 |  |  | 2609.5 |  |  | 2474 |  |  | 2610 |  |  | 2514.5 |  |  | 2674 |  |  | 2477.5 |  |  | 2552 |  |  | 2382.5 |  |  | 2646.5 |  |  | 2470 |  |  | 2615 |  |  | 2735.5 |  |  | 2489.5 |  |  | 2614 |  |  | 2597 |  |  | 2622 |  |  | 2630.5 |  |  | 2634 |  |  | 2398 |  |  | 2478 |  |  | 2665.5 |  |  | 2615.5 |  |  | 2644 |  |  | 2675 |  |  | 2587 |  |  | 2558 |  |  | 2632 |  |  | 2554 |  |  | 2577 |  |  | 2564.5 |  |  | 2756.5 |  |  | 2455.5 |  |  | 2524 |  |  | 2549.5 |  |  | 2623 |  |  | 2572 |  |  | 2591.5 |  |  | 2466.5 |  |  | 2468 |  |  | 2611 |  |  | 2514.5 |  |  | 2544 |  |  | 2600 |  |  | 2446.5 |  |  | 2671.5 |  |  | 2527 |  |  | 2553 |  |  | 2546 |  |  | 2468.5 |  |  | 2507 |  |  | 2467 |  |  | 2548 |  |  | 2644 |  |  | 2720 |  |  | 2443.5 |  |  | 2684 |  |  | 2591 |  |  | 2450 |  |  | 2679.5 |  |  | 2601 |  |  | 2443.5 |  |  | 2487.5 |  |  | 2502 |  |  | 2698 |  |  | 2580.5 |  |  | 2516.5 |  |  | 2493.5 |  |  | 2528.5 |  |  | 2603.5 |  |  | 2641 |  |  | 2548 |  |  | 2546.5 |  |  | 2547.5 |  |  | 2528 |  |  | 2480 |  |  | 2548.5 |  |  | 2786 |  |  | 2571 |  |  | 2449 |  |  | 2637.5 |  |  | 2733 |  |  | 2518.5 |  |  | 2431 |  |  | 2596.5 |  |  | 2775.5 |  |  | 2709.5 |  |  | 2688 |  |  | 2581 |  |  | 2580.5 |  |  | 2500.5 |  |  | 2655 |  |  | 2574 |  |  | 2637.5 |  |  | 2744 |  |  | 2567.5 |  |  | 2567.5 |  |  | 2516 |  |  | 2592 |  |  | 2421.5 |  |  | 2688.5 |  |  | 2618 |  |  | 2543.5 |  |  | 2597.5 |  |  | 2636 |  |  | 2672 |  |  | 2674 |  |  | 2612.5 |  |  | 2613 |  |  | 2477 |  |  | 2566 |  |  | 2494 |  |  | 2541 |  |  | 2549 |  |  | 2766.5 |  |  | 2595.5 |  |  | 2539 |  |  | 2540 |  |  | 2631 |  |  | 2487.5 |  |  | 2594 |  |  | 2704 |  |  | 2541.5 |  |  | 2732.5 |  |  | 2570 |  |  | 2532.5 |  |  | 2700 |  |  | 2476 |  |  | 2584 |  |  | 2691.5 |  |  | 2652 |  |  | 2455.5 |  |  | 2535.5 |  |  | 2417 |  |  | 2570.5 |  |  | 2386.5 |  |  | 2575 |  |  | 2471 |  |  | 2678 |  |  | 2554.5 |  |  | 2483 |  |  | 2515.5 |  |  | 2708.5 |  |  | 2679 |  |  | 2463.5 |  |  | 2458 |  |  | 2594 |  |  | 2543 |  |  | 2561 |  |  | 2454 |  |  | 2665.5 |  |  | 2582 |  |  | 2676 |  |  | 2529 |  |  | 2687 |  |  | 2594.5 |  |  | 2583.5 |  |  | 2588 |  |  | 2691 |  |  | 2555 |  |  | 2587 |  |  | 2613 |  |  | 2467.5 |  |  | 2547 |  |  | 2676.5 |  |  | 2647 |  |  | 2448 |  |  | 2604 |  |  | 2568 |  |  | 2631.5 |  |  | 2623 |  |  | 2646.5 |  |  | 2487 |  |  | 2700 |  |  | 2652 |  |  | 2601.5 |  |  | 2497 |  |  | 2449 |  |  | 2514 |  |  | 2747 |  |  | 2873 |  |  | 2531.5 |  |  | 2642.5 |  |  | 2468 |  |  | 2495.5 |  |  | 2512 |  |  | 2566.5 |  |  | 2514.5 |  |  | 2548.5 |  |  | 2555.5 |  |  | 2475 |  |  | 2760 |  |  | 2437 |  |  | 2430 |  |  | 2547 |  |  | 2675 |  |  | 2564.5 |  |  | 2550.5 |  |  | 2733.5 |  |  | 2552 |  |  | 2725.5 |  |  | 2477.5 |  |  | 2672.5 |  |  | 2445.5 |  |  | 2579 |  |  | 2583.5 |  |  | 2628.5 |  |  | 2686 |  |  | 2461.5 |  |  | 2727.5 |  |  | 2604.5 |  |  | 2720 |  |  | 2636.5 |  |  | 2649 |  |  | 2596 |  |  | 2547.5 |  |  | 2608.5 |  |  | 2627 |  |  | 2712 |  |  | 2390.5 |  |  | 2420.5 |  |  | 2528.5 |  |  | 2617 |  |  | 2480 |  |  | 2543 |  |  | 2686.5 |  |  | 2633.5 |  |  | 2573 |  |  | 2634.5 |  |  | 2425 |  |  | 2558 |  |  | 2601.5 |  |  | 2461.5 |  |  | 2511 |  |  | 2542.5 |  |  | 2678 |  |  | 2471.5 |  |  | 2692.5 |  |  | 2697 |  |  | 2591.5 |  |  | 2642 |  |  | 2564.5 |  |  | 2563 |  |  | 2608 |  |  | 2611 |  |  | 2542.5 |  |  | 2478.5 |  |  | 2594 |  |  | 2514 |  |  | 2482 |  |  | 2547.5 |  |  | 2608.5 |  |  | 2701 |  |  | 2601.5 |  |  | 2522 |  |  | 2399.5 |  |  | 2623.5 |  |  | 2454 |  |  | 2491 |  |  | 2510 |  |  | 2543.5 |  |  | 2466 |  |  | 2624.5 |  |  | 2574 |  |  | 2535.5 |  |  | 2766 |  |  | 2421.5 |  |  | 2563 |  |  | 2590.5 |  |  | 2614.5 |  |  | 2490 |  |  | 2530 |  |  | 2789 |  |  | 2591 |  |  | 2642.5 |  |  | 2514 |  |  | 2535.5 |  |  | 2475 |  |  | 2503 |  |  | 2556 |  |  | 2711 |  |  | 2650 |  |  | 2596 |  |  | 2668 |  |  | 2505.5 |  |  | 2561 |  |  | 2615
90 |  | 2726.5 |  |  | 2720 |  |  | 2744.5 |  |  | 2653 |  |  | 2514.5 |  |  | 2785 |  |  | 2689 |  |  | 2618 |  |  | 2477.5 |  |  | 2480 |  |  | 2568 |  |  | 2747 |  |  | 2700 |  |  | 2746 |  |  | 2523.5 |  |  | 2671.5 |  |  | 2582 |  |  | 2671 |  |  | 2770 |  |  | 2508.5 |  |  | 2708 |  |  | 2704 |  |  | 2531 |  |  | 2652 |  |  | 2628.5 |  |  | 2741 |  |  | 2546 |  |  | 2647 |  |  | 2755 |  |  | 2447 |  |  | 2621 |  |  | 2538.5 |  |  | 2703.5 |  |  | 2580.5 |  |  | 2572 |  |  | 2627.5 |  |  | 2655.5 |  |  | 2663.5 |  |  | 2684 |  |  | 2633 |  |  | 2492.5 |  |  | 2538 |  |  | 2587.5 |  |  | 2540.5 |  |  | 2629.5 |  |  | 2791.5 |  |  | 2721.5 |  |  | 2571 |  |  | 2433 |  |  | 2563.5 |  |  | 2529 |  |  | 2565.5 |  |  | 2549.5 |  |  | 2641 |  |  | 2584 |  |  | 2569 |  |  | 2509 |  |  | 2701 |  |  | 2581 |  |  | 2627.5 |  |  | 2633.5 |  |  | 2566.5 |  |  | 2532 |  |  | 2631 |  |  | 2419 |  |  | 2515.5 |  |  | 2647 |  |  | 2546.5 |  |  | 2705.5 |  |  | 2709.5 |  |  | 2635 |  |  | 2752 |  |  | 2714 |  |  | 2624.5 |  |  | 2701.5 |  |  | 2591.5 |  |  | 2703.5 |  |  | 2680.5 |  |  | 2652.5 |  |  | 2613.5 |  |  | 2548.5 |  |  | 2426 |  |  | 2711 |  |  | 2509 |  |  | 2687.5 |  |  | 2686 |  |  | 2553.5 |  |  | 2701 |  |  | 2594 |  |  | 2585.5 |  |  | 2749.5 |  |  | 2500 |  |  | 2705 |  |  | 2533.5 |  |  | 2810 |  |  | 2532.5 |  |  | 2655.5 |  |  | 2619.5 |  |  | 2569.5 |  |  | 2513.5 |  |  | 2557 |  |  | 2603 |  |  | 2448 |  |  | 2528.5 |  |  | 2603.5 |  |  | 2648.5 |  |  | 2521.5 |  |  | 2578 |  |  | 2529 |  |  | 2643.5 |  |  | 2561 |  |  | 2678.5 |  |  | 2640 |  |  | 2535 |  |  | 2572.5 |  |  | 2603 |  |  | 2596 |  |  | 2518 |  |  | 2648 |  |  | 2591.5 |  |  | 2613.5 |  |  | 2526.5 |  |  | 2709 |  |  | 2544 |  |  | 2515 |  |  | 2539 |  |  | 2564.5 |  |  | 2639 |  |  | 2647.5 |  |  | 2614 |  |  | 2449 |  |  | 2567.5 |  |  | 2524.5 |  |  | 2486 |  |  | 2533.5 |  |  | 2617 |  |  | 2705 |  |  | 2573 |  |  | 2728 |  |  | 2516 |  |  | 2530 |  |  | 2532 |  |  | 2602 |  |  | 2489 |  |  | 2524.5 |  |  | 2523 |  |  | 2500 |  |  | 2777 |  |  | 2640 |  |  | 2576 |  |  | 2499 |  |  | 2594 |  |  | 2612.5 |  |  | 2594 |  |  | 2621.5 |  |  | 2583 |  |  | 2564 |  |  | 2724.5 |  |  | 2651 |  |  | 2719.5 |  |  | 2531 |  |  | 2381 |  |  | 2576.5 |  |  | 2678 |  |  | 2682.5 |  |  | 2697 |  |  | 2464 |  |  | 2641.5 |  |  | 2671.5 |  |  | 2645 |  |  | 2609.5 |  |  | 2619.5 |  |  | 2634 |  |  | 2663 |  |  | 2768.5 |  |  | 2486.5 |  |  | 2707.5 |  |  | 2666 |  |  | 2678 |  |  | 2581 |  |  | 2705 |  |  | 2740 |  |  | 2603.5 |  |  | 2585 |  |  | 2514.5 |  |  | 2630.5 |  |  | 2551 |  |  | 2662 |  |  | 2822.5 |  |  | 2525.5 |  |  | 2521 |  |  | 2661.5 |  |  | 2494.5 |  |  | 2632 |  |  | 2542 |  |  | 2571 |  |  | 2543.5 |  |  | 2641 |  |  | 2606.5 |  |  | 2732.5 |  |  | 2621 |  |  | 2535.5 |  |  | 2572 |  |  | 2565 |  |  | 2682 |  |  | 2710 |  |  | 2421 |  |  | 2680 |  |  | 2753 |  |  | 2611 |  |  | 2689 |  |  | 2562 |  |  | 2635.5 |  |  | 2750.5 |  |  | 2562 |  |  | 2488 |  |  | 2750 |  |  | 2620.5 |  |  | 2720.5 |  |  | 2762.5 |  |  | 2492 |  |  | 2629 |  |  | 2701.5 |  |  | 2668.5 |  |  | 2459.5 |  |  | 2612 |  |  | 2688 |  |  | 2571 |  |  | 2674 |  |  | 2541 |  |  | 2624.5 |  |  | 2503.5 |  |  | 2726 |  |  | 2563 |  |  | 2544 |  |  | 2720 |  |  | 2542 |  |  | 2757.5 |  |  | 2654 |  |  | 2594 |  |  | 2509 |  |  | 2550 |  |  | 2622.5 |  |  | 2710 |  |  | 2603 |  |  | 2597 |  |  | 2674 |  |  | 2706.5 |  |  | 2624 |  |  | 2579 |  |  | 2531 |  |  | 2677.5 |  |  | 2646.5 |  |  | 2709.5 |  |  | 2699 |  |  | 2593 |  |  | 2469 |  |  | 2759 |  |  | 2557 |  |  | 2536.5 |  |  | 2661 |  |  | 2526.5 |  |  | 2692.5 |  |  | 2636.5 |  |  | 2665 |  |  | 2781.5 |  |  | 2471 |  |  | 2458 |  |  | 2565.5 |  |  | 2590.5 |  |  | 2710 |  |  | 2706.5 |  |  | 2766.5 |  |  | 2538 |  |  | 2691 |  |  | 2487.5 |  |  | 2553.5 |  |  | 2778 |  |  | 2664.5 |  |  | 2737 |  |  | 2622 |  |  | 2557.5 |  |  | 2657 |  |  | 2520 |  |  | 2644.5 |  |  | 2591 |  |  | 2699.5 |  |  | 2618 |  |  | 2764 |  |  | 2641 |  |  | 2564 |  |  | 2727.5 |  |  | 2732 |  |  | 2726.5 |  |  | 2496.5 |  |  | 2731.5 |  |  | 2683 |  |  | 2668.5 |  |  | 2786 |  |  | 2654 |  |  | 2428.5 |  |  | 2570.5 |  |  | 2689 |  |  | 2564.5 |  |  | 2789 |  |  | 2608 |  |  | 2793.5 |  |  | 2541 |  |  | 2570.5 |  |  | 2615.5 |  |  | 2646.5 |  |  | 2641 |  |  | 2472 |  |  | 2536 |  |  | 2556.5 |  |  | 2532 |  |  | 2788.5 |  |  | 2623 |  |  | 2592 |  |  | 2594 |  |  | 2629 |  |  | 2734 |  |  | 2555 |  |  | 2611 |  |  | 2817 |  |  | 2617 |  |  | 2626.5 |  |  | 2695 |  |  | 2593 |  |  | 2661.5 |  |  | 2494.5 |  |  | 2580.5 |  |  | 2567.5 |  |  | 2609 |  |  | 2708 |  |  | 2390.5 |  |  | 2820.5 |  |  | 2580.5 |  |  | 2627 |  |  | 2599 |  |  | 2500 |  |  | 2622 |  |  | 2474 |  |  | 2674 |  |  | 2693 |  |  | 2616.5 |  |  | 2668.5 |  |  | 2504 |  |  | 2507.5 |  |  | 2622.5 |  |  | 2566 |  |  | 2625 |  |  | 2616 |  |  | 2664 |  |  | 2560.5 |  |  | 2506.5 |  |  | 2628.5 |  |  | 2546 |  |  | 2597.5 |  |  | 2682 |  |  | 2582 |  |  | 2701 |  |  | 2504.5 |  |  | 2600 |  |  | 2469 |  |  | 2640.5 |  |  | 2541 |  |  | 2670.5 |  |  | 2755 |  |  | 2638.5 |  |  | 2584 |  |  | 2513.5 |  |  | 2639.5 |  |  | 2741 |  |  | 2651 |  |  | 2430 |  |  | 2602 |  |  | 2465.5 |  |  | 2571 |  |  | 2770 |  |  | 2542.5 |  |  | 2688.5 |  |  | 2425.5 |  |  | 2539 |  |  | 2700.5 |  |  | 2715.5 |  |  | 2517.5 |  |  | 2712 |  |  | 2637 |  |  | 2743.5 |  |  | 2631 |  |  | 2808 |  |  | 2607.5 |  |  | 2595 |  |  | 2720 |  |  | 2576 |  |  | 2488 |  |  | 2463.5 |  |  | 2652.5 |  |  | 2559 |  |  | 2715 |  |  | 2629 |  |  | 2580 |  |  | 2590 |  |  | 2561.5 |  |  | 2541.5 |  |  | 2617 |  |  | 2782 |  |  | 2780 |  |  | 2509.5 |  |  | 2821.5 |  |  | 2519 |  |  | 2624 |  |  | 2461 |  |  | 2652.5 |  |  | 2687.5 |  |  | 2587 |  |  | 2482 |  |  | 2693 |  |  | 2556 |  |  | 2568 |  |  | 2726 |  |  | 2584 |  |  | 2816.5 |  |  | 2579 |  |  | 2750 |  |  | 2618 |  |  | 2661.5 |  |  | 2696 |  |  | 2550 |  |  | 2455 |  |  | 2572 |  |  | 2560 |  |  | 2634 |  |  | 2668 |  |  | 2551.5 |  |  | 2580.5 |  |  | 2458.5 |  |  | 2692 |  |  | 2551 |  |  | 2594.5 |  |  | 2411 |  |  | 2505.5 |  |  | 2620.5 |  |  | 2568 |  |  | 2665 |  |  | 2636.5 |  |  | 2614 |  |  | 2662 |  |  | 2621 |  |  | 2652 |  |  | 2605 |  |  | 2541 |  |  | 2520 |  |  | 2639.5 |  |  | 2567 |  |  | 2727 |  |  | 2669 |  |  | 2607 |  |  | 2584 |  |  | 2646 |  |  | 2733 |  |  | 2691 |  |  | 2600 |  |  | 2667.5 |  |  | 2673.5 |  |  | 2597.5 |  |  | 2645.5 |  |  | 2633 |  |  | 2410 |  |  | 2719.5 |  |  | 2459 |  |  | 2619 |  |  | 2549.5 |  |  | 2702.5 |  |  | 2698 |  |  | 2598.5 |  |  | 2585.5 |  |  | 2419 |  |  | 2736 |  |  | 2565 |  |  | 2636 |  |  | 2562.5 |  |  | 2662 |  |  | 2532.5 |  |  | 2534.5 |  |  | 2609 |  |  | 2579 |  |  | 2679.5 |  |  | 2527 |  |  | 2597.5 |  |  | 2598 |  |  | 2649.5 |  |  | 2531.5 |  |  | 2377.5 |  |  | 2758.5 |  |  | 2636.5 |  |  | 2430 |  |  | 2540 |  |  | 2670.5 |  |  | 2626 |  |  | 2533 |  |  | 2605 |  |  | 2766 |  |  | 2714.5 |  |  | 2415 |  |  | 2543 |  |  | 2734 |  |  | 2553.5 |  |  | 2585 |  |  | 2456 |  |  | 2585 |  |  | 2793.5 |  |  | 2718 |  |  | 2439 |  |  | 2605 |  |  | 2733 |  |  | 2876.5 |  |  | 2599 |  |  | 2493.5 |  |  | 2606 |  |  | 2676 |  |  | 2847.5 |  |  | 2685 |  |  | 2567 |  |  | 2541.5 |  |  | 2616 |  |  | 2476 |  |  | 2481 |  |  | 2936.5 |  |  | 2640.5 |  |  | 2676 |  |  | 2520 |  |  | 2614.5 |  |  | 2640.5 |  |  | 2571 |  |  | 2706 |  |  | 2694.5 |  |  | 2826.5 |  |  | 2561.5 |  |  | 2678.5 |  |  | 2547.5 |  |  | 2833 |  |  | 2578.5 |  |  | 2722 |  |  | 2590 |  |  | 2725 |  |  | 2778 |  |  | 2630.5 |  |  | 2572 |  |  | 2544 |  |  | 2591.5 |  |  | 2634.5 |  |  | 2500 |  |  | 2697.5 |  |  | 2547.5 |  |  | 2680 |  |  | 2524 |  |  | 2636 |  |  | 2591.5 |  |  | 2665 |  |  | 2655.5 |  |  | 2694 |  |  | 2643 |  |  | 2883.5 |  |  | 2572 |  |  | 2725 |  |  | 2480 |  |  | 2688 |  |  | 2725 |  |  | 2619 |  |  | 2643 |  |  | 2570 |  |  | 2506.5 |  |  | 2509.5 |  |  | 2548 |  |  | 2635.5 |  |  | 2452.5 |  |  | 2503 |  |  | 2533 |  |  | 2645 |  |  | 2663.5 |  |  | 2516.5 |  |  | 2661 |  |  | 2657 |  |  | 2466 |  |  | 2557 |  |  | 2554 |  |  | 2525 |  |  | 2664 |  |  | 2543.5 |  |  | 2747 |  |  | 2758 |  |  | 2704 |  |  | 2492 |  |  | 2491 |  |  | 2613.5 |  |  | 2811.5 |  |  | 2451.5 |  |  | 2513 |  |  | 2557 |  |  | 2517.5 |  |  | 2680.5 |  |  | 2668.5 |  |  | 2497 |  |  | 2650.5 |  |  | 2716.5 |  |  | 2702 |  |  | 2609.5 |  |  | 2676.5 |  |  | 2576 |  |  | 2488 |  |  | 2568 |  |  | 2698 |  |  | 2574 |  |  | 2414 |  |  | 2719 |  |  | 2665 |  |  | 2494 |  |  | 2628 |  |  | 2764.5 |  |  | 2598 |  |  | 2567 |  |  | 2549 |  |  | 2462.5 |  |  | 2545 |  |  | 2636.5 |  |  | 2757 |  |  | 2721 |  |  | 2617 |  |  | 2673 |  |  | 2757.5 |  |  | 2591 |  |  | 2466 |  |  | 2649.5 |  |  | 2621 |  |  | 2511 |  |  | 2578.5 |  |  | 2576.5 |  |  | 2601 |  |  | 2515.5 |  |  | 2688 |  |  | 2532.5 |  |  | 2673 |  |  | 2636 |  |  | 2519.5 |  |  | 2655.5 |  |  | 2636 |  |  | 2665 |  |  | 2619 |  |  | 2591 |  |  | 2545 |  |  | 2589 |  |  | 2455 |  |  | 2518 |  |  | 2672.5 |  |  | 2438 |  |  | 2708.5 |  |  | 2501 |  |  | 2604.5 |  |  | 2564.5 |  |  | 2561 |  |  | 2688 |  |  | 2691.5 |  |  | 2646 |  |  | 2655 |  |  | 2670 |  |  | 2586.5 |  |  | 2703 |  |  | 2516.5 |  |  | 2361 |  |  | 2521 |  |  | 2562 |  |  | 2589 |  |  | 2660.5 |  |  | 2589 |  |  | 2579 |  |  | 2724 |  |  | 2509.5 |  |  | 2785 |  |  | 2664 |  |  | 2698 |  |  | 2617 |  |  | 2625.5 |  |  | 2450.5 |  |  | 2763 |  |  | 2774 |  |  | 2669 |  |  | 2676.5 |  |  | 2644 |  |  | 2505 |  |  | 2525 |  |  | 2772.5 |  |  | 2619.5 |  |  | 2591.5 |  |  | 2687 |  |  | 2670 |  |  | 2674 |  |  | 2520.5 |  |  | 2656 |  |  | 2510.5 |  |  | 2471 |  |  | 2535 |  |  | 2572 |  |  | 2525.5 |  |  | 2632.5 |  |  | 2604 |  |  | 2614 |  |  | 2670.5 |  |  | 2675 |  |  | 2551 |  |  | 2659.5 |  |  | 2486 |  |  | 2459 |  |  | 2648.5 |  |  | 2513 |  |  | 2625 |  |  | 2561.5 |  |  | 2700 |  |  | 2516.5 |  |  | 2581 |  |  | 2406.5 |  |  | 2661.5 |  |  | 2517 |  |  | 2662 |  |  | 2761.5 |  |  | 2536.5 |  |  | 2640 |  |  | 2612 |  |  | 2651 |  |  | 2651.5 |  |  | 2660 |  |  | 2427 |  |  | 2517 |  |  | 2689.5 |  |  | 2641.5 |  |  | 2691 |  |  | 2714 |  |  | 2611 |  |  | 2579 |  |  | 2679 |  |  | 2580 |  |  | 2616 |  |  | 2588.5 |  |  | 2785.5 |  |  | 2494.5 |  |  | 2545 |  |  | 2575.5 |  |  | 2662 |  |  | 2587 |  |  | 2630.5 |  |  | 2487.5 |  |  | 2492 |  |  | 2640 |  |  | 2543.5 |  |  | 2573 |  |  | 2621 |  |  | 2485.5 |  |  | 2697.5 |  |  | 2551 |  |  | 2568 |  |  | 2593 |  |  | 2489.5 |  |  | 2536 |  |  | 2514 |  |  | 2569 |  |  | 2668 |  |  | 2749 |  |  | 2490.5 |  |  | 2708 |  |  | 2612 |  |  | 2471 |  |  | 2718.5 |  |  | 2616 |  |  | 2464.5 |  |  | 2526.5 |  |  | 2549 |  |  | 2727 |  |  | 2627.5 |  |  | 2537.5 |  |  | 2517.5 |  |  | 2552.5 |  |  | 2642.5 |  |  | 2680 |  |  | 2595 |  |  | 2575.5 |  |  | 2562.5 |  |  | 2552 |  |  | 2509 |  |  | 2572.5 |  |  | 2825 |  |  | 2618 |  |  | 2496 |  |  | 2661.5 |  |  | 2759 |  |  | 2533.5 |  |  | 2470 |  |  | 2620.5 |  |  | 2822.5 |  |  | 2724.5 |  |  | 2727 |  |  | 2620 |  |  | 2627.5 |  |  | 2529.5 |  |  | 2676 |  |  | 2613 |  |  | 2658.5 |  |  | 2765 |  |  | 2614.5 |  |  | 2591.5 |  |  | 2555 |  |  | 2631 |  |  | 2450.5 |  |  | 2703.5 |  |  | 2657 |  |  | 2582.5 |  |  | 2621.5 |  |  | 2662 |  |  | 2701 |  |  | 2713 |  |  | 2636.5 |  |  | 2634 |  |  | 2492 |  |  | 2595 |  |  | 2523 |  |  | 2556 |  |  | 2570 |  |  | 2805.5 |  |  | 2619.5 |  |  | 2586 |  |  | 2579 |  |  | 2652 |  |  | 2508.5 |  |  | 2620 |  |  | 2743 |  |  | 2580.5 |  |  | 2771.5 |  |  | 2591 |  |  | 2547.5 |  |  | 2739 |  |  | 2515 |  |  | 2631 |  |  | 2730.5 |  |  | 2691 |  |  | 2494.5 |  |  | 2574.5 |  |  | 2464 |  |  | 2585.5 |  |  | 2412.5 |  |  | 2614 |  |  | 2518 |  |  | 2717 |  |  | 2593.5 |  |  | 2522 |  |  | 2536.5 |  |  | 2747.5 |  |  | 2726 |  |  | 2502.5 |  |  | 2497 |  |  | 2609 |  |  | 2582 |  |  | 2600 |  |  | 2483 |  |  | 2686.5 |  |  | 2603 |  |  | 2723 |  |  | 2576 |  |  | 2711 |  |  | 2615.5 |  |  | 2622.5 |  |  | 2609 |  |  | 2730 |  |  | 2579 |  |  | 2626 |  |  | 2652 |  |  | 2493.5 |  |  | 2573 |  |  | 2691.5 |  |  | 2686 |  |  | 2469 |  |  | 2651 |  |  | 2615 |  |  | 2670.5 |  |  | 2670 |  |  | 2667.5 |  |  | 2508 |  |  | 2739 |  |  | 2676 |  |  | 2616.5 |  |  | 2523 |  |  | 2496 |  |  | 2540 |  |  | 2768 |  |  | 2899 |  |  | 2555.5 |  |  | 2668.5 |  |  | 2494 |  |  | 2521.5 |  |  | 2551 |  |  | 2581.5 |  |  | 2529.5 |  |  | 2577.5 |  |  | 2576.5 |  |  | 2499 |  |  | 2799 |  |  | 2484 |  |  | 2445 |  |  | 2568 |  |  | 2690 |  |  | 2588.5 |  |  | 2574.5 |  |  | 2748.5 |  |  | 2591 |  |  | 2746.5 |  |  | 2501.5 |  |  | 2698.5 |  |  | 2484.5 |  |  | 2600 |  |  | 2622.5 |  |  | 2667.5 |  |  | 2712 |  |  | 2476.5 |  |  | 2742.5 |  |  | 2628.5 |  |  | 2767 |  |  | 2683.5 |  |  | 2678 |  |  | 2622 |  |  | 2571.5 |  |  | 2632.5 |  |  | 2666 |  |  | 2751 |  |  | 2411.5 |  |  | 2459.5 |  |  | 2567.5 |  |  | 2656 |  |  | 2504 |  |  | 2582 |  |  | 2715.5 |  |  | 2659.5 |  |  | 2612 |  |  | 2673.5 |  |  | 2446 |  |  | 2597 |  |  | 2630.5 |  |  | 2482.5 |  |  | 2535 |  |  | 2571.5 |  |  | 2699 |  |  | 2495.5 |  |  | 2718.5 |  |  | 2744 |  |  | 2630.5 |  |  | 2681 |  |  | 2593.5 |  |  | 2610 |  |  | 2647 |  |  | 2640 |  |  | 2566.5 |  |  | 2525.5 |  |  | 2623 |  |  | 2538 |  |  | 2521 |  |  | 2571.5 |  |  | 2655.5 |  |  | 2725 |  |  | 2616.5 |  |  | 2561 |  |  | 2425.5 |  |  | 2647.5 |  |  | 2475 |  |  | 2515 |  |  | 2525 |  |  | 2567.5 |  |  | 2490 |  |  | 2671.5 |  |  | 2589 |  |  | 2564.5 |  |  | 2805 |  |  | 2447.5 |  |  | 2584 |  |  | 2619.5 |  |  | 2638.5 |  |  | 2537 |  |  | 2556 |  |  | 2828 |  |  | 2630 |  |  | 2689.5 |  |  | 2561 |  |  | 2574.5 |  |  | 2504 |  |  | 2550 |  |  | 2580 |  |  | 2758 |  |  | 2671 |  |  | 2620 |  |  | 2694 |  |  | 2552.5 |  |  | 2582 |  |  | 2662
91 |  | 2773.5 |  |  | 2746 |  |  | 2783.5 |  |  | 2668 |  |  | 2538.5 |  |  | 2809 |  |  | 2704 |  |  | 2644 |  |  | 2501.5 |  |  | 2519 |  |  | 2594 |  |  | 2786 |  |  | 2739 |  |  | 2785 |  |  | 2552.5 |  |  | 2695.5 |  |  | 2621 |  |  | 2710 |  |  | 2796 |  |  | 2523.5 |  |  | 2732 |  |  | 2725 |  |  | 2546 |  |  | 2691 |  |  | 2654.5 |  |  | 2765 |  |  | 2567 |  |  | 2686 |  |  | 2770 |  |  | 2462 |  |  | 2636 |  |  | 2567.5 |  |  | 2727.5 |  |  | 2595.5 |  |  | 2598 |  |  | 2651.5 |  |  | 2684.5 |  |  | 2710.5 |  |  | 2731 |  |  | 2657 |  |  | 2516.5 |  |  | 2567 |  |  | 2634.5 |  |  | 2561.5 |  |  | 2650.5 |  |  | 2820.5 |  |  | 2747.5 |  |  | 2610 |  |  | 2472 |  |  | 2589.5 |  |  | 2544 |  |  | 2604.5 |  |  | 2570.5 |  |  | 2667 |  |  | 2608 |  |  | 2584 |  |  | 2535 |  |  | 2740 |  |  | 2607 |  |  | 2666.5 |  |  | 2680.5 |  |  | 2590.5 |  |  | 2579 |  |  | 2657 |  |  | 2443 |  |  | 2554.5 |  |  | 2673 |  |  | 2572.5 |  |  | 2752.5 |  |  | 2748.5 |  |  | 2656 |  |  | 2791 |  |  | 2740 |  |  | 2645.5 |  |  | 2727.5 |  |  | 2612.5 |  |  | 2750.5 |  |  | 2704.5 |  |  | 2699.5 |  |  | 2660.5 |  |  | 2574.5 |  |  | 2447 |  |  | 2758 |  |  | 2535 |  |  | 2713.5 |  |  | 2725 |  |  | 2592.5 |  |  | 2725 |  |  | 2615 |  |  | 2609.5 |  |  | 2778.5 |  |  | 2521 |  |  | 2744 |  |  | 2554.5 |  |  | 2831 |  |  | 2547.5 |  |  | 2702.5 |  |  | 2666.5 |  |  | 2608.5 |  |  | 2539.5 |  |  | 2604 |  |  | 2618 |  |  | 2495 |  |  | 2567.5 |  |  | 2642.5 |  |  | 2672.5 |  |  | 2560.5 |  |  | 2617 |  |  | 2550 |  |  | 2672.5 |  |  | 2587 |  |  | 2702.5 |  |  | 2669 |  |  | 2574 |  |  | 2596.5 |  |  | 2618 |  |  | 2625 |  |  | 2539 |  |  | 2677 |  |  | 2620.5 |  |  | 2652.5 |  |  | 2565.5 |  |  | 2738 |  |  | 2559 |  |  | 2562 |  |  | 2560 |  |  | 2579.5 |  |  | 2654 |  |  | 2668.5 |  |  | 2653 |  |  | 2470 |  |  | 2606.5 |  |  | 2553.5 |  |  | 2515 |  |  | 2562.5 |  |  | 2632 |  |  | 2734 |  |  | 2599 |  |  | 2749 |  |  | 2540 |  |  | 2545 |  |  | 2553 |  |  | 2649 |  |  | 2513 |  |  | 2539.5 |  |  | 2570 |  |  | 2539 |  |  | 2792 |  |  | 2679 |  |  | 2623 |  |  | 2538 |  |  | 2609 |  |  | 2638.5 |  |  | 2633 |  |  | 2668.5 |  |  | 2612 |  |  | 2588 |  |  | 2763.5 |  |  | 2666 |  |  | 2758.5 |  |  | 2570 |  |  | 2420 |  |  | 2602.5 |  |  | 2707 |  |  | 2708.5 |  |  | 2721 |  |  | 2511 |  |  | 2662.5 |  |  | 2695.5 |  |  | 2666 |  |  | 2648.5 |  |  | 2640.5 |  |  | 2655 |  |  | 2702 |  |  | 2797.5 |  |  | 2525.5 |  |  | 2722.5 |  |  | 2692 |  |  | 2725 |  |  | 2610 |  |  | 2744 |  |  | 2761 |  |  | 2650.5 |  |  | 2606 |  |  | 2529.5 |  |  | 2645.5 |  |  | 2575 |  |  | 2701 |  |  | 2861.5 |  |  | 2564.5 |  |  | 2550 |  |  | 2685.5 |  |  | 2509.5 |  |  | 2647 |  |  | 2563 |  |  | 2597 |  |  | 2558.5 |  |  | 2680 |  |  | 2645.5 |  |  | 2747.5 |  |  | 2660 |  |  | 2564.5 |  |  | 2598 |  |  | 2604 |  |  | 2703 |  |  | 2757 |  |  | 2450 |  |  | 2695 |  |  | 2782 |  |  | 2650 |  |  | 2718 |  |  | 2601 |  |  | 2659.5 |  |  | 2765.5 |  |  | 2583 |  |  | 2527 |  |  | 2779 |  |  | 2635.5 |  |  | 2735.5 |  |  | 2791.5 |  |  | 2521 |  |  | 2676 |  |  | 2740.5 |  |  | 2694.5 |  |  | 2488.5 |  |  | 2633 |  |  | 2709 |  |  | 2610 |  |  | 2713 |  |  | 2588 |  |  | 2639.5 |  |  | 2524.5 |  |  | 2765 |  |  | 2602 |  |  | 2573 |  |  | 2749 |  |  | 2571 |  |  | 2778.5 |  |  | 2678 |  |  | 2623 |  |  | 2524 |  |  | 2565 |  |  | 2669.5 |  |  | 2731 |  |  | 2642 |  |  | 2623 |  |  | 2689 |  |  | 2727.5 |  |  | 2645 |  |  | 2626 |  |  | 2570 |  |  | 2703.5 |  |  | 2670.5 |  |  | 2730.5 |  |  | 2738 |  |  | 2622 |  |  | 2495 |  |  | 2774 |  |  | 2596 |  |  | 2575.5 |  |  | 2687 |  |  | 2573.5 |  |  | 2731.5 |  |  | 2662.5 |  |  | 2704 |  |  | 2820.5 |  |  | 2518 |  |  | 2497 |  |  | 2591.5 |  |  | 2605.5 |  |  | 2736 |  |  | 2730.5 |  |  | 2813.5 |  |  | 2564 |  |  | 2730 |  |  | 2534.5 |  |  | 2579.5 |  |  | 2817 |  |  | 2685.5 |  |  | 2784 |  |  | 2661 |  |  | 2581.5 |  |  | 2672 |  |  | 2549 |  |  | 2673.5 |  |  | 2606 |  |  | 2720.5 |  |  | 2633 |  |  | 2811 |  |  | 2662 |  |  | 2611 |  |  | 2756.5 |  |  | 2779 |  |  | 2755.5 |  |  | 2525.5 |  |  | 2770.5 |  |  | 2730 |  |  | 2707.5 |  |  | 2812 |  |  | 2680 |  |  | 2467.5 |  |  | 2591.5 |  |  | 2736 |  |  | 2603.5 |  |  | 2828 |  |  | 2637 |  |  | 2814.5 |  |  | 2567 |  |  | 2599.5 |  |  | 2644.5 |  |  | 2685.5 |  |  | 2667 |  |  | 2501 |  |  | 2551 |  |  | 2595.5 |  |  | 2571 |  |  | 2812.5 |  |  | 2652 |  |  | 2621 |  |  | 2641 |  |  | 2676 |  |  | 2763 |  |  | 2570 |  |  | 2650 |  |  | 2846 |  |  | 2646 |  |  | 2652.5 |  |  | 2719 |  |  | 2619 |  |  | 2708.5 |  |  | 2518.5 |  |  | 2619.5 |  |  | 2614.5 |  |  | 2648 |  |  | 2723 |  |  | 2429.5 |  |  | 2849.5 |  |  | 2595.5 |  |  | 2648 |  |  | 2638 |  |  | 2524 |  |  | 2651 |  |  | 2495 |  |  | 2721 |  |  | 2732 |  |  | 2637.5 |  |  | 2715.5 |  |  | 2519 |  |  | 2546.5 |  |  | 2637.5 |  |  | 2590 |  |  | 2651 |  |  | 2637 |  |  | 2711 |  |  | 2589.5 |  |  | 2545.5 |  |  | 2652.5 |  |  | 2572 |  |  | 2644.5 |  |  | 2729 |  |  | 2603 |  |  | 2722 |  |  | 2525.5 |  |  | 2624 |  |  | 2508 |  |  | 2679.5 |  |  | 2556 |  |  | 2699.5 |  |  | 2770 |  |  | 2653.5 |  |  | 2613 |  |  | 2542.5 |  |  | 2665.5 |  |  | 2756 |  |  | 2675 |  |  | 2445 |  |  | 2649 |  |  | 2491.5 |  |  | 2610 |  |  | 2809 |  |  | 2581.5 |  |  | 2727.5 |  |  | 2464.5 |  |  | 2565 |  |  | 2729.5 |  |  | 2754.5 |  |  | 2564.5 |  |  | 2741 |  |  | 2661 |  |  | 2767.5 |  |  | 2646 |  |  | 2837 |  |  | 2654.5 |  |  | 2621 |  |  | 2767 |  |  | 2623 |  |  | 2514 |  |  | 2510.5 |  |  | 2681.5 |  |  | 2588 |  |  | 2754 |  |  | 2644 |  |  | 2609 |  |  | 2629 |  |  | 2608.5 |  |  | 2562.5 |  |  | 2646 |  |  | 2803 |  |  | 2819 |  |  | 2530.5 |  |  | 2860.5 |  |  | 2548 |  |  | 2650 |  |  | 2490 |  |  | 2691.5 |  |  | 2716.5 |  |  | 2602 |  |  | 2508 |  |  | 2717 |  |  | 2595 |  |  | 2607 |  |  | 2750 |  |  | 2605 |  |  | 2831.5 |  |  | 2608 |  |  | 2779 |  |  | 2657 |  |  | 2685.5 |  |  | 2735 |  |  | 2589 |  |  | 2494 |  |  | 2596 |  |  | 2607 |  |  | 2673 |  |  | 2707 |  |  | 2566.5 |  |  | 2627.5 |  |  | 2482.5 |  |  | 2716 |  |  | 2590 |  |  | 2620.5 |  |  | 2440 |  |  | 2552.5 |  |  | 2641.5 |  |  | 2615 |  |  | 2689 |  |  | 2660.5 |  |  | 2640 |  |  | 2688 |  |  | 2660 |  |  | 2667 |  |  | 2652 |  |  | 2580 |  |  | 2567 |  |  | 2660.5 |  |  | 2588 |  |  | 2774 |  |  | 2695 |  |  | 2646 |  |  | 2610 |  |  | 2693 |  |  | 2754 |  |  | 2706 |  |  | 2639 |  |  | 2696.5 |  |  | 2702.5 |  |  | 2636.5 |  |  | 2669.5 |  |  | 2680 |  |  | 2436 |  |  | 2758.5 |  |  | 2498 |  |  | 2658 |  |  | 2564.5 |  |  | 2726.5 |  |  | 2727 |  |  | 2637.5 |  |  | 2614.5 |  |  | 2443 |  |  | 2757 |  |  | 2612 |  |  | 2651 |  |  | 2583.5 |  |  | 2691 |  |  | 2558.5 |  |  | 2560.5 |  |  | 2656 |  |  | 2626 |  |  | 2718.5 |  |  | 2566 |  |  | 2636.5 |  |  | 2627 |  |  | 2673.5 |  |  | 2552.5 |  |  | 2424.5 |  |  | 2797.5 |  |  | 2675.5 |  |  | 2469 |  |  | 2561 |  |  | 2696.5 |  |  | 2641 |  |  | 2562 |  |  | 2634 |  |  | 2792 |  |  | 2753.5 |  |  | 2441 |  |  | 2572 |  |  | 2760 |  |  | 2592.5 |  |  | 2614 |  |  | 2503 |  |  | 2624 |  |  | 2819.5 |  |  | 2742 |  |  | 2478 |  |  | 2634 |  |  | 2762 |  |  | 2915.5 |  |  | 2638 |  |  | 2508.5 |  |  | 2627 |  |  | 2691 |  |  | 2873.5 |  |  | 2724 |  |  | 2606 |  |  | 2580.5 |  |  | 2655 |  |  | 2515 |  |  | 2528 |  |  | 2975.5 |  |  | 2666.5 |  |  | 2697 |  |  | 2559 |  |  | 2653.5 |  |  | 2669.5 |  |  | 2618 |  |  | 2727 |  |  | 2715.5 |  |  | 2865.5 |  |  | 2600.5 |  |  | 2704.5 |  |  | 2586.5 |  |  | 2862 |  |  | 2602.5 |  |  | 2748 |  |  | 2629 |  |  | 2764 |  |  | 2804 |  |  | 2669.5 |  |  | 2601 |  |  | 2568 |  |  | 2620.5 |  |  | 2681.5 |  |  | 2529 |  |  | 2744.5 |  |  | 2586.5 |  |  | 2719 |  |  | 2553 |  |  | 2675 |  |  | 2612.5 |  |  | 2691 |  |  | 2670.5 |  |  | 2715 |  |  | 2690 |  |  | 2898.5 |  |  | 2611 |  |  | 2754 |  |  | 2495 |  |  | 2703 |  |  | 2749 |  |  | 2640 |  |  | 2690 |  |  | 2609 |  |  | 2545.5 |  |  | 2530.5 |  |  | 2595 |  |  | 2674.5 |  |  | 2473.5 |  |  | 2542 |  |  | 2557 |  |  | 2671 |  |  | 2692.5 |  |  | 2531.5 |  |  | 2687 |  |  | 2672 |  |  | 2495 |  |  | 2578 |  |  | 2601 |  |  | 2540 |  |  | 2679 |  |  | 2564.5 |  |  | 2771 |  |  | 2787 |  |  | 2743 |  |  | 2539 |  |  | 2512 |  |  | 2642.5 |  |  | 2840.5 |  |  | 2477.5 |  |  | 2539 |  |  | 2583 |  |  | 2543.5 |  |  | 2704.5 |  |  | 2697.5 |  |  | 2518 |  |  | 2689.5 |  |  | 2755.5 |  |  | 2741 |  |  | 2635.5 |  |  | 2715.5 |  |  | 2600 |  |  | 2527 |  |  | 2583 |  |  | 2727 |  |  | 2600 |  |  | 2440 |  |  | 2758 |  |  | 2704 |  |  | 2533 |  |  | 2667 |  |  | 2788.5 |  |  | 2624 |  |  | 2593 |  |  | 2573 |  |  | 2477.5 |  |  | 2592 |  |  | 2683.5 |  |  | 2772 |  |  | 2760 |  |  | 2656 |  |  | 2697 |  |  | 2796.5 |  |  | 2620 |  |  | 2490 |  |  | 2678.5 |  |  | 2642 |  |  | 2558 |  |  | 2593.5 |  |  | 2600.5 |  |  | 2616 |  |  | 2536.5 |  |  | 2727 |  |  | 2561.5 |  |  | 2699 |  |  | 2651 |  |  | 2534.5 |  |  | 2694.5 |  |  | 2660 |  |  | 2689 |  |  | 2658 |  |  | 2606 |  |  | 2584 |  |  | 2628 |  |  | 2484 |  |  | 2544 |  |  | 2687.5 |  |  | 2477 |  |  | 2747.5 |  |  | 2540 |  |  | 2643.5 |  |  | 2585.5 |  |  | 2576 |  |  | 2703 |  |  | 2738.5 |  |  | 2672 |  |  | 2676 |  |  | 2685 |  |  | 2615.5 |  |  | 2718 |  |  | 2531.5 |  |  | 2400 |  |  | 2550 |  |  | 2583 |  |  | 2628 |  |  | 2675.5 |  |  | 2618 |  |  | 2626 |  |  | 2753 |  |  | 2556.5 |  |  | 2814 |  |  | 2685 |  |  | 2737 |  |  | 2638 |  |  | 2672.5 |  |  | 2479.5 |  |  | 2802 |  |  | 2789 |  |  | 2693 |  |  | 2700.5 |  |  | 2683 |  |  | 2526 |  |  | 2554 |  |  | 2811.5 |  |  | 2645.5 |  |  | 2630.5 |  |  | 2726 |  |  | 2685 |  |  | 2695 |  |  | 2559.5 |  |  | 2680 |  |  | 2549.5 |  |  | 2486 |  |  | 2561 |  |  | 2601 |  |  | 2564.5 |  |  | 2671.5 |  |  | 2630 |  |  | 2643 |  |  | 2685.5 |  |  | 2690 |  |  | 2580 |  |  | 2683.5 |  |  | 2512 |  |  | 2488 |  |  | 2663.5 |  |  | 2560 |  |  | 2649 |  |  | 2600.5 |  |  | 2739 |  |  | 2542.5 |  |  | 2607 |  |  | 2445.5 |  |  | 2700.5 |  |  | 2556 |  |  | 2677 |  |  | 2787.5 |  |  | 2575.5 |  |  | 2679 |  |  | 2633 |  |  | 2698 |  |  | 2690.5 |  |  | 2689 |  |  | 2456 |  |  | 2541 |  |  | 2710.5 |  |  | 2688.5 |  |  | 2730 |  |  | 2738 |  |  | 2658 |  |  | 2618 |  |  | 2708 |  |  | 2619 |  |  | 2640 |  |  | 2614.5 |  |  | 2832.5 |  |  | 2515.5 |  |  | 2584 |  |  | 2590.5 |  |  | 2686 |  |  | 2626 |  |  | 2669.5 |  |  | 2511.5 |  |  | 2513 |  |  | 2679 |  |  | 2590.5 |  |  | 2612 |  |  | 2642 |  |  | 2506.5 |  |  | 2723.5 |  |  | 2575 |  |  | 2607 |  |  | 2619 |  |  | 2515.5 |  |  | 2575 |  |  | 2540 |  |  | 2608 |  |  | 2707 |  |  | 2775 |  |  | 2514.5 |  |  | 2723 |  |  | 2651 |  |  | 2500 |  |  | 2757.5 |  |  | 2642 |  |  | 2503.5 |  |  | 2565.5 |  |  | 2573 |  |  | 2753 |  |  | 2666.5 |  |  | 2558.5 |  |  | 2538.5 |  |  | 2591.5 |  |  | 2657.5 |  |  | 2704 |  |  | 2624 |  |  | 2604.5 |  |  | 2583.5 |  |  | 2576 |  |  | 2530 |  |  | 2611.5 |  |  | 2864 |  |  | 2657 |  |  | 2525 |  |  | 2687.5 |  |  | 2806 |  |  | 2559.5 |  |  | 2494 |  |  | 2644.5 |  |  | 2851.5 |  |  | 2763.5 |  |  | 2774 |  |  | 2659 |  |  | 2651.5 |  |  | 2550.5 |  |  | 2723 |  |  | 2639 |  |  | 2697.5 |  |  | 2789 |  |  | 2635.5 |  |  | 2615.5 |  |  | 2579 |  |  | 2657 |  |  | 2489.5 |  |  | 2742.5 |  |  | 2704 |  |  | 2621.5 |  |  | 2642.5 |  |  | 2709 |  |  | 2730 |  |  | 2728 |  |  | 2683.5 |  |  | 2673 |  |  | 2531 |  |  | 2634 |  |  | 2570 |  |  | 2580 |  |  | 2617 |  |  | 2834.5 |  |  | 2640.5 |  |  | 2625 |  |  | 2594 |  |  | 2676 |  |  | 2547.5 |  |  | 2659 |  |  | 2758 |  |  | 2619.5 |  |  | 2786.5 |  |  | 2638 |  |  | 2576.5 |  |  | 2778 |  |  | 2554 |  |  | 2660 |  |  | 2751.5 |  |  | 2717 |  |  | 2518.5 |  |  | 2595.5 |  |  | 2488 |  |  | 2624.5 |  |  | 2451.5 |  |  | 2640 |  |  | 2544 |  |  | 2756 |  |  | 2622.5 |  |  | 2543 |  |  | 2575.5 |  |  | 2794.5 |  |  | 2755 |  |  | 2541.5 |  |  | 2544 |  |  | 2648 |  |  | 2608 |  |  | 2647 |  |  | 2498 |  |  | 2707.5 |  |  | 2627 |  |  | 2752 |  |  | 2615 |  |  | 2732 |  |  | 2662.5 |  |  | 2643.5 |  |  | 2635 |  |  | 2754 |  |  | 2594 |  |  | 2650 |  |  | 2691 |  |  | 2517.5 |  |  | 2597 |  |  | 2712.5 |  |  | 2733 |  |  | 2516 |  |  | 2690 |  |  | 2639 |  |  | 2709.5 |  |  | 2694 |  |  | 2693.5 |  |  | 2532 |  |  | 2778 |  |  | 2691 |  |  | 2655.5 |  |  | 2544 |  |  | 2535 |  |  | 2561 |  |  | 2794 |  |  | 2938 |  |  | 2594.5 |  |  | 2697.5 |  |  | 2523 |  |  | 2536.5 |  |  | 2590 |  |  | 2628.5 |  |  | 2568.5 |  |  | 2624.5 |  |  | 2615.5 |  |  | 2514 |  |  | 2820 |  |  | 2505 |  |  | 2471 |  |  | 2597 |  |  | 2737 |  |  | 2635.5 |  |  | 2595.5 |  |  | 2777.5 |  |  | 2606 |  |  | 2775.5 |  |  | 2530.5 |  |  | 2745.5 |  |  | 2510.5 |  |  | 2647 |  |  | 2643.5 |  |  | 2714.5 |  |  | 2736 |  |  | 2515.5 |  |  | 2789.5 |  |  | 2652.5 |  |  | 2782 |  |  | 2709.5 |  |  | 2725 |  |  | 2646 |  |  | 2595.5 |  |  | 2671.5 |  |  | 2713 |  |  | 2766 |  |  | 2450.5 |  |  | 2488.5 |  |  | 2593.5 |  |  | 2680 |  |  | 2530 |  |  | 2611 |  |  | 2739.5 |  |  | 2680.5 |  |  | 2627 |  |  | 2688.5 |  |  | 2467 |  |  | 2644 |  |  | 2645.5 |  |  | 2497.5 |  |  | 2564 |  |  | 2610.5 |  |  | 2714 |  |  | 2521.5 |  |  | 2744.5 |  |  | 2759 |  |  | 2669.5 |  |  | 2710 |  |  | 2608.5 |  |  | 2636 |  |  | 2662 |  |  | 2666 |  |  | 2605.5 |  |  | 2546.5 |  |  | 2662 |  |  | 2577 |  |  | 2560 |  |  | 2610.5 |  |  | 2694.5 |  |  | 2754 |  |  | 2655.5 |  |  | 2600 |  |  | 2440.5 |  |  | 2671.5 |  |  | 2499 |  |  | 2554 |  |  | 2554 |  |  | 2614.5 |  |  | 2516 |  |  | 2686.5 |  |  | 2618 |  |  | 2603.5 |  |  | 2844 |  |  | 2473.5 |  |  | 2613 |  |  | 2634.5 |  |  | 2677.5 |  |  | 2563 |  |  | 2595 |  |  | 2867 |  |  | 2651 |  |  | 2704.5 |  |  | 2600 |  |  | 2603.5 |  |  | 2530 |  |  | 2597 |  |  | 2627 |  |  | 2779 |  |  | 2710 |  |  | 2659 |  |  | 2733 |  |  | 2591.5 |  |  | 2597 |  |  | 2701
92 |  | 2802.5 |  |  | 2785 |  |  | 2809.5 |  |  | 2683 |  |  | 2559.5 |  |  | 2835 |  |  | 2733 |  |  | 2668 |  |  | 2527.5 |  |  | 2566 |  |  | 2623 |  |  | 2815 |  |  | 2765 |  |  | 2832 |  |  | 2573.5 |  |  | 2719.5 |  |  | 2642 |  |  | 2739 |  |  | 2835 |  |  | 2544.5 |  |  | 2761 |  |  | 2754 |  |  | 2585 |  |  | 2712 |  |  | 2693.5 |  |  | 2794 |  |  | 2606 |  |  | 2725 |  |  | 2799 |  |  | 2488 |  |  | 2657 |  |  | 2593.5 |  |  | 2774.5 |  |  | 2616.5 |  |  | 2624 |  |  | 2690.5 |  |  | 2723.5 |  |  | 2736.5 |  |  | 2752 |  |  | 2683 |  |  | 2542.5 |  |  | 2606 |  |  | 2658.5 |  |  | 2576.5 |  |  | 2665.5 |  |  | 2867.5 |  |  | 2776.5 |  |  | 2631 |  |  | 2498 |  |  | 2628.5 |  |  | 2573 |  |  | 2643.5 |  |  | 2617.5 |  |  | 2706 |  |  | 2634 |  |  | 2605 |  |  | 2550 |  |  | 2779 |  |  | 2654 |  |  | 2687.5 |  |  | 2706.5 |  |  | 2637.5 |  |  | 2608 |  |  | 2704 |  |  | 2472 |  |  | 2593.5 |  |  | 2702 |  |  | 2593.5 |  |  | 2781.5 |  |  | 2772.5 |  |  | 2695 |  |  | 2815 |  |  | 2761 |  |  | 2671.5 |  |  | 2742.5 |  |  | 2636.5 |  |  | 2765.5 |  |  | 2743.5 |  |  | 2738.5 |  |  | 2686.5 |  |  | 2600.5 |  |  | 2471 |  |  | 2797 |  |  | 2574 |  |  | 2742.5 |  |  | 2764 |  |  | 2618.5 |  |  | 2749 |  |  | 2639 |  |  | 2635.5 |  |  | 2817.5 |  |  | 2545 |  |  | 2765 |  |  | 2575.5 |  |  | 2846 |  |  | 2576.5 |  |  | 2731.5 |  |  | 2705.5 |  |  | 2647.5 |  |  | 2586.5 |  |  | 2630 |  |  | 2642 |  |  | 2519 |  |  | 2606.5 |  |  | 2681.5 |  |  | 2719.5 |  |  | 2584.5 |  |  | 2646 |  |  | 2589 |  |  | 2696.5 |  |  | 2626 |  |  | 2723.5 |  |  | 2693 |  |  | 2613 |  |  | 2620.5 |  |  | 2665 |  |  | 2672 |  |  | 2560 |  |  | 2698 |  |  | 2667.5 |  |  | 2691.5 |  |  | 2580.5 |  |  | 2777 |  |  | 2598 |  |  | 2591 |  |  | 2599 |  |  | 2618.5 |  |  | 2693 |  |  | 2692.5 |  |  | 2668 |  |  | 2485 |  |  | 2653.5 |  |  | 2577.5 |  |  | 2554 |  |  | 2601.5 |  |  | 2661 |  |  | 2773 |  |  | 2625 |  |  | 2788 |  |  | 2587 |  |  | 2584 |  |  | 2592 |  |  | 2675 |  |  | 2528 |  |  | 2586.5 |  |  | 2609 |  |  | 2578 |  |  | 2821 |  |  | 2703 |  |  | 2638 |  |  | 2577 |  |  | 2648 |  |  | 2662.5 |  |  | 2654 |  |  | 2694.5 |  |  | 2633 |  |  | 2614 |  |  | 2784.5 |  |  | 2713 |  |  | 2779.5 |  |  | 2609 |  |  | 2444 |  |  | 2641.5 |  |  | 2754 |  |  | 2747.5 |  |  | 2768 |  |  | 2558 |  |  | 2688.5 |  |  | 2716.5 |  |  | 2681 |  |  | 2677.5 |  |  | 2687.5 |  |  | 2676 |  |  | 2726 |  |  | 2836.5 |  |  | 2551.5 |  |  | 2769.5 |  |  | 2721 |  |  | 2740 |  |  | 2634 |  |  | 2791 |  |  | 2790 |  |  | 2679.5 |  |  | 2630 |  |  | 2550.5 |  |  | 2671.5 |  |  | 2622 |  |  | 2725 |  |  | 2900.5 |  |  | 2603.5 |  |  | 2579 |  |  | 2732.5 |  |  | 2538.5 |  |  | 2694 |  |  | 2587 |  |  | 2623 |  |  | 2582.5 |  |  | 2719 |  |  | 2671.5 |  |  | 2773.5 |  |  | 2675 |  |  | 2590.5 |  |  | 2613 |  |  | 2630 |  |  | 2742 |  |  | 2796 |  |  | 2497 |  |  | 2734 |  |  | 2821 |  |  | 2689 |  |  | 2739 |  |  | 2616 |  |  | 2685.5 |  |  | 2789.5 |  |  | 2607 |  |  | 2551 |  |  | 2818 |  |  | 2664.5 |  |  | 2774.5 |  |  | 2830.5 |  |  | 2536 |  |  | 2700 |  |  | 2779.5 |  |  | 2741.5 |  |  | 2509.5 |  |  | 2672 |  |  | 2730 |  |  | 2636 |  |  | 2742 |  |  | 2612 |  |  | 2663.5 |  |  | 2548.5 |  |  | 2804 |  |  | 2617 |  |  | 2612 |  |  | 2770 |  |  | 2610 |  |  | 2825.5 |  |  | 2717 |  |  | 2662 |  |  | 2571 |  |  | 2604 |  |  | 2695.5 |  |  | 2752 |  |  | 2657 |  |  | 2652 |  |  | 2704 |  |  | 2748.5 |  |  | 2666 |  |  | 2652 |  |  | 2609 |  |  | 2729.5 |  |  | 2709.5 |  |  | 2769.5 |  |  | 2759 |  |  | 2643 |  |  | 2524 |  |  | 2798 |  |  | 2635 |  |  | 2604.5 |  |  | 2711 |  |  | 2602.5 |  |  | 2770.5 |  |  | 2691.5 |  |  | 2719 |  |  | 2867.5 |  |  | 2565 |  |  | 2521 |  |  | 2606.5 |  |  | 2644.5 |  |  | 2775 |  |  | 2769.5 |  |  | 2834.5 |  |  | 2603 |  |  | 2745 |  |  | 2558.5 |  |  | 2594.5 |  |  | 2864 |  |  | 2700.5 |  |  | 2805 |  |  | 2687 |  |  | 2628.5 |  |  | 2711 |  |  | 2588 |  |  | 2697.5 |  |  | 2645 |  |  | 2735.5 |  |  | 2648 |  |  | 2840 |  |  | 2701 |  |  | 2650 |  |  | 2795.5 |  |  | 2805 |  |  | 2794.5 |  |  | 2551.5 |  |  | 2796.5 |  |  | 2777 |  |  | 2746.5 |  |  | 2851 |  |  | 2704 |  |  | 2506.5 |  |  | 2620.5 |  |  | 2751 |  |  | 2642.5 |  |  | 2867 |  |  | 2663 |  |  | 2835.5 |  |  | 2591 |  |  | 2638.5 |  |  | 2683.5 |  |  | 2732.5 |  |  | 2706 |  |  | 2516 |  |  | 2566 |  |  | 2624.5 |  |  | 2600 |  |  | 2859.5 |  |  | 2678 |  |  | 2636 |  |  | 2680 |  |  | 2723 |  |  | 2802 |  |  | 2596 |  |  | 2689 |  |  | 2872 |  |  | 2667 |  |  | 2681.5 |  |  | 2734 |  |  | 2645 |  |  | 2729.5 |  |  | 2544.5 |  |  | 2643.5 |  |  | 2653.5 |  |  | 2674 |  |  | 2744 |  |  | 2468.5 |  |  | 2888.5 |  |  | 2616.5 |  |  | 2677 |  |  | 2685 |  |  | 2563 |  |  | 2672 |  |  | 2534 |  |  | 2750 |  |  | 2771 |  |  | 2676.5 |  |  | 2739.5 |  |  | 2545 |  |  | 2561.5 |  |  | 2676.5 |  |  | 2619 |  |  | 2675 |  |  | 2663 |  |  | 2758 |  |  | 2613.5 |  |  | 2566.5 |  |  | 2678.5 |  |  | 2587 |  |  | 2673.5 |  |  | 2758 |  |  | 2650 |  |  | 2746 |  |  | 2554.5 |  |  | 2663 |  |  | 2537 |  |  | 2705.5 |  |  | 2580 |  |  | 2720.5 |  |  | 2785 |  |  | 2692.5 |  |  | 2660 |  |  | 2566.5 |  |  | 2680.5 |  |  | 2777 |  |  | 2690 |  |  | 2469 |  |  | 2675 |  |  | 2515.5 |  |  | 2649 |  |  | 2830 |  |  | 2607.5 |  |  | 2753.5 |  |  | 2479.5 |  |  | 2580 |  |  | 2776.5 |  |  | 2801.5 |  |  | 2603.5 |  |  | 2770 |  |  | 2708 |  |  | 2791.5 |  |  | 2672 |  |  | 2852 |  |  | 2683.5 |  |  | 2645 |  |  | 2782 |  |  | 2662 |  |  | 2553 |  |  | 2536.5 |  |  | 2720.5 |  |  | 2617 |  |  | 2801 |  |  | 2683 |  |  | 2656 |  |  | 2655 |  |  | 2632.5 |  |  | 2583.5 |  |  | 2685 |  |  | 2827 |  |  | 2843 |  |  | 2545.5 |  |  | 2889.5 |  |  | 2587 |  |  | 2689 |  |  | 2511 |  |  | 2730.5 |  |  | 2763.5 |  |  | 2641 |  |  | 2537 |  |  | 2746 |  |  | 2619 |  |  | 2654 |  |  | 2765 |  |  | 2629 |  |  | 2870.5 |  |  | 2655 |  |  | 2818 |  |  | 2696 |  |  | 2732.5 |  |  | 2750 |  |  | 2636 |  |  | 2520 |  |  | 2625 |  |  | 2654 |  |  | 2712 |  |  | 2736 |  |  | 2587.5 |  |  | 2674.5 |  |  | 2511.5 |  |  | 2755 |  |  | 2616 |  |  | 2646.5 |  |  | 2487 |  |  | 2576.5 |  |  | 2665.5 |  |  | 2639 |  |  | 2713 |  |  | 2675.5 |  |  | 2664 |  |  | 2727 |  |  | 2707 |  |  | 2682 |  |  | 2673 |  |  | 2601 |  |  | 2591 |  |  | 2707.5 |  |  | 2603 |  |  | 2813 |  |  | 2721 |  |  | 2685 |  |  | 2657 |  |  | 2714 |  |  | 2801 |  |  | 2730 |  |  | 2678 |  |  | 2720.5 |  |  | 2723.5 |  |  | 2683.5 |  |  | 2698.5 |  |  | 2709 |  |  | 2457 |  |  | 2782.5 |  |  | 2537 |  |  | 2682 |  |  | 2585.5 |  |  | 2765.5 |  |  | 2774 |  |  | 2661.5 |  |  | 2661.5 |  |  | 2472 |  |  | 2772 |  |  | 2641 |  |  | 2690 |  |  | 2622.5 |  |  | 2720 |  |  | 2597.5 |  |  | 2589.5 |  |  | 2682 |  |  | 2665 |  |  | 2733.5 |  |  | 2605 |  |  | 2662.5 |  |  | 2651 |  |  | 2688.5 |  |  | 2581.5 |  |  | 2439.5 |  |  | 2812.5 |  |  | 2696.5 |  |  | 2508 |  |  | 2587 |  |  | 2743.5 |  |  | 2688 |  |  | 2609 |  |  | 2663 |  |  | 2813 |  |  | 2782.5 |  |  | 2480 |  |  | 2619 |  |  | 2784 |  |  | 2639.5 |  |  | 2638 |  |  | 2518 |  |  | 2653 |  |  | 2834.5 |  |  | 2789 |  |  | 2502 |  |  | 2673 |  |  | 2788 |  |  | 2962.5 |  |  | 2662 |  |  | 2555.5 |  |  | 2666 |  |  | 2730 |  |  | 2912.5 |  |  | 2771 |  |  | 2630 |  |  | 2609.5 |  |  | 2702 |  |  | 2554 |  |  | 2567 |  |  | 3001.5 |  |  | 2692.5 |  |  | 2744 |  |  | 2588 |  |  | 2692.5 |  |  | 2698.5 |  |  | 2633 |  |  | 2774 |  |  | 2739.5 |  |  | 2886.5 |  |  | 2639.5 |  |  | 2751.5 |  |  | 2615.5 |  |  | 2877 |  |  | 2617.5 |  |  | 2769 |  |  | 2668 |  |  | 2803 |  |  | 2843 |  |  | 2690.5 |  |  | 2630 |  |  | 2583 |  |  | 2659.5 |  |  | 2705.5 |  |  | 2555 |  |  | 2759.5 |  |  | 2601.5 |  |  | 2734 |  |  | 2579 |  |  | 2714 |  |  | 2627.5 |  |  | 2717 |  |  | 2717.5 |  |  | 2741 |  |  | 2729 |  |  | 2927.5 |  |  | 2632 |  |  | 2775 |  |  | 2534 |  |  | 2732 |  |  | 2788 |  |  | 2655 |  |  | 2705 |  |  | 2638 |  |  | 2566.5 |  |  | 2559.5 |  |  | 2610 |  |  | 2700.5 |  |  | 2520.5 |  |  | 2566 |  |  | 2596 |  |  | 2710 |  |  | 2716.5 |  |  | 2557.5 |  |  | 2726 |  |  | 2698 |  |  | 2519 |  |  | 2625 |  |  | 2648 |  |  | 2569 |  |  | 2700 |  |  | 2585.5 |  |  | 2786 |  |  | 2802 |  |  | 2758 |  |  | 2565 |  |  | 2551 |  |  | 2668.5 |  |  | 2864.5 |  |  | 2503.5 |  |  | 2560 |  |  | 2622 |  |  | 2558.5 |  |  | 2743.5 |  |  | 2744.5 |  |  | 2557 |  |  | 2728.5 |  |  | 2794.5 |  |  | 2762 |  |  | 2674.5 |  |  | 2730.5 |  |  | 2647 |  |  | 2556 |  |  | 2609 |  |  | 2766 |  |  | 2647 |  |  | 2479 |  |  | 2773 |  |  | 2751 |  |  | 2548 |  |  | 2706 |  |  | 2835.5 |  |  | 2650 |  |  | 2614 |  |  | 2594 |  |  | 2516.5 |  |  | 2607 |  |  | 2712.5 |  |  | 2811 |  |  | 2775 |  |  | 2682 |  |  | 2744 |  |  | 2820.5 |  |  | 2659 |  |  | 2514 |  |  | 2699.5 |  |  | 2671 |  |  | 2584 |  |  | 2614.5 |  |  | 2621.5 |  |  | 2642 |  |  | 2557.5 |  |  | 2753 |  |  | 2600.5 |  |  | 2720 |  |  | 2677 |  |  | 2558.5 |  |  | 2718.5 |  |  | 2699 |  |  | 2728 |  |  | 2682 |  |  | 2632 |  |  | 2613 |  |  | 2649 |  |  | 2505 |  |  | 2583 |  |  | 2726.5 |  |  | 2516 |  |  | 2762.5 |  |  | 2566 |  |  | 2682.5 |  |  | 2614.5 |  |  | 2600 |  |  | 2732 |  |  | 2767.5 |  |  | 2696 |  |  | 2715 |  |  | 2700 |  |  | 2636.5 |  |  | 2742 |  |  | 2570.5 |  |  | 2415 |  |  | 2576 |  |  | 2622 |  |  | 2667 |  |  | 2699.5 |  |  | 2644 |  |  | 2652 |  |  | 2774 |  |  | 2582.5 |  |  | 2843 |  |  | 2724 |  |  | 2776 |  |  | 2685 |  |  | 2711.5 |  |  | 2526.5 |  |  | 2841 |  |  | 2813 |  |  | 2722 |  |  | 2721.5 |  |  | 2722 |  |  | 2550 |  |  | 2578 |  |  | 2837.5 |  |  | 2669.5 |  |  | 2651.5 |  |  | 2747 |  |  | 2724 |  |  | 2716 |  |  | 2606.5 |  |  | 2719 |  |  | 2570.5 |  |  | 2510 |  |  | 2576 |  |  | 2630 |  |  | 2579.5 |  |  | 2718.5 |  |  | 2656 |  |  | 2682 |  |  | 2711.5 |  |  | 2737 |  |  | 2595 |  |  | 2730.5 |  |  | 2559 |  |  | 2527 |  |  | 2710.5 |  |  | 2599 |  |  | 2688 |  |  | 2615.5 |  |  | 2754 |  |  | 2568.5 |  |  | 2622 |  |  | 2492.5 |  |  | 2715.5 |  |  | 2577 |  |  | 2706 |  |  | 2811.5 |  |  | 2614.5 |  |  | 2726 |  |  | 2654 |  |  | 2722 |  |  | 2705.5 |  |  | 2736 |  |  | 2503 |  |  | 2588 |  |  | 2725.5 |  |  | 2703.5 |  |  | 2777 |  |  | 2759 |  |  | 2705 |  |  | 2657 |  |  | 2729 |  |  | 2640 |  |  | 2679 |  |  | 2661.5 |  |  | 2853.5 |  |  | 2536.5 |  |  | 2631 |  |  | 2611.5 |  |  | 2707 |  |  | 2673 |  |  | 2708.5 |  |  | 2540.5 |  |  | 2539 |  |  | 2708 |  |  | 2614.5 |  |  | 2651 |  |  | 2666 |  |  | 2545.5 |  |  | 2744.5 |  |  | 2599 |  |  | 2646 |  |  | 2640 |  |  | 2536.5 |  |  | 2614 |  |  | 2564 |  |  | 2634 |  |  | 2746 |  |  | 2796 |  |  | 2553.5 |  |  | 2738 |  |  | 2680 |  |  | 2529 |  |  | 2804.5 |  |  | 2668 |  |  | 2532.5 |  |  | 2604.5 |  |  | 2599 |  |  | 2782 |  |  | 2705.5 |  |  | 2579.5 |  |  | 2559.5 |  |  | 2638.5 |  |  | 2704.5 |  |  | 2728 |  |  | 2645 |  |  | 2643.5 |  |  | 2598.5 |  |  | 2597 |  |  | 2577 |  |  | 2650.5 |  |  | 2879 |  |  | 2678 |  |  | 2540 |  |  | 2726.5 |  |  | 2845 |  |  | 2588.5 |  |  | 2523 |  |  | 2665.5 |  |  | 2890.5 |  |  | 2784.5 |  |  | 2795 |  |  | 2688 |  |  | 2680.5 |  |  | 2571.5 |  |  | 2738 |  |  | 2660 |  |  | 2721.5 |  |  | 2810 |  |  | 2656.5 |  |  | 2654.5 |  |  | 2608 |  |  | 2672 |  |  | 2528.5 |  |  | 2781.5 |  |  | 2728 |  |  | 2650.5 |  |  | 2681.5 |  |  | 2738 |  |  | 2769 |  |  | 2767 |  |  | 2722.5 |  |  | 2712 |  |  | 2578 |  |  | 2681 |  |  | 2591 |  |  | 2601 |  |  | 2656 |  |  | 2873.5 |  |  | 2666.5 |  |  | 2664 |  |  | 2609 |  |  | 2700 |  |  | 2586.5 |  |  | 2698 |  |  | 2782 |  |  | 2643.5 |  |  | 2825.5 |  |  | 2677 |  |  | 2605.5 |  |  | 2807 |  |  | 2578 |  |  | 2689 |  |  | 2766.5 |  |  | 2741 |  |  | 2557.5 |  |  | 2616.5 |  |  | 2517 |  |  | 2648.5 |  |  | 2466.5 |  |  | 2666 |  |  | 2565 |  |  | 2780 |  |  | 2661.5 |  |  | 2582 |  |  | 2590.5 |  |  | 2818.5 |  |  | 2781 |  |  | 2562.5 |  |  | 2573 |  |  | 2687 |  |  | 2647 |  |  | 2686 |  |  | 2513 |  |  | 2746.5 |  |  | 2642 |  |  | 2776 |  |  | 2641 |  |  | 2753 |  |  | 2677.5 |  |  | 2669.5 |  |  | 2664 |  |  | 2778 |  |  | 2620 |  |  | 2697 |  |  | 2717 |  |  | 2538.5 |  |  | 2621 |  |  | 2741.5 |  |  | 2757 |  |  | 2555 |  |  | 2716 |  |  | 2660 |  |  | 2735.5 |  |  | 2709 |  |  | 2717.5 |  |  | 2553 |  |  | 2807 |  |  | 2720 |  |  | 2694.5 |  |  | 2568 |  |  | 2564 |  |  | 2600 |  |  | 2820 |  |  | 2985 |  |  | 2618.5 |  |  | 2721.5 |  |  | 2552 |  |  | 2551.5 |  |  | 2637 |  |  | 2667.5 |  |  | 2583.5 |  |  | 2663.5 |  |  | 2630.5 |  |  | 2529 |  |  | 2835 |  |  | 2531 |  |  | 2486 |  |  | 2618 |  |  | 2758 |  |  | 2682.5 |  |  | 2624.5 |  |  | 2801.5 |  |  | 2645 |  |  | 2814.5 |  |  | 2551.5 |  |  | 2760.5 |  |  | 2549.5 |  |  | 2694 |  |  | 2664.5 |  |  | 2735.5 |  |  | 2751 |  |  | 2554.5 |  |  | 2810.5 |  |  | 2673.5 |  |  | 2808 |  |  | 2735.5 |  |  | 2746 |  |  | 2667 |  |  | 2642.5 |  |  | 2700.5 |  |  | 2752 |  |  | 2813 |  |  | 2479.5 |  |  | 2527.5 |  |  | 2632.5 |  |  | 2704 |  |  | 2569 |  |  | 2658 |  |  | 2786.5 |  |  | 2701.5 |  |  | 2656 |  |  | 2735.5 |  |  | 2491 |  |  | 2691 |  |  | 2692.5 |  |  | 2536.5 |  |  | 2579 |  |  | 2634.5 |  |  | 2735 |  |  | 2545.5 |  |  | 2768.5 |  |  | 2798 |  |  | 2684.5 |  |  | 2749 |  |  | 2655.5 |  |  | 2675 |  |  | 2683 |  |  | 2690 |  |  | 2644.5 |  |  | 2575.5 |  |  | 2677 |  |  | 2616 |  |  | 2599 |  |  | 2631.5 |  |  | 2715.5 |  |  | 2783 |  |  | 2694.5 |  |  | 2624 |  |  | 2466.5 |  |  | 2700.5 |  |  | 2523 |  |  | 2575 |  |  | 2583 |  |  | 2653.5 |  |  | 2540 |  |  | 2707.5 |  |  | 2657 |  |  | 2629.5 |  |  | 2883 |  |  | 2499.5 |  |  | 2660 |  |  | 2673.5 |  |  | 2692.5 |  |  | 2584 |  |  | 2642 |  |  | 2882 |  |  | 2672 |  |  | 2743.5 |  |  | 2626 |  |  | 2624.5 |  |  | 2559 |  |  | 2612 |  |  | 2648 |  |  | 2794 |  |  | 2734 |  |  | 2698 |  |  | 2762 |  |  | 2617.5 |  |  | 2644 |  |  | 2740
93 |  | 2841.5 |  |  | 2814 |  |  | 2848.5 |  |  | 2730 |  |  | 2598.5 |  |  | 2861 |  |  | 2772 |  |  | 2694 |  |  | 2542.5 |  |  | 2595 |  |  | 2649 |  |  | 2844 |  |  | 2804 |  |  | 2871 |  |  | 2602.5 |  |  | 2748.5 |  |  | 2657 |  |  | 2760 |  |  | 2850 |  |  | 2565.5 |  |  | 2785 |  |  | 2793 |  |  | 2614 |  |  | 2751 |  |  | 2714.5 |  |  | 2809 |  |  | 2635 |  |  | 2764 |  |  | 2820 |  |  | 2514 |  |  | 2683 |  |  | 2619.5 |  |  | 2798.5 |  |  | 2640.5 |  |  | 2645 |  |  | 2714.5 |  |  | 2762.5 |  |  | 2775.5 |  |  | 2791 |  |  | 2730 |  |  | 2568.5 |  |  | 2653 |  |  | 2705.5 |  |  | 2623.5 |  |  | 2712.5 |  |  | 2891.5 |  |  | 2805.5 |  |  | 2660 |  |  | 2513 |  |  | 2657.5 |  |  | 2597 |  |  | 2682.5 |  |  | 2641.5 |  |  | 2732 |  |  | 2660 |  |  | 2626 |  |  | 2576 |  |  | 2800 |  |  | 2693 |  |  | 2713.5 |  |  | 2735.5 |  |  | 2652.5 |  |  | 2647 |  |  | 2728 |  |  | 2496 |  |  | 2614.5 |  |  | 2741 |  |  | 2632.5 |  |  | 2820.5 |  |  | 2811.5 |  |  | 2721 |  |  | 2854 |  |  | 2800 |  |  | 2718.5 |  |  | 2768.5 |  |  | 2651.5 |  |  | 2789.5 |  |  | 2782.5 |  |  | 2753.5 |  |  | 2701.5 |  |  | 2615.5 |  |  | 2510 |  |  | 2818 |  |  | 2600 |  |  | 2781.5 |  |  | 2788 |  |  | 2633.5 |  |  | 2796 |  |  | 2668 |  |  | 2682.5 |  |  | 2841.5 |  |  | 2560 |  |  | 2786 |  |  | 2622.5 |  |  | 2893 |  |  | 2597.5 |  |  | 2755.5 |  |  | 2720.5 |  |  | 2662.5 |  |  | 2612.5 |  |  | 2645 |  |  | 2681 |  |  | 2558 |  |  | 2627.5 |  |  | 2702.5 |  |  | 2743.5 |  |  | 2623.5 |  |  | 2667 |  |  | 2610 |  |  | 2722.5 |  |  | 2665 |  |  | 2747.5 |  |  | 2719 |  |  | 2652 |  |  | 2635.5 |  |  | 2704 |  |  | 2693 |  |  | 2599 |  |  | 2719 |  |  | 2706.5 |  |  | 2738.5 |  |  | 2619.5 |  |  | 2816 |  |  | 2613 |  |  | 2630 |  |  | 2646 |  |  | 2639.5 |  |  | 2732 |  |  | 2721.5 |  |  | 2707 |  |  | 2511 |  |  | 2668.5 |  |  | 2598.5 |  |  | 2578 |  |  | 2640.5 |  |  | 2682 |  |  | 2820 |  |  | 2649 |  |  | 2814 |  |  | 2608 |  |  | 2623 |  |  | 2631 |  |  | 2696 |  |  | 2549 |  |  | 2625.5 |  |  | 2656 |  |  | 2602 |  |  | 2836 |  |  | 2742 |  |  | 2667 |  |  | 2606 |  |  | 2695 |  |  | 2688.5 |  |  | 2669 |  |  | 2718.5 |  |  | 2662 |  |  | 2640 |  |  | 2805.5 |  |  | 2728 |  |  | 2818.5 |  |  | 2635 |  |  | 2473 |  |  | 2688.5 |  |  | 2769 |  |  | 2794.5 |  |  | 2807 |  |  | 2584 |  |  | 2717.5 |  |  | 2755.5 |  |  | 2696 |  |  | 2698.5 |  |  | 2726.5 |  |  | 2700 |  |  | 2750 |  |  | 2875.5 |  |  | 2572.5 |  |  | 2784.5 |  |  | 2742 |  |  | 2766 |  |  | 2673 |  |  | 2830 |  |  | 2811 |  |  | 2703.5 |  |  | 2651 |  |  | 2565.5 |  |  | 2692.5 |  |  | 2661 |  |  | 2749 |  |  | 2947.5 |  |  | 2642.5 |  |  | 2600 |  |  | 2779.5 |  |  | 2577.5 |  |  | 2723 |  |  | 2611 |  |  | 2662 |  |  | 2611.5 |  |  | 2745 |  |  | 2686.5 |  |  | 2788.5 |  |  | 2690 |  |  | 2629.5 |  |  | 2642 |  |  | 2677 |  |  | 2766 |  |  | 2817 |  |  | 2523 |  |  | 2781 |  |  | 2860 |  |  | 2715 |  |  | 2778 |  |  | 2655 |  |  | 2709.5 |  |  | 2813.5 |  |  | 2628 |  |  | 2590 |  |  | 2847 |  |  | 2693.5 |  |  | 2789.5 |  |  | 2856.5 |  |  | 2551 |  |  | 2739 |  |  | 2826.5 |  |  | 2762.5 |  |  | 2548.5 |  |  | 2698 |  |  | 2759 |  |  | 2660 |  |  | 2768 |  |  | 2627 |  |  | 2702.5 |  |  | 2563.5 |  |  | 2830 |  |  | 2646 |  |  | 2659 |  |  | 2817 |  |  | 2639 |  |  | 2840.5 |  |  | 2738 |  |  | 2701 |  |  | 2597 |  |  | 2651 |  |  | 2724.5 |  |  | 2781 |  |  | 2672 |  |  | 2667 |  |  | 2751 |  |  | 2787.5 |  |  | 2692 |  |  | 2678 |  |  | 2638 |  |  | 2744.5 |  |  | 2735.5 |  |  | 2795.5 |  |  | 2780 |  |  | 2672 |  |  | 2550 |  |  | 2845 |  |  | 2650 |  |  | 2630.5 |  |  | 2750 |  |  | 2626.5 |  |  | 2785.5 |  |  | 2715.5 |  |  | 2766 |  |  | 2914.5 |  |  | 2604 |  |  | 2545 |  |  | 2645.5 |  |  | 2668.5 |  |  | 2801 |  |  | 2784.5 |  |  | 2873.5 |  |  | 2624 |  |  | 2774 |  |  | 2582.5 |  |  | 2633.5 |  |  | 2879 |  |  | 2739.5 |  |  | 2826 |  |  | 2708 |  |  | 2652.5 |  |  | 2750 |  |  | 2627 |  |  | 2718.5 |  |  | 2666 |  |  | 2761.5 |  |  | 2695 |  |  | 2879 |  |  | 2727 |  |  | 2689 |  |  | 2810.5 |  |  | 2834 |  |  | 2841.5 |  |  | 2566.5 |  |  | 2835.5 |  |  | 2801 |  |  | 2767.5 |  |  | 2890 |  |  | 2725 |  |  | 2532.5 |  |  | 2641.5 |  |  | 2766 |  |  | 2666.5 |  |  | 2906 |  |  | 2702 |  |  | 2874.5 |  |  | 2617 |  |  | 2667.5 |  |  | 2709.5 |  |  | 2761.5 |  |  | 2735 |  |  | 2540 |  |  | 2581 |  |  | 2648.5 |  |  | 2639 |  |  | 2885.5 |  |  | 2725 |  |  | 2662 |  |  | 2727 |  |  | 2762 |  |  | 2828 |  |  | 2643 |  |  | 2718 |  |  | 2893 |  |  | 2706 |  |  | 2696.5 |  |  | 2781 |  |  | 2674 |  |  | 2768.5 |  |  | 2573.5 |  |  | 2672.5 |  |  | 2682.5 |  |  | 2689 |  |  | 2783 |  |  | 2483.5 |  |  | 2912.5 |  |  | 2655.5 |  |  | 2724 |  |  | 2711 |  |  | 2602 |  |  | 2701 |  |  | 2549 |  |  | 2797 |  |  | 2818 |  |  | 2702.5 |  |  | 2778.5 |  |  | 2592 |  |  | 2600.5 |  |  | 2723.5 |  |  | 2640 |  |  | 2701 |  |  | 2710 |  |  | 2787 |  |  | 2652.5 |  |  | 2587.5 |  |  | 2704.5 |  |  | 2608 |  |  | 2697.5 |  |  | 2779 |  |  | 2697 |  |  | 2767 |  |  | 2580.5 |  |  | 2702 |  |  | 2566 |  |  | 2720.5 |  |  | 2601 |  |  | 2746.5 |  |  | 2811 |  |  | 2716.5 |  |  | 2681 |  |  | 2590.5 |  |  | 2695.5 |  |  | 2792 |  |  | 2737 |  |  | 2508 |  |  | 2722 |  |  | 2562.5 |  |  | 2664 |  |  | 2869 |  |  | 2633.5 |  |  | 2779.5 |  |  | 2503.5 |  |  | 2609 |  |  | 2802.5 |  |  | 2840.5 |  |  | 2618.5 |  |  | 2809 |  |  | 2737 |  |  | 2815.5 |  |  | 2693 |  |  | 2899 |  |  | 2704.5 |  |  | 2684 |  |  | 2821 |  |  | 2709 |  |  | 2568 |  |  | 2562.5 |  |  | 2741.5 |  |  | 2643 |  |  | 2827 |  |  | 2698 |  |  | 2703 |  |  | 2694 |  |  | 2656.5 |  |  | 2622.5 |  |  | 2706 |  |  | 2856 |  |  | 2882 |  |  | 2569.5 |  |  | 2936.5 |  |  | 2616 |  |  | 2715 |  |  | 2537 |  |  | 2759.5 |  |  | 2778.5 |  |  | 2680 |  |  | 2552 |  |  | 2785 |  |  | 2658 |  |  | 2675 |  |  | 2786 |  |  | 2668 |  |  | 2894.5 |  |  | 2681 |  |  | 2857 |  |  | 2725 |  |  | 2758.5 |  |  | 2774 |  |  | 2683 |  |  | 2535 |  |  | 2651 |  |  | 2701 |  |  | 2759 |  |  | 2757 |  |  | 2626.5 |  |  | 2689.5 |  |  | 2558.5 |  |  | 2784 |  |  | 2645 |  |  | 2670.5 |  |  | 2513 |  |  | 2615.5 |  |  | 2691.5 |  |  | 2686 |  |  | 2728 |  |  | 2714.5 |  |  | 2685 |  |  | 2756 |  |  | 2754 |  |  | 2697 |  |  | 2697 |  |  | 2616 |  |  | 2606 |  |  | 2722.5 |  |  | 2642 |  |  | 2837 |  |  | 2768 |  |  | 2711 |  |  | 2696 |  |  | 2735 |  |  | 2822 |  |  | 2769 |  |  | 2717 |  |  | 2767.5 |  |  | 2738.5 |  |  | 2730.5 |  |  | 2713.5 |  |  | 2756 |  |  | 2496 |  |  | 2797.5 |  |  | 2584 |  |  | 2721 |  |  | 2600.5 |  |  | 2786.5 |  |  | 2800 |  |  | 2700.5 |  |  | 2685.5 |  |  | 2501 |  |  | 2796 |  |  | 2665 |  |  | 2729 |  |  | 2651.5 |  |  | 2759 |  |  | 2644.5 |  |  | 2636.5 |  |  | 2708 |  |  | 2691 |  |  | 2754.5 |  |  | 2652 |  |  | 2686.5 |  |  | 2677 |  |  | 2709.5 |  |  | 2605.5 |  |  | 2463.5 |  |  | 2851.5 |  |  | 2735.5 |  |  | 2547 |  |  | 2616 |  |  | 2782.5 |  |  | 2735 |  |  | 2638 |  |  | 2702 |  |  | 2834 |  |  | 2811.5 |  |  | 2519 |  |  | 2645 |  |  | 2805 |  |  | 2663.5 |  |  | 2659 |  |  | 2557 |  |  | 2682 |  |  | 2873.5 |  |  | 2836 |  |  | 2517 |  |  | 2688 |  |  | 2803 |  |  | 2986.5 |  |  | 2688 |  |  | 2581.5 |  |  | 2687 |  |  | 2751 |  |  | 2951.5 |  |  | 2792 |  |  | 2645 |  |  | 2656.5 |  |  | 2723 |  |  | 2593 |  |  | 2596 |  |  | 3048.5 |  |  | 2716.5 |  |  | 2783 |  |  | 2614 |  |  | 2713.5 |  |  | 2727.5 |  |  | 2659 |  |  | 2813 |  |  | 2778.5 |  |  | 2925.5 |  |  | 2668.5 |  |  | 2777.5 |  |  | 2662.5 |  |  | 2901 |  |  | 2643.5 |  |  | 2808 |  |  | 2683 |  |  | 2842 |  |  | 2869 |  |  | 2719.5 |  |  | 2677 |  |  | 2622 |  |  | 2680.5 |  |  | 2729.5 |  |  | 2594 |  |  | 2788.5 |  |  | 2640.5 |  |  | 2758 |  |  | 2618 |  |  | 2753 |  |  | 2648.5 |  |  | 2746 |  |  | 2741.5 |  |  | 2767 |  |  | 2776 |  |  | 2956.5 |  |  | 2653 |  |  | 2801 |  |  | 2573 |  |  | 2771 |  |  | 2835 |  |  | 2670 |  |  | 2752 |  |  | 2677 |  |  | 2581.5 |  |  | 2580.5 |  |  | 2649 |  |  | 2726.5 |  |  | 2535.5 |  |  | 2605 |  |  | 2617 |  |  | 2734 |  |  | 2740.5 |  |  | 2578.5 |  |  | 2765 |  |  | 2745 |  |  | 2543 |  |  | 2664 |  |  | 2687 |  |  | 2590 |  |  | 2729 |  |  | 2632.5 |  |  | 2810 |  |  | 2841 |  |  | 2797 |  |  | 2594 |  |  | 2580 |  |  | 2683.5 |  |  | 2890.5 |  |  | 2550.5 |  |  | 2589 |  |  | 2648 |  |  | 2584.5 |  |  | 2764.5 |  |  | 2773.5 |  |  | 2586 |  |  | 2767.5 |  |  | 2823.5 |  |  | 2809 |  |  | 2721.5 |  |  | 2754.5 |  |  | 2668 |  |  | 2603 |  |  | 2638 |  |  | 2792 |  |  | 2673 |  |  | 2518 |  |  | 2812 |  |  | 2777 |  |  | 2574 |  |  | 2753 |  |  | 2856.5 |  |  | 2674 |  |  | 2661 |  |  | 2623 |  |  | 2545.5 |  |  | 2646 |  |  | 2736.5 |  |  | 2826 |  |  | 2801 |  |  | 2711 |  |  | 2783 |  |  | 2846.5 |  |  | 2688 |  |  | 2561 |  |  | 2714.5 |  |  | 2710 |  |  | 2605 |  |  | 2643.5 |  |  | 2642.5 |  |  | 2671 |  |  | 2604.5 |  |  | 2768 |  |  | 2621.5 |  |  | 2759 |  |  | 2692 |  |  | 2587.5 |  |  | 2742.5 |  |  | 2746 |  |  | 2754 |  |  | 2697 |  |  | 2671 |  |  | 2628 |  |  | 2664 |  |  | 2529 |  |  | 2622 |  |  | 2765.5 |  |  | 2563 |  |  | 2801.5 |  |  | 2590 |  |  | 2706.5 |  |  | 2653.5 |  |  | 2639 |  |  | 2758 |  |  | 2806.5 |  |  | 2735 |  |  | 2736 |  |  | 2739 |  |  | 2683.5 |  |  | 2771 |  |  | 2609.5 |  |  | 2441 |  |  | 2615 |  |  | 2661 |  |  | 2691 |  |  | 2746.5 |  |  | 2691 |  |  | 2667 |  |  | 2803 |  |  | 2629.5 |  |  | 2864 |  |  | 2753 |  |  | 2800 |  |  | 2724 |  |  | 2740.5 |  |  | 2550.5 |  |  | 2867 |  |  | 2837 |  |  | 2743 |  |  | 2747.5 |  |  | 2746 |  |  | 2579 |  |  | 2604 |  |  | 2876.5 |  |  | 2690.5 |  |  | 2672.5 |  |  | 2786 |  |  | 2753 |  |  | 2755 |  |  | 2630.5 |  |  | 2766 |  |  | 2594.5 |  |  | 2549 |  |  | 2615 |  |  | 2669 |  |  | 2608.5 |  |  | 2757.5 |  |  | 2680 |  |  | 2706 |  |  | 2732.5 |  |  | 2776 |  |  | 2619 |  |  | 2777.5 |  |  | 2598 |  |  | 2551 |  |  | 2739.5 |  |  | 2646 |  |  | 2727 |  |  | 2654.5 |  |  | 2793 |  |  | 2607.5 |  |  | 2661 |  |  | 2539.5 |  |  | 2741.5 |  |  | 2598 |  |  | 2730 |  |  | 2835.5 |  |  | 2638.5 |  |  | 2752 |  |  | 2669 |  |  | 2737 |  |  | 2731.5 |  |  | 2760 |  |  | 2524 |  |  | 2614 |  |  | 2772.5 |  |  | 2742.5 |  |  | 2803 |  |  | 2798 |  |  | 2731 |  |  | 2686 |  |  | 2768 |  |  | 2655 |  |  | 2703 |  |  | 2708.5 |  |  | 2874.5 |  |  | 2560.5 |  |  | 2670 |  |  | 2626.5 |  |  | 2754 |  |  | 2720 |  |  | 2723.5 |  |  | 2561.5 |  |  | 2586 |  |  | 2755 |  |  | 2635.5 |  |  | 2675 |  |  | 2695 |  |  | 2566.5 |  |  | 2791.5 |  |  | 2623 |  |  | 2661 |  |  | 2655 |  |  | 2551.5 |  |  | 2653 |  |  | 2603 |  |  | 2660 |  |  | 2793 |  |  | 2835 |  |  | 2568.5 |  |  | 2767 |  |  | 2719 |  |  | 2558 |  |  | 2825.5 |  |  | 2697 |  |  | 2571.5 |  |  | 2625.5 |  |  | 2638 |  |  | 2811 |  |  | 2726.5 |  |  | 2594.5 |  |  | 2583.5 |  |  | 2677.5 |  |  | 2730.5 |  |  | 2757 |  |  | 2669 |  |  | 2658.5 |  |  | 2627.5 |  |  | 2621 |  |  | 2601 |  |  | 2676.5 |  |  | 2894 |  |  | 2704 |  |  | 2579 |  |  | 2750.5 |  |  | 2869 |  |  | 2612.5 |  |  | 2549 |  |  | 2686.5 |  |  | 2905.5 |  |  | 2823.5 |  |  | 2821 |  |  | 2727 |  |  | 2701.5 |  |  | 2595.5 |  |  | 2785 |  |  | 2707 |  |  | 2742.5 |  |  | 2849 |  |  | 2695.5 |  |  | 2693.5 |  |  | 2637 |  |  | 2701 |  |  | 2549.5 |  |  | 2805.5 |  |  | 2767 |  |  | 2676.5 |  |  | 2710.5 |  |  | 2767 |  |  | 2790 |  |  | 2782 |  |  | 2748.5 |  |  | 2751 |  |  | 2604 |  |  | 2696 |  |  | 2630 |  |  | 2622 |  |  | 2685 |  |  | 2902.5 |  |  | 2713.5 |  |  | 2679 |  |  | 2635 |  |  | 2739 |  |  | 2601.5 |  |  | 2737 |  |  | 2806 |  |  | 2682.5 |  |  | 2854.5 |  |  | 2716 |  |  | 2644.5 |  |  | 2822 |  |  | 2617 |  |  | 2715 |  |  | 2792.5 |  |  | 2780 |  |  | 2586.5 |  |  | 2637.5 |  |  | 2556 |  |  | 2672.5 |  |  | 2505.5 |  |  | 2713 |  |  | 2580 |  |  | 2801 |  |  | 2708.5 |  |  | 2608 |  |  | 2637.5 |  |  | 2857.5 |  |  | 2802 |  |  | 2601.5 |  |  | 2612 |  |  | 2734 |  |  | 2694 |  |  | 2715 |  |  | 2560 |  |  | 2772.5 |  |  | 2681 |  |  | 2800 |  |  | 2688 |  |  | 2774 |  |  | 2724.5 |  |  | 2708.5 |  |  | 2688 |  |  | 2793 |  |  | 2644 |  |  | 2723 |  |  | 2756 |  |  | 2562.5 |  |  | 2668 |  |  | 2780.5 |  |  | 2796 |  |  | 2570 |  |  | 2740 |  |  | 2684 |  |  | 2774.5 |  |  | 2738 |  |  | 2743.5 |  |  | 2582 |  |  | 2836 |  |  | 2741 |  |  | 2723.5 |  |  | 2607 |  |  | 2588 |  |  | 2647 |  |  | 2859 |  |  | 3024 |  |  | 2642.5 |  |  | 2768.5 |  |  | 2573 |  |  | 2590.5 |  |  | 2676 |  |  | 2706.5 |  |  | 2612.5 |  |  | 2689.5 |  |  | 2656.5 |  |  | 2576 |  |  | 2859 |  |  | 2570 |  |  | 2525 |  |  | 2657 |  |  | 2782 |  |  | 2706.5 |  |  | 2663.5 |  |  | 2822.5 |  |  | 2666 |  |  | 2835.5 |  |  | 2598.5 |  |  | 2784.5 |  |  | 2575.5 |  |  | 2733 |  |  | 2693.5 |  |  | 2774.5 |  |  | 2766 |  |  | 2578.5 |  |  | 2825.5 |  |  | 2694.5 |  |  | 2834 |  |  | 2764.5 |  |  | 2770 |  |  | 2696 |  |  | 2681.5 |  |  | 2747.5 |  |  | 2799 |  |  | 2842 |  |  | 2508.5 |  |  | 2548.5 |  |  | 2661.5 |  |  | 2751 |  |  | 2590 |  |  | 2682 |  |  | 2807.5 |  |  | 2716.5 |  |  | 2695 |  |  | 2759.5 |  |  | 2530 |  |  | 2730 |  |  | 2739.5 |  |  | 2551.5 |  |  | 2605 |  |  | 2655.5 |  |  | 2774 |  |  | 2592.5 |  |  | 2789.5 |  |  | 2827 |  |  | 2713.5 |  |  | 2796 |  |  | 2670.5 |  |  | 2704 |  |  | 2730 |  |  | 2716 |  |  | 2668.5 |  |  | 2601.5 |  |  | 2692 |  |  | 2645 |  |  | 2638 |  |  | 2646.5 |  |  | 2754.5 |  |  | 2830 |  |  | 2733.5 |  |  | 2653 |  |  | 2492.5 |  |  | 2739.5 |  |  | 2544 |  |  | 2596 |  |  | 2607 |  |  | 2692.5 |  |  | 2579 |  |  | 2746.5 |  |  | 2686 |  |  | 2644.5 |  |  | 2907 |  |  | 2523.5 |  |  | 2707 |  |  | 2720.5 |  |  | 2713.5 |  |  | 2631 |  |  | 2657 |  |  | 2906 |  |  | 2698 |  |  | 2764.5 |  |  | 2655 |  |  | 2663.5 |  |  | 2598 |  |  | 2633 |  |  | 2669 |  |  | 2841 |  |  | 2763 |  |  | 2745 |  |  | 2786 |  |  | 2646.5 |  |  | 2659 |  |  | 2766
94 |  | 2888.5 |  |  | 2861 |  |  | 2895.5 |  |  | 2769 |  |  | 2645.5 |  |  | 2900 |  |  | 2801 |  |  | 2709 |  |  | 2557.5 |  |  | 2610 |  |  | 2688 |  |  | 2865 |  |  | 2843 |  |  | 2900 |  |  | 2641.5 |  |  | 2774.5 |  |  | 2672 |  |  | 2786 |  |  | 2865 |  |  | 2591.5 |  |  | 2809 |  |  | 2840 |  |  | 2653 |  |  | 2775 |  |  | 2738.5 |  |  | 2848 |  |  | 2650 |  |  | 2793 |  |  | 2859 |  |  | 2561 |  |  | 2709 |  |  | 2640.5 |  |  | 2837.5 |  |  | 2687.5 |  |  | 2671 |  |  | 2729.5 |  |  | 2809.5 |  |  | 2822.5 |  |  | 2815 |  |  | 2754 |  |  | 2615.5 |  |  | 2682 |  |  | 2726.5 |  |  | 2638.5 |  |  | 2727.5 |  |  | 2906.5 |  |  | 2844.5 |  |  | 2699 |  |  | 2537 |  |  | 2681.5 |  |  | 2621 |  |  | 2721.5 |  |  | 2680.5 |  |  | 2771 |  |  | 2675 |  |  | 2652 |  |  | 2615 |  |  | 2815 |  |  | 2717 |  |  | 2734.5 |  |  | 2750.5 |  |  | 2678.5 |  |  | 2686 |  |  | 2767 |  |  | 2535 |  |  | 2653.5 |  |  | 2780 |  |  | 2658.5 |  |  | 2859.5 |  |  | 2832.5 |  |  | 2760 |  |  | 2883 |  |  | 2847 |  |  | 2733.5 |  |  | 2807.5 |  |  | 2677.5 |  |  | 2810.5 |  |  | 2821.5 |  |  | 2800.5 |  |  | 2727.5 |  |  | 2644.5 |  |  | 2534 |  |  | 2833 |  |  | 2647 |  |  | 2820.5 |  |  | 2817 |  |  | 2672.5 |  |  | 2835 |  |  | 2707 |  |  | 2721.5 |  |  | 2867.5 |  |  | 2599 |  |  | 2825 |  |  | 2669.5 |  |  | 2908 |  |  | 2612.5 |  |  | 2776.5 |  |  | 2744.5 |  |  | 2701.5 |  |  | 2633.5 |  |  | 2660 |  |  | 2705 |  |  | 2579 |  |  | 2656.5 |  |  | 2717.5 |  |  | 2790.5 |  |  | 2662.5 |  |  | 2691 |  |  | 2657 |  |  | 2769.5 |  |  | 2712 |  |  | 2794.5 |  |  | 2758 |  |  | 2699 |  |  | 2682.5 |  |  | 2743 |  |  | 2732 |  |  | 2646 |  |  | 2743 |  |  | 2745.5 |  |  | 2762.5 |  |  | 2645.5 |  |  | 2863 |  |  | 2637 |  |  | 2654 |  |  | 2685 |  |  | 2665.5 |  |  | 2758 |  |  | 2760.5 |  |  | 2728 |  |  | 2535 |  |  | 2715.5 |  |  | 2627.5 |  |  | 2602 |  |  | 2666.5 |  |  | 2697 |  |  | 2849 |  |  | 2688 |  |  | 2853 |  |  | 2647 |  |  | 2662 |  |  | 2670 |  |  | 2735 |  |  | 2596 |  |  | 2646.5 |  |  | 2703 |  |  | 2623 |  |  | 2865 |  |  | 2771 |  |  | 2682 |  |  | 2653 |  |  | 2724 |  |  | 2703.5 |  |  | 2695 |  |  | 2765.5 |  |  | 2701 |  |  | 2661 |  |  | 2829.5 |  |  | 2743 |  |  | 2847.5 |  |  | 2674 |  |  | 2520 |  |  | 2712.5 |  |  | 2798 |  |  | 2823.5 |  |  | 2846 |  |  | 2599 |  |  | 2756.5 |  |  | 2770.5 |  |  | 2717 |  |  | 2722.5 |  |  | 2741.5 |  |  | 2747 |  |  | 2789 |  |  | 2914.5 |  |  | 2611.5 |  |  | 2823.5 |  |  | 2771 |  |  | 2805 |  |  | 2699 |  |  | 2859 |  |  | 2826 |  |  | 2729.5 |  |  | 2690 |  |  | 2580.5 |  |  | 2731.5 |  |  | 2682 |  |  | 2796 |  |  | 2976.5 |  |  | 2681.5 |  |  | 2629 |  |  | 2818.5 |  |  | 2616.5 |  |  | 2744 |  |  | 2658 |  |  | 2677 |  |  | 2658.5 |  |  | 2792 |  |  | 2707.5 |  |  | 2803.5 |  |  | 2716 |  |  | 2650.5 |  |  | 2681 |  |  | 2724 |  |  | 2795 |  |  | 2846 |  |  | 2544 |  |  | 2807 |  |  | 2889 |  |  | 2754 |  |  | 2825 |  |  | 2681 |  |  | 2733.5 |  |  | 2852.5 |  |  | 2675 |  |  | 2605 |  |  | 2894 |  |  | 2714.5 |  |  | 2828.5 |  |  | 2885.5 |  |  | 2572 |  |  | 2765 |  |  | 2865.5 |  |  | 2809.5 |  |  | 2595.5 |  |  | 2727 |  |  | 2806 |  |  | 2681 |  |  | 2815 |  |  | 2642 |  |  | 2723.5 |  |  | 2589.5 |  |  | 2845 |  |  | 2693 |  |  | 2698 |  |  | 2838 |  |  | 2665 |  |  | 2879.5 |  |  | 2764 |  |  | 2725 |  |  | 2636 |  |  | 2690 |  |  | 2748.5 |  |  | 2810 |  |  | 2719 |  |  | 2696 |  |  | 2777 |  |  | 2816.5 |  |  | 2713 |  |  | 2707 |  |  | 2685 |  |  | 2768.5 |  |  | 2750.5 |  |  | 2834.5 |  |  | 2819 |  |  | 2711 |  |  | 2589 |  |  | 2884 |  |  | 2689 |  |  | 2677.5 |  |  | 2776 |  |  | 2655.5 |  |  | 2811.5 |  |  | 2739.5 |  |  | 2805 |  |  | 2953.5 |  |  | 2625 |  |  | 2566 |  |  | 2671.5 |  |  | 2683.5 |  |  | 2827 |  |  | 2823.5 |  |  | 2912.5 |  |  | 2650 |  |  | 2813 |  |  | 2597.5 |  |  | 2659.5 |  |  | 2903 |  |  | 2778.5 |  |  | 2873 |  |  | 2737 |  |  | 2678.5 |  |  | 2789 |  |  | 2648 |  |  | 2757.5 |  |  | 2695 |  |  | 2790.5 |  |  | 2710 |  |  | 2926 |  |  | 2774 |  |  | 2718 |  |  | 2834.5 |  |  | 2863 |  |  | 2856.5 |  |  | 2590.5 |  |  | 2850.5 |  |  | 2848 |  |  | 2806.5 |  |  | 2929 |  |  | 2751 |  |  | 2556.5 |  |  | 2656.5 |  |  | 2795 |  |  | 2687.5 |  |  | 2927 |  |  | 2726 |  |  | 2913.5 |  |  | 2632 |  |  | 2706.5 |  |  | 2730.5 |  |  | 2776.5 |  |  | 2774 |  |  | 2561 |  |  | 2610 |  |  | 2663.5 |  |  | 2660 |  |  | 2932.5 |  |  | 2754 |  |  | 2701 |  |  | 2766 |  |  | 2809 |  |  | 2843 |  |  | 2682 |  |  | 2744 |  |  | 2914 |  |  | 2753 |  |  | 2717.5 |  |  | 2807 |  |  | 2695 |  |  | 2792.5 |  |  | 2612.5 |  |  | 2701.5 |  |  | 2697.5 |  |  | 2718 |  |  | 2807 |  |  | 2504.5 |  |  | 2938.5 |  |  | 2694.5 |  |  | 2763 |  |  | 2737 |  |  | 2641 |  |  | 2716 |  |  | 2575 |  |  | 2826 |  |  | 2857 |  |  | 2731.5 |  |  | 2807.5 |  |  | 2631 |  |  | 2629.5 |  |  | 2744.5 |  |  | 2666 |  |  | 2722 |  |  | 2736 |  |  | 2826 |  |  | 2667.5 |  |  | 2634.5 |  |  | 2751.5 |  |  | 2629 |  |  | 2726.5 |  |  | 2818 |  |  | 2723 |  |  | 2791 |  |  | 2604.5 |  |  | 2723 |  |  | 2605 |  |  | 2744.5 |  |  | 2627 |  |  | 2775.5 |  |  | 2832 |  |  | 2742.5 |  |  | 2728 |  |  | 2619.5 |  |  | 2734.5 |  |  | 2831 |  |  | 2761 |  |  | 2532 |  |  | 2761 |  |  | 2591.5 |  |  | 2693 |  |  | 2908 |  |  | 2680.5 |  |  | 2805.5 |  |  | 2518.5 |  |  | 2648 |  |  | 2828.5 |  |  | 2855.5 |  |  | 2644.5 |  |  | 2835 |  |  | 2763 |  |  | 2839.5 |  |  | 2717 |  |  | 2920 |  |  | 2730.5 |  |  | 2723 |  |  | 2845 |  |  | 2738 |  |  | 2594 |  |  | 2583.5 |  |  | 2762.5 |  |  | 2682 |  |  | 2866 |  |  | 2719 |  |  | 2742 |  |  | 2741 |  |  | 2677.5 |  |  | 2669.5 |  |  | 2745 |  |  | 2877 |  |  | 2921 |  |  | 2593.5 |  |  | 2965.5 |  |  | 2645 |  |  | 2754 |  |  | 2552 |  |  | 2806.5 |  |  | 2802.5 |  |  | 2709 |  |  | 2578 |  |  | 2800 |  |  | 2705 |  |  | 2690 |  |  | 2812 |  |  | 2683 |  |  | 2920.5 |  |  | 2710 |  |  | 2872 |  |  | 2751 |  |  | 2797.5 |  |  | 2803 |  |  | 2722 |  |  | 2582 |  |  | 2675 |  |  | 2740 |  |  | 2798 |  |  | 2804 |  |  | 2647.5 |  |  | 2718.5 |  |  | 2579.5 |  |  | 2810 |  |  | 2684 |  |  | 2709.5 |  |  | 2537 |  |  | 2636.5 |  |  | 2715.5 |  |  | 2710 |  |  | 2743 |  |  | 2740.5 |  |  | 2709 |  |  | 2780 |  |  | 2780 |  |  | 2726 |  |  | 2718 |  |  | 2645 |  |  | 2635 |  |  | 2761.5 |  |  | 2657 |  |  | 2876 |  |  | 2797 |  |  | 2758 |  |  | 2743 |  |  | 2750 |  |  | 2851 |  |  | 2808 |  |  | 2756 |  |  | 2793.5 |  |  | 2777.5 |  |  | 2759.5 |  |  | 2734.5 |  |  | 2795 |  |  | 2511 |  |  | 2844.5 |  |  | 2599 |  |  | 2750 |  |  | 2639.5 |  |  | 2825.5 |  |  | 2815 |  |  | 2721.5 |  |  | 2714.5 |  |  | 2530 |  |  | 2820 |  |  | 2691 |  |  | 2755 |  |  | 2690.5 |  |  | 2785 |  |  | 2659.5 |  |  | 2660.5 |  |  | 2747 |  |  | 2715 |  |  | 2793.5 |  |  | 2681 |  |  | 2725.5 |  |  | 2724 |  |  | 2733.5 |  |  | 2631.5 |  |  | 2502.5 |  |  | 2890.5 |  |  | 2761.5 |  |  | 2573 |  |  | 2655 |  |  | 2821.5 |  |  | 2774 |  |  | 2653 |  |  | 2731 |  |  | 2881 |  |  | 2840.5 |  |  | 2540 |  |  | 2660 |  |  | 2844 |  |  | 2702.5 |  |  | 2706 |  |  | 2578 |  |  | 2711 |  |  | 2894.5 |  |  | 2860 |  |  | 2564 |  |  | 2735 |  |  | 2842 |  |  | 3001.5 |  |  | 2712 |  |  | 2628.5 |  |  | 2713 |  |  | 2780 |  |  | 2980.5 |  |  | 2831 |  |  | 2674 |  |  | 2677.5 |  |  | 2762 |  |  | 2617 |  |  | 2635 |  |  | 3072.5 |  |  | 2742.5 |  |  | 2809 |  |  | 2640 |  |  | 2752.5 |  |  | 2742.5 |  |  | 2685 |  |  | 2834 |  |  | 2807.5 |  |  | 2964.5 |  |  | 2715.5 |  |  | 2803.5 |  |  | 2688.5 |  |  | 2940 |  |  | 2667.5 |  |  | 2834 |  |  | 2698 |  |  | 2881 |  |  | 2884 |  |  | 2743.5 |  |  | 2701 |  |  | 2643 |  |  | 2706.5 |  |  | 2744.5 |  |  | 2633 |  |  | 2814.5 |  |  | 2661.5 |  |  | 2797 |  |  | 2644 |  |  | 2792 |  |  | 2695.5 |  |  | 2770 |  |  | 2780.5 |  |  | 2814 |  |  | 2800 |  |  | 2982.5 |  |  | 2679 |  |  | 2848 |  |  | 2612 |  |  | 2795 |  |  | 2882 |  |  | 2709 |  |  | 2773 |  |  | 2724 |  |  | 2620.5 |  |  | 2609.5 |  |  | 2670 |  |  | 2765.5 |  |  | 2559.5 |  |  | 2644 |  |  | 2656 |  |  | 2758 |  |  | 2769.5 |  |  | 2599.5 |  |  | 2804 |  |  | 2784 |  |  | 2590 |  |  | 2679 |  |  | 2708 |  |  | 2614 |  |  | 2744 |  |  | 2653.5 |  |  | 2836 |  |  | 2865 |  |  | 2836 |  |  | 2618 |  |  | 2595 |  |  | 2698.5 |  |  | 2929.5 |  |  | 2576.5 |  |  | 2636 |  |  | 2695 |  |  | 2605.5 |  |  | 2779.5 |  |  | 2812.5 |  |  | 2633 |  |  | 2814.5 |  |  | 2844.5 |  |  | 2835 |  |  | 2750.5 |  |  | 2783.5 |  |  | 2692 |  |  | 2632 |  |  | 2653 |  |  | 2816 |  |  | 2712 |  |  | 2557 |  |  | 2827 |  |  | 2824 |  |  | 2589 |  |  | 2774 |  |  | 2895.5 |  |  | 2698 |  |  | 2708 |  |  | 2638 |  |  | 2566.5 |  |  | 2667 |  |  | 2765.5 |  |  | 2873 |  |  | 2827 |  |  | 2750 |  |  | 2807 |  |  | 2867.5 |  |  | 2727 |  |  | 2582 |  |  | 2753.5 |  |  | 2749 |  |  | 2626 |  |  | 2658.5 |  |  | 2668.5 |  |  | 2686 |  |  | 2633.5 |  |  | 2789 |  |  | 2647.5 |  |  | 2798 |  |  | 2718 |  |  | 2602.5 |  |  | 2768.5 |  |  | 2761 |  |  | 2793 |  |  | 2744 |  |  | 2710 |  |  | 2649 |  |  | 2711 |  |  | 2553 |  |  | 2646 |  |  | 2804.5 |  |  | 2584 |  |  | 2830.5 |  |  | 2616 |  |  | 2721.5 |  |  | 2674.5 |  |  | 2678 |  |  | 2787 |  |  | 2827.5 |  |  | 2774 |  |  | 2751 |  |  | 2768 |  |  | 2698.5 |  |  | 2786 |  |  | 2638.5 |  |  | 2462 |  |  | 2644 |  |  | 2708 |  |  | 2706 |  |  | 2785.5 |  |  | 2720 |  |  | 2706 |  |  | 2842 |  |  | 2655.5 |  |  | 2890 |  |  | 2774 |  |  | 2839 |  |  | 2750 |  |  | 2769.5 |  |  | 2576.5 |  |  | 2906 |  |  | 2858 |  |  | 2772 |  |  | 2771.5 |  |  | 2761 |  |  | 2618 |  |  | 2628 |  |  | 2923.5 |  |  | 2705.5 |  |  | 2701.5 |  |  | 2825 |  |  | 2774 |  |  | 2779 |  |  | 2677.5 |  |  | 2805 |  |  | 2633.5 |  |  | 2588 |  |  | 2662 |  |  | 2695 |  |  | 2623.5 |  |  | 2786.5 |  |  | 2719 |  |  | 2753 |  |  | 2761.5 |  |  | 2791 |  |  | 2634 |  |  | 2798.5 |  |  | 2637 |  |  | 2580 |  |  | 2768.5 |  |  | 2670 |  |  | 2742 |  |  | 2693.5 |  |  | 2819 |  |  | 2628.5 |  |  | 2682 |  |  | 2554.5 |  |  | 2780.5 |  |  | 2627 |  |  | 2769 |  |  | 2864.5 |  |  | 2659.5 |  |  | 2781 |  |  | 2708 |  |  | 2752 |  |  | 2757.5 |  |  | 2799 |  |  | 2571 |  |  | 2653 |  |  | 2796.5 |  |  | 2757.5 |  |  | 2850 |  |  | 2845 |  |  | 2755 |  |  | 2712 |  |  | 2807 |  |  | 2676 |  |  | 2718 |  |  | 2755.5 |  |  | 2913.5 |  |  | 2599.5 |  |  | 2691 |  |  | 2641.5 |  |  | 2801 |  |  | 2746 |  |  | 2770.5 |  |  | 2585.5 |  |  | 2615 |  |  | 2779 |  |  | 2674.5 |  |  | 2701 |  |  | 2734 |  |  | 2581.5 |  |  | 2817.5 |  |  | 2638 |  |  | 2676 |  |  | 2679 |  |  | 2572.5 |  |  | 2677 |  |  | 2629 |  |  | 2686 |  |  | 2822 |  |  | 2882 |  |  | 2615.5 |  |  | 2796 |  |  | 2758 |  |  | 2584 |  |  | 2872.5 |  |  | 2736 |  |  | 2592.5 |  |  | 2649.5 |  |  | 2659 |  |  | 2826 |  |  | 2773.5 |  |  | 2615.5 |  |  | 2609.5 |  |  | 2716.5 |  |  | 2754.5 |  |  | 2796 |  |  | 2693 |  |  | 2684.5 |  |  | 2666.5 |  |  | 2660 |  |  | 2622 |  |  | 2715.5 |  |  | 2933 |  |  | 2719 |  |  | 2603 |  |  | 2765.5 |  |  | 2893 |  |  | 2638.5 |  |  | 2588 |  |  | 2701.5 |  |  | 2934.5 |  |  | 2838.5 |  |  | 2868 |  |  | 2748 |  |  | 2722.5 |  |  | 2634.5 |  |  | 2824 |  |  | 2731 |  |  | 2766.5 |  |  | 2896 |  |  | 2721.5 |  |  | 2732.5 |  |  | 2661 |  |  | 2748 |  |  | 2570.5 |  |  | 2826.5 |  |  | 2796 |  |  | 2705.5 |  |  | 2749.5 |  |  | 2796 |  |  | 2814 |  |  | 2829 |  |  | 2763.5 |  |  | 2780 |  |  | 2619 |  |  | 2725 |  |  | 2669 |  |  | 2661 |  |  | 2724 |  |  | 2941.5 |  |  | 2742.5 |  |  | 2703 |  |  | 2650 |  |  | 2765 |  |  | 2616.5 |  |  | 2776 |  |  | 2827 |  |  | 2708.5 |  |  | 2901.5 |  |  | 2755 |  |  | 2670.5 |  |  | 2851 |  |  | 2638 |  |  | 2744 |  |  | 2839.5 |  |  | 2809 |  |  | 2610.5 |  |  | 2684.5 |  |  | 2571 |  |  | 2711.5 |  |  | 2529.5 |  |  | 2728 |  |  | 2606 |  |  | 2830 |  |  | 2755.5 |  |  | 2647 |  |  | 2658.5 |  |  | 2878.5 |  |  | 2823 |  |  | 2630.5 |  |  | 2636 |  |  | 2781 |  |  | 2723 |  |  | 2762 |  |  | 2584 |  |  | 2819.5 |  |  | 2705 |  |  | 2847 |  |  | 2712 |  |  | 2800 |  |  | 2748.5 |  |  | 2723.5 |  |  | 2717 |  |  | 2822 |  |  | 2683 |  |  | 2752 |  |  | 2795 |  |  | 2601.5 |  |  | 2692 |  |  | 2806.5 |  |  | 2835 |  |  | 2594 |  |  | 2761 |  |  | 2723 |  |  | 2789.5 |  |  | 2777 |  |  | 2782.5 |  |  | 2603 |  |  | 2865 |  |  | 2788 |  |  | 2762.5 |  |  | 2631 |  |  | 2609 |  |  | 2662 |  |  | 2880 |  |  | 3063 |  |  | 2668.5 |  |  | 2797.5 |  |  | 2612 |  |  | 2619.5 |  |  | 2697 |  |  | 2727.5 |  |  | 2636.5 |  |  | 2713.5 |  |  | 2685.5 |  |  | 2605 |  |  | 2880 |  |  | 2609 |  |  | 2549 |  |  | 2683 |  |  | 2803 |  |  | 2730.5 |  |  | 2684.5 |  |  | 2861.5 |  |  | 2705 |  |  | 2874.5 |  |  | 2637.5 |  |  | 2813.5 |  |  | 2590.5 |  |  | 2757 |  |  | 2719.5 |  |  | 2798.5 |  |  | 2790 |  |  | 2599.5 |  |  | 2846.5 |  |  | 2718.5 |  |  | 2863 |  |  | 2785.5 |  |  | 2785 |  |  | 2722 |  |  | 2707.5 |  |  | 2762.5 |  |  | 2814 |  |  | 2868 |  |  | 2523.5 |  |  | 2572.5 |  |  | 2685.5 |  |  | 2790 |  |  | 2637 |  |  | 2697 |  |  | 2846.5 |  |  | 2755.5 |  |  | 2710 |  |  | 2798.5 |  |  | 2554 |  |  | 2777 |  |  | 2760.5 |  |  | 2577.5 |  |  | 2644 |  |  | 2670.5 |  |  | 2821 |  |  | 2631.5 |  |  | 2804.5 |  |  | 2874 |  |  | 2742.5 |  |  | 2820 |  |  | 2717.5 |  |  | 2733 |  |  | 2759 |  |  | 2755 |  |  | 2697.5 |  |  | 2640.5 |  |  | 2716 |  |  | 2671 |  |  | 2659 |  |  | 2693.5 |  |  | 2801.5 |  |  | 2877 |  |  | 2780.5 |  |  | 2679 |  |  | 2516.5 |  |  | 2778.5 |  |  | 2573 |  |  | 2622 |  |  | 2622 |  |  | 2731.5 |  |  | 2603 |  |  | 2785.5 |  |  | 2715 |  |  | 2691.5 |  |  | 2936 |  |  | 2544.5 |  |  | 2733 |  |  | 2767.5 |  |  | 2734.5 |  |  | 2678 |  |  | 2683 |  |  | 2921 |  |  | 2737 |  |  | 2788.5 |  |  | 2684 |  |  | 2702.5 |  |  | 2622 |  |  | 2648 |  |  | 2708 |  |  | 2867 |  |  | 2810 |  |  | 2792 |  |  | 2807 |  |  | 2661.5 |  |  | 2698 |  |  | 2795
95 |  | 2909.5 |  |  | 2908 |  |  | 2921.5 |  |  | 2808 |  |  | 2684.5 |  |  | 2947 |  |  | 2822 |  |  | 2733 |  |  | 2586.5 |  |  | 2657 |  |  | 2712 |  |  | 2894 |  |  | 2882 |  |  | 2929 |  |  | 2670.5 |  |  | 2795.5 |  |  | 2687 |  |  | 2801 |  |  | 2889 |  |  | 2606.5 |  |  | 2824 |  |  | 2879 |  |  | 2668 |  |  | 2796 |  |  | 2785.5 |  |  | 2872 |  |  | 2676 |  |  | 2814 |  |  | 2885 |  |  | 2585 |  |  | 2748 |  |  | 2666.5 |  |  | 2884.5 |  |  | 2734.5 |  |  | 2710 |  |  | 2744.5 |  |  | 2830.5 |  |  | 2843.5 |  |  | 2836 |  |  | 2778 |  |  | 2644.5 |  |  | 2703 |  |  | 2741.5 |  |  | 2667.5 |  |  | 2756.5 |  |  | 2953.5 |  |  | 2870.5 |  |  | 2738 |  |  | 2576 |  |  | 2710.5 |  |  | 2650 |  |  | 2750.5 |  |  | 2719.5 |  |  | 2800 |  |  | 2699 |  |  | 2681 |  |  | 2654 |  |  | 2841 |  |  | 2756 |  |  | 2781.5 |  |  | 2765.5 |  |  | 2725.5 |  |  | 2725 |  |  | 2806 |  |  | 2559 |  |  | 2679.5 |  |  | 2806 |  |  | 2705.5 |  |  | 2885.5 |  |  | 2871.5 |  |  | 2789 |  |  | 2922 |  |  | 2868 |  |  | 2759.5 |  |  | 2854.5 |  |  | 2701.5 |  |  | 2849.5 |  |  | 2836.5 |  |  | 2821.5 |  |  | 2751.5 |  |  | 2659.5 |  |  | 2560 |  |  | 2854 |  |  | 2694 |  |  | 2844.5 |  |  | 2841 |  |  | 2711.5 |  |  | 2874 |  |  | 2722 |  |  | 2768.5 |  |  | 2896.5 |  |  | 2614 |  |  | 2854 |  |  | 2716.5 |  |  | 2947 |  |  | 2659.5 |  |  | 2815.5 |  |  | 2770.5 |  |  | 2740.5 |  |  | 2662.5 |  |  | 2675 |  |  | 2729 |  |  | 2603 |  |  | 2695.5 |  |  | 2732.5 |  |  | 2805.5 |  |  | 2683.5 |  |  | 2720 |  |  | 2696 |  |  | 2793.5 |  |  | 2741 |  |  | 2818.5 |  |  | 2805 |  |  | 2720 |  |  | 2721.5 |  |  | 2764 |  |  | 2779 |  |  | 2693 |  |  | 2769 |  |  | 2784.5 |  |  | 2801.5 |  |  | 2669.5 |  |  | 2892 |  |  | 2661 |  |  | 2693 |  |  | 2724 |  |  | 2689.5 |  |  | 2787 |  |  | 2799.5 |  |  | 2752 |  |  | 2574 |  |  | 2730.5 |  |  | 2656.5 |  |  | 2628 |  |  | 2713.5 |  |  | 2712 |  |  | 2870 |  |  | 2727 |  |  | 2892 |  |  | 2668 |  |  | 2701 |  |  | 2694 |  |  | 2761 |  |  | 2643 |  |  | 2661.5 |  |  | 2718 |  |  | 2644 |  |  | 2894 |  |  | 2797 |  |  | 2729 |  |  | 2677 |  |  | 2748 |  |  | 2718.5 |  |  | 2742 |  |  | 2791.5 |  |  | 2727 |  |  | 2682 |  |  | 2868.5 |  |  | 2790 |  |  | 2886.5 |  |  | 2695 |  |  | 2541 |  |  | 2751.5 |  |  | 2845 |  |  | 2847.5 |  |  | 2893 |  |  | 2620 |  |  | 2785.5 |  |  | 2785.5 |  |  | 2741 |  |  | 2746.5 |  |  | 2765.5 |  |  | 2762 |  |  | 2828 |  |  | 2961.5 |  |  | 2626.5 |  |  | 2849.5 |  |  | 2786 |  |  | 2826 |  |  | 2746 |  |  | 2874 |  |  | 2841 |  |  | 2768.5 |  |  | 2711 |  |  | 2609.5 |  |  | 2778.5 |  |  | 2721 |  |  | 2835 |  |  | 3023.5 |  |  | 2720.5 |  |  | 2676 |  |  | 2847.5 |  |  | 2637.5 |  |  | 2791 |  |  | 2682 |  |  | 2716 |  |  | 2697.5 |  |  | 2831 |  |  | 2728.5 |  |  | 2824.5 |  |  | 2755 |  |  | 2689.5 |  |  | 2710 |  |  | 2771 |  |  | 2834 |  |  | 2875 |  |  | 2583 |  |  | 2828 |  |  | 2918 |  |  | 2780 |  |  | 2849 |  |  | 2720 |  |  | 2759.5 |  |  | 2873.5 |  |  | 2696 |  |  | 2631 |  |  | 2941 |  |  | 2735.5 |  |  | 2849.5 |  |  | 2909.5 |  |  | 2611 |  |  | 2804 |  |  | 2889.5 |  |  | 2830.5 |  |  | 2616.5 |  |  | 2766 |  |  | 2832 |  |  | 2728 |  |  | 2830 |  |  | 2668 |  |  | 2752.5 |  |  | 2615.5 |  |  | 2884 |  |  | 2714 |  |  | 2727 |  |  | 2885 |  |  | 2689 |  |  | 2905.5 |  |  | 2803 |  |  | 2772 |  |  | 2662 |  |  | 2729 |  |  | 2787.5 |  |  | 2834 |  |  | 2734 |  |  | 2720 |  |  | 2801 |  |  | 2863.5 |  |  | 2734 |  |  | 2722 |  |  | 2700 |  |  | 2815.5 |  |  | 2771.5 |  |  | 2849.5 |  |  | 2866 |  |  | 2737 |  |  | 2628 |  |  | 2931 |  |  | 2704 |  |  | 2724.5 |  |  | 2802 |  |  | 2694.5 |  |  | 2850.5 |  |  | 2778.5 |  |  | 2829 |  |  | 2992.5 |  |  | 2664 |  |  | 2581 |  |  | 2710.5 |  |  | 2722.5 |  |  | 2848 |  |  | 2862.5 |  |  | 2933.5 |  |  | 2671 |  |  | 2837 |  |  | 2636.5 |  |  | 2698.5 |  |  | 2924 |  |  | 2799.5 |  |  | 2902 |  |  | 2761 |  |  | 2717.5 |  |  | 2810 |  |  | 2672 |  |  | 2781.5 |  |  | 2716 |  |  | 2805.5 |  |  | 2757 |  |  | 2973 |  |  | 2821 |  |  | 2744 |  |  | 2881.5 |  |  | 2887 |  |  | 2880.5 |  |  | 2637.5 |  |  | 2876.5 |  |  | 2887 |  |  | 2845.5 |  |  | 2968 |  |  | 2766 |  |  | 2585.5 |  |  | 2703.5 |  |  | 2819 |  |  | 2711.5 |  |  | 2942 |  |  | 2765 |  |  | 2960.5 |  |  | 2661 |  |  | 2745.5 |  |  | 2745.5 |  |  | 2815.5 |  |  | 2798 |  |  | 2585 |  |  | 2634 |  |  | 2702.5 |  |  | 2675 |  |  | 2958.5 |  |  | 2775 |  |  | 2725 |  |  | 2795 |  |  | 2824 |  |  | 2882 |  |  | 2706 |  |  | 2770 |  |  | 2938 |  |  | 2782 |  |  | 2756.5 |  |  | 2836 |  |  | 2724 |  |  | 2821.5 |  |  | 2651.5 |  |  | 2727.5 |  |  | 2721.5 |  |  | 2744 |  |  | 2828 |  |  | 2551.5 |  |  | 2977.5 |  |  | 2723.5 |  |  | 2802 |  |  | 2776 |  |  | 2680 |  |  | 2755 |  |  | 2614 |  |  | 2865 |  |  | 2886 |  |  | 2746.5 |  |  | 2833.5 |  |  | 2660 |  |  | 2658.5 |  |  | 2783.5 |  |  | 2681 |  |  | 2743 |  |  | 2762 |  |  | 2852 |  |  | 2688.5 |  |  | 2658.5 |  |  | 2790.5 |  |  | 2653 |  |  | 2750.5 |  |  | 2857 |  |  | 2747 |  |  | 2815 |  |  | 2651.5 |  |  | 2744 |  |  | 2631 |  |  | 2791.5 |  |  | 2648 |  |  | 2801.5 |  |  | 2853 |  |  | 2789.5 |  |  | 2767 |  |  | 2645.5 |  |  | 2781.5 |  |  | 2870 |  |  | 2800 |  |  | 2556 |  |  | 2790 |  |  | 2606.5 |  |  | 2722 |  |  | 2923 |  |  | 2719.5 |  |  | 2834.5 |  |  | 2542.5 |  |  | 2687 |  |  | 2854.5 |  |  | 2884.5 |  |  | 2691.5 |  |  | 2859 |  |  | 2787 |  |  | 2878.5 |  |  | 2732 |  |  | 2959 |  |  | 2754.5 |  |  | 2752 |  |  | 2874 |  |  | 2785 |  |  | 2618 |  |  | 2609.5 |  |  | 2791.5 |  |  | 2711 |  |  | 2905 |  |  | 2734 |  |  | 2757 |  |  | 2756 |  |  | 2716.5 |  |  | 2698.5 |  |  | 2784 |  |  | 2892 |  |  | 2950 |  |  | 2622.5 |  |  | 3004.5 |  |  | 2692 |  |  | 2793 |  |  | 2591 |  |  | 2845.5 |  |  | 2841.5 |  |  | 2748 |  |  | 2617 |  |  | 2821 |  |  | 2734 |  |  | 2714 |  |  | 2833 |  |  | 2730 |  |  | 2949.5 |  |  | 2731 |  |  | 2901 |  |  | 2798 |  |  | 2823.5 |  |  | 2818 |  |  | 2761 |  |  | 2621 |  |  | 2722 |  |  | 2755 |  |  | 2827 |  |  | 2851 |  |  | 2694.5 |  |  | 2747.5 |  |  | 2618.5 |  |  | 2849 |  |  | 2731 |  |  | 2738.5 |  |  | 2561 |  |  | 2660.5 |  |  | 2754.5 |  |  | 2731 |  |  | 2769 |  |  | 2764.5 |  |  | 2733 |  |  | 2801 |  |  | 2809 |  |  | 2750 |  |  | 2744 |  |  | 2692 |  |  | 2650 |  |  | 2800.5 |  |  | 2696 |  |  | 2905 |  |  | 2821 |  |  | 2782 |  |  | 2764 |  |  | 2774 |  |  | 2890 |  |  | 2837 |  |  | 2780 |  |  | 2832.5 |  |  | 2803.5 |  |  | 2780.5 |  |  | 2773.5 |  |  | 2834 |  |  | 2540 |  |  | 2868.5 |  |  | 2638 |  |  | 2789 |  |  | 2686.5 |  |  | 2872.5 |  |  | 2830 |  |  | 2760.5 |  |  | 2735.5 |  |  | 2551 |  |  | 2859 |  |  | 2720 |  |  | 2781 |  |  | 2705.5 |  |  | 2800 |  |  | 2698.5 |  |  | 2689.5 |  |  | 2762 |  |  | 2754 |  |  | 2817.5 |  |  | 2696 |  |  | 2749.5 |  |  | 2763 |  |  | 2772.5 |  |  | 2670.5 |  |  | 2526.5 |  |  | 2937.5 |  |  | 2808.5 |  |  | 2612 |  |  | 2681 |  |  | 2847.5 |  |  | 2789 |  |  | 2682 |  |  | 2746 |  |  | 2910 |  |  | 2861.5 |  |  | 2566 |  |  | 2686 |  |  | 2883 |  |  | 2741.5 |  |  | 2727 |  |  | 2602 |  |  | 2758 |  |  | 2918.5 |  |  | 2889 |  |  | 2603 |  |  | 2774 |  |  | 2881 |  |  | 3025.5 |  |  | 2736 |  |  | 2667.5 |  |  | 2760 |  |  | 2819 |  |  | 3004.5 |  |  | 2870 |  |  | 2713 |  |  | 2698.5 |  |  | 2801 |  |  | 2641 |  |  | 2682 |  |  | 3101.5 |  |  | 2763.5 |  |  | 2833 |  |  | 2679 |  |  | 2799.5 |  |  | 2781.5 |  |  | 2711 |  |  | 2873 |  |  | 2846.5 |  |  | 2985.5 |  |  | 2762.5 |  |  | 2824.5 |  |  | 2727.5 |  |  | 2987 |  |  | 2682.5 |  |  | 2873 |  |  | 2719 |  |  | 2910 |  |  | 2899 |  |  | 2764.5 |  |  | 2730 |  |  | 2690 |  |  | 2735.5 |  |  | 2770.5 |  |  | 2648 |  |  | 2829.5 |  |  | 2685.5 |  |  | 2844 |  |  | 2673 |  |  | 2831 |  |  | 2734.5 |  |  | 2785 |  |  | 2819.5 |  |  | 2853 |  |  | 2824 |  |  | 3011.5 |  |  | 2726 |  |  | 2869 |  |  | 2641 |  |  | 2842 |  |  | 2921 |  |  | 2730 |  |  | 2802 |  |  | 2745 |  |  | 2641.5 |  |  | 2656.5 |  |  | 2709 |  |  | 2804.5 |  |  | 2574.5 |  |  | 2668 |  |  | 2695 |  |  | 2787 |  |  | 2816.5 |  |  | 2638.5 |  |  | 2851 |  |  | 2799 |  |  | 2629 |  |  | 2726 |  |  | 2747 |  |  | 2638 |  |  | 2791 |  |  | 2682.5 |  |  | 2860 |  |  | 2891 |  |  | 2865 |  |  | 2644 |  |  | 2642 |  |  | 2722.5 |  |  | 2976.5 |  |  | 2597.5 |  |  | 2665 |  |  | 2742 |  |  | 2634.5 |  |  | 2803.5 |  |  | 2851.5 |  |  | 2680 |  |  | 2861.5 |  |  | 2865.5 |  |  | 2874 |  |  | 2771.5 |  |  | 2809.5 |  |  | 2716 |  |  | 2647 |  |  | 2679 |  |  | 2842 |  |  | 2727 |  |  | 2586 |  |  | 2848 |  |  | 2850 |  |  | 2628 |  |  | 2813 |  |  | 2921.5 |  |  | 2727 |  |  | 2747 |  |  | 2659 |  |  | 2613.5 |  |  | 2688 |  |  | 2812.5 |  |  | 2912 |  |  | 2856 |  |  | 2779 |  |  | 2833 |  |  | 2882.5 |  |  | 2748 |  |  | 2608 |  |  | 2779.5 |  |  | 2796 |  |  | 2655 |  |  | 2697.5 |  |  | 2689.5 |  |  | 2710 |  |  | 2672.5 |  |  | 2828 |  |  | 2662.5 |  |  | 2827 |  |  | 2757 |  |  | 2649.5 |  |  | 2815.5 |  |  | 2790 |  |  | 2822 |  |  | 2765 |  |  | 2731 |  |  | 2675 |  |  | 2740 |  |  | 2592 |  |  | 2675 |  |  | 2843.5 |  |  | 2599 |  |  | 2877.5 |  |  | 2655 |  |  | 2742.5 |  |  | 2703.5 |  |  | 2704 |  |  | 2826 |  |  | 2842.5 |  |  | 2789 |  |  | 2777 |  |  | 2794 |  |  | 2722.5 |  |  | 2812 |  |  | 2662.5 |  |  | 2501 |  |  | 2659 |  |  | 2747 |  |  | 2732 |  |  | 2811.5 |  |  | 2735 |  |  | 2730 |  |  | 2871 |  |  | 2702.5 |  |  | 2929 |  |  | 2803 |  |  | 2878 |  |  | 2765 |  |  | 2808.5 |  |  | 2615.5 |  |  | 2935 |  |  | 2905 |  |  | 2801 |  |  | 2810.5 |  |  | 2776 |  |  | 2639 |  |  | 2667 |  |  | 2947.5 |  |  | 2744.5 |  |  | 2725.5 |  |  | 2849 |  |  | 2813 |  |  | 2805 |  |  | 2706.5 |  |  | 2831 |  |  | 2680.5 |  |  | 2627 |  |  | 2677 |  |  | 2734 |  |  | 2644.5 |  |  | 2825.5 |  |  | 2758 |  |  | 2774 |  |  | 2800.5 |  |  | 2830 |  |  | 2681 |  |  | 2824.5 |  |  | 2661 |  |  | 2606 |  |  | 2807.5 |  |  | 2709 |  |  | 2763 |  |  | 2719.5 |  |  | 2848 |  |  | 2667.5 |  |  | 2729 |  |  | 2593.5 |  |  | 2806.5 |  |  | 2666 |  |  | 2795 |  |  | 2911.5 |  |  | 2706.5 |  |  | 2807 |  |  | 2734 |  |  | 2791 |  |  | 2804.5 |  |  | 2846 |  |  | 2600 |  |  | 2692 |  |  | 2822.5 |  |  | 2796.5 |  |  | 2876 |  |  | 2874 |  |  | 2794 |  |  | 2727 |  |  | 2833 |  |  | 2697 |  |  | 2739 |  |  | 2802.5 |  |  | 2952.5 |  |  | 2614.5 |  |  | 2715 |  |  | 2688.5 |  |  | 2830 |  |  | 2761 |  |  | 2794.5 |  |  | 2624.5 |  |  | 2636 |  |  | 2826 |  |  | 2695.5 |  |  | 2727 |  |  | 2773 |  |  | 2620.5 |  |  | 2838.5 |  |  | 2653 |  |  | 2691 |  |  | 2705 |  |  | 2611.5 |  |  | 2701 |  |  | 2676 |  |  | 2707 |  |  | 2837 |  |  | 2911 |  |  | 2654.5 |  |  | 2817 |  |  | 2805 |  |  | 2623 |  |  | 2887.5 |  |  | 2762 |  |  | 2631.5 |  |  | 2688.5 |  |  | 2688 |  |  | 2865 |  |  | 2788.5 |  |  | 2641.5 |  |  | 2633.5 |  |  | 2763.5 |  |  | 2778.5 |  |  | 2820 |  |  | 2732 |  |  | 2723.5 |  |  | 2695.5 |  |  | 2689 |  |  | 2643 |  |  | 2730.5 |  |  | 2962 |  |  | 2766 |  |  | 2624 |  |  | 2804.5 |  |  | 2932 |  |  | 2677.5 |  |  | 2614 |  |  | 2748.5 |  |  | 2963.5 |  |  | 2853.5 |  |  | 2889 |  |  | 2777 |  |  | 2769.5 |  |  | 2673.5 |  |  | 2845 |  |  | 2746 |  |  | 2813.5 |  |  | 2922 |  |  | 2747.5 |  |  | 2753.5 |  |  | 2700 |  |  | 2769 |  |  | 2591.5 |  |  | 2865.5 |  |  | 2817 |  |  | 2720.5 |  |  | 2788.5 |  |  | 2825 |  |  | 2843 |  |  | 2855 |  |  | 2792.5 |  |  | 2804 |  |  | 2634 |  |  | 2749 |  |  | 2695 |  |  | 2685 |  |  | 2750 |  |  | 2980.5 |  |  | 2789.5 |  |  | 2729 |  |  | 2674 |  |  | 2804 |  |  | 2631.5 |  |  | 2797 |  |  | 2856 |  |  | 2732.5 |  |  | 2948.5 |  |  | 2776 |  |  | 2696.5 |  |  | 2872 |  |  | 2664 |  |  | 2791 |  |  | 2886.5 |  |  | 2848 |  |  | 2639.5 |  |  | 2699.5 |  |  | 2592 |  |  | 2750.5 |  |  | 2576.5 |  |  | 2775 |  |  | 2645 |  |  | 2877 |  |  | 2794.5 |  |  | 2673 |  |  | 2679.5 |  |  | 2899.5 |  |  | 2838 |  |  | 2669.5 |  |  | 2665 |  |  | 2820 |  |  | 2762 |  |  | 2791 |  |  | 2610 |  |  | 2866.5 |  |  | 2744 |  |  | 2868 |  |  | 2751 |  |  | 2839 |  |  | 2769.5 |  |  | 2752.5 |  |  | 2764 |  |  | 2861 |  |  | 2730 |  |  | 2791 |  |  | 2819 |  |  | 2640.5 |  |  | 2718 |  |  | 2853.5 |  |  | 2874 |  |  | 2633 |  |  | 2808 |  |  | 2747 |  |  | 2818.5 |  |  | 2806 |  |  | 2829.5 |  |  | 2629 |  |  | 2889 |  |  | 2817 |  |  | 2777.5 |  |  | 2652 |  |  | 2624 |  |  | 2677 |  |  | 2909 |  |  | 3087 |  |  | 2692.5 |  |  | 2823.5 |  |  | 2651 |  |  | 2645.5 |  |  | 2736 |  |  | 2742.5 |  |  | 2651.5 |  |  | 2742.5 |  |  | 2711.5 |  |  | 2631 |  |  | 2901 |  |  | 2648 |  |  | 2596 |  |  | 2730 |  |  | 2827 |  |  | 2745.5 |  |  | 2699.5 |  |  | 2908.5 |  |  | 2752 |  |  | 2900.5 |  |  | 2661.5 |  |  | 2852.5 |  |  | 2629.5 |  |  | 2772 |  |  | 2766.5 |  |  | 2837.5 |  |  | 2829 |  |  | 2625.5 |  |  | 2893.5 |  |  | 2739.5 |  |  | 2910 |  |  | 2814.5 |  |  | 2811 |  |  | 2769 |  |  | 2754.5 |  |  | 2788.5 |  |  | 2835 |  |  | 2883 |  |  | 2547.5 |  |  | 2611.5 |  |  | 2724.5 |  |  | 2819 |  |  | 2684 |  |  | 2712 |  |  | 2885.5 |  |  | 2770.5 |  |  | 2736 |  |  | 2845.5 |  |  | 2569 |  |  | 2798 |  |  | 2784.5 |  |  | 2616.5 |  |  | 2673 |  |  | 2685.5 |  |  | 2845 |  |  | 2652.5 |  |  | 2843.5 |  |  | 2898 |  |  | 2763.5 |  |  | 2835 |  |  | 2741.5 |  |  | 2762 |  |  | 2798 |  |  | 2781 |  |  | 2721.5 |  |  | 2687.5 |  |  | 2742 |  |  | 2718 |  |  | 2698 |  |  | 2719.5 |  |  | 2816.5 |  |  | 2892 |  |  | 2809.5 |  |  | 2694 |  |  | 2537.5 |  |  | 2817.5 |  |  | 2594 |  |  | 2669 |  |  | 2637 |  |  | 2760.5 |  |  | 2642 |  |  | 2806.5 |  |  | 2739 |  |  | 2720.5 |  |  | 2957 |  |  | 2568.5 |  |  | 2772 |  |  | 2782.5 |  |  | 2755.5 |  |  | 2717 |  |  | 2712 |  |  | 2960 |  |  | 2776 |  |  | 2814.5 |  |  | 2708 |  |  | 2723.5 |  |  | 2646 |  |  | 2687 |  |  | 2747 |  |  | 2893 |  |  | 2849 |  |  | 2816 |  |  | 2828 |  |  | 2708.5 |  |  | 2737 |  |  | 2834
96 |  | 2948.5 |  |  | 2937 |  |  | 2960.5 |  |  | 2834 |  |  | 2723.5 |  |  | 2976 |  |  | 2837 |  |  | 2772 |  |  | 2601.5 |  |  | 2704 |  |  | 2759 |  |  | 2915 |  |  | 2897 |  |  | 2944 |  |  | 2709.5 |  |  | 2819.5 |  |  | 2726 |  |  | 2825 |  |  | 2918 |  |  | 2630.5 |  |  | 2853 |  |  | 2894 |  |  | 2707 |  |  | 2822 |  |  | 2809.5 |  |  | 2896 |  |  | 2700 |  |  | 2840 |  |  | 2924 |  |  | 2632 |  |  | 2763 |  |  | 2705.5 |  |  | 2910.5 |  |  | 2749.5 |  |  | 2749 |  |  | 2783.5 |  |  | 2859.5 |  |  | 2869.5 |  |  | 2857 |  |  | 2793 |  |  | 2673.5 |  |  | 2732 |  |  | 2770.5 |  |  | 2691.5 |  |  | 2771.5 |  |  | 2992.5 |  |  | 2896.5 |  |  | 2762 |  |  | 2602 |  |  | 2757.5 |  |  | 2697 |  |  | 2771.5 |  |  | 2740.5 |  |  | 2824 |  |  | 2723 |  |  | 2696 |  |  | 2683 |  |  | 2867 |  |  | 2780 |  |  | 2820.5 |  |  | 2804.5 |  |  | 2751.5 |  |  | 2740 |  |  | 2845 |  |  | 2598 |  |  | 2705.5 |  |  | 2832 |  |  | 2729.5 |  |  | 2900.5 |  |  | 2910.5 |  |  | 2810 |  |  | 2946 |  |  | 2907 |  |  | 2774.5 |  |  | 2893.5 |  |  | 2748.5 |  |  | 2875.5 |  |  | 2875.5 |  |  | 2868.5 |  |  | 2775.5 |  |  | 2698.5 |  |  | 2575 |  |  | 2901 |  |  | 2718 |  |  | 2865.5 |  |  | 2865 |  |  | 2737.5 |  |  | 2898 |  |  | 2737 |  |  | 2792.5 |  |  | 2911.5 |  |  | 2629 |  |  | 2901 |  |  | 2755.5 |  |  | 2994 |  |  | 2683.5 |  |  | 2854.5 |  |  | 2791.5 |  |  | 2787.5 |  |  | 2688.5 |  |  | 2701 |  |  | 2750 |  |  | 2618 |  |  | 2734.5 |  |  | 2753.5 |  |  | 2852.5 |  |  | 2709.5 |  |  | 2744 |  |  | 2725 |  |  | 2840.5 |  |  | 2767 |  |  | 2847.5 |  |  | 2829 |  |  | 2767 |  |  | 2745.5 |  |  | 2790 |  |  | 2818 |  |  | 2708 |  |  | 2816 |  |  | 2805.5 |  |  | 2827.5 |  |  | 2708.5 |  |  | 2916 |  |  | 2682 |  |  | 2708 |  |  | 2750 |  |  | 2736.5 |  |  | 2802 |  |  | 2838.5 |  |  | 2776 |  |  | 2595 |  |  | 2769.5 |  |  | 2703.5 |  |  | 2649 |  |  | 2742.5 |  |  | 2751 |  |  | 2899 |  |  | 2748 |  |  | 2913 |  |  | 2715 |  |  | 2722 |  |  | 2720 |  |  | 2787 |  |  | 2690 |  |  | 2687.5 |  |  | 2747 |  |  | 2665 |  |  | 2918 |  |  | 2836 |  |  | 2768 |  |  | 2716 |  |  | 2787 |  |  | 2765.5 |  |  | 2766 |  |  | 2806.5 |  |  | 2751 |  |  | 2708 |  |  | 2894.5 |  |  | 2814 |  |  | 2907.5 |  |  | 2710 |  |  | 2567 |  |  | 2790.5 |  |  | 2871 |  |  | 2886.5 |  |  | 2917 |  |  | 2659 |  |  | 2824.5 |  |  | 2811.5 |  |  | 2780 |  |  | 2770.5 |  |  | 2786.5 |  |  | 2777 |  |  | 2857 |  |  | 3008.5 |  |  | 2665.5 |  |  | 2896.5 |  |  | 2815 |  |  | 2865 |  |  | 2761 |  |  | 2921 |  |  | 2888 |  |  | 2807.5 |  |  | 2750 |  |  | 2648.5 |  |  | 2799.5 |  |  | 2745 |  |  | 2861 |  |  | 3062.5 |  |  | 2744.5 |  |  | 2697 |  |  | 2876.5 |  |  | 2676.5 |  |  | 2830 |  |  | 2729 |  |  | 2755 |  |  | 2726.5 |  |  | 2852 |  |  | 2752.5 |  |  | 2853.5 |  |  | 2794 |  |  | 2715.5 |  |  | 2749 |  |  | 2818 |  |  | 2855 |  |  | 2904 |  |  | 2622 |  |  | 2875 |  |  | 2957 |  |  | 2827 |  |  | 2873 |  |  | 2759 |  |  | 2780.5 |  |  | 2899.5 |  |  | 2717 |  |  | 2657 |  |  | 2965 |  |  | 2750.5 |  |  | 2873.5 |  |  | 2938.5 |  |  | 2626 |  |  | 2843 |  |  | 2915.5 |  |  | 2869.5 |  |  | 2640.5 |  |  | 2805 |  |  | 2871 |  |  | 2743 |  |  | 2854 |  |  | 2707 |  |  | 2778.5 |  |  | 2639.5 |  |  | 2923 |  |  | 2729 |  |  | 2748 |  |  | 2924 |  |  | 2713 |  |  | 2926.5 |  |  | 2824 |  |  | 2787 |  |  | 2683 |  |  | 2768 |  |  | 2813.5 |  |  | 2873 |  |  | 2763 |  |  | 2759 |  |  | 2822 |  |  | 2887.5 |  |  | 2760 |  |  | 2743 |  |  | 2721 |  |  | 2841.5 |  |  | 2792.5 |  |  | 2888.5 |  |  | 2887 |  |  | 2761 |  |  | 2667 |  |  | 2978 |  |  | 2719 |  |  | 2748.5 |  |  | 2823 |  |  | 2733.5 |  |  | 2876.5 |  |  | 2802.5 |  |  | 2868 |  |  | 3021.5 |  |  | 2711 |  |  | 2596 |  |  | 2736.5 |  |  | 2769.5 |  |  | 2872 |  |  | 2886.5 |  |  | 2954.5 |  |  | 2700 |  |  | 2876 |  |  | 2675.5 |  |  | 2713.5 |  |  | 2945 |  |  | 2814.5 |  |  | 2941 |  |  | 2776 |  |  | 2764.5 |  |  | 2849 |  |  | 2693 |  |  | 2802.5 |  |  | 2737 |  |  | 2829.5 |  |  | 2796 |  |  | 2999 |  |  | 2836 |  |  | 2768 |  |  | 2920.5 |  |  | 2908 |  |  | 2904.5 |  |  | 2676.5 |  |  | 2923.5 |  |  | 2934 |  |  | 2869.5 |  |  | 2997 |  |  | 2787 |  |  | 2600.5 |  |  | 2729.5 |  |  | 2843 |  |  | 2732.5 |  |  | 2981 |  |  | 2804 |  |  | 2984.5 |  |  | 2682 |  |  | 2784.5 |  |  | 2784.5 |  |  | 2862.5 |  |  | 2813 |  |  | 2624 |  |  | 2681 |  |  | 2731.5 |  |  | 2722 |  |  | 2982.5 |  |  | 2804 |  |  | 2740 |  |  | 2834 |  |  | 2848 |  |  | 2906 |  |  | 2735 |  |  | 2809 |  |  | 2964 |  |  | 2806 |  |  | 2777.5 |  |  | 2875 |  |  | 2745 |  |  | 2860.5 |  |  | 2672.5 |  |  | 2766.5 |  |  | 2736.5 |  |  | 2783 |  |  | 2854 |  |  | 2580.5 |  |  | 3016.5 |  |  | 2770.5 |  |  | 2828 |  |  | 2815 |  |  | 2719 |  |  | 2784 |  |  | 2638 |  |  | 2912 |  |  | 2910 |  |  | 2793.5 |  |  | 2872.5 |  |  | 2699 |  |  | 2705.5 |  |  | 2807.5 |  |  | 2705 |  |  | 2782 |  |  | 2809 |  |  | 2873 |  |  | 2712.5 |  |  | 2687.5 |  |  | 2816.5 |  |  | 2692 |  |  | 2779.5 |  |  | 2878 |  |  | 2794 |  |  | 2836 |  |  | 2680.5 |  |  | 2783 |  |  | 2655 |  |  | 2812.5 |  |  | 2669 |  |  | 2848.5 |  |  | 2892 |  |  | 2810.5 |  |  | 2791 |  |  | 2671.5 |  |  | 2802.5 |  |  | 2894 |  |  | 2847 |  |  | 2580 |  |  | 2837 |  |  | 2635.5 |  |  | 2769 |  |  | 2952 |  |  | 2766.5 |  |  | 2873.5 |  |  | 2563.5 |  |  | 2711 |  |  | 2875.5 |  |  | 2913.5 |  |  | 2717.5 |  |  | 2888 |  |  | 2813 |  |  | 2899.5 |  |  | 2756 |  |  | 2983 |  |  | 2783.5 |  |  | 2778 |  |  | 2900 |  |  | 2806 |  |  | 2639 |  |  | 2648.5 |  |  | 2830.5 |  |  | 2750 |  |  | 2931 |  |  | 2760 |  |  | 2796 |  |  | 2785 |  |  | 2731.5 |  |  | 2745.5 |  |  | 2799 |  |  | 2921 |  |  | 2976 |  |  | 2661.5 |  |  | 3033.5 |  |  | 2713 |  |  | 2819 |  |  | 2630 |  |  | 2892.5 |  |  | 2880.5 |  |  | 2763 |  |  | 2643 |  |  | 2845 |  |  | 2773 |  |  | 2740 |  |  | 2872 |  |  | 2769 |  |  | 2970.5 |  |  | 2770 |  |  | 2927 |  |  | 2813 |  |  | 2870.5 |  |  | 2857 |  |  | 2782 |  |  | 2645 |  |  | 2761 |  |  | 2776 |  |  | 2851 |  |  | 2880 |  |  | 2720.5 |  |  | 2776.5 |  |  | 2633.5 |  |  | 2896 |  |  | 2752 |  |  | 2767.5 |  |  | 2600 |  |  | 2684.5 |  |  | 2783.5 |  |  | 2770 |  |  | 2793 |  |  | 2779.5 |  |  | 2772 |  |  | 2825 |  |  | 2824 |  |  | 2771 |  |  | 2765 |  |  | 2721 |  |  | 2679 |  |  | 2815.5 |  |  | 2735 |  |  | 2920 |  |  | 2860 |  |  | 2821 |  |  | 2790 |  |  | 2795 |  |  | 2905 |  |  | 2852 |  |  | 2804 |  |  | 2861.5 |  |  | 2818.5 |  |  | 2806.5 |  |  | 2812.5 |  |  | 2863 |  |  | 2566 |  |  | 2883.5 |  |  | 2662 |  |  | 2813 |  |  | 2715.5 |  |  | 2893.5 |  |  | 2869 |  |  | 2789.5 |  |  | 2774.5 |  |  | 2590 |  |  | 2888 |  |  | 2744 |  |  | 2820 |  |  | 2752.5 |  |  | 2815 |  |  | 2727.5 |  |  | 2728.5 |  |  | 2783 |  |  | 2801 |  |  | 2838.5 |  |  | 2717 |  |  | 2775.5 |  |  | 2789 |  |  | 2796.5 |  |  | 2709.5 |  |  | 2550.5 |  |  | 2961.5 |  |  | 2832.5 |  |  | 2638 |  |  | 2720 |  |  | 2886.5 |  |  | 2836 |  |  | 2721 |  |  | 2775 |  |  | 2936 |  |  | 2887.5 |  |  | 2587 |  |  | 2725 |  |  | 2912 |  |  | 2788.5 |  |  | 2756 |  |  | 2617 |  |  | 2784 |  |  | 2942.5 |  |  | 2915 |  |  | 2624 |  |  | 2813 |  |  | 2907 |  |  | 3072.5 |  |  | 2762 |  |  | 2714.5 |  |  | 2784 |  |  | 2843 |  |  | 3043.5 |  |  | 2894 |  |  | 2737 |  |  | 2745.5 |  |  | 2830 |  |  | 2670 |  |  | 2697 |  |  | 3125.5 |  |  | 2810.5 |  |  | 2854 |  |  | 2718 |  |  | 2825.5 |  |  | 2796.5 |  |  | 2758 |  |  | 2899 |  |  | 2885.5 |  |  | 3000.5 |  |  | 2777.5 |  |  | 2845.5 |  |  | 2756.5 |  |  | 3008 |  |  | 2711.5 |  |  | 2912 |  |  | 2745 |  |  | 2957 |  |  | 2928 |  |  | 2779.5 |  |  | 2754 |  |  | 2714 |  |  | 2759.5 |  |  | 2799.5 |  |  | 2695 |  |  | 2868.5 |  |  | 2700.5 |  |  | 2859 |  |  | 2699 |  |  | 2857 |  |  | 2755.5 |  |  | 2806 |  |  | 2840.5 |  |  | 2900 |  |  | 2863 |  |  | 3040.5 |  |  | 2752 |  |  | 2908 |  |  | 2680 |  |  | 2871 |  |  | 2960 |  |  | 2769 |  |  | 2841 |  |  | 2792 |  |  | 2688.5 |  |  | 2695.5 |  |  | 2748 |  |  | 2833.5 |  |  | 2598.5 |  |  | 2715 |  |  | 2719 |  |  | 2811 |  |  | 2831.5 |  |  | 2662.5 |  |  | 2872 |  |  | 2814 |  |  | 2668 |  |  | 2752 |  |  | 2768 |  |  | 2659 |  |  | 2817 |  |  | 2697.5 |  |  | 2881 |  |  | 2930 |  |  | 2912 |  |  | 2665 |  |  | 2663 |  |  | 2737.5 |  |  | 3000.5 |  |  | 2621.5 |  |  | 2691 |  |  | 2757 |  |  | 2673.5 |  |  | 2824.5 |  |  | 2890.5 |  |  | 2704 |  |  | 2900.5 |  |  | 2904.5 |  |  | 2913 |  |  | 2792.5 |  |  | 2830.5 |  |  | 2745 |  |  | 2686 |  |  | 2718 |  |  | 2881 |  |  | 2753 |  |  | 2615 |  |  | 2869 |  |  | 2865 |  |  | 2649 |  |  | 2860 |  |  | 2968.5 |  |  | 2753 |  |  | 2786 |  |  | 2698 |  |  | 2637.5 |  |  | 2717 |  |  | 2836.5 |  |  | 2951 |  |  | 2903 |  |  | 2805 |  |  | 2859 |  |  | 2908.5 |  |  | 2787 |  |  | 2634 |  |  | 2805.5 |  |  | 2822 |  |  | 2679 |  |  | 2721.5 |  |  | 2710.5 |  |  | 2739 |  |  | 2719.5 |  |  | 2867 |  |  | 2688.5 |  |  | 2856 |  |  | 2781 |  |  | 2696.5 |  |  | 2839.5 |  |  | 2829 |  |  | 2843 |  |  | 2786 |  |  | 2770 |  |  | 2701 |  |  | 2779 |  |  | 2639 |  |  | 2690 |  |  | 2864.5 |  |  | 2646 |  |  | 2916.5 |  |  | 2670 |  |  | 2781.5 |  |  | 2727.5 |  |  | 2725 |  |  | 2847 |  |  | 2857.5 |  |  | 2813 |  |  | 2803 |  |  | 2823 |  |  | 2737.5 |  |  | 2851 |  |  | 2683.5 |  |  | 2530 |  |  | 2706 |  |  | 2768 |  |  | 2747 |  |  | 2850.5 |  |  | 2756 |  |  | 2745 |  |  | 2910 |  |  | 2741.5 |  |  | 2976 |  |  | 2829 |  |  | 2907 |  |  | 2812 |  |  | 2834.5 |  |  | 2636.5 |  |  | 2974 |  |  | 2926 |  |  | 2840 |  |  | 2857.5 |  |  | 2797 |  |  | 2663 |  |  | 2706 |  |  | 2962.5 |  |  | 2770.5 |  |  | 2746.5 |  |  | 2888 |  |  | 2839 |  |  | 2844 |  |  | 2730.5 |  |  | 2878 |  |  | 2701.5 |  |  | 2674 |  |  | 2716 |  |  | 2773 |  |  | 2668.5 |  |  | 2872.5 |  |  | 2797 |  |  | 2813 |  |  | 2815.5 |  |  | 2859 |  |  | 2710 |  |  | 2871.5 |  |  | 2676 |  |  | 2621 |  |  | 2828.5 |  |  | 2738 |  |  | 2802 |  |  | 2758.5 |  |  | 2869 |  |  | 2706.5 |  |  | 2758 |  |  | 2617.5 |  |  | 2853.5 |  |  | 2690 |  |  | 2824 |  |  | 2940.5 |  |  | 2735.5 |  |  | 2846 |  |  | 2773 |  |  | 2812 |  |  | 2830.5 |  |  | 2875 |  |  | 2615 |  |  | 2721 |  |  | 2843.5 |  |  | 2817.5 |  |  | 2905 |  |  | 2889 |  |  | 2815 |  |  | 2756 |  |  | 2872 |  |  | 2718 |  |  | 2763 |  |  | 2831.5 |  |  | 2967.5 |  |  | 2638.5 |  |  | 2744 |  |  | 2714.5 |  |  | 2854 |  |  | 2785 |  |  | 2820.5 |  |  | 2653.5 |  |  | 2665 |  |  | 2847 |  |  | 2719.5 |  |  | 2766 |  |  | 2788 |  |  | 2646.5 |  |  | 2867.5 |  |  | 2679 |  |  | 2730 |  |  | 2744 |  |  | 2626.5 |  |  | 2725 |  |  | 2697 |  |  | 2731 |  |  | 2876 |  |  | 2935 |  |  | 2693.5 |  |  | 2856 |  |  | 2844 |  |  | 2670 |  |  | 2902.5 |  |  | 2801 |  |  | 2655.5 |  |  | 2714.5 |  |  | 2714 |  |  | 2904 |  |  | 2812.5 |  |  | 2665.5 |  |  | 2659.5 |  |  | 2787.5 |  |  | 2825.5 |  |  | 2859 |  |  | 2756 |  |  | 2762.5 |  |  | 2721.5 |  |  | 2718 |  |  | 2669 |  |  | 2754.5 |  |  | 2991 |  |  | 2787 |  |  | 2663 |  |  | 2819.5 |  |  | 2947 |  |  | 2701.5 |  |  | 2653 |  |  | 2772.5 |  |  | 2987.5 |  |  | 2874.5 |  |  | 2928 |  |  | 2798 |  |  | 2793.5 |  |  | 2697.5 |  |  | 2860 |  |  | 2761 |  |  | 2852.5 |  |  | 2961 |  |  | 2786.5 |  |  | 2792.5 |  |  | 2747 |  |  | 2784 |  |  | 2620.5 |  |  | 2889.5 |  |  | 2864 |  |  | 2767.5 |  |  | 2803.5 |  |  | 2864 |  |  | 2872 |  |  | 2884 |  |  | 2831.5 |  |  | 2851 |  |  | 2673 |  |  | 2796 |  |  | 2716 |  |  | 2732 |  |  | 2765 |  |  | 3001.5 |  |  | 2828.5 |  |  | 2753 |  |  | 2721 |  |  | 2819 |  |  | 2670.5 |  |  | 2826 |  |  | 2895 |  |  | 2758.5 |  |  | 2972.5 |  |  | 2797 |  |  | 2711.5 |  |  | 2893 |  |  | 2679 |  |  | 2817 |  |  | 2901.5 |  |  | 2895 |  |  | 2660.5 |  |  | 2738.5 |  |  | 2616 |  |  | 2797.5 |  |  | 2602.5 |  |  | 2799 |  |  | 2692 |  |  | 2903 |  |  | 2818.5 |  |  | 2712 |  |  | 2708.5 |  |  | 2914.5 |  |  | 2859 |  |  | 2695.5 |  |  | 2686 |  |  | 2867 |  |  | 2791 |  |  | 2806 |  |  | 2631 |  |  | 2881.5 |  |  | 2768 |  |  | 2907 |  |  | 2775 |  |  | 2878 |  |  | 2784.5 |  |  | 2767.5 |  |  | 2793 |  |  | 2887 |  |  | 2777 |  |  | 2830 |  |  | 2834 |  |  | 2655.5 |  |  | 2747 |  |  | 2882.5 |  |  | 2913 |  |  | 2680 |  |  | 2847 |  |  | 2771 |  |  | 2833.5 |  |  | 2827 |  |  | 2876.5 |  |  | 2676 |  |  | 2904 |  |  | 2838 |  |  | 2803.5 |  |  | 2681 |  |  | 2639 |  |  | 2716 |  |  | 2956 |  |  | 3116 |  |  | 2731.5 |  |  | 2838.5 |  |  | 2690 |  |  | 2660.5 |  |  | 2757 |  |  | 2768.5 |  |  | 2666.5 |  |  | 2768.5 |  |  | 2750.5 |  |  | 2678 |  |  | 2930 |  |  | 2672 |  |  | 2635 |  |  | 2769 |  |  | 2853 |  |  | 2792.5 |  |  | 2725.5 |  |  | 2932.5 |  |  | 2767 |  |  | 2924.5 |  |  | 2700.5 |  |  | 2876.5 |  |  | 2676.5 |  |  | 2796 |  |  | 2805.5 |  |  | 2861.5 |  |  | 2850 |  |  | 2640.5 |  |  | 2932.5 |  |  | 2765.5 |  |  | 2949 |  |  | 2840.5 |  |  | 2850 |  |  | 2795 |  |  | 2775.5 |  |  | 2803.5 |  |  | 2861 |  |  | 2922 |  |  | 2568.5 |  |  | 2650.5 |  |  | 2750.5 |  |  | 2858 |  |  | 2705 |  |  | 2738 |  |  | 2906.5 |  |  | 2796.5 |  |  | 2765 |  |  | 2892.5 |  |  | 2593 |  |  | 2822 |  |  | 2810.5 |  |  | 2655.5 |  |  | 2688 |  |  | 2724.5 |  |  | 2884 |  |  | 2673.5 |  |  | 2882.5 |  |  | 2927 |  |  | 2810.5 |  |  | 2856 |  |  | 2788.5 |  |  | 2801 |  |  | 2837 |  |  | 2820 |  |  | 2750.5 |  |  | 2716.5 |  |  | 2781 |  |  | 2757 |  |  | 2724 |  |  | 2745.5 |  |  | 2831.5 |  |  | 2913 |  |  | 2848.5 |  |  | 2741 |  |  | 2566.5 |  |  | 2846.5 |  |  | 2623 |  |  | 2716 |  |  | 2666 |  |  | 2799.5 |  |  | 2671 |  |  | 2832.5 |  |  | 2763 |  |  | 2767.5 |  |  | 3004 |  |  | 2592.5 |  |  | 2801 |  |  | 2808.5 |  |  | 2779.5 |  |  | 2756 |  |  | 2751 |  |  | 2989 |  |  | 2797 |  |  | 2840.5 |  |  | 2755 |  |  | 2762.5 |  |  | 2661 |  |  | 2716 |  |  | 2768 |  |  | 2919 |  |  | 2870 |  |  | 2855 |  |  | 2875 |  |  | 2747.5 |  |  | 2784 |  |  | 2849
97 |  | 2987.5 |  |  | 2976 |  |  | 2975.5 |  |  | 2860 |  |  | 2738.5 |  |  | 2991 |  |  | 2866 |  |  | 2787 |  |  | 2648.5 |  |  | 2728 |  |  | 2788 |  |  | 2941 |  |  | 2912 |  |  | 2968 |  |  | 2748.5 |  |  | 2858.5 |  |  | 2765 |  |  | 2854 |  |  | 2939 |  |  | 2677.5 |  |  | 2892 |  |  | 2933 |  |  | 2754 |  |  | 2837 |  |  | 2824.5 |  |  | 2920 |  |  | 2721 |  |  | 2866 |  |  | 2971 |  |  | 2671 |  |  | 2789 |  |  | 2731.5 |  |  | 2957.5 |  |  | 2773.5 |  |  | 2770 |  |  | 2809.5 |  |  | 2874.5 |  |  | 2908.5 |  |  | 2886 |  |  | 2832 |  |  | 2712.5 |  |  | 2779 |  |  | 2809.5 |  |  | 2720.5 |  |  | 2818.5 |  |  | 3039.5 |  |  | 2917.5 |  |  | 2809 |  |  | 2626 |  |  | 2781.5 |  |  | 2736 |  |  | 2810.5 |  |  | 2755.5 |  |  | 2871 |  |  | 2749 |  |  | 2720 |  |  | 2707 |  |  | 2888 |  |  | 2806 |  |  | 2835.5 |  |  | 2851.5 |  |  | 2780.5 |  |  | 2779 |  |  | 2871 |  |  | 2637 |  |  | 2744.5 |  |  | 2871 |  |  | 2744.5 |  |  | 2947.5 |  |  | 2936.5 |  |  | 2836 |  |  | 2993 |  |  | 2928 |  |  | 2795.5 |  |  | 2940.5 |  |  | 2763.5 |  |  | 2914.5 |  |  | 2901.5 |  |  | 2883.5 |  |  | 2790.5 |  |  | 2745.5 |  |  | 2614 |  |  | 2916 |  |  | 2757 |  |  | 2904.5 |  |  | 2904 |  |  | 2776.5 |  |  | 2919 |  |  | 2763 |  |  | 2807.5 |  |  | 2950.5 |  |  | 2668 |  |  | 2916 |  |  | 2794.5 |  |  | 3033 |  |  | 2722.5 |  |  | 2880.5 |  |  | 2806.5 |  |  | 2826.5 |  |  | 2709.5 |  |  | 2730 |  |  | 2774 |  |  | 2639 |  |  | 2763.5 |  |  | 2800.5 |  |  | 2867.5 |  |  | 2730.5 |  |  | 2770 |  |  | 2754 |  |  | 2869.5 |  |  | 2791 |  |  | 2886.5 |  |  | 2855 |  |  | 2796 |  |  | 2766.5 |  |  | 2814 |  |  | 2844 |  |  | 2755 |  |  | 2863 |  |  | 2844.5 |  |  | 2848.5 |  |  | 2734.5 |  |  | 2937 |  |  | 2706 |  |  | 2755 |  |  | 2797 |  |  | 2751.5 |  |  | 2817 |  |  | 2877.5 |  |  | 2791 |  |  | 2610 |  |  | 2793.5 |  |  | 2724.5 |  |  | 2696 |  |  | 2763.5 |  |  | 2798 |  |  | 2938 |  |  | 2769 |  |  | 2952 |  |  | 2736 |  |  | 2746 |  |  | 2746 |  |  | 2813 |  |  | 2716 |  |  | 2708.5 |  |  | 2773 |  |  | 2694 |  |  | 2944 |  |  | 2875 |  |  | 2794 |  |  | 2763 |  |  | 2834 |  |  | 2786.5 |  |  | 2790 |  |  | 2830.5 |  |  | 2790 |  |  | 2723 |  |  | 2918.5 |  |  | 2843 |  |  | 2936.5 |  |  | 2749 |  |  | 2614 |  |  | 2837.5 |  |  | 2918 |  |  | 2915.5 |  |  | 2941 |  |  | 2688 |  |  | 2863.5 |  |  | 2850.5 |  |  | 2795 |  |  | 2799.5 |  |  | 2810.5 |  |  | 2801 |  |  | 2886 |  |  | 3055.5 |  |  | 2704.5 |  |  | 2911.5 |  |  | 2854 |  |  | 2891 |  |  | 2800 |  |  | 2960 |  |  | 2927 |  |  | 2833.5 |  |  | 2771 |  |  | 2687.5 |  |  | 2838.5 |  |  | 2774 |  |  | 2900 |  |  | 3083.5 |  |  | 2768.5 |  |  | 2718 |  |  | 2915.5 |  |  | 2691.5 |  |  | 2856 |  |  | 2753 |  |  | 2779 |  |  | 2765.5 |  |  | 2881 |  |  | 2781.5 |  |  | 2892.5 |  |  | 2809 |  |  | 2754.5 |  |  | 2770 |  |  | 2842 |  |  | 2879 |  |  | 2933 |  |  | 2648 |  |  | 2901 |  |  | 3004 |  |  | 2851 |  |  | 2902 |  |  | 2785 |  |  | 2809.5 |  |  | 2938.5 |  |  | 2746 |  |  | 2678 |  |  | 2994 |  |  | 2797.5 |  |  | 2894.5 |  |  | 2985.5 |  |  | 2650 |  |  | 2882 |  |  | 2941.5 |  |  | 2908.5 |  |  | 2679.5 |  |  | 2844 |  |  | 2897 |  |  | 2782 |  |  | 2880 |  |  | 2722 |  |  | 2793.5 |  |  | 2654.5 |  |  | 2952 |  |  | 2750 |  |  | 2777 |  |  | 2963 |  |  | 2737 |  |  | 2973.5 |  |  | 2863 |  |  | 2813 |  |  | 2712 |  |  | 2815 |  |  | 2852.5 |  |  | 2902 |  |  | 2778 |  |  | 2798 |  |  | 2837 |  |  | 2926.5 |  |  | 2784 |  |  | 2764 |  |  | 2760 |  |  | 2856.5 |  |  | 2818.5 |  |  | 2909.5 |  |  | 2926 |  |  | 2808 |  |  | 2696 |  |  | 2999 |  |  | 2758 |  |  | 2763.5 |  |  | 2847 |  |  | 2757.5 |  |  | 2891.5 |  |  | 2841.5 |  |  | 2907 |  |  | 3060.5 |  |  | 2726 |  |  | 2643 |  |  | 2765.5 |  |  | 2808.5 |  |  | 2911 |  |  | 2915.5 |  |  | 3001.5 |  |  | 2747 |  |  | 2923 |  |  | 2696.5 |  |  | 2739.5 |  |  | 2971 |  |  | 2840.5 |  |  | 2956 |  |  | 2823 |  |  | 2803.5 |  |  | 2888 |  |  | 2714 |  |  | 2823.5 |  |  | 2763 |  |  | 2868.5 |  |  | 2825 |  |  | 3028 |  |  | 2883 |  |  | 2797 |  |  | 2935.5 |  |  | 2947 |  |  | 2919.5 |  |  | 2715.5 |  |  | 2970.5 |  |  | 2981 |  |  | 2908.5 |  |  | 3018 |  |  | 2808 |  |  | 2639.5 |  |  | 2755.5 |  |  | 2872 |  |  | 2753.5 |  |  | 3002 |  |  | 2819 |  |  | 3005.5 |  |  | 2697 |  |  | 2799.5 |  |  | 2810.5 |  |  | 2877.5 |  |  | 2828 |  |  | 2663 |  |  | 2696 |  |  | 2746.5 |  |  | 2761 |  |  | 3003.5 |  |  | 2833 |  |  | 2761 |  |  | 2873 |  |  | 2863 |  |  | 2932 |  |  | 2750 |  |  | 2833 |  |  | 2979 |  |  | 2845 |  |  | 2801.5 |  |  | 2922 |  |  | 2771 |  |  | 2889.5 |  |  | 2719.5 |  |  | 2805.5 |  |  | 2757.5 |  |  | 2798 |  |  | 2883 |  |  | 2619.5 |  |  | 3045.5 |  |  | 2796.5 |  |  | 2843 |  |  | 2839 |  |  | 2745 |  |  | 2831 |  |  | 2677 |  |  | 2938 |  |  | 2939 |  |  | 2808.5 |  |  | 2898.5 |  |  | 2746 |  |  | 2729.5 |  |  | 2846.5 |  |  | 2744 |  |  | 2803 |  |  | 2835 |  |  | 2894 |  |  | 2751.5 |  |  | 2702.5 |  |  | 2831.5 |  |  | 2713 |  |  | 2818.5 |  |  | 2925 |  |  | 2820 |  |  | 2875 |  |  | 2701.5 |  |  | 2830 |  |  | 2694 |  |  | 2827.5 |  |  | 2693 |  |  | 2887.5 |  |  | 2916 |  |  | 2839.5 |  |  | 2820 |  |  | 2710.5 |  |  | 2817.5 |  |  | 2941 |  |  | 2886 |  |  | 2601 |  |  | 2866 |  |  | 2659.5 |  |  | 2808 |  |  | 2981 |  |  | 2781.5 |  |  | 2920.5 |  |  | 2589.5 |  |  | 2735 |  |  | 2914.5 |  |  | 2942.5 |  |  | 2741.5 |  |  | 2917 |  |  | 2852 |  |  | 2923.5 |  |  | 2780 |  |  | 3004 |  |  | 2809.5 |  |  | 2817 |  |  | 2926 |  |  | 2845 |  |  | 2654 |  |  | 2672.5 |  |  | 2851.5 |  |  | 2779 |  |  | 2952 |  |  | 2789 |  |  | 2835 |  |  | 2800 |  |  | 2770.5 |  |  | 2769.5 |  |  | 2838 |  |  | 2945 |  |  | 2997 |  |  | 2690.5 |  |  | 3072.5 |  |  | 2737 |  |  | 2858 |  |  | 2669 |  |  | 2907.5 |  |  | 2927.5 |  |  | 2792 |  |  | 2669 |  |  | 2869 |  |  | 2812 |  |  | 2787 |  |  | 2898 |  |  | 2795 |  |  | 2985.5 |  |  | 2817 |  |  | 2974 |  |  | 2837 |  |  | 2885.5 |  |  | 2904 |  |  | 2808 |  |  | 2671 |  |  | 2808 |  |  | 2791 |  |  | 2877 |  |  | 2901 |  |  | 2767.5 |  |  | 2815.5 |  |  | 2659.5 |  |  | 2920 |  |  | 2791 |  |  | 2806.5 |  |  | 2639 |  |  | 2731.5 |  |  | 2830.5 |  |  | 2809 |  |  | 2832 |  |  | 2805.5 |  |  | 2796 |  |  | 2849 |  |  | 2871 |  |  | 2810 |  |  | 2786 |  |  | 2750 |  |  | 2718 |  |  | 2830.5 |  |  | 2782 |  |  | 2944 |  |  | 2881 |  |  | 2842 |  |  | 2814 |  |  | 2824 |  |  | 2934 |  |  | 2873 |  |  | 2843 |  |  | 2885.5 |  |  | 2847.5 |  |  | 2827.5 |  |  | 2836.5 |  |  | 2902 |  |  | 2595 |  |  | 2904.5 |  |  | 2709 |  |  | 2852 |  |  | 2739.5 |  |  | 2932.5 |  |  | 2908 |  |  | 2828.5 |  |  | 2813.5 |  |  | 2637 |  |  | 2914 |  |  | 2770 |  |  | 2835 |  |  | 2791.5 |  |  | 2854 |  |  | 2753.5 |  |  | 2752.5 |  |  | 2822 |  |  | 2827 |  |  | 2877.5 |  |  | 2743 |  |  | 2804.5 |  |  | 2815 |  |  | 2843.5 |  |  | 2756.5 |  |  | 2574.5 |  |  | 3000.5 |  |  | 2858.5 |  |  | 2659 |  |  | 2759 |  |  | 2912.5 |  |  | 2860 |  |  | 2747 |  |  | 2799 |  |  | 2960 |  |  | 2934.5 |  |  | 2602 |  |  | 2746 |  |  | 2941 |  |  | 2812.5 |  |  | 2777 |  |  | 2632 |  |  | 2808 |  |  | 2981.5 |  |  | 2936 |  |  | 2663 |  |  | 2842 |  |  | 2946 |  |  | 3101.5 |  |  | 2801 |  |  | 2729.5 |  |  | 2813 |  |  | 2890 |  |  | 3069.5 |  |  | 2933 |  |  | 2761 |  |  | 2766.5 |  |  | 2854 |  |  | 2717 |  |  | 2721 |  |  | 3149.5 |  |  | 2839.5 |  |  | 2893 |  |  | 2757 |  |  | 2864.5 |  |  | 2843.5 |  |  | 2805 |  |  | 2938 |  |  | 2911.5 |  |  | 3024.5 |  |  | 2803.5 |  |  | 2871.5 |  |  | 2777.5 |  |  | 3029 |  |  | 2750.5 |  |  | 2959 |  |  | 2769 |  |  | 2986 |  |  | 2957 |  |  | 2794.5 |  |  | 2775 |  |  | 2761 |  |  | 2783.5 |  |  | 2825.5 |  |  | 2716 |  |  | 2894.5 |  |  | 2724.5 |  |  | 2880 |  |  | 2725 |  |  | 2881 |  |  | 2781.5 |  |  | 2827 |  |  | 2861.5 |  |  | 2921 |  |  | 2902 |  |  | 3055.5 |  |  | 2791 |  |  | 2955 |  |  | 2727 |  |  | 2897 |  |  | 2981 |  |  | 2793 |  |  | 2867 |  |  | 2821 |  |  | 2717.5 |  |  | 2734.5 |  |  | 2787 |  |  | 2872.5 |  |  | 2637.5 |  |  | 2754 |  |  | 2748 |  |  | 2840 |  |  | 2860.5 |  |  | 2701.5 |  |  | 2919 |  |  | 2838 |  |  | 2689 |  |  | 2799 |  |  | 2794 |  |  | 2698 |  |  | 2856 |  |  | 2736.5 |  |  | 2910 |  |  | 2954 |  |  | 2936 |  |  | 2704 |  |  | 2702 |  |  | 2758.5 |  |  | 3015.5 |  |  | 2660.5 |  |  | 2720 |  |  | 2796 |  |  | 2688.5 |  |  | 2848.5 |  |  | 2937.5 |  |  | 2751 |  |  | 2924.5 |  |  | 2928.5 |  |  | 2952 |  |  | 2816.5 |  |  | 2877.5 |  |  | 2771 |  |  | 2733 |  |  | 2744 |  |  | 2928 |  |  | 2774 |  |  | 2644 |  |  | 2908 |  |  | 2894 |  |  | 2675 |  |  | 2884 |  |  | 3007.5 |  |  | 2774 |  |  | 2825 |  |  | 2737 |  |  | 2661.5 |  |  | 2743 |  |  | 2875.5 |  |  | 2990 |  |  | 2929 |  |  | 2834 |  |  | 2885 |  |  | 2955.5 |  |  | 2826 |  |  | 2649 |  |  | 2844.5 |  |  | 2861 |  |  | 2694 |  |  | 2750.5 |  |  | 2725.5 |  |  | 2763 |  |  | 2748.5 |  |  | 2896 |  |  | 2714.5 |  |  | 2877 |  |  | 2828 |  |  | 2725.5 |  |  | 2886.5 |  |  | 2868 |  |  | 2858 |  |  | 2812 |  |  | 2796 |  |  | 2730 |  |  | 2818 |  |  | 2686 |  |  | 2714 |  |  | 2911.5 |  |  | 2661 |  |  | 2963.5 |  |  | 2694 |  |  | 2828.5 |  |  | 2774.5 |  |  | 2772 |  |  | 2876 |  |  | 2883.5 |  |  | 2852 |  |  | 2850 |  |  | 2862 |  |  | 2758.5 |  |  | 2875 |  |  | 2698.5 |  |  | 2554 |  |  | 2730 |  |  | 2815 |  |  | 2786 |  |  | 2865.5 |  |  | 2782 |  |  | 2784 |  |  | 2936 |  |  | 2762.5 |  |  | 2997 |  |  | 2876 |  |  | 2931 |  |  | 2838 |  |  | 2873.5 |  |  | 2665.5 |  |  | 3000 |  |  | 2955 |  |  | 2866 |  |  | 2896.5 |  |  | 2836 |  |  | 2689 |  |  | 2745 |  |  | 2991.5 |  |  | 2796.5 |  |  | 2761.5 |  |  | 2927 |  |  | 2863 |  |  | 2865 |  |  | 2756.5 |  |  | 2902 |  |  | 2740.5 |  |  | 2695 |  |  | 2740 |  |  | 2797 |  |  | 2707.5 |  |  | 2893.5 |  |  | 2818 |  |  | 2839 |  |  | 2844.5 |  |  | 2906 |  |  | 2757 |  |  | 2900.5 |  |  | 2705 |  |  | 2660 |  |  | 2857.5 |  |  | 2759 |  |  | 2823 |  |  | 2782.5 |  |  | 2893 |  |  | 2730.5 |  |  | 2784 |  |  | 2646.5 |  |  | 2900.5 |  |  | 2737 |  |  | 2863 |  |  | 2979.5 |  |  | 2761.5 |  |  | 2861 |  |  | 2812 |  |  | 2841 |  |  | 2859.5 |  |  | 2896 |  |  | 2654 |  |  | 2760 |  |  | 2872.5 |  |  | 2856.5 |  |  | 2952 |  |  | 2936 |  |  | 2854 |  |  | 2777 |  |  | 2901 |  |  | 2747 |  |  | 2792 |  |  | 2870.5 |  |  | 3006.5 |  |  | 2662.5 |  |  | 2791 |  |  | 2735.5 |  |  | 2875 |  |  | 2809 |  |  | 2846.5 |  |  | 2700.5 |  |  | 2694 |  |  | 2862 |  |  | 2758.5 |  |  | 2792 |  |  | 2809 |  |  | 2667.5 |  |  | 2888.5 |  |  | 2718 |  |  | 2754 |  |  | 2759 |  |  | 2650.5 |  |  | 2749 |  |  | 2712 |  |  | 2746 |  |  | 2915 |  |  | 2959 |  |  | 2717.5 |  |  | 2895 |  |  | 2859 |  |  | 2709 |  |  | 2949.5 |  |  | 2840 |  |  | 2684.5 |  |  | 2735.5 |  |  | 2753 |  |  | 2943 |  |  | 2838.5 |  |  | 2680.5 |  |  | 2706.5 |  |  | 2813.5 |  |  | 2846.5 |  |  | 2880 |  |  | 2803 |  |  | 2786.5 |  |  | 2768.5 |  |  | 2742 |  |  | 2695 |  |  | 2769.5 |  |  | 3030 |  |  | 2808 |  |  | 2687 |  |  | 2840.5 |  |  | 2986 |  |  | 2740.5 |  |  | 2679 |  |  | 2796.5 |  |  | 3002.5 |  |  | 2913.5 |  |  | 2967 |  |  | 2827 |  |  | 2808.5 |  |  | 2712.5 |  |  | 2881 |  |  | 2790 |  |  | 2881.5 |  |  | 2976 |  |  | 2812.5 |  |  | 2831.5 |  |  | 2786 |  |  | 2813 |  |  | 2644.5 |  |  | 2913.5 |  |  | 2890 |  |  | 2791.5 |  |  | 2818.5 |  |  | 2903 |  |  | 2901 |  |  | 2908 |  |  | 2846.5 |  |  | 2875 |  |  | 2694 |  |  | 2825 |  |  | 2737 |  |  | 2771 |  |  | 2812 |  |  | 3030.5 |  |  | 2852.5 |  |  | 2768 |  |  | 2760 |  |  | 2848 |  |  | 2691.5 |  |  | 2873 |  |  | 2934 |  |  | 2787.5 |  |  | 2996.5 |  |  | 2821 |  |  | 2726.5 |  |  | 2908 |  |  | 2694 |  |  | 2841 |  |  | 2940.5 |  |  | 2919 |  |  | 2681.5 |  |  | 2767.5 |  |  | 2645 |  |  | 2826.5 |  |  | 2626.5 |  |  | 2823 |  |  | 2721 |  |  | 2932 |  |  | 2857.5 |  |  | 2733 |  |  | 2737.5 |  |  | 2935.5 |  |  | 2883 |  |  | 2710.5 |  |  | 2733 |  |  | 2914 |  |  | 2830 |  |  | 2830 |  |  | 2646 |  |  | 2905.5 |  |  | 2815 |  |  | 2922 |  |  | 2799 |  |  | 2902 |  |  | 2810.5 |  |  | 2788.5 |  |  | 2817 |  |  | 2911 |  |  | 2816 |  |  | 2859 |  |  | 2873 |  |  | 2702.5 |  |  | 2771 |  |  | 2921.5 |  |  | 2928 |  |  | 2719 |  |  | 2873 |  |  | 2800 |  |  | 2857.5 |  |  | 2874 |  |  | 2902.5 |  |  | 2715 |  |  | 2933 |  |  | 2853 |  |  | 2829.5 |  |  | 2702 |  |  | 2678 |  |  | 2737 |  |  | 2985 |  |  | 3163 |  |  | 2760.5 |  |  | 2877.5 |  |  | 2705 |  |  | 2699.5 |  |  | 2772 |  |  | 2807.5 |  |  | 2705.5 |  |  | 2807.5 |  |  | 2789.5 |  |  | 2725 |  |  | 2956 |  |  | 2693 |  |  | 2659 |  |  | 2784 |  |  | 2892 |  |  | 2818.5 |  |  | 2754.5 |  |  | 2961.5 |  |  | 2806 |  |  | 2950.5 |  |  | 2729.5 |  |  | 2915.5 |  |  | 2697.5 |  |  | 2820 |  |  | 2826.5 |  |  | 2908.5 |  |  | 2889 |  |  | 2679.5 |  |  | 2971.5 |  |  | 2812.5 |  |  | 2973 |  |  | 2864.5 |  |  | 2897 |  |  | 2821 |  |  | 2814.5 |  |  | 2827.5 |  |  | 2900 |  |  | 2969 |  |  | 2607.5 |  |  | 2676.5 |  |  | 2774.5 |  |  | 2873 |  |  | 2744 |  |  | 2777 |  |  | 2945.5 |  |  | 2811.5 |  |  | 2804 |  |  | 2907.5 |  |  | 2614 |  |  | 2846 |  |  | 2857.5 |  |  | 2702.5 |  |  | 2717 |  |  | 2763.5 |  |  | 2905 |  |  | 2699.5 |  |  | 2911.5 |  |  | 2956 |  |  | 2839.5 |  |  | 2903 |  |  | 2803.5 |  |  | 2825 |  |  | 2863 |  |  | 2835 |  |  | 2779.5 |  |  | 2755.5 |  |  | 2796 |  |  | 2786 |  |  | 2763 |  |  | 2771.5 |  |  | 2860.5 |  |  | 2960 |  |  | 2869.5 |  |  | 2780 |  |  | 2587.5 |  |  | 2885.5 |  |  | 2644 |  |  | 2737 |  |  | 2695 |  |  | 2828.5 |  |  | 2710 |  |  | 2871.5 |  |  | 2778 |  |  | 2806.5 |  |  | 3019 |  |  | 2616.5 |  |  | 2816 |  |  | 2847.5 |  |  | 2818.5 |  |  | 2782 |  |  | 2790 |  |  | 3018 |  |  | 2836 |  |  | 2855.5 |  |  | 2802 |  |  | 2783.5 |  |  | 2676 |  |  | 2755 |  |  | 2792 |  |  | 2943 |  |  | 2896 |  |  | 2894 |  |  | 2899 |  |  | 2776.5 |  |  | 2805 |  |  | 2864
98 |  | 3008.5 |  |  | 3023 |  |  | 3014.5 |  |  | 2889 |  |  | 2777.5 |  |  | 3020 |  |  | 2895 |  |  | 2802 |  |  | 2663.5 |  |  | 2767 |  |  | 2803 |  |  | 2980 |  |  | 2927 |  |  | 2992 |  |  | 2777.5 |  |  | 2882.5 |  |  | 2786 |  |  | 2893 |  |  | 2960 |  |  | 2703.5 |  |  | 2918 |  |  | 2954 |  |  | 2780 |  |  | 2866 |  |  | 2871.5 |  |  | 2946 |  |  | 2768 |  |  | 2890 |  |  | 2992 |  |  | 2718 |  |  | 2810 |  |  | 2752.5 |  |  | 2986.5 |  |  | 2799.5 |  |  | 2809 |  |  | 2848.5 |  |  | 2898.5 |  |  | 2937.5 |  |  | 2915 |  |  | 2879 |  |  | 2751.5 |  |  | 2808 |  |  | 2848.5 |  |  | 2746.5 |  |  | 2844.5 |  |  | 3054.5 |  |  | 2964.5 |  |  | 2824 |  |  | 2665 |  |  | 2796.5 |  |  | 2765 |  |  | 2834.5 |  |  | 2802.5 |  |  | 2895 |  |  | 2775 |  |  | 2749 |  |  | 2733 |  |  | 2935 |  |  | 2853 |  |  | 2861.5 |  |  | 2890.5 |  |  | 2795.5 |  |  | 2818 |  |  | 2900 |  |  | 2676 |  |  | 2783.5 |  |  | 2900 |  |  | 2773.5 |  |  | 2968.5 |  |  | 2962.5 |  |  | 2875 |  |  | 3040 |  |  | 2957 |  |  | 2834.5 |  |  | 2979.5 |  |  | 2784.5 |  |  | 2938.5 |  |  | 2930.5 |  |  | 2907.5 |  |  | 2814.5 |  |  | 2766.5 |  |  | 2653 |  |  | 2955 |  |  | 2786 |  |  | 2928.5 |  |  | 2951 |  |  | 2802.5 |  |  | 2945 |  |  | 2784 |  |  | 2854.5 |  |  | 2974.5 |  |  | 2697 |  |  | 2945 |  |  | 2820.5 |  |  | 3072 |  |  | 2748.5 |  |  | 2909.5 |  |  | 2832.5 |  |  | 2865.5 |  |  | 2730.5 |  |  | 2769 |  |  | 2813 |  |  | 2665 |  |  | 2802.5 |  |  | 2847.5 |  |  | 2906.5 |  |  | 2745.5 |  |  | 2817 |  |  | 2801 |  |  | 2893.5 |  |  | 2806 |  |  | 2933.5 |  |  | 2894 |  |  | 2820 |  |  | 2805.5 |  |  | 2838 |  |  | 2891 |  |  | 2784 |  |  | 2892 |  |  | 2859.5 |  |  | 2895.5 |  |  | 2760.5 |  |  | 2976 |  |  | 2732 |  |  | 2779 |  |  | 2821 |  |  | 2790.5 |  |  | 2864 |  |  | 2892.5 |  |  | 2830 |  |  | 2625 |  |  | 2808.5 |  |  | 2771.5 |  |  | 2722 |  |  | 2787.5 |  |  | 2837 |  |  | 2964 |  |  | 2808 |  |  | 2967 |  |  | 2775 |  |  | 2772 |  |  | 2793 |  |  | 2834 |  |  | 2737 |  |  | 2755.5 |  |  | 2799 |  |  | 2741 |  |  | 2973 |  |  | 2890 |  |  | 2809 |  |  | 2778 |  |  | 2881 |  |  | 2812.5 |  |  | 2819 |  |  | 2869.5 |  |  | 2816 |  |  | 2770 |  |  | 2957.5 |  |  | 2882 |  |  | 2962.5 |  |  | 2764 |  |  | 2643 |  |  | 2876.5 |  |  | 2947 |  |  | 2936.5 |  |  | 2970 |  |  | 2717 |  |  | 2889.5 |  |  | 2874.5 |  |  | 2821 |  |  | 2825.5 |  |  | 2839.5 |  |  | 2816 |  |  | 2933 |  |  | 3079.5 |  |  | 2743.5 |  |  | 2926.5 |  |  | 2893 |  |  | 2915 |  |  | 2839 |  |  | 2986 |  |  | 2966 |  |  | 2859.5 |  |  | 2810 |  |  | 2711.5 |  |  | 2877.5 |  |  | 2821 |  |  | 2921 |  |  | 3122.5 |  |  | 2797.5 |  |  | 2747 |  |  | 2941.5 |  |  | 2730.5 |  |  | 2895 |  |  | 2800 |  |  | 2794 |  |  | 2804.5 |  |  | 2920 |  |  | 2805.5 |  |  | 2931.5 |  |  | 2824 |  |  | 2769.5 |  |  | 2799 |  |  | 2857 |  |  | 2905 |  |  | 2980 |  |  | 2687 |  |  | 2930 |  |  | 3028 |  |  | 2880 |  |  | 2926 |  |  | 2824 |  |  | 2856.5 |  |  | 2962.5 |  |  | 2767 |  |  | 2725 |  |  | 3020 |  |  | 2826.5 |  |  | 2923.5 |  |  | 3024.5 |  |  | 2689 |  |  | 2906 |  |  | 2962.5 |  |  | 2923.5 |  |  | 2703.5 |  |  | 2868 |  |  | 2936 |  |  | 2808 |  |  | 2919 |  |  | 2761 |  |  | 2832.5 |  |  | 2693.5 |  |  | 2967 |  |  | 2789 |  |  | 2792 |  |  | 2984 |  |  | 2766 |  |  | 3012.5 |  |  | 2887 |  |  | 2852 |  |  | 2759 |  |  | 2854 |  |  | 2867.5 |  |  | 2928 |  |  | 2799 |  |  | 2837 |  |  | 2876 |  |  | 2955.5 |  |  | 2810 |  |  | 2793 |  |  | 2781 |  |  | 2895.5 |  |  | 2844.5 |  |  | 2933.5 |  |  | 2955 |  |  | 2847 |  |  | 2735 |  |  | 3023 |  |  | 2779 |  |  | 2784.5 |  |  | 2862 |  |  | 2783.5 |  |  | 2915.5 |  |  | 2880.5 |  |  | 2928 |  |  | 3075.5 |  |  | 2747 |  |  | 2667 |  |  | 2794.5 |  |  | 2834.5 |  |  | 2932 |  |  | 2930.5 |  |  | 3030.5 |  |  | 2794 |  |  | 2947 |  |  | 2743.5 |  |  | 2754.5 |  |  | 3010 |  |  | 2855.5 |  |  | 2980 |  |  | 2870 |  |  | 2818.5 |  |  | 2909 |  |  | 2761 |  |  | 2844.5 |  |  | 2789 |  |  | 2894.5 |  |  | 2872 |  |  | 3057 |  |  | 2912 |  |  | 2818 |  |  | 2956.5 |  |  | 2971 |  |  | 2934.5 |  |  | 2754.5 |  |  | 3017.5 |  |  | 3007 |  |  | 2947.5 |  |  | 3044 |  |  | 2855 |  |  | 2654.5 |  |  | 2784.5 |  |  | 2898 |  |  | 2779.5 |  |  | 3026 |  |  | 2840 |  |  | 3020.5 |  |  | 2736 |  |  | 2838.5 |  |  | 2857.5 |  |  | 2916.5 |  |  | 2867 |  |  | 2710 |  |  | 2743 |  |  | 2761.5 |  |  | 2800 |  |  | 3050.5 |  |  | 2859 |  |  | 2787 |  |  | 2899 |  |  | 2887 |  |  | 2958 |  |  | 2765 |  |  | 2848 |  |  | 3008 |  |  | 2874 |  |  | 2816.5 |  |  | 2948 |  |  | 2810 |  |  | 2928.5 |  |  | 2740.5 |  |  | 2831.5 |  |  | 2778.5 |  |  | 2813 |  |  | 2922 |  |  | 2640.5 |  |  | 3092.5 |  |  | 2811.5 |  |  | 2872 |  |  | 2860 |  |  | 2784 |  |  | 2857 |  |  | 2703 |  |  | 2977 |  |  | 2965 |  |  | 2855.5 |  |  | 2937.5 |  |  | 2761 |  |  | 2750.5 |  |  | 2885.5 |  |  | 2770 |  |  | 2832 |  |  | 2864 |  |  | 2915 |  |  | 2790.5 |  |  | 2717.5 |  |  | 2846.5 |  |  | 2728 |  |  | 2857.5 |  |  | 2940 |  |  | 2844 |  |  | 2896 |  |  | 2722.5 |  |  | 2869 |  |  | 2733 |  |  | 2874.5 |  |  | 2714 |  |  | 2926.5 |  |  | 2945 |  |  | 2860.5 |  |  | 2846 |  |  | 2736.5 |  |  | 2832.5 |  |  | 2967 |  |  | 2925 |  |  | 2616 |  |  | 2905 |  |  | 2680.5 |  |  | 2823 |  |  | 3007 |  |  | 2820.5 |  |  | 2946.5 |  |  | 2604.5 |  |  | 2774 |  |  | 2929.5 |  |  | 2981.5 |  |  | 2762.5 |  |  | 2946 |  |  | 2899 |  |  | 2949.5 |  |  | 2819 |  |  | 3019 |  |  | 2856.5 |  |  | 2864 |  |  | 2965 |  |  | 2892 |  |  | 2693 |  |  | 2719.5 |  |  | 2866.5 |  |  | 2808 |  |  | 2991 |  |  | 2828 |  |  | 2864 |  |  | 2824 |  |  | 2817.5 |  |  | 2790.5 |  |  | 2862 |  |  | 2969 |  |  | 3044 |  |  | 2711.5 |  |  | 3101.5 |  |  | 2761 |  |  | 2897 |  |  | 2690 |  |  | 2931.5 |  |  | 2942.5 |  |  | 2813 |  |  | 2693 |  |  | 2893 |  |  | 2827 |  |  | 2811 |  |  | 2919 |  |  | 2821 |  |  | 3024.5 |  |  | 2856 |  |  | 3013 |  |  | 2861 |  |  | 2924.5 |  |  | 2928 |  |  | 2823 |  |  | 2710 |  |  | 2829 |  |  | 2820 |  |  | 2916 |  |  | 2940 |  |  | 2796.5 |  |  | 2854.5 |  |  | 2683.5 |  |  | 2935 |  |  | 2806 |  |  | 2821.5 |  |  | 2678 |  |  | 2755.5 |  |  | 2845.5 |  |  | 2848 |  |  | 2879 |  |  | 2820.5 |  |  | 2843 |  |  | 2878 |  |  | 2886 |  |  | 2834 |  |  | 2807 |  |  | 2776 |  |  | 2733 |  |  | 2856.5 |  |  | 2811 |  |  | 2959 |  |  | 2920 |  |  | 2889 |  |  | 2843 |  |  | 2863 |  |  | 2973 |  |  | 2897 |  |  | 2869 |  |  | 2924.5 |  |  | 2876.5 |  |  | 2866.5 |  |  | 2875.5 |  |  | 2949 |  |  | 2619 |  |  | 2919.5 |  |  | 2724 |  |  | 2891 |  |  | 2778.5 |  |  | 2971.5 |  |  | 2932 |  |  | 2875.5 |  |  | 2852.5 |  |  | 2676 |  |  | 2929 |  |  | 2809 |  |  | 2882 |  |  | 2817.5 |  |  | 2901 |  |  | 2779.5 |  |  | 2776.5 |  |  | 2861 |  |  | 2842 |  |  | 2892.5 |  |  | 2764 |  |  | 2830.5 |  |  | 2841 |  |  | 2882.5 |  |  | 2795.5 |  |  | 2600.5 |  |  | 3015.5 |  |  | 2887.5 |  |  | 2706 |  |  | 2774 |  |  | 2951.5 |  |  | 2899 |  |  | 2786 |  |  | 2814 |  |  | 3007 |  |  | 2973.5 |  |  | 2649 |  |  | 2785 |  |  | 2980 |  |  | 2851.5 |  |  | 2792 |  |  | 2658 |  |  | 2832 |  |  | 3002.5 |  |  | 2983 |  |  | 2692 |  |  | 2881 |  |  | 2970 |  |  | 3140.5 |  |  | 2827 |  |  | 2750.5 |  |  | 2852 |  |  | 2929 |  |  | 3098.5 |  |  | 2957 |  |  | 2787 |  |  | 2813.5 |  |  | 2875 |  |  | 2764 |  |  | 2760 |  |  | 3188.5 |  |  | 2854.5 |  |  | 2919 |  |  | 2778 |  |  | 2893.5 |  |  | 2882.5 |  |  | 2831 |  |  | 2962 |  |  | 2950.5 |  |  | 3039.5 |  |  | 2832.5 |  |  | 2900.5 |  |  | 2816.5 |  |  | 3055 |  |  | 2765.5 |  |  | 3006 |  |  | 2784 |  |  | 3012 |  |  | 2996 |  |  | 2823.5 |  |  | 2799 |  |  | 2808 |  |  | 2822.5 |  |  | 2864.5 |  |  | 2740 |  |  | 2920.5 |  |  | 2739.5 |  |  | 2895 |  |  | 2751 |  |  | 2902 |  |  | 2796.5 |  |  | 2874 |  |  | 2887.5 |  |  | 2945 |  |  | 2941 |  |  | 3076.5 |  |  | 2830 |  |  | 3002 |  |  | 2756 |  |  | 2923 |  |  | 3007 |  |  | 2817 |  |  | 2888 |  |  | 2847 |  |  | 2738.5 |  |  | 2773.5 |  |  | 2816 |  |  | 2887.5 |  |  | 2666.5 |  |  | 2801 |  |  | 2787 |  |  | 2855 |  |  | 2881.5 |  |  | 2727.5 |  |  | 2934 |  |  | 2867 |  |  | 2713 |  |  | 2828 |  |  | 2809 |  |  | 2737 |  |  | 2871 |  |  | 2757.5 |  |  | 2931 |  |  | 2993 |  |  | 2983 |  |  | 2725 |  |  | 2726 |  |  | 2805.5 |  |  | 3054.5 |  |  | 2707.5 |  |  | 2744 |  |  | 2817 |  |  | 2735.5 |  |  | 2887.5 |  |  | 2976.5 |  |  | 2780 |  |  | 2948.5 |  |  | 2952.5 |  |  | 2967 |  |  | 2863.5 |  |  | 2916.5 |  |  | 2786 |  |  | 2757 |  |  | 2759 |  |  | 2967 |  |  | 2803 |  |  | 2665 |  |  | 2923 |  |  | 2933 |  |  | 2699 |  |  | 2931 |  |  | 3033.5 |  |  | 2813 |  |  | 2872 |  |  | 2766 |  |  | 2700.5 |  |  | 2782 |  |  | 2896.5 |  |  | 3029 |  |  | 2950 |  |  | 2855 |  |  | 2906 |  |  | 2979.5 |  |  | 2847 |  |  | 2678 |  |  | 2873.5 |  |  | 2887 |  |  | 2733 |  |  | 2765.5 |  |  | 2772.5 |  |  | 2802 |  |  | 2772.5 |  |  | 2925 |  |  | 2738.5 |  |  | 2901 |  |  | 2843 |  |  | 2740.5 |  |  | 2915.5 |  |  | 2894 |  |  | 2873 |  |  | 2851 |  |  | 2817 |  |  | 2777 |  |  | 2842 |  |  | 2710 |  |  | 2761 |  |  | 2950.5 |  |  | 2700 |  |  | 3010.5 |  |  | 2733 |  |  | 2875.5 |  |  | 2821.5 |  |  | 2801 |  |  | 2905 |  |  | 2909.5 |  |  | 2876 |  |  | 2889 |  |  | 2888 |  |  | 2797.5 |  |  | 2914 |  |  | 2719.5 |  |  | 2601 |  |  | 2756 |  |  | 2836 |  |  | 2815 |  |  | 2891.5 |  |  | 2808 |  |  | 2805 |  |  | 2965 |  |  | 2801.5 |  |  | 3026 |  |  | 2923 |  |  | 2970 |  |  | 2877 |  |  | 2912.5 |  |  | 2704.5 |  |  | 3026 |  |  | 2976 |  |  | 2881 |  |  | 2925.5 |  |  | 2860 |  |  | 2704 |  |  | 2766 |  |  | 3012.5 |  |  | 2822.5 |  |  | 2776.5 |  |  | 2942 |  |  | 2878 |  |  | 2904 |  |  | 2795.5 |  |  | 2928 |  |  | 2779.5 |  |  | 2716 |  |  | 2755 |  |  | 2844 |  |  | 2754.5 |  |  | 2940.5 |  |  | 2839 |  |  | 2854 |  |  | 2870.5 |  |  | 2945 |  |  | 2796 |  |  | 2926.5 |  |  | 2731 |  |  | 2684 |  |  | 2883.5 |  |  | 2798 |  |  | 2838 |  |  | 2806.5 |  |  | 2919 |  |  | 2745.5 |  |  | 2823 |  |  | 2675.5 |  |  | 2915.5 |  |  | 2766 |  |  | 2902 |  |  | 3008.5 |  |  | 2785.5 |  |  | 2908 |  |  | 2851 |  |  | 2865 |  |  | 2898.5 |  |  | 2911 |  |  | 2675 |  |  | 2789 |  |  | 2911.5 |  |  | 2871.5 |  |  | 2976 |  |  | 2975 |  |  | 2875 |  |  | 2824 |  |  | 2922 |  |  | 2786 |  |  | 2831 |  |  | 2891.5 |  |  | 3030.5 |  |  | 2688.5 |  |  | 2830 |  |  | 2782.5 |  |  | 2914 |  |  | 2848 |  |  | 2875.5 |  |  | 2715.5 |  |  | 2709 |  |  | 2901 |  |  | 2797.5 |  |  | 2821 |  |  | 2833 |  |  | 2706.5 |  |  | 2909.5 |  |  | 2757 |  |  | 2778 |  |  | 2780 |  |  | 2674.5 |  |  | 2775 |  |  | 2738 |  |  | 2761 |  |  | 2962 |  |  | 2988 |  |  | 2743.5 |  |  | 2910 |  |  | 2880 |  |  | 2730 |  |  | 2988.5 |  |  | 2866 |  |  | 2723.5 |  |  | 2756.5 |  |  | 2774 |  |  | 2990 |  |  | 2877.5 |  |  | 2719.5 |  |  | 2745.5 |  |  | 2852.5 |  |  | 2893.5 |  |  | 2906 |  |  | 2832 |  |  | 2825.5 |  |  | 2807.5 |  |  | 2757 |  |  | 2724 |  |  | 2808.5 |  |  | 3069 |  |  | 2847 |  |  | 2716 |  |  | 2879.5 |  |  | 3025 |  |  | 2764.5 |  |  | 2726 |  |  | 2825.5 |  |  | 3026.5 |  |  | 2942.5 |  |  | 3006 |  |  | 2853 |  |  | 2847.5 |  |  | 2736.5 |  |  | 2907 |  |  | 2805 |  |  | 2896.5 |  |  | 3015 |  |  | 2833.5 |  |  | 2870.5 |  |  | 2807 |  |  | 2860 |  |  | 2673.5 |  |  | 2952.5 |  |  | 2905 |  |  | 2820.5 |  |  | 2842.5 |  |  | 2918 |  |  | 2940 |  |  | 2955 |  |  | 2885.5 |  |  | 2890 |  |  | 2720 |  |  | 2849 |  |  | 2761 |  |  | 2795 |  |  | 2859 |  |  | 3077.5 |  |  | 2891.5 |  |  | 2807 |  |  | 2775 |  |  | 2887 |  |  | 2730.5 |  |  | 2899 |  |  | 2955 |  |  | 2808.5 |  |  | 3035.5 |  |  | 2842 |  |  | 2747.5 |  |  | 2937 |  |  | 2720 |  |  | 2888 |  |  | 2955.5 |  |  | 2966 |  |  | 2710.5 |  |  | 2791.5 |  |  | 2666 |  |  | 2865.5 |  |  | 2655.5 |  |  | 2862 |  |  | 2742 |  |  | 2961 |  |  | 2896.5 |  |  | 2759 |  |  | 2763.5 |  |  | 2961.5 |  |  | 2922 |  |  | 2749.5 |  |  | 2759 |  |  | 2953 |  |  | 2869 |  |  | 2854 |  |  | 2685 |  |  | 2934.5 |  |  | 2844 |  |  | 2948 |  |  | 2823 |  |  | 2926 |  |  | 2831.5 |  |  | 2827.5 |  |  | 2864 |  |  | 2932 |  |  | 2842 |  |  | 2883 |  |  | 2894 |  |  | 2741.5 |  |  | 2810 |  |  | 2960.5 |  |  | 2954 |  |  | 2745 |  |  | 2912 |  |  | 2839 |  |  | 2878.5 |  |  | 2898 |  |  | 2923.5 |  |  | 2739 |  |  | 2972 |  |  | 2892 |  |  | 2868.5 |  |  | 2741 |  |  | 2717 |  |  | 2784 |  |  | 3011 |  |  | 3184 |  |  | 2799.5 |  |  | 2924.5 |  |  | 2752 |  |  | 2714.5 |  |  | 2819 |  |  | 2831.5 |  |  | 2734.5 |  |  | 2846.5 |  |  | 2804.5 |  |  | 2749 |  |  | 2995 |  |  | 2717 |  |  | 2688 |  |  | 2831 |  |  | 2916 |  |  | 2839.5 |  |  | 2769.5 |  |  | 2976.5 |  |  | 2821 |  |  | 2997.5 |  |  | 2744.5 |  |  | 2954.5 |  |  | 2712.5 |  |  | 2849 |  |  | 2841.5 |  |  | 2929.5 |  |  | 2936 |  |  | 2708.5 |  |  | 3018.5 |  |  | 2838.5 |  |  | 3012 |  |  | 2879.5 |  |  | 2936 |  |  | 2860 |  |  | 2843.5 |  |  | 2853.5 |  |  | 2926 |  |  | 3008 |  |  | 2646.5 |  |  | 2715.5 |  |  | 2821.5 |  |  | 2897 |  |  | 2783 |  |  | 2798 |  |  | 2974.5 |  |  | 2858.5 |  |  | 2825 |  |  | 2946.5 |  |  | 2629 |  |  | 2893 |  |  | 2886.5 |  |  | 2741.5 |  |  | 2743 |  |  | 2792.5 |  |  | 2934 |  |  | 2714.5 |  |  | 2940.5 |  |  | 2982 |  |  | 2868.5 |  |  | 2932 |  |  | 2824.5 |  |  | 2846 |  |  | 2889 |  |  | 2882 |  |  | 2800.5 |  |  | 2776.5 |  |  | 2835 |  |  | 2801 |  |  | 2778 |  |  | 2810.5 |  |  | 2884.5 |  |  | 2999 |  |  | 2884.5 |  |  | 2795 |  |  | 2602.5 |  |  | 2924.5 |  |  | 2683 |  |  | 2758 |  |  | 2716 |  |  | 2843.5 |  |  | 2749 |  |  | 2918.5 |  |  | 2793 |  |  | 2845.5 |  |  | 3048 |  |  | 2655.5 |  |  | 2855 |  |  | 2886.5 |  |  | 2844.5 |  |  | 2797 |  |  | 2829 |  |  | 3033 |  |  | 2865 |  |  | 2876.5 |  |  | 2828 |  |  | 2809.5 |  |  | 2691 |  |  | 2781 |  |  | 2839 |  |  | 2990 |  |  | 2943 |  |  | 2918 |  |  | 2946 |  |  | 2815.5 |  |  | 2852 |  |  | 2893
99 |  | 3037.5 |  |  | 3038 |  |  | 3053.5 |  |  | 2918 |  |  | 2816.5 |  |  | 3044 |  |  | 2921 |  |  | 2823 |  |  | 2702.5 |  |  | 2806 |  |  | 2829 |  |  | 2995 |  |  | 2966 |  |  | 3021 |  |  | 2803.5 |  |  | 2921.5 |  |  | 2801 |  |  | 2940 |  |  | 2986 |  |  | 2750.5 |  |  | 2939 |  |  | 2993 |  |  | 2819 |  |  | 2913 |  |  | 2895.5 |  |  | 2961 |  |  | 2789 |  |  | 2905 |  |  | 3031 |  |  | 2739 |  |  | 2831 |  |  | 2791.5 |  |  | 3025.5 |  |  | 2825.5 |  |  | 2856 |  |  | 2872.5 |  |  | 2927.5 |  |  | 2976.5 |  |  | 2954 |  |  | 2918 |  |  | 2772.5 |  |  | 2837 |  |  | 2877.5 |  |  | 2761.5 |  |  | 2859.5 |  |  | 3093.5 |  |  | 2993.5 |  |  | 2839 |  |  | 2680 |  |  | 2820.5 |  |  | 2804 |  |  | 2849.5 |  |  | 2828.5 |  |  | 2910 |  |  | 2790 |  |  | 2775 |  |  | 2780 |  |  | 2959 |  |  | 2874 |  |  | 2887.5 |  |  | 2911.5 |  |  | 2819.5 |  |  | 2842 |  |  | 2939 |  |  | 2715 |  |  | 2807.5 |  |  | 2939 |  |  | 2812.5 |  |  | 2989.5 |  |  | 2983.5 |  |  | 2901 |  |  | 3055 |  |  | 3004 |  |  | 2860.5 |  |  | 3008.5 |  |  | 2805.5 |  |  | 2953.5 |  |  | 2945.5 |  |  | 2933.5 |  |  | 2843.5 |  |  | 2805.5 |  |  | 2668 |  |  | 2981 |  |  | 2825 |  |  | 2975.5 |  |  | 2975 |  |  | 2823.5 |  |  | 2971 |  |  | 2823 |  |  | 2883.5 |  |  | 3021.5 |  |  | 2736 |  |  | 2992 |  |  | 2849.5 |  |  | 3119 |  |  | 2774.5 |  |  | 2933.5 |  |  | 2871.5 |  |  | 2904.5 |  |  | 2777.5 |  |  | 2795 |  |  | 2852 |  |  | 2689 |  |  | 2831.5 |  |  | 2886.5 |  |  | 2935.5 |  |  | 2766.5 |  |  | 2841 |  |  | 2840 |  |  | 2940.5 |  |  | 2832 |  |  | 2957.5 |  |  | 2918 |  |  | 2846 |  |  | 2831.5 |  |  | 2877 |  |  | 2930 |  |  | 2799 |  |  | 2918 |  |  | 2906.5 |  |  | 2916.5 |  |  | 2781.5 |  |  | 3002 |  |  | 2771 |  |  | 2826 |  |  | 2868 |  |  | 2829.5 |  |  | 2903 |  |  | 2918.5 |  |  | 2877 |  |  | 2640 |  |  | 2837.5 |  |  | 2792.5 |  |  | 2769 |  |  | 2826.5 |  |  | 2861 |  |  | 3011 |  |  | 2837 |  |  | 2991 |  |  | 2796 |  |  | 2811 |  |  | 2822 |  |  | 2873 |  |  | 2776 |  |  | 2802.5 |  |  | 2838 |  |  | 2788 |  |  | 2988 |  |  | 2916 |  |  | 2824 |  |  | 2793 |  |  | 2907 |  |  | 2838.5 |  |  | 2866 |  |  | 2908.5 |  |  | 2863 |  |  | 2785 |  |  | 3004.5 |  |  | 2897 |  |  | 3001.5 |  |  | 2785 |  |  | 2667 |  |  | 2900.5 |  |  | 2994 |  |  | 2951.5 |  |  | 3009 |  |  | 2741 |  |  | 2910.5 |  |  | 2898.5 |  |  | 2868 |  |  | 2864.5 |  |  | 2868.5 |  |  | 2840 |  |  | 2972 |  |  | 3108.5 |  |  | 2782.5 |  |  | 2965.5 |  |  | 2932 |  |  | 2941 |  |  | 2878 |  |  | 3033 |  |  | 3013 |  |  | 2880.5 |  |  | 2834 |  |  | 2726.5 |  |  | 2903.5 |  |  | 2868 |  |  | 2947 |  |  | 3148.5 |  |  | 2836.5 |  |  | 2773 |  |  | 2980.5 |  |  | 2745.5 |  |  | 2916 |  |  | 2829 |  |  | 2833 |  |  | 2819.5 |  |  | 2949 |  |  | 2831.5 |  |  | 2970.5 |  |  | 2839 |  |  | 2795.5 |  |  | 2828 |  |  | 2904 |  |  | 2929 |  |  | 3001 |  |  | 2726 |  |  | 2956 |  |  | 3075 |  |  | 2927 |  |  | 2955 |  |  | 2871 |  |  | 2880.5 |  |  | 2977.5 |  |  | 2796 |  |  | 2746 |  |  | 3059 |  |  | 2855.5 |  |  | 2962.5 |  |  | 3039.5 |  |  | 2704 |  |  | 2945 |  |  | 3001.5 |  |  | 2962.5 |  |  | 2732.5 |  |  | 2907 |  |  | 2960 |  |  | 2834 |  |  | 2943 |  |  | 2790 |  |  | 2847.5 |  |  | 2708.5 |  |  | 3006 |  |  | 2836 |  |  | 2816 |  |  | 3008 |  |  | 2805 |  |  | 3033.5 |  |  | 2902 |  |  | 2891 |  |  | 2806 |  |  | 2880 |  |  | 2914.5 |  |  | 2975 |  |  | 2838 |  |  | 2866 |  |  | 2923 |  |  | 3002.5 |  |  | 2834 |  |  | 2808 |  |  | 2820 |  |  | 2942.5 |  |  | 2883.5 |  |  | 2972.5 |  |  | 2984 |  |  | 2871 |  |  | 2764 |  |  | 3052 |  |  | 2800 |  |  | 2805.5 |  |  | 2909 |  |  | 2830.5 |  |  | 2936.5 |  |  | 2906.5 |  |  | 2957 |  |  | 3096.5 |  |  | 2786 |  |  | 2714 |  |  | 2833.5 |  |  | 2863.5 |  |  | 2971 |  |  | 2954.5 |  |  | 3069.5 |  |  | 2841 |  |  | 2971 |  |  | 2782.5 |  |  | 2793.5 |  |  | 3049 |  |  | 2870.5 |  |  | 3001 |  |  | 2899 |  |  | 2833.5 |  |  | 2938 |  |  | 2776 |  |  | 2883.5 |  |  | 2804 |  |  | 2915.5 |  |  | 2898 |  |  | 3086 |  |  | 2951 |  |  | 2844 |  |  | 2971.5 |  |  | 3010 |  |  | 2960.5 |  |  | 2769.5 |  |  | 3046.5 |  |  | 3036 |  |  | 2994.5 |  |  | 3068 |  |  | 2876 |  |  | 2693.5 |  |  | 2799.5 |  |  | 2922 |  |  | 2794.5 |  |  | 3047 |  |  | 2861 |  |  | 3035.5 |  |  | 2783 |  |  | 2877.5 |  |  | 2886.5 |  |  | 2940.5 |  |  | 2914 |  |  | 2736 |  |  | 2764 |  |  | 2785.5 |  |  | 2815 |  |  | 3089.5 |  |  | 2898 |  |  | 2813 |  |  | 2925 |  |  | 2902 |  |  | 2984 |  |  | 2794 |  |  | 2887 |  |  | 3029 |  |  | 2913 |  |  | 2855.5 |  |  | 2987 |  |  | 2857 |  |  | 2975.5 |  |  | 2787.5 |  |  | 2855.5 |  |  | 2807.5 |  |  | 2852 |  |  | 2937 |  |  | 2679.5 |  |  | 3107.5 |  |  | 2840.5 |  |  | 2893 |  |  | 2884 |  |  | 2808 |  |  | 2872 |  |  | 2727 |  |  | 3016 |  |  | 2989 |  |  | 2876.5 |  |  | 2958.5 |  |  | 2782 |  |  | 2771.5 |  |  | 2924.5 |  |  | 2794 |  |  | 2861 |  |  | 2893 |  |  | 2962 |  |  | 2837.5 |  |  | 2756.5 |  |  | 2867.5 |  |  | 2767 |  |  | 2904.5 |  |  | 2987 |  |  | 2883 |  |  | 2925 |  |  | 2746.5 |  |  | 2893 |  |  | 2759 |  |  | 2903.5 |  |  | 2729 |  |  | 2973.5 |  |  | 2984 |  |  | 2899.5 |  |  | 2870 |  |  | 2775.5 |  |  | 2856.5 |  |  | 2982 |  |  | 2940 |  |  | 2663 |  |  | 2952 |  |  | 2701.5 |  |  | 2862 |  |  | 3046 |  |  | 2846.5 |  |  | 2993.5 |  |  | 2643.5 |  |  | 2789 |  |  | 2976.5 |  |  | 3028.5 |  |  | 2801.5 |  |  | 2985 |  |  | 2914 |  |  | 2996.5 |  |  | 2858 |  |  | 3058 |  |  | 2877.5 |  |  | 2911 |  |  | 3012 |  |  | 2931 |  |  | 2740 |  |  | 2745.5 |  |  | 2913.5 |  |  | 2823 |  |  | 3017 |  |  | 2849 |  |  | 2879 |  |  | 2848 |  |  | 2838.5 |  |  | 2829.5 |  |  | 2901 |  |  | 2990 |  |  | 3065 |  |  | 2726.5 |  |  | 3116.5 |  |  | 2800 |  |  | 2944 |  |  | 2714 |  |  | 2946.5 |  |  | 2989.5 |  |  | 2837 |  |  | 2714 |  |  | 2908 |  |  | 2866 |  |  | 2837 |  |  | 2943 |  |  | 2850 |  |  | 3071.5 |  |  | 2895 |  |  | 3060 |  |  | 2885 |  |  | 2971.5 |  |  | 2975 |  |  | 2862 |  |  | 2739 |  |  | 2844 |  |  | 2849 |  |  | 2937 |  |  | 2987 |  |  | 2817.5 |  |  | 2875.5 |  |  | 2730.5 |  |  | 2959 |  |  | 2832 |  |  | 2836.5 |  |  | 2725 |  |  | 2770.5 |  |  | 2874.5 |  |  | 2863 |  |  | 2918 |  |  | 2867.5 |  |  | 2872 |  |  | 2917 |  |  | 2933 |  |  | 2849 |  |  | 2833 |  |  | 2802 |  |  | 2772 |  |  | 2903.5 |  |  | 2832 |  |  | 2980 |  |  | 2959 |  |  | 2910 |  |  | 2867 |  |  | 2892 |  |  | 3002 |  |  | 2921 |  |  | 2908 |  |  | 2948.5 |  |  | 2897.5 |  |  | 2905.5 |  |  | 2914.5 |  |  | 2970 |  |  | 2640 |  |  | 2934.5 |  |  | 2771 |  |  | 2938 |  |  | 2793.5 |  |  | 3018.5 |  |  | 2961 |  |  | 2922.5 |  |  | 2891.5 |  |  | 2697 |  |  | 2968 |  |  | 2838 |  |  | 2921 |  |  | 2841.5 |  |  | 2925 |  |  | 2818.5 |  |  | 2815.5 |  |  | 2900 |  |  | 2863 |  |  | 2921.5 |  |  | 2790 |  |  | 2859.5 |  |  | 2888 |  |  | 2897.5 |  |  | 2824.5 |  |  | 2624.5 |  |  | 3054.5 |  |  | 2911.5 |  |  | 2730 |  |  | 2821 |  |  | 2998.5 |  |  | 2928 |  |  | 2807 |  |  | 2861 |  |  | 3022 |  |  | 3012.5 |  |  | 2688 |  |  | 2814 |  |  | 3027 |  |  | 2872.5 |  |  | 2831 |  |  | 2682 |  |  | 2847 |  |  | 3026.5 |  |  | 3012 |  |  | 2707 |  |  | 2907 |  |  | 2994 |  |  | 3164.5 |  |  | 2866 |  |  | 2774.5 |  |  | 2876 |  |  | 2944 |  |  | 3145.5 |  |  | 2986 |  |  | 2826 |  |  | 2852.5 |  |  | 2904 |  |  | 2803 |  |  | 2775 |  |  | 3209.5 |  |  | 2893.5 |  |  | 2940 |  |  | 2817 |  |  | 2914.5 |  |  | 2929.5 |  |  | 2870 |  |  | 2991 |  |  | 2989.5 |  |  | 3068.5 |  |  | 2871.5 |  |  | 2939.5 |  |  | 2855.5 |  |  | 3084 |  |  | 2794.5 |  |  | 3032 |  |  | 2831 |  |  | 3059 |  |  | 3017 |  |  | 2870.5 |  |  | 2825 |  |  | 2832 |  |  | 2846.5 |  |  | 2885.5 |  |  | 2787 |  |  | 2944.5 |  |  | 2754.5 |  |  | 2919 |  |  | 2798 |  |  | 2941 |  |  | 2822.5 |  |  | 2898 |  |  | 2926.5 |  |  | 2966 |  |  | 2962 |  |  | 3123.5 |  |  | 2869 |  |  | 3041 |  |  | 2795 |  |  | 2938 |  |  | 3031 |  |  | 2832 |  |  | 2909 |  |  | 2871 |  |  | 2785.5 |  |  | 2794.5 |  |  | 2837 |  |  | 2926.5 |  |  | 2687.5 |  |  | 2816 |  |  | 2826 |  |  | 2876 |  |  | 2928.5 |  |  | 2774.5 |  |  | 2973 |  |  | 2893 |  |  | 2752 |  |  | 2857 |  |  | 2835 |  |  | 2766 |  |  | 2892 |  |  | 2796.5 |  |  | 2978 |  |  | 3022 |  |  | 3022 |  |  | 2751 |  |  | 2765 |  |  | 2831.5 |  |  | 3069.5 |  |  | 2746.5 |  |  | 2783 |  |  | 2846 |  |  | 2774.5 |  |  | 2911.5 |  |  | 2991.5 |  |  | 2795 |  |  | 2995.5 |  |  | 2967.5 |  |  | 2982 |  |  | 2902.5 |  |  | 2955.5 |  |  | 2801 |  |  | 2778 |  |  | 2780 |  |  | 2982 |  |  | 2842 |  |  | 2691 |  |  | 2970 |  |  | 2972 |  |  | 2723 |  |  | 2970 |  |  | 3080.5 |  |  | 2852 |  |  | 2911 |  |  | 2805 |  |  | 2724.5 |  |  | 2797 |  |  | 2935.5 |  |  | 3076 |  |  | 2989 |  |  | 2876 |  |  | 2932 |  |  | 3005.5 |  |  | 2871 |  |  | 2699 |  |  | 2920.5 |  |  | 2902 |  |  | 2762 |  |  | 2794.5 |  |  | 2819.5 |  |  | 2841 |  |  | 2801.5 |  |  | 2964 |  |  | 2753.5 |  |  | 2930 |  |  | 2882 |  |  | 2787.5 |  |  | 2941.5 |  |  | 2918 |  |  | 2920 |  |  | 2890 |  |  | 2838 |  |  | 2792 |  |  | 2857 |  |  | 2749 |  |  | 2785 |  |  | 2965.5 |  |  | 2747 |  |  | 3034.5 |  |  | 2748 |  |  | 2922.5 |  |  | 2836.5 |  |  | 2840 |  |  | 2926 |  |  | 2935.5 |  |  | 2923 |  |  | 2913 |  |  | 2927 |  |  | 2812.5 |  |  | 2938 |  |  | 2745.5 |  |  | 2648 |  |  | 2782 |  |  | 2875 |  |  | 2854 |  |  | 2938.5 |  |  | 2823 |  |  | 2831 |  |  | 2994 |  |  | 2827.5 |  |  | 3055 |  |  | 2952 |  |  | 2999 |  |  | 2924 |  |  | 2933.5 |  |  | 2733.5 |  |  | 3055 |  |  | 3002 |  |  | 2907 |  |  | 2972.5 |  |  | 2884 |  |  | 2728 |  |  | 2781 |  |  | 3036.5 |  |  | 2869.5 |  |  | 2815.5 |  |  | 2989 |  |  | 2925 |  |  | 2925 |  |  | 2819.5 |  |  | 2949 |  |  | 2803.5 |  |  | 2745 |  |  | 2781 |  |  | 2870 |  |  | 2780.5 |  |  | 2966.5 |  |  | 2878 |  |  | 2880 |  |  | 2899.5 |  |  | 2966 |  |  | 2835 |  |  | 2947.5 |  |  | 2752 |  |  | 2710 |  |  | 2907.5 |  |  | 2827 |  |  | 2885 |  |  | 2821.5 |  |  | 2948 |  |  | 2766.5 |  |  | 2844 |  |  | 2690.5 |  |  | 2962.5 |  |  | 2781 |  |  | 2928 |  |  | 3034.5 |  |  | 2824.5 |  |  | 2929 |  |  | 2872 |  |  | 2886 |  |  | 2945.5 |  |  | 2926 |  |  | 2699 |  |  | 2828 |  |  | 2926.5 |  |  | 2895.5 |  |  | 2997 |  |  | 3022 |  |  | 2922 |  |  | 2848 |  |  | 2961 |  |  | 2825 |  |  | 2870 |  |  | 2912.5 |  |  | 3054.5 |  |  | 2727.5 |  |  | 2856 |  |  | 2821.5 |  |  | 2943 |  |  | 2887 |  |  | 2901.5 |  |  | 2730.5 |  |  | 2748 |  |  | 2922 |  |  | 2844.5 |  |  | 2860 |  |  | 2848 |  |  | 2753.5 |  |  | 2938.5 |  |  | 2786 |  |  | 2802 |  |  | 2809 |  |  | 2721.5 |  |  | 2814 |  |  | 2764 |  |  | 2800 |  |  | 2988 |  |  | 3012 |  |  | 2772.5 |  |  | 2934 |  |  | 2895 |  |  | 2777 |  |  | 3014.5 |  |  | 2890 |  |  | 2770.5 |  |  | 2771.5 |  |  | 2813 |  |  | 3037 |  |  | 2906.5 |  |  | 2745.5 |  |  | 2766.5 |  |  | 2899.5 |  |  | 2919.5 |  |  | 2921 |  |  | 2871 |  |  | 2854.5 |  |  | 2854.5 |  |  | 2781 |  |  | 2745 |  |  | 2823.5 |  |  | 3116 |  |  | 2876 |  |  | 2742 |  |  | 2905.5 |  |  | 3049 |  |  | 2790.5 |  |  | 2773 |  |  | 2846.5 |  |  | 3052.5 |  |  | 2968.5 |  |  | 3032 |  |  | 2892 |  |  | 2871.5 |  |  | 2765.5 |  |  | 2936 |  |  | 2826 |  |  | 2920.5 |  |  | 3039 |  |  | 2859.5 |  |  | 2894.5 |  |  | 2833 |  |  | 2875 |  |  | 2688.5 |  |  | 2967.5 |  |  | 2920 |  |  | 2859.5 |  |  | 2889.5 |  |  | 2942 |  |  | 2961 |  |  | 2981 |  |  | 2911.5 |  |  | 2929 |  |  | 2744 |  |  | 2875 |  |  | 2782 |  |  | 2816 |  |  | 2888 |  |  | 3098.5 |  |  | 2912.5 |  |  | 2846 |  |  | 2801 |  |  | 2926 |  |  | 2777.5 |  |  | 2923 |  |  | 2984 |  |  | 2834.5 |  |  | 3050.5 |  |  | 2881 |  |  | 2776.5 |  |  | 2952 |  |  | 2759 |  |  | 2903 |  |  | 2994.5 |  |  | 2981 |  |  | 2736.5 |  |  | 2838.5 |  |  | 2687 |  |  | 2880.5 |  |  | 2702.5 |  |  | 2909 |  |  | 2763 |  |  | 3008 |  |  | 2911.5 |  |  | 2806 |  |  | 2792.5 |  |  | 2976.5 |  |  | 2961 |  |  | 2778.5 |  |  | 2798 |  |  | 2992 |  |  | 2916 |  |  | 2883 |  |  | 2709 |  |  | 2963.5 |  |  | 2868 |  |  | 2995 |  |  | 2870 |  |  | 2941 |  |  | 2846.5 |  |  | 2874.5 |  |  | 2911 |  |  | 2961 |  |  | 2889 |  |  | 2904 |  |  | 2933 |  |  | 2762.5 |  |  | 2849 |  |  | 2999.5 |  |  | 2983 |  |  | 2792 |  |  | 2927 |  |  | 2860 |  |  | 2893.5 |  |  | 2927 |  |  | 2944.5 |  |  | 2778 |  |  | 3011 |  |  | 2916 |  |  | 2897.5 |  |  | 2765 |  |  | 2732 |  |  | 2810 |  |  | 3050 |  |  | 3208 |  |  | 2846.5 |  |  | 2950.5 |  |  | 2778 |  |  | 2740.5 |  |  | 2858 |  |  | 2878.5 |  |  | 2781.5 |  |  | 2875.5 |  |  | 2843.5 |  |  | 2773 |  |  | 3034 |  |  | 2743 |  |  | 2727 |  |  | 2870 |  |  | 2942 |  |  | 2865.5 |  |  | 2784.5 |  |  | 3023.5 |  |  | 2860 |  |  | 3036.5 |  |  | 2768.5 |  |  | 2993.5 |  |  | 2727.5 |  |  | 2864 |  |  | 2880.5 |  |  | 2953.5 |  |  | 2965 |  |  | 2755.5 |  |  | 3047.5 |  |  | 2885.5 |  |  | 3038 |  |  | 2894.5 |  |  | 2983 |  |  | 2899 |  |  | 2882.5 |  |  | 2868.5 |  |  | 2955 |  |  | 3034 |  |  | 2670.5 |  |  | 2754.5 |  |  | 2868.5 |  |  | 2918 |  |  | 2809 |  |  | 2819 |  |  | 2998.5 |  |  | 2905.5 |  |  | 2864 |  |  | 2975.5 |  |  | 2644 |  |  | 2908 |  |  | 2907.5 |  |  | 2770.5 |  |  | 2772 |  |  | 2816.5 |  |  | 2973 |  |  | 2740.5 |  |  | 2979.5 |  |  | 3029 |  |  | 2907.5 |  |  | 2956 |  |  | 2871.5 |  |  | 2893 |  |  | 2928 |  |  | 2903 |  |  | 2847.5 |  |  | 2823.5 |  |  | 2856 |  |  | 2825 |  |  | 2825 |  |  | 2831.5 |  |  | 2899.5 |  |  | 3046 |  |  | 2899.5 |  |  | 2842 |  |  | 2641.5 |  |  | 2945.5 |  |  | 2709 |  |  | 2773 |  |  | 2755 |  |  | 2882.5 |  |  | 2788 |  |  | 2942.5 |  |  | 2817 |  |  | 2871.5 |  |  | 3087 |  |  | 2679.5 |  |  | 2870 |  |  | 2925.5 |  |  | 2891.5 |  |  | 2836 |  |  | 2853 |  |  | 3062 |  |  | 2894 |  |  | 2905.5 |  |  | 2852 |  |  | 2830.5 |  |  | 2715 |  |  | 2820 |  |  | 2860 |  |  | 3014 |  |  | 2958 |  |  | 2957 |  |  | 2961 |  |  | 2841.5 |  |  | 2867 |  |  | 2932
100 |  | 3066.5 |  |  | 3059 |  |  | 3100.5 |  |  | 2957 |  |  | 2855.5 |  |  | 3070 |  |  | 2960 |  |  | 2870 |  |  | 2731.5 |  |  | 2845 |  |  | 2844 |  |  | 3021 |  |  | 3005 |  |  | 3068 |  |  | 2829.5 |  |  | 2968.5 |  |  | 2827 |  |  | 2969 |  |  | 3007 |  |  | 2774.5 |  |  | 2963 |  |  | 3008 |  |  | 2834 |  |  | 2960 |  |  | 2916.5 |  |  | 2990 |  |  | 2836 |  |  | 2931 |  |  | 3055 |  |  | 2760 |  |  | 2855 |  |  | 2830.5 |  |  | 3040.5 |  |  | 2872.5 |  |  | 2895 |  |  | 2896.5 |  |  | 2974.5 |  |  | 2991.5 |  |  | 2978 |  |  | 2942 |  |  | 2811.5 |  |  | 2866 |  |  | 2916.5 |  |  | 2790.5 |  |  | 2885.5 |  |  | 3132.5 |  |  | 3032.5 |  |  | 2860 |  |  | 2704 |  |  | 2846.5 |  |  | 2825 |  |  | 2873.5 |  |  | 2843.5 |  |  | 2949 |  |  | 2829 |  |  | 2814 |  |  | 2819 |  |  | 2974 |  |  | 2903 |  |  | 2934.5 |  |  | 2926.5 |  |  | 2845.5 |  |  | 2868 |  |  | 2978 |  |  | 2736 |  |  | 2822.5 |  |  | 2963 |  |  | 2841.5 |  |  | 3015.5 |  |  | 3004.5 |  |  | 2922 |  |  | 3094 |  |  | 3028 |  |  | 2884.5 |  |  | 3029.5 |  |  | 2844.5 |  |  | 2992.5 |  |  | 2971.5 |  |  | 2972.5 |  |  | 2864.5 |  |  | 2844.5 |  |  | 2694 |  |  | 2996 |  |  | 2846 |  |  | 2990.5 |  |  | 3001 |  |  | 2849.5 |  |  | 3018 |  |  | 2862 |  |  | 2898.5 |  |  | 3068.5 |  |  | 2775 |  |  | 3021 |  |  | 2870.5 |  |  | 3140 |  |  | 2813.5 |  |  | 2980.5 |  |  | 2886.5 |  |  | 2930.5 |  |  | 2824.5 |  |  | 2816 |  |  | 2899 |  |  | 2728 |  |  | 2846.5 |  |  | 2933.5 |  |  | 2961.5 |  |  | 2795.5 |  |  | 2862 |  |  | 2855 |  |  | 2979.5 |  |  | 2861 |  |  | 2981.5 |  |  | 2957 |  |  | 2872 |  |  | 2852.5 |  |  | 2924 |  |  | 2945 |  |  | 2838 |  |  | 2942 |  |  | 2953.5 |  |  | 2955.5 |  |  | 2805.5 |  |  | 3023 |  |  | 2786 |  |  | 2850 |  |  | 2897 |  |  | 2876.5 |  |  | 2927 |  |  | 2957.5 |  |  | 2916 |  |  | 2687 |  |  | 2876.5 |  |  | 2807.5 |  |  | 2808 |  |  | 2865.5 |  |  | 2885 |  |  | 3058 |  |  | 2858 |  |  | 3015 |  |  | 2843 |  |  | 2850 |  |  | 2848 |  |  | 2902 |  |  | 2823 |  |  | 2841.5 |  |  | 2877 |  |  | 2812 |  |  | 3003 |  |  | 2940 |  |  | 2853 |  |  | 2814 |  |  | 2936 |  |  | 2867.5 |  |  | 2887 |  |  | 2934.5 |  |  | 2892 |  |  | 2809 |  |  | 3030.5 |  |  | 2936 |  |  | 3030.5 |  |  | 2824 |  |  | 2693 |  |  | 2915.5 |  |  | 3009 |  |  | 2975.5 |  |  | 3048 |  |  | 2770 |  |  | 2931.5 |  |  | 2924.5 |  |  | 2915 |  |  | 2903.5 |  |  | 2892.5 |  |  | 2879 |  |  | 3019 |  |  | 3123.5 |  |  | 2808.5 |  |  | 3004.5 |  |  | 2971 |  |  | 2970 |  |  | 2917 |  |  | 3059 |  |  | 3034 |  |  | 2919.5 |  |  | 2849 |  |  | 2765.5 |  |  | 2918.5 |  |  | 2894 |  |  | 2986 |  |  | 3177.5 |  |  | 2865.5 |  |  | 2812 |  |  | 3004.5 |  |  | 2774.5 |  |  | 2931 |  |  | 2868 |  |  | 2848 |  |  | 2866.5 |  |  | 2988 |  |  | 2855.5 |  |  | 2991.5 |  |  | 2886 |  |  | 2824.5 |  |  | 2867 |  |  | 2951 |  |  | 2944 |  |  | 3040 |  |  | 2741 |  |  | 3003 |  |  | 3122 |  |  | 2942 |  |  | 2970 |  |  | 2897 |  |  | 2919.5 |  |  | 3016.5 |  |  | 2820 |  |  | 2785 |  |  | 3106 |  |  | 2876.5 |  |  | 2983.5 |  |  | 3068.5 |  |  | 2719 |  |  | 2971 |  |  | 3048.5 |  |  | 2988.5 |  |  | 2771.5 |  |  | 2946 |  |  | 2989 |  |  | 2858 |  |  | 2958 |  |  | 2829 |  |  | 2886.5 |  |  | 2747.5 |  |  | 3053 |  |  | 2857 |  |  | 2855 |  |  | 3029 |  |  | 2834 |  |  | 3057.5 |  |  | 2923 |  |  | 2915 |  |  | 2845 |  |  | 2919 |  |  | 2940.5 |  |  | 3001 |  |  | 2853 |  |  | 2905 |  |  | 2962 |  |  | 3049.5 |  |  | 2858 |  |  | 2832 |  |  | 2849 |  |  | 2989.5 |  |  | 2898.5 |  |  | 3019.5 |  |  | 3008 |  |  | 2910 |  |  | 2788 |  |  | 3078 |  |  | 2829 |  |  | 2852.5 |  |  | 2930 |  |  | 2869.5 |  |  | 2951.5 |  |  | 2932.5 |  |  | 2996 |  |  | 3135.5 |  |  | 2825 |  |  | 2729 |  |  | 2862.5 |  |  | 2884.5 |  |  | 3010 |  |  | 2993.5 |  |  | 3108.5 |  |  | 2862 |  |  | 3010 |  |  | 2803.5 |  |  | 2840.5 |  |  | 3070 |  |  | 2909.5 |  |  | 3040 |  |  | 2938 |  |  | 2854.5 |  |  | 2964 |  |  | 2802 |  |  | 2922.5 |  |  | 2851 |  |  | 2944.5 |  |  | 2945 |  |  | 3112 |  |  | 2972 |  |  | 2870 |  |  | 2986.5 |  |  | 3039 |  |  | 2989.5 |  |  | 2784.5 |  |  | 3093.5 |  |  | 3062 |  |  | 3009.5 |  |  | 3115 |  |  | 2915 |  |  | 2732.5 |  |  | 2823.5 |  |  | 2951 |  |  | 2833.5 |  |  | 3073 |  |  | 2900 |  |  | 3059.5 |  |  | 2812 |  |  | 2916.5 |  |  | 2933.5 |  |  | 2961.5 |  |  | 2940 |  |  | 2757 |  |  | 2785 |  |  | 2814.5 |  |  | 2841 |  |  | 3113.5 |  |  | 2919 |  |  | 2852 |  |  | 2964 |  |  | 2926 |  |  | 3013 |  |  | 2823 |  |  | 2934 |  |  | 3053 |  |  | 2952 |  |  | 2879.5 |  |  | 3016 |  |  | 2881 |  |  | 3001.5 |  |  | 2816.5 |  |  | 2894.5 |  |  | 2831.5 |  |  | 2891 |  |  | 2958 |  |  | 2708.5 |  |  | 3128.5 |  |  | 2869.5 |  |  | 2932 |  |  | 2910 |  |  | 2847 |  |  | 2911 |  |  | 2766 |  |  | 3040 |  |  | 3028 |  |  | 2923.5 |  |  | 2979.5 |  |  | 2808 |  |  | 2786.5 |  |  | 2950.5 |  |  | 2820 |  |  | 2908 |  |  | 2917 |  |  | 3009 |  |  | 2876.5 |  |  | 2777.5 |  |  | 2888.5 |  |  | 2796 |  |  | 2943.5 |  |  | 3002 |  |  | 2909 |  |  | 2964 |  |  | 2785.5 |  |  | 2922 |  |  | 2774 |  |  | 2932.5 |  |  | 2758 |  |  | 2997.5 |  |  | 2999 |  |  | 2925.5 |  |  | 2909 |  |  | 2814.5 |  |  | 2871.5 |  |  | 2997 |  |  | 2987 |  |  | 2687 |  |  | 2991 |  |  | 2727.5 |  |  | 2886 |  |  | 3085 |  |  | 2870.5 |  |  | 3019.5 |  |  | 2682.5 |  |  | 2804 |  |  | 3015.5 |  |  | 3043.5 |  |  | 2830.5 |  |  | 3024 |  |  | 2961 |  |  | 3035.5 |  |  | 2897 |  |  | 3105 |  |  | 2924.5 |  |  | 2932 |  |  | 3041 |  |  | 2955 |  |  | 2779 |  |  | 2792.5 |  |  | 2952.5 |  |  | 2870 |  |  | 3064 |  |  | 2888 |  |  | 2900 |  |  | 2887 |  |  | 2885.5 |  |  | 2855.5 |  |  | 2916 |  |  | 3029 |  |  | 3104 |  |  | 2755.5 |  |  | 3155.5 |  |  | 2847 |  |  | 2991 |  |  | 2740 |  |  | 2970.5 |  |  | 3013.5 |  |  | 2876 |  |  | 2729 |  |  | 2947 |  |  | 2892 |  |  | 2852 |  |  | 2958 |  |  | 2865 |  |  | 3100.5 |  |  | 2934 |  |  | 3084 |  |  | 2924 |  |  | 3010.5 |  |  | 2990 |  |  | 2901 |  |  | 2778 |  |  | 2891 |  |  | 2878 |  |  | 2952 |  |  | 3026 |  |  | 2864.5 |  |  | 2896.5 |  |  | 2745.5 |  |  | 2985 |  |  | 2861 |  |  | 2860.5 |  |  | 2764 |  |  | 2809.5 |  |  | 2913.5 |  |  | 2902 |  |  | 2957 |  |  | 2882.5 |  |  | 2896 |  |  | 2932 |  |  | 2948 |  |  | 2870 |  |  | 2854 |  |  | 2823 |  |  | 2811 |  |  | 2950.5 |  |  | 2871 |  |  | 3001 |  |  | 2998 |  |  | 2939 |  |  | 2896 |  |  | 2907 |  |  | 3041 |  |  | 2936 |  |  | 2932 |  |  | 2977.5 |  |  | 2926.5 |  |  | 2920.5 |  |  | 2943.5 |  |  | 3017 |  |  | 2679 |  |  | 2949.5 |  |  | 2800 |  |  | 2953 |  |  | 2832.5 |  |  | 3042.5 |  |  | 2985 |  |  | 2961.5 |  |  | 2938.5 |  |  | 2744 |  |  | 2983 |  |  | 2885 |  |  | 2960 |  |  | 2867.5 |  |  | 2940 |  |  | 2857.5 |  |  | 2841.5 |  |  | 2924 |  |  | 2910 |  |  | 2942.5 |  |  | 2829 |  |  | 2874.5 |  |  | 2914 |  |  | 2926.5 |  |  | 2845.5 |  |  | 2663.5 |  |  | 3069.5 |  |  | 2926.5 |  |  | 2754 |  |  | 2850 |  |  | 3037.5 |  |  | 2949 |  |  | 2833 |  |  | 2876 |  |  | 3048 |  |  | 3051.5 |  |  | 2703 |  |  | 2838 |  |  | 3048 |  |  | 2919.5 |  |  | 2857 |  |  | 2711 |  |  | 2886 |  |  | 3052.5 |  |  | 3059 |  |  | 2754 |  |  | 2954 |  |  | 3023 |  |  | 3190.5 |  |  | 2881 |  |  | 2813.5 |  |  | 2915 |  |  | 2965 |  |  | 3192.5 |  |  | 3033 |  |  | 2841 |  |  | 2891.5 |  |  | 2928 |  |  | 2824 |  |  | 2799 |  |  | 3248.5 |  |  | 2908.5 |  |  | 2987 |  |  | 2856 |  |  | 2961.5 |  |  | 2953.5 |  |  | 2899 |  |  | 3030 |  |  | 3015.5 |  |  | 3092.5 |  |  | 2910.5 |  |  | 2978.5 |  |  | 2881.5 |  |  | 3110 |  |  | 2833.5 |  |  | 3053 |  |  | 2870 |  |  | 3074 |  |  | 3056 |  |  | 2885.5 |  |  | 2872 |  |  | 2871 |  |  | 2870.5 |  |  | 2932.5 |  |  | 2802 |  |  | 2991.5 |  |  | 2793.5 |  |  | 2966 |  |  | 2819 |  |  | 2970 |  |  | 2861.5 |  |  | 2945 |  |  | 2952.5 |  |  | 2990 |  |  | 2983 |  |  | 3162.5 |  |  | 2893 |  |  | 3088 |  |  | 2834 |  |  | 2962 |  |  | 3057 |  |  | 2871 |  |  | 2930 |  |  | 2918 |  |  | 2800.5 |  |  | 2820.5 |  |  | 2852 |  |  | 2965.5 |  |  | 2734.5 |  |  | 2842 |  |  | 2852 |  |  | 2905 |  |  | 2975.5 |  |  | 2795.5 |  |  | 3002 |  |  | 2922 |  |  | 2767 |  |  | 2883 |  |  | 2856 |  |  | 2792 |  |  | 2907 |  |  | 2811.5 |  |  | 3004 |  |  | 3046 |  |  | 3061 |  |  | 2798 |  |  | 2794 |  |  | 2870.5 |  |  | 3095.5 |  |  | 2767.5 |  |  | 2812 |  |  | 2872 |  |  | 2813.5 |  |  | 2958.5 |  |  | 3012.5 |  |  | 2834 |  |  | 3034.5 |  |  | 2996.5 |  |  | 3011 |  |  | 2926.5 |  |  | 2970.5 |  |  | 2822 |  |  | 2817 |  |  | 2795 |  |  | 3021 |  |  | 2868 |  |  | 2738 |  |  | 2999 |  |  | 2987 |  |  | 2747 |  |  | 2996 |  |  | 3109.5 |  |  | 2878 |  |  | 2926 |  |  | 2844 |  |  | 2750.5 |  |  | 2818 |  |  | 2974.5 |  |  | 3091 |  |  | 3015 |  |  | 2891 |  |  | 2971 |  |  | 3026.5 |  |  | 2900 |  |  | 2720 |  |  | 2946.5 |  |  | 2926 |  |  | 2783 |  |  | 2815.5 |  |  | 2866.5 |  |  | 2870 |  |  | 2825.5 |  |  | 2993 |  |  | 2792.5 |  |  | 2969 |  |  | 2921 |  |  | 2802.5 |  |  | 2962.5 |  |  | 2933 |  |  | 2946 |  |  | 2905 |  |  | 2867 |  |  | 2816 |  |  | 2881 |  |  | 2778 |  |  | 2824 |  |  | 2991.5 |  |  | 2794 |  |  | 3063.5 |  |  | 2774 |  |  | 2961.5 |  |  | 2857.5 |  |  | 2855 |  |  | 2955 |  |  | 2959.5 |  |  | 2949 |  |  | 2960 |  |  | 2953 |  |  | 2859.5 |  |  | 2977 |  |  | 2771.5 |  |  | 2674 |  |  | 2806 |  |  | 2901 |  |  | 2893 |  |  | 2964.5 |  |  | 2849 |  |  | 2860 |  |  | 3041 |  |  | 2856.5 |  |  | 3081 |  |  | 2967 |  |  | 3023 |  |  | 2971 |  |  | 2980.5 |  |  | 2772.5 |  |  | 3070 |  |  | 3041 |  |  | 2936 |  |  | 3019.5 |  |  | 2931 |  |  | 2767 |  |  | 2805 |  |  | 3062.5 |  |  | 2908.5 |  |  | 2854.5 |  |  | 3004 |  |  | 2964 |  |  | 2949 |  |  | 2845.5 |  |  | 2996 |  |  | 2842.5 |  |  | 2774 |  |  | 2805 |  |  | 2896 |  |  | 2801.5 |  |  | 2992.5 |  |  | 2899 |  |  | 2927 |  |  | 2938.5 |  |  | 2995 |  |  | 2859 |  |  | 2973.5 |  |  | 2791 |  |  | 2734 |  |  | 2946.5 |  |  | 2866 |  |  | 2924 |  |  | 2860.5 |  |  | 2987 |  |  | 2795.5 |  |  | 2859 |  |  | 2714.5 |  |  | 2986.5 |  |  | 2810 |  |  | 2967 |  |  | 3063.5 |  |  | 2848.5 |  |  | 2944 |  |  | 2896 |  |  | 2933 |  |  | 2974.5 |  |  | 2950 |  |  | 2738 |  |  | 2849 |  |  | 2941.5 |  |  | 2910.5 |  |  | 3012 |  |  | 3051 |  |  | 2937 |  |  | 2872 |  |  | 2982 |  |  | 2851 |  |  | 2917 |  |  | 2938.5 |  |  | 3069.5 |  |  | 2756.5 |  |  | 2895 |  |  | 2847.5 |  |  | 2972 |  |  | 2913 |  |  | 2922.5 |  |  | 2777.5 |  |  | 2763 |  |  | 2943 |  |  | 2883.5 |  |  | 2889 |  |  | 2887 |  |  | 2768.5 |  |  | 2977.5 |  |  | 2825 |  |  | 2841 |  |  | 2848 |  |  | 2747.5 |  |  | 2843 |  |  | 2803 |  |  | 2847 |  |  | 3012 |  |  | 3051 |  |  | 2796.5 |  |  | 2955 |  |  | 2942 |  |  | 2806 |  |  | 3043.5 |  |  | 2919 |  |  | 2809.5 |  |  | 2792.5 |  |  | 2852 |  |  | 3076 |  |  | 2945.5 |  |  | 2769.5 |  |  | 2795.5 |  |  | 2928.5 |  |  | 2940.5 |  |  | 2960 |  |  | 2895 |  |  | 2883.5 |  |  | 2901.5 |  |  | 2820 |  |  | 2784 |  |  | 2852.5 |  |  | 3155 |  |  | 2923 |  |  | 2763 |  |  | 2944.5 |  |  | 3088 |  |  | 2811.5 |  |  | 2797 |  |  | 2893.5 |  |  | 3076.5 |  |  | 2983.5 |  |  | 3058 |  |  | 2921 |  |  | 2897.5 |  |  | 2791.5 |  |  | 2975 |  |  | 2865 |  |  | 2935.5 |  |  | 3078 |  |  | 2880.5 |  |  | 2920.5 |  |  | 2862 |  |  | 2914 |  |  | 2727.5 |  |  | 2991.5 |  |  | 2946 |  |  | 2885.5 |  |  | 2915.5 |  |  | 2957 |  |  | 3000 |  |  | 3020 |  |  | 2937.5 |  |  | 2968 |  |  | 2768 |  |  | 2896 |  |  | 2803 |  |  | 2842 |  |  | 2927 |  |  | 3113.5 |  |  | 2933.5 |  |  | 2885 |  |  | 2848 |  |  | 2952 |  |  | 2801.5 |  |  | 2938 |  |  | 3010 |  |  | 2849.5 |  |  | 3076.5 |  |  | 2907 |  |  | 2802.5 |  |  | 2973 |  |  | 2780 |  |  | 2950 |  |  | 3023.5 |  |  | 3007 |  |  | 2775.5 |  |  | 2885.5 |  |  | 2713 |  |  | 2919.5 |  |  | 2741.5 |  |  | 2933 |  |  | 2792 |  |  | 3047 |  |  | 2937.5 |  |  | 2832 |  |  | 2807.5 |  |  | 3015.5 |  |  | 2987 |  |  | 2807.5 |  |  | 2819 |  |  | 3031 |  |  | 2963 |  |  | 2898 |  |  | 2730 |  |  | 2984.5 |  |  | 2894 |  |  | 3016 |  |  | 2894 |  |  | 2970 |  |  | 2885.5 |  |  | 2898.5 |  |  | 2950 |  |  | 2976 |  |  | 2915 |  |  | 2928 |  |  | 2980 |  |  | 2777.5 |  |  | 2878 |  |  | 3038.5 |  |  | 3022 |  |  | 2818 |  |  | 2966 |  |  | 2889 |  |  | 2917.5 |  |  | 2948 |  |  | 2983.5 |  |  | 2804 |  |  | 3050 |  |  | 2955 |  |  | 2944.5 |  |  | 2794 |  |  | 2779 |  |  | 2831 |  |  | 3089 |  |  | 3247 |  |  | 2875.5 |  |  | 2997.5 |  |  | 2817 |  |  | 2761.5 |  |  | 2879 |  |  | 2925.5 |  |  | 2805.5 |  |  | 2914.5 |  |  | 2872.5 |  |  | 2812 |  |  | 3060 |  |  | 2764 |  |  | 2753 |  |  | 2894 |  |  | 2957 |  |  | 2880.5 |  |  | 2823.5 |  |  | 3044.5 |  |  | 2884 |  |  | 3083.5 |  |  | 2794.5 |  |  | 3032.5 |  |  | 2751.5 |  |  | 2885 |  |  | 2927.5 |  |  | 2992.5 |  |  | 2980 |  |  | 2802.5 |  |  | 3094.5 |  |  | 2924.5 |  |  | 3062 |  |  | 2923.5 |  |  | 3004 |  |  | 2946 |  |  | 2897.5 |  |  | 2892.5 |  |  | 2994 |  |  | 3049 |  |  | 2696.5 |  |  | 2775.5 |  |  | 2894.5 |  |  | 2957 |  |  | 2856 |  |  | 2845 |  |  | 3037.5 |  |  | 2934.5 |  |  | 2888 |  |  | 3004.5 |  |  | 2683 |  |  | 2932 |  |  | 2954.5 |  |  | 2817.5 |  |  | 2787 |  |  | 2837.5 |  |  | 2988 |  |  | 2779.5 |  |  | 3008.5 |  |  | 3044 |  |  | 2928.5 |  |  | 2977 |  |  | 2892.5 |  |  | 2919 |  |  | 2967 |  |  | 2932 |  |  | 2886.5 |  |  | 2838.5 |  |  | 2882 |  |  | 2840 |  |  | 2854 |  |  | 2878.5 |  |  | 2925.5 |  |  | 3093 |  |  | 2938.5 |  |  | 2881 |  |  | 2662.5 |  |  | 2984.5 |  |  | 2748 |  |  | 2812 |  |  | 2781 |  |  | 2911.5 |  |  | 2803 |  |  | 2966.5 |  |  | 2864 |  |  | 2910.5 |  |  | 3108 |  |  | 2705.5 |  |  | 2891 |  |  | 2954.5 |  |  | 2906.5 |  |  | 2883 |  |  | 2868 |  |  | 3083 |  |  | 2920 |  |  | 2926.5 |  |  | 2881 |  |  | 2851.5 |  |  | 2730 |  |  | 2849 |  |  | 2899 |  |  | 3053 |  |  | 2997 |  |  | 2986 |  |  | 2982 |  |  | 2870.5 |  |  | 2896 |  |  | 2958
8.9559 | ← Std. Deviation |  | 62.3594 |  |  | 65.5 |  |  | 62.25 |  |  | 101.25 |  |  | 54.1875 |  |  | 95.7344 |  |  | 45.1875 |  |  | 77.6875 |  |  | 106.7344 |  |  | 89.6875 |  |  | 111.1875 |  |  | 101.25 |  |  | 110.4844 |  |  | 80.7344 |  |  | 64.6875 |  |  | 77.25 |  |  | 101.25 |  |  | 56.8594 |  |  | 74.25 |  |  | 125.4844 |  |  | 106.7344 |  |  | 65.5 |  |  | 103.6875 |  |  | 99.2344 |  |  | 53.4844 |  |  | 97.5 |  |  | 60.2344 |  |  | 43.3594 |  |  | 60.1875 |  |  | 129.1875 |  |  | 72.9844 |  |  | 65.5 |  |  | 103.6875 |  |  | 72.9844 |  |  | 42.6094 |  |  | 114.2344 |  |  | 103.6875 |  |  | 95.8594 |  |  | 79.9844 |  |  | 61.3594 |  |  | 54.1875 |  |  | 43 |  |  | 41.25 |  |  | 61.5 |  |  | 95.7344 |  |  | 125.4844 |  |  | 43.6875 |  |  | 96.1875 |  |  | 61.5 |  |  | 60.1875 |  |  | 61.5 |  |  | 41.4375 |  |  | 42.1094 |  |  | 95.7344 |  |  | 61.3594 |  |  | 97.5 |  |  | 61.3594 |  |  | 99.2344 |  |  | 153.2344 |  |  | 65.1094 |  |  | 108.9844 |  |  | 126.2344 |  |  | 90.4844 |  |  | 129.1875 |  |  | 90.4844 |  |  | 97.5 |  |  | 125.4844 |  |  | 101.25 |  |  | 125.4844 |  |  | 95.7344 |  |  | 97.5 |  |  | 53.1094 |  |  | 53.1094 |  |  | 45.8594 |  |  | 74.25 |  |  | 114.2344 |  |  | 99.2344 |  |  | 41.4375 |  |  | 88.6094 |  |  | 93.6094 |  |  | 103.6875 |  |  | 106.7344 |  |  | 96.1875 |  |  | 65.5 |  |  | 96.1875 |  |  | 64.6875 |  |  | 55.5 |  |  | 45.1875 |  |  | 57.6094 |  |  | 126.2344 |  |  | 90.4844 |  |  | 110.4844 |  |  | 72.9844 |  |  | 125.4844 |  |  | 56.8594 |  |  | 74.25 |  |  | 114.2344 |  |  | 40.9375 |  |  | 126.2344 |  |  | 77.6875 |  |  | 43.3594 |  |  | 56.8594 |  |  | 114.2344 |  |  | 79.9844 |  |  | 125.4844 |  |  | 42.9844 |  |  | 55.6875 |  |  | 80.7344 |  |  | 64.6875 |  |  | 59.8594 |  |  | 95.8594 |  |  | 43.3594 |  |  | 108.9844 |  |  | 111.1875 |  |  | 125.4844 |  |  | 42.1094 |  |  | 79.9844 |  |  | 72.9844 |  |  | 54.1875 |  |  | 110.25 |  |  | 106.7344 |  |  | 96.1875 |  |  | 123.4844 |  |  | 114.2344 |  |  | 111.1875 |  |  | 59.8594 |  |  | 65.1094 |  |  | 43.2344 |  |  | 96.1875 |  |  | 76.1875 |  |  | 92.1094 |  |  | 128.4844 |  |  | 41.4375 |  |  | 41.5 |  |  | 53.4844 |  |  | 60.2344 |  |  | 41.4375 |  |  | 59.8594 |  |  | 108.9844 |  |  | 43.6094 |  |  | 53.5 |  |  | 78.2344 |  |  | 125.4844 |  |  | 77.6875 |  |  | 59.8594 |  |  | 65.4844 |  |  | 57.6094 |  |  | 64.6875 |  |  | 101.25 |  |  | 77.6875 |  |  | 65.1094 |  |  | 114.2344 |  |  | 79.9844 |  |  | 62.25 |  |  | 65.1094 |  |  | 125.4844 |  |  | 65.4844 |  |  | 125.4844 |  |  | 56.8594 |  |  | 82.9844 |  |  | 129.1875 |  |  | 65.5 |  |  | 129.1875 |  |  | 56.8594 |  |  | 90.4844 |  |  | 45 |  |  | 95.7344 |  |  | 108.9844 |  |  | 60.2344 |  |  | 76.1875 |  |  | 123.4844 |  |  | 68.3594 |  |  | 72.9844 |  |  | 80.7344 |  |  | 64.6875 |  |  | 61.5 |  |  | 61.5 |  |  | 43 |  |  | 110.25 |  |  | 77.6875 |  |  | 43.3594 |  |  | 47.1094 |  |  | 125.4844 |  |  | 53.4844 |  |  | 90.4844 |  |  | 65.5 |  |  | 59.8594 |  |  | 41.4375 |  |  | 61.5 |  |  | 47.1094 |  |  | 55.5 |  |  | 103.6875 |  |  | 88.6094 |  |  | 101.25 |  |  | 64.6875 |  |  | 125.4844 |  |  | 60.1875 |  |  | 43.6094 |  |  | 89.6875 |  |  | 129.1875 |  |  | 103.6875 |  |  | 74.25 |  |  | 61.2344 |  |  | 95.7344 |  |  | 99.2344 |  |  | 57.6094 |  |  | 78.2344 |  |  | 78.2344 |  |  | 62.3594 |  |  | 53.5 |  |  | 95.8594 |  |  | 111.1875 |  |  | 126.2344 |  |  | 76.1875 |  |  | 64.6875 |  |  | 43 |  |  | 126.25 |  |  | 77.25 |  |  | 80.7344 |  |  | 108.9844 |  |  | 110.25 |  |  | 125.4844 |  |  | 111.1875 |  |  | 65.1094 |  |  | 95.8594 |  |  | 95.8594 |  |  | 44.6875 |  |  | 95.7344 |  |  | 103.6875 |  |  | 110.4844 |  |  | 111.1875 |  |  | 54.1875 |  |  | 78.2344 |  |  | 43 |  |  | 76.1875 |  |  | 43.3594 |  |  | 56.8594 |  |  | 77.6875 |  |  | 92.1094 |  |  | 129.1875 |  |  | 65.1094 |  |  | 65.5 |  |  | 46.3594 |  |  | 106.7344 |  |  | 45.1875 |  |  | 56.8594 |  |  | 97.5 |  |  | 61.5 |  |  | 106.7344 |  |  | 106.7344 |  |  | 61.2344 |  |  | 110.4844 |  |  | 65.5 |  |  | 65.5 |  |  | 125.4844 |  |  | 65.5 |  |  | 82.9844 |  |  | 126.2344 |  |  | 96.1875 |  |  | 61.5 |  |  | 114.2344 |  |  | 43.3594 |  |  | 78.2344 |  |  | 68.3594 |  |  | 72.9844 |  |  | 99.2344 |  |  | 91.5 |  |  | 61.3594 |  |  | 60.1875 |  |  | 54.1094 |  |  | 60.2344 |  |  | 125.4844 |  |  | 82.9844 |  |  | 47.1094 |  |  | 108.9844 |  |  | 59.8594 |  |  | 53.1094 |  |  | 77.25 |  |  | 43.3594 |  |  | 74.25 |  |  | 45 |  |  | 61.5 |  |  | 129.1875 |  |  | 55.6875 |  |  | 42.9844 |  |  | 77.6875 |  |  | 125.4844 |  |  | 125.4844 |  |  | 88.6094 |  |  | 90.4844 |  |  | 77.6875 |  |  | 72.9844 |  |  | 111.1875 |  |  | 77.25 |  |  | 103.6875 |  |  | 106.7344 |  |  | 135.2344 |  |  | 95.7344 |  |  | 101.25 |  |  | 153.2344 |  |  | 77.6875 |  |  | 45.1875 |  |  | 77.25 |  |  | 125.4844 |  |  | 55.5 |  |  | 65.4844 |  |  | 135.2344 |  |  | 126.2344 |  |  | 64.6875 |  |  | 101.25 |  |  | 74.25 |  |  | 91.5 |  |  | 56.8594 |  |  | 82.9844 |  |  | 111.1875 |  |  | 41.4375 |  |  | 65.5 |  |  | 65.1094 |  |  | 77.6875 |  |  | 45.1875 |  |  | 41.25 |  |  | 111.1875 |  |  | 125.4844 |  |  | 45 |  |  | 41.4375 |  |  | 61.3594 |  |  | 45 |  |  | 42.9844 |  |  | 45 |  |  | 129.1875 |  |  | 77.25 |  |  | 129.1875 |  |  | 101.25 |  |  | 42.6094 |  |  | 125.4844 |  |  | 45.1875 |  |  | 76.1875 |  |  | 82.9844 |  |  | 82.9844 |  |  | 59.8594 |  |  | 126.2344 |  |  | 106.7344 |  |  | 65.4844 |  |  | 43.6094 |  |  | 55.5 |  |  | 61.3594 |  |  | 45 |  |  | 103.6875 |  |  | 128.4844 |  |  | 89.6875 |  |  | 45.1875 |  |  | 72.9844 |  |  | 103.6875 |  |  | 110.4844 |  |  | 52.6094 |  |  | 111.1875 |  |  | 79.9844 |  |  | 77.6875 |  |  | 99.2344 |  |  | 93.6094 |  |  | 103.6875 |  |  | 106.7344 |  |  | 125.4844 |  |  | 76.1875 |  |  | 52.6094 |  |  | 92.1094 |  |  | 106.7344 |  |  | 60.2344 |  |  | 95.7344 |  |  | 60.1875 |  |  | 80.7344 |  |  | 55.5 |  |  | 61.3594 |  |  | 72.9844 |  |  | 61.5 |  |  | 65.5 |  |  | 46.3594 |  |  | 80.7344 |  |  | 43.2344 |  |  | 97.5 |  |  | 78.2344 |  |  | 95.7344 |  |  | 60.1875 |  |  | 68.3594 |  |  | 65.5 |  |  | 110.25 |  |  | 79.9844 |  |  | 61.5 |  |  | 65.1094 |  |  | 54.1875 |  |  | 54.1875 |  |  | 126.25 |  |  | 77.25 |  |  | 114.2344 |  |  | 74.25 |  |  | 125.4844 |  |  | 55.5 |  |  | 106.7344 |  |  | 55.5 |  |  | 41.5 |  |  | 80.7344 |  |  | 53.5 |  |  | 47.1094 |  |  | 64.6875 |  |  | 45.1875 |  |  | 110.25 |  |  | 95.7344 |  |  | 108.9844 |  |  | 60.2344 |  |  | 60.2344 |  |  | 99.2344 |  |  | 108.9844 |  |  | 43.3594 |  |  | 110.25 |  |  | 90.4844 |  |  | 74.25 |  |  | 103.6875 |  |  | 53.4844 |  |  | 108.9844 |  |  | 106.7344 |  |  | 68.3594 |  |  | 43.3594 |  |  | 43.3594 |  |  | 90.4844 |  |  | 64.6875 |  |  | 106.7344 |  |  | 55.5 |  |  | 91.5 |  |  | 52.6094 |  |  | 55.6875 |  |  | 61.3594 |  |  | 90.4844 |  |  | 61.5 |  |  | 95.8594 |  |  | 68.3594 |  |  | 43.3594 |  |  | 110.4844 |  |  | 65.5 |  |  | 74.25 |  |  | 57.6094 |  |  | 57.6094 |  |  | 80.7344 |  |  | 78.2344 |  |  | 61.3594 |  |  | 67.2344 |  |  | 64.6875 |  |  | 96.1875 |  |  | 108.9844 |  |  | 65.1094 |  |  | 96.1875 |  |  | 78.2344 |  |  | 45.1875 |  |  | 43.2344 |  |  | 135.2344 |  |  | 106.7344 |  |  | 41.4375 |  |  | 95.7344 |  |  | 56.8594 |  |  | 64.6875 |  |  | 78.2344 |  |  | 72.9844 |  |  | 82.9844 |  |  | 60.1875 |  |  | 106.7344 |  |  | 103.6875 |  |  | 74.25 |  |  | 53.5 |  |  | 108.9844 |  |  | 103.6875 |  |  | 135.2344 |  |  | 106.7344 |  |  | 77.25 |  |  | 101.25 |  |  | 53.5 |  |  | 126.2344 |  |  | 43.6875 |  |  | 61.3594 |  |  | 72.9844 |  |  | 62.25 |  |  | 60.1875 |  |  | 42.6094 |  |  | 110.25 |  |  | 103.6875 |  |  | 62.3594 |  |  | 95.7344 |  |  | 95.7344 |  |  | 65.1094 |  |  | 64.6875 |  |  | 55.5 |  |  | 101.25 |  |  | 90.4844 |  |  | 95.7344 |  |  | 55.5 |  |  | 59.8594 |  |  | 42.1094 |  |  | 60.2344 |  |  | 99.2344 |  |  | 64.6875 |  |  | 76.1875 |  |  | 95.8594 |  |  | 110.4844 |  |  | 76.1875 |  |  | 148.2344 |  |  | 95.8594 |  |  | 126.25 |  |  | 59.8594 |  |  | 61.3594 |  |  | 77.25 |  |  | 74.25 |  |  | 79.9844 |  |  | 62.3594 |  |  | 56.8594 |  |  | 106.7344 |  |  | 126.25 |  |  | 45.1875 |  |  | 61.3594 |  |  | 61.5 |  |  | 128.4844 |  |  | 41.4375 |  |  | 61.3594 |  |  | 108.9844 |  |  | 65.5 |  |  | 128.4844 |  |  | 43.6875 |  |  | 76.1875 |  |  | 101.1094 |  |  | 61.3594 |  |  | 79.9844 |  |  | 74.25 |  |  | 62.25 |  |  | 61.5 |  |  | 92.1094 |  |  | 67.2344 |  |  | 91.5 |  |  | 72.9844 |  |  | 53.1094 |  |  | 76.1875 |  |  | 106.7344 |  |  | 95.7344 |  |  | 55.5 |  |  | 54.1094 |  |  | 80.7344 |  |  | 72.9844 |  |  | 78.2344 |  |  | 110.4844 |  |  | 59.8594 |  |  | 65.5 |  |  | 59.8594 |  |  | 77.6875 |  |  | 78.2344 |  |  | 68.3594 |  |  | 106.7344 |  |  | 53.4844 |  |  | 125.4844 |  |  | 55.5 |  |  | 47.1094 |  |  | 82.9844 |  |  | 77.25 |  |  | 125.4844 |  |  | 108.9844 |  |  | 95.7344 |  |  | 65.1094 |  |  | 65.5 |  |  | 80.7344 |  |  | 90.4844 |  |  | 64.6875 |  |  | 103.6875 |  |  | 77.25 |  |  | 123.4844 |  |  | 78.2344 |  |  | 126.2344 |  |  | 108.9844 |  |  | 76.1875 |  |  | 46.3594 |  |  | 111.1875 |  |  | 110.4844 |  |  | 56.8594 |  |  | 65.1094 |  |  | 96.1875 |  |  | 45 |  |  | 126.25 |  |  | 110.4844 |  |  | 101.1094 |  |  | 77.6875 |  |  | 61.5 |  |  | 61.3594 |  |  | 78.2344 |  |  | 91.5 |  |  | 95.7344 |  |  | 106.7344 |  |  | 61.5 |  |  | 106.7344 |  |  | 62.25 |  |  | 106.7344 |  |  | 101.1094 |  |  | 43.6094 |  |  | 60.1875 |  |  | 99.2344 |  |  | 65.5 |  |  | 106.7344 |  |  | 77.25 |  |  | 96.1875 |  |  | 99.2344 |  |  | 43.2344 |  |  | 110.25 |  |  | 78.2344 |  |  | 91.5 |  |  | 88.6094 |  |  | 53.5 |  |  | 103.6875 |  |  | 77.6875 |  |  | 41.25 |  |  | 108.9844 |  |  | 55.5 |  |  | 55.5 |  |  | 52.6094 |  |  | 82.9844 |  |  | 82.9844 |  |  | 95.8594 |  |  | 95.8594 |  |  | 80.7344 |  |  | 43.2344 |  |  | 126.25 |  |  | 110.25 |  |  | 64.6875 |  |  | 126.25 |  |  | 99.2344 |  |  | 90.4844 |  |  | 43 |  |  | 44.6875 |  |  | 43.3594 |  |  | 99.2344 |  |  | 45 |  |  | 65.5 |  |  | 128.4844 |  |  | 129.1875 |  |  | 77.25 |  |  | 80.7344 |  |  | 43.3594 |  |  | 61.5 |  |  | 41.5 |  |  | 47.1094 |  |  | 125.4844 |  |  | 46.3594 |  |  | 43.6094 |  |  | 91.5 |  |  | 55.5 |  |  | 82.9844 |  |  | 78.2344 |  |  | 60.1875 |  |  | 99.2344 |  |  | 55.5 |  |  | 54.1094 |  |  | 47.1094 |  |  | 43.2344 |  |  | 45.1875 |  |  | 53.5 |  |  | 60.1875 |  |  | 60.1875 |  |  | 72.9844 |  |  | 79.9844 |  |  | 60.1875 |  |  | 77.25 |  |  | 64.6875 |  |  | 110.4844 |  |  | 111.1875 |  |  | 126.25 |  |  | 129.1875 |  |  | 74.25 |  |  | 62.25 |  |  | 77.6875 |  |  | 54.1875 |  |  | 60.2344 |  |  | 68.3594 |  |  | 76.1875 |  |  | 59.8594 |  |  | 93.6094 |  |  | 108.9844 |  |  | 103.6875 |  |  | 101.1094 |  |  | 74.25 |  |  | 43.3594 |  |  | 77.6875 |  |  | 77.6875 |  |  | 110.4844 |  |  | 54.1875 |  |  | 103.6875 |  |  | 62.3594 |  |  | 125.4844 |  |  | 78.2344 |  |  | 45 |  |  | 62.3594 |  |  | 96.1875 |  |  | 77.25 |  |  | 76.1875 |  |  | 55.5 |  |  | 74.25 |  |  | 80.7344 |  |  | 90.4844 |  |  | 55.6875 |  |  | 53.5 |  |  | 68.3594 |  |  | 91.5 |  |  | 72.9844 |  |  | 64.6875 |  |  | 82.9844 |  |  | 80.7344 |  |  | 90.4844 |  |  | 47.1094 |  |  | 95.7344 |  |  | 74.25 |  |  | 111.1875 |  |  | 43 |  |  | 106.7344 |  |  | 90.4844 |  |  | 62.25 |  |  | 88.6094 |  |  | 79.9844 |  |  | 65.1094 |  |  | 43.2344 |  |  | 74.25 |  |  | 61.3594 |  |  | 76.1875 |  |  | 54.1094 |  |  | 60.1875 |  |  | 88.6094 |  |  | 45 |  |  | 126.2344 |  |  | 110.25 |  |  | 89.6875 |  |  | 43 |  |  | 61.3594 |  |  | 54.1875 |  |  | 47.1094 |  |  | 111.1875 |  |  | 90.4844 |  |  | 55.6875 |  |  | 65.5 |  |  | 61.3594 |  |  | 64.6875 |  |  | 103.6875 |  |  | 60.1875 |  |  | 108.9844 |  |  | 97.5 |  |  | 103.6875 |  |  | 110.4844 |  |  | 78.2344 |  |  | 106.7344 |  |  | 55.5 |  |  | 90.4844 |  |  | 99.2344 |  |  | 77.6875 |  |  | 111.1875 |  |  | 65.5 |  |  | 43.6875 |  |  | 114.2344 |  |  | 77.25 |  |  | 79.9844 |  |  | 103.6875 |  |  | 80.7344 |  |  | 95.7344 |  |  | 74.25 |  |  | 77.25 |  |  | 45 |  |  | 53.5 |  |  | 54.1094 |  |  | 45 |  |  | 123.4844 |  |  | 126.2344 |  |  | 64.6875 |  |  | 114.2344 |  |  | 41.4375 |  |  | 72.9844 |  |  | 82.9844 |  |  | 80.7344 |  |  | 99.2344 |  |  | 77.6875 |  |  | 80.7344 |  |  | 42.6094 |  |  | 61.2344 |  |  | 125.4844 |  |  | 43.3594 |  |  | 106.7344 |  |  | 80.7344 |  |  | 45.1875 |  |  | 43.6875 |  |  | 64.6875 |  |  | 101.1094 |  |  | 95.7344 |  |  | 99.2344 |  |  | 65.4844 |  |  | 78.2344 |  |  | 64.6875 |  |  | 99.2344 |  |  | 77.6875 |  |  | 65.5 |  |  | 79.9844 |  |  | 99.2344 |  |  | 103.6875 |  |  | 43 |  |  | 77.25 |  |  | 43.3594 |  |  | 64.6875 |  |  | 82.9844 |  |  | 125.4844 |  |  | 65.1094 |  |  | 43.6875 |  |  | 43.6094 |  |  | 43 |  |  | 108.9844 |  |  | 76.1875 |  |  | 99.2344 |  |  | 77.6875 |  |  | 78.2344 |  |  | 96.1875 |  |  | 54.1094 |  |  | 74.25 |  |  | 76.1875 |  |  | 42.1094 |  |  | 103.6875 |  |  | 45 |  |  | 91.5 |  |  | 60.2344 |  |  | 56.8594 |  |  | 153.2344 |  |  | 82.9844 |  |  | 56.8594 |  |  | 61.3594 |  |  | 43.3594 |  |  | 95.7344 |  |  | 64.6875 |  |  | 110.4844 |  |  | 56.8594 |  |  | 62.3594 |  |  | 74.25 |  |  | 42.6094 |  |  | 101.1094 |  |  | 43.3594 |  |  | 99.2344 |  |  | 42.6094 |  |  | 123.4844 |  |  | 95.7344 |  |  | 90.4844 |  |  | 80.7344 |  |  | 72.9844 |  |  | 72.9844 |  |  | 111.1875 |  |  | 65.1094 |  |  | 42.6094 |  |  | 79.9844 |  |  | 79.9844 |  |  | 103.6875 |  |  | 45.1875 |  |  | 60.1875 |  |  | 108.9844 |  |  | 79.9844 |  |  | 56.8594 |  |  | 45.1875 |  |  | 65.4844 |  |  | 101.25 |  |  | 95.7344 |  |  | 80.7344 |  |  | 54.1875 |  |  | 74.25 |  |  | 61.3594 |  |  | 43.6094 |  |  | 42.9844 |  |  | 106.7344 |  |  | 54.1094 |  |  | 76.1875 |  |  | 65.5 |  |  | 45 |  |  | 126.2344 |  |  | 72.9844 |  |  | 90.4844 |  |  | 99.2344 |  |  | 80.7344 |  |  | 110.25 |  |  | 106.7344 |  |  | 54.1094 |  |  | 78.2344 |  |  | 65.5 |  |  | 99.2344 |  |  | 52.6094 |  |  | 88.6094 |  |  | 79.9844 |  |  | 61.3594 |  |  | 56.8594 |  |  | 82.9844 |  |  | 95.8594 |  |  | 78.2344 |  |  | 54.1875 |  |  | 128.4844 |  |  | 92.1094 |  |  | 103.6875 |  |  | 42.6094 |  |  | 53.1094 |  |  | 65.1094 |  |  | 64.6875 |  |  | 110.4844 |  |  | 43.6875 |  |  | 110.25 |  |  | 61.3594 |  |  | 45 |  |  | 103.6875 |  |  | 110.4844 |  |  | 65.1094 |  |  | 55.5 |  |  | 54.1094 |  |  | 99.2344 |  |  | 129.1875 |  |  | 60.2344 |  |  | 108.9844 |  |  | 129.1875 |  |  | 76.1875 |  |  | 60.1875 |  |  | 61.5 |  |  | 57.6094 |  |  | 111.1875 |  |  | 43.3594 |  |  | 106.7344 |  |  | 72.9844 |  |  | 46.3594 |  |  | 95.7344 |  |  | 108.9844 |  |  | 99.2344 |  |  | 74.25 |  |  | 72.9844 |  |  | 72.9844 |  |  | 99.2344 |  |  | 76.1875 |  |  | 95.8594 |  |  | 72.9844 |  |  | 65.5 |  |  | 80.7344 |  |  | 55.6875 |  |  | 54.1094 |  |  | 61.3594 |  |  | 60.2344 |  |  | 65.1094 |  |  | 53.1094 |  |  | 43.2344 |  |  | 97.5 |  |  | 97.5 |  |  | 42.1094 |  |  | 74.25 |  |  | 59.8594 |  |  | 97.5 |  |  | 77.6875 |  |  | 103.6875 |  |  | 111.1875 |  |  | 44.6875 |  |  | 125.4844 |  |  | 79.9844 |  |  | 59.8594 |  |  | 96.1875 |  |  | 72.9844 |  |  | 95.7344 |  |  | 61.3594 |  |  | 77.25 |  |  | 53.5 |  |  | 74.25 |  |  | 90.4844 |  |  | 62.3594 |  |  | 77.6875 |  |  | 78.2344 |  |  | 60.2344 |  |  | 43.3594 |  |  | 65.5 |  |  | 41.25 |  |  | 101.1094 |  |  | 123.4844 |  |  | 103.6875 |  |  | 108.9844 |  |  | 53.5 |  |  | 79.9844 |  |  | 43.2344 |  |  | 106.7344 |  |  | 42.6094 |  |  | 108.9844 |  |  | 56.8594 |  |  | 62.3594 |  |  | 114.2344 |  |  | 68.3594 |  |  | 53.1094 |  |  | 65.4844 |  |  | 54.1094 |  |  | 52.6094 |  |  | 54.1094 |  |  | 72.9844 |  |  | 54.1094 |  |  | 103.6875 |  |  | 61.5 |  |  | 61.5 |  |  | 125.4844 |  |  | 61.5 |  |  | 59.8594 |  |  | 79.9844 |  |  | 78.2344 |  |  | 52.6094
27.3 | ← Mean |  | 26.875 |  |  | 26.5 |  |  | 23 |  |  | 30 |  |  | 23.75 |  |  | 27.625 |  |  | 25.25 |  |  | 25.75 |  |  | 31.625 |  |  | 28.75 |  |  | 26.75 |  |  | 30 |  |  | 27.375 |  |  | 28.375 |  |  | 26.75 |  |  | 26 |  |  | 30 |  |  | 24.125 |  |  | 29 |  |  | 28.625 |  |  | 31.625 |  |  | 26.5 |  |  | 29.75 |  |  | 30.375 |  |  | 24.375 |  |  | 27.5 |  |  | 27.375 |  |  | 25.125 |  |  | 27.75 |  |  | 30.75 |  |  | 29.375 |  |  | 26.5 |  |  | 29.75 |  |  | 29.375 |  |  | 25.875 |  |  | 26.375 |  |  | 29.75 |  |  | 28.125 |  |  | 25.375 |  |  | 27.125 |  |  | 23.75 |  |  | 26.5 |  |  | 25.5 |  |  | 27.5 |  |  | 27.625 |  |  | 28.625 |  |  | 26.25 |  |  | 27.75 |  |  | 27.5 |  |  | 27.75 |  |  | 27.5 |  |  | 25.25 |  |  | 26.125 |  |  | 27.625 |  |  | 27.125 |  |  | 27.5 |  |  | 27.125 |  |  | 30.375 |  |  | 29.625 |  |  | 27.125 |  |  | 29.375 |  |  | 25.625 |  |  | 24.625 |  |  | 30.75 |  |  | 28.375 |  |  | 27.5 |  |  | 28.625 |  |  | 30 |  |  | 28.625 |  |  | 27.625 |  |  | 27.5 |  |  | 24.125 |  |  | 24.125 |  |  | 23.875 |  |  | 29 |  |  | 26.375 |  |  | 30.375 |  |  | 25.25 |  |  | 29.125 |  |  | 27.875 |  |  | 29.75 |  |  | 31.625 |  |  | 27.75 |  |  | 26.5 |  |  | 27.75 |  |  | 26.75 |  |  | 24.5 |  |  | 25.25 |  |  | 25.125 |  |  | 25.625 |  |  | 24.625 |  |  | 27.375 |  |  | 29.375 |  |  | 28.625 |  |  | 24.125 |  |  | 29 |  |  | 26.375 |  |  | 25.75 |  |  | 25.625 |  |  | 25.75 |  |  | 25.125 |  |  | 24.125 |  |  | 26.375 |  |  | 25.375 |  |  | 28.625 |  |  | 25.625 |  |  | 24.75 |  |  | 28.375 |  |  | 26.75 |  |  | 28.125 |  |  | 28.125 |  |  | 25.125 |  |  | 29.375 |  |  | 26.75 |  |  | 28.625 |  |  | 26.125 |  |  | 25.375 |  |  | 29.375 |  |  | 23.75 |  |  | 27 |  |  | 31.625 |  |  | 27.75 |  |  | 31.375 |  |  | 26.375 |  |  | 26.75 |  |  | 28.125 |  |  | 27.125 |  |  | 24.625 |  |  | 27.75 |  |  | 28.75 |  |  | 28.125 |  |  | 32.625 |  |  | 25.25 |  |  | 25 |  |  | 24.375 |  |  | 27.375 |  |  | 25.25 |  |  | 28.125 |  |  | 29.375 |  |  | 26.875 |  |  | 23.5 |  |  | 26.375 |  |  | 28.625 |  |  | 25.75 |  |  | 28.125 |  |  | 23.375 |  |  | 25.125 |  |  | 26.75 |  |  | 30 |  |  | 25.75 |  |  | 27.125 |  |  | 26.375 |  |  | 25.375 |  |  | 23 |  |  | 27.125 |  |  | 28.625 |  |  | 23.375 |  |  | 28.625 |  |  | 24.125 |  |  | 30.625 |  |  | 30.75 |  |  | 26.5 |  |  | 30.75 |  |  | 24.125 |  |  | 24.625 |  |  | 25.5 |  |  | 27.625 |  |  | 29.375 |  |  | 27.375 |  |  | 28.75 |  |  | 31.375 |  |  | 26.125 |  |  | 29.375 |  |  | 28.375 |  |  | 26.75 |  |  | 27.5 |  |  | 27.5 |  |  | 26.5 |  |  | 27 |  |  | 25.75 |  |  | 24.875 |  |  | 24.875 |  |  | 28.625 |  |  | 24.375 |  |  | 24.625 |  |  | 26.5 |  |  | 28.125 |  |  | 25.25 |  |  | 27.5 |  |  | 24.875 |  |  | 24.5 |  |  | 29.75 |  |  | 29.125 |  |  | 30 |  |  | 26.75 |  |  | 28.625 |  |  | 27.75 |  |  | 26.875 |  |  | 28.75 |  |  | 30.75 |  |  | 29.75 |  |  | 29 |  |  | 22.375 |  |  | 27.625 |  |  | 30.375 |  |  | 25.125 |  |  | 26.375 |  |  | 26.375 |  |  | 26.875 |  |  | 23.5 |  |  | 28.125 |  |  | 26.75 |  |  | 25.625 |  |  | 28.75 |  |  | 26.75 |  |  | 26.5 |  |  | 31 |  |  | 26 |  |  | 28.375 |  |  | 29.375 |  |  | 27 |  |  | 28.625 |  |  | 26.75 |  |  | 27.125 |  |  | 28.125 |  |  | 28.125 |  |  | 24.25 |  |  | 27.625 |  |  | 29.75 |  |  | 27.375 |  |  | 26.75 |  |  | 23.75 |  |  | 26.375 |  |  | 26.5 |  |  | 28.75 |  |  | 25.125 |  |  | 24.125 |  |  | 25.75 |  |  | 28.125 |  |  | 30.75 |  |  | 27.125 |  |  | 26.5 |  |  | 25.875 |  |  | 31.625 |  |  | 25.25 |  |  | 24.125 |  |  | 27.5 |  |  | 27.5 |  |  | 31.625 |  |  | 31.625 |  |  | 22.375 |  |  | 27.375 |  |  | 26.5 |  |  | 26.5 |  |  | 28.625 |  |  | 26.5 |  |  | 30.625 |  |  | 25.625 |  |  | 27.75 |  |  | 27.5 |  |  | 26.375 |  |  | 24.875 |  |  | 26.375 |  |  | 26.125 |  |  | 29.375 |  |  | 30.375 |  |  | 28.5 |  |  | 27.125 |  |  | 27.75 |  |  | 23.125 |  |  | 27.375 |  |  | 28.625 |  |  | 30.625 |  |  | 24.875 |  |  | 29.375 |  |  | 28.125 |  |  | 24.125 |  |  | 26 |  |  | 25.125 |  |  | 29 |  |  | 24.5 |  |  | 27.5 |  |  | 30.75 |  |  | 24.75 |  |  | 25.625 |  |  | 25.75 |  |  | 28.625 |  |  | 28.625 |  |  | 29.125 |  |  | 28.375 |  |  | 25.75 |  |  | 29.375 |  |  | 26.75 |  |  | 26 |  |  | 29.75 |  |  | 31.625 |  |  | 30.375 |  |  | 27.625 |  |  | 30 |  |  | 29.625 |  |  | 25.75 |  |  | 25.25 |  |  | 26 |  |  | 28.625 |  |  | 24.5 |  |  | 23.375 |  |  | 30.375 |  |  | 25.625 |  |  | 26.75 |  |  | 30 |  |  | 29 |  |  | 28.5 |  |  | 24.125 |  |  | 30.625 |  |  | 26.75 |  |  | 25.25 |  |  | 26.5 |  |  | 27.125 |  |  | 25.75 |  |  | 25.25 |  |  | 25.5 |  |  | 26.75 |  |  | 28.625 |  |  | 25.5 |  |  | 25.25 |  |  | 27.125 |  |  | 25.5 |  |  | 25.625 |  |  | 24.5 |  |  | 30.75 |  |  | 26 |  |  | 30.75 |  |  | 30 |  |  | 25.875 |  |  | 28.625 |  |  | 25.25 |  |  | 28.75 |  |  | 30.625 |  |  | 30.625 |  |  | 28.125 |  |  | 25.625 |  |  | 31.625 |  |  | 23.375 |  |  | 26.875 |  |  | 24.5 |  |  | 27.125 |  |  | 25.5 |  |  | 29.75 |  |  | 32.625 |  |  | 28.75 |  |  | 25.25 |  |  | 29.375 |  |  | 29.75 |  |  | 27.375 |  |  | 23.875 |  |  | 26.75 |  |  | 25.375 |  |  | 25.75 |  |  | 30.375 |  |  | 27.875 |  |  | 29.75 |  |  | 31.625 |  |  | 28.625 |  |  | 28.75 |  |  | 23.875 |  |  | 28.125 |  |  | 31.625 |  |  | 27.375 |  |  | 27.625 |  |  | 27.75 |  |  | 28.375 |  |  | 24.5 |  |  | 27.125 |  |  | 29.375 |  |  | 27.5 |  |  | 26.5 |  |  | 25.875 |  |  | 28.375 |  |  | 24.625 |  |  | 27.5 |  |  | 26.375 |  |  | 27.625 |  |  | 27.75 |  |  | 26.125 |  |  | 26.5 |  |  | 27 |  |  | 25.375 |  |  | 27.5 |  |  | 27.125 |  |  | 23.75 |  |  | 23.75 |  |  | 31 |  |  | 26 |  |  | 26.375 |  |  | 29 |  |  | 28.625 |  |  | 24.5 |  |  | 31.625 |  |  | 24.5 |  |  | 25 |  |  | 28.375 |  |  | 23.5 |  |  | 24.875 |  |  | 26.75 |  |  | 25.25 |  |  | 27 |  |  | 27.625 |  |  | 29.375 |  |  | 27.375 |  |  | 27.375 |  |  | 30.375 |  |  | 29.375 |  |  | 24.875 |  |  | 27 |  |  | 28.375 |  |  | 29 |  |  | 29.75 |  |  | 24.375 |  |  | 29.375 |  |  | 31.625 |  |  | 26.125 |  |  | 24.875 |  |  | 24.875 |  |  | 24.625 |  |  | 26.75 |  |  | 31.625 |  |  | 24.5 |  |  | 28.5 |  |  | 23.875 |  |  | 24.75 |  |  | 27.125 |  |  | 28.375 |  |  | 27.5 |  |  | 28.125 |  |  | 26.125 |  |  | 24.875 |  |  | 27.375 |  |  | 26.5 |  |  | 29 |  |  | 25.125 |  |  | 25.125 |  |  | 28.375 |  |  | 26.375 |  |  | 27.125 |  |  | 21.625 |  |  | 26.75 |  |  | 27.75 |  |  | 29.375 |  |  | 27.125 |  |  | 27.75 |  |  | 26.375 |  |  | 25.25 |  |  | 24.625 |  |  | 30.375 |  |  | 31.625 |  |  | 25.25 |  |  | 27.625 |  |  | 24.125 |  |  | 26.75 |  |  | 26.375 |  |  | 29.375 |  |  | 30.625 |  |  | 27.75 |  |  | 31.625 |  |  | 29.75 |  |  | 29 |  |  | 23.5 |  |  | 29.375 |  |  | 29.75 |  |  | 30.375 |  |  | 31.625 |  |  | 26 |  |  | 30 |  |  | 23.5 |  |  | 25.625 |  |  | 26.25 |  |  | 27.125 |  |  | 29.375 |  |  | 23 |  |  | 27.75 |  |  | 25.875 |  |  | 27 |  |  | 29.75 |  |  | 26.875 |  |  | 27.625 |  |  | 27.625 |  |  | 27.125 |  |  | 26.75 |  |  | 24.5 |  |  | 30 |  |  | 24.625 |  |  | 27.625 |  |  | 24.5 |  |  | 28.125 |  |  | 26.125 |  |  | 27.375 |  |  | 30.375 |  |  | 26.75 |  |  | 28.75 |  |  | 28.125 |  |  | 27.375 |  |  | 28.75 |  |  | 33.625 |  |  | 28.125 |  |  | 31 |  |  | 28.125 |  |  | 27.125 |  |  | 26 |  |  | 29 |  |  | 25.375 |  |  | 26.875 |  |  | 24.125 |  |  | 31.625 |  |  | 31 |  |  | 25.25 |  |  | 27.125 |  |  | 27.5 |  |  | 32.625 |  |  | 25.25 |  |  | 27.125 |  |  | 29.375 |  |  | 26.5 |  |  | 32.625 |  |  | 26.25 |  |  | 28.75 |  |  | 27.125 |  |  | 27.125 |  |  | 25.375 |  |  | 29 |  |  | 23 |  |  | 27.5 |  |  | 28.125 |  |  | 21.625 |  |  | 28.5 |  |  | 29.375 |  |  | 24.125 |  |  | 28.75 |  |  | 31.625 |  |  | 27.625 |  |  | 24.5 |  |  | 23.125 |  |  | 28.375 |  |  | 29.375 |  |  | 26.375 |  |  | 27.375 |  |  | 28.125 |  |  | 26.5 |  |  | 28.125 |  |  | 25.75 |  |  | 26.375 |  |  | 26.125 |  |  | 31.625 |  |  | 24.375 |  |  | 28.625 |  |  | 24.5 |  |  | 24.875 |  |  | 30.625 |  |  | 26 |  |  | 28.625 |  |  | 29.375 |  |  | 27.625 |  |  | 27.125 |  |  | 26.5 |  |  | 28.375 |  |  | 28.375 |  |  | 26.75 |  |  | 29.75 |  |  | 26 |  |  | 31.375 |  |  | 26.375 |  |  | 25.625 |  |  | 29.375 |  |  | 28.75 |  |  | 25.875 |  |  | 26.75 |  |  | 27.375 |  |  | 24.125 |  |  | 27.125 |  |  | 27.75 |  |  | 25.5 |  |  | 31 |  |  | 27.375 |  |  | 27.125 |  |  | 25.75 |  |  | 27.5 |  |  | 27.125 |  |  | 26.375 |  |  | 28.5 |  |  | 27.625 |  |  | 31.625 |  |  | 27.5 |  |  | 31.625 |  |  | 23 |  |  | 31.625 |  |  | 27.125 |  |  | 26.875 |  |  | 27.75 |  |  | 30.375 |  |  | 26.5 |  |  | 31.625 |  |  | 26 |  |  | 27.75 |  |  | 30.375 |  |  | 24.625 |  |  | 27 |  |  | 26.375 |  |  | 28.5 |  |  | 29.125 |  |  | 23.5 |  |  | 29.75 |  |  | 25.75 |  |  | 25.5 |  |  | 29.375 |  |  | 24.5 |  |  | 24.5 |  |  | 23.875 |  |  | 30.625 |  |  | 30.625 |  |  | 28.125 |  |  | 28.125 |  |  | 28.375 |  |  | 24.625 |  |  | 31 |  |  | 27 |  |  | 26.75 |  |  | 31 |  |  | 30.375 |  |  | 24.625 |  |  | 26.5 |  |  | 24.25 |  |  | 25.125 |  |  | 30.375 |  |  | 25.5 |  |  | 26.5 |  |  | 32.625 |  |  | 30.75 |  |  | 26 |  |  | 28.375 |  |  | 24.875 |  |  | 27.5 |  |  | 25 |  |  | 24.875 |  |  | 28.625 |  |  | 25.875 |  |  | 26.875 |  |  | 28.5 |  |  | 24.5 |  |  | 30.625 |  |  | 26.375 |  |  | 27.75 |  |  | 30.375 |  |  | 24.5 |  |  | 23.125 |  |  | 24.875 |  |  | 24.625 |  |  | 25.25 |  |  | 23.5 |  |  | 27.75 |  |  | 27.75 |  |  | 29.375 |  |  | 25.375 |  |  | 27.75 |  |  | 26 |  |  | 26.75 |  |  | 27.375 |  |  | 26.75 |  |  | 31 |  |  | 30.75 |  |  | 29 |  |  | 23 |  |  | 25.75 |  |  | 23.75 |  |  | 27.375 |  |  | 26.125 |  |  | 28.75 |  |  | 28.125 |  |  | 27.875 |  |  | 29.375 |  |  | 29.75 |  |  | 27.125 |  |  | 29 |  |  | 24.875 |  |  | 25.75 |  |  | 25.75 |  |  | 27.375 |  |  | 23.75 |  |  | 29.75 |  |  | 26.875 |  |  | 28.625 |  |  | 26.375 |  |  | 25.5 |  |  | 26.875 |  |  | 27.75 |  |  | 26 |  |  | 28.75 |  |  | 24.5 |  |  | 29 |  |  | 28.375 |  |  | 28.375 |  |  | 24.75 |  |  | 23.5 |  |  | 26.125 |  |  | 28.5 |  |  | 29.375 |  |  | 26.75 |  |  | 30.625 |  |  | 28.375 |  |  | 28.375 |  |  | 24.875 |  |  | 27.625 |  |  | 29 |  |  | 26.75 |  |  | 26.5 |  |  | 31.625 |  |  | 28.375 |  |  | 23 |  |  | 29.125 |  |  | 25.375 |  |  | 27.125 |  |  | 24.625 |  |  | 29 |  |  | 27.125 |  |  | 28.75 |  |  | 23.125 |  |  | 27.75 |  |  | 29.125 |  |  | 25.5 |  |  | 25.625 |  |  | 27 |  |  | 28.75 |  |  | 26.5 |  |  | 27.125 |  |  | 23.75 |  |  | 24.875 |  |  | 26.75 |  |  | 28.375 |  |  | 24.75 |  |  | 26.5 |  |  | 27.125 |  |  | 26.75 |  |  | 29.75 |  |  | 27.75 |  |  | 29.375 |  |  | 27.5 |  |  | 29.75 |  |  | 27.375 |  |  | 26.375 |  |  | 31.625 |  |  | 24.5 |  |  | 24.625 |  |  | 30.375 |  |  | 25.75 |  |  | 26.75 |  |  | 26.5 |  |  | 26.25 |  |  | 26.375 |  |  | 26 |  |  | 25.375 |  |  | 29.75 |  |  | 28.375 |  |  | 27.625 |  |  | 29 |  |  | 26 |  |  | 25.5 |  |  | 23.5 |  |  | 23.125 |  |  | 25.5 |  |  | 31.375 |  |  | 25.625 |  |  | 26.75 |  |  | 26.375 |  |  | 25.25 |  |  | 29.375 |  |  | 30.625 |  |  | 28.375 |  |  | 30.375 |  |  | 25.75 |  |  | 28.375 |  |  | 25.875 |  |  | 22.375 |  |  | 28.625 |  |  | 24.875 |  |  | 31.625 |  |  | 28.375 |  |  | 25.25 |  |  | 26.25 |  |  | 26.75 |  |  | 27.125 |  |  | 27.625 |  |  | 30.375 |  |  | 23.375 |  |  | 26.375 |  |  | 26.75 |  |  | 30.375 |  |  | 25.75 |  |  | 26.5 |  |  | 25.375 |  |  | 30.375 |  |  | 29.75 |  |  | 26.5 |  |  | 26 |  |  | 24.875 |  |  | 26.75 |  |  | 30.625 |  |  | 28.625 |  |  | 27.125 |  |  | 26.25 |  |  | 26.875 |  |  | 26.5 |  |  | 29.375 |  |  | 28.75 |  |  | 30.375 |  |  | 25.75 |  |  | 26.375 |  |  | 27.75 |  |  | 23.125 |  |  | 29 |  |  | 28.75 |  |  | 26.125 |  |  | 29.75 |  |  | 25.5 |  |  | 28.5 |  |  | 27.375 |  |  | 24.125 |  |  | 29.625 |  |  | 30.625 |  |  | 24.125 |  |  | 27.125 |  |  | 24.875 |  |  | 27.625 |  |  | 26.75 |  |  | 27.375 |  |  | 24.125 |  |  | 26.875 |  |  | 29 |  |  | 25.875 |  |  | 27.125 |  |  | 24.875 |  |  | 30.375 |  |  | 25.875 |  |  | 31.375 |  |  | 27.625 |  |  | 28.375 |  |  | 28.375 |  |  | 29.375 |  |  | 29.375 |  |  | 26.75 |  |  | 27.125 |  |  | 25.875 |  |  | 25.375 |  |  | 25.375 |  |  | 29.75 |  |  | 25.25 |  |  | 27.75 |  |  | 29.375 |  |  | 25.375 |  |  | 24.125 |  |  | 25.25 |  |  | 23.375 |  |  | 30 |  |  | 27.625 |  |  | 28.375 |  |  | 23.75 |  |  | 29 |  |  | 27.125 |  |  | 26.875 |  |  | 25.625 |  |  | 31.625 |  |  | 23.125 |  |  | 28.75 |  |  | 26.5 |  |  | 24.5 |  |  | 25.625 |  |  | 29.375 |  |  | 28.375 |  |  | 30.375 |  |  | 28.375 |  |  | 27 |  |  | 31.625 |  |  | 23.125 |  |  | 26.375 |  |  | 26.5 |  |  | 30.375 |  |  | 23.875 |  |  | 29.125 |  |  | 25.375 |  |  | 27.125 |  |  | 24.125 |  |  | 30.625 |  |  | 28.125 |  |  | 26.375 |  |  | 23.75 |  |  | 32.625 |  |  | 28.125 |  |  | 29.75 |  |  | 25.875 |  |  | 24.125 |  |  | 27.125 |  |  | 26.75 |  |  | 27.375 |  |  | 26.25 |  |  | 27 |  |  | 27.125 |  |  | 25.5 |  |  | 29.75 |  |  | 27.375 |  |  | 27.125 |  |  | 24.5 |  |  | 23.125 |  |  | 30.375 |  |  | 30.75 |  |  | 27.375 |  |  | 29.375 |  |  | 30.75 |  |  | 28.75 |  |  | 27.75 |  |  | 27.5 |  |  | 25.125 |  |  | 26.75 |  |  | 25.125 |  |  | 31.625 |  |  | 29.375 |  |  | 25.875 |  |  | 27.625 |  |  | 29.375 |  |  | 30.375 |  |  | 29 |  |  | 29.375 |  |  | 29.375 |  |  | 30.375 |  |  | 28.75 |  |  | 28.125 |  |  | 29.375 |  |  | 26.5 |  |  | 28.375 |  |  | 24.75 |  |  | 23.125 |  |  | 27.125 |  |  | 27.375 |  |  | 27.125 |  |  | 24.125 |  |  | 24.625 |  |  | 27.5 |  |  | 27.5 |  |  | 26.125 |  |  | 29 |  |  | 28.125 |  |  | 27.5 |  |  | 25.75 |  |  | 29.75 |  |  | 26.75 |  |  | 24.25 |  |  | 28.625 |  |  | 25.375 |  |  | 28.125 |  |  | 27.75 |  |  | 29.375 |  |  | 27.625 |  |  | 27.125 |  |  | 26 |  |  | 23.5 |  |  | 29 |  |  | 24.625 |  |  | 26.875 |  |  | 25.75 |  |  | 26.375 |  |  | 27.375 |  |  | 24.875 |  |  | 26.5 |  |  | 25.5 |  |  | 27.125 |  |  | 31.375 |  |  | 29.75 |  |  | 29.375 |  |  | 23.5 |  |  | 25.375 |  |  | 24.625 |  |  | 31.625 |  |  | 25.875 |  |  | 29.375 |  |  | 24.125 |  |  | 26.875 |  |  | 26.375 |  |  | 26.125 |  |  | 24.125 |  |  | 23.375 |  |  | 23.125 |  |  | 23.875 |  |  | 23.125 |  |  | 29.375 |  |  | 23.125 |  |  | 29.75 |  |  | 27.5 |  |  | 27.5 |  |  | 28.625 |  |  | 27.5 |  |  | 28.125 |  |  | 25.375 |  |  | 26.375 |  |  | 23.875
Version 1.2 – © 2021-2025, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Note on B2: This simulation model uses 1000 trials to simulate future sprints. Then, all forecast date calculations are made based upon the stastistics calculated from 1000 trials.
Note on B3: This is a random number between 1 and the count of all historical Scrum sprints entered in the SPERT Bootstrap Scrum worksheet. This random number result will then be used to resample the sprint history for use with future sprints. The actual sprint history may be adjusted when used in a future sprint if the Team % capacity is something other than 100%. For example, if the number in this column is 9, then the team's 9th sprint will be used to simulate the performance of a future Scrum sprint.
Note on C3: The random number cacluated in the cell to the left is used to resample the Scrum sprint history for use with a future sprint. However, for Iterations 1 and later, the Result calculation will be the actual team history, not a resampled value. Only future sprints will have their values resampled from the team's actual sprint history. Therefore, the values in the Result column will, at first, mirror the team's actual team history exactly. Only future sprints will be simulated through a process of resampling from the team's historical "Done" record. Values in the Result column are used for all the forecast date calculations on the Bootstrap Scrum worksheet. The values in the Result column reflect any changes to the Team % capacity to work (<> 100%).
Note on D3: William W. Davis: The Base column shows either the actual team history for prior Scrum sprints (Iteration 1 and later until the last historical entry was made in the Bootstrap Scrum worksheet), or it shows a randomly selected resampled value from the team's history as a possible outcome for the team's future performance. The Base value is not adjusted in future sprints for changes to the Team % capacity to work (the Result column does this, however). All forecasted dates are based on the Result column, not directly from the Base column.
Note on B207: This simulation model uses 1000 trials to simulate future iterations. Then, all forecast date calculations are made based upon the stastistics calculated from 1000 trials.
Note on B208: This is a random number between 1 and the count of all historical Kanban sprints entered in the SPERT Bootstrap Kanban worksheet. This random number result will then be used to resample the iteration history for use with future iterations The actual iteration history may be adjusted when used in a future iteration if the Team % capacity is something other than 100%. For example, if the number in this column is 9, then the team's 9th iteration will be used to simulate the performance of a future Kanban iteration.
Note on C208: The random number cacluated in the cell to the left is used to resample the Kanban iteration history for use with a future iteration. However, for Iterations 1 and later, the Result calculation will be the actual team history, not a resampled value. Only future iterations will have their values resampled from the team's actual iteration history. Therefore, the values in the Result column will, at first, mirror the team's actual team history exactly. Only future iterations will be simulated through a process of resampling from the team's historical "Done" record. Values in the Result column are used for all the forecast date calculations on the Bootstrap Kanban worksheet. The values in the Result column reflect any changes to the Team % capacity to work (<> 100%).
Note on D208: The Base column shows either the actual team history for prior Kanban iterations (Iteration 1 and later until the last historical entry was made in the Bootstrap Kanban worksheet), or it shows a randomly selected resampled value from the team's history as a possible outcome for the team's future performance. The Base value is not adjusted in future iterations for changes to the Team % capacity to work (the Result column does this, however). All forecasted dates are based on the Result column, not directly from the Base column.

## Vlookups
Statistical PERT® (SPERT®) Bootstrap Edition Vlookups
For the Bootstrap Scrum worksheet
ID | Simulation Row Start | Simulation Row End
1 | BootstrapData!C105 | BootstrapData!DKK105
2 | BootstrapData!C106 | BootstrapData!DKK106
3 | BootstrapData!C107 | BootstrapData!DKK107
4 | BootstrapData!C108 | BootstrapData!DKK108
5 | BootstrapData!C109 | BootstrapData!DKK109
6 | BootstrapData!C110 | BootstrapData!DKK110
7 | BootstrapData!C111 | BootstrapData!DKK111
8 | BootstrapData!C112 | BootstrapData!DKK112
9 | BootstrapData!C113 | BootstrapData!DKK113
10 | BootstrapData!C114 | BootstrapData!DKK114
11 | BootstrapData!C115 | BootstrapData!DKK115
12 | BootstrapData!C116 | BootstrapData!DKK116
13 | BootstrapData!C117 | BootstrapData!DKK117
14 | BootstrapData!C118 | BootstrapData!DKK118
15 | BootstrapData!C119 | BootstrapData!DKK119
16 | BootstrapData!C120 | BootstrapData!DKK120
17 | BootstrapData!C121 | BootstrapData!DKK121
18 | BootstrapData!C122 | BootstrapData!DKK122
19 | BootstrapData!C123 | BootstrapData!DKK123
20 | BootstrapData!C124 | BootstrapData!DKK124
21 | BootstrapData!C125 | BootstrapData!DKK125
22 | BootstrapData!C126 | BootstrapData!DKK126
23 | BootstrapData!C127 | BootstrapData!DKK127
24 | BootstrapData!C128 | BootstrapData!DKK128
25 | BootstrapData!C129 | BootstrapData!DKK129
26 | BootstrapData!C130 | BootstrapData!DKK130
27 | BootstrapData!C131 | BootstrapData!DKK131
28 | BootstrapData!C132 | BootstrapData!DKK132
29 | BootstrapData!C133 | BootstrapData!DKK133
30 | BootstrapData!C134 | BootstrapData!DKK134
31 | BootstrapData!C135 | BootstrapData!DKK135
32 | BootstrapData!C136 | BootstrapData!DKK136
33 | BootstrapData!C137 | BootstrapData!DKK137
34 | BootstrapData!C138 | BootstrapData!DKK138
35 | BootstrapData!C139 | BootstrapData!DKK139
36 | BootstrapData!C140 | BootstrapData!DKK140
37 | BootstrapData!C141 | BootstrapData!DKK141
38 | BootstrapData!C142 | BootstrapData!DKK142
39 | BootstrapData!C143 | BootstrapData!DKK143
40 | BootstrapData!C144 | BootstrapData!DKK144
41 | BootstrapData!C145 | BootstrapData!DKK145
42 | BootstrapData!C146 | BootstrapData!DKK146
43 | BootstrapData!C147 | BootstrapData!DKK147
44 | BootstrapData!C148 | BootstrapData!DKK148
45 | BootstrapData!C149 | BootstrapData!DKK149
46 | BootstrapData!C150 | BootstrapData!DKK150
47 | BootstrapData!C151 | BootstrapData!DKK151
48 | BootstrapData!C152 | BootstrapData!DKK152
49 | BootstrapData!C153 | BootstrapData!DKK153
50 | BootstrapData!C154 | BootstrapData!DKK154
51 | BootstrapData!C155 | BootstrapData!DKK155
52 | BootstrapData!C156 | BootstrapData!DKK156
53 | BootstrapData!C157 | BootstrapData!DKK157
54 | BootstrapData!C158 | BootstrapData!DKK158
55 | BootstrapData!C159 | BootstrapData!DKK159
56 | BootstrapData!C160 | BootstrapData!DKK160
57 | BootstrapData!C161 | BootstrapData!DKK161
58 | BootstrapData!C162 | BootstrapData!DKK162
59 | BootstrapData!C163 | BootstrapData!DKK163
60 | BootstrapData!C164 | BootstrapData!DKK164
61 | BootstrapData!C165 | BootstrapData!DKK165
62 | BootstrapData!C166 | BootstrapData!DKK166
63 | BootstrapData!C167 | BootstrapData!DKK167
64 | BootstrapData!C168 | BootstrapData!DKK168
65 | BootstrapData!C169 | BootstrapData!DKK169
66 | BootstrapData!C170 | BootstrapData!DKK170
67 | BootstrapData!C171 | BootstrapData!DKK171
68 | BootstrapData!C172 | BootstrapData!DKK172
69 | BootstrapData!C173 | BootstrapData!DKK173
70 | BootstrapData!C174 | BootstrapData!DKK174
71 | BootstrapData!C175 | BootstrapData!DKK175
72 | BootstrapData!C176 | BootstrapData!DKK176
73 | BootstrapData!C177 | BootstrapData!DKK177
74 | BootstrapData!C178 | BootstrapData!DKK178
75 | BootstrapData!C179 | BootstrapData!DKK179
76 | BootstrapData!C180 | BootstrapData!DKK180
77 | BootstrapData!C181 | BootstrapData!DKK181
78 | BootstrapData!C182 | BootstrapData!DKK182
79 | BootstrapData!C183 | BootstrapData!DKK183
80 | BootstrapData!C184 | BootstrapData!DKK184
81 | BootstrapData!C185 | BootstrapData!DKK185
82 | BootstrapData!C186 | BootstrapData!DKK186
83 | BootstrapData!C187 | BootstrapData!DKK187
84 | BootstrapData!C188 | BootstrapData!DKK188
85 | BootstrapData!C189 | BootstrapData!DKK189
86 | BootstrapData!C190 | BootstrapData!DKK190
87 | BootstrapData!C191 | BootstrapData!DKK191
88 | BootstrapData!C192 | BootstrapData!DKK192
89 | BootstrapData!C193 | BootstrapData!DKK193
90 | BootstrapData!C194 | BootstrapData!DKK194
91 | BootstrapData!C195 | BootstrapData!DKK195
92 | BootstrapData!C196 | BootstrapData!DKK196
93 | BootstrapData!C197 | BootstrapData!DKK197
94 | BootstrapData!C198 | BootstrapData!DKK198
95 | BootstrapData!C199 | BootstrapData!DKK199
96 | BootstrapData!C200 | BootstrapData!DKK200
97 | BootstrapData!C201 | BootstrapData!DKK201
98 | BootstrapData!C202 | BootstrapData!DKK202
99 | BootstrapData!C203 | BootstrapData!DKK203
100 | BootstrapData!C204 | BootstrapData!DKK204
For the Bootstrap Kanban worksheet
ID | Simulation Row Start | Simulation Row End
1 | BootstrapData!C310 | BootstrapData!DKK310
2 | BootstrapData!C311 | BootstrapData!DKK311
3 | BootstrapData!C312 | BootstrapData!DKK312
4 | BootstrapData!C313 | BootstrapData!DKK313
5 | BootstrapData!C314 | BootstrapData!DKK314
6 | BootstrapData!C315 | BootstrapData!DKK315
7 | BootstrapData!C316 | BootstrapData!DKK316
8 | BootstrapData!C317 | BootstrapData!DKK317
9 | BootstrapData!C318 | BootstrapData!DKK318
10 | BootstrapData!C319 | BootstrapData!DKK319
11 | BootstrapData!C320 | BootstrapData!DKK320
12 | BootstrapData!C321 | BootstrapData!DKK321
13 | BootstrapData!C322 | BootstrapData!DKK322
14 | BootstrapData!C323 | BootstrapData!DKK323
15 | BootstrapData!C324 | BootstrapData!DKK324
16 | BootstrapData!C325 | BootstrapData!DKK325
17 | BootstrapData!C326 | BootstrapData!DKK326
18 | BootstrapData!C327 | BootstrapData!DKK327
19 | BootstrapData!C328 | BootstrapData!DKK328
20 | BootstrapData!C329 | BootstrapData!DKK329
21 | BootstrapData!C330 | BootstrapData!DKK330
22 | BootstrapData!C331 | BootstrapData!DKK331
23 | BootstrapData!C332 | BootstrapData!DKK332
24 | BootstrapData!C333 | BootstrapData!DKK333
25 | BootstrapData!C334 | BootstrapData!DKK334
26 | BootstrapData!C335 | BootstrapData!DKK335
27 | BootstrapData!C336 | BootstrapData!DKK336
28 | BootstrapData!C337 | BootstrapData!DKK337
29 | BootstrapData!C338 | BootstrapData!DKK338
30 | BootstrapData!C339 | BootstrapData!DKK339
31 | BootstrapData!C340 | BootstrapData!DKK340
32 | BootstrapData!C341 | BootstrapData!DKK341
33 | BootstrapData!C342 | BootstrapData!DKK342
34 | BootstrapData!C343 | BootstrapData!DKK343
35 | BootstrapData!C344 | BootstrapData!DKK344
36 | BootstrapData!C345 | BootstrapData!DKK345
37 | BootstrapData!C346 | BootstrapData!DKK346
38 | BootstrapData!C347 | BootstrapData!DKK347
39 | BootstrapData!C348 | BootstrapData!DKK348
40 | BootstrapData!C349 | BootstrapData!DKK349
41 | BootstrapData!C350 | BootstrapData!DKK350
42 | BootstrapData!C351 | BootstrapData!DKK351
43 | BootstrapData!C352 | BootstrapData!DKK352
44 | BootstrapData!C353 | BootstrapData!DKK353
45 | BootstrapData!C354 | BootstrapData!DKK354
46 | BootstrapData!C355 | BootstrapData!DKK355
47 | BootstrapData!C356 | BootstrapData!DKK356
48 | BootstrapData!C357 | BootstrapData!DKK357
49 | BootstrapData!C358 | BootstrapData!DKK358
50 | BootstrapData!C359 | BootstrapData!DKK359
51 | BootstrapData!C360 | BootstrapData!DKK360
52 | BootstrapData!C361 | BootstrapData!DKK361
53 | BootstrapData!C362 | BootstrapData!DKK362
54 | BootstrapData!C363 | BootstrapData!DKK363
55 | BootstrapData!C364 | BootstrapData!DKK364
56 | BootstrapData!C365 | BootstrapData!DKK365
57 | BootstrapData!C366 | BootstrapData!DKK366
58 | BootstrapData!C367 | BootstrapData!DKK367
59 | BootstrapData!C368 | BootstrapData!DKK368
60 | BootstrapData!C369 | BootstrapData!DKK369
61 | BootstrapData!C370 | BootstrapData!DKK370
62 | BootstrapData!C371 | BootstrapData!DKK371
63 | BootstrapData!C372 | BootstrapData!DKK372
64 | BootstrapData!C373 | BootstrapData!DKK373
65 | BootstrapData!C374 | BootstrapData!DKK374
66 | BootstrapData!C375 | BootstrapData!DKK375
67 | BootstrapData!C376 | BootstrapData!DKK376
68 | BootstrapData!C377 | BootstrapData!DKK377
69 | BootstrapData!C378 | BootstrapData!DKK378
70 | BootstrapData!C379 | BootstrapData!DKK379
71 | BootstrapData!C380 | BootstrapData!DKK380
72 | BootstrapData!C381 | BootstrapData!DKK381
73 | BootstrapData!C382 | BootstrapData!DKK382
74 | BootstrapData!C383 | BootstrapData!DKK383
75 | BootstrapData!C384 | BootstrapData!DKK384
76 | BootstrapData!C385 | BootstrapData!DKK385
77 | BootstrapData!C386 | BootstrapData!DKK386
78 | BootstrapData!C387 | BootstrapData!DKK387
79 | BootstrapData!C388 | BootstrapData!DKK388
80 | BootstrapData!C389 | BootstrapData!DKK389
81 | BootstrapData!C390 | BootstrapData!DKK390
82 | BootstrapData!C391 | BootstrapData!DKK391
83 | BootstrapData!C392 | BootstrapData!DKK392
84 | BootstrapData!C393 | BootstrapData!DKK393
85 | BootstrapData!C394 | BootstrapData!DKK394
86 | BootstrapData!C395 | BootstrapData!DKK395
87 | BootstrapData!C396 | BootstrapData!DKK396
88 | BootstrapData!C397 | BootstrapData!DKK397
89 | BootstrapData!C398 | BootstrapData!DKK398
90 | BootstrapData!C399 | BootstrapData!DKK399
91 | BootstrapData!C400 | BootstrapData!DKK400
92 | BootstrapData!C401 | BootstrapData!DKK401
93 | BootstrapData!C402 | BootstrapData!DKK402
94 | BootstrapData!C403 | BootstrapData!DKK403
95 | BootstrapData!C404 | BootstrapData!DKK404
96 | BootstrapData!C405 | BootstrapData!DKK405
97 | BootstrapData!C406 | BootstrapData!DKK406
98 | BootstrapData!C407 | BootstrapData!DKK407
99 | BootstrapData!C408 | BootstrapData!DKK408
100 | BootstrapData!C409 | BootstrapData!DKK409
Conditional Formatting Sensitivity - Bootstrap Scrum
'SPERT® Bootstrap Scrum'!M4:M22 | 0.5 | Forecast Horizon
'SPERT® Bootstrap Scrum'!R4:R103 | 2 | 10%
'SPERT® Bootstrap Scrum'!S4:S103 | 1.5 | Optimistic
'SPERT® Bootstrap Scrum'!T4:T103 | 1.5 | Expected
'SPERT® Bootstrap Scrum'!U4:U103 | 1.5 | Conservative
'SPERT® Bootstrap Scrum'!V4:V103 | 1.5 | 90%
Conditional Formatting Sensitivity - Bootstrap Kanban
'SPERT® Bootstrap Kanban'!K4:K22 | 0.5 | Forecast Horizon
'SPERT® Bootstrap Kanban'!P4:P103 | 2 | 10%
'SPERT® Bootstrap Kanban'!Q4:Q103 | 1.5 | Optimistic
'SPERT® Bootstrap Kanban'!R4:R103 | 1.5 | Expected
'SPERT® Bootstrap Kanban'!S4:S103 | 1.5 | Conservative
'SPERT® Bootstrap Kanban'!T4:T103 | 1.5 | 90%
Team Capacity values
0% = team will not work this iteration | 0%
20% = capacity reduced by 80% | 20%
30% = capacity reduced by 70% | 30%
40% = capacity reduced by 40% | 40%
50% = capacity reduced by 50% | 50%
60% = capacity reduced by 40% | 60%
70% = capacity reduced by 30% | 70%
80% = capacity reduced by 20% | 80%
Version 1.2 – © 2021-2025, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
IMPORTANT NOTE:
SPERT users have very little reason to change the Vlookup values in rows 5-208.
These lookup values are used to calculate which data values to use in the Bootstrap Scrum and Bootstrap Kanban worksheets.
If you choose to reduce or increase the number of simulated trials (which by default is set to 1000), then you may have to change column C ("Simulation Row End").
Reducing the number of trials will reduce the statistical accuracy of the forecast burn-up charts and other calculated values, but it will shrink the file size and increase the speed of calculations in every worksheet.
Increasing the number of trials will increase the statistical accuracy of the forecast burn-up charts and other calculated values, but it will increase the file size and reduce the speed of calculations in every worksheet.
Generally, for most agile forecasting, using 1000 trials strikes a very good balance between speed and accuracy.
IMPORTANT NOTE:
SPERT uses conditional formatting in the tables found in both the Bootstrap Scrum and Bootstrap Kanban worksheets. Conditional formatting changes the background color of certain cells to the same pale pink color as used in this information text box.
The conditional formatting helps you quickly pick out cell data of interest.
For example, in the Bootstrap Scrum worksheet, in column N, any cells that change background color to be pale pink are cells with values that approximate the total amount of work left to do on the Product Backlog (tracked in column E).
Another example is the table on the right-side of the Bootstrap Scrum worksheet. Cells which change background color to pale pink approximate the total amount of work of the product (To-do, Doing and Done). By quickly identifying these cells, you can see on which row they appear and find the finish date that matches the probability of each cell value.
On this worksheet, the Vlookup values in column B are conditional formatting sensitivity values that are used in conditional format formulas. These conditional formatting sensitivity values adjust the sensitivity of the conditional formatting. You may need to increase these values if you aren't seeing any pale pink-shaded cells as described above. Or, if you see too many pale pink-shaded cells, you may need to decrease these conditional formatting sensitivity values.

## Compare with @Risk model
Compare SPERT Bootstrap Model (Scrum worksheet) with a Palisade @Risk bootstrap model
To validate the Statistical PERT® Bootstrap Edition, I used Palisade @Risk to perform a 50,000 trial simulation which created a forecast of
how much work can be completed in 13 iterations by bootstrapping the historical record from 8 completed iterations. The results between the SPERT model and
the @Risk model were nearly identical. Note that SPERT probabilities are for the area to the RIGHT of the X value, where @Risk probabilities are for the LEFT.
For example, to evaluate these results, compare the @Risk 10th percentile value with SPERT's 90th percentile value.
Palisade's @Risk |  | SPERT® Bootstrap Edition
Cell | M25 |  | By December 15, 2020,
Minimum | 242
Maximum | 555 | Likelihood | we'll complete at least
Mean | 390 | 95% | 335
90% CI | ± 0.267 | 90% | 344.1
Mode | 387 | 85% | 353
Median | 389 | 80% | 360
Std Dev | 36.27 | 75% | 365
Skewness | 0.0886 | 70% | 370
Kurtosis | 2.9756 | 65% | 375
Values | 50000 | 60% | 380
Errors | 0 | 55% | 385
Filtered | 0 | 50% | 389
Left X | 332 | 45% | 392.55
Left P | 5% | 40% | 399
Right X | 450 | 35% | 403
Right P | 95% | 30% | 408
Dif. X | 118 | 25% | 413
Dif. P | 90% | 20% | 419
1% | 308 | 15% | 427
2.5% | 321 | 10% | 436
5% | 332 | 5% | 450.95
10% | 344
20% | 359
25% | 365 |  | 13th Iteration
30% | 370
35% | 375
40% | 380
45% | 385
50% | 389
55% | 394
60% | 399
65% | 404
70% | 409
75% | 414
80% | 421
90% | 437
95% | 450
97.5% | 462
99% | 476

## Change Log
Statistical PERT® (SPERT®) Bootstrap Edition Change Log
Change Date | Version | Authored By | Description
2025-10-28 | 1.2 | William W. Davis | Replace the deprecated CONCATENATE function with CONCAT. Update example data with 2026-2027 dates.
Create a new version! Update row 3 above; insert a new row below this one; on the Insert Options action dropdown, choose "Format Same as Below"; copy cells A3:D3; only paste the Values into row 5
2025-10-28 | 1.2 | William W. Davis | Replace the deprecated CONCATENATE function with CONCAT. Update example data with 2026-2027 dates.
2025-01-03 | 1.1.6 | William W. Davis | Updated example date dates to 2025-2026
2024-01-13 | 1.1.5 | William W. Davis | Updated example date dates to 2024-2025
2023-03-31 | 1.1.4 | William W. Davis | Modified the hover-over comment for "Finish Date" which originally instructed not to use this model to forecast days, just weeks or months
2023-03-27 | 1.1.3 | William W. Davis | Changed both Scrum and Kanban worksheets so the "Finish by" date calculation only works if the iteration length is 1 week or more.
2023-03-26 | 1.1.2 | William W. Davis | Set the "Finish Date" columns to the Date format, to make it easier to copy-down dates with expected results
2023-03-04 | 1.1.1 | William W. Davis | Updated sample dates data to 2023
2022-01-01 | 1.1 | William W. Davis | Changed copyright footer so modified SPERT spreadsheets done by other authors are easier to legally indicate; updated 2022-2023 USA holidays
2021-09-09 | 1.0.1 | William W. Davis | Clarify the meaning of the cells using PERCENTILE and PERCENTRANK functions
2021-08-17 | 1.0.0 | William W. Davis | Initial release
Note on A3: The date value in cell A3 is used to calculate the copyright year in all the worksheet footers.
Note on B3: The version number in cell B3 is used to calculate the SPERT version in all the worksheet footers.
Note on C3: The name appearing in cell C3 will appear as a "Modified by" user in all the worksheet footers ONLY IF IT IS NOT "William W. Davis" (the original SPERT creator)
Note on D3: Enter a short description of the change you've made to this SPERT spreadsheet.

## GNU GPL
GNU GENERAL PUBLIC LICENSE
Version 3, 29 June 2007
Copyright (C) 2007 Free Software Foundation, Inc. <https://fsf.org/>
Everyone is permitted to copy and distribute verbatim copies
of this license document, but changing it is not allowed.
Preamble
The GNU General Public License is a free, copyleft license for
software and other kinds of works.
The licenses for most software and other practical works are designed
to take away your freedom to share and change the works. By contrast,
the GNU General Public License is intended to guarantee your freedom to
share and change all versions of a program--to make sure it remains free
software for all its users. We, the Free Software Foundation, use the
GNU General Public License for most of our software; it applies also to
any other work released this way by its authors. You can apply it to
your programs, too.
When we speak of free software, we are referring to freedom, not
price. Our General Public Licenses are designed to make sure that you
have the freedom to distribute copies of free software (and charge for
them if you wish), that you receive source code or can get it if you
want it, that you can change the software or use pieces of it in new
free programs, and that you know you can do these things.
To protect your rights, we need to prevent others from denying you
these rights or asking you to surrender the rights. Therefore, you have
certain responsibilities if you distribute copies of the software, or if
you modify it: responsibilities to respect the freedom of others.
For example, if you distribute copies of such a program, whether
gratis or for a fee, you must pass on to the recipients the same
freedoms that you received. You must make sure that they, too, receive
or can get the source code. And you must show them these terms so they
know their rights.
Developers that use the GNU GPL protect your rights with two steps:
(1) assert copyright on the software, and (2) offer you this License
giving you legal permission to copy, distribute and/or modify it.
For the developers' and authors' protection, the GPL clearly explains
that there is no warranty for this free software. For both users' and
authors' sake, the GPL requires that modified versions be marked as
changed, so that their problems will not be attributed erroneously to
authors of previous versions.
Some devices are designed to deny users access to install or run
modified versions of the software inside them, although the manufacturer
can do so. This is fundamentally incompatible with the aim of
protecting users' freedom to change the software. The systematic
pattern of such abuse occurs in the area of products for individuals to
use, which is precisely where it is most unacceptable. Therefore, we
have designed this version of the GPL to prohibit the practice for those
products. If such problems arise substantially in other domains, we
stand ready to extend this provision to those domains in future versions
of the GPL, as needed to protect the freedom of users.
Finally, every program is threatened constantly by software patents.
States should not allow patents to restrict development and use of
software on general-purpose computers, but in those that do, we wish to
avoid the special danger that patents applied to a free program could
make it effectively proprietary. To prevent this, the GPL assures that
patents cannot be used to render the program non-free.
The precise terms and conditions for copying, distribution and
modification follow.
TERMS AND CONDITIONS
0. Definitions.
"This License" refers to version 3 of the GNU General Public License.
"Copyright" also means copyright-like laws that apply to other kinds of
works, such as semiconductor masks.
"The Program" refers to any copyrightable work licensed under this
License. Each licensee is addressed as "you". "Licensees" and
"recipients" may be individuals or organizations.
To "modify" a work means to copy from or adapt all or part of the work
in a fashion requiring copyright permission, other than the making of an
exact copy. The resulting work is called a "modified version" of the
earlier work or a work "based on" the earlier work.
A "covered work" means either the unmodified Program or a work based
on the Program.
To "propagate" a work means to do anything with it that, without
permission, would make you directly or secondarily liable for
infringement under applicable copyright law, except executing it on a
computer or modifying a private copy. Propagation includes copying,
distribution (with or without modification), making available to the
public, and in some countries other activities as well.
To "convey" a work means any kind of propagation that enables other
parties to make or receive copies. Mere interaction with a user through
a computer network, with no transfer of a copy, is not conveying.
An interactive user interface displays "Appropriate Legal Notices"
to the extent that it includes a convenient and prominently visible
feature that (1) displays an appropriate copyright notice, and (2)
tells the user that there is no warranty for the work (except to the
extent that warranties are provided), that licensees may convey the
work under this License, and how to view a copy of this License. If
the interface presents a list of user commands or options, such as a
menu, a prominent item in the list meets this criterion.
1. Source Code.
The "source code" for a work means the preferred form of the work
for making modifications to it. "Object code" means any non-source
form of a work.
A "Standard Interface" means an interface that either is an official
standard defined by a recognized standards body, or, in the case of
interfaces specified for a particular programming language, one that
is widely used among developers working in that language.
The "System Libraries" of an executable work include anything, other
than the work as a whole, that (a) is included in the normal form of
packaging a Major Component, but which is not part of that Major
Component, and (b) serves only to enable use of the work with that
Major Component, or to implement a Standard Interface for which an
implementation is available to the public in source code form. A
"Major Component", in this context, means a major essential component
(kernel, window system, and so on) of the specific operating system
(if any) on which the executable work runs, or a compiler used to
produce the work, or an object code interpreter used to run it.
The "Corresponding Source" for a work in object code form means all
the source code needed to generate, install, and (for an executable
work) run the object code and to modify the work, including scripts to
control those activities. However, it does not include the work's
System Libraries, or general-purpose tools or generally available free
programs which are used unmodified in performing those activities but
which are not part of the work. For example, Corresponding Source
includes interface definition files associated with source files for
the work, and the source code for shared libraries and dynamically
linked subprograms that the work is specifically designed to require,
such as by intimate data communication or control flow between those
subprograms and other parts of the work.
The Corresponding Source need not include anything that users
can regenerate automatically from other parts of the Corresponding
Source.
The Corresponding Source for a work in source code form is that
same work.
2. Basic Permissions.
All rights granted under this License are granted for the term of
copyright on the Program, and are irrevocable provided the stated
conditions are met. This License explicitly affirms your unlimited
permission to run the unmodified Program. The output from running a
covered work is covered by this License only if the output, given its
content, constitutes a covered work. This License acknowledges your
rights of fair use or other equivalent, as provided by copyright law.
You may make, run and propagate covered works that you do not
convey, without conditions so long as your license otherwise remains
in force. You may convey covered works to others for the sole purpose
of having them make modifications exclusively for you, or provide you
with facilities for running those works, provided that you comply with
the terms of this License in conveying all material for which you do
not control copyright. Those thus making or running the covered works
for you must do so exclusively on your behalf, under your direction
and control, on terms that prohibit them from making any copies of
your copyrighted material outside their relationship with you.
Conveying under any other circumstances is permitted solely under
the conditions stated below. Sublicensing is not allowed; section 10
makes it unnecessary.
3. Protecting Users' Legal Rights From Anti-Circumvention Law.
No covered work shall be deemed part of an effective technological
measure under any applicable law fulfilling obligations under article
11 of the WIPO copyright treaty adopted on 20 December 1996, or
similar laws prohibiting or restricting circumvention of such
measures.
When you convey a covered work, you waive any legal power to forbid
circumvention of technological measures to the extent such circumvention
is effected by exercising rights under this License with respect to
the covered work, and you disclaim any intention to limit operation or
modification of the work as a means of enforcing, against the work's
users, your or third parties' legal rights to forbid circumvention of
technological measures.
4. Conveying Verbatim Copies.
You may convey verbatim copies of the Program's source code as you
receive it, in any medium, provided that you conspicuously and
appropriately publish on each copy an appropriate copyright notice;
keep intact all notices stating that this License and any
non-permissive terms added in accord with section 7 apply to the code;
keep intact all notices of the absence of any warranty; and give all
recipients a copy of this License along with the Program.
You may charge any price or no price for each copy that you convey,
and you may offer support or warranty protection for a fee.
5. Conveying Modified Source Versions.
You may convey a work based on the Program, or the modifications to
produce it from the Program, in the form of source code under the
terms of section 4, provided that you also meet all of these conditions:
a) The work must carry prominent notices stating that you modified
it, and giving a relevant date.
b) The work must carry prominent notices stating that it is
released under this License and any conditions added under section
7. This requirement modifies the requirement in section 4 to
"keep intact all notices".
c) You must license the entire work, as a whole, under this
License to anyone who comes into possession of a copy. This
License will therefore apply, along with any applicable section 7
additional terms, to the whole of the work, and all its parts,
regardless of how they are packaged. This License gives no
permission to license the work in any other way, but it does not
invalidate such permission if you have separately received it.
d) If the work has interactive user interfaces, each must display
Appropriate Legal Notices; however, if the Program has interactive
interfaces that do not display Appropriate Legal Notices, your
work need not make them do so.
A compilation of a covered work with other separate and independent
works, which are not by their nature extensions of the covered work,
and which are not combined with it such as to form a larger program,
in or on a volume of a storage or distribution medium, is called an
"aggregate" if the compilation and its resulting copyright are not
used to limit the access or legal rights of the compilation's users
beyond what the individual works permit. Inclusion of a covered work
in an aggregate does not cause this License to apply to the other
parts of the aggregate.
6. Conveying Non-Source Forms.
You may convey a covered work in object code form under the terms
of sections 4 and 5, provided that you also convey the
machine-readable Corresponding Source under the terms of this License,
in one of these ways:
a) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by the
Corresponding Source fixed on a durable physical medium
customarily used for software interchange.
b) Convey the object code in, or embodied in, a physical product
(including a physical distribution medium), accompanied by a
written offer, valid for at least three years and valid for as
long as you offer spare parts or customer support for that product
model, to give anyone who possesses the object code either (1) a
copy of the Corresponding Source for all the software in the
product that is covered by this License, on a durable physical
medium customarily used for software interchange, for a price no
more than your reasonable cost of physically performing this
conveying of source, or (2) access to copy the
Corresponding Source from a network server at no charge.
c) Convey individual copies of the object code with a copy of the
written offer to provide the Corresponding Source. This
alternative is allowed only occasionally and noncommercially, and
only if you received the object code with such an offer, in accord
with subsection 6b.
d) Convey the object code by offering access from a designated
place (gratis or for a charge), and offer equivalent access to the
Corresponding Source in the same way through the same place at no
further charge. You need not require recipients to copy the
Corresponding Source along with the object code. If the place to
copy the object code is a network server, the Corresponding Source
may be on a different server (operated by you or a third party)
that supports equivalent copying facilities, provided you maintain
clear directions next to the object code saying where to find the
Corresponding Source. Regardless of what server hosts the
Corresponding Source, you remain obligated to ensure that it is
available for as long as needed to satisfy these requirements.
e) Convey the object code using peer-to-peer transmission, provided
you inform other peers where the object code and Corresponding
Source of the work are being offered to the general public at no
charge under subsection 6d.
A separable portion of the object code, whose source code is excluded
from the Corresponding Source as a System Library, need not be
included in conveying the object code work.
A "User Product" is either (1) a "consumer product", which means any
tangible personal property which is normally used for personal, family,
or household purposes, or (2) anything designed or sold for incorporation
into a dwelling. In determining whether a product is a consumer product,
doubtful cases shall be resolved in favor of coverage. For a particular
product received by a particular user, "normally used" refers to a
typical or common use of that class of product, regardless of the status
of the particular user or of the way in which the particular user
actually uses, or expects or is expected to use, the product. A product
is a consumer product regardless of whether the product has substantial
commercial, industrial or non-consumer uses, unless such uses represent
the only significant mode of use of the product.
"Installation Information" for a User Product means any methods,
procedures, authorization keys, or other information required to install
and execute modified versions of a covered work in that User Product from
a modified version of its Corresponding Source. The information must
suffice to ensure that the continued functioning of the modified object
code is in no case prevented or interfered with solely because
modification has been made.
If you convey an object code work under this section in, or with, or
specifically for use in, a User Product, and the conveying occurs as
part of a transaction in which the right of possession and use of the
User Product is transferred to the recipient in perpetuity or for a
fixed term (regardless of how the transaction is characterized), the
Corresponding Source conveyed under this section must be accompanied
by the Installation Information. But this requirement does not apply
if neither you nor any third party retains the ability to install
modified object code on the User Product (for example, the work has
been installed in ROM).
The requirement to provide Installation Information does not include a
requirement to continue to provide support service, warranty, or updates
for a work that has been modified or installed by the recipient, or for
the User Product in which it has been modified or installed. Access to a
network may be denied when the modification itself materially and
adversely affects the operation of the network or violates the rules and
protocols for communication across the network.
Corresponding Source conveyed, and Installation Information provided,
in accord with this section must be in a format that is publicly
documented (and with an implementation available to the public in
source code form), and must require no special password or key for
unpacking, reading or copying.
7. Additional Terms.
"Additional permissions" are terms that supplement the terms of this
License by making exceptions from one or more of its conditions.
Additional permissions that are applicable to the entire Program shall
be treated as though they were included in this License, to the extent
that they are valid under applicable law. If additional permissions
apply only to part of the Program, that part may be used separately
under those permissions, but the entire Program remains governed by
this License without regard to the additional permissions.
When you convey a copy of a covered work, you may at your option
remove any additional permissions from that copy, or from any part of
it. (Additional permissions may be written to require their own
removal in certain cases when you modify the work.) You may place
additional permissions on material, added by you to a covered work,
for which you have or can give appropriate copyright permission.
Notwithstanding any other provision of this License, for material you
add to a covered work, you may (if authorized by the copyright holders of
that material) supplement the terms of this License with terms:
a) Disclaiming warranty or limiting liability differently from the
terms of sections 15 and 16 of this License; or
b) Requiring preservation of specified reasonable legal notices or
author attributions in that material or in the Appropriate Legal
Notices displayed by works containing it; or
c) Prohibiting misrepresentation of the origin of that material, or
requiring that modified versions of such material be marked in
reasonable ways as different from the original version; or
d) Limiting the use for publicity purposes of names of licensors or
authors of the material; or
e) Declining to grant rights under trademark law for use of some
trade names, trademarks, or service marks; or
f) Requiring indemnification of licensors and authors of that
material by anyone who conveys the material (or modified versions of
it) with contractual assumptions of liability to the recipient, for
any liability that these contractual assumptions directly impose on
those licensors and authors.
All other non-permissive additional terms are considered "further
restrictions" within the meaning of section 10. If the Program as you
received it, or any part of it, contains a notice stating that it is
governed by this License along with a term that is a further
restriction, you may remove that term. If a license document contains
a further restriction but permits relicensing or conveying under this
License, you may add to a covered work material governed by the terms
of that license document, provided that the further restriction does
not survive such relicensing or conveying.
If you add terms to a covered work in accord with this section, you
must place, in the relevant source files, a statement of the
additional terms that apply to those files, or a notice indicating
where to find the applicable terms.
Additional terms, permissive or non-permissive, may be stated in the
form of a separately written license, or stated as exceptions;
the above requirements apply either way.
8. Termination.
You may not propagate or modify a covered work except as expressly
provided under this License. Any attempt otherwise to propagate or
modify it is void, and will automatically terminate your rights under
this License (including any patent licenses granted under the third
paragraph of section 11).
However, if you cease all violation of this License, then your
license from a particular copyright holder is reinstated (a)
provisionally, unless and until the copyright holder explicitly and
finally terminates your license, and (b) permanently, if the copyright
holder fails to notify you of the violation by some reasonable means
prior to 60 days after the cessation.
Moreover, your license from a particular copyright holder is
reinstated permanently if the copyright holder notifies you of the
violation by some reasonable means, this is the first time you have
received notice of violation of this License (for any work) from that
copyright holder, and you cure the violation prior to 30 days after
your receipt of the notice.
Termination of your rights under this section does not terminate the
licenses of parties who have received copies or rights from you under
this License. If your rights have been terminated and not permanently
reinstated, you do not qualify to receive new licenses for the same
material under section 10.
9. Acceptance Not Required for Having Copies.
You are not required to accept this License in order to receive or
run a copy of the Program. Ancillary propagation of a covered work
occurring solely as a consequence of using peer-to-peer transmission
to receive a copy likewise does not require acceptance. However,
nothing other than this License grants you permission to propagate or
modify any covered work. These actions infringe copyright if you do
not accept this License. Therefore, by modifying or propagating a
covered work, you indicate your acceptance of this License to do so.
10. Automatic Licensing of Downstream Recipients.
Each time you convey a covered work, the recipient automatically
receives a license from the original licensors, to run, modify and
propagate that work, subject to this License. You are not responsible
for enforcing compliance by third parties with this License.
An "entity transaction" is a transaction transferring control of an
organization, or substantially all assets of one, or subdividing an
organization, or merging organizations. If propagation of a covered
work results from an entity transaction, each party to that
transaction who receives a copy of the work also receives whatever
licenses to the work the party's predecessor in interest had or could
give under the previous paragraph, plus a right to possession of the
Corresponding Source of the work from the predecessor in interest, if
the predecessor has it or can get it with reasonable efforts.
You may not impose any further restrictions on the exercise of the
rights granted or affirmed under this License. For example, you may
not impose a license fee, royalty, or other charge for exercise of
rights granted under this License, and you may not initiate litigation
(including a cross-claim or counterclaim in a lawsuit) alleging that
any patent claim is infringed by making, using, selling, offering for
sale, or importing the Program or any portion of it.
11. Patents.
A "contributor" is a copyright holder who authorizes use under this
License of the Program or a work on which the Program is based. The
work thus licensed is called the contributor's "contributor version".
A contributor's "essential patent claims" are all patent claims
owned or controlled by the contributor, whether already acquired or
hereafter acquired, that would be infringed by some manner, permitted
by this License, of making, using, or selling its contributor version,
but do not include claims that would be infringed only as a
consequence of further modification of the contributor version. For
purposes of this definition, "control" includes the right to grant
patent sublicenses in a manner consistent with the requirements of
this License.
Each contributor grants you a non-exclusive, worldwide, royalty-free
patent license under the contributor's essential patent claims, to
make, use, sell, offer for sale, import and otherwise run, modify and
propagate the contents of its contributor version.
In the following three paragraphs, a "patent license" is any express
agreement or commitment, however denominated, not to enforce a patent
(such as an express permission to practice a patent or covenant not to
sue for patent infringement). To "grant" such a patent license to a
party means to make such an agreement or commitment not to enforce a
patent against the party.
If you convey a covered work, knowingly relying on a patent license,
and the Corresponding Source of the work is not available for anyone
to copy, free of charge and under the terms of this License, through a
publicly available network server or other readily accessible means,
then you must either (1) cause the Corresponding Source to be so
available, or (2) arrange to deprive yourself of the benefit of the
patent license for this particular work, or (3) arrange, in a manner
consistent with the requirements of this License, to extend the patent
license to downstream recipients. "Knowingly relying" means you have
actual knowledge that, but for the patent license, your conveying the
covered work in a country, or your recipient's use of the covered work
in a country, would infringe one or more identifiable patents in that
country that you have reason to believe are valid.
If, pursuant to or in connection with a single transaction or
arrangement, you convey, or propagate by procuring conveyance of, a
covered work, and grant a patent license to some of the parties
receiving the covered work authorizing them to use, propagate, modify
or convey a specific copy of the covered work, then the patent license
you grant is automatically extended to all recipients of the covered
work and works based on it.
A patent license is "discriminatory" if it does not include within
the scope of its coverage, prohibits the exercise of, or is
conditioned on the non-exercise of one or more of the rights that are
specifically granted under this License. You may not convey a covered
work if you are a party to an arrangement with a third party that is
in the business of distributing software, under which you make payment
to the third party based on the extent of your activity of conveying
the work, and under which the third party grants, to any of the
parties who would receive the covered work from you, a discriminatory
patent license (a) in connection with copies of the covered work
conveyed by you (or copies made from those copies), or (b) primarily
for and in connection with specific products or compilations that
contain the covered work, unless you entered into that arrangement,
or that patent license was granted, prior to 28 March 2007.
Nothing in this License shall be construed as excluding or limiting
any implied license or other defenses to infringement that may
otherwise be available to you under applicable patent law.
12. No Surrender of Others' Freedom.
If conditions are imposed on you (whether by court order, agreement or
otherwise) that contradict the conditions of this License, they do not
excuse you from the conditions of this License. If you cannot convey a
covered work so as to satisfy simultaneously your obligations under this
License and any other pertinent obligations, then as a consequence you may
not convey it at all. For example, if you agree to terms that obligate you
to collect a royalty for further conveying from those to whom you convey
the Program, the only way you could satisfy both those terms and this
License would be to refrain entirely from conveying the Program.
13. Use with the GNU Affero General Public License.
Notwithstanding any other provision of this License, you have
permission to link or combine any covered work with a work licensed
under version 3 of the GNU Affero General Public License into a single
combined work, and to convey the resulting work. The terms of this
License will continue to apply to the part which is the covered work,
but the special requirements of the GNU Affero General Public License,
section 13, concerning interaction through a network will apply to the
combination as such.
14. Revised Versions of this License.
The Free Software Foundation may publish revised and/or new versions of
the GNU General Public License from time to time. Such new versions will
be similar in spirit to the present version, but may differ in detail to
address new problems or concerns.
Each version is given a distinguishing version number. If the
Program specifies that a certain numbered version of the GNU General
Public License "or any later version" applies to it, you have the
option of following the terms and conditions either of that numbered
version or of any later version published by the Free Software
Foundation. If the Program does not specify a version number of the
GNU General Public License, you may choose any version ever published
by the Free Software Foundation.
If the Program specifies that a proxy can decide which future
versions of the GNU General Public License can be used, that proxy's
public statement of acceptance of a version permanently authorizes you
to choose that version for the Program.
Later license versions may give you additional or different
permissions. However, no additional obligations are imposed on any
author or copyright holder as a result of your choosing to follow a
later version.
15. Disclaimer of Warranty.
THERE IS NO WARRANTY FOR THE PROGRAM, TO THE EXTENT PERMITTED BY
APPLICABLE LAW. EXCEPT WHEN OTHERWISE STATED IN WRITING THE COPYRIGHT
HOLDERS AND/OR OTHER PARTIES PROVIDE THE PROGRAM "AS IS" WITHOUT WARRANTY
OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO,
THE IMPLIED WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR
PURPOSE. THE ENTIRE RISK AS TO THE QUALITY AND PERFORMANCE OF THE PROGRAM
IS WITH YOU. SHOULD THE PROGRAM PROVE DEFECTIVE, YOU ASSUME THE COST OF
ALL NECESSARY SERVICING, REPAIR OR CORRECTION.
16. Limitation of Liability.
IN NO EVENT UNLESS REQUIRED BY APPLICABLE LAW OR AGREED TO IN WRITING
WILL ANY COPYRIGHT HOLDER, OR ANY OTHER PARTY WHO MODIFIES AND/OR CONVEYS
THE PROGRAM AS PERMITTED ABOVE, BE LIABLE TO YOU FOR DAMAGES, INCLUDING ANY
GENERAL, SPECIAL, INCIDENTAL OR CONSEQUENTIAL DAMAGES ARISING OUT OF THE
USE OR INABILITY TO USE THE PROGRAM (INCLUDING BUT NOT LIMITED TO LOSS OF
DATA OR DATA BEING RENDERED INACCURATE OR LOSSES SUSTAINED BY YOU OR THIRD
PARTIES OR A FAILURE OF THE PROGRAM TO OPERATE WITH ANY OTHER PROGRAMS),
EVEN IF SUCH HOLDER OR OTHER PARTY HAS BEEN ADVISED OF THE POSSIBILITY OF
SUCH DAMAGES.
17. Interpretation of Sections 15 and 16.
If the disclaimer of warranty and limitation of liability provided
above cannot be given local legal effect according to their terms,
reviewing courts shall apply local law that most closely approximates
an absolute waiver of all civil liability in connection with the
Program, unless a warranty or assumption of liability accompanies a
copy of the Program in return for a fee.
END OF TERMS AND CONDITIONS