## Welcome!
Welcome to Statistical PERT® Bootstrap Edition
Statistical PERT® (SPERT®) is a freely licensed, probabilistic, estimation technique. Use Statistical PERT® | All models are wrong, but some are useful.
Bootstrap Edition to estimate uncertainties that are highly unpredictable in nature, and may not have any | George E. P. Box, British statistician (1919-2013)
pattern and cannot be easily or reliably fitted to a known probability distribution.
Statistical PERT® Bootstrap Edition uses statistical bootstrapping to create five different forecast | Facts are stubborn things, but statistics are pliable.
lines of future team performance. Bootstrapping does not try to fit the team's historical record | Mark Twain, American humorist (1835-1910)
into a known probability distribution, like the normal or beta distributions. Instead, bootstrapping
simply acknowledges that what the team has actually done may occur again in the future. This
bootstrapping model performs a simulation 1000 times for each future iteration, using the team's
historical record as a possible outcome for each random sample.
This model is dynamically constructed. Depending on the number of historical data points you add to the
model, the simulation-with-replacement that occurs will correctly select from all your historical data (up to
50 data points).
If you have any questions, suggestions, or comments, I'd love to hear from you!
Contact me!
Version 1.2 – © 2021-2025, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com | New! SPERT Bootstrap 5-Line Forecast™
Watch a Pluralsight course on Statistical PERT® Normal Edition | - Shows a user-controlled confidence interval for the bootstrapped mean
Watch Statistical PERT videos on YouTube | - Shows a user-controlled confidence interval for all delivery date possibilities
Connect with or follow William W. Davis on LinkedIn | - Tracks changes to the Product Backlog over time
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications | - Dynamic boostrapping without macros!
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## README for Version 1
Statistical PERT® Bootstrap Edition README for Version 1
In this edition of Statistical PERT, a forecast is built using a bootstrapping approach.
Click here to learn about bootstrapping.
You should have several historical data values of team history before using this forecasting model.
Normally, a bootstrapped model would use 20 or more values from a randomly sampled population.
When using this model to forecast agile software development, you will likely want to use "done" history
from as few as five or six time periods, but usually not more than the last 6-12 months of the team's
history to ensure that the bootstrapped historical data is reflective of the current team conditions.
If using less than 20 historical data values in the "Done" column (on the Bootstrap Scrum and Bootstrap Kanban
worksheets), be prepared for possible forecast volatility if the team inconsistently delivers "done" work.
To achieve bootstrapping using only built-in Excel functions and no macros, this spreadsheet uses
several Excel functions: RANDBETWEEN, PERCENTRANK.EXC, INDEX, INDIRECT, AVERAGE, STDEV.P and others.
The BootstrapData worksheet creates all the simulated data. Do not rename this worksheet.
Renaming this particular worksheet might break the use of the INDIRECT function on other worksheets.
In the BootstrapData worksheet, rows 4-103 create simulated results for a forecast iteration.
As you enter the team's actual "Done" work in the Bootstrap Scrum worksheet, the simulated results
in the BootstrapData worksheet are replaced using your team's actual history. The first 50 rows of data
(rows 4-53) will either be your team's actual history OR a simulated outcome. The next 50 rows of data
(rows 54-103) will always be simulated outcomes. The RANDBETWEEN function will choose which value to use
from the "Done" column in the Bootstrap Scrum worksheet when it is simulating an outcome.
Not all data from BootstrapData is used in the Bootstrap Scrum worksheet. What's used is dependent
on what you've entered in the Bootstrap Scrum worksheet.
In rows 105-204 of the BootstrapData worksheet, this model keeps a running total of all "Done" work, both
actual "Done" work (from the Bootstrap Scrum worksheet) or the simulated "Done" work (from rows 4-103
on the BootstrapData worksheet). These rows use the bootstrapped mean (average) for each iteration.
In rows 310-409 of the BootstrapData worksheet, this model keeps a running total of only the simulated
"Done" work (from rows 209-308 on the BootstrapData worksheet). These values are used in the
Bootstrap Kanban worksheet.
Both Bootstrap Scrum and Bootstrap Kanban worksheets use PERCENTRANK.EXC to calculate the
confidence interval for the bootstrapped dataset. That is how the "Percentile Rank" value is calculated.
This model dynamically adjusts to how much actual history you have entered in the "Done" column on the
Bootstrap forecast worksheets. As you enter more actual history (up to 50 data values), the bootstrap formulas
in the Bootstrap forecast worksheets will adjust accordingly to include the correct number of simulated
results in the BootstrapData worksheet. If you have entered 10 values in the "Done" column on the
Bootstrap Scrum worksheet, then the bootstrap simulation will use 10 possible values in the BootstrapData
worksheet.
Bootstrap Scrum was developed with Scrum teams in mind. These teams work with an ordered Product
Backlog and in sprints (iterations). This worksheet will chart the changes in all the work of the Product
Increment including work that is To-do, Doing and Done.
Bootstrap Kanban was developed with Kanban teams in mind. These teams have a backlog which may or
may not be ordered. They work in a continuous flow fashion, so to use this forecast worksheet, Kanban teams
should select a time period to track their throughput, and use their throughput counts in the "Done" column.
Version 1.2 – © 2021-2025, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).

## How to read a burn-up chart
Statistical PERT® (SPERT®) Bootstrap Edition How to read a 5-line burn-up chart
Version 1.2 – © 2021-2025, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
The 10% forecast line shows an unlikely outcome. Using the normal distribution and the historical data only, there is a 10% probability that the true outcome will be earlier than this forecast line. There is a 90% probability that the true outcome will be later than this forecast line.
The Expected forecast line shows the P50 outcome based upon the simulation. There is a 50% chance the true outcome may be earlier and 50% chance the true value may be later than this forecast line.
The 90% forecast line shows an unlikely outcome. Using the normal distribution and the historical data only, there is a 10% probability that the true outcome will be later than this forecast line. There is a 90% probability that the true outcome will be earlier than this forecast line.
The Optimistic forecast line shows the 5th percentile of the bootstrapped data. 95% of all simulations had a finish date that was later than this forecast line, and 5% of all simulations had a finish date that was equal to or earlier than this forecast line.
The Conservative forecast line shows where the 95th percentile of the bootstrapped data. 95% of all simulations had a finish date that was earlier than this forecast line, and 5% of all simulations had a finish date that was later than this forecast line.
All of the forecast lines are configurable except the Expected forecast line, which will always show the P50 value. You can choose different probabilities for the other four forecast lines.

## SPERT® Bootstrap Scrum
Statistical PERT® (SPERT®) Bootstrap Edition Bootstrap Scrum | [18 empty] | Total Product = 690
[6 empty] | Total "Done" | Total "Done" | To-Do & All "Done" | To-Do & All "Done" |  |  |  |  | By January 18, 2027, |  |  | 10% | Optimistic | Expected | Conservative | 90%
[17 empty] | 39.9915 |  |  |  | 18.3728
ID | Iteration | Finish Dates | Capacity | Product Backlog | "Done" |  |  |  |  | Number of iterations to forecast | 16 |  | Likelihood | we'll complete at least | ID/Iter | Finish Dates | 10% | 5% | 50% | 95% | 90% | Finish Dates
1 | 1 | 2026-03-02 |  | 552 | 47 | 47 | 47 | 552 | 552 | Iteration duration | 2 | weeks | 95% | 369.025 | 1 | 2026-03-02 | 47 | 47 | 47 | 47 | 47 | 2026-03-02
2 | 2 | 2026-03-16 |  | 505 | 26 | 73 | 73 | 552 | 552 | Total Product Backlog | 690 | (To-do, doing, done) | 90% | 385 | 2 | 2026-03-16 | 73 | 73 | 73 | 73 | 73 | 2026-03-16
3 | 3 | 2026-03-30 |  | 479 | 39 | 112 | 112 | 552 | 552 | Start From date | 2026-06-08 |  | 85% | 395.075 | 3 | 2026-03-30 | 112 | 112 | 112 | 112 | 112 | 2026-03-30
4 | 4 | 2026-04-13 |  | 440 | 21 | 133 | 133 | 552 | 552 | Finish By date | 2027-01-18 |  | 80% | 402.5 | 4 | 2026-04-13 | 133 | 133 | 133 | 133 | 133 | 2026-04-13
5 | 5 | 2026-04-27 |  | 419 | 39 | 172 | 172 | 552 | 552 | Percentile Rank | 37.3% |  | 75% | 409.5 | 5 | 2026-04-27 | 172 | 172 | 172 | 172 | 172 | 2026-04-27
6 | 6 | 2026-05-11 |  | 380 | 15 | 187 | 187 | 552 | 552 |  |  |  | 70% | 415.5 | 6 | 2026-05-11 | 187 | 187 | 187 | 187 | 187 | 2026-05-11
7 | 7 | 2026-05-25 |  | 365 | 29 | 216 | 216 | 552 | 552 |  |  |  | 65% | 421.5 | 7 | 2026-05-25 | 216 | 216 | 216 | 216 | 216 | 2026-05-25
8 | 8 | 2026-06-08 |  | 365 | 24 | 240 | 240 | 581 | 581 |  |  |  | 60% | 425.5 | 8 | 2026-06-08 | 240 | 240 | 240 | 240 | 240 | 2026-06-08
9 | 9 | 2026-06-22 |  | 375 |  | #N/A |  | 615 | 615 |  |  |  | 55% | 430 | 9 | 2026-06-22 | 279.9915 | 287 | 269 | 255 | 258.3728 | 2026-06-22
10 | 10 | 2026-07-06 |  | 385 |  | #N/A |  | 625 | 625 |  |  |  | 50% | 435.5 | 10 | 2026-07-06 | 319.9831 | 326 | 300 | 279 | 276.7455 | 2026-07-06
11 | 11 | 2026-07-20 |  | 395 |  | #N/A |  | 635 | 635 |  |  |  | 45% | 440.275 | 11 | 2026-07-20 | 359.9746 | 360 | 331 | 302 | 295.1183 | 2026-07-20
12 | 12 | 2026-08-03 |  | 405 |  | #N/A |  | 645 | 645 |  |  |  | 40% | 445 | 12 | 2026-08-03 | 399.9662 | 396 | 361 | 329 | 313.4911 | 2026-08-03
13 | 13 | 2026-08-17 |  | 415 |  | #N/A |  | 655 | 655 |  |  |  | 35% | 452 | 13 | 2026-08-17 | 439.9577 | 428 | 391 | 356 | 331.8638 | 2026-08-17
14 | 14 | 2026-08-31 |  | 425 |  | #N/A |  | 665 | 665 |  |  |  | 30% | 457.5 | 14 | 2026-08-31 | 479.9493 | 462 | 421 | 383 | 350.2366 | 2026-08-31
15 | 15 | 2026-09-14 |  | 430 |  | #N/A |  | 670 | 670 |  |  |  | 25% | 462.5 | 15 | 2026-09-14 | 519.9408 | 496 | 450 | 408 | 368.6094 | 2026-09-14
16 | 16 | 2026-09-28 |  | 435 |  | #N/A |  | 675 | 675 |  |  |  | 20% | 469.9 | 16 | 2026-09-28 | 559.9324 | 532 | 481 | 436 | 386.9822 | 2026-09-28
17 | 17 | 2026-10-12 |  | 440 |  | #N/A |  | 680 | 680 |  |  |  | 15% | 477.5 | 17 | 2026-10-12 | 599.9239 | 564 | 510 | 464 | 405.3549 | 2026-10-12
18 | 18 | 2026-10-26 |  | 445 |  | #N/A |  | 685 | 685 |  |  |  | 10% | 486.5 | 18 | 2026-10-26 | 639.9155 | 598 | 540.5 | 491 | 423.7277 | 2026-10-26
19 | 19 | 2026-11-09 |  | 450 |  | #N/A |  | 690 | 690 |  |  |  | 5% | 500.5 | 19 | 2026-11-09 | 679.907 | 630.95 | 571 | 514.05 | 442.1005 | 2026-11-09
20 | 20 | 2026-11-23 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 20 | 2026-11-23 | 719.8986 | 663 | 602 | 542 | 460.4732 | 2026-11-23
21 | 21 | 2026-12-07 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 21 | 2026-12-07 | 759.8901 | 692.95 | 631 | 566.05 | 478.846 | 2026-12-07
22 | 22 | 2026-12-21 | 50% |  |  | #N/A |  | 690 | 690 | [5 empty] | 22 | 2026-12-21 | 779.8859 | 709.45 | 645.5 | 581.65 | 488.0324 | 2026-12-21
23 | 23 | 2027-01-04 | 0% |  |  | #N/A |  | 690 | 690 | [5 empty] | 23 | 2027-01-04 | 779.8859 | 709.45 | 645.5 | 581.65 | 488.0324 | 2027-01-04
24 | 24 | 2027-01-18 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 24 | 2027-01-18 | 819.8774 | 740.5 | 675.5 | 609.025 | 506.4052 | 2027-01-18
25 | 25 | 2027-02-01 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 25 | 2027-02-01 | 859.869 | 774.5 | 704.75 | 639.5 | 524.7779 | 2027-02-01
26 | 26 | 2027-02-15 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 26 | 2027-02-15 | 899.8605 | 804.475 | 734.5 | 665.025 | 543.1507 | 2027-02-15
27 | 27 | 2027-03-01 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 27 | 2027-03-01 | 939.8521 | 838.975 | 765.5 | 693 | 561.5235 | 2027-03-01
28 | 28 | 2027-03-15 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 28 | 2027-03-15 | 979.8436 | 867.975 | 794 | 722.5 | 579.8962 | 2027-03-15
29 | 29 | 2027-03-29 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 29 | 2027-03-29 | 1019.8352 | 898.45 | 824.75 | 752.5 | 598.269 | 2027-03-29
30 | 30 | 2027-04-12 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 30 | 2027-04-12 | 1059.8267 | 930.5 | 854 | 782.025 | 616.6418 | 2027-04-12
31 | 31 | 2027-04-26 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 31 | 2027-04-26 | 1099.8183 | 963.5 | 883.5 | 809.5 | 635.0146 | 2027-04-26
32 | 32 | 2027-05-10 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 32 | 2027-05-10 | 1139.8098 | 994.45 | 916.5 | 837.525 | 653.3873 | 2027-05-10
33 | 33 | 2027-05-24 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 33 | 2027-05-24 | 1179.8014 | 1025.975 | 945.5 | 866.025 | 671.7601 | 2027-05-24
34 | 34 | 2027-06-07 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 34 | 2027-06-07 | 1219.7929 | 1054.5 | 975 | 892.525 | 690.1329 | 2027-06-07
35 | 35 | 2027-06-21 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 35 | 2027-06-21 | 1259.7845 | 1086.925 | 1005.5 | 921.025 | 708.5056 | 2027-06-21
36 | 36 | 2027-07-05 |  |  |  | #N/A |  | 690 | 690 | [5 empty] | 36 | 2027-07-05 | 1299.776 | 1116.4 | 1034.25 | 945.5 | 726.8784 | 2027-07-05
37 | [5 empty] | #N/A |  | #N/A
38 | [5 empty] | #N/A |  | #N/A
39 | [5 empty] | #N/A |  | #N/A
40 | [5 empty] | #N/A |  | #N/A
41 | [5 empty] | #N/A |  | #N/A
42 | [5 empty] | #N/A |  | #N/A
43 | [5 empty] | #N/A |  | #N/A
44 | [5 empty] | #N/A |  | #N/A |  | Bootstrapped Mean | 29.1822 | per iteration
45 | [5 empty] | #N/A |  | #N/A |  | Bootstrapped Standard Deviation | 8.4346
46 | [5 empty] | #N/A |  | #N/A |  | Total work left to-do | 450
47 | [5 empty] | #N/A |  | #N/A
48 | [5 empty] | #N/A |  | #N/A
49 | [5 empty] | #N/A |  | #N/A
50 | [5 empty] | #N/A |  | #N/A
51 | [5 empty] | #N/A |  | #N/A
52 | [5 empty] | #N/A |  | #N/A
53 | [5 empty] | #N/A |  | #N/A
54 | [5 empty] | #N/A |  | #N/A
55 | [5 empty] | #N/A |  | #N/A
56 | [5 empty] | #N/A |  | #N/A
57 | [5 empty] | #N/A |  | #N/A
58 | [5 empty] | #N/A |  | #N/A
59 | [5 empty] | #N/A |  | #N/A
60 | [5 empty] | #N/A |  | #N/A
61 | [5 empty] | #N/A |  | #N/A
62 | [5 empty] | #N/A |  | #N/A
63 | [5 empty] | #N/A |  | #N/A
64 | [5 empty] | #N/A |  | #N/A
65 | [5 empty] | #N/A |  | #N/A
66 | [5 empty] | #N/A |  | #N/A
67 | [5 empty] | #N/A |  | #N/A
68 | [5 empty] | #N/A |  | #N/A
69 | [5 empty] | #N/A |  | #N/A
70 | [5 empty] | #N/A |  | #N/A
71 | [5 empty] | #N/A |  | #N/A
72 | [5 empty] | #N/A |  | #N/A
73 | [5 empty] | #N/A |  | #N/A
74 | [5 empty] | #N/A |  | #N/A
75 | [5 empty] | #N/A |  | #N/A
76 | [5 empty] | #N/A |  | #N/A
77 | [5 empty] | #N/A |  | #N/A
78 | [5 empty] | #N/A |  | #N/A
79 | [5 empty] | #N/A |  | #N/A
80 | [5 empty] | #N/A |  | #N/A
81 | [5 empty] | #N/A |  | #N/A
82 | [5 empty] | #N/A |  | #N/A
83 | [5 empty] | #N/A |  | #N/A
84 | [5 empty] | #N/A |  | #N/A
85 | [5 empty] | #N/A |  | #N/A
86 | [5 empty] | #N/A |  | #N/A
87 | [5 empty] | #N/A |  | #N/A
88 | [5 empty] | #N/A |  | #N/A
89 | [5 empty] | #N/A |  | #N/A
90 | [5 empty] | #N/A |  | #N/A
91 | [5 empty] | #N/A |  | #N/A
92 | [5 empty] | #N/A |  | #N/A
93 | [5 empty] | #N/A |  | #N/A
94 | [5 empty] | #N/A |  | #N/A
95 | [5 empty] | #N/A |  | #N/A
96 | [5 empty] | #N/A |  | #N/A
97 | [5 empty] | #N/A |  | #N/A
98 | [5 empty] | #N/A |  | #N/A
99 | [5 empty] | #N/A |  | #N/A
100 | [5 empty] | #N/A |  | #N/A
|  |  |  | 19 | 8
[22 empty] | Used by the histogram. Used to choose the column in BootstrapData in the next row down | 1 | 4 | 7 | 10 | 13 | 16 | 19 | 22 | 25 | 28 | 31 | 34 | 37 | 40 | 43 | 46 | 49 | 52 | 55 | 58 | 61 | 64 | 67 | 70 | 73 | 76 | 79 | 82 | 85 | 88 | 91 | 94 | 97 | 100 | 103 | 106 | 109 | 112 | 115 | 118 | 121 | 124 | 127 | 130 | 133 | 136 | 139 | 142 | 145 | 148 | 151 | 154 | 157 | 160 | 163 | 166 | 169 | 172 | 175 | 178 | 181 | 184 | 187 | 190 | 193 | 196 | 199 | 202 | 205 | 208 | 211 | 214 | 217 | 220 | 223 | 226 | 229 | 232 | 235 | 238 | 241 | 244 | 247 | 250 | 253 | 256 | 259 | 262 | 265 | 268 | 271 | 274 | 277 | 280 | 283 | 286 | 289 | 292 | 295 | 298 | 301 | 304 | 307 | 310 | 313 | 316 | 319 | 322 | 325 | 328 | 331 | 334 | 337 | 340 | 343 | 346 | 349 | 352 | 355 | 358 | 361 | 364 | 367 | 370 | 373 | 376 | 379 | 382 | 385 | 388 | 391 | 394 | 397 | 400 | 403 | 406 | 409 | 412 | 415 | 418 | 421 | 424 | 427 | 430 | 433 | 436 | 439 | 442 | 445 | 448 | 451 | 454 | 457 | 460 | 463 | 466 | 469 | 472 | 475 | 478 | 481 | 484 | 487 | 490 | 493 | 496 | 499 | 502 | 505 | 508 | 511 | 514 | 517 | 520 | 523 | 526 | 529 | 532 | 535 | 538 | 541 | 544 | 547 | 550 | 553 | 556 | 559 | 562 | 565 | 568 | 571 | 574 | 577 | 580 | 583 | 586 | 589 | 592 | 595 | 598 | 601 | 604 | 607 | 610 | 613 | 616 | 619 | 622 | 625 | 628 | 631 | 634 | 637 | 640 | 643 | 646 | 649 | 652 | 655 | 658 | 661 | 664 | 667 | 670 | 673 | 676 | 679 | 682 | 685 | 688 | 691 | 694 | 697 | 700 | 703 | 706 | 709 | 712 | 715 | 718 | 721 | 724 | 727 | 730 | 733 | 736 | 739 | 742 | 745 | 748 | 751 | 754 | 757 | 760 | 763 | 766 | 769 | 772 | 775 | 778 | 781 | 784 | 787 | 790 | 793 | 796 | 799 | 802 | 805 | 808 | 811 | 814 | 817 | 820 | 823 | 826 | 829 | 832 | 835 | 838 | 841 | 844 | 847 | 850 | 853 | 856 | 859 | 862 | 865 | 868 | 871 | 874 | 877 | 880 | 883 | 886 | 889 | 892 | 895 | 898 | 901 | 904 | 907 | 910 | 913 | 916 | 919 | 922 | 925 | 928 | 931 | 934 | 937 | 940 | 943 | 946 | 949 | 952 | 955 | 958 | 961 | 964 | 967 | 970 | 973 | 976 | 979 | 982 | 985 | 988 | 991 | 994 | 997 | 1000 | 1003 | 1006 | 1009 | 1012 | 1015 | 1018 | 1021 | 1024 | 1027 | 1030 | 1033 | 1036 | 1039 | 1042 | 1045 | 1048 | 1051 | 1054 | 1057 | 1060 | 1063 | 1066 | 1069 | 1072 | 1075 | 1078 | 1081 | 1084 | 1087 | 1090 | 1093 | 1096 | 1099 | 1102 | 1105 | 1108 | 1111 | 1114 | 1117 | 1120 | 1123 | 1126 | 1129 | 1132 | 1135 | 1138 | 1141 | 1144 | 1147 | 1150 | 1153 | 1156 | 1159 | 1162 | 1165 | 1168 | 1171 | 1174 | 1177 | 1180 | 1183 | 1186 | 1189 | 1192 | 1195 | 1198 | 1201 | 1204 | 1207 | 1210 | 1213 | 1216 | 1219 | 1222 | 1225 | 1228 | 1231 | 1234 | 1237 | 1240 | 1243 | 1246 | 1249 | 1252 | 1255 | 1258 | 1261 | 1264 | 1267 | 1270 | 1273 | 1276 | 1279 | 1282 | 1285 | 1288 | 1291 | 1294 | 1297 | 1300 | 1303 | 1306 | 1309 | 1312 | 1315 | 1318 | 1321 | 1324 | 1327 | 1330 | 1333 | 1336 | 1339 | 1342 | 1345 | 1348 | 1351 | 1354 | 1357 | 1360 | 1363 | 1366 | 1369 | 1372 | 1375 | 1378 | 1381 | 1384 | 1387 | 1390 | 1393 | 1396 | 1399 | 1402 | 1405 | 1408 | 1411 | 1414 | 1417 | 1420 | 1423 | 1426 | 1429 | 1432 | 1435 | 1438 | 1441 | 1444 | 1447 | 1450 | 1453 | 1456 | 1459 | 1462 | 1465 | 1468 | 1471 | 1474 | 1477 | 1480 | 1483 | 1486 | 1489 | 1492 | 1495 | 1498 | 1501 | 1504 | 1507 | 1510 | 1513 | 1516 | 1519 | 1522 | 1525 | 1528 | 1531 | 1534 | 1537 | 1540 | 1543 | 1546 | 1549 | 1552 | 1555 | 1558 | 1561 | 1564 | 1567 | 1570 | 1573 | 1576 | 1579 | 1582 | 1585 | 1588 | 1591 | 1594 | 1597 | 1600 | 1603 | 1606 | 1609 | 1612 | 1615 | 1618 | 1621 | 1624 | 1627 | 1630 | 1633 | 1636 | 1639 | 1642 | 1645 | 1648 | 1651 | 1654 | 1657 | 1660 | 1663 | 1666 | 1669 | 1672 | 1675 | 1678 | 1681 | 1684 | 1687 | 1690 | 1693 | 1696 | 1699 | 1702 | 1705 | 1708 | 1711 | 1714 | 1717 | 1720 | 1723 | 1726 | 1729 | 1732 | 1735 | 1738 | 1741 | 1744 | 1747 | 1750 | 1753 | 1756 | 1759 | 1762 | 1765 | 1768 | 1771 | 1774 | 1777 | 1780 | 1783 | 1786 | 1789 | 1792 | 1795 | 1798 | 1801 | 1804 | 1807 | 1810 | 1813 | 1816 | 1819 | 1822 | 1825 | 1828 | 1831 | 1834 | 1837 | 1840 | 1843 | 1846 | 1849 | 1852 | 1855 | 1858 | 1861 | 1864 | 1867 | 1870 | 1873 | 1876 | 1879 | 1882 | 1885 | 1888 | 1891 | 1894 | 1897 | 1900 | 1903 | 1906 | 1909 | 1912 | 1915 | 1918 | 1921 | 1924 | 1927 | 1930 | 1933 | 1936 | 1939 | 1942 | 1945 | 1948 | 1951 | 1954 | 1957 | 1960 | 1963 | 1966 | 1969 | 1972 | 1975 | 1978 | 1981 | 1984 | 1987 | 1990 | 1993 | 1996 | 1999 | 2002 | 2005 | 2008 | 2011 | 2014 | 2017 | 2020 | 2023 | 2026 | 2029 | 2032 | 2035 | 2038 | 2041 | 2044 | 2047 | 2050 | 2053 | 2056 | 2059 | 2062 | 2065 | 2068 | 2071 | 2074 | 2077 | 2080 | 2083 | 2086 | 2089 | 2092 | 2095 | 2098 | 2101 | 2104 | 2107 | 2110 | 2113 | 2116 | 2119 | 2122 | 2125 | 2128 | 2131 | 2134 | 2137 | 2140 | 2143 | 2146 | 2149 | 2152 | 2155 | 2158 | 2161 | 2164 | 2167 | 2170 | 2173 | 2176 | 2179 | 2182 | 2185 | 2188 | 2191 | 2194 | 2197 | 2200 | 2203 | 2206 | 2209 | 2212 | 2215 | 2218 | 2221 | 2224 | 2227 | 2230 | 2233 | 2236 | 2239 | 2242 | 2245 | 2248 | 2251 | 2254 | 2257 | 2260 | 2263 | 2266 | 2269 | 2272 | 2275 | 2278 | 2281 | 2284 | 2287 | 2290 | 2293 | 2296 | 2299 | 2302 | 2305 | 2308 | 2311 | 2314 | 2317 | 2320 | 2323 | 2326 | 2329 | 2332 | 2335 | 2338 | 2341 | 2344 | 2347 | 2350 | 2353 | 2356 | 2359 | 2362 | 2365 | 2368 | 2371 | 2374 | 2377 | 2380 | 2383 | 2386 | 2389 | 2392 | 2395 | 2398 | 2401 | 2404 | 2407 | 2410 | 2413 | 2416 | 2419 | 2422 | 2425 | 2428 | 2431 | 2434 | 2437 | 2440 | 2443 | 2446 | 2449 | 2452 | 2455 | 2458 | 2461 | 2464 | 2467 | 2470 | 2473 | 2476 | 2479 | 2482 | 2485 | 2488 | 2491 | 2494 | 2497 | 2500 | 2503 | 2506 | 2509 | 2512 | 2515 | 2518 | 2521 | 2524 | 2527 | 2530 | 2533 | 2536 | 2539 | 2542 | 2545 | 2548 | 2551 | 2554 | 2557 | 2560 | 2563 | 2566 | 2569 | 2572 | 2575 | 2578 | 2581 | 2584 | 2587 | 2590 | 2593 | 2596 | 2599 | 2602 | 2605 | 2608 | 2611 | 2614 | 2617 | 2620 | 2623 | 2626 | 2629 | 2632 | 2635 | 2638 | 2641 | 2644 | 2647 | 2650 | 2653 | 2656 | 2659 | 2662 | 2665 | 2668 | 2671 | 2674 | 2677 | 2680 | 2683 | 2686 | 2689 | 2692 | 2695 | 2698 | 2701 | 2704 | 2707 | 2710 | 2713 | 2716 | 2719 | 2722 | 2725 | 2728 | 2731 | 2734 | 2737 | 2740 | 2743 | 2746 | 2749 | 2752 | 2755 | 2758 | 2761 | 2764 | 2767 | 2770 | 2773 | 2776 | 2779 | 2782 | 2785 | 2788 | 2791 | 2794 | 2797 | 2800 | 2803 | 2806 | 2809 | 2812 | 2815 | 2818 | 2821 | 2824 | 2827 | 2830 | 2833 | 2836 | 2839 | 2842 | 2845 | 2848 | 2851 | 2854 | 2857 | 2860 | 2863 | 2866 | 2869 | 2872 | 2875 | 2878 | 2881 | 2884 | 2887 | 2890 | 2893 | 2896 | 2899 | 2902 | 2905 | 2908 | 2911 | 2914 | 2917 | 2920 | 2923 | 2926 | 2929 | 2932 | 2935 | 2938 | 2941 | 2944 | 2947 | 2950 | 2953 | 2956 | 2959 | 2962 | 2965 | 2968 | 2971 | 2974 | 2977 | 2980 | 2983 | 2986 | 2989 | 2992 | 2995 | 2998
[22 empty] | Used by the histogram. Used to copy the BoostrapData values to build a histogram of the boostrapped data | 472 | 530 | 499 | 421 | 498 | 432 | 512 | 434 | 456 | 456 | 427 | 494 | 502 | 419 | 390 | 483 | 461 | 461 | 532 | 368 | 448 | 414 | 425 | 443 | 396 | 461 | 387 | 462 | 420 | 361 | 447 | 454 | 395 | 425 | 326 | 428 | 454 | 402 | 421 | 488 | 412 | 450 | 460 | 405 | 486 | 483 | 428 | 462 | 406 | 403 | 409 | 426 | 427 | 419 | 451 | 418 | 406 | 454 | 454 | 412 | 415 | 385 | 475 | 432 | 396 | 415 | 433 | 378 | 400 | 422 | 476 | 454 | 412 | 484 | 482 | 394 | 421 | 367 | 357 | 432 | 436 | 409 | 448 | 468 | 484 | 508 | 493 | 422 | 389 | 473 | 443 | 411 | 440 | 412 | 425 | 400 | 463 | 425 | 407 | 383 | 431 | 452 | 470 | 452 | 443 | 420 | 416 | 500 | 443 | 449 | 472 | 424 | 479 | 465 | 483 | 434 | 468 | 405 | 470 | 508 | 451 | 438 | 433 | 456 | 410 | 527 | 441 | 473 | 374 | 386 | 471 | 383 | 416 | 499 | 380 | 474 | 418 | 448 | 485 | 437 | 412 | 385 | 437 | 484 | 454 | 484 | 411 | 489 | 424 | 462 | 466 | 444 | 444 | 516 | 487 | 450 | 366 | 390 | 423 | 437 | 458 | 431 | 434 | 420 | 424 | 425 | 414 | 458 | 462 | 427 | 391 | 392 | 401 | 428 | 371 | 434 | 453 | 465 | 429 | 463 | 462 | 429 | 428 | 417 | 380 | 481 | 465 | 467 | 447 | 424 | 443 | 341 | 402 | 435 | 453 | 440 | 384 | 434 | 496 | 480 | 467 | 424 | 368 | 462 | 407 | 516 | 397 | 386 | 462 | 461 | 415 | 453 | 429 | 401 | 475 | 434 | 404 | 449 | 514 | 470 | 426 | 399 | 399 | 411 | 422 | 390 | 358 | 435 | 462 | 456 | 365 | 379 | 436 | 523 | 489 | 421 | 421 | 493 | 424 | 480 | 407 | 437 | 483 | 491 | 446 | 459 | 448 | 427 | 414 | 438 | 405 | 365 | 424 | 398 | 465 | 433 | 438 | 385 | 387 | 427 | 406 | 432 | 459 | 465 | 473 | 469 | 400 | 470 | 427 | 495 | 418 | 387 | 552 | 399 | 485 | 465 | 446 | 472 | 433 | 442 | 513 | 423 | 417 | 434 | 436 | 445 | 428 | 452 | 382 | 476 | 408 | 458 | 454 | 450 | 425 | 471 | 400 | 443 | 383 | 401 | 430 | 395 | 450 | 388 | 439 | 478 | 426 | 415 | 432 | 393 | 487 | 532 | 368 | 483 | 505 | 479 | 398 | 477 | 441 | 430 | 408 | 483 | 404 | 413 | 426 | 431 | 474 | 467 | 501 | 471 | 479 | 439 | 457 | 386 | 443 | 414 | 443 | 351 | 418 | 410 | 477 | 420 | 406 | 455 | 479 | 426 | 431 | 489 | 459 | 365 | 457 | 392 | 478 | 426 | 440 | 413 | 499 | 445 | 373 | 394 | 406 | 449 | 415 | 557 | 394 | 394 | 395 | 375 | 382 | 483 | 436 | 446 | 518 | 400 | 362 | 458 | 426 | 440 | 465 | 417 | 453 | 475 | 471 | 435 | 395 | 402 | 350 | 479 | 421 | 403 | 421 | 448 | 452 | 445 | 402 | 485 | 527 | 386 | 474 | 483 | 429 | 422 | 427 | 477 | 472 | 433 | 447 | 364 | 437 | 497 | 366 | 398 | 469 | 397 | 361 | 371 | 438 | 418 | 466 | 452 | 483 | 444 | 426 | 453 | 420 | 428 | 434 | 459 | 442 | 451 | 455 | 452 | 413 | 508 | 410 | 439 | 432 | 453 | 415 | 417 | 444 | 421 | 494 | 442 | 482 | 478 | 451 | 318 | 461 | 400 | 502 | 378 | 402 | 462 | 360 | 421 | 424 | 354 | 503 | 444 | 531 | 523 | 350 | 459 | 461 | 397 | 437 | 360 | 457 | 478 | 372 | 444 | 440 | 453 | 406 | 468 | 499 | 430 | 478 | 409 | 530 | 416 | 416 | 422 | 450 | 464 | 418 | 466 | 375 | 395 | 435 | 379 | 488 | 436 | 470 | 440 | 393 | 430 | 392 | 374 | 421 | 425 | 445 | 410 | 442 | 486 | 490 | 431 | 504 | 404 | 444 | 385 | 392 | 424 | 407 | 373 | 445 | 435 | 422 | 439 | 452 | 437 | 421 | 474 | 470 | 491 | 472 | 385 | 464 | 371 | 448 | 416 | 459 | 423 | 439 | 450 | 374 | 402 | 427 | 420 | 426 | 440 | 444 | 369 | 430 | 375 | 453 | 431 | 422 | 426 | 393 | 423 | 450 | 476 | 396 | 452 | 522 | 465 | 443 | 451 | 455 | 442 | 389 | 495 | 405 | 439 | 430 | 471 | 440 | 522 | 350 | 472 | 317 | 482 | 444 | 451 | 492 | 442 | 436 | 424 | 498 | 362 | 452 | 484 | 475 | 439 | 397 | 487 | 379 | 368 | 435 | 428 | 365 | 428 | 499 | 403 | 415 | 427 | 424 | 433 | 376 | 404 | 427 | 454 | 532 | 412 | 440 | 473 | 446 | 413 | 377 | 500 | 441 | 368 | 405 | 426 | 438 | 391 | 406 | 424 | 408 | 465 | 457 | 456 | 489 | 465 | 427 | 426 | 496 | 407 | 491 | 514 | 501 | 416 | 488 | 410 | 512 | 379 | 427 | 371 | 406 | 416 | 382 | 487 | 496 | 433 | 437 | 388 | 465 | 329 | 459 | 413 | 403 | 458 | 398 | 423 | 394 | 439 | 446 | 404 | 484 | 461 | 368 | 448 | 384 | 391 | 397 | 549 | 467 | 536 | 404 | 440 | 328 | 467 | 382 | 430 | 475 | 428 | 381 | 385 | 478 | 392 | 472 | 491 | 427 | 371 | 455 | 395 | 438 | 435 | 418 | 447 | 385 | 470 | 418 | 391 | 426 | 408 | 393 | 464 | 385 | 364 | 515 | 519 | 413 | 461 | 417 | 367 | 438 | 405 | 451 | 476 | 457 | 491 | 430 | 459 | 445 | 330 | 443 | 388 | 445 | 451 | 416 | 408 | 469 | 456 | 415 | 455 | 483 | 436 | 395 | 400 | 410 | 466 | 516 | 446 | 467 | 414 | 427 | 431 | 485 | 432 | 486 | 485 | 464 | 427 | 406 | 423 | 342 | 485 | 401 | 397 | 460 | 404 | 476 | 451 | 433 | 380 | 440 | 428 | 437 | 416 | 473 | 403 | 438 | 432 | 488 | 382 | 393 | 458 | 545 | 434 | 536 | 456 | 437 | 454 | 458 | 490 | 489 | 441 | 471 | 469 | 445 | 356 | 431 | 409 | 455 | 444 | 430 | 492 | 444 | 363 | 416 | 489 | 506 | 430 | 477 | 416 | 373 | 485 | 452 | 458 | 396 | 495 | 440 | 414 | 415 | 422 | 428 | 393 | 353 | 485 | 458 | 429 | 462 | 345 | 451 | 443 | 471 | 456 | 404 | 407 | 399 | 458 | 375 | 414 | 458 | 453 | 452 | 402 | 418 | 456 | 478 | 403 | 512 | 392 | 409 | 496 | 407 | 361 | 397 | 444 | 436 | 459 | 431 | 423 | 466 | 430 | 439 | 422 | 401 | 465 | 457 | 413 | 465 | 468 | 466 | 416 | 545 | 458 | 483 | 455 | 486 | 427 | 400 | 407 | 445 | 409 | 413 | 410 | 480 | 405 | 411 | 424 | 443 | 426 | 421 | 453 | 387 | 366 | 453 | 349 | 487 | 515 | 370 | 501 | 424 | 415 | 463 | 437 | 422 | 400 | 424 | 467 | 458 | 516 | 459 | 506 | 401 | 459 | 410 | 433 | 430 | 431 | 461 | 472 | 386 | 425 | 405 | 409 | 437 | 468 | 447 | 469 | 434 | 458 | 480 | 454 | 413 | 417 | 438 | 451 | 435 | 390 | 442 | 368 | 397 | 376 | 493 | 383 | 373 | 478 | 475 | 432 | 403 | 441 | 428 | 460 | 369 | 441 | 450 | 472 | 472 | 386 | 460 | 450 | 468 | 392 | 512 | 493 | 456 | 490 | 479 | 436 | 464 | 512 | 457 | 466 | 480 | 410 | 353 | 482 | 401 | 415 | 362 | 416 | 402 | 463 | 526 | 402 | 472 | 445 | 420 | 417 | 415 | 445 | 421 | 429 | 406 | 516 | 410 | 472 | 395 | 444 | 427 | 494 | 423 | 444 | 428 | 410 | 374 | 431 | 342 | 463 | 474 | 410 | 511 | 457 | 444 | 500
Version 1.2 – © 2021-2025, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Instructions:
1) Enter your iteration Finish Dates for every completed iteration in column C (column B is optional). Then, add future iteration finish dates (in column C) to match your forecast time horizon.
2) For each completed iteration, enter the amount of work "Done" in column F, then, re-calculate the amount of work left to-do on the Total Product Backlog and enter it in column E (next row down).
After a few completed iterations, examine the 5-Line Forecast™
chart, which tracks the work done each iteration and creates forecast lines showing a confidence interval for the most probable outcome (the average outcome) plus the feasible region for nearly all other, possible outcomes.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
Note on O2: This forecast is built using the bootstrapped sum for each time period in the future, up to the number of time periods specified in cell L5. It also includes the sum of all "Done" work from column H.
Note on S2: By default, this column heading is "10%" (and cell S4 is set to 10%) to create a forecast line where 10% of all possible, future finish dates are on or before the intersection of the "10%" forecast line and the Product Backlog line. This line is drawn using the normal distribution and the bootstrapped mean and standard deviation. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on T2: This is an optimistic value calculation (when cell T4 is set to 1%-20%). It is an optimistic forecast based upon bootstrapping future iterations and summing the total amount of work completed for each iteration. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on U2: When cell U4 is set to 50%, this is the expected value calculation. It is a forecast based upon bootstrapping future iterations and summing the total amount of work completed for each iteration. Although this is the most likely outcome (when cell U4 is 50%), there are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on V2: This is a conservative value calculation (when cell V4 is set to 80%-99%). It is a conservative forecast based upon bootstrapping future iterations and summing the total amount of work completed for each iteration. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on W2: By default, this column heading is "90%" (and cell W4 is set to 90%) to create a forecast line where 90% of all possible, future finish dates are on or before the intersection of the "90%" forecast line and the Product Backlog line. This line is drawn using the normal distribution and the bootstrapped mean and standard deviation. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on A4: SPERT uses the ID column to lookup simulated values. DO NOT CHANGE THIS COLUMN!!!
Note on B4: You can specify any meaningful identifier for your iterations in this column, like, "Sprint 21", "Sprint 22", etc. This is an optional column; you don't have to use it.
Note on C4: Populate the finish dates of all your completed iterations plus all your upcoming iterations that may be included in your forecast. Iterations normally use weekly cycles (1, 2, 3 or 4 week cycles), but can be used with forecasting days or months, too. You can can specify as many iteration finish dates as you want, up to 100 rows.
Note on D4: Optional column. Use this column to indicate iterations when your team capacity is less than 100%. The forecast lines will accordingly adjust for lower team capacity.
Note on E4: Tracks all the work of the Product Backog (to-do) items. Any unit-of-measure can be used (story points, user story count, feature count, ideal hours or days, etc.) as long as it is used consistently to track undone and done work. As one iteration finishes, sum up all the remaining work left on the Product Backlog and enter that value in the next, empty cell in this column. DO NOT CHANGE the historical record of how much work was on the Product Backlog after a sprint is finished! That way, you can see how the total work effort to build the product changes over time.
Note on F4: Enter all the "done" work items at the end of each iteration corresponding to the finish date in column C. After entering a value in this column, sum up the remaining work left to do in the Product Backlog and enter that value in the next, empty cell in column E.
Note on N4: These probabilities are used in column O to create a probabilistic forecast of the bootstrapped sum. Hover over cell K9 to learn more about the Percentile Rank calculation.
Note on P4: This is either the ID (column A) or the user-specified Iteration number (column B)
Note on K9: Among the 1000 simulation trials, the Percentile Rank value shows what percent of the simulated trials had a finish date that is sooner than the Finished By date shown in cell L8. When the Percentile Rank is ~50%, then the Finished By date is the most probable outcome among many other, possible outcomes. When the Percentile Rank is less than 50%, the Finished By date grows more optimistic (and less likely to occur by that date or earlier). When the Percentile Rank is greater than 50%, the Finished By date grows more conservative (and more likely to occur by that date or earlier). When no value is displayed for the Percentile Rank, the bootstrapped sum did not include the Finished By date in cell L8 among any of the simulated trials.

## SPERT® Bootstrap Kanban
Statistical PERT® (SPERT®) Bootstrap Edition Bootstrap Kanban | [15 empty] | Total Product = 615
[11 empty] | By November 25, 2025, |  |  | 10% | Optimistic | Expected | Conservative | 90%
[14 empty] | 38.7775 |  |  |  | 15.8225
ID | Period | Finish Dates | Capacity | "Done" | All "Done" | Backlog | Current Backlog | 375 | Total Product = 615 | Likelihood | we'll complete at least | ID/Per | Finish Dates | 10% | 5% | 50% | 95% | 90% | Finish Dates
1 | 1 | 2025-07-08 |  | 47 | 47 | 615 | Number of time periods to forecast | 13 |  | 95% | 332 | 1 | 2025-07-08 | 47 | 47 | 47 | 47 | 47 | 2025-07-08
2 | 2 | 2025-07-15 |  | 26 | 73 | 615 | Time period duration | 1 | weeks | 90% | 343 | 2 | 2025-07-15 | 73 | 73 | 73 | 73 | 73 | 2025-07-15
3 | 3 | 2025-07-22 |  | 39 | 112 | 615 | Start From date | 2025-08-26 |  | 85% | 352 | 3 | 2025-07-22 | 112 | 112 | 112 | 112 | 112 | 2025-07-22
4 | 4 | 2025-07-29 |  | 21 | 133 | 615 | Finish By date | 2025-11-25 |  | 80% | 361 | 4 | 2025-07-29 | 133 | 133 | 133 | 133 | 133 | 2025-07-29
5 | 5 | 2025-08-05 |  | 39 | 172 | 615 | Percentile Rank | 67.3% |  | 75% | 367 | 5 | 2025-08-05 | 172 | 172 | 172 | 172 | 172 | 2025-08-05
6 | 6 | 2025-08-12 |  | 15 | 187 | 615 |  |  |  | 70% | 371 | 6 | 2025-08-12 | 187 | 187 | 187 | 187 | 187 | 2025-08-12
7 | 7 | 2025-08-19 |  | 29 | 216 | 615 |  |  |  | 65% | 378 | 7 | 2025-08-19 | 216 | 216 | 216 | 216 | 216 | 2025-08-19
8 | 8 | 2025-08-26 |  | 24 | 240 | 615 |  |  |  | 60% | 382 | 8 | 2025-08-26 | 240 | 240 | 240 | 240 | 240 | 2025-08-26
9 | 9 | 2025-09-02 |  |  | #N/A | 615 |  |  |  | 55% | 386 | 9 | 2025-09-02 | 278.7775 | 287 | 269 | 255 | 255.8225 | 2025-09-02
10 | 10 | 2025-09-09 |  |  | #N/A | 615 |  |  |  | 50% | 391 | 10 | 2025-09-09 | 317.5551 | 326 | 300 | 276 | 271.6451 | 2025-09-09
11 | 11 | 2025-09-16 |  |  | #N/A | 615 |  |  |  | 45% | 394 | 11 | 2025-09-16 | 356.3326 | 360 | 329 | 302 | 287.4676 | 2025-09-16
12 | 12 | 2025-09-23 |  |  | #N/A | 615 |  |  |  | 40% | 400 | 12 | 2025-09-23 | 395.1101 | 394 | 360 | 328 | 303.2902 | 2025-09-23
13 | 13 | 2025-09-30 |  |  | #N/A | 615 |  |  |  | 35% | 405.65 | 13 | 2025-09-30 | 433.8877 | 430 | 389 | 354 | 319.1127 | 2025-09-30
14 | 14 | 2025-10-07 |  |  | #N/A | 615 |  |  |  | 30% | 410 | 14 | 2025-10-07 | 472.6652 | 462 | 419 | 383 | 334.9353 | 2025-10-07
15 | 15 | 2025-10-14 |  |  | #N/A | 615 |  |  |  | 25% | 416 | 15 | 2025-10-14 | 511.4427 | 496 | 450 | 408 | 350.7578 | 2025-10-14
16 | 16 | 2025-10-21 |  |  | #N/A | 615 |  |  |  | 20% | 421.8 | 16 | 2025-10-21 | 550.2203 | 530 | 480 | 434.05 | 366.5803 | 2025-10-21
17 | 17 | 2025-10-28 |  |  | #N/A | 615 |  |  |  | 15% | 430 | 17 | 2025-10-28 | 588.9978 | 563 | 510 | 463 | 382.4029 | 2025-10-28
18 | 18 | 2025-11-04 |  |  | #N/A | 615 |  |  |  | 10% | 439 | 18 | 2025-11-04 | 627.7753 | 594 | 539 | 490 | 398.2254 | 2025-11-04
19 | 19 | 2025-11-11 |  |  | #N/A | 615 |  |  |  | 5% | 452 | 19 | 2025-11-11 | 666.5528 | 626 | 569 | 516 | 414.048 | 2025-11-11
20 | 20 | 2025-11-18 |  |  | #N/A | 615 | [5 empty] | 20 | 2025-11-18 | 705.3304 | 661.95 | 600.5 | 545 | 429.8705 | 2025-11-18
21 | 21 | 2025-11-25 |  |  | #N/A | 615 | [5 empty] | 21 | 2025-11-25 | 744.1079 | 692 | 631 | 572 | 445.6931 | 2025-11-25
22 | 22 | 2025-12-02 |  |  | #N/A | 615 | [5 empty] | 22 | 2025-12-02 | 782.8854 | 723 | 661 | 599 | 461.5156 | 2025-12-02
23 | 23 | 2025-12-09 |  |  | #N/A | 615 | [5 empty] | 23 | 2025-12-09 | 821.663 | 756 | 691.5 | 625 | 477.3382 | 2025-12-09
24 | 24 | 2025-12-16 | 50% |  | #N/A | 615 | [5 empty] | 24 | 2025-12-16 | 841.0517 | 769.975 | 706.5 | 639.5 | 485.2494 | 2025-12-16
25 | 25 | 2025-12-23 | 0% |  | #N/A | 615 | [5 empty] | 25 | 2025-12-23 | 841.0517 | 769.975 | 706.5 | 639.5 | 485.2494 | 2025-12-23
26 | 26 | 2025-12-30 | 0% |  | #N/A | 615 | [5 empty] | 26 | 2025-12-30 | 841.0517 | 769.975 | 706.5 | 639.5 | 485.2494 | 2025-12-30
27 | 27 | 2026-01-06 | 50% |  | #N/A | 615 | [5 empty] | 27 | 2026-01-06 | 860.4405 | 784.5 | 720.5 | 654.525 | 493.1607 | 2026-01-06
28 | 28 | 2026-01-13 |  |  | #N/A | 615 | [5 empty] | 28 | 2026-01-13 | 899.218 | 816.975 | 750 | 684 | 508.9832 | 2026-01-13
29 | 29 | 2026-01-20 |  |  | #N/A | 615 | [5 empty] | 29 | 2026-01-20 | 937.9956 | 847.975 | 780.25 | 712.025 | 524.8058 | 2026-01-20
30 | 30 | 2026-01-27 |  |  | #N/A | 615 | [5 empty] | 30 | 2026-01-27 | 976.7731 | 880.95 | 812 | 741.025 | 540.6283 | 2026-01-27
31 | 31 | 2026-02-03 |  |  | #N/A | 615 | [5 empty] | 31 | 2026-02-03 | 1015.5506 | 914.4 | 840.25 | 773 | 556.4509 | 2026-02-03
32 | 32 | 2026-02-10 |  |  | #N/A | 615 | [5 empty] | 32 | 2026-02-10 | 1054.3282 | 945.975 | 870 | 799.025 | 572.2734 | 2026-02-10
33 | 33 | 2026-02-17 |  |  | #N/A | 615 | [5 empty] | 33 | 2026-02-17 | 1093.1057 | 977.95 | 901 | 827.525 | 588.096 | 2026-02-17
34 | 34 | 2026-02-24 |  |  | #N/A | 615 | [5 empty] | 34 | 2026-02-24 | 1131.8832 | 1010.475 | 931.75 | 853 | 603.9185 | 2026-02-24
35 | 35 | 2026-03-03 |  |  | #N/A | 615 | [5 empty] | 35 | 2026-03-03 | 1170.6608 | 1043.975 | 961.5 | 882.025 | 619.741 | 2026-03-03
36 |  |  |  |  | #N/A | #N/A
37 |  |  |  |  | #N/A | #N/A
38 |  |  |  |  | #N/A | #N/A
39 |  |  |  |  | #N/A | #N/A
40 |  |  |  |  | #N/A | #N/A
41 |  |  |  |  | #N/A | #N/A
42 |  |  |  |  | #N/A | #N/A
43 |  |  |  |  | #N/A | #N/A
44 |  |  |  |  | #N/A | #N/A | Bootstrapped Mean | 27.3 | per time period
45 |  |  |  |  | #N/A | #N/A | Bootstrapped Standard Deviation | 8.9559
46 |  |  |  |  | #N/A | #N/A | Total work (to-do & done) | 615
47 |  |  |  |  | #N/A | #N/A
48 |  |  |  |  | #N/A | #N/A
49 |  |  |  |  | #N/A | #N/A
50 |  |  |  |  | #N/A | #N/A
51 | [5 empty] | #N/A
52 | [5 empty] | #N/A
53 | [5 empty] | #N/A
54 | [5 empty] | #N/A
55 | [5 empty] | #N/A
56 | [5 empty] | #N/A
57 | [5 empty] | #N/A
58 | [5 empty] | #N/A
59 | [5 empty] | #N/A
60 | [5 empty] | #N/A
61 | [5 empty] | #N/A
62 | [5 empty] | #N/A
63 | [5 empty] | #N/A
64 | [5 empty] | #N/A
65 | [5 empty] | #N/A
66 | [5 empty] | #N/A
67 | [5 empty] | #N/A
68 | [5 empty] | #N/A
69 | [5 empty] | #N/A
70 | [5 empty] | #N/A
71 | [5 empty] | #N/A
72 | [5 empty] | #N/A
73 | [5 empty] | #N/A
74 | [5 empty] | #N/A
75 | [5 empty] | #N/A
76 | [5 empty] | #N/A
77 | [5 empty] | #N/A
78 | [5 empty] | #N/A
79 | [5 empty] | #N/A
80 | [5 empty] | #N/A
81 | [5 empty] | #N/A
82 | [5 empty] | #N/A
83 | [5 empty] | #N/A
84 | [5 empty] | #N/A
85 | [5 empty] | #N/A
86 | [5 empty] | #N/A
87 | [5 empty] | #N/A
88 | [5 empty] | #N/A
89 | [5 empty] | #N/A
90 | [5 empty] | #N/A
91 | [5 empty] | #N/A
92 | [5 empty] | #N/A
93 | [5 empty] | #N/A
94 | [5 empty] | #N/A
95 | [5 empty] | #N/A
96 | [5 empty] | #N/A
97 | [5 empty] | #N/A
98 | [5 empty] | #N/A
99 | [5 empty] | #N/A
100 | [5 empty] | #N/A
8
[19 empty] | Used by the histogram. Used to choose the column in BootstrapData in the next row down | 1 | 4 | 7 | 10 | 13 | 16 | 19 | 22 | 25 | 28 | 31 | 34 | 37 | 40 | 43 | 46 | 49 | 52 | 55 | 58 | 61 | 64 | 67 | 70 | 73 | 76 | 79 | 82 | 85 | 88 | 91 | 94 | 97 | 100 | 103 | 106 | 109 | 112 | 115 | 118 | 121 | 124 | 127 | 130 | 133 | 136 | 139 | 142 | 145 | 148 | 151 | 154 | 157 | 160 | 163 | 166 | 169 | 172 | 175 | 178 | 181 | 184 | 187 | 190 | 193 | 196 | 199 | 202 | 205 | 208 | 211 | 214 | 217 | 220 | 223 | 226 | 229 | 232 | 235 | 238 | 241 | 244 | 247 | 250 | 253 | 256 | 259 | 262 | 265 | 268 | 271 | 274 | 277 | 280 | 283 | 286 | 289 | 292 | 295 | 298 | 301 | 304 | 307 | 310 | 313 | 316 | 319 | 322 | 325 | 328 | 331 | 334 | 337 | 340 | 343 | 346 | 349 | 352 | 355 | 358 | 361 | 364 | 367 | 370 | 373 | 376 | 379 | 382 | 385 | 388 | 391 | 394 | 397 | 400 | 403 | 406 | 409 | 412 | 415 | 418 | 421 | 424 | 427 | 430 | 433 | 436 | 439 | 442 | 445 | 448 | 451 | 454 | 457 | 460 | 463 | 466 | 469 | 472 | 475 | 478 | 481 | 484 | 487 | 490 | 493 | 496 | 499 | 502 | 505 | 508 | 511 | 514 | 517 | 520 | 523 | 526 | 529 | 532 | 535 | 538 | 541 | 544 | 547 | 550 | 553 | 556 | 559 | 562 | 565 | 568 | 571 | 574 | 577 | 580 | 583 | 586 | 589 | 592 | 595 | 598 | 601 | 604 | 607 | 610 | 613 | 616 | 619 | 622 | 625 | 628 | 631 | 634 | 637 | 640 | 643 | 646 | 649 | 652 | 655 | 658 | 661 | 664 | 667 | 670 | 673 | 676 | 679 | 682 | 685 | 688 | 691 | 694 | 697 | 700 | 703 | 706 | 709 | 712 | 715 | 718 | 721 | 724 | 727 | 730 | 733 | 736 | 739 | 742 | 745 | 748 | 751 | 754 | 757 | 760 | 763 | 766 | 769 | 772 | 775 | 778 | 781 | 784 | 787 | 790 | 793 | 796 | 799 | 802 | 805 | 808 | 811 | 814 | 817 | 820 | 823 | 826 | 829 | 832 | 835 | 838 | 841 | 844 | 847 | 850 | 853 | 856 | 859 | 862 | 865 | 868 | 871 | 874 | 877 | 880 | 883 | 886 | 889 | 892 | 895 | 898 | 901 | 904 | 907 | 910 | 913 | 916 | 919 | 922 | 925 | 928 | 931 | 934 | 937 | 940 | 943 | 946 | 949 | 952 | 955 | 958 | 961 | 964 | 967 | 970 | 973 | 976 | 979 | 982 | 985 | 988 | 991 | 994 | 997 | 1000 | 1003 | 1006 | 1009 | 1012 | 1015 | 1018 | 1021 | 1024 | 1027 | 1030 | 1033 | 1036 | 1039 | 1042 | 1045 | 1048 | 1051 | 1054 | 1057 | 1060 | 1063 | 1066 | 1069 | 1072 | 1075 | 1078 | 1081 | 1084 | 1087 | 1090 | 1093 | 1096 | 1099 | 1102 | 1105 | 1108 | 1111 | 1114 | 1117 | 1120 | 1123 | 1126 | 1129 | 1132 | 1135 | 1138 | 1141 | 1144 | 1147 | 1150 | 1153 | 1156 | 1159 | 1162 | 1165 | 1168 | 1171 | 1174 | 1177 | 1180 | 1183 | 1186 | 1189 | 1192 | 1195 | 1198 | 1201 | 1204 | 1207 | 1210 | 1213 | 1216 | 1219 | 1222 | 1225 | 1228 | 1231 | 1234 | 1237 | 1240 | 1243 | 1246 | 1249 | 1252 | 1255 | 1258 | 1261 | 1264 | 1267 | 1270 | 1273 | 1276 | 1279 | 1282 | 1285 | 1288 | 1291 | 1294 | 1297 | 1300 | 1303 | 1306 | 1309 | 1312 | 1315 | 1318 | 1321 | 1324 | 1327 | 1330 | 1333 | 1336 | 1339 | 1342 | 1345 | 1348 | 1351 | 1354 | 1357 | 1360 | 1363 | 1366 | 1369 | 1372 | 1375 | 1378 | 1381 | 1384 | 1387 | 1390 | 1393 | 1396 | 1399 | 1402 | 1405 | 1408 | 1411 | 1414 | 1417 | 1420 | 1423 | 1426 | 1429 | 1432 | 1435 | 1438 | 1441 | 1444 | 1447 | 1450 | 1453 | 1456 | 1459 | 1462 | 1465 | 1468 | 1471 | 1474 | 1477 | 1480 | 1483 | 1486 | 1489 | 1492 | 1495 | 1498 | 1501 | 1504 | 1507 | 1510 | 1513 | 1516 | 1519 | 1522 | 1525 | 1528 | 1531 | 1534 | 1537 | 1540 | 1543 | 1546 | 1549 | 1552 | 1555 | 1558 | 1561 | 1564 | 1567 | 1570 | 1573 | 1576 | 1579 | 1582 | 1585 | 1588 | 1591 | 1594 | 1597 | 1600 | 1603 | 1606 | 1609 | 1612 | 1615 | 1618 | 1621 | 1624 | 1627 | 1630 | 1633 | 1636 | 1639 | 1642 | 1645 | 1648 | 1651 | 1654 | 1657 | 1660 | 1663 | 1666 | 1669 | 1672 | 1675 | 1678 | 1681 | 1684 | 1687 | 1690 | 1693 | 1696 | 1699 | 1702 | 1705 | 1708 | 1711 | 1714 | 1717 | 1720 | 1723 | 1726 | 1729 | 1732 | 1735 | 1738 | 1741 | 1744 | 1747 | 1750 | 1753 | 1756 | 1759 | 1762 | 1765 | 1768 | 1771 | 1774 | 1777 | 1780 | 1783 | 1786 | 1789 | 1792 | 1795 | 1798 | 1801 | 1804 | 1807 | 1810 | 1813 | 1816 | 1819 | 1822 | 1825 | 1828 | 1831 | 1834 | 1837 | 1840 | 1843 | 1846 | 1849 | 1852 | 1855 | 1858 | 1861 | 1864 | 1867 | 1870 | 1873 | 1876 | 1879 | 1882 | 1885 | 1888 | 1891 | 1894 | 1897 | 1900 | 1903 | 1906 | 1909 | 1912 | 1915 | 1918 | 1921 | 1924 | 1927 | 1930 | 1933 | 1936 | 1939 | 1942 | 1945 | 1948 | 1951 | 1954 | 1957 | 1960 | 1963 | 1966 | 1969 | 1972 | 1975 | 1978 | 1981 | 1984 | 1987 | 1990 | 1993 | 1996 | 1999 | 2002 | 2005 | 2008 | 2011 | 2014 | 2017 | 2020 | 2023 | 2026 | 2029 | 2032 | 2035 | 2038 | 2041 | 2044 | 2047 | 2050 | 2053 | 2056 | 2059 | 2062 | 2065 | 2068 | 2071 | 2074 | 2077 | 2080 | 2083 | 2086 | 2089 | 2092 | 2095 | 2098 | 2101 | 2104 | 2107 | 2110 | 2113 | 2116 | 2119 | 2122 | 2125 | 2128 | 2131 | 2134 | 2137 | 2140 | 2143 | 2146 | 2149 | 2152 | 2155 | 2158 | 2161 | 2164 | 2167 | 2170 | 2173 | 2176 | 2179 | 2182 | 2185 | 2188 | 2191 | 2194 | 2197 | 2200 | 2203 | 2206 | 2209 | 2212 | 2215 | 2218 | 2221 | 2224 | 2227 | 2230 | 2233 | 2236 | 2239 | 2242 | 2245 | 2248 | 2251 | 2254 | 2257 | 2260 | 2263 | 2266 | 2269 | 2272 | 2275 | 2278 | 2281 | 2284 | 2287 | 2290 | 2293 | 2296 | 2299 | 2302 | 2305 | 2308 | 2311 | 2314 | 2317 | 2320 | 2323 | 2326 | 2329 | 2332 | 2335 | 2338 | 2341 | 2344 | 2347 | 2350 | 2353 | 2356 | 2359 | 2362 | 2365 | 2368 | 2371 | 2374 | 2377 | 2380 | 2383 | 2386 | 2389 | 2392 | 2395 | 2398 | 2401 | 2404 | 2407 | 2410 | 2413 | 2416 | 2419 | 2422 | 2425 | 2428 | 2431 | 2434 | 2437 | 2440 | 2443 | 2446 | 2449 | 2452 | 2455 | 2458 | 2461 | 2464 | 2467 | 2470 | 2473 | 2476 | 2479 | 2482 | 2485 | 2488 | 2491 | 2494 | 2497 | 2500 | 2503 | 2506 | 2509 | 2512 | 2515 | 2518 | 2521 | 2524 | 2527 | 2530 | 2533 | 2536 | 2539 | 2542 | 2545 | 2548 | 2551 | 2554 | 2557 | 2560 | 2563 | 2566 | 2569 | 2572 | 2575 | 2578 | 2581 | 2584 | 2587 | 2590 | 2593 | 2596 | 2599 | 2602 | 2605 | 2608 | 2611 | 2614 | 2617 | 2620 | 2623 | 2626 | 2629 | 2632 | 2635 | 2638 | 2641 | 2644 | 2647 | 2650 | 2653 | 2656 | 2659 | 2662 | 2665 | 2668 | 2671 | 2674 | 2677 | 2680 | 2683 | 2686 | 2689 | 2692 | 2695 | 2698 | 2701 | 2704 | 2707 | 2710 | 2713 | 2716 | 2719 | 2722 | 2725 | 2728 | 2731 | 2734 | 2737 | 2740 | 2743 | 2746 | 2749 | 2752 | 2755 | 2758 | 2761 | 2764 | 2767 | 2770 | 2773 | 2776 | 2779 | 2782 | 2785 | 2788 | 2791 | 2794 | 2797 | 2800 | 2803 | 2806 | 2809 | 2812 | 2815 | 2818 | 2821 | 2824 | 2827 | 2830 | 2833 | 2836 | 2839 | 2842 | 2845 | 2848 | 2851 | 2854 | 2857 | 2860 | 2863 | 2866 | 2869 | 2872 | 2875 | 2878 | 2881 | 2884 | 2887 | 2890 | 2893 | 2896 | 2899 | 2902 | 2905 | 2908 | 2911 | 2914 | 2917 | 2920 | 2923 | 2926 | 2929 | 2932 | 2935 | 2938 | 2941 | 2944 | 2947 | 2950 | 2953 | 2956 | 2959 | 2962 | 2965 | 2968 | 2971 | 2974 | 2977 | 2980 | 2983 | 2986 | 2989 | 2992 | 2995 | 2998
[19 empty] | Used by the histogram. Used to copy the BoostrapData values to build a histogram of the boostrapped data | 451 | 411 | 378 | 432 | 412 | 401 | 368 | 413 | 436 | 398 | 414 | 475 | 401 | 425 | 407 | 392 | 379 | 404 | 407 | 304 | 396 | 416 | 415 | 421 | 344 | 416 | 438 | 399 | 444 | 409 | 385 | 384 | 483 | 371 | 353 | 358 | 378 | 358 | 407 | 442 | 321 | 381 | 420 | 437 | 437 | 440 | 393 | 418 | 347 | 354 | 433 | 422 | 356 | 415 | 334 | 393 | 407 | 450 | 406 | 431 | 470 | 414 | 386 | 389 | 322 | 337 | 445 | 451 | 448 | 401 | 391 | 382 | 370 | 339 | 416 | 348 | 410 | 368 | 393 | 409 | 437 | 413 | 346 | 387 | 379 | 395 | 334 | 391 | 341 | 405 | 391 | 379 | 501 | 406 | 367 | 383 | 416 | 383 | 376 | 373 | 387 | 347 | 377 | 407 | 394 | 376 | 358 | 385 | 402 | 392 | 384 | 359 | 387 | 386 | 377 | 403 | 421 | 366 | 351 | 441 | 454 | 342 | 435 | 356 | 317 | 415 | 414 | 418 | 344 | 452 | 402 | 452 | 321 | 318 | 356 | 384 | 387 | 410 | 413 | 382 | 326 | 394 | 372 | 392 | 379 | 363 | 318 | 362 | 439 | 339 | 326 | 417 | 368 | 424 | 392 | 425 | 314 | 424 | 364 | 486 | 438 | 372 | 379 | 336 | 350 | 353 | 364 | 370 | 388 | 436 | 359 | 370 | 388 | 429 | 406 | 379 | 333 | 429 | 451 | 348 | 409 | 451 | 411 | 359 | 344 | 442 | 389 | 383 | 397 | 365 | 370 | 406 | 452 | 372 | 336 | 371 | 330 | 361 | 414 | 370 | 389 | 406 | 368 | 370 | 449 | 410 | 345 | 415 | 411 | 412 | 462 | 342 | 363 | 418 | 381 | 322 | 420 | 373 | 393 | 433 | 341 | 415 | 435 | 366 | 323 | 392 | 415 | 401 | 395 | 356 | 362 | 344 | 414 | 392 | 402 | 388 | 334 | 347 | 357 | 446 | 406 | 418 | 360 | 418 | 416 | 340 | 450 | 449 | 410 | 386 | 358 | 413 | 406 | 421 | 427 | 329 | 358 | 392 | 404 | 406 | 423 | 369 | 384 | 423 | 390 | 415 | 405 | 354 | 376 | 397 | 419 | 461 | 437 | 418 | 449 | 382 | 323 | 392 | 344 | 456 | 326 | 410 | 380 | 330 | 431 | 398 | 431 | 405 | 436 | 396 | 333 | 419 | 402 | 379 | 434 | 422 | 424 | 415 | 456 | 420 | 387 | 420 | 384 | 410 | 358 | 393 | 449 | 366 | 378 | 404 | 485 | 359 | 338 | 430 | 387 | 362 | 409 | 386 | 382 | 374 | 363 | 439 | 417 | 336 | 382 | 364 | 388 | 421 | 350 | 456 | 367 | 455 | 457 | 417 | 435 | 351 | 440 | 455 | 459 | 376 | 401 | 379 | 359 | 387 | 348 | 358 | 361 | 370 | 468 | 393 | 358 | 418 | 411 | 395 | 360 | 354 | 387 | 385 | 408 | 405 | 365 | 351 | 366 | 429 | 350 | 413 | 417 | 430 | 456 | 412 | 348 | 318 | 362 | 444 | 337 | 335 | 360 | 390 | 328 | 382 | 386 | 445 | 381 | 430 | 374 | 404 | 396 | 386 | 437 | 375 | 333 | 459 | 373 | 384 | 395 | 392 | 303 | 395 | 407 | 340 | 472 | 393 | 390 | 351 | 383 | 345 | 356 | 472 | 426 | 375 | 434 | 390 | 363 | 399 | 427 | 426 | 402 | 337 | 467 | 417 | 384 | 404 | 335 | 395 | 338 | 447 | 373 | 416 | 427 | 366 | 324 | 443 | 413 | 390 | 369 | 349 | 423 | 349 | 391 | 426 | 386 | 382 | 385 | 411 | 355 | 400 | 472 | 414 | 410 | 425 | 364 | 372 | 384 | 392 | 470 | 354 | 384 | 380 | 381 | 414 | 336 | 468 | 434 | 427 | 443 | 395 | 333 | 441 | 419 | 381 | 441 | 370 | 394 | 391 | 408 | 426 | 352 | 404 | 323 | 407 | 349 | 384 | 416 | 376 | 425 | 391 | 355 | 374 | 369 | 392 | 406 | 369 | 383 | 382 | 425 | 419 | 379 | 381 | 397 | 446 | 385 | 374 | 414 | 437 | 431 | 383 | 373 | 337 | 403 | 342 | 366 | 393 | 466 | 450 | 313 | 408 | 407 | 479 | 363 | 341 | 394 | 423 | 459 | 411 | 399 | 313 | 397 | 391 | 475 | 359 | 378 | 402 | 369 | 400 | 420 | 366 | 407 | 407 | 405 | 363 | 324 | 437 | 423 | 418 | 396 | 368 | 349 | 435 | 407 | 357 | 387 | 388 | 356 | 371 | 321 | 399 | 433 | 386 | 401 | 386 | 419 | 400 | 368 | 441 | 404 | 394 | 470 | 394 | 429 | 431 | 364 | 334 | 323 | 386 | 383 | 376 | 388 | 360 | 361 | 326 | 442 | 396 | 389 | 383 | 425 | 339 | 347 | 419 | 375 | 465 | 418 | 448 | 351 | 461 | 355 | 358 | 392 | 455 | 339 | 364 | 368 | 361 | 478 | 362 | 386 | 440 | 400 | 379 | 325 | 408 | 403 | 369 | 388 | 372 | 401 | 351 | 406 | 438 | 329 | 358 | 381 | 391 | 432 | 305 | 431 | 424 | 364 | 380 | 384 | 375 | 341 | 443 | 398 | 336 | 490 | 433 | 374 | 371 | 414 | 424 | 375 | 391 | 370 | 383 | 399 | 405 | 404 | 407 | 389 | 439 | 453 | 310 | 377 | 367 | 361 | 395 | 363 | 411 | 421 | 440 | 387 | 378 | 446 | 403 | 418 | 391 | 390 | 391 | 427 | 368 | 435 | 380 | 413 | 397 | 433 | 360 | 402 | 422 | 357 | 470 | 364 | 383 | 366 | 461 | 352 | 404 | 354 | 449 | 396 | 419 | 322 | 343 | 446 | 386 | 427 | 367 | 432 | 417 | 373 | 391 | 369 | 332 | 356 | 401 | 368 | 436 | 403 | 327 | 402 | 361 | 442 | 403 | 395 | 387 | 383 | 266 | 491 | 366 | 378 | 421 | 448 | 322 | 426 | 316 | 400 | 426 | 390 | 379 | 366 | 426 | 387 | 422 | 372 | 405 | 442 | 379 | 390 | 450 | 433 | 418 | 428 | 389 | 420 | 362 | 393 | 374 | 371 | 384 | 369 | 377 | 424 | 342 | 289 | 406 | 283 | 384 | 430 | 367 | 383 | 427 | 409 | 416 | 362 | 335 | 313 | 345 | 342 | 406 | 400 | 345 | 343 | 295 | 426 | 465 | 436 | 416 | 364 | 379 | 368 | 348 | 391 | 372 | 463 | 461 | 368 | 421 | 410 | 397 | 351 | 424 | 368 | 402 | 349 | 352 | 371 | 352 | 373 | 392 | 434 | 424 | 392 | 347 | 398 | 415 | 431 | 339 | 367 | 394 | 338 | 433 | 378 | 414 | 341 | 398 | 353 | 391 | 410 | 386 | 421 | 400 | 394 | 371 | 379 | 362 | 393 | 444 | 351 | 430 | 371 | 353 | 341 | 377 | 382 | 376 | 433 | 371 | 392 | 372 | 389 | 388 | 406 | 391 | 454 | 447 | 370 | 341 | 385 | 404 | 346 | 301 | 336 | 407 | 344 | 383 | 368 | 413 | 417 | 380 | 348 | 430 | 366 | 373 | 327 | 441 | 415 | 407 | 393 | 463 | 352 | 476 | 380 | 384 | 389 | 368 | 408 | 390 | 434 | 384 | 447 | 345 | 415 | 377 | 378 | 393 | 393 | 335 | 388 | 397 | 396 | 425 | 381 | 352 | 503 | 416 | 393 | 371 | 337 | 371 | 387 | 391 | 411 | 398 | 380 | 362 | 418 | 397 | 366 | 407 | 349 | 370 | 368 | 368 | 397 | 379 | 449 | 404 | 416 | 352 | 338 | 370 | 376 | 470 | 382 | 463 | 410 | 402 | 382 | 363 | 399 | 439 | 397 | 414 | 342 | 327 | 434 | 401 | 374 | 378 | 393 | 405 | 381 | 388 | 392 | 354 | 410 | 328 | 392 | 420 | 408 | 368 | 451 | 419 | 368 | 383 | 403 | 392 | 446 | 436 | 395 | 349 | 412 | 379 | 305 | 378 | 359 | 386 | 415 | 326 | 392 | 371 | 350 | 390 | 368 | 407 | 300 | 349 | 346 | 409 | 417 | 362 | 390 | 377 | 372 | 361 | 332 | 376 | 394 | 392 | 327 | 375 | 337 | 425 | 402 | 424 | 396 | 399 | 383 | 395 | 378 | 417
Version 1.2 – © 2021-2025, William W. Davis, MSPM, PMP
Download more FREE Statistical PERT® templates at https://www.statisticalpert.com
Watch a Pluralsight course on Statistical PERT® Normal Edition
Watch Statistical PERT videos on YouTube
Connect with or follow William W. Davis on LinkedIn
Subscribe to the SPERT® newsletter for free tips, free webinars, and new release notifications
Statistical PERT® is a free spreadsheet file; you can redistribute it and/or modify it under the terms of the
GNU General Public License as published by the Free Software Foundation, either version 3 of the License,
or (at your option) any later version. Statistical PERT® and SPERT® are federally-registered trademarks. If you modify
this spreadsheet in any material way, please remove these trademarked names from the modified spreadsheet.
On both verbatim and modified copies of this file, you must always retain the original copyright notice,
including the author's name, copyright year, and a notice that this file is licensed under the GNU General Public License.
This file is distributed in the hope that it will be useful, but WITHOUT ANY WARRANTY;
without even the implied warranty of MERCHANTABILITY or FITNESS FOR A PARTICULAR PURPOSE.
See the GNU General Public License for more details (https://www.gnu.org/licenses/).
Instructions:
1) Enter your iteration Finish Dates for every completed iteration in column C (column B is optional). Then, add future iteration finish dates (in column C) to match your forecast time horizon.
2) For each completed time period, enter the amount of work "Done" in column E, then, re-calculate the amount of work left to-do on the Current Backlog and enter it in cell I4.
After a few completed time periods, examine the 5-Line Forecast™
chart, which tracks the work done each time period and creates forecast lines showing a confidence interval for the most probable outcome (the average outcome) plus the feasible region for nearly all other, possible outcomes.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
Note on L2: This forecast is built using a bootstrapped sum for each time period in the future, up to the number of time periods specified in cell I5. It also includes the sum of all "Done" work from column E.
Note on P2: By default, this column heading is "10%" (and cell P4 is set to 10%) to create a forecast line where 10% of all possible, future finish dates are on or before the intersection of the "10%" forecast line and the Product Backlog line. This line is drawn using the normal distribution and the bootstrapped mean and standard deviation. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on Q2: This is an optimistic value calculation (when cell Q4 is set to 1%-20%). It is an optimistic forecast based upon bootstrapping future iterations and summing the total amount of work completed for each iteration. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on R2: When cell R4 is set to 50%, this is the expected value calculation. It is a forecast based upon bootstrapping future iterations and summing the total amount of work completed for each iteration. Although this is the most likely outcome (when cell R4 is 50%), there are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on S2: This is a conservative value calculation (when cell S4 is set to 80%-99%). It is a conservative forecast based upon bootstrapping future iterations and summing the total amount of work completed for each iteration. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on T2: By default, this column heading is "90%" (and cell T4 is set to 90%) to create a forecast line where 90% of all possible, future finish dates are on or before the intersection of the "90%" forecast line and the Product Backlog line. This line is drawn using the normal distribution and the bootstrapped mean and standard deviation. There are many other, possible outcomes, and every newly-completed iteration will change all forecast values.
Note on A4: SPERT uses the ID column to lookup simulated values. DO NOT CHANGE THIS COLUMN!!!
Note on B4: You can specify any meaningful identifier for your time periods in this column, like, "Week 21", "Week 22", etc. This is an optional column; you don't have to use it.
Note on C4: Populate the finish dates of all your completed iterations plus all your upcoming iterations that may be included in your forecast. Iterations normally use weekly cycles (1, 2, 3 or 4 week cycles), but can be used with forecasting days or months, too. You can can specify as many iteration finish dates as you want, up to 100 rows.
Note on D4: Optional column. Use this column to indicate iterations when your team capacity is less than 100%. The forecast lines will accordingly adjust for lower team capacity.
Note on E4: Enter all the "done" work items at the end of each time period corresponding to the finish date in column C. After entering a value in this column, sum up the remaining work left to do in the Backlog and enter that value in cell I4.
Note on K4: These probabilities are used in column L to create a probabilistic forecast of the bootstrapped sum. Hover over cell H9 to learn more about the Percentile Rank calculation.
Note on M4: This is either the ID (column A) or the user-specified Period number (column B)
Note on H9: Among the 1000 simulation trials, the Percentile Rank value shows what percent of the simulated trials had a finish date that is sooner than the Finished By date shown in cell L8. When the Percentile Rank is ~50%, then the Finished By date is the most probable outcome among many other, possible outcomes. When the Percentile Rank is less than 50%, the Finished By date grows more optimistic (and less likely to occur by that date or earlier). When the Percentile Rank is greater than 50%, the Finished By date grows more conservative (and more likely to occur by that date or earlier). When no value is displayed for the Percentile Rank, the bootstrapped sum did not include the Finished By date in cell L8 among any of the simulated trials.

## BootstrapData
Statistical PERT® (SPERT®) Bootstrap Edition BootstrapData (DO NOT CHANGE)
Scrum | Trial 1 |  |  | Trial 2 |  |  | Trial 3 |  |  | Trial 4 |  |  | Trial 5 |  |  | Trial 6 |  |  | Trial 7 |  |  | Trial 8 |  |  | Trial 9 |  |  | Trial 10 |  |  | Trial 11 |  |  | Trial 12 |  |  | Trial 13 |  |  | Trial 14 |  |  | Trial 15 |  |  | Trial 16 |  |  | Trial 17 |  |  | Trial 18 |  |  | Trial 19 |  |  | Trial 20 |  |  | Trial 21 |  |  | Trial 22 |  |  | Trial 23 |  |  | Trial 24 |  |  | Trial 25 |  |  | Trial 26 |  |  | Trial 27 |  |  | Trial 28 |  |  | Trial 29 |  |  | Trial 30 |  |  | Trial 31 |  |  | Trial 32 |  |  | Trial 33 |  |  | Trial 34 |  |  | Trial 35 |  |  | Trial 36 |  |  | Trial 37 |  |  | Trial 38 |  |  | Trial 39 |  |  | Trial 40 |  |  | Trial 41 |  |  | Trial 42 |  |  | Trial 43 |  |  | Trial 44 |  |  | Trial 45 |  |  | Trial 46 |  |  | Trial 47 |  |  | Trial 48 |  |  | Trial 49 |  |  | Trial 50 |  |  | Trial 51 |  |  | Trial 52 |  |  | Trial 53 |  |  | Trial 54 |  |  | Trial 55 |  |  | Trial 56 |  |  | Trial 57 |  |  | Trial 58 |  |  | Trial 59 |  |  | Trial 60 |  |  | Trial 61 |  |  | Trial 62 |  |  | Trial 63 |  |  | Trial 64 |  |  | Trial 65 |  |  | Trial 66 |  |  | Trial 67 |  |  | Trial 68 |  |  | Trial 69 |  |  | Trial 70 |  |  | Trial 71 |  |  | Trial 72 |  |  | Trial 73 |  |  | Trial 74 |  |  | Trial 75 |  |  | Trial 76 |  |  | Trial 77 |  |  | Trial 78 |  |  | Trial 79 |  |  | Trial 80 |  |  | Trial 81 |  |  | Trial 82 |  |  | Trial 83 |  |  | Trial 84 |  |  | Trial 85 |  |  | Trial 86 |  |  | Trial 87 |  |  | Trial 88 |  |  | Trial 89 |  |  | Trial 90 |  |  | Trial 91 |  |  | Trial 92 |  |  | Trial 93 |  |  | Trial 94 |  |  | Trial 95 |  |  | Trial 96 |  |  | Trial 97 |  |  | Trial 98 |  |  | Trial 99 |  |  | Trial 100 |  |  | Trial 101 |  |  | Trial 102 |  |  | Trial 103 |  |  | Trial 104 |  |  | Trial 105 |  |  | Trial 106 |  |  | Trial 107 |  |  | Trial 108 |  |  | Trial 109 |  |  | Trial 110 |  |  | Trial 111 |  |  | Trial 112 |  |  | Trial 113 |  |  | Trial 114 |  |  | Trial 115 |  |  | Trial 116 |  |  | Trial 117 |  |  | Trial 118 |  |  | Trial 119 |  |  | Trial 120 |  |  | Trial 121 |  |  | Trial 122 |  |  | Trial 123 |  |  | Trial 124 |  |  | Trial 125 |  |  | Trial 126 |  |  | Trial 127 |  |  | Trial 128 |  |  | Trial 129 |  |  | Trial 130 |  |  | Trial 131 |  |  | Trial 132 |  |  | Trial 133 |  |  | Trial 134 |  |  | Trial 135 |  |  | Trial 136 |  |  | Trial 137 |  |  | Trial 138 |  |  | Trial 139 |  |  | Trial 140 |  |  | Trial 141 |  |  | Trial 142 |  |  | Trial 143 |  |  | Trial 144 |  |  | Trial 145 |  |  | Trial 146 |  |  | Trial 147 |  |  | Trial 148 |  |  | Trial 149 |  |  | Trial 150 |  |  | Trial 151 |  |  | Trial 152 |  |  | Trial 153 |  |  | Trial 154 |  |  | Trial 155 |  |  | Trial 156 |  |  | Trial 157 |  |  | Trial 158 |  |  | Trial 159 |  |  | Trial 160 |  |  | Trial 161 |  |  | Trial 162 |  |  | Trial 163 |  |  | Trial 164 |  |  | Trial 165 |  |  | Trial 166 |  |  | Trial 167 |  |  | Trial 168 |  |  | Trial 169 |  |  | Trial 170 |  |  | Trial 171 |  |  | Trial 172 |  |  | Trial 173 |  |  | Trial 174 |  |  | Trial 175 |  |  | Trial 176 |  |  | Trial 177 |  |  | Trial 178 |  |  | Trial 179 |  |  | Trial 180 |  |  | Trial 181 |  |  | Trial 182 |  |  | Trial 183 |  |  | Trial 184 |  |  | Trial 185 |  |  | Trial 186 |  |  | Trial 187 |  |  | Trial 188 |  |  | Trial 189 |  |  | Trial 190 |  |  | Trial 191 |  |  | Trial 192 |  |  | Trial 193 |  |  | Trial 194 |  |  | Trial 195 |  |  | Trial 196 |  |  | Trial 197 |  |  | Trial 198 |  |  | Trial 199 |  |  | Trial 200 |  |  | Trial 201 |  |  | Trial 202 |  |  | Trial 203 |  |  | Trial 204 |  |  | Trial 205 |  |  | Trial 206 |  |  | Trial 207 |  |  | Trial 208 |  |  | Trial 209 |  |  | Trial 210 |  |  | Trial 211 |  |  | Trial 212 |  |  | Trial 213 |  |  | Trial 214 |  |  | Trial 215 |  |  | Trial 216 |  |  | Trial 217 |  |  | Trial 218 |  |  | Trial 219 |  |  | Trial 220 |  |  | Trial 221 |  |  | Trial 222 |  |  | Trial 223 |  |  | Trial 224 |  |  | Trial 225 |  |  | Trial 226 |  |  | Trial 227 |  |  | Trial 228 |  |  | Trial 229 |  |  | Trial 230 |  |  | Trial 231 |  |  | Trial 232 |  |  | Trial 233 |  |  | Trial 234 |  |  | Trial 235 |  |  | Trial 236 |  |  | Trial 237 |  |  | Trial 238 |  |  | Trial 239 |  |  | Trial 240 |  |  | Trial 241 |  |  | Trial 242 |  |  | Trial 243 |  |  | Trial 244 |  |  | Trial 245 |  |  | Trial 246 |  |  | Trial 247 |  |  | Trial 248 |  |  | Trial 249 |  |  | Trial 250 |  |  | Trial 251 |  |  | Trial 252 |  |  | Trial 253 |  |  | Trial 254 |  |  | Trial 255 |  |  | Trial 256 |  |  | Trial 257 |  |  | Trial 258 |  |  | Trial 259 |  |  | Trial 260 |  |  | Trial 261 |  |  | Trial 262 |  |  | Trial 263 |  |  | Trial 264 |  |  | Trial 265 |  |  | Trial 266 |  |  | Trial 267 |  |  | Trial 268 |  |  | Trial 269 |  |  | Trial 270 |  |  | Trial 271 |  |  | Trial 272 |  |  | Trial 273 |  |  | Trial 274 |  |  | Trial 275 |  |  | Trial 276 |  |  | Trial 277 |  |  | Trial 278 |  |  | Trial 279 |  |  | Trial 280 |  |  | Trial 281 |  |  | Trial 282 |  |  | Trial 283 |  |  | Trial 284 |  |  | Trial 285 |  |  | Trial 286 |  |  | Trial 287 |  |  | Trial 288 |  |  | Trial 289 |  |  | Trial 290 |  |  | Trial 291 |  |  | Trial 292 |  |  | Trial 293 |  |  | Trial 294 |  |  | Trial 295 |  |  | Trial 296 |  |  | Trial 297 |  |  | Trial 298 |  |  | Trial 299 |  |  | Trial 300 |  |  | Trial 301 |  |  | Trial 302 |  |  | Trial 303 |  |  | Trial 304 |  |  | Trial 305 |  |  | Trial 306 |  |  | Trial 307 |  |  | Trial 308 |  |  | Trial 309 |  |  | Trial 310 |  |  | Trial 311 |  |  | Trial 312 |  |  | Trial 313 |  |  | Trial 314 |  |  | Trial 315 |  |  | Trial 316 |  |  | Trial 317 |  |  | Trial 318 |  |  | Trial 319 |  |  | Trial 320 |  |  | Trial 321 |  |  | Trial 322 |  |  | Trial 323 |  |  | Trial 324 |  |  | Trial 325 |  |  | Trial 326 |  |  | Trial 327 |  |  | Trial 328 |  |  | Trial 329 |  |  | Trial 330 |  |  | Trial 331 |  |  | Trial 332 |  |  | Trial 333 |  |  | Trial 334 |  |  | Trial 335 |  |  | Trial 336 |  |  | Trial 337 |  |  | Trial 338 |  |  | Trial 339 |  |  | Trial 340 |  |  | Trial 341 |  |  | Trial 342 |  |  | Trial 343 |  |  | Trial 344 |  |  | Trial 345 |  |  | Trial 346 |  |  | Trial 347 |  |  | Trial 348 |  |  | Trial 349 |  |  | Trial 350 |  |  | Trial 351 |  |  | Trial 352 |  |  | Trial 353 |  |  | Trial 354 |  |  | Trial 355 |  |  | Trial 356 |  |  | Trial 357 |  |  | Trial 358 |  |  | Trial 359 |  |  | Trial 360 |  |  | Trial 361 |  |  | Trial 362 |  |  | Trial 363 |  |  | Trial 364 |  |  | Trial 365 |  |  | Trial 366 |  |  | Trial 367 |  |  | Trial 368 |  |  | Trial 369 |  |  | Trial 370 |  |  | Trial 371 |  |  | Trial 372 |  |  | Trial 373 |  |  | Trial 374 |  |  | Trial 375 |  |  | Trial 376 |  |  | Trial 377 |  |  | Trial 378 |  |  | Trial 379 |  |  | Trial 380 |  |  | Trial 381 |  |  | Trial 382 |  |  | Trial 383 |  |  | Trial 384 |  |  | Trial 385 |  |  | Trial 386 |  |  | Trial 387 |  |  | Trial 388 |  |  | Trial 389 |  |  | Trial 390 |  |  | Trial 391 |  |  | Trial 392 |  |  | Trial 393 |  |  | Trial 394 |  |  | Trial 395 |  |  | Trial 396 |  |  | Trial 397 |  |  | Trial 398 |  |  | Trial 399 |  |  | Trial 400 |  |  | Trial 401 |  |  | Trial 402 |  |  | Trial 403 |  |  | Trial 404 |  |  | Trial 405 |  |  | Trial 406 |  |  | Trial 407 |  |  | Trial 408 |  |  | Trial 409 |  |  | Trial 410 |  |  | Trial 411 |  |  | Trial 412 |  |  | Trial 413 |  |  | Trial 414 |  |  | Trial 415 |  |  | Trial 416 |  |  | Trial 417 |  |  | Trial 418 |  |  | Trial 419 |  |  | Trial 420 |  |  | Trial 421 |  |  | Trial 422 |  |  | Trial 423 |  |  | Trial 424 |  |  | Trial 425 |  |  | Trial 426 |  |  | Trial 427 |  |  | Trial 428 |  |  | Trial 429 |  |  | Trial 430 |  |  | Trial 431 |  |  | Trial 432 |  |  | Trial 433 |  |  | Trial 434 |  |  | Trial 435 |  |  | Trial 436 |  |  | Trial 437 |  |  | Trial 438 |  |  | Trial 439 |  |  | Trial 440 |  |  | Trial 441 |  |  | Trial 442 |  |  | Trial 443 |  |  | Trial 444 |  |  | Trial 445 |  |  | Trial 446 |  |  | Trial 447 |  |  | Trial 448 |  |  | Trial 449 |  |  | Trial 450 |  |  | Trial 451 |  |  | Trial 452 |  |  | Trial 453 |  |  | Trial 454 |  |  | Trial 455 |  |  | Trial 456 |  |  | Trial 457 |  |  | Trial 458 |  |  | Trial 459 |  |  | Trial 460 |  |  | Trial 461 |  |  | Trial 462 |  |  | Trial 463 |  |  | Trial 464 |  |  | Trial 465 |  |  | Trial 466 |  |  | Trial 467 |  |  | Trial 468 |  |  | Trial 469 |  |  | Trial 470 |  |  | Trial 471 |  |  | Trial 472 |  |  | Trial 473 |  |  | Trial 474 |  |  | Trial 475 |  |  | Trial 476 |  |  | Trial 477 |  |  | Trial 478 |  |  | Trial 479 |  |  | Trial 480 |  |  | Trial 481 |  |  | Trial 482 |  |  | Trial 483 |  |  | Trial 484 |  |  | Trial 485 |  |  | Trial 486 |  |  | Trial 487 |  |  | Trial 488 |  |  | Trial 489 |  |  | Trial 490 |  |  | Trial 491 |  |  | Trial 492 |  |  | Trial 493 |  |  | Trial 494 |  |  | Trial 495 |  |  | Trial 496 |  |  | Trial 497 |  |  | Trial 498 |  |  | Trial 499 |  |  | Trial 500 |  |  | Trial 501 |  |  | Trial 502 |  |  | Trial 503 |  |  | Trial 504 |  |  | Trial 505 |  |  | Trial 506 |  |  | Trial 507 |  |  | Trial 508 |  |  | Trial 509 |  |  | Trial 510 |  |  | Trial 511 |  |  | Trial 512 |  |  | Trial 513 |  |  | Trial 514 |  |  | Trial 515 |  |  | Trial 516 |  |  | Trial 517 |  |  | Trial 518 |  |  | Trial 519 |  |  | Trial 520 |  |  | Trial 521 |  |  | Trial 522 |  |  | Trial 523 |  |  | Trial 524 |  |  | Trial 525 |  |  | Trial 526 |  |  | Trial 527 |  |  | Trial 528 |  |  | Trial 529 |  |  | Trial 530 |  |  | Trial 531 |  |  | Trial 532 |  |  | Trial 533 |  |  | Trial 534 |  |  | Trial 535 |  |  | Trial 536 |  |  | Trial 537 |  |  | Trial 538 |  |  | Trial 539 |  |  | Trial 540 |  |  | Trial 541 |  |  | Trial 542 |  |  | Trial 543 |  |  | Trial 544 |  |  | Trial 545 |  |  | Trial 546 |  |  | Trial 547 |  |  | Trial 548 |  |  | Trial 549 |  |  | Trial 550 |  |  | Trial 551 |  |  | Trial 552 |  |  | Trial 553 |  |  | Trial 554 |  |  | Trial 555 |  |  | Trial 556 |  |  | Trial 557 |  |  | Trial 558 |  |  | Trial 559 |  |  | Trial 560 |  |  | Trial 561 |  |  | Trial 562 |  |  | Trial 563 |  |  | Trial 564 |  |  | Trial 565 |  |  | Trial 566 |  |  | Trial 567 |  |  | Trial 568 |  |  | Trial 569 |  |  | Trial 570 |  |  | Trial 571 |  |  | Trial 572 |  |  | Trial 573 |  |  | Trial 574 |  |  | Trial 575 |  |  | Trial 576 |  |  | Trial 577 |  |  | Trial 578 |  |  | Trial 579 |  |  | Trial 580 |  |  | Trial 581 |  |  | Trial 582 |  |  | Trial 583 |  |  | Trial 584 |  |  | Trial 585 |  |  | Trial 586 |  |  | Trial 587 |  |  | Trial 588 |  |  | Trial 589 |  |  | Trial 590 |  |  | Trial 591 |  |  | Trial 592 |  |  | Trial 593 |  |  | Trial 594 |  |  | Trial 595 |  |  | Trial 596 |  |  | Trial 597 |  |  | Trial 598 |  |  | Trial 599 |  |  | Trial 600 |  |  | Trial 601 |  |  | Trial 602 |  |  | Trial 603 |  |  | Trial 604 |  |  | Trial 605 |  |  | Trial 606 |  |  | Trial 607 |  |  | Trial 608 |  |  | Trial 609 |  |  | Trial 610 |  |  | Trial 611 |  |  | Trial 612 |  |  | Trial 613 |  |  | Trial 614 |  |  | Trial 615 |  |  | Trial 616 |  |  | Trial 617 |  |  | Trial 618 |  |  | Trial 619 |  |  | Trial 620 |  |  | Trial 621 |  |  | Trial 622 |  |  | Trial 623 |  |  | Trial 624 |  |  | Trial 625 |  |  | Trial 626 |  |  | Trial 627 |  |  | Trial 628 |  |  | Trial 629 |  |  | Trial 630 |  |  | Trial 631 |  |  | Trial 632 |  |  | Trial 633 |  |  | Trial 634 |  |  | Trial 635 |  |  | Trial 636 |  |  | Trial 637 |  |  | Trial 638 |  |  | Trial 639 |  |  | Trial 640 |  |  | Trial 641 |  |  | Trial 642 |  |  | Trial 643 |  |  | Trial 644 |  |  | Trial 645 |  |  | Trial 646 |  |  | Trial 647 |  |  | Trial 648 |  |  | Trial 649 |  |  | Trial 650 |  |  | Trial 651 |  |  | Trial 652 |  |  | Trial 653 |  |  | Trial 654 |  |  | Trial 655 |  |  | Trial 656 |  |  | Trial 657 |  |  | Trial 658 |  |  | Trial 659 |  |  | Trial 660 |  |  | Trial 661 |  |  | Trial 662 |  |  | Trial 663 |  |  | Trial 664 |  |  | Trial 665 |  |  | Trial 666 |  |  | Trial 667 |  |  | Trial 668 |  |  | Trial 669 |  |  | Trial 670 |  |  | Trial 671 |  |  | Trial 672 |  |  | Trial 673 |  |  | Trial 674 |  |  | Trial 675 |  |  | Trial 676 |  |  | Trial 677 |  |  | Trial 678 |  |  | Trial 679 |  |  | Trial 680 |  |  | Trial 681 |  |  | Trial 682 |  |  | Trial 683 |  |  | Trial 684 |  |  | Trial 685 |  |  | Trial 686 |  |  | Trial 687 |  |  | Trial 688 |  |  | Trial 689 |  |  | Trial 690 |  |  | Trial 691 |  |  | Trial 692 |  |  | Trial 693 |  |  | Trial 694 |  |  | Trial 695 |  |  | Trial 696 |  |  | Trial 697 |  |  | Trial 698 |  |  | Trial 699 |  |  | Trial 700 |  |  | Trial 701 |  |  | Trial 702 |  |  | Trial 703 |  |  | Trial 704 |  |  | Trial 705 |  |  | Trial 706 |  |  | Trial 707 |  |  | Trial 708 |  |  | Trial 709 |  |  | Trial 710 |  |  | Trial 711 |  |  | Trial 712 |  |  | Trial 713 |  |  | Trial 714 |  |  | Trial 715 |  |  | Trial 716 |  |  | Trial 717 |  |  | Trial 718 |  |  | Trial 719 |  |  | Trial 720 |  |  | Trial 721 |  |  | Trial 722 |  |  | Trial 723 |  |  | Trial 724 |  |  | Trial 725 |  |  | Trial 726 |  |  | Trial 727 |  |  | Trial 728 |  |  | Trial 729 |  |  | Trial 730 |  |  | Trial 731 |  |  | Trial 732 |  |  | Trial 733 |  |  | Trial 734 |  |  | Trial 735 |  |  | Trial 736 |  |  | Trial 737 |  |  | Trial 738 |  |  | Trial 739 |  |  | Trial 740 |  |  | Trial 741 |  |  | Trial 742 |  |  | Trial 743 |  |  | Trial 744 |  |  | Trial 745 |  |  | Trial 746 |  |  | Trial 747 |  |  | Trial 748 |  |  | Trial 749 |  |  | Trial 750 |  |  | Trial 751 |  |  | Trial 752 |  |  | Trial 753 |  |  | Trial 754 |  |  | Trial 755 |  |  | Trial 756 |  |  | Trial 757 |  |  | Trial 758 |  |  | Trial 759 |  |  | Trial 760 |  |  | Trial 761 |  |  | Trial 762 |  |  | Trial 763 |  |  | Trial 764 |  |  | Trial 765 |  |  | Trial 766 |  |  | Trial 767 |  |  | Trial 768 |  |  | Trial 769 |  |  | Trial 770 |  |  | Trial 771 |  |  | Trial 772 |  |  | Trial 773 |  |  | Trial 774 |  |  | Trial 775 |  |  | Trial 776 |  |  | Trial 777 |  |  | Trial 778 |  |  | Trial 779 |  |  | Trial 780 |  |  | Trial 781 |  |  | Trial 782 |  |  | Trial 783 |  |  | Trial 784 |  |  | Trial 785 |  |  | Trial 786 |  |  | Trial 787 |  |  | Trial 788 |  |  | Trial 789 |  |  | Trial 790 |  |  | Trial 791 |  |  | Trial 792 |  |  | Trial 793 |  |  | Trial 794 |  |  | Trial 795 |  |  | Trial 796 |  |  | Trial 797 |  |  | Trial 798 |  |  | Trial 799 |  |  | Trial 800 |  |  | Trial 801 |  |  | Trial 802 |  |  | Trial 803 |  |  | Trial 804 |  |  | Trial 805 |  |  | Trial 806 |  |  | Trial 807 |  |  | Trial 808 |  |  | Trial 809 |  |  | Trial 810 |  |  | Trial 811 |  |  | Trial 812 |  |  | Trial 813 |  |  | Trial 814 |  |  | Trial 815 |  |  | Trial 816 |  |  | Trial 817 |  |  | Trial 818 |  |  | Trial 819 |  |  | Trial 820 |  |  | Trial 821 |  |  | Trial 822 |  |  | Trial 823 |  |  | Trial 824 |  |  | Trial 825 |  |  | Trial 826 |  |  | Trial 827 |  |  | Trial 828 |  |  | Trial 829 |  |  | Trial 830 |  |  | Trial 831 |  |  | Trial 832 |  |  | Trial 833 |  |  | Trial 834 |  |  | Trial 835 |  |  | Trial 836 |  |  | Trial 837 |  |  | Trial 838 |  |  | Trial 839 |  |  | Trial 840 |  |  | Trial 841 |  |  | Trial 842 |  |  | Trial 843 |  |  | Trial 844 |  |  | Trial 845 |  |  | Trial 846 |  |  | Trial 847 |  |  | Trial 848 |  |  | Trial 849 |  |  | Trial 850 |  |  | Trial 851 |  |  | Trial 852 |  |  | Trial 853 |  |  | Trial 854 |  |  | Trial 855 |  |  | Trial 856 |  |  | Trial 857 |  |  | Trial 858 |  |  | Trial 859 |  |  | Trial 860 |  |  | Trial 861 |  |  | Trial 862 |  |  | Trial 863 |  |  | Trial 864 |  |  | Trial 865 |  |  | Trial 866 |  |  | Trial 867 |  |  | Trial 868 |  |  | Trial 869 |  |  | Trial 870 |  |  | Trial 871 |  |  | Trial 872 |  |  | Trial 873 |  |  | Trial 874 |  |  | Trial 875 |  |  | Trial 876 |  |  | Trial 877 |  |  | Trial 878 |  |  | Trial 879 |  |  | Trial 880 |  |  | Trial 881 |  |  | Trial 882 |  |  | Trial 883 |  |  | Trial 884 |  |  | Trial 885 |  |  | Trial 886 |  |  | Trial 887 |  |  | Trial 888 |  |  | Trial 889 |  |  | Trial 890 |  |  | Trial 891 |  |  | Trial 892 |  |  | Trial 893 |  |  | Trial 894 |  |  | Trial 895 |  |  | Trial 896 |  |  | Trial 897 |  |  | Trial 898 |  |  | Trial 899 |  |  | Trial 900 |  |  | Trial 901 |  |  | Trial 902 |  |  | Trial 903 |  |  | Trial 904 |  |  | Trial 905 |  |  | Trial 906 |  |  | Trial 907 |  |  | Trial 908 |  |  | Trial 909 |  |  | Trial 910 |  |  | Trial 911 |  |  | Trial 912 |  |  | Trial 913 |  |  | Trial 914 |  |  | Trial 915 |  |  | Trial 916 |  |  | Trial 917 |  |  | Trial 918 |  |  | Trial 919 |  |  | Trial 920 |  |  | Trial 921 |  |  | Trial 922 |  |  | Trial 923 |  |  | Trial 924 |  |  | Trial 925 |  |  | Trial 926 |  |  | Trial 927 |  |  | Trial 928 |  |  | Trial 929 |  |  | Trial 930 |  |  | Trial 931 |  |  | Trial 932 |  |  | Trial 933 |  |  | Trial 934 |  |  | Trial 935 |  |  | Trial 936 |  |  | Trial 937 |  |  | Trial 938 |  |  | Trial 939 |  |  | Trial 940 |  |  | Trial 941 |  |  | Trial 942 |  |  | Trial 943 |  |  | Trial 944 |  |  | Trial 945 |  |  | Trial 946 |  |  | Trial 947 |  |  | Trial 948 |  |  | Trial 949 |  |  | Trial 950 |  |  | Trial 951 |  |  | Trial 952 |  |  | Trial 953 |  |  | Trial 954 |  |  | Trial 955 |  |  | Trial 956 |  |  | Trial 957 |  |  | Trial 958 |  |  | Trial 959 |  |  | Trial 960 |  |  | Trial 961 |  |  | Trial 962 |  |  | Trial 963 |  |  | Trial 964 |  |  | Trial 965 |  |  | Trial 966 |  |  | Trial 967 |  |  | Trial 968 |  |  | Trial 969 |  |  | Trial 970 |  |  | Trial 971 |  |  | Trial 972 |  |  | Trial 973 |  |  | Trial 974 |  |  | Trial 975 |  |  | Trial 976 |  |  | Trial 977 |  |  | Trial 978 |  |  | Trial 979 |  |  | Trial 980 |  |  | Trial 981 |  |  | Trial 982 |  |  | Trial 983 |  |  | Trial 984 |  |  | Trial 985 |  |  | Trial 986 |  |  | Trial 987 |  |  | Trial 988 |  |  | Trial 989 |  |  | Trial 990 |  |  | Trial 991 |  |  | Trial 992 |  |  | Trial 993 |  |  | Trial 994 |  |  | Trial 995 |  |  | Trial 996 |  |  | Trial 997 |  |  | Trial 998 |  |  | Trial 999 |  |  | Trial 1000
Iteration | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base
1 | 3 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47
2 | 2 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26
3 | 5 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39
4 | 4 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21
5 | 8 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39
6 | 3 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15
7 | 3 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29
8 | 5 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24
9 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39
10 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26
11 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39
12 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39
13 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24
14 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26
15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39
16 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15
17 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47
18 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47
19 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47
20 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39
21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39
22 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 8 | 12 | 24 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 8 | 12 | 24 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 3 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 8 | 12 | 24 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 8 | 12 | 24 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 1 | 23.5 | 47 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 2 | 13 | 26 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 2 | 13 | 26 | 1 | 23.5 | 47 | 2 | 13 | 26 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 8 | 12 | 24 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 2 | 13 | 26 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 2 | 13 | 26 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 8 | 12 | 24 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 8 | 12 | 24 | 8 | 12 | 24 | 2 | 13 | 26 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 8 | 12 | 24 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 8 | 12 | 24 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 8 | 12 | 24 | 1 | 23.5 | 47 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 6 | 7.5 | 15 | 2 | 13 | 26 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 2 | 13 | 26 | 2 | 13 | 26 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 2 | 13 | 26 | 1 | 23.5 | 47 | 8 | 12 | 24 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 7 | 14.5 | 29 | 2 | 13 | 26 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 2 | 13 | 26 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 2 | 13 | 26 | 2 | 13 | 26 | 4 | 10.5 | 21 | 2 | 13 | 26 | 8 | 12 | 24 | 3 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 8 | 12 | 24 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 8 | 12 | 24 | 5 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 2 | 13 | 26 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 8 | 12 | 24 | 3 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 8 | 12 | 24 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 2 | 13 | 26 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 2 | 13 | 26 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 8 | 12 | 24 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 2 | 13 | 26 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 3 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 2 | 13 | 26 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26
23 | 8 | 0 | 24 | 3 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 8 | 0 | 24 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 1 | 0 | 47 | 8 | 0 | 24 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 6 | 0 | 15 | 8 | 0 | 24 | 8 | 0 | 24 | 5 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 1 | 0 | 47 | 5 | 0 | 39 | 1 | 0 | 47 | 1 | 0 | 47 | 5 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 2 | 0 | 26 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 3 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 2 | 0 | 26 | 2 | 0 | 26 | 3 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 7 | 0 | 29 | 6 | 0 | 15 | 2 | 0 | 26 | 3 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 3 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 4 | 0 | 21 | 5 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 8 | 0 | 24 | 4 | 0 | 21 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 2 | 0 | 26 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 5 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 3 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 3 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 1 | 0 | 47 | 5 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 3 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 4 | 0 | 21 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 5 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 4 | 0 | 21 | 6 | 0 | 15 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 5 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 6 | 0 | 15 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 3 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 2 | 0 | 26 | 6 | 0 | 15 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 1 | 0 | 47 | 1 | 0 | 47 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 7 | 0 | 29 | 7 | 0 | 29 | 8 | 0 | 24 | 3 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 2 | 0 | 26 | 8 | 0 | 24 | 2 | 0 | 26 | 1 | 0 | 47 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 8 | 0 | 24 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 5 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 7 | 0 | 29 | 6 | 0 | 15 | 8 | 0 | 24 | 3 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 3 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 6 | 0 | 15 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 8 | 0 | 24 | 6 | 0 | 15 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 2 | 0 | 26 | 5 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 5 | 0 | 39 | 1 | 0 | 47 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 3 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 5 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 8 | 0 | 24 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 3 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 1 | 0 | 47 | 3 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 6 | 0 | 15 | 6 | 0 | 15 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 3 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 6 | 0 | 15 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 3 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 5 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 4 | 0 | 21 | 5 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 2 | 0 | 26 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 5 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 2 | 0 | 26 | 3 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 1 | 0 | 47 | 5 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 6 | 0 | 15 | 2 | 0 | 26 | 7 | 0 | 29 | 4 | 0 | 21 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 1 | 0 | 47 | 5 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 6 | 0 | 15 | 8 | 0 | 24 | 3 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 3 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 2 | 0 | 26 | 2 | 0 | 26 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 1 | 0 | 47 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 6 | 0 | 15 | 5 | 0 | 39 | 4 | 0 | 21 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 4 | 0 | 21 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 2 | 0 | 26 | 3 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 2 | 0 | 26 | 4 | 0 | 21 | 8 | 0 | 24 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 4 | 0 | 21 | 4 | 0 | 21 | 2 | 0 | 26 | 1 | 0 | 47 | 1 | 0 | 47 | 2 | 0 | 26 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 8 | 0 | 24 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 3 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 1 | 0 | 47 | 7 | 0 | 29 | 8 | 0 | 24 | 7 | 0 | 29 | 6 | 0 | 15 | 7 | 0 | 29 | 2 | 0 | 26 | 3 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 1 | 0 | 47 | 2 | 0 | 26 | 3 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 1 | 0 | 47 | 6 | 0 | 15 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 3 | 0 | 39 | 5 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 3 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 2 | 0 | 26 | 6 | 0 | 15 | 8 | 0 | 24 | 8 | 0 | 24 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 8 | 0 | 24 | 2 | 0 | 26 | 4 | 0 | 21 | 8 | 0 | 24 | 6 | 0 | 15 | 6 | 0 | 15 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 7 | 0 | 29 | 4 | 0 | 21 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 4 | 0 | 21 | 3 | 0 | 39 | 3 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 5 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 1 | 0 | 47 | 8 | 0 | 24 | 6 | 0 | 15 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 4 | 0 | 21 | 8 | 0 | 24 | 6 | 0 | 15 | 5 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 6 | 0 | 15 | 2 | 0 | 26 | 2 | 0 | 26 | 6 | 0 | 15 | 1 | 0 | 47 | 6 | 0 | 15 | 2 | 0 | 26 | 1 | 0 | 47 | 4 | 0 | 21 | 8 | 0 | 24 | 4 | 0 | 21 | 5 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 6 | 0 | 15 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 1 | 0 | 47 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 2 | 0 | 26 | 4 | 0 | 21 | 3 | 0 | 39 | 1 | 0 | 47 | 1 | 0 | 47 | 2 | 0 | 26 | 8 | 0 | 24 | 5 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 8 | 0 | 24 | 5 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 3 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 7 | 0 | 29 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 6 | 0 | 15 | 2 | 0 | 26 | 2 | 0 | 26 | 6 | 0 | 15 | 7 | 0 | 29 | 3 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 4 | 0 | 21 | 5 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 3 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 7 | 0 | 29 | 7 | 0 | 29 | 7 | 0 | 29 | 7 | 0 | 29
24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21
25 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26
26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39
27 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15
28 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29
29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24
30 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39
31 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47
32 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26
33 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15
34 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47
35 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47
36 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39
37 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26
38 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15
39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47
40 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21
41 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26
42 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39
43 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21
44 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21
45 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26
46 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39
47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24
48 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26
49 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21
50 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39
51 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24
52 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29
53 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29
54 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21
55 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26
56 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24
57 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39
58 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29
59 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47
60 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24
61 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15
62 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26
63 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47
64 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21
65 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24
66 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15
67 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39
68 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24
69 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29
70 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15
71 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26
72 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29
73 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47
74 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21
75 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47
76 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29
77 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47
78 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29
79 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21
80 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39
81 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21
82 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26
83 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26
84 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47
85 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47
86 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15
87 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29
88 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26
89 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15
90 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21
91 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21
92 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39
93 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47
94 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39
95 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47
96 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39
97 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24
98 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29
99 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39
100 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39
| Running Total for Trial 1 |  |  | Running Total for Trial 2 |  |  | Running Total for Trial 3 |  |  | Running Total for Trial 4 |  |  | Running Total for Trial 5 |  |  | Running Total for Trial 6 |  |  | Running Total for Trial 7 |  |  | Running Total for Trial 8 |  |  | Running Total for Trial 9 |  |  | Running Total for Trial 10 |  |  | Running Total for Trial 11 |  |  | Running Total for Trial 12 |  |  | Running Total for Trial 13 |  |  | Running Total for Trial 14 |  |  | Running Total for Trial 15 |  |  | Running Total for Trial 16 |  |  | Running Total for Trial 17 |  |  | Running Total for Trial 18 |  |  | Running Total for Trial 19 |  |  | Running Total for Trial 20 |  |  | Running Total for Trial 21 |  |  | Running Total for Trial 22 |  |  | Running Total for Trial 23 |  |  | Running Total for Trial 24 |  |  | Running Total for Trial 25 |  |  | Running Total for Trial 26 |  |  | Running Total for Trial 27 |  |  | Running Total for Trial 28 |  |  | Running Total for Trial 29 |  |  | Running Total for Trial 30 |  |  | Running Total for Trial 31 |  |  | Running Total for Trial 32 |  |  | Running Total for Trial 33 |  |  | Running Total for Trial 34 |  |  | Running Total for Trial 35 |  |  | Running Total for Trial 36 |  |  | Running Total for Trial 37 |  |  | Running Total for Trial 38 |  |  | Running Total for Trial 39 |  |  | Running Total for Trial 40 |  |  | Running Total for Trial 41 |  |  | Running Total for Trial 42 |  |  | Running Total for Trial 43 |  |  | Running Total for Trial 44 |  |  | Running Total for Trial 45 |  |  | Running Total for Trial 46 |  |  | Running Total for Trial 47 |  |  | Running Total for Trial 48 |  |  | Running Total for Trial 49 |  |  | Running Total for Trial 50 |  |  | Running Total for Trial 51 |  |  | Running Total for Trial 52 |  |  | Running Total for Trial 53 |  |  | Running Total for Trial 54 |  |  | Running Total for Trial 55 |  |  | Running Total for Trial 56 |  |  | Running Total for Trial 57 |  |  | Running Total for Trial 58 |  |  | Running Total for Trial 59 |  |  | Running Total for Trial 60 |  |  | Running Total for Trial 61 |  |  | Running Total for Trial 62 |  |  | Running Total for Trial 63 |  |  | Running Total for Trial 64 |  |  | Running Total for Trial 65 |  |  | Running Total for Trial 66 |  |  | Running Total for Trial 67 |  |  | Running Total for Trial 68 |  |  | Running Total for Trial 69 |  |  | Running Total for Trial 70 |  |  | Running Total for Trial 71 |  |  | Running Total for Trial 72 |  |  | Running Total for Trial 73 |  |  | Running Total for Trial 74 |  |  | Running Total for Trial 75 |  |  | Running Total for Trial 76 |  |  | Running Total for Trial 77 |  |  | Running Total for Trial 78 |  |  | Running Total for Trial 79 |  |  | Running Total for Trial 80 |  |  | Running Total for Trial 81 |  |  | Running Total for Trial 82 |  |  | Running Total for Trial 83 |  |  | Running Total for Trial 84 |  |  | Running Total for Trial 85 |  |  | Running Total for Trial 86 |  |  | Running Total for Trial 87 |  |  | Running Total for Trial 88 |  |  | Running Total for Trial 89 |  |  | Running Total for Trial 90 |  |  | Running Total for Trial 91 |  |  | Running Total for Trial 92 |  |  | Running Total for Trial 93 |  |  | Running Total for Trial 94 |  |  | Running Total for Trial 95 |  |  | Running Total for Trial 96 |  |  | Running Total for Trial 97 |  |  | Running Total for Trial 98 |  |  | Running Total for Trial 99 |  |  | Running Total for Trial 100 |  |  | Running Total for Trial 101 |  |  | Running Total for Trial 102 |  |  | Running Total for Trial 103 |  |  | Running Total for Trial 104 |  |  | Running Total for Trial 105 |  |  | Running Total for Trial 106 |  |  | Running Total for Trial 107 |  |  | Running Total for Trial 108 |  |  | Running Total for Trial 109 |  |  | Running Total for Trial 110 |  |  | Running Total for Trial 111 |  |  | Running Total for Trial 112 |  |  | Running Total for Trial 113 |  |  | Running Total for Trial 114 |  |  | Running Total for Trial 115 |  |  | Running Total for Trial 116 |  |  | Running Total for Trial 117 |  |  | Running Total for Trial 118 |  |  | Running Total for Trial 119 |  |  | Running Total for Trial 120 |  |  | Running Total for Trial 121 |  |  | Running Total for Trial 122 |  |  | Running Total for Trial 123 |  |  | Running Total for Trial 124 |  |  | Running Total for Trial 125 |  |  | Running Total for Trial 126 |  |  | Running Total for Trial 127 |  |  | Running Total for Trial 128 |  |  | Running Total for Trial 129 |  |  | Running Total for Trial 130 |  |  | Running Total for Trial 131 |  |  | Running Total for Trial 132 |  |  | Running Total for Trial 133 |  |  | Running Total for Trial 134 |  |  | Running Total for Trial 135 |  |  | Running Total for Trial 136 |  |  | Running Total for Trial 137 |  |  | Running Total for Trial 138 |  |  | Running Total for Trial 139 |  |  | Running Total for Trial 140 |  |  | Running Total for Trial 141 |  |  | Running Total for Trial 142 |  |  | Running Total for Trial 143 |  |  | Running Total for Trial 144 |  |  | Running Total for Trial 145 |  |  | Running Total for Trial 146 |  |  | Running Total for Trial 147 |  |  | Running Total for Trial 148 |  |  | Running Total for Trial 149 |  |  | Running Total for Trial 150 |  |  | Running Total for Trial 151 |  |  | Running Total for Trial 152 |  |  | Running Total for Trial 153 |  |  | Running Total for Trial 154 |  |  | Running Total for Trial 155 |  |  | Running Total for Trial 156 |  |  | Running Total for Trial 157 |  |  | Running Total for Trial 158 |  |  | Running Total for Trial 159 |  |  | Running Total for Trial 160 |  |  | Running Total for Trial 161 |  |  | Running Total for Trial 162 |  |  | Running Total for Trial 163 |  |  | Running Total for Trial 164 |  |  | Running Total for Trial 165 |  |  | Running Total for Trial 166 |  |  | Running Total for Trial 167 |  |  | Running Total for Trial 168 |  |  | Running Total for Trial 169 |  |  | Running Total for Trial 170 |  |  | Running Total for Trial 171 |  |  | Running Total for Trial 172 |  |  | Running Total for Trial 173 |  |  | Running Total for Trial 174 |  |  | Running Total for Trial 175 |  |  | Running Total for Trial 176 |  |  | Running Total for Trial 177 |  |  | Running Total for Trial 178 |  |  | Running Total for Trial 179 |  |  | Running Total for Trial 180 |  |  | Running Total for Trial 181 |  |  | Running Total for Trial 182 |  |  | Running Total for Trial 183 |  |  | Running Total for Trial 184 |  |  | Running Total for Trial 185 |  |  | Running Total for Trial 186 |  |  | Running Total for Trial 187 |  |  | Running Total for Trial 188 |  |  | Running Total for Trial 189 |  |  | Running Total for Trial 190 |  |  | Running Total for Trial 191 |  |  | Running Total for Trial 192 |  |  | Running Total for Trial 193 |  |  | Running Total for Trial 194 |  |  | Running Total for Trial 195 |  |  | Running Total for Trial 196 |  |  | Running Total for Trial 197 |  |  | Running Total for Trial 198 |  |  | Running Total for Trial 199 |  |  | Running Total for Trial 200 |  |  | Running Total for Trial 201 |  |  | Running Total for Trial 202 |  |  | Running Total for Trial 203 |  |  | Running Total for Trial 204 |  |  | Running Total for Trial 205 |  |  | Running Total for Trial 206 |  |  | Running Total for Trial 207 |  |  | Running Total for Trial 208 |  |  | Running Total for Trial 209 |  |  | Running Total for Trial 210 |  |  | Running Total for Trial 211 |  |  | Running Total for Trial 212 |  |  | Running Total for Trial 213 |  |  | Running Total for Trial 214 |  |  | Running Total for Trial 215 |  |  | Running Total for Trial 216 |  |  | Running Total for Trial 217 |  |  | Running Total for Trial 218 |  |  | Running Total for Trial 219 |  |  | Running Total for Trial 220 |  |  | Running Total for Trial 221 |  |  | Running Total for Trial 222 |  |  | Running Total for Trial 223 |  |  | Running Total for Trial 224 |  |  | Running Total for Trial 225 |  |  | Running Total for Trial 226 |  |  | Running Total for Trial 227 |  |  | Running Total for Trial 228 |  |  | Running Total for Trial 229 |  |  | Running Total for Trial 230 |  |  | Running Total for Trial 231 |  |  | Running Total for Trial 232 |  |  | Running Total for Trial 233 |  |  | Running Total for Trial 234 |  |  | Running Total for Trial 235 |  |  | Running Total for Trial 236 |  |  | Running Total for Trial 237 |  |  | Running Total for Trial 238 |  |  | Running Total for Trial 239 |  |  | Running Total for Trial 240 |  |  | Running Total for Trial 241 |  |  | Running Total for Trial 242 |  |  | Running Total for Trial 243 |  |  | Running Total for Trial 244 |  |  | Running Total for Trial 245 |  |  | Running Total for Trial 246 |  |  | Running Total for Trial 247 |  |  | Running Total for Trial 248 |  |  | Running Total for Trial 249 |  |  | Running Total for Trial 250 |  |  | Running Total for Trial 251 |  |  | Running Total for Trial 252 |  |  | Running Total for Trial 253 |  |  | Running Total for Trial 254 |  |  | Running Total for Trial 255 |  |  | Running Total for Trial 256 |  |  | Running Total for Trial 257 |  |  | Running Total for Trial 258 |  |  | Running Total for Trial 259 |  |  | Running Total for Trial 260 |  |  | Running Total for Trial 261 |  |  | Running Total for Trial 262 |  |  | Running Total for Trial 263 |  |  | Running Total for Trial 264 |  |  | Running Total for Trial 265 |  |  | Running Total for Trial 266 |  |  | Running Total for Trial 267 |  |  | Running Total for Trial 268 |  |  | Running Total for Trial 269 |  |  | Running Total for Trial 270 |  |  | Running Total for Trial 271 |  |  | Running Total for Trial 272 |  |  | Running Total for Trial 273 |  |  | Running Total for Trial 274 |  |  | Running Total for Trial 275 |  |  | Running Total for Trial 276 |  |  | Running Total for Trial 277 |  |  | Running Total for Trial 278 |  |  | Running Total for Trial 279 |  |  | Running Total for Trial 280 |  |  | Running Total for Trial 281 |  |  | Running Total for Trial 282 |  |  | Running Total for Trial 283 |  |  | Running Total for Trial 284 |  |  | Running Total for Trial 285 |  |  | Running Total for Trial 286 |  |  | Running Total for Trial 287 |  |  | Running Total for Trial 288 |  |  | Running Total for Trial 289 |  |  | Running Total for Trial 290 |  |  | Running Total for Trial 291 |  |  | Running Total for Trial 292 |  |  | Running Total for Trial 293 |  |  | Running Total for Trial 294 |  |  | Running Total for Trial 295 |  |  | Running Total for Trial 296 |  |  | Running Total for Trial 297 |  |  | Running Total for Trial 298 |  |  | Running Total for Trial 299 |  |  | Running Total for Trial 300 |  |  | Running Total for Trial 301 |  |  | Running Total for Trial 302 |  |  | Running Total for Trial 303 |  |  | Running Total for Trial 304 |  |  | Running Total for Trial 305 |  |  | Running Total for Trial 306 |  |  | Running Total for Trial 307 |  |  | Running Total for Trial 308 |  |  | Running Total for Trial 309 |  |  | Running Total for Trial 310 |  |  | Running Total for Trial 311 |  |  | Running Total for Trial 312 |  |  | Running Total for Trial 313 |  |  | Running Total for Trial 314 |  |  | Running Total for Trial 315 |  |  | Running Total for Trial 316 |  |  | Running Total for Trial 317 |  |  | Running Total for Trial 318 |  |  | Running Total for Trial 319 |  |  | Running Total for Trial 320 |  |  | Running Total for Trial 321 |  |  | Running Total for Trial 322 |  |  | Running Total for Trial 323 |  |  | Running Total for Trial 324 |  |  | Running Total for Trial 325 |  |  | Running Total for Trial 326 |  |  | Running Total for Trial 327 |  |  | Running Total for Trial 328 |  |  | Running Total for Trial 329 |  |  | Running Total for Trial 330 |  |  | Running Total for Trial 331 |  |  | Running Total for Trial 332 |  |  | Running Total for Trial 333 |  |  | Running Total for Trial 334 |  |  | Running Total for Trial 335 |  |  | Running Total for Trial 336 |  |  | Running Total for Trial 337 |  |  | Running Total for Trial 338 |  |  | Running Total for Trial 339 |  |  | Running Total for Trial 340 |  |  | Running Total for Trial 341 |  |  | Running Total for Trial 342 |  |  | Running Total for Trial 343 |  |  | Running Total for Trial 344 |  |  | Running Total for Trial 345 |  |  | Running Total for Trial 346 |  |  | Running Total for Trial 347 |  |  | Running Total for Trial 348 |  |  | Running Total for Trial 349 |  |  | Running Total for Trial 350 |  |  | Running Total for Trial 351 |  |  | Running Total for Trial 352 |  |  | Running Total for Trial 353 |  |  | Running Total for Trial 354 |  |  | Running Total for Trial 355 |  |  | Running Total for Trial 356 |  |  | Running Total for Trial 357 |  |  | Running Total for Trial 358 |  |  | Running Total for Trial 359 |  |  | Running Total for Trial 360 |  |  | Running Total for Trial 361 |  |  | Running Total for Trial 362 |  |  | Running Total for Trial 363 |  |  | Running Total for Trial 364 |  |  | Running Total for Trial 365 |  |  | Running Total for Trial 366 |  |  | Running Total for Trial 367 |  |  | Running Total for Trial 368 |  |  | Running Total for Trial 369 |  |  | Running Total for Trial 370 |  |  | Running Total for Trial 371 |  |  | Running Total for Trial 372 |  |  | Running Total for Trial 373 |  |  | Running Total for Trial 374 |  |  | Running Total for Trial 375 |  |  | Running Total for Trial 376 |  |  | Running Total for Trial 377 |  |  | Running Total for Trial 378 |  |  | Running Total for Trial 379 |  |  | Running Total for Trial 380 |  |  | Running Total for Trial 381 |  |  | Running Total for Trial 382 |  |  | Running Total for Trial 383 |  |  | Running Total for Trial 384 |  |  | Running Total for Trial 385 |  |  | Running Total for Trial 386 |  |  | Running Total for Trial 387 |  |  | Running Total for Trial 388 |  |  | Running Total for Trial 389 |  |  | Running Total for Trial 390 |  |  | Running Total for Trial 391 |  |  | Running Total for Trial 392 |  |  | Running Total for Trial 393 |  |  | Running Total for Trial 394 |  |  | Running Total for Trial 395 |  |  | Running Total for Trial 396 |  |  | Running Total for Trial 397 |  |  | Running Total for Trial 398 |  |  | Running Total for Trial 399 |  |  | Running Total for Trial 400 |  |  | Running Total for Trial 401 |  |  | Running Total for Trial 402 |  |  | Running Total for Trial 403 |  |  | Running Total for Trial 404 |  |  | Running Total for Trial 405 |  |  | Running Total for Trial 406 |  |  | Running Total for Trial 407 |  |  | Running Total for Trial 408 |  |  | Running Total for Trial 409 |  |  | Running Total for Trial 410 |  |  | Running Total for Trial 411 |  |  | Running Total for Trial 412 |  |  | Running Total for Trial 413 |  |  | Running Total for Trial 414 |  |  | Running Total for Trial 415 |  |  | Running Total for Trial 416 |  |  | Running Total for Trial 417 |  |  | Running Total for Trial 418 |  |  | Running Total for Trial 419 |  |  | Running Total for Trial 420 |  |  | Running Total for Trial 421 |  |  | Running Total for Trial 422 |  |  | Running Total for Trial 423 |  |  | Running Total for Trial 424 |  |  | Running Total for Trial 425 |  |  | Running Total for Trial 426 |  |  | Running Total for Trial 427 |  |  | Running Total for Trial 428 |  |  | Running Total for Trial 429 |  |  | Running Total for Trial 430 |  |  | Running Total for Trial 431 |  |  | Running Total for Trial 432 |  |  | Running Total for Trial 433 |  |  | Running Total for Trial 434 |  |  | Running Total for Trial 435 |  |  | Running Total for Trial 436 |  |  | Running Total for Trial 437 |  |  | Running Total for Trial 438 |  |  | Running Total for Trial 439 |  |  | Running Total for Trial 440 |  |  | Running Total for Trial 441 |  |  | Running Total for Trial 442 |  |  | Running Total for Trial 443 |  |  | Running Total for Trial 444 |  |  | Running Total for Trial 445 |  |  | Running Total for Trial 446 |  |  | Running Total for Trial 447 |  |  | Running Total for Trial 448 |  |  | Running Total for Trial 449 |  |  | Running Total for Trial 450 |  |  | Running Total for Trial 451 |  |  | Running Total for Trial 452 |  |  | Running Total for Trial 453 |  |  | Running Total for Trial 454 |  |  | Running Total for Trial 455 |  |  | Running Total for Trial 456 |  |  | Running Total for Trial 457 |  |  | Running Total for Trial 458 |  |  | Running Total for Trial 459 |  |  | Running Total for Trial 460 |  |  | Running Total for Trial 461 |  |  | Running Total for Trial 462 |  |  | Running Total for Trial 463 |  |  | Running Total for Trial 464 |  |  | Running Total for Trial 465 |  |  | Running Total for Trial 466 |  |  | Running Total for Trial 467 |  |  | Running Total for Trial 468 |  |  | Running Total for Trial 469 |  |  | Running Total for Trial 470 |  |  | Running Total for Trial 471 |  |  | Running Total for Trial 472 |  |  | Running Total for Trial 473 |  |  | Running Total for Trial 474 |  |  | Running Total for Trial 475 |  |  | Running Total for Trial 476 |  |  | Running Total for Trial 477 |  |  | Running Total for Trial 478 |  |  | Running Total for Trial 479 |  |  | Running Total for Trial 480 |  |  | Running Total for Trial 481 |  |  | Running Total for Trial 482 |  |  | Running Total for Trial 483 |  |  | Running Total for Trial 484 |  |  | Running Total for Trial 485 |  |  | Running Total for Trial 486 |  |  | Running Total for Trial 487 |  |  | Running Total for Trial 488 |  |  | Running Total for Trial 489 |  |  | Running Total for Trial 490 |  |  | Running Total for Trial 491 |  |  | Running Total for Trial 492 |  |  | Running Total for Trial 493 |  |  | Running Total for Trial 494 |  |  | Running Total for Trial 495 |  |  | Running Total for Trial 496 |  |  | Running Total for Trial 497 |  |  | Running Total for Trial 498 |  |  | Running Total for Trial 499 |  |  | Running Total for Trial 500 |  |  | Running Total for Trial 501 |  |  | Running Total for Trial 502 |  |  | Running Total for Trial 503 |  |  | Running Total for Trial 504 |  |  | Running Total for Trial 505 |  |  | Running Total for Trial 506 |  |  | Running Total for Trial 507 |  |  | Running Total for Trial 508 |  |  | Running Total for Trial 509 |  |  | Running Total for Trial 510 |  |  | Running Total for Trial 511 |  |  | Running Total for Trial 512 |  |  | Running Total for Trial 513 |  |  | Running Total for Trial 514 |  |  | Running Total for Trial 515 |  |  | Running Total for Trial 516 |  |  | Running Total for Trial 517 |  |  | Running Total for Trial 518 |  |  | Running Total for Trial 519 |  |  | Running Total for Trial 520 |  |  | Running Total for Trial 521 |  |  | Running Total for Trial 522 |  |  | Running Total for Trial 523 |  |  | Running Total for Trial 524 |  |  | Running Total for Trial 525 |  |  | Running Total for Trial 526 |  |  | Running Total for Trial 527 |  |  | Running Total for Trial 528 |  |  | Running Total for Trial 529 |  |  | Running Total for Trial 530 |  |  | Running Total for Trial 531 |  |  | Running Total for Trial 532 |  |  | Running Total for Trial 533 |  |  | Running Total for Trial 534 |  |  | Running Total for Trial 535 |  |  | Running Total for Trial 536 |  |  | Running Total for Trial 537 |  |  | Running Total for Trial 538 |  |  | Running Total for Trial 539 |  |  | Running Total for Trial 540 |  |  | Running Total for Trial 541 |  |  | Running Total for Trial 542 |  |  | Running Total for Trial 543 |  |  | Running Total for Trial 544 |  |  | Running Total for Trial 545 |  |  | Running Total for Trial 546 |  |  | Running Total for Trial 547 |  |  | Running Total for Trial 548 |  |  | Running Total for Trial 549 |  |  | Running Total for Trial 550 |  |  | Running Total for Trial 551 |  |  | Running Total for Trial 552 |  |  | Running Total for Trial 553 |  |  | Running Total for Trial 554 |  |  | Running Total for Trial 555 |  |  | Running Total for Trial 556 |  |  | Running Total for Trial 557 |  |  | Running Total for Trial 558 |  |  | Running Total for Trial 559 |  |  | Running Total for Trial 560 |  |  | Running Total for Trial 561 |  |  | Running Total for Trial 562 |  |  | Running Total for Trial 563 |  |  | Running Total for Trial 564 |  |  | Running Total for Trial 565 |  |  | Running Total for Trial 566 |  |  | Running Total for Trial 567 |  |  | Running Total for Trial 568 |  |  | Running Total for Trial 569 |  |  | Running Total for Trial 570 |  |  | Running Total for Trial 571 |  |  | Running Total for Trial 572 |  |  | Running Total for Trial 573 |  |  | Running Total for Trial 574 |  |  | Running Total for Trial 575 |  |  | Running Total for Trial 576 |  |  | Running Total for Trial 577 |  |  | Running Total for Trial 578 |  |  | Running Total for Trial 579 |  |  | Running Total for Trial 580 |  |  | Running Total for Trial 581 |  |  | Running Total for Trial 582 |  |  | Running Total for Trial 583 |  |  | Running Total for Trial 584 |  |  | Running Total for Trial 585 |  |  | Running Total for Trial 586 |  |  | Running Total for Trial 587 |  |  | Running Total for Trial 588 |  |  | Running Total for Trial 589 |  |  | Running Total for Trial 590 |  |  | Running Total for Trial 591 |  |  | Running Total for Trial 592 |  |  | Running Total for Trial 593 |  |  | Running Total for Trial 594 |  |  | Running Total for Trial 595 |  |  | Running Total for Trial 596 |  |  | Running Total for Trial 597 |  |  | Running Total for Trial 598 |  |  | Running Total for Trial 599 |  |  | Running Total for Trial 600 |  |  | Running Total for Trial 601 |  |  | Running Total for Trial 602 |  |  | Running Total for Trial 603 |  |  | Running Total for Trial 604 |  |  | Running Total for Trial 605 |  |  | Running Total for Trial 606 |  |  | Running Total for Trial 607 |  |  | Running Total for Trial 608 |  |  | Running Total for Trial 609 |  |  | Running Total for Trial 610 |  |  | Running Total for Trial 611 |  |  | Running Total for Trial 612 |  |  | Running Total for Trial 613 |  |  | Running Total for Trial 614 |  |  | Running Total for Trial 615 |  |  | Running Total for Trial 616 |  |  | Running Total for Trial 617 |  |  | Running Total for Trial 618 |  |  | Running Total for Trial 619 |  |  | Running Total for Trial 620 |  |  | Running Total for Trial 621 |  |  | Running Total for Trial 622 |  |  | Running Total for Trial 623 |  |  | Running Total for Trial 624 |  |  | Running Total for Trial 625 |  |  | Running Total for Trial 626 |  |  | Running Total for Trial 627 |  |  | Running Total for Trial 628 |  |  | Running Total for Trial 629 |  |  | Running Total for Trial 630 |  |  | Running Total for Trial 631 |  |  | Running Total for Trial 632 |  |  | Running Total for Trial 633 |  |  | Running Total for Trial 634 |  |  | Running Total for Trial 635 |  |  | Running Total for Trial 636 |  |  | Running Total for Trial 637 |  |  | Running Total for Trial 638 |  |  | Running Total for Trial 639 |  |  | Running Total for Trial 640 |  |  | Running Total for Trial 641 |  |  | Running Total for Trial 642 |  |  | Running Total for Trial 643 |  |  | Running Total for Trial 644 |  |  | Running Total for Trial 645 |  |  | Running Total for Trial 646 |  |  | Running Total for Trial 647 |  |  | Running Total for Trial 648 |  |  | Running Total for Trial 649 |  |  | Running Total for Trial 650 |  |  | Running Total for Trial 651 |  |  | Running Total for Trial 652 |  |  | Running Total for Trial 653 |  |  | Running Total for Trial 654 |  |  | Running Total for Trial 655 |  |  | Running Total for Trial 656 |  |  | Running Total for Trial 657 |  |  | Running Total for Trial 658 |  |  | Running Total for Trial 659 |  |  | Running Total for Trial 660 |  |  | Running Total for Trial 661 |  |  | Running Total for Trial 662 |  |  | Running Total for Trial 663 |  |  | Running Total for Trial 664 |  |  | Running Total for Trial 665 |  |  | Running Total for Trial 666 |  |  | Running Total for Trial 667 |  |  | Running Total for Trial 668 |  |  | Running Total for Trial 669 |  |  | Running Total for Trial 670 |  |  | Running Total for Trial 671 |  |  | Running Total for Trial 672 |  |  | Running Total for Trial 673 |  |  | Running Total for Trial 674 |  |  | Running Total for Trial 675 |  |  | Running Total for Trial 676 |  |  | Running Total for Trial 677 |  |  | Running Total for Trial 678 |  |  | Running Total for Trial 679 |  |  | Running Total for Trial 680 |  |  | Running Total for Trial 681 |  |  | Running Total for Trial 682 |  |  | Running Total for Trial 683 |  |  | Running Total for Trial 684 |  |  | Running Total for Trial 685 |  |  | Running Total for Trial 686 |  |  | Running Total for Trial 687 |  |  | Running Total for Trial 688 |  |  | Running Total for Trial 689 |  |  | Running Total for Trial 690 |  |  | Running Total for Trial 691 |  |  | Running Total for Trial 692 |  |  | Running Total for Trial 693 |  |  | Running Total for Trial 694 |  |  | Running Total for Trial 695 |  |  | Running Total for Trial 696 |  |  | Running Total for Trial 697 |  |  | Running Total for Trial 698 |  |  | Running Total for Trial 699 |  |  | Running Total for Trial 700 |  |  | Running Total for Trial 701 |  |  | Running Total for Trial 702 |  |  | Running Total for Trial 703 |  |  | Running Total for Trial 704 |  |  | Running Total for Trial 705 |  |  | Running Total for Trial 706 |  |  | Running Total for Trial 707 |  |  | Running Total for Trial 708 |  |  | Running Total for Trial 709 |  |  | Running Total for Trial 710 |  |  | Running Total for Trial 711 |  |  | Running Total for Trial 712 |  |  | Running Total for Trial 713 |  |  | Running Total for Trial 714 |  |  | Running Total for Trial 715 |  |  | Running Total for Trial 716 |  |  | Running Total for Trial 717 |  |  | Running Total for Trial 718 |  |  | Running Total for Trial 719 |  |  | Running Total for Trial 720 |  |  | Running Total for Trial 721 |  |  | Running Total for Trial 722 |  |  | Running Total for Trial 723 |  |  | Running Total for Trial 724 |  |  | Running Total for Trial 725 |  |  | Running Total for Trial 726 |  |  | Running Total for Trial 727 |  |  | Running Total for Trial 728 |  |  | Running Total for Trial 729 |  |  | Running Total for Trial 730 |  |  | Running Total for Trial 731 |  |  | Running Total for Trial 732 |  |  | Running Total for Trial 733 |  |  | Running Total for Trial 734 |  |  | Running Total for Trial 735 |  |  | Running Total for Trial 736 |  |  | Running Total for Trial 737 |  |  | Running Total for Trial 738 |  |  | Running Total for Trial 739 |  |  | Running Total for Trial 740 |  |  | Running Total for Trial 741 |  |  | Running Total for Trial 742 |  |  | Running Total for Trial 743 |  |  | Running Total for Trial 744 |  |  | Running Total for Trial 745 |  |  | Running Total for Trial 746 |  |  | Running Total for Trial 747 |  |  | Running Total for Trial 748 |  |  | Running Total for Trial 749 |  |  | Running Total for Trial 750 |  |  | Running Total for Trial 751 |  |  | Running Total for Trial 752 |  |  | Running Total for Trial 753 |  |  | Running Total for Trial 754 |  |  | Running Total for Trial 755 |  |  | Running Total for Trial 756 |  |  | Running Total for Trial 757 |  |  | Running Total for Trial 758 |  |  | Running Total for Trial 759 |  |  | Running Total for Trial 760 |  |  | Running Total for Trial 761 |  |  | Running Total for Trial 762 |  |  | Running Total for Trial 763 |  |  | Running Total for Trial 764 |  |  | Running Total for Trial 765 |  |  | Running Total for Trial 766 |  |  | Running Total for Trial 767 |  |  | Running Total for Trial 768 |  |  | Running Total for Trial 769 |  |  | Running Total for Trial 770 |  |  | Running Total for Trial 771 |  |  | Running Total for Trial 772 |  |  | Running Total for Trial 773 |  |  | Running Total for Trial 774 |  |  | Running Total for Trial 775 |  |  | Running Total for Trial 776 |  |  | Running Total for Trial 777 |  |  | Running Total for Trial 778 |  |  | Running Total for Trial 779 |  |  | Running Total for Trial 780 |  |  | Running Total for Trial 781 |  |  | Running Total for Trial 782 |  |  | Running Total for Trial 783 |  |  | Running Total for Trial 784 |  |  | Running Total for Trial 785 |  |  | Running Total for Trial 786 |  |  | Running Total for Trial 787 |  |  | Running Total for Trial 788 |  |  | Running Total for Trial 789 |  |  | Running Total for Trial 790 |  |  | Running Total for Trial 791 |  |  | Running Total for Trial 792 |  |  | Running Total for Trial 793 |  |  | Running Total for Trial 794 |  |  | Running Total for Trial 795 |  |  | Running Total for Trial 796 |  |  | Running Total for Trial 797 |  |  | Running Total for Trial 798 |  |  | Running Total for Trial 799 |  |  | Running Total for Trial 800 |  |  | Running Total for Trial 801 |  |  | Running Total for Trial 802 |  |  | Running Total for Trial 803 |  |  | Running Total for Trial 804 |  |  | Running Total for Trial 805 |  |  | Running Total for Trial 806 |  |  | Running Total for Trial 807 |  |  | Running Total for Trial 808 |  |  | Running Total for Trial 809 |  |  | Running Total for Trial 810 |  |  | Running Total for Trial 811 |  |  | Running Total for Trial 812 |  |  | Running Total for Trial 813 |  |  | Running Total for Trial 814 |  |  | Running Total for Trial 815 |  |  | Running Total for Trial 816 |  |  | Running Total for Trial 817 |  |  | Running Total for Trial 818 |  |  | Running Total for Trial 819 |  |  | Running Total for Trial 820 |  |  | Running Total for Trial 821 |  |  | Running Total for Trial 822 |  |  | Running Total for Trial 823 |  |  | Running Total for Trial 824 |  |  | Running Total for Trial 825 |  |  | Running Total for Trial 826 |  |  | Running Total for Trial 827 |  |  | Running Total for Trial 828 |  |  | Running Total for Trial 829 |  |  | Running Total for Trial 830 |  |  | Running Total for Trial 831 |  |  | Running Total for Trial 832 |  |  | Running Total for Trial 833 |  |  | Running Total for Trial 834 |  |  | Running Total for Trial 835 |  |  | Running Total for Trial 836 |  |  | Running Total for Trial 837 |  |  | Running Total for Trial 838 |  |  | Running Total for Trial 839 |  |  | Running Total for Trial 840 |  |  | Running Total for Trial 841 |  |  | Running Total for Trial 842 |  |  | Running Total for Trial 843 |  |  | Running Total for Trial 844 |  |  | Running Total for Trial 845 |  |  | Running Total for Trial 846 |  |  | Running Total for Trial 847 |  |  | Running Total for Trial 848 |  |  | Running Total for Trial 849 |  |  | Running Total for Trial 850 |  |  | Running Total for Trial 851 |  |  | Running Total for Trial 852 |  |  | Running Total for Trial 853 |  |  | Running Total for Trial 854 |  |  | Running Total for Trial 855 |  |  | Running Total for Trial 856 |  |  | Running Total for Trial 857 |  |  | Running Total for Trial 858 |  |  | Running Total for Trial 859 |  |  | Running Total for Trial 860 |  |  | Running Total for Trial 861 |  |  | Running Total for Trial 862 |  |  | Running Total for Trial 863 |  |  | Running Total for Trial 864 |  |  | Running Total for Trial 865 |  |  | Running Total for Trial 866 |  |  | Running Total for Trial 867 |  |  | Running Total for Trial 868 |  |  | Running Total for Trial 869 |  |  | Running Total for Trial 870 |  |  | Running Total for Trial 871 |  |  | Running Total for Trial 872 |  |  | Running Total for Trial 873 |  |  | Running Total for Trial 874 |  |  | Running Total for Trial 875 |  |  | Running Total for Trial 876 |  |  | Running Total for Trial 877 |  |  | Running Total for Trial 878 |  |  | Running Total for Trial 879 |  |  | Running Total for Trial 880 |  |  | Running Total for Trial 881 |  |  | Running Total for Trial 882 |  |  | Running Total for Trial 883 |  |  | Running Total for Trial 884 |  |  | Running Total for Trial 885 |  |  | Running Total for Trial 886 |  |  | Running Total for Trial 887 |  |  | Running Total for Trial 888 |  |  | Running Total for Trial 889 |  |  | Running Total for Trial 890 |  |  | Running Total for Trial 891 |  |  | Running Total for Trial 892 |  |  | Running Total for Trial 893 |  |  | Running Total for Trial 894 |  |  | Running Total for Trial 895 |  |  | Running Total for Trial 896 |  |  | Running Total for Trial 897 |  |  | Running Total for Trial 898 |  |  | Running Total for Trial 899 |  |  | Running Total for Trial 900 |  |  | Running Total for Trial 901 |  |  | Running Total for Trial 902 |  |  | Running Total for Trial 903 |  |  | Running Total for Trial 904 |  |  | Running Total for Trial 905 |  |  | Running Total for Trial 906 |  |  | Running Total for Trial 907 |  |  | Running Total for Trial 908 |  |  | Running Total for Trial 909 |  |  | Running Total for Trial 910 |  |  | Running Total for Trial 911 |  |  | Running Total for Trial 912 |  |  | Running Total for Trial 913 |  |  | Running Total for Trial 914 |  |  | Running Total for Trial 915 |  |  | Running Total for Trial 916 |  |  | Running Total for Trial 917 |  |  | Running Total for Trial 918 |  |  | Running Total for Trial 919 |  |  | Running Total for Trial 920 |  |  | Running Total for Trial 921 |  |  | Running Total for Trial 922 |  |  | Running Total for Trial 923 |  |  | Running Total for Trial 924 |  |  | Running Total for Trial 925 |  |  | Running Total for Trial 926 |  |  | Running Total for Trial 927 |  |  | Running Total for Trial 928 |  |  | Running Total for Trial 929 |  |  | Running Total for Trial 930 |  |  | Running Total for Trial 931 |  |  | Running Total for Trial 932 |  |  | Running Total for Trial 933 |  |  | Running Total for Trial 934 |  |  | Running Total for Trial 935 |  |  | Running Total for Trial 936 |  |  | Running Total for Trial 937 |  |  | Running Total for Trial 938 |  |  | Running Total for Trial 939 |  |  | Running Total for Trial 940 |  |  | Running Total for Trial 941 |  |  | Running Total for Trial 942 |  |  | Running Total for Trial 943 |  |  | Running Total for Trial 944 |  |  | Running Total for Trial 945 |  |  | Running Total for Trial 946 |  |  | Running Total for Trial 947 |  |  | Running Total for Trial 948 |  |  | Running Total for Trial 949 |  |  | Running Total for Trial 950 |  |  | Running Total for Trial 951 |  |  | Running Total for Trial 952 |  |  | Running Total for Trial 953 |  |  | Running Total for Trial 954 |  |  | Running Total for Trial 955 |  |  | Running Total for Trial 956 |  |  | Running Total for Trial 957 |  |  | Running Total for Trial 958 |  |  | Running Total for Trial 959 |  |  | Running Total for Trial 960 |  |  | Running Total for Trial 961 |  |  | Running Total for Trial 962 |  |  | Running Total for Trial 963 |  |  | Running Total for Trial 964 |  |  | Running Total for Trial 965 |  |  | Running Total for Trial 966 |  |  | Running Total for Trial 967 |  |  | Running Total for Trial 968 |  |  | Running Total for Trial 969 |  |  | Running Total for Trial 970 |  |  | Running Total for Trial 971 |  |  | Running Total for Trial 972 |  |  | Running Total for Trial 973 |  |  | Running Total for Trial 974 |  |  | Running Total for Trial 975 |  |  | Running Total for Trial 976 |  |  | Running Total for Trial 977 |  |  | Running Total for Trial 978 |  |  | Running Total for Trial 979 |  |  | Running Total for Trial 980 |  |  | Running Total for Trial 981 |  |  | Running Total for Trial 982 |  |  | Running Total for Trial 983 |  |  | Running Total for Trial 984 |  |  | Running Total for Trial 985 |  |  | Running Total for Trial 986 |  |  | Running Total for Trial 987 |  |  | Running Total for Trial 988 |  |  | Running Total for Trial 989 |  |  | Running Total for Trial 990 |  |  | Running Total for Trial 991 |  |  | Running Total for Trial 992 |  |  | Running Total for Trial 993 |  |  | Running Total for Trial 994 |  |  | Running Total for Trial 995 |  |  | Running Total for Trial 996 |  |  | Running Total for Trial 997 |  |  | Running Total for Trial 998 |  |  | Running Total for Trial 999 |  |  | Running Total for Trial 1000
1 |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47 |  |  | 47
2 |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73 |  |  | 73
3 |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112 |  |  | 112
4 |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133 |  |  | 133
5 |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172 |  |  | 172
6 |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187 |  |  | 187
7 |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216 |  |  | 216
8 |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240 |  |  | 240
9 |  | 269 |  |  | 279 |  |  | 269 |  |  | 269 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 269 |  |  | 279 |  |  | 264 |  |  | 266 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 266 |  |  | 261 |  |  | 255 |  |  | 261 |  |  | 255 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 264 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 287 |  |  | 261 |  |  | 264 |  |  | 266 |  |  | 264 |  |  | 269 |  |  | 255 |  |  | 266 |  |  | 255 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 269 |  |  | 255 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 266 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 266 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 266 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 287 |  |  | 266 |  |  | 264 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 269 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 266 |  |  | 266 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 266 |  |  | 255 |  |  | 269 |  |  | 269 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 255 |  |  | 264 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 255 |  |  | 264 |  |  | 269 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 255 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 261 |  |  | 261 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 287 |  |  | 261 |  |  | 255 |  |  | 269 |  |  | 264 |  |  | 261 |  |  | 261 |  |  | 266 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 255 |  |  | 287 |  |  | 261 |  |  | 261 |  |  | 255 |  |  | 287 |  |  | 287 |  |  | 287 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 255 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 261 |  |  | 266 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 269 |  |  | 269 |  |  | 287 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 255 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 269 |  |  | 261 |  |  | 261 |  |  | 264 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 261 |  |  | 287 |  |  | 255 |  |  | 269 |  |  | 255 |  |  | 287 |  |  | 266 |  |  | 269 |  |  | 264 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 269 |  |  | 255 |  |  | 264 |  |  | 279 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 266 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 261 |  |  | 287 |  |  | 261 |  |  | 264 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 264 |  |  | 279 |  |  | 287 |  |  | 264 |  |  | 255 |  |  | 261 |  |  | 266 |  |  | 255 |  |  | 264 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 264 |  |  | 261 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 255 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 264 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 255 |  |  | 287 |  |  | 266 |  |  | 266 |  |  | 287 |  |  | 266 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 255 |  |  | 264 |  |  | 266 |  |  | 269 |  |  | 255 |  |  | 264 |  |  | 279 |  |  | 261 |  |  | 266 |  |  | 287 |  |  | 255 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 261 |  |  | 266 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 264 |  |  | 264 |  |  | 261 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 266 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 287 |  |  | 261 |  |  | 269 |  |  | 261 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 255 |  |  | 279 |  |  | 261 |  |  | 266 |  |  | 264 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 266 |  |  | 266 |  |  | 264 |  |  | 264 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 287 |  |  | 269 |  |  | 255 |  |  | 269 |  |  | 269 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 261 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 266 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 261 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 264 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 266 |  |  | 269 |  |  | 287 |  |  | 264 |  |  | 266 |  |  | 269 |  |  | 266 |  |  | 269 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 255 |  |  | 287 |  |  | 269 |  |  | 266 |  |  | 269 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 255 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 261 |  |  | 255 |  |  | 261 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 264 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 287 |  |  | 269 |  |  | 287 |  |  | 287 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 264 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 264 |  |  | 269 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 287 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 287 |  |  | 261 |  |  | 266 |  |  | 261 |  |  | 261 |  |  | 266 |  |  | 255 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 261 |  |  | 261 |  |  | 255 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 266 |  |  | 261 |  |  | 266 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 255 |  |  | 255 |  |  | 261 |  |  | 261 |  |  | 261 |  |  | 261 |  |  | 269 |  |  | 255 |  |  | 255 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 266 |  |  | 264 |  |  | 279 |  |  | 287 |  |  | 255 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 255 |  |  | 287 |  |  | 264 |  |  | 255 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 264 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 261 |  |  | 269 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 261 |  |  | 266 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 264 |  |  | 279 |  |  | 264 |  |  | 255 |  |  | 269 |  |  | 261 |  |  | 264 |  |  | 255 |  |  | 266 |  |  | 266 |  |  | 266 |  |  | 264 |  |  | 266 |  |  | 261 |  |  | 264 |  |  | 261 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 255 |  |  | 287 |  |  | 255 |  |  | 266 |  |  | 266 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 269 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 264 |  |  | 287 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 264 |  |  | 261 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 287 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 264 |  |  | 269 |  |  | 269 |  |  | 264 |  |  | 266 |  |  | 269 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 287 |  |  | 287 |  |  | 261 |  |  | 287 |  |  | 287 |  |  | 255 |  |  | 255 |  |  | 269 |  |  | 287 |  |  | 255 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 287 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 279 |  |  | 264 |  |  | 287 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 266 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 255 |  |  | 279 |  |  | 269 |  |  | 261 |  |  | 266 |  |  | 269 |  |  | 255 |  |  | 264 |  |  | 266 |  |  | 261 |  |  | 264 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 269 |  |  | 279 |  |  | 266 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 266 |  |  | 279 |  |  | 255 |  |  | 266 |  |  | 264 |  |  | 279 |  |  | 264 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 269 |  |  | 264 |  |  | 255 |  |  | 261 |  |  | 287 |  |  | 264 |  |  | 266 |  |  | 287 |  |  | 261 |  |  | 287 |  |  | 269 |  |  | 287 |  |  | 264 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 261 |  |  | 266 |  |  | 255 |  |  | 266 |  |  | 255 |  |  | 255 |  |  | 261 |  |  | 266 |  |  | 269 |  |  | 269 |  |  | 261 |  |  | 279 |  |  | 279 |  |  | 261 |  |  | 261 |  |  | 287 |  |  | 255 |  |  | 266 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 269 |  |  | 279 |  |  | 261 |  |  | 279 |  |  | 255 |  |  | 287 |  |  | 279 |  |  | 255 |  |  | 287 |  |  | 269 |  |  | 266 |  |  | 269 |  |  | 287 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 264 |  |  | 266 |  |  | 279 |  |  | 266 |  |  | 266 |  |  | 266 |  |  | 266 |  |  | 264 |  |  | 269 |  |  | 287 |  |  | 269 |  |  | 261 |  |  | 255 |  |  | 287 |  |  | 264 |  |  | 287 |  |  | 269 |  |  | 266 |  |  | 287 |  |  | 264 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 287 |  |  | 269 |  |  | 255 |  |  | 279 |  |  | 279 |  |  | 279 |  |  | 255 |  |  | 264 |  |  | 261 |  |  | 264 |  |  | 269 |  |  | 266 |  |  | 279 |  |  | 279 |  |  | 264 |  |  | 266 |  |  | 279 |  |  | 279
10 |  | 290 |  |  | 318 |  |  | 308 |  |  | 290 |  |  | 326 |  |  | 285 |  |  | 318 |  |  | 302 |  |  | 334 |  |  | 303 |  |  | 287 |  |  | 294 |  |  | 302 |  |  | 281 |  |  | 316 |  |  | 318 |  |  | 290 |  |  | 292 |  |  | 311 |  |  | 276 |  |  | 300 |  |  | 284 |  |  | 318 |  |  | 302 |  |  | 290 |  |  | 300 |  |  | 294 |  |  | 279 |  |  | 292 |  |  | 276 |  |  | 276 |  |  | 300 |  |  | 281 |  |  | 313 |  |  | 295 |  |  | 326 |  |  | 305 |  |  | 295 |  |  | 305 |  |  | 300 |  |  | 300 |  |  | 316 |  |  | 303 |  |  | 281 |  |  | 326 |  |  | 326 |  |  | 293 |  |  | 300 |  |  | 313 |  |  | 300 |  |  | 303 |  |  | 305 |  |  | 303 |  |  | 293 |  |  | 276 |  |  | 281 |  |  | 294 |  |  | 303 |  |  | 308 |  |  | 326 |  |  | 318 |  |  | 313 |  |  | 305 |  |  | 300 |  |  | 279 |  |  | 298 |  |  | 316 |  |  | 294 |  |  | 300 |  |  | 313 |  |  | 318 |  |  | 318 |  |  | 308 |  |  | 302 |  |  | 294 |  |  | 287 |  |  | 305 |  |  | 282 |  |  | 281 |  |  | 294 |  |  | 302 |  |  | 305 |  |  | 308 |  |  | 300 |  |  | 300 |  |  | 295 |  |  | 326 |  |  | 313 |  |  | 284 |  |  | 318 |  |  | 292 |  |  | 294 |  |  | 284 |  |  | 300 |  |  | 290 |  |  | 292 |  |  | 294 |  |  | 290 |  |  | 308 |  |  | 279 |  |  | 295 |  |  | 313 |  |  | 294 |  |  | 318 |  |  | 313 |  |  | 308 |  |  | 305 |  |  | 334 |  |  | 326 |  |  | 313 |  |  | 311 |  |  | 318 |  |  | 311 |  |  | 318 |  |  | 292 |  |  | 293 |  |  | 293 |  |  | 303 |  |  | 311 |  |  | 308 |  |  | 326 |  |  | 290 |  |  | 305 |  |  | 290 |  |  | 298 |  |  | 316 |  |  | 287 |  |  | 313 |  |  | 302 |  |  | 308 |  |  | 293 |  |  | 303 |  |  | 298 |  |  | 292 |  |  | 294 |  |  | 288 |  |  | 308 |  |  | 313 |  |  | 318 |  |  | 285 |  |  | 300 |  |  | 294 |  |  | 282 |  |  | 308 |  |  | 303 |  |  | 326 |  |  | 305 |  |  | 300 |  |  | 284 |  |  | 334 |  |  | 308 |  |  | 288 |  |  | 290 |  |  | 316 |  |  | 318 |  |  | 334 |  |  | 300 |  |  | 281 |  |  | 295 |  |  | 294 |  |  | 305 |  |  | 308 |  |  | 303 |  |  | 316 |  |  | 281 |  |  | 276 |  |  | 316 |  |  | 308 |  |  | 281 |  |  | 308 |  |  | 282 |  |  | 300 |  |  | 305 |  |  | 300 |  |  | 276 |  |  | 311 |  |  | 326 |  |  | 326 |  |  | 294 |  |  | 318 |  |  | 294 |  |  | 300 |  |  | 284 |  |  | 281 |  |  | 279 |  |  | 303 |  |  | 308 |  |  | 303 |  |  | 300 |  |  | 318 |  |  | 303 |  |  | 293 |  |  | 318 |  |  | 302 |  |  | 305 |  |  | 284 |  |  | 282 |  |  | 284 |  |  | 303 |  |  | 305 |  |  | 326 |  |  | 287 |  |  | 287 |  |  | 287 |  |  | 311 |  |  | 334 |  |  | 305 |  |  | 279 |  |  | 318 |  |  | 308 |  |  | 308 |  |  | 313 |  |  | 298 |  |  | 302 |  |  | 326 |  |  | 313 |  |  | 300 |  |  | 294 |  |  | 290 |  |  | 311 |  |  | 300 |  |  | 276 |  |  | 292 |  |  | 279 |  |  | 290 |  |  | 282 |  |  | 311 |  |  | 293 |  |  | 294 |  |  | 308 |  |  | 303 |  |  | 276 |  |  | 294 |  |  | 311 |  |  | 300 |  |  | 300 |  |  | 281 |  |  | 334 |  |  | 316 |  |  | 316 |  |  | 293 |  |  | 288 |  |  | 326 |  |  | 303 |  |  | 308 |  |  | 316 |  |  | 326 |  |  | 294 |  |  | 294 |  |  | 300 |  |  | 295 |  |  | 284 |  |  | 285 |  |  | 313 |  |  | 290 |  |  | 295 |  |  | 303 |  |  | 284 |  |  | 279 |  |  | 313 |  |  | 326 |  |  | 279 |  |  | 308 |  |  | 294 |  |  | 305 |  |  | 284 |  |  | 298 |  |  | 326 |  |  | 284 |  |  | 318 |  |  | 318 |  |  | 287 |  |  | 313 |  |  | 290 |  |  | 294 |  |  | 318 |  |  | 298 |  |  | 311 |  |  | 281 |  |  | 288 |  |  | 303 |  |  | 316 |  |  | 318 |  |  | 295 |  |  | 316 |  |  | 316 |  |  | 334 |  |  | 326 |  |  | 284 |  |  | 290 |  |  | 326 |  |  | 302 |  |  | 302 |  |  | 300 |  |  | 300 |  |  | 295 |  |  | 308 |  |  | 290 |  |  | 276 |  |  | 293 |  |  | 305 |  |  | 270 |  |  | 279 |  |  | 287 |  |  | 311 |  |  | 294 |  |  | 308 |  |  | 281 |  |  | 326 |  |  | 313 |  |  | 298 |  |  | 311 |  |  | 308 |  |  | 308 |  |  | 300 |  |  | 298 |  |  | 298 |  |  | 294 |  |  | 293 |  |  | 303 |  |  | 282 |  |  | 311 |  |  | 285 |  |  | 290 |  |  | 308 |  |  | 290 |  |  | 305 |  |  | 303 |  |  | 308 |  |  | 313 |  |  | 316 |  |  | 308 |  |  | 334 |  |  | 287 |  |  | 303 |  |  | 284 |  |  | 326 |  |  | 305 |  |  | 316 |  |  | 318 |  |  | 318 |  |  | 276 |  |  | 287 |  |  | 300 |  |  | 308 |  |  | 285 |  |  | 303 |  |  | 318 |  |  | 326 |  |  | 293 |  |  | 276 |  |  | 282 |  |  | 290 |  |  | 276 |  |  | 293 |  |  | 276 |  |  | 293 |  |  | 334 |  |  | 305 |  |  | 279 |  |  | 285 |  |  | 287 |  |  | 290 |  |  | 334 |  |  | 305 |  |  | 318 |  |  | 292 |  |  | 270 |  |  | 302 |  |  | 300 |  |  | 284 |  |  | 308 |  |  | 303 |  |  | 276 |  |  | 285 |  |  | 326 |  |  | 300 |  |  | 302 |  |  | 311 |  |  | 287 |  |  | 287 |  |  | 326 |  |  | 290 |  |  | 295 |  |  | 279 |  |  | 308 |  |  | 308 |  |  | 326 |  |  | 284 |  |  | 290 |  |  | 285 |  |  | 302 |  |  | 303 |  |  | 290 |  |  | 318 |  |  | 326 |  |  | 334 |  |  | 300 |  |  | 308 |  |  | 298 |  |  | 334 |  |  | 287 |  |  | 302 |  |  | 303 |  |  | 326 |  |  | 279 |  |  | 292 |  |  | 281 |  |  | 290 |  |  | 305 |  |  | 293 |  |  | 284 |  |  | 303 |  |  | 308 |  |  | 276 |  |  | 295 |  |  | 302 |  |  | 294 |  |  | 295 |  |  | 326 |  |  | 285 |  |  | 316 |  |  | 303 |  |  | 326 |  |  | 302 |  |  | 318 |  |  | 279 |  |  | 290 |  |  | 305 |  |  | 305 |  |  | 313 |  |  | 308 |  |  | 287 |  |  | 326 |  |  | 279 |  |  | 316 |  |  | 308 |  |  | 326 |  |  | 285 |  |  | 290 |  |  | 308 |  |  | 284 |  |  | 326 |  |  | 308 |  |  | 290 |  |  | 285 |  |  | 290 |  |  | 282 |  |  | 287 |  |  | 302 |  |  | 326 |  |  | 287 |  |  | 303 |  |  | 326 |  |  | 293 |  |  | 290 |  |  | 311 |  |  | 279 |  |  | 313 |  |  | 285 |  |  | 288 |  |  | 316 |  |  | 294 |  |  | 311 |  |  | 279 |  |  | 308 |  |  | 300 |  |  | 284 |  |  | 285 |  |  | 293 |  |  | 305 |  |  | 305 |  |  | 302 |  |  | 292 |  |  | 308 |  |  | 292 |  |  | 305 |  |  | 308 |  |  | 294 |  |  | 294 |  |  | 305 |  |  | 293 |  |  | 300 |  |  | 279 |  |  | 303 |  |  | 300 |  |  | 305 |  |  | 311 |  |  | 281 |  |  | 300 |  |  | 285 |  |  | 303 |  |  | 316 |  |  | 287 |  |  | 308 |  |  | 305 |  |  | 316 |  |  | 292 |  |  | 295 |  |  | 305 |  |  | 288 |  |  | 279 |  |  | 308 |  |  | 305 |  |  | 313 |  |  | 311 |  |  | 316 |  |  | 270 |  |  | 308 |  |  | 295 |  |  | 294 |  |  | 287 |  |  | 318 |  |  | 279 |  |  | 295 |  |  | 285 |  |  | 300 |  |  | 308 |  |  | 303 |  |  | 279 |  |  | 290 |  |  | 313 |  |  | 302 |  |  | 316 |  |  | 303 |  |  | 303 |  |  | 326 |  |  | 300 |  |  | 281 |  |  | 287 |  |  | 303 |  |  | 308 |  |  | 308 |  |  | 290 |  |  | 303 |  |  | 294 |  |  | 305 |  |  | 290 |  |  | 305 |  |  | 318 |  |  | 294 |  |  | 300 |  |  | 300 |  |  | 294 |  |  | 287 |  |  | 298 |  |  | 316 |  |  | 288 |  |  | 281 |  |  | 316 |  |  | 290 |  |  | 316 |  |  | 326 |  |  | 300 |  |  | 293 |  |  | 318 |  |  | 334 |  |  | 276 |  |  | 318 |  |  | 326 |  |  | 300 |  |  | 298 |  |  | 279 |  |  | 281 |  |  | 313 |  |  | 295 |  |  | 281 |  |  | 308 |  |  | 300 |  |  | 298 |  |  | 318 |  |  | 284 |  |  | 284 |  |  | 300 |  |  | 318 |  |  | 313 |  |  | 318 |  |  | 287 |  |  | 308 |  |  | 305 |  |  | 298 |  |  | 276 |  |  | 282 |  |  | 318 |  |  | 318 |  |  | 276 |  |  | 290 |  |  | 302 |  |  | 300 |  |  | 285 |  |  | 290 |  |  | 303 |  |  | 302 |  |  | 292 |  |  | 290 |  |  | 279 |  |  | 287 |  |  | 318 |  |  | 281 |  |  | 305 |  |  | 281 |  |  | 302 |  |  | 295 |  |  | 316 |  |  | 326 |  |  | 313 |  |  | 287 |  |  | 318 |  |  | 311 |  |  | 295 |  |  | 285 |  |  | 308 |  |  | 308 |  |  | 295 |  |  | 279 |  |  | 290 |  |  | 294 |  |  | 285 |  |  | 303 |  |  | 308 |  |  | 281 |  |  | 313 |  |  | 326 |  |  | 318 |  |  | 326 |  |  | 318 |  |  | 290 |  |  | 292 |  |  | 334 |  |  | 298 |  |  | 313 |  |  | 300 |  |  | 294 |  |  | 294 |  |  | 318 |  |  | 302 |  |  | 334 |  |  | 276 |  |  | 305 |  |  | 300 |  |  | 287 |  |  | 313 |  |  | 276 |  |  | 326 |  |  | 313 |  |  | 279 |  |  | 285 |  |  | 276 |  |  | 279 |  |  | 294 |  |  | 302 |  |  | 300 |  |  | 281 |  |  | 303 |  |  | 326 |  |  | 311 |  |  | 276 |  |  | 282 |  |  | 318 |  |  | 302 |  |  | 287 |  |  | 300 |  |  | 281 |  |  | 270 |  |  | 308 |  |  | 318 |  |  | 303 |  |  | 318 |  |  | 326 |  |  | 326 |  |  | 276 |  |  | 326 |  |  | 285 |  |  | 302 |  |  | 279 |  |  | 287 |  |  | 282 |  |  | 282 |  |  | 276 |  |  | 293 |  |  | 294 |  |  | 302 |  |  | 294 |  |  | 326 |  |  | 305 |  |  | 290 |  |  | 313 |  |  | 288 |  |  | 303 |  |  | 316 |  |  | 294 |  |  | 303 |  |  | 276 |  |  | 305 |  |  | 303 |  |  | 290 |  |  | 300 |  |  | 300 |  |  | 303 |  |  | 298 |  |  | 300 |  |  | 287 |  |  | 334 |  |  | 303 |  |  | 284 |  |  | 326 |  |  | 305 |  |  | 285 |  |  | 279 |  |  | 305 |  |  | 305 |  |  | 308 |  |  | 284 |  |  | 316 |  |  | 303 |  |  | 276 |  |  | 318 |  |  | 276 |  |  | 305 |  |  | 288 |  |  | 276 |  |  | 318 |  |  | 294 |  |  | 300 |  |  | 282 |  |  | 308 |  |  | 334 |  |  | 295 |  |  | 326 |  |  | 303 |  |  | 284 |  |  | 313 |  |  | 287 |  |  | 290 |  |  | 318 |  |  | 294 |  |  | 334 |  |  | 276 |  |  | 295 |  |  | 298 |  |  | 326 |  |  | 308 |  |  | 318 |  |  | 308 |  |  | 326 |  |  | 285 |  |  | 288 |  |  | 305 |  |  | 288 |  |  | 294 |  |  | 290 |  |  | 287 |  |  | 303 |  |  | 279 |  |  | 295 |  |  | 292 |  |  | 287 |  |  | 285 |  |  | 313 |  |  | 300 |  |  | 288 |  |  | 300 |  |  | 308 |  |  | 316 |  |  | 305 |  |  | 294 |  |  | 311 |  |  | 279 |  |  | 287 |  |  | 305 |  |  | 318 |  |  | 290 |  |  | 316 |  |  | 316 |  |  | 308 |  |  | 294 |  |  | 308 |  |  | 303 |  |  | 303 |  |  | 311 |  |  | 326 |  |  | 292 |  |  | 308 |  |  | 285 |  |  | 293 |  |  | 326 |  |  | 293 |  |  | 279 |  |  | 282 |  |  | 302 |  |  | 318 |  |  | 290 |  |  | 281 |  |  | 313 |  |  | 318 |  |  | 292 |  |  | 326 |  |  | 305 |  |  | 318 |  |  | 290 |  |  | 294 |  |  | 326 |  |  | 282 |  |  | 318 |  |  | 308 |  |  | 326 |  |  | 290 |  |  | 302 |  |  | 284 |  |  | 294 |  |  | 305 |  |  | 292 |  |  | 290 |  |  | 300 |  |  | 308 |  |  | 270 |  |  | 293 |  |  | 311 |  |  | 311 |  |  | 308 |  |  | 305 |  |  | 308 |  |  | 298 |  |  | 308 |  |  | 303 |  |  | 303 |  |  | 293 |  |  | 290 |  |  | 303 |  |  | 292 |  |  | 290 |  |  | 334 |  |  | 305 |  |  | 294 |  |  | 302 |  |  | 316 |  |  | 300 |  |  | 313 |  |  | 313 |  |  | 302 |  |  | 276 |  |  | 308 |  |  | 311 |  |  | 281 |  |  | 292 |  |  | 326 |  |  | 294 |  |  | 290 |  |  | 316 |  |  | 282 |  |  | 308 |  |  | 308 |  |  | 290 |  |  | 302 |  |  | 288 |  |  | 300 |  |  | 290 |  |  | 300 |  |  | 326 |  |  | 311 |  |  | 334 |  |  | 305 |  |  | 334 |  |  | 303 |  |  | 292 |  |  | 300 |  |  | 318 |  |  | 276 |  |  | 326 |  |  | 294 |  |  | 303 |  |  | 290 |  |  | 285 |  |  | 292 |  |  | 316 |  |  | 294 |  |  | 288 |  |  | 290 |  |  | 276 |  |  | 303 |  |  | 308 |  |  | 284 |  |  | 326 |  |  | 326 |  |  | 308 |  |  | 334 |  |  | 298 |  |  | 285 |  |  | 326 |  |  | 326 |  |  | 293 |  |  | 303 |  |  | 290 |  |  | 281 |  |  | 285 |  |  | 302 |  |  | 292 |  |  | 308 |  |  | 276 |  |  | 281 |  |  | 279 |  |  | 305 |  |  | 303 |  |  | 305 |  |  | 300 |  |  | 305 |  |  | 284 |  |  | 293 |  |  | 276 |  |  | 290 |  |  | 302 |  |  | 303 |  |  | 295 |  |  | 326 |  |  | 300 |  |  | 334 |  |  | 293 |  |  | 308 |  |  | 303 |  |  | 295 |  |  | 282 |  |  | 305 |  |  | 300 |  |  | 292 |  |  | 294 |  |  | 281 |  |  | 281 |  |  | 302 |  |  | 300 |  |  | 295 |  |  | 293 |  |  | 293 |  |  | 290 |  |  | 294 |  |  | 308 |  |  | 308 |  |  | 300 |  |  | 334 |  |  | 270 |  |  | 305 |  |  | 311 |  |  | 318 |  |  | 294 |  |  | 308 |  |  | 326 |  |  | 282 |  |  | 303 |  |  | 279 |  |  | 334 |  |  | 326 |  |  | 284 |  |  | 326 |  |  | 308 |  |  | 292 |  |  | 316 |  |  | 316 |  |  | 305 |  |  | 305 |  |  | 305 |  |  | 293 |  |  | 290 |  |  | 318 |  |  | 290 |  |  | 290 |  |  | 292 |  |  | 305 |  |  | 303 |  |  | 290 |  |  | 311 |  |  | 295 |  |  | 287 |  |  | 302 |  |  | 326 |  |  | 288 |  |  | 308 |  |  | 316 |  |  | 292 |  |  | 316 |  |  | 290 |  |  | 303 |  |  | 294 |  |  | 318 |  |  | 302 |  |  | 298 |  |  | 284 |  |  | 300 |  |  | 318 |  |  | 300 |  |  | 281 |  |  | 288 |  |  | 276 |  |  | 288 |  |  | 284 |  |  | 305 |  |  | 318 |  |  | 318 |  |  | 311 |  |  | 290 |  |  | 318 |  |  | 305
11 |  | 319 |  |  | 357 |  |  | 334 |  |  | 305 |  |  | 350 |  |  | 324 |  |  | 342 |  |  | 323 |  |  | 358 |  |  | 342 |  |  | 334 |  |  | 333 |  |  | 349 |  |  | 307 |  |  | 331 |  |  | 357 |  |  | 329 |  |  | 321 |  |  | 350 |  |  | 291 |  |  | 339 |  |  | 313 |  |  | 339 |  |  | 326 |  |  | 316 |  |  | 321 |  |  | 333 |  |  | 318 |  |  | 331 |  |  | 315 |  |  | 302 |  |  | 326 |  |  | 307 |  |  | 352 |  |  | 319 |  |  | 352 |  |  | 344 |  |  | 319 |  |  | 329 |  |  | 347 |  |  | 329 |  |  | 342 |  |  | 350 |  |  | 328 |  |  | 365 |  |  | 352 |  |  | 319 |  |  | 324 |  |  | 328 |  |  | 339 |  |  | 324 |  |  | 329 |  |  | 332 |  |  | 317 |  |  | 315 |  |  | 296 |  |  | 315 |  |  | 342 |  |  | 337 |  |  | 365 |  |  | 342 |  |  | 342 |  |  | 344 |  |  | 324 |  |  | 303 |  |  | 337 |  |  | 337 |  |  | 318 |  |  | 339 |  |  | 337 |  |  | 347 |  |  | 347 |  |  | 329 |  |  | 349 |  |  | 333 |  |  | 326 |  |  | 329 |  |  | 329 |  |  | 320 |  |  | 315 |  |  | 317 |  |  | 334 |  |  | 329 |  |  | 347 |  |  | 347 |  |  | 334 |  |  | 365 |  |  | 342 |  |  | 308 |  |  | 347 |  |  | 339 |  |  | 318 |  |  | 323 |  |  | 324 |  |  | 319 |  |  | 321 |  |  | 315 |  |  | 337 |  |  | 329 |  |  | 294 |  |  | 324 |  |  | 328 |  |  | 323 |  |  | 342 |  |  | 334 |  |  | 332 |  |  | 329 |  |  | 373 |  |  | 365 |  |  | 360 |  |  | 332 |  |  | 344 |  |  | 337 |  |  | 357 |  |  | 331 |  |  | 332 |  |  | 332 |  |  | 332 |  |  | 350 |  |  | 355 |  |  | 365 |  |  | 316 |  |  | 320 |  |  | 329 |  |  | 324 |  |  | 337 |  |  | 308 |  |  | 360 |  |  | 317 |  |  | 332 |  |  | 314 |  |  | 327 |  |  | 319 |  |  | 316 |  |  | 318 |  |  | 317 |  |  | 347 |  |  | 360 |  |  | 357 |  |  | 311 |  |  | 339 |  |  | 318 |  |  | 329 |  |  | 347 |  |  | 318 |  |  | 373 |  |  | 326 |  |  | 339 |  |  | 299 |  |  | 363 |  |  | 347 |  |  | 314 |  |  | 319 |  |  | 355 |  |  | 357 |  |  | 373 |  |  | 315 |  |  | 310 |  |  | 334 |  |  | 318 |  |  | 320 |  |  | 332 |  |  | 318 |  |  | 340 |  |  | 320 |  |  | 291 |  |  | 342 |  |  | 347 |  |  | 310 |  |  | 337 |  |  | 321 |  |  | 329 |  |  | 320 |  |  | 315 |  |  | 297 |  |  | 335 |  |  | 365 |  |  | 350 |  |  | 333 |  |  | 342 |  |  | 333 |  |  | 324 |  |  | 310 |  |  | 305 |  |  | 294 |  |  | 342 |  |  | 355 |  |  | 332 |  |  | 315 |  |  | 342 |  |  | 324 |  |  | 322 |  |  | 339 |  |  | 317 |  |  | 331 |  |  | 305 |  |  | 303 |  |  | 313 |  |  | 324 |  |  | 334 |  |  | 347 |  |  | 313 |  |  | 334 |  |  | 302 |  |  | 335 |  |  | 373 |  |  | 344 |  |  | 318 |  |  | 333 |  |  | 337 |  |  | 355 |  |  | 328 |  |  | 337 |  |  | 341 |  |  | 347 |  |  | 352 |  |  | 326 |  |  | 333 |  |  | 316 |  |  | 337 |  |  | 324 |  |  | 315 |  |  | 316 |  |  | 303 |  |  | 329 |  |  | 321 |  |  | 335 |  |  | 319 |  |  | 341 |  |  | 323 |  |  | 324 |  |  | 302 |  |  | 320 |  |  | 337 |  |  | 329 |  |  | 347 |  |  | 320 |  |  | 355 |  |  | 331 |  |  | 345 |  |  | 317 |  |  | 312 |  |  | 352 |  |  | 342 |  |  | 329 |  |  | 342 |  |  | 341 |  |  | 315 |  |  | 323 |  |  | 339 |  |  | 319 |  |  | 308 |  |  | 309 |  |  | 337 |  |  | 329 |  |  | 334 |  |  | 327 |  |  | 299 |  |  | 308 |  |  | 337 |  |  | 350 |  |  | 303 |  |  | 347 |  |  | 341 |  |  | 334 |  |  | 331 |  |  | 313 |  |  | 373 |  |  | 308 |  |  | 357 |  |  | 365 |  |  | 326 |  |  | 360 |  |  | 319 |  |  | 333 |  |  | 342 |  |  | 345 |  |  | 332 |  |  | 320 |  |  | 312 |  |  | 350 |  |  | 355 |  |  | 339 |  |  | 342 |  |  | 337 |  |  | 345 |  |  | 360 |  |  | 355 |  |  | 310 |  |  | 314 |  |  | 355 |  |  | 326 |  |  | 341 |  |  | 329 |  |  | 339 |  |  | 342 |  |  | 332 |  |  | 311 |  |  | 302 |  |  | 308 |  |  | 320 |  |  | 309 |  |  | 308 |  |  | 302 |  |  | 337 |  |  | 318 |  |  | 332 |  |  | 305 |  |  | 347 |  |  | 352 |  |  | 345 |  |  | 358 |  |  | 323 |  |  | 329 |  |  | 347 |  |  | 337 |  |  | 327 |  |  | 315 |  |  | 319 |  |  | 350 |  |  | 308 |  |  | 350 |  |  | 332 |  |  | 337 |  |  | 347 |  |  | 329 |  |  | 329 |  |  | 342 |  |  | 355 |  |  | 360 |  |  | 363 |  |  | 347 |  |  | 360 |  |  | 308 |  |  | 350 |  |  | 331 |  |  | 350 |  |  | 320 |  |  | 345 |  |  | 347 |  |  | 333 |  |  | 300 |  |  | 313 |  |  | 315 |  |  | 334 |  |  | 324 |  |  | 350 |  |  | 357 |  |  | 350 |  |  | 322 |  |  | 323 |  |  | 303 |  |  | 311 |  |  | 300 |  |  | 322 |  |  | 291 |  |  | 332 |  |  | 360 |  |  | 326 |  |  | 308 |  |  | 332 |  |  | 326 |  |  | 305 |  |  | 358 |  |  | 326 |  |  | 342 |  |  | 316 |  |  | 294 |  |  | 317 |  |  | 339 |  |  | 313 |  |  | 355 |  |  | 350 |  |  | 302 |  |  | 309 |  |  | 365 |  |  | 326 |  |  | 331 |  |  | 350 |  |  | 302 |  |  | 316 |  |  | 373 |  |  | 329 |  |  | 324 |  |  | 326 |  |  | 332 |  |  | 332 |  |  | 365 |  |  | 305 |  |  | 337 |  |  | 309 |  |  | 341 |  |  | 329 |  |  | 337 |  |  | 344 |  |  | 347 |  |  | 358 |  |  | 321 |  |  | 355 |  |  | 337 |  |  | 360 |  |  | 326 |  |  | 323 |  |  | 350 |  |  | 365 |  |  | 303 |  |  | 331 |  |  | 305 |  |  | 329 |  |  | 352 |  |  | 317 |  |  | 308 |  |  | 332 |  |  | 334 |  |  | 305 |  |  | 316 |  |  | 349 |  |  | 318 |  |  | 334 |  |  | 350 |  |  | 332 |  |  | 331 |  |  | 342 |  |  | 350 |  |  | 328 |  |  | 357 |  |  | 300 |  |  | 316 |  |  | 329 |  |  | 334 |  |  | 352 |  |  | 355 |  |  | 308 |  |  | 350 |  |  | 308 |  |  | 345 |  |  | 337 |  |  | 365 |  |  | 324 |  |  | 314 |  |  | 323 |  |  | 331 |  |  | 373 |  |  | 329 |  |  | 337 |  |  | 311 |  |  | 337 |  |  | 297 |  |  | 326 |  |  | 331 |  |  | 355 |  |  | 302 |  |  | 324 |  |  | 352 |  |  | 340 |  |  | 316 |  |  | 350 |  |  | 300 |  |  | 328 |  |  | 300 |  |  | 327 |  |  | 363 |  |  | 323 |  |  | 335 |  |  | 294 |  |  | 323 |  |  | 326 |  |  | 299 |  |  | 311 |  |  | 332 |  |  | 331 |  |  | 352 |  |  | 331 |  |  | 313 |  |  | 323 |  |  | 321 |  |  | 331 |  |  | 332 |  |  | 333 |  |  | 333 |  |  | 329 |  |  | 340 |  |  | 326 |  |  | 318 |  |  | 342 |  |  | 329 |  |  | 320 |  |  | 358 |  |  | 302 |  |  | 326 |  |  | 324 |  |  | 324 |  |  | 355 |  |  | 326 |  |  | 329 |  |  | 344 |  |  | 340 |  |  | 331 |  |  | 316 |  |  | 329 |  |  | 317 |  |  | 326 |  |  | 355 |  |  | 344 |  |  | 328 |  |  | 350 |  |  | 363 |  |  | 285 |  |  | 329 |  |  | 334 |  |  | 320 |  |  | 334 |  |  | 365 |  |  | 318 |  |  | 321 |  |  | 306 |  |  | 339 |  |  | 337 |  |  | 324 |  |  | 308 |  |  | 311 |  |  | 334 |  |  | 341 |  |  | 355 |  |  | 342 |  |  | 350 |  |  | 365 |  |  | 315 |  |  | 328 |  |  | 326 |  |  | 342 |  |  | 323 |  |  | 332 |  |  | 311 |  |  | 324 |  |  | 341 |  |  | 329 |  |  | 314 |  |  | 320 |  |  | 357 |  |  | 333 |  |  | 321 |  |  | 339 |  |  | 318 |  |  | 316 |  |  | 322 |  |  | 331 |  |  | 314 |  |  | 320 |  |  | 331 |  |  | 329 |  |  | 355 |  |  | 355 |  |  | 339 |  |  | 308 |  |  | 339 |  |  | 373 |  |  | 315 |  |  | 344 |  |  | 347 |  |  | 324 |  |  | 337 |  |  | 303 |  |  | 320 |  |  | 352 |  |  | 334 |  |  | 328 |  |  | 347 |  |  | 321 |  |  | 337 |  |  | 342 |  |  | 323 |  |  | 305 |  |  | 326 |  |  | 357 |  |  | 360 |  |  | 342 |  |  | 326 |  |  | 347 |  |  | 344 |  |  | 345 |  |  | 305 |  |  | 321 |  |  | 339 |  |  | 347 |  |  | 315 |  |  | 329 |  |  | 341 |  |  | 315 |  |  | 314 |  |  | 314 |  |  | 329 |  |  | 326 |  |  | 331 |  |  | 319 |  |  | 300 |  |  | 313 |  |  | 347 |  |  | 307 |  |  | 326 |  |  | 296 |  |  | 317 |  |  | 310 |  |  | 331 |  |  | 365 |  |  | 342 |  |  | 326 |  |  | 342 |  |  | 350 |  |  | 324 |  |  | 309 |  |  | 355 |  |  | 347 |  |  | 316 |  |  | 300 |  |  | 337 |  |  | 323 |  |  | 314 |  |  | 318 |  |  | 323 |  |  | 302 |  |  | 334 |  |  | 352 |  |  | 357 |  |  | 365 |  |  | 347 |  |  | 311 |  |  | 313 |  |  | 360 |  |  | 337 |  |  | 337 |  |  | 347 |  |  | 333 |  |  | 320 |  |  | 357 |  |  | 331 |  |  | 363 |  |  | 302 |  |  | 329 |  |  | 326 |  |  | 326 |  |  | 342 |  |  | 300 |  |  | 355 |  |  | 337 |  |  | 326 |  |  | 309 |  |  | 291 |  |  | 326 |  |  | 318 |  |  | 341 |  |  | 329 |  |  | 305 |  |  | 332 |  |  | 355 |  |  | 350 |  |  | 297 |  |  | 311 |  |  | 342 |  |  | 317 |  |  | 334 |  |  | 339 |  |  | 296 |  |  | 317 |  |  | 332 |  |  | 347 |  |  | 329 |  |  | 357 |  |  | 350 |  |  | 373 |  |  | 315 |  |  | 365 |  |  | 309 |  |  | 328 |  |  | 303 |  |  | 334 |  |  | 321 |  |  | 321 |  |  | 302 |  |  | 322 |  |  | 341 |  |  | 326 |  |  | 318 |  |  | 373 |  |  | 331 |  |  | 337 |  |  | 334 |  |  | 317 |  |  | 327 |  |  | 345 |  |  | 333 |  |  | 342 |  |  | 300 |  |  | 326 |  |  | 342 |  |  | 337 |  |  | 347 |  |  | 315 |  |  | 342 |  |  | 337 |  |  | 326 |  |  | 302 |  |  | 373 |  |  | 332 |  |  | 305 |  |  | 355 |  |  | 326 |  |  | 311 |  |  | 318 |  |  | 326 |  |  | 331 |  |  | 334 |  |  | 331 |  |  | 331 |  |  | 329 |  |  | 315 |  |  | 342 |  |  | 297 |  |  | 329 |  |  | 327 |  |  | 305 |  |  | 357 |  |  | 333 |  |  | 339 |  |  | 311 |  |  | 329 |  |  | 355 |  |  | 310 |  |  | 352 |  |  | 324 |  |  | 299 |  |  | 352 |  |  | 316 |  |  | 316 |  |  | 339 |  |  | 315 |  |  | 349 |  |  | 291 |  |  | 334 |  |  | 337 |  |  | 365 |  |  | 355 |  |  | 365 |  |  | 337 |  |  | 365 |  |  | 311 |  |  | 309 |  |  | 329 |  |  | 314 |  |  | 320 |  |  | 316 |  |  | 326 |  |  | 342 |  |  | 300 |  |  | 321 |  |  | 313 |  |  | 326 |  |  | 309 |  |  | 339 |  |  | 329 |  |  | 317 |  |  | 339 |  |  | 347 |  |  | 342 |  |  | 352 |  |  | 315 |  |  | 332 |  |  | 308 |  |  | 316 |  |  | 326 |  |  | 342 |  |  | 337 |  |  | 345 |  |  | 337 |  |  | 347 |  |  | 323 |  |  | 323 |  |  | 342 |  |  | 342 |  |  | 337 |  |  | 352 |  |  | 318 |  |  | 334 |  |  | 306 |  |  | 340 |  |  | 355 |  |  | 340 |  |  | 318 |  |  | 311 |  |  | 331 |  |  | 347 |  |  | 316 |  |  | 305 |  |  | 337 |  |  | 339 |  |  | 313 |  |  | 341 |  |  | 329 |  |  | 357 |  |  | 337 |  |  | 320 |  |  | 347 |  |  | 321 |  |  | 333 |  |  | 332 |  |  | 365 |  |  | 314 |  |  | 349 |  |  | 308 |  |  | 341 |  |  | 331 |  |  | 331 |  |  | 329 |  |  | 339 |  |  | 355 |  |  | 299 |  |  | 340 |  |  | 337 |  |  | 326 |  |  | 323 |  |  | 320 |  |  | 334 |  |  | 337 |  |  | 332 |  |  | 318 |  |  | 318 |  |  | 340 |  |  | 329 |  |  | 318 |  |  | 321 |  |  | 319 |  |  | 355 |  |  | 344 |  |  | 309 |  |  | 331 |  |  | 331 |  |  | 339 |  |  | 352 |  |  | 337 |  |  | 326 |  |  | 297 |  |  | 347 |  |  | 332 |  |  | 320 |  |  | 331 |  |  | 347 |  |  | 333 |  |  | 311 |  |  | 345 |  |  | 306 |  |  | 347 |  |  | 355 |  |  | 311 |  |  | 341 |  |  | 303 |  |  | 339 |  |  | 337 |  |  | 329 |  |  | 352 |  |  | 350 |  |  | 381 |  |  | 331 |  |  | 373 |  |  | 342 |  |  | 318 |  |  | 339 |  |  | 344 |  |  | 323 |  |  | 347 |  |  | 309 |  |  | 350 |  |  | 329 |  |  | 300 |  |  | 313 |  |  | 342 |  |  | 341 |  |  | 335 |  |  | 337 |  |  | 300 |  |  | 324 |  |  | 323 |  |  | 299 |  |  | 352 |  |  | 347 |  |  | 337 |  |  | 373 |  |  | 327 |  |  | 309 |  |  | 341 |  |  | 365 |  |  | 322 |  |  | 318 |  |  | 319 |  |  | 310 |  |  | 311 |  |  | 349 |  |  | 313 |  |  | 355 |  |  | 323 |  |  | 328 |  |  | 318 |  |  | 344 |  |  | 318 |  |  | 326 |  |  | 339 |  |  | 344 |  |  | 323 |  |  | 314 |  |  | 300 |  |  | 314 |  |  | 331 |  |  | 350 |  |  | 321 |  |  | 365 |  |  | 324 |  |  | 360 |  |  | 332 |  |  | 332 |  |  | 342 |  |  | 310 |  |  | 321 |  |  | 334 |  |  | 347 |  |  | 339 |  |  | 309 |  |  | 296 |  |  | 305 |  |  | 323 |  |  | 339 |  |  | 316 |  |  | 308 |  |  | 319 |  |  | 311 |  |  | 333 |  |  | 323 |  |  | 332 |  |  | 315 |  |  | 358 |  |  | 291 |  |  | 329 |  |  | 326 |  |  | 357 |  |  | 341 |  |  | 355 |  |  | 350 |  |  | 329 |  |  | 329 |  |  | 326 |  |  | 373 |  |  | 373 |  |  | 308 |  |  | 347 |  |  | 334 |  |  | 339 |  |  | 337 |  |  | 355 |  |  | 334 |  |  | 331 |  |  | 352 |  |  | 317 |  |  | 319 |  |  | 357 |  |  | 329 |  |  | 311 |  |  | 321 |  |  | 326 |  |  | 327 |  |  | 337 |  |  | 350 |  |  | 334 |  |  | 326 |  |  | 328 |  |  | 355 |  |  | 314 |  |  | 323 |  |  | 331 |  |  | 316 |  |  | 337 |  |  | 337 |  |  | 350 |  |  | 333 |  |  | 347 |  |  | 328 |  |  | 324 |  |  | 299 |  |  | 339 |  |  | 339 |  |  | 329 |  |  | 328 |  |  | 335 |  |  | 291 |  |  | 317 |  |  | 310 |  |  | 352 |  |  | 344 |  |  | 342 |  |  | 358 |  |  | 319 |  |  | 339 |  |  | 344
12 |  | 358 |  |  | 396 |  |  | 373 |  |  | 320 |  |  | 397 |  |  | 363 |  |  | 368 |  |  | 362 |  |  | 397 |  |  | 381 |  |  | 381 |  |  | 380 |  |  | 396 |  |  | 346 |  |  | 357 |  |  | 381 |  |  | 344 |  |  | 360 |  |  | 389 |  |  | 330 |  |  | 354 |  |  | 352 |  |  | 386 |  |  | 365 |  |  | 331 |  |  | 350 |  |  | 354 |  |  | 347 |  |  | 370 |  |  | 330 |  |  | 331 |  |  | 373 |  |  | 322 |  |  | 367 |  |  | 334 |  |  | 373 |  |  | 383 |  |  | 334 |  |  | 344 |  |  | 376 |  |  | 368 |  |  | 389 |  |  | 371 |  |  | 367 |  |  | 404 |  |  | 378 |  |  | 340 |  |  | 363 |  |  | 349 |  |  | 363 |  |  | 363 |  |  | 376 |  |  | 371 |  |  | 338 |  |  | 330 |  |  | 311 |  |  | 344 |  |  | 363 |  |  | 384 |  |  | 404 |  |  | 381 |  |  | 363 |  |  | 359 |  |  | 353 |  |  | 342 |  |  | 352 |  |  | 361 |  |  | 357 |  |  | 368 |  |  | 366 |  |  | 386 |  |  | 386 |  |  | 344 |  |  | 375 |  |  | 372 |  |  | 352 |  |  | 368 |  |  | 368 |  |  | 346 |  |  | 354 |  |  | 346 |  |  | 355 |  |  | 355 |  |  | 376 |  |  | 373 |  |  | 373 |  |  | 391 |  |  | 363 |  |  | 334 |  |  | 362 |  |  | 360 |  |  | 347 |  |  | 362 |  |  | 363 |  |  | 366 |  |  | 342 |  |  | 354 |  |  | 376 |  |  | 358 |  |  | 333 |  |  | 350 |  |  | 375 |  |  | 370 |  |  | 389 |  |  | 360 |  |  | 361 |  |  | 376 |  |  | 420 |  |  | 404 |  |  | 381 |  |  | 371 |  |  | 383 |  |  | 352 |  |  | 383 |  |  | 370 |  |  | 353 |  |  | 347 |  |  | 353 |  |  | 389 |  |  | 394 |  |  | 404 |  |  | 342 |  |  | 349 |  |  | 355 |  |  | 353 |  |  | 358 |  |  | 329 |  |  | 407 |  |  | 356 |  |  | 358 |  |  | 361 |  |  | 356 |  |  | 366 |  |  | 342 |  |  | 347 |  |  | 338 |  |  | 386 |  |  | 381 |  |  | 378 |  |  | 326 |  |  | 365 |  |  | 339 |  |  | 368 |  |  | 394 |  |  | 344 |  |  | 397 |  |  | 350 |  |  | 365 |  |  | 325 |  |  | 378 |  |  | 373 |  |  | 353 |  |  | 345 |  |  | 384 |  |  | 386 |  |  | 397 |  |  | 344 |  |  | 331 |  |  | 358 |  |  | 339 |  |  | 359 |  |  | 347 |  |  | 365 |  |  | 364 |  |  | 335 |  |  | 315 |  |  | 363 |  |  | 368 |  |  | 357 |  |  | 363 |  |  | 360 |  |  | 353 |  |  | 359 |  |  | 344 |  |  | 344 |  |  | 364 |  |  | 389 |  |  | 389 |  |  | 359 |  |  | 389 |  |  | 354 |  |  | 345 |  |  | 331 |  |  | 344 |  |  | 309 |  |  | 363 |  |  | 376 |  |  | 347 |  |  | 362 |  |  | 368 |  |  | 348 |  |  | 343 |  |  | 354 |  |  | 338 |  |  | 370 |  |  | 334 |  |  | 342 |  |  | 360 |  |  | 371 |  |  | 363 |  |  | 362 |  |  | 352 |  |  | 349 |  |  | 326 |  |  | 364 |  |  | 399 |  |  | 373 |  |  | 365 |  |  | 372 |  |  | 376 |  |  | 379 |  |  | 354 |  |  | 363 |  |  | 370 |  |  | 386 |  |  | 376 |  |  | 350 |  |  | 372 |  |  | 355 |  |  | 361 |  |  | 348 |  |  | 341 |  |  | 342 |  |  | 342 |  |  | 344 |  |  | 350 |  |  | 364 |  |  | 348 |  |  | 380 |  |  | 349 |  |  | 348 |  |  | 349 |  |  | 335 |  |  | 376 |  |  | 376 |  |  | 394 |  |  | 344 |  |  | 394 |  |  | 352 |  |  | 384 |  |  | 338 |  |  | 336 |  |  | 381 |  |  | 368 |  |  | 376 |  |  | 389 |  |  | 365 |  |  | 341 |  |  | 352 |  |  | 368 |  |  | 366 |  |  | 329 |  |  | 333 |  |  | 352 |  |  | 353 |  |  | 355 |  |  | 374 |  |  | 325 |  |  | 337 |  |  | 358 |  |  | 371 |  |  | 327 |  |  | 394 |  |  | 367 |  |  | 373 |  |  | 378 |  |  | 334 |  |  | 388 |  |  | 323 |  |  | 404 |  |  | 389 |  |  | 341 |  |  | 384 |  |  | 366 |  |  | 372 |  |  | 381 |  |  | 366 |  |  | 353 |  |  | 335 |  |  | 327 |  |  | 376 |  |  | 381 |  |  | 354 |  |  | 366 |  |  | 376 |  |  | 384 |  |  | 386 |  |  | 402 |  |  | 334 |  |  | 361 |  |  | 379 |  |  | 373 |  |  | 367 |  |  | 376 |  |  | 360 |  |  | 381 |  |  | 347 |  |  | 350 |  |  | 317 |  |  | 329 |  |  | 359 |  |  | 335 |  |  | 355 |  |  | 326 |  |  | 366 |  |  | 347 |  |  | 353 |  |  | 352 |  |  | 373 |  |  | 373 |  |  | 369 |  |  | 405 |  |  | 338 |  |  | 358 |  |  | 386 |  |  | 366 |  |  | 348 |  |  | 362 |  |  | 366 |  |  | 376 |  |  | 334 |  |  | 389 |  |  | 347 |  |  | 376 |  |  | 386 |  |  | 355 |  |  | 353 |  |  | 389 |  |  | 394 |  |  | 375 |  |  | 402 |  |  | 362 |  |  | 399 |  |  | 355 |  |  | 397 |  |  | 352 |  |  | 397 |  |  | 346 |  |  | 384 |  |  | 362 |  |  | 372 |  |  | 329 |  |  | 334 |  |  | 344 |  |  | 355 |  |  | 363 |  |  | 389 |  |  | 404 |  |  | 389 |  |  | 337 |  |  | 370 |  |  | 329 |  |  | 358 |  |  | 326 |  |  | 369 |  |  | 315 |  |  | 371 |  |  | 389 |  |  | 355 |  |  | 323 |  |  | 347 |  |  | 373 |  |  | 326 |  |  | 405 |  |  | 350 |  |  | 363 |  |  | 342 |  |  | 318 |  |  | 338 |  |  | 386 |  |  | 352 |  |  | 381 |  |  | 389 |  |  | 326 |  |  | 330 |  |  | 380 |  |  | 350 |  |  | 352 |  |  | 374 |  |  | 341 |  |  | 355 |  |  | 402 |  |  | 358 |  |  | 350 |  |  | 341 |  |  | 358 |  |  | 371 |  |  | 404 |  |  | 344 |  |  | 366 |  |  | 356 |  |  | 367 |  |  | 368 |  |  | 358 |  |  | 365 |  |  | 376 |  |  | 397 |  |  | 368 |  |  | 394 |  |  | 358 |  |  | 389 |  |  | 355 |  |  | 347 |  |  | 371 |  |  | 386 |  |  | 342 |  |  | 370 |  |  | 326 |  |  | 355 |  |  | 376 |  |  | 332 |  |  | 355 |  |  | 371 |  |  | 381 |  |  | 331 |  |  | 342 |  |  | 375 |  |  | 333 |  |  | 358 |  |  | 371 |  |  | 371 |  |  | 370 |  |  | 371 |  |  | 389 |  |  | 352 |  |  | 386 |  |  | 339 |  |  | 340 |  |  | 368 |  |  | 373 |  |  | 381 |  |  | 370 |  |  | 355 |  |  | 374 |  |  | 337 |  |  | 384 |  |  | 376 |  |  | 404 |  |  | 339 |  |  | 353 |  |  | 347 |  |  | 357 |  |  | 412 |  |  | 344 |  |  | 366 |  |  | 350 |  |  | 376 |  |  | 323 |  |  | 355 |  |  | 346 |  |  | 384 |  |  | 328 |  |  | 363 |  |  | 391 |  |  | 361 |  |  | 355 |  |  | 365 |  |  | 339 |  |  | 352 |  |  | 339 |  |  | 374 |  |  | 410 |  |  | 347 |  |  | 356 |  |  | 323 |  |  | 349 |  |  | 347 |  |  | 320 |  |  | 350 |  |  | 379 |  |  | 378 |  |  | 376 |  |  | 370 |  |  | 342 |  |  | 349 |  |  | 360 |  |  | 355 |  |  | 371 |  |  | 372 |  |  | 372 |  |  | 368 |  |  | 361 |  |  | 341 |  |  | 365 |  |  | 389 |  |  | 350 |  |  | 341 |  |  | 405 |  |  | 326 |  |  | 373 |  |  | 353 |  |  | 350 |  |  | 379 |  |  | 365 |  |  | 376 |  |  | 368 |  |  | 369 |  |  | 352 |  |  | 355 |  |  | 344 |  |  | 346 |  |  | 365 |  |  | 381 |  |  | 373 |  |  | 354 |  |  | 397 |  |  | 402 |  |  | 332 |  |  | 350 |  |  | 373 |  |  | 359 |  |  | 373 |  |  | 380 |  |  | 357 |  |  | 360 |  |  | 345 |  |  | 378 |  |  | 352 |  |  | 363 |  |  | 347 |  |  | 358 |  |  | 360 |  |  | 388 |  |  | 379 |  |  | 366 |  |  | 397 |  |  | 404 |  |  | 341 |  |  | 343 |  |  | 355 |  |  | 389 |  |  | 362 |  |  | 358 |  |  | 332 |  |  | 348 |  |  | 370 |  |  | 358 |  |  | 353 |  |  | 341 |  |  | 381 |  |  | 372 |  |  | 347 |  |  | 360 |  |  | 342 |  |  | 345 |  |  | 343 |  |  | 370 |  |  | 340 |  |  | 341 |  |  | 357 |  |  | 353 |  |  | 379 |  |  | 394 |  |  | 363 |  |  | 337 |  |  | 378 |  |  | 420 |  |  | 336 |  |  | 373 |  |  | 386 |  |  | 339 |  |  | 376 |  |  | 327 |  |  | 359 |  |  | 376 |  |  | 349 |  |  | 349 |  |  | 394 |  |  | 368 |  |  | 384 |  |  | 357 |  |  | 347 |  |  | 326 |  |  | 373 |  |  | 378 |  |  | 381 |  |  | 363 |  |  | 341 |  |  | 362 |  |  | 370 |  |  | 366 |  |  | 352 |  |  | 342 |  |  | 368 |  |  | 371 |  |  | 339 |  |  | 344 |  |  | 380 |  |  | 330 |  |  | 343 |  |  | 329 |  |  | 368 |  |  | 365 |  |  | 378 |  |  | 358 |  |  | 321 |  |  | 342 |  |  | 386 |  |  | 331 |  |  | 365 |  |  | 322 |  |  | 356 |  |  | 357 |  |  | 370 |  |  | 389 |  |  | 363 |  |  | 365 |  |  | 366 |  |  | 397 |  |  | 339 |  |  | 335 |  |  | 384 |  |  | 394 |  |  | 342 |  |  | 326 |  |  | 384 |  |  | 362 |  |  | 338 |  |  | 357 |  |  | 338 |  |  | 349 |  |  | 363 |  |  | 399 |  |  | 383 |  |  | 391 |  |  | 386 |  |  | 326 |  |  | 360 |  |  | 399 |  |  | 376 |  |  | 376 |  |  | 371 |  |  | 372 |  |  | 359 |  |  | 396 |  |  | 357 |  |  | 402 |  |  | 317 |  |  | 376 |  |  | 341 |  |  | 347 |  |  | 366 |  |  | 329 |  |  | 402 |  |  | 384 |  |  | 350 |  |  | 333 |  |  | 330 |  |  | 365 |  |  | 333 |  |  | 380 |  |  | 344 |  |  | 352 |  |  | 361 |  |  | 394 |  |  | 371 |  |  | 336 |  |  | 350 |  |  | 381 |  |  | 338 |  |  | 358 |  |  | 386 |  |  | 335 |  |  | 364 |  |  | 358 |  |  | 376 |  |  | 344 |  |  | 378 |  |  | 389 |  |  | 412 |  |  | 336 |  |  | 386 |  |  | 324 |  |  | 354 |  |  | 327 |  |  | 363 |  |  | 360 |  |  | 368 |  |  | 331 |  |  | 348 |  |  | 362 |  |  | 365 |  |  | 342 |  |  | 397 |  |  | 357 |  |  | 363 |  |  | 349 |  |  | 356 |  |  | 348 |  |  | 374 |  |  | 372 |  |  | 381 |  |  | 329 |  |  | 373 |  |  | 371 |  |  | 361 |  |  | 386 |  |  | 354 |  |  | 363 |  |  | 384 |  |  | 365 |  |  | 331 |  |  | 388 |  |  | 379 |  |  | 329 |  |  | 376 |  |  | 373 |  |  | 350 |  |  | 333 |  |  | 350 |  |  | 378 |  |  | 349 |  |  | 355 |  |  | 370 |  |  | 358 |  |  | 354 |  |  | 381 |  |  | 312 |  |  | 376 |  |  | 342 |  |  | 352 |  |  | 386 |  |  | 372 |  |  | 360 |  |  | 340 |  |  | 344 |  |  | 394 |  |  | 334 |  |  | 381 |  |  | 339 |  |  | 325 |  |  | 367 |  |  | 340 |  |  | 355 |  |  | 365 |  |  | 341 |  |  | 370 |  |  | 330 |  |  | 355 |  |  | 366 |  |  | 386 |  |  | 370 |  |  | 386 |  |  | 361 |  |  | 386 |  |  | 350 |  |  | 348 |  |  | 355 |  |  | 338 |  |  | 349 |  |  | 345 |  |  | 355 |  |  | 368 |  |  | 339 |  |  | 345 |  |  | 342 |  |  | 365 |  |  | 324 |  |  | 363 |  |  | 368 |  |  | 341 |  |  | 363 |  |  | 386 |  |  | 363 |  |  | 391 |  |  | 339 |  |  | 353 |  |  | 355 |  |  | 342 |  |  | 355 |  |  | 371 |  |  | 361 |  |  | 369 |  |  | 361 |  |  | 394 |  |  | 349 |  |  | 362 |  |  | 389 |  |  | 389 |  |  | 376 |  |  | 373 |  |  | 347 |  |  | 349 |  |  | 321 |  |  | 387 |  |  | 381 |  |  | 361 |  |  | 357 |  |  | 358 |  |  | 370 |  |  | 368 |  |  | 342 |  |  | 344 |  |  | 376 |  |  | 360 |  |  | 360 |  |  | 380 |  |  | 344 |  |  | 372 |  |  | 366 |  |  | 344 |  |  | 386 |  |  | 347 |  |  | 348 |  |  | 347 |  |  | 391 |  |  | 343 |  |  | 388 |  |  | 355 |  |  | 367 |  |  | 352 |  |  | 346 |  |  | 368 |  |  | 365 |  |  | 384 |  |  | 323 |  |  | 387 |  |  | 352 |  |  | 365 |  |  | 362 |  |  | 341 |  |  | 358 |  |  | 352 |  |  | 371 |  |  | 347 |  |  | 357 |  |  | 379 |  |  | 355 |  |  | 357 |  |  | 350 |  |  | 358 |  |  | 394 |  |  | 383 |  |  | 324 |  |  | 360 |  |  | 360 |  |  | 386 |  |  | 399 |  |  | 366 |  |  | 347 |  |  | 326 |  |  | 394 |  |  | 356 |  |  | 367 |  |  | 355 |  |  | 371 |  |  | 372 |  |  | 350 |  |  | 374 |  |  | 353 |  |  | 362 |  |  | 376 |  |  | 350 |  |  | 380 |  |  | 318 |  |  | 363 |  |  | 358 |  |  | 368 |  |  | 399 |  |  | 389 |  |  | 410 |  |  | 346 |  |  | 412 |  |  | 357 |  |  | 357 |  |  | 365 |  |  | 373 |  |  | 349 |  |  | 371 |  |  | 348 |  |  | 397 |  |  | 368 |  |  | 329 |  |  | 352 |  |  | 357 |  |  | 388 |  |  | 374 |  |  | 384 |  |  | 339 |  |  | 353 |  |  | 362 |  |  | 320 |  |  | 399 |  |  | 373 |  |  | 352 |  |  | 420 |  |  | 353 |  |  | 356 |  |  | 370 |  |  | 386 |  |  | 361 |  |  | 344 |  |  | 366 |  |  | 349 |  |  | 335 |  |  | 388 |  |  | 360 |  |  | 394 |  |  | 347 |  |  | 349 |  |  | 357 |  |  | 383 |  |  | 357 |  |  | 352 |  |  | 378 |  |  | 383 |  |  | 352 |  |  | 338 |  |  | 347 |  |  | 329 |  |  | 355 |  |  | 371 |  |  | 350 |  |  | 391 |  |  | 339 |  |  | 389 |  |  | 379 |  |  | 371 |  |  | 381 |  |  | 349 |  |  | 336 |  |  | 355 |  |  | 373 |  |  | 378 |  |  | 338 |  |  | 335 |  |  | 320 |  |  | 344 |  |  | 368 |  |  | 331 |  |  | 323 |  |  | 366 |  |  | 350 |  |  | 372 |  |  | 344 |  |  | 379 |  |  | 354 |  |  | 379 |  |  | 312 |  |  | 368 |  |  | 365 |  |  | 396 |  |  | 380 |  |  | 370 |  |  | 371 |  |  | 350 |  |  | 355 |  |  | 365 |  |  | 412 |  |  | 420 |  |  | 334 |  |  | 386 |  |  | 360 |  |  | 386 |  |  | 376 |  |  | 394 |  |  | 363 |  |  | 370 |  |  | 381 |  |  | 332 |  |  | 334 |  |  | 372 |  |  | 353 |  |  | 335 |  |  | 336 |  |  | 355 |  |  | 351 |  |  | 366 |  |  | 371 |  |  | 355 |  |  | 365 |  |  | 343 |  |  | 394 |  |  | 343 |  |  | 349 |  |  | 370 |  |  | 355 |  |  | 363 |  |  | 363 |  |  | 379 |  |  | 359 |  |  | 371 |  |  | 367 |  |  | 363 |  |  | 338 |  |  | 378 |  |  | 354 |  |  | 376 |  |  | 343 |  |  | 361 |  |  | 315 |  |  | 346 |  |  | 331 |  |  | 378 |  |  | 373 |  |  | 363 |  |  | 397 |  |  | 348 |  |  | 378 |  |  | 383
13 |  | 382 |  |  | 425 |  |  | 397 |  |  | 349 |  |  | 444 |  |  | 384 |  |  | 397 |  |  | 388 |  |  | 436 |  |  | 405 |  |  | 420 |  |  | 419 |  |  | 422 |  |  | 367 |  |  | 372 |  |  | 428 |  |  | 373 |  |  | 384 |  |  | 436 |  |  | 354 |  |  | 375 |  |  | 381 |  |  | 407 |  |  | 386 |  |  | 357 |  |  | 379 |  |  | 375 |  |  | 394 |  |  | 399 |  |  | 345 |  |  | 346 |  |  | 412 |  |  | 346 |  |  | 382 |  |  | 363 |  |  | 412 |  |  | 404 |  |  | 360 |  |  | 391 |  |  | 405 |  |  | 394 |  |  | 413 |  |  | 392 |  |  | 414 |  |  | 425 |  |  | 417 |  |  | 379 |  |  | 384 |  |  | 388 |  |  | 392 |  |  | 384 |  |  | 402 |  |  | 386 |  |  | 385 |  |  | 369 |  |  | 340 |  |  | 359 |  |  | 378 |  |  | 423 |  |  | 433 |  |  | 396 |  |  | 384 |  |  | 385 |  |  | 368 |  |  | 381 |  |  | 373 |  |  | 390 |  |  | 383 |  |  | 392 |  |  | 387 |  |  | 433 |  |  | 415 |  |  | 359 |  |  | 414 |  |  | 419 |  |  | 376 |  |  | 394 |  |  | 383 |  |  | 367 |  |  | 383 |  |  | 361 |  |  | 379 |  |  | 394 |  |  | 391 |  |  | 397 |  |  | 412 |  |  | 420 |  |  | 384 |  |  | 360 |  |  | 388 |  |  | 375 |  |  | 362 |  |  | 377 |  |  | 389 |  |  | 392 |  |  | 381 |  |  | 393 |  |  | 400 |  |  | 405 |  |  | 348 |  |  | 376 |  |  | 414 |  |  | 409 |  |  | 404 |  |  | 375 |  |  | 390 |  |  | 405 |  |  | 449 |  |  | 419 |  |  | 410 |  |  | 395 |  |  | 422 |  |  | 367 |  |  | 422 |  |  | 409 |  |  | 382 |  |  | 368 |  |  | 377 |  |  | 404 |  |  | 433 |  |  | 443 |  |  | 381 |  |  | 388 |  |  | 394 |  |  | 400 |  |  | 405 |  |  | 368 |  |  | 431 |  |  | 371 |  |  | 373 |  |  | 408 |  |  | 395 |  |  | 405 |  |  | 389 |  |  | 371 |  |  | 367 |  |  | 425 |  |  | 410 |  |  | 417 |  |  | 373 |  |  | 389 |  |  | 360 |  |  | 397 |  |  | 415 |  |  | 383 |  |  | 436 |  |  | 397 |  |  | 389 |  |  | 349 |  |  | 399 |  |  | 412 |  |  | 379 |  |  | 371 |  |  | 410 |  |  | 425 |  |  | 418 |  |  | 373 |  |  | 370 |  |  | 373 |  |  | 365 |  |  | 398 |  |  | 386 |  |  | 380 |  |  | 379 |  |  | 364 |  |  | 330 |  |  | 384 |  |  | 389 |  |  | 396 |  |  | 378 |  |  | 375 |  |  | 379 |  |  | 383 |  |  | 368 |  |  | 368 |  |  | 385 |  |  | 410 |  |  | 413 |  |  | 388 |  |  | 428 |  |  | 401 |  |  | 384 |  |  | 370 |  |  | 391 |  |  | 330 |  |  | 392 |  |  | 400 |  |  | 386 |  |  | 409 |  |  | 407 |  |  | 363 |  |  | 382 |  |  | 375 |  |  | 359 |  |  | 396 |  |  | 381 |  |  | 357 |  |  | 384 |  |  | 418 |  |  | 387 |  |  | 401 |  |  | 381 |  |  | 364 |  |  | 373 |  |  | 403 |  |  | 420 |  |  | 412 |  |  | 394 |  |  | 387 |  |  | 397 |  |  | 394 |  |  | 375 |  |  | 387 |  |  | 394 |  |  | 410 |  |  | 400 |  |  | 397 |  |  | 393 |  |  | 394 |  |  | 400 |  |  | 395 |  |  | 380 |  |  | 381 |  |  | 357 |  |  | 383 |  |  | 376 |  |  | 403 |  |  | 377 |  |  | 395 |  |  | 370 |  |  | 369 |  |  | 373 |  |  | 382 |  |  | 402 |  |  | 415 |  |  | 409 |  |  | 373 |  |  | 423 |  |  | 367 |  |  | 408 |  |  | 385 |  |  | 375 |  |  | 407 |  |  | 415 |  |  | 415 |  |  | 428 |  |  | 386 |  |  | 367 |  |  | 376 |  |  | 415 |  |  | 405 |  |  | 350 |  |  | 372 |  |  | 367 |  |  | 392 |  |  | 370 |  |  | 413 |  |  | 364 |  |  | 363 |  |  | 373 |  |  | 395 |  |  | 356 |  |  | 433 |  |  | 406 |  |  | 412 |  |  | 404 |  |  | 360 |  |  | 427 |  |  | 349 |  |  | 443 |  |  | 413 |  |  | 380 |  |  | 423 |  |  | 395 |  |  | 419 |  |  | 428 |  |  | 381 |  |  | 382 |  |  | 356 |  |  | 366 |  |  | 423 |  |  | 410 |  |  | 393 |  |  | 392 |  |  | 405 |  |  | 431 |  |  | 425 |  |  | 431 |  |  | 355 |  |  | 390 |  |  | 408 |  |  | 388 |  |  | 388 |  |  | 391 |  |  | 407 |  |  | 405 |  |  | 394 |  |  | 389 |  |  | 356 |  |  | 376 |  |  | 383 |  |  | 374 |  |  | 394 |  |  | 355 |  |  | 395 |  |  | 394 |  |  | 368 |  |  | 381 |  |  | 388 |  |  | 388 |  |  | 408 |  |  | 444 |  |  | 359 |  |  | 397 |  |  | 412 |  |  | 387 |  |  | 387 |  |  | 401 |  |  | 392 |  |  | 391 |  |  | 381 |  |  | 413 |  |  | 386 |  |  | 391 |  |  | 415 |  |  | 381 |  |  | 377 |  |  | 428 |  |  | 441 |  |  | 401 |  |  | 426 |  |  | 401 |  |  | 438 |  |  | 376 |  |  | 418 |  |  | 381 |  |  | 423 |  |  | 372 |  |  | 413 |  |  | 383 |  |  | 411 |  |  | 368 |  |  | 381 |  |  | 383 |  |  | 402 |  |  | 402 |  |  | 404 |  |  | 443 |  |  | 415 |  |  | 384 |  |  | 409 |  |  | 376 |  |  | 405 |  |  | 365 |  |  | 408 |  |  | 344 |  |  | 410 |  |  | 418 |  |  | 370 |  |  | 349 |  |  | 373 |  |  | 412 |  |  | 365 |  |  | 444 |  |  | 374 |  |  | 392 |  |  | 366 |  |  | 333 |  |  | 353 |  |  | 425 |  |  | 381 |  |  | 396 |  |  | 428 |  |  | 365 |  |  | 351 |  |  | 427 |  |  | 389 |  |  | 367 |  |  | 400 |  |  | 362 |  |  | 370 |  |  | 417 |  |  | 405 |  |  | 371 |  |  | 362 |  |  | 397 |  |  | 397 |  |  | 451 |  |  | 373 |  |  | 381 |  |  | 395 |  |  | 414 |  |  | 415 |  |  | 397 |  |  | 404 |  |  | 423 |  |  | 426 |  |  | 383 |  |  | 433 |  |  | 405 |  |  | 415 |  |  | 384 |  |  | 386 |  |  | 410 |  |  | 425 |  |  | 381 |  |  | 409 |  |  | 355 |  |  | 376 |  |  | 415 |  |  | 353 |  |  | 394 |  |  | 400 |  |  | 396 |  |  | 360 |  |  | 357 |  |  | 396 |  |  | 354 |  |  | 379 |  |  | 397 |  |  | 397 |  |  | 391 |  |  | 395 |  |  | 428 |  |  | 399 |  |  | 407 |  |  | 360 |  |  | 369 |  |  | 389 |  |  | 399 |  |  | 410 |  |  | 399 |  |  | 379 |  |  | 413 |  |  | 363 |  |  | 410 |  |  | 400 |  |  | 433 |  |  | 363 |  |  | 374 |  |  | 394 |  |  | 372 |  |  | 438 |  |  | 365 |  |  | 405 |  |  | 389 |  |  | 405 |  |  | 338 |  |  | 381 |  |  | 375 |  |  | 408 |  |  | 367 |  |  | 378 |  |  | 415 |  |  | 382 |  |  | 376 |  |  | 404 |  |  | 354 |  |  | 391 |  |  | 386 |  |  | 400 |  |  | 439 |  |  | 362 |  |  | 382 |  |  | 349 |  |  | 375 |  |  | 371 |  |  | 335 |  |  | 389 |  |  | 418 |  |  | 399 |  |  | 402 |  |  | 409 |  |  | 381 |  |  | 388 |  |  | 407 |  |  | 384 |  |  | 392 |  |  | 419 |  |  | 387 |  |  | 407 |  |  | 400 |  |  | 365 |  |  | 389 |  |  | 428 |  |  | 365 |  |  | 356 |  |  | 452 |  |  | 341 |  |  | 388 |  |  | 392 |  |  | 365 |  |  | 418 |  |  | 391 |  |  | 423 |  |  | 389 |  |  | 390 |  |  | 381 |  |  | 379 |  |  | 359 |  |  | 385 |  |  | 389 |  |  | 407 |  |  | 388 |  |  | 378 |  |  | 436 |  |  | 426 |  |  | 379 |  |  | 397 |  |  | 402 |  |  | 374 |  |  | 397 |  |  | 395 |  |  | 381 |  |  | 389 |  |  | 369 |  |  | 393 |  |  | 376 |  |  | 378 |  |  | 368 |  |  | 397 |  |  | 386 |  |  | 412 |  |  | 408 |  |  | 390 |  |  | 412 |  |  | 451 |  |  | 380 |  |  | 364 |  |  | 379 |  |  | 428 |  |  | 383 |  |  | 405 |  |  | 356 |  |  | 363 |  |  | 385 |  |  | 379 |  |  | 368 |  |  | 362 |  |  | 405 |  |  | 398 |  |  | 376 |  |  | 399 |  |  | 357 |  |  | 360 |  |  | 382 |  |  | 391 |  |  | 369 |  |  | 370 |  |  | 386 |  |  | 382 |  |  | 418 |  |  | 433 |  |  | 402 |  |  | 361 |  |  | 399 |  |  | 446 |  |  | 362 |  |  | 394 |  |  | 410 |  |  | 365 |  |  | 402 |  |  | 374 |  |  | 398 |  |  | 391 |  |  | 364 |  |  | 375 |  |  | 433 |  |  | 415 |  |  | 423 |  |  | 372 |  |  | 371 |  |  | 341 |  |  | 394 |  |  | 402 |  |  | 407 |  |  | 387 |  |  | 380 |  |  | 409 |  |  | 385 |  |  | 395 |  |  | 367 |  |  | 371 |  |  | 407 |  |  | 392 |  |  | 378 |  |  | 365 |  |  | 406 |  |  | 359 |  |  | 390 |  |  | 344 |  |  | 392 |  |  | 380 |  |  | 417 |  |  | 397 |  |  | 360 |  |  | 381 |  |  | 433 |  |  | 378 |  |  | 391 |  |  | 369 |  |  | 371 |  |  | 381 |  |  | 409 |  |  | 413 |  |  | 378 |  |  | 389 |  |  | 392 |  |  | 426 |  |  | 386 |  |  | 359 |  |  | 408 |  |  | 418 |  |  | 368 |  |  | 373 |  |  | 423 |  |  | 401 |  |  | 367 |  |  | 396 |  |  | 377 |  |  | 373 |  |  | 402 |  |  | 425 |  |  | 404 |  |  | 415 |  |  | 425 |  |  | 365 |  |  | 399 |  |  | 438 |  |  | 391 |  |  | 415 |  |  | 386 |  |  | 387 |  |  | 398 |  |  | 411 |  |  | 372 |  |  | 441 |  |  | 338 |  |  | 400 |  |  | 362 |  |  | 386 |  |  | 392 |  |  | 353 |  |  | 441 |  |  | 431 |  |  | 389 |  |  | 380 |  |  | 351 |  |  | 391 |  |  | 362 |  |  | 409 |  |  | 359 |  |  | 391 |  |  | 387 |  |  | 409 |  |  | 410 |  |  | 362 |  |  | 389 |  |  | 405 |  |  | 362 |  |  | 379 |  |  | 425 |  |  | 364 |  |  | 379 |  |  | 382 |  |  | 391 |  |  | 368 |  |  | 417 |  |  | 404 |  |  | 451 |  |  | 365 |  |  | 425 |  |  | 339 |  |  | 401 |  |  | 374 |  |  | 389 |  |  | 386 |  |  | 383 |  |  | 352 |  |  | 363 |  |  | 377 |  |  | 412 |  |  | 368 |  |  | 444 |  |  | 386 |  |  | 378 |  |  | 373 |  |  | 395 |  |  | 369 |  |  | 403 |  |  | 401 |  |  | 420 |  |  | 376 |  |  | 402 |  |  | 410 |  |  | 382 |  |  | 410 |  |  | 369 |  |  | 389 |  |  | 405 |  |  | 380 |  |  | 370 |  |  | 427 |  |  | 418 |  |  | 376 |  |  | 415 |  |  | 394 |  |  | 374 |  |  | 359 |  |  | 371 |  |  | 399 |  |  | 364 |  |  | 384 |  |  | 394 |  |  | 382 |  |  | 393 |  |  | 410 |  |  | 333 |  |  | 405 |  |  | 363 |  |  | 399 |  |  | 425 |  |  | 393 |  |  | 384 |  |  | 379 |  |  | 373 |  |  | 420 |  |  | 363 |  |  | 405 |  |  | 363 |  |  | 354 |  |  | 393 |  |  | 366 |  |  | 394 |  |  | 404 |  |  | 356 |  |  | 409 |  |  | 354 |  |  | 394 |  |  | 381 |  |  | 410 |  |  | 409 |  |  | 412 |  |  | 400 |  |  | 433 |  |  | 389 |  |  | 372 |  |  | 394 |  |  | 362 |  |  | 388 |  |  | 374 |  |  | 384 |  |  | 389 |  |  | 363 |  |  | 384 |  |  | 381 |  |  | 404 |  |  | 363 |  |  | 410 |  |  | 397 |  |  | 380 |  |  | 402 |  |  | 415 |  |  | 389 |  |  | 406 |  |  | 368 |  |  | 374 |  |  | 370 |  |  | 357 |  |  | 402 |  |  | 418 |  |  | 382 |  |  | 393 |  |  | 400 |  |  | 409 |  |  | 396 |  |  | 401 |  |  | 418 |  |  | 418 |  |  | 402 |  |  | 412 |  |  | 368 |  |  | 388 |  |  | 347 |  |  | 402 |  |  | 410 |  |  | 400 |  |  | 372 |  |  | 397 |  |  | 409 |  |  | 392 |  |  | 381 |  |  | 368 |  |  | 405 |  |  | 399 |  |  | 399 |  |  | 419 |  |  | 391 |  |  | 396 |  |  | 405 |  |  | 383 |  |  | 412 |  |  | 362 |  |  | 387 |  |  | 386 |  |  | 406 |  |  | 372 |  |  | 409 |  |  | 381 |  |  | 406 |  |  | 367 |  |  | 372 |  |  | 407 |  |  | 412 |  |  | 423 |  |  | 338 |  |  | 413 |  |  | 381 |  |  | 389 |  |  | 409 |  |  | 370 |  |  | 387 |  |  | 376 |  |  | 392 |  |  | 362 |  |  | 396 |  |  | 394 |  |  | 394 |  |  | 378 |  |  | 376 |  |  | 384 |  |  | 423 |  |  | 422 |  |  | 371 |  |  | 407 |  |  | 381 |  |  | 401 |  |  | 446 |  |  | 390 |  |  | 362 |  |  | 373 |  |  | 418 |  |  | 377 |  |  | 406 |  |  | 394 |  |  | 410 |  |  | 393 |  |  | 389 |  |  | 389 |  |  | 392 |  |  | 377 |  |  | 405 |  |  | 376 |  |  | 419 |  |  | 357 |  |  | 410 |  |  | 397 |  |  | 397 |  |  | 446 |  |  | 410 |  |  | 431 |  |  | 393 |  |  | 438 |  |  | 386 |  |  | 396 |  |  | 394 |  |  | 394 |  |  | 388 |  |  | 410 |  |  | 377 |  |  | 421 |  |  | 394 |  |  | 358 |  |  | 367 |  |  | 386 |  |  | 403 |  |  | 403 |  |  | 423 |  |  | 360 |  |  | 379 |  |  | 386 |  |  | 367 |  |  | 414 |  |  | 397 |  |  | 373 |  |  | 435 |  |  | 374 |  |  | 395 |  |  | 409 |  |  | 415 |  |  | 385 |  |  | 370 |  |  | 413 |  |  | 370 |  |  | 364 |  |  | 427 |  |  | 384 |  |  | 423 |  |  | 373 |  |  | 364 |  |  | 381 |  |  | 398 |  |  | 396 |  |  | 399 |  |  | 417 |  |  | 407 |  |  | 381 |  |  | 359 |  |  | 371 |  |  | 376 |  |  | 384 |  |  | 395 |  |  | 389 |  |  | 412 |  |  | 360 |  |  | 413 |  |  | 405 |  |  | 395 |  |  | 396 |  |  | 388 |  |  | 351 |  |  | 384 |  |  | 420 |  |  | 407 |  |  | 359 |  |  | 374 |  |  | 359 |  |  | 370 |  |  | 415 |  |  | 346 |  |  | 352 |  |  | 405 |  |  | 389 |  |  | 398 |  |  | 373 |  |  | 408 |  |  | 393 |  |  | 408 |  |  | 341 |  |  | 397 |  |  | 391 |  |  | 435 |  |  | 401 |  |  | 417 |  |  | 410 |  |  | 389 |  |  | 394 |  |  | 386 |  |  | 433 |  |  | 444 |  |  | 358 |  |  | 433 |  |  | 375 |  |  | 425 |  |  | 391 |  |  | 420 |  |  | 410 |  |  | 409 |  |  | 420 |  |  | 356 |  |  | 358 |  |  | 396 |  |  | 368 |  |  | 361 |  |  | 360 |  |  | 402 |  |  | 377 |  |  | 413 |  |  | 410 |  |  | 384 |  |  | 404 |  |  | 390 |  |  | 409 |  |  | 367 |  |  | 373 |  |  | 396 |  |  | 370 |  |  | 402 |  |  | 378 |  |  | 418 |  |  | 380 |  |  | 410 |  |  | 391 |  |  | 392 |  |  | 385 |  |  | 399 |  |  | 393 |  |  | 400 |  |  | 367 |  |  | 385 |  |  | 341 |  |  | 385 |  |  | 370 |  |  | 399 |  |  | 402 |  |  | 410 |  |  | 423 |  |  | 372 |  |  | 407 |  |  | 407
14 |  | 397 |  |  | 454 |  |  | 444 |  |  | 370 |  |  | 468 |  |  | 410 |  |  | 436 |  |  | 435 |  |  | 460 |  |  | 434 |  |  | 435 |  |  | 458 |  |  | 461 |  |  | 414 |  |  | 387 |  |  | 443 |  |  | 397 |  |  | 405 |  |  | 465 |  |  | 375 |  |  | 414 |  |  | 405 |  |  | 428 |  |  | 407 |  |  | 386 |  |  | 400 |  |  | 399 |  |  | 420 |  |  | 438 |  |  | 366 |  |  | 370 |  |  | 436 |  |  | 370 |  |  | 411 |  |  | 389 |  |  | 433 |  |  | 425 |  |  | 386 |  |  | 415 |  |  | 420 |  |  | 409 |  |  | 452 |  |  | 439 |  |  | 443 |  |  | 454 |  |  | 464 |  |  | 405 |  |  | 423 |  |  | 409 |  |  | 407 |  |  | 423 |  |  | 428 |  |  | 407 |  |  | 424 |  |  | 398 |  |  | 366 |  |  | 388 |  |  | 417 |  |  | 452 |  |  | 454 |  |  | 420 |  |  | 413 |  |  | 409 |  |  | 415 |  |  | 402 |  |  | 394 |  |  | 416 |  |  | 407 |  |  | 421 |  |  | 416 |  |  | 448 |  |  | 436 |  |  | 383 |  |  | 435 |  |  | 458 |  |  | 415 |  |  | 418 |  |  | 407 |  |  | 391 |  |  | 404 |  |  | 400 |  |  | 403 |  |  | 409 |  |  | 406 |  |  | 423 |  |  | 436 |  |  | 459 |  |  | 423 |  |  | 389 |  |  | 403 |  |  | 404 |  |  | 386 |  |  | 403 |  |  | 415 |  |  | 407 |  |  | 420 |  |  | 432 |  |  | 447 |  |  | 420 |  |  | 374 |  |  | 415 |  |  | 435 |  |  | 433 |  |  | 443 |  |  | 422 |  |  | 405 |  |  | 444 |  |  | 488 |  |  | 440 |  |  | 449 |  |  | 434 |  |  | 448 |  |  | 406 |  |  | 451 |  |  | 424 |  |  | 397 |  |  | 392 |  |  | 392 |  |  | 443 |  |  | 462 |  |  | 458 |  |  | 420 |  |  | 427 |  |  | 423 |  |  | 426 |  |  | 452 |  |  | 392 |  |  | 446 |  |  | 410 |  |  | 394 |  |  | 434 |  |  | 419 |  |  | 420 |  |  | 436 |  |  | 386 |  |  | 414 |  |  | 440 |  |  | 449 |  |  | 446 |  |  | 412 |  |  | 428 |  |  | 389 |  |  | 426 |  |  | 454 |  |  | 398 |  |  | 483 |  |  | 423 |  |  | 428 |  |  | 364 |  |  | 428 |  |  | 459 |  |  | 405 |  |  | 397 |  |  | 439 |  |  | 464 |  |  | 442 |  |  | 394 |  |  | 394 |  |  | 412 |  |  | 391 |  |  | 419 |  |  | 415 |  |  | 419 |  |  | 403 |  |  | 411 |  |  | 369 |  |  | 405 |  |  | 428 |  |  | 420 |  |  | 399 |  |  | 399 |  |  | 408 |  |  | 398 |  |  | 407 |  |  | 397 |  |  | 414 |  |  | 434 |  |  | 439 |  |  | 414 |  |  | 457 |  |  | 448 |  |  | 408 |  |  | 399 |  |  | 430 |  |  | 351 |  |  | 431 |  |  | 424 |  |  | 433 |  |  | 424 |  |  | 422 |  |  | 384 |  |  | 406 |  |  | 422 |  |  | 398 |  |  | 425 |  |  | 396 |  |  | 372 |  |  | 413 |  |  | 465 |  |  | 416 |  |  | 440 |  |  | 405 |  |  | 390 |  |  | 402 |  |  | 442 |  |  | 435 |  |  | 427 |  |  | 409 |  |  | 426 |  |  | 418 |  |  | 409 |  |  | 422 |  |  | 402 |  |  | 415 |  |  | 425 |  |  | 426 |  |  | 412 |  |  | 432 |  |  | 423 |  |  | 439 |  |  | 424 |  |  | 406 |  |  | 405 |  |  | 386 |  |  | 407 |  |  | 405 |  |  | 424 |  |  | 424 |  |  | 424 |  |  | 409 |  |  | 408 |  |  | 397 |  |  | 429 |  |  | 449 |  |  | 444 |  |  | 430 |  |  | 420 |  |  | 470 |  |  | 406 |  |  | 434 |  |  | 432 |  |  | 414 |  |  | 446 |  |  | 462 |  |  | 439 |  |  | 449 |  |  | 433 |  |  | 396 |  |  | 402 |  |  | 441 |  |  | 429 |  |  | 379 |  |  | 396 |  |  | 388 |  |  | 416 |  |  | 409 |  |  | 439 |  |  | 393 |  |  | 387 |  |  | 420 |  |  | 442 |  |  | 380 |  |  | 472 |  |  | 445 |  |  | 451 |  |  | 419 |  |  | 407 |  |  | 451 |  |  | 388 |  |  | 464 |  |  | 437 |  |  | 395 |  |  | 470 |  |  | 419 |  |  | 443 |  |  | 443 |  |  | 420 |  |  | 411 |  |  | 395 |  |  | 413 |  |  | 449 |  |  | 439 |  |  | 422 |  |  | 418 |  |  | 420 |  |  | 446 |  |  | 464 |  |  | 452 |  |  | 381 |  |  | 437 |  |  | 423 |  |  | 435 |  |  | 403 |  |  | 412 |  |  | 431 |  |  | 426 |  |  | 415 |  |  | 428 |  |  | 377 |  |  | 415 |  |  | 398 |  |  | 421 |  |  | 420 |  |  | 379 |  |  | 421 |  |  | 433 |  |  | 415 |  |  | 420 |  |  | 417 |  |  | 403 |  |  | 429 |  |  | 483 |  |  | 398 |  |  | 444 |  |  | 451 |  |  | 416 |  |  | 408 |  |  | 440 |  |  | 416 |  |  | 430 |  |  | 407 |  |  | 452 |  |  | 401 |  |  | 417 |  |  | 430 |  |  | 396 |  |  | 424 |  |  | 449 |  |  | 462 |  |  | 440 |  |  | 473 |  |  | 425 |  |  | 462 |  |  | 397 |  |  | 457 |  |  | 407 |  |  | 449 |  |  | 393 |  |  | 428 |  |  | 422 |  |  | 450 |  |  | 397 |  |  | 407 |  |  | 422 |  |  | 428 |  |  | 441 |  |  | 428 |  |  | 490 |  |  | 430 |  |  | 405 |  |  | 438 |  |  | 397 |  |  | 444 |  |  | 391 |  |  | 432 |  |  | 383 |  |  | 434 |  |  | 439 |  |  | 385 |  |  | 388 |  |  | 402 |  |  | 427 |  |  | 394 |  |  | 483 |  |  | 398 |  |  | 407 |  |  | 381 |  |  | 357 |  |  | 392 |  |  | 454 |  |  | 428 |  |  | 420 |  |  | 457 |  |  | 391 |  |  | 366 |  |  | 474 |  |  | 404 |  |  | 406 |  |  | 447 |  |  | 391 |  |  | 394 |  |  | 456 |  |  | 426 |  |  | 400 |  |  | 377 |  |  | 412 |  |  | 412 |  |  | 472 |  |  | 399 |  |  | 407 |  |  | 416 |  |  | 453 |  |  | 439 |  |  | 412 |  |  | 428 |  |  | 462 |  |  | 465 |  |  | 412 |  |  | 448 |  |  | 420 |  |  | 444 |  |  | 410 |  |  | 433 |  |  | 436 |  |  | 451 |  |  | 420 |  |  | 456 |  |  | 384 |  |  | 397 |  |  | 444 |  |  | 392 |  |  | 415 |  |  | 424 |  |  | 411 |  |  | 384 |  |  | 386 |  |  | 435 |  |  | 393 |  |  | 408 |  |  | 426 |  |  | 436 |  |  | 438 |  |  | 410 |  |  | 467 |  |  | 428 |  |  | 431 |  |  | 407 |  |  | 408 |  |  | 415 |  |  | 425 |  |  | 439 |  |  | 423 |  |  | 403 |  |  | 460 |  |  | 392 |  |  | 434 |  |  | 421 |  |  | 472 |  |  | 389 |  |  | 389 |  |  | 418 |  |  | 419 |  |  | 462 |  |  | 404 |  |  | 444 |  |  | 428 |  |  | 426 |  |  | 362 |  |  | 428 |  |  | 396 |  |  | 447 |  |  | 396 |  |  | 393 |  |  | 441 |  |  | 408 |  |  | 405 |  |  | 443 |  |  | 369 |  |  | 412 |  |  | 407 |  |  | 439 |  |  | 465 |  |  | 386 |  |  | 429 |  |  | 396 |  |  | 390 |  |  | 410 |  |  | 361 |  |  | 428 |  |  | 457 |  |  | 423 |  |  | 423 |  |  | 448 |  |  | 420 |  |  | 412 |  |  | 422 |  |  | 431 |  |  | 421 |  |  | 434 |  |  | 402 |  |  | 454 |  |  | 415 |  |  | 389 |  |  | 436 |  |  | 454 |  |  | 412 |  |  | 385 |  |  | 499 |  |  | 367 |  |  | 414 |  |  | 431 |  |  | 380 |  |  | 447 |  |  | 406 |  |  | 447 |  |  | 428 |  |  | 419 |  |  | 402 |  |  | 400 |  |  | 374 |  |  | 424 |  |  | 418 |  |  | 433 |  |  | 427 |  |  | 417 |  |  | 465 |  |  | 465 |  |  | 418 |  |  | 436 |  |  | 423 |  |  | 413 |  |  | 423 |  |  | 421 |  |  | 405 |  |  | 418 |  |  | 395 |  |  | 417 |  |  | 405 |  |  | 407 |  |  | 415 |  |  | 412 |  |  | 407 |  |  | 441 |  |  | 447 |  |  | 437 |  |  | 441 |  |  | 466 |  |  | 419 |  |  | 390 |  |  | 405 |  |  | 475 |  |  | 398 |  |  | 444 |  |  | 382 |  |  | 402 |  |  | 432 |  |  | 400 |  |  | 397 |  |  | 391 |  |  | 434 |  |  | 419 |  |  | 405 |  |  | 438 |  |  | 383 |  |  | 386 |  |  | 403 |  |  | 438 |  |  | 390 |  |  | 396 |  |  | 401 |  |  | 406 |  |  | 444 |  |  | 462 |  |  | 426 |  |  | 400 |  |  | 438 |  |  | 485 |  |  | 409 |  |  | 420 |  |  | 457 |  |  | 404 |  |  | 449 |  |  | 413 |  |  | 445 |  |  | 420 |  |  | 403 |  |  | 404 |  |  | 472 |  |  | 436 |  |  | 462 |  |  | 387 |  |  | 410 |  |  | 356 |  |  | 441 |  |  | 417 |  |  | 446 |  |  | 434 |  |  | 404 |  |  | 430 |  |  | 400 |  |  | 434 |  |  | 396 |  |  | 410 |  |  | 436 |  |  | 407 |  |  | 425 |  |  | 380 |  |  | 427 |  |  | 383 |  |  | 429 |  |  | 391 |  |  | 413 |  |  | 419 |  |  | 432 |  |  | 444 |  |  | 375 |  |  | 428 |  |  | 457 |  |  | 402 |  |  | 417 |  |  | 384 |  |  | 400 |  |  | 420 |  |  | 448 |  |  | 452 |  |  | 417 |  |  | 436 |  |  | 421 |  |  | 465 |  |  | 425 |  |  | 380 |  |  | 447 |  |  | 457 |  |  | 389 |  |  | 399 |  |  | 449 |  |  | 430 |  |  | 406 |  |  | 435 |  |  | 424 |  |  | 402 |  |  | 428 |  |  | 472 |  |  | 428 |  |  | 436 |  |  | 446 |  |  | 389 |  |  | 438 |  |  | 462 |  |  | 406 |  |  | 462 |  |  | 415 |  |  | 426 |  |  | 419 |  |  | 458 |  |  | 393 |  |  | 488 |  |  | 367 |  |  | 424 |  |  | 409 |  |  | 410 |  |  | 431 |  |  | 392 |  |  | 462 |  |  | 478 |  |  | 413 |  |  | 395 |  |  | 372 |  |  | 420 |  |  | 383 |  |  | 456 |  |  | 398 |  |  | 438 |  |  | 411 |  |  | 433 |  |  | 434 |  |  | 391 |  |  | 415 |  |  | 444 |  |  | 383 |  |  | 426 |  |  | 440 |  |  | 403 |  |  | 400 |  |  | 403 |  |  | 415 |  |  | 397 |  |  | 456 |  |  | 419 |  |  | 477 |  |  | 412 |  |  | 446 |  |  | 360 |  |  | 448 |  |  | 400 |  |  | 428 |  |  | 433 |  |  | 398 |  |  | 378 |  |  | 389 |  |  | 416 |  |  | 427 |  |  | 392 |  |  | 465 |  |  | 415 |  |  | 393 |  |  | 412 |  |  | 421 |  |  | 384 |  |  | 424 |  |  | 430 |  |  | 459 |  |  | 391 |  |  | 417 |  |  | 449 |  |  | 429 |  |  | 431 |  |  | 416 |  |  | 410 |  |  | 434 |  |  | 395 |  |  | 391 |  |  | 456 |  |  | 465 |  |  | 397 |  |  | 454 |  |  | 409 |  |  | 398 |  |  | 398 |  |  | 395 |  |  | 428 |  |  | 390 |  |  | 410 |  |  | 441 |  |  | 397 |  |  | 432 |  |  | 436 |  |  | 354 |  |  | 434 |  |  | 387 |  |  | 423 |  |  | 464 |  |  | 419 |  |  | 413 |  |  | 418 |  |  | 420 |  |  | 446 |  |  | 402 |  |  | 444 |  |  | 402 |  |  | 393 |  |  | 417 |  |  | 413 |  |  | 441 |  |  | 451 |  |  | 385 |  |  | 448 |  |  | 383 |  |  | 420 |  |  | 428 |  |  | 439 |  |  | 433 |  |  | 427 |  |  | 439 |  |  | 459 |  |  | 404 |  |  | 393 |  |  | 423 |  |  | 386 |  |  | 409 |  |  | 413 |  |  | 399 |  |  | 428 |  |  | 402 |  |  | 399 |  |  | 420 |  |  | 433 |  |  | 410 |  |  | 425 |  |  | 444 |  |  | 401 |  |  | 449 |  |  | 454 |  |  | 428 |  |  | 432 |  |  | 407 |  |  | 413 |  |  | 396 |  |  | 386 |  |  | 441 |  |  | 447 |  |  | 429 |  |  | 440 |  |  | 426 |  |  | 448 |  |  | 425 |  |  | 416 |  |  | 447 |  |  | 433 |  |  | 423 |  |  | 433 |  |  | 394 |  |  | 427 |  |  | 386 |  |  | 423 |  |  | 431 |  |  | 429 |  |  | 411 |  |  | 444 |  |  | 430 |  |  | 431 |  |  | 407 |  |  | 397 |  |  | 452 |  |  | 423 |  |  | 423 |  |  | 458 |  |  | 406 |  |  | 417 |  |  | 452 |  |  | 422 |  |  | 438 |  |  | 391 |  |  | 426 |  |  | 412 |  |  | 421 |  |  | 411 |  |  | 424 |  |  | 428 |  |  | 435 |  |  | 382 |  |  | 419 |  |  | 433 |  |  | 459 |  |  | 449 |  |  | 362 |  |  | 452 |  |  | 420 |  |  | 413 |  |  | 433 |  |  | 391 |  |  | 411 |  |  | 405 |  |  | 431 |  |  | 377 |  |  | 417 |  |  | 409 |  |  | 418 |  |  | 425 |  |  | 415 |  |  | 399 |  |  | 470 |  |  | 448 |  |  | 395 |  |  | 454 |  |  | 402 |  |  | 425 |  |  | 475 |  |  | 414 |  |  | 383 |  |  | 388 |  |  | 447 |  |  | 401 |  |  | 421 |  |  | 433 |  |  | 439 |  |  | 432 |  |  | 410 |  |  | 428 |  |  | 439 |  |  | 392 |  |  | 429 |  |  | 397 |  |  | 445 |  |  | 404 |  |  | 457 |  |  | 418 |  |  | 423 |  |  | 475 |  |  | 425 |  |  | 457 |  |  | 440 |  |  | 459 |  |  | 410 |  |  | 425 |  |  | 420 |  |  | 433 |  |  | 409 |  |  | 425 |  |  | 403 |  |  | 460 |  |  | 409 |  |  | 397 |  |  | 382 |  |  | 425 |  |  | 427 |  |  | 450 |  |  | 447 |  |  | 399 |  |  | 408 |  |  | 425 |  |  | 406 |  |  | 453 |  |  | 421 |  |  | 388 |  |  | 482 |  |  | 398 |  |  | 421 |  |  | 424 |  |  | 441 |  |  | 432 |  |  | 385 |  |  | 437 |  |  | 396 |  |  | 411 |  |  | 456 |  |  | 399 |  |  | 470 |  |  | 388 |  |  | 390 |  |  | 396 |  |  | 413 |  |  | 422 |  |  | 438 |  |  | 446 |  |  | 422 |  |  | 402 |  |  | 383 |  |  | 397 |  |  | 423 |  |  | 423 |  |  | 410 |  |  | 428 |  |  | 451 |  |  | 389 |  |  | 428 |  |  | 426 |  |  | 434 |  |  | 417 |  |  | 427 |  |  | 390 |  |  | 431 |  |  | 435 |  |  | 428 |  |  | 398 |  |  | 398 |  |  | 388 |  |  | 399 |  |  | 441 |  |  | 385 |  |  | 376 |  |  | 444 |  |  | 428 |  |  | 424 |  |  | 402 |  |  | 432 |  |  | 408 |  |  | 447 |  |  | 356 |  |  | 421 |  |  | 415 |  |  | 482 |  |  | 427 |  |  | 432 |  |  | 434 |  |  | 418 |  |  | 409 |  |  | 425 |  |  | 480 |  |  | 483 |  |  | 405 |  |  | 472 |  |  | 422 |  |  | 454 |  |  | 415 |  |  | 446 |  |  | 431 |  |  | 448 |  |  | 441 |  |  | 395 |  |  | 373 |  |  | 422 |  |  | 383 |  |  | 400 |  |  | 381 |  |  | 431 |  |  | 416 |  |  | 437 |  |  | 457 |  |  | 413 |  |  | 451 |  |  | 437 |  |  | 424 |  |  | 406 |  |  | 402 |  |  | 443 |  |  | 394 |  |  | 449 |  |  | 402 |  |  | 439 |  |  | 409 |  |  | 434 |  |  | 430 |  |  | 431 |  |  | 411 |  |  | 428 |  |  | 432 |  |  | 439 |  |  | 396 |  |  | 432 |  |  | 367 |  |  | 432 |  |  | 385 |  |  | 438 |  |  | 423 |  |  | 431 |  |  | 438 |  |  | 411 |  |  | 422 |  |  | 433
15 |  | 426 |  |  | 501 |  |  | 468 |  |  | 417 |  |  | 507 |  |  | 431 |  |  | 475 |  |  | 459 |  |  | 475 |  |  | 449 |  |  | 474 |  |  | 484 |  |  | 500 |  |  | 443 |  |  | 413 |  |  | 467 |  |  | 436 |  |  | 444 |  |  | 494 |  |  | 414 |  |  | 453 |  |  | 452 |  |  | 467 |  |  | 433 |  |  | 410 |  |  | 439 |  |  | 428 |  |  | 449 |  |  | 459 |  |  | 390 |  |  | 409 |  |  | 475 |  |  | 409 |  |  | 450 |  |  | 410 |  |  | 448 |  |  | 454 |  |  | 407 |  |  | 454 |  |  | 441 |  |  | 433 |  |  | 491 |  |  | 463 |  |  | 472 |  |  | 480 |  |  | 490 |  |  | 444 |  |  | 452 |  |  | 430 |  |  | 454 |  |  | 452 |  |  | 452 |  |  | 433 |  |  | 439 |  |  | 427 |  |  | 405 |  |  | 417 |  |  | 441 |  |  | 476 |  |  | 483 |  |  | 435 |  |  | 437 |  |  | 430 |  |  | 454 |  |  | 431 |  |  | 418 |  |  | 463 |  |  | 428 |  |  | 447 |  |  | 442 |  |  | 469 |  |  | 475 |  |  | 407 |  |  | 459 |  |  | 497 |  |  | 444 |  |  | 444 |  |  | 436 |  |  | 430 |  |  | 419 |  |  | 424 |  |  | 442 |  |  | 448 |  |  | 435 |  |  | 449 |  |  | 475 |  |  | 488 |  |  | 444 |  |  | 410 |  |  | 442 |  |  | 451 |  |  | 401 |  |  | 424 |  |  | 430 |  |  | 454 |  |  | 449 |  |  | 456 |  |  | 473 |  |  | 449 |  |  | 413 |  |  | 441 |  |  | 459 |  |  | 454 |  |  | 469 |  |  | 461 |  |  | 444 |  |  | 459 |  |  | 535 |  |  | 479 |  |  | 464 |  |  | 449 |  |  | 487 |  |  | 430 |  |  | 498 |  |  | 471 |  |  | 436 |  |  | 439 |  |  | 416 |  |  | 490 |  |  | 509 |  |  | 497 |  |  | 459 |  |  | 448 |  |  | 470 |  |  | 452 |  |  | 491 |  |  | 431 |  |  | 475 |  |  | 449 |  |  | 433 |  |  | 460 |  |  | 440 |  |  | 467 |  |  | 465 |  |  | 401 |  |  | 438 |  |  | 466 |  |  | 470 |  |  | 485 |  |  | 459 |  |  | 467 |  |  | 410 |  |  | 450 |  |  | 493 |  |  | 437 |  |  | 522 |  |  | 470 |  |  | 467 |  |  | 403 |  |  | 475 |  |  | 480 |  |  | 444 |  |  | 436 |  |  | 465 |  |  | 485 |  |  | 463 |  |  | 409 |  |  | 441 |  |  | 451 |  |  | 420 |  |  | 445 |  |  | 454 |  |  | 448 |  |  | 427 |  |  | 450 |  |  | 416 |  |  | 444 |  |  | 452 |  |  | 459 |  |  | 446 |  |  | 428 |  |  | 434 |  |  | 419 |  |  | 454 |  |  | 444 |  |  | 440 |  |  | 455 |  |  | 460 |  |  | 438 |  |  | 472 |  |  | 495 |  |  | 437 |  |  | 425 |  |  | 469 |  |  | 380 |  |  | 478 |  |  | 439 |  |  | 448 |  |  | 463 |  |  | 437 |  |  | 431 |  |  | 427 |  |  | 437 |  |  | 424 |  |  | 464 |  |  | 425 |  |  | 419 |  |  | 434 |  |  | 504 |  |  | 455 |  |  | 487 |  |  | 431 |  |  | 416 |  |  | 441 |  |  | 457 |  |  | 482 |  |  | 466 |  |  | 424 |  |  | 465 |  |  | 457 |  |  | 448 |  |  | 448 |  |  | 441 |  |  | 439 |  |  | 464 |  |  | 473 |  |  | 433 |  |  | 447 |  |  | 462 |  |  | 486 |  |  | 445 |  |  | 453 |  |  | 426 |  |  | 425 |  |  | 454 |  |  | 426 |  |  | 450 |  |  | 448 |  |  | 471 |  |  | 456 |  |  | 432 |  |  | 436 |  |  | 450 |  |  | 475 |  |  | 473 |  |  | 469 |  |  | 441 |  |  | 509 |  |  | 430 |  |  | 473 |  |  | 461 |  |  | 438 |  |  | 470 |  |  | 491 |  |  | 486 |  |  | 488 |  |  | 448 |  |  | 420 |  |  | 417 |  |  | 480 |  |  | 453 |  |  | 408 |  |  | 443 |  |  | 427 |  |  | 463 |  |  | 430 |  |  | 486 |  |  | 432 |  |  | 411 |  |  | 444 |  |  | 468 |  |  | 419 |  |  | 487 |  |  | 466 |  |  | 466 |  |  | 445 |  |  | 422 |  |  | 498 |  |  | 417 |  |  | 511 |  |  | 458 |  |  | 410 |  |  | 509 |  |  | 448 |  |  | 467 |  |  | 472 |  |  | 449 |  |  | 450 |  |  | 424 |  |  | 428 |  |  | 488 |  |  | 454 |  |  | 437 |  |  | 439 |  |  | 467 |  |  | 470 |  |  | 490 |  |  | 467 |  |  | 420 |  |  | 476 |  |  | 462 |  |  | 459 |  |  | 442 |  |  | 459 |  |  | 470 |  |  | 450 |  |  | 436 |  |  | 467 |  |  | 424 |  |  | 441 |  |  | 424 |  |  | 447 |  |  | 467 |  |  | 408 |  |  | 436 |  |  | 462 |  |  | 454 |  |  | 467 |  |  | 441 |  |  | 442 |  |  | 468 |  |  | 512 |  |  | 437 |  |  | 491 |  |  | 490 |  |  | 463 |  |  | 423 |  |  | 455 |  |  | 442 |  |  | 445 |  |  | 422 |  |  | 491 |  |  | 430 |  |  | 456 |  |  | 477 |  |  | 435 |  |  | 463 |  |  | 464 |  |  | 488 |  |  | 487 |  |  | 488 |  |  | 472 |  |  | 501 |  |  | 418 |  |  | 486 |  |  | 433 |  |  | 464 |  |  | 432 |  |  | 454 |  |  | 437 |  |  | 479 |  |  | 436 |  |  | 446 |  |  | 451 |  |  | 467 |  |  | 462 |  |  | 467 |  |  | 516 |  |  | 469 |  |  | 420 |  |  | 467 |  |  | 418 |  |  | 459 |  |  | 430 |  |  | 458 |  |  | 422 |  |  | 481 |  |  | 478 |  |  | 406 |  |  | 403 |  |  | 441 |  |  | 474 |  |  | 415 |  |  | 509 |  |  | 437 |  |  | 436 |  |  | 396 |  |  | 404 |  |  | 431 |  |  | 493 |  |  | 443 |  |  | 441 |  |  | 504 |  |  | 412 |  |  | 392 |  |  | 495 |  |  | 443 |  |  | 430 |  |  | 473 |  |  | 430 |  |  | 433 |  |  | 480 |  |  | 452 |  |  | 426 |  |  | 406 |  |  | 459 |  |  | 427 |  |  | 496 |  |  | 428 |  |  | 431 |  |  | 463 |  |  | 492 |  |  | 460 |  |  | 459 |  |  | 452 |  |  | 486 |  |  | 512 |  |  | 451 |  |  | 472 |  |  | 467 |  |  | 468 |  |  | 434 |  |  | 454 |  |  | 475 |  |  | 498 |  |  | 444 |  |  | 482 |  |  | 405 |  |  | 444 |  |  | 468 |  |  | 407 |  |  | 454 |  |  | 453 |  |  | 450 |  |  | 408 |  |  | 401 |  |  | 474 |  |  | 417 |  |  | 455 |  |  | 465 |  |  | 475 |  |  | 459 |  |  | 436 |  |  | 514 |  |  | 457 |  |  | 457 |  |  | 428 |  |  | 432 |  |  | 462 |  |  | 440 |  |  | 465 |  |  | 438 |  |  | 427 |  |  | 507 |  |  | 413 |  |  | 460 |  |  | 436 |  |  | 498 |  |  | 436 |  |  | 404 |  |  | 442 |  |  | 466 |  |  | 491 |  |  | 425 |  |  | 483 |  |  | 475 |  |  | 465 |  |  | 377 |  |  | 467 |  |  | 443 |  |  | 476 |  |  | 420 |  |  | 432 |  |  | 488 |  |  | 437 |  |  | 431 |  |  | 469 |  |  | 390 |  |  | 459 |  |  | 446 |  |  | 478 |  |  | 512 |  |  | 415 |  |  | 476 |  |  | 435 |  |  | 429 |  |  | 431 |  |  | 390 |  |  | 467 |  |  | 496 |  |  | 462 |  |  | 438 |  |  | 477 |  |  | 449 |  |  | 427 |  |  | 461 |  |  | 478 |  |  | 460 |  |  | 449 |  |  | 431 |  |  | 483 |  |  | 441 |  |  | 404 |  |  | 475 |  |  | 483 |  |  | 436 |  |  | 409 |  |  | 514 |  |  | 391 |  |  | 443 |  |  | 478 |  |  | 419 |  |  | 486 |  |  | 435 |  |  | 473 |  |  | 449 |  |  | 445 |  |  | 426 |  |  | 421 |  |  | 413 |  |  | 453 |  |  | 447 |  |  | 454 |  |  | 456 |  |  | 446 |  |  | 494 |  |  | 512 |  |  | 465 |  |  | 475 |  |  | 438 |  |  | 442 |  |  | 449 |  |  | 445 |  |  | 434 |  |  | 439 |  |  | 421 |  |  | 438 |  |  | 444 |  |  | 436 |  |  | 454 |  |  | 438 |  |  | 446 |  |  | 467 |  |  | 494 |  |  | 458 |  |  | 488 |  |  | 513 |  |  | 440 |  |  | 411 |  |  | 420 |  |  | 522 |  |  | 437 |  |  | 470 |  |  | 421 |  |  | 441 |  |  | 456 |  |  | 426 |  |  | 412 |  |  | 430 |  |  | 449 |  |  | 448 |  |  | 434 |  |  | 467 |  |  | 407 |  |  | 415 |  |  | 429 |  |  | 462 |  |  | 429 |  |  | 422 |  |  | 430 |  |  | 435 |  |  | 491 |  |  | 488 |  |  | 455 |  |  | 439 |  |  | 477 |  |  | 509 |  |  | 424 |  |  | 446 |  |  | 472 |  |  | 451 |  |  | 470 |  |  | 452 |  |  | 469 |  |  | 441 |  |  | 450 |  |  | 443 |  |  | 493 |  |  | 483 |  |  | 488 |  |  | 416 |  |  | 431 |  |  | 371 |  |  | 488 |  |  | 456 |  |  | 461 |  |  | 481 |  |  | 425 |  |  | 469 |  |  | 447 |  |  | 463 |  |  | 411 |  |  | 434 |  |  | 462 |  |  | 446 |  |  | 440 |  |  | 395 |  |  | 466 |  |  | 404 |  |  | 453 |  |  | 430 |  |  | 434 |  |  | 440 |  |  | 461 |  |  | 470 |  |  | 396 |  |  | 475 |  |  | 478 |  |  | 426 |  |  | 443 |  |  | 410 |  |  | 415 |  |  | 441 |  |  | 477 |  |  | 476 |  |  | 438 |  |  | 475 |  |  | 447 |  |  | 491 |  |  | 454 |  |  | 401 |  |  | 471 |  |  | 481 |  |  | 404 |  |  | 446 |  |  | 464 |  |  | 451 |  |  | 430 |  |  | 461 |  |  | 439 |  |  | 441 |  |  | 457 |  |  | 493 |  |  | 443 |  |  | 457 |  |  | 475 |  |  | 436 |  |  | 453 |  |  | 483 |  |  | 445 |  |  | 509 |  |  | 439 |  |  | 473 |  |  | 445 |  |  | 497 |  |  | 432 |  |  | 512 |  |  | 406 |  |  | 448 |  |  | 424 |  |  | 434 |  |  | 446 |  |  | 413 |  |  | 477 |  |  | 507 |  |  | 442 |  |  | 434 |  |  | 396 |  |  | 459 |  |  | 404 |  |  | 495 |  |  | 437 |  |  | 453 |  |  | 450 |  |  | 448 |  |  | 455 |  |  | 420 |  |  | 462 |  |  | 483 |  |  | 430 |  |  | 465 |  |  | 464 |  |  | 429 |  |  | 415 |  |  | 424 |  |  | 430 |  |  | 412 |  |  | 495 |  |  | 445 |  |  | 516 |  |  | 433 |  |  | 461 |  |  | 384 |  |  | 477 |  |  | 426 |  |  | 452 |  |  | 457 |  |  | 437 |  |  | 425 |  |  | 428 |  |  | 463 |  |  | 451 |  |  | 431 |  |  | 504 |  |  | 430 |  |  | 417 |  |  | 436 |  |  | 450 |  |  | 431 |  |  | 445 |  |  | 451 |  |  | 488 |  |  | 420 |  |  | 446 |  |  | 473 |  |  | 468 |  |  | 470 |  |  | 440 |  |  | 431 |  |  | 460 |  |  | 419 |  |  | 406 |  |  | 503 |  |  | 491 |  |  | 444 |  |  | 469 |  |  | 448 |  |  | 419 |  |  | 424 |  |  | 419 |  |  | 457 |  |  | 419 |  |  | 436 |  |  | 488 |  |  | 436 |  |  | 458 |  |  | 465 |  |  | 393 |  |  | 460 |  |  | 408 |  |  | 462 |  |  | 479 |  |  | 434 |  |  | 452 |  |  | 457 |  |  | 446 |  |  | 485 |  |  | 423 |  |  | 470 |  |  | 441 |  |  | 422 |  |  | 432 |  |  | 442 |  |  | 462 |  |  | 490 |  |  | 432 |  |  | 487 |  |  | 407 |  |  | 459 |  |  | 452 |  |  | 468 |  |  | 457 |  |  | 442 |  |  | 478 |  |  | 483 |  |  | 425 |  |  | 419 |  |  | 470 |  |  | 401 |  |  | 448 |  |  | 437 |  |  | 414 |  |  | 443 |  |  | 441 |  |  | 423 |  |  | 446 |  |  | 480 |  |  | 425 |  |  | 472 |  |  | 459 |  |  | 422 |  |  | 473 |  |  | 478 |  |  | 449 |  |  | 453 |  |  | 446 |  |  | 452 |  |  | 443 |  |  | 401 |  |  | 467 |  |  | 476 |  |  | 450 |  |  | 479 |  |  | 452 |  |  | 487 |  |  | 464 |  |  | 445 |  |  | 494 |  |  | 472 |  |  | 462 |  |  | 480 |  |  | 433 |  |  | 466 |  |  | 410 |  |  | 444 |  |  | 455 |  |  | 455 |  |  | 437 |  |  | 470 |  |  | 477 |  |  | 460 |  |  | 422 |  |  | 444 |  |  | 491 |  |  | 452 |  |  | 452 |  |  | 497 |  |  | 445 |  |  | 438 |  |  | 478 |  |  | 461 |  |  | 462 |  |  | 412 |  |  | 473 |  |  | 459 |  |  | 445 |  |  | 440 |  |  | 471 |  |  | 454 |  |  | 464 |  |  | 408 |  |  | 448 |  |  | 454 |  |  | 488 |  |  | 475 |  |  | 377 |  |  | 473 |  |  | 446 |  |  | 452 |  |  | 472 |  |  | 420 |  |  | 440 |  |  | 426 |  |  | 470 |  |  | 401 |  |  | 432 |  |  | 448 |  |  | 447 |  |  | 454 |  |  | 441 |  |  | 425 |  |  | 491 |  |  | 495 |  |  | 419 |  |  | 493 |  |  | 431 |  |  | 440 |  |  | 514 |  |  | 438 |  |  | 409 |  |  | 403 |  |  | 473 |  |  | 440 |  |  | 447 |  |  | 457 |  |  | 465 |  |  | 453 |  |  | 449 |  |  | 443 |  |  | 454 |  |  | 407 |  |  | 444 |  |  | 426 |  |  | 460 |  |  | 451 |  |  | 496 |  |  | 457 |  |  | 470 |  |  | 522 |  |  | 446 |  |  | 496 |  |  | 466 |  |  | 506 |  |  | 431 |  |  | 464 |  |  | 435 |  |  | 480 |  |  | 448 |  |  | 449 |  |  | 427 |  |  | 484 |  |  | 448 |  |  | 418 |  |  | 421 |  |  | 454 |  |  | 451 |  |  | 465 |  |  | 486 |  |  | 438 |  |  | 432 |  |  | 449 |  |  | 421 |  |  | 474 |  |  | 468 |  |  | 414 |  |  | 508 |  |  | 437 |  |  | 445 |  |  | 471 |  |  | 467 |  |  | 456 |  |  | 432 |  |  | 463 |  |  | 435 |  |  | 458 |  |  | 503 |  |  | 438 |  |  | 509 |  |  | 427 |  |  | 429 |  |  | 435 |  |  | 434 |  |  | 437 |  |  | 485 |  |  | 475 |  |  | 437 |  |  | 441 |  |  | 422 |  |  | 423 |  |  | 444 |  |  | 452 |  |  | 449 |  |  | 454 |  |  | 490 |  |  | 410 |  |  | 467 |  |  | 452 |  |  | 481 |  |  | 443 |  |  | 453 |  |  | 429 |  |  | 455 |  |  | 474 |  |  | 443 |  |  | 422 |  |  | 413 |  |  | 414 |  |  | 414 |  |  | 467 |  |  | 424 |  |  | 402 |  |  | 465 |  |  | 475 |  |  | 453 |  |  | 417 |  |  | 447 |  |  | 447 |  |  | 462 |  |  | 380 |  |  | 436 |  |  | 454 |  |  | 497 |  |  | 466 |  |  | 453 |  |  | 458 |  |  | 447 |  |  | 448 |  |  | 454 |  |  | 519 |  |  | 504 |  |  | 444 |  |  | 496 |  |  | 451 |  |  | 469 |  |  | 462 |  |  | 485 |  |  | 446 |  |  | 474 |  |  | 480 |  |  | 442 |  |  | 402 |  |  | 469 |  |  | 409 |  |  | 429 |  |  | 396 |  |  | 470 |  |  | 437 |  |  | 463 |  |  | 496 |  |  | 439 |  |  | 490 |  |  | 476 |  |  | 445 |  |  | 445 |  |  | 417 |  |  | 467 |  |  | 423 |  |  | 475 |  |  | 428 |  |  | 486 |  |  | 433 |  |  | 473 |  |  | 454 |  |  | 470 |  |  | 432 |  |  | 454 |  |  | 458 |  |  | 465 |  |  | 411 |  |  | 461 |  |  | 382 |  |  | 461 |  |  | 414 |  |  | 462 |  |  | 444 |  |  | 452 |  |  | 462 |  |  | 432 |  |  | 461 |  |  | 472
16 |  | 473 |  |  | 527 |  |  | 497 |  |  | 441 |  |  | 554 |  |  | 470 |  |  | 514 |  |  | 483 |  |  | 501 |  |  | 488 |  |  | 521 |  |  | 510 |  |  | 539 |  |  | 482 |  |  | 442 |  |  | 506 |  |  | 457 |  |  | 470 |  |  | 515 |  |  | 453 |  |  | 477 |  |  | 467 |  |  | 493 |  |  | 472 |  |  | 425 |  |  | 478 |  |  | 475 |  |  | 488 |  |  | 474 |  |  | 414 |  |  | 456 |  |  | 504 |  |  | 433 |  |  | 471 |  |  | 425 |  |  | 474 |  |  | 493 |  |  | 454 |  |  | 483 |  |  | 462 |  |  | 462 |  |  | 512 |  |  | 484 |  |  | 511 |  |  | 519 |  |  | 537 |  |  | 459 |  |  | 491 |  |  | 469 |  |  | 493 |  |  | 491 |  |  | 478 |  |  | 462 |  |  | 465 |  |  | 466 |  |  | 426 |  |  | 464 |  |  | 467 |  |  | 505 |  |  | 507 |  |  | 482 |  |  | 458 |  |  | 477 |  |  | 469 |  |  | 455 |  |  | 465 |  |  | 502 |  |  | 457 |  |  | 473 |  |  | 466 |  |  | 508 |  |  | 499 |  |  | 446 |  |  | 506 |  |  | 544 |  |  | 465 |  |  | 468 |  |  | 451 |  |  | 454 |  |  | 466 |  |  | 445 |  |  | 457 |  |  | 474 |  |  | 482 |  |  | 488 |  |  | 522 |  |  | 514 |  |  | 470 |  |  | 457 |  |  | 481 |  |  | 480 |  |  | 440 |  |  | 463 |  |  | 459 |  |  | 480 |  |  | 464 |  |  | 477 |  |  | 512 |  |  | 464 |  |  | 452 |  |  | 470 |  |  | 485 |  |  | 501 |  |  | 493 |  |  | 487 |  |  | 473 |  |  | 488 |  |  | 556 |  |  | 494 |  |  | 511 |  |  | 488 |  |  | 502 |  |  | 456 |  |  | 513 |  |  | 518 |  |  | 451 |  |  | 486 |  |  | 455 |  |  | 514 |  |  | 556 |  |  | 521 |  |  | 498 |  |  | 487 |  |  | 494 |  |  | 491 |  |  | 538 |  |  | 452 |  |  | 499 |  |  | 464 |  |  | 457 |  |  | 499 |  |  | 466 |  |  | 488 |  |  | 504 |  |  | 422 |  |  | 477 |  |  | 481 |  |  | 509 |  |  | 509 |  |  | 498 |  |  | 496 |  |  | 449 |  |  | 497 |  |  | 532 |  |  | 476 |  |  | 548 |  |  | 491 |  |  | 514 |  |  | 442 |  |  | 504 |  |  | 501 |  |  | 465 |  |  | 483 |  |  | 504 |  |  | 532 |  |  | 510 |  |  | 433 |  |  | 467 |  |  | 466 |  |  | 467 |  |  | 484 |  |  | 475 |  |  | 463 |  |  | 448 |  |  | 465 |  |  | 455 |  |  | 459 |  |  | 481 |  |  | 506 |  |  | 485 |  |  | 443 |  |  | 458 |  |  | 448 |  |  | 493 |  |  | 459 |  |  | 466 |  |  | 481 |  |  | 486 |  |  | 459 |  |  | 487 |  |  | 524 |  |  | 463 |  |  | 464 |  |  | 490 |  |  | 419 |  |  | 502 |  |  | 465 |  |  | 474 |  |  | 489 |  |  | 463 |  |  | 452 |  |  | 453 |  |  | 452 |  |  | 453 |  |  | 493 |  |  | 451 |  |  | 434 |  |  | 481 |  |  | 551 |  |  | 470 |  |  | 526 |  |  | 478 |  |  | 431 |  |  | 470 |  |  | 504 |  |  | 521 |  |  | 481 |  |  | 471 |  |  | 504 |  |  | 483 |  |  | 487 |  |  | 495 |  |  | 465 |  |  | 478 |  |  | 503 |  |  | 499 |  |  | 472 |  |  | 486 |  |  | 509 |  |  | 525 |  |  | 460 |  |  | 482 |  |  | 465 |  |  | 440 |  |  | 469 |  |  | 441 |  |  | 465 |  |  | 487 |  |  | 500 |  |  | 485 |  |  | 447 |  |  | 451 |  |  | 479 |  |  | 504 |  |  | 520 |  |  | 498 |  |  | 456 |  |  | 524 |  |  | 459 |  |  | 520 |  |  | 476 |  |  | 453 |  |  | 491 |  |  | 520 |  |  | 501 |  |  | 503 |  |  | 463 |  |  | 441 |  |  | 456 |  |  | 519 |  |  | 477 |  |  | 432 |  |  | 469 |  |  | 466 |  |  | 489 |  |  | 459 |  |  | 510 |  |  | 461 |  |  | 437 |  |  | 483 |  |  | 494 |  |  | 458 |  |  | 502 |  |  | 505 |  |  | 490 |  |  | 474 |  |  | 443 |  |  | 522 |  |  | 443 |  |  | 537 |  |  | 487 |  |  | 449 |  |  | 548 |  |  | 487 |  |  | 506 |  |  | 498 |  |  | 470 |  |  | 489 |  |  | 463 |  |  | 457 |  |  | 527 |  |  | 475 |  |  | 476 |  |  | 478 |  |  | 488 |  |  | 496 |  |  | 529 |  |  | 506 |  |  | 446 |  |  | 505 |  |  | 477 |  |  | 506 |  |  | 481 |  |  | 506 |  |  | 491 |  |  | 497 |  |  | 465 |  |  | 488 |  |  | 463 |  |  | 456 |  |  | 450 |  |  | 462 |  |  | 506 |  |  | 429 |  |  | 460 |  |  | 509 |  |  | 480 |  |  | 491 |  |  | 467 |  |  | 463 |  |  | 497 |  |  | 559 |  |  | 452 |  |  | 515 |  |  | 516 |  |  | 502 |  |  | 462 |  |  | 494 |  |  | 468 |  |  | 471 |  |  | 448 |  |  | 517 |  |  | 445 |  |  | 495 |  |  | 501 |  |  | 474 |  |  | 502 |  |  | 511 |  |  | 512 |  |  | 508 |  |  | 514 |  |  | 498 |  |  | 516 |  |  | 444 |  |  | 507 |  |  | 462 |  |  | 493 |  |  | 447 |  |  | 501 |  |  | 452 |  |  | 505 |  |  | 475 |  |  | 470 |  |  | 466 |  |  | 493 |  |  | 483 |  |  | 491 |  |  | 540 |  |  | 490 |  |  | 449 |  |  | 491 |  |  | 447 |  |  | 498 |  |  | 459 |  |  | 497 |  |  | 448 |  |  | 510 |  |  | 493 |  |  | 430 |  |  | 432 |  |  | 456 |  |  | 503 |  |  | 444 |  |  | 556 |  |  | 461 |  |  | 457 |  |  | 443 |  |  | 443 |  |  | 446 |  |  | 517 |  |  | 458 |  |  | 467 |  |  | 525 |  |  | 433 |  |  | 431 |  |  | 516 |  |  | 482 |  |  | 477 |  |  | 499 |  |  | 456 |  |  | 480 |  |  | 501 |  |  | 481 |  |  | 465 |  |  | 430 |  |  | 480 |  |  | 448 |  |  | 522 |  |  | 475 |  |  | 478 |  |  | 487 |  |  | 507 |  |  | 486 |  |  | 506 |  |  | 467 |  |  | 533 |  |  | 559 |  |  | 472 |  |  | 511 |  |  | 514 |  |  | 494 |  |  | 473 |  |  | 493 |  |  | 499 |  |  | 545 |  |  | 470 |  |  | 511 |  |  | 426 |  |  | 483 |  |  | 515 |  |  | 431 |  |  | 469 |  |  | 500 |  |  | 476 |  |  | 432 |  |  | 440 |  |  | 521 |  |  | 464 |  |  | 484 |  |  | 486 |  |  | 522 |  |  | 474 |  |  | 483 |  |  | 553 |  |  | 472 |  |  | 483 |  |  | 467 |  |  | 471 |  |  | 488 |  |  | 469 |  |  | 491 |  |  | 485 |  |  | 451 |  |  | 546 |  |  | 439 |  |  | 499 |  |  | 483 |  |  | 527 |  |  | 460 |  |  | 443 |  |  | 463 |  |  | 505 |  |  | 512 |  |  | 464 |  |  | 509 |  |  | 522 |  |  | 504 |  |  | 401 |  |  | 488 |  |  | 464 |  |  | 502 |  |  | 441 |  |  | 453 |  |  | 535 |  |  | 466 |  |  | 455 |  |  | 484 |  |  | 419 |  |  | 488 |  |  | 485 |  |  | 493 |  |  | 536 |  |  | 430 |  |  | 505 |  |  | 464 |  |  | 468 |  |  | 460 |  |  | 414 |  |  | 506 |  |  | 525 |  |  | 486 |  |  | 477 |  |  | 492 |  |  | 488 |  |  | 442 |  |  | 482 |  |  | 507 |  |  | 475 |  |  | 475 |  |  | 470 |  |  | 522 |  |  | 467 |  |  | 443 |  |  | 501 |  |  | 512 |  |  | 475 |  |  | 448 |  |  | 553 |  |  | 438 |  |  | 464 |  |  | 517 |  |  | 458 |  |  | 515 |  |  | 464 |  |  | 494 |  |  | 488 |  |  | 474 |  |  | 452 |  |  | 468 |  |  | 452 |  |  | 477 |  |  | 494 |  |  | 469 |  |  | 485 |  |  | 475 |  |  | 523 |  |  | 551 |  |  | 489 |  |  | 514 |  |  | 464 |  |  | 468 |  |  | 475 |  |  | 484 |  |  | 463 |  |  | 454 |  |  | 450 |  |  | 462 |  |  | 465 |  |  | 462 |  |  | 501 |  |  | 477 |  |  | 485 |  |  | 491 |  |  | 515 |  |  | 505 |  |  | 509 |  |  | 542 |  |  | 455 |  |  | 435 |  |  | 441 |  |  | 546 |  |  | 476 |  |  | 509 |  |  | 436 |  |  | 480 |  |  | 471 |  |  | 450 |  |  | 451 |  |  | 445 |  |  | 475 |  |  | 487 |  |  | 481 |  |  | 482 |  |  | 433 |  |  | 454 |  |  | 468 |  |  | 477 |  |  | 468 |  |  | 451 |  |  | 445 |  |  | 474 |  |  | 506 |  |  | 512 |  |  | 484 |  |  | 468 |  |  | 503 |  |  | 535 |  |  | 471 |  |  | 485 |  |  | 501 |  |  | 477 |  |  | 496 |  |  | 467 |  |  | 493 |  |  | 462 |  |  | 471 |  |  | 467 |  |  | 514 |  |  | 504 |  |  | 535 |  |  | 442 |  |  | 470 |  |  | 397 |  |  | 503 |  |  | 503 |  |  | 490 |  |  | 502 |  |  | 464 |  |  | 508 |  |  | 486 |  |  | 487 |  |  | 440 |  |  | 481 |  |  | 509 |  |  | 485 |  |  | 461 |  |  | 442 |  |  | 495 |  |  | 443 |  |  | 477 |  |  | 459 |  |  | 473 |  |  | 464 |  |  | 476 |  |  | 499 |  |  | 443 |  |  | 496 |  |  | 499 |  |  | 450 |  |  | 490 |  |  | 439 |  |  | 436 |  |  | 467 |  |  | 501 |  |  | 515 |  |  | 477 |  |  | 499 |  |  | 486 |  |  | 515 |  |  | 475 |  |  | 448 |  |  | 495 |  |  | 528 |  |  | 443 |  |  | 467 |  |  | 488 |  |  | 475 |  |  | 445 |  |  | 485 |  |  | 478 |  |  | 470 |  |  | 504 |  |  | 532 |  |  | 469 |  |  | 483 |  |  | 496 |  |  | 462 |  |  | 479 |  |  | 530 |  |  | 471 |  |  | 538 |  |  | 486 |  |  | 502 |  |  | 471 |  |  | 544 |  |  | 471 |  |  | 551 |  |  | 432 |  |  | 477 |  |  | 445 |  |  | 449 |  |  | 470 |  |  | 428 |  |  | 503 |  |  | 533 |  |  | 481 |  |  | 449 |  |  | 435 |  |  | 488 |  |  | 430 |  |  | 510 |  |  | 476 |  |  | 468 |  |  | 489 |  |  | 477 |  |  | 479 |  |  | 449 |  |  | 501 |  |  | 504 |  |  | 445 |  |  | 504 |  |  | 479 |  |  | 455 |  |  | 454 |  |  | 450 |  |  | 477 |  |  | 459 |  |  | 542 |  |  | 474 |  |  | 563 |  |  | 459 |  |  | 490 |  |  | 423 |  |  | 501 |  |  | 455 |  |  | 491 |  |  | 504 |  |  | 476 |  |  | 446 |  |  | 457 |  |  | 489 |  |  | 475 |  |  | 470 |  |  | 525 |  |  | 454 |  |  | 432 |  |  | 451 |  |  | 471 |  |  | 470 |  |  | 469 |  |  | 466 |  |  | 503 |  |  | 441 |  |  | 470 |  |  | 499 |  |  | 483 |  |  | 491 |  |  | 461 |  |  | 457 |  |  | 507 |  |  | 448 |  |  | 427 |  |  | 529 |  |  | 538 |  |  | 483 |  |  | 498 |  |  | 495 |  |  | 458 |  |  | 439 |  |  | 466 |  |  | 472 |  |  | 443 |  |  | 483 |  |  | 514 |  |  | 475 |  |  | 482 |  |  | 494 |  |  | 408 |  |  | 489 |  |  | 432 |  |  | 501 |  |  | 500 |  |  | 458 |  |  | 476 |  |  | 504 |  |  | 485 |  |  | 509 |  |  | 452 |  |  | 496 |  |  | 480 |  |  | 446 |  |  | 456 |  |  | 457 |  |  | 491 |  |  | 537 |  |  | 479 |  |  | 516 |  |  | 446 |  |  | 485 |  |  | 499 |  |  | 489 |  |  | 486 |  |  | 481 |  |  | 499 |  |  | 522 |  |  | 464 |  |  | 448 |  |  | 491 |  |  | 427 |  |  | 487 |  |  | 452 |  |  | 438 |  |  | 490 |  |  | 480 |  |  | 449 |  |  | 485 |  |  | 504 |  |  | 446 |  |  | 487 |  |  | 480 |  |  | 461 |  |  | 499 |  |  | 517 |  |  | 470 |  |  | 482 |  |  | 493 |  |  | 499 |  |  | 482 |  |  | 430 |  |  | 488 |  |  | 515 |  |  | 474 |  |  | 518 |  |  | 499 |  |  | 511 |  |  | 490 |  |  | 492 |  |  | 518 |  |  | 487 |  |  | 483 |  |  | 519 |  |  | 472 |  |  | 495 |  |  | 431 |  |  | 465 |  |  | 484 |  |  | 484 |  |  | 463 |  |  | 491 |  |  | 524 |  |  | 499 |  |  | 448 |  |  | 459 |  |  | 520 |  |  | 481 |  |  | 478 |  |  | 512 |  |  | 471 |  |  | 477 |  |  | 525 |  |  | 482 |  |  | 488 |  |  | 438 |  |  | 512 |  |  | 498 |  |  | 460 |  |  | 466 |  |  | 495 |  |  | 469 |  |  | 479 |  |  | 429 |  |  | 487 |  |  | 483 |  |  | 509 |  |  | 522 |  |  | 401 |  |  | 499 |  |  | 485 |  |  | 491 |  |  | 487 |  |  | 459 |  |  | 479 |  |  | 465 |  |  | 485 |  |  | 440 |  |  | 471 |  |  | 487 |  |  | 468 |  |  | 493 |  |  | 467 |  |  | 464 |  |  | 512 |  |  | 534 |  |  | 466 |  |  | 540 |  |  | 446 |  |  | 464 |  |  | 540 |  |  | 467 |  |  | 438 |  |  | 442 |  |  | 488 |  |  | 479 |  |  | 486 |  |  | 483 |  |  | 504 |  |  | 474 |  |  | 478 |  |  | 482 |  |  | 501 |  |  | 446 |  |  | 491 |  |  | 452 |  |  | 481 |  |  | 475 |  |  | 535 |  |  | 496 |  |  | 499 |  |  | 561 |  |  | 485 |  |  | 535 |  |  | 490 |  |  | 545 |  |  | 470 |  |  | 485 |  |  | 459 |  |  | 519 |  |  | 474 |  |  | 464 |  |  | 448 |  |  | 531 |  |  | 463 |  |  | 465 |  |  | 460 |  |  | 483 |  |  | 466 |  |  | 504 |  |  | 515 |  |  | 462 |  |  | 456 |  |  | 464 |  |  | 442 |  |  | 513 |  |  | 494 |  |  | 453 |  |  | 547 |  |  | 476 |  |  | 469 |  |  | 497 |  |  | 496 |  |  | 477 |  |  | 453 |  |  | 484 |  |  | 464 |  |  | 505 |  |  | 529 |  |  | 467 |  |  | 556 |  |  | 466 |  |  | 468 |  |  | 456 |  |  | 463 |  |  | 463 |  |  | 511 |  |  | 501 |  |  | 476 |  |  | 462 |  |  | 443 |  |  | 444 |  |  | 470 |  |  | 476 |  |  | 496 |  |  | 483 |  |  | 529 |  |  | 436 |  |  | 493 |  |  | 499 |  |  | 507 |  |  | 472 |  |  | 492 |  |  | 455 |  |  | 494 |  |  | 489 |  |  | 458 |  |  | 461 |  |  | 439 |  |  | 435 |  |  | 440 |  |  | 496 |  |  | 445 |  |  | 431 |  |  | 512 |  |  | 501 |  |  | 500 |  |  | 441 |  |  | 486 |  |  | 471 |  |  | 509 |  |  | 427 |  |  | 475 |  |  | 501 |  |  | 521 |  |  | 487 |  |  | 468 |  |  | 473 |  |  | 473 |  |  | 477 |  |  | 483 |  |  | 548 |  |  | 551 |  |  | 483 |  |  | 535 |  |  | 490 |  |  | 493 |  |  | 486 |  |  | 532 |  |  | 493 |  |  | 500 |  |  | 527 |  |  | 457 |  |  | 426 |  |  | 495 |  |  | 448 |  |  | 458 |  |  | 422 |  |  | 485 |  |  | 463 |  |  | 510 |  |  | 535 |  |  | 454 |  |  | 505 |  |  | 502 |  |  | 492 |  |  | 466 |  |  | 441 |  |  | 491 |  |  | 462 |  |  | 501 |  |  | 443 |  |  | 501 |  |  | 459 |  |  | 512 |  |  | 483 |  |  | 517 |  |  | 453 |  |  | 501 |  |  | 482 |  |  | 480 |  |  | 432 |  |  | 487 |  |  | 429 |  |  | 490 |  |  | 435 |  |  | 483 |  |  | 491 |  |  | 478 |  |  | 509 |  |  | 453 |  |  | 487 |  |  | 487
17 |  | 512 |  |  | 574 |  |  | 544 |  |  | 462 |  |  | 569 |  |  | 496 |  |  | 543 |  |  | 504 |  |  | 548 |  |  | 535 |  |  | 560 |  |  | 549 |  |  | 565 |  |  | 503 |  |  | 466 |  |  | 545 |  |  | 496 |  |  | 509 |  |  | 562 |  |  | 477 |  |  | 516 |  |  | 482 |  |  | 532 |  |  | 501 |  |  | 464 |  |  | 502 |  |  | 496 |  |  | 535 |  |  | 500 |  |  | 438 |  |  | 482 |  |  | 519 |  |  | 459 |  |  | 500 |  |  | 440 |  |  | 503 |  |  | 540 |  |  | 501 |  |  | 504 |  |  | 501 |  |  | 491 |  |  | 536 |  |  | 505 |  |  | 532 |  |  | 558 |  |  | 552 |  |  | 485 |  |  | 538 |  |  | 493 |  |  | 508 |  |  | 517 |  |  | 502 |  |  | 501 |  |  | 504 |  |  | 490 |  |  | 452 |  |  | 485 |  |  | 514 |  |  | 552 |  |  | 531 |  |  | 497 |  |  | 497 |  |  | 524 |  |  | 493 |  |  | 494 |  |  | 491 |  |  | 549 |  |  | 472 |  |  | 488 |  |  | 505 |  |  | 547 |  |  | 520 |  |  | 475 |  |  | 545 |  |  | 573 |  |  | 489 |  |  | 507 |  |  | 477 |  |  | 478 |  |  | 513 |  |  | 466 |  |  | 496 |  |  | 521 |  |  | 521 |  |  | 514 |  |  | 569 |  |  | 561 |  |  | 509 |  |  | 483 |  |  | 528 |  |  | 506 |  |  | 487 |  |  | 492 |  |  | 488 |  |  | 519 |  |  | 493 |  |  | 516 |  |  | 538 |  |  | 479 |  |  | 491 |  |  | 499 |  |  | 514 |  |  | 540 |  |  | 532 |  |  | 508 |  |  | 488 |  |  | 527 |  |  | 585 |  |  | 520 |  |  | 526 |  |  | 509 |  |  | 517 |  |  | 495 |  |  | 552 |  |  | 565 |  |  | 498 |  |  | 525 |  |  | 481 |  |  | 535 |  |  | 595 |  |  | 550 |  |  | 513 |  |  | 516 |  |  | 533 |  |  | 512 |  |  | 585 |  |  | 491 |  |  | 525 |  |  | 479 |  |  | 496 |  |  | 538 |  |  | 481 |  |  | 512 |  |  | 530 |  |  | 446 |  |  | 516 |  |  | 507 |  |  | 530 |  |  | 538 |  |  | 513 |  |  | 522 |  |  | 470 |  |  | 521 |  |  | 571 |  |  | 515 |  |  | 587 |  |  | 512 |  |  | 553 |  |  | 481 |  |  | 543 |  |  | 525 |  |  | 504 |  |  | 522 |  |  | 543 |  |  | 571 |  |  | 536 |  |  | 454 |  |  | 493 |  |  | 490 |  |  | 482 |  |  | 523 |  |  | 514 |  |  | 489 |  |  | 487 |  |  | 489 |  |  | 494 |  |  | 498 |  |  | 520 |  |  | 532 |  |  | 506 |  |  | 464 |  |  | 484 |  |  | 487 |  |  | 514 |  |  | 485 |  |  | 505 |  |  | 510 |  |  | 533 |  |  | 480 |  |  | 511 |  |  | 553 |  |  | 502 |  |  | 485 |  |  | 511 |  |  | 443 |  |  | 531 |  |  | 480 |  |  | 503 |  |  | 510 |  |  | 484 |  |  | 491 |  |  | 474 |  |  | 473 |  |  | 474 |  |  | 514 |  |  | 490 |  |  | 455 |  |  | 510 |  |  | 580 |  |  | 517 |  |  | 565 |  |  | 517 |  |  | 446 |  |  | 517 |  |  | 528 |  |  | 568 |  |  | 520 |  |  | 492 |  |  | 525 |  |  | 522 |  |  | 502 |  |  | 521 |  |  | 494 |  |  | 493 |  |  | 542 |  |  | 528 |  |  | 511 |  |  | 507 |  |  | 556 |  |  | 551 |  |  | 507 |  |  | 506 |  |  | 504 |  |  | 466 |  |  | 495 |  |  | 480 |  |  | 489 |  |  | 502 |  |  | 529 |  |  | 506 |  |  | 462 |  |  | 466 |  |  | 518 |  |  | 551 |  |  | 541 |  |  | 537 |  |  | 485 |  |  | 548 |  |  | 498 |  |  | 559 |  |  | 502 |  |  | 468 |  |  | 520 |  |  | 567 |  |  | 530 |  |  | 542 |  |  | 484 |  |  | 470 |  |  | 495 |  |  | 534 |  |  | 506 |  |  | 453 |  |  | 508 |  |  | 487 |  |  | 528 |  |  | 488 |  |  | 525 |  |  | 487 |  |  | 476 |  |  | 522 |  |  | 509 |  |  | 497 |  |  | 523 |  |  | 534 |  |  | 519 |  |  | 513 |  |  | 464 |  |  | 569 |  |  | 482 |  |  | 561 |  |  | 502 |  |  | 488 |  |  | 572 |  |  | 508 |  |  | 521 |  |  | 537 |  |  | 494 |  |  | 528 |  |  | 510 |  |  | 504 |  |  | 566 |  |  | 514 |  |  | 502 |  |  | 517 |  |  | 509 |  |  | 535 |  |  | 544 |  |  | 545 |  |  | 470 |  |  | 534 |  |  | 506 |  |  | 527 |  |  | 507 |  |  | 530 |  |  | 517 |  |  | 518 |  |  | 480 |  |  | 512 |  |  | 489 |  |  | 480 |  |  | 479 |  |  | 491 |  |  | 545 |  |  | 444 |  |  | 507 |  |  | 524 |  |  | 509 |  |  | 530 |  |  | 493 |  |  | 489 |  |  | 544 |  |  | 606 |  |  | 473 |  |  | 554 |  |  | 555 |  |  | 541 |  |  | 477 |  |  | 533 |  |  | 507 |  |  | 518 |  |  | 474 |  |  | 556 |  |  | 460 |  |  | 519 |  |  | 516 |  |  | 500 |  |  | 549 |  |  | 550 |  |  | 538 |  |  | 523 |  |  | 553 |  |  | 524 |  |  | 537 |  |  | 465 |  |  | 531 |  |  | 501 |  |  | 517 |  |  | 486 |  |  | 516 |  |  | 499 |  |  | 544 |  |  | 514 |  |  | 494 |  |  | 505 |  |  | 532 |  |  | 522 |  |  | 506 |  |  | 579 |  |  | 537 |  |  | 470 |  |  | 530 |  |  | 473 |  |  | 537 |  |  | 488 |  |  | 526 |  |  | 477 |  |  | 557 |  |  | 514 |  |  | 454 |  |  | 458 |  |  | 480 |  |  | 550 |  |  | 483 |  |  | 580 |  |  | 485 |  |  | 472 |  |  | 482 |  |  | 467 |  |  | 475 |  |  | 564 |  |  | 497 |  |  | 506 |  |  | 540 |  |  | 462 |  |  | 470 |  |  | 545 |  |  | 503 |  |  | 503 |  |  | 538 |  |  | 477 |  |  | 501 |  |  | 527 |  |  | 520 |  |  | 504 |  |  | 469 |  |  | 509 |  |  | 463 |  |  | 569 |  |  | 490 |  |  | 517 |  |  | 508 |  |  | 546 |  |  | 533 |  |  | 527 |  |  | 506 |  |  | 559 |  |  | 583 |  |  | 496 |  |  | 550 |  |  | 535 |  |  | 515 |  |  | 499 |  |  | 508 |  |  | 525 |  |  | 569 |  |  | 509 |  |  | 532 |  |  | 465 |  |  | 498 |  |  | 562 |  |  | 452 |  |  | 490 |  |  | 529 |  |  | 515 |  |  | 471 |  |  | 466 |  |  | 547 |  |  | 511 |  |  | 513 |  |  | 525 |  |  | 537 |  |  | 503 |  |  | 507 |  |  | 577 |  |  | 498 |  |  | 522 |  |  | 488 |  |  | 510 |  |  | 514 |  |  | 508 |  |  | 530 |  |  | 524 |  |  | 498 |  |  | 585 |  |  | 465 |  |  | 528 |  |  | 522 |  |  | 551 |  |  | 475 |  |  | 482 |  |  | 502 |  |  | 520 |  |  | 541 |  |  | 503 |  |  | 548 |  |  | 551 |  |  | 533 |  |  | 416 |  |  | 527 |  |  | 479 |  |  | 549 |  |  | 456 |  |  | 482 |  |  | 574 |  |  | 481 |  |  | 494 |  |  | 510 |  |  | 440 |  |  | 535 |  |  | 524 |  |  | 532 |  |  | 583 |  |  | 469 |  |  | 534 |  |  | 490 |  |  | 497 |  |  | 489 |  |  | 453 |  |  | 532 |  |  | 564 |  |  | 507 |  |  | 501 |  |  | 531 |  |  | 517 |  |  | 481 |  |  | 503 |  |  | 546 |  |  | 522 |  |  | 499 |  |  | 485 |  |  | 543 |  |  | 491 |  |  | 490 |  |  | 540 |  |  | 536 |  |  | 514 |  |  | 472 |  |  | 574 |  |  | 467 |  |  | 488 |  |  | 532 |  |  | 482 |  |  | 536 |  |  | 511 |  |  | 533 |  |  | 527 |  |  | 495 |  |  | 491 |  |  | 489 |  |  | 491 |  |  | 503 |  |  | 509 |  |  | 508 |  |  | 511 |  |  | 501 |  |  | 552 |  |  | 598 |  |  | 536 |  |  | 540 |  |  | 493 |  |  | 507 |  |  | 504 |  |  | 531 |  |  | 487 |  |  | 501 |  |  | 476 |  |  | 501 |  |  | 491 |  |  | 491 |  |  | 540 |  |  | 516 |  |  | 509 |  |  | 517 |  |  | 541 |  |  | 544 |  |  | 538 |  |  | 563 |  |  | 481 |  |  | 482 |  |  | 480 |  |  | 561 |  |  | 505 |  |  | 548 |  |  | 475 |  |  | 509 |  |  | 518 |  |  | 489 |  |  | 490 |  |  | 484 |  |  | 496 |  |  | 502 |  |  | 502 |  |  | 511 |  |  | 454 |  |  | 478 |  |  | 494 |  |  | 501 |  |  | 494 |  |  | 477 |  |  | 492 |  |  | 489 |  |  | 553 |  |  | 527 |  |  | 505 |  |  | 497 |  |  | 527 |  |  | 561 |  |  | 518 |  |  | 524 |  |  | 522 |  |  | 503 |  |  | 543 |  |  | 482 |  |  | 519 |  |  | 486 |  |  | 510 |  |  | 506 |  |  | 553 |  |  | 530 |  |  | 564 |  |  | 457 |  |  | 485 |  |  | 426 |  |  | 550 |  |  | 532 |  |  | 511 |  |  | 549 |  |  | 490 |  |  | 547 |  |  | 510 |  |  | 513 |  |  | 469 |  |  | 496 |  |  | 556 |  |  | 532 |  |  | 508 |  |  | 489 |  |  | 524 |  |  | 472 |  |  | 492 |  |  | 498 |  |  | 494 |  |  | 493 |  |  | 505 |  |  | 538 |  |  | 469 |  |  | 525 |  |  | 523 |  |  | 497 |  |  | 519 |  |  | 478 |  |  | 475 |  |  | 482 |  |  | 527 |  |  | 554 |  |  | 492 |  |  | 520 |  |  | 533 |  |  | 536 |  |  | 499 |  |  | 469 |  |  | 534 |  |  | 554 |  |  | 467 |  |  | 482 |  |  | 512 |  |  | 514 |  |  | 466 |  |  | 509 |  |  | 507 |  |  | 496 |  |  | 543 |  |  | 547 |  |  | 498 |  |  | 512 |  |  | 525 |  |  | 488 |  |  | 518 |  |  | 545 |  |  | 510 |  |  | 585 |  |  | 512 |  |  | 549 |  |  | 495 |  |  | 570 |  |  | 510 |  |  | 590 |  |  | 458 |  |  | 503 |  |  | 474 |  |  | 475 |  |  | 485 |  |  | 467 |  |  | 532 |  |  | 554 |  |  | 520 |  |  | 496 |  |  | 464 |  |  | 535 |  |  | 445 |  |  | 549 |  |  | 502 |  |  | 489 |  |  | 513 |  |  | 501 |  |  | 500 |  |  | 475 |  |  | 540 |  |  | 533 |  |  | 484 |  |  | 533 |  |  | 508 |  |  | 476 |  |  | 501 |  |  | 474 |  |  | 503 |  |  | 483 |  |  | 581 |  |  | 521 |  |  | 602 |  |  | 485 |  |  | 514 |  |  | 438 |  |  | 540 |  |  | 479 |  |  | 512 |  |  | 525 |  |  | 515 |  |  | 475 |  |  | 472 |  |  | 536 |  |  | 504 |  |  | 517 |  |  | 572 |  |  | 475 |  |  | 479 |  |  | 498 |  |  | 492 |  |  | 491 |  |  | 508 |  |  | 487 |  |  | 542 |  |  | 480 |  |  | 517 |  |  | 514 |  |  | 498 |  |  | 517 |  |  | 476 |  |  | 483 |  |  | 536 |  |  | 463 |  |  | 466 |  |  | 568 |  |  | 577 |  |  | 522 |  |  | 545 |  |  | 510 |  |  | 479 |  |  | 460 |  |  | 495 |  |  | 511 |  |  | 482 |  |  | 522 |  |  | 538 |  |  | 514 |  |  | 521 |  |  | 509 |  |  | 434 |  |  | 513 |  |  | 453 |  |  | 516 |  |  | 526 |  |  | 487 |  |  | 491 |  |  | 543 |  |  | 514 |  |  | 548 |  |  | 491 |  |  | 520 |  |  | 495 |  |  | 485 |  |  | 503 |  |  | 496 |  |  | 538 |  |  | 563 |  |  | 518 |  |  | 545 |  |  | 485 |  |  | 511 |  |  | 520 |  |  | 528 |  |  | 510 |  |  | 507 |  |  | 520 |  |  | 561 |  |  | 511 |  |  | 495 |  |  | 506 |  |  | 442 |  |  | 508 |  |  | 467 |  |  | 459 |  |  | 519 |  |  | 495 |  |  | 473 |  |  | 511 |  |  | 525 |  |  | 475 |  |  | 526 |  |  | 519 |  |  | 487 |  |  | 523 |  |  | 556 |  |  | 509 |  |  | 529 |  |  | 514 |  |  | 538 |  |  | 497 |  |  | 459 |  |  | 535 |  |  | 554 |  |  | 489 |  |  | 565 |  |  | 525 |  |  | 537 |  |  | 529 |  |  | 521 |  |  | 557 |  |  | 526 |  |  | 498 |  |  | 548 |  |  | 519 |  |  | 519 |  |  | 460 |  |  | 504 |  |  | 505 |  |  | 523 |  |  | 502 |  |  | 515 |  |  | 563 |  |  | 538 |  |  | 463 |  |  | 485 |  |  | 544 |  |  | 528 |  |  | 502 |  |  | 551 |  |  | 500 |  |  | 498 |  |  | 546 |  |  | 508 |  |  | 527 |  |  | 464 |  |  | 538 |  |  | 537 |  |  | 489 |  |  | 505 |  |  | 534 |  |  | 508 |  |  | 518 |  |  | 455 |  |  | 534 |  |  | 530 |  |  | 535 |  |  | 546 |  |  | 425 |  |  | 546 |  |  | 511 |  |  | 520 |  |  | 534 |  |  | 485 |  |  | 503 |  |  | 494 |  |  | 524 |  |  | 487 |  |  | 495 |  |  | 534 |  |  | 507 |  |  | 532 |  |  | 496 |  |  | 503 |  |  | 551 |  |  | 549 |  |  | 490 |  |  | 555 |  |  | 472 |  |  | 503 |  |  | 587 |  |  | 506 |  |  | 453 |  |  | 471 |  |  | 509 |  |  | 494 |  |  | 525 |  |  | 509 |  |  | 528 |  |  | 498 |  |  | 499 |  |  | 529 |  |  | 525 |  |  | 485 |  |  | 506 |  |  | 491 |  |  | 520 |  |  | 496 |  |  | 550 |  |  | 522 |  |  | 523 |  |  | 608 |  |  | 506 |  |  | 559 |  |  | 529 |  |  | 569 |  |  | 509 |  |  | 506 |  |  | 488 |  |  | 534 |  |  | 521 |  |  | 488 |  |  | 495 |  |  | 557 |  |  | 478 |  |  | 486 |  |  | 499 |  |  | 512 |  |  | 505 |  |  | 533 |  |  | 539 |  |  | 509 |  |  | 477 |  |  | 490 |  |  | 466 |  |  | 539 |  |  | 541 |  |  | 492 |  |  | 571 |  |  | 497 |  |  | 516 |  |  | 526 |  |  | 517 |  |  | 516 |  |  | 468 |  |  | 531 |  |  | 511 |  |  | 526 |  |  | 576 |  |  | 491 |  |  | 580 |  |  | 495 |  |  | 515 |  |  | 495 |  |  | 492 |  |  | 487 |  |  | 550 |  |  | 516 |  |  | 491 |  |  | 477 |  |  | 490 |  |  | 483 |  |  | 499 |  |  | 500 |  |  | 525 |  |  | 530 |  |  | 555 |  |  | 483 |  |  | 532 |  |  | 538 |  |  | 536 |  |  | 487 |  |  | 518 |  |  | 502 |  |  | 541 |  |  | 528 |  |  | 487 |  |  | 500 |  |  | 463 |  |  | 474 |  |  | 461 |  |  | 535 |  |  | 484 |  |  | 455 |  |  | 536 |  |  | 540 |  |  | 526 |  |  | 465 |  |  | 515 |  |  | 500 |  |  | 556 |  |  | 451 |  |  | 514 |  |  | 527 |  |  | 545 |  |  | 516 |  |  | 489 |  |  | 520 |  |  | 512 |  |  | 503 |  |  | 522 |  |  | 587 |  |  | 577 |  |  | 507 |  |  | 556 |  |  | 537 |  |  | 532 |  |  | 533 |  |  | 558 |  |  | 517 |  |  | 521 |  |  | 566 |  |  | 496 |  |  | 473 |  |  | 521 |  |  | 487 |  |  | 487 |  |  | 446 |  |  | 524 |  |  | 478 |  |  | 557 |  |  | 561 |  |  | 501 |  |  | 534 |  |  | 528 |  |  | 518 |  |  | 490 |  |  | 462 |  |  | 530 |  |  | 491 |  |  | 530 |  |  | 482 |  |  | 530 |  |  | 483 |  |  | 551 |  |  | 512 |  |  | 538 |  |  | 492 |  |  | 527 |  |  | 497 |  |  | 504 |  |  | 479 |  |  | 526 |  |  | 453 |  |  | 505 |  |  | 450 |  |  | 530 |  |  | 520 |  |  | 499 |  |  | 556 |  |  | 492 |  |  | 534 |  |  | 534
18 |  | 551 |  |  | 600 |  |  | 565 |  |  | 501 |  |  | 598 |  |  | 543 |  |  | 564 |  |  | 519 |  |  | 563 |  |  | 559 |  |  | 581 |  |  | 564 |  |  | 604 |  |  | 542 |  |  | 481 |  |  | 560 |  |  | 535 |  |  | 535 |  |  | 588 |  |  | 492 |  |  | 542 |  |  | 508 |  |  | 553 |  |  | 530 |  |  | 488 |  |  | 528 |  |  | 535 |  |  | 556 |  |  | 526 |  |  | 485 |  |  | 529 |  |  | 545 |  |  | 506 |  |  | 539 |  |  | 469 |  |  | 527 |  |  | 579 |  |  | 540 |  |  | 551 |  |  | 548 |  |  | 515 |  |  | 551 |  |  | 544 |  |  | 547 |  |  | 582 |  |  | 578 |  |  | 524 |  |  | 585 |  |  | 514 |  |  | 534 |  |  | 532 |  |  | 528 |  |  | 540 |  |  | 543 |  |  | 519 |  |  | 473 |  |  | 532 |  |  | 535 |  |  | 591 |  |  | 555 |  |  | 512 |  |  | 523 |  |  | 563 |  |  | 508 |  |  | 515 |  |  | 512 |  |  | 573 |  |  | 511 |  |  | 527 |  |  | 529 |  |  | 586 |  |  | 541 |  |  | 499 |  |  | 592 |  |  | 620 |  |  | 528 |  |  | 533 |  |  | 516 |  |  | 502 |  |  | 539 |  |  | 513 |  |  | 535 |  |  | 545 |  |  | 550 |  |  | 540 |  |  | 616 |  |  | 600 |  |  | 548 |  |  | 509 |  |  | 567 |  |  | 521 |  |  | 534 |  |  | 531 |  |  | 512 |  |  | 558 |  |  | 540 |  |  | 537 |  |  | 567 |  |  | 505 |  |  | 512 |  |  | 538 |  |  | 553 |  |  | 555 |  |  | 558 |  |  | 534 |  |  | 527 |  |  | 542 |  |  | 606 |  |  | 546 |  |  | 541 |  |  | 556 |  |  | 546 |  |  | 519 |  |  | 599 |  |  | 604 |  |  | 537 |  |  | 564 |  |  | 520 |  |  | 564 |  |  | 610 |  |  | 576 |  |  | 542 |  |  | 531 |  |  | 580 |  |  | 527 |  |  | 609 |  |  | 512 |  |  | 554 |  |  | 500 |  |  | 517 |  |  | 553 |  |  | 505 |  |  | 536 |  |  | 577 |  |  | 472 |  |  | 555 |  |  | 528 |  |  | 554 |  |  | 559 |  |  | 542 |  |  | 551 |  |  | 485 |  |  | 547 |  |  | 586 |  |  | 562 |  |  | 602 |  |  | 551 |  |  | 592 |  |  | 520 |  |  | 564 |  |  | 572 |  |  | 533 |  |  | 561 |  |  | 582 |  |  | 586 |  |  | 562 |  |  | 483 |  |  | 522 |  |  | 519 |  |  | 529 |  |  | 552 |  |  | 553 |  |  | 528 |  |  | 508 |  |  | 518 |  |  | 520 |  |  | 545 |  |  | 559 |  |  | 571 |  |  | 535 |  |  | 479 |  |  | 523 |  |  | 513 |  |  | 553 |  |  | 514 |  |  | 534 |  |  | 549 |  |  | 562 |  |  | 509 |  |  | 558 |  |  | 568 |  |  | 549 |  |  | 511 |  |  | 535 |  |  | 469 |  |  | 555 |  |  | 501 |  |  | 529 |  |  | 549 |  |  | 523 |  |  | 538 |  |  | 498 |  |  | 488 |  |  | 503 |  |  | 535 |  |  | 529 |  |  | 502 |  |  | 536 |  |  | 609 |  |  | 564 |  |  | 586 |  |  | 541 |  |  | 485 |  |  | 538 |  |  | 554 |  |  | 607 |  |  | 535 |  |  | 516 |  |  | 564 |  |  | 561 |  |  | 541 |  |  | 560 |  |  | 515 |  |  | 508 |  |  | 563 |  |  | 567 |  |  | 540 |  |  | 554 |  |  | 595 |  |  | 575 |  |  | 533 |  |  | 521 |  |  | 533 |  |  | 505 |  |  | 519 |  |  | 506 |  |  | 504 |  |  | 523 |  |  | 568 |  |  | 532 |  |  | 488 |  |  | 495 |  |  | 533 |  |  | 590 |  |  | 565 |  |  | 552 |  |  | 514 |  |  | 595 |  |  | 519 |  |  | 598 |  |  | 526 |  |  | 507 |  |  | 559 |  |  | 593 |  |  | 551 |  |  | 566 |  |  | 508 |  |  | 509 |  |  | 521 |  |  | 573 |  |  | 527 |  |  | 492 |  |  | 529 |  |  | 534 |  |  | 567 |  |  | 517 |  |  | 546 |  |  | 511 |  |  | 500 |  |  | 537 |  |  | 535 |  |  | 523 |  |  | 552 |  |  | 549 |  |  | 558 |  |  | 537 |  |  | 488 |  |  | 608 |  |  | 529 |  |  | 600 |  |  | 531 |  |  | 512 |  |  | 619 |  |  | 529 |  |  | 560 |  |  | 584 |  |  | 518 |  |  | 567 |  |  | 534 |  |  | 551 |  |  | 587 |  |  | 529 |  |  | 526 |  |  | 546 |  |  | 533 |  |  | 564 |  |  | 573 |  |  | 574 |  |  | 509 |  |  | 573 |  |  | 545 |  |  | 542 |  |  | 554 |  |  | 569 |  |  | 564 |  |  | 565 |  |  | 501 |  |  | 551 |  |  | 504 |  |  | 495 |  |  | 503 |  |  | 520 |  |  | 560 |  |  | 470 |  |  | 533 |  |  | 563 |  |  | 548 |  |  | 554 |  |  | 532 |  |  | 515 |  |  | 591 |  |  | 630 |  |  | 512 |  |  | 601 |  |  | 602 |  |  | 562 |  |  | 498 |  |  | 572 |  |  | 533 |  |  | 544 |  |  | 495 |  |  | 595 |  |  | 486 |  |  | 540 |  |  | 540 |  |  | 515 |  |  | 596 |  |  | 574 |  |  | 585 |  |  | 562 |  |  | 574 |  |  | 563 |  |  | 552 |  |  | 504 |  |  | 555 |  |  | 540 |  |  | 564 |  |  | 501 |  |  | 545 |  |  | 528 |  |  | 559 |  |  | 538 |  |  | 515 |  |  | 520 |  |  | 571 |  |  | 551 |  |  | 532 |  |  | 594 |  |  | 576 |  |  | 485 |  |  | 554 |  |  | 512 |  |  | 584 |  |  | 514 |  |  | 550 |  |  | 503 |  |  | 586 |  |  | 538 |  |  | 493 |  |  | 479 |  |  | 501 |  |  | 574 |  |  | 522 |  |  | 609 |  |  | 506 |  |  | 493 |  |  | 506 |  |  | 496 |  |  | 501 |  |  | 603 |  |  | 518 |  |  | 545 |  |  | 579 |  |  | 491 |  |  | 485 |  |  | 566 |  |  | 524 |  |  | 518 |  |  | 562 |  |  | 516 |  |  | 548 |  |  | 551 |  |  | 567 |  |  | 530 |  |  | 495 |  |  | 548 |  |  | 484 |  |  | 598 |  |  | 529 |  |  | 543 |  |  | 537 |  |  | 561 |  |  | 572 |  |  | 548 |  |  | 527 |  |  | 585 |  |  | 609 |  |  | 517 |  |  | 589 |  |  | 561 |  |  | 530 |  |  | 525 |  |  | 534 |  |  | 564 |  |  | 598 |  |  | 533 |  |  | 571 |  |  | 486 |  |  | 513 |  |  | 601 |  |  | 473 |  |  | 505 |  |  | 553 |  |  | 544 |  |  | 486 |  |  | 492 |  |  | 571 |  |  | 558 |  |  | 552 |  |  | 564 |  |  | 566 |  |  | 542 |  |  | 528 |  |  | 601 |  |  | 545 |  |  | 561 |  |  | 527 |  |  | 549 |  |  | 553 |  |  | 547 |  |  | 554 |  |  | 553 |  |  | 522 |  |  | 632 |  |  | 504 |  |  | 543 |  |  | 561 |  |  | 566 |  |  | 501 |  |  | 503 |  |  | 541 |  |  | 535 |  |  | 580 |  |  | 542 |  |  | 574 |  |  | 577 |  |  | 557 |  |  | 440 |  |  | 553 |  |  | 518 |  |  | 575 |  |  | 495 |  |  | 521 |  |  | 600 |  |  | 496 |  |  | 533 |  |  | 536 |  |  | 469 |  |  | 574 |  |  | 571 |  |  | 579 |  |  | 630 |  |  | 498 |  |  | 558 |  |  | 537 |  |  | 521 |  |  | 528 |  |  | 492 |  |  | 547 |  |  | 590 |  |  | 528 |  |  | 525 |  |  | 578 |  |  | 541 |  |  | 528 |  |  | 550 |  |  | 593 |  |  | 548 |  |  | 538 |  |  | 532 |  |  | 590 |  |  | 538 |  |  | 511 |  |  | 579 |  |  | 560 |  |  | 561 |  |  | 511 |  |  | 589 |  |  | 493 |  |  | 527 |  |  | 571 |  |  | 497 |  |  | 562 |  |  | 532 |  |  | 580 |  |  | 566 |  |  | 516 |  |  | 530 |  |  | 510 |  |  | 517 |  |  | 524 |  |  | 548 |  |  | 547 |  |  | 526 |  |  | 540 |  |  | 576 |  |  | 613 |  |  | 551 |  |  | 569 |  |  | 540 |  |  | 546 |  |  | 533 |  |  | 546 |  |  | 516 |  |  | 548 |  |  | 515 |  |  | 522 |  |  | 530 |  |  | 530 |  |  | 569 |  |  | 531 |  |  | 538 |  |  | 532 |  |  | 580 |  |  | 559 |  |  | 585 |  |  | 589 |  |  | 520 |  |  | 521 |  |  | 495 |  |  | 576 |  |  | 526 |  |  | 574 |  |  | 514 |  |  | 535 |  |  | 547 |  |  | 513 |  |  | 519 |  |  | 510 |  |  | 517 |  |  | 517 |  |  | 541 |  |  | 550 |  |  | 483 |  |  | 517 |  |  | 509 |  |  | 548 |  |  | 533 |  |  | 492 |  |  | 513 |  |  | 504 |  |  | 574 |  |  | 548 |  |  | 552 |  |  | 526 |  |  | 556 |  |  | 608 |  |  | 565 |  |  | 563 |  |  | 561 |  |  | 542 |  |  | 572 |  |  | 508 |  |  | 558 |  |  | 510 |  |  | 531 |  |  | 530 |  |  | 592 |  |  | 569 |  |  | 611 |  |  | 483 |  |  | 532 |  |  | 441 |  |  | 589 |  |  | 547 |  |  | 550 |  |  | 578 |  |  | 537 |  |  | 562 |  |  | 536 |  |  | 560 |  |  | 498 |  |  | 522 |  |  | 585 |  |  | 579 |  |  | 532 |  |  | 513 |  |  | 571 |  |  | 498 |  |  | 518 |  |  | 513 |  |  | 533 |  |  | 519 |  |  | 552 |  |  | 564 |  |  | 484 |  |  | 564 |  |  | 538 |  |  | 536 |  |  | 543 |  |  | 502 |  |  | 504 |  |  | 521 |  |  | 556 |  |  | 601 |  |  | 516 |  |  | 544 |  |  | 572 |  |  | 575 |  |  | 520 |  |  | 484 |  |  | 581 |  |  | 580 |  |  | 491 |  |  | 521 |  |  | 533 |  |  | 553 |  |  | 495 |  |  | 524 |  |  | 522 |  |  | 517 |  |  | 582 |  |  | 573 |  |  | 537 |  |  | 559 |  |  | 564 |  |  | 535 |  |  | 547 |  |  | 574 |  |  | 531 |  |  | 606 |  |  | 551 |  |  | 578 |  |  | 542 |  |  | 594 |  |  | 531 |  |  | 616 |  |  | 505 |  |  | 550 |  |  | 500 |  |  | 514 |  |  | 532 |  |  | 514 |  |  | 547 |  |  | 580 |  |  | 549 |  |  | 535 |  |  | 503 |  |  | 559 |  |  | 469 |  |  | 564 |  |  | 523 |  |  | 528 |  |  | 552 |  |  | 522 |  |  | 539 |  |  | 496 |  |  | 561 |  |  | 559 |  |  | 513 |  |  | 580 |  |  | 555 |  |  | 491 |  |  | 522 |  |  | 495 |  |  | 518 |  |  | 504 |  |  | 620 |  |  | 560 |  |  | 641 |  |  | 532 |  |  | 553 |  |  | 464 |  |  | 566 |  |  | 503 |  |  | 536 |  |  | 564 |  |  | 539 |  |  | 499 |  |  | 498 |  |  | 551 |  |  | 525 |  |  | 543 |  |  | 611 |  |  | 514 |  |  | 494 |  |  | 519 |  |  | 531 |  |  | 538 |  |  | 529 |  |  | 508 |  |  | 566 |  |  | 519 |  |  | 546 |  |  | 543 |  |  | 524 |  |  | 543 |  |  | 523 |  |  | 512 |  |  | 575 |  |  | 502 |  |  | 481 |  |  | 607 |  |  | 606 |  |  | 543 |  |  | 584 |  |  | 534 |  |  | 494 |  |  | 484 |  |  | 516 |  |  | 537 |  |  | 529 |  |  | 543 |  |  | 567 |  |  | 543 |  |  | 550 |  |  | 556 |  |  | 460 |  |  | 539 |  |  | 492 |  |  | 545 |  |  | 573 |  |  | 511 |  |  | 515 |  |  | 558 |  |  | 540 |  |  | 563 |  |  | 538 |  |  | 559 |  |  | 510 |  |  | 524 |  |  | 527 |  |  | 522 |  |  | 553 |  |  | 589 |  |  | 547 |  |  | 566 |  |  | 506 |  |  | 558 |  |  | 549 |  |  | 543 |  |  | 539 |  |  | 554 |  |  | 559 |  |  | 585 |  |  | 526 |  |  | 519 |  |  | 532 |  |  | 481 |  |  | 547 |  |  | 496 |  |  | 498 |  |  | 566 |  |  | 516 |  |  | 520 |  |  | 540 |  |  | 540 |  |  | 490 |  |  | 541 |  |  | 540 |  |  | 516 |  |  | 538 |  |  | 585 |  |  | 538 |  |  | 555 |  |  | 553 |  |  | 562 |  |  | 521 |  |  | 480 |  |  | 559 |  |  | 593 |  |  | 518 |  |  | 589 |  |  | 549 |  |  | 576 |  |  | 576 |  |  | 542 |  |  | 581 |  |  | 565 |  |  | 537 |  |  | 587 |  |  | 548 |  |  | 548 |  |  | 475 |  |  | 525 |  |  | 544 |  |  | 570 |  |  | 541 |  |  | 530 |  |  | 602 |  |  | 553 |  |  | 487 |  |  | 506 |  |  | 591 |  |  | 567 |  |  | 531 |  |  | 566 |  |  | 539 |  |  | 522 |  |  | 572 |  |  | 534 |  |  | 566 |  |  | 493 |  |  | 577 |  |  | 552 |  |  | 528 |  |  | 520 |  |  | 560 |  |  | 523 |  |  | 533 |  |  | 479 |  |  | 558 |  |  | 569 |  |  | 550 |  |  | 585 |  |  | 472 |  |  | 561 |  |  | 535 |  |  | 549 |  |  | 573 |  |  | 506 |  |  | 532 |  |  | 515 |  |  | 545 |  |  | 513 |  |  | 519 |  |  | 563 |  |  | 546 |  |  | 553 |  |  | 525 |  |  | 542 |  |  | 575 |  |  | 588 |  |  | 505 |  |  | 570 |  |  | 493 |  |  | 527 |  |  | 634 |  |  | 527 |  |  | 479 |  |  | 495 |  |  | 556 |  |  | 515 |  |  | 549 |  |  | 533 |  |  | 552 |  |  | 522 |  |  | 528 |  |  | 550 |  |  | 549 |  |  | 532 |  |  | 545 |  |  | 520 |  |  | 549 |  |  | 543 |  |  | 576 |  |  | 569 |  |  | 549 |  |  | 647 |  |  | 545 |  |  | 598 |  |  | 550 |  |  | 590 |  |  | 524 |  |  | 521 |  |  | 517 |  |  | 549 |  |  | 536 |  |  | 527 |  |  | 524 |  |  | 586 |  |  | 507 |  |  | 525 |  |  | 538 |  |  | 551 |  |  | 531 |  |  | 557 |  |  | 565 |  |  | 530 |  |  | 516 |  |  | 516 |  |  | 492 |  |  | 565 |  |  | 588 |  |  | 507 |  |  | 618 |  |  | 526 |  |  | 537 |  |  | 573 |  |  | 541 |  |  | 545 |  |  | 507 |  |  | 546 |  |  | 535 |  |  | 555 |  |  | 615 |  |  | 515 |  |  | 619 |  |  | 516 |  |  | 554 |  |  | 521 |  |  | 521 |  |  | 526 |  |  | 571 |  |  | 555 |  |  | 538 |  |  | 492 |  |  | 514 |  |  | 509 |  |  | 528 |  |  | 524 |  |  | 554 |  |  | 559 |  |  | 602 |  |  | 509 |  |  | 571 |  |  | 564 |  |  | 575 |  |  | 502 |  |  | 557 |  |  | 531 |  |  | 580 |  |  | 552 |  |  | 508 |  |  | 547 |  |  | 484 |  |  | 495 |  |  | 508 |  |  | 574 |  |  | 505 |  |  | 481 |  |  | 583 |  |  | 579 |  |  | 547 |  |  | 504 |  |  | 536 |  |  | 539 |  |  | 582 |  |  | 472 |  |  | 535 |  |  | 566 |  |  | 592 |  |  | 555 |  |  | 510 |  |  | 559 |  |  | 538 |  |  | 524 |  |  | 543 |  |  | 602 |  |  | 616 |  |  | 554 |  |  | 603 |  |  | 576 |  |  | 556 |  |  | 548 |  |  | 587 |  |  | 532 |  |  | 550 |  |  | 587 |  |  | 535 |  |  | 494 |  |  | 542 |  |  | 513 |  |  | 508 |  |  | 472 |  |  | 553 |  |  | 502 |  |  | 596 |  |  | 600 |  |  | 527 |  |  | 581 |  |  | 557 |  |  | 557 |  |  | 529 |  |  | 509 |  |  | 556 |  |  | 517 |  |  | 551 |  |  | 508 |  |  | 569 |  |  | 522 |  |  | 575 |  |  | 541 |  |  | 585 |  |  | 516 |  |  | 574 |  |  | 536 |  |  | 543 |  |  | 505 |  |  | 541 |  |  | 482 |  |  | 520 |  |  | 479 |  |  | 551 |  |  | 567 |  |  | 523 |  |  | 582 |  |  | 539 |  |  | 549 |  |  | 581
19 |  | 590 |  |  | 629 |  |  | 604 |  |  | 516 |  |  | 637 |  |  | 567 |  |  | 603 |  |  | 548 |  |  | 578 |  |  | 606 |  |  | 596 |  |  | 603 |  |  | 643 |  |  | 563 |  |  | 528 |  |  | 589 |  |  | 582 |  |  | 574 |  |  | 635 |  |  | 513 |  |  | 571 |  |  | 523 |  |  | 592 |  |  | 559 |  |  | 527 |  |  | 554 |  |  | 556 |  |  | 595 |  |  | 565 |  |  | 500 |  |  | 568 |  |  | 560 |  |  | 521 |  |  | 565 |  |  | 484 |  |  | 548 |  |  | 608 |  |  | 561 |  |  | 572 |  |  | 587 |  |  | 554 |  |  | 590 |  |  | 583 |  |  | 571 |  |  | 608 |  |  | 599 |  |  | 545 |  |  | 609 |  |  | 540 |  |  | 558 |  |  | 553 |  |  | 549 |  |  | 566 |  |  | 572 |  |  | 558 |  |  | 520 |  |  | 547 |  |  | 561 |  |  | 612 |  |  | 576 |  |  | 551 |  |  | 547 |  |  | 602 |  |  | 537 |  |  | 536 |  |  | 541 |  |  | 602 |  |  | 526 |  |  | 551 |  |  | 576 |  |  | 610 |  |  | 567 |  |  | 538 |  |  | 639 |  |  | 641 |  |  | 554 |  |  | 557 |  |  | 545 |  |  | 523 |  |  | 578 |  |  | 560 |  |  | 559 |  |  | 566 |  |  | 589 |  |  | 579 |  |  | 642 |  |  | 629 |  |  | 577 |  |  | 535 |  |  | 614 |  |  | 568 |  |  | 573 |  |  | 560 |  |  | 533 |  |  | 587 |  |  | 555 |  |  | 576 |  |  | 606 |  |  | 529 |  |  | 541 |  |  | 562 |  |  | 592 |  |  | 594 |  |  | 582 |  |  | 549 |  |  | 574 |  |  | 563 |  |  | 627 |  |  | 585 |  |  | 567 |  |  | 582 |  |  | 575 |  |  | 566 |  |  | 628 |  |  | 619 |  |  | 584 |  |  | 603 |  |  | 559 |  |  | 588 |  |  | 631 |  |  | 600 |  |  | 568 |  |  | 557 |  |  | 601 |  |  | 548 |  |  | 648 |  |  | 559 |  |  | 569 |  |  | 521 |  |  | 532 |  |  | 592 |  |  | 531 |  |  | 557 |  |  | 606 |  |  | 501 |  |  | 584 |  |  | 552 |  |  | 601 |  |  | 598 |  |  | 581 |  |  | 572 |  |  | 511 |  |  | 562 |  |  | 607 |  |  | 583 |  |  | 628 |  |  | 572 |  |  | 621 |  |  | 549 |  |  | 611 |  |  | 611 |  |  | 572 |  |  | 582 |  |  | 621 |  |  | 601 |  |  | 601 |  |  | 522 |  |  | 561 |  |  | 534 |  |  | 558 |  |  | 578 |  |  | 600 |  |  | 567 |  |  | 547 |  |  | 557 |  |  | 567 |  |  | 566 |  |  | 585 |  |  | 592 |  |  | 574 |  |  | 518 |  |  | 549 |  |  | 542 |  |  | 574 |  |  | 529 |  |  | 573 |  |  | 570 |  |  | 586 |  |  | 548 |  |  | 597 |  |  | 589 |  |  | 578 |  |  | 550 |  |  | 574 |  |  | 498 |  |  | 594 |  |  | 548 |  |  | 568 |  |  | 573 |  |  | 549 |  |  | 562 |  |  | 513 |  |  | 527 |  |  | 550 |  |  | 574 |  |  | 568 |  |  | 523 |  |  | 575 |  |  | 624 |  |  | 593 |  |  | 633 |  |  | 567 |  |  | 500 |  |  | 577 |  |  | 569 |  |  | 654 |  |  | 561 |  |  | 545 |  |  | 593 |  |  | 600 |  |  | 556 |  |  | 581 |  |  | 554 |  |  | 529 |  |  | 592 |  |  | 591 |  |  | 561 |  |  | 593 |  |  | 634 |  |  | 622 |  |  | 572 |  |  | 542 |  |  | 554 |  |  | 544 |  |  | 548 |  |  | 545 |  |  | 519 |  |  | 547 |  |  | 607 |  |  | 571 |  |  | 509 |  |  | 510 |  |  | 572 |  |  | 637 |  |  | 612 |  |  | 578 |  |  | 561 |  |  | 634 |  |  | 545 |  |  | 624 |  |  | 552 |  |  | 546 |  |  | 588 |  |  | 640 |  |  | 566 |  |  | 592 |  |  | 547 |  |  | 556 |  |  | 547 |  |  | 588 |  |  | 553 |  |  | 513 |  |  | 544 |  |  | 558 |  |  | 591 |  |  | 564 |  |  | 572 |  |  | 532 |  |  | 539 |  |  | 576 |  |  | 564 |  |  | 562 |  |  | 591 |  |  | 596 |  |  | 584 |  |  | 552 |  |  | 527 |  |  | 629 |  |  | 576 |  |  | 639 |  |  | 555 |  |  | 533 |  |  | 666 |  |  | 553 |  |  | 589 |  |  | 610 |  |  | 565 |  |  | 591 |  |  | 560 |  |  | 572 |  |  | 626 |  |  | 544 |  |  | 552 |  |  | 567 |  |  | 562 |  |  | 593 |  |  | 597 |  |  | 589 |  |  | 535 |  |  | 612 |  |  | 574 |  |  | 563 |  |  | 569 |  |  | 608 |  |  | 593 |  |  | 580 |  |  | 522 |  |  | 566 |  |  | 519 |  |  | 519 |  |  | 542 |  |  | 544 |  |  | 599 |  |  | 494 |  |  | 554 |  |  | 602 |  |  | 577 |  |  | 580 |  |  | 561 |  |  | 539 |  |  | 630 |  |  | 659 |  |  | 527 |  |  | 627 |  |  | 628 |  |  | 601 |  |  | 522 |  |  | 587 |  |  | 559 |  |  | 570 |  |  | 521 |  |  | 634 |  |  | 512 |  |  | 566 |  |  | 561 |  |  | 562 |  |  | 635 |  |  | 598 |  |  | 606 |  |  | 609 |  |  | 600 |  |  | 578 |  |  | 599 |  |  | 528 |  |  | 594 |  |  | 569 |  |  | 593 |  |  | 522 |  |  | 569 |  |  | 567 |  |  | 588 |  |  | 577 |  |  | 554 |  |  | 559 |  |  | 610 |  |  | 577 |  |  | 556 |  |  | 633 |  |  | 615 |  |  | 514 |  |  | 593 |  |  | 551 |  |  | 610 |  |  | 535 |  |  | 589 |  |  | 518 |  |  | 615 |  |  | 577 |  |  | 514 |  |  | 518 |  |  | 530 |  |  | 598 |  |  | 569 |  |  | 648 |  |  | 527 |  |  | 517 |  |  | 553 |  |  | 511 |  |  | 522 |  |  | 624 |  |  | 542 |  |  | 592 |  |  | 605 |  |  | 515 |  |  | 524 |  |  | 587 |  |  | 563 |  |  | 544 |  |  | 601 |  |  | 555 |  |  | 595 |  |  | 590 |  |  | 596 |  |  | 569 |  |  | 510 |  |  | 574 |  |  | 505 |  |  | 619 |  |  | 544 |  |  | 572 |  |  | 584 |  |  | 576 |  |  | 611 |  |  | 587 |  |  | 574 |  |  | 624 |  |  | 630 |  |  | 541 |  |  | 610 |  |  | 585 |  |  | 554 |  |  | 554 |  |  | 549 |  |  | 590 |  |  | 624 |  |  | 572 |  |  | 586 |  |  | 515 |  |  | 552 |  |  | 640 |  |  | 502 |  |  | 544 |  |  | 592 |  |  | 565 |  |  | 510 |  |  | 516 |  |  | 592 |  |  | 573 |  |  | 591 |  |  | 593 |  |  | 613 |  |  | 581 |  |  | 557 |  |  | 622 |  |  | 569 |  |  | 582 |  |  | 553 |  |  | 596 |  |  | 574 |  |  | 562 |  |  | 583 |  |  | 579 |  |  | 546 |  |  | 658 |  |  | 519 |  |  | 569 |  |  | 576 |  |  | 587 |  |  | 530 |  |  | 542 |  |  | 565 |  |  | 556 |  |  | 606 |  |  | 589 |  |  | 613 |  |  | 598 |  |  | 586 |  |  | 455 |  |  | 574 |  |  | 547 |  |  | 614 |  |  | 510 |  |  | 536 |  |  | 615 |  |  | 511 |  |  | 572 |  |  | 562 |  |  | 508 |  |  | 613 |  |  | 595 |  |  | 626 |  |  | 669 |  |  | 527 |  |  | 582 |  |  | 576 |  |  | 550 |  |  | 567 |  |  | 507 |  |  | 586 |  |  | 614 |  |  | 543 |  |  | 546 |  |  | 593 |  |  | 562 |  |  | 557 |  |  | 589 |  |  | 632 |  |  | 587 |  |  | 585 |  |  | 579 |  |  | 637 |  |  | 567 |  |  | 550 |  |  | 594 |  |  | 581 |  |  | 600 |  |  | 537 |  |  | 618 |  |  | 522 |  |  | 551 |  |  | 600 |  |  | 521 |  |  | 601 |  |  | 571 |  |  | 609 |  |  | 590 |  |  | 531 |  |  | 551 |  |  | 549 |  |  | 556 |  |  | 563 |  |  | 563 |  |  | 576 |  |  | 547 |  |  | 587 |  |  | 623 |  |  | 639 |  |  | 572 |  |  | 598 |  |  | 561 |  |  | 593 |  |  | 548 |  |  | 561 |  |  | 555 |  |  | 574 |  |  | 536 |  |  | 561 |  |  | 569 |  |  | 545 |  |  | 590 |  |  | 570 |  |  | 562 |  |  | 561 |  |  | 604 |  |  | 598 |  |  | 609 |  |  | 604 |  |  | 549 |  |  | 568 |  |  | 516 |  |  | 597 |  |  | 573 |  |  | 613 |  |  | 538 |  |  | 564 |  |  | 576 |  |  | 534 |  |  | 543 |  |  | 539 |  |  | 556 |  |  | 543 |  |  | 580 |  |  | 589 |  |  | 507 |  |  | 543 |  |  | 524 |  |  | 574 |  |  | 572 |  |  | 518 |  |  | 560 |  |  | 525 |  |  | 595 |  |  | 569 |  |  | 599 |  |  | 541 |  |  | 585 |  |  | 632 |  |  | 604 |  |  | 584 |  |  | 600 |  |  | 571 |  |  | 587 |  |  | 537 |  |  | 605 |  |  | 534 |  |  | 570 |  |  | 551 |  |  | 631 |  |  | 590 |  |  | 658 |  |  | 498 |  |  | 579 |  |  | 456 |  |  | 628 |  |  | 586 |  |  | 576 |  |  | 617 |  |  | 563 |  |  | 577 |  |  | 583 |  |  | 589 |  |  | 522 |  |  | 561 |  |  | 624 |  |  | 600 |  |  | 571 |  |  | 528 |  |  | 618 |  |  | 519 |  |  | 542 |  |  | 537 |  |  | 562 |  |  | 534 |  |  | 591 |  |  | 593 |  |  | 510 |  |  | 579 |  |  | 553 |  |  | 560 |  |  | 569 |  |  | 517 |  |  | 551 |  |  | 545 |  |  | 582 |  |  | 640 |  |  | 563 |  |  | 583 |  |  | 611 |  |  | 596 |  |  | 559 |  |  | 508 |  |  | 602 |  |  | 604 |  |  | 538 |  |  | 560 |  |  | 562 |  |  | 568 |  |  | 534 |  |  | 550 |  |  | 561 |  |  | 556 |  |  | 606 |  |  | 597 |  |  | 563 |  |  | 598 |  |  | 585 |  |  | 561 |  |  | 571 |  |  | 595 |  |  | 560 |  |  | 632 |  |  | 598 |  |  | 617 |  |  | 566 |  |  | 620 |  |  | 560 |  |  | 637 |  |  | 526 |  |  | 589 |  |  | 524 |  |  | 535 |  |  | 547 |  |  | 540 |  |  | 586 |  |  | 609 |  |  | 596 |  |  | 582 |  |  | 524 |  |  | 598 |  |  | 484 |  |  | 588 |  |  | 562 |  |  | 543 |  |  | 591 |  |  | 543 |  |  | 568 |  |  | 522 |  |  | 590 |  |  | 598 |  |  | 537 |  |  | 619 |  |  | 594 |  |  | 506 |  |  | 569 |  |  | 534 |  |  | 547 |  |  | 519 |  |  | 644 |  |  | 575 |  |  | 670 |  |  | 558 |  |  | 568 |  |  | 485 |  |  | 587 |  |  | 542 |  |  | 575 |  |  | 611 |  |  | 563 |  |  | 525 |  |  | 524 |  |  | 598 |  |  | 546 |  |  | 582 |  |  | 626 |  |  | 553 |  |  | 509 |  |  | 558 |  |  | 552 |  |  | 553 |  |  | 558 |  |  | 529 |  |  | 581 |  |  | 540 |  |  | 585 |  |  | 572 |  |  | 548 |  |  | 582 |  |  | 562 |  |  | 538 |  |  | 590 |  |  | 517 |  |  | 507 |  |  | 633 |  |  | 635 |  |  | 558 |  |  | 608 |  |  | 555 |  |  | 518 |  |  | 531 |  |  | 531 |  |  | 561 |  |  | 568 |  |  | 582 |  |  | 614 |  |  | 582 |  |  | 589 |  |  | 582 |  |  | 481 |  |  | 563 |  |  | 516 |  |  | 571 |  |  | 602 |  |  | 540 |  |  | 554 |  |  | 597 |  |  | 579 |  |  | 584 |  |  | 585 |  |  | 598 |  |  | 549 |  |  | 548 |  |  | 551 |  |  | 551 |  |  | 600 |  |  | 636 |  |  | 573 |  |  | 592 |  |  | 545 |  |  | 579 |  |  | 588 |  |  | 590 |  |  | 578 |  |  | 601 |  |  | 598 |  |  | 624 |  |  | 552 |  |  | 540 |  |  | 556 |  |  | 502 |  |  | 594 |  |  | 535 |  |  | 524 |  |  | 605 |  |  | 540 |  |  | 559 |  |  | 564 |  |  | 569 |  |  | 511 |  |  | 565 |  |  | 564 |  |  | 555 |  |  | 564 |  |  | 624 |  |  | 567 |  |  | 576 |  |  | 574 |  |  | 601 |  |  | 536 |  |  | 519 |  |  | 598 |  |  | 640 |  |  | 547 |  |  | 636 |  |  | 596 |  |  | 600 |  |  | 591 |  |  | 581 |  |  | 620 |  |  | 604 |  |  | 576 |  |  | 602 |  |  | 587 |  |  | 572 |  |  | 496 |  |  | 572 |  |  | 559 |  |  | 609 |  |  | 556 |  |  | 559 |  |  | 631 |  |  | 574 |  |  | 526 |  |  | 521 |  |  | 617 |  |  | 606 |  |  | 570 |  |  | 590 |  |  | 568 |  |  | 537 |  |  | 593 |  |  | 563 |  |  | 595 |  |  | 519 |  |  | 603 |  |  | 591 |  |  | 552 |  |  | 559 |  |  | 584 |  |  | 570 |  |  | 559 |  |  | 505 |  |  | 587 |  |  | 598 |  |  | 565 |  |  | 600 |  |  | 493 |  |  | 590 |  |  | 559 |  |  | 596 |  |  | 602 |  |  | 527 |  |  | 558 |  |  | 539 |  |  | 584 |  |  | 539 |  |  | 548 |  |  | 592 |  |  | 561 |  |  | 579 |  |  | 551 |  |  | 566 |  |  | 596 |  |  | 603 |  |  | 531 |  |  | 617 |  |  | 517 |  |  | 553 |  |  | 658 |  |  | 553 |  |  | 505 |  |  | 521 |  |  | 595 |  |  | 562 |  |  | 588 |  |  | 554 |  |  | 567 |  |  | 561 |  |  | 567 |  |  | 565 |  |  | 573 |  |  | 556 |  |  | 592 |  |  | 567 |  |  | 573 |  |  | 582 |  |  | 600 |  |  | 593 |  |  | 573 |  |  | 673 |  |  | 584 |  |  | 622 |  |  | 574 |  |  | 614 |  |  | 545 |  |  | 542 |  |  | 556 |  |  | 573 |  |  | 551 |  |  | 548 |  |  | 550 |  |  | 607 |  |  | 536 |  |  | 564 |  |  | 553 |  |  | 572 |  |  | 557 |  |  | 572 |  |  | 604 |  |  | 556 |  |  | 542 |  |  | 555 |  |  | 507 |  |  | 604 |  |  | 627 |  |  | 522 |  |  | 665 |  |  | 547 |  |  | 566 |  |  | 612 |  |  | 580 |  |  | 571 |  |  | 536 |  |  | 572 |  |  | 550 |  |  | 594 |  |  | 662 |  |  | 562 |  |  | 666 |  |  | 537 |  |  | 593 |  |  | 545 |  |  | 560 |  |  | 573 |  |  | 600 |  |  | 602 |  |  | 577 |  |  | 513 |  |  | 540 |  |  | 530 |  |  | 543 |  |  | 571 |  |  | 578 |  |  | 598 |  |  | 617 |  |  | 556 |  |  | 597 |  |  | 593 |  |  | 590 |  |  | 531 |  |  | 572 |  |  | 570 |  |  | 604 |  |  | 591 |  |  | 534 |  |  | 573 |  |  | 505 |  |  | 516 |  |  | 547 |  |  | 603 |  |  | 534 |  |  | 520 |  |  | 622 |  |  | 605 |  |  | 586 |  |  | 543 |  |  | 575 |  |  | 560 |  |  | 603 |  |  | 511 |  |  | 582 |  |  | 590 |  |  | 621 |  |  | 584 |  |  | 536 |  |  | 606 |  |  | 577 |  |  | 563 |  |  | 564 |  |  | 631 |  |  | 642 |  |  | 593 |  |  | 632 |  |  | 605 |  |  | 585 |  |  | 595 |  |  | 613 |  |  | 571 |  |  | 597 |  |  | 611 |  |  | 574 |  |  | 509 |  |  | 581 |  |  | 537 |  |  | 547 |  |  | 511 |  |  | 574 |  |  | 526 |  |  | 611 |  |  | 639 |  |  | 542 |  |  | 620 |  |  | 604 |  |  | 572 |  |  | 558 |  |  | 548 |  |  | 577 |  |  | 546 |  |  | 572 |  |  | 534 |  |  | 616 |  |  | 551 |  |  | 590 |  |  | 556 |  |  | 606 |  |  | 563 |  |  | 603 |  |  | 562 |  |  | 567 |  |  | 552 |  |  | 556 |  |  | 503 |  |  | 546 |  |  | 503 |  |  | 572 |  |  | 614 |  |  | 549 |  |  | 621 |  |  | 578 |  |  | 575 |  |  | 628
20 |  | 629 |  |  | 668 |  |  | 651 |  |  | 563 |  |  | 676 |  |  | 606 |  |  | 642 |  |  | 587 |  |  | 617 |  |  | 635 |  |  | 625 |  |  | 650 |  |  | 664 |  |  | 589 |  |  | 554 |  |  | 613 |  |  | 621 |  |  | 613 |  |  | 674 |  |  | 528 |  |  | 600 |  |  | 552 |  |  | 607 |  |  | 585 |  |  | 556 |  |  | 601 |  |  | 577 |  |  | 619 |  |  | 586 |  |  | 539 |  |  | 589 |  |  | 584 |  |  | 547 |  |  | 594 |  |  | 505 |  |  | 595 |  |  | 623 |  |  | 582 |  |  | 611 |  |  | 626 |  |  | 575 |  |  | 605 |  |  | 604 |  |  | 592 |  |  | 634 |  |  | 638 |  |  | 584 |  |  | 638 |  |  | 566 |  |  | 582 |  |  | 577 |  |  | 588 |  |  | 605 |  |  | 593 |  |  | 597 |  |  | 567 |  |  | 568 |  |  | 608 |  |  | 638 |  |  | 602 |  |  | 580 |  |  | 576 |  |  | 617 |  |  | 566 |  |  | 560 |  |  | 570 |  |  | 617 |  |  | 552 |  |  | 575 |  |  | 591 |  |  | 639 |  |  | 588 |  |  | 577 |  |  | 668 |  |  | 662 |  |  | 580 |  |  | 586 |  |  | 560 |  |  | 538 |  |  | 604 |  |  | 586 |  |  | 598 |  |  | 605 |  |  | 615 |  |  | 618 |  |  | 671 |  |  | 655 |  |  | 606 |  |  | 550 |  |  | 629 |  |  | 607 |  |  | 594 |  |  | 589 |  |  | 572 |  |  | 616 |  |  | 581 |  |  | 615 |  |  | 621 |  |  | 568 |  |  | 562 |  |  | 609 |  |  | 621 |  |  | 620 |  |  | 606 |  |  | 596 |  |  | 598 |  |  | 578 |  |  | 656 |  |  | 614 |  |  | 606 |  |  | 621 |  |  | 596 |  |  | 613 |  |  | 649 |  |  | 640 |  |  | 613 |  |  | 629 |  |  | 585 |  |  | 612 |  |  | 646 |  |  | 629 |  |  | 607 |  |  | 604 |  |  | 625 |  |  | 572 |  |  | 669 |  |  | 585 |  |  | 616 |  |  | 560 |  |  | 558 |  |  | 613 |  |  | 546 |  |  | 596 |  |  | 645 |  |  | 522 |  |  | 631 |  |  | 591 |  |  | 630 |  |  | 637 |  |  | 602 |  |  | 587 |  |  | 558 |  |  | 601 |  |  | 631 |  |  | 630 |  |  | 643 |  |  | 601 |  |  | 645 |  |  | 578 |  |  | 632 |  |  | 632 |  |  | 611 |  |  | 621 |  |  | 668 |  |  | 622 |  |  | 630 |  |  | 543 |  |  | 576 |  |  | 581 |  |  | 582 |  |  | 607 |  |  | 624 |  |  | 614 |  |  | 586 |  |  | 604 |  |  | 591 |  |  | 595 |  |  | 624 |  |  | 631 |  |  | 598 |  |  | 547 |  |  | 578 |  |  | 589 |  |  | 589 |  |  | 550 |  |  | 612 |  |  | 596 |  |  | 625 |  |  | 595 |  |  | 623 |  |  | 628 |  |  | 593 |  |  | 589 |  |  | 595 |  |  | 545 |  |  | 615 |  |  | 587 |  |  | 597 |  |  | 620 |  |  | 588 |  |  | 577 |  |  | 534 |  |  | 551 |  |  | 576 |  |  | 621 |  |  | 607 |  |  | 547 |  |  | 599 |  |  | 653 |  |  | 640 |  |  | 654 |  |  | 596 |  |  | 529 |  |  | 616 |  |  | 584 |  |  | 680 |  |  | 576 |  |  | 560 |  |  | 632 |  |  | 647 |  |  | 571 |  |  | 620 |  |  | 593 |  |  | 550 |  |  | 631 |  |  | 617 |  |  | 585 |  |  | 614 |  |  | 681 |  |  | 646 |  |  | 596 |  |  | 568 |  |  | 575 |  |  | 583 |  |  | 587 |  |  | 569 |  |  | 543 |  |  | 586 |  |  | 622 |  |  | 618 |  |  | 538 |  |  | 539 |  |  | 611 |  |  | 684 |  |  | 633 |  |  | 602 |  |  | 585 |  |  | 649 |  |  | 592 |  |  | 663 |  |  | 591 |  |  | 575 |  |  | 617 |  |  | 661 |  |  | 613 |  |  | 621 |  |  | 594 |  |  | 603 |  |  | 573 |  |  | 609 |  |  | 577 |  |  | 537 |  |  | 583 |  |  | 573 |  |  | 630 |  |  | 590 |  |  | 587 |  |  | 571 |  |  | 554 |  |  | 605 |  |  | 593 |  |  | 601 |  |  | 615 |  |  | 625 |  |  | 608 |  |  | 599 |  |  | 574 |  |  | 653 |  |  | 602 |  |  | 660 |  |  | 579 |  |  | 557 |  |  | 713 |  |  | 568 |  |  | 636 |  |  | 625 |  |  | 580 |  |  | 630 |  |  | 599 |  |  | 611 |  |  | 665 |  |  | 568 |  |  | 573 |  |  | 588 |  |  | 591 |  |  | 608 |  |  | 621 |  |  | 604 |  |  | 574 |  |  | 651 |  |  | 595 |  |  | 592 |  |  | 608 |  |  | 629 |  |  | 608 |  |  | 619 |  |  | 569 |  |  | 613 |  |  | 566 |  |  | 558 |  |  | 581 |  |  | 565 |  |  | 623 |  |  | 518 |  |  | 593 |  |  | 626 |  |  | 601 |  |  | 606 |  |  | 600 |  |  | 568 |  |  | 645 |  |  | 685 |  |  | 542 |  |  | 648 |  |  | 652 |  |  | 640 |  |  | 561 |  |  | 634 |  |  | 598 |  |  | 609 |  |  | 560 |  |  | 649 |  |  | 538 |  |  | 587 |  |  | 590 |  |  | 586 |  |  | 650 |  |  | 645 |  |  | 645 |  |  | 633 |  |  | 639 |  |  | 593 |  |  | 623 |  |  | 552 |  |  | 615 |  |  | 598 |  |  | 617 |  |  | 543 |  |  | 595 |  |  | 582 |  |  | 627 |  |  | 592 |  |  | 569 |  |  | 606 |  |  | 657 |  |  | 603 |  |  | 603 |  |  | 659 |  |  | 639 |  |  | 543 |  |  | 632 |  |  | 580 |  |  | 657 |  |  | 574 |  |  | 615 |  |  | 557 |  |  | 641 |  |  | 624 |  |  | 553 |  |  | 547 |  |  | 559 |  |  | 613 |  |  | 584 |  |  | 687 |  |  | 556 |  |  | 556 |  |  | 577 |  |  | 558 |  |  | 561 |  |  | 645 |  |  | 589 |  |  | 639 |  |  | 652 |  |  | 541 |  |  | 553 |  |  | 626 |  |  | 610 |  |  | 583 |  |  | 622 |  |  | 581 |  |  | 621 |  |  | 629 |  |  | 643 |  |  | 608 |  |  | 536 |  |  | 595 |  |  | 520 |  |  | 658 |  |  | 570 |  |  | 587 |  |  | 610 |  |  | 600 |  |  | 626 |  |  | 626 |  |  | 589 |  |  | 663 |  |  | 669 |  |  | 565 |  |  | 625 |  |  | 624 |  |  | 580 |  |  | 593 |  |  | 588 |  |  | 629 |  |  | 639 |  |  | 587 |  |  | 607 |  |  | 539 |  |  | 591 |  |  | 666 |  |  | 526 |  |  | 583 |  |  | 616 |  |  | 589 |  |  | 536 |  |  | 537 |  |  | 631 |  |  | 602 |  |  | 615 |  |  | 640 |  |  | 642 |  |  | 628 |  |  | 572 |  |  | 637 |  |  | 598 |  |  | 597 |  |  | 600 |  |  | 622 |  |  | 598 |  |  | 609 |  |  | 609 |  |  | 603 |  |  | 585 |  |  | 673 |  |  | 543 |  |  | 593 |  |  | 602 |  |  | 613 |  |  | 569 |  |  | 568 |  |  | 604 |  |  | 603 |  |  | 632 |  |  | 628 |  |  | 639 |  |  | 637 |  |  | 615 |  |  | 484 |  |  | 621 |  |  | 568 |  |  | 640 |  |  | 557 |  |  | 575 |  |  | 654 |  |  | 526 |  |  | 596 |  |  | 588 |  |  | 529 |  |  | 637 |  |  | 616 |  |  | 673 |  |  | 698 |  |  | 542 |  |  | 621 |  |  | 591 |  |  | 565 |  |  | 606 |  |  | 533 |  |  | 625 |  |  | 638 |  |  | 558 |  |  | 570 |  |  | 619 |  |  | 601 |  |  | 578 |  |  | 628 |  |  | 671 |  |  | 608 |  |  | 624 |  |  | 600 |  |  | 684 |  |  | 591 |  |  | 565 |  |  | 615 |  |  | 610 |  |  | 615 |  |  | 576 |  |  | 644 |  |  | 546 |  |  | 577 |  |  | 621 |  |  | 550 |  |  | 640 |  |  | 597 |  |  | 624 |  |  | 616 |  |  | 560 |  |  | 598 |  |  | 564 |  |  | 571 |  |  | 592 |  |  | 602 |  |  | 615 |  |  | 562 |  |  | 608 |  |  | 647 |  |  | 654 |  |  | 611 |  |  | 637 |  |  | 600 |  |  | 622 |  |  | 569 |  |  | 576 |  |  | 594 |  |  | 600 |  |  | 557 |  |  | 587 |  |  | 595 |  |  | 560 |  |  | 614 |  |  | 609 |  |  | 601 |  |  | 585 |  |  | 628 |  |  | 624 |  |  | 635 |  |  | 643 |  |  | 564 |  |  | 615 |  |  | 545 |  |  | 623 |  |  | 602 |  |  | 652 |  |  | 577 |  |  | 611 |  |  | 605 |  |  | 549 |  |  | 567 |  |  | 586 |  |  | 585 |  |  | 572 |  |  | 601 |  |  | 610 |  |  | 528 |  |  | 572 |  |  | 548 |  |  | 595 |  |  | 598 |  |  | 565 |  |  | 589 |  |  | 551 |  |  | 610 |  |  | 616 |  |  | 638 |  |  | 556 |  |  | 614 |  |  | 656 |  |  | 643 |  |  | 610 |  |  | 624 |  |  | 610 |  |  | 608 |  |  | 561 |  |  | 644 |  |  | 581 |  |  | 609 |  |  | 577 |  |  | 670 |  |  | 614 |  |  | 682 |  |  | 513 |  |  | 626 |  |  | 495 |  |  | 649 |  |  | 625 |  |  | 623 |  |  | 646 |  |  | 610 |  |  | 601 |  |  | 604 |  |  | 628 |  |  | 537 |  |  | 608 |  |  | 650 |  |  | 647 |  |  | 597 |  |  | 557 |  |  | 639 |  |  | 540 |  |  | 557 |  |  | 561 |  |  | 609 |  |  | 563 |  |  | 615 |  |  | 640 |  |  | 549 |  |  | 608 |  |  | 592 |  |  | 599 |  |  | 608 |  |  | 538 |  |  | 577 |  |  | 574 |  |  | 629 |  |  | 679 |  |  | 602 |  |  | 622 |  |  | 640 |  |  | 625 |  |  | 583 |  |  | 529 |  |  | 641 |  |  | 619 |  |  | 567 |  |  | 575 |  |  | 586 |  |  | 607 |  |  | 558 |  |  | 579 |  |  | 576 |  |  | 582 |  |  | 627 |  |  | 621 |  |  | 610 |  |  | 645 |  |  | 632 |  |  | 585 |  |  | 610 |  |  | 634 |  |  | 589 |  |  | 679 |  |  | 645 |  |  | 656 |  |  | 592 |  |  | 649 |  |  | 586 |  |  | 684 |  |  | 565 |  |  | 615 |  |  | 550 |  |  | 574 |  |  | 586 |  |  | 555 |  |  | 625 |  |  | 656 |  |  | 620 |  |  | 603 |  |  | 563 |  |  | 637 |  |  | 505 |  |  | 612 |  |  | 601 |  |  | 582 |  |  | 615 |  |  | 564 |  |  | 589 |  |  | 569 |  |  | 605 |  |  | 613 |  |  | 576 |  |  | 648 |  |  | 615 |  |  | 530 |  |  | 608 |  |  | 560 |  |  | 571 |  |  | 543 |  |  | 683 |  |  | 622 |  |  | 699 |  |  | 597 |  |  | 592 |  |  | 511 |  |  | 611 |  |  | 566 |  |  | 614 |  |  | 635 |  |  | 610 |  |  | 551 |  |  | 563 |  |  | 622 |  |  | 585 |  |  | 606 |  |  | 655 |  |  | 592 |  |  | 524 |  |  | 597 |  |  | 573 |  |  | 577 |  |  | 584 |  |  | 568 |  |  | 607 |  |  | 569 |  |  | 632 |  |  | 601 |  |  | 569 |  |  | 597 |  |  | 591 |  |  | 564 |  |  | 629 |  |  | 564 |  |  | 528 |  |  | 680 |  |  | 674 |  |  | 584 |  |  | 623 |  |  | 584 |  |  | 542 |  |  | 560 |  |  | 557 |  |  | 600 |  |  | 615 |  |  | 603 |  |  | 653 |  |  | 611 |  |  | 613 |  |  | 611 |  |  | 507 |  |  | 610 |  |  | 563 |  |  | 595 |  |  | 617 |  |  | 561 |  |  | 578 |  |  | 644 |  |  | 618 |  |  | 599 |  |  | 624 |  |  | 637 |  |  | 588 |  |  | 577 |  |  | 575 |  |  | 580 |  |  | 639 |  |  | 675 |  |  | 588 |  |  | 631 |  |  | 592 |  |  | 594 |  |  | 609 |  |  | 637 |  |  | 604 |  |  | 640 |  |  | 637 |  |  | 653 |  |  | 576 |  |  | 561 |  |  | 603 |  |  | 517 |  |  | 633 |  |  | 574 |  |  | 563 |  |  | 634 |  |  | 564 |  |  | 606 |  |  | 590 |  |  | 595 |  |  | 532 |  |  | 612 |  |  | 603 |  |  | 579 |  |  | 611 |  |  | 653 |  |  | 593 |  |  | 600 |  |  | 595 |  |  | 630 |  |  | 557 |  |  | 545 |  |  | 627 |  |  | 679 |  |  | 586 |  |  | 683 |  |  | 625 |  |  | 615 |  |  | 638 |  |  | 628 |  |  | 646 |  |  | 643 |  |  | 605 |  |  | 626 |  |  | 611 |  |  | 611 |  |  | 522 |  |  | 601 |  |  | 598 |  |  | 630 |  |  | 603 |  |  | 598 |  |  | 670 |  |  | 595 |  |  | 547 |  |  | 568 |  |  | 656 |  |  | 645 |  |  | 591 |  |  | 629 |  |  | 592 |  |  | 558 |  |  | 632 |  |  | 602 |  |  | 634 |  |  | 558 |  |  | 642 |  |  | 615 |  |  | 591 |  |  | 606 |  |  | 608 |  |  | 599 |  |  | 574 |  |  | 520 |  |  | 634 |  |  | 637 |  |  | 591 |  |  | 626 |  |  | 514 |  |  | 611 |  |  | 585 |  |  | 617 |  |  | 631 |  |  | 548 |  |  | 587 |  |  | 563 |  |  | 605 |  |  | 568 |  |  | 587 |  |  | 613 |  |  | 608 |  |  | 600 |  |  | 575 |  |  | 592 |  |  | 617 |  |  | 632 |  |  | 557 |  |  | 664 |  |  | 564 |  |  | 574 |  |  | 679 |  |  | 574 |  |  | 534 |  |  | 568 |  |  | 634 |  |  | 591 |  |  | 612 |  |  | 583 |  |  | 593 |  |  | 600 |  |  | 614 |  |  | 604 |  |  | 602 |  |  | 585 |  |  | 616 |  |  | 588 |  |  | 597 |  |  | 629 |  |  | 639 |  |  | 632 |  |  | 594 |  |  | 697 |  |  | 623 |  |  | 661 |  |  | 603 |  |  | 653 |  |  | 574 |  |  | 557 |  |  | 582 |  |  | 612 |  |  | 566 |  |  | 569 |  |  | 576 |  |  | 646 |  |  | 562 |  |  | 603 |  |  | 592 |  |  | 601 |  |  | 596 |  |  | 601 |  |  | 643 |  |  | 577 |  |  | 557 |  |  | 602 |  |  | 531 |  |  | 643 |  |  | 666 |  |  | 548 |  |  | 680 |  |  | 586 |  |  | 605 |  |  | 627 |  |  | 609 |  |  | 618 |  |  | 562 |  |  | 593 |  |  | 589 |  |  | 623 |  |  | 701 |  |  | 609 |  |  | 690 |  |  | 558 |  |  | 619 |  |  | 584 |  |  | 581 |  |  | 602 |  |  | 615 |  |  | 626 |  |  | 624 |  |  | 552 |  |  | 587 |  |  | 569 |  |  | 590 |  |  | 586 |  |  | 607 |  |  | 622 |  |  | 646 |  |  | 585 |  |  | 621 |  |  | 632 |  |  | 611 |  |  | 578 |  |  | 601 |  |  | 609 |  |  | 628 |  |  | 612 |  |  | 581 |  |  | 602 |  |  | 520 |  |  | 537 |  |  | 568 |  |  | 650 |  |  | 549 |  |  | 544 |  |  | 643 |  |  | 644 |  |  | 625 |  |  | 569 |  |  | 596 |  |  | 575 |  |  | 624 |  |  | 535 |  |  | 608 |  |  | 614 |  |  | 668 |  |  | 623 |  |  | 560 |  |  | 635 |  |  | 606 |  |  | 602 |  |  | 588 |  |  | 670 |  |  | 663 |  |  | 640 |  |  | 679 |  |  | 644 |  |  | 614 |  |  | 621 |  |  | 652 |  |  | 618 |  |  | 626 |  |  | 658 |  |  | 589 |  |  | 548 |  |  | 620 |  |  | 563 |  |  | 594 |  |  | 535 |  |  | 600 |  |  | 550 |  |  | 640 |  |  | 668 |  |  | 581 |  |  | 644 |  |  | 633 |  |  | 593 |  |  | 582 |  |  | 572 |  |  | 616 |  |  | 585 |  |  | 593 |  |  | 581 |  |  | 663 |  |  | 598 |  |  | 619 |  |  | 577 |  |  | 621 |  |  | 584 |  |  | 642 |  |  | 591 |  |  | 591 |  |  | 591 |  |  | 577 |  |  | 518 |  |  | 585 |  |  | 518 |  |  | 611 |  |  | 653 |  |  | 575 |  |  | 660 |  |  | 604 |  |  | 601 |  |  | 667
21 |  | 658 |  |  | 707 |  |  | 680 |  |  | 602 |  |  | 697 |  |  | 627 |  |  | 681 |  |  | 626 |  |  | 656 |  |  | 664 |  |  | 640 |  |  | 676 |  |  | 688 |  |  | 610 |  |  | 593 |  |  | 652 |  |  | 642 |  |  | 660 |  |  | 713 |  |  | 554 |  |  | 629 |  |  | 599 |  |  | 628 |  |  | 624 |  |  | 595 |  |  | 648 |  |  | 592 |  |  | 643 |  |  | 615 |  |  | 565 |  |  | 636 |  |  | 631 |  |  | 573 |  |  | 615 |  |  | 520 |  |  | 616 |  |  | 644 |  |  | 606 |  |  | 632 |  |  | 665 |  |  | 622 |  |  | 644 |  |  | 633 |  |  | 607 |  |  | 663 |  |  | 685 |  |  | 605 |  |  | 662 |  |  | 587 |  |  | 606 |  |  | 603 |  |  | 627 |  |  | 626 |  |  | 614 |  |  | 644 |  |  | 614 |  |  | 583 |  |  | 655 |  |  | 659 |  |  | 623 |  |  | 619 |  |  | 591 |  |  | 656 |  |  | 605 |  |  | 599 |  |  | 596 |  |  | 632 |  |  | 591 |  |  | 596 |  |  | 630 |  |  | 678 |  |  | 635 |  |  | 603 |  |  | 694 |  |  | 686 |  |  | 606 |  |  | 615 |  |  | 581 |  |  | 553 |  |  | 628 |  |  | 625 |  |  | 613 |  |  | 629 |  |  | 662 |  |  | 657 |  |  | 686 |  |  | 694 |  |  | 627 |  |  | 571 |  |  | 668 |  |  | 636 |  |  | 623 |  |  | 636 |  |  | 593 |  |  | 637 |  |  | 602 |  |  | 662 |  |  | 642 |  |  | 594 |  |  | 577 |  |  | 635 |  |  | 650 |  |  | 659 |  |  | 653 |  |  | 620 |  |  | 637 |  |  | 617 |  |  | 703 |  |  | 635 |  |  | 630 |  |  | 650 |  |  | 625 |  |  | 660 |  |  | 670 |  |  | 679 |  |  | 639 |  |  | 658 |  |  | 606 |  |  | 651 |  |  | 685 |  |  | 644 |  |  | 646 |  |  | 643 |  |  | 649 |  |  | 601 |  |  | 716 |  |  | 632 |  |  | 655 |  |  | 584 |  |  | 587 |  |  | 652 |  |  | 585 |  |  | 620 |  |  | 692 |  |  | 561 |  |  | 655 |  |  | 606 |  |  | 651 |  |  | 666 |  |  | 626 |  |  | 602 |  |  | 587 |  |  | 640 |  |  | 657 |  |  | 656 |  |  | 669 |  |  | 616 |  |  | 684 |  |  | 617 |  |  | 658 |  |  | 671 |  |  | 637 |  |  | 650 |  |  | 707 |  |  | 669 |  |  | 654 |  |  | 567 |  |  | 602 |  |  | 628 |  |  | 606 |  |  | 646 |  |  | 645 |  |  | 629 |  |  | 625 |  |  | 630 |  |  | 606 |  |  | 610 |  |  | 648 |  |  | 670 |  |  | 613 |  |  | 594 |  |  | 604 |  |  | 618 |  |  | 628 |  |  | 576 |  |  | 638 |  |  | 643 |  |  | 651 |  |  | 616 |  |  | 662 |  |  | 649 |  |  | 640 |  |  | 628 |  |  | 616 |  |  | 584 |  |  | 654 |  |  | 634 |  |  | 636 |  |  | 646 |  |  | 617 |  |  | 616 |  |  | 555 |  |  | 580 |  |  | 623 |  |  | 645 |  |  | 631 |  |  | 576 |  |  | 625 |  |  | 692 |  |  | 661 |  |  | 675 |  |  | 620 |  |  | 558 |  |  | 655 |  |  | 608 |  |  | 706 |  |  | 605 |  |  | 589 |  |  | 661 |  |  | 671 |  |  | 618 |  |  | 667 |  |  | 632 |  |  | 589 |  |  | 652 |  |  | 632 |  |  | 609 |  |  | 635 |  |  | 720 |  |  | 675 |  |  | 620 |  |  | 592 |  |  | 599 |  |  | 607 |  |  | 602 |  |  | 593 |  |  | 558 |  |  | 625 |  |  | 661 |  |  | 644 |  |  | 564 |  |  | 565 |  |  | 635 |  |  | 705 |  |  | 680 |  |  | 631 |  |  | 614 |  |  | 675 |  |  | 613 |  |  | 687 |  |  | 606 |  |  | 614 |  |  | 656 |  |  | 690 |  |  | 660 |  |  | 660 |  |  | 633 |  |  | 629 |  |  | 599 |  |  | 624 |  |  | 598 |  |  | 566 |  |  | 630 |  |  | 588 |  |  | 669 |  |  | 637 |  |  | 611 |  |  | 597 |  |  | 569 |  |  | 631 |  |  | 617 |  |  | 640 |  |  | 662 |  |  | 654 |  |  | 655 |  |  | 646 |  |  | 603 |  |  | 674 |  |  | 617 |  |  | 707 |  |  | 608 |  |  | 581 |  |  | 737 |  |  | 607 |  |  | 683 |  |  | 672 |  |  | 619 |  |  | 677 |  |  | 638 |  |  | 635 |  |  | 691 |  |  | 592 |  |  | 620 |  |  | 635 |  |  | 630 |  |  | 647 |  |  | 645 |  |  | 625 |  |  | 589 |  |  | 675 |  |  | 616 |  |  | 631 |  |  | 634 |  |  | 655 |  |  | 623 |  |  | 658 |  |  | 608 |  |  | 660 |  |  | 590 |  |  | 582 |  |  | 607 |  |  | 580 |  |  | 662 |  |  | 565 |  |  | 608 |  |  | 655 |  |  | 622 |  |  | 621 |  |  | 621 |  |  | 583 |  |  | 660 |  |  | 709 |  |  | 557 |  |  | 663 |  |  | 678 |  |  | 666 |  |  | 608 |  |  | 655 |  |  | 622 |  |  | 624 |  |  | 586 |  |  | 664 |  |  | 577 |  |  | 616 |  |  | 614 |  |  | 612 |  |  | 679 |  |  | 671 |  |  | 674 |  |  | 672 |  |  | 678 |  |  | 632 |  |  | 652 |  |  | 578 |  |  | 636 |  |  | 627 |  |  | 656 |  |  | 558 |  |  | 619 |  |  | 603 |  |  | 666 |  |  | 631 |  |  | 595 |  |  | 645 |  |  | 672 |  |  | 629 |  |  | 627 |  |  | 706 |  |  | 665 |  |  | 558 |  |  | 658 |  |  | 609 |  |  | 681 |  |  | 621 |  |  | 644 |  |  | 604 |  |  | 688 |  |  | 653 |  |  | 577 |  |  | 586 |  |  | 598 |  |  | 652 |  |  | 610 |  |  | 734 |  |  | 585 |  |  | 585 |  |  | 598 |  |  | 582 |  |  | 587 |  |  | 674 |  |  | 636 |  |  | 660 |  |  | 691 |  |  | 588 |  |  | 579 |  |  | 665 |  |  | 625 |  |  | 630 |  |  | 651 |  |  | 620 |  |  | 660 |  |  | 653 |  |  | 658 |  |  | 634 |  |  | 583 |  |  | 610 |  |  | 549 |  |  | 687 |  |  | 594 |  |  | 602 |  |  | 625 |  |  | 647 |  |  | 641 |  |  | 650 |  |  | 610 |  |  | 702 |  |  | 708 |  |  | 591 |  |  | 654 |  |  | 663 |  |  | 619 |  |  | 617 |  |  | 612 |  |  | 658 |  |  | 678 |  |  | 602 |  |  | 646 |  |  | 563 |  |  | 617 |  |  | 687 |  |  | 547 |  |  | 604 |  |  | 663 |  |  | 604 |  |  | 557 |  |  | 552 |  |  | 652 |  |  | 617 |  |  | 644 |  |  | 655 |  |  | 681 |  |  | 643 |  |  | 619 |  |  | 666 |  |  | 619 |  |  | 618 |  |  | 615 |  |  | 648 |  |  | 619 |  |  | 656 |  |  | 656 |  |  | 642 |  |  | 609 |  |  | 712 |  |  | 590 |  |  | 632 |  |  | 617 |  |  | 652 |  |  | 608 |  |  | 597 |  |  | 643 |  |  | 624 |  |  | 671 |  |  | 643 |  |  | 678 |  |  | 663 |  |  | 654 |  |  | 505 |  |  | 660 |  |  | 594 |  |  | 679 |  |  | 581 |  |  | 614 |  |  | 675 |  |  | 565 |  |  | 617 |  |  | 627 |  |  | 558 |  |  | 684 |  |  | 645 |  |  | 712 |  |  | 727 |  |  | 557 |  |  | 660 |  |  | 638 |  |  | 604 |  |  | 632 |  |  | 562 |  |  | 651 |  |  | 677 |  |  | 573 |  |  | 617 |  |  | 648 |  |  | 648 |  |  | 607 |  |  | 667 |  |  | 697 |  |  | 629 |  |  | 663 |  |  | 626 |  |  | 708 |  |  | 612 |  |  | 604 |  |  | 630 |  |  | 631 |  |  | 654 |  |  | 591 |  |  | 683 |  |  | 585 |  |  | 598 |  |  | 645 |  |  | 579 |  |  | 679 |  |  | 626 |  |  | 671 |  |  | 645 |  |  | 599 |  |  | 637 |  |  | 585 |  |  | 586 |  |  | 621 |  |  | 628 |  |  | 644 |  |  | 588 |  |  | 623 |  |  | 686 |  |  | 683 |  |  | 632 |  |  | 684 |  |  | 621 |  |  | 637 |  |  | 598 |  |  | 591 |  |  | 623 |  |  | 615 |  |  | 572 |  |  | 626 |  |  | 634 |  |  | 599 |  |  | 635 |  |  | 648 |  |  | 640 |  |  | 624 |  |  | 667 |  |  | 663 |  |  | 682 |  |  | 682 |  |  | 579 |  |  | 641 |  |  | 574 |  |  | 647 |  |  | 628 |  |  | 667 |  |  | 624 |  |  | 632 |  |  | 631 |  |  | 588 |  |  | 606 |  |  | 612 |  |  | 624 |  |  | 619 |  |  | 648 |  |  | 634 |  |  | 575 |  |  | 611 |  |  | 587 |  |  | 634 |  |  | 622 |  |  | 604 |  |  | 615 |  |  | 575 |  |  | 636 |  |  | 663 |  |  | 662 |  |  | 595 |  |  | 653 |  |  | 703 |  |  | 664 |  |  | 649 |  |  | 653 |  |  | 636 |  |  | 647 |  |  | 585 |  |  | 691 |  |  | 610 |  |  | 624 |  |  | 624 |  |  | 685 |  |  | 653 |  |  | 703 |  |  | 552 |  |  | 641 |  |  | 510 |  |  | 688 |  |  | 646 |  |  | 649 |  |  | 693 |  |  | 634 |  |  | 625 |  |  | 630 |  |  | 675 |  |  | 558 |  |  | 629 |  |  | 671 |  |  | 671 |  |  | 612 |  |  | 596 |  |  | 686 |  |  | 579 |  |  | 578 |  |  | 608 |  |  | 633 |  |  | 578 |  |  | 636 |  |  | 687 |  |  | 588 |  |  | 629 |  |  | 613 |  |  | 625 |  |  | 637 |  |  | 562 |  |  | 616 |  |  | 613 |  |  | 644 |  |  | 718 |  |  | 617 |  |  | 646 |  |  | 666 |  |  | 651 |  |  | 630 |  |  | 558 |  |  | 688 |  |  | 640 |  |  | 582 |  |  | 601 |  |  | 607 |  |  | 631 |  |  | 579 |  |  | 618 |  |  | 605 |  |  | 611 |  |  | 651 |  |  | 668 |  |  | 649 |  |  | 666 |  |  | 661 |  |  | 632 |  |  | 634 |  |  | 673 |  |  | 610 |  |  | 705 |  |  | 692 |  |  | 682 |  |  | 618 |  |  | 688 |  |  | 601 |  |  | 710 |  |  | 580 |  |  | 630 |  |  | 574 |  |  | 613 |  |  | 607 |  |  | 594 |  |  | 664 |  |  | 682 |  |  | 641 |  |  | 632 |  |  | 587 |  |  | 658 |  |  | 520 |  |  | 641 |  |  | 630 |  |  | 606 |  |  | 639 |  |  | 611 |  |  | 628 |  |  | 598 |  |  | 634 |  |  | 639 |  |  | 615 |  |  | 674 |  |  | 654 |  |  | 545 |  |  | 655 |  |  | 575 |  |  | 592 |  |  | 582 |  |  | 722 |  |  | 661 |  |  | 725 |  |  | 612 |  |  | 639 |  |  | 540 |  |  | 658 |  |  | 587 |  |  | 640 |  |  | 661 |  |  | 639 |  |  | 572 |  |  | 584 |  |  | 651 |  |  | 600 |  |  | 645 |  |  | 684 |  |  | 616 |  |  | 548 |  |  | 636 |  |  | 594 |  |  | 624 |  |  | 631 |  |  | 607 |  |  | 646 |  |  | 584 |  |  | 647 |  |  | 630 |  |  | 590 |  |  | 612 |  |  | 612 |  |  | 579 |  |  | 658 |  |  | 588 |  |  | 557 |  |  | 709 |  |  | 713 |  |  | 613 |  |  | 649 |  |  | 623 |  |  | 566 |  |  | 607 |  |  | 578 |  |  | 639 |  |  | 654 |  |  | 650 |  |  | 692 |  |  | 626 |  |  | 652 |  |  | 650 |  |  | 533 |  |  | 639 |  |  | 592 |  |  | 634 |  |  | 656 |  |  | 608 |  |  | 604 |  |  | 668 |  |  | 642 |  |  | 614 |  |  | 645 |  |  | 684 |  |  | 617 |  |  | 606 |  |  | 601 |  |  | 609 |  |  | 660 |  |  | 714 |  |  | 627 |  |  | 657 |  |  | 616 |  |  | 618 |  |  | 624 |  |  | 666 |  |  | 625 |  |  | 655 |  |  | 666 |  |  | 668 |  |  | 623 |  |  | 600 |  |  | 624 |  |  | 538 |  |  | 654 |  |  | 600 |  |  | 602 |  |  | 673 |  |  | 593 |  |  | 653 |  |  | 637 |  |  | 634 |  |  | 579 |  |  | 636 |  |  | 627 |  |  | 618 |  |  | 626 |  |  | 679 |  |  | 608 |  |  | 626 |  |  | 634 |  |  | 669 |  |  | 581 |  |  | 574 |  |  | 666 |  |  | 718 |  |  | 633 |  |  | 722 |  |  | 664 |  |  | 644 |  |  | 659 |  |  | 675 |  |  | 685 |  |  | 669 |  |  | 652 |  |  | 665 |  |  | 650 |  |  | 626 |  |  | 537 |  |  | 630 |  |  | 613 |  |  | 669 |  |  | 650 |  |  | 619 |  |  | 685 |  |  | 634 |  |  | 571 |  |  | 597 |  |  | 680 |  |  | 684 |  |  | 630 |  |  | 668 |  |  | 607 |  |  | 579 |  |  | 679 |  |  | 641 |  |  | 663 |  |  | 587 |  |  | 668 |  |  | 639 |  |  | 615 |  |  | 632 |  |  | 629 |  |  | 614 |  |  | 589 |  |  | 541 |  |  | 673 |  |  | 663 |  |  | 617 |  |  | 655 |  |  | 553 |  |  | 650 |  |  | 624 |  |  | 664 |  |  | 652 |  |  | 577 |  |  | 611 |  |  | 602 |  |  | 631 |  |  | 592 |  |  | 613 |  |  | 652 |  |  | 634 |  |  | 621 |  |  | 601 |  |  | 613 |  |  | 638 |  |  | 671 |  |  | 596 |  |  | 711 |  |  | 585 |  |  | 600 |  |  | 694 |  |  | 598 |  |  | 560 |  |  | 589 |  |  | 655 |  |  | 638 |  |  | 651 |  |  | 630 |  |  | 619 |  |  | 639 |  |  | 643 |  |  | 633 |  |  | 628 |  |  | 611 |  |  | 655 |  |  | 635 |  |  | 612 |  |  | 668 |  |  | 678 |  |  | 656 |  |  | 615 |  |  | 744 |  |  | 638 |  |  | 676 |  |  | 632 |  |  | 677 |  |  | 613 |  |  | 596 |  |  | 597 |  |  | 633 |  |  | 587 |  |  | 616 |  |  | 591 |  |  | 661 |  |  | 601 |  |  | 618 |  |  | 631 |  |  | 616 |  |  | 622 |  |  | 627 |  |  | 658 |  |  | 598 |  |  | 572 |  |  | 649 |  |  | 555 |  |  | 672 |  |  | 705 |  |  | 563 |  |  | 706 |  |  | 625 |  |  | 626 |  |  | 674 |  |  | 648 |  |  | 633 |  |  | 591 |  |  | 632 |  |  | 636 |  |  | 649 |  |  | 716 |  |  | 648 |  |  | 714 |  |  | 582 |  |  | 640 |  |  | 623 |  |  | 610 |  |  | 641 |  |  | 630 |  |  | 655 |  |  | 653 |  |  | 591 |  |  | 616 |  |  | 608 |  |  | 616 |  |  | 625 |  |  | 646 |  |  | 637 |  |  | 670 |  |  | 624 |  |  | 660 |  |  | 679 |  |  | 650 |  |  | 617 |  |  | 630 |  |  | 624 |  |  | 657 |  |  | 641 |  |  | 607 |  |  | 631 |  |  | 541 |  |  | 566 |  |  | 583 |  |  | 697 |  |  | 575 |  |  | 583 |  |  | 682 |  |  | 665 |  |  | 640 |  |  | 608 |  |  | 622 |  |  | 614 |  |  | 663 |  |  | 574 |  |  | 623 |  |  | 653 |  |  | 689 |  |  | 652 |  |  | 589 |  |  | 656 |  |  | 645 |  |  | 649 |  |  | 609 |  |  | 717 |  |  | 687 |  |  | 666 |  |  | 703 |  |  | 665 |  |  | 635 |  |  | 660 |  |  | 681 |  |  | 644 |  |  | 665 |  |  | 684 |  |  | 610 |  |  | 563 |  |  | 659 |  |  | 589 |  |  | 618 |  |  | 564 |  |  | 624 |  |  | 579 |  |  | 666 |  |  | 707 |  |  | 596 |  |  | 665 |  |  | 648 |  |  | 619 |  |  | 606 |  |  | 611 |  |  | 631 |  |  | 632 |  |  | 617 |  |  | 602 |  |  | 702 |  |  | 622 |  |  | 645 |  |  | 598 |  |  | 647 |  |  | 623 |  |  | 671 |  |  | 615 |  |  | 630 |  |  | 606 |  |  | 592 |  |  | 547 |  |  | 624 |  |  | 547 |  |  | 640 |  |  | 682 |  |  | 614 |  |  | 699 |  |  | 630 |  |  | 640 |  |  | 706
22 |  | 672.5 |  |  | 730.5 |  |  | 692 |  |  | 621.5 |  |  | 716.5 |  |  | 650.5 |  |  | 704.5 |  |  | 649.5 |  |  | 666.5 |  |  | 671.5 |  |  | 652 |  |  | 686.5 |  |  | 702.5 |  |  | 629.5 |  |  | 606 |  |  | 675.5 |  |  | 661.5 |  |  | 679.5 |  |  | 732.5 |  |  | 568.5 |  |  | 648.5 |  |  | 606.5 |  |  | 638.5 |  |  | 643.5 |  |  | 607 |  |  | 671.5 |  |  | 611.5 |  |  | 662.5 |  |  | 638.5 |  |  | 577 |  |  | 648 |  |  | 654.5 |  |  | 587.5 |  |  | 625.5 |  |  | 539.5 |  |  | 629 |  |  | 654.5 |  |  | 618 |  |  | 639.5 |  |  | 688.5 |  |  | 636.5 |  |  | 663.5 |  |  | 652.5 |  |  | 619 |  |  | 686.5 |  |  | 697 |  |  | 628.5 |  |  | 672.5 |  |  | 606.5 |  |  | 616.5 |  |  | 622.5 |  |  | 650.5 |  |  | 645.5 |  |  | 637.5 |  |  | 651.5 |  |  | 628.5 |  |  | 606.5 |  |  | 668 |  |  | 678.5 |  |  | 630.5 |  |  | 631 |  |  | 598.5 |  |  | 675.5 |  |  | 624.5 |  |  | 609.5 |  |  | 608 |  |  | 651.5 |  |  | 603 |  |  | 610.5 |  |  | 637.5 |  |  | 690 |  |  | 654.5 |  |  | 622.5 |  |  | 708.5 |  |  | 698 |  |  | 619 |  |  | 634.5 |  |  | 591.5 |  |  | 572.5 |  |  | 647.5 |  |  | 637 |  |  | 627.5 |  |  | 648.5 |  |  | 681.5 |  |  | 676.5 |  |  | 700.5 |  |  | 708.5 |  |  | 637.5 |  |  | 581.5 |  |  | 691.5 |  |  | 643.5 |  |  | 636 |  |  | 655.5 |  |  | 605 |  |  | 650 |  |  | 614 |  |  | 681.5 |  |  | 649.5 |  |  | 617.5 |  |  | 596.5 |  |  | 649.5 |  |  | 663 |  |  | 671 |  |  | 676.5 |  |  | 643.5 |  |  | 644.5 |  |  | 640.5 |  |  | 710.5 |  |  | 658.5 |  |  | 649.5 |  |  | 664.5 |  |  | 648.5 |  |  | 679.5 |  |  | 680.5 |  |  | 693.5 |  |  | 649.5 |  |  | 668.5 |  |  | 629.5 |  |  | 670.5 |  |  | 708.5 |  |  | 651.5 |  |  | 653.5 |  |  | 657.5 |  |  | 656.5 |  |  | 620.5 |  |  | 728 |  |  | 651.5 |  |  | 665.5 |  |  | 598.5 |  |  | 610.5 |  |  | 671.5 |  |  | 597 |  |  | 634.5 |  |  | 699.5 |  |  | 580.5 |  |  | 674.5 |  |  | 619 |  |  | 658.5 |  |  | 685.5 |  |  | 638 |  |  | 612.5 |  |  | 599 |  |  | 653 |  |  | 676.5 |  |  | 668 |  |  | 676.5 |  |  | 635.5 |  |  | 707.5 |  |  | 624.5 |  |  | 677.5 |  |  | 690.5 |  |  | 644.5 |  |  | 657.5 |  |  | 726.5 |  |  | 679.5 |  |  | 666 |  |  | 590.5 |  |  | 615 |  |  | 647.5 |  |  | 629.5 |  |  | 659 |  |  | 655.5 |  |  | 652.5 |  |  | 635.5 |  |  | 643 |  |  | 625.5 |  |  | 624.5 |  |  | 658.5 |  |  | 677.5 |  |  | 627.5 |  |  | 604.5 |  |  | 617 |  |  | 625.5 |  |  | 638.5 |  |  | 595.5 |  |  | 652.5 |  |  | 653.5 |  |  | 665.5 |  |  | 639.5 |  |  | 674 |  |  | 672.5 |  |  | 647.5 |  |  | 638.5 |  |  | 630.5 |  |  | 598.5 |  |  | 673.5 |  |  | 657.5 |  |  | 659.5 |  |  | 660.5 |  |  | 624.5 |  |  | 635.5 |  |  | 565.5 |  |  | 594.5 |  |  | 636 |  |  | 668.5 |  |  | 650.5 |  |  | 599.5 |  |  | 644.5 |  |  | 711.5 |  |  | 680.5 |  |  | 685.5 |  |  | 639.5 |  |  | 568.5 |  |  | 662.5 |  |  | 631.5 |  |  | 716.5 |  |  | 612.5 |  |  | 599.5 |  |  | 680.5 |  |  | 685.5 |  |  | 631 |  |  | 677.5 |  |  | 642.5 |  |  | 602 |  |  | 675.5 |  |  | 645 |  |  | 619.5 |  |  | 649.5 |  |  | 727.5 |  |  | 694.5 |  |  | 639.5 |  |  | 599.5 |  |  | 609.5 |  |  | 621.5 |  |  | 615 |  |  | 603.5 |  |  | 568.5 |  |  | 648.5 |  |  | 680.5 |  |  | 657 |  |  | 578.5 |  |  | 579.5 |  |  | 654.5 |  |  | 715.5 |  |  | 699.5 |  |  | 645.5 |  |  | 621.5 |  |  | 685.5 |  |  | 625 |  |  | 699 |  |  | 625.5 |  |  | 637.5 |  |  | 675.5 |  |  | 702 |  |  | 670.5 |  |  | 683.5 |  |  | 640.5 |  |  | 641 |  |  | 606.5 |  |  | 638.5 |  |  | 605.5 |  |  | 589.5 |  |  | 637.5 |  |  | 611.5 |  |  | 683.5 |  |  | 651.5 |  |  | 630.5 |  |  | 610 |  |  | 579.5 |  |  | 645.5 |  |  | 624.5 |  |  | 647.5 |  |  | 669.5 |  |  | 666 |  |  | 665.5 |  |  | 669.5 |  |  | 616 |  |  | 688.5 |  |  | 640.5 |  |  | 720 |  |  | 631.5 |  |  | 600.5 |  |  | 744.5 |  |  | 614.5 |  |  | 696 |  |  | 684 |  |  | 638.5 |  |  | 687.5 |  |  | 657.5 |  |  | 642.5 |  |  | 705.5 |  |  | 615.5 |  |  | 633 |  |  | 658.5 |  |  | 649.5 |  |  | 659 |  |  | 652.5 |  |  | 644.5 |  |  | 601 |  |  | 689.5 |  |  | 623.5 |  |  | 650.5 |  |  | 647 |  |  | 674.5 |  |  | 636 |  |  | 681.5 |  |  | 618.5 |  |  | 667.5 |  |  | 602 |  |  | 601.5 |  |  | 630.5 |  |  | 587.5 |  |  | 675 |  |  | 588.5 |  |  | 631.5 |  |  | 678.5 |  |  | 636.5 |  |  | 628.5 |  |  | 633 |  |  | 606.5 |  |  | 679.5 |  |  | 732.5 |  |  | 569 |  |  | 676 |  |  | 697.5 |  |  | 689.5 |  |  | 622.5 |  |  | 669.5 |  |  | 641.5 |  |  | 643.5 |  |  | 600.5 |  |  | 683.5 |  |  | 596.5 |  |  | 626.5 |  |  | 627 |  |  | 631.5 |  |  | 698.5 |  |  | 685.5 |  |  | 693.5 |  |  | 685 |  |  | 697.5 |  |  | 639.5 |  |  | 675.5 |  |  | 601.5 |  |  | 643.5 |  |  | 639 |  |  | 668 |  |  | 570 |  |  | 632 |  |  | 610.5 |  |  | 678 |  |  | 638.5 |  |  | 607 |  |  | 655.5 |  |  | 679.5 |  |  | 639.5 |  |  | 646.5 |  |  | 713.5 |  |  | 678 |  |  | 565.5 |  |  | 681.5 |  |  | 616.5 |  |  | 694 |  |  | 644.5 |  |  | 658.5 |  |  | 623.5 |  |  | 700 |  |  | 663.5 |  |  | 591.5 |  |  | 609.5 |  |  | 621.5 |  |  | 659.5 |  |  | 633.5 |  |  | 757.5 |  |  | 604.5 |  |  | 604.5 |  |  | 608.5 |  |  | 594 |  |  | 606.5 |  |  | 693.5 |  |  | 646.5 |  |  | 670.5 |  |  | 710.5 |  |  | 601 |  |  | 586.5 |  |  | 677 |  |  | 637 |  |  | 640.5 |  |  | 665.5 |  |  | 630.5 |  |  | 672 |  |  | 667.5 |  |  | 681.5 |  |  | 653.5 |  |  | 596 |  |  | 617.5 |  |  | 563.5 |  |  | 697.5 |  |  | 613.5 |  |  | 621.5 |  |  | 637 |  |  | 666.5 |  |  | 653 |  |  | 669.5 |  |  | 620.5 |  |  | 709.5 |  |  | 720 |  |  | 601.5 |  |  | 667 |  |  | 676 |  |  | 629.5 |  |  | 640.5 |  |  | 619.5 |  |  | 677.5 |  |  | 691 |  |  | 625.5 |  |  | 665.5 |  |  | 577.5 |  |  | 630 |  |  | 710.5 |  |  | 566.5 |  |  | 611.5 |  |  | 682.5 |  |  | 616 |  |  | 571.5 |  |  | 571.5 |  |  | 662.5 |  |  | 636.5 |  |  | 658.5 |  |  | 665.5 |  |  | 694 |  |  | 657.5 |  |  | 626.5 |  |  | 678 |  |  | 638.5 |  |  | 628.5 |  |  | 634.5 |  |  | 660 |  |  | 642.5 |  |  | 675.5 |  |  | 670.5 |  |  | 652.5 |  |  | 628.5 |  |  | 724 |  |  | 603 |  |  | 639.5 |  |  | 624.5 |  |  | 671.5 |  |  | 615.5 |  |  | 610 |  |  | 655 |  |  | 637 |  |  | 694.5 |  |  | 656 |  |  | 697.5 |  |  | 670.5 |  |  | 667 |  |  | 528.5 |  |  | 674.5 |  |  | 613.5 |  |  | 702.5 |  |  | 588.5 |  |  | 627 |  |  | 687 |  |  | 584.5 |  |  | 631.5 |  |  | 640 |  |  | 572.5 |  |  | 703.5 |  |  | 658 |  |  | 731.5 |  |  | 741.5 |  |  | 569 |  |  | 683.5 |  |  | 661.5 |  |  | 616 |  |  | 655.5 |  |  | 574 |  |  | 670.5 |  |  | 689 |  |  | 587.5 |  |  | 636.5 |  |  | 655.5 |  |  | 671.5 |  |  | 630.5 |  |  | 681.5 |  |  | 710 |  |  | 643.5 |  |  | 670.5 |  |  | 633.5 |  |  | 722.5 |  |  | 631.5 |  |  | 617 |  |  | 640.5 |  |  | 643 |  |  | 664.5 |  |  | 610.5 |  |  | 690.5 |  |  | 599.5 |  |  | 608.5 |  |  | 659.5 |  |  | 589.5 |  |  | 698.5 |  |  | 636.5 |  |  | 684 |  |  | 664.5 |  |  | 612 |  |  | 649 |  |  | 592.5 |  |  | 599 |  |  | 631.5 |  |  | 635.5 |  |  | 663.5 |  |  | 602.5 |  |  | 642.5 |  |  | 696.5 |  |  | 690.5 |  |  | 645 |  |  | 697 |  |  | 628.5 |  |  | 644.5 |  |  | 610 |  |  | 610.5 |  |  | 637.5 |  |  | 622.5 |  |  | 591.5 |  |  | 645.5 |  |  | 646 |  |  | 622.5 |  |  | 654.5 |  |  | 662.5 |  |  | 653 |  |  | 631.5 |  |  | 674.5 |  |  | 670.5 |  |  | 701.5 |  |  | 696.5 |  |  | 598.5 |  |  | 664.5 |  |  | 584.5 |  |  | 661.5 |  |  | 641 |  |  | 677.5 |  |  | 638.5 |  |  | 639.5 |  |  | 650.5 |  |  | 598.5 |  |  | 620.5 |  |  | 619.5 |  |  | 636 |  |  | 626.5 |  |  | 655.5 |  |  | 644.5 |  |  | 588 |  |  | 630.5 |  |  | 600 |  |  | 653.5 |  |  | 641.5 |  |  | 614.5 |  |  | 627 |  |  | 585.5 |  |  | 648 |  |  | 675 |  |  | 676.5 |  |  | 607 |  |  | 666 |  |  | 722.5 |  |  | 678.5 |  |  | 656.5 |  |  | 665 |  |  | 655.5 |  |  | 657.5 |  |  | 599.5 |  |  | 705.5 |  |  | 629.5 |  |  | 631.5 |  |  | 643.5 |  |  | 695.5 |  |  | 665 |  |  | 722.5 |  |  | 564 |  |  | 664.5 |  |  | 517.5 |  |  | 695.5 |  |  | 658 |  |  | 662 |  |  | 706 |  |  | 657.5 |  |  | 637 |  |  | 637.5 |  |  | 698.5 |  |  | 577.5 |  |  | 652.5 |  |  | 694.5 |  |  | 690.5 |  |  | 631.5 |  |  | 615.5 |  |  | 698 |  |  | 589.5 |  |  | 592.5 |  |  | 627.5 |  |  | 643.5 |  |  | 590 |  |  | 646.5 |  |  | 700 |  |  | 595.5 |  |  | 639.5 |  |  | 627.5 |  |  | 648.5 |  |  | 649 |  |  | 576.5 |  |  | 629 |  |  | 627.5 |  |  | 654.5 |  |  | 732.5 |  |  | 627.5 |  |  | 653.5 |  |  | 673.5 |  |  | 670.5 |  |  | 637.5 |  |  | 577.5 |  |  | 701 |  |  | 654.5 |  |  | 592.5 |  |  | 615.5 |  |  | 626.5 |  |  | 638.5 |  |  | 592 |  |  | 631 |  |  | 624.5 |  |  | 624 |  |  | 665.5 |  |  | 675.5 |  |  | 656.5 |  |  | 689.5 |  |  | 680.5 |  |  | 651.5 |  |  | 644.5 |  |  | 696.5 |  |  | 623 |  |  | 715.5 |  |  | 706.5 |  |  | 701.5 |  |  | 630 |  |  | 698.5 |  |  | 620.5 |  |  | 723 |  |  | 593 |  |  | 640.5 |  |  | 587 |  |  | 625 |  |  | 626.5 |  |  | 607 |  |  | 687.5 |  |  | 696.5 |  |  | 648.5 |  |  | 655.5 |  |  | 606.5 |  |  | 665.5 |  |  | 539.5 |  |  | 651.5 |  |  | 637.5 |  |  | 613.5 |  |  | 651 |  |  | 623 |  |  | 647.5 |  |  | 612.5 |  |  | 657.5 |  |  | 646.5 |  |  | 622.5 |  |  | 684.5 |  |  | 661.5 |  |  | 568.5 |  |  | 667 |  |  | 594.5 |  |  | 605 |  |  | 589.5 |  |  | 741.5 |  |  | 680.5 |  |  | 737 |  |  | 619.5 |  |  | 653.5 |  |  | 553 |  |  | 677.5 |  |  | 606.5 |  |  | 654.5 |  |  | 675.5 |  |  | 646.5 |  |  | 591.5 |  |  | 596 |  |  | 670.5 |  |  | 607.5 |  |  | 664.5 |  |  | 691.5 |  |  | 628 |  |  | 571.5 |  |  | 655.5 |  |  | 606 |  |  | 638.5 |  |  | 650.5 |  |  | 619 |  |  | 665.5 |  |  | 603.5 |  |  | 670.5 |  |  | 643 |  |  | 609.5 |  |  | 626.5 |  |  | 624 |  |  | 593.5 |  |  | 677.5 |  |  | 598.5 |  |  | 564.5 |  |  | 728.5 |  |  | 732.5 |  |  | 623.5 |  |  | 662 |  |  | 636 |  |  | 580.5 |  |  | 630.5 |  |  | 597.5 |  |  | 652 |  |  | 668.5 |  |  | 657.5 |  |  | 715.5 |  |  | 640.5 |  |  | 659.5 |  |  | 660.5 |  |  | 540.5 |  |  | 658.5 |  |  | 606.5 |  |  | 646 |  |  | 675.5 |  |  | 631.5 |  |  | 623.5 |  |  | 687.5 |  |  | 656.5 |  |  | 633.5 |  |  | 655.5 |  |  | 707.5 |  |  | 636.5 |  |  | 613.5 |  |  | 615.5 |  |  | 623.5 |  |  | 679.5 |  |  | 727 |  |  | 646.5 |  |  | 667.5 |  |  | 628 |  |  | 637.5 |  |  | 631.5 |  |  | 678 |  |  | 632.5 |  |  | 678.5 |  |  | 685.5 |  |  | 680 |  |  | 637.5 |  |  | 619.5 |  |  | 647.5 |  |  | 557.5 |  |  | 677.5 |  |  | 612 |  |  | 621.5 |  |  | 685 |  |  | 605 |  |  | 676.5 |  |  | 651.5 |  |  | 657.5 |  |  | 598.5 |  |  | 655.5 |  |  | 641.5 |  |  | 630 |  |  | 640.5 |  |  | 692 |  |  | 627.5 |  |  | 639 |  |  | 646 |  |  | 681 |  |  | 600.5 |  |  | 586 |  |  | 676.5 |  |  | 737.5 |  |  | 652.5 |  |  | 736.5 |  |  | 671.5 |  |  | 656 |  |  | 678.5 |  |  | 682.5 |  |  | 708.5 |  |  | 682 |  |  | 659.5 |  |  | 684.5 |  |  | 669.5 |  |  | 645.5 |  |  | 549 |  |  | 642 |  |  | 625 |  |  | 679.5 |  |  | 663 |  |  | 631 |  |  | 692.5 |  |  | 644.5 |  |  | 578.5 |  |  | 616.5 |  |  | 699.5 |  |  | 698.5 |  |  | 640.5 |  |  | 687.5 |  |  | 626.5 |  |  | 592 |  |  | 698.5 |  |  | 653 |  |  | 682.5 |  |  | 606.5 |  |  | 687.5 |  |  | 653.5 |  |  | 628 |  |  | 639.5 |  |  | 641 |  |  | 628.5 |  |  | 608.5 |  |  | 554 |  |  | 686 |  |  | 682.5 |  |  | 630 |  |  | 662.5 |  |  | 563.5 |  |  | 664.5 |  |  | 643.5 |  |  | 671.5 |  |  | 671.5 |  |  | 596.5 |  |  | 623 |  |  | 612.5 |  |  | 650.5 |  |  | 599.5 |  |  | 627.5 |  |  | 671.5 |  |  | 653.5 |  |  | 644.5 |  |  | 620.5 |  |  | 636.5 |  |  | 648.5 |  |  | 678.5 |  |  | 603.5 |  |  | 723 |  |  | 592.5 |  |  | 619.5 |  |  | 707 |  |  | 617.5 |  |  | 579.5 |  |  | 612.5 |  |  | 662.5 |  |  | 650 |  |  | 674.5 |  |  | 649.5 |  |  | 638.5 |  |  | 658.5 |  |  | 655 |  |  | 652.5 |  |  | 635.5 |  |  | 625.5 |  |  | 665.5 |  |  | 649.5 |  |  | 631.5 |  |  | 675.5 |  |  | 692.5 |  |  | 666.5 |  |  | 629.5 |  |  | 758.5 |  |  | 651 |  |  | 683.5 |  |  | 655.5 |  |  | 696.5 |  |  | 627.5 |  |  | 615.5 |  |  | 607.5 |  |  | 646 |  |  | 601.5 |  |  | 629 |  |  | 610.5 |  |  | 680.5 |  |  | 620.5 |  |  | 630 |  |  | 643 |  |  | 635.5 |  |  | 636.5 |  |  | 634.5 |  |  | 668.5 |  |  | 605.5 |  |  | 579.5 |  |  | 663.5 |  |  | 562.5 |  |  | 679.5 |  |  | 715.5 |  |  | 570.5 |  |  | 716.5 |  |  | 639.5 |  |  | 633.5 |  |  | 681.5 |  |  | 655.5 |  |  | 640.5 |  |  | 610.5 |  |  | 642.5 |  |  | 659.5 |  |  | 668.5 |  |  | 726.5 |  |  | 660 |  |  | 721.5 |  |  | 601.5 |  |  | 659.5 |  |  | 635 |  |  | 633.5 |  |  | 648.5 |  |  | 649.5 |  |  | 674.5 |  |  | 665 |  |  | 610.5 |  |  | 635.5 |  |  | 621 |  |  | 628 |  |  | 638 |  |  | 660.5 |  |  | 660.5 |  |  | 684.5 |  |  | 634.5 |  |  | 672 |  |  | 698.5 |  |  | 669.5 |  |  | 629 |  |  | 642 |  |  | 638.5 |  |  | 664.5 |  |  | 654 |  |  | 614.5 |  |  | 643 |  |  | 560.5 |  |  | 589.5 |  |  | 595 |  |  | 711.5 |  |  | 598.5 |  |  | 597.5 |  |  | 694 |  |  | 688.5 |  |  | 647.5 |  |  | 627.5 |  |  | 641.5 |  |  | 628.5 |  |  | 670.5 |  |  | 584.5 |  |  | 633.5 |  |  | 660.5 |  |  | 696.5 |  |  | 665 |  |  | 596.5 |  |  | 675.5 |  |  | 668.5 |  |  | 668.5 |  |  | 616.5 |  |  | 727.5 |  |  | 706.5 |  |  | 680.5 |  |  | 715 |  |  | 679.5 |  |  | 647 |  |  | 679.5 |  |  | 704.5 |  |  | 667.5 |  |  | 679.5 |  |  | 698.5 |  |  | 620.5 |  |  | 577.5 |  |  | 682.5 |  |  | 602 |  |  | 625.5 |  |  | 576 |  |  | 631.5 |  |  | 602.5 |  |  | 676.5 |  |  | 719 |  |  | 615.5 |  |  | 672.5 |  |  | 661 |  |  | 638.5 |  |  | 618 |  |  | 625.5 |  |  | 645.5 |  |  | 639.5 |  |  | 630 |  |  | 621.5 |  |  | 716.5 |  |  | 635 |  |  | 664.5 |  |  | 605.5 |  |  | 660 |  |  | 642.5 |  |  | 694.5 |  |  | 638.5 |  |  | 644.5 |  |  | 620.5 |  |  | 602.5 |  |  | 566.5 |  |  | 631.5 |  |  | 566.5 |  |  | 663.5 |  |  | 692.5 |  |  | 626 |  |  | 712 |  |  | 649.5 |  |  | 659.5 |  |  | 719
23 |  | 672.5 |  |  | 730.5 |  |  | 692 |  |  | 621.5 |  |  | 716.5 |  |  | 650.5 |  |  | 704.5 |  |  | 649.5 |  |  | 666.5 |  |  | 671.5 |  |  | 652 |  |  | 686.5 |  |  | 702.5 |  |  | 629.5 |  |  | 606 |  |  | 675.5 |  |  | 661.5 |  |  | 679.5 |  |  | 732.5 |  |  | 568.5 |  |  | 648.5 |  |  | 606.5 |  |  | 638.5 |  |  | 643.5 |  |  | 607 |  |  | 671.5 |  |  | 611.5 |  |  | 662.5 |  |  | 638.5 |  |  | 577 |  |  | 648 |  |  | 654.5 |  |  | 587.5 |  |  | 625.5 |  |  | 539.5 |  |  | 629 |  |  | 654.5 |  |  | 618 |  |  | 639.5 |  |  | 688.5 |  |  | 636.5 |  |  | 663.5 |  |  | 652.5 |  |  | 619 |  |  | 686.5 |  |  | 697 |  |  | 628.5 |  |  | 672.5 |  |  | 606.5 |  |  | 616.5 |  |  | 622.5 |  |  | 650.5 |  |  | 645.5 |  |  | 637.5 |  |  | 651.5 |  |  | 628.5 |  |  | 606.5 |  |  | 668 |  |  | 678.5 |  |  | 630.5 |  |  | 631 |  |  | 598.5 |  |  | 675.5 |  |  | 624.5 |  |  | 609.5 |  |  | 608 |  |  | 651.5 |  |  | 603 |  |  | 610.5 |  |  | 637.5 |  |  | 690 |  |  | 654.5 |  |  | 622.5 |  |  | 708.5 |  |  | 698 |  |  | 619 |  |  | 634.5 |  |  | 591.5 |  |  | 572.5 |  |  | 647.5 |  |  | 637 |  |  | 627.5 |  |  | 648.5 |  |  | 681.5 |  |  | 676.5 |  |  | 700.5 |  |  | 708.5 |  |  | 637.5 |  |  | 581.5 |  |  | 691.5 |  |  | 643.5 |  |  | 636 |  |  | 655.5 |  |  | 605 |  |  | 650 |  |  | 614 |  |  | 681.5 |  |  | 649.5 |  |  | 617.5 |  |  | 596.5 |  |  | 649.5 |  |  | 663 |  |  | 671 |  |  | 676.5 |  |  | 643.5 |  |  | 644.5 |  |  | 640.5 |  |  | 710.5 |  |  | 658.5 |  |  | 649.5 |  |  | 664.5 |  |  | 648.5 |  |  | 679.5 |  |  | 680.5 |  |  | 693.5 |  |  | 649.5 |  |  | 668.5 |  |  | 629.5 |  |  | 670.5 |  |  | 708.5 |  |  | 651.5 |  |  | 653.5 |  |  | 657.5 |  |  | 656.5 |  |  | 620.5 |  |  | 728 |  |  | 651.5 |  |  | 665.5 |  |  | 598.5 |  |  | 610.5 |  |  | 671.5 |  |  | 597 |  |  | 634.5 |  |  | 699.5 |  |  | 580.5 |  |  | 674.5 |  |  | 619 |  |  | 658.5 |  |  | 685.5 |  |  | 638 |  |  | 612.5 |  |  | 599 |  |  | 653 |  |  | 676.5 |  |  | 668 |  |  | 676.5 |  |  | 635.5 |  |  | 707.5 |  |  | 624.5 |  |  | 677.5 |  |  | 690.5 |  |  | 644.5 |  |  | 657.5 |  |  | 726.5 |  |  | 679.5 |  |  | 666 |  |  | 590.5 |  |  | 615 |  |  | 647.5 |  |  | 629.5 |  |  | 659 |  |  | 655.5 |  |  | 652.5 |  |  | 635.5 |  |  | 643 |  |  | 625.5 |  |  | 624.5 |  |  | 658.5 |  |  | 677.5 |  |  | 627.5 |  |  | 604.5 |  |  | 617 |  |  | 625.5 |  |  | 638.5 |  |  | 595.5 |  |  | 652.5 |  |  | 653.5 |  |  | 665.5 |  |  | 639.5 |  |  | 674 |  |  | 672.5 |  |  | 647.5 |  |  | 638.5 |  |  | 630.5 |  |  | 598.5 |  |  | 673.5 |  |  | 657.5 |  |  | 659.5 |  |  | 660.5 |  |  | 624.5 |  |  | 635.5 |  |  | 565.5 |  |  | 594.5 |  |  | 636 |  |  | 668.5 |  |  | 650.5 |  |  | 599.5 |  |  | 644.5 |  |  | 711.5 |  |  | 680.5 |  |  | 685.5 |  |  | 639.5 |  |  | 568.5 |  |  | 662.5 |  |  | 631.5 |  |  | 716.5 |  |  | 612.5 |  |  | 599.5 |  |  | 680.5 |  |  | 685.5 |  |  | 631 |  |  | 677.5 |  |  | 642.5 |  |  | 602 |  |  | 675.5 |  |  | 645 |  |  | 619.5 |  |  | 649.5 |  |  | 727.5 |  |  | 694.5 |  |  | 639.5 |  |  | 599.5 |  |  | 609.5 |  |  | 621.5 |  |  | 615 |  |  | 603.5 |  |  | 568.5 |  |  | 648.5 |  |  | 680.5 |  |  | 657 |  |  | 578.5 |  |  | 579.5 |  |  | 654.5 |  |  | 715.5 |  |  | 699.5 |  |  | 645.5 |  |  | 621.5 |  |  | 685.5 |  |  | 625 |  |  | 699 |  |  | 625.5 |  |  | 637.5 |  |  | 675.5 |  |  | 702 |  |  | 670.5 |  |  | 683.5 |  |  | 640.5 |  |  | 641 |  |  | 606.5 |  |  | 638.5 |  |  | 605.5 |  |  | 589.5 |  |  | 637.5 |  |  | 611.5 |  |  | 683.5 |  |  | 651.5 |  |  | 630.5 |  |  | 610 |  |  | 579.5 |  |  | 645.5 |  |  | 624.5 |  |  | 647.5 |  |  | 669.5 |  |  | 666 |  |  | 665.5 |  |  | 669.5 |  |  | 616 |  |  | 688.5 |  |  | 640.5 |  |  | 720 |  |  | 631.5 |  |  | 600.5 |  |  | 744.5 |  |  | 614.5 |  |  | 696 |  |  | 684 |  |  | 638.5 |  |  | 687.5 |  |  | 657.5 |  |  | 642.5 |  |  | 705.5 |  |  | 615.5 |  |  | 633 |  |  | 658.5 |  |  | 649.5 |  |  | 659 |  |  | 652.5 |  |  | 644.5 |  |  | 601 |  |  | 689.5 |  |  | 623.5 |  |  | 650.5 |  |  | 647 |  |  | 674.5 |  |  | 636 |  |  | 681.5 |  |  | 618.5 |  |  | 667.5 |  |  | 602 |  |  | 601.5 |  |  | 630.5 |  |  | 587.5 |  |  | 675 |  |  | 588.5 |  |  | 631.5 |  |  | 678.5 |  |  | 636.5 |  |  | 628.5 |  |  | 633 |  |  | 606.5 |  |  | 679.5 |  |  | 732.5 |  |  | 569 |  |  | 676 |  |  | 697.5 |  |  | 689.5 |  |  | 622.5 |  |  | 669.5 |  |  | 641.5 |  |  | 643.5 |  |  | 600.5 |  |  | 683.5 |  |  | 596.5 |  |  | 626.5 |  |  | 627 |  |  | 631.5 |  |  | 698.5 |  |  | 685.5 |  |  | 693.5 |  |  | 685 |  |  | 697.5 |  |  | 639.5 |  |  | 675.5 |  |  | 601.5 |  |  | 643.5 |  |  | 639 |  |  | 668 |  |  | 570 |  |  | 632 |  |  | 610.5 |  |  | 678 |  |  | 638.5 |  |  | 607 |  |  | 655.5 |  |  | 679.5 |  |  | 639.5 |  |  | 646.5 |  |  | 713.5 |  |  | 678 |  |  | 565.5 |  |  | 681.5 |  |  | 616.5 |  |  | 694 |  |  | 644.5 |  |  | 658.5 |  |  | 623.5 |  |  | 700 |  |  | 663.5 |  |  | 591.5 |  |  | 609.5 |  |  | 621.5 |  |  | 659.5 |  |  | 633.5 |  |  | 757.5 |  |  | 604.5 |  |  | 604.5 |  |  | 608.5 |  |  | 594 |  |  | 606.5 |  |  | 693.5 |  |  | 646.5 |  |  | 670.5 |  |  | 710.5 |  |  | 601 |  |  | 586.5 |  |  | 677 |  |  | 637 |  |  | 640.5 |  |  | 665.5 |  |  | 630.5 |  |  | 672 |  |  | 667.5 |  |  | 681.5 |  |  | 653.5 |  |  | 596 |  |  | 617.5 |  |  | 563.5 |  |  | 697.5 |  |  | 613.5 |  |  | 621.5 |  |  | 637 |  |  | 666.5 |  |  | 653 |  |  | 669.5 |  |  | 620.5 |  |  | 709.5 |  |  | 720 |  |  | 601.5 |  |  | 667 |  |  | 676 |  |  | 629.5 |  |  | 640.5 |  |  | 619.5 |  |  | 677.5 |  |  | 691 |  |  | 625.5 |  |  | 665.5 |  |  | 577.5 |  |  | 630 |  |  | 710.5 |  |  | 566.5 |  |  | 611.5 |  |  | 682.5 |  |  | 616 |  |  | 571.5 |  |  | 571.5 |  |  | 662.5 |  |  | 636.5 |  |  | 658.5 |  |  | 665.5 |  |  | 694 |  |  | 657.5 |  |  | 626.5 |  |  | 678 |  |  | 638.5 |  |  | 628.5 |  |  | 634.5 |  |  | 660 |  |  | 642.5 |  |  | 675.5 |  |  | 670.5 |  |  | 652.5 |  |  | 628.5 |  |  | 724 |  |  | 603 |  |  | 639.5 |  |  | 624.5 |  |  | 671.5 |  |  | 615.5 |  |  | 610 |  |  | 655 |  |  | 637 |  |  | 694.5 |  |  | 656 |  |  | 697.5 |  |  | 670.5 |  |  | 667 |  |  | 528.5 |  |  | 674.5 |  |  | 613.5 |  |  | 702.5 |  |  | 588.5 |  |  | 627 |  |  | 687 |  |  | 584.5 |  |  | 631.5 |  |  | 640 |  |  | 572.5 |  |  | 703.5 |  |  | 658 |  |  | 731.5 |  |  | 741.5 |  |  | 569 |  |  | 683.5 |  |  | 661.5 |  |  | 616 |  |  | 655.5 |  |  | 574 |  |  | 670.5 |  |  | 689 |  |  | 587.5 |  |  | 636.5 |  |  | 655.5 |  |  | 671.5 |  |  | 630.5 |  |  | 681.5 |  |  | 710 |  |  | 643.5 |  |  | 670.5 |  |  | 633.5 |  |  | 722.5 |  |  | 631.5 |  |  | 617 |  |  | 640.5 |  |  | 643 |  |  | 664.5 |  |  | 610.5 |  |  | 690.5 |  |  | 599.5 |  |  | 608.5 |  |  | 659.5 |  |  | 589.5 |  |  | 698.5 |  |  | 636.5 |  |  | 684 |  |  | 664.5 |  |  | 612 |  |  | 649 |  |  | 592.5 |  |  | 599 |  |  | 631.5 |  |  | 635.5 |  |  | 663.5 |  |  | 602.5 |  |  | 642.5 |  |  | 696.5 |  |  | 690.5 |  |  | 645 |  |  | 697 |  |  | 628.5 |  |  | 644.5 |  |  | 610 |  |  | 610.5 |  |  | 637.5 |  |  | 622.5 |  |  | 591.5 |  |  | 645.5 |  |  | 646 |  |  | 622.5 |  |  | 654.5 |  |  | 662.5 |  |  | 653 |  |  | 631.5 |  |  | 674.5 |  |  | 670.5 |  |  | 701.5 |  |  | 696.5 |  |  | 598.5 |  |  | 664.5 |  |  | 584.5 |  |  | 661.5 |  |  | 641 |  |  | 677.5 |  |  | 638.5 |  |  | 639.5 |  |  | 650.5 |  |  | 598.5 |  |  | 620.5 |  |  | 619.5 |  |  | 636 |  |  | 626.5 |  |  | 655.5 |  |  | 644.5 |  |  | 588 |  |  | 630.5 |  |  | 600 |  |  | 653.5 |  |  | 641.5 |  |  | 614.5 |  |  | 627 |  |  | 585.5 |  |  | 648 |  |  | 675 |  |  | 676.5 |  |  | 607 |  |  | 666 |  |  | 722.5 |  |  | 678.5 |  |  | 656.5 |  |  | 665 |  |  | 655.5 |  |  | 657.5 |  |  | 599.5 |  |  | 705.5 |  |  | 629.5 |  |  | 631.5 |  |  | 643.5 |  |  | 695.5 |  |  | 665 |  |  | 722.5 |  |  | 564 |  |  | 664.5 |  |  | 517.5 |  |  | 695.5 |  |  | 658 |  |  | 662 |  |  | 706 |  |  | 657.5 |  |  | 637 |  |  | 637.5 |  |  | 698.5 |  |  | 577.5 |  |  | 652.5 |  |  | 694.5 |  |  | 690.5 |  |  | 631.5 |  |  | 615.5 |  |  | 698 |  |  | 589.5 |  |  | 592.5 |  |  | 627.5 |  |  | 643.5 |  |  | 590 |  |  | 646.5 |  |  | 700 |  |  | 595.5 |  |  | 639.5 |  |  | 627.5 |  |  | 648.5 |  |  | 649 |  |  | 576.5 |  |  | 629 |  |  | 627.5 |  |  | 654.5 |  |  | 732.5 |  |  | 627.5 |  |  | 653.5 |  |  | 673.5 |  |  | 670.5 |  |  | 637.5 |  |  | 577.5 |  |  | 701 |  |  | 654.5 |  |  | 592.5 |  |  | 615.5 |  |  | 626.5 |  |  | 638.5 |  |  | 592 |  |  | 631 |  |  | 624.5 |  |  | 624 |  |  | 665.5 |  |  | 675.5 |  |  | 656.5 |  |  | 689.5 |  |  | 680.5 |  |  | 651.5 |  |  | 644.5 |  |  | 696.5 |  |  | 623 |  |  | 715.5 |  |  | 706.5 |  |  | 701.5 |  |  | 630 |  |  | 698.5 |  |  | 620.5 |  |  | 723 |  |  | 593 |  |  | 640.5 |  |  | 587 |  |  | 625 |  |  | 626.5 |  |  | 607 |  |  | 687.5 |  |  | 696.5 |  |  | 648.5 |  |  | 655.5 |  |  | 606.5 |  |  | 665.5 |  |  | 539.5 |  |  | 651.5 |  |  | 637.5 |  |  | 613.5 |  |  | 651 |  |  | 623 |  |  | 647.5 |  |  | 612.5 |  |  | 657.5 |  |  | 646.5 |  |  | 622.5 |  |  | 684.5 |  |  | 661.5 |  |  | 568.5 |  |  | 667 |  |  | 594.5 |  |  | 605 |  |  | 589.5 |  |  | 741.5 |  |  | 680.5 |  |  | 737 |  |  | 619.5 |  |  | 653.5 |  |  | 553 |  |  | 677.5 |  |  | 606.5 |  |  | 654.5 |  |  | 675.5 |  |  | 646.5 |  |  | 591.5 |  |  | 596 |  |  | 670.5 |  |  | 607.5 |  |  | 664.5 |  |  | 691.5 |  |  | 628 |  |  | 571.5 |  |  | 655.5 |  |  | 606 |  |  | 638.5 |  |  | 650.5 |  |  | 619 |  |  | 665.5 |  |  | 603.5 |  |  | 670.5 |  |  | 643 |  |  | 609.5 |  |  | 626.5 |  |  | 624 |  |  | 593.5 |  |  | 677.5 |  |  | 598.5 |  |  | 564.5 |  |  | 728.5 |  |  | 732.5 |  |  | 623.5 |  |  | 662 |  |  | 636 |  |  | 580.5 |  |  | 630.5 |  |  | 597.5 |  |  | 652 |  |  | 668.5 |  |  | 657.5 |  |  | 715.5 |  |  | 640.5 |  |  | 659.5 |  |  | 660.5 |  |  | 540.5 |  |  | 658.5 |  |  | 606.5 |  |  | 646 |  |  | 675.5 |  |  | 631.5 |  |  | 623.5 |  |  | 687.5 |  |  | 656.5 |  |  | 633.5 |  |  | 655.5 |  |  | 707.5 |  |  | 636.5 |  |  | 613.5 |  |  | 615.5 |  |  | 623.5 |  |  | 679.5 |  |  | 727 |  |  | 646.5 |  |  | 667.5 |  |  | 628 |  |  | 637.5 |  |  | 631.5 |  |  | 678 |  |  | 632.5 |  |  | 678.5 |  |  | 685.5 |  |  | 680 |  |  | 637.5 |  |  | 619.5 |  |  | 647.5 |  |  | 557.5 |  |  | 677.5 |  |  | 612 |  |  | 621.5 |  |  | 685 |  |  | 605 |  |  | 676.5 |  |  | 651.5 |  |  | 657.5 |  |  | 598.5 |  |  | 655.5 |  |  | 641.5 |  |  | 630 |  |  | 640.5 |  |  | 692 |  |  | 627.5 |  |  | 639 |  |  | 646 |  |  | 681 |  |  | 600.5 |  |  | 586 |  |  | 676.5 |  |  | 737.5 |  |  | 652.5 |  |  | 736.5 |  |  | 671.5 |  |  | 656 |  |  | 678.5 |  |  | 682.5 |  |  | 708.5 |  |  | 682 |  |  | 659.5 |  |  | 684.5 |  |  | 669.5 |  |  | 645.5 |  |  | 549 |  |  | 642 |  |  | 625 |  |  | 679.5 |  |  | 663 |  |  | 631 |  |  | 692.5 |  |  | 644.5 |  |  | 578.5 |  |  | 616.5 |  |  | 699.5 |  |  | 698.5 |  |  | 640.5 |  |  | 687.5 |  |  | 626.5 |  |  | 592 |  |  | 698.5 |  |  | 653 |  |  | 682.5 |  |  | 606.5 |  |  | 687.5 |  |  | 653.5 |  |  | 628 |  |  | 639.5 |  |  | 641 |  |  | 628.5 |  |  | 608.5 |  |  | 554 |  |  | 686 |  |  | 682.5 |  |  | 630 |  |  | 662.5 |  |  | 563.5 |  |  | 664.5 |  |  | 643.5 |  |  | 671.5 |  |  | 671.5 |  |  | 596.5 |  |  | 623 |  |  | 612.5 |  |  | 650.5 |  |  | 599.5 |  |  | 627.5 |  |  | 671.5 |  |  | 653.5 |  |  | 644.5 |  |  | 620.5 |  |  | 636.5 |  |  | 648.5 |  |  | 678.5 |  |  | 603.5 |  |  | 723 |  |  | 592.5 |  |  | 619.5 |  |  | 707 |  |  | 617.5 |  |  | 579.5 |  |  | 612.5 |  |  | 662.5 |  |  | 650 |  |  | 674.5 |  |  | 649.5 |  |  | 638.5 |  |  | 658.5 |  |  | 655 |  |  | 652.5 |  |  | 635.5 |  |  | 625.5 |  |  | 665.5 |  |  | 649.5 |  |  | 631.5 |  |  | 675.5 |  |  | 692.5 |  |  | 666.5 |  |  | 629.5 |  |  | 758.5 |  |  | 651 |  |  | 683.5 |  |  | 655.5 |  |  | 696.5 |  |  | 627.5 |  |  | 615.5 |  |  | 607.5 |  |  | 646 |  |  | 601.5 |  |  | 629 |  |  | 610.5 |  |  | 680.5 |  |  | 620.5 |  |  | 630 |  |  | 643 |  |  | 635.5 |  |  | 636.5 |  |  | 634.5 |  |  | 668.5 |  |  | 605.5 |  |  | 579.5 |  |  | 663.5 |  |  | 562.5 |  |  | 679.5 |  |  | 715.5 |  |  | 570.5 |  |  | 716.5 |  |  | 639.5 |  |  | 633.5 |  |  | 681.5 |  |  | 655.5 |  |  | 640.5 |  |  | 610.5 |  |  | 642.5 |  |  | 659.5 |  |  | 668.5 |  |  | 726.5 |  |  | 660 |  |  | 721.5 |  |  | 601.5 |  |  | 659.5 |  |  | 635 |  |  | 633.5 |  |  | 648.5 |  |  | 649.5 |  |  | 674.5 |  |  | 665 |  |  | 610.5 |  |  | 635.5 |  |  | 621 |  |  | 628 |  |  | 638 |  |  | 660.5 |  |  | 660.5 |  |  | 684.5 |  |  | 634.5 |  |  | 672 |  |  | 698.5 |  |  | 669.5 |  |  | 629 |  |  | 642 |  |  | 638.5 |  |  | 664.5 |  |  | 654 |  |  | 614.5 |  |  | 643 |  |  | 560.5 |  |  | 589.5 |  |  | 595 |  |  | 711.5 |  |  | 598.5 |  |  | 597.5 |  |  | 694 |  |  | 688.5 |  |  | 647.5 |  |  | 627.5 |  |  | 641.5 |  |  | 628.5 |  |  | 670.5 |  |  | 584.5 |  |  | 633.5 |  |  | 660.5 |  |  | 696.5 |  |  | 665 |  |  | 596.5 |  |  | 675.5 |  |  | 668.5 |  |  | 668.5 |  |  | 616.5 |  |  | 727.5 |  |  | 706.5 |  |  | 680.5 |  |  | 715 |  |  | 679.5 |  |  | 647 |  |  | 679.5 |  |  | 704.5 |  |  | 667.5 |  |  | 679.5 |  |  | 698.5 |  |  | 620.5 |  |  | 577.5 |  |  | 682.5 |  |  | 602 |  |  | 625.5 |  |  | 576 |  |  | 631.5 |  |  | 602.5 |  |  | 676.5 |  |  | 719 |  |  | 615.5 |  |  | 672.5 |  |  | 661 |  |  | 638.5 |  |  | 618 |  |  | 625.5 |  |  | 645.5 |  |  | 639.5 |  |  | 630 |  |  | 621.5 |  |  | 716.5 |  |  | 635 |  |  | 664.5 |  |  | 605.5 |  |  | 660 |  |  | 642.5 |  |  | 694.5 |  |  | 638.5 |  |  | 644.5 |  |  | 620.5 |  |  | 602.5 |  |  | 566.5 |  |  | 631.5 |  |  | 566.5 |  |  | 663.5 |  |  | 692.5 |  |  | 626 |  |  | 712 |  |  | 649.5 |  |  | 659.5 |  |  | 719
24 |  | 711.5 |  |  | 769.5 |  |  | 739 |  |  | 660.5 |  |  | 737.5 |  |  | 671.5 |  |  | 751.5 |  |  | 673.5 |  |  | 695.5 |  |  | 695.5 |  |  | 667 |  |  | 733.5 |  |  | 741.5 |  |  | 658.5 |  |  | 630 |  |  | 722.5 |  |  | 700.5 |  |  | 700.5 |  |  | 771.5 |  |  | 607.5 |  |  | 687.5 |  |  | 653.5 |  |  | 664.5 |  |  | 682.5 |  |  | 636 |  |  | 700.5 |  |  | 626.5 |  |  | 701.5 |  |  | 659.5 |  |  | 601 |  |  | 687 |  |  | 693.5 |  |  | 634.5 |  |  | 664.5 |  |  | 565.5 |  |  | 668 |  |  | 693.5 |  |  | 642 |  |  | 660.5 |  |  | 727.5 |  |  | 651.5 |  |  | 689.5 |  |  | 699.5 |  |  | 645 |  |  | 725.5 |  |  | 723 |  |  | 667.5 |  |  | 701.5 |  |  | 645.5 |  |  | 642.5 |  |  | 648.5 |  |  | 665.5 |  |  | 666.5 |  |  | 658.5 |  |  | 690.5 |  |  | 657.5 |  |  | 645.5 |  |  | 694 |  |  | 693.5 |  |  | 651.5 |  |  | 655 |  |  | 624.5 |  |  | 714.5 |  |  | 671.5 |  |  | 635.5 |  |  | 655 |  |  | 672.5 |  |  | 618 |  |  | 639.5 |  |  | 661.5 |  |  | 716 |  |  | 693.5 |  |  | 651.5 |  |  | 723.5 |  |  | 722 |  |  | 634 |  |  | 660.5 |  |  | 606.5 |  |  | 596.5 |  |  | 671.5 |  |  | 676 |  |  | 648.5 |  |  | 687.5 |  |  | 707.5 |  |  | 723.5 |  |  | 747.5 |  |  | 732.5 |  |  | 661.5 |  |  | 628.5 |  |  | 712.5 |  |  | 682.5 |  |  | 651 |  |  | 679.5 |  |  | 652 |  |  | 665 |  |  | 640 |  |  | 702.5 |  |  | 664.5 |  |  | 646.5 |  |  | 622.5 |  |  | 670.5 |  |  | 692 |  |  | 710 |  |  | 691.5 |  |  | 682.5 |  |  | 659.5 |  |  | 655.5 |  |  | 739.5 |  |  | 682.5 |  |  | 688.5 |  |  | 711.5 |  |  | 663.5 |  |  | 718.5 |  |  | 704.5 |  |  | 722.5 |  |  | 673.5 |  |  | 707.5 |  |  | 644.5 |  |  | 709.5 |  |  | 747.5 |  |  | 690.5 |  |  | 677.5 |  |  | 672.5 |  |  | 695.5 |  |  | 649.5 |  |  | 767 |  |  | 680.5 |  |  | 712.5 |  |  | 613.5 |  |  | 625.5 |  |  | 710.5 |  |  | 623 |  |  | 655.5 |  |  | 738.5 |  |  | 619.5 |  |  | 713.5 |  |  | 658 |  |  | 687.5 |  |  | 724.5 |  |  | 677 |  |  | 651.5 |  |  | 625 |  |  | 677 |  |  | 723.5 |  |  | 694 |  |  | 723.5 |  |  | 650.5 |  |  | 728.5 |  |  | 663.5 |  |  | 701.5 |  |  | 705.5 |  |  | 683.5 |  |  | 683.5 |  |  | 755.5 |  |  | 726.5 |  |  | 690 |  |  | 605.5 |  |  | 630 |  |  | 662.5 |  |  | 676.5 |  |  | 698 |  |  | 670.5 |  |  | 673.5 |  |  | 659.5 |  |  | 664 |  |  | 664.5 |  |  | 653.5 |  |  | 697.5 |  |  | 701.5 |  |  | 666.5 |  |  | 630.5 |  |  | 632 |  |  | 640.5 |  |  | 667.5 |  |  | 610.5 |  |  | 673.5 |  |  | 692.5 |  |  | 704.5 |  |  | 668.5 |  |  | 703 |  |  | 701.5 |  |  | 668.5 |  |  | 667.5 |  |  | 656.5 |  |  | 619.5 |  |  | 720.5 |  |  | 704.5 |  |  | 706.5 |  |  | 686.5 |  |  | 663.5 |  |  | 682.5 |  |  | 580.5 |  |  | 641.5 |  |  | 675 |  |  | 692.5 |  |  | 679.5 |  |  | 623.5 |  |  | 673.5 |  |  | 735.5 |  |  | 719.5 |  |  | 706.5 |  |  | 663.5 |  |  | 607.5 |  |  | 701.5 |  |  | 646.5 |  |  | 755.5 |  |  | 636.5 |  |  | 625.5 |  |  | 701.5 |  |  | 700.5 |  |  | 655 |  |  | 692.5 |  |  | 668.5 |  |  | 641 |  |  | 714.5 |  |  | 674 |  |  | 643.5 |  |  | 688.5 |  |  | 753.5 |  |  | 709.5 |  |  | 665.5 |  |  | 638.5 |  |  | 638.5 |  |  | 650.5 |  |  | 662 |  |  | 629.5 |  |  | 597.5 |  |  | 674.5 |  |  | 701.5 |  |  | 696 |  |  | 604.5 |  |  | 618.5 |  |  | 675.5 |  |  | 762.5 |  |  | 728.5 |  |  | 660.5 |  |  | 660.5 |  |  | 732.5 |  |  | 664 |  |  | 720 |  |  | 646.5 |  |  | 676.5 |  |  | 722.5 |  |  | 731 |  |  | 685.5 |  |  | 698.5 |  |  | 687.5 |  |  | 667 |  |  | 653.5 |  |  | 677.5 |  |  | 644.5 |  |  | 604.5 |  |  | 663.5 |  |  | 637.5 |  |  | 704.5 |  |  | 672.5 |  |  | 677.5 |  |  | 625 |  |  | 626.5 |  |  | 666.5 |  |  | 645.5 |  |  | 671.5 |  |  | 698.5 |  |  | 705 |  |  | 712.5 |  |  | 708.5 |  |  | 640 |  |  | 709.5 |  |  | 666.5 |  |  | 735 |  |  | 657.5 |  |  | 626.5 |  |  | 791.5 |  |  | 638.5 |  |  | 725 |  |  | 705 |  |  | 685.5 |  |  | 711.5 |  |  | 672.5 |  |  | 681.5 |  |  | 752.5 |  |  | 662.5 |  |  | 657 |  |  | 673.5 |  |  | 675.5 |  |  | 685 |  |  | 667.5 |  |  | 691.5 |  |  | 622 |  |  | 715.5 |  |  | 647.5 |  |  | 697.5 |  |  | 694 |  |  | 689.5 |  |  | 665 |  |  | 710.5 |  |  | 639.5 |  |  | 682.5 |  |  | 623 |  |  | 640.5 |  |  | 669.5 |  |  | 634.5 |  |  | 690 |  |  | 627.5 |  |  | 678.5 |  |  | 717.5 |  |  | 665.5 |  |  | 654.5 |  |  | 672 |  |  | 632.5 |  |  | 726.5 |  |  | 771.5 |  |  | 608 |  |  | 723 |  |  | 744.5 |  |  | 718.5 |  |  | 637.5 |  |  | 716.5 |  |  | 680.5 |  |  | 669.5 |  |  | 647.5 |  |  | 722.5 |  |  | 643.5 |  |  | 652.5 |  |  | 666 |  |  | 670.5 |  |  | 713.5 |  |  | 706.5 |  |  | 740.5 |  |  | 711 |  |  | 718.5 |  |  | 678.5 |  |  | 696.5 |  |  | 625.5 |  |  | 682.5 |  |  | 654 |  |  | 683 |  |  | 591 |  |  | 658 |  |  | 649.5 |  |  | 717 |  |  | 659.5 |  |  | 646 |  |  | 694.5 |  |  | 718.5 |  |  | 665.5 |  |  | 670.5 |  |  | 728.5 |  |  | 699 |  |  | 604.5 |  |  | 696.5 |  |  | 631.5 |  |  | 718 |  |  | 665.5 |  |  | 679.5 |  |  | 652.5 |  |  | 739 |  |  | 684.5 |  |  | 612.5 |  |  | 633.5 |  |  | 645.5 |  |  | 688.5 |  |  | 654.5 |  |  | 796.5 |  |  | 633.5 |  |  | 633.5 |  |  | 634.5 |  |  | 615 |  |  | 621.5 |  |  | 722.5 |  |  | 675.5 |  |  | 685.5 |  |  | 757.5 |  |  | 640 |  |  | 601.5 |  |  | 698 |  |  | 666 |  |  | 679.5 |  |  | 704.5 |  |  | 656.5 |  |  | 693 |  |  | 714.5 |  |  | 710.5 |  |  | 674.5 |  |  | 635 |  |  | 641.5 |  |  | 589.5 |  |  | 718.5 |  |  | 660.5 |  |  | 642.5 |  |  | 661 |  |  | 687.5 |  |  | 692 |  |  | 684.5 |  |  | 641.5 |  |  | 724.5 |  |  | 767 |  |  | 625.5 |  |  | 714 |  |  | 723 |  |  | 668.5 |  |  | 661.5 |  |  | 666.5 |  |  | 716.5 |  |  | 712 |  |  | 672.5 |  |  | 686.5 |  |  | 603.5 |  |  | 677 |  |  | 736.5 |  |  | 605.5 |  |  | 637.5 |  |  | 708.5 |  |  | 637 |  |  | 600.5 |  |  | 610.5 |  |  | 677.5 |  |  | 657.5 |  |  | 705.5 |  |  | 691.5 |  |  | 723 |  |  | 683.5 |  |  | 665.5 |  |  | 693 |  |  | 659.5 |  |  | 667.5 |  |  | 673.5 |  |  | 699 |  |  | 681.5 |  |  | 690.5 |  |  | 694.5 |  |  | 691.5 |  |  | 652.5 |  |  | 748 |  |  | 650 |  |  | 678.5 |  |  | 671.5 |  |  | 692.5 |  |  | 654.5 |  |  | 657 |  |  | 684 |  |  | 661 |  |  | 733.5 |  |  | 682 |  |  | 721.5 |  |  | 717.5 |  |  | 691 |  |  | 557.5 |  |  | 700.5 |  |  | 639.5 |  |  | 741.5 |  |  | 617.5 |  |  | 642 |  |  | 702 |  |  | 599.5 |  |  | 660.5 |  |  | 664 |  |  | 593.5 |  |  | 742.5 |  |  | 684 |  |  | 770.5 |  |  | 762.5 |  |  | 590 |  |  | 698.5 |  |  | 700.5 |  |  | 637 |  |  | 676.5 |  |  | 600 |  |  | 696.5 |  |  | 718 |  |  | 611.5 |  |  | 683.5 |  |  | 679.5 |  |  | 692.5 |  |  | 645.5 |  |  | 707.5 |  |  | 739 |  |  | 669.5 |  |  | 717.5 |  |  | 648.5 |  |  | 769.5 |  |  | 655.5 |  |  | 656 |  |  | 661.5 |  |  | 690 |  |  | 703.5 |  |  | 657.5 |  |  | 705.5 |  |  | 614.5 |  |  | 634.5 |  |  | 674.5 |  |  | 618.5 |  |  | 727.5 |  |  | 675.5 |  |  | 710 |  |  | 679.5 |  |  | 633 |  |  | 670 |  |  | 631.5 |  |  | 614 |  |  | 660.5 |  |  | 664.5 |  |  | 684.5 |  |  | 649.5 |  |  | 681.5 |  |  | 725.5 |  |  | 729.5 |  |  | 671 |  |  | 744 |  |  | 643.5 |  |  | 683.5 |  |  | 625 |  |  | 631.5 |  |  | 663.5 |  |  | 646.5 |  |  | 612.5 |  |  | 684.5 |  |  | 675 |  |  | 661.5 |  |  | 678.5 |  |  | 691.5 |  |  | 677 |  |  | 660.5 |  |  | 713.5 |  |  | 709.5 |  |  | 730.5 |  |  | 711.5 |  |  | 624.5 |  |  | 703.5 |  |  | 610.5 |  |  | 687.5 |  |  | 656 |  |  | 698.5 |  |  | 662.5 |  |  | 678.5 |  |  | 689.5 |  |  | 613.5 |  |  | 641.5 |  |  | 666.5 |  |  | 660 |  |  | 665.5 |  |  | 679.5 |  |  | 683.5 |  |  | 609 |  |  | 669.5 |  |  | 615 |  |  | 692.5 |  |  | 670.5 |  |  | 661.5 |  |  | 666 |  |  | 632.5 |  |  | 663 |  |  | 690 |  |  | 715.5 |  |  | 636 |  |  | 692 |  |  | 761.5 |  |  | 704.5 |  |  | 682.5 |  |  | 691 |  |  | 694.5 |  |  | 681.5 |  |  | 628.5 |  |  | 734.5 |  |  | 644.5 |  |  | 678.5 |  |  | 669.5 |  |  | 710.5 |  |  | 680 |  |  | 761.5 |  |  | 590 |  |  | 711.5 |  |  | 556.5 |  |  | 721.5 |  |  | 684 |  |  | 691 |  |  | 732 |  |  | 681.5 |  |  | 676 |  |  | 663.5 |  |  | 737.5 |  |  | 601.5 |  |  | 691.5 |  |  | 723.5 |  |  | 714.5 |  |  | 678.5 |  |  | 636.5 |  |  | 727 |  |  | 618.5 |  |  | 607.5 |  |  | 674.5 |  |  | 667.5 |  |  | 605 |  |  | 667.5 |  |  | 739 |  |  | 642.5 |  |  | 654.5 |  |  | 666.5 |  |  | 663.5 |  |  | 673 |  |  | 615.5 |  |  | 644 |  |  | 666.5 |  |  | 693.5 |  |  | 771.5 |  |  | 651.5 |  |  | 679.5 |  |  | 712.5 |  |  | 685.5 |  |  | 652.5 |  |  | 616.5 |  |  | 740 |  |  | 680.5 |  |  | 607.5 |  |  | 644.5 |  |  | 665.5 |  |  | 677.5 |  |  | 631 |  |  | 646 |  |  | 663.5 |  |  | 648 |  |  | 704.5 |  |  | 696.5 |  |  | 695.5 |  |  | 728.5 |  |  | 704.5 |  |  | 666.5 |  |  | 665.5 |  |  | 735.5 |  |  | 647 |  |  | 730.5 |  |  | 753.5 |  |  | 740.5 |  |  | 656 |  |  | 727.5 |  |  | 649.5 |  |  | 752 |  |  | 619 |  |  | 666.5 |  |  | 611 |  |  | 646 |  |  | 655.5 |  |  | 622 |  |  | 726.5 |  |  | 735.5 |  |  | 672.5 |  |  | 676.5 |  |  | 627.5 |  |  | 704.5 |  |  | 568.5 |  |  | 698.5 |  |  | 652.5 |  |  | 642.5 |  |  | 698 |  |  | 638 |  |  | 662.5 |  |  | 633.5 |  |  | 678.5 |  |  | 685.5 |  |  | 643.5 |  |  | 723.5 |  |  | 700.5 |  |  | 607.5 |  |  | 688 |  |  | 623.5 |  |  | 631 |  |  | 636.5 |  |  | 788.5 |  |  | 706.5 |  |  | 776 |  |  | 643.5 |  |  | 679.5 |  |  | 568 |  |  | 706.5 |  |  | 621.5 |  |  | 669.5 |  |  | 714.5 |  |  | 667.5 |  |  | 620.5 |  |  | 625 |  |  | 717.5 |  |  | 631.5 |  |  | 711.5 |  |  | 730.5 |  |  | 667 |  |  | 610.5 |  |  | 694.5 |  |  | 635 |  |  | 677.5 |  |  | 674.5 |  |  | 658 |  |  | 686.5 |  |  | 624.5 |  |  | 709.5 |  |  | 658 |  |  | 630.5 |  |  | 665.5 |  |  | 648 |  |  | 632.5 |  |  | 703.5 |  |  | 624.5 |  |  | 603.5 |  |  | 754.5 |  |  | 758.5 |  |  | 652.5 |  |  | 701 |  |  | 657 |  |  | 606.5 |  |  | 677.5 |  |  | 644.5 |  |  | 691 |  |  | 715.5 |  |  | 696.5 |  |  | 730.5 |  |  | 669.5 |  |  | 698.5 |  |  | 684.5 |  |  | 569.5 |  |  | 682.5 |  |  | 627.5 |  |  | 685 |  |  | 690.5 |  |  | 655.5 |  |  | 647.5 |  |  | 708.5 |  |  | 695.5 |  |  | 654.5 |  |  | 694.5 |  |  | 722.5 |  |  | 675.5 |  |  | 634.5 |  |  | 639.5 |  |  | 649.5 |  |  | 705.5 |  |  | 756 |  |  | 685.5 |  |  | 706.5 |  |  | 654 |  |  | 666.5 |  |  | 670.5 |  |  | 725 |  |  | 671.5 |  |  | 725.5 |  |  | 724.5 |  |  | 704 |  |  | 666.5 |  |  | 645.5 |  |  | 662.5 |  |  | 581.5 |  |  | 724.5 |  |  | 641 |  |  | 636.5 |  |  | 700 |  |  | 644 |  |  | 715.5 |  |  | 690.5 |  |  | 672.5 |  |  | 619.5 |  |  | 679.5 |  |  | 667.5 |  |  | 677 |  |  | 655.5 |  |  | 713 |  |  | 642.5 |  |  | 678 |  |  | 672 |  |  | 728 |  |  | 621.5 |  |  | 633 |  |  | 697.5 |  |  | 784.5 |  |  | 673.5 |  |  | 775.5 |  |  | 695.5 |  |  | 677 |  |  | 693.5 |  |  | 697.5 |  |  | 729.5 |  |  | 729 |  |  | 680.5 |  |  | 710.5 |  |  | 708.5 |  |  | 684.5 |  |  | 596 |  |  | 671 |  |  | 649 |  |  | 694.5 |  |  | 684 |  |  | 670 |  |  | 731.5 |  |  | 683.5 |  |  | 602.5 |  |  | 655.5 |  |  | 728.5 |  |  | 745.5 |  |  | 669.5 |  |  | 716.5 |  |  | 655.5 |  |  | 613 |  |  | 724.5 |  |  | 692 |  |  | 697.5 |  |  | 635.5 |  |  | 734.5 |  |  | 679.5 |  |  | 654 |  |  | 654.5 |  |  | 662 |  |  | 667.5 |  |  | 632.5 |  |  | 593 |  |  | 725 |  |  | 697.5 |  |  | 669 |  |  | 701.5 |  |  | 584.5 |  |  | 690.5 |  |  | 682.5 |  |  | 710.5 |  |  | 695.5 |  |  | 643.5 |  |  | 647 |  |  | 638.5 |  |  | 697.5 |  |  | 614.5 |  |  | 653.5 |  |  | 697.5 |  |  | 692.5 |  |  | 691.5 |  |  | 641.5 |  |  | 657.5 |  |  | 695.5 |  |  | 717.5 |  |  | 642.5 |  |  | 752 |  |  | 631.5 |  |  | 648.5 |  |  | 736 |  |  | 646.5 |  |  | 600.5 |  |  | 636.5 |  |  | 683.5 |  |  | 676 |  |  | 698.5 |  |  | 670.5 |  |  | 662.5 |  |  | 705.5 |  |  | 670 |  |  | 678.5 |  |  | 661.5 |  |  | 640.5 |  |  | 704.5 |  |  | 696.5 |  |  | 652.5 |  |  | 704.5 |  |  | 707.5 |  |  | 705.5 |  |  | 655.5 |  |  | 784.5 |  |  | 698 |  |  | 722.5 |  |  | 694.5 |  |  | 725.5 |  |  | 666.5 |  |  | 639.5 |  |  | 646.5 |  |  | 685 |  |  | 648.5 |  |  | 653 |  |  | 649.5 |  |  | 719.5 |  |  | 644.5 |  |  | 651 |  |  | 664 |  |  | 682.5 |  |  | 665.5 |  |  | 660.5 |  |  | 692.5 |  |  | 626.5 |  |  | 605.5 |  |  | 692.5 |  |  | 588.5 |  |  | 726.5 |  |  | 754.5 |  |  | 609.5 |  |  | 740.5 |  |  | 663.5 |  |  | 654.5 |  |  | 702.5 |  |  | 676.5 |  |  | 661.5 |  |  | 639.5 |  |  | 663.5 |  |  | 706.5 |  |  | 697.5 |  |  | 755.5 |  |  | 699 |  |  | 745.5 |  |  | 640.5 |  |  | 698.5 |  |  | 650 |  |  | 672.5 |  |  | 669.5 |  |  | 670.5 |  |  | 700.5 |  |  | 712 |  |  | 625.5 |  |  | 664.5 |  |  | 645 |  |  | 649 |  |  | 677 |  |  | 707.5 |  |  | 686.5 |  |  | 708.5 |  |  | 673.5 |  |  | 698 |  |  | 719.5 |  |  | 693.5 |  |  | 653 |  |  | 657 |  |  | 677.5 |  |  | 690.5 |  |  | 675 |  |  | 629.5 |  |  | 682 |  |  | 607.5 |  |  | 636.5 |  |  | 616 |  |  | 732.5 |  |  | 622.5 |  |  | 612.5 |  |  | 718 |  |  | 714.5 |  |  | 671.5 |  |  | 642.5 |  |  | 680.5 |  |  | 667.5 |  |  | 699.5 |  |  | 608.5 |  |  | 680.5 |  |  | 689.5 |  |  | 711.5 |  |  | 712 |  |  | 625.5 |  |  | 699.5 |  |  | 689.5 |  |  | 707.5 |  |  | 631.5 |  |  | 751.5 |  |  | 732.5 |  |  | 695.5 |  |  | 730 |  |  | 718.5 |  |  | 676 |  |  | 703.5 |  |  | 751.5 |  |  | 696.5 |  |  | 705.5 |  |  | 719.5 |  |  | 649.5 |  |  | 592.5 |  |  | 721.5 |  |  | 641 |  |  | 654.5 |  |  | 602 |  |  | 655.5 |  |  | 641.5 |  |  | 702.5 |  |  | 766 |  |  | 641.5 |  |  | 711.5 |  |  | 685 |  |  | 659.5 |  |  | 657 |  |  | 654.5 |  |  | 684.5 |  |  | 660.5 |  |  | 669 |  |  | 645.5 |  |  | 755.5 |  |  | 650 |  |  | 711.5 |  |  | 634.5 |  |  | 684 |  |  | 666.5 |  |  | 733.5 |  |  | 662.5 |  |  | 683.5 |  |  | 667.5 |  |  | 649.5 |  |  | 613.5 |  |  | 670.5 |  |  | 581.5 |  |  | 702.5 |  |  | 713.5 |  |  | 650 |  |  | 751 |  |  | 696.5 |  |  | 683.5 |  |  | 740
25 |  | 737.5 |  |  | 795.5 |  |  | 754 |  |  | 686.5 |  |  | 766.5 |  |  | 692.5 |  |  | 790.5 |  |  | 720.5 |  |  | 742.5 |  |  | 716.5 |  |  | 682 |  |  | 762.5 |  |  | 770.5 |  |  | 705.5 |  |  | 654 |  |  | 761.5 |  |  | 747.5 |  |  | 739.5 |  |  | 792.5 |  |  | 622.5 |  |  | 716.5 |  |  | 682.5 |  |  | 703.5 |  |  | 706.5 |  |  | 683 |  |  | 747.5 |  |  | 647.5 |  |  | 740.5 |  |  | 688.5 |  |  | 627 |  |  | 734 |  |  | 717.5 |  |  | 649.5 |  |  | 693.5 |  |  | 612.5 |  |  | 694 |  |  | 740.5 |  |  | 666 |  |  | 684.5 |  |  | 753.5 |  |  | 666.5 |  |  | 728.5 |  |  | 746.5 |  |  | 692 |  |  | 772.5 |  |  | 762 |  |  | 693.5 |  |  | 716.5 |  |  | 692.5 |  |  | 663.5 |  |  | 677.5 |  |  | 704.5 |  |  | 687.5 |  |  | 679.5 |  |  | 719.5 |  |  | 704.5 |  |  | 674.5 |  |  | 715 |  |  | 717.5 |  |  | 675.5 |  |  | 681 |  |  | 639.5 |  |  | 740.5 |  |  | 697.5 |  |  | 674.5 |  |  | 681 |  |  | 711.5 |  |  | 642 |  |  | 678.5 |  |  | 690.5 |  |  | 755 |  |  | 714.5 |  |  | 690.5 |  |  | 744.5 |  |  | 746 |  |  | 673 |  |  | 689.5 |  |  | 653.5 |  |  | 625.5 |  |  | 697.5 |  |  | 702 |  |  | 687.5 |  |  | 713.5 |  |  | 754.5 |  |  | 762.5 |  |  | 773.5 |  |  | 753.5 |  |  | 690.5 |  |  | 657.5 |  |  | 733.5 |  |  | 711.5 |  |  | 690 |  |  | 703.5 |  |  | 673 |  |  | 680 |  |  | 679 |  |  | 726.5 |  |  | 688.5 |  |  | 670.5 |  |  | 661.5 |  |  | 699.5 |  |  | 739 |  |  | 736 |  |  | 715.5 |  |  | 708.5 |  |  | 680.5 |  |  | 694.5 |  |  | 778.5 |  |  | 729.5 |  |  | 709.5 |  |  | 750.5 |  |  | 710.5 |  |  | 739.5 |  |  | 730.5 |  |  | 748.5 |  |  | 720.5 |  |  | 733.5 |  |  | 673.5 |  |  | 730.5 |  |  | 794.5 |  |  | 729.5 |  |  | 716.5 |  |  | 719.5 |  |  | 742.5 |  |  | 688.5 |  |  | 782 |  |  | 695.5 |  |  | 733.5 |  |  | 652.5 |  |  | 654.5 |  |  | 757.5 |  |  | 670 |  |  | 681.5 |  |  | 767.5 |  |  | 643.5 |  |  | 752.5 |  |  | 697 |  |  | 716.5 |  |  | 739.5 |  |  | 701 |  |  | 690.5 |  |  | 664 |  |  | 706 |  |  | 752.5 |  |  | 718 |  |  | 744.5 |  |  | 676.5 |  |  | 749.5 |  |  | 687.5 |  |  | 730.5 |  |  | 731.5 |  |  | 698.5 |  |  | 712.5 |  |  | 794.5 |  |  | 765.5 |  |  | 711 |  |  | 644.5 |  |  | 645 |  |  | 677.5 |  |  | 715.5 |  |  | 724 |  |  | 709.5 |  |  | 694.5 |  |  | 688.5 |  |  | 679 |  |  | 703.5 |  |  | 674.5 |  |  | 718.5 |  |  | 716.5 |  |  | 690.5 |  |  | 677.5 |  |  | 658 |  |  | 664.5 |  |  | 706.5 |  |  | 649.5 |  |  | 697.5 |  |  | 716.5 |  |  | 728.5 |  |  | 707.5 |  |  | 732 |  |  | 725.5 |  |  | 694.5 |  |  | 688.5 |  |  | 703.5 |  |  | 634.5 |  |  | 759.5 |  |  | 733.5 |  |  | 753.5 |  |  | 707.5 |  |  | 687.5 |  |  | 729.5 |  |  | 595.5 |  |  | 662.5 |  |  | 704 |  |  | 721.5 |  |  | 718.5 |  |  | 662.5 |  |  | 699.5 |  |  | 774.5 |  |  | 734.5 |  |  | 730.5 |  |  | 692.5 |  |  | 631.5 |  |  | 730.5 |  |  | 685.5 |  |  | 779.5 |  |  | 657.5 |  |  | 664.5 |  |  | 730.5 |  |  | 739.5 |  |  | 702 |  |  | 739.5 |  |  | 697.5 |  |  | 688 |  |  | 753.5 |  |  | 689 |  |  | 667.5 |  |  | 735.5 |  |  | 792.5 |  |  | 735.5 |  |  | 680.5 |  |  | 685.5 |  |  | 685.5 |  |  | 671.5 |  |  | 677 |  |  | 653.5 |  |  | 618.5 |  |  | 698.5 |  |  | 730.5 |  |  | 722 |  |  | 625.5 |  |  | 642.5 |  |  | 704.5 |  |  | 786.5 |  |  | 767.5 |  |  | 684.5 |  |  | 675.5 |  |  | 747.5 |  |  | 693 |  |  | 749 |  |  | 667.5 |  |  | 697.5 |  |  | 751.5 |  |  | 757 |  |  | 724.5 |  |  | 727.5 |  |  | 726.5 |  |  | 688 |  |  | 674.5 |  |  | 701.5 |  |  | 683.5 |  |  | 630.5 |  |  | 692.5 |  |  | 676.5 |  |  | 751.5 |  |  | 687.5 |  |  | 716.5 |  |  | 640 |  |  | 652.5 |  |  | 705.5 |  |  | 692.5 |  |  | 686.5 |  |  | 713.5 |  |  | 734 |  |  | 736.5 |  |  | 747.5 |  |  | 679 |  |  | 730.5 |  |  | 690.5 |  |  | 759 |  |  | 696.5 |  |  | 655.5 |  |  | 838.5 |  |  | 664.5 |  |  | 749 |  |  | 734 |  |  | 709.5 |  |  | 737.5 |  |  | 711.5 |  |  | 696.5 |  |  | 773.5 |  |  | 683.5 |  |  | 683 |  |  | 720.5 |  |  | 722.5 |  |  | 700 |  |  | 693.5 |  |  | 706.5 |  |  | 643 |  |  | 730.5 |  |  | 668.5 |  |  | 723.5 |  |  | 733 |  |  | 736.5 |  |  | 686 |  |  | 739.5 |  |  | 660.5 |  |  | 729.5 |  |  | 638 |  |  | 679.5 |  |  | 708.5 |  |  | 658.5 |  |  | 714 |  |  | 642.5 |  |  | 699.5 |  |  | 756.5 |  |  | 704.5 |  |  | 680.5 |  |  | 696 |  |  | 671.5 |  |  | 755.5 |  |  | 810.5 |  |  | 655 |  |  | 770 |  |  | 773.5 |  |  | 739.5 |  |  | 676.5 |  |  | 742.5 |  |  | 719.5 |  |  | 708.5 |  |  | 673.5 |  |  | 737.5 |  |  | 669.5 |  |  | 691.5 |  |  | 687 |  |  | 709.5 |  |  | 739.5 |  |  | 745.5 |  |  | 779.5 |  |  | 726 |  |  | 742.5 |  |  | 704.5 |  |  | 722.5 |  |  | 654.5 |  |  | 706.5 |  |  | 683 |  |  | 704 |  |  | 638 |  |  | 705 |  |  | 664.5 |  |  | 756 |  |  | 680.5 |  |  | 675 |  |  | 723.5 |  |  | 747.5 |  |  | 689.5 |  |  | 694.5 |  |  | 757.5 |  |  | 746 |  |  | 643.5 |  |  | 735.5 |  |  | 646.5 |  |  | 739 |  |  | 712.5 |  |  | 694.5 |  |  | 691.5 |  |  | 768 |  |  | 705.5 |  |  | 633.5 |  |  | 672.5 |  |  | 684.5 |  |  | 714.5 |  |  | 669.5 |  |  | 817.5 |  |  | 672.5 |  |  | 648.5 |  |  | 649.5 |  |  | 639 |  |  | 668.5 |  |  | 761.5 |  |  | 714.5 |  |  | 714.5 |  |  | 772.5 |  |  | 679 |  |  | 627.5 |  |  | 713 |  |  | 705 |  |  | 700.5 |  |  | 743.5 |  |  | 703.5 |  |  | 717 |  |  | 753.5 |  |  | 734.5 |  |  | 695.5 |  |  | 656 |  |  | 667.5 |  |  | 615.5 |  |  | 757.5 |  |  | 675.5 |  |  | 657.5 |  |  | 690 |  |  | 702.5 |  |  | 716 |  |  | 705.5 |  |  | 670.5 |  |  | 750.5 |  |  | 791 |  |  | 664.5 |  |  | 729 |  |  | 752 |  |  | 692.5 |  |  | 676.5 |  |  | 687.5 |  |  | 731.5 |  |  | 741 |  |  | 711.5 |  |  | 710.5 |  |  | 642.5 |  |  | 701 |  |  | 762.5 |  |  | 629.5 |  |  | 658.5 |  |  | 732.5 |  |  | 676 |  |  | 624.5 |  |  | 657.5 |  |  | 716.5 |  |  | 686.5 |  |  | 744.5 |  |  | 738.5 |  |  | 752 |  |  | 709.5 |  |  | 680.5 |  |  | 722 |  |  | 674.5 |  |  | 688.5 |  |  | 702.5 |  |  | 738 |  |  | 702.5 |  |  | 711.5 |  |  | 741.5 |  |  | 738.5 |  |  | 691.5 |  |  | 777 |  |  | 679 |  |  | 702.5 |  |  | 695.5 |  |  | 731.5 |  |  | 693.5 |  |  | 683 |  |  | 723 |  |  | 690 |  |  | 748.5 |  |  | 703 |  |  | 760.5 |  |  | 732.5 |  |  | 717 |  |  | 604.5 |  |  | 715.5 |  |  | 678.5 |  |  | 788.5 |  |  | 643.5 |  |  | 671 |  |  | 723 |  |  | 628.5 |  |  | 675.5 |  |  | 703 |  |  | 617.5 |  |  | 781.5 |  |  | 705 |  |  | 785.5 |  |  | 809.5 |  |  | 629 |  |  | 737.5 |  |  | 724.5 |  |  | 676 |  |  | 702.5 |  |  | 624 |  |  | 720.5 |  |  | 733 |  |  | 658.5 |  |  | 722.5 |  |  | 703.5 |  |  | 713.5 |  |  | 684.5 |  |  | 746.5 |  |  | 768 |  |  | 716.5 |  |  | 764.5 |  |  | 687.5 |  |  | 798.5 |  |  | 679.5 |  |  | 671 |  |  | 676.5 |  |  | 714 |  |  | 750.5 |  |  | 696.5 |  |  | 726.5 |  |  | 661.5 |  |  | 673.5 |  |  | 695.5 |  |  | 642.5 |  |  | 756.5 |  |  | 699.5 |  |  | 734 |  |  | 705.5 |  |  | 659 |  |  | 699 |  |  | 670.5 |  |  | 640 |  |  | 681.5 |  |  | 679.5 |  |  | 699.5 |  |  | 688.5 |  |  | 720.5 |  |  | 754.5 |  |  | 768.5 |  |  | 718 |  |  | 765 |  |  | 667.5 |  |  | 698.5 |  |  | 649 |  |  | 655.5 |  |  | 710.5 |  |  | 670.5 |  |  | 636.5 |  |  | 710.5 |  |  | 704 |  |  | 682.5 |  |  | 707.5 |  |  | 712.5 |  |  | 716 |  |  | 707.5 |  |  | 752.5 |  |  | 756.5 |  |  | 777.5 |  |  | 740.5 |  |  | 671.5 |  |  | 750.5 |  |  | 625.5 |  |  | 711.5 |  |  | 680 |  |  | 722.5 |  |  | 701.5 |  |  | 717.5 |  |  | 715.5 |  |  | 652.5 |  |  | 662.5 |  |  | 690.5 |  |  | 681 |  |  | 689.5 |  |  | 718.5 |  |  | 722.5 |  |  | 638 |  |  | 698.5 |  |  | 654 |  |  | 718.5 |  |  | 694.5 |  |  | 690.5 |  |  | 705 |  |  | 658.5 |  |  | 702 |  |  | 714 |  |  | 741.5 |  |  | 683 |  |  | 713 |  |  | 782.5 |  |  | 743.5 |  |  | 729.5 |  |  | 715 |  |  | 723.5 |  |  | 705.5 |  |  | 657.5 |  |  | 758.5 |  |  | 683.5 |  |  | 717.5 |  |  | 698.5 |  |  | 725.5 |  |  | 695 |  |  | 808.5 |  |  | 619 |  |  | 726.5 |  |  | 582.5 |  |  | 768.5 |  |  | 710 |  |  | 738 |  |  | 771 |  |  | 728.5 |  |  | 702 |  |  | 702.5 |  |  | 752.5 |  |  | 640.5 |  |  | 720.5 |  |  | 738.5 |  |  | 761.5 |  |  | 707.5 |  |  | 665.5 |  |  | 753 |  |  | 657.5 |  |  | 646.5 |  |  | 713.5 |  |  | 682.5 |  |  | 620 |  |  | 693.5 |  |  | 778 |  |  | 681.5 |  |  | 683.5 |  |  | 705.5 |  |  | 687.5 |  |  | 694 |  |  | 654.5 |  |  | 659 |  |  | 713.5 |  |  | 719.5 |  |  | 792.5 |  |  | 672.5 |  |  | 703.5 |  |  | 738.5 |  |  | 706.5 |  |  | 699.5 |  |  | 631.5 |  |  | 779 |  |  | 719.5 |  |  | 654.5 |  |  | 673.5 |  |  | 704.5 |  |  | 698.5 |  |  | 652 |  |  | 667 |  |  | 702.5 |  |  | 672 |  |  | 730.5 |  |  | 735.5 |  |  | 734.5 |  |  | 775.5 |  |  | 719.5 |  |  | 713.5 |  |  | 686.5 |  |  | 774.5 |  |  | 662 |  |  | 769.5 |  |  | 774.5 |  |  | 761.5 |  |  | 695 |  |  | 748.5 |  |  | 675.5 |  |  | 781 |  |  | 645 |  |  | 713.5 |  |  | 632 |  |  | 670 |  |  | 670.5 |  |  | 648 |  |  | 765.5 |  |  | 759.5 |  |  | 693.5 |  |  | 697.5 |  |  | 651.5 |  |  | 725.5 |  |  | 592.5 |  |  | 727.5 |  |  | 681.5 |  |  | 681.5 |  |  | 737 |  |  | 685 |  |  | 683.5 |  |  | 654.5 |  |  | 704.5 |  |  | 711.5 |  |  | 667.5 |  |  | 770.5 |  |  | 739.5 |  |  | 646.5 |  |  | 717 |  |  | 647.5 |  |  | 652 |  |  | 675.5 |  |  | 812.5 |  |  | 730.5 |  |  | 800 |  |  | 658.5 |  |  | 708.5 |  |  | 583 |  |  | 727.5 |  |  | 647.5 |  |  | 698.5 |  |  | 729.5 |  |  | 688.5 |  |  | 646.5 |  |  | 640 |  |  | 756.5 |  |  | 657.5 |  |  | 735.5 |  |  | 759.5 |  |  | 691 |  |  | 649.5 |  |  | 741.5 |  |  | 659 |  |  | 724.5 |  |  | 713.5 |  |  | 684 |  |  | 701.5 |  |  | 653.5 |  |  | 735.5 |  |  | 682 |  |  | 654.5 |  |  | 680.5 |  |  | 663 |  |  | 671.5 |  |  | 718.5 |  |  | 671.5 |  |  | 624.5 |  |  | 783.5 |  |  | 782.5 |  |  | 676.5 |  |  | 725 |  |  | 686 |  |  | 630.5 |  |  | 701.5 |  |  | 670.5 |  |  | 730 |  |  | 762.5 |  |  | 720.5 |  |  | 759.5 |  |  | 690.5 |  |  | 724.5 |  |  | 699.5 |  |  | 608.5 |  |  | 697.5 |  |  | 642.5 |  |  | 700 |  |  | 705.5 |  |  | 684.5 |  |  | 671.5 |  |  | 734.5 |  |  | 742.5 |  |  | 680.5 |  |  | 709.5 |  |  | 743.5 |  |  | 701.5 |  |  | 681.5 |  |  | 660.5 |  |  | 688.5 |  |  | 731.5 |  |  | 785 |  |  | 706.5 |  |  | 730.5 |  |  | 675 |  |  | 690.5 |  |  | 717.5 |  |  | 764 |  |  | 700.5 |  |  | 740.5 |  |  | 763.5 |  |  | 743 |  |  | 681.5 |  |  | 692.5 |  |  | 701.5 |  |  | 596.5 |  |  | 745.5 |  |  | 680 |  |  | 662.5 |  |  | 739 |  |  | 673 |  |  | 754.5 |  |  | 705.5 |  |  | 696.5 |  |  | 648.5 |  |  | 718.5 |  |  | 682.5 |  |  | 698 |  |  | 684.5 |  |  | 752 |  |  | 689.5 |  |  | 725 |  |  | 701 |  |  | 757 |  |  | 642.5 |  |  | 648 |  |  | 736.5 |  |  | 810.5 |  |  | 720.5 |  |  | 814.5 |  |  | 724.5 |  |  | 716 |  |  | 732.5 |  |  | 736.5 |  |  | 776.5 |  |  | 776 |  |  | 719.5 |  |  | 734.5 |  |  | 737.5 |  |  | 710.5 |  |  | 635 |  |  | 697 |  |  | 670 |  |  | 741.5 |  |  | 710 |  |  | 691 |  |  | 752.5 |  |  | 709.5 |  |  | 631.5 |  |  | 681.5 |  |  | 757.5 |  |  | 771.5 |  |  | 690.5 |  |  | 755.5 |  |  | 676.5 |  |  | 639 |  |  | 763.5 |  |  | 718 |  |  | 726.5 |  |  | 674.5 |  |  | 773.5 |  |  | 705.5 |  |  | 675 |  |  | 693.5 |  |  | 709 |  |  | 682.5 |  |  | 656.5 |  |  | 632 |  |  | 764 |  |  | 736.5 |  |  | 708 |  |  | 740.5 |  |  | 605.5 |  |  | 716.5 |  |  | 711.5 |  |  | 725.5 |  |  | 716.5 |  |  | 682.5 |  |  | 671 |  |  | 685.5 |  |  | 723.5 |  |  | 643.5 |  |  | 692.5 |  |  | 736.5 |  |  | 713.5 |  |  | 730.5 |  |  | 662.5 |  |  | 686.5 |  |  | 734.5 |  |  | 746.5 |  |  | 666.5 |  |  | 791 |  |  | 652.5 |  |  | 672.5 |  |  | 765 |  |  | 670.5 |  |  | 629.5 |  |  | 683.5 |  |  | 709.5 |  |  | 715 |  |  | 737.5 |  |  | 699.5 |  |  | 683.5 |  |  | 726.5 |  |  | 699 |  |  | 699.5 |  |  | 700.5 |  |  | 669.5 |  |  | 743.5 |  |  | 735.5 |  |  | 681.5 |  |  | 743.5 |  |  | 733.5 |  |  | 726.5 |  |  | 670.5 |  |  | 799.5 |  |  | 745 |  |  | 743.5 |  |  | 715.5 |  |  | 772.5 |  |  | 705.5 |  |  | 654.5 |  |  | 667.5 |  |  | 714 |  |  | 674.5 |  |  | 700 |  |  | 678.5 |  |  | 745.5 |  |  | 668.5 |  |  | 680 |  |  | 679 |  |  | 706.5 |  |  | 704.5 |  |  | 681.5 |  |  | 707.5 |  |  | 650.5 |  |  | 644.5 |  |  | 716.5 |  |  | 627.5 |  |  | 752.5 |  |  | 793.5 |  |  | 648.5 |  |  | 766.5 |  |  | 692.5 |  |  | 680.5 |  |  | 726.5 |  |  | 702.5 |  |  | 682.5 |  |  | 654.5 |  |  | 702.5 |  |  | 727.5 |  |  | 721.5 |  |  | 784.5 |  |  | 738 |  |  | 784.5 |  |  | 664.5 |  |  | 722.5 |  |  | 697 |  |  | 711.5 |  |  | 708.5 |  |  | 694.5 |  |  | 715.5 |  |  | 736 |  |  | 654.5 |  |  | 703.5 |  |  | 674 |  |  | 664 |  |  | 716 |  |  | 733.5 |  |  | 733.5 |  |  | 734.5 |  |  | 720.5 |  |  | 727 |  |  | 734.5 |  |  | 722.5 |  |  | 668 |  |  | 681 |  |  | 716.5 |  |  | 737.5 |  |  | 701 |  |  | 658.5 |  |  | 729 |  |  | 628.5 |  |  | 675.5 |  |  | 655 |  |  | 747.5 |  |  | 669.5 |  |  | 641.5 |  |  | 765 |  |  | 740.5 |  |  | 718.5 |  |  | 657.5 |  |  | 701.5 |  |  | 714.5 |  |  | 723.5 |  |  | 629.5 |  |  | 701.5 |  |  | 715.5 |  |  | 726.5 |  |  | 733 |  |  | 664.5 |  |  | 746.5 |  |  | 728.5 |  |  | 722.5 |  |  | 678.5 |  |  | 780.5 |  |  | 771.5 |  |  | 734.5 |  |  | 769 |  |  | 744.5 |  |  | 705 |  |  | 729.5 |  |  | 777.5 |  |  | 711.5 |  |  | 731.5 |  |  | 745.5 |  |  | 670.5 |  |  | 613.5 |  |  | 745.5 |  |  | 667 |  |  | 693.5 |  |  | 626 |  |  | 681.5 |  |  | 665.5 |  |  | 741.5 |  |  | 790 |  |  | 680.5 |  |  | 735.5 |  |  | 724 |  |  | 706.5 |  |  | 678 |  |  | 678.5 |  |  | 723.5 |  |  | 699.5 |  |  | 684 |  |  | 674.5 |  |  | 802.5 |  |  | 665 |  |  | 750.5 |  |  | 649.5 |  |  | 723 |  |  | 681.5 |  |  | 780.5 |  |  | 701.5 |  |  | 709.5 |  |  | 691.5 |  |  | 678.5 |  |  | 639.5 |  |  | 694.5 |  |  | 605.5 |  |  | 726.5 |  |  | 752.5 |  |  | 676 |  |  | 790 |  |  | 717.5 |  |  | 722.5 |  |  | 766
26 |  | 758.5 |  |  | 834.5 |  |  | 778 |  |  | 725.5 |  |  | 792.5 |  |  | 731.5 |  |  | 837.5 |  |  | 735.5 |  |  | 757.5 |  |  | 737.5 |  |  | 721 |  |  | 791.5 |  |  | 796.5 |  |  | 744.5 |  |  | 678 |  |  | 787.5 |  |  | 768.5 |  |  | 778.5 |  |  | 807.5 |  |  | 651.5 |  |  | 740.5 |  |  | 706.5 |  |  | 750.5 |  |  | 735.5 |  |  | 707 |  |  | 768.5 |  |  | 671.5 |  |  | 755.5 |  |  | 709.5 |  |  | 651 |  |  | 760 |  |  | 741.5 |  |  | 664.5 |  |  | 740.5 |  |  | 633.5 |  |  | 709 |  |  | 766.5 |  |  | 713 |  |  | 713.5 |  |  | 768.5 |  |  | 692.5 |  |  | 754.5 |  |  | 770.5 |  |  | 718 |  |  | 819.5 |  |  | 809 |  |  | 717.5 |  |  | 740.5 |  |  | 716.5 |  |  | 710.5 |  |  | 724.5 |  |  | 719.5 |  |  | 713.5 |  |  | 726.5 |  |  | 748.5 |  |  | 725.5 |  |  | 698.5 |  |  | 739 |  |  | 743.5 |  |  | 704.5 |  |  | 728 |  |  | 668.5 |  |  | 779.5 |  |  | 736.5 |  |  | 700.5 |  |  | 720 |  |  | 740.5 |  |  | 657 |  |  | 717.5 |  |  | 737.5 |  |  | 794 |  |  | 740.5 |  |  | 705.5 |  |  | 773.5 |  |  | 793 |  |  | 712 |  |  | 710.5 |  |  | 692.5 |  |  | 646.5 |  |  | 723.5 |  |  | 726 |  |  | 708.5 |  |  | 752.5 |  |  | 775.5 |  |  | 783.5 |  |  | 802.5 |  |  | 782.5 |  |  | 711.5 |  |  | 696.5 |  |  | 759.5 |  |  | 726.5 |  |  | 711 |  |  | 724.5 |  |  | 712 |  |  | 719 |  |  | 718 |  |  | 765.5 |  |  | 714.5 |  |  | 694.5 |  |  | 708.5 |  |  | 746.5 |  |  | 765 |  |  | 775 |  |  | 739.5 |  |  | 723.5 |  |  | 701.5 |  |  | 720.5 |  |  | 804.5 |  |  | 768.5 |  |  | 756.5 |  |  | 779.5 |  |  | 739.5 |  |  | 786.5 |  |  | 777.5 |  |  | 787.5 |  |  | 735.5 |  |  | 754.5 |  |  | 720.5 |  |  | 754.5 |  |  | 818.5 |  |  | 758.5 |  |  | 745.5 |  |  | 745.5 |  |  | 771.5 |  |  | 717.5 |  |  | 808 |  |  | 710.5 |  |  | 759.5 |  |  | 678.5 |  |  | 701.5 |  |  | 796.5 |  |  | 694 |  |  | 707.5 |  |  | 793.5 |  |  | 682.5 |  |  | 791.5 |  |  | 721 |  |  | 742.5 |  |  | 768.5 |  |  | 740 |  |  | 729.5 |  |  | 690 |  |  | 732 |  |  | 791.5 |  |  | 742 |  |  | 783.5 |  |  | 723.5 |  |  | 764.5 |  |  | 708.5 |  |  | 745.5 |  |  | 778.5 |  |  | 745.5 |  |  | 727.5 |  |  | 818.5 |  |  | 789.5 |  |  | 726 |  |  | 670.5 |  |  | 669 |  |  | 701.5 |  |  | 754.5 |  |  | 750 |  |  | 724.5 |  |  | 715.5 |  |  | 727.5 |  |  | 718 |  |  | 729.5 |  |  | 689.5 |  |  | 747.5 |  |  | 731.5 |  |  | 729.5 |  |  | 703.5 |  |  | 682 |  |  | 703.5 |  |  | 735.5 |  |  | 688.5 |  |  | 723.5 |  |  | 763.5 |  |  | 767.5 |  |  | 722.5 |  |  | 779 |  |  | 746.5 |  |  | 715.5 |  |  | 735.5 |  |  | 742.5 |  |  | 649.5 |  |  | 798.5 |  |  | 754.5 |  |  | 782.5 |  |  | 728.5 |  |  | 711.5 |  |  | 744.5 |  |  | 624.5 |  |  | 683.5 |  |  | 743 |  |  | 742.5 |  |  | 747.5 |  |  | 677.5 |  |  | 728.5 |  |  | 821.5 |  |  | 773.5 |  |  | 756.5 |  |  | 707.5 |  |  | 670.5 |  |  | 745.5 |  |  | 706.5 |  |  | 805.5 |  |  | 696.5 |  |  | 688.5 |  |  | 759.5 |  |  | 778.5 |  |  | 728 |  |  | 765.5 |  |  | 744.5 |  |  | 703 |  |  | 782.5 |  |  | 710 |  |  | 696.5 |  |  | 774.5 |  |  | 831.5 |  |  | 750.5 |  |  | 695.5 |  |  | 724.5 |  |  | 732.5 |  |  | 686.5 |  |  | 706 |  |  | 679.5 |  |  | 644.5 |  |  | 727.5 |  |  | 754.5 |  |  | 761 |  |  | 646.5 |  |  | 657.5 |  |  | 743.5 |  |  | 825.5 |  |  | 793.5 |  |  | 710.5 |  |  | 699.5 |  |  | 794.5 |  |  | 740 |  |  | 796 |  |  | 696.5 |  |  | 744.5 |  |  | 775.5 |  |  | 772 |  |  | 753.5 |  |  | 748.5 |  |  | 773.5 |  |  | 709 |  |  | 713.5 |  |  | 748.5 |  |  | 709.5 |  |  | 651.5 |  |  | 716.5 |  |  | 697.5 |  |  | 775.5 |  |  | 708.5 |  |  | 755.5 |  |  | 679 |  |  | 676.5 |  |  | 729.5 |  |  | 713.5 |  |  | 725.5 |  |  | 742.5 |  |  | 781 |  |  | 760.5 |  |  | 768.5 |  |  | 718 |  |  | 777.5 |  |  | 714.5 |  |  | 788 |  |  | 717.5 |  |  | 679.5 |  |  | 862.5 |  |  | 690.5 |  |  | 773 |  |  | 781 |  |  | 748.5 |  |  | 752.5 |  |  | 758.5 |  |  | 722.5 |  |  | 794.5 |  |  | 707.5 |  |  | 709 |  |  | 735.5 |  |  | 748.5 |  |  | 747 |  |  | 717.5 |  |  | 721.5 |  |  | 667 |  |  | 769.5 |  |  | 683.5 |  |  | 762.5 |  |  | 754 |  |  | 760.5 |  |  | 725 |  |  | 778.5 |  |  | 681.5 |  |  | 755.5 |  |  | 685 |  |  | 708.5 |  |  | 734.5 |  |  | 687.5 |  |  | 735 |  |  | 663.5 |  |  | 723.5 |  |  | 785.5 |  |  | 733.5 |  |  | 701.5 |  |  | 725 |  |  | 718.5 |  |  | 770.5 |  |  | 849.5 |  |  | 694 |  |  | 799 |  |  | 820.5 |  |  | 765.5 |  |  | 705.5 |  |  | 781.5 |  |  | 740.5 |  |  | 737.5 |  |  | 699.5 |  |  | 776.5 |  |  | 693.5 |  |  | 720.5 |  |  | 713 |  |  | 748.5 |  |  | 768.5 |  |  | 774.5 |  |  | 818.5 |  |  | 752 |  |  | 766.5 |  |  | 728.5 |  |  | 751.5 |  |  | 678.5 |  |  | 721.5 |  |  | 722 |  |  | 725 |  |  | 659 |  |  | 731 |  |  | 685.5 |  |  | 803 |  |  | 727.5 |  |  | 699 |  |  | 762.5 |  |  | 762.5 |  |  | 710.5 |  |  | 718.5 |  |  | 783.5 |  |  | 767 |  |  | 669.5 |  |  | 750.5 |  |  | 667.5 |  |  | 765 |  |  | 738.5 |  |  | 715.5 |  |  | 717.5 |  |  | 807 |  |  | 726.5 |  |  | 680.5 |  |  | 719.5 |  |  | 708.5 |  |  | 735.5 |  |  | 695.5 |  |  | 832.5 |  |  | 693.5 |  |  | 687.5 |  |  | 688.5 |  |  | 665 |  |  | 707.5 |  |  | 785.5 |  |  | 738.5 |  |  | 738.5 |  |  | 811.5 |  |  | 705 |  |  | 666.5 |  |  | 752 |  |  | 752 |  |  | 715.5 |  |  | 790.5 |  |  | 718.5 |  |  | 741 |  |  | 782.5 |  |  | 763.5 |  |  | 716.5 |  |  | 677 |  |  | 691.5 |  |  | 644.5 |  |  | 796.5 |  |  | 699.5 |  |  | 696.5 |  |  | 714 |  |  | 717.5 |  |  | 755 |  |  | 744.5 |  |  | 709.5 |  |  | 776.5 |  |  | 838 |  |  | 685.5 |  |  | 768 |  |  | 776 |  |  | 713.5 |  |  | 715.5 |  |  | 726.5 |  |  | 778.5 |  |  | 780 |  |  | 740.5 |  |  | 734.5 |  |  | 671.5 |  |  | 730 |  |  | 801.5 |  |  | 650.5 |  |  | 679.5 |  |  | 756.5 |  |  | 715 |  |  | 653.5 |  |  | 686.5 |  |  | 755.5 |  |  | 725.5 |  |  | 759.5 |  |  | 764.5 |  |  | 778 |  |  | 756.5 |  |  | 695.5 |  |  | 737 |  |  | 698.5 |  |  | 703.5 |  |  | 723.5 |  |  | 777 |  |  | 726.5 |  |  | 750.5 |  |  | 767.5 |  |  | 759.5 |  |  | 738.5 |  |  | 816 |  |  | 705 |  |  | 728.5 |  |  | 742.5 |  |  | 752.5 |  |  | 732.5 |  |  | 712 |  |  | 762 |  |  | 714 |  |  | 787.5 |  |  | 727 |  |  | 799.5 |  |  | 756.5 |  |  | 764 |  |  | 651.5 |  |  | 741.5 |  |  | 699.5 |  |  | 827.5 |  |  | 690.5 |  |  | 710 |  |  | 749 |  |  | 657.5 |  |  | 701.5 |  |  | 727 |  |  | 641.5 |  |  | 810.5 |  |  | 744 |  |  | 809.5 |  |  | 848.5 |  |  | 644 |  |  | 766.5 |  |  | 771.5 |  |  | 723 |  |  | 726.5 |  |  | 671 |  |  | 759.5 |  |  | 772 |  |  | 687.5 |  |  | 751.5 |  |  | 750.5 |  |  | 734.5 |  |  | 710.5 |  |  | 772.5 |  |  | 797 |  |  | 737.5 |  |  | 790.5 |  |  | 716.5 |  |  | 819.5 |  |  | 718.5 |  |  | 718 |  |  | 715.5 |  |  | 729 |  |  | 771.5 |  |  | 717.5 |  |  | 765.5 |  |  | 690.5 |  |  | 712.5 |  |  | 710.5 |  |  | 663.5 |  |  | 785.5 |  |  | 720.5 |  |  | 773 |  |  | 744.5 |  |  | 698 |  |  | 728 |  |  | 696.5 |  |  | 661 |  |  | 720.5 |  |  | 705.5 |  |  | 738.5 |  |  | 727.5 |  |  | 759.5 |  |  | 769.5 |  |  | 815.5 |  |  | 742 |  |  | 780 |  |  | 682.5 |  |  | 719.5 |  |  | 673 |  |  | 694.5 |  |  | 749.5 |  |  | 699.5 |  |  | 657.5 |  |  | 725.5 |  |  | 725 |  |  | 711.5 |  |  | 746.5 |  |  | 741.5 |  |  | 755 |  |  | 746.5 |  |  | 791.5 |  |  | 795.5 |  |  | 792.5 |  |  | 766.5 |  |  | 697.5 |  |  | 789.5 |  |  | 640.5 |  |  | 735.5 |  |  | 706 |  |  | 746.5 |  |  | 730.5 |  |  | 756.5 |  |  | 754.5 |  |  | 681.5 |  |  | 701.5 |  |  | 705.5 |  |  | 705 |  |  | 713.5 |  |  | 765.5 |  |  | 761.5 |  |  | 664 |  |  | 713.5 |  |  | 701 |  |  | 747.5 |  |  | 723.5 |  |  | 716.5 |  |  | 729 |  |  | 682.5 |  |  | 731 |  |  | 753 |  |  | 780.5 |  |  | 712 |  |  | 734 |  |  | 806.5 |  |  | 790.5 |  |  | 744.5 |  |  | 741 |  |  | 752.5 |  |  | 752.5 |  |  | 672.5 |  |  | 773.5 |  |  | 730.5 |  |  | 764.5 |  |  | 713.5 |  |  | 751.5 |  |  | 716 |  |  | 847.5 |  |  | 634 |  |  | 755.5 |  |  | 608.5 |  |  | 792.5 |  |  | 731 |  |  | 753 |  |  | 797 |  |  | 775.5 |  |  | 741 |  |  | 731.5 |  |  | 799.5 |  |  | 669.5 |  |  | 746.5 |  |  | 759.5 |  |  | 782.5 |  |  | 731.5 |  |  | 704.5 |  |  | 792 |  |  | 678.5 |  |  | 661.5 |  |  | 739.5 |  |  | 706.5 |  |  | 659 |  |  | 732.5 |  |  | 793 |  |  | 710.5 |  |  | 704.5 |  |  | 744.5 |  |  | 708.5 |  |  | 733 |  |  | 683.5 |  |  | 685 |  |  | 734.5 |  |  | 758.5 |  |  | 816.5 |  |  | 711.5 |  |  | 742.5 |  |  | 753.5 |  |  | 735.5 |  |  | 738.5 |  |  | 657.5 |  |  | 803 |  |  | 740.5 |  |  | 675.5 |  |  | 694.5 |  |  | 751.5 |  |  | 737.5 |  |  | 681 |  |  | 706 |  |  | 749.5 |  |  | 693 |  |  | 769.5 |  |  | 759.5 |  |  | 758.5 |  |  | 801.5 |  |  | 758.5 |  |  | 739.5 |  |  | 710.5 |  |  | 789.5 |  |  | 701 |  |  | 784.5 |  |  | 803.5 |  |  | 782.5 |  |  | 719 |  |  | 795.5 |  |  | 699.5 |  |  | 805 |  |  | 671 |  |  | 760.5 |  |  | 656 |  |  | 709 |  |  | 699.5 |  |  | 695 |  |  | 789.5 |  |  | 774.5 |  |  | 740.5 |  |  | 736.5 |  |  | 666.5 |  |  | 740.5 |  |  | 607.5 |  |  | 766.5 |  |  | 702.5 |  |  | 720.5 |  |  | 776 |  |  | 714 |  |  | 698.5 |  |  | 693.5 |  |  | 730.5 |  |  | 758.5 |  |  | 696.5 |  |  | 796.5 |  |  | 754.5 |  |  | 685.5 |  |  | 764 |  |  | 671.5 |  |  | 699 |  |  | 690.5 |  |  | 851.5 |  |  | 769.5 |  |  | 815 |  |  | 697.5 |  |  | 747.5 |  |  | 622 |  |  | 751.5 |  |  | 694.5 |  |  | 737.5 |  |  | 750.5 |  |  | 703.5 |  |  | 672.5 |  |  | 655 |  |  | 795.5 |  |  | 672.5 |  |  | 782.5 |  |  | 785.5 |  |  | 715 |  |  | 688.5 |  |  | 770.5 |  |  | 685 |  |  | 748.5 |  |  | 734.5 |  |  | 723 |  |  | 730.5 |  |  | 700.5 |  |  | 759.5 |  |  | 708 |  |  | 669.5 |  |  | 727.5 |  |  | 702 |  |  | 710.5 |  |  | 742.5 |  |  | 692.5 |  |  | 645.5 |  |  | 798.5 |  |  | 821.5 |  |  | 715.5 |  |  | 764 |  |  | 733 |  |  | 659.5 |  |  | 740.5 |  |  | 694.5 |  |  | 751 |  |  | 777.5 |  |  | 741.5 |  |  | 785.5 |  |  | 711.5 |  |  | 745.5 |  |  | 725.5 |  |  | 637.5 |  |  | 736.5 |  |  | 689.5 |  |  | 721 |  |  | 720.5 |  |  | 723.5 |  |  | 692.5 |  |  | 773.5 |  |  | 789.5 |  |  | 706.5 |  |  | 730.5 |  |  | 767.5 |  |  | 722.5 |  |  | 696.5 |  |  | 675.5 |  |  | 714.5 |  |  | 752.5 |  |  | 811 |  |  | 727.5 |  |  | 754.5 |  |  | 714 |  |  | 729.5 |  |  | 741.5 |  |  | 811 |  |  | 721.5 |  |  | 755.5 |  |  | 802.5 |  |  | 782 |  |  | 707.5 |  |  | 716.5 |  |  | 722.5 |  |  | 611.5 |  |  | 760.5 |  |  | 706 |  |  | 709.5 |  |  | 786 |  |  | 712 |  |  | 769.5 |  |  | 752.5 |  |  | 720.5 |  |  | 677.5 |  |  | 742.5 |  |  | 729.5 |  |  | 713 |  |  | 708.5 |  |  | 776 |  |  | 728.5 |  |  | 740 |  |  | 748 |  |  | 778 |  |  | 689.5 |  |  | 672 |  |  | 783.5 |  |  | 834.5 |  |  | 746.5 |  |  | 861.5 |  |  | 771.5 |  |  | 755 |  |  | 771.5 |  |  | 760.5 |  |  | 802.5 |  |  | 800 |  |  | 745.5 |  |  | 763.5 |  |  | 766.5 |  |  | 749.5 |  |  | 659 |  |  | 736 |  |  | 691 |  |  | 756.5 |  |  | 749 |  |  | 720 |  |  | 767.5 |  |  | 756.5 |  |  | 660.5 |  |  | 728.5 |  |  | 783.5 |  |  | 800.5 |  |  | 714.5 |  |  | 781.5 |  |  | 697.5 |  |  | 654 |  |  | 789.5 |  |  | 765 |  |  | 750.5 |  |  | 721.5 |  |  | 794.5 |  |  | 731.5 |  |  | 704 |  |  | 732.5 |  |  | 738 |  |  | 729.5 |  |  | 703.5 |  |  | 658 |  |  | 803 |  |  | 765.5 |  |  | 747 |  |  | 779.5 |  |  | 629.5 |  |  | 731.5 |  |  | 750.5 |  |  | 751.5 |  |  | 731.5 |  |  | 703.5 |  |  | 686 |  |  | 706.5 |  |  | 738.5 |  |  | 682.5 |  |  | 731.5 |  |  | 762.5 |  |  | 737.5 |  |  | 745.5 |  |  | 683.5 |  |  | 725.5 |  |  | 749.5 |  |  | 775.5 |  |  | 687.5 |  |  | 830 |  |  | 673.5 |  |  | 711.5 |  |  | 780 |  |  | 691.5 |  |  | 644.5 |  |  | 704.5 |  |  | 730.5 |  |  | 762 |  |  | 776.5 |  |  | 720.5 |  |  | 712.5 |  |  | 752.5 |  |  | 728 |  |  | 738.5 |  |  | 729.5 |  |  | 708.5 |  |  | 772.5 |  |  | 756.5 |  |  | 696.5 |  |  | 769.5 |  |  | 762.5 |  |  | 752.5 |  |  | 709.5 |  |  | 838.5 |  |  | 792 |  |  | 758.5 |  |  | 741.5 |  |  | 796.5 |  |  | 720.5 |  |  | 683.5 |  |  | 688.5 |  |  | 753 |  |  | 695.5 |  |  | 715 |  |  | 717.5 |  |  | 760.5 |  |  | 707.5 |  |  | 704 |  |  | 703 |  |  | 745.5 |  |  | 730.5 |  |  | 707.5 |  |  | 728.5 |  |  | 679.5 |  |  | 665.5 |  |  | 745.5 |  |  | 656.5 |  |  | 776.5 |  |  | 814.5 |  |  | 687.5 |  |  | 792.5 |  |  | 739.5 |  |  | 727.5 |  |  | 750.5 |  |  | 728.5 |  |  | 706.5 |  |  | 680.5 |  |  | 741.5 |  |  | 748.5 |  |  | 760.5 |  |  | 799.5 |  |  | 767 |  |  | 831.5 |  |  | 711.5 |  |  | 751.5 |  |  | 721 |  |  | 740.5 |  |  | 734.5 |  |  | 723.5 |  |  | 762.5 |  |  | 762 |  |  | 678.5 |  |  | 724.5 |  |  | 698 |  |  | 703 |  |  | 731 |  |  | 762.5 |  |  | 748.5 |  |  | 755.5 |  |  | 735.5 |  |  | 751 |  |  | 755.5 |  |  | 751.5 |  |  | 707 |  |  | 696 |  |  | 742.5 |  |  | 776.5 |  |  | 727 |  |  | 682.5 |  |  | 744 |  |  | 675.5 |  |  | 690.5 |  |  | 694 |  |  | 794.5 |  |  | 708.5 |  |  | 667.5 |  |  | 804 |  |  | 787.5 |  |  | 733.5 |  |  | 704.5 |  |  | 740.5 |  |  | 729.5 |  |  | 744.5 |  |  | 644.5 |  |  | 730.5 |  |  | 754.5 |  |  | 750.5 |  |  | 754 |  |  | 711.5 |  |  | 767.5 |  |  | 767.5 |  |  | 748.5 |  |  | 707.5 |  |  | 819.5 |  |  | 818.5 |  |  | 749.5 |  |  | 784 |  |  | 770.5 |  |  | 734 |  |  | 750.5 |  |  | 803.5 |  |  | 750.5 |  |  | 770.5 |  |  | 760.5 |  |  | 709.5 |  |  | 628.5 |  |  | 769.5 |  |  | 688 |  |  | 722.5 |  |  | 673 |  |  | 710.5 |  |  | 704.5 |  |  | 780.5 |  |  | 819 |  |  | 704.5 |  |  | 764.5 |  |  | 739 |  |  | 732.5 |  |  | 704 |  |  | 717.5 |  |  | 762.5 |  |  | 738.5 |  |  | 699 |  |  | 700.5 |  |  | 823.5 |  |  | 691 |  |  | 789.5 |  |  | 670.5 |  |  | 762 |  |  | 707.5 |  |  | 806.5 |  |  | 740.5 |  |  | 756.5 |  |  | 717.5 |  |  | 702.5 |  |  | 668.5 |  |  | 733.5 |  |  | 644.5 |  |  | 755.5 |  |  | 791.5 |  |  | 691 |  |  | 814 |  |  | 764.5 |  |  | 746.5 |  |  | 805
27 |  | 797.5 |  |  | 855.5 |  |  | 807 |  |  | 754.5 |  |  | 813.5 |  |  | 778.5 |  |  | 884.5 |  |  | 756.5 |  |  | 786.5 |  |  | 784.5 |  |  | 760 |  |  | 830.5 |  |  | 822.5 |  |  | 759.5 |  |  | 704 |  |  | 826.5 |  |  | 807.5 |  |  | 807.5 |  |  | 822.5 |  |  | 666.5 |  |  | 766.5 |  |  | 732.5 |  |  | 789.5 |  |  | 750.5 |  |  | 754 |  |  | 815.5 |  |  | 692.5 |  |  | 779.5 |  |  | 735.5 |  |  | 680 |  |  | 775 |  |  | 765.5 |  |  | 685.5 |  |  | 764.5 |  |  | 672.5 |  |  | 733 |  |  | 790.5 |  |  | 739 |  |  | 752.5 |  |  | 797.5 |  |  | 713.5 |  |  | 793.5 |  |  | 785.5 |  |  | 733 |  |  | 858.5 |  |  | 848 |  |  | 741.5 |  |  | 761.5 |  |  | 740.5 |  |  | 725.5 |  |  | 763.5 |  |  | 748.5 |  |  | 739.5 |  |  | 773.5 |  |  | 774.5 |  |  | 751.5 |  |  | 727.5 |  |  | 778 |  |  | 782.5 |  |  | 743.5 |  |  | 757 |  |  | 707.5 |  |  | 805.5 |  |  | 765.5 |  |  | 726.5 |  |  | 759 |  |  | 779.5 |  |  | 683 |  |  | 764.5 |  |  | 776.5 |  |  | 820 |  |  | 761.5 |  |  | 729.5 |  |  | 794.5 |  |  | 808 |  |  | 733 |  |  | 757.5 |  |  | 721.5 |  |  | 661.5 |  |  | 738.5 |  |  | 747 |  |  | 723.5 |  |  | 799.5 |  |  | 814.5 |  |  | 807.5 |  |  | 841.5 |  |  | 829.5 |  |  | 750.5 |  |  | 735.5 |  |  | 798.5 |  |  | 773.5 |  |  | 740 |  |  | 750.5 |  |  | 727 |  |  | 758 |  |  | 757 |  |  | 812.5 |  |  | 740.5 |  |  | 720.5 |  |  | 747.5 |  |  | 767.5 |  |  | 780 |  |  | 814 |  |  | 754.5 |  |  | 762.5 |  |  | 716.5 |  |  | 767.5 |  |  | 833.5 |  |  | 807.5 |  |  | 795.5 |  |  | 818.5 |  |  | 760.5 |  |  | 833.5 |  |  | 798.5 |  |  | 826.5 |  |  | 782.5 |  |  | 780.5 |  |  | 749.5 |  |  | 780.5 |  |  | 833.5 |  |  | 773.5 |  |  | 771.5 |  |  | 769.5 |  |  | 795.5 |  |  | 764.5 |  |  | 847 |  |  | 739.5 |  |  | 806.5 |  |  | 702.5 |  |  | 740.5 |  |  | 817.5 |  |  | 733 |  |  | 746.5 |  |  | 840.5 |  |  | 721.5 |  |  | 817.5 |  |  | 750 |  |  | 768.5 |  |  | 815.5 |  |  | 761 |  |  | 776.5 |  |  | 714 |  |  | 758 |  |  | 812.5 |  |  | 757 |  |  | 812.5 |  |  | 744.5 |  |  | 788.5 |  |  | 729.5 |  |  | 784.5 |  |  | 807.5 |  |  | 766.5 |  |  | 766.5 |  |  | 842.5 |  |  | 815.5 |  |  | 765 |  |  | 696.5 |  |  | 708 |  |  | 716.5 |  |  | 801.5 |  |  | 789 |  |  | 748.5 |  |  | 741.5 |  |  | 742.5 |  |  | 765 |  |  | 758.5 |  |  | 718.5 |  |  | 786.5 |  |  | 778.5 |  |  | 758.5 |  |  | 742.5 |  |  | 711 |  |  | 732.5 |  |  | 750.5 |  |  | 714.5 |  |  | 747.5 |  |  | 792.5 |  |  | 814.5 |  |  | 737.5 |  |  | 818 |  |  | 761.5 |  |  | 739.5 |  |  | 782.5 |  |  | 781.5 |  |  | 670.5 |  |  | 819.5 |  |  | 778.5 |  |  | 821.5 |  |  | 752.5 |  |  | 726.5 |  |  | 770.5 |  |  | 645.5 |  |  | 707.5 |  |  | 772 |  |  | 766.5 |  |  | 773.5 |  |  | 724.5 |  |  | 775.5 |  |  | 847.5 |  |  | 812.5 |  |  | 780.5 |  |  | 728.5 |  |  | 691.5 |  |  | 784.5 |  |  | 745.5 |  |  | 852.5 |  |  | 722.5 |  |  | 727.5 |  |  | 806.5 |  |  | 817.5 |  |  | 767 |  |  | 794.5 |  |  | 783.5 |  |  | 729 |  |  | 821.5 |  |  | 736 |  |  | 720.5 |  |  | 803.5 |  |  | 846.5 |  |  | 771.5 |  |  | 734.5 |  |  | 753.5 |  |  | 771.5 |  |  | 701.5 |  |  | 735 |  |  | 705.5 |  |  | 659.5 |  |  | 751.5 |  |  | 793.5 |  |  | 808 |  |  | 675.5 |  |  | 696.5 |  |  | 790.5 |  |  | 840.5 |  |  | 819.5 |  |  | 725.5 |  |  | 725.5 |  |  | 815.5 |  |  | 755 |  |  | 811 |  |  | 725.5 |  |  | 765.5 |  |  | 814.5 |  |  | 796 |  |  | 777.5 |  |  | 777.5 |  |  | 788.5 |  |  | 748 |  |  | 752.5 |  |  | 795.5 |  |  | 756.5 |  |  | 690.5 |  |  | 745.5 |  |  | 736.5 |  |  | 790.5 |  |  | 723.5 |  |  | 779.5 |  |  | 694 |  |  | 700.5 |  |  | 776.5 |  |  | 734.5 |  |  | 740.5 |  |  | 768.5 |  |  | 810 |  |  | 786.5 |  |  | 815.5 |  |  | 757 |  |  | 816.5 |  |  | 738.5 |  |  | 827 |  |  | 756.5 |  |  | 718.5 |  |  | 888.5 |  |  | 737.5 |  |  | 799 |  |  | 805 |  |  | 772.5 |  |  | 778.5 |  |  | 797.5 |  |  | 769.5 |  |  | 818.5 |  |  | 728.5 |  |  | 735 |  |  | 750.5 |  |  | 763.5 |  |  | 768 |  |  | 738.5 |  |  | 750.5 |  |  | 706 |  |  | 793.5 |  |  | 707.5 |  |  | 786.5 |  |  | 801 |  |  | 784.5 |  |  | 740 |  |  | 817.5 |  |  | 720.5 |  |  | 794.5 |  |  | 711 |  |  | 747.5 |  |  | 763.5 |  |  | 726.5 |  |  | 756 |  |  | 684.5 |  |  | 749.5 |  |  | 814.5 |  |  | 762.5 |  |  | 730.5 |  |  | 746 |  |  | 757.5 |  |  | 794.5 |  |  | 888.5 |  |  | 723 |  |  | 825 |  |  | 859.5 |  |  | 786.5 |  |  | 744.5 |  |  | 802.5 |  |  | 766.5 |  |  | 784.5 |  |  | 738.5 |  |  | 797.5 |  |  | 722.5 |  |  | 759.5 |  |  | 752 |  |  | 795.5 |  |  | 807.5 |  |  | 813.5 |  |  | 842.5 |  |  | 781 |  |  | 805.5 |  |  | 757.5 |  |  | 790.5 |  |  | 707.5 |  |  | 747.5 |  |  | 769 |  |  | 772 |  |  | 680 |  |  | 760 |  |  | 711.5 |  |  | 829 |  |  | 751.5 |  |  | 720 |  |  | 777.5 |  |  | 777.5 |  |  | 734.5 |  |  | 757.5 |  |  | 809.5 |  |  | 793 |  |  | 684.5 |  |  | 779.5 |  |  | 688.5 |  |  | 780 |  |  | 777.5 |  |  | 736.5 |  |  | 738.5 |  |  | 846 |  |  | 752.5 |  |  | 719.5 |  |  | 748.5 |  |  | 732.5 |  |  | 759.5 |  |  | 734.5 |  |  | 853.5 |  |  | 714.5 |  |  | 726.5 |  |  | 727.5 |  |  | 704 |  |  | 722.5 |  |  | 806.5 |  |  | 759.5 |  |  | 762.5 |  |  | 840.5 |  |  | 720 |  |  | 690.5 |  |  | 791 |  |  | 791 |  |  | 736.5 |  |  | 837.5 |  |  | 739.5 |  |  | 756 |  |  | 803.5 |  |  | 810.5 |  |  | 745.5 |  |  | 698 |  |  | 715.5 |  |  | 683.5 |  |  | 820.5 |  |  | 723.5 |  |  | 722.5 |  |  | 738 |  |  | 756.5 |  |  | 776 |  |  | 783.5 |  |  | 756.5 |  |  | 805.5 |  |  | 885 |  |  | 714.5 |  |  | 794 |  |  | 800 |  |  | 734.5 |  |  | 754.5 |  |  | 752.5 |  |  | 817.5 |  |  | 801 |  |  | 779.5 |  |  | 781.5 |  |  | 718.5 |  |  | 769 |  |  | 840.5 |  |  | 679.5 |  |  | 708.5 |  |  | 771.5 |  |  | 754 |  |  | 674.5 |  |  | 725.5 |  |  | 794.5 |  |  | 764.5 |  |  | 798.5 |  |  | 803.5 |  |  | 825 |  |  | 771.5 |  |  | 724.5 |  |  | 766 |  |  | 719.5 |  |  | 729.5 |  |  | 770.5 |  |  | 806 |  |  | 750.5 |  |  | 774.5 |  |  | 793.5 |  |  | 788.5 |  |  | 762.5 |  |  | 831 |  |  | 734 |  |  | 743.5 |  |  | 781.5 |  |  | 781.5 |  |  | 771.5 |  |  | 738 |  |  | 777 |  |  | 738 |  |  | 816.5 |  |  | 756 |  |  | 846.5 |  |  | 785.5 |  |  | 803 |  |  | 672.5 |  |  | 770.5 |  |  | 738.5 |  |  | 866.5 |  |  | 716.5 |  |  | 749 |  |  | 788 |  |  | 696.5 |  |  | 748.5 |  |  | 753 |  |  | 656.5 |  |  | 849.5 |  |  | 768 |  |  | 848.5 |  |  | 887.5 |  |  | 670 |  |  | 787.5 |  |  | 818.5 |  |  | 738 |  |  | 773.5 |  |  | 710 |  |  | 798.5 |  |  | 819 |  |  | 702.5 |  |  | 780.5 |  |  | 789.5 |  |  | 773.5 |  |  | 749.5 |  |  | 787.5 |  |  | 818 |  |  | 784.5 |  |  | 819.5 |  |  | 737.5 |  |  | 834.5 |  |  | 739.5 |  |  | 757 |  |  | 741.5 |  |  | 755 |  |  | 795.5 |  |  | 746.5 |  |  | 791.5 |  |  | 711.5 |  |  | 741.5 |  |  | 749.5 |  |  | 702.5 |  |  | 809.5 |  |  | 767.5 |  |  | 812 |  |  | 768.5 |  |  | 713 |  |  | 767 |  |  | 722.5 |  |  | 690 |  |  | 735.5 |  |  | 734.5 |  |  | 777.5 |  |  | 766.5 |  |  | 780.5 |  |  | 808.5 |  |  | 836.5 |  |  | 768 |  |  | 801 |  |  | 703.5 |  |  | 734.5 |  |  | 697 |  |  | 733.5 |  |  | 773.5 |  |  | 714.5 |  |  | 678.5 |  |  | 749.5 |  |  | 746 |  |  | 750.5 |  |  | 772.5 |  |  | 762.5 |  |  | 776 |  |  | 761.5 |  |  | 815.5 |  |  | 821.5 |  |  | 821.5 |  |  | 787.5 |  |  | 712.5 |  |  | 828.5 |  |  | 661.5 |  |  | 782.5 |  |  | 745 |  |  | 793.5 |  |  | 756.5 |  |  | 785.5 |  |  | 793.5 |  |  | 707.5 |  |  | 730.5 |  |  | 726.5 |  |  | 726 |  |  | 742.5 |  |  | 791.5 |  |  | 787.5 |  |  | 688 |  |  | 739.5 |  |  | 748 |  |  | 773.5 |  |  | 770.5 |  |  | 740.5 |  |  | 744 |  |  | 708.5 |  |  | 755 |  |  | 792 |  |  | 804.5 |  |  | 759 |  |  | 781 |  |  | 845.5 |  |  | 829.5 |  |  | 773.5 |  |  | 767 |  |  | 791.5 |  |  | 781.5 |  |  | 698.5 |  |  | 802.5 |  |  | 751.5 |  |  | 793.5 |  |  | 739.5 |  |  | 772.5 |  |  | 740 |  |  | 876.5 |  |  | 658 |  |  | 776.5 |  |  | 655.5 |  |  | 831.5 |  |  | 746 |  |  | 774 |  |  | 823 |  |  | 796.5 |  |  | 780 |  |  | 770.5 |  |  | 838.5 |  |  | 708.5 |  |  | 785.5 |  |  | 783.5 |  |  | 821.5 |  |  | 755.5 |  |  | 733.5 |  |  | 839 |  |  | 725.5 |  |  | 690.5 |  |  | 763.5 |  |  | 745.5 |  |  | 698 |  |  | 753.5 |  |  | 832 |  |  | 739.5 |  |  | 733.5 |  |  | 765.5 |  |  | 729.5 |  |  | 754 |  |  | 704.5 |  |  | 709 |  |  | 763.5 |  |  | 779.5 |  |  | 855.5 |  |  | 732.5 |  |  | 771.5 |  |  | 777.5 |  |  | 759.5 |  |  | 785.5 |  |  | 672.5 |  |  | 818 |  |  | 766.5 |  |  | 714.5 |  |  | 715.5 |  |  | 790.5 |  |  | 776.5 |  |  | 696 |  |  | 753 |  |  | 796.5 |  |  | 740 |  |  | 793.5 |  |  | 780.5 |  |  | 782.5 |  |  | 840.5 |  |  | 779.5 |  |  | 786.5 |  |  | 749.5 |  |  | 810.5 |  |  | 748 |  |  | 813.5 |  |  | 829.5 |  |  | 797.5 |  |  | 745 |  |  | 810.5 |  |  | 738.5 |  |  | 844 |  |  | 697 |  |  | 807.5 |  |  | 680 |  |  | 730 |  |  | 720.5 |  |  | 721 |  |  | 815.5 |  |  | 795.5 |  |  | 779.5 |  |  | 775.5 |  |  | 705.5 |  |  | 755.5 |  |  | 646.5 |  |  | 790.5 |  |  | 726.5 |  |  | 741.5 |  |  | 802 |  |  | 743 |  |  | 724.5 |  |  | 732.5 |  |  | 769.5 |  |  | 797.5 |  |  | 735.5 |  |  | 835.5 |  |  | 780.5 |  |  | 709.5 |  |  | 779 |  |  | 697.5 |  |  | 738 |  |  | 719.5 |  |  | 898.5 |  |  | 793.5 |  |  | 839 |  |  | 744.5 |  |  | 786.5 |  |  | 643 |  |  | 780.5 |  |  | 709.5 |  |  | 776.5 |  |  | 779.5 |  |  | 742.5 |  |  | 698.5 |  |  | 694 |  |  | 824.5 |  |  | 711.5 |  |  | 808.5 |  |  | 809.5 |  |  | 730 |  |  | 727.5 |  |  | 809.5 |  |  | 732 |  |  | 777.5 |  |  | 763.5 |  |  | 749 |  |  | 756.5 |  |  | 747.5 |  |  | 788.5 |  |  | 747 |  |  | 690.5 |  |  | 766.5 |  |  | 731 |  |  | 749.5 |  |  | 763.5 |  |  | 739.5 |  |  | 660.5 |  |  | 819.5 |  |  | 868.5 |  |  | 754.5 |  |  | 790 |  |  | 780 |  |  | 683.5 |  |  | 766.5 |  |  | 733.5 |  |  | 766 |  |  | 798.5 |  |  | 780.5 |  |  | 824.5 |  |  | 732.5 |  |  | 760.5 |  |  | 746.5 |  |  | 676.5 |  |  | 760.5 |  |  | 728.5 |  |  | 745 |  |  | 759.5 |  |  | 762.5 |  |  | 713.5 |  |  | 802.5 |  |  | 828.5 |  |  | 721.5 |  |  | 754.5 |  |  | 806.5 |  |  | 746.5 |  |  | 725.5 |  |  | 714.5 |  |  | 743.5 |  |  | 776.5 |  |  | 835 |  |  | 751.5 |  |  | 793.5 |  |  | 738 |  |  | 768.5 |  |  | 788.5 |  |  | 826 |  |  | 747.5 |  |  | 802.5 |  |  | 828.5 |  |  | 803 |  |  | 746.5 |  |  | 755.5 |  |  | 761.5 |  |  | 640.5 |  |  | 781.5 |  |  | 730 |  |  | 748.5 |  |  | 812 |  |  | 727 |  |  | 795.5 |  |  | 776.5 |  |  | 741.5 |  |  | 698.5 |  |  | 768.5 |  |  | 744.5 |  |  | 739 |  |  | 729.5 |  |  | 800 |  |  | 757.5 |  |  | 787 |  |  | 763 |  |  | 793 |  |  | 728.5 |  |  | 693 |  |  | 798.5 |  |  | 860.5 |  |  | 770.5 |  |  | 900.5 |  |  | 810.5 |  |  | 776 |  |  | 795.5 |  |  | 807.5 |  |  | 849.5 |  |  | 821 |  |  | 792.5 |  |  | 789.5 |  |  | 795.5 |  |  | 796.5 |  |  | 706 |  |  | 751 |  |  | 730 |  |  | 782.5 |  |  | 770 |  |  | 759 |  |  | 796.5 |  |  | 795.5 |  |  | 675.5 |  |  | 775.5 |  |  | 822.5 |  |  | 847.5 |  |  | 740.5 |  |  | 796.5 |  |  | 718.5 |  |  | 693 |  |  | 815.5 |  |  | 791 |  |  | 797.5 |  |  | 747.5 |  |  | 820.5 |  |  | 757.5 |  |  | 743 |  |  | 761.5 |  |  | 777 |  |  | 753.5 |  |  | 718.5 |  |  | 679 |  |  | 827 |  |  | 786.5 |  |  | 786 |  |  | 818.5 |  |  | 658.5 |  |  | 760.5 |  |  | 771.5 |  |  | 798.5 |  |  | 757.5 |  |  | 750.5 |  |  | 710 |  |  | 745.5 |  |  | 777.5 |  |  | 706.5 |  |  | 752.5 |  |  | 777.5 |  |  | 766.5 |  |  | 760.5 |  |  | 730.5 |  |  | 751.5 |  |  | 796.5 |  |  | 804.5 |  |  | 726.5 |  |  | 854 |  |  | 697.5 |  |  | 750.5 |  |  | 801 |  |  | 715.5 |  |  | 665.5 |  |  | 730.5 |  |  | 756.5 |  |  | 801 |  |  | 815.5 |  |  | 767.5 |  |  | 741.5 |  |  | 799.5 |  |  | 749 |  |  | 767.5 |  |  | 768.5 |  |  | 734.5 |  |  | 811.5 |  |  | 803.5 |  |  | 720.5 |  |  | 808.5 |  |  | 788.5 |  |  | 791.5 |  |  | 756.5 |  |  | 853.5 |  |  | 831 |  |  | 797.5 |  |  | 770.5 |  |  | 825.5 |  |  | 767.5 |  |  | 704.5 |  |  | 709.5 |  |  | 792 |  |  | 734.5 |  |  | 736 |  |  | 746.5 |  |  | 789.5 |  |  | 722.5 |  |  | 730 |  |  | 742 |  |  | 771.5 |  |  | 777.5 |  |  | 733.5 |  |  | 754.5 |  |  | 703.5 |  |  | 689.5 |  |  | 771.5 |  |  | 703.5 |  |  | 800.5 |  |  | 835.5 |  |  | 734.5 |  |  | 813.5 |  |  | 765.5 |  |  | 766.5 |  |  | 779.5 |  |  | 775.5 |  |  | 745.5 |  |  | 719.5 |  |  | 780.5 |  |  | 769.5 |  |  | 784.5 |  |  | 838.5 |  |  | 806 |  |  | 852.5 |  |  | 735.5 |  |  | 775.5 |  |  | 736 |  |  | 769.5 |  |  | 781.5 |  |  | 762.5 |  |  | 788.5 |  |  | 788 |  |  | 725.5 |  |  | 745.5 |  |  | 722 |  |  | 732 |  |  | 746 |  |  | 786.5 |  |  | 763.5 |  |  | 781.5 |  |  | 774.5 |  |  | 780 |  |  | 770.5 |  |  | 790.5 |  |  | 731 |  |  | 720 |  |  | 781.5 |  |  | 791.5 |  |  | 748 |  |  | 721.5 |  |  | 759 |  |  | 714.5 |  |  | 729.5 |  |  | 741 |  |  | 823.5 |  |  | 729.5 |  |  | 691.5 |  |  | 843 |  |  | 816.5 |  |  | 762.5 |  |  | 743.5 |  |  | 764.5 |  |  | 776.5 |  |  | 783.5 |  |  | 673.5 |  |  | 769.5 |  |  | 780.5 |  |  | 779.5 |  |  | 780 |  |  | 732.5 |  |  | 788.5 |  |  | 791.5 |  |  | 769.5 |  |  | 728.5 |  |  | 843.5 |  |  | 847.5 |  |  | 775.5 |  |  | 813 |  |  | 791.5 |  |  | 781 |  |  | 797.5 |  |  | 850.5 |  |  | 797.5 |  |  | 799.5 |  |  | 807.5 |  |  | 724.5 |  |  | 652.5 |  |  | 784.5 |  |  | 735 |  |  | 746.5 |  |  | 699 |  |  | 749.5 |  |  | 728.5 |  |  | 819.5 |  |  | 843 |  |  | 733.5 |  |  | 785.5 |  |  | 754 |  |  | 747.5 |  |  | 719 |  |  | 732.5 |  |  | 783.5 |  |  | 762.5 |  |  | 720 |  |  | 715.5 |  |  | 852.5 |  |  | 712 |  |  | 818.5 |  |  | 696.5 |  |  | 783 |  |  | 746.5 |  |  | 845.5 |  |  | 766.5 |  |  | 795.5 |  |  | 764.5 |  |  | 741.5 |  |  | 694.5 |  |  | 759.5 |  |  | 683.5 |  |  | 794.5 |  |  | 817.5 |  |  | 720 |  |  | 840 |  |  | 790.5 |  |  | 770.5 |  |  | 820
28 |  | 818.5 |  |  | 876.5 |  |  | 822 |  |  | 793.5 |  |  | 842.5 |  |  | 817.5 |  |  | 899.5 |  |  | 795.5 |  |  | 810.5 |  |  | 810.5 |  |  | 784 |  |  | 845.5 |  |  | 861.5 |  |  | 785.5 |  |  | 730 |  |  | 841.5 |  |  | 828.5 |  |  | 831.5 |  |  | 869.5 |  |  | 713.5 |  |  | 790.5 |  |  | 771.5 |  |  | 828.5 |  |  | 789.5 |  |  | 769 |  |  | 854.5 |  |  | 731.5 |  |  | 800.5 |  |  | 764.5 |  |  | 706 |  |  | 790 |  |  | 791.5 |  |  | 709.5 |  |  | 803.5 |  |  | 693.5 |  |  | 772 |  |  | 805.5 |  |  | 763 |  |  | 773.5 |  |  | 844.5 |  |  | 760.5 |  |  | 840.5 |  |  | 806.5 |  |  | 757 |  |  | 897.5 |  |  | 887 |  |  | 756.5 |  |  | 790.5 |  |  | 779.5 |  |  | 751.5 |  |  | 789.5 |  |  | 795.5 |  |  | 760.5 |  |  | 788.5 |  |  | 803.5 |  |  | 780.5 |  |  | 748.5 |  |  | 793 |  |  | 806.5 |  |  | 782.5 |  |  | 783 |  |  | 728.5 |  |  | 852.5 |  |  | 804.5 |  |  | 741.5 |  |  | 806 |  |  | 800.5 |  |  | 707 |  |  | 788.5 |  |  | 802.5 |  |  | 841 |  |  | 800.5 |  |  | 768.5 |  |  | 841.5 |  |  | 829 |  |  | 780 |  |  | 781.5 |  |  | 750.5 |  |  | 690.5 |  |  | 777.5 |  |  | 771 |  |  | 747.5 |  |  | 838.5 |  |  | 838.5 |  |  | 828.5 |  |  | 880.5 |  |  | 853.5 |  |  | 776.5 |  |  | 761.5 |  |  | 824.5 |  |  | 812.5 |  |  | 787 |  |  | 779.5 |  |  | 753 |  |  | 787 |  |  | 783 |  |  | 838.5 |  |  | 766.5 |  |  | 767.5 |  |  | 786.5 |  |  | 793.5 |  |  | 827 |  |  | 861 |  |  | 769.5 |  |  | 783.5 |  |  | 755.5 |  |  | 806.5 |  |  | 859.5 |  |  | 831.5 |  |  | 819.5 |  |  | 842.5 |  |  | 784.5 |  |  | 848.5 |  |  | 845.5 |  |  | 855.5 |  |  | 797.5 |  |  | 806.5 |  |  | 770.5 |  |  | 801.5 |  |  | 854.5 |  |  | 799.5 |  |  | 797.5 |  |  | 816.5 |  |  | 821.5 |  |  | 803.5 |  |  | 886 |  |  | 768.5 |  |  | 832.5 |  |  | 731.5 |  |  | 755.5 |  |  | 846.5 |  |  | 780 |  |  | 772.5 |  |  | 879.5 |  |  | 736.5 |  |  | 832.5 |  |  | 774 |  |  | 792.5 |  |  | 854.5 |  |  | 785 |  |  | 823.5 |  |  | 735 |  |  | 797 |  |  | 859.5 |  |  | 778 |  |  | 838.5 |  |  | 765.5 |  |  | 835.5 |  |  | 768.5 |  |  | 805.5 |  |  | 833.5 |  |  | 813.5 |  |  | 790.5 |  |  | 863.5 |  |  | 836.5 |  |  | 812 |  |  | 717.5 |  |  | 755 |  |  | 745.5 |  |  | 822.5 |  |  | 810 |  |  | 787.5 |  |  | 765.5 |  |  | 771.5 |  |  | 791 |  |  | 784.5 |  |  | 744.5 |  |  | 801.5 |  |  | 804.5 |  |  | 787.5 |  |  | 766.5 |  |  | 750 |  |  | 761.5 |  |  | 776.5 |  |  | 753.5 |  |  | 794.5 |  |  | 839.5 |  |  | 843.5 |  |  | 766.5 |  |  | 842 |  |  | 808.5 |  |  | 768.5 |  |  | 821.5 |  |  | 820.5 |  |  | 709.5 |  |  | 858.5 |  |  | 817.5 |  |  | 842.5 |  |  | 781.5 |  |  | 741.5 |  |  | 785.5 |  |  | 669.5 |  |  | 728.5 |  |  | 796 |  |  | 813.5 |  |  | 802.5 |  |  | 771.5 |  |  | 801.5 |  |  | 873.5 |  |  | 838.5 |  |  | 809.5 |  |  | 775.5 |  |  | 738.5 |  |  | 831.5 |  |  | 784.5 |  |  | 899.5 |  |  | 743.5 |  |  | 756.5 |  |  | 845.5 |  |  | 856.5 |  |  | 814 |  |  | 841.5 |  |  | 798.5 |  |  | 755 |  |  | 842.5 |  |  | 765 |  |  | 767.5 |  |  | 850.5 |  |  | 875.5 |  |  | 795.5 |  |  | 781.5 |  |  | 779.5 |  |  | 795.5 |  |  | 727.5 |  |  | 750 |  |  | 752.5 |  |  | 680.5 |  |  | 790.5 |  |  | 808.5 |  |  | 855 |  |  | 722.5 |  |  | 725.5 |  |  | 829.5 |  |  | 864.5 |  |  | 845.5 |  |  | 740.5 |  |  | 746.5 |  |  | 830.5 |  |  | 794 |  |  | 840 |  |  | 740.5 |  |  | 794.5 |  |  | 840.5 |  |  | 843 |  |  | 816.5 |  |  | 816.5 |  |  | 812.5 |  |  | 774 |  |  | 791.5 |  |  | 842.5 |  |  | 780.5 |  |  | 711.5 |  |  | 769.5 |  |  | 775.5 |  |  | 819.5 |  |  | 747.5 |  |  | 818.5 |  |  | 709 |  |  | 739.5 |  |  | 797.5 |  |  | 773.5 |  |  | 764.5 |  |  | 789.5 |  |  | 849 |  |  | 825.5 |  |  | 841.5 |  |  | 781 |  |  | 855.5 |  |  | 777.5 |  |  | 848 |  |  | 785.5 |  |  | 739.5 |  |  | 927.5 |  |  | 784.5 |  |  | 838 |  |  | 852 |  |  | 793.5 |  |  | 799.5 |  |  | 818.5 |  |  | 795.5 |  |  | 842.5 |  |  | 767.5 |  |  | 782 |  |  | 776.5 |  |  | 810.5 |  |  | 794 |  |  | 764.5 |  |  | 779.5 |  |  | 721 |  |  | 822.5 |  |  | 754.5 |  |  | 825.5 |  |  | 822 |  |  | 823.5 |  |  | 755 |  |  | 846.5 |  |  | 759.5 |  |  | 815.5 |  |  | 735 |  |  | 773.5 |  |  | 810.5 |  |  | 747.5 |  |  | 771 |  |  | 705.5 |  |  | 788.5 |  |  | 829.5 |  |  | 809.5 |  |  | 759.5 |  |  | 772 |  |  | 778.5 |  |  | 841.5 |  |  | 909.5 |  |  | 749 |  |  | 846 |  |  | 888.5 |  |  | 812.5 |  |  | 759.5 |  |  | 817.5 |  |  | 790.5 |  |  | 813.5 |  |  | 777.5 |  |  | 818.5 |  |  | 737.5 |  |  | 785.5 |  |  | 778 |  |  | 824.5 |  |  | 833.5 |  |  | 852.5 |  |  | 857.5 |  |  | 820 |  |  | 831.5 |  |  | 796.5 |  |  | 814.5 |  |  | 733.5 |  |  | 786.5 |  |  | 790 |  |  | 811 |  |  | 704 |  |  | 786 |  |  | 758.5 |  |  | 855 |  |  | 766.5 |  |  | 749 |  |  | 824.5 |  |  | 816.5 |  |  | 773.5 |  |  | 796.5 |  |  | 856.5 |  |  | 808 |  |  | 723.5 |  |  | 803.5 |  |  | 735.5 |  |  | 809 |  |  | 801.5 |  |  | 783.5 |  |  | 764.5 |  |  | 870 |  |  | 778.5 |  |  | 740.5 |  |  | 763.5 |  |  | 779.5 |  |  | 774.5 |  |  | 755.5 |  |  | 879.5 |  |  | 753.5 |  |  | 765.5 |  |  | 748.5 |  |  | 728 |  |  | 751.5 |  |  | 827.5 |  |  | 788.5 |  |  | 783.5 |  |  | 866.5 |  |  | 759 |  |  | 716.5 |  |  | 830 |  |  | 817 |  |  | 762.5 |  |  | 876.5 |  |  | 760.5 |  |  | 771 |  |  | 829.5 |  |  | 834.5 |  |  | 769.5 |  |  | 737 |  |  | 754.5 |  |  | 722.5 |  |  | 835.5 |  |  | 747.5 |  |  | 743.5 |  |  | 762 |  |  | 771.5 |  |  | 805 |  |  | 830.5 |  |  | 795.5 |  |  | 820.5 |  |  | 909 |  |  | 740.5 |  |  | 820 |  |  | 824 |  |  | 773.5 |  |  | 775.5 |  |  | 791.5 |  |  | 843.5 |  |  | 840 |  |  | 818.5 |  |  | 807.5 |  |  | 757.5 |  |  | 798 |  |  | 879.5 |  |  | 700.5 |  |  | 737.5 |  |  | 800.5 |  |  | 793 |  |  | 721.5 |  |  | 764.5 |  |  | 818.5 |  |  | 793.5 |  |  | 813.5 |  |  | 827.5 |  |  | 849 |  |  | 792.5 |  |  | 745.5 |  |  | 790 |  |  | 758.5 |  |  | 768.5 |  |  | 785.5 |  |  | 830 |  |  | 771.5 |  |  | 800.5 |  |  | 832.5 |  |  | 827.5 |  |  | 791.5 |  |  | 855 |  |  | 755 |  |  | 767.5 |  |  | 802.5 |  |  | 796.5 |  |  | 795.5 |  |  | 777 |  |  | 806 |  |  | 759 |  |  | 855.5 |  |  | 780 |  |  | 885.5 |  |  | 814.5 |  |  | 829 |  |  | 701.5 |  |  | 809.5 |  |  | 764.5 |  |  | 905.5 |  |  | 740.5 |  |  | 775 |  |  | 817 |  |  | 717.5 |  |  | 787.5 |  |  | 800 |  |  | 685.5 |  |  | 873.5 |  |  | 807 |  |  | 872.5 |  |  | 911.5 |  |  | 717 |  |  | 826.5 |  |  | 833.5 |  |  | 753 |  |  | 812.5 |  |  | 749 |  |  | 819.5 |  |  | 858 |  |  | 731.5 |  |  | 809.5 |  |  | 828.5 |  |  | 799.5 |  |  | 773.5 |  |  | 813.5 |  |  | 857 |  |  | 799.5 |  |  | 845.5 |  |  | 752.5 |  |  | 858.5 |  |  | 768.5 |  |  | 772 |  |  | 762.5 |  |  | 779 |  |  | 810.5 |  |  | 761.5 |  |  | 806.5 |  |  | 735.5 |  |  | 770.5 |  |  | 770.5 |  |  | 728.5 |  |  | 856.5 |  |  | 806.5 |  |  | 827 |  |  | 792.5 |  |  | 752 |  |  | 793 |  |  | 751.5 |  |  | 705 |  |  | 782.5 |  |  | 749.5 |  |  | 816.5 |  |  | 805.5 |  |  | 819.5 |  |  | 847.5 |  |  | 860.5 |  |  | 794 |  |  | 816 |  |  | 718.5 |  |  | 760.5 |  |  | 721 |  |  | 754.5 |  |  | 812.5 |  |  | 753.5 |  |  | 725.5 |  |  | 775.5 |  |  | 775 |  |  | 779.5 |  |  | 811.5 |  |  | 801.5 |  |  | 800 |  |  | 790.5 |  |  | 830.5 |  |  | 842.5 |  |  | 868.5 |  |  | 813.5 |  |  | 738.5 |  |  | 857.5 |  |  | 682.5 |  |  | 808.5 |  |  | 771 |  |  | 822.5 |  |  | 795.5 |  |  | 824.5 |  |  | 832.5 |  |  | 728.5 |  |  | 769.5 |  |  | 773.5 |  |  | 755 |  |  | 768.5 |  |  | 830.5 |  |  | 813.5 |  |  | 735 |  |  | 760.5 |  |  | 777 |  |  | 799.5 |  |  | 791.5 |  |  | 779.5 |  |  | 783 |  |  | 734.5 |  |  | 802 |  |  | 807 |  |  | 843.5 |  |  | 780 |  |  | 820 |  |  | 874.5 |  |  | 850.5 |  |  | 788.5 |  |  | 796 |  |  | 830.5 |  |  | 796.5 |  |  | 737.5 |  |  | 849.5 |  |  | 790.5 |  |  | 832.5 |  |  | 765.5 |  |  | 793.5 |  |  | 779 |  |  | 915.5 |  |  | 679 |  |  | 802.5 |  |  | 676.5 |  |  | 857.5 |  |  | 775 |  |  | 821 |  |  | 870 |  |  | 811.5 |  |  | 804 |  |  | 799.5 |  |  | 859.5 |  |  | 732.5 |  |  | 814.5 |  |  | 798.5 |  |  | 836.5 |  |  | 776.5 |  |  | 757.5 |  |  | 860 |  |  | 764.5 |  |  | 729.5 |  |  | 810.5 |  |  | 760.5 |  |  | 719 |  |  | 774.5 |  |  | 858 |  |  | 778.5 |  |  | 759.5 |  |  | 812.5 |  |  | 744.5 |  |  | 778 |  |  | 730.5 |  |  | 730 |  |  | 784.5 |  |  | 818.5 |  |  | 876.5 |  |  | 779.5 |  |  | 800.5 |  |  | 792.5 |  |  | 788.5 |  |  | 824.5 |  |  | 698.5 |  |  | 857 |  |  | 781.5 |  |  | 743.5 |  |  | 736.5 |  |  | 805.5 |  |  | 791.5 |  |  | 720 |  |  | 792 |  |  | 817.5 |  |  | 779 |  |  | 832.5 |  |  | 806.5 |  |  | 811.5 |  |  | 864.5 |  |  | 805.5 |  |  | 801.5 |  |  | 788.5 |  |  | 825.5 |  |  | 787 |  |  | 842.5 |  |  | 868.5 |  |  | 823.5 |  |  | 769 |  |  | 849.5 |  |  | 762.5 |  |  | 883 |  |  | 726 |  |  | 828.5 |  |  | 719 |  |  | 759 |  |  | 749.5 |  |  | 750 |  |  | 844.5 |  |  | 834.5 |  |  | 808.5 |  |  | 822.5 |  |  | 734.5 |  |  | 794.5 |  |  | 670.5 |  |  | 811.5 |  |  | 765.5 |  |  | 756.5 |  |  | 823 |  |  | 772 |  |  | 763.5 |  |  | 756.5 |  |  | 808.5 |  |  | 821.5 |  |  | 759.5 |  |  | 859.5 |  |  | 827.5 |  |  | 733.5 |  |  | 794 |  |  | 726.5 |  |  | 753 |  |  | 743.5 |  |  | 945.5 |  |  | 808.5 |  |  | 878 |  |  | 765.5 |  |  | 815.5 |  |  | 682 |  |  | 827.5 |  |  | 748.5 |  |  | 823.5 |  |  | 794.5 |  |  | 768.5 |  |  | 713.5 |  |  | 733 |  |  | 863.5 |  |  | 726.5 |  |  | 837.5 |  |  | 838.5 |  |  | 754 |  |  | 766.5 |  |  | 856.5 |  |  | 771 |  |  | 803.5 |  |  | 789.5 |  |  | 788 |  |  | 780.5 |  |  | 786.5 |  |  | 814.5 |  |  | 773 |  |  | 729.5 |  |  | 795.5 |  |  | 746 |  |  | 773.5 |  |  | 792.5 |  |  | 765.5 |  |  | 681.5 |  |  | 834.5 |  |  | 907.5 |  |  | 793.5 |  |  | 811 |  |  | 806 |  |  | 707.5 |  |  | 805.5 |  |  | 772.5 |  |  | 805 |  |  | 827.5 |  |  | 795.5 |  |  | 850.5 |  |  | 753.5 |  |  | 799.5 |  |  | 785.5 |  |  | 697.5 |  |  | 775.5 |  |  | 749.5 |  |  | 784 |  |  | 788.5 |  |  | 791.5 |  |  | 728.5 |  |  | 826.5 |  |  | 849.5 |  |  | 760.5 |  |  | 780.5 |  |  | 853.5 |  |  | 772.5 |  |  | 772.5 |  |  | 743.5 |  |  | 772.5 |  |  | 815.5 |  |  | 874 |  |  | 790.5 |  |  | 819.5 |  |  | 762 |  |  | 815.5 |  |  | 817.5 |  |  | 847 |  |  | 786.5 |  |  | 831.5 |  |  | 867.5 |  |  | 850 |  |  | 785.5 |  |  | 794.5 |  |  | 808.5 |  |  | 655.5 |  |  | 810.5 |  |  | 754 |  |  | 787.5 |  |  | 838 |  |  | 742 |  |  | 834.5 |  |  | 805.5 |  |  | 770.5 |  |  | 727.5 |  |  | 783.5 |  |  | 759.5 |  |  | 786 |  |  | 755.5 |  |  | 847 |  |  | 778.5 |  |  | 834 |  |  | 787 |  |  | 832 |  |  | 749.5 |  |  | 722 |  |  | 827.5 |  |  | 881.5 |  |  | 796.5 |  |  | 926.5 |  |  | 849.5 |  |  | 805 |  |  | 834.5 |  |  | 828.5 |  |  | 896.5 |  |  | 868 |  |  | 821.5 |  |  | 828.5 |  |  | 816.5 |  |  | 835.5 |  |  | 753 |  |  | 766 |  |  | 754 |  |  | 806.5 |  |  | 809 |  |  | 785 |  |  | 811.5 |  |  | 821.5 |  |  | 714.5 |  |  | 814.5 |  |  | 846.5 |  |  | 886.5 |  |  | 787.5 |  |  | 811.5 |  |  | 733.5 |  |  | 732 |  |  | 836.5 |  |  | 817 |  |  | 812.5 |  |  | 771.5 |  |  | 841.5 |  |  | 796.5 |  |  | 764 |  |  | 776.5 |  |  | 816 |  |  | 779.5 |  |  | 765.5 |  |  | 705 |  |  | 856 |  |  | 812.5 |  |  | 815 |  |  | 865.5 |  |  | 673.5 |  |  | 799.5 |  |  | 800.5 |  |  | 819.5 |  |  | 781.5 |  |  | 789.5 |  |  | 749 |  |  | 784.5 |  |  | 816.5 |  |  | 753.5 |  |  | 781.5 |  |  | 792.5 |  |  | 790.5 |  |  | 807.5 |  |  | 769.5 |  |  | 790.5 |  |  | 822.5 |  |  | 828.5 |  |  | 741.5 |  |  | 893 |  |  | 726.5 |  |  | 776.5 |  |  | 840 |  |  | 730.5 |  |  | 704.5 |  |  | 751.5 |  |  | 777.5 |  |  | 848 |  |  | 836.5 |  |  | 782.5 |  |  | 765.5 |  |  | 825.5 |  |  | 770 |  |  | 791.5 |  |  | 797.5 |  |  | 758.5 |  |  | 858.5 |  |  | 827.5 |  |  | 735.5 |  |  | 847.5 |  |  | 812.5 |  |  | 815.5 |  |  | 780.5 |  |  | 868.5 |  |  | 857 |  |  | 818.5 |  |  | 809.5 |  |  | 851.5 |  |  | 814.5 |  |  | 730.5 |  |  | 733.5 |  |  | 813 |  |  | 755.5 |  |  | 760 |  |  | 767.5 |  |  | 836.5 |  |  | 746.5 |  |  | 777 |  |  | 771 |  |  | 810.5 |  |  | 803.5 |  |  | 762.5 |  |  | 780.5 |  |  | 750.5 |  |  | 728.5 |  |  | 800.5 |  |  | 718.5 |  |  | 847.5 |  |  | 850.5 |  |  | 773.5 |  |  | 860.5 |  |  | 791.5 |  |  | 813.5 |  |  | 800.5 |  |  | 804.5 |  |  | 766.5 |  |  | 734.5 |  |  | 819.5 |  |  | 793.5 |  |  | 810.5 |  |  | 862.5 |  |  | 830 |  |  | 881.5 |  |  | 759.5 |  |  | 801.5 |  |  | 783 |  |  | 816.5 |  |  | 807.5 |  |  | 801.5 |  |  | 812.5 |  |  | 835 |  |  | 740.5 |  |  | 792.5 |  |  | 761 |  |  | 758 |  |  | 775 |  |  | 815.5 |  |  | 802.5 |  |  | 802.5 |  |  | 813.5 |  |  | 801 |  |  | 796.5 |  |  | 805.5 |  |  | 757 |  |  | 741 |  |  | 828.5 |  |  | 820.5 |  |  | 777 |  |  | 742.5 |  |  | 783 |  |  | 738.5 |  |  | 750.5 |  |  | 780 |  |  | 849.5 |  |  | 755.5 |  |  | 730.5 |  |  | 882 |  |  | 842.5 |  |  | 791.5 |  |  | 769.5 |  |  | 788.5 |  |  | 797.5 |  |  | 822.5 |  |  | 712.5 |  |  | 790.5 |  |  | 804.5 |  |  | 818.5 |  |  | 809 |  |  | 758.5 |  |  | 827.5 |  |  | 830.5 |  |  | 808.5 |  |  | 767.5 |  |  | 864.5 |  |  | 894.5 |  |  | 801.5 |  |  | 834 |  |  | 830.5 |  |  | 828 |  |  | 826.5 |  |  | 874.5 |  |  | 844.5 |  |  | 823.5 |  |  | 836.5 |  |  | 745.5 |  |  | 667.5 |  |  | 799.5 |  |  | 782 |  |  | 785.5 |  |  | 746 |  |  | 796.5 |  |  | 743.5 |  |  | 843.5 |  |  | 872 |  |  | 757.5 |  |  | 814.5 |  |  | 793 |  |  | 762.5 |  |  | 758 |  |  | 753.5 |  |  | 804.5 |  |  | 777.5 |  |  | 741 |  |  | 744.5 |  |  | 899.5 |  |  | 751 |  |  | 844.5 |  |  | 722.5 |  |  | 804 |  |  | 775.5 |  |  | 884.5 |  |  | 790.5 |  |  | 824.5 |  |  | 790.5 |  |  | 780.5 |  |  | 733.5 |  |  | 798.5 |  |  | 709.5 |  |  | 815.5 |  |  | 846.5 |  |  | 741 |  |  | 887 |  |  | 811.5 |  |  | 817.5 |  |  | 849
29 |  | 857.5 |  |  | 915.5 |  |  | 846 |  |  | 808.5 |  |  | 866.5 |  |  | 856.5 |  |  | 925.5 |  |  | 816.5 |  |  | 825.5 |  |  | 825.5 |  |  | 813 |  |  | 869.5 |  |  | 908.5 |  |  | 800.5 |  |  | 754 |  |  | 870.5 |  |  | 867.5 |  |  | 860.5 |  |  | 908.5 |  |  | 752.5 |  |  | 805.5 |  |  | 810.5 |  |  | 843.5 |  |  | 815.5 |  |  | 793 |  |  | 880.5 |  |  | 770.5 |  |  | 815.5 |  |  | 788.5 |  |  | 735 |  |  | 819 |  |  | 806.5 |  |  | 748.5 |  |  | 832.5 |  |  | 717.5 |  |  | 811 |  |  | 831.5 |  |  | 792 |  |  | 802.5 |  |  | 865.5 |  |  | 807.5 |  |  | 855.5 |  |  | 821.5 |  |  | 778 |  |  | 936.5 |  |  | 926 |  |  | 780.5 |  |  | 837.5 |  |  | 818.5 |  |  | 790.5 |  |  | 828.5 |  |  | 816.5 |  |  | 799.5 |  |  | 809.5 |  |  | 842.5 |  |  | 819.5 |  |  | 769.5 |  |  | 832 |  |  | 845.5 |  |  | 806.5 |  |  | 798 |  |  | 752.5 |  |  | 891.5 |  |  | 843.5 |  |  | 762.5 |  |  | 845 |  |  | 824.5 |  |  | 746 |  |  | 812.5 |  |  | 841.5 |  |  | 867 |  |  | 826.5 |  |  | 815.5 |  |  | 862.5 |  |  | 855 |  |  | 801 |  |  | 828.5 |  |  | 779.5 |  |  | 729.5 |  |  | 816.5 |  |  | 797 |  |  | 776.5 |  |  | 867.5 |  |  | 867.5 |  |  | 867.5 |  |  | 895.5 |  |  | 882.5 |  |  | 791.5 |  |  | 782.5 |  |  | 863.5 |  |  | 851.5 |  |  | 802 |  |  | 818.5 |  |  | 779 |  |  | 802 |  |  | 807 |  |  | 864.5 |  |  | 805.5 |  |  | 782.5 |  |  | 812.5 |  |  | 832.5 |  |  | 856 |  |  | 885 |  |  | 790.5 |  |  | 822.5 |  |  | 781.5 |  |  | 830.5 |  |  | 885.5 |  |  | 870.5 |  |  | 845.5 |  |  | 871.5 |  |  | 823.5 |  |  | 895.5 |  |  | 884.5 |  |  | 884.5 |  |  | 844.5 |  |  | 827.5 |  |  | 817.5 |  |  | 830.5 |  |  | 869.5 |  |  | 823.5 |  |  | 818.5 |  |  | 837.5 |  |  | 836.5 |  |  | 829.5 |  |  | 907 |  |  | 794.5 |  |  | 879.5 |  |  | 760.5 |  |  | 784.5 |  |  | 885.5 |  |  | 795 |  |  | 787.5 |  |  | 903.5 |  |  | 775.5 |  |  | 847.5 |  |  | 795 |  |  | 813.5 |  |  | 869.5 |  |  | 832 |  |  | 847.5 |  |  | 782 |  |  | 823 |  |  | 906.5 |  |  | 802 |  |  | 877.5 |  |  | 786.5 |  |  | 850.5 |  |  | 794.5 |  |  | 844.5 |  |  | 872.5 |  |  | 852.5 |  |  | 829.5 |  |  | 884.5 |  |  | 862.5 |  |  | 851 |  |  | 764.5 |  |  | 802 |  |  | 784.5 |  |  | 861.5 |  |  | 849 |  |  | 826.5 |  |  | 804.5 |  |  | 792.5 |  |  | 815 |  |  | 810.5 |  |  | 770.5 |  |  | 825.5 |  |  | 843.5 |  |  | 811.5 |  |  | 792.5 |  |  | 789 |  |  | 800.5 |  |  | 815.5 |  |  | 768.5 |  |  | 815.5 |  |  | 878.5 |  |  | 872.5 |  |  | 795.5 |  |  | 889 |  |  | 847.5 |  |  | 792.5 |  |  | 860.5 |  |  | 844.5 |  |  | 735.5 |  |  | 897.5 |  |  | 838.5 |  |  | 857.5 |  |  | 810.5 |  |  | 780.5 |  |  | 806.5 |  |  | 716.5 |  |  | 752.5 |  |  | 817 |  |  | 828.5 |  |  | 841.5 |  |  | 797.5 |  |  | 816.5 |  |  | 897.5 |  |  | 867.5 |  |  | 835.5 |  |  | 801.5 |  |  | 767.5 |  |  | 870.5 |  |  | 831.5 |  |  | 923.5 |  |  | 767.5 |  |  | 780.5 |  |  | 892.5 |  |  | 882.5 |  |  | 835 |  |  | 865.5 |  |  | 813.5 |  |  | 770 |  |  | 866.5 |  |  | 794 |  |  | 806.5 |  |  | 889.5 |  |  | 914.5 |  |  | 810.5 |  |  | 820.5 |  |  | 818.5 |  |  | 810.5 |  |  | 753.5 |  |  | 771 |  |  | 778.5 |  |  | 706.5 |  |  | 819.5 |  |  | 847.5 |  |  | 902 |  |  | 751.5 |  |  | 746.5 |  |  | 876.5 |  |  | 888.5 |  |  | 884.5 |  |  | 755.5 |  |  | 767.5 |  |  | 845.5 |  |  | 820 |  |  | 864 |  |  | 755.5 |  |  | 820.5 |  |  | 855.5 |  |  | 867 |  |  | 863.5 |  |  | 855.5 |  |  | 841.5 |  |  | 813 |  |  | 820.5 |  |  | 857.5 |  |  | 804.5 |  |  | 750.5 |  |  | 790.5 |  |  | 799.5 |  |  | 848.5 |  |  | 768.5 |  |  | 857.5 |  |  | 733 |  |  | 768.5 |  |  | 821.5 |  |  | 799.5 |  |  | 788.5 |  |  | 828.5 |  |  | 888 |  |  | 864.5 |  |  | 862.5 |  |  | 810 |  |  | 902.5 |  |  | 816.5 |  |  | 869 |  |  | 814.5 |  |  | 763.5 |  |  | 942.5 |  |  | 805.5 |  |  | 867 |  |  | 878 |  |  | 832.5 |  |  | 820.5 |  |  | 857.5 |  |  | 816.5 |  |  | 881.5 |  |  | 791.5 |  |  | 806 |  |  | 823.5 |  |  | 831.5 |  |  | 833 |  |  | 803.5 |  |  | 805.5 |  |  | 750 |  |  | 843.5 |  |  | 801.5 |  |  | 849.5 |  |  | 861 |  |  | 849.5 |  |  | 794 |  |  | 875.5 |  |  | 780.5 |  |  | 830.5 |  |  | 764 |  |  | 802.5 |  |  | 831.5 |  |  | 776.5 |  |  | 800 |  |  | 729.5 |  |  | 817.5 |  |  | 858.5 |  |  | 856.5 |  |  | 806.5 |  |  | 796 |  |  | 817.5 |  |  | 880.5 |  |  | 924.5 |  |  | 788 |  |  | 861 |  |  | 912.5 |  |  | 836.5 |  |  | 798.5 |  |  | 838.5 |  |  | 819.5 |  |  | 852.5 |  |  | 816.5 |  |  | 857.5 |  |  | 752.5 |  |  | 832.5 |  |  | 825 |  |  | 863.5 |  |  | 859.5 |  |  | 891.5 |  |  | 886.5 |  |  | 835 |  |  | 878.5 |  |  | 835.5 |  |  | 843.5 |  |  | 757.5 |  |  | 810.5 |  |  | 816 |  |  | 850 |  |  | 725 |  |  | 825 |  |  | 805.5 |  |  | 881 |  |  | 795.5 |  |  | 773 |  |  | 848.5 |  |  | 855.5 |  |  | 812.5 |  |  | 811.5 |  |  | 882.5 |  |  | 847 |  |  | 752.5 |  |  | 832.5 |  |  | 750.5 |  |  | 833 |  |  | 816.5 |  |  | 830.5 |  |  | 803.5 |  |  | 917 |  |  | 799.5 |  |  | 769.5 |  |  | 789.5 |  |  | 818.5 |  |  | 789.5 |  |  | 781.5 |  |  | 905.5 |  |  | 768.5 |  |  | 804.5 |  |  | 772.5 |  |  | 757 |  |  | 790.5 |  |  | 851.5 |  |  | 817.5 |  |  | 809.5 |  |  | 905.5 |  |  | 774 |  |  | 745.5 |  |  | 851 |  |  | 832 |  |  | 786.5 |  |  | 915.5 |  |  | 799.5 |  |  | 795 |  |  | 876.5 |  |  | 881.5 |  |  | 798.5 |  |  | 766 |  |  | 783.5 |  |  | 743.5 |  |  | 874.5 |  |  | 773.5 |  |  | 772.5 |  |  | 809 |  |  | 795.5 |  |  | 831 |  |  | 854.5 |  |  | 821.5 |  |  | 859.5 |  |  | 948 |  |  | 787.5 |  |  | 849 |  |  | 848 |  |  | 820.5 |  |  | 814.5 |  |  | 830.5 |  |  | 864.5 |  |  | 879 |  |  | 857.5 |  |  | 836.5 |  |  | 796.5 |  |  | 837 |  |  | 900.5 |  |  | 747.5 |  |  | 776.5 |  |  | 839.5 |  |  | 840 |  |  | 742.5 |  |  | 790.5 |  |  | 842.5 |  |  | 840.5 |  |  | 828.5 |  |  | 866.5 |  |  | 864 |  |  | 807.5 |  |  | 784.5 |  |  | 819 |  |  | 797.5 |  |  | 807.5 |  |  | 832.5 |  |  | 869 |  |  | 797.5 |  |  | 821.5 |  |  | 853.5 |  |  | 848.5 |  |  | 830.5 |  |  | 879 |  |  | 779 |  |  | 782.5 |  |  | 849.5 |  |  | 825.5 |  |  | 821.5 |  |  | 803 |  |  | 830 |  |  | 785 |  |  | 879.5 |  |  | 819 |  |  | 906.5 |  |  | 853.5 |  |  | 850 |  |  | 748.5 |  |  | 848.5 |  |  | 790.5 |  |  | 920.5 |  |  | 764.5 |  |  | 822 |  |  | 856 |  |  | 732.5 |  |  | 811.5 |  |  | 815 |  |  | 711.5 |  |  | 899.5 |  |  | 846 |  |  | 898.5 |  |  | 932.5 |  |  | 732 |  |  | 841.5 |  |  | 854.5 |  |  | 774 |  |  | 838.5 |  |  | 773 |  |  | 866.5 |  |  | 882 |  |  | 770.5 |  |  | 848.5 |  |  | 852.5 |  |  | 828.5 |  |  | 812.5 |  |  | 839.5 |  |  | 883 |  |  | 825.5 |  |  | 874.5 |  |  | 773.5 |  |  | 873.5 |  |  | 797.5 |  |  | 811 |  |  | 791.5 |  |  | 805 |  |  | 857.5 |  |  | 800.5 |  |  | 830.5 |  |  | 761.5 |  |  | 794.5 |  |  | 809.5 |  |  | 775.5 |  |  | 882.5 |  |  | 845.5 |  |  | 848 |  |  | 831.5 |  |  | 778 |  |  | 832 |  |  | 766.5 |  |  | 731 |  |  | 803.5 |  |  | 773.5 |  |  | 837.5 |  |  | 844.5 |  |  | 858.5 |  |  | 886.5 |  |  | 889.5 |  |  | 820 |  |  | 855 |  |  | 757.5 |  |  | 784.5 |  |  | 760 |  |  | 775.5 |  |  | 859.5 |  |  | 792.5 |  |  | 764.5 |  |  | 790.5 |  |  | 804 |  |  | 805.5 |  |  | 837.5 |  |  | 840.5 |  |  | 815 |  |  | 829.5 |  |  | 869.5 |  |  | 863.5 |  |  | 883.5 |  |  | 842.5 |  |  | 777.5 |  |  | 896.5 |  |  | 729.5 |  |  | 832.5 |  |  | 795 |  |  | 861.5 |  |  | 821.5 |  |  | 845.5 |  |  | 847.5 |  |  | 754.5 |  |  | 793.5 |  |  | 812.5 |  |  | 770 |  |  | 794.5 |  |  | 859.5 |  |  | 860.5 |  |  | 774 |  |  | 789.5 |  |  | 798 |  |  | 820.5 |  |  | 838.5 |  |  | 805.5 |  |  | 807 |  |  | 763.5 |  |  | 828 |  |  | 828 |  |  | 890.5 |  |  | 804 |  |  | 859 |  |  | 921.5 |  |  | 879.5 |  |  | 827.5 |  |  | 822 |  |  | 856.5 |  |  | 835.5 |  |  | 776.5 |  |  | 878.5 |  |  | 805.5 |  |  | 871.5 |  |  | 794.5 |  |  | 840.5 |  |  | 794 |  |  | 944.5 |  |  | 703 |  |  | 817.5 |  |  | 702.5 |  |  | 872.5 |  |  | 814 |  |  | 860 |  |  | 894 |  |  | 840.5 |  |  | 819 |  |  | 823.5 |  |  | 880.5 |  |  | 761.5 |  |  | 843.5 |  |  | 813.5 |  |  | 860.5 |  |  | 815.5 |  |  | 796.5 |  |  | 884 |  |  | 779.5 |  |  | 755.5 |  |  | 839.5 |  |  | 799.5 |  |  | 758 |  |  | 813.5 |  |  | 884 |  |  | 799.5 |  |  | 788.5 |  |  | 827.5 |  |  | 783.5 |  |  | 817 |  |  | 769.5 |  |  | 769 |  |  | 799.5 |  |  | 844.5 |  |  | 902.5 |  |  | 794.5 |  |  | 839.5 |  |  | 831.5 |  |  | 817.5 |  |  | 848.5 |  |  | 724.5 |  |  | 878 |  |  | 828.5 |  |  | 772.5 |  |  | 765.5 |  |  | 826.5 |  |  | 830.5 |  |  | 741 |  |  | 818 |  |  | 843.5 |  |  | 805 |  |  | 871.5 |  |  | 821.5 |  |  | 858.5 |  |  | 888.5 |  |  | 826.5 |  |  | 822.5 |  |  | 827.5 |  |  | 849.5 |  |  | 816 |  |  | 871.5 |  |  | 894.5 |  |  | 870.5 |  |  | 798 |  |  | 888.5 |  |  | 777.5 |  |  | 909 |  |  | 741 |  |  | 854.5 |  |  | 734 |  |  | 783 |  |  | 764.5 |  |  | 779 |  |  | 891.5 |  |  | 849.5 |  |  | 837.5 |  |  | 846.5 |  |  | 773.5 |  |  | 841.5 |  |  | 696.5 |  |  | 840.5 |  |  | 786.5 |  |  | 803.5 |  |  | 852 |  |  | 787 |  |  | 802.5 |  |  | 777.5 |  |  | 837.5 |  |  | 860.5 |  |  | 788.5 |  |  | 906.5 |  |  | 842.5 |  |  | 780.5 |  |  | 833 |  |  | 765.5 |  |  | 782 |  |  | 782.5 |  |  | 960.5 |  |  | 837.5 |  |  | 893 |  |  | 804.5 |  |  | 836.5 |  |  | 708 |  |  | 851.5 |  |  | 772.5 |  |  | 847.5 |  |  | 820.5 |  |  | 797.5 |  |  | 760.5 |  |  | 772 |  |  | 887.5 |  |  | 765.5 |  |  | 876.5 |  |  | 877.5 |  |  | 780 |  |  | 781.5 |  |  | 882.5 |  |  | 795 |  |  | 832.5 |  |  | 818.5 |  |  | 817 |  |  | 804.5 |  |  | 833.5 |  |  | 838.5 |  |  | 799 |  |  | 744.5 |  |  | 842.5 |  |  | 767 |  |  | 802.5 |  |  | 813.5 |  |  | 812.5 |  |  | 702.5 |  |  | 881.5 |  |  | 922.5 |  |  | 817.5 |  |  | 850 |  |  | 830 |  |  | 746.5 |  |  | 834.5 |  |  | 801.5 |  |  | 829 |  |  | 851.5 |  |  | 834.5 |  |  | 876.5 |  |  | 774.5 |  |  | 825.5 |  |  | 806.5 |  |  | 723.5 |  |  | 804.5 |  |  | 775.5 |  |  | 831 |  |  | 814.5 |  |  | 817.5 |  |  | 749.5 |  |  | 852.5 |  |  | 873.5 |  |  | 789.5 |  |  | 827.5 |  |  | 892.5 |  |  | 811.5 |  |  | 796.5 |  |  | 782.5 |  |  | 819.5 |  |  | 854.5 |  |  | 895 |  |  | 829.5 |  |  | 858.5 |  |  | 809 |  |  | 862.5 |  |  | 864.5 |  |  | 894 |  |  | 825.5 |  |  | 870.5 |  |  | 914.5 |  |  | 889 |  |  | 811.5 |  |  | 823.5 |  |  | 829.5 |  |  | 670.5 |  |  | 831.5 |  |  | 769 |  |  | 826.5 |  |  | 853 |  |  | 768 |  |  | 881.5 |  |  | 844.5 |  |  | 794.5 |  |  | 756.5 |  |  | 804.5 |  |  | 806.5 |  |  | 807 |  |  | 802.5 |  |  | 886 |  |  | 817.5 |  |  | 855 |  |  | 816 |  |  | 879 |  |  | 788.5 |  |  | 761 |  |  | 848.5 |  |  | 907.5 |  |  | 835.5 |  |  | 952.5 |  |  | 873.5 |  |  | 831 |  |  | 873.5 |  |  | 867.5 |  |  | 935.5 |  |  | 883 |  |  | 860.5 |  |  | 857.5 |  |  | 855.5 |  |  | 882.5 |  |  | 774 |  |  | 813 |  |  | 801 |  |  | 835.5 |  |  | 848 |  |  | 832 |  |  | 858.5 |  |  | 836.5 |  |  | 753.5 |  |  | 861.5 |  |  | 861.5 |  |  | 912.5 |  |  | 802.5 |  |  | 837.5 |  |  | 772.5 |  |  | 779 |  |  | 857.5 |  |  | 841 |  |  | 851.5 |  |  | 818.5 |  |  | 862.5 |  |  | 835.5 |  |  | 793 |  |  | 805.5 |  |  | 837 |  |  | 803.5 |  |  | 804.5 |  |  | 720 |  |  | 885 |  |  | 827.5 |  |  | 830 |  |  | 912.5 |  |  | 712.5 |  |  | 838.5 |  |  | 821.5 |  |  | 840.5 |  |  | 807.5 |  |  | 815.5 |  |  | 764 |  |  | 823.5 |  |  | 863.5 |  |  | 774.5 |  |  | 820.5 |  |  | 818.5 |  |  | 814.5 |  |  | 846.5 |  |  | 790.5 |  |  | 819.5 |  |  | 848.5 |  |  | 849.5 |  |  | 762.5 |  |  | 919 |  |  | 747.5 |  |  | 800.5 |  |  | 879 |  |  | 745.5 |  |  | 725.5 |  |  | 775.5 |  |  | 801.5 |  |  | 874 |  |  | 860.5 |  |  | 803.5 |  |  | 804.5 |  |  | 851.5 |  |  | 785 |  |  | 838.5 |  |  | 844.5 |  |  | 779.5 |  |  | 882.5 |  |  | 842.5 |  |  | 774.5 |  |  | 886.5 |  |  | 833.5 |  |  | 854.5 |  |  | 795.5 |  |  | 892.5 |  |  | 883 |  |  | 857.5 |  |  | 848.5 |  |  | 872.5 |  |  | 829.5 |  |  | 751.5 |  |  | 780.5 |  |  | 860 |  |  | 776.5 |  |  | 784 |  |  | 806.5 |  |  | 875.5 |  |  | 785.5 |  |  | 806 |  |  | 818 |  |  | 839.5 |  |  | 824.5 |  |  | 783.5 |  |  | 819.5 |  |  | 776.5 |  |  | 767.5 |  |  | 821.5 |  |  | 757.5 |  |  | 886.5 |  |  | 889.5 |  |  | 799.5 |  |  | 899.5 |  |  | 815.5 |  |  | 837.5 |  |  | 815.5 |  |  | 843.5 |  |  | 805.5 |  |  | 773.5 |  |  | 843.5 |  |  | 832.5 |  |  | 849.5 |  |  | 891.5 |  |  | 856 |  |  | 920.5 |  |  | 785.5 |  |  | 825.5 |  |  | 809 |  |  | 845.5 |  |  | 854.5 |  |  | 830.5 |  |  | 851.5 |  |  | 850 |  |  | 769.5 |  |  | 807.5 |  |  | 776 |  |  | 784 |  |  | 804 |  |  | 830.5 |  |  | 841.5 |  |  | 823.5 |  |  | 852.5 |  |  | 840 |  |  | 820.5 |  |  | 852.5 |  |  | 786 |  |  | 780 |  |  | 852.5 |  |  | 841.5 |  |  | 816 |  |  | 789.5 |  |  | 809 |  |  | 764.5 |  |  | 771.5 |  |  | 819 |  |  | 873.5 |  |  | 779.5 |  |  | 754.5 |  |  | 906 |  |  | 889.5 |  |  | 817.5 |  |  | 795.5 |  |  | 812.5 |  |  | 826.5 |  |  | 837.5 |  |  | 741.5 |  |  | 837.5 |  |  | 843.5 |  |  | 833.5 |  |  | 835 |  |  | 782.5 |  |  | 842.5 |  |  | 877.5 |  |  | 855.5 |  |  | 806.5 |  |  | 893.5 |  |  | 909.5 |  |  | 827.5 |  |  | 873 |  |  | 856.5 |  |  | 857 |  |  | 865.5 |  |  | 903.5 |  |  | 883.5 |  |  | 862.5 |  |  | 875.5 |  |  | 766.5 |  |  | 706.5 |  |  | 823.5 |  |  | 806 |  |  | 832.5 |  |  | 767 |  |  | 820.5 |  |  | 767.5 |  |  | 882.5 |  |  | 919 |  |  | 804.5 |  |  | 843.5 |  |  | 808 |  |  | 809.5 |  |  | 797 |  |  | 792.5 |  |  | 833.5 |  |  | 816.5 |  |  | 780 |  |  | 791.5 |  |  | 914.5 |  |  | 766 |  |  | 870.5 |  |  | 761.5 |  |  | 833 |  |  | 814.5 |  |  | 923.5 |  |  | 829.5 |  |  | 845.5 |  |  | 837.5 |  |  | 819.5 |  |  | 772.5 |  |  | 837.5 |  |  | 748.5 |  |  | 836.5 |  |  | 885.5 |  |  | 780 |  |  | 913 |  |  | 832.5 |  |  | 843.5 |  |  | 873
30 |  | 896.5 |  |  | 930.5 |  |  | 885 |  |  | 847.5 |  |  | 895.5 |  |  | 903.5 |  |  | 964.5 |  |  | 840.5 |  |  | 849.5 |  |  | 864.5 |  |  | 834 |  |  | 890.5 |  |  | 929.5 |  |  | 847.5 |  |  | 769 |  |  | 917.5 |  |  | 896.5 |  |  | 881.5 |  |  | 947.5 |  |  | 799.5 |  |  | 844.5 |  |  | 825.5 |  |  | 867.5 |  |  | 836.5 |  |  | 822 |  |  | 919.5 |  |  | 799.5 |  |  | 830.5 |  |  | 835.5 |  |  | 782 |  |  | 858 |  |  | 827.5 |  |  | 772.5 |  |  | 847.5 |  |  | 738.5 |  |  | 837 |  |  | 852.5 |  |  | 839 |  |  | 826.5 |  |  | 880.5 |  |  | 831.5 |  |  | 894.5 |  |  | 847.5 |  |  | 825 |  |  | 975.5 |  |  | 950 |  |  | 819.5 |  |  | 884.5 |  |  | 839.5 |  |  | 816.5 |  |  | 867.5 |  |  | 855.5 |  |  | 828.5 |  |  | 856.5 |  |  | 857.5 |  |  | 834.5 |  |  | 808.5 |  |  | 861 |  |  | 884.5 |  |  | 832.5 |  |  | 837 |  |  | 791.5 |  |  | 920.5 |  |  | 867.5 |  |  | 809.5 |  |  | 860 |  |  | 863.5 |  |  | 785 |  |  | 838.5 |  |  | 870.5 |  |  | 891 |  |  | 841.5 |  |  | 854.5 |  |  | 901.5 |  |  | 894 |  |  | 827 |  |  | 875.5 |  |  | 794.5 |  |  | 758.5 |  |  | 842.5 |  |  | 826 |  |  | 800.5 |  |  | 896.5 |  |  | 914.5 |  |  | 882.5 |  |  | 921.5 |  |  | 921.5 |  |  | 817.5 |  |  | 803.5 |  |  | 887.5 |  |  | 890.5 |  |  | 841 |  |  | 842.5 |  |  | 826 |  |  | 841 |  |  | 831 |  |  | 903.5 |  |  | 829.5 |  |  | 803.5 |  |  | 851.5 |  |  | 871.5 |  |  | 895 |  |  | 932 |  |  | 816.5 |  |  | 843.5 |  |  | 828.5 |  |  | 856.5 |  |  | 906.5 |  |  | 891.5 |  |  | 884.5 |  |  | 918.5 |  |  | 838.5 |  |  | 919.5 |  |  | 899.5 |  |  | 908.5 |  |  | 873.5 |  |  | 848.5 |  |  | 841.5 |  |  | 869.5 |  |  | 908.5 |  |  | 870.5 |  |  | 865.5 |  |  | 861.5 |  |  | 851.5 |  |  | 876.5 |  |  | 928 |  |  | 815.5 |  |  | 905.5 |  |  | 807.5 |  |  | 805.5 |  |  | 924.5 |  |  | 842 |  |  | 813.5 |  |  | 932.5 |  |  | 801.5 |  |  | 886.5 |  |  | 834 |  |  | 837.5 |  |  | 916.5 |  |  | 858 |  |  | 886.5 |  |  | 806 |  |  | 844 |  |  | 921.5 |  |  | 849 |  |  | 916.5 |  |  | 810.5 |  |  | 865.5 |  |  | 820.5 |  |  | 883.5 |  |  | 887.5 |  |  | 867.5 |  |  | 868.5 |  |  | 913.5 |  |  | 877.5 |  |  | 875 |  |  | 793.5 |  |  | 817 |  |  | 813.5 |  |  | 890.5 |  |  | 878 |  |  | 852.5 |  |  | 843.5 |  |  | 816.5 |  |  | 854 |  |  | 849.5 |  |  | 785.5 |  |  | 854.5 |  |  | 882.5 |  |  | 850.5 |  |  | 813.5 |  |  | 836 |  |  | 839.5 |  |  | 844.5 |  |  | 815.5 |  |  | 844.5 |  |  | 907.5 |  |  | 898.5 |  |  | 834.5 |  |  | 936 |  |  | 886.5 |  |  | 807.5 |  |  | 907.5 |  |  | 873.5 |  |  | 774.5 |  |  | 944.5 |  |  | 867.5 |  |  | 872.5 |  |  | 849.5 |  |  | 809.5 |  |  | 830.5 |  |  | 740.5 |  |  | 791.5 |  |  | 832 |  |  | 843.5 |  |  | 865.5 |  |  | 836.5 |  |  | 837.5 |  |  | 936.5 |  |  | 882.5 |  |  | 882.5 |  |  | 822.5 |  |  | 791.5 |  |  | 899.5 |  |  | 870.5 |  |  | 947.5 |  |  | 791.5 |  |  | 819.5 |  |  | 916.5 |  |  | 903.5 |  |  | 861 |  |  | 894.5 |  |  | 828.5 |  |  | 791 |  |  | 905.5 |  |  | 841 |  |  | 835.5 |  |  | 915.5 |  |  | 938.5 |  |  | 857.5 |  |  | 859.5 |  |  | 857.5 |  |  | 825.5 |  |  | 782.5 |  |  | 786 |  |  | 825.5 |  |  | 721.5 |  |  | 843.5 |  |  | 868.5 |  |  | 949 |  |  | 798.5 |  |  | 785.5 |  |  | 923.5 |  |  | 912.5 |  |  | 908.5 |  |  | 794.5 |  |  | 793.5 |  |  | 866.5 |  |  | 844 |  |  | 890 |  |  | 784.5 |  |  | 859.5 |  |  | 884.5 |  |  | 893 |  |  | 910.5 |  |  | 894.5 |  |  | 862.5 |  |  | 839 |  |  | 859.5 |  |  | 904.5 |  |  | 819.5 |  |  | 765.5 |  |  | 829.5 |  |  | 838.5 |  |  | 877.5 |  |  | 807.5 |  |  | 896.5 |  |  | 772 |  |  | 783.5 |  |  | 847.5 |  |  | 820.5 |  |  | 803.5 |  |  | 857.5 |  |  | 927 |  |  | 879.5 |  |  | 901.5 |  |  | 849 |  |  | 928.5 |  |  | 855.5 |  |  | 898 |  |  | 853.5 |  |  | 810.5 |  |  | 989.5 |  |  | 844.5 |  |  | 914 |  |  | 904 |  |  | 858.5 |  |  | 841.5 |  |  | 886.5 |  |  | 837.5 |  |  | 905.5 |  |  | 806.5 |  |  | 821 |  |  | 862.5 |  |  | 860.5 |  |  | 854 |  |  | 842.5 |  |  | 844.5 |  |  | 797 |  |  | 867.5 |  |  | 825.5 |  |  | 875.5 |  |  | 908 |  |  | 878.5 |  |  | 818 |  |  | 904.5 |  |  | 806.5 |  |  | 877.5 |  |  | 785 |  |  | 823.5 |  |  | 878.5 |  |  | 805.5 |  |  | 824 |  |  | 768.5 |  |  | 841.5 |  |  | 879.5 |  |  | 877.5 |  |  | 835.5 |  |  | 822 |  |  | 856.5 |  |  | 927.5 |  |  | 948.5 |  |  | 814 |  |  | 885 |  |  | 933.5 |  |  | 857.5 |  |  | 819.5 |  |  | 885.5 |  |  | 840.5 |  |  | 867.5 |  |  | 845.5 |  |  | 881.5 |  |  | 778.5 |  |  | 861.5 |  |  | 840 |  |  | 878.5 |  |  | 880.5 |  |  | 930.5 |  |  | 907.5 |  |  | 856 |  |  | 907.5 |  |  | 882.5 |  |  | 872.5 |  |  | 804.5 |  |  | 831.5 |  |  | 840 |  |  | 876 |  |  | 751 |  |  | 840 |  |  | 834.5 |  |  | 896 |  |  | 810.5 |  |  | 802 |  |  | 869.5 |  |  | 902.5 |  |  | 838.5 |  |  | 858.5 |  |  | 897.5 |  |  | 871 |  |  | 791.5 |  |  | 871.5 |  |  | 774.5 |  |  | 854 |  |  | 863.5 |  |  | 859.5 |  |  | 827.5 |  |  | 932 |  |  | 838.5 |  |  | 798.5 |  |  | 815.5 |  |  | 839.5 |  |  | 810.5 |  |  | 796.5 |  |  | 920.5 |  |  | 794.5 |  |  | 833.5 |  |  | 811.5 |  |  | 781 |  |  | 837.5 |  |  | 890.5 |  |  | 864.5 |  |  | 848.5 |  |  | 952.5 |  |  | 813 |  |  | 792.5 |  |  | 890 |  |  | 847 |  |  | 825.5 |  |  | 954.5 |  |  | 838.5 |  |  | 834 |  |  | 900.5 |  |  | 920.5 |  |  | 845.5 |  |  | 805 |  |  | 809.5 |  |  | 790.5 |  |  | 900.5 |  |  | 797.5 |  |  | 798.5 |  |  | 856 |  |  | 816.5 |  |  | 855 |  |  | 878.5 |  |  | 860.5 |  |  | 880.5 |  |  | 963 |  |  | 816.5 |  |  | 896 |  |  | 887 |  |  | 859.5 |  |  | 829.5 |  |  | 851.5 |  |  | 903.5 |  |  | 900 |  |  | 886.5 |  |  | 875.5 |  |  | 817.5 |  |  | 876 |  |  | 915.5 |  |  | 786.5 |  |  | 797.5 |  |  | 868.5 |  |  | 887 |  |  | 766.5 |  |  | 816.5 |  |  | 881.5 |  |  | 864.5 |  |  | 843.5 |  |  | 905.5 |  |  | 888 |  |  | 833.5 |  |  | 813.5 |  |  | 834 |  |  | 826.5 |  |  | 831.5 |  |  | 847.5 |  |  | 908 |  |  | 823.5 |  |  | 845.5 |  |  | 892.5 |  |  | 874.5 |  |  | 856.5 |  |  | 903 |  |  | 818 |  |  | 797.5 |  |  | 888.5 |  |  | 872.5 |  |  | 850.5 |  |  | 824 |  |  | 851 |  |  | 806 |  |  | 908.5 |  |  | 848 |  |  | 927.5 |  |  | 892.5 |  |  | 889 |  |  | 795.5 |  |  | 872.5 |  |  | 816.5 |  |  | 944.5 |  |  | 788.5 |  |  | 851 |  |  | 871 |  |  | 753.5 |  |  | 826.5 |  |  | 841 |  |  | 740.5 |  |  | 946.5 |  |  | 861 |  |  | 945.5 |  |  | 961.5 |  |  | 779 |  |  | 880.5 |  |  | 883.5 |  |  | 800 |  |  | 885.5 |  |  | 820 |  |  | 913.5 |  |  | 921 |  |  | 785.5 |  |  | 895.5 |  |  | 873.5 |  |  | 849.5 |  |  | 838.5 |  |  | 865.5 |  |  | 922 |  |  | 840.5 |  |  | 913.5 |  |  | 797.5 |  |  | 894.5 |  |  | 812.5 |  |  | 840 |  |  | 830.5 |  |  | 834 |  |  | 881.5 |  |  | 826.5 |  |  | 869.5 |  |  | 790.5 |  |  | 815.5 |  |  | 848.5 |  |  | 799.5 |  |  | 921.5 |  |  | 871.5 |  |  | 869 |  |  | 878.5 |  |  | 804 |  |  | 861 |  |  | 805.5 |  |  | 755 |  |  | 827.5 |  |  | 802.5 |  |  | 884.5 |  |  | 891.5 |  |  | 879.5 |  |  | 915.5 |  |  | 904.5 |  |  | 867 |  |  | 902 |  |  | 778.5 |  |  | 808.5 |  |  | 807 |  |  | 801.5 |  |  | 898.5 |  |  | 818.5 |  |  | 803.5 |  |  | 819.5 |  |  | 819 |  |  | 826.5 |  |  | 866.5 |  |  | 861.5 |  |  | 830 |  |  | 858.5 |  |  | 890.5 |  |  | 889.5 |  |  | 912.5 |  |  | 889.5 |  |  | 816.5 |  |  | 943.5 |  |  | 750.5 |  |  | 861.5 |  |  | 821 |  |  | 885.5 |  |  | 836.5 |  |  | 892.5 |  |  | 876.5 |  |  | 775.5 |  |  | 808.5 |  |  | 841.5 |  |  | 785 |  |  | 815.5 |  |  | 885.5 |  |  | 907.5 |  |  | 795 |  |  | 818.5 |  |  | 813 |  |  | 846.5 |  |  | 877.5 |  |  | 831.5 |  |  | 833 |  |  | 784.5 |  |  | 852 |  |  | 854 |  |  | 911.5 |  |  | 843 |  |  | 906 |  |  | 950.5 |  |  | 894.5 |  |  | 842.5 |  |  | 861 |  |  | 880.5 |  |  | 850.5 |  |  | 797.5 |  |  | 917.5 |  |  | 820.5 |  |  | 886.5 |  |  | 823.5 |  |  | 887.5 |  |  | 833 |  |  | 970.5 |  |  | 724 |  |  | 832.5 |  |  | 731.5 |  |  | 887.5 |  |  | 840 |  |  | 899 |  |  | 918 |  |  | 866.5 |  |  | 848 |  |  | 847.5 |  |  | 909.5 |  |  | 782.5 |  |  | 858.5 |  |  | 837.5 |  |  | 889.5 |  |  | 844.5 |  |  | 835.5 |  |  | 910 |  |  | 803.5 |  |  | 776.5 |  |  | 878.5 |  |  | 820.5 |  |  | 797 |  |  | 837.5 |  |  | 908 |  |  | 823.5 |  |  | 817.5 |  |  | 842.5 |  |  | 804.5 |  |  | 832 |  |  | 793.5 |  |  | 816 |  |  | 820.5 |  |  | 865.5 |  |  | 941.5 |  |  | 841.5 |  |  | 886.5 |  |  | 855.5 |  |  | 843.5 |  |  | 874.5 |  |  | 753.5 |  |  | 917 |  |  | 867.5 |  |  | 801.5 |  |  | 789.5 |  |  | 865.5 |  |  | 856.5 |  |  | 765 |  |  | 865 |  |  | 867.5 |  |  | 831 |  |  | 910.5 |  |  | 850.5 |  |  | 882.5 |  |  | 917.5 |  |  | 855.5 |  |  | 848.5 |  |  | 853.5 |  |  | 888.5 |  |  | 845 |  |  | 910.5 |  |  | 920.5 |  |  | 899.5 |  |  | 837 |  |  | 903.5 |  |  | 816.5 |  |  | 956 |  |  | 756 |  |  | 893.5 |  |  | 758 |  |  | 807 |  |  | 790.5 |  |  | 800 |  |  | 938.5 |  |  | 896.5 |  |  | 866.5 |  |  | 885.5 |  |  | 820.5 |  |  | 880.5 |  |  | 735.5 |  |  | 879.5 |  |  | 833.5 |  |  | 850.5 |  |  | 878 |  |  | 811 |  |  | 828.5 |  |  | 803.5 |  |  | 863.5 |  |  | 899.5 |  |  | 803.5 |  |  | 930.5 |  |  | 889.5 |  |  | 806.5 |  |  | 880 |  |  | 789.5 |  |  | 806 |  |  | 821.5 |  |  | 984.5 |  |  | 876.5 |  |  | 908 |  |  | 819.5 |  |  | 851.5 |  |  | 737 |  |  | 872.5 |  |  | 798.5 |  |  | 886.5 |  |  | 835.5 |  |  | 836.5 |  |  | 807.5 |  |  | 801 |  |  | 934.5 |  |  | 780.5 |  |  | 902.5 |  |  | 916.5 |  |  | 806 |  |  | 807.5 |  |  | 929.5 |  |  | 819 |  |  | 858.5 |  |  | 833.5 |  |  | 838 |  |  | 828.5 |  |  | 872.5 |  |  | 885.5 |  |  | 820 |  |  | 759.5 |  |  | 866.5 |  |  | 791 |  |  | 823.5 |  |  | 828.5 |  |  | 851.5 |  |  | 723.5 |  |  | 907.5 |  |  | 951.5 |  |  | 843.5 |  |  | 889 |  |  | 869 |  |  | 772.5 |  |  | 873.5 |  |  | 827.5 |  |  | 844 |  |  | 866.5 |  |  | 849.5 |  |  | 900.5 |  |  | 813.5 |  |  | 846.5 |  |  | 832.5 |  |  | 747.5 |  |  | 843.5 |  |  | 801.5 |  |  | 870 |  |  | 835.5 |  |  | 864.5 |  |  | 788.5 |  |  | 891.5 |  |  | 894.5 |  |  | 813.5 |  |  | 856.5 |  |  | 916.5 |  |  | 826.5 |  |  | 843.5 |  |  | 808.5 |  |  | 858.5 |  |  | 875.5 |  |  | 942 |  |  | 876.5 |  |  | 873.5 |  |  | 830 |  |  | 888.5 |  |  | 885.5 |  |  | 920 |  |  | 846.5 |  |  | 885.5 |  |  | 929.5 |  |  | 904 |  |  | 837.5 |  |  | 870.5 |  |  | 855.5 |  |  | 709.5 |  |  | 878.5 |  |  | 798 |  |  | 841.5 |  |  | 892 |  |  | 792 |  |  | 907.5 |  |  | 868.5 |  |  | 833.5 |  |  | 780.5 |  |  | 843.5 |  |  | 832.5 |  |  | 822 |  |  | 849.5 |  |  | 933 |  |  | 838.5 |  |  | 894 |  |  | 840 |  |  | 918 |  |  | 817.5 |  |  | 776 |  |  | 874.5 |  |  | 936.5 |  |  | 859.5 |  |  | 976.5 |  |  | 888.5 |  |  | 878 |  |  | 897.5 |  |  | 906.5 |  |  | 982.5 |  |  | 912 |  |  | 886.5 |  |  | 881.5 |  |  | 902.5 |  |  | 911.5 |  |  | 789 |  |  | 839 |  |  | 840 |  |  | 874.5 |  |  | 895 |  |  | 879 |  |  | 879.5 |  |  | 865.5 |  |  | 800.5 |  |  | 876.5 |  |  | 900.5 |  |  | 959.5 |  |  | 849.5 |  |  | 884.5 |  |  | 793.5 |  |  | 805 |  |  | 878.5 |  |  | 867 |  |  | 890.5 |  |  | 844.5 |  |  | 877.5 |  |  | 856.5 |  |  | 840 |  |  | 820.5 |  |  | 861 |  |  | 832.5 |  |  | 825.5 |  |  | 749 |  |  | 906 |  |  | 866.5 |  |  | 877 |  |  | 951.5 |  |  | 751.5 |  |  | 877.5 |  |  | 868.5 |  |  | 866.5 |  |  | 833.5 |  |  | 841.5 |  |  | 803 |  |  | 862.5 |  |  | 902.5 |  |  | 800.5 |  |  | 859.5 |  |  | 839.5 |  |  | 835.5 |  |  | 870.5 |  |  | 829.5 |  |  | 840.5 |  |  | 874.5 |  |  | 873.5 |  |  | 777.5 |  |  | 943 |  |  | 771.5 |  |  | 847.5 |  |  | 900 |  |  | 760.5 |  |  | 749.5 |  |  | 801.5 |  |  | 816.5 |  |  | 895 |  |  | 881.5 |  |  | 824.5 |  |  | 833.5 |  |  | 875.5 |  |  | 800 |  |  | 853.5 |  |  | 873.5 |  |  | 818.5 |  |  | 897.5 |  |  | 871.5 |  |  | 798.5 |  |  | 901.5 |  |  | 880.5 |  |  | 875.5 |  |  | 810.5 |  |  | 931.5 |  |  | 904 |  |  | 886.5 |  |  | 877.5 |  |  | 911.5 |  |  | 876.5 |  |  | 790.5 |  |  | 801.5 |  |  | 886 |  |  | 823.5 |  |  | 813 |  |  | 832.5 |  |  | 904.5 |  |  | 824.5 |  |  | 853 |  |  | 857 |  |  | 868.5 |  |  | 871.5 |  |  | 822.5 |  |  | 845.5 |  |  | 800.5 |  |  | 793.5 |  |  | 850.5 |  |  | 796.5 |  |  | 901.5 |  |  | 915.5 |  |  | 823.5 |  |  | 914.5 |  |  | 854.5 |  |  | 866.5 |  |  | 830.5 |  |  | 882.5 |  |  | 834.5 |  |  | 812.5 |  |  | 882.5 |  |  | 853.5 |  |  | 888.5 |  |  | 920.5 |  |  | 871 |  |  | 959.5 |  |  | 811.5 |  |  | 854.5 |  |  | 838 |  |  | 866.5 |  |  | 875.5 |  |  | 854.5 |  |  | 890.5 |  |  | 897 |  |  | 784.5 |  |  | 833.5 |  |  | 800 |  |  | 799 |  |  | 833 |  |  | 869.5 |  |  | 865.5 |  |  | 862.5 |  |  | 891.5 |  |  | 855 |  |  | 835.5 |  |  | 876.5 |  |  | 801 |  |  | 809 |  |  | 878.5 |  |  | 867.5 |  |  | 840 |  |  | 828.5 |  |  | 835 |  |  | 779.5 |  |  | 795.5 |  |  | 858 |  |  | 894.5 |  |  | 818.5 |  |  | 793.5 |  |  | 927 |  |  | 904.5 |  |  | 843.5 |  |  | 821.5 |  |  | 836.5 |  |  | 855.5 |  |  | 876.5 |  |  | 788.5 |  |  | 852.5 |  |  | 882.5 |  |  | 872.5 |  |  | 874 |  |  | 803.5 |  |  | 866.5 |  |  | 892.5 |  |  | 884.5 |  |  | 821.5 |  |  | 917.5 |  |  | 948.5 |  |  | 853.5 |  |  | 894 |  |  | 877.5 |  |  | 881 |  |  | 894.5 |  |  | 942.5 |  |  | 930.5 |  |  | 883.5 |  |  | 901.5 |  |  | 805.5 |  |  | 721.5 |  |  | 847.5 |  |  | 845 |  |  | 847.5 |  |  | 788 |  |  | 849.5 |  |  | 782.5 |  |  | 908.5 |  |  | 958 |  |  | 819.5 |  |  | 882.5 |  |  | 829 |  |  | 833.5 |  |  | 823 |  |  | 816.5 |  |  | 872.5 |  |  | 855.5 |  |  | 806 |  |  | 812.5 |  |  | 961.5 |  |  | 781 |  |  | 909.5 |  |  | 800.5 |  |  | 872 |  |  | 843.5 |  |  | 947.5 |  |  | 876.5 |  |  | 892.5 |  |  | 863.5 |  |  | 834.5 |  |  | 811.5 |  |  | 852.5 |  |  | 763.5 |  |  | 875.5 |  |  | 914.5 |  |  | 819 |  |  | 939 |  |  | 871.5 |  |  | 867.5 |  |  | 912
31 |  | 911.5 |  |  | 969.5 |  |  | 906 |  |  | 871.5 |  |  | 919.5 |  |  | 942.5 |  |  | 990.5 |  |  | 879.5 |  |  | 888.5 |  |  | 911.5 |  |  | 873 |  |  | 905.5 |  |  | 976.5 |  |  | 886.5 |  |  | 816 |  |  | 941.5 |  |  | 925.5 |  |  | 920.5 |  |  | 994.5 |  |  | 825.5 |  |  | 883.5 |  |  | 854.5 |  |  | 893.5 |  |  | 851.5 |  |  | 846 |  |  | 966.5 |  |  | 838.5 |  |  | 877.5 |  |  | 864.5 |  |  | 829 |  |  | 897 |  |  | 874.5 |  |  | 819.5 |  |  | 886.5 |  |  | 762.5 |  |  | 876 |  |  | 867.5 |  |  | 860 |  |  | 852.5 |  |  | 927.5 |  |  | 857.5 |  |  | 941.5 |  |  | 871.5 |  |  | 854 |  |  | 999.5 |  |  | 979 |  |  | 858.5 |  |  | 910.5 |  |  | 878.5 |  |  | 863.5 |  |  | 896.5 |  |  | 884.5 |  |  | 867.5 |  |  | 871.5 |  |  | 896.5 |  |  | 860.5 |  |  | 834.5 |  |  | 885 |  |  | 923.5 |  |  | 853.5 |  |  | 858 |  |  | 838.5 |  |  | 941.5 |  |  | 891.5 |  |  | 835.5 |  |  | 899 |  |  | 910.5 |  |  | 814 |  |  | 859.5 |  |  | 891.5 |  |  | 930 |  |  | 888.5 |  |  | 875.5 |  |  | 940.5 |  |  | 915 |  |  | 848 |  |  | 922.5 |  |  | 823.5 |  |  | 782.5 |  |  | 881.5 |  |  | 873 |  |  | 826.5 |  |  | 911.5 |  |  | 953.5 |  |  | 906.5 |  |  | 936.5 |  |  | 968.5 |  |  | 846.5 |  |  | 842.5 |  |  | 916.5 |  |  | 919.5 |  |  | 888 |  |  | 857.5 |  |  | 847 |  |  | 880 |  |  | 855 |  |  | 932.5 |  |  | 868.5 |  |  | 850.5 |  |  | 877.5 |  |  | 900.5 |  |  | 934 |  |  | 947 |  |  | 845.5 |  |  | 864.5 |  |  | 854.5 |  |  | 895.5 |  |  | 945.5 |  |  | 930.5 |  |  | 923.5 |  |  | 933.5 |  |  | 877.5 |  |  | 958.5 |  |  | 923.5 |  |  | 923.5 |  |  | 897.5 |  |  | 887.5 |  |  | 862.5 |  |  | 893.5 |  |  | 929.5 |  |  | 917.5 |  |  | 904.5 |  |  | 885.5 |  |  | 877.5 |  |  | 915.5 |  |  | 967 |  |  | 854.5 |  |  | 926.5 |  |  | 831.5 |  |  | 831.5 |  |  | 963.5 |  |  | 881 |  |  | 834.5 |  |  | 971.5 |  |  | 816.5 |  |  | 933.5 |  |  | 873 |  |  | 884.5 |  |  | 955.5 |  |  | 897 |  |  | 907.5 |  |  | 821 |  |  | 883 |  |  | 950.5 |  |  | 873 |  |  | 931.5 |  |  | 834.5 |  |  | 904.5 |  |  | 859.5 |  |  | 909.5 |  |  | 902.5 |  |  | 906.5 |  |  | 907.5 |  |  | 934.5 |  |  | 916.5 |  |  | 899 |  |  | 817.5 |  |  | 841 |  |  | 842.5 |  |  | 916.5 |  |  | 899 |  |  | 876.5 |  |  | 858.5 |  |  | 855.5 |  |  | 880 |  |  | 888.5 |  |  | 809.5 |  |  | 878.5 |  |  | 921.5 |  |  | 874.5 |  |  | 852.5 |  |  | 883 |  |  | 860.5 |  |  | 873.5 |  |  | 841.5 |  |  | 883.5 |  |  | 936.5 |  |  | 937.5 |  |  | 873.5 |  |  | 951 |  |  | 901.5 |  |  | 836.5 |  |  | 946.5 |  |  | 920.5 |  |  | 798.5 |  |  | 983.5 |  |  | 906.5 |  |  | 911.5 |  |  | 864.5 |  |  | 833.5 |  |  | 845.5 |  |  | 769.5 |  |  | 815.5 |  |  | 858 |  |  | 867.5 |  |  | 904.5 |  |  | 860.5 |  |  | 858.5 |  |  | 975.5 |  |  | 908.5 |  |  | 903.5 |  |  | 848.5 |  |  | 830.5 |  |  | 946.5 |  |  | 896.5 |  |  | 968.5 |  |  | 830.5 |  |  | 834.5 |  |  | 955.5 |  |  | 927.5 |  |  | 900 |  |  | 923.5 |  |  | 867.5 |  |  | 806 |  |  | 929.5 |  |  | 880 |  |  | 850.5 |  |  | 936.5 |  |  | 977.5 |  |  | 896.5 |  |  | 883.5 |  |  | 878.5 |  |  | 846.5 |  |  | 811.5 |  |  | 812 |  |  | 864.5 |  |  | 742.5 |  |  | 882.5 |  |  | 889.5 |  |  | 973 |  |  | 819.5 |  |  | 811.5 |  |  | 949.5 |  |  | 933.5 |  |  | 932.5 |  |  | 823.5 |  |  | 819.5 |  |  | 887.5 |  |  | 859 |  |  | 914 |  |  | 808.5 |  |  | 898.5 |  |  | 913.5 |  |  | 922 |  |  | 957.5 |  |  | 920.5 |  |  | 891.5 |  |  | 868 |  |  | 906.5 |  |  | 933.5 |  |  | 840.5 |  |  | 786.5 |  |  | 850.5 |  |  | 877.5 |  |  | 916.5 |  |  | 831.5 |  |  | 922.5 |  |  | 796 |  |  | 830.5 |  |  | 873.5 |  |  | 867.5 |  |  | 842.5 |  |  | 896.5 |  |  | 948 |  |  | 905.5 |  |  | 948.5 |  |  | 870 |  |  | 949.5 |  |  | 884.5 |  |  | 913 |  |  | 874.5 |  |  | 857.5 |  |  | 1018.5 |  |  | 859.5 |  |  | 953 |  |  | 943 |  |  | 879.5 |  |  | 888.5 |  |  | 933.5 |  |  | 876.5 |  |  | 952.5 |  |  | 835.5 |  |  | 842 |  |  | 909.5 |  |  | 907.5 |  |  | 878 |  |  | 881.5 |  |  | 868.5 |  |  | 821 |  |  | 906.5 |  |  | 851.5 |  |  | 899.5 |  |  | 923 |  |  | 893.5 |  |  | 839 |  |  | 951.5 |  |  | 835.5 |  |  | 892.5 |  |  | 824 |  |  | 847.5 |  |  | 902.5 |  |  | 834.5 |  |  | 839 |  |  | 797.5 |  |  | 880.5 |  |  | 926.5 |  |  | 901.5 |  |  | 861.5 |  |  | 861 |  |  | 880.5 |  |  | 966.5 |  |  | 977.5 |  |  | 840 |  |  | 911 |  |  | 980.5 |  |  | 896.5 |  |  | 858.5 |  |  | 924.5 |  |  | 879.5 |  |  | 893.5 |  |  | 892.5 |  |  | 905.5 |  |  | 799.5 |  |  | 900.5 |  |  | 879 |  |  | 893.5 |  |  | 919.5 |  |  | 969.5 |  |  | 933.5 |  |  | 885 |  |  | 946.5 |  |  | 929.5 |  |  | 898.5 |  |  | 819.5 |  |  | 878.5 |  |  | 866 |  |  | 915 |  |  | 790 |  |  | 869 |  |  | 873.5 |  |  | 935 |  |  | 849.5 |  |  | 828 |  |  | 908.5 |  |  | 931.5 |  |  | 877.5 |  |  | 873.5 |  |  | 912.5 |  |  | 886 |  |  | 838.5 |  |  | 910.5 |  |  | 798.5 |  |  | 893 |  |  | 910.5 |  |  | 883.5 |  |  | 874.5 |  |  | 979 |  |  | 864.5 |  |  | 827.5 |  |  | 854.5 |  |  | 863.5 |  |  | 836.5 |  |  | 835.5 |  |  | 935.5 |  |  | 809.5 |  |  | 872.5 |  |  | 826.5 |  |  | 796 |  |  | 876.5 |  |  | 911.5 |  |  | 911.5 |  |  | 895.5 |  |  | 981.5 |  |  | 852 |  |  | 807.5 |  |  | 937 |  |  | 868 |  |  | 864.5 |  |  | 983.5 |  |  | 877.5 |  |  | 855 |  |  | 915.5 |  |  | 935.5 |  |  | 892.5 |  |  | 826 |  |  | 838.5 |  |  | 829.5 |  |  | 939.5 |  |  | 821.5 |  |  | 845.5 |  |  | 871 |  |  | 837.5 |  |  | 881 |  |  | 902.5 |  |  | 886.5 |  |  | 895.5 |  |  | 1010 |  |  | 845.5 |  |  | 925 |  |  | 913 |  |  | 888.5 |  |  | 850.5 |  |  | 872.5 |  |  | 927.5 |  |  | 929 |  |  | 907.5 |  |  | 901.5 |  |  | 846.5 |  |  | 891 |  |  | 939.5 |  |  | 810.5 |  |  | 818.5 |  |  | 883.5 |  |  | 902 |  |  | 795.5 |  |  | 855.5 |  |  | 907.5 |  |  | 903.5 |  |  | 858.5 |  |  | 934.5 |  |  | 903 |  |  | 854.5 |  |  | 852.5 |  |  | 881 |  |  | 841.5 |  |  | 870.5 |  |  | 876.5 |  |  | 947 |  |  | 862.5 |  |  | 866.5 |  |  | 907.5 |  |  | 913.5 |  |  | 882.5 |  |  | 942 |  |  | 842 |  |  | 823.5 |  |  | 909.5 |  |  | 893.5 |  |  | 874.5 |  |  | 863 |  |  | 890 |  |  | 821 |  |  | 947.5 |  |  | 874 |  |  | 951.5 |  |  | 931.5 |  |  | 928 |  |  | 819.5 |  |  | 896.5 |  |  | 840.5 |  |  | 973.5 |  |  | 827.5 |  |  | 875 |  |  | 918 |  |  | 779.5 |  |  | 855.5 |  |  | 880 |  |  | 764.5 |  |  | 975.5 |  |  | 887 |  |  | 966.5 |  |  | 976.5 |  |  | 818 |  |  | 906.5 |  |  | 922.5 |  |  | 821 |  |  | 914.5 |  |  | 849 |  |  | 934.5 |  |  | 942 |  |  | 809.5 |  |  | 924.5 |  |  | 912.5 |  |  | 888.5 |  |  | 862.5 |  |  | 886.5 |  |  | 948 |  |  | 887.5 |  |  | 928.5 |  |  | 844.5 |  |  | 920.5 |  |  | 841.5 |  |  | 866 |  |  | 877.5 |  |  | 860 |  |  | 902.5 |  |  | 865.5 |  |  | 916.5 |  |  | 829.5 |  |  | 854.5 |  |  | 872.5 |  |  | 820.5 |  |  | 960.5 |  |  | 886.5 |  |  | 908 |  |  | 907.5 |  |  | 828 |  |  | 887 |  |  | 852.5 |  |  | 784 |  |  | 866.5 |  |  | 817.5 |  |  | 923.5 |  |  | 912.5 |  |  | 926.5 |  |  | 936.5 |  |  | 919.5 |  |  | 893 |  |  | 941 |  |  | 802.5 |  |  | 837.5 |  |  | 854 |  |  | 827.5 |  |  | 922.5 |  |  | 847.5 |  |  | 850.5 |  |  | 834.5 |  |  | 866 |  |  | 865.5 |  |  | 913.5 |  |  | 887.5 |  |  | 869 |  |  | 905.5 |  |  | 919.5 |  |  | 936.5 |  |  | 951.5 |  |  | 928.5 |  |  | 831.5 |  |  | 969.5 |  |  | 765.5 |  |  | 876.5 |  |  | 850 |  |  | 924.5 |  |  | 860.5 |  |  | 921.5 |  |  | 902.5 |  |  | 814.5 |  |  | 823.5 |  |  | 865.5 |  |  | 811 |  |  | 844.5 |  |  | 900.5 |  |  | 936.5 |  |  | 824 |  |  | 839.5 |  |  | 860 |  |  | 861.5 |  |  | 903.5 |  |  | 870.5 |  |  | 862 |  |  | 823.5 |  |  | 891 |  |  | 880 |  |  | 932.5 |  |  | 858 |  |  | 921 |  |  | 989.5 |  |  | 941.5 |  |  | 868.5 |  |  | 900 |  |  | 909.5 |  |  | 865.5 |  |  | 823.5 |  |  | 938.5 |  |  | 835.5 |  |  | 925.5 |  |  | 870.5 |  |  | 913.5 |  |  | 848 |  |  | 999.5 |  |  | 771 |  |  | 856.5 |  |  | 770.5 |  |  | 916.5 |  |  | 887 |  |  | 938 |  |  | 957 |  |  | 905.5 |  |  | 863 |  |  | 894.5 |  |  | 956.5 |  |  | 803.5 |  |  | 879.5 |  |  | 876.5 |  |  | 904.5 |  |  | 865.5 |  |  | 882.5 |  |  | 949 |  |  | 827.5 |  |  | 800.5 |  |  | 902.5 |  |  | 849.5 |  |  | 818 |  |  | 876.5 |  |  | 923 |  |  | 849.5 |  |  | 856.5 |  |  | 881.5 |  |  | 825.5 |  |  | 879 |  |  | 832.5 |  |  | 831 |  |  | 835.5 |  |  | 912.5 |  |  | 967.5 |  |  | 880.5 |  |  | 901.5 |  |  | 876.5 |  |  | 872.5 |  |  | 903.5 |  |  | 768.5 |  |  | 932 |  |  | 891.5 |  |  | 825.5 |  |  | 818.5 |  |  | 891.5 |  |  | 871.5 |  |  | 791 |  |  | 904 |  |  | 882.5 |  |  | 852 |  |  | 936.5 |  |  | 865.5 |  |  | 911.5 |  |  | 946.5 |  |  | 876.5 |  |  | 895.5 |  |  | 879.5 |  |  | 927.5 |  |  | 860 |  |  | 957.5 |  |  | 959.5 |  |  | 925.5 |  |  | 852 |  |  | 942.5 |  |  | 845.5 |  |  | 977 |  |  | 803 |  |  | 917.5 |  |  | 805 |  |  | 828 |  |  | 816.5 |  |  | 839 |  |  | 977.5 |  |  | 925.5 |  |  | 895.5 |  |  | 932.5 |  |  | 849.5 |  |  | 919.5 |  |  | 764.5 |  |  | 918.5 |  |  | 848.5 |  |  | 874.5 |  |  | 907 |  |  | 840 |  |  | 849.5 |  |  | 827.5 |  |  | 892.5 |  |  | 928.5 |  |  | 824.5 |  |  | 969.5 |  |  | 904.5 |  |  | 853.5 |  |  | 919 |  |  | 818.5 |  |  | 827 |  |  | 836.5 |  |  | 1031.5 |  |  | 915.5 |  |  | 923 |  |  | 848.5 |  |  | 875.5 |  |  | 776 |  |  | 898.5 |  |  | 845.5 |  |  | 907.5 |  |  | 882.5 |  |  | 883.5 |  |  | 854.5 |  |  | 840 |  |  | 955.5 |  |  | 806.5 |  |  | 917.5 |  |  | 963.5 |  |  | 832 |  |  | 846.5 |  |  | 953.5 |  |  | 858 |  |  | 905.5 |  |  | 872.5 |  |  | 885 |  |  | 875.5 |  |  | 901.5 |  |  | 932.5 |  |  | 859 |  |  | 798.5 |  |  | 892.5 |  |  | 838 |  |  | 838.5 |  |  | 843.5 |  |  | 866.5 |  |  | 770.5 |  |  | 946.5 |  |  | 998.5 |  |  | 882.5 |  |  | 910 |  |  | 893 |  |  | 798.5 |  |  | 912.5 |  |  | 866.5 |  |  | 868 |  |  | 890.5 |  |  | 888.5 |  |  | 924.5 |  |  | 837.5 |  |  | 861.5 |  |  | 853.5 |  |  | 794.5 |  |  | 864.5 |  |  | 827.5 |  |  | 909 |  |  | 859.5 |  |  | 879.5 |  |  | 814.5 |  |  | 930.5 |  |  | 933.5 |  |  | 852.5 |  |  | 877.5 |  |  | 955.5 |  |  | 841.5 |  |  | 882.5 |  |  | 847.5 |  |  | 887.5 |  |  | 901.5 |  |  | 957 |  |  | 905.5 |  |  | 902.5 |  |  | 856 |  |  | 903.5 |  |  | 924.5 |  |  | 949 |  |  | 885.5 |  |  | 924.5 |  |  | 950.5 |  |  | 933 |  |  | 876.5 |  |  | 917.5 |  |  | 876.5 |  |  | 748.5 |  |  | 899.5 |  |  | 813 |  |  | 880.5 |  |  | 931 |  |  | 831 |  |  | 946.5 |  |  | 907.5 |  |  | 857.5 |  |  | 804.5 |  |  | 890.5 |  |  | 879.5 |  |  | 846 |  |  | 873.5 |  |  | 959 |  |  | 864.5 |  |  | 915 |  |  | 864 |  |  | 957 |  |  | 856.5 |  |  | 815 |  |  | 921.5 |  |  | 957.5 |  |  | 906.5 |  |  | 1023.5 |  |  | 927.5 |  |  | 899 |  |  | 918.5 |  |  | 945.5 |  |  | 1006.5 |  |  | 936 |  |  | 925.5 |  |  | 910.5 |  |  | 928.5 |  |  | 950.5 |  |  | 810 |  |  | 863 |  |  | 866 |  |  | 903.5 |  |  | 910 |  |  | 908 |  |  | 894.5 |  |  | 880.5 |  |  | 824.5 |  |  | 923.5 |  |  | 947.5 |  |  | 974.5 |  |  | 896.5 |  |  | 899.5 |  |  | 840.5 |  |  | 844 |  |  | 917.5 |  |  | 893 |  |  | 929.5 |  |  | 883.5 |  |  | 916.5 |  |  | 903.5 |  |  | 887 |  |  | 859.5 |  |  | 876 |  |  | 871.5 |  |  | 840.5 |  |  | 773 |  |  | 921 |  |  | 881.5 |  |  | 916 |  |  | 977.5 |  |  | 766.5 |  |  | 898.5 |  |  | 883.5 |  |  | 895.5 |  |  | 872.5 |  |  | 888.5 |  |  | 842 |  |  | 883.5 |  |  | 923.5 |  |  | 815.5 |  |  | 898.5 |  |  | 878.5 |  |  | 859.5 |  |  | 885.5 |  |  | 868.5 |  |  | 864.5 |  |  | 903.5 |  |  | 894.5 |  |  | 806.5 |  |  | 972 |  |  | 797.5 |  |  | 876.5 |  |  | 921 |  |  | 775.5 |  |  | 775.5 |  |  | 848.5 |  |  | 842.5 |  |  | 934 |  |  | 907.5 |  |  | 853.5 |  |  | 848.5 |  |  | 914.5 |  |  | 826 |  |  | 877.5 |  |  | 912.5 |  |  | 857.5 |  |  | 936.5 |  |  | 886.5 |  |  | 827.5 |  |  | 940.5 |  |  | 901.5 |  |  | 914.5 |  |  | 857.5 |  |  | 952.5 |  |  | 930 |  |  | 915.5 |  |  | 906.5 |  |  | 937.5 |  |  | 915.5 |  |  | 837.5 |  |  | 840.5 |  |  | 925 |  |  | 870.5 |  |  | 852 |  |  | 847.5 |  |  | 919.5 |  |  | 863.5 |  |  | 892 |  |  | 896 |  |  | 892.5 |  |  | 886.5 |  |  | 843.5 |  |  | 871.5 |  |  | 839.5 |  |  | 814.5 |  |  | 871.5 |  |  | 825.5 |  |  | 922.5 |  |  | 936.5 |  |  | 862.5 |  |  | 938.5 |  |  | 878.5 |  |  | 905.5 |  |  | 877.5 |  |  | 921.5 |  |  | 863.5 |  |  | 851.5 |  |  | 903.5 |  |  | 882.5 |  |  | 914.5 |  |  | 935.5 |  |  | 910 |  |  | 974.5 |  |  | 832.5 |  |  | 893.5 |  |  | 862 |  |  | 913.5 |  |  | 914.5 |  |  | 875.5 |  |  | 929.5 |  |  | 923 |  |  | 813.5 |  |  | 872.5 |  |  | 847 |  |  | 828 |  |  | 857 |  |  | 895.5 |  |  | 912.5 |  |  | 883.5 |  |  | 915.5 |  |  | 876 |  |  | 859.5 |  |  | 900.5 |  |  | 840 |  |  | 856 |  |  | 904.5 |  |  | 893.5 |  |  | 866 |  |  | 852.5 |  |  | 882 |  |  | 808.5 |  |  | 824.5 |  |  | 897 |  |  | 915.5 |  |  | 839.5 |  |  | 808.5 |  |  | 942 |  |  | 928.5 |  |  | 872.5 |  |  | 847.5 |  |  | 851.5 |  |  | 884.5 |  |  | 905.5 |  |  | 803.5 |  |  | 891.5 |  |  | 929.5 |  |  | 911.5 |  |  | 913 |  |  | 829.5 |  |  | 890.5 |  |  | 916.5 |  |  | 931.5 |  |  | 847.5 |  |  | 932.5 |  |  | 969.5 |  |  | 882.5 |  |  | 933 |  |  | 892.5 |  |  | 896 |  |  | 933.5 |  |  | 968.5 |  |  | 956.5 |  |  | 907.5 |  |  | 940.5 |  |  | 820.5 |  |  | 768.5 |  |  | 862.5 |  |  | 884 |  |  | 876.5 |  |  | 817 |  |  | 873.5 |  |  | 829.5 |  |  | 934.5 |  |  | 984 |  |  | 858.5 |  |  | 921.5 |  |  | 844 |  |  | 859.5 |  |  | 870 |  |  | 831.5 |  |  | 911.5 |  |  | 870.5 |  |  | 845 |  |  | 836.5 |  |  | 1000.5 |  |  | 796 |  |  | 948.5 |  |  | 821.5 |  |  | 901 |  |  | 864.5 |  |  | 994.5 |  |  | 923.5 |  |  | 931.5 |  |  | 887.5 |  |  | 849.5 |  |  | 850.5 |  |  | 891.5 |  |  | 810.5 |  |  | 901.5 |  |  | 953.5 |  |  | 858 |  |  | 986 |  |  | 918.5 |  |  | 891.5 |  |  | 959
32 |  | 958.5 |  |  | 995.5 |  |  | 945 |  |  | 918.5 |  |  | 966.5 |  |  | 957.5 |  |  | 1014.5 |  |  | 918.5 |  |  | 914.5 |  |  | 935.5 |  |  | 902 |  |  | 944.5 |  |  | 1002.5 |  |  | 910.5 |  |  | 855 |  |  | 956.5 |  |  | 964.5 |  |  | 949.5 |  |  | 1015.5 |  |  | 854.5 |  |  | 907.5 |  |  | 875.5 |  |  | 932.5 |  |  | 872.5 |  |  | 872 |  |  | 987.5 |  |  | 864.5 |  |  | 906.5 |  |  | 885.5 |  |  | 853 |  |  | 936 |  |  | 900.5 |  |  | 858.5 |  |  | 910.5 |  |  | 801.5 |  |  | 900 |  |  | 888.5 |  |  | 899 |  |  | 899.5 |  |  | 966.5 |  |  | 886.5 |  |  | 970.5 |  |  | 892.5 |  |  | 869 |  |  | 1038.5 |  |  | 1008 |  |  | 897.5 |  |  | 934.5 |  |  | 907.5 |  |  | 910.5 |  |  | 917.5 |  |  | 913.5 |  |  | 882.5 |  |  | 900.5 |  |  | 935.5 |  |  | 886.5 |  |  | 855.5 |  |  | 932 |  |  | 970.5 |  |  | 879.5 |  |  | 882 |  |  | 853.5 |  |  | 980.5 |  |  | 920.5 |  |  | 874.5 |  |  | 938 |  |  | 949.5 |  |  | 838 |  |  | 898.5 |  |  | 938.5 |  |  | 969 |  |  | 914.5 |  |  | 904.5 |  |  | 969.5 |  |  | 954 |  |  | 895 |  |  | 946.5 |  |  | 838.5 |  |  | 803.5 |  |  | 920.5 |  |  | 897 |  |  | 852.5 |  |  | 932.5 |  |  | 977.5 |  |  | 945.5 |  |  | 965.5 |  |  | 1015.5 |  |  | 893.5 |  |  | 868.5 |  |  | 931.5 |  |  | 958.5 |  |  | 927 |  |  | 872.5 |  |  | 873 |  |  | 919 |  |  | 881 |  |  | 971.5 |  |  | 915.5 |  |  | 897.5 |  |  | 898.5 |  |  | 921.5 |  |  | 973 |  |  | 962 |  |  | 860.5 |  |  | 879.5 |  |  | 875.5 |  |  | 934.5 |  |  | 984.5 |  |  | 969.5 |  |  | 970.5 |  |  | 948.5 |  |  | 903.5 |  |  | 973.5 |  |  | 938.5 |  |  | 962.5 |  |  | 936.5 |  |  | 908.5 |  |  | 886.5 |  |  | 922.5 |  |  | 968.5 |  |  | 946.5 |  |  | 943.5 |  |  | 914.5 |  |  | 892.5 |  |  | 944.5 |  |  | 982 |  |  | 869.5 |  |  | 950.5 |  |  | 870.5 |  |  | 878.5 |  |  | 978.5 |  |  | 920 |  |  | 881.5 |  |  | 986.5 |  |  | 855.5 |  |  | 959.5 |  |  | 888 |  |  | 931.5 |  |  | 970.5 |  |  | 923 |  |  | 946.5 |  |  | 860 |  |  | 898 |  |  | 976.5 |  |  | 920 |  |  | 970.5 |  |  | 881.5 |  |  | 933.5 |  |  | 898.5 |  |  | 956.5 |  |  | 923.5 |  |  | 930.5 |  |  | 922.5 |  |  | 958.5 |  |  | 931.5 |  |  | 923 |  |  | 838.5 |  |  | 880 |  |  | 857.5 |  |  | 942.5 |  |  | 938 |  |  | 923.5 |  |  | 882.5 |  |  | 884.5 |  |  | 906 |  |  | 927.5 |  |  | 838.5 |  |  | 917.5 |  |  | 945.5 |  |  | 903.5 |  |  | 891.5 |  |  | 909 |  |  | 875.5 |  |  | 920.5 |  |  | 888.5 |  |  | 912.5 |  |  | 962.5 |  |  | 958.5 |  |  | 902.5 |  |  | 990 |  |  | 940.5 |  |  | 875.5 |  |  | 975.5 |  |  | 944.5 |  |  | 813.5 |  |  | 1007.5 |  |  | 932.5 |  |  | 935.5 |  |  | 911.5 |  |  | 854.5 |  |  | 871.5 |  |  | 808.5 |  |  | 830.5 |  |  | 884 |  |  | 882.5 |  |  | 919.5 |  |  | 899.5 |  |  | 905.5 |  |  | 1004.5 |  |  | 937.5 |  |  | 929.5 |  |  | 895.5 |  |  | 869.5 |  |  | 985.5 |  |  | 925.5 |  |  | 997.5 |  |  | 859.5 |  |  | 860.5 |  |  | 984.5 |  |  | 956.5 |  |  | 924 |  |  | 947.5 |  |  | 891.5 |  |  | 835 |  |  | 950.5 |  |  | 901 |  |  | 876.5 |  |  | 962.5 |  |  | 1003.5 |  |  | 935.5 |  |  | 922.5 |  |  | 899.5 |  |  | 885.5 |  |  | 850.5 |  |  | 859 |  |  | 888.5 |  |  | 766.5 |  |  | 921.5 |  |  | 913.5 |  |  | 997 |  |  | 866.5 |  |  | 835.5 |  |  | 964.5 |  |  | 948.5 |  |  | 961.5 |  |  | 844.5 |  |  | 843.5 |  |  | 926.5 |  |  | 898 |  |  | 943 |  |  | 837.5 |  |  | 937.5 |  |  | 934.5 |  |  | 946 |  |  | 978.5 |  |  | 941.5 |  |  | 906.5 |  |  | 892 |  |  | 930.5 |  |  | 972.5 |  |  | 879.5 |  |  | 825.5 |  |  | 889.5 |  |  | 916.5 |  |  | 940.5 |  |  | 870.5 |  |  | 951.5 |  |  | 817 |  |  | 851.5 |  |  | 912.5 |  |  | 891.5 |  |  | 881.5 |  |  | 917.5 |  |  | 987 |  |  | 931.5 |  |  | 987.5 |  |  | 909 |  |  | 973.5 |  |  | 908.5 |  |  | 942 |  |  | 898.5 |  |  | 878.5 |  |  | 1057.5 |  |  | 906.5 |  |  | 979 |  |  | 982 |  |  | 908.5 |  |  | 917.5 |  |  | 954.5 |  |  | 915.5 |  |  | 991.5 |  |  | 856.5 |  |  | 863 |  |  | 935.5 |  |  | 946.5 |  |  | 904 |  |  | 920.5 |  |  | 889.5 |  |  | 847 |  |  | 930.5 |  |  | 890.5 |  |  | 946.5 |  |  | 952 |  |  | 917.5 |  |  | 860 |  |  | 977.5 |  |  | 882.5 |  |  | 916.5 |  |  | 871 |  |  | 876.5 |  |  | 949.5 |  |  | 860.5 |  |  | 886 |  |  | 836.5 |  |  | 904.5 |  |  | 973.5 |  |  | 948.5 |  |  | 908.5 |  |  | 890 |  |  | 895.5 |  |  | 990.5 |  |  | 992.5 |  |  | 866 |  |  | 950 |  |  | 1009.5 |  |  | 925.5 |  |  | 897.5 |  |  | 953.5 |  |  | 926.5 |  |  | 917.5 |  |  | 907.5 |  |  | 929.5 |  |  | 814.5 |  |  | 915.5 |  |  | 918 |  |  | 917.5 |  |  | 958.5 |  |  | 995.5 |  |  | 980.5 |  |  | 924 |  |  | 985.5 |  |  | 976.5 |  |  | 922.5 |  |  | 845.5 |  |  | 902.5 |  |  | 887 |  |  | 930 |  |  | 829 |  |  | 893 |  |  | 902.5 |  |  | 956 |  |  | 873.5 |  |  | 843 |  |  | 932.5 |  |  | 952.5 |  |  | 924.5 |  |  | 897.5 |  |  | 936.5 |  |  | 912 |  |  | 885.5 |  |  | 957.5 |  |  | 827.5 |  |  | 922 |  |  | 936.5 |  |  | 912.5 |  |  | 913.5 |  |  | 1005 |  |  | 903.5 |  |  | 842.5 |  |  | 883.5 |  |  | 887.5 |  |  | 857.5 |  |  | 864.5 |  |  | 974.5 |  |  | 838.5 |  |  | 898.5 |  |  | 852.5 |  |  | 835 |  |  | 915.5 |  |  | 926.5 |  |  | 935.5 |  |  | 910.5 |  |  | 1002.5 |  |  | 891 |  |  | 854.5 |  |  | 961 |  |  | 915 |  |  | 888.5 |  |  | 1022.5 |  |  | 901.5 |  |  | 870 |  |  | 941.5 |  |  | 964.5 |  |  | 913.5 |  |  | 847 |  |  | 853.5 |  |  | 850.5 |  |  | 960.5 |  |  | 868.5 |  |  | 860.5 |  |  | 918 |  |  | 861.5 |  |  | 920 |  |  | 941.5 |  |  | 925.5 |  |  | 942.5 |  |  | 1049 |  |  | 866.5 |  |  | 951 |  |  | 937 |  |  | 935.5 |  |  | 865.5 |  |  | 901.5 |  |  | 956.5 |  |  | 955 |  |  | 931.5 |  |  | 916.5 |  |  | 867.5 |  |  | 938 |  |  | 954.5 |  |  | 836.5 |  |  | 839.5 |  |  | 922.5 |  |  | 923 |  |  | 834.5 |  |  | 902.5 |  |  | 936.5 |  |  | 924.5 |  |  | 897.5 |  |  | 963.5 |  |  | 950 |  |  | 893.5 |  |  | 891.5 |  |  | 907 |  |  | 867.5 |  |  | 899.5 |  |  | 923.5 |  |  | 968 |  |  | 883.5 |  |  | 905.5 |  |  | 922.5 |  |  | 939.5 |  |  | 921.5 |  |  | 981 |  |  | 881 |  |  | 852.5 |  |  | 948.5 |  |  | 919.5 |  |  | 900.5 |  |  | 889 |  |  | 937 |  |  | 847 |  |  | 962.5 |  |  | 913 |  |  | 975.5 |  |  | 970.5 |  |  | 975 |  |  | 866.5 |  |  | 925.5 |  |  | 887.5 |  |  | 988.5 |  |  | 848.5 |  |  | 914 |  |  | 947 |  |  | 818.5 |  |  | 894.5 |  |  | 906 |  |  | 803.5 |  |  | 999.5 |  |  | 926 |  |  | 1005.5 |  |  | 1002.5 |  |  | 865 |  |  | 932.5 |  |  | 943.5 |  |  | 860 |  |  | 935.5 |  |  | 896 |  |  | 973.5 |  |  | 981 |  |  | 835.5 |  |  | 950.5 |  |  | 938.5 |  |  | 914.5 |  |  | 891.5 |  |  | 912.5 |  |  | 972 |  |  | 913.5 |  |  | 943.5 |  |  | 873.5 |  |  | 967.5 |  |  | 867.5 |  |  | 905 |  |  | 916.5 |  |  | 881 |  |  | 928.5 |  |  | 912.5 |  |  | 937.5 |  |  | 850.5 |  |  | 878.5 |  |  | 901.5 |  |  | 859.5 |  |  | 989.5 |  |  | 910.5 |  |  | 932 |  |  | 946.5 |  |  | 852 |  |  | 911 |  |  | 891.5 |  |  | 805 |  |  | 881.5 |  |  | 856.5 |  |  | 938.5 |  |  | 936.5 |  |  | 950.5 |  |  | 975.5 |  |  | 945.5 |  |  | 919 |  |  | 988 |  |  | 849.5 |  |  | 863.5 |  |  | 883 |  |  | 856.5 |  |  | 961.5 |  |  | 873.5 |  |  | 879.5 |  |  | 849.5 |  |  | 887 |  |  | 886.5 |  |  | 937.5 |  |  | 934.5 |  |  | 890 |  |  | 944.5 |  |  | 940.5 |  |  | 960.5 |  |  | 977.5 |  |  | 975.5 |  |  | 855.5 |  |  | 1008.5 |  |  | 794.5 |  |  | 905.5 |  |  | 879 |  |  | 945.5 |  |  | 889.5 |  |  | 960.5 |  |  | 917.5 |  |  | 840.5 |  |  | 847.5 |  |  | 912.5 |  |  | 840 |  |  | 891.5 |  |  | 929.5 |  |  | 983.5 |  |  | 863 |  |  | 863.5 |  |  | 875 |  |  | 882.5 |  |  | 942.5 |  |  | 899.5 |  |  | 877 |  |  | 844.5 |  |  | 938 |  |  | 919 |  |  | 953.5 |  |  | 905 |  |  | 945 |  |  | 1013.5 |  |  | 962.5 |  |  | 892.5 |  |  | 939 |  |  | 938.5 |  |  | 904.5 |  |  | 862.5 |  |  | 977.5 |  |  | 861.5 |  |  | 949.5 |  |  | 917.5 |  |  | 928.5 |  |  | 863 |  |  | 1028.5 |  |  | 800 |  |  | 895.5 |  |  | 809.5 |  |  | 931.5 |  |  | 934 |  |  | 964 |  |  | 1004 |  |  | 934.5 |  |  | 892 |  |  | 915.5 |  |  | 971.5 |  |  | 824.5 |  |  | 918.5 |  |  | 891.5 |  |  | 928.5 |  |  | 894.5 |  |  | 906.5 |  |  | 988 |  |  | 866.5 |  |  | 826.5 |  |  | 941.5 |  |  | 896.5 |  |  | 857 |  |  | 915.5 |  |  | 938 |  |  | 878.5 |  |  | 882.5 |  |  | 902.5 |  |  | 849.5 |  |  | 894 |  |  | 871.5 |  |  | 857 |  |  | 859.5 |  |  | 927.5 |  |  | 1014.5 |  |  | 919.5 |  |  | 922.5 |  |  | 915.5 |  |  | 911.5 |  |  | 950.5 |  |  | 807.5 |  |  | 958 |  |  | 915.5 |  |  | 851.5 |  |  | 857.5 |  |  | 930.5 |  |  | 886.5 |  |  | 830 |  |  | 930 |  |  | 908.5 |  |  | 873 |  |  | 983.5 |  |  | 904.5 |  |  | 935.5 |  |  | 993.5 |  |  | 915.5 |  |  | 942.5 |  |  | 918.5 |  |  | 948.5 |  |  | 886 |  |  | 996.5 |  |  | 998.5 |  |  | 951.5 |  |  | 899 |  |  | 963.5 |  |  | 874.5 |  |  | 1003 |  |  | 827 |  |  | 941.5 |  |  | 826 |  |  | 854 |  |  | 840.5 |  |  | 878 |  |  | 1006.5 |  |  | 954.5 |  |  | 934.5 |  |  | 947.5 |  |  | 878.5 |  |  | 934.5 |  |  | 811.5 |  |  | 965.5 |  |  | 887.5 |  |  | 889.5 |  |  | 954 |  |  | 855 |  |  | 864.5 |  |  | 866.5 |  |  | 916.5 |  |  | 967.5 |  |  | 848.5 |  |  | 995.5 |  |  | 928.5 |  |  | 868.5 |  |  | 945 |  |  | 865.5 |  |  | 856 |  |  | 851.5 |  |  | 1078.5 |  |  | 941.5 |  |  | 962 |  |  | 877.5 |  |  | 904.5 |  |  | 823 |  |  | 922.5 |  |  | 860.5 |  |  | 946.5 |  |  | 897.5 |  |  | 909.5 |  |  | 901.5 |  |  | 879 |  |  | 970.5 |  |  | 853.5 |  |  | 943.5 |  |  | 1010.5 |  |  | 871 |  |  | 872.5 |  |  | 977.5 |  |  | 897 |  |  | 944.5 |  |  | 919.5 |  |  | 909 |  |  | 914.5 |  |  | 930.5 |  |  | 947.5 |  |  | 888 |  |  | 813.5 |  |  | 931.5 |  |  | 862 |  |  | 885.5 |  |  | 882.5 |  |  | 895.5 |  |  | 785.5 |  |  | 985.5 |  |  | 1024.5 |  |  | 903.5 |  |  | 939 |  |  | 940 |  |  | 822.5 |  |  | 938.5 |  |  | 905.5 |  |  | 889 |  |  | 916.5 |  |  | 914.5 |  |  | 945.5 |  |  | 861.5 |  |  | 900.5 |  |  | 892.5 |  |  | 818.5 |  |  | 911.5 |  |  | 856.5 |  |  | 935 |  |  | 883.5 |  |  | 900.5 |  |  | 835.5 |  |  | 959.5 |  |  | 972.5 |  |  | 876.5 |  |  | 898.5 |  |  | 981.5 |  |  | 880.5 |  |  | 897.5 |  |  | 876.5 |  |  | 902.5 |  |  | 925.5 |  |  | 983 |  |  | 931.5 |  |  | 926.5 |  |  | 882 |  |  | 929.5 |  |  | 939.5 |  |  | 988 |  |  | 909.5 |  |  | 948.5 |  |  | 974.5 |  |  | 962 |  |  | 897.5 |  |  | 932.5 |  |  | 915.5 |  |  | 763.5 |  |  | 946.5 |  |  | 839 |  |  | 919.5 |  |  | 970 |  |  | 870 |  |  | 975.5 |  |  | 933.5 |  |  | 896.5 |  |  | 830.5 |  |  | 937.5 |  |  | 926.5 |  |  | 867 |  |  | 894.5 |  |  | 980 |  |  | 885.5 |  |  | 944 |  |  | 903 |  |  | 972 |  |  | 877.5 |  |  | 841 |  |  | 968.5 |  |  | 996.5 |  |  | 945.5 |  |  | 1049.5 |  |  | 951.5 |  |  | 938 |  |  | 965.5 |  |  | 969.5 |  |  | 1045.5 |  |  | 975 |  |  | 940.5 |  |  | 931.5 |  |  | 975.5 |  |  | 997.5 |  |  | 839 |  |  | 910 |  |  | 905 |  |  | 950.5 |  |  | 957 |  |  | 955 |  |  | 941.5 |  |  | 895.5 |  |  | 839.5 |  |  | 962.5 |  |  | 968.5 |  |  | 1013.5 |  |  | 922.5 |  |  | 920.5 |  |  | 864.5 |  |  | 859 |  |  | 946.5 |  |  | 919 |  |  | 976.5 |  |  | 930.5 |  |  | 945.5 |  |  | 929.5 |  |  | 926 |  |  | 898.5 |  |  | 915 |  |  | 895.5 |  |  | 879.5 |  |  | 802 |  |  | 942 |  |  | 907.5 |  |  | 931 |  |  | 1001.5 |  |  | 795.5 |  |  | 924.5 |  |  | 930.5 |  |  | 916.5 |  |  | 911.5 |  |  | 912.5 |  |  | 863 |  |  | 922.5 |  |  | 952.5 |  |  | 854.5 |  |  | 922.5 |  |  | 893.5 |  |  | 898.5 |  |  | 924.5 |  |  | 915.5 |  |  | 893.5 |  |  | 929.5 |  |  | 923.5 |  |  | 832.5 |  |  | 1019 |  |  | 823.5 |  |  | 891.5 |  |  | 960 |  |  | 799.5 |  |  | 814.5 |  |  | 887.5 |  |  | 871.5 |  |  | 960 |  |  | 936.5 |  |  | 900.5 |  |  | 869.5 |  |  | 940.5 |  |  | 841 |  |  | 916.5 |  |  | 927.5 |  |  | 904.5 |  |  | 951.5 |  |  | 933.5 |  |  | 842.5 |  |  | 969.5 |  |  | 922.5 |  |  | 961.5 |  |  | 883.5 |  |  | 991.5 |  |  | 945 |  |  | 930.5 |  |  | 930.5 |  |  | 963.5 |  |  | 941.5 |  |  | 876.5 |  |  | 879.5 |  |  | 949 |  |  | 885.5 |  |  | 876 |  |  | 873.5 |  |  | 958.5 |  |  | 878.5 |  |  | 907 |  |  | 922 |  |  | 931.5 |  |  | 910.5 |  |  | 858.5 |  |  | 897.5 |  |  | 868.5 |  |  | 843.5 |  |  | 895.5 |  |  | 840.5 |  |  | 937.5 |  |  | 951.5 |  |  | 901.5 |  |  | 967.5 |  |  | 917.5 |  |  | 944.5 |  |  | 906.5 |  |  | 960.5 |  |  | 902.5 |  |  | 890.5 |  |  | 927.5 |  |  | 903.5 |  |  | 953.5 |  |  | 959.5 |  |  | 934 |  |  | 1003.5 |  |  | 871.5 |  |  | 932.5 |  |  | 901 |  |  | 960.5 |  |  | 943.5 |  |  | 904.5 |  |  | 953.5 |  |  | 952 |  |  | 852.5 |  |  | 901.5 |  |  | 868 |  |  | 854 |  |  | 872 |  |  | 916.5 |  |  | 941.5 |  |  | 930.5 |  |  | 936.5 |  |  | 891 |  |  | 898.5 |  |  | 947.5 |  |  | 864 |  |  | 882 |  |  | 928.5 |  |  | 922.5 |  |  | 905 |  |  | 881.5 |  |  | 906 |  |  | 829.5 |  |  | 850.5 |  |  | 918 |  |  | 941.5 |  |  | 854.5 |  |  | 829.5 |  |  | 963 |  |  | 967.5 |  |  | 919.5 |  |  | 871.5 |  |  | 890.5 |  |  | 908.5 |  |  | 944.5 |  |  | 824.5 |  |  | 906.5 |  |  | 976.5 |  |  | 932.5 |  |  | 952 |  |  | 855.5 |  |  | 937.5 |  |  | 942.5 |  |  | 955.5 |  |  | 862.5 |  |  | 953.5 |  |  | 995.5 |  |  | 911.5 |  |  | 972 |  |  | 931.5 |  |  | 943 |  |  | 957.5 |  |  | 994.5 |  |  | 995.5 |  |  | 928.5 |  |  | 955.5 |  |  | 844.5 |  |  | 794.5 |  |  | 909.5 |  |  | 905 |  |  | 891.5 |  |  | 843 |  |  | 920.5 |  |  | 853.5 |  |  | 973.5 |  |  | 1005 |  |  | 879.5 |  |  | 942.5 |  |  | 870 |  |  | 885.5 |  |  | 885 |  |  | 870.5 |  |  | 940.5 |  |  | 894.5 |  |  | 871 |  |  | 875.5 |  |  | 1029.5 |  |  | 843 |  |  | 974.5 |  |  | 845.5 |  |  | 925 |  |  | 903.5 |  |  | 1023.5 |  |  | 952.5 |  |  | 978.5 |  |  | 911.5 |  |  | 888.5 |  |  | 865.5 |  |  | 912.5 |  |  | 839.5 |  |  | 922.5 |  |  | 992.5 |  |  | 897 |  |  | 1010 |  |  | 965.5 |  |  | 920.5 |  |  | 985
33 |  | 982.5 |  |  | 1010.5 |  |  | 966 |  |  | 947.5 |  |  | 1005.5 |  |  | 978.5 |  |  | 1043.5 |  |  | 942.5 |  |  | 938.5 |  |  | 982.5 |  |  | 941 |  |  | 968.5 |  |  | 1031.5 |  |  | 934.5 |  |  | 894 |  |  | 971.5 |  |  | 1011.5 |  |  | 973.5 |  |  | 1030.5 |  |  | 875.5 |  |  | 946.5 |  |  | 896.5 |  |  | 961.5 |  |  | 901.5 |  |  | 893 |  |  | 1026.5 |  |  | 890.5 |  |  | 945.5 |  |  | 909.5 |  |  | 900 |  |  | 975 |  |  | 947.5 |  |  | 897.5 |  |  | 949.5 |  |  | 816.5 |  |  | 939 |  |  | 917.5 |  |  | 920 |  |  | 923.5 |  |  | 981.5 |  |  | 910.5 |  |  | 999.5 |  |  | 916.5 |  |  | 893 |  |  | 1085.5 |  |  | 1032 |  |  | 918.5 |  |  | 958.5 |  |  | 933.5 |  |  | 939.5 |  |  | 941.5 |  |  | 952.5 |  |  | 911.5 |  |  | 924.5 |  |  | 956.5 |  |  | 925.5 |  |  | 894.5 |  |  | 958 |  |  | 1009.5 |  |  | 903.5 |  |  | 903 |  |  | 877.5 |  |  | 1004.5 |  |  | 946.5 |  |  | 895.5 |  |  | 967 |  |  | 970.5 |  |  | 862 |  |  | 945.5 |  |  | 977.5 |  |  | 1008 |  |  | 953.5 |  |  | 928.5 |  |  | 1008.5 |  |  | 1001 |  |  | 942 |  |  | 975.5 |  |  | 859.5 |  |  | 829.5 |  |  | 944.5 |  |  | 923 |  |  | 876.5 |  |  | 947.5 |  |  | 1024.5 |  |  | 969.5 |  |  | 994.5 |  |  | 1036.5 |  |  | 917.5 |  |  | 892.5 |  |  | 970.5 |  |  | 982.5 |  |  | 951 |  |  | 887.5 |  |  | 920 |  |  | 958 |  |  | 902 |  |  | 995.5 |  |  | 954.5 |  |  | 921.5 |  |  | 924.5 |  |  | 936.5 |  |  | 994 |  |  | 983 |  |  | 889.5 |  |  | 918.5 |  |  | 899.5 |  |  | 963.5 |  |  | 1008.5 |  |  | 1016.5 |  |  | 985.5 |  |  | 995.5 |  |  | 942.5 |  |  | 999.5 |  |  | 959.5 |  |  | 977.5 |  |  | 960.5 |  |  | 955.5 |  |  | 912.5 |  |  | 948.5 |  |  | 1007.5 |  |  | 985.5 |  |  | 982.5 |  |  | 929.5 |  |  | 931.5 |  |  | 965.5 |  |  | 1003 |  |  | 898.5 |  |  | 989.5 |  |  | 885.5 |  |  | 904.5 |  |  | 1004.5 |  |  | 959 |  |  | 907.5 |  |  | 1010.5 |  |  | 894.5 |  |  | 983.5 |  |  | 927 |  |  | 946.5 |  |  | 1009.5 |  |  | 952 |  |  | 975.5 |  |  | 907 |  |  | 924 |  |  | 1002.5 |  |  | 967 |  |  | 1009.5 |  |  | 910.5 |  |  | 980.5 |  |  | 919.5 |  |  | 980.5 |  |  | 962.5 |  |  | 977.5 |  |  | 961.5 |  |  | 982.5 |  |  | 955.5 |  |  | 962 |  |  | 859.5 |  |  | 919 |  |  | 872.5 |  |  | 963.5 |  |  | 977 |  |  | 962.5 |  |  | 929.5 |  |  | 923.5 |  |  | 953 |  |  | 966.5 |  |  | 877.5 |  |  | 938.5 |  |  | 960.5 |  |  | 942.5 |  |  | 930.5 |  |  | 948 |  |  | 914.5 |  |  | 944.5 |  |  | 927.5 |  |  | 933.5 |  |  | 988.5 |  |  | 997.5 |  |  | 941.5 |  |  | 1037 |  |  | 966.5 |  |  | 914.5 |  |  | 999.5 |  |  | 991.5 |  |  | 837.5 |  |  | 1054.5 |  |  | 958.5 |  |  | 956.5 |  |  | 932.5 |  |  | 880.5 |  |  | 910.5 |  |  | 855.5 |  |  | 854.5 |  |  | 910 |  |  | 921.5 |  |  | 966.5 |  |  | 914.5 |  |  | 934.5 |  |  | 1028.5 |  |  | 963.5 |  |  | 950.5 |  |  | 916.5 |  |  | 895.5 |  |  | 1006.5 |  |  | 954.5 |  |  | 1036.5 |  |  | 885.5 |  |  | 886.5 |  |  | 1013.5 |  |  | 995.5 |  |  | 963 |  |  | 994.5 |  |  | 930.5 |  |  | 850 |  |  | 989.5 |  |  | 940 |  |  | 900.5 |  |  | 1001.5 |  |  | 1050.5 |  |  | 959.5 |  |  | 951.5 |  |  | 923.5 |  |  | 914.5 |  |  | 879.5 |  |  | 906 |  |  | 903.5 |  |  | 787.5 |  |  | 945.5 |  |  | 928.5 |  |  | 1026 |  |  | 913.5 |  |  | 874.5 |  |  | 1003.5 |  |  | 995.5 |  |  | 985.5 |  |  | 868.5 |  |  | 872.5 |  |  | 955.5 |  |  | 937 |  |  | 967 |  |  | 861.5 |  |  | 961.5 |  |  | 955.5 |  |  | 985 |  |  | 1025.5 |  |  | 956.5 |  |  | 945.5 |  |  | 918 |  |  | 951.5 |  |  | 1011.5 |  |  | 900.5 |  |  | 864.5 |  |  | 928.5 |  |  | 945.5 |  |  | 987.5 |  |  | 894.5 |  |  | 980.5 |  |  | 841 |  |  | 877.5 |  |  | 933.5 |  |  | 912.5 |  |  | 910.5 |  |  | 938.5 |  |  | 1026 |  |  | 960.5 |  |  | 1008.5 |  |  | 930 |  |  | 1020.5 |  |  | 947.5 |  |  | 981 |  |  | 919.5 |  |  | 917.5 |  |  | 1096.5 |  |  | 921.5 |  |  | 1018 |  |  | 1003 |  |  | 947.5 |  |  | 938.5 |  |  | 969.5 |  |  | 954.5 |  |  | 1006.5 |  |  | 903.5 |  |  | 902 |  |  | 982.5 |  |  | 985.5 |  |  | 943 |  |  | 935.5 |  |  | 913.5 |  |  | 894 |  |  | 945.5 |  |  | 929.5 |  |  | 961.5 |  |  | 999 |  |  | 964.5 |  |  | 889 |  |  | 1006.5 |  |  | 921.5 |  |  | 931.5 |  |  | 895 |  |  | 905.5 |  |  | 978.5 |  |  | 907.5 |  |  | 910 |  |  | 862.5 |  |  | 930.5 |  |  | 1002.5 |  |  | 987.5 |  |  | 932.5 |  |  | 916 |  |  | 916.5 |  |  | 1016.5 |  |  | 1039.5 |  |  | 895 |  |  | 979 |  |  | 1035.5 |  |  | 949.5 |  |  | 944.5 |  |  | 992.5 |  |  | 950.5 |  |  | 956.5 |  |  | 928.5 |  |  | 968.5 |  |  | 835.5 |  |  | 930.5 |  |  | 939 |  |  | 964.5 |  |  | 997.5 |  |  | 1034.5 |  |  | 1027.5 |  |  | 948 |  |  | 1024.5 |  |  | 1023.5 |  |  | 961.5 |  |  | 860.5 |  |  | 941.5 |  |  | 926 |  |  | 954 |  |  | 876 |  |  | 940 |  |  | 928.5 |  |  | 971 |  |  | 920.5 |  |  | 872 |  |  | 961.5 |  |  | 967.5 |  |  | 953.5 |  |  | 926.5 |  |  | 951.5 |  |  | 927 |  |  | 932.5 |  |  | 996.5 |  |  | 874.5 |  |  | 946 |  |  | 951.5 |  |  | 951.5 |  |  | 934.5 |  |  | 1020 |  |  | 927.5 |  |  | 868.5 |  |  | 898.5 |  |  | 913.5 |  |  | 872.5 |  |  | 903.5 |  |  | 1013.5 |  |  | 877.5 |  |  | 927.5 |  |  | 876.5 |  |  | 874 |  |  | 954.5 |  |  | 950.5 |  |  | 961.5 |  |  | 936.5 |  |  | 1026.5 |  |  | 920 |  |  | 880.5 |  |  | 1000 |  |  | 941 |  |  | 912.5 |  |  | 1043.5 |  |  | 925.5 |  |  | 891 |  |  | 988.5 |  |  | 1011.5 |  |  | 952.5 |  |  | 871 |  |  | 900.5 |  |  | 871.5 |  |  | 999.5 |  |  | 894.5 |  |  | 881.5 |  |  | 933 |  |  | 890.5 |  |  | 935 |  |  | 980.5 |  |  | 954.5 |  |  | 963.5 |  |  | 1070 |  |  | 895.5 |  |  | 972 |  |  | 958 |  |  | 961.5 |  |  | 912.5 |  |  | 930.5 |  |  | 995.5 |  |  | 981 |  |  | 946.5 |  |  | 931.5 |  |  | 888.5 |  |  | 964 |  |  | 978.5 |  |  | 857.5 |  |  | 886.5 |  |  | 961.5 |  |  | 970 |  |  | 881.5 |  |  | 941.5 |  |  | 975.5 |  |  | 971.5 |  |  | 926.5 |  |  | 989.5 |  |  | 979 |  |  | 922.5 |  |  | 938.5 |  |  | 922 |  |  | 896.5 |  |  | 925.5 |  |  | 962.5 |  |  | 992 |  |  | 922.5 |  |  | 934.5 |  |  | 937.5 |  |  | 986.5 |  |  | 960.5 |  |  | 1005 |  |  | 902 |  |  | 881.5 |  |  | 969.5 |  |  | 958.5 |  |  | 921.5 |  |  | 918 |  |  | 976 |  |  | 894 |  |  | 1001.5 |  |  | 960 |  |  | 1001.5 |  |  | 1009.5 |  |  | 1004 |  |  | 905.5 |  |  | 964.5 |  |  | 934.5 |  |  | 1012.5 |  |  | 877.5 |  |  | 940 |  |  | 971 |  |  | 865.5 |  |  | 918.5 |  |  | 945 |  |  | 829.5 |  |  | 1025.5 |  |  | 965 |  |  | 1044.5 |  |  | 1028.5 |  |  | 880 |  |  | 958.5 |  |  | 982.5 |  |  | 907 |  |  | 956.5 |  |  | 911 |  |  | 994.5 |  |  | 1002 |  |  | 874.5 |  |  | 965.5 |  |  | 962.5 |  |  | 929.5 |  |  | 930.5 |  |  | 927.5 |  |  | 1019 |  |  | 960.5 |  |  | 964.5 |  |  | 899.5 |  |  | 982.5 |  |  | 893.5 |  |  | 944 |  |  | 940.5 |  |  | 928 |  |  | 943.5 |  |  | 936.5 |  |  | 966.5 |  |  | 889.5 |  |  | 904.5 |  |  | 916.5 |  |  | 898.5 |  |  | 1036.5 |  |  | 939.5 |  |  | 979 |  |  | 967.5 |  |  | 891 |  |  | 926 |  |  | 930.5 |  |  | 844 |  |  | 907.5 |  |  | 880.5 |  |  | 967.5 |  |  | 962.5 |  |  | 989.5 |  |  | 1014.5 |  |  | 984.5 |  |  | 948 |  |  | 1012 |  |  | 888.5 |  |  | 887.5 |  |  | 930 |  |  | 895.5 |  |  | 985.5 |  |  | 912.5 |  |  | 900.5 |  |  | 873.5 |  |  | 911 |  |  | 925.5 |  |  | 976.5 |  |  | 955.5 |  |  | 937 |  |  | 983.5 |  |  | 961.5 |  |  | 984.5 |  |  | 1016.5 |  |  | 1004.5 |  |  | 902.5 |  |  | 1034.5 |  |  | 823.5 |  |  | 952.5 |  |  | 926 |  |  | 984.5 |  |  | 904.5 |  |  | 981.5 |  |  | 946.5 |  |  | 887.5 |  |  | 876.5 |  |  | 936.5 |  |  | 866 |  |  | 938.5 |  |  | 955.5 |  |  | 1022.5 |  |  | 892 |  |  | 892.5 |  |  | 896 |  |  | 921.5 |  |  | 966.5 |  |  | 938.5 |  |  | 906 |  |  | 868.5 |  |  | 959 |  |  | 934 |  |  | 992.5 |  |  | 931 |  |  | 971 |  |  | 1039.5 |  |  | 988.5 |  |  | 907.5 |  |  | 986 |  |  | 953.5 |  |  | 943.5 |  |  | 877.5 |  |  | 1016.5 |  |  | 882.5 |  |  | 975.5 |  |  | 964.5 |  |  | 957.5 |  |  | 892 |  |  | 1054.5 |  |  | 826 |  |  | 916.5 |  |  | 833.5 |  |  | 970.5 |  |  | 960 |  |  | 1003 |  |  | 1019 |  |  | 958.5 |  |  | 921 |  |  | 944.5 |  |  | 997.5 |  |  | 871.5 |  |  | 942.5 |  |  | 915.5 |  |  | 975.5 |  |  | 915.5 |  |  | 953.5 |  |  | 1014 |  |  | 913.5 |  |  | 865.5 |  |  | 967.5 |  |  | 935.5 |  |  | 881 |  |  | 936.5 |  |  | 977 |  |  | 917.5 |  |  | 929.5 |  |  | 917.5 |  |  | 873.5 |  |  | 909 |  |  | 892.5 |  |  | 896 |  |  | 888.5 |  |  | 953.5 |  |  | 1029.5 |  |  | 966.5 |  |  | 961.5 |  |  | 944.5 |  |  | 932.5 |  |  | 974.5 |  |  | 831.5 |  |  | 973 |  |  | 936.5 |  |  | 872.5 |  |  | 886.5 |  |  | 956.5 |  |  | 915.5 |  |  | 869 |  |  | 945 |  |  | 932.5 |  |  | 897 |  |  | 1022.5 |  |  | 933.5 |  |  | 974.5 |  |  | 1032.5 |  |  | 939.5 |  |  | 971.5 |  |  | 957.5 |  |  | 969.5 |  |  | 907 |  |  | 1035.5 |  |  | 1037.5 |  |  | 998.5 |  |  | 920 |  |  | 984.5 |  |  | 913.5 |  |  | 1042 |  |  | 866 |  |  | 970.5 |  |  | 865 |  |  | 878 |  |  | 879.5 |  |  | 899 |  |  | 1027.5 |  |  | 1001.5 |  |  | 973.5 |  |  | 962.5 |  |  | 902.5 |  |  | 981.5 |  |  | 837.5 |  |  | 991.5 |  |  | 926.5 |  |  | 918.5 |  |  | 975 |  |  | 876 |  |  | 903.5 |  |  | 913.5 |  |  | 955.5 |  |  | 996.5 |  |  | 877.5 |  |  | 1016.5 |  |  | 957.5 |  |  | 883.5 |  |  | 971 |  |  | 886.5 |  |  | 895 |  |  | 866.5 |  |  | 1104.5 |  |  | 980.5 |  |  | 1001 |  |  | 901.5 |  |  | 943.5 |  |  | 847 |  |  | 969.5 |  |  | 899.5 |  |  | 993.5 |  |  | 912.5 |  |  | 935.5 |  |  | 940.5 |  |  | 900 |  |  | 985.5 |  |  | 892.5 |  |  | 982.5 |  |  | 1036.5 |  |  | 895 |  |  | 896.5 |  |  | 992.5 |  |  | 936 |  |  | 959.5 |  |  | 945.5 |  |  | 933 |  |  | 961.5 |  |  | 969.5 |  |  | 971.5 |  |  | 912 |  |  | 839.5 |  |  | 952.5 |  |  | 901 |  |  | 924.5 |  |  | 929.5 |  |  | 916.5 |  |  | 814.5 |  |  | 1024.5 |  |  | 1053.5 |  |  | 918.5 |  |  | 963 |  |  | 969 |  |  | 846.5 |  |  | 953.5 |  |  | 931.5 |  |  | 928 |  |  | 963.5 |  |  | 940.5 |  |  | 969.5 |  |  | 876.5 |  |  | 929.5 |  |  | 931.5 |  |  | 847.5 |  |  | 950.5 |  |  | 882.5 |  |  | 950 |  |  | 930.5 |  |  | 929.5 |  |  | 861.5 |  |  | 998.5 |  |  | 1001.5 |  |  | 915.5 |  |  | 913.5 |  |  | 996.5 |  |  | 904.5 |  |  | 944.5 |  |  | 897.5 |  |  | 941.5 |  |  | 940.5 |  |  | 1007 |  |  | 957.5 |  |  | 965.5 |  |  | 921 |  |  | 944.5 |  |  | 960.5 |  |  | 1017 |  |  | 930.5 |  |  | 987.5 |  |  | 1000.5 |  |  | 1009 |  |  | 944.5 |  |  | 979.5 |  |  | 939.5 |  |  | 792.5 |  |  | 975.5 |  |  | 854 |  |  | 945.5 |  |  | 999 |  |  | 917 |  |  | 1014.5 |  |  | 959.5 |  |  | 922.5 |  |  | 854.5 |  |  | 958.5 |  |  | 947.5 |  |  | 882 |  |  | 918.5 |  |  | 1027 |  |  | 924.5 |  |  | 970 |  |  | 927 |  |  | 1001 |  |  | 924.5 |  |  | 862 |  |  | 1007.5 |  |  | 1020.5 |  |  | 984.5 |  |  | 1088.5 |  |  | 990.5 |  |  | 962 |  |  | 994.5 |  |  | 1008.5 |  |  | 1069.5 |  |  | 999 |  |  | 964.5 |  |  | 957.5 |  |  | 1022.5 |  |  | 1021.5 |  |  | 860 |  |  | 957 |  |  | 944 |  |  | 976.5 |  |  | 996 |  |  | 981 |  |  | 980.5 |  |  | 921.5 |  |  | 886.5 |  |  | 986.5 |  |  | 1007.5 |  |  | 1042.5 |  |  | 946.5 |  |  | 941.5 |  |  | 890.5 |  |  | 885 |  |  | 961.5 |  |  | 945 |  |  | 997.5 |  |  | 954.5 |  |  | 969.5 |  |  | 968.5 |  |  | 965 |  |  | 919.5 |  |  | 930 |  |  | 919.5 |  |  | 918.5 |  |  | 841 |  |  | 966 |  |  | 946.5 |  |  | 960 |  |  | 1040.5 |  |  | 810.5 |  |  | 945.5 |  |  | 959.5 |  |  | 963.5 |  |  | 935.5 |  |  | 927.5 |  |  | 902 |  |  | 969.5 |  |  | 976.5 |  |  | 878.5 |  |  | 946.5 |  |  | 932.5 |  |  | 924.5 |  |  | 945.5 |  |  | 930.5 |  |  | 919.5 |  |  | 958.5 |  |  | 949.5 |  |  | 858.5 |  |  | 1040 |  |  | 862.5 |  |  | 912.5 |  |  | 999 |  |  | 838.5 |  |  | 838.5 |  |  | 916.5 |  |  | 895.5 |  |  | 986 |  |  | 975.5 |  |  | 947.5 |  |  | 898.5 |  |  | 964.5 |  |  | 856 |  |  | 955.5 |  |  | 966.5 |  |  | 930.5 |  |  | 980.5 |  |  | 972.5 |  |  | 881.5 |  |  | 998.5 |  |  | 969.5 |  |  | 990.5 |  |  | 904.5 |  |  | 1006.5 |  |  | 969 |  |  | 956.5 |  |  | 969.5 |  |  | 1010.5 |  |  | 967.5 |  |  | 923.5 |  |  | 926.5 |  |  | 988 |  |  | 909.5 |  |  | 923 |  |  | 897.5 |  |  | 1005.5 |  |  | 902.5 |  |  | 936 |  |  | 943 |  |  | 946.5 |  |  | 949.5 |  |  | 873.5 |  |  | 918.5 |  |  | 897.5 |  |  | 872.5 |  |  | 921.5 |  |  | 887.5 |  |  | 958.5 |  |  | 998.5 |  |  | 922.5 |  |  | 991.5 |  |  | 943.5 |  |  | 973.5 |  |  | 932.5 |  |  | 975.5 |  |  | 926.5 |  |  | 929.5 |  |  | 956.5 |  |  | 918.5 |  |  | 977.5 |  |  | 974.5 |  |  | 981 |  |  | 1050.5 |  |  | 886.5 |  |  | 961.5 |  |  | 940 |  |  | 984.5 |  |  | 958.5 |  |  | 928.5 |  |  | 992.5 |  |  | 991 |  |  | 876.5 |  |  | 948.5 |  |  | 889 |  |  | 878 |  |  | 911 |  |  | 955.5 |  |  | 980.5 |  |  | 959.5 |  |  | 975.5 |  |  | 920 |  |  | 937.5 |  |  | 968.5 |  |  | 885 |  |  | 929 |  |  | 949.5 |  |  | 961.5 |  |  | 931 |  |  | 910.5 |  |  | 945 |  |  | 876.5 |  |  | 871.5 |  |  | 942 |  |  | 965.5 |  |  | 875.5 |  |  | 855.5 |  |  | 989 |  |  | 982.5 |  |  | 958.5 |  |  | 910.5 |  |  | 916.5 |  |  | 937.5 |  |  | 991.5 |  |  | 871.5 |  |  | 953.5 |  |  | 1005.5 |  |  | 958.5 |  |  | 976 |  |  | 902.5 |  |  | 966.5 |  |  | 981.5 |  |  | 1002.5 |  |  | 888.5 |  |  | 992.5 |  |  | 1016.5 |  |  | 926.5 |  |  | 1001 |  |  | 970.5 |  |  | 982 |  |  | 986.5 |  |  | 1009.5 |  |  | 1034.5 |  |  | 952.5 |  |  | 994.5 |  |  | 883.5 |  |  | 820.5 |  |  | 935.5 |  |  | 944 |  |  | 920.5 |  |  | 869 |  |  | 941.5 |  |  | 877.5 |  |  | 1002.5 |  |  | 1034 |  |  | 903.5 |  |  | 981.5 |  |  | 899 |  |  | 914.5 |  |  | 924 |  |  | 891.5 |  |  | 969.5 |  |  | 933.5 |  |  | 886 |  |  | 914.5 |  |  | 1044.5 |  |  | 882 |  |  | 1000.5 |  |  | 892.5 |  |  | 954 |  |  | 929.5 |  |  | 1062.5 |  |  | 978.5 |  |  | 993.5 |  |  | 940.5 |  |  | 909.5 |  |  | 889.5 |  |  | 951.5 |  |  | 865.5 |  |  | 961.5 |  |  | 1031.5 |  |  | 923 |  |  | 1034 |  |  | 980.5 |  |  | 949.5 |  |  | 1000
34 |  | 1021.5 |  |  | 1049.5 |  |  | 1005 |  |  | 986.5 |  |  | 1044.5 |  |  | 1002.5 |  |  | 1067.5 |  |  | 968.5 |  |  | 964.5 |  |  | 1021.5 |  |  | 970 |  |  | 994.5 |  |  | 1078.5 |  |  | 958.5 |  |  | 933 |  |  | 997.5 |  |  | 1050.5 |  |  | 1002.5 |  |  | 1077.5 |  |  | 914.5 |  |  | 961.5 |  |  | 943.5 |  |  | 1000.5 |  |  | 930.5 |  |  | 932 |  |  | 1041.5 |  |  | 937.5 |  |  | 974.5 |  |  | 938.5 |  |  | 929 |  |  | 996 |  |  | 962.5 |  |  | 944.5 |  |  | 970.5 |  |  | 863.5 |  |  | 978 |  |  | 946.5 |  |  | 935 |  |  | 962.5 |  |  | 1020.5 |  |  | 925.5 |  |  | 1014.5 |  |  | 945.5 |  |  | 908 |  |  | 1114.5 |  |  | 1058 |  |  | 933.5 |  |  | 997.5 |  |  | 972.5 |  |  | 963.5 |  |  | 962.5 |  |  | 976.5 |  |  | 926.5 |  |  | 963.5 |  |  | 982.5 |  |  | 951.5 |  |  | 915.5 |  |  | 979 |  |  | 1035.5 |  |  | 927.5 |  |  | 924 |  |  | 903.5 |  |  | 1025.5 |  |  | 972.5 |  |  | 921.5 |  |  | 988 |  |  | 994.5 |  |  | 888 |  |  | 960.5 |  |  | 992.5 |  |  | 1029 |  |  | 992.5 |  |  | 952.5 |  |  | 1023.5 |  |  | 1016 |  |  | 966 |  |  | 999.5 |  |  | 906.5 |  |  | 844.5 |  |  | 959.5 |  |  | 944 |  |  | 900.5 |  |  | 986.5 |  |  | 1048.5 |  |  | 1008.5 |  |  | 1033.5 |  |  | 1060.5 |  |  | 956.5 |  |  | 931.5 |  |  | 1009.5 |  |  | 1011.5 |  |  | 972 |  |  | 926.5 |  |  | 949 |  |  | 982 |  |  | 928 |  |  | 1021.5 |  |  | 993.5 |  |  | 950.5 |  |  | 971.5 |  |  | 951.5 |  |  | 1018 |  |  | 1007 |  |  | 913.5 |  |  | 947.5 |  |  | 946.5 |  |  | 987.5 |  |  | 1047.5 |  |  | 1042.5 |  |  | 1024.5 |  |  | 1021.5 |  |  | 966.5 |  |  | 1046.5 |  |  | 974.5 |  |  | 1016.5 |  |  | 989.5 |  |  | 994.5 |  |  | 927.5 |  |  | 974.5 |  |  | 1046.5 |  |  | 1011.5 |  |  | 1008.5 |  |  | 944.5 |  |  | 970.5 |  |  | 986.5 |  |  | 1029 |  |  | 937.5 |  |  | 1004.5 |  |  | 906.5 |  |  | 928.5 |  |  | 1051.5 |  |  | 980 |  |  | 946.5 |  |  | 1034.5 |  |  | 918.5 |  |  | 1007.5 |  |  | 951 |  |  | 975.5 |  |  | 1048.5 |  |  | 973 |  |  | 1001.5 |  |  | 922 |  |  | 963 |  |  | 1041.5 |  |  | 996 |  |  | 1033.5 |  |  | 934.5 |  |  | 1019.5 |  |  | 943.5 |  |  | 1019.5 |  |  | 988.5 |  |  | 992.5 |  |  | 990.5 |  |  | 1021.5 |  |  | 1002.5 |  |  | 1001 |  |  | 883.5 |  |  | 958 |  |  | 911.5 |  |  | 1002.5 |  |  | 992 |  |  | 1009.5 |  |  | 955.5 |  |  | 938.5 |  |  | 1000 |  |  | 1005.5 |  |  | 916.5 |  |  | 953.5 |  |  | 975.5 |  |  | 971.5 |  |  | 969.5 |  |  | 995 |  |  | 953.5 |  |  | 959.5 |  |  | 951.5 |  |  | 954.5 |  |  | 1012.5 |  |  | 1012.5 |  |  | 967.5 |  |  | 1061 |  |  | 995.5 |  |  | 961.5 |  |  | 1025.5 |  |  | 1017.5 |  |  | 876.5 |  |  | 1080.5 |  |  | 973.5 |  |  | 995.5 |  |  | 971.5 |  |  | 919.5 |  |  | 957.5 |  |  | 881.5 |  |  | 878.5 |  |  | 931 |  |  | 945.5 |  |  | 981.5 |  |  | 943.5 |  |  | 960.5 |  |  | 1054.5 |  |  | 1002.5 |  |  | 989.5 |  |  | 937.5 |  |  | 934.5 |  |  | 1021.5 |  |  | 978.5 |  |  | 1083.5 |  |  | 932.5 |  |  | 915.5 |  |  | 1028.5 |  |  | 1019.5 |  |  | 1002 |  |  | 1020.5 |  |  | 959.5 |  |  | 874 |  |  | 1010.5 |  |  | 964 |  |  | 939.5 |  |  | 1040.5 |  |  | 1079.5 |  |  | 998.5 |  |  | 966.5 |  |  | 938.5 |  |  | 953.5 |  |  | 908.5 |  |  | 921 |  |  | 924.5 |  |  | 802.5 |  |  | 992.5 |  |  | 967.5 |  |  | 1065 |  |  | 934.5 |  |  | 913.5 |  |  | 1024.5 |  |  | 1034.5 |  |  | 1032.5 |  |  | 894.5 |  |  | 898.5 |  |  | 976.5 |  |  | 966 |  |  | 988 |  |  | 882.5 |  |  | 990.5 |  |  | 984.5 |  |  | 1032 |  |  | 1054.5 |  |  | 995.5 |  |  | 984.5 |  |  | 939 |  |  | 966.5 |  |  | 1035.5 |  |  | 939.5 |  |  | 911.5 |  |  | 952.5 |  |  | 992.5 |  |  | 1034.5 |  |  | 933.5 |  |  | 1027.5 |  |  | 870 |  |  | 901.5 |  |  | 954.5 |  |  | 938.5 |  |  | 931.5 |  |  | 977.5 |  |  | 1041 |  |  | 989.5 |  |  | 1037.5 |  |  | 969 |  |  | 1046.5 |  |  | 986.5 |  |  | 1028 |  |  | 943.5 |  |  | 964.5 |  |  | 1135.5 |  |  | 945.5 |  |  | 1039 |  |  | 1032 |  |  | 986.5 |  |  | 959.5 |  |  | 1008.5 |  |  | 993.5 |  |  | 1053.5 |  |  | 918.5 |  |  | 949 |  |  | 1011.5 |  |  | 1011.5 |  |  | 972 |  |  | 959.5 |  |  | 942.5 |  |  | 923 |  |  | 992.5 |  |  | 958.5 |  |  | 982.5 |  |  | 1025 |  |  | 1003.5 |  |  | 915 |  |  | 1032.5 |  |  | 942.5 |  |  | 960.5 |  |  | 924 |  |  | 931.5 |  |  | 1025.5 |  |  | 946.5 |  |  | 949 |  |  | 888.5 |  |  | 954.5 |  |  | 1041.5 |  |  | 1026.5 |  |  | 958.5 |  |  | 955 |  |  | 945.5 |  |  | 1055.5 |  |  | 1078.5 |  |  | 942 |  |  | 994 |  |  | 1059.5 |  |  | 996.5 |  |  | 973.5 |  |  | 1007.5 |  |  | 989.5 |  |  | 995.5 |  |  | 952.5 |  |  | 989.5 |  |  | 874.5 |  |  | 969.5 |  |  | 954 |  |  | 1011.5 |  |  | 1036.5 |  |  | 1081.5 |  |  | 1074.5 |  |  | 969 |  |  | 1039.5 |  |  | 1062.5 |  |  | 987.5 |  |  | 886.5 |  |  | 980.5 |  |  | 973 |  |  | 1001 |  |  | 891 |  |  | 987 |  |  | 952.5 |  |  | 986 |  |  | 959.5 |  |  | 901 |  |  | 987.5 |  |  | 1006.5 |  |  | 992.5 |  |  | 965.5 |  |  | 966.5 |  |  | 951 |  |  | 956.5 |  |  | 1035.5 |  |  | 889.5 |  |  | 985 |  |  | 972.5 |  |  | 998.5 |  |  | 973.5 |  |  | 1035 |  |  | 951.5 |  |  | 889.5 |  |  | 927.5 |  |  | 928.5 |  |  | 901.5 |  |  | 927.5 |  |  | 1037.5 |  |  | 906.5 |  |  | 974.5 |  |  | 900.5 |  |  | 900 |  |  | 1001.5 |  |  | 989.5 |  |  | 1000.5 |  |  | 962.5 |  |  | 1065.5 |  |  | 959 |  |  | 919.5 |  |  | 1047 |  |  | 956 |  |  | 933.5 |  |  | 1082.5 |  |  | 940.5 |  |  | 906 |  |  | 1003.5 |  |  | 1032.5 |  |  | 999.5 |  |  | 897 |  |  | 947.5 |  |  | 895.5 |  |  | 1038.5 |  |  | 909.5 |  |  | 928.5 |  |  | 954 |  |  | 905.5 |  |  | 982 |  |  | 1009.5 |  |  | 978.5 |  |  | 992.5 |  |  | 1091 |  |  | 924.5 |  |  | 998 |  |  | 997 |  |  | 985.5 |  |  | 951.5 |  |  | 969.5 |  |  | 1021.5 |  |  | 1020 |  |  | 961.5 |  |  | 957.5 |  |  | 927.5 |  |  | 1003 |  |  | 1025.5 |  |  | 896.5 |  |  | 915.5 |  |  | 990.5 |  |  | 1009 |  |  | 902.5 |  |  | 962.5 |  |  | 1014.5 |  |  | 1010.5 |  |  | 965.5 |  |  | 1028.5 |  |  | 1026 |  |  | 961.5 |  |  | 953.5 |  |  | 961 |  |  | 922.5 |  |  | 964.5 |  |  | 977.5 |  |  | 1018 |  |  | 946.5 |  |  | 949.5 |  |  | 976.5 |  |  | 1001.5 |  |  | 984.5 |  |  | 1052 |  |  | 928 |  |  | 907.5 |  |  | 1008.5 |  |  | 984.5 |  |  | 960.5 |  |  | 965 |  |  | 1015 |  |  | 941 |  |  | 1030.5 |  |  | 975 |  |  | 1022.5 |  |  | 1048.5 |  |  | 1033 |  |  | 944.5 |  |  | 1003.5 |  |  | 960.5 |  |  | 1051.5 |  |  | 916.5 |  |  | 955 |  |  | 992 |  |  | 912.5 |  |  | 965.5 |  |  | 984 |  |  | 876.5 |  |  | 1040.5 |  |  | 986 |  |  | 1091.5 |  |  | 1054.5 |  |  | 919 |  |  | 979.5 |  |  | 1006.5 |  |  | 954 |  |  | 995.5 |  |  | 958 |  |  | 1020.5 |  |  | 1049 |  |  | 889.5 |  |  | 994.5 |  |  | 1001.5 |  |  | 958.5 |  |  | 951.5 |  |  | 942.5 |  |  | 1043 |  |  | 989.5 |  |  | 988.5 |  |  | 938.5 |  |  | 1003.5 |  |  | 914.5 |  |  | 968 |  |  | 979.5 |  |  | 943 |  |  | 964.5 |  |  | 975.5 |  |  | 987.5 |  |  | 910.5 |  |  | 943.5 |  |  | 931.5 |  |  | 922.5 |  |  | 1065.5 |  |  | 968.5 |  |  | 1005 |  |  | 982.5 |  |  | 938 |  |  | 965 |  |  | 959.5 |  |  | 891 |  |  | 928.5 |  |  | 906.5 |  |  | 1006.5 |  |  | 991.5 |  |  | 1010.5 |  |  | 1053.5 |  |  | 1005.5 |  |  | 977 |  |  | 1059 |  |  | 903.5 |  |  | 902.5 |  |  | 969 |  |  | 934.5 |  |  | 1014.5 |  |  | 941.5 |  |  | 921.5 |  |  | 912.5 |  |  | 926 |  |  | 972.5 |  |  | 1015.5 |  |  | 979.5 |  |  | 952 |  |  | 1030.5 |  |  | 985.5 |  |  | 1013.5 |  |  | 1040.5 |  |  | 1033.5 |  |  | 941.5 |  |  | 1060.5 |  |  | 844.5 |  |  | 973.5 |  |  | 947 |  |  | 1008.5 |  |  | 943.5 |  |  | 1002.5 |  |  | 967.5 |  |  | 916.5 |  |  | 915.5 |  |  | 975.5 |  |  | 881 |  |  | 953.5 |  |  | 970.5 |  |  | 1048.5 |  |  | 916 |  |  | 931.5 |  |  | 943 |  |  | 968.5 |  |  | 1005.5 |  |  | 977.5 |  |  | 945 |  |  | 892.5 |  |  | 998 |  |  | 973 |  |  | 1016.5 |  |  | 946 |  |  | 986 |  |  | 1063.5 |  |  | 1027.5 |  |  | 931.5 |  |  | 1025 |  |  | 992.5 |  |  | 982.5 |  |  | 892.5 |  |  | 1031.5 |  |  | 921.5 |  |  | 999.5 |  |  | 979.5 |  |  | 996.5 |  |  | 913 |  |  | 1083.5 |  |  | 855 |  |  | 931.5 |  |  | 862.5 |  |  | 994.5 |  |  | 1007 |  |  | 1032 |  |  | 1034 |  |  | 997.5 |  |  | 942 |  |  | 983.5 |  |  | 1021.5 |  |  | 897.5 |  |  | 989.5 |  |  | 954.5 |  |  | 996.5 |  |  | 962.5 |  |  | 977.5 |  |  | 1029 |  |  | 942.5 |  |  | 904.5 |  |  | 1014.5 |  |  | 950.5 |  |  | 907 |  |  | 960.5 |  |  | 1016 |  |  | 956.5 |  |  | 944.5 |  |  | 956.5 |  |  | 899.5 |  |  | 924 |  |  | 921.5 |  |  | 917 |  |  | 927.5 |  |  | 1000.5 |  |  | 1053.5 |  |  | 992.5 |  |  | 976.5 |  |  | 983.5 |  |  | 947.5 |  |  | 998.5 |  |  | 860.5 |  |  | 1002 |  |  | 951.5 |  |  | 896.5 |  |  | 912.5 |  |  | 1003.5 |  |  | 962.5 |  |  | 893 |  |  | 966 |  |  | 947.5 |  |  | 926 |  |  | 1046.5 |  |  | 954.5 |  |  | 1000.5 |  |  | 1061.5 |  |  | 968.5 |  |  | 1018.5 |  |  | 996.5 |  |  | 995.5 |  |  | 946 |  |  | 1050.5 |  |  | 1076.5 |  |  | 1024.5 |  |  | 949 |  |  | 1008.5 |  |  | 939.5 |  |  | 1081 |  |  | 890 |  |  | 994.5 |  |  | 912 |  |  | 907 |  |  | 894.5 |  |  | 925 |  |  | 1066.5 |  |  | 1027.5 |  |  | 1012.5 |  |  | 991.5 |  |  | 941.5 |  |  | 1010.5 |  |  | 866.5 |  |  | 1012.5 |  |  | 941.5 |  |  | 942.5 |  |  | 1022 |  |  | 905 |  |  | 950.5 |  |  | 952.5 |  |  | 981.5 |  |  | 1017.5 |  |  | 903.5 |  |  | 1045.5 |  |  | 986.5 |  |  | 922.5 |  |  | 1018 |  |  | 910.5 |  |  | 919 |  |  | 881.5 |  |  | 1130.5 |  |  | 995.5 |  |  | 1027 |  |  | 948.5 |  |  | 964.5 |  |  | 862 |  |  | 1008.5 |  |  | 923.5 |  |  | 1032.5 |  |  | 951.5 |  |  | 961.5 |  |  | 964.5 |  |  | 939 |  |  | 1000.5 |  |  | 921.5 |  |  | 997.5 |  |  | 1075.5 |  |  | 916 |  |  | 935.5 |  |  | 1013.5 |  |  | 960 |  |  | 998.5 |  |  | 992.5 |  |  | 972 |  |  | 1008.5 |  |  | 1016.5 |  |  | 997.5 |  |  | 938 |  |  | 868.5 |  |  | 967.5 |  |  | 927 |  |  | 953.5 |  |  | 976.5 |  |  | 955.5 |  |  | 829.5 |  |  | 1048.5 |  |  | 1077.5 |  |  | 944.5 |  |  | 1002 |  |  | 998 |  |  | 885.5 |  |  | 992.5 |  |  | 952.5 |  |  | 975 |  |  | 1002.5 |  |  | 969.5 |  |  | 993.5 |  |  | 891.5 |  |  | 950.5 |  |  | 978.5 |  |  | 862.5 |  |  | 974.5 |  |  | 921.5 |  |  | 974 |  |  | 945.5 |  |  | 944.5 |  |  | 900.5 |  |  | 1022.5 |  |  | 1030.5 |  |  | 941.5 |  |  | 934.5 |  |  | 1035.5 |  |  | 943.5 |  |  | 973.5 |  |  | 936.5 |  |  | 980.5 |  |  | 969.5 |  |  | 1033 |  |  | 983.5 |  |  | 980.5 |  |  | 942 |  |  | 973.5 |  |  | 986.5 |  |  | 1038 |  |  | 956.5 |  |  | 1008.5 |  |  | 1047.5 |  |  | 1024 |  |  | 991.5 |  |  | 1026.5 |  |  | 954.5 |  |  | 831.5 |  |  | 1001.5 |  |  | 878 |  |  | 974.5 |  |  | 1038 |  |  | 964 |  |  | 1061.5 |  |  | 980.5 |  |  | 937.5 |  |  | 883.5 |  |  | 979.5 |  |  | 986.5 |  |  | 921 |  |  | 957.5 |  |  | 1066 |  |  | 963.5 |  |  | 991 |  |  | 942 |  |  | 1030 |  |  | 945.5 |  |  | 891 |  |  | 1054.5 |  |  | 1067.5 |  |  | 1023.5 |  |  | 1135.5 |  |  | 1029.5 |  |  | 988 |  |  | 1009.5 |  |  | 1023.5 |  |  | 1095.5 |  |  | 1020 |  |  | 1011.5 |  |  | 978.5 |  |  | 1051.5 |  |  | 1042.5 |  |  | 907 |  |  | 978 |  |  | 968 |  |  | 1000.5 |  |  | 1025 |  |  | 996 |  |  | 1004.5 |  |  | 936.5 |  |  | 925.5 |  |  | 1007.5 |  |  | 1022.5 |  |  | 1068.5 |  |  | 993.5 |  |  | 980.5 |  |  | 905.5 |  |  | 911 |  |  | 987.5 |  |  | 992 |  |  | 1026.5 |  |  | 993.5 |  |  | 1008.5 |  |  | 1007.5 |  |  | 1004 |  |  | 940.5 |  |  | 959 |  |  | 958.5 |  |  | 965.5 |  |  | 880 |  |  | 981 |  |  | 993.5 |  |  | 999 |  |  | 1079.5 |  |  | 825.5 |  |  | 969.5 |  |  | 988.5 |  |  | 989.5 |  |  | 956.5 |  |  | 966.5 |  |  | 917 |  |  | 1016.5 |  |  | 991.5 |  |  | 907.5 |  |  | 993.5 |  |  | 958.5 |  |  | 953.5 |  |  | 960.5 |  |  | 969.5 |  |  | 958.5 |  |  | 1005.5 |  |  | 975.5 |  |  | 897.5 |  |  | 1061 |  |  | 883.5 |  |  | 959.5 |  |  | 1025 |  |  | 877.5 |  |  | 877.5 |  |  | 955.5 |  |  | 942.5 |  |  | 1033 |  |  | 1001.5 |  |  | 994.5 |  |  | 927.5 |  |  | 1003.5 |  |  | 895 |  |  | 981.5 |  |  | 990.5 |  |  | 977.5 |  |  | 1027.5 |  |  | 1001.5 |  |  | 920.5 |  |  | 1037.5 |  |  | 1016.5 |  |  | 1019.5 |  |  | 943.5 |  |  | 1032.5 |  |  | 1008 |  |  | 995.5 |  |  | 984.5 |  |  | 1034.5 |  |  | 1006.5 |  |  | 944.5 |  |  | 950.5 |  |  | 1014 |  |  | 948.5 |  |  | 949 |  |  | 921.5 |  |  | 1031.5 |  |  | 928.5 |  |  | 951 |  |  | 972 |  |  | 961.5 |  |  | 975.5 |  |  | 888.5 |  |  | 957.5 |  |  | 921.5 |  |  | 911.5 |  |  | 945.5 |  |  | 916.5 |  |  | 984.5 |  |  | 1037.5 |  |  | 961.5 |  |  | 1012.5 |  |  | 982.5 |  |  | 1002.5 |  |  | 979.5 |  |  | 999.5 |  |  | 973.5 |  |  | 955.5 |  |  | 982.5 |  |  | 944.5 |  |  | 992.5 |  |  | 1013.5 |  |  | 1007 |  |  | 1089.5 |  |  | 925.5 |  |  | 1000.5 |  |  | 979 |  |  | 1005.5 |  |  | 984.5 |  |  | 975.5 |  |  | 1016.5 |  |  | 1017 |  |  | 891.5 |  |  | 987.5 |  |  | 904 |  |  | 904 |  |  | 940 |  |  | 970.5 |  |  | 995.5 |  |  | 980.5 |  |  | 1022.5 |  |  | 944 |  |  | 963.5 |  |  | 994.5 |  |  | 906 |  |  | 976 |  |  | 978.5 |  |  | 987.5 |  |  | 978 |  |  | 934.5 |  |  | 992 |  |  | 915.5 |  |  | 918.5 |  |  | 966 |  |  | 986.5 |  |  | 899.5 |  |  | 884.5 |  |  | 1028 |  |  | 1011.5 |  |  | 973.5 |  |  | 925.5 |  |  | 931.5 |  |  | 963.5 |  |  | 1038.5 |  |  | 910.5 |  |  | 974.5 |  |  | 1044.5 |  |  | 997.5 |  |  | 1015 |  |  | 917.5 |  |  | 981.5 |  |  | 996.5 |  |  | 1031.5 |  |  | 917.5 |  |  | 1018.5 |  |  | 1045.5 |  |  | 941.5 |  |  | 1025 |  |  | 1009.5 |  |  | 1003 |  |  | 1007.5 |  |  | 1035.5 |  |  | 1073.5 |  |  | 973.5 |  |  | 1020.5 |  |  | 912.5 |  |  | 849.5 |  |  | 974.5 |  |  | 968 |  |  | 935.5 |  |  | 916 |  |  | 956.5 |  |  | 903.5 |  |  | 1023.5 |  |  | 1060 |  |  | 942.5 |  |  | 1010.5 |  |  | 925 |  |  | 943.5 |  |  | 948 |  |  | 920.5 |  |  | 995.5 |  |  | 959.5 |  |  | 925 |  |  | 943.5 |  |  | 1083.5 |  |  | 908 |  |  | 1024.5 |  |  | 918.5 |  |  | 975 |  |  | 968.5 |  |  | 1101.5 |  |  | 1007.5 |  |  | 1040.5 |  |  | 955.5 |  |  | 935.5 |  |  | 915.5 |  |  | 972.5 |  |  | 880.5 |  |  | 1008.5 |  |  | 1055.5 |  |  | 949 |  |  | 1049 |  |  | 995.5 |  |  | 973.5 |  |  | 1047
35 |  | 1045.5 |  |  | 1070.5 |  |  | 1044 |  |  | 1010.5 |  |  | 1073.5 |  |  | 1049.5 |  |  | 1088.5 |  |  | 1015.5 |  |  | 993.5 |  |  | 1042.5 |  |  | 1017 |  |  | 1023.5 |  |  | 1093.5 |  |  | 982.5 |  |  | 957 |  |  | 1012.5 |  |  | 1097.5 |  |  | 1026.5 |  |  | 1103.5 |  |  | 940.5 |  |  | 1000.5 |  |  | 969.5 |  |  | 1029.5 |  |  | 969.5 |  |  | 947 |  |  | 1062.5 |  |  | 966.5 |  |  | 1000.5 |  |  | 985.5 |  |  | 944 |  |  | 1020 |  |  | 991.5 |  |  | 970.5 |  |  | 996.5 |  |  | 878.5 |  |  | 993 |  |  | 975.5 |  |  | 974 |  |  | 988.5 |  |  | 1041.5 |  |  | 949.5 |  |  | 1053.5 |  |  | 969.5 |  |  | 955 |  |  | 1138.5 |  |  | 1082 |  |  | 948.5 |  |  | 1026.5 |  |  | 1019.5 |  |  | 984.5 |  |  | 991.5 |  |  | 991.5 |  |  | 955.5 |  |  | 1010.5 |  |  | 1003.5 |  |  | 975.5 |  |  | 936.5 |  |  | 1003 |  |  | 1061.5 |  |  | 956.5 |  |  | 939 |  |  | 932.5 |  |  | 1064.5 |  |  | 1011.5 |  |  | 968.5 |  |  | 1035 |  |  | 1023.5 |  |  | 909 |  |  | 989.5 |  |  | 1016.5 |  |  | 1044 |  |  | 1031.5 |  |  | 999.5 |  |  | 1052.5 |  |  | 1037 |  |  | 1013 |  |  | 1014.5 |  |  | 935.5 |  |  | 883.5 |  |  | 988.5 |  |  | 968 |  |  | 939.5 |  |  | 1025.5 |  |  | 1087.5 |  |  | 1032.5 |  |  | 1057.5 |  |  | 1081.5 |  |  | 977.5 |  |  | 960.5 |  |  | 1035.5 |  |  | 1032.5 |  |  | 998 |  |  | 965.5 |  |  | 973 |  |  | 1021 |  |  | 954 |  |  | 1042.5 |  |  | 1032.5 |  |  | 965.5 |  |  | 992.5 |  |  | 980.5 |  |  | 1065 |  |  | 1046 |  |  | 952.5 |  |  | 976.5 |  |  | 985.5 |  |  | 1011.5 |  |  | 1062.5 |  |  | 1066.5 |  |  | 1048.5 |  |  | 1045.5 |  |  | 992.5 |  |  | 1085.5 |  |  | 998.5 |  |  | 1055.5 |  |  | 1018.5 |  |  | 1023.5 |  |  | 966.5 |  |  | 1021.5 |  |  | 1085.5 |  |  | 1032.5 |  |  | 1047.5 |  |  | 991.5 |  |  | 1009.5 |  |  | 1012.5 |  |  | 1050 |  |  | 958.5 |  |  | 1033.5 |  |  | 927.5 |  |  | 943.5 |  |  | 1098.5 |  |  | 1019 |  |  | 970.5 |  |  | 1058.5 |  |  | 947.5 |  |  | 1054.5 |  |  | 966 |  |  | 1001.5 |  |  | 1072.5 |  |  | 988 |  |  | 1040.5 |  |  | 969 |  |  | 1002 |  |  | 1065.5 |  |  | 1022 |  |  | 1072.5 |  |  | 973.5 |  |  | 1034.5 |  |  | 958.5 |  |  | 1066.5 |  |  | 1035.5 |  |  | 1016.5 |  |  | 1014.5 |  |  | 1060.5 |  |  | 1023.5 |  |  | 1040 |  |  | 912.5 |  |  | 997 |  |  | 926.5 |  |  | 1028.5 |  |  | 1031 |  |  | 1033.5 |  |  | 979.5 |  |  | 977.5 |  |  | 1026 |  |  | 1029.5 |  |  | 963.5 |  |  | 968.5 |  |  | 1001.5 |  |  | 995.5 |  |  | 998.5 |  |  | 1016 |  |  | 982.5 |  |  | 988.5 |  |  | 998.5 |  |  | 993.5 |  |  | 1041.5 |  |  | 1051.5 |  |  | 991.5 |  |  | 1100 |  |  | 1021.5 |  |  | 1000.5 |  |  | 1072.5 |  |  | 1056.5 |  |  | 915.5 |  |  | 1127.5 |  |  | 999.5 |  |  | 1034.5 |  |  | 986.5 |  |  | 958.5 |  |  | 1004.5 |  |  | 920.5 |  |  | 902.5 |  |  | 970 |  |  | 960.5 |  |  | 1020.5 |  |  | 967.5 |  |  | 986.5 |  |  | 1080.5 |  |  | 1028.5 |  |  | 1018.5 |  |  | 952.5 |  |  | 958.5 |  |  | 1042.5 |  |  | 993.5 |  |  | 1107.5 |  |  | 956.5 |  |  | 954.5 |  |  | 1075.5 |  |  | 1043.5 |  |  | 1017 |  |  | 1041.5 |  |  | 988.5 |  |  | 921 |  |  | 1031.5 |  |  | 1003 |  |  | 986.5 |  |  | 1079.5 |  |  | 1103.5 |  |  | 1024.5 |  |  | 1005.5 |  |  | 977.5 |  |  | 974.5 |  |  | 947.5 |  |  | 936 |  |  | 950.5 |  |  | 841.5 |  |  | 1039.5 |  |  | 991.5 |  |  | 1094 |  |  | 949.5 |  |  | 937.5 |  |  | 1045.5 |  |  | 1063.5 |  |  | 1079.5 |  |  | 941.5 |  |  | 945.5 |  |  | 1015.5 |  |  | 995 |  |  | 1012 |  |  | 906.5 |  |  | 1005.5 |  |  | 1023.5 |  |  | 1071 |  |  | 1093.5 |  |  | 1034.5 |  |  | 1008.5 |  |  | 963 |  |  | 1013.5 |  |  | 1059.5 |  |  | 986.5 |  |  | 950.5 |  |  | 991.5 |  |  | 1021.5 |  |  | 1049.5 |  |  | 948.5 |  |  | 1051.5 |  |  | 891 |  |  | 940.5 |  |  | 993.5 |  |  | 953.5 |  |  | 978.5 |  |  | 1016.5 |  |  | 1062 |  |  | 1004.5 |  |  | 1063.5 |  |  | 1008 |  |  | 1085.5 |  |  | 1001.5 |  |  | 1075 |  |  | 958.5 |  |  | 1003.5 |  |  | 1161.5 |  |  | 971.5 |  |  | 1068 |  |  | 1071 |  |  | 1015.5 |  |  | 998.5 |  |  | 1037.5 |  |  | 1008.5 |  |  | 1077.5 |  |  | 933.5 |  |  | 978 |  |  | 1035.5 |  |  | 1035.5 |  |  | 1011 |  |  | 1006.5 |  |  | 957.5 |  |  | 962 |  |  | 1007.5 |  |  | 973.5 |  |  | 997.5 |  |  | 1051 |  |  | 1050.5 |  |  | 944 |  |  | 1061.5 |  |  | 981.5 |  |  | 1007.5 |  |  | 948 |  |  | 978.5 |  |  | 1064.5 |  |  | 972.5 |  |  | 988 |  |  | 903.5 |  |  | 978.5 |  |  | 1067.5 |  |  | 1073.5 |  |  | 997.5 |  |  | 970 |  |  | 966.5 |  |  | 1094.5 |  |  | 1107.5 |  |  | 968 |  |  | 1015 |  |  | 1080.5 |  |  | 1020.5 |  |  | 988.5 |  |  | 1054.5 |  |  | 1036.5 |  |  | 1042.5 |  |  | 976.5 |  |  | 1028.5 |  |  | 900.5 |  |  | 1008.5 |  |  | 980 |  |  | 1035.5 |  |  | 1075.5 |  |  | 1128.5 |  |  | 1113.5 |  |  | 993 |  |  | 1068.5 |  |  | 1077.5 |  |  | 1026.5 |  |  | 912.5 |  |  | 1001.5 |  |  | 999 |  |  | 1016 |  |  | 917 |  |  | 1016 |  |  | 973.5 |  |  | 1015 |  |  | 980.5 |  |  | 948 |  |  | 1011.5 |  |  | 1045.5 |  |  | 1007.5 |  |  | 991.5 |  |  | 981.5 |  |  | 990 |  |  | 1003.5 |  |  | 1064.5 |  |  | 904.5 |  |  | 1032 |  |  | 1001.5 |  |  | 1037.5 |  |  | 999.5 |  |  | 1082 |  |  | 966.5 |  |  | 915.5 |  |  | 951.5 |  |  | 943.5 |  |  | 948.5 |  |  | 966.5 |  |  | 1076.5 |  |  | 932.5 |  |  | 1021.5 |  |  | 926.5 |  |  | 924 |  |  | 1030.5 |  |  | 1018.5 |  |  | 1015.5 |  |  | 986.5 |  |  | 1104.5 |  |  | 988 |  |  | 945.5 |  |  | 1071 |  |  | 971 |  |  | 954.5 |  |  | 1097.5 |  |  | 969.5 |  |  | 953 |  |  | 1042.5 |  |  | 1056.5 |  |  | 1020.5 |  |  | 936 |  |  | 994.5 |  |  | 919.5 |  |  | 1077.5 |  |  | 924.5 |  |  | 957.5 |  |  | 978 |  |  | 920.5 |  |  | 1008 |  |  | 1030.5 |  |  | 999.5 |  |  | 1007.5 |  |  | 1117 |  |  | 953.5 |  |  | 1045 |  |  | 1044 |  |  | 1014.5 |  |  | 990.5 |  |  | 984.5 |  |  | 1060.5 |  |  | 1059 |  |  | 985.5 |  |  | 996.5 |  |  | 956.5 |  |  | 1018 |  |  | 1046.5 |  |  | 935.5 |  |  | 954.5 |  |  | 1029.5 |  |  | 1038 |  |  | 941.5 |  |  | 977.5 |  |  | 1040.5 |  |  | 1025.5 |  |  | 994.5 |  |  | 1067.5 |  |  | 1047 |  |  | 1008.5 |  |  | 1000.5 |  |  | 1000 |  |  | 937.5 |  |  | 985.5 |  |  | 1016.5 |  |  | 1033 |  |  | 970.5 |  |  | 996.5 |  |  | 1005.5 |  |  | 1040.5 |  |  | 1023.5 |  |  | 1067 |  |  | 975 |  |  | 933.5 |  |  | 1029.5 |  |  | 1008.5 |  |  | 986.5 |  |  | 980 |  |  | 1036 |  |  | 980 |  |  | 1051.5 |  |  | 996 |  |  | 1043.5 |  |  | 1077.5 |  |  | 1072 |  |  | 991.5 |  |  | 1024.5 |  |  | 989.5 |  |  | 1098.5 |  |  | 963.5 |  |  | 979 |  |  | 1031 |  |  | 927.5 |  |  | 994.5 |  |  | 1005 |  |  | 905.5 |  |  | 1061.5 |  |  | 1025 |  |  | 1130.5 |  |  | 1083.5 |  |  | 934 |  |  | 1008.5 |  |  | 1030.5 |  |  | 975 |  |  | 1024.5 |  |  | 973 |  |  | 1046.5 |  |  | 1070 |  |  | 910.5 |  |  | 1009.5 |  |  | 1030.5 |  |  | 987.5 |  |  | 990.5 |  |  | 966.5 |  |  | 1072 |  |  | 1010.5 |  |  | 1009.5 |  |  | 959.5 |  |  | 1032.5 |  |  | 938.5 |  |  | 1015 |  |  | 1005.5 |  |  | 969 |  |  | 985.5 |  |  | 1004.5 |  |  | 1016.5 |  |  | 925.5 |  |  | 982.5 |  |  | 960.5 |  |  | 937.5 |  |  | 1094.5 |  |  | 994.5 |  |  | 1052 |  |  | 1029.5 |  |  | 959 |  |  | 1012 |  |  | 980.5 |  |  | 920 |  |  | 943.5 |  |  | 945.5 |  |  | 1030.5 |  |  | 1017.5 |  |  | 1031.5 |  |  | 1074.5 |  |  | 1031.5 |  |  | 1006 |  |  | 1106 |  |  | 942.5 |  |  | 928.5 |  |  | 998 |  |  | 955.5 |  |  | 1061.5 |  |  | 962.5 |  |  | 945.5 |  |  | 951.5 |  |  | 965 |  |  | 993.5 |  |  | 1041.5 |  |  | 994.5 |  |  | 991 |  |  | 1069.5 |  |  | 1024.5 |  |  | 1052.5 |  |  | 1079.5 |  |  | 1072.5 |  |  | 967.5 |  |  | 1089.5 |  |  | 873.5 |  |  | 994.5 |  |  | 994 |  |  | 1055.5 |  |  | 990.5 |  |  | 1041.5 |  |  | 993.5 |  |  | 931.5 |  |  | 939.5 |  |  | 1001.5 |  |  | 920 |  |  | 974.5 |  |  | 991.5 |  |  | 1087.5 |  |  | 942 |  |  | 960.5 |  |  | 969 |  |  | 989.5 |  |  | 1020.5 |  |  | 1003.5 |  |  | 984 |  |  | 916.5 |  |  | 1022 |  |  | 997 |  |  | 1031.5 |  |  | 970 |  |  | 1015 |  |  | 1084.5 |  |  | 1066.5 |  |  | 970.5 |  |  | 1064 |  |  | 1031.5 |  |  | 1008.5 |  |  | 921.5 |  |  | 1055.5 |  |  | 936.5 |  |  | 1025.5 |  |  | 1018.5 |  |  | 1022.5 |  |  | 942 |  |  | 1109.5 |  |  | 870 |  |  | 955.5 |  |  | 901.5 |  |  | 1023.5 |  |  | 1046 |  |  | 1056 |  |  | 1049 |  |  | 1012.5 |  |  | 971 |  |  | 1030.5 |  |  | 1045.5 |  |  | 918.5 |  |  | 1010.5 |  |  | 993.5 |  |  | 1025.5 |  |  | 986.5 |  |  | 1016.5 |  |  | 1068 |  |  | 966.5 |  |  | 930.5 |  |  | 1043.5 |  |  | 974.5 |  |  | 946 |  |  | 999.5 |  |  | 1045 |  |  | 982.5 |  |  | 991.5 |  |  | 971.5 |  |  | 914.5 |  |  | 945 |  |  | 950.5 |  |  | 932 |  |  | 956.5 |  |  | 1047.5 |  |  | 1077.5 |  |  | 1016.5 |  |  | 1005.5 |  |  | 1007.5 |  |  | 976.5 |  |  | 1022.5 |  |  | 884.5 |  |  | 1023 |  |  | 990.5 |  |  | 943.5 |  |  | 941.5 |  |  | 1042.5 |  |  | 986.5 |  |  | 908 |  |  | 981 |  |  | 962.5 |  |  | 952 |  |  | 1075.5 |  |  | 975.5 |  |  | 1047.5 |  |  | 1100.5 |  |  | 1007.5 |  |  | 1044.5 |  |  | 1011.5 |  |  | 1024.5 |  |  | 993 |  |  | 1097.5 |  |  | 1097.5 |  |  | 1045.5 |  |  | 970 |  |  | 1047.5 |  |  | 968.5 |  |  | 1105 |  |  | 911 |  |  | 1020.5 |  |  | 951 |  |  | 922 |  |  | 923.5 |  |  | 940 |  |  | 1095.5 |  |  | 1056.5 |  |  | 1059.5 |  |  | 1012.5 |  |  | 980.5 |  |  | 1049.5 |  |  | 913.5 |  |  | 1027.5 |  |  | 965.5 |  |  | 963.5 |  |  | 1037 |  |  | 944 |  |  | 974.5 |  |  | 976.5 |  |  | 996.5 |  |  | 1056.5 |  |  | 929.5 |  |  | 1084.5 |  |  | 1025.5 |  |  | 951.5 |  |  | 1044 |  |  | 949.5 |  |  | 934 |  |  | 910.5 |  |  | 1154.5 |  |  | 1042.5 |  |  | 1048 |  |  | 987.5 |  |  | 990.5 |  |  | 886 |  |  | 1047.5 |  |  | 962.5 |  |  | 1071.5 |  |  | 972.5 |  |  | 990.5 |  |  | 990.5 |  |  | 960 |  |  | 1021.5 |  |  | 968.5 |  |  | 1012.5 |  |  | 1104.5 |  |  | 931 |  |  | 961.5 |  |  | 1037.5 |  |  | 981 |  |  | 1022.5 |  |  | 1039.5 |  |  | 996 |  |  | 1047.5 |  |  | 1031.5 |  |  | 1012.5 |  |  | 953 |  |  | 892.5 |  |  | 1006.5 |  |  | 966 |  |  | 968.5 |  |  | 1023.5 |  |  | 994.5 |  |  | 876.5 |  |  | 1069.5 |  |  | 1116.5 |  |  | 973.5 |  |  | 1028 |  |  | 1013 |  |  | 924.5 |  |  | 1007.5 |  |  | 976.5 |  |  | 1022 |  |  | 1041.5 |  |  | 990.5 |  |  | 1017.5 |  |  | 917.5 |  |  | 997.5 |  |  | 1002.5 |  |  | 909.5 |  |  | 989.5 |  |  | 945.5 |  |  | 1013 |  |  | 974.5 |  |  | 983.5 |  |  | 939.5 |  |  | 1069.5 |  |  | 1054.5 |  |  | 988.5 |  |  | 960.5 |  |  | 1064.5 |  |  | 958.5 |  |  | 997.5 |  |  | 957.5 |  |  | 1004.5 |  |  | 990.5 |  |  | 1059 |  |  | 1009.5 |  |  | 1004.5 |  |  | 966 |  |  | 1002.5 |  |  | 1025.5 |  |  | 1064 |  |  | 995.5 |  |  | 1037.5 |  |  | 1094.5 |  |  | 1071 |  |  | 1030.5 |  |  | 1065.5 |  |  | 993.5 |  |  | 852.5 |  |  | 1040.5 |  |  | 917 |  |  | 998.5 |  |  | 1059 |  |  | 1011 |  |  | 1076.5 |  |  | 995.5 |  |  | 961.5 |  |  | 922.5 |  |  | 1003.5 |  |  | 1010.5 |  |  | 968 |  |  | 996.5 |  |  | 1090 |  |  | 984.5 |  |  | 1030 |  |  | 968 |  |  | 1051 |  |  | 969.5 |  |  | 930 |  |  | 1078.5 |  |  | 1093.5 |  |  | 1062.5 |  |  | 1174.5 |  |  | 1050.5 |  |  | 1012 |  |  | 1030.5 |  |  | 1070.5 |  |  | 1142.5 |  |  | 1035 |  |  | 1040.5 |  |  | 1017.5 |  |  | 1072.5 |  |  | 1071.5 |  |  | 931 |  |  | 1025 |  |  | 1007 |  |  | 1047.5 |  |  | 1072 |  |  | 1022 |  |  | 1025.5 |  |  | 975.5 |  |  | 964.5 |  |  | 1028.5 |  |  | 1061.5 |  |  | 1107.5 |  |  | 1032.5 |  |  | 1027.5 |  |  | 944.5 |  |  | 926 |  |  | 1011.5 |  |  | 1021 |  |  | 1052.5 |  |  | 1032.5 |  |  | 1029.5 |  |  | 1031.5 |  |  | 1043 |  |  | 979.5 |  |  | 974 |  |  | 979.5 |  |  | 1012.5 |  |  | 909 |  |  | 996 |  |  | 1008.5 |  |  | 1023 |  |  | 1100.5 |  |  | 864.5 |  |  | 990.5 |  |  | 1009.5 |  |  | 1010.5 |  |  | 995.5 |  |  | 981.5 |  |  | 943 |  |  | 1055.5 |  |  | 1030.5 |  |  | 931.5 |  |  | 1019.5 |  |  | 973.5 |  |  | 977.5 |  |  | 984.5 |  |  | 998.5 |  |  | 984.5 |  |  | 1031.5 |  |  | 999.5 |  |  | 944.5 |  |  | 1087 |  |  | 922.5 |  |  | 988.5 |  |  | 1051 |  |  | 898.5 |  |  | 903.5 |  |  | 979.5 |  |  | 963.5 |  |  | 1072 |  |  | 1048.5 |  |  | 1020.5 |  |  | 956.5 |  |  | 1018.5 |  |  | 934 |  |  | 1028.5 |  |  | 1019.5 |  |  | 1006.5 |  |  | 1074.5 |  |  | 1025.5 |  |  | 967.5 |  |  | 1061.5 |  |  | 1055.5 |  |  | 1043.5 |  |  | 982.5 |  |  | 1047.5 |  |  | 1034 |  |  | 1021.5 |  |  | 999.5 |  |  | 1073.5 |  |  | 1021.5 |  |  | 973.5 |  |  | 971.5 |  |  | 1038 |  |  | 977.5 |  |  | 975 |  |  | 947.5 |  |  | 1070.5 |  |  | 957.5 |  |  | 980 |  |  | 1011 |  |  | 982.5 |  |  | 1014.5 |  |  | 903.5 |  |  | 1004.5 |  |  | 968.5 |  |  | 932.5 |  |  | 960.5 |  |  | 937.5 |  |  | 999.5 |  |  | 1058.5 |  |  | 976.5 |  |  | 1036.5 |  |  | 1006.5 |  |  | 1017.5 |  |  | 1018.5 |  |  | 1046.5 |  |  | 1020.5 |  |  | 994.5 |  |  | 1021.5 |  |  | 959.5 |  |  | 1013.5 |  |  | 1037.5 |  |  | 1028 |  |  | 1118.5 |  |  | 972.5 |  |  | 1039.5 |  |  | 1018 |  |  | 1026.5 |  |  | 1023.5 |  |  | 1001.5 |  |  | 1031.5 |  |  | 1046 |  |  | 906.5 |  |  | 1013.5 |  |  | 925 |  |  | 925 |  |  | 961 |  |  | 991.5 |  |  | 1010.5 |  |  | 1019.5 |  |  | 1037.5 |  |  | 991 |  |  | 1010.5 |  |  | 1018.5 |  |  | 921 |  |  | 997 |  |  | 1002.5 |  |  | 1011.5 |  |  | 993 |  |  | 981.5 |  |  | 1031 |  |  | 930.5 |  |  | 957.5 |  |  | 1013 |  |  | 1033.5 |  |  | 923.5 |  |  | 910.5 |  |  | 1067 |  |  | 1040.5 |  |  | 997.5 |  |  | 949.5 |  |  | 946.5 |  |  | 1002.5 |  |  | 1077.5 |  |  | 931.5 |  |  | 1013.5 |  |  | 1068.5 |  |  | 1021.5 |  |  | 1054 |  |  | 938.5 |  |  | 1007.5 |  |  | 1043.5 |  |  | 1055.5 |  |  | 932.5 |  |  | 1057.5 |  |  | 1084.5 |  |  | 967.5 |  |  | 1051 |  |  | 1038.5 |  |  | 1042 |  |  | 1046.5 |  |  | 1082.5 |  |  | 1102.5 |  |  | 994.5 |  |  | 1041.5 |  |  | 959.5 |  |  | 873.5 |  |  | 1013.5 |  |  | 1007 |  |  | 961.5 |  |  | 963 |  |  | 980.5 |  |  | 927.5 |  |  | 1052.5 |  |  | 1081 |  |  | 968.5 |  |  | 1031.5 |  |  | 940 |  |  | 967.5 |  |  | 972 |  |  | 959.5 |  |  | 1019.5 |  |  | 998.5 |  |  | 954 |  |  | 990.5 |  |  | 1130.5 |  |  | 934 |  |  | 1050.5 |  |  | 939.5 |  |  | 1004 |  |  | 1015.5 |  |  | 1148.5 |  |  | 1033.5 |  |  | 1055.5 |  |  | 1002.5 |  |  | 974.5 |  |  | 941.5 |  |  | 1019.5 |  |  | 927.5 |  |  | 1029.5 |  |  | 1102.5 |  |  | 978 |  |  | 1078 |  |  | 1019.5 |  |  | 1012.5 |  |  | 1094
36 |  | 1069.5 |  |  | 1117.5 |  |  | 1059 |  |  | 1039.5 |  |  | 1102.5 |  |  | 1075.5 |  |  | 1112.5 |  |  | 1044.5 |  |  | 1019.5 |  |  | 1066.5 |  |  | 1038 |  |  | 1044.5 |  |  | 1114.5 |  |  | 1029.5 |  |  | 983 |  |  | 1027.5 |  |  | 1144.5 |  |  | 1065.5 |  |  | 1142.5 |  |  | 966.5 |  |  | 1029.5 |  |  | 995.5 |  |  | 1050.5 |  |  | 990.5 |  |  | 971 |  |  | 1091.5 |  |  | 990.5 |  |  | 1024.5 |  |  | 1024.5 |  |  | 970 |  |  | 1049 |  |  | 1015.5 |  |  | 1017.5 |  |  | 1043.5 |  |  | 925.5 |  |  | 1019 |  |  | 1001.5 |  |  | 1013 |  |  | 1009.5 |  |  | 1065.5 |  |  | 978.5 |  |  | 1100.5 |  |  | 984.5 |  |  | 976 |  |  | 1159.5 |  |  | 1097 |  |  | 969.5 |  |  | 1047.5 |  |  | 1066.5 |  |  | 1005.5 |  |  | 1030.5 |  |  | 1006.5 |  |  | 981.5 |  |  | 1031.5 |  |  | 1050.5 |  |  | 1022.5 |  |  | 965.5 |  |  | 1032 |  |  | 1087.5 |  |  | 995.5 |  |  | 986 |  |  | 979.5 |  |  | 1085.5 |  |  | 1035.5 |  |  | 1007.5 |  |  | 1059 |  |  | 1047.5 |  |  | 933 |  |  | 1004.5 |  |  | 1040.5 |  |  | 1059 |  |  | 1055.5 |  |  | 1023.5 |  |  | 1081.5 |  |  | 1052 |  |  | 1039 |  |  | 1038.5 |  |  | 950.5 |  |  | 898.5 |  |  | 1012.5 |  |  | 983 |  |  | 978.5 |  |  | 1064.5 |  |  | 1126.5 |  |  | 1079.5 |  |  | 1096.5 |  |  | 1102.5 |  |  | 1006.5 |  |  | 1007.5 |  |  | 1074.5 |  |  | 1071.5 |  |  | 1037 |  |  | 980.5 |  |  | 1012 |  |  | 1050 |  |  | 1001 |  |  | 1063.5 |  |  | 1071.5 |  |  | 1004.5 |  |  | 1039.5 |  |  | 1006.5 |  |  | 1091 |  |  | 1070 |  |  | 976.5 |  |  | 1000.5 |  |  | 1006.5 |  |  | 1026.5 |  |  | 1077.5 |  |  | 1105.5 |  |  | 1087.5 |  |  | 1071.5 |  |  | 1031.5 |  |  | 1106.5 |  |  | 1027.5 |  |  | 1084.5 |  |  | 1065.5 |  |  | 1038.5 |  |  | 981.5 |  |  | 1047.5 |  |  | 1111.5 |  |  | 1058.5 |  |  | 1062.5 |  |  | 1020.5 |  |  | 1035.5 |  |  | 1059.5 |  |  | 1076 |  |  | 979.5 |  |  | 1057.5 |  |  | 942.5 |  |  | 958.5 |  |  | 1127.5 |  |  | 1048 |  |  | 985.5 |  |  | 1087.5 |  |  | 962.5 |  |  | 1083.5 |  |  | 987 |  |  | 1022.5 |  |  | 1101.5 |  |  | 1009 |  |  | 1079.5 |  |  | 990 |  |  | 1031 |  |  | 1104.5 |  |  | 1061 |  |  | 1101.5 |  |  | 1002.5 |  |  | 1049.5 |  |  | 987.5 |  |  | 1087.5 |  |  | 1074.5 |  |  | 1040.5 |  |  | 1038.5 |  |  | 1099.5 |  |  | 1047.5 |  |  | 1079 |  |  | 941.5 |  |  | 1012 |  |  | 941.5 |  |  | 1067.5 |  |  | 1052 |  |  | 1072.5 |  |  | 994.5 |  |  | 992.5 |  |  | 1055 |  |  | 1058.5 |  |  | 987.5 |  |  | 992.5 |  |  | 1027.5 |  |  | 1024.5 |  |  | 1037.5 |  |  | 1045 |  |  | 1029.5 |  |  | 1009.5 |  |  | 1013.5 |  |  | 1014.5 |  |  | 1088.5 |  |  | 1098.5 |  |  | 1006.5 |  |  | 1121 |  |  | 1060.5 |  |  | 1047.5 |  |  | 1111.5 |  |  | 1103.5 |  |  | 954.5 |  |  | 1174.5 |  |  | 1046.5 |  |  | 1055.5 |  |  | 1007.5 |  |  | 982.5 |  |  | 1030.5 |  |  | 949.5 |  |  | 926.5 |  |  | 994 |  |  | 999.5 |  |  | 1049.5 |  |  | 988.5 |  |  | 1025.5 |  |  | 1101.5 |  |  | 1049.5 |  |  | 1047.5 |  |  | 973.5 |  |  | 979.5 |  |  | 1063.5 |  |  | 1019.5 |  |  | 1154.5 |  |  | 995.5 |  |  | 969.5 |  |  | 1114.5 |  |  | 1064.5 |  |  | 1064 |  |  | 1070.5 |  |  | 1012.5 |  |  | 942 |  |  | 1060.5 |  |  | 1024 |  |  | 1007.5 |  |  | 1105.5 |  |  | 1127.5 |  |  | 1045.5 |  |  | 1034.5 |  |  | 992.5 |  |  | 1013.5 |  |  | 973.5 |  |  | 957 |  |  | 979.5 |  |  | 870.5 |  |  | 1078.5 |  |  | 1012.5 |  |  | 1109 |  |  | 988.5 |  |  | 966.5 |  |  | 1074.5 |  |  | 1084.5 |  |  | 1103.5 |  |  | 962.5 |  |  | 992.5 |  |  | 1054.5 |  |  | 1024 |  |  | 1038 |  |  | 930.5 |  |  | 1020.5 |  |  | 1062.5 |  |  | 1100 |  |  | 1108.5 |  |  | 1058.5 |  |  | 1032.5 |  |  | 1010 |  |  | 1042.5 |  |  | 1074.5 |  |  | 1025.5 |  |  | 997.5 |  |  | 1030.5 |  |  | 1042.5 |  |  | 1070.5 |  |  | 974.5 |  |  | 1077.5 |  |  | 915 |  |  | 961.5 |  |  | 1008.5 |  |  | 974.5 |  |  | 1002.5 |  |  | 1045.5 |  |  | 1109 |  |  | 1033.5 |  |  | 1102.5 |  |  | 1032 |  |  | 1100.5 |  |  | 1040.5 |  |  | 1099 |  |  | 997.5 |  |  | 1050.5 |  |  | 1190.5 |  |  | 992.5 |  |  | 1089 |  |  | 1092 |  |  | 1054.5 |  |  | 1045.5 |  |  | 1084.5 |  |  | 1055.5 |  |  | 1098.5 |  |  | 972.5 |  |  | 1017 |  |  | 1074.5 |  |  | 1074.5 |  |  | 1037 |  |  | 1027.5 |  |  | 972.5 |  |  | 983 |  |  | 1036.5 |  |  | 997.5 |  |  | 1018.5 |  |  | 1072 |  |  | 1074.5 |  |  | 983 |  |  | 1082.5 |  |  | 1002.5 |  |  | 1033.5 |  |  | 977 |  |  | 1007.5 |  |  | 1103.5 |  |  | 993.5 |  |  | 1027 |  |  | 929.5 |  |  | 999.5 |  |  | 1093.5 |  |  | 1112.5 |  |  | 1021.5 |  |  | 996 |  |  | 990.5 |  |  | 1133.5 |  |  | 1128.5 |  |  | 992 |  |  | 1041 |  |  | 1101.5 |  |  | 1059.5 |  |  | 1003.5 |  |  | 1075.5 |  |  | 1075.5 |  |  | 1081.5 |  |  | 1015.5 |  |  | 1049.5 |  |  | 929.5 |  |  | 1023.5 |  |  | 1019 |  |  | 1074.5 |  |  | 1104.5 |  |  | 1157.5 |  |  | 1142.5 |  |  | 1022 |  |  | 1107.5 |  |  | 1092.5 |  |  | 1073.5 |  |  | 936.5 |  |  | 1040.5 |  |  | 1046 |  |  | 1031 |  |  | 943 |  |  | 1037 |  |  | 988.5 |  |  | 1054 |  |  | 1027.5 |  |  | 987 |  |  | 1037.5 |  |  | 1066.5 |  |  | 1033.5 |  |  | 1017.5 |  |  | 1002.5 |  |  | 1011 |  |  | 1050.5 |  |  | 1088.5 |  |  | 943.5 |  |  | 1061 |  |  | 1048.5 |  |  | 1061.5 |  |  | 1020.5 |  |  | 1108 |  |  | 995.5 |  |  | 930.5 |  |  | 990.5 |  |  | 982.5 |  |  | 987.5 |  |  | 987.5 |  |  | 1091.5 |  |  | 971.5 |  |  | 1050.5 |  |  | 947.5 |  |  | 971 |  |  | 1069.5 |  |  | 1033.5 |  |  | 1030.5 |  |  | 1012.5 |  |  | 1151.5 |  |  | 1027 |  |  | 992.5 |  |  | 1086 |  |  | 992 |  |  | 980.5 |  |  | 1144.5 |  |  | 990.5 |  |  | 982 |  |  | 1081.5 |  |  | 1082.5 |  |  | 1049.5 |  |  | 960 |  |  | 1033.5 |  |  | 948.5 |  |  | 1116.5 |  |  | 948.5 |  |  | 1004.5 |  |  | 999 |  |  | 944.5 |  |  | 1034 |  |  | 1059.5 |  |  | 1020.5 |  |  | 1033.5 |  |  | 1164 |  |  | 982.5 |  |  | 1092 |  |  | 1083 |  |  | 1053.5 |  |  | 1029.5 |  |  | 1010.5 |  |  | 1099.5 |  |  | 1085 |  |  | 1024.5 |  |  | 1035.5 |  |  | 982.5 |  |  | 1044 |  |  | 1075.5 |  |  | 974.5 |  |  | 969.5 |  |  | 1050.5 |  |  | 1077 |  |  | 967.5 |  |  | 1003.5 |  |  | 1079.5 |  |  | 1040.5 |  |  | 1033.5 |  |  | 1091.5 |  |  | 1068 |  |  | 1023.5 |  |  | 1021.5 |  |  | 1015 |  |  | 976.5 |  |  | 1011.5 |  |  | 1055.5 |  |  | 1057 |  |  | 994.5 |  |  | 1011.5 |  |  | 1020.5 |  |  | 1064.5 |  |  | 1052.5 |  |  | 1088 |  |  | 999 |  |  | 972.5 |  |  | 1044.5 |  |  | 1029.5 |  |  | 1012.5 |  |  | 1006 |  |  | 1051 |  |  | 995 |  |  | 1090.5 |  |  | 1011 |  |  | 1072.5 |  |  | 1106.5 |  |  | 1111 |  |  | 1017.5 |  |  | 1063.5 |  |  | 1028.5 |  |  | 1137.5 |  |  | 978.5 |  |  | 1018 |  |  | 1055 |  |  | 942.5 |  |  | 1033.5 |  |  | 1020 |  |  | 934.5 |  |  | 1108.5 |  |  | 1064 |  |  | 1154.5 |  |  | 1098.5 |  |  | 958 |  |  | 1037.5 |  |  | 1077.5 |  |  | 1014 |  |  | 1048.5 |  |  | 999 |  |  | 1070.5 |  |  | 1109 |  |  | 949.5 |  |  | 1038.5 |  |  | 1051.5 |  |  | 1016.5 |  |  | 1029.5 |  |  | 1005.5 |  |  | 1119 |  |  | 1031.5 |  |  | 1038.5 |  |  | 980.5 |  |  | 1071.5 |  |  | 977.5 |  |  | 1036 |  |  | 1026.5 |  |  | 1008 |  |  | 1032.5 |  |  | 1019.5 |  |  | 1031.5 |  |  | 949.5 |  |  | 1021.5 |  |  | 989.5 |  |  | 976.5 |  |  | 1118.5 |  |  | 1015.5 |  |  | 1078 |  |  | 1076.5 |  |  | 980 |  |  | 1041 |  |  | 1004.5 |  |  | 935 |  |  | 982.5 |  |  | 974.5 |  |  | 1054.5 |  |  | 1046.5 |  |  | 1052.5 |  |  | 1095.5 |  |  | 1078.5 |  |  | 1030 |  |  | 1127 |  |  | 966.5 |  |  | 952.5 |  |  | 1022 |  |  | 976.5 |  |  | 1076.5 |  |  | 977.5 |  |  | 969.5 |  |  | 990.5 |  |  | 980 |  |  | 1008.5 |  |  | 1065.5 |  |  | 1020.5 |  |  | 1015 |  |  | 1084.5 |  |  | 1045.5 |  |  | 1091.5 |  |  | 1126.5 |  |  | 1098.5 |  |  | 988.5 |  |  | 1128.5 |  |  | 897.5 |  |  | 1009.5 |  |  | 1009 |  |  | 1081.5 |  |  | 1029.5 |  |  | 1080.5 |  |  | 1017.5 |  |  | 957.5 |  |  | 960.5 |  |  | 1040.5 |  |  | 935 |  |  | 989.5 |  |  | 1030.5 |  |  | 1102.5 |  |  | 968 |  |  | 999.5 |  |  | 993 |  |  | 1028.5 |  |  | 1059.5 |  |  | 1024.5 |  |  | 999 |  |  | 942.5 |  |  | 1051 |  |  | 1023 |  |  | 1070.5 |  |  | 1017 |  |  | 1036 |  |  | 1099.5 |  |  | 1105.5 |  |  | 1009.5 |  |  | 1088 |  |  | 1057.5 |  |  | 1029.5 |  |  | 960.5 |  |  | 1102.5 |  |  | 975.5 |  |  | 1064.5 |  |  | 1047.5 |  |  | 1048.5 |  |  | 963 |  |  | 1130.5 |  |  | 894 |  |  | 994.5 |  |  | 940.5 |  |  | 1062.5 |  |  | 1072 |  |  | 1103 |  |  | 1078 |  |  | 1041.5 |  |  | 992 |  |  | 1069.5 |  |  | 1092.5 |  |  | 957.5 |  |  | 1039.5 |  |  | 1014.5 |  |  | 1040.5 |  |  | 1025.5 |  |  | 1055.5 |  |  | 1107 |  |  | 981.5 |  |  | 945.5 |  |  | 1064.5 |  |  | 1003.5 |  |  | 985 |  |  | 1023.5 |  |  | 1092 |  |  | 997.5 |  |  | 1038.5 |  |  | 992.5 |  |  | 953.5 |  |  | 969 |  |  | 974.5 |  |  | 953 |  |  | 1003.5 |  |  | 1086.5 |  |  | 1098.5 |  |  | 1055.5 |  |  | 1044.5 |  |  | 1028.5 |  |  | 991.5 |  |  | 1048.5 |  |  | 923.5 |  |  | 1049 |  |  | 1037.5 |  |  | 990.5 |  |  | 956.5 |  |  | 1066.5 |  |  | 1033.5 |  |  | 934 |  |  | 1020 |  |  | 1001.5 |  |  | 976 |  |  | 1122.5 |  |  | 1022.5 |  |  | 1086.5 |  |  | 1129.5 |  |  | 1028.5 |  |  | 1083.5 |  |  | 1032.5 |  |  | 1039.5 |  |  | 1014 |  |  | 1112.5 |  |  | 1126.5 |  |  | 1060.5 |  |  | 985 |  |  | 1073.5 |  |  | 994.5 |  |  | 1131 |  |  | 940 |  |  | 1041.5 |  |  | 966 |  |  | 937 |  |  | 947.5 |  |  | 979 |  |  | 1110.5 |  |  | 1095.5 |  |  | 1098.5 |  |  | 1051.5 |  |  | 1004.5 |  |  | 1078.5 |  |  | 928.5 |  |  | 1048.5 |  |  | 1004.5 |  |  | 1002.5 |  |  | 1058 |  |  | 965 |  |  | 1003.5 |  |  | 1000.5 |  |  | 1035.5 |  |  | 1085.5 |  |  | 968.5 |  |  | 1113.5 |  |  | 1064.5 |  |  | 980.5 |  |  | 1083 |  |  | 973.5 |  |  | 949 |  |  | 931.5 |  |  | 1183.5 |  |  | 1081.5 |  |  | 1087 |  |  | 1011.5 |  |  | 1014.5 |  |  | 925 |  |  | 1086.5 |  |  | 977.5 |  |  | 1092.5 |  |  | 996.5 |  |  | 1014.5 |  |  | 1014.5 |  |  | 981 |  |  | 1045.5 |  |  | 983.5 |  |  | 1036.5 |  |  | 1151.5 |  |  | 960 |  |  | 982.5 |  |  | 1058.5 |  |  | 1020 |  |  | 1051.5 |  |  | 1054.5 |  |  | 1035 |  |  | 1071.5 |  |  | 1057.5 |  |  | 1036.5 |  |  | 968 |  |  | 907.5 |  |  | 1045.5 |  |  | 1005 |  |  | 1007.5 |  |  | 1062.5 |  |  | 1033.5 |  |  | 897.5 |  |  | 1095.5 |  |  | 1145.5 |  |  | 997.5 |  |  | 1054 |  |  | 1034 |  |  | 939.5 |  |  | 1046.5 |  |  | 1000.5 |  |  | 1046 |  |  | 1067.5 |  |  | 1016.5 |  |  | 1064.5 |  |  | 932.5 |  |  | 1023.5 |  |  | 1041.5 |  |  | 930.5 |  |  | 1036.5 |  |  | 971.5 |  |  | 1042 |  |  | 989.5 |  |  | 1022.5 |  |  | 986.5 |  |  | 1090.5 |  |  | 1080.5 |  |  | 1003.5 |  |  | 999.5 |  |  | 1103.5 |  |  | 979.5 |  |  | 1036.5 |  |  | 996.5 |  |  | 1025.5 |  |  | 1029.5 |  |  | 1106 |  |  | 1033.5 |  |  | 1051.5 |  |  | 981 |  |  | 1023.5 |  |  | 1051.5 |  |  | 1103 |  |  | 1019.5 |  |  | 1058.5 |  |  | 1120.5 |  |  | 1100 |  |  | 1077.5 |  |  | 1089.5 |  |  | 1017.5 |  |  | 876.5 |  |  | 1069.5 |  |  | 941 |  |  | 1027.5 |  |  | 1106 |  |  | 1040 |  |  | 1100.5 |  |  | 1042.5 |  |  | 1000.5 |  |  | 961.5 |  |  | 1024.5 |  |  | 1049.5 |  |  | 997 |  |  | 1020.5 |  |  | 1119 |  |  | 999.5 |  |  | 1059 |  |  | 997 |  |  | 1072 |  |  | 1008.5 |  |  | 951 |  |  | 1117.5 |  |  | 1117.5 |  |  | 1083.5 |  |  | 1200.5 |  |  | 1079.5 |  |  | 1027 |  |  | 1069.5 |  |  | 1094.5 |  |  | 1181.5 |  |  | 1074 |  |  | 1079.5 |  |  | 1056.5 |  |  | 1111.5 |  |  | 1092.5 |  |  | 978 |  |  | 1049 |  |  | 1033 |  |  | 1076.5 |  |  | 1101 |  |  | 1043 |  |  | 1064.5 |  |  | 1001.5 |  |  | 979.5 |  |  | 1067.5 |  |  | 1100.5 |  |  | 1146.5 |  |  | 1053.5 |  |  | 1066.5 |  |  | 965.5 |  |  | 973 |  |  | 1050.5 |  |  | 1036 |  |  | 1081.5 |  |  | 1079.5 |  |  | 1076.5 |  |  | 1055.5 |  |  | 1069 |  |  | 1000.5 |  |  | 1013 |  |  | 1003.5 |  |  | 1038.5 |  |  | 924 |  |  | 1020 |  |  | 1029.5 |  |  | 1047 |  |  | 1147.5 |  |  | 903.5 |  |  | 1005.5 |  |  | 1048.5 |  |  | 1034.5 |  |  | 1019.5 |  |  | 1020.5 |  |  | 972 |  |  | 1094.5 |  |  | 1045.5 |  |  | 955.5 |  |  | 1058.5 |  |  | 988.5 |  |  | 1003.5 |  |  | 1013.5 |  |  | 1037.5 |  |  | 1013.5 |  |  | 1057.5 |  |  | 1028.5 |  |  | 965.5 |  |  | 1102 |  |  | 948.5 |  |  | 1027.5 |  |  | 1090 |  |  | 945.5 |  |  | 942.5 |  |  | 1003.5 |  |  | 1010.5 |  |  | 1087 |  |  | 1095.5 |  |  | 1035.5 |  |  | 982.5 |  |  | 1044.5 |  |  | 973 |  |  | 1049.5 |  |  | 1066.5 |  |  | 1035.5 |  |  | 1098.5 |  |  | 1049.5 |  |  | 991.5 |  |  | 1085.5 |  |  | 1079.5 |  |  | 1082.5 |  |  | 1029.5 |  |  | 1086.5 |  |  | 1055 |  |  | 1060.5 |  |  | 1038.5 |  |  | 1112.5 |  |  | 1042.5 |  |  | 988.5 |  |  | 992.5 |  |  | 1064 |  |  | 1003.5 |  |  | 1004 |  |  | 962.5 |  |  | 1085.5 |  |  | 978.5 |  |  | 1027 |  |  | 1026 |  |  | 1011.5 |  |  | 1053.5 |  |  | 929.5 |  |  | 1019.5 |  |  | 1015.5 |  |  | 979.5 |  |  | 984.5 |  |  | 984.5 |  |  | 1046.5 |  |  | 1079.5 |  |  | 1005.5 |  |  | 1051.5 |  |  | 1027.5 |  |  | 1043.5 |  |  | 1044.5 |  |  | 1075.5 |  |  | 1059.5 |  |  | 1041.5 |  |  | 1036.5 |  |  | 980.5 |  |  | 1037.5 |  |  | 1063.5 |  |  | 1067 |  |  | 1157.5 |  |  | 1019.5 |  |  | 1054.5 |  |  | 1044 |  |  | 1047.5 |  |  | 1052.5 |  |  | 1030.5 |  |  | 1055.5 |  |  | 1085 |  |  | 921.5 |  |  | 1028.5 |  |  | 964 |  |  | 946 |  |  | 1000 |  |  | 1017.5 |  |  | 1057.5 |  |  | 1066.5 |  |  | 1084.5 |  |  | 1030 |  |  | 1025.5 |  |  | 1057.5 |  |  | 960 |  |  | 1026 |  |  | 1026.5 |  |  | 1035.5 |  |  | 1040 |  |  | 996.5 |  |  | 1060 |  |  | 951.5 |  |  | 981.5 |  |  | 1052 |  |  | 1072.5 |  |  | 938.5 |  |  | 931.5 |  |  | 1091 |  |  | 1064.5 |  |  | 1023.5 |  |  | 970.5 |  |  | 967.5 |  |  | 1026.5 |  |  | 1124.5 |  |  | 970.5 |  |  | 1042.5 |  |  | 1094.5 |  |  | 1036.5 |  |  | 1078 |  |  | 962.5 |  |  | 1046.5 |  |  | 1067.5 |  |  | 1076.5 |  |  | 971.5 |  |  | 1104.5 |  |  | 1099.5 |  |  | 1014.5 |  |  | 1090 |  |  | 1064.5 |  |  | 1066 |  |  | 1061.5 |  |  | 1121.5 |  |  | 1141.5 |  |  | 1023.5 |  |  | 1070.5 |  |  | 980.5 |  |  | 897.5 |  |  | 1060.5 |  |  | 1046 |  |  | 982.5 |  |  | 989 |  |  | 1001.5 |  |  | 942.5 |  |  | 1076.5 |  |  | 1110 |  |  | 1007.5 |  |  | 1057.5 |  |  | 966 |  |  | 991.5 |  |  | 998 |  |  | 980.5 |  |  | 1045.5 |  |  | 1013.5 |  |  | 983 |  |  | 1019.5 |  |  | 1151.5 |  |  | 958 |  |  | 1065.5 |  |  | 963.5 |  |  | 1043 |  |  | 1062.5 |  |  | 1163.5 |  |  | 1062.5 |  |  | 1070.5 |  |  | 1031.5 |  |  | 1000.5 |  |  | 965.5 |  |  | 1043.5 |  |  | 951.5 |  |  | 1076.5 |  |  | 1131.5 |  |  | 1017 |  |  | 1107 |  |  | 1058.5 |  |  | 1051.5 |  |  | 1133
37 |  | 1108.5 |  |  | 1156.5 |  |  | 1088 |  |  | 1065.5 |  |  | 1141.5 |  |  | 1101.5 |  |  | 1133.5 |  |  | 1059.5 |  |  | 1043.5 |  |  | 1095.5 |  |  | 1053 |  |  | 1070.5 |  |  | 1161.5 |  |  | 1055.5 |  |  | 1004 |  |  | 1066.5 |  |  | 1183.5 |  |  | 1080.5 |  |  | 1171.5 |  |  | 990.5 |  |  | 1044.5 |  |  | 1010.5 |  |  | 1076.5 |  |  | 1005.5 |  |  | 986 |  |  | 1115.5 |  |  | 1014.5 |  |  | 1045.5 |  |  | 1050.5 |  |  | 991 |  |  | 1075 |  |  | 1030.5 |  |  | 1041.5 |  |  | 1064.5 |  |  | 946.5 |  |  | 1058 |  |  | 1025.5 |  |  | 1037 |  |  | 1033.5 |  |  | 1104.5 |  |  | 1007.5 |  |  | 1139.5 |  |  | 1005.5 |  |  | 1000 |  |  | 1206.5 |  |  | 1126 |  |  | 998.5 |  |  | 1068.5 |  |  | 1081.5 |  |  | 1031.5 |  |  | 1051.5 |  |  | 1045.5 |  |  | 1020.5 |  |  | 1046.5 |  |  | 1089.5 |  |  | 1051.5 |  |  | 1012.5 |  |  | 1058 |  |  | 1126.5 |  |  | 1034.5 |  |  | 1010 |  |  | 1005.5 |  |  | 1106.5 |  |  | 1082.5 |  |  | 1046.5 |  |  | 1098 |  |  | 1076.5 |  |  | 959 |  |  | 1051.5 |  |  | 1064.5 |  |  | 1098 |  |  | 1102.5 |  |  | 1047.5 |  |  | 1107.5 |  |  | 1099 |  |  | 1060 |  |  | 1064.5 |  |  | 989.5 |  |  | 927.5 |  |  | 1027.5 |  |  | 998 |  |  | 1025.5 |  |  | 1093.5 |  |  | 1152.5 |  |  | 1118.5 |  |  | 1135.5 |  |  | 1149.5 |  |  | 1032.5 |  |  | 1022.5 |  |  | 1113.5 |  |  | 1110.5 |  |  | 1084 |  |  | 1009.5 |  |  | 1041 |  |  | 1071 |  |  | 1022 |  |  | 1084.5 |  |  | 1095.5 |  |  | 1030.5 |  |  | 1078.5 |  |  | 1053.5 |  |  | 1130 |  |  | 1117 |  |  | 1015.5 |  |  | 1047.5 |  |  | 1053.5 |  |  | 1065.5 |  |  | 1103.5 |  |  | 1134.5 |  |  | 1126.5 |  |  | 1118.5 |  |  | 1078.5 |  |  | 1121.5 |  |  | 1066.5 |  |  | 1123.5 |  |  | 1104.5 |  |  | 1077.5 |  |  | 1005.5 |  |  | 1071.5 |  |  | 1126.5 |  |  | 1082.5 |  |  | 1088.5 |  |  | 1067.5 |  |  | 1074.5 |  |  | 1080.5 |  |  | 1091 |  |  | 1000.5 |  |  | 1081.5 |  |  | 968.5 |  |  | 997.5 |  |  | 1174.5 |  |  | 1087 |  |  | 1006.5 |  |  | 1126.5 |  |  | 1001.5 |  |  | 1107.5 |  |  | 1026 |  |  | 1046.5 |  |  | 1125.5 |  |  | 1030 |  |  | 1118.5 |  |  | 1029 |  |  | 1060 |  |  | 1128.5 |  |  | 1087 |  |  | 1127.5 |  |  | 1041.5 |  |  | 1073.5 |  |  | 1002.5 |  |  | 1102.5 |  |  | 1113.5 |  |  | 1069.5 |  |  | 1064.5 |  |  | 1120.5 |  |  | 1068.5 |  |  | 1108 |  |  | 970.5 |  |  | 1036 |  |  | 988.5 |  |  | 1088.5 |  |  | 1081 |  |  | 1093.5 |  |  | 1020.5 |  |  | 1007.5 |  |  | 1070 |  |  | 1079.5 |  |  | 1008.5 |  |  | 1018.5 |  |  | 1053.5 |  |  | 1048.5 |  |  | 1076.5 |  |  | 1071 |  |  | 1050.5 |  |  | 1048.5 |  |  | 1052.5 |  |  | 1043.5 |  |  | 1127.5 |  |  | 1124.5 |  |  | 1021.5 |  |  | 1142 |  |  | 1099.5 |  |  | 1094.5 |  |  | 1150.5 |  |  | 1124.5 |  |  | 1001.5 |  |  | 1189.5 |  |  | 1075.5 |  |  | 1076.5 |  |  | 1033.5 |  |  | 1003.5 |  |  | 1054.5 |  |  | 978.5 |  |  | 950.5 |  |  | 1020 |  |  | 1038.5 |  |  | 1088.5 |  |  | 1012.5 |  |  | 1064.5 |  |  | 1148.5 |  |  | 1064.5 |  |  | 1086.5 |  |  | 1002.5 |  |  | 994.5 |  |  | 1084.5 |  |  | 1045.5 |  |  | 1201.5 |  |  | 1042.5 |  |  | 1016.5 |  |  | 1129.5 |  |  | 1103.5 |  |  | 1090 |  |  | 1117.5 |  |  | 1027.5 |  |  | 966 |  |  | 1099.5 |  |  | 1071 |  |  | 1054.5 |  |  | 1131.5 |  |  | 1166.5 |  |  | 1074.5 |  |  | 1060.5 |  |  | 1018.5 |  |  | 1037.5 |  |  | 997.5 |  |  | 972 |  |  | 1018.5 |  |  | 894.5 |  |  | 1125.5 |  |  | 1041.5 |  |  | 1138 |  |  | 1012.5 |  |  | 995.5 |  |  | 1098.5 |  |  | 1099.5 |  |  | 1118.5 |  |  | 991.5 |  |  | 1007.5 |  |  | 1080.5 |  |  | 1063 |  |  | 1062 |  |  | 959.5 |  |  | 1049.5 |  |  | 1088.5 |  |  | 1126 |  |  | 1129.5 |  |  | 1097.5 |  |  | 1047.5 |  |  | 1036 |  |  | 1081.5 |  |  | 1113.5 |  |  | 1046.5 |  |  | 1023.5 |  |  | 1069.5 |  |  | 1081.5 |  |  | 1094.5 |  |  | 1021.5 |  |  | 1103.5 |  |  | 930 |  |  | 1000.5 |  |  | 1055.5 |  |  | 998.5 |  |  | 1049.5 |  |  | 1060.5 |  |  | 1138 |  |  | 1048.5 |  |  | 1128.5 |  |  | 1047 |  |  | 1139.5 |  |  | 1066.5 |  |  | 1114 |  |  | 1044.5 |  |  | 1097.5 |  |  | 1214.5 |  |  | 1031.5 |  |  | 1104 |  |  | 1118 |  |  | 1101.5 |  |  | 1084.5 |  |  | 1113.5 |  |  | 1084.5 |  |  | 1145.5 |  |  | 1001.5 |  |  | 1056 |  |  | 1103.5 |  |  | 1089.5 |  |  | 1076 |  |  | 1048.5 |  |  | 998.5 |  |  | 1030 |  |  | 1065.5 |  |  | 1044.5 |  |  | 1042.5 |  |  | 1098 |  |  | 1100.5 |  |  | 1004 |  |  | 1103.5 |  |  | 1017.5 |  |  | 1057.5 |  |  | 1016 |  |  | 1028.5 |  |  | 1150.5 |  |  | 1022.5 |  |  | 1056 |  |  | 944.5 |  |  | 1038.5 |  |  | 1117.5 |  |  | 1138.5 |  |  | 1045.5 |  |  | 1035 |  |  | 1037.5 |  |  | 1157.5 |  |  | 1167.5 |  |  | 1016 |  |  | 1070 |  |  | 1148.5 |  |  | 1083.5 |  |  | 1024.5 |  |  | 1104.5 |  |  | 1104.5 |  |  | 1102.5 |  |  | 1054.5 |  |  | 1073.5 |  |  | 976.5 |  |  | 1070.5 |  |  | 1043 |  |  | 1121.5 |  |  | 1128.5 |  |  | 1204.5 |  |  | 1181.5 |  |  | 1069 |  |  | 1136.5 |  |  | 1118.5 |  |  | 1112.5 |  |  | 951.5 |  |  | 1087.5 |  |  | 1061 |  |  | 1055 |  |  | 982 |  |  | 1061 |  |  | 1035.5 |  |  | 1080 |  |  | 1066.5 |  |  | 1026 |  |  | 1076.5 |  |  | 1105.5 |  |  | 1048.5 |  |  | 1043.5 |  |  | 1031.5 |  |  | 1050 |  |  | 1079.5 |  |  | 1127.5 |  |  | 982.5 |  |  | 1100 |  |  | 1095.5 |  |  | 1082.5 |  |  | 1046.5 |  |  | 1155 |  |  | 1016.5 |  |  | 954.5 |  |  | 1014.5 |  |  | 1021.5 |  |  | 1002.5 |  |  | 1034.5 |  |  | 1115.5 |  |  | 986.5 |  |  | 1089.5 |  |  | 962.5 |  |  | 986 |  |  | 1084.5 |  |  | 1057.5 |  |  | 1059.5 |  |  | 1059.5 |  |  | 1166.5 |  |  | 1051 |  |  | 1031.5 |  |  | 1125 |  |  | 1007 |  |  | 995.5 |  |  | 1168.5 |  |  | 1029.5 |  |  | 1029 |  |  | 1120.5 |  |  | 1121.5 |  |  | 1088.5 |  |  | 984 |  |  | 1062.5 |  |  | 987.5 |  |  | 1131.5 |  |  | 969.5 |  |  | 1051.5 |  |  | 1046 |  |  | 970.5 |  |  | 1049 |  |  | 1083.5 |  |  | 1059.5 |  |  | 1072.5 |  |  | 1193 |  |  | 1006.5 |  |  | 1118 |  |  | 1122 |  |  | 1092.5 |  |  | 1068.5 |  |  | 1057.5 |  |  | 1146.5 |  |  | 1106 |  |  | 1071.5 |  |  | 1061.5 |  |  | 1003.5 |  |  | 1083 |  |  | 1101.5 |  |  | 1013.5 |  |  | 990.5 |  |  | 1065.5 |  |  | 1116 |  |  | 988.5 |  |  | 1018.5 |  |  | 1100.5 |  |  | 1066.5 |  |  | 1072.5 |  |  | 1138.5 |  |  | 1094 |  |  | 1038.5 |  |  | 1036.5 |  |  | 1036 |  |  | 1005.5 |  |  | 1026.5 |  |  | 1094.5 |  |  | 1078 |  |  | 1033.5 |  |  | 1040.5 |  |  | 1044.5 |  |  | 1079.5 |  |  | 1099.5 |  |  | 1114 |  |  | 1025 |  |  | 996.5 |  |  | 1065.5 |  |  | 1050.5 |  |  | 1059.5 |  |  | 1027 |  |  | 1090 |  |  | 1010 |  |  | 1111.5 |  |  | 1035 |  |  | 1101.5 |  |  | 1130.5 |  |  | 1132 |  |  | 1043.5 |  |  | 1110.5 |  |  | 1075.5 |  |  | 1184.5 |  |  | 1004.5 |  |  | 1057 |  |  | 1084 |  |  | 968.5 |  |  | 1057.5 |  |  | 1046 |  |  | 958.5 |  |  | 1147.5 |  |  | 1103 |  |  | 1183.5 |  |  | 1124.5 |  |  | 997 |  |  | 1076.5 |  |  | 1106.5 |  |  | 1043 |  |  | 1087.5 |  |  | 1020 |  |  | 1117.5 |  |  | 1135 |  |  | 970.5 |  |  | 1059.5 |  |  | 1066.5 |  |  | 1055.5 |  |  | 1058.5 |  |  | 1031.5 |  |  | 1148 |  |  | 1078.5 |  |  | 1077.5 |  |  | 1019.5 |  |  | 1110.5 |  |  | 1003.5 |  |  | 1057 |  |  | 1047.5 |  |  | 1034 |  |  | 1058.5 |  |  | 1040.5 |  |  | 1055.5 |  |  | 996.5 |  |  | 1047.5 |  |  | 1036.5 |  |  | 997.5 |  |  | 1157.5 |  |  | 1062.5 |  |  | 1117 |  |  | 1115.5 |  |  | 995 |  |  | 1056 |  |  | 1043.5 |  |  | 982 |  |  | 1029.5 |  |  | 1013.5 |  |  | 1101.5 |  |  | 1061.5 |  |  | 1078.5 |  |  | 1121.5 |  |  | 1117.5 |  |  | 1059 |  |  | 1166 |  |  | 990.5 |  |  | 991.5 |  |  | 1069 |  |  | 1023.5 |  |  | 1105.5 |  |  | 1001.5 |  |  | 984.5 |  |  | 1016.5 |  |  | 1009 |  |  | 1034.5 |  |  | 1080.5 |  |  | 1035.5 |  |  | 1030 |  |  | 1108.5 |  |  | 1069.5 |  |  | 1115.5 |  |  | 1152.5 |  |  | 1127.5 |  |  | 1017.5 |  |  | 1143.5 |  |  | 918.5 |  |  | 1048.5 |  |  | 1056 |  |  | 1120.5 |  |  | 1053.5 |  |  | 1106.5 |  |  | 1038.5 |  |  | 986.5 |  |  | 975.5 |  |  | 1066.5 |  |  | 956 |  |  | 1004.5 |  |  | 1069.5 |  |  | 1128.5 |  |  | 994 |  |  | 1038.5 |  |  | 1032 |  |  | 1057.5 |  |  | 1074.5 |  |  | 1063.5 |  |  | 1025 |  |  | 981.5 |  |  | 1077 |  |  | 1062 |  |  | 1109.5 |  |  | 1056 |  |  | 1057 |  |  | 1138.5 |  |  | 1120.5 |  |  | 1024.5 |  |  | 1135 |  |  | 1096.5 |  |  | 1044.5 |  |  | 975.5 |  |  | 1141.5 |  |  | 1004.5 |  |  | 1085.5 |  |  | 1068.5 |  |  | 1063.5 |  |  | 992 |  |  | 1169.5 |  |  | 941 |  |  | 1009.5 |  |  | 955.5 |  |  | 1091.5 |  |  | 1111 |  |  | 1118 |  |  | 1104 |  |  | 1062.5 |  |  | 1007 |  |  | 1098.5 |  |  | 1113.5 |  |  | 972.5 |  |  | 1086.5 |  |  | 1038.5 |  |  | 1055.5 |  |  | 1072.5 |  |  | 1094.5 |  |  | 1154 |  |  | 1007.5 |  |  | 969.5 |  |  | 1088.5 |  |  | 1027.5 |  |  | 1006 |  |  | 1038.5 |  |  | 1131 |  |  | 1036.5 |  |  | 1085.5 |  |  | 1039.5 |  |  | 1000.5 |  |  | 984 |  |  | 995.5 |  |  | 979 |  |  | 1024.5 |  |  | 1107.5 |  |  | 1137.5 |  |  | 1084.5 |  |  | 1065.5 |  |  | 1049.5 |  |  | 1020.5 |  |  | 1095.5 |  |  | 944.5 |  |  | 1070 |  |  | 1058.5 |  |  | 1011.5 |  |  | 995.5 |  |  | 1081.5 |  |  | 1054.5 |  |  | 973 |  |  | 1059 |  |  | 1048.5 |  |  | 1023 |  |  | 1143.5 |  |  | 1043.5 |  |  | 1125.5 |  |  | 1150.5 |  |  | 1043.5 |  |  | 1112.5 |  |  | 1071.5 |  |  | 1054.5 |  |  | 1040 |  |  | 1127.5 |  |  | 1141.5 |  |  | 1089.5 |  |  | 1009 |  |  | 1094.5 |  |  | 1023.5 |  |  | 1155 |  |  | 964 |  |  | 1056.5 |  |  | 995 |  |  | 958 |  |  | 962.5 |  |  | 1000 |  |  | 1131.5 |  |  | 1142.5 |  |  | 1119.5 |  |  | 1077.5 |  |  | 1051.5 |  |  | 1117.5 |  |  | 975.5 |  |  | 1074.5 |  |  | 1019.5 |  |  | 1028.5 |  |  | 1073 |  |  | 989 |  |  | 1029.5 |  |  | 1026.5 |  |  | 1061.5 |  |  | 1111.5 |  |  | 992.5 |  |  | 1142.5 |  |  | 1103.5 |  |  | 995.5 |  |  | 1122 |  |  | 1002.5 |  |  | 988 |  |  | 978.5 |  |  | 1230.5 |  |  | 1102.5 |  |  | 1111 |  |  | 1058.5 |  |  | 1038.5 |  |  | 964 |  |  | 1110.5 |  |  | 1016.5 |  |  | 1139.5 |  |  | 1022.5 |  |  | 1061.5 |  |  | 1038.5 |  |  | 1010 |  |  | 1069.5 |  |  | 1012.5 |  |  | 1065.5 |  |  | 1180.5 |  |  | 999 |  |  | 1008.5 |  |  | 1097.5 |  |  | 1049 |  |  | 1080.5 |  |  | 1080.5 |  |  | 1059 |  |  | 1100.5 |  |  | 1096.5 |  |  | 1065.5 |  |  | 994 |  |  | 936.5 |  |  | 1071.5 |  |  | 1026 |  |  | 1022.5 |  |  | 1091.5 |  |  | 1054.5 |  |  | 912.5 |  |  | 1134.5 |  |  | 1184.5 |  |  | 1012.5 |  |  | 1093 |  |  | 1049 |  |  | 954.5 |  |  | 1061.5 |  |  | 1024.5 |  |  | 1070 |  |  | 1096.5 |  |  | 1037.5 |  |  | 1103.5 |  |  | 956.5 |  |  | 1047.5 |  |  | 1065.5 |  |  | 956.5 |  |  | 1051.5 |  |  | 986.5 |  |  | 1081 |  |  | 1015.5 |  |  | 1037.5 |  |  | 1001.5 |  |  | 1119.5 |  |  | 1119.5 |  |  | 1027.5 |  |  | 1038.5 |  |  | 1127.5 |  |  | 1026.5 |  |  | 1057.5 |  |  | 1017.5 |  |  | 1064.5 |  |  | 1044.5 |  |  | 1127 |  |  | 1072.5 |  |  | 1090.5 |  |  | 1020 |  |  | 1062.5 |  |  | 1066.5 |  |  | 1142 |  |  | 1058.5 |  |  | 1087.5 |  |  | 1141.5 |  |  | 1129 |  |  | 1098.5 |  |  | 1136.5 |  |  | 1046.5 |  |  | 891.5 |  |  | 1090.5 |  |  | 965 |  |  | 1051.5 |  |  | 1145 |  |  | 1061 |  |  | 1139.5 |  |  | 1081.5 |  |  | 1039.5 |  |  | 982.5 |  |  | 1045.5 |  |  | 1088.5 |  |  | 1026 |  |  | 1049.5 |  |  | 1166 |  |  | 1023.5 |  |  | 1074 |  |  | 1036 |  |  | 1111 |  |  | 1055.5 |  |  | 998 |  |  | 1132.5 |  |  | 1132.5 |  |  | 1130.5 |  |  | 1224.5 |  |  | 1105.5 |  |  | 1074 |  |  | 1095.5 |  |  | 1123.5 |  |  | 1220.5 |  |  | 1121 |  |  | 1100.5 |  |  | 1080.5 |  |  | 1158.5 |  |  | 1131.5 |  |  | 1025 |  |  | 1078 |  |  | 1057 |  |  | 1115.5 |  |  | 1140 |  |  | 1082 |  |  | 1111.5 |  |  | 1048.5 |  |  | 994.5 |  |  | 1106.5 |  |  | 1126.5 |  |  | 1161.5 |  |  | 1074.5 |  |  | 1105.5 |  |  | 980.5 |  |  | 988 |  |  | 1065.5 |  |  | 1083 |  |  | 1128.5 |  |  | 1118.5 |  |  | 1100.5 |  |  | 1076.5 |  |  | 1093 |  |  | 1047.5 |  |  | 1060 |  |  | 1042.5 |  |  | 1085.5 |  |  | 945 |  |  | 1046 |  |  | 1058.5 |  |  | 1076 |  |  | 1194.5 |  |  | 942.5 |  |  | 1031.5 |  |  | 1074.5 |  |  | 1060.5 |  |  | 1066.5 |  |  | 1035.5 |  |  | 996 |  |  | 1123.5 |  |  | 1074.5 |  |  | 994.5 |  |  | 1097.5 |  |  | 1012.5 |  |  | 1050.5 |  |  | 1060.5 |  |  | 1076.5 |  |  | 1052.5 |  |  | 1081.5 |  |  | 1067.5 |  |  | 1004.5 |  |  | 1128 |  |  | 963.5 |  |  | 1048.5 |  |  | 1129 |  |  | 969.5 |  |  | 963.5 |  |  | 1042.5 |  |  | 1034.5 |  |  | 1113 |  |  | 1124.5 |  |  | 1064.5 |  |  | 997.5 |  |  | 1083.5 |  |  | 994 |  |  | 1088.5 |  |  | 1105.5 |  |  | 1074.5 |  |  | 1127.5 |  |  | 1096.5 |  |  | 1030.5 |  |  | 1124.5 |  |  | 1108.5 |  |  | 1103.5 |  |  | 1068.5 |  |  | 1107.5 |  |  | 1081 |  |  | 1084.5 |  |  | 1077.5 |  |  | 1127.5 |  |  | 1068.5 |  |  | 1017.5 |  |  | 1018.5 |  |  | 1090 |  |  | 1024.5 |  |  | 1043 |  |  | 1009.5 |  |  | 1109.5 |  |  | 1017.5 |  |  | 1056 |  |  | 1041 |  |  | 1037.5 |  |  | 1082.5 |  |  | 976.5 |  |  | 1066.5 |  |  | 1044.5 |  |  | 1018.5 |  |  | 1010.5 |  |  | 1031.5 |  |  | 1070.5 |  |  | 1094.5 |  |  | 1029.5 |  |  | 1080.5 |  |  | 1051.5 |  |  | 1069.5 |  |  | 1070.5 |  |  | 1104.5 |  |  | 1085.5 |  |  | 1065.5 |  |  | 1051.5 |  |  | 1004.5 |  |  | 1066.5 |  |  | 1089.5 |  |  | 1106 |  |  | 1178.5 |  |  | 1043.5 |  |  | 1069.5 |  |  | 1073 |  |  | 1076.5 |  |  | 1078.5 |  |  | 1069.5 |  |  | 1081.5 |  |  | 1111 |  |  | 968.5 |  |  | 1049.5 |  |  | 985 |  |  | 961 |  |  | 1039 |  |  | 1041.5 |  |  | 1083.5 |  |  | 1113.5 |  |  | 1099.5 |  |  | 1051 |  |  | 1064.5 |  |  | 1081.5 |  |  | 986 |  |  | 1073 |  |  | 1073.5 |  |  | 1061.5 |  |  | 1066 |  |  | 1035.5 |  |  | 1099 |  |  | 975.5 |  |  | 1007.5 |  |  | 1076 |  |  | 1111.5 |  |  | 962.5 |  |  | 970.5 |  |  | 1112 |  |  | 1090.5 |  |  | 1038.5 |  |  | 1009.5 |  |  | 1014.5 |  |  | 1047.5 |  |  | 1171.5 |  |  | 1009.5 |  |  | 1066.5 |  |  | 1118.5 |  |  | 1083.5 |  |  | 1099 |  |  | 1001.5 |  |  | 1061.5 |  |  | 1093.5 |  |  | 1123.5 |  |  | 1010.5 |  |  | 1143.5 |  |  | 1138.5 |  |  | 1053.5 |  |  | 1129 |  |  | 1085.5 |  |  | 1081 |  |  | 1082.5 |  |  | 1160.5 |  |  | 1188.5 |  |  | 1049.5 |  |  | 1109.5 |  |  | 1009.5 |  |  | 936.5 |  |  | 1099.5 |  |  | 1085 |  |  | 1003.5 |  |  | 1018 |  |  | 1016.5 |  |  | 966.5 |  |  | 1115.5 |  |  | 1125 |  |  | 1028.5 |  |  | 1104.5 |  |  | 1005 |  |  | 1017.5 |  |  | 1022 |  |  | 995.5 |  |  | 1084.5 |  |  | 1034.5 |  |  | 998 |  |  | 1048.5 |  |  | 1180.5 |  |  | 987 |  |  | 1094.5 |  |  | 984.5 |  |  | 1082 |  |  | 1091.5 |  |  | 1178.5 |  |  | 1077.5 |  |  | 1094.5 |  |  | 1057.5 |  |  | 1029.5 |  |  | 1004.5 |  |  | 1082.5 |  |  | 972.5 |  |  | 1115.5 |  |  | 1170.5 |  |  | 1056 |  |  | 1133 |  |  | 1105.5 |  |  | 1077.5 |  |  | 1159
38 |  | 1132.5 |  |  | 1180.5 |  |  | 1112 |  |  | 1080.5 |  |  | 1162.5 |  |  | 1148.5 |  |  | 1180.5 |  |  | 1083.5 |  |  | 1082.5 |  |  | 1121.5 |  |  | 1079 |  |  | 1085.5 |  |  | 1200.5 |  |  | 1076.5 |  |  | 1033 |  |  | 1087.5 |  |  | 1222.5 |  |  | 1095.5 |  |  | 1210.5 |  |  | 1016.5 |  |  | 1059.5 |  |  | 1034.5 |  |  | 1102.5 |  |  | 1044.5 |  |  | 1012 |  |  | 1162.5 |  |  | 1061.5 |  |  | 1060.5 |  |  | 1065.5 |  |  | 1006 |  |  | 1099 |  |  | 1045.5 |  |  | 1067.5 |  |  | 1090.5 |  |  | 993.5 |  |  | 1087 |  |  | 1064.5 |  |  | 1076 |  |  | 1057.5 |  |  | 1143.5 |  |  | 1031.5 |  |  | 1154.5 |  |  | 1031.5 |  |  | 1021 |  |  | 1253.5 |  |  | 1152 |  |  | 1027.5 |  |  | 1107.5 |  |  | 1120.5 |  |  | 1055.5 |  |  | 1072.5 |  |  | 1074.5 |  |  | 1049.5 |  |  | 1072.5 |  |  | 1136.5 |  |  | 1072.5 |  |  | 1027.5 |  |  | 1079 |  |  | 1152.5 |  |  | 1081.5 |  |  | 1049 |  |  | 1044.5 |  |  | 1145.5 |  |  | 1097.5 |  |  | 1067.5 |  |  | 1124 |  |  | 1091.5 |  |  | 988 |  |  | 1090.5 |  |  | 1088.5 |  |  | 1124 |  |  | 1131.5 |  |  | 1071.5 |  |  | 1146.5 |  |  | 1125 |  |  | 1086 |  |  | 1093.5 |  |  | 1015.5 |  |  | 966.5 |  |  | 1048.5 |  |  | 1037 |  |  | 1064.5 |  |  | 1117.5 |  |  | 1176.5 |  |  | 1139.5 |  |  | 1161.5 |  |  | 1178.5 |  |  | 1047.5 |  |  | 1048.5 |  |  | 1160.5 |  |  | 1134.5 |  |  | 1108 |  |  | 1035.5 |  |  | 1062 |  |  | 1092 |  |  | 1037 |  |  | 1123.5 |  |  | 1134.5 |  |  | 1045.5 |  |  | 1102.5 |  |  | 1092.5 |  |  | 1151 |  |  | 1156 |  |  | 1041.5 |  |  | 1073.5 |  |  | 1092.5 |  |  | 1089.5 |  |  | 1132.5 |  |  | 1155.5 |  |  | 1141.5 |  |  | 1147.5 |  |  | 1102.5 |  |  | 1147.5 |  |  | 1105.5 |  |  | 1144.5 |  |  | 1128.5 |  |  | 1116.5 |  |  | 1026.5 |  |  | 1110.5 |  |  | 1155.5 |  |  | 1106.5 |  |  | 1117.5 |  |  | 1096.5 |  |  | 1095.5 |  |  | 1104.5 |  |  | 1117 |  |  | 1039.5 |  |  | 1110.5 |  |  | 994.5 |  |  | 1044.5 |  |  | 1198.5 |  |  | 1134 |  |  | 1030.5 |  |  | 1147.5 |  |  | 1040.5 |  |  | 1122.5 |  |  | 1041 |  |  | 1075.5 |  |  | 1154.5 |  |  | 1054 |  |  | 1133.5 |  |  | 1068 |  |  | 1075 |  |  | 1143.5 |  |  | 1134 |  |  | 1156.5 |  |  | 1080.5 |  |  | 1099.5 |  |  | 1023.5 |  |  | 1149.5 |  |  | 1137.5 |  |  | 1108.5 |  |  | 1111.5 |  |  | 1159.5 |  |  | 1115.5 |  |  | 1155 |  |  | 991.5 |  |  | 1060 |  |  | 1035.5 |  |  | 1112.5 |  |  | 1102 |  |  | 1119.5 |  |  | 1035.5 |  |  | 1031.5 |  |  | 1085 |  |  | 1118.5 |  |  | 1047.5 |  |  | 1033.5 |  |  | 1092.5 |  |  | 1063.5 |  |  | 1091.5 |  |  | 1100 |  |  | 1065.5 |  |  | 1095.5 |  |  | 1073.5 |  |  | 1069.5 |  |  | 1153.5 |  |  | 1163.5 |  |  | 1036.5 |  |  | 1189 |  |  | 1123.5 |  |  | 1120.5 |  |  | 1176.5 |  |  | 1163.5 |  |  | 1025.5 |  |  | 1210.5 |  |  | 1114.5 |  |  | 1091.5 |  |  | 1072.5 |  |  | 1032.5 |  |  | 1078.5 |  |  | 1025.5 |  |  | 974.5 |  |  | 1044 |  |  | 1059.5 |  |  | 1135.5 |  |  | 1051.5 |  |  | 1103.5 |  |  | 1187.5 |  |  | 1079.5 |  |  | 1133.5 |  |  | 1017.5 |  |  | 1009.5 |  |  | 1110.5 |  |  | 1071.5 |  |  | 1230.5 |  |  | 1081.5 |  |  | 1055.5 |  |  | 1144.5 |  |  | 1142.5 |  |  | 1105 |  |  | 1141.5 |  |  | 1048.5 |  |  | 987 |  |  | 1138.5 |  |  | 1118 |  |  | 1093.5 |  |  | 1155.5 |  |  | 1213.5 |  |  | 1089.5 |  |  | 1084.5 |  |  | 1057.5 |  |  | 1061.5 |  |  | 1023.5 |  |  | 1019 |  |  | 1039.5 |  |  | 941.5 |  |  | 1164.5 |  |  | 1080.5 |  |  | 1177 |  |  | 1038.5 |  |  | 1019.5 |  |  | 1122.5 |  |  | 1123.5 |  |  | 1144.5 |  |  | 1038.5 |  |  | 1046.5 |  |  | 1101.5 |  |  | 1110 |  |  | 1101 |  |  | 998.5 |  |  | 1078.5 |  |  | 1117.5 |  |  | 1165 |  |  | 1168.5 |  |  | 1126.5 |  |  | 1073.5 |  |  | 1051 |  |  | 1110.5 |  |  | 1142.5 |  |  | 1093.5 |  |  | 1044.5 |  |  | 1090.5 |  |  | 1096.5 |  |  | 1133.5 |  |  | 1068.5 |  |  | 1150.5 |  |  | 956 |  |  | 1039.5 |  |  | 1102.5 |  |  | 1045.5 |  |  | 1075.5 |  |  | 1107.5 |  |  | 1159 |  |  | 1077.5 |  |  | 1143.5 |  |  | 1094 |  |  | 1186.5 |  |  | 1095.5 |  |  | 1161 |  |  | 1083.5 |  |  | 1112.5 |  |  | 1238.5 |  |  | 1057.5 |  |  | 1119 |  |  | 1142 |  |  | 1125.5 |  |  | 1113.5 |  |  | 1152.5 |  |  | 1105.5 |  |  | 1184.5 |  |  | 1016.5 |  |  | 1077 |  |  | 1129.5 |  |  | 1104.5 |  |  | 1100 |  |  | 1063.5 |  |  | 1022.5 |  |  | 1056 |  |  | 1104.5 |  |  | 1059.5 |  |  | 1081.5 |  |  | 1119 |  |  | 1139.5 |  |  | 1043 |  |  | 1124.5 |  |  | 1064.5 |  |  | 1104.5 |  |  | 1055 |  |  | 1052.5 |  |  | 1197.5 |  |  | 1043.5 |  |  | 1095 |  |  | 991.5 |  |  | 1067.5 |  |  | 1164.5 |  |  | 1153.5 |  |  | 1084.5 |  |  | 1059 |  |  | 1066.5 |  |  | 1204.5 |  |  | 1196.5 |  |  | 1031 |  |  | 1099 |  |  | 1169.5 |  |  | 1130.5 |  |  | 1039.5 |  |  | 1119.5 |  |  | 1133.5 |  |  | 1131.5 |  |  | 1080.5 |  |  | 1112.5 |  |  | 991.5 |  |  | 1096.5 |  |  | 1069 |  |  | 1150.5 |  |  | 1167.5 |  |  | 1219.5 |  |  | 1228.5 |  |  | 1116 |  |  | 1175.5 |  |  | 1147.5 |  |  | 1136.5 |  |  | 980.5 |  |  | 1116.5 |  |  | 1087 |  |  | 1076 |  |  | 1008 |  |  | 1100 |  |  | 1056.5 |  |  | 1109 |  |  | 1105.5 |  |  | 1055 |  |  | 1097.5 |  |  | 1144.5 |  |  | 1087.5 |  |  | 1082.5 |  |  | 1057.5 |  |  | 1089 |  |  | 1126.5 |  |  | 1156.5 |  |  | 1006.5 |  |  | 1139 |  |  | 1119.5 |  |  | 1106.5 |  |  | 1070.5 |  |  | 1181 |  |  | 1037.5 |  |  | 969.5 |  |  | 1061.5 |  |  | 1045.5 |  |  | 1041.5 |  |  | 1058.5 |  |  | 1136.5 |  |  | 1025.5 |  |  | 1136.5 |  |  | 991.5 |  |  | 1007 |  |  | 1123.5 |  |  | 1096.5 |  |  | 1088.5 |  |  | 1074.5 |  |  | 1213.5 |  |  | 1080 |  |  | 1052.5 |  |  | 1151 |  |  | 1028 |  |  | 1034.5 |  |  | 1189.5 |  |  | 1055.5 |  |  | 1068 |  |  | 1135.5 |  |  | 1145.5 |  |  | 1112.5 |  |  | 1005 |  |  | 1101.5 |  |  | 1013.5 |  |  | 1152.5 |  |  | 1016.5 |  |  | 1066.5 |  |  | 1067 |  |  | 985.5 |  |  | 1088 |  |  | 1112.5 |  |  | 1098.5 |  |  | 1098.5 |  |  | 1219 |  |  | 1027.5 |  |  | 1157 |  |  | 1146 |  |  | 1107.5 |  |  | 1092.5 |  |  | 1096.5 |  |  | 1185.5 |  |  | 1145 |  |  | 1110.5 |  |  | 1087.5 |  |  | 1042.5 |  |  | 1122 |  |  | 1130.5 |  |  | 1042.5 |  |  | 1016.5 |  |  | 1094.5 |  |  | 1145 |  |  | 1027.5 |  |  | 1047.5 |  |  | 1139.5 |  |  | 1090.5 |  |  | 1093.5 |  |  | 1162.5 |  |  | 1120 |  |  | 1059.5 |  |  | 1057.5 |  |  | 1062 |  |  | 1044.5 |  |  | 1041.5 |  |  | 1118.5 |  |  | 1107 |  |  | 1057.5 |  |  | 1079.5 |  |  | 1073.5 |  |  | 1118.5 |  |  | 1138.5 |  |  | 1135 |  |  | 1054 |  |  | 1017.5 |  |  | 1104.5 |  |  | 1079.5 |  |  | 1106.5 |  |  | 1053 |  |  | 1129 |  |  | 1049 |  |  | 1140.5 |  |  | 1059 |  |  | 1130.5 |  |  | 1156.5 |  |  | 1147 |  |  | 1058.5 |  |  | 1136.5 |  |  | 1101.5 |  |  | 1223.5 |  |  | 1033.5 |  |  | 1078 |  |  | 1123 |  |  | 1007.5 |  |  | 1078.5 |  |  | 1061 |  |  | 982.5 |  |  | 1168.5 |  |  | 1118 |  |  | 1222.5 |  |  | 1153.5 |  |  | 1023 |  |  | 1115.5 |  |  | 1127.5 |  |  | 1090 |  |  | 1113.5 |  |  | 1044 |  |  | 1156.5 |  |  | 1164 |  |  | 1009.5 |  |  | 1074.5 |  |  | 1090.5 |  |  | 1076.5 |  |  | 1097.5 |  |  | 1070.5 |  |  | 1172 |  |  | 1104.5 |  |  | 1103.5 |  |  | 1034.5 |  |  | 1131.5 |  |  | 1042.5 |  |  | 1083 |  |  | 1068.5 |  |  | 1073 |  |  | 1084.5 |  |  | 1069.5 |  |  | 1070.5 |  |  | 1011.5 |  |  | 1086.5 |  |  | 1075.5 |  |  | 1021.5 |  |  | 1172.5 |  |  | 1077.5 |  |  | 1143 |  |  | 1141.5 |  |  | 1010 |  |  | 1077 |  |  | 1069.5 |  |  | 997 |  |  | 1050.5 |  |  | 1060.5 |  |  | 1130.5 |  |  | 1085.5 |  |  | 1107.5 |  |  | 1147.5 |  |  | 1156.5 |  |  | 1088 |  |  | 1181 |  |  | 1037.5 |  |  | 1020.5 |  |  | 1108 |  |  | 1062.5 |  |  | 1134.5 |  |  | 1022.5 |  |  | 1008.5 |  |  | 1042.5 |  |  | 1038 |  |  | 1055.5 |  |  | 1106.5 |  |  | 1074.5 |  |  | 1069 |  |  | 1123.5 |  |  | 1084.5 |  |  | 1139.5 |  |  | 1181.5 |  |  | 1166.5 |  |  | 1046.5 |  |  | 1182.5 |  |  | 942.5 |  |  | 1077.5 |  |  | 1082 |  |  | 1146.5 |  |  | 1082.5 |  |  | 1135.5 |  |  | 1062.5 |  |  | 1025.5 |  |  | 1022.5 |  |  | 1105.5 |  |  | 977 |  |  | 1019.5 |  |  | 1116.5 |  |  | 1152.5 |  |  | 1023 |  |  | 1067.5 |  |  | 1071 |  |  | 1096.5 |  |  | 1098.5 |  |  | 1084.5 |  |  | 1064 |  |  | 1005.5 |  |  | 1092 |  |  | 1083 |  |  | 1130.5 |  |  | 1103 |  |  | 1081 |  |  | 1177.5 |  |  | 1167.5 |  |  | 1045.5 |  |  | 1174 |  |  | 1122.5 |  |  | 1059.5 |  |  | 999.5 |  |  | 1165.5 |  |  | 1043.5 |  |  | 1111.5 |  |  | 1083.5 |  |  | 1089.5 |  |  | 1031 |  |  | 1208.5 |  |  | 980 |  |  | 1030.5 |  |  | 1002.5 |  |  | 1120.5 |  |  | 1140 |  |  | 1133 |  |  | 1151 |  |  | 1083.5 |  |  | 1028 |  |  | 1137.5 |  |  | 1152.5 |  |  | 1001.5 |  |  | 1115.5 |  |  | 1059.5 |  |  | 1094.5 |  |  | 1111.5 |  |  | 1109.5 |  |  | 1180 |  |  | 1033.5 |  |  | 990.5 |  |  | 1127.5 |  |  | 1042.5 |  |  | 1032 |  |  | 1085.5 |  |  | 1152 |  |  | 1075.5 |  |  | 1106.5 |  |  | 1078.5 |  |  | 1026.5 |  |  | 1008 |  |  | 1021.5 |  |  | 994 |  |  | 1039.5 |  |  | 1131.5 |  |  | 1166.5 |  |  | 1123.5 |  |  | 1080.5 |  |  | 1064.5 |  |  | 1067.5 |  |  | 1134.5 |  |  | 983.5 |  |  | 1094 |  |  | 1084.5 |  |  | 1050.5 |  |  | 1016.5 |  |  | 1120.5 |  |  | 1093.5 |  |  | 997 |  |  | 1080 |  |  | 1069.5 |  |  | 1044 |  |  | 1182.5 |  |  | 1064.5 |  |  | 1149.5 |  |  | 1189.5 |  |  | 1058.5 |  |  | 1133.5 |  |  | 1095.5 |  |  | 1069.5 |  |  | 1069 |  |  | 1142.5 |  |  | 1165.5 |  |  | 1136.5 |  |  | 1030 |  |  | 1133.5 |  |  | 1038.5 |  |  | 1179 |  |  | 993 |  |  | 1071.5 |  |  | 1010 |  |  | 987 |  |  | 1001.5 |  |  | 1026 |  |  | 1170.5 |  |  | 1189.5 |  |  | 1134.5 |  |  | 1092.5 |  |  | 1066.5 |  |  | 1132.5 |  |  | 996.5 |  |  | 1095.5 |  |  | 1034.5 |  |  | 1049.5 |  |  | 1088 |  |  | 1036 |  |  | 1055.5 |  |  | 1065.5 |  |  | 1085.5 |  |  | 1150.5 |  |  | 1018.5 |  |  | 1163.5 |  |  | 1129.5 |  |  | 1034.5 |  |  | 1161 |  |  | 1028.5 |  |  | 1003 |  |  | 1017.5 |  |  | 1256.5 |  |  | 1117.5 |  |  | 1150 |  |  | 1097.5 |  |  | 1053.5 |  |  | 1011 |  |  | 1136.5 |  |  | 1055.5 |  |  | 1165.5 |  |  | 1061.5 |  |  | 1087.5 |  |  | 1053.5 |  |  | 1031 |  |  | 1090.5 |  |  | 1038.5 |  |  | 1091.5 |  |  | 1201.5 |  |  | 1014 |  |  | 1037.5 |  |  | 1136.5 |  |  | 1088 |  |  | 1119.5 |  |  | 1104.5 |  |  | 1083 |  |  | 1139.5 |  |  | 1120.5 |  |  | 1086.5 |  |  | 1018 |  |  | 960.5 |  |  | 1100.5 |  |  | 1065 |  |  | 1069.5 |  |  | 1138.5 |  |  | 1093.5 |  |  | 933.5 |  |  | 1181.5 |  |  | 1231.5 |  |  | 1036.5 |  |  | 1122 |  |  | 1075 |  |  | 980.5 |  |  | 1108.5 |  |  | 1063.5 |  |  | 1109 |  |  | 1111.5 |  |  | 1076.5 |  |  | 1129.5 |  |  | 977.5 |  |  | 1086.5 |  |  | 1104.5 |  |  | 971.5 |  |  | 1072.5 |  |  | 1001.5 |  |  | 1120 |  |  | 1062.5 |  |  | 1084.5 |  |  | 1048.5 |  |  | 1140.5 |  |  | 1145.5 |  |  | 1048.5 |  |  | 1077.5 |  |  | 1151.5 |  |  | 1047.5 |  |  | 1096.5 |  |  | 1038.5 |  |  | 1103.5 |  |  | 1083.5 |  |  | 1156 |  |  | 1093.5 |  |  | 1114.5 |  |  | 1067 |  |  | 1101.5 |  |  | 1105.5 |  |  | 1166 |  |  | 1084.5 |  |  | 1134.5 |  |  | 1180.5 |  |  | 1155 |  |  | 1122.5 |  |  | 1151.5 |  |  | 1085.5 |  |  | 938.5 |  |  | 1105.5 |  |  | 1004 |  |  | 1080.5 |  |  | 1171 |  |  | 1090 |  |  | 1178.5 |  |  | 1128.5 |  |  | 1068.5 |  |  | 1021.5 |  |  | 1084.5 |  |  | 1103.5 |  |  | 1041 |  |  | 1075.5 |  |  | 1190 |  |  | 1052.5 |  |  | 1103 |  |  | 1075 |  |  | 1132 |  |  | 1081.5 |  |  | 1027 |  |  | 1158.5 |  |  | 1158.5 |  |  | 1177.5 |  |  | 1263.5 |  |  | 1129.5 |  |  | 1103 |  |  | 1116.5 |  |  | 1149.5 |  |  | 1259.5 |  |  | 1145 |  |  | 1129.5 |  |  | 1101.5 |  |  | 1187.5 |  |  | 1155.5 |  |  | 1054 |  |  | 1107 |  |  | 1083 |  |  | 1141.5 |  |  | 1155 |  |  | 1129 |  |  | 1140.5 |  |  | 1069.5 |  |  | 1033.5 |  |  | 1121.5 |  |  | 1150.5 |  |  | 1200.5 |  |  | 1103.5 |  |  | 1129.5 |  |  | 1004.5 |  |  | 1027 |  |  | 1091.5 |  |  | 1104 |  |  | 1167.5 |  |  | 1142.5 |  |  | 1124.5 |  |  | 1115.5 |  |  | 1119 |  |  | 1076.5 |  |  | 1084 |  |  | 1066.5 |  |  | 1106.5 |  |  | 984 |  |  | 1085 |  |  | 1084.5 |  |  | 1100 |  |  | 1223.5 |  |  | 981.5 |  |  | 1052.5 |  |  | 1095.5 |  |  | 1089.5 |  |  | 1087.5 |  |  | 1059.5 |  |  | 1020 |  |  | 1138.5 |  |  | 1113.5 |  |  | 1018.5 |  |  | 1136.5 |  |  | 1027.5 |  |  | 1071.5 |  |  | 1089.5 |  |  | 1097.5 |  |  | 1073.5 |  |  | 1096.5 |  |  | 1093.5 |  |  | 1028.5 |  |  | 1154 |  |  | 1002.5 |  |  | 1063.5 |  |  | 1158 |  |  | 1016.5 |  |  | 978.5 |  |  | 1071.5 |  |  | 1049.5 |  |  | 1137 |  |  | 1148.5 |  |  | 1090.5 |  |  | 1012.5 |  |  | 1109.5 |  |  | 1015 |  |  | 1114.5 |  |  | 1131.5 |  |  | 1100.5 |  |  | 1148.5 |  |  | 1120.5 |  |  | 1045.5 |  |  | 1163.5 |  |  | 1147.5 |  |  | 1118.5 |  |  | 1083.5 |  |  | 1146.5 |  |  | 1107 |  |  | 1113.5 |  |  | 1124.5 |  |  | 1153.5 |  |  | 1107.5 |  |  | 1038.5 |  |  | 1057.5 |  |  | 1111 |  |  | 1045.5 |  |  | 1058 |  |  | 1030.5 |  |  | 1124.5 |  |  | 1056.5 |  |  | 1071 |  |  | 1067 |  |  | 1084.5 |  |  | 1129.5 |  |  | 997.5 |  |  | 1113.5 |  |  | 1083.5 |  |  | 1044.5 |  |  | 1049.5 |  |  | 1070.5 |  |  | 1099.5 |  |  | 1120.5 |  |  | 1053.5 |  |  | 1101.5 |  |  | 1072.5 |  |  | 1090.5 |  |  | 1109.5 |  |  | 1119.5 |  |  | 1106.5 |  |  | 1104.5 |  |  | 1066.5 |  |  | 1030.5 |  |  | 1113.5 |  |  | 1104.5 |  |  | 1132 |  |  | 1199.5 |  |  | 1058.5 |  |  | 1084.5 |  |  | 1102 |  |  | 1115.5 |  |  | 1099.5 |  |  | 1093.5 |  |  | 1110.5 |  |  | 1140 |  |  | 997.5 |  |  | 1073.5 |  |  | 1011 |  |  | 990 |  |  | 1063 |  |  | 1062.5 |  |  | 1122.5 |  |  | 1128.5 |  |  | 1138.5 |  |  | 1077 |  |  | 1103.5 |  |  | 1102.5 |  |  | 1012 |  |  | 1099 |  |  | 1097.5 |  |  | 1076.5 |  |  | 1105 |  |  | 1082.5 |  |  | 1138 |  |  | 990.5 |  |  | 1033.5 |  |  | 1115 |  |  | 1137.5 |  |  | 1001.5 |  |  | 999.5 |  |  | 1133 |  |  | 1105.5 |  |  | 1067.5 |  |  | 1048.5 |  |  | 1029.5 |  |  | 1076.5 |  |  | 1197.5 |  |  | 1033.5 |  |  | 1105.5 |  |  | 1139.5 |  |  | 1098.5 |  |  | 1138 |  |  | 1040.5 |  |  | 1100.5 |  |  | 1114.5 |  |  | 1144.5 |  |  | 1031.5 |  |  | 1182.5 |  |  | 1177.5 |  |  | 1092.5 |  |  | 1144 |  |  | 1111.5 |  |  | 1110 |  |  | 1108.5 |  |  | 1186.5 |  |  | 1235.5 |  |  | 1075.5 |  |  | 1124.5 |  |  | 1048.5 |  |  | 957.5 |  |  | 1138.5 |  |  | 1132 |  |  | 1029.5 |  |  | 1033 |  |  | 1042.5 |  |  | 987.5 |  |  | 1154.5 |  |  | 1164 |  |  | 1067.5 |  |  | 1143.5 |  |  | 1034 |  |  | 1041.5 |  |  | 1043 |  |  | 1034.5 |  |  | 1099.5 |  |  | 1055.5 |  |  | 1027 |  |  | 1087.5 |  |  | 1219.5 |  |  | 1034 |  |  | 1141.5 |  |  | 1013.5 |  |  | 1103 |  |  | 1106.5 |  |  | 1217.5 |  |  | 1106.5 |  |  | 1133.5 |  |  | 1096.5 |  |  | 1076.5 |  |  | 1019.5 |  |  | 1106.5 |  |  | 998.5 |  |  | 1162.5 |  |  | 1185.5 |  |  | 1095 |  |  | 1154 |  |  | 1144.5 |  |  | 1106.5 |  |  | 1174
39 |  | 1156.5 |  |  | 1204.5 |  |  | 1151 |  |  | 1119.5 |  |  | 1201.5 |  |  | 1177.5 |  |  | 1204.5 |  |  | 1109.5 |  |  | 1108.5 |  |  | 1142.5 |  |  | 1094 |  |  | 1109.5 |  |  | 1239.5 |  |  | 1091.5 |  |  | 1048 |  |  | 1102.5 |  |  | 1251.5 |  |  | 1134.5 |  |  | 1231.5 |  |  | 1037.5 |  |  | 1098.5 |  |  | 1063.5 |  |  | 1128.5 |  |  | 1059.5 |  |  | 1051 |  |  | 1209.5 |  |  | 1082.5 |  |  | 1089.5 |  |  | 1091.5 |  |  | 1035 |  |  | 1125 |  |  | 1066.5 |  |  | 1093.5 |  |  | 1129.5 |  |  | 1032.5 |  |  | 1108 |  |  | 1088.5 |  |  | 1097 |  |  | 1081.5 |  |  | 1167.5 |  |  | 1057.5 |  |  | 1180.5 |  |  | 1052.5 |  |  | 1060 |  |  | 1268.5 |  |  | 1167 |  |  | 1066.5 |  |  | 1136.5 |  |  | 1144.5 |  |  | 1076.5 |  |  | 1111.5 |  |  | 1113.5 |  |  | 1088.5 |  |  | 1101.5 |  |  | 1151.5 |  |  | 1111.5 |  |  | 1048.5 |  |  | 1105 |  |  | 1199.5 |  |  | 1110.5 |  |  | 1096 |  |  | 1083.5 |  |  | 1166.5 |  |  | 1123.5 |  |  | 1082.5 |  |  | 1139 |  |  | 1138.5 |  |  | 1014 |  |  | 1129.5 |  |  | 1117.5 |  |  | 1148 |  |  | 1157.5 |  |  | 1086.5 |  |  | 1185.5 |  |  | 1172 |  |  | 1115 |  |  | 1119.5 |  |  | 1044.5 |  |  | 1005.5 |  |  | 1077.5 |  |  | 1084 |  |  | 1103.5 |  |  | 1156.5 |  |  | 1202.5 |  |  | 1186.5 |  |  | 1200.5 |  |  | 1193.5 |  |  | 1086.5 |  |  | 1087.5 |  |  | 1175.5 |  |  | 1163.5 |  |  | 1137 |  |  | 1059.5 |  |  | 1077 |  |  | 1107 |  |  | 1058 |  |  | 1144.5 |  |  | 1173.5 |  |  | 1092.5 |  |  | 1149.5 |  |  | 1113.5 |  |  | 1180 |  |  | 1180 |  |  | 1080.5 |  |  | 1099.5 |  |  | 1121.5 |  |  | 1104.5 |  |  | 1147.5 |  |  | 1170.5 |  |  | 1180.5 |  |  | 1176.5 |  |  | 1117.5 |  |  | 1194.5 |  |  | 1134.5 |  |  | 1173.5 |  |  | 1149.5 |  |  | 1140.5 |  |  | 1047.5 |  |  | 1139.5 |  |  | 1176.5 |  |  | 1153.5 |  |  | 1164.5 |  |  | 1111.5 |  |  | 1124.5 |  |  | 1151.5 |  |  | 1146 |  |  | 1078.5 |  |  | 1131.5 |  |  | 1041.5 |  |  | 1073.5 |  |  | 1237.5 |  |  | 1158 |  |  | 1051.5 |  |  | 1162.5 |  |  | 1079.5 |  |  | 1169.5 |  |  | 1080 |  |  | 1122.5 |  |  | 1183.5 |  |  | 1080 |  |  | 1148.5 |  |  | 1107 |  |  | 1101 |  |  | 1182.5 |  |  | 1158 |  |  | 1195.5 |  |  | 1095.5 |  |  | 1128.5 |  |  | 1052.5 |  |  | 1164.5 |  |  | 1163.5 |  |  | 1147.5 |  |  | 1135.5 |  |  | 1206.5 |  |  | 1162.5 |  |  | 1179 |  |  | 1038.5 |  |  | 1089 |  |  | 1059.5 |  |  | 1151.5 |  |  | 1123 |  |  | 1158.5 |  |  | 1074.5 |  |  | 1070.5 |  |  | 1111 |  |  | 1157.5 |  |  | 1086.5 |  |  | 1062.5 |  |  | 1113.5 |  |  | 1089.5 |  |  | 1112.5 |  |  | 1139 |  |  | 1086.5 |  |  | 1142.5 |  |  | 1102.5 |  |  | 1084.5 |  |  | 1174.5 |  |  | 1210.5 |  |  | 1051.5 |  |  | 1218 |  |  | 1162.5 |  |  | 1146.5 |  |  | 1223.5 |  |  | 1178.5 |  |  | 1054.5 |  |  | 1236.5 |  |  | 1143.5 |  |  | 1112.5 |  |  | 1098.5 |  |  | 1047.5 |  |  | 1117.5 |  |  | 1072.5 |  |  | 1013.5 |  |  | 1068 |  |  | 1080.5 |  |  | 1159.5 |  |  | 1090.5 |  |  | 1124.5 |  |  | 1208.5 |  |  | 1118.5 |  |  | 1159.5 |  |  | 1056.5 |  |  | 1056.5 |  |  | 1149.5 |  |  | 1118.5 |  |  | 1256.5 |  |  | 1128.5 |  |  | 1076.5 |  |  | 1168.5 |  |  | 1157.5 |  |  | 1131 |  |  | 1165.5 |  |  | 1087.5 |  |  | 1011 |  |  | 1185.5 |  |  | 1142 |  |  | 1122.5 |  |  | 1179.5 |  |  | 1234.5 |  |  | 1110.5 |  |  | 1110.5 |  |  | 1096.5 |  |  | 1085.5 |  |  | 1044.5 |  |  | 1045 |  |  | 1054.5 |  |  | 988.5 |  |  | 1185.5 |  |  | 1101.5 |  |  | 1216 |  |  | 1059.5 |  |  | 1043.5 |  |  | 1148.5 |  |  | 1152.5 |  |  | 1168.5 |  |  | 1059.5 |  |  | 1075.5 |  |  | 1122.5 |  |  | 1136 |  |  | 1122 |  |  | 1037.5 |  |  | 1117.5 |  |  | 1156.5 |  |  | 1180 |  |  | 1197.5 |  |  | 1165.5 |  |  | 1099.5 |  |  | 1098 |  |  | 1149.5 |  |  | 1181.5 |  |  | 1122.5 |  |  | 1065.5 |  |  | 1129.5 |  |  | 1143.5 |  |  | 1159.5 |  |  | 1089.5 |  |  | 1171.5 |  |  | 985 |  |  | 1054.5 |  |  | 1141.5 |  |  | 1084.5 |  |  | 1099.5 |  |  | 1146.5 |  |  | 1206 |  |  | 1116.5 |  |  | 1182.5 |  |  | 1133 |  |  | 1233.5 |  |  | 1142.5 |  |  | 1182 |  |  | 1130.5 |  |  | 1151.5 |  |  | 1259.5 |  |  | 1081.5 |  |  | 1143 |  |  | 1181 |  |  | 1154.5 |  |  | 1137.5 |  |  | 1173.5 |  |  | 1144.5 |  |  | 1213.5 |  |  | 1055.5 |  |  | 1103 |  |  | 1155.5 |  |  | 1143.5 |  |  | 1115 |  |  | 1092.5 |  |  | 1061.5 |  |  | 1103 |  |  | 1133.5 |  |  | 1098.5 |  |  | 1107.5 |  |  | 1143 |  |  | 1154.5 |  |  | 1082 |  |  | 1163.5 |  |  | 1088.5 |  |  | 1125.5 |  |  | 1084 |  |  | 1073.5 |  |  | 1212.5 |  |  | 1069.5 |  |  | 1142 |  |  | 1012.5 |  |  | 1093.5 |  |  | 1190.5 |  |  | 1182.5 |  |  | 1099.5 |  |  | 1085 |  |  | 1095.5 |  |  | 1243.5 |  |  | 1225.5 |  |  | 1070 |  |  | 1125 |  |  | 1190.5 |  |  | 1169.5 |  |  | 1054.5 |  |  | 1158.5 |  |  | 1180.5 |  |  | 1160.5 |  |  | 1095.5 |  |  | 1138.5 |  |  | 1038.5 |  |  | 1125.5 |  |  | 1108 |  |  | 1171.5 |  |  | 1206.5 |  |  | 1243.5 |  |  | 1252.5 |  |  | 1155 |  |  | 1214.5 |  |  | 1162.5 |  |  | 1151.5 |  |  | 1001.5 |  |  | 1145.5 |  |  | 1116 |  |  | 1105 |  |  | 1029 |  |  | 1115 |  |  | 1082.5 |  |  | 1124 |  |  | 1134.5 |  |  | 1079 |  |  | 1118.5 |  |  | 1183.5 |  |  | 1134.5 |  |  | 1106.5 |  |  | 1086.5 |  |  | 1118 |  |  | 1150.5 |  |  | 1203.5 |  |  | 1032.5 |  |  | 1178 |  |  | 1148.5 |  |  | 1130.5 |  |  | 1091.5 |  |  | 1207 |  |  | 1076.5 |  |  | 1016.5 |  |  | 1100.5 |  |  | 1071.5 |  |  | 1088.5 |  |  | 1084.5 |  |  | 1157.5 |  |  | 1054.5 |  |  | 1175.5 |  |  | 1030.5 |  |  | 1036 |  |  | 1162.5 |  |  | 1117.5 |  |  | 1135.5 |  |  | 1113.5 |  |  | 1234.5 |  |  | 1127 |  |  | 1099.5 |  |  | 1166 |  |  | 1057 |  |  | 1073.5 |  |  | 1204.5 |  |  | 1094.5 |  |  | 1107 |  |  | 1174.5 |  |  | 1184.5 |  |  | 1141.5 |  |  | 1026 |  |  | 1125.5 |  |  | 1060.5 |  |  | 1181.5 |  |  | 1040.5 |  |  | 1081.5 |  |  | 1096 |  |  | 1032.5 |  |  | 1112 |  |  | 1141.5 |  |  | 1122.5 |  |  | 1145.5 |  |  | 1240 |  |  | 1051.5 |  |  | 1172 |  |  | 1167 |  |  | 1128.5 |  |  | 1113.5 |  |  | 1117.5 |  |  | 1224.5 |  |  | 1171 |  |  | 1134.5 |  |  | 1102.5 |  |  | 1068.5 |  |  | 1151 |  |  | 1151.5 |  |  | 1081.5 |  |  | 1040.5 |  |  | 1120.5 |  |  | 1192 |  |  | 1051.5 |  |  | 1086.5 |  |  | 1163.5 |  |  | 1129.5 |  |  | 1122.5 |  |  | 1186.5 |  |  | 1144 |  |  | 1098.5 |  |  | 1086.5 |  |  | 1109 |  |  | 1068.5 |  |  | 1056.5 |  |  | 1147.5 |  |  | 1146 |  |  | 1104.5 |  |  | 1105.5 |  |  | 1120.5 |  |  | 1157.5 |  |  | 1164.5 |  |  | 1174 |  |  | 1101 |  |  | 1056.5 |  |  | 1133.5 |  |  | 1105.5 |  |  | 1127.5 |  |  | 1079 |  |  | 1153 |  |  | 1088 |  |  | 1179.5 |  |  | 1106 |  |  | 1177.5 |  |  | 1195.5 |  |  | 1173 |  |  | 1082.5 |  |  | 1175.5 |  |  | 1125.5 |  |  | 1262.5 |  |  | 1080.5 |  |  | 1117 |  |  | 1147 |  |  | 1028.5 |  |  | 1099.5 |  |  | 1090 |  |  | 1029.5 |  |  | 1197.5 |  |  | 1142 |  |  | 1251.5 |  |  | 1200.5 |  |  | 1047 |  |  | 1141.5 |  |  | 1142.5 |  |  | 1105 |  |  | 1134.5 |  |  | 1068 |  |  | 1185.5 |  |  | 1203 |  |  | 1035.5 |  |  | 1100.5 |  |  | 1119.5 |  |  | 1115.5 |  |  | 1118.5 |  |  | 1091.5 |  |  | 1196 |  |  | 1133.5 |  |  | 1127.5 |  |  | 1060.5 |  |  | 1157.5 |  |  | 1057.5 |  |  | 1122 |  |  | 1097.5 |  |  | 1097 |  |  | 1123.5 |  |  | 1098.5 |  |  | 1109.5 |  |  | 1050.5 |  |  | 1110.5 |  |  | 1122.5 |  |  | 1036.5 |  |  | 1219.5 |  |  | 1106.5 |  |  | 1182 |  |  | 1162.5 |  |  | 1049 |  |  | 1116 |  |  | 1093.5 |  |  | 1026 |  |  | 1076.5 |  |  | 1089.5 |  |  | 1145.5 |  |  | 1114.5 |  |  | 1136.5 |  |  | 1173.5 |  |  | 1182.5 |  |  | 1114 |  |  | 1202 |  |  | 1076.5 |  |  | 1044.5 |  |  | 1147 |  |  | 1077.5 |  |  | 1149.5 |  |  | 1061.5 |  |  | 1047.5 |  |  | 1063.5 |  |  | 1077 |  |  | 1084.5 |  |  | 1135.5 |  |  | 1103.5 |  |  | 1098 |  |  | 1162.5 |  |  | 1131.5 |  |  | 1160.5 |  |  | 1220.5 |  |  | 1190.5 |  |  | 1070.5 |  |  | 1229.5 |  |  | 971.5 |  |  | 1106.5 |  |  | 1106 |  |  | 1161.5 |  |  | 1121.5 |  |  | 1161.5 |  |  | 1077.5 |  |  | 1046.5 |  |  | 1048.5 |  |  | 1131.5 |  |  | 992 |  |  | 1043.5 |  |  | 1137.5 |  |  | 1167.5 |  |  | 1049 |  |  | 1088.5 |  |  | 1100 |  |  | 1125.5 |  |  | 1124.5 |  |  | 1105.5 |  |  | 1085 |  |  | 1031.5 |  |  | 1139 |  |  | 1130 |  |  | 1156.5 |  |  | 1118 |  |  | 1110 |  |  | 1192.5 |  |  | 1206.5 |  |  | 1060.5 |  |  | 1195 |  |  | 1146.5 |  |  | 1098.5 |  |  | 1025.5 |  |  | 1191.5 |  |  | 1064.5 |  |  | 1158.5 |  |  | 1098.5 |  |  | 1128.5 |  |  | 1052 |  |  | 1232.5 |  |  | 1027 |  |  | 1051.5 |  |  | 1023.5 |  |  | 1159.5 |  |  | 1155 |  |  | 1172 |  |  | 1198 |  |  | 1104.5 |  |  | 1057 |  |  | 1184.5 |  |  | 1167.5 |  |  | 1030.5 |  |  | 1139.5 |  |  | 1080.5 |  |  | 1123.5 |  |  | 1150.5 |  |  | 1148.5 |  |  | 1201 |  |  | 1057.5 |  |  | 1029.5 |  |  | 1151.5 |  |  | 1057.5 |  |  | 1058 |  |  | 1111.5 |  |  | 1181 |  |  | 1114.5 |  |  | 1132.5 |  |  | 1117.5 |  |  | 1050.5 |  |  | 1037 |  |  | 1045.5 |  |  | 1009 |  |  | 1054.5 |  |  | 1157.5 |  |  | 1192.5 |  |  | 1149.5 |  |  | 1104.5 |  |  | 1088.5 |  |  | 1096.5 |  |  | 1160.5 |  |  | 1004.5 |  |  | 1120 |  |  | 1105.5 |  |  | 1079.5 |  |  | 1055.5 |  |  | 1135.5 |  |  | 1114.5 |  |  | 1021 |  |  | 1101 |  |  | 1116.5 |  |  | 1070 |  |  | 1221.5 |  |  | 1093.5 |  |  | 1175.5 |  |  | 1210.5 |  |  | 1084.5 |  |  | 1172.5 |  |  | 1121.5 |  |  | 1090.5 |  |  | 1116 |  |  | 1168.5 |  |  | 1204.5 |  |  | 1175.5 |  |  | 1059 |  |  | 1157.5 |  |  | 1077.5 |  |  | 1200 |  |  | 1008 |  |  | 1095.5 |  |  | 1031 |  |  | 1034 |  |  | 1016.5 |  |  | 1041 |  |  | 1199.5 |  |  | 1213.5 |  |  | 1173.5 |  |  | 1116.5 |  |  | 1092.5 |  |  | 1156.5 |  |  | 1022.5 |  |  | 1116.5 |  |  | 1073.5 |  |  | 1073.5 |  |  | 1127 |  |  | 1057 |  |  | 1102.5 |  |  | 1089.5 |  |  | 1106.5 |  |  | 1174.5 |  |  | 1057.5 |  |  | 1210.5 |  |  | 1144.5 |  |  | 1081.5 |  |  | 1200 |  |  | 1057.5 |  |  | 1029 |  |  | 1056.5 |  |  | 1280.5 |  |  | 1143.5 |  |  | 1176 |  |  | 1126.5 |  |  | 1079.5 |  |  | 1037 |  |  | 1151.5 |  |  | 1094.5 |  |  | 1180.5 |  |  | 1108.5 |  |  | 1108.5 |  |  | 1100.5 |  |  | 1070 |  |  | 1137.5 |  |  | 1067.5 |  |  | 1130.5 |  |  | 1227.5 |  |  | 1038 |  |  | 1066.5 |  |  | 1183.5 |  |  | 1127 |  |  | 1158.5 |  |  | 1133.5 |  |  | 1098 |  |  | 1160.5 |  |  | 1141.5 |  |  | 1125.5 |  |  | 1044 |  |  | 975.5 |  |  | 1139.5 |  |  | 1089 |  |  | 1084.5 |  |  | 1167.5 |  |  | 1117.5 |  |  | 962.5 |  |  | 1228.5 |  |  | 1270.5 |  |  | 1051.5 |  |  | 1151 |  |  | 1104 |  |  | 1027.5 |  |  | 1129.5 |  |  | 1078.5 |  |  | 1135 |  |  | 1150.5 |  |  | 1115.5 |  |  | 1150.5 |  |  | 1001.5 |  |  | 1101.5 |  |  | 1143.5 |  |  | 1018.5 |  |  | 1111.5 |  |  | 1016.5 |  |  | 1159 |  |  | 1086.5 |  |  | 1099.5 |  |  | 1074.5 |  |  | 1179.5 |  |  | 1166.5 |  |  | 1063.5 |  |  | 1098.5 |  |  | 1166.5 |  |  | 1073.5 |  |  | 1122.5 |  |  | 1067.5 |  |  | 1132.5 |  |  | 1130.5 |  |  | 1185 |  |  | 1132.5 |  |  | 1135.5 |  |  | 1096 |  |  | 1140.5 |  |  | 1131.5 |  |  | 1213 |  |  | 1123.5 |  |  | 1158.5 |  |  | 1219.5 |  |  | 1202 |  |  | 1151.5 |  |  | 1177.5 |  |  | 1124.5 |  |  | 953.5 |  |  | 1131.5 |  |  | 1051 |  |  | 1109.5 |  |  | 1192 |  |  | 1116 |  |  | 1193.5 |  |  | 1157.5 |  |  | 1094.5 |  |  | 1045.5 |  |  | 1123.5 |  |  | 1124.5 |  |  | 1062 |  |  | 1101.5 |  |  | 1205 |  |  | 1067.5 |  |  | 1150 |  |  | 1114 |  |  | 1158 |  |  | 1096.5 |  |  | 1066 |  |  | 1179.5 |  |  | 1182.5 |  |  | 1192.5 |  |  | 1287.5 |  |  | 1155.5 |  |  | 1127 |  |  | 1155.5 |  |  | 1188.5 |  |  | 1285.5 |  |  | 1184 |  |  | 1153.5 |  |  | 1116.5 |  |  | 1216.5 |  |  | 1170.5 |  |  | 1101 |  |  | 1146 |  |  | 1104 |  |  | 1162.5 |  |  | 1184 |  |  | 1150 |  |  | 1179.5 |  |  | 1095.5 |  |  | 1054.5 |  |  | 1145.5 |  |  | 1179.5 |  |  | 1247.5 |  |  | 1127.5 |  |  | 1153.5 |  |  | 1051.5 |  |  | 1066 |  |  | 1115.5 |  |  | 1125 |  |  | 1206.5 |  |  | 1157.5 |  |  | 1148.5 |  |  | 1162.5 |  |  | 1145 |  |  | 1115.5 |  |  | 1123 |  |  | 1113.5 |  |  | 1145.5 |  |  | 1010 |  |  | 1100 |  |  | 1099.5 |  |  | 1139 |  |  | 1238.5 |  |  | 1007.5 |  |  | 1076.5 |  |  | 1116.5 |  |  | 1115.5 |  |  | 1126.5 |  |  | 1098.5 |  |  | 1041 |  |  | 1177.5 |  |  | 1152.5 |  |  | 1042.5 |  |  | 1160.5 |  |  | 1056.5 |  |  | 1110.5 |  |  | 1136.5 |  |  | 1136.5 |  |  | 1094.5 |  |  | 1135.5 |  |  | 1117.5 |  |  | 1075.5 |  |  | 1169 |  |  | 1028.5 |  |  | 1092.5 |  |  | 1173 |  |  | 1055.5 |  |  | 1017.5 |  |  | 1092.5 |  |  | 1096.5 |  |  | 1166 |  |  | 1187.5 |  |  | 1137.5 |  |  | 1033.5 |  |  | 1130.5 |  |  | 1054 |  |  | 1161.5 |  |  | 1160.5 |  |  | 1147.5 |  |  | 1172.5 |  |  | 1146.5 |  |  | 1060.5 |  |  | 1184.5 |  |  | 1186.5 |  |  | 1157.5 |  |  | 1122.5 |  |  | 1185.5 |  |  | 1131 |  |  | 1160.5 |  |  | 1145.5 |  |  | 1192.5 |  |  | 1128.5 |  |  | 1077.5 |  |  | 1086.5 |  |  | 1135 |  |  | 1074.5 |  |  | 1087 |  |  | 1069.5 |  |  | 1171.5 |  |  | 1082.5 |  |  | 1097 |  |  | 1096 |  |  | 1113.5 |  |  | 1153.5 |  |  | 1036.5 |  |  | 1137.5 |  |  | 1104.5 |  |  | 1083.5 |  |  | 1064.5 |  |  | 1085.5 |  |  | 1123.5 |  |  | 1141.5 |  |  | 1092.5 |  |  | 1125.5 |  |  | 1098.5 |  |  | 1129.5 |  |  | 1138.5 |  |  | 1148.5 |  |  | 1130.5 |  |  | 1143.5 |  |  | 1090.5 |  |  | 1051.5 |  |  | 1137.5 |  |  | 1151.5 |  |  | 1161 |  |  | 1246.5 |  |  | 1087.5 |  |  | 1123.5 |  |  | 1149 |  |  | 1162.5 |  |  | 1120.5 |  |  | 1140.5 |  |  | 1139.5 |  |  | 1187 |  |  | 1036.5 |  |  | 1112.5 |  |  | 1026 |  |  | 1011 |  |  | 1110 |  |  | 1091.5 |  |  | 1148.5 |  |  | 1149.5 |  |  | 1185.5 |  |  | 1106 |  |  | 1129.5 |  |  | 1117.5 |  |  | 1027 |  |  | 1120 |  |  | 1126.5 |  |  | 1115.5 |  |  | 1134 |  |  | 1121.5 |  |  | 1164 |  |  | 1019.5 |  |  | 1054.5 |  |  | 1154 |  |  | 1184.5 |  |  | 1025.5 |  |  | 1038.5 |  |  | 1180 |  |  | 1144.5 |  |  | 1091.5 |  |  | 1069.5 |  |  | 1068.5 |  |  | 1102.5 |  |  | 1218.5 |  |  | 1062.5 |  |  | 1131.5 |  |  | 1186.5 |  |  | 1122.5 |  |  | 1159 |  |  | 1069.5 |  |  | 1147.5 |  |  | 1161.5 |  |  | 1165.5 |  |  | 1078.5 |  |  | 1203.5 |  |  | 1203.5 |  |  | 1107.5 |  |  | 1168 |  |  | 1132.5 |  |  | 1134 |  |  | 1155.5 |  |  | 1225.5 |  |  | 1256.5 |  |  | 1090.5 |  |  | 1148.5 |  |  | 1087.5 |  |  | 983.5 |  |  | 1164.5 |  |  | 1161 |  |  | 1076.5 |  |  | 1062 |  |  | 1071.5 |  |  | 1002.5 |  |  | 1193.5 |  |  | 1193 |  |  | 1082.5 |  |  | 1158.5 |  |  | 1060 |  |  | 1070.5 |  |  | 1082 |  |  | 1049.5 |  |  | 1138.5 |  |  | 1081.5 |  |  | 1074 |  |  | 1134.5 |  |  | 1240.5 |  |  | 1055 |  |  | 1180.5 |  |  | 1039.5 |  |  | 1150 |  |  | 1145.5 |  |  | 1243.5 |  |  | 1135.5 |  |  | 1157.5 |  |  | 1117.5 |  |  | 1097.5 |  |  | 1058.5 |  |  | 1145.5 |  |  | 1013.5 |  |  | 1183.5 |  |  | 1214.5 |  |  | 1134 |  |  | 1169 |  |  | 1165.5 |  |  | 1145.5 |  |  | 1221
40 |  | 1171.5 |  |  | 1243.5 |  |  | 1190 |  |  | 1148.5 |  |  | 1248.5 |  |  | 1198.5 |  |  | 1243.5 |  |  | 1130.5 |  |  | 1137.5 |  |  | 1181.5 |  |  | 1120 |  |  | 1148.5 |  |  | 1254.5 |  |  | 1106.5 |  |  | 1077 |  |  | 1131.5 |  |  | 1266.5 |  |  | 1149.5 |  |  | 1257.5 |  |  | 1084.5 |  |  | 1124.5 |  |  | 1102.5 |  |  | 1149.5 |  |  | 1074.5 |  |  | 1072 |  |  | 1238.5 |  |  | 1121.5 |  |  | 1128.5 |  |  | 1130.5 |  |  | 1059 |  |  | 1140 |  |  | 1081.5 |  |  | 1108.5 |  |  | 1144.5 |  |  | 1056.5 |  |  | 1147 |  |  | 1127.5 |  |  | 1123 |  |  | 1096.5 |  |  | 1182.5 |  |  | 1086.5 |  |  | 1201.5 |  |  | 1091.5 |  |  | 1081 |  |  | 1292.5 |  |  | 1188 |  |  | 1105.5 |  |  | 1162.5 |  |  | 1173.5 |  |  | 1100.5 |  |  | 1135.5 |  |  | 1137.5 |  |  | 1127.5 |  |  | 1140.5 |  |  | 1198.5 |  |  | 1137.5 |  |  | 1063.5 |  |  | 1134 |  |  | 1238.5 |  |  | 1139.5 |  |  | 1117 |  |  | 1130.5 |  |  | 1195.5 |  |  | 1152.5 |  |  | 1103.5 |  |  | 1168 |  |  | 1177.5 |  |  | 1061 |  |  | 1144.5 |  |  | 1156.5 |  |  | 1177 |  |  | 1172.5 |  |  | 1101.5 |  |  | 1224.5 |  |  | 1193 |  |  | 1136 |  |  | 1148.5 |  |  | 1068.5 |  |  | 1052.5 |  |  | 1101.5 |  |  | 1110 |  |  | 1118.5 |  |  | 1195.5 |  |  | 1217.5 |  |  | 1210.5 |  |  | 1224.5 |  |  | 1214.5 |  |  | 1101.5 |  |  | 1113.5 |  |  | 1199.5 |  |  | 1202.5 |  |  | 1176 |  |  | 1074.5 |  |  | 1103 |  |  | 1136 |  |  | 1097 |  |  | 1183.5 |  |  | 1194.5 |  |  | 1116.5 |  |  | 1188.5 |  |  | 1128.5 |  |  | 1206 |  |  | 1227 |  |  | 1104.5 |  |  | 1120.5 |  |  | 1150.5 |  |  | 1143.5 |  |  | 1168.5 |  |  | 1217.5 |  |  | 1195.5 |  |  | 1202.5 |  |  | 1141.5 |  |  | 1209.5 |  |  | 1173.5 |  |  | 1220.5 |  |  | 1196.5 |  |  | 1161.5 |  |  | 1068.5 |  |  | 1168.5 |  |  | 1202.5 |  |  | 1179.5 |  |  | 1190.5 |  |  | 1137.5 |  |  | 1163.5 |  |  | 1190.5 |  |  | 1170 |  |  | 1099.5 |  |  | 1157.5 |  |  | 1056.5 |  |  | 1112.5 |  |  | 1258.5 |  |  | 1182 |  |  | 1075.5 |  |  | 1188.5 |  |  | 1100.5 |  |  | 1184.5 |  |  | 1095 |  |  | 1169.5 |  |  | 1222.5 |  |  | 1104 |  |  | 1163.5 |  |  | 1146 |  |  | 1140 |  |  | 1197.5 |  |  | 1184 |  |  | 1234.5 |  |  | 1116.5 |  |  | 1157.5 |  |  | 1091.5 |  |  | 1211.5 |  |  | 1178.5 |  |  | 1186.5 |  |  | 1150.5 |  |  | 1253.5 |  |  | 1183.5 |  |  | 1203 |  |  | 1059.5 |  |  | 1118 |  |  | 1098.5 |  |  | 1175.5 |  |  | 1170 |  |  | 1197.5 |  |  | 1121.5 |  |  | 1117.5 |  |  | 1137 |  |  | 1181.5 |  |  | 1115.5 |  |  | 1086.5 |  |  | 1142.5 |  |  | 1118.5 |  |  | 1151.5 |  |  | 1178 |  |  | 1101.5 |  |  | 1166.5 |  |  | 1128.5 |  |  | 1131.5 |  |  | 1203.5 |  |  | 1234.5 |  |  | 1066.5 |  |  | 1257 |  |  | 1201.5 |  |  | 1161.5 |  |  | 1262.5 |  |  | 1199.5 |  |  | 1069.5 |  |  | 1265.5 |  |  | 1182.5 |  |  | 1151.5 |  |  | 1137.5 |  |  | 1086.5 |  |  | 1146.5 |  |  | 1111.5 |  |  | 1052.5 |  |  | 1083 |  |  | 1101.5 |  |  | 1174.5 |  |  | 1116.5 |  |  | 1171.5 |  |  | 1223.5 |  |  | 1133.5 |  |  | 1188.5 |  |  | 1085.5 |  |  | 1095.5 |  |  | 1164.5 |  |  | 1133.5 |  |  | 1285.5 |  |  | 1143.5 |  |  | 1091.5 |  |  | 1207.5 |  |  | 1196.5 |  |  | 1178 |  |  | 1189.5 |  |  | 1134.5 |  |  | 1026 |  |  | 1232.5 |  |  | 1181 |  |  | 1148.5 |  |  | 1203.5 |  |  | 1263.5 |  |  | 1134.5 |  |  | 1125.5 |  |  | 1135.5 |  |  | 1124.5 |  |  | 1068.5 |  |  | 1066 |  |  | 1075.5 |  |  | 1012.5 |  |  | 1206.5 |  |  | 1127.5 |  |  | 1263 |  |  | 1085.5 |  |  | 1082.5 |  |  | 1163.5 |  |  | 1191.5 |  |  | 1197.5 |  |  | 1083.5 |  |  | 1101.5 |  |  | 1169.5 |  |  | 1157 |  |  | 1161 |  |  | 1061.5 |  |  | 1156.5 |  |  | 1195.5 |  |  | 1219 |  |  | 1218.5 |  |  | 1212.5 |  |  | 1125.5 |  |  | 1137 |  |  | 1178.5 |  |  | 1196.5 |  |  | 1151.5 |  |  | 1112.5 |  |  | 1144.5 |  |  | 1182.5 |  |  | 1198.5 |  |  | 1104.5 |  |  | 1186.5 |  |  | 1000 |  |  | 1078.5 |  |  | 1167.5 |  |  | 1123.5 |  |  | 1120.5 |  |  | 1167.5 |  |  | 1221 |  |  | 1137.5 |  |  | 1221.5 |  |  | 1162 |  |  | 1280.5 |  |  | 1157.5 |  |  | 1229 |  |  | 1156.5 |  |  | 1177.5 |  |  | 1285.5 |  |  | 1096.5 |  |  | 1190 |  |  | 1210 |  |  | 1178.5 |  |  | 1161.5 |  |  | 1188.5 |  |  | 1183.5 |  |  | 1237.5 |  |  | 1084.5 |  |  | 1124 |  |  | 1184.5 |  |  | 1182.5 |  |  | 1162 |  |  | 1107.5 |  |  | 1082.5 |  |  | 1142 |  |  | 1154.5 |  |  | 1127.5 |  |  | 1122.5 |  |  | 1167 |  |  | 1193.5 |  |  | 1121 |  |  | 1187.5 |  |  | 1127.5 |  |  | 1146.5 |  |  | 1123 |  |  | 1112.5 |  |  | 1233.5 |  |  | 1084.5 |  |  | 1168 |  |  | 1051.5 |  |  | 1114.5 |  |  | 1229.5 |  |  | 1211.5 |  |  | 1114.5 |  |  | 1114 |  |  | 1121.5 |  |  | 1269.5 |  |  | 1240.5 |  |  | 1117 |  |  | 1164 |  |  | 1229.5 |  |  | 1195.5 |  |  | 1078.5 |  |  | 1197.5 |  |  | 1219.5 |  |  | 1184.5 |  |  | 1110.5 |  |  | 1185.5 |  |  | 1067.5 |  |  | 1172.5 |  |  | 1137 |  |  | 1195.5 |  |  | 1235.5 |  |  | 1282.5 |  |  | 1273.5 |  |  | 1170 |  |  | 1238.5 |  |  | 1183.5 |  |  | 1190.5 |  |  | 1016.5 |  |  | 1160.5 |  |  | 1140 |  |  | 1120 |  |  | 1068 |  |  | 1141 |  |  | 1129.5 |  |  | 1171 |  |  | 1160.5 |  |  | 1118 |  |  | 1142.5 |  |  | 1212.5 |  |  | 1181.5 |  |  | 1145.5 |  |  | 1125.5 |  |  | 1147 |  |  | 1179.5 |  |  | 1242.5 |  |  | 1071.5 |  |  | 1207 |  |  | 1163.5 |  |  | 1156.5 |  |  | 1130.5 |  |  | 1231 |  |  | 1102.5 |  |  | 1045.5 |  |  | 1124.5 |  |  | 1097.5 |  |  | 1114.5 |  |  | 1099.5 |  |  | 1196.5 |  |  | 1101.5 |  |  | 1201.5 |  |  | 1051.5 |  |  | 1075 |  |  | 1186.5 |  |  | 1156.5 |  |  | 1161.5 |  |  | 1137.5 |  |  | 1273.5 |  |  | 1166 |  |  | 1120.5 |  |  | 1190 |  |  | 1096 |  |  | 1120.5 |  |  | 1243.5 |  |  | 1123.5 |  |  | 1131 |  |  | 1213.5 |  |  | 1199.5 |  |  | 1188.5 |  |  | 1065 |  |  | 1146.5 |  |  | 1081.5 |  |  | 1228.5 |  |  | 1066.5 |  |  | 1105.5 |  |  | 1122 |  |  | 1061.5 |  |  | 1151 |  |  | 1156.5 |  |  | 1148.5 |  |  | 1169.5 |  |  | 1255 |  |  | 1090.5 |  |  | 1201 |  |  | 1182 |  |  | 1149.5 |  |  | 1128.5 |  |  | 1156.5 |  |  | 1263.5 |  |  | 1192 |  |  | 1173.5 |  |  | 1126.5 |  |  | 1097.5 |  |  | 1175 |  |  | 1180.5 |  |  | 1107.5 |  |  | 1079.5 |  |  | 1141.5 |  |  | 1216 |  |  | 1090.5 |  |  | 1125.5 |  |  | 1210.5 |  |  | 1155.5 |  |  | 1143.5 |  |  | 1207.5 |  |  | 1173 |  |  | 1127.5 |  |  | 1110.5 |  |  | 1156 |  |  | 1107.5 |  |  | 1082.5 |  |  | 1194.5 |  |  | 1167 |  |  | 1128.5 |  |  | 1126.5 |  |  | 1159.5 |  |  | 1186.5 |  |  | 1193.5 |  |  | 1213 |  |  | 1140 |  |  | 1071.5 |  |  | 1172.5 |  |  | 1129.5 |  |  | 1153.5 |  |  | 1118 |  |  | 1192 |  |  | 1103 |  |  | 1218.5 |  |  | 1127 |  |  | 1216.5 |  |  | 1219.5 |  |  | 1194 |  |  | 1121.5 |  |  | 1196.5 |  |  | 1164.5 |  |  | 1286.5 |  |  | 1104.5 |  |  | 1146 |  |  | 1168 |  |  | 1049.5 |  |  | 1146.5 |  |  | 1116 |  |  | 1068.5 |  |  | 1223.5 |  |  | 1163 |  |  | 1290.5 |  |  | 1221.5 |  |  | 1076 |  |  | 1180.5 |  |  | 1171.5 |  |  | 1131 |  |  | 1160.5 |  |  | 1092 |  |  | 1211.5 |  |  | 1232 |  |  | 1074.5 |  |  | 1147.5 |  |  | 1134.5 |  |  | 1139.5 |  |  | 1142.5 |  |  | 1106.5 |  |  | 1225 |  |  | 1162.5 |  |  | 1156.5 |  |  | 1081.5 |  |  | 1196.5 |  |  | 1096.5 |  |  | 1161 |  |  | 1126.5 |  |  | 1136 |  |  | 1149.5 |  |  | 1127.5 |  |  | 1148.5 |  |  | 1079.5 |  |  | 1139.5 |  |  | 1151.5 |  |  | 1075.5 |  |  | 1240.5 |  |  | 1127.5 |  |  | 1206 |  |  | 1177.5 |  |  | 1064 |  |  | 1131 |  |  | 1140.5 |  |  | 1052 |  |  | 1102.5 |  |  | 1118.5 |  |  | 1160.5 |  |  | 1153.5 |  |  | 1165.5 |  |  | 1199.5 |  |  | 1203.5 |  |  | 1138 |  |  | 1231 |  |  | 1091.5 |  |  | 1059.5 |  |  | 1194 |  |  | 1103.5 |  |  | 1196.5 |  |  | 1108.5 |  |  | 1068.5 |  |  | 1089.5 |  |  | 1124 |  |  | 1123.5 |  |  | 1156.5 |  |  | 1124.5 |  |  | 1122 |  |  | 1186.5 |  |  | 1160.5 |  |  | 1199.5 |  |  | 1267.5 |  |  | 1211.5 |  |  | 1109.5 |  |  | 1255.5 |  |  | 1000.5 |  |  | 1121.5 |  |  | 1130 |  |  | 1190.5 |  |  | 1145.5 |  |  | 1200.5 |  |  | 1106.5 |  |  | 1085.5 |  |  | 1072.5 |  |  | 1152.5 |  |  | 1021 |  |  | 1090.5 |  |  | 1176.5 |  |  | 1214.5 |  |  | 1078 |  |  | 1103.5 |  |  | 1115 |  |  | 1151.5 |  |  | 1148.5 |  |  | 1126.5 |  |  | 1100 |  |  | 1046.5 |  |  | 1178 |  |  | 1145 |  |  | 1185.5 |  |  | 1157 |  |  | 1157 |  |  | 1213.5 |  |  | 1235.5 |  |  | 1081.5 |  |  | 1219 |  |  | 1175.5 |  |  | 1119.5 |  |  | 1064.5 |  |  | 1230.5 |  |  | 1088.5 |  |  | 1184.5 |  |  | 1122.5 |  |  | 1175.5 |  |  | 1091 |  |  | 1253.5 |  |  | 1053 |  |  | 1072.5 |  |  | 1062.5 |  |  | 1188.5 |  |  | 1179 |  |  | 1211 |  |  | 1245 |  |  | 1130.5 |  |  | 1086 |  |  | 1213.5 |  |  | 1193.5 |  |  | 1054.5 |  |  | 1163.5 |  |  | 1106.5 |  |  | 1170.5 |  |  | 1165.5 |  |  | 1172.5 |  |  | 1216 |  |  | 1086.5 |  |  | 1076.5 |  |  | 1198.5 |  |  | 1081.5 |  |  | 1082 |  |  | 1135.5 |  |  | 1207 |  |  | 1140.5 |  |  | 1161.5 |  |  | 1164.5 |  |  | 1097.5 |  |  | 1076 |  |  | 1084.5 |  |  | 1033 |  |  | 1093.5 |  |  | 1196.5 |  |  | 1239.5 |  |  | 1188.5 |  |  | 1119.5 |  |  | 1112.5 |  |  | 1111.5 |  |  | 1207.5 |  |  | 1051.5 |  |  | 1141 |  |  | 1120.5 |  |  | 1108.5 |  |  | 1094.5 |  |  | 1164.5 |  |  | 1153.5 |  |  | 1047 |  |  | 1130 |  |  | 1140.5 |  |  | 1109 |  |  | 1245.5 |  |  | 1117.5 |  |  | 1199.5 |  |  | 1236.5 |  |  | 1123.5 |  |  | 1193.5 |  |  | 1160.5 |  |  | 1114.5 |  |  | 1155 |  |  | 1207.5 |  |  | 1228.5 |  |  | 1214.5 |  |  | 1074 |  |  | 1196.5 |  |  | 1101.5 |  |  | 1239 |  |  | 1037 |  |  | 1124.5 |  |  | 1070 |  |  | 1049 |  |  | 1042.5 |  |  | 1080 |  |  | 1238.5 |  |  | 1239.5 |  |  | 1202.5 |  |  | 1155.5 |  |  | 1107.5 |  |  | 1203.5 |  |  | 1061.5 |  |  | 1131.5 |  |  | 1097.5 |  |  | 1120.5 |  |  | 1148 |  |  | 1081 |  |  | 1141.5 |  |  | 1110.5 |  |  | 1132.5 |  |  | 1213.5 |  |  | 1078.5 |  |  | 1225.5 |  |  | 1173.5 |  |  | 1110.5 |  |  | 1224 |  |  | 1072.5 |  |  | 1053 |  |  | 1095.5 |  |  | 1309.5 |  |  | 1182.5 |  |  | 1191 |  |  | 1173.5 |  |  | 1100.5 |  |  | 1076 |  |  | 1180.5 |  |  | 1118.5 |  |  | 1204.5 |  |  | 1129.5 |  |  | 1123.5 |  |  | 1121.5 |  |  | 1099 |  |  | 1152.5 |  |  | 1082.5 |  |  | 1156.5 |  |  | 1266.5 |  |  | 1062 |  |  | 1081.5 |  |  | 1222.5 |  |  | 1156 |  |  | 1173.5 |  |  | 1180.5 |  |  | 1127 |  |  | 1189.5 |  |  | 1170.5 |  |  | 1149.5 |  |  | 1083 |  |  | 999.5 |  |  | 1165.5 |  |  | 1115 |  |  | 1099.5 |  |  | 1191.5 |  |  | 1156.5 |  |  | 1001.5 |  |  | 1249.5 |  |  | 1291.5 |  |  | 1098.5 |  |  | 1166 |  |  | 1130 |  |  | 1053.5 |  |  | 1176.5 |  |  | 1117.5 |  |  | 1156 |  |  | 1179.5 |  |  | 1141.5 |  |  | 1174.5 |  |  | 1022.5 |  |  | 1125.5 |  |  | 1158.5 |  |  | 1047.5 |  |  | 1137.5 |  |  | 1045.5 |  |  | 1206 |  |  | 1110.5 |  |  | 1123.5 |  |  | 1098.5 |  |  | 1226.5 |  |  | 1181.5 |  |  | 1102.5 |  |  | 1124.5 |  |  | 1190.5 |  |  | 1112.5 |  |  | 1161.5 |  |  | 1114.5 |  |  | 1171.5 |  |  | 1169.5 |  |  | 1214 |  |  | 1156.5 |  |  | 1161.5 |  |  | 1122 |  |  | 1187.5 |  |  | 1160.5 |  |  | 1252 |  |  | 1144.5 |  |  | 1184.5 |  |  | 1234.5 |  |  | 1249 |  |  | 1190.5 |  |  | 1198.5 |  |  | 1171.5 |  |  | 982.5 |  |  | 1160.5 |  |  | 1090 |  |  | 1138.5 |  |  | 1231 |  |  | 1163 |  |  | 1208.5 |  |  | 1178.5 |  |  | 1133.5 |  |  | 1084.5 |  |  | 1162.5 |  |  | 1163.5 |  |  | 1109 |  |  | 1140.5 |  |  | 1220 |  |  | 1088.5 |  |  | 1189 |  |  | 1161 |  |  | 1182 |  |  | 1135.5 |  |  | 1105 |  |  | 1218.5 |  |  | 1206.5 |  |  | 1218.5 |  |  | 1334.5 |  |  | 1194.5 |  |  | 1166 |  |  | 1170.5 |  |  | 1235.5 |  |  | 1332.5 |  |  | 1223 |  |  | 1168.5 |  |  | 1163.5 |  |  | 1237.5 |  |  | 1196.5 |  |  | 1116 |  |  | 1185 |  |  | 1125 |  |  | 1188.5 |  |  | 1208 |  |  | 1189 |  |  | 1218.5 |  |  | 1119.5 |  |  | 1075.5 |  |  | 1169.5 |  |  | 1205.5 |  |  | 1273.5 |  |  | 1166.5 |  |  | 1192.5 |  |  | 1090.5 |  |  | 1081 |  |  | 1162.5 |  |  | 1146 |  |  | 1235.5 |  |  | 1186.5 |  |  | 1169.5 |  |  | 1209.5 |  |  | 1184 |  |  | 1130.5 |  |  | 1149 |  |  | 1128.5 |  |  | 1184.5 |  |  | 1034 |  |  | 1147 |  |  | 1120.5 |  |  | 1160 |  |  | 1277.5 |  |  | 1028.5 |  |  | 1100.5 |  |  | 1137.5 |  |  | 1154.5 |  |  | 1173.5 |  |  | 1113.5 |  |  | 1067 |  |  | 1216.5 |  |  | 1181.5 |  |  | 1081.5 |  |  | 1181.5 |  |  | 1103.5 |  |  | 1131.5 |  |  | 1160.5 |  |  | 1165.5 |  |  | 1109.5 |  |  | 1174.5 |  |  | 1138.5 |  |  | 1101.5 |  |  | 1208 |  |  | 1043.5 |  |  | 1131.5 |  |  | 1202 |  |  | 1084.5 |  |  | 1041.5 |  |  | 1116.5 |  |  | 1120.5 |  |  | 1205 |  |  | 1226.5 |  |  | 1176.5 |  |  | 1062.5 |  |  | 1159.5 |  |  | 1093 |  |  | 1176.5 |  |  | 1181.5 |  |  | 1176.5 |  |  | 1211.5 |  |  | 1167.5 |  |  | 1075.5 |  |  | 1199.5 |  |  | 1233.5 |  |  | 1196.5 |  |  | 1143.5 |  |  | 1206.5 |  |  | 1170 |  |  | 1184.5 |  |  | 1184.5 |  |  | 1213.5 |  |  | 1154.5 |  |  | 1092.5 |  |  | 1125.5 |  |  | 1182 |  |  | 1100.5 |  |  | 1134 |  |  | 1108.5 |  |  | 1192.5 |  |  | 1121.5 |  |  | 1112 |  |  | 1125 |  |  | 1134.5 |  |  | 1179.5 |  |  | 1065.5 |  |  | 1152.5 |  |  | 1128.5 |  |  | 1122.5 |  |  | 1079.5 |  |  | 1114.5 |  |  | 1138.5 |  |  | 1188.5 |  |  | 1121.5 |  |  | 1149.5 |  |  | 1119.5 |  |  | 1158.5 |  |  | 1185.5 |  |  | 1187.5 |  |  | 1154.5 |  |  | 1167.5 |  |  | 1114.5 |  |  | 1072.5 |  |  | 1166.5 |  |  | 1180.5 |  |  | 1200 |  |  | 1285.5 |  |  | 1126.5 |  |  | 1147.5 |  |  | 1188 |  |  | 1188.5 |  |  | 1141.5 |  |  | 1187.5 |  |  | 1163.5 |  |  | 1211 |  |  | 1060.5 |  |  | 1127.5 |  |  | 1065 |  |  | 1050 |  |  | 1134 |  |  | 1115.5 |  |  | 1187.5 |  |  | 1188.5 |  |  | 1224.5 |  |  | 1130 |  |  | 1158.5 |  |  | 1146.5 |  |  | 1051 |  |  | 1135 |  |  | 1173.5 |  |  | 1154.5 |  |  | 1149 |  |  | 1168.5 |  |  | 1211 |  |  | 1066.5 |  |  | 1083.5 |  |  | 1175 |  |  | 1205.5 |  |  | 1072.5 |  |  | 1053.5 |  |  | 1227 |  |  | 1159.5 |  |  | 1138.5 |  |  | 1095.5 |  |  | 1089.5 |  |  | 1141.5 |  |  | 1265.5 |  |  | 1109.5 |  |  | 1170.5 |  |  | 1225.5 |  |  | 1151.5 |  |  | 1198 |  |  | 1093.5 |  |  | 1186.5 |  |  | 1190.5 |  |  | 1180.5 |  |  | 1102.5 |  |  | 1224.5 |  |  | 1232.5 |  |  | 1136.5 |  |  | 1207 |  |  | 1171.5 |  |  | 1163 |  |  | 1202.5 |  |  | 1264.5 |  |  | 1271.5 |  |  | 1114.5 |  |  | 1169.5 |  |  | 1134.5 |  |  | 998.5 |  |  | 1193.5 |  |  | 1190 |  |  | 1102.5 |  |  | 1091 |  |  | 1110.5 |  |  | 1041.5 |  |  | 1222.5 |  |  | 1222 |  |  | 1097.5 |  |  | 1182.5 |  |  | 1089 |  |  | 1099.5 |  |  | 1108 |  |  | 1088.5 |  |  | 1159.5 |  |  | 1105.5 |  |  | 1103 |  |  | 1160.5 |  |  | 1264.5 |  |  | 1102 |  |  | 1219.5 |  |  | 1054.5 |  |  | 1189 |  |  | 1184.5 |  |  | 1264.5 |  |  | 1164.5 |  |  | 1204.5 |  |  | 1143.5 |  |  | 1144.5 |  |  | 1084.5 |  |  | 1160.5 |  |  | 1042.5 |  |  | 1198.5 |  |  | 1235.5 |  |  | 1173 |  |  | 1198 |  |  | 1204.5 |  |  | 1184.5 |  |  | 1242
41 |  | 1210.5 |  |  | 1269.5 |  |  | 1214 |  |  | 1187.5 |  |  | 1295.5 |  |  | 1237.5 |  |  | 1267.5 |  |  | 1169.5 |  |  | 1184.5 |  |  | 1220.5 |  |  | 1159 |  |  | 1195.5 |  |  | 1278.5 |  |  | 1121.5 |  |  | 1124 |  |  | 1170.5 |  |  | 1292.5 |  |  | 1170.5 |  |  | 1304.5 |  |  | 1123.5 |  |  | 1148.5 |  |  | 1149.5 |  |  | 1188.5 |  |  | 1113.5 |  |  | 1093 |  |  | 1253.5 |  |  | 1168.5 |  |  | 1157.5 |  |  | 1159.5 |  |  | 1098 |  |  | 1187 |  |  | 1120.5 |  |  | 1137.5 |  |  | 1168.5 |  |  | 1080.5 |  |  | 1162 |  |  | 1174.5 |  |  | 1162 |  |  | 1135.5 |  |  | 1229.5 |  |  | 1101.5 |  |  | 1240.5 |  |  | 1117.5 |  |  | 1120 |  |  | 1339.5 |  |  | 1227 |  |  | 1152.5 |  |  | 1188.5 |  |  | 1212.5 |  |  | 1124.5 |  |  | 1164.5 |  |  | 1161.5 |  |  | 1166.5 |  |  | 1161.5 |  |  | 1227.5 |  |  | 1176.5 |  |  | 1087.5 |  |  | 1181 |  |  | 1262.5 |  |  | 1178.5 |  |  | 1146 |  |  | 1159.5 |  |  | 1234.5 |  |  | 1176.5 |  |  | 1142.5 |  |  | 1215 |  |  | 1216.5 |  |  | 1085 |  |  | 1173.5 |  |  | 1185.5 |  |  | 1198 |  |  | 1187.5 |  |  | 1140.5 |  |  | 1245.5 |  |  | 1232 |  |  | 1165 |  |  | 1172.5 |  |  | 1083.5 |  |  | 1073.5 |  |  | 1127.5 |  |  | 1131 |  |  | 1157.5 |  |  | 1234.5 |  |  | 1232.5 |  |  | 1236.5 |  |  | 1263.5 |  |  | 1238.5 |  |  | 1125.5 |  |  | 1137.5 |  |  | 1225.5 |  |  | 1241.5 |  |  | 1205 |  |  | 1100.5 |  |  | 1124 |  |  | 1160 |  |  | 1112 |  |  | 1230.5 |  |  | 1215.5 |  |  | 1155.5 |  |  | 1217.5 |  |  | 1157.5 |  |  | 1245 |  |  | 1251 |  |  | 1143.5 |  |  | 1141.5 |  |  | 1165.5 |  |  | 1169.5 |  |  | 1215.5 |  |  | 1246.5 |  |  | 1234.5 |  |  | 1241.5 |  |  | 1188.5 |  |  | 1224.5 |  |  | 1199.5 |  |  | 1235.5 |  |  | 1220.5 |  |  | 1182.5 |  |  | 1107.5 |  |  | 1194.5 |  |  | 1241.5 |  |  | 1226.5 |  |  | 1219.5 |  |  | 1161.5 |  |  | 1202.5 |  |  | 1211.5 |  |  | 1209 |  |  | 1138.5 |  |  | 1183.5 |  |  | 1103.5 |  |  | 1141.5 |  |  | 1287.5 |  |  | 1211 |  |  | 1096.5 |  |  | 1235.5 |  |  | 1126.5 |  |  | 1213.5 |  |  | 1134 |  |  | 1208.5 |  |  | 1243.5 |  |  | 1143 |  |  | 1210.5 |  |  | 1185 |  |  | 1164 |  |  | 1244.5 |  |  | 1223 |  |  | 1273.5 |  |  | 1145.5 |  |  | 1204.5 |  |  | 1130.5 |  |  | 1240.5 |  |  | 1207.5 |  |  | 1225.5 |  |  | 1189.5 |  |  | 1268.5 |  |  | 1204.5 |  |  | 1218 |  |  | 1106.5 |  |  | 1139 |  |  | 1113.5 |  |  | 1196.5 |  |  | 1217 |  |  | 1236.5 |  |  | 1145.5 |  |  | 1141.5 |  |  | 1176 |  |  | 1220.5 |  |  | 1141.5 |  |  | 1125.5 |  |  | 1189.5 |  |  | 1133.5 |  |  | 1175.5 |  |  | 1193 |  |  | 1140.5 |  |  | 1213.5 |  |  | 1157.5 |  |  | 1178.5 |  |  | 1232.5 |  |  | 1255.5 |  |  | 1105.5 |  |  | 1286 |  |  | 1240.5 |  |  | 1182.5 |  |  | 1283.5 |  |  | 1238.5 |  |  | 1108.5 |  |  | 1280.5 |  |  | 1208.5 |  |  | 1180.5 |  |  | 1184.5 |  |  | 1125.5 |  |  | 1170.5 |  |  | 1140.5 |  |  | 1081.5 |  |  | 1122 |  |  | 1148.5 |  |  | 1213.5 |  |  | 1140.5 |  |  | 1186.5 |  |  | 1262.5 |  |  | 1159.5 |  |  | 1217.5 |  |  | 1114.5 |  |  | 1142.5 |  |  | 1188.5 |  |  | 1172.5 |  |  | 1300.5 |  |  | 1158.5 |  |  | 1138.5 |  |  | 1246.5 |  |  | 1220.5 |  |  | 1193 |  |  | 1218.5 |  |  | 1173.5 |  |  | 1065 |  |  | 1271.5 |  |  | 1220 |  |  | 1187.5 |  |  | 1242.5 |  |  | 1284.5 |  |  | 1173.5 |  |  | 1146.5 |  |  | 1161.5 |  |  | 1139.5 |  |  | 1094.5 |  |  | 1081 |  |  | 1104.5 |  |  | 1033.5 |  |  | 1245.5 |  |  | 1156.5 |  |  | 1289 |  |  | 1132.5 |  |  | 1129.5 |  |  | 1202.5 |  |  | 1230.5 |  |  | 1236.5 |  |  | 1112.5 |  |  | 1125.5 |  |  | 1216.5 |  |  | 1183 |  |  | 1200 |  |  | 1082.5 |  |  | 1182.5 |  |  | 1221.5 |  |  | 1240 |  |  | 1239.5 |  |  | 1233.5 |  |  | 1164.5 |  |  | 1176 |  |  | 1207.5 |  |  | 1217.5 |  |  | 1175.5 |  |  | 1159.5 |  |  | 1170.5 |  |  | 1221.5 |  |  | 1237.5 |  |  | 1151.5 |  |  | 1233.5 |  |  | 1015 |  |  | 1117.5 |  |  | 1206.5 |  |  | 1162.5 |  |  | 1159.5 |  |  | 1196.5 |  |  | 1260 |  |  | 1152.5 |  |  | 1250.5 |  |  | 1188 |  |  | 1309.5 |  |  | 1204.5 |  |  | 1276 |  |  | 1203.5 |  |  | 1203.5 |  |  | 1311.5 |  |  | 1120.5 |  |  | 1237 |  |  | 1225 |  |  | 1217.5 |  |  | 1176.5 |  |  | 1227.5 |  |  | 1230.5 |  |  | 1266.5 |  |  | 1131.5 |  |  | 1153 |  |  | 1213.5 |  |  | 1203.5 |  |  | 1186 |  |  | 1122.5 |  |  | 1121.5 |  |  | 1189 |  |  | 1183.5 |  |  | 1156.5 |  |  | 1137.5 |  |  | 1182 |  |  | 1222.5 |  |  | 1145 |  |  | 1234.5 |  |  | 1151.5 |  |  | 1185.5 |  |  | 1162 |  |  | 1133.5 |  |  | 1262.5 |  |  | 1110.5 |  |  | 1189 |  |  | 1098.5 |  |  | 1129.5 |  |  | 1244.5 |  |  | 1258.5 |  |  | 1153.5 |  |  | 1143 |  |  | 1160.5 |  |  | 1308.5 |  |  | 1266.5 |  |  | 1156 |  |  | 1185 |  |  | 1268.5 |  |  | 1221.5 |  |  | 1117.5 |  |  | 1221.5 |  |  | 1248.5 |  |  | 1208.5 |  |  | 1157.5 |  |  | 1209.5 |  |  | 1106.5 |  |  | 1196.5 |  |  | 1184 |  |  | 1216.5 |  |  | 1282.5 |  |  | 1321.5 |  |  | 1320.5 |  |  | 1217 |  |  | 1285.5 |  |  | 1230.5 |  |  | 1211.5 |  |  | 1037.5 |  |  | 1207.5 |  |  | 1166 |  |  | 1149 |  |  | 1089 |  |  | 1180 |  |  | 1168.5 |  |  | 1200 |  |  | 1199.5 |  |  | 1147 |  |  | 1166.5 |  |  | 1251.5 |  |  | 1196.5 |  |  | 1184.5 |  |  | 1149.5 |  |  | 1162 |  |  | 1205.5 |  |  | 1263.5 |  |  | 1097.5 |  |  | 1246 |  |  | 1202.5 |  |  | 1185.5 |  |  | 1145.5 |  |  | 1270 |  |  | 1141.5 |  |  | 1060.5 |  |  | 1163.5 |  |  | 1136.5 |  |  | 1153.5 |  |  | 1128.5 |  |  | 1243.5 |  |  | 1148.5 |  |  | 1222.5 |  |  | 1066.5 |  |  | 1101 |  |  | 1210.5 |  |  | 1203.5 |  |  | 1176.5 |  |  | 1184.5 |  |  | 1312.5 |  |  | 1195 |  |  | 1159.5 |  |  | 1229 |  |  | 1120 |  |  | 1167.5 |  |  | 1269.5 |  |  | 1162.5 |  |  | 1152 |  |  | 1239.5 |  |  | 1220.5 |  |  | 1203.5 |  |  | 1086 |  |  | 1167.5 |  |  | 1096.5 |  |  | 1267.5 |  |  | 1105.5 |  |  | 1134.5 |  |  | 1169 |  |  | 1108.5 |  |  | 1166 |  |  | 1171.5 |  |  | 1195.5 |  |  | 1184.5 |  |  | 1281 |  |  | 1116.5 |  |  | 1240 |  |  | 1211 |  |  | 1175.5 |  |  | 1167.5 |  |  | 1195.5 |  |  | 1289.5 |  |  | 1231 |  |  | 1197.5 |  |  | 1165.5 |  |  | 1126.5 |  |  | 1204 |  |  | 1227.5 |  |  | 1122.5 |  |  | 1105.5 |  |  | 1156.5 |  |  | 1245 |  |  | 1116.5 |  |  | 1172.5 |  |  | 1239.5 |  |  | 1184.5 |  |  | 1172.5 |  |  | 1222.5 |  |  | 1212 |  |  | 1166.5 |  |  | 1131.5 |  |  | 1203 |  |  | 1136.5 |  |  | 1121.5 |  |  | 1218.5 |  |  | 1188 |  |  | 1167.5 |  |  | 1150.5 |  |  | 1185.5 |  |  | 1225.5 |  |  | 1222.5 |  |  | 1252 |  |  | 1179 |  |  | 1110.5 |  |  | 1211.5 |  |  | 1168.5 |  |  | 1179.5 |  |  | 1157 |  |  | 1221 |  |  | 1150 |  |  | 1257.5 |  |  | 1153 |  |  | 1237.5 |  |  | 1266.5 |  |  | 1215 |  |  | 1168.5 |  |  | 1235.5 |  |  | 1193.5 |  |  | 1312.5 |  |  | 1133.5 |  |  | 1175 |  |  | 1183 |  |  | 1078.5 |  |  | 1172.5 |  |  | 1142 |  |  | 1097.5 |  |  | 1249.5 |  |  | 1184 |  |  | 1305.5 |  |  | 1236.5 |  |  | 1115 |  |  | 1201.5 |  |  | 1200.5 |  |  | 1157 |  |  | 1199.5 |  |  | 1121 |  |  | 1240.5 |  |  | 1258 |  |  | 1113.5 |  |  | 1173.5 |  |  | 1160.5 |  |  | 1163.5 |  |  | 1171.5 |  |  | 1135.5 |  |  | 1264 |  |  | 1183.5 |  |  | 1203.5 |  |  | 1120.5 |  |  | 1222.5 |  |  | 1117.5 |  |  | 1176 |  |  | 1155.5 |  |  | 1162 |  |  | 1196.5 |  |  | 1166.5 |  |  | 1187.5 |  |  | 1094.5 |  |  | 1178.5 |  |  | 1190.5 |  |  | 1114.5 |  |  | 1264.5 |  |  | 1153.5 |  |  | 1232 |  |  | 1216.5 |  |  | 1079 |  |  | 1170 |  |  | 1179.5 |  |  | 1091 |  |  | 1128.5 |  |  | 1157.5 |  |  | 1189.5 |  |  | 1174.5 |  |  | 1191.5 |  |  | 1238.5 |  |  | 1242.5 |  |  | 1164 |  |  | 1246 |  |  | 1120.5 |  |  | 1088.5 |  |  | 1241 |  |  | 1129.5 |  |  | 1225.5 |  |  | 1147.5 |  |  | 1097.5 |  |  | 1128.5 |  |  | 1163 |  |  | 1170.5 |  |  | 1203.5 |  |  | 1148.5 |  |  | 1146 |  |  | 1225.5 |  |  | 1207.5 |  |  | 1228.5 |  |  | 1291.5 |  |  | 1237.5 |  |  | 1156.5 |  |  | 1284.5 |  |  | 1024.5 |  |  | 1147.5 |  |  | 1145 |  |  | 1237.5 |  |  | 1174.5 |  |  | 1229.5 |  |  | 1153.5 |  |  | 1100.5 |  |  | 1119.5 |  |  | 1173.5 |  |  | 1068 |  |  | 1114.5 |  |  | 1223.5 |  |  | 1240.5 |  |  | 1093 |  |  | 1142.5 |  |  | 1136 |  |  | 1180.5 |  |  | 1177.5 |  |  | 1150.5 |  |  | 1126 |  |  | 1072.5 |  |  | 1217 |  |  | 1184 |  |  | 1232.5 |  |  | 1172 |  |  | 1196 |  |  | 1252.5 |  |  | 1274.5 |  |  | 1105.5 |  |  | 1243 |  |  | 1214.5 |  |  | 1158.5 |  |  | 1093.5 |  |  | 1269.5 |  |  | 1117.5 |  |  | 1210.5 |  |  | 1161.5 |  |  | 1204.5 |  |  | 1106 |  |  | 1292.5 |  |  | 1082 |  |  | 1119.5 |  |  | 1101.5 |  |  | 1235.5 |  |  | 1208 |  |  | 1240 |  |  | 1274 |  |  | 1156.5 |  |  | 1125 |  |  | 1234.5 |  |  | 1240.5 |  |  | 1101.5 |  |  | 1189.5 |  |  | 1153.5 |  |  | 1199.5 |  |  | 1189.5 |  |  | 1187.5 |  |  | 1237 |  |  | 1107.5 |  |  | 1102.5 |  |  | 1213.5 |  |  | 1107.5 |  |  | 1111 |  |  | 1174.5 |  |  | 1222 |  |  | 1169.5 |  |  | 1176.5 |  |  | 1203.5 |  |  | 1112.5 |  |  | 1100 |  |  | 1123.5 |  |  | 1072 |  |  | 1132.5 |  |  | 1217.5 |  |  | 1286.5 |  |  | 1235.5 |  |  | 1134.5 |  |  | 1136.5 |  |  | 1135.5 |  |  | 1254.5 |  |  | 1098.5 |  |  | 1165 |  |  | 1144.5 |  |  | 1147.5 |  |  | 1109.5 |  |  | 1185.5 |  |  | 1200.5 |  |  | 1086 |  |  | 1151 |  |  | 1166.5 |  |  | 1138 |  |  | 1292.5 |  |  | 1143.5 |  |  | 1225.5 |  |  | 1275.5 |  |  | 1152.5 |  |  | 1240.5 |  |  | 1181.5 |  |  | 1153.5 |  |  | 1170 |  |  | 1228.5 |  |  | 1275.5 |  |  | 1253.5 |  |  | 1095 |  |  | 1220.5 |  |  | 1116.5 |  |  | 1278 |  |  | 1076 |  |  | 1163.5 |  |  | 1099 |  |  | 1064 |  |  | 1089.5 |  |  | 1119 |  |  | 1285.5 |  |  | 1254.5 |  |  | 1223.5 |  |  | 1184.5 |  |  | 1122.5 |  |  | 1232.5 |  |  | 1087.5 |  |  | 1170.5 |  |  | 1144.5 |  |  | 1159.5 |  |  | 1163 |  |  | 1120 |  |  | 1165.5 |  |  | 1139.5 |  |  | 1171.5 |  |  | 1239.5 |  |  | 1125.5 |  |  | 1240.5 |  |  | 1212.5 |  |  | 1149.5 |  |  | 1271 |  |  | 1101.5 |  |  | 1068 |  |  | 1134.5 |  |  | 1356.5 |  |  | 1221.5 |  |  | 1212 |  |  | 1212.5 |  |  | 1124.5 |  |  | 1115 |  |  | 1195.5 |  |  | 1157.5 |  |  | 1243.5 |  |  | 1176.5 |  |  | 1162.5 |  |  | 1145.5 |  |  | 1138 |  |  | 1167.5 |  |  | 1111.5 |  |  | 1182.5 |  |  | 1305.5 |  |  | 1077 |  |  | 1120.5 |  |  | 1269.5 |  |  | 1203 |  |  | 1194.5 |  |  | 1219.5 |  |  | 1153 |  |  | 1210.5 |  |  | 1209.5 |  |  | 1164.5 |  |  | 1109 |  |  | 1020.5 |  |  | 1189.5 |  |  | 1139 |  |  | 1138.5 |  |  | 1230.5 |  |  | 1203.5 |  |  | 1048.5 |  |  | 1270.5 |  |  | 1312.5 |  |  | 1124.5 |  |  | 1181 |  |  | 1145 |  |  | 1068.5 |  |  | 1200.5 |  |  | 1156.5 |  |  | 1177 |  |  | 1203.5 |  |  | 1188.5 |  |  | 1213.5 |  |  | 1046.5 |  |  | 1146.5 |  |  | 1173.5 |  |  | 1062.5 |  |  | 1166.5 |  |  | 1084.5 |  |  | 1230 |  |  | 1134.5 |  |  | 1138.5 |  |  | 1137.5 |  |  | 1265.5 |  |  | 1228.5 |  |  | 1128.5 |  |  | 1153.5 |  |  | 1205.5 |  |  | 1133.5 |  |  | 1208.5 |  |  | 1143.5 |  |  | 1186.5 |  |  | 1195.5 |  |  | 1261 |  |  | 1195.5 |  |  | 1200.5 |  |  | 1137 |  |  | 1216.5 |  |  | 1199.5 |  |  | 1278 |  |  | 1183.5 |  |  | 1223.5 |  |  | 1263.5 |  |  | 1278 |  |  | 1205.5 |  |  | 1237.5 |  |  | 1192.5 |  |  | 1021.5 |  |  | 1175.5 |  |  | 1114 |  |  | 1177.5 |  |  | 1278 |  |  | 1202 |  |  | 1255.5 |  |  | 1193.5 |  |  | 1180.5 |  |  | 1108.5 |  |  | 1183.5 |  |  | 1210.5 |  |  | 1148 |  |  | 1155.5 |  |  | 1235 |  |  | 1109.5 |  |  | 1215 |  |  | 1200 |  |  | 1221 |  |  | 1159.5 |  |  | 1144 |  |  | 1257.5 |  |  | 1227.5 |  |  | 1257.5 |  |  | 1360.5 |  |  | 1209.5 |  |  | 1213 |  |  | 1191.5 |  |  | 1264.5 |  |  | 1371.5 |  |  | 1270 |  |  | 1207.5 |  |  | 1184.5 |  |  | 1276.5 |  |  | 1220.5 |  |  | 1163 |  |  | 1232 |  |  | 1172 |  |  | 1214.5 |  |  | 1255 |  |  | 1228 |  |  | 1244.5 |  |  | 1140.5 |  |  | 1096.5 |  |  | 1193.5 |  |  | 1244.5 |  |  | 1312.5 |  |  | 1213.5 |  |  | 1207.5 |  |  | 1114.5 |  |  | 1107 |  |  | 1201.5 |  |  | 1175 |  |  | 1256.5 |  |  | 1212.5 |  |  | 1208.5 |  |  | 1238.5 |  |  | 1223 |  |  | 1169.5 |  |  | 1175 |  |  | 1149.5 |  |  | 1210.5 |  |  | 1049 |  |  | 1176 |  |  | 1159.5 |  |  | 1184 |  |  | 1303.5 |  |  | 1067.5 |  |  | 1147.5 |  |  | 1176.5 |  |  | 1180.5 |  |  | 1220.5 |  |  | 1142.5 |  |  | 1096 |  |  | 1231.5 |  |  | 1196.5 |  |  | 1096.5 |  |  | 1196.5 |  |  | 1127.5 |  |  | 1157.5 |  |  | 1199.5 |  |  | 1194.5 |  |  | 1148.5 |  |  | 1213.5 |  |  | 1159.5 |  |  | 1125.5 |  |  | 1223 |  |  | 1067.5 |  |  | 1146.5 |  |  | 1231 |  |  | 1108.5 |  |  | 1070.5 |  |  | 1142.5 |  |  | 1149.5 |  |  | 1244 |  |  | 1265.5 |  |  | 1223.5 |  |  | 1083.5 |  |  | 1198.5 |  |  | 1140 |  |  | 1215.5 |  |  | 1220.5 |  |  | 1205.5 |  |  | 1258.5 |  |  | 1193.5 |  |  | 1090.5 |  |  | 1238.5 |  |  | 1254.5 |  |  | 1220.5 |  |  | 1158.5 |  |  | 1221.5 |  |  | 1209 |  |  | 1208.5 |  |  | 1208.5 |  |  | 1234.5 |  |  | 1175.5 |  |  | 1121.5 |  |  | 1164.5 |  |  | 1206 |  |  | 1139.5 |  |  | 1158 |  |  | 1132.5 |  |  | 1221.5 |  |  | 1142.5 |  |  | 1127 |  |  | 1151 |  |  | 1155.5 |  |  | 1200.5 |  |  | 1089.5 |  |  | 1199.5 |  |  | 1167.5 |  |  | 1161.5 |  |  | 1105.5 |  |  | 1129.5 |  |  | 1167.5 |  |  | 1227.5 |  |  | 1136.5 |  |  | 1173.5 |  |  | 1148.5 |  |  | 1182.5 |  |  | 1200.5 |  |  | 1208.5 |  |  | 1183.5 |  |  | 1206.5 |  |  | 1153.5 |  |  | 1111.5 |  |  | 1213.5 |  |  | 1195.5 |  |  | 1247 |  |  | 1309.5 |  |  | 1173.5 |  |  | 1171.5 |  |  | 1217 |  |  | 1212.5 |  |  | 1170.5 |  |  | 1226.5 |  |  | 1202.5 |  |  | 1258 |  |  | 1086.5 |  |  | 1153.5 |  |  | 1094 |  |  | 1097 |  |  | 1149 |  |  | 1136.5 |  |  | 1208.5 |  |  | 1203.5 |  |  | 1263.5 |  |  | 1177 |  |  | 1184.5 |  |  | 1185.5 |  |  | 1066 |  |  | 1150 |  |  | 1202.5 |  |  | 1175.5 |  |  | 1188 |  |  | 1194.5 |  |  | 1237 |  |  | 1081.5 |  |  | 1112.5 |  |  | 1204 |  |  | 1234.5 |  |  | 1093.5 |  |  | 1092.5 |  |  | 1248 |  |  | 1188.5 |  |  | 1164.5 |  |  | 1116.5 |  |  | 1136.5 |  |  | 1170.5 |  |  | 1312.5 |  |  | 1138.5 |  |  | 1199.5 |  |  | 1249.5 |  |  | 1172.5 |  |  | 1219 |  |  | 1132.5 |  |  | 1233.5 |  |  | 1229.5 |  |  | 1206.5 |  |  | 1126.5 |  |  | 1263.5 |  |  | 1253.5 |  |  | 1157.5 |  |  | 1231 |  |  | 1192.5 |  |  | 1178 |  |  | 1223.5 |  |  | 1303.5 |  |  | 1310.5 |  |  | 1153.5 |  |  | 1190.5 |  |  | 1181.5 |  |  | 1037.5 |  |  | 1232.5 |  |  | 1229 |  |  | 1123.5 |  |  | 1120 |  |  | 1131.5 |  |  | 1080.5 |  |  | 1246.5 |  |  | 1237 |  |  | 1126.5 |  |  | 1197.5 |  |  | 1136 |  |  | 1120.5 |  |  | 1147 |  |  | 1127.5 |  |  | 1180.5 |  |  | 1120.5 |  |  | 1142 |  |  | 1199.5 |  |  | 1290.5 |  |  | 1141 |  |  | 1240.5 |  |  | 1080.5 |  |  | 1228 |  |  | 1231.5 |  |  | 1293.5 |  |  | 1211.5 |  |  | 1230.5 |  |  | 1167.5 |  |  | 1183.5 |  |  | 1131.5 |  |  | 1175.5 |  |  | 1081.5 |  |  | 1222.5 |  |  | 1274.5 |  |  | 1212 |  |  | 1245 |  |  | 1225.5 |  |  | 1223.5 |  |  | 1268
42 |  | 1231.5 |  |  | 1316.5 |  |  | 1238 |  |  | 1211.5 |  |  | 1321.5 |  |  | 1261.5 |  |  | 1314.5 |  |  | 1216.5 |  |  | 1223.5 |  |  | 1235.5 |  |  | 1206 |  |  | 1216.5 |  |  | 1317.5 |  |  | 1145.5 |  |  | 1148 |  |  | 1209.5 |  |  | 1339.5 |  |  | 1217.5 |  |  | 1343.5 |  |  | 1149.5 |  |  | 1187.5 |  |  | 1178.5 |  |  | 1209.5 |  |  | 1134.5 |  |  | 1108 |  |  | 1279.5 |  |  | 1207.5 |  |  | 1196.5 |  |  | 1206.5 |  |  | 1137 |  |  | 1234 |  |  | 1159.5 |  |  | 1152.5 |  |  | 1207.5 |  |  | 1119.5 |  |  | 1201 |  |  | 1189.5 |  |  | 1177 |  |  | 1159.5 |  |  | 1244.5 |  |  | 1122.5 |  |  | 1255.5 |  |  | 1143.5 |  |  | 1146 |  |  | 1378.5 |  |  | 1253 |  |  | 1191.5 |  |  | 1217.5 |  |  | 1238.5 |  |  | 1163.5 |  |  | 1190.5 |  |  | 1185.5 |  |  | 1205.5 |  |  | 1200.5 |  |  | 1253.5 |  |  | 1200.5 |  |  | 1126.5 |  |  | 1205 |  |  | 1301.5 |  |  | 1207.5 |  |  | 1172 |  |  | 1174.5 |  |  | 1281.5 |  |  | 1202.5 |  |  | 1168.5 |  |  | 1236 |  |  | 1255.5 |  |  | 1124 |  |  | 1188.5 |  |  | 1232.5 |  |  | 1237 |  |  | 1234.5 |  |  | 1179.5 |  |  | 1284.5 |  |  | 1279 |  |  | 1212 |  |  | 1211.5 |  |  | 1104.5 |  |  | 1120.5 |  |  | 1153.5 |  |  | 1170 |  |  | 1196.5 |  |  | 1249.5 |  |  | 1271.5 |  |  | 1275.5 |  |  | 1287.5 |  |  | 1264.5 |  |  | 1140.5 |  |  | 1176.5 |  |  | 1254.5 |  |  | 1280.5 |  |  | 1229 |  |  | 1126.5 |  |  | 1139 |  |  | 1181 |  |  | 1133 |  |  | 1269.5 |  |  | 1241.5 |  |  | 1194.5 |  |  | 1238.5 |  |  | 1204.5 |  |  | 1284 |  |  | 1275 |  |  | 1158.5 |  |  | 1167.5 |  |  | 1186.5 |  |  | 1193.5 |  |  | 1262.5 |  |  | 1272.5 |  |  | 1260.5 |  |  | 1288.5 |  |  | 1227.5 |  |  | 1263.5 |  |  | 1238.5 |  |  | 1250.5 |  |  | 1235.5 |  |  | 1203.5 |  |  | 1133.5 |  |  | 1220.5 |  |  | 1288.5 |  |  | 1273.5 |  |  | 1248.5 |  |  | 1185.5 |  |  | 1228.5 |  |  | 1258.5 |  |  | 1238 |  |  | 1159.5 |  |  | 1204.5 |  |  | 1124.5 |  |  | 1188.5 |  |  | 1308.5 |  |  | 1232 |  |  | 1111.5 |  |  | 1259.5 |  |  | 1165.5 |  |  | 1234.5 |  |  | 1155 |  |  | 1247.5 |  |  | 1282.5 |  |  | 1182 |  |  | 1225.5 |  |  | 1209 |  |  | 1193 |  |  | 1291.5 |  |  | 1252 |  |  | 1299.5 |  |  | 1192.5 |  |  | 1251.5 |  |  | 1154.5 |  |  | 1287.5 |  |  | 1246.5 |  |  | 1246.5 |  |  | 1228.5 |  |  | 1315.5 |  |  | 1243.5 |  |  | 1257 |  |  | 1145.5 |  |  | 1168 |  |  | 1152.5 |  |  | 1243.5 |  |  | 1264 |  |  | 1251.5 |  |  | 1160.5 |  |  | 1170.5 |  |  | 1205 |  |  | 1259.5 |  |  | 1170.5 |  |  | 1172.5 |  |  | 1236.5 |  |  | 1159.5 |  |  | 1222.5 |  |  | 1217 |  |  | 1169.5 |  |  | 1239.5 |  |  | 1204.5 |  |  | 1193.5 |  |  | 1258.5 |  |  | 1276.5 |  |  | 1126.5 |  |  | 1325 |  |  | 1264.5 |  |  | 1203.5 |  |  | 1312.5 |  |  | 1277.5 |  |  | 1147.5 |  |  | 1319.5 |  |  | 1255.5 |  |  | 1201.5 |  |  | 1231.5 |  |  | 1172.5 |  |  | 1209.5 |  |  | 1155.5 |  |  | 1096.5 |  |  | 1146 |  |  | 1187.5 |  |  | 1242.5 |  |  | 1179.5 |  |  | 1210.5 |  |  | 1309.5 |  |  | 1188.5 |  |  | 1232.5 |  |  | 1161.5 |  |  | 1181.5 |  |  | 1203.5 |  |  | 1196.5 |  |  | 1339.5 |  |  | 1197.5 |  |  | 1177.5 |  |  | 1275.5 |  |  | 1235.5 |  |  | 1217 |  |  | 1244.5 |  |  | 1194.5 |  |  | 1094 |  |  | 1310.5 |  |  | 1267 |  |  | 1216.5 |  |  | 1268.5 |  |  | 1331.5 |  |  | 1199.5 |  |  | 1185.5 |  |  | 1190.5 |  |  | 1165.5 |  |  | 1109.5 |  |  | 1128 |  |  | 1119.5 |  |  | 1059.5 |  |  | 1269.5 |  |  | 1171.5 |  |  | 1315 |  |  | 1156.5 |  |  | 1158.5 |  |  | 1226.5 |  |  | 1277.5 |  |  | 1275.5 |  |  | 1127.5 |  |  | 1172.5 |  |  | 1255.5 |  |  | 1207 |  |  | 1239 |  |  | 1129.5 |  |  | 1208.5 |  |  | 1247.5 |  |  | 1269 |  |  | 1260.5 |  |  | 1248.5 |  |  | 1193.5 |  |  | 1197 |  |  | 1231.5 |  |  | 1238.5 |  |  | 1199.5 |  |  | 1185.5 |  |  | 1196.5 |  |  | 1260.5 |  |  | 1276.5 |  |  | 1177.5 |  |  | 1272.5 |  |  | 1039 |  |  | 1141.5 |  |  | 1253.5 |  |  | 1188.5 |  |  | 1180.5 |  |  | 1220.5 |  |  | 1299 |  |  | 1199.5 |  |  | 1271.5 |  |  | 1227 |  |  | 1324.5 |  |  | 1228.5 |  |  | 1323 |  |  | 1229.5 |  |  | 1229.5 |  |  | 1350.5 |  |  | 1144.5 |  |  | 1252 |  |  | 1264 |  |  | 1243.5 |  |  | 1191.5 |  |  | 1248.5 |  |  | 1245.5 |  |  | 1305.5 |  |  | 1170.5 |  |  | 1174 |  |  | 1234.5 |  |  | 1242.5 |  |  | 1225 |  |  | 1137.5 |  |  | 1142.5 |  |  | 1204 |  |  | 1198.5 |  |  | 1177.5 |  |  | 1184.5 |  |  | 1208 |  |  | 1246.5 |  |  | 1160 |  |  | 1260.5 |  |  | 1180.5 |  |  | 1209.5 |  |  | 1177 |  |  | 1162.5 |  |  | 1286.5 |  |  | 1131.5 |  |  | 1210 |  |  | 1127.5 |  |  | 1168.5 |  |  | 1265.5 |  |  | 1297.5 |  |  | 1192.5 |  |  | 1182 |  |  | 1184.5 |  |  | 1334.5 |  |  | 1305.5 |  |  | 1180 |  |  | 1214 |  |  | 1283.5 |  |  | 1268.5 |  |  | 1146.5 |  |  | 1247.5 |  |  | 1274.5 |  |  | 1247.5 |  |  | 1196.5 |  |  | 1248.5 |  |  | 1135.5 |  |  | 1235.5 |  |  | 1199 |  |  | 1263.5 |  |  | 1321.5 |  |  | 1360.5 |  |  | 1335.5 |  |  | 1243 |  |  | 1306.5 |  |  | 1269.5 |  |  | 1235.5 |  |  | 1066.5 |  |  | 1246.5 |  |  | 1190 |  |  | 1175 |  |  | 1113 |  |  | 1227 |  |  | 1192.5 |  |  | 1226 |  |  | 1228.5 |  |  | 1162 |  |  | 1205.5 |  |  | 1290.5 |  |  | 1235.5 |  |  | 1231.5 |  |  | 1188.5 |  |  | 1201 |  |  | 1220.5 |  |  | 1289.5 |  |  | 1136.5 |  |  | 1285 |  |  | 1226.5 |  |  | 1206.5 |  |  | 1174.5 |  |  | 1285 |  |  | 1180.5 |  |  | 1075.5 |  |  | 1210.5 |  |  | 1175.5 |  |  | 1192.5 |  |  | 1167.5 |  |  | 1264.5 |  |  | 1163.5 |  |  | 1269.5 |  |  | 1113.5 |  |  | 1116 |  |  | 1239.5 |  |  | 1227.5 |  |  | 1223.5 |  |  | 1210.5 |  |  | 1336.5 |  |  | 1234 |  |  | 1183.5 |  |  | 1268 |  |  | 1159 |  |  | 1193.5 |  |  | 1290.5 |  |  | 1177.5 |  |  | 1191 |  |  | 1268.5 |  |  | 1244.5 |  |  | 1227.5 |  |  | 1107 |  |  | 1196.5 |  |  | 1120.5 |  |  | 1291.5 |  |  | 1126.5 |  |  | 1163.5 |  |  | 1195 |  |  | 1147.5 |  |  | 1205 |  |  | 1195.5 |  |  | 1242.5 |  |  | 1223.5 |  |  | 1305 |  |  | 1155.5 |  |  | 1269 |  |  | 1250 |  |  | 1190.5 |  |  | 1182.5 |  |  | 1221.5 |  |  | 1318.5 |  |  | 1270 |  |  | 1223.5 |  |  | 1189.5 |  |  | 1150.5 |  |  | 1251 |  |  | 1266.5 |  |  | 1161.5 |  |  | 1152.5 |  |  | 1185.5 |  |  | 1284 |  |  | 1142.5 |  |  | 1211.5 |  |  | 1254.5 |  |  | 1231.5 |  |  | 1187.5 |  |  | 1269.5 |  |  | 1233 |  |  | 1187.5 |  |  | 1152.5 |  |  | 1224 |  |  | 1160.5 |  |  | 1142.5 |  |  | 1239.5 |  |  | 1212 |  |  | 1188.5 |  |  | 1174.5 |  |  | 1209.5 |  |  | 1246.5 |  |  | 1261.5 |  |  | 1291 |  |  | 1208 |  |  | 1134.5 |  |  | 1240.5 |  |  | 1194.5 |  |  | 1194.5 |  |  | 1186 |  |  | 1247 |  |  | 1176 |  |  | 1283.5 |  |  | 1179 |  |  | 1252.5 |  |  | 1305.5 |  |  | 1239 |  |  | 1192.5 |  |  | 1250.5 |  |  | 1217.5 |  |  | 1341.5 |  |  | 1172.5 |  |  | 1201 |  |  | 1198 |  |  | 1117.5 |  |  | 1219.5 |  |  | 1171 |  |  | 1121.5 |  |  | 1264.5 |  |  | 1205 |  |  | 1326.5 |  |  | 1260.5 |  |  | 1141 |  |  | 1240.5 |  |  | 1239.5 |  |  | 1181 |  |  | 1246.5 |  |  | 1168 |  |  | 1279.5 |  |  | 1297 |  |  | 1152.5 |  |  | 1212.5 |  |  | 1181.5 |  |  | 1178.5 |  |  | 1210.5 |  |  | 1159.5 |  |  | 1303 |  |  | 1212.5 |  |  | 1242.5 |  |  | 1135.5 |  |  | 1243.5 |  |  | 1156.5 |  |  | 1200 |  |  | 1202.5 |  |  | 1183 |  |  | 1217.5 |  |  | 1190.5 |  |  | 1208.5 |  |  | 1133.5 |  |  | 1217.5 |  |  | 1237.5 |  |  | 1153.5 |  |  | 1288.5 |  |  | 1182.5 |  |  | 1279 |  |  | 1231.5 |  |  | 1094 |  |  | 1199 |  |  | 1200.5 |  |  | 1117 |  |  | 1154.5 |  |  | 1172.5 |  |  | 1215.5 |  |  | 1195.5 |  |  | 1230.5 |  |  | 1277.5 |  |  | 1271.5 |  |  | 1211 |  |  | 1272 |  |  | 1141.5 |  |  | 1114.5 |  |  | 1262 |  |  | 1155.5 |  |  | 1249.5 |  |  | 1176.5 |  |  | 1136.5 |  |  | 1175.5 |  |  | 1202 |  |  | 1217.5 |  |  | 1242.5 |  |  | 1169.5 |  |  | 1170 |  |  | 1264.5 |  |  | 1246.5 |  |  | 1252.5 |  |  | 1320.5 |  |  | 1261.5 |  |  | 1195.5 |  |  | 1313.5 |  |  | 1039.5 |  |  | 1176.5 |  |  | 1184 |  |  | 1261.5 |  |  | 1213.5 |  |  | 1255.5 |  |  | 1182.5 |  |  | 1121.5 |  |  | 1158.5 |  |  | 1212.5 |  |  | 1089 |  |  | 1138.5 |  |  | 1244.5 |  |  | 1279.5 |  |  | 1132 |  |  | 1181.5 |  |  | 1157 |  |  | 1219.5 |  |  | 1216.5 |  |  | 1179.5 |  |  | 1165 |  |  | 1111.5 |  |  | 1256 |  |  | 1223 |  |  | 1261.5 |  |  | 1201 |  |  | 1217 |  |  | 1276.5 |  |  | 1295.5 |  |  | 1144.5 |  |  | 1269 |  |  | 1229.5 |  |  | 1184.5 |  |  | 1108.5 |  |  | 1284.5 |  |  | 1156.5 |  |  | 1225.5 |  |  | 1190.5 |  |  | 1225.5 |  |  | 1145 |  |  | 1316.5 |  |  | 1103 |  |  | 1166.5 |  |  | 1122.5 |  |  | 1274.5 |  |  | 1247 |  |  | 1287 |  |  | 1298 |  |  | 1185.5 |  |  | 1164 |  |  | 1273.5 |  |  | 1279.5 |  |  | 1140.5 |  |  | 1228.5 |  |  | 1182.5 |  |  | 1238.5 |  |  | 1213.5 |  |  | 1226.5 |  |  | 1284 |  |  | 1128.5 |  |  | 1141.5 |  |  | 1234.5 |  |  | 1146.5 |  |  | 1126 |  |  | 1213.5 |  |  | 1248 |  |  | 1193.5 |  |  | 1191.5 |  |  | 1218.5 |  |  | 1151.5 |  |  | 1121 |  |  | 1170.5 |  |  | 1111 |  |  | 1147.5 |  |  | 1232.5 |  |  | 1307.5 |  |  | 1274.5 |  |  | 1181.5 |  |  | 1165.5 |  |  | 1156.5 |  |  | 1301.5 |  |  | 1137.5 |  |  | 1180 |  |  | 1170.5 |  |  | 1186.5 |  |  | 1148.5 |  |  | 1200.5 |  |  | 1239.5 |  |  | 1125 |  |  | 1177 |  |  | 1192.5 |  |  | 1162 |  |  | 1331.5 |  |  | 1190.5 |  |  | 1249.5 |  |  | 1314.5 |  |  | 1173.5 |  |  | 1279.5 |  |  | 1220.5 |  |  | 1192.5 |  |  | 1199 |  |  | 1267.5 |  |  | 1322.5 |  |  | 1300.5 |  |  | 1124 |  |  | 1235.5 |  |  | 1163.5 |  |  | 1302 |  |  | 1097 |  |  | 1202.5 |  |  | 1138 |  |  | 1090 |  |  | 1136.5 |  |  | 1158 |  |  | 1314.5 |  |  | 1275.5 |  |  | 1238.5 |  |  | 1199.5 |  |  | 1151.5 |  |  | 1253.5 |  |  | 1113.5 |  |  | 1196.5 |  |  | 1183.5 |  |  | 1206.5 |  |  | 1202 |  |  | 1146 |  |  | 1204.5 |  |  | 1178.5 |  |  | 1210.5 |  |  | 1278.5 |  |  | 1140.5 |  |  | 1255.5 |  |  | 1259.5 |  |  | 1196.5 |  |  | 1297 |  |  | 1116.5 |  |  | 1107 |  |  | 1158.5 |  |  | 1395.5 |  |  | 1260.5 |  |  | 1259 |  |  | 1251.5 |  |  | 1145.5 |  |  | 1136 |  |  | 1234.5 |  |  | 1178.5 |  |  | 1282.5 |  |  | 1191.5 |  |  | 1191.5 |  |  | 1184.5 |  |  | 1162 |  |  | 1191.5 |  |  | 1150.5 |  |  | 1206.5 |  |  | 1334.5 |  |  | 1116 |  |  | 1141.5 |  |  | 1316.5 |  |  | 1218 |  |  | 1220.5 |  |  | 1234.5 |  |  | 1177 |  |  | 1239.5 |  |  | 1256.5 |  |  | 1203.5 |  |  | 1133 |  |  | 1044.5 |  |  | 1236.5 |  |  | 1160 |  |  | 1185.5 |  |  | 1277.5 |  |  | 1218.5 |  |  | 1063.5 |  |  | 1285.5 |  |  | 1359.5 |  |  | 1148.5 |  |  | 1207 |  |  | 1160 |  |  | 1092.5 |  |  | 1215.5 |  |  | 1185.5 |  |  | 1198 |  |  | 1250.5 |  |  | 1214.5 |  |  | 1228.5 |  |  | 1067.5 |  |  | 1193.5 |  |  | 1188.5 |  |  | 1101.5 |  |  | 1195.5 |  |  | 1108.5 |  |  | 1269 |  |  | 1181.5 |  |  | 1185.5 |  |  | 1184.5 |  |  | 1304.5 |  |  | 1249.5 |  |  | 1167.5 |  |  | 1192.5 |  |  | 1231.5 |  |  | 1162.5 |  |  | 1255.5 |  |  | 1190.5 |  |  | 1210.5 |  |  | 1234.5 |  |  | 1300 |  |  | 1210.5 |  |  | 1221.5 |  |  | 1176 |  |  | 1263.5 |  |  | 1238.5 |  |  | 1317 |  |  | 1212.5 |  |  | 1270.5 |  |  | 1292.5 |  |  | 1293 |  |  | 1226.5 |  |  | 1263.5 |  |  | 1221.5 |  |  | 1060.5 |  |  | 1214.5 |  |  | 1138 |  |  | 1192.5 |  |  | 1304 |  |  | 1241 |  |  | 1284.5 |  |  | 1217.5 |  |  | 1195.5 |  |  | 1147.5 |  |  | 1198.5 |  |  | 1234.5 |  |  | 1169 |  |  | 1179.5 |  |  | 1261 |  |  | 1135.5 |  |  | 1244 |  |  | 1239 |  |  | 1260 |  |  | 1188.5 |  |  | 1173 |  |  | 1286.5 |  |  | 1242.5 |  |  | 1272.5 |  |  | 1386.5 |  |  | 1233.5 |  |  | 1239 |  |  | 1238.5 |  |  | 1303.5 |  |  | 1392.5 |  |  | 1291 |  |  | 1228.5 |  |  | 1223.5 |  |  | 1305.5 |  |  | 1246.5 |  |  | 1192 |  |  | 1256 |  |  | 1211 |  |  | 1235.5 |  |  | 1281 |  |  | 1267 |  |  | 1270.5 |  |  | 1155.5 |  |  | 1125.5 |  |  | 1217.5 |  |  | 1283.5 |  |  | 1333.5 |  |  | 1260.5 |  |  | 1246.5 |  |  | 1153.5 |  |  | 1122 |  |  | 1216.5 |  |  | 1201 |  |  | 1280.5 |  |  | 1259.5 |  |  | 1234.5 |  |  | 1285.5 |  |  | 1252 |  |  | 1190.5 |  |  | 1201 |  |  | 1164.5 |  |  | 1249.5 |  |  | 1088 |  |  | 1215 |  |  | 1185.5 |  |  | 1199 |  |  | 1332.5 |  |  | 1091.5 |  |  | 1168.5 |  |  | 1205.5 |  |  | 1201.5 |  |  | 1267.5 |  |  | 1181.5 |  |  | 1122 |  |  | 1270.5 |  |  | 1220.5 |  |  | 1143.5 |  |  | 1225.5 |  |  | 1153.5 |  |  | 1181.5 |  |  | 1238.5 |  |  | 1241.5 |  |  | 1195.5 |  |  | 1234.5 |  |  | 1174.5 |  |  | 1172.5 |  |  | 1238 |  |  | 1082.5 |  |  | 1172.5 |  |  | 1260 |  |  | 1132.5 |  |  | 1096.5 |  |  | 1168.5 |  |  | 1170.5 |  |  | 1273 |  |  | 1304.5 |  |  | 1252.5 |  |  | 1130.5 |  |  | 1224.5 |  |  | 1187 |  |  | 1254.5 |  |  | 1259.5 |  |  | 1226.5 |  |  | 1287.5 |  |  | 1222.5 |  |  | 1116.5 |  |  | 1267.5 |  |  | 1283.5 |  |  | 1249.5 |  |  | 1205.5 |  |  | 1260.5 |  |  | 1235 |  |  | 1223.5 |  |  | 1223.5 |  |  | 1281.5 |  |  | 1214.5 |  |  | 1168.5 |  |  | 1190.5 |  |  | 1245 |  |  | 1160.5 |  |  | 1184 |  |  | 1171.5 |  |  | 1260.5 |  |  | 1181.5 |  |  | 1166 |  |  | 1180 |  |  | 1194.5 |  |  | 1239.5 |  |  | 1115.5 |  |  | 1225.5 |  |  | 1206.5 |  |  | 1208.5 |  |  | 1134.5 |  |  | 1168.5 |  |  | 1188.5 |  |  | 1242.5 |  |  | 1175.5 |  |  | 1212.5 |  |  | 1174.5 |  |  | 1229.5 |  |  | 1215.5 |  |  | 1237.5 |  |  | 1209.5 |  |  | 1235.5 |  |  | 1177.5 |  |  | 1150.5 |  |  | 1260.5 |  |  | 1234.5 |  |  | 1273 |  |  | 1333.5 |  |  | 1199.5 |  |  | 1210.5 |  |  | 1264 |  |  | 1251.5 |  |  | 1209.5 |  |  | 1241.5 |  |  | 1228.5 |  |  | 1297 |  |  | 1125.5 |  |  | 1179.5 |  |  | 1120 |  |  | 1121 |  |  | 1188 |  |  | 1157.5 |  |  | 1223.5 |  |  | 1232.5 |  |  | 1310.5 |  |  | 1192 |  |  | 1205.5 |  |  | 1214.5 |  |  | 1095 |  |  | 1171 |  |  | 1231.5 |  |  | 1204.5 |  |  | 1217 |  |  | 1209.5 |  |  | 1276 |  |  | 1120.5 |  |  | 1133.5 |  |  | 1243 |  |  | 1260.5 |  |  | 1122.5 |  |  | 1139.5 |  |  | 1277 |  |  | 1209.5 |  |  | 1188.5 |  |  | 1163.5 |  |  | 1160.5 |  |  | 1191.5 |  |  | 1327.5 |  |  | 1164.5 |  |  | 1223.5 |  |  | 1264.5 |  |  | 1198.5 |  |  | 1248 |  |  | 1171.5 |  |  | 1248.5 |  |  | 1258.5 |  |  | 1245.5 |  |  | 1165.5 |  |  | 1310.5 |  |  | 1292.5 |  |  | 1196.5 |  |  | 1252 |  |  | 1216.5 |  |  | 1217 |  |  | 1262.5 |  |  | 1318.5 |  |  | 1349.5 |  |  | 1179.5 |  |  | 1219.5 |  |  | 1202.5 |  |  | 1066.5 |  |  | 1279.5 |  |  | 1276 |  |  | 1147.5 |  |  | 1159 |  |  | 1146.5 |  |  | 1104.5 |  |  | 1272.5 |  |  | 1252 |  |  | 1155.5 |  |  | 1244.5 |  |  | 1160 |  |  | 1159.5 |  |  | 1186 |  |  | 1174.5 |  |  | 1201.5 |  |  | 1167.5 |  |  | 1171 |  |  | 1238.5 |  |  | 1311.5 |  |  | 1165 |  |  | 1255.5 |  |  | 1101.5 |  |  | 1254 |  |  | 1255.5 |  |  | 1332.5 |  |  | 1250.5 |  |  | 1251.5 |  |  | 1188.5 |  |  | 1230.5 |  |  | 1155.5 |  |  | 1196.5 |  |  | 1128.5 |  |  | 1261.5 |  |  | 1289.5 |  |  | 1241 |  |  | 1274 |  |  | 1264.5 |  |  | 1238.5 |  |  | 1307
43 |  | 1257.5 |  |  | 1355.5 |  |  | 1277 |  |  | 1237.5 |  |  | 1368.5 |  |  | 1300.5 |  |  | 1353.5 |  |  | 1263.5 |  |  | 1247.5 |  |  | 1261.5 |  |  | 1230 |  |  | 1245.5 |  |  | 1343.5 |  |  | 1160.5 |  |  | 1187 |  |  | 1248.5 |  |  | 1378.5 |  |  | 1256.5 |  |  | 1382.5 |  |  | 1175.5 |  |  | 1213.5 |  |  | 1217.5 |  |  | 1248.5 |  |  | 1149.5 |  |  | 1155 |  |  | 1318.5 |  |  | 1222.5 |  |  | 1225.5 |  |  | 1253.5 |  |  | 1184 |  |  | 1273 |  |  | 1174.5 |  |  | 1178.5 |  |  | 1236.5 |  |  | 1158.5 |  |  | 1240 |  |  | 1210.5 |  |  | 1216 |  |  | 1198.5 |  |  | 1273.5 |  |  | 1151.5 |  |  | 1302.5 |  |  | 1169.5 |  |  | 1172 |  |  | 1393.5 |  |  | 1282 |  |  | 1217.5 |  |  | 1264.5 |  |  | 1285.5 |  |  | 1192.5 |  |  | 1205.5 |  |  | 1224.5 |  |  | 1231.5 |  |  | 1239.5 |  |  | 1277.5 |  |  | 1239.5 |  |  | 1155.5 |  |  | 1229 |  |  | 1340.5 |  |  | 1222.5 |  |  | 1196 |  |  | 1213.5 |  |  | 1320.5 |  |  | 1249.5 |  |  | 1189.5 |  |  | 1251 |  |  | 1294.5 |  |  | 1139 |  |  | 1203.5 |  |  | 1279.5 |  |  | 1261 |  |  | 1260.5 |  |  | 1218.5 |  |  | 1323.5 |  |  | 1318 |  |  | 1251 |  |  | 1232.5 |  |  | 1143.5 |  |  | 1149.5 |  |  | 1179.5 |  |  | 1194 |  |  | 1235.5 |  |  | 1270.5 |  |  | 1297.5 |  |  | 1304.5 |  |  | 1334.5 |  |  | 1293.5 |  |  | 1166.5 |  |  | 1215.5 |  |  | 1293.5 |  |  | 1304.5 |  |  | 1268 |  |  | 1165.5 |  |  | 1178 |  |  | 1228 |  |  | 1172 |  |  | 1316.5 |  |  | 1270.5 |  |  | 1223.5 |  |  | 1264.5 |  |  | 1219.5 |  |  | 1299 |  |  | 1290 |  |  | 1179.5 |  |  | 1193.5 |  |  | 1215.5 |  |  | 1240.5 |  |  | 1301.5 |  |  | 1301.5 |  |  | 1289.5 |  |  | 1303.5 |  |  | 1266.5 |  |  | 1302.5 |  |  | 1259.5 |  |  | 1265.5 |  |  | 1282.5 |  |  | 1250.5 |  |  | 1154.5 |  |  | 1259.5 |  |  | 1317.5 |  |  | 1312.5 |  |  | 1274.5 |  |  | 1214.5 |  |  | 1243.5 |  |  | 1273.5 |  |  | 1277 |  |  | 1198.5 |  |  | 1228.5 |  |  | 1139.5 |  |  | 1203.5 |  |  | 1329.5 |  |  | 1261 |  |  | 1158.5 |  |  | 1285.5 |  |  | 1180.5 |  |  | 1273.5 |  |  | 1202 |  |  | 1271.5 |  |  | 1311.5 |  |  | 1203 |  |  | 1254.5 |  |  | 1235 |  |  | 1240 |  |  | 1330.5 |  |  | 1278 |  |  | 1346.5 |  |  | 1239.5 |  |  | 1290.5 |  |  | 1180.5 |  |  | 1308.5 |  |  | 1272.5 |  |  | 1285.5 |  |  | 1257.5 |  |  | 1339.5 |  |  | 1269.5 |  |  | 1281 |  |  | 1174.5 |  |  | 1194 |  |  | 1199.5 |  |  | 1264.5 |  |  | 1285 |  |  | 1275.5 |  |  | 1207.5 |  |  | 1209.5 |  |  | 1226 |  |  | 1298.5 |  |  | 1194.5 |  |  | 1196.5 |  |  | 1275.5 |  |  | 1174.5 |  |  | 1243.5 |  |  | 1232 |  |  | 1198.5 |  |  | 1263.5 |  |  | 1228.5 |  |  | 1217.5 |  |  | 1287.5 |  |  | 1302.5 |  |  | 1141.5 |  |  | 1340 |  |  | 1303.5 |  |  | 1250.5 |  |  | 1327.5 |  |  | 1301.5 |  |  | 1173.5 |  |  | 1340.5 |  |  | 1294.5 |  |  | 1225.5 |  |  | 1260.5 |  |  | 1201.5 |  |  | 1233.5 |  |  | 1194.5 |  |  | 1120.5 |  |  | 1175 |  |  | 1211.5 |  |  | 1266.5 |  |  | 1194.5 |  |  | 1257.5 |  |  | 1330.5 |  |  | 1235.5 |  |  | 1261.5 |  |  | 1200.5 |  |  | 1228.5 |  |  | 1224.5 |  |  | 1235.5 |  |  | 1365.5 |  |  | 1244.5 |  |  | 1192.5 |  |  | 1290.5 |  |  | 1274.5 |  |  | 1241 |  |  | 1259.5 |  |  | 1220.5 |  |  | 1120 |  |  | 1339.5 |  |  | 1296 |  |  | 1255.5 |  |  | 1315.5 |  |  | 1370.5 |  |  | 1246.5 |  |  | 1206.5 |  |  | 1216.5 |  |  | 1204.5 |  |  | 1138.5 |  |  | 1157 |  |  | 1148.5 |  |  | 1098.5 |  |  | 1293.5 |  |  | 1186.5 |  |  | 1341 |  |  | 1171.5 |  |  | 1197.5 |  |  | 1265.5 |  |  | 1324.5 |  |  | 1290.5 |  |  | 1151.5 |  |  | 1198.5 |  |  | 1294.5 |  |  | 1231 |  |  | 1268 |  |  | 1155.5 |  |  | 1247.5 |  |  | 1276.5 |  |  | 1293 |  |  | 1307.5 |  |  | 1263.5 |  |  | 1217.5 |  |  | 1212 |  |  | 1270.5 |  |  | 1285.5 |  |  | 1228.5 |  |  | 1232.5 |  |  | 1235.5 |  |  | 1281.5 |  |  | 1305.5 |  |  | 1224.5 |  |  | 1319.5 |  |  | 1065 |  |  | 1167.5 |  |  | 1277.5 |  |  | 1217.5 |  |  | 1227.5 |  |  | 1249.5 |  |  | 1320 |  |  | 1214.5 |  |  | 1318.5 |  |  | 1251 |  |  | 1353.5 |  |  | 1249.5 |  |  | 1352 |  |  | 1250.5 |  |  | 1253.5 |  |  | 1379.5 |  |  | 1165.5 |  |  | 1291 |  |  | 1311 |  |  | 1272.5 |  |  | 1230.5 |  |  | 1277.5 |  |  | 1269.5 |  |  | 1329.5 |  |  | 1185.5 |  |  | 1200 |  |  | 1258.5 |  |  | 1268.5 |  |  | 1264 |  |  | 1176.5 |  |  | 1181.5 |  |  | 1243 |  |  | 1213.5 |  |  | 1224.5 |  |  | 1205.5 |  |  | 1232 |  |  | 1275.5 |  |  | 1199 |  |  | 1281.5 |  |  | 1219.5 |  |  | 1233.5 |  |  | 1224 |  |  | 1201.5 |  |  | 1325.5 |  |  | 1170.5 |  |  | 1231 |  |  | 1166.5 |  |  | 1183.5 |  |  | 1312.5 |  |  | 1344.5 |  |  | 1231.5 |  |  | 1221 |  |  | 1199.5 |  |  | 1373.5 |  |  | 1344.5 |  |  | 1219 |  |  | 1238 |  |  | 1322.5 |  |  | 1315.5 |  |  | 1185.5 |  |  | 1262.5 |  |  | 1303.5 |  |  | 1276.5 |  |  | 1235.5 |  |  | 1274.5 |  |  | 1164.5 |  |  | 1256.5 |  |  | 1238 |  |  | 1278.5 |  |  | 1350.5 |  |  | 1386.5 |  |  | 1359.5 |  |  | 1269 |  |  | 1335.5 |  |  | 1308.5 |  |  | 1259.5 |  |  | 1081.5 |  |  | 1267.5 |  |  | 1219 |  |  | 1201 |  |  | 1152 |  |  | 1266 |  |  | 1213.5 |  |  | 1250 |  |  | 1249.5 |  |  | 1209 |  |  | 1220.5 |  |  | 1305.5 |  |  | 1264.5 |  |  | 1246.5 |  |  | 1214.5 |  |  | 1240 |  |  | 1235.5 |  |  | 1310.5 |  |  | 1151.5 |  |  | 1332 |  |  | 1265.5 |  |  | 1235.5 |  |  | 1213.5 |  |  | 1306 |  |  | 1227.5 |  |  | 1114.5 |  |  | 1249.5 |  |  | 1199.5 |  |  | 1231.5 |  |  | 1182.5 |  |  | 1311.5 |  |  | 1202.5 |  |  | 1316.5 |  |  | 1134.5 |  |  | 1155 |  |  | 1278.5 |  |  | 1242.5 |  |  | 1244.5 |  |  | 1236.5 |  |  | 1375.5 |  |  | 1249 |  |  | 1204.5 |  |  | 1294 |  |  | 1206 |  |  | 1214.5 |  |  | 1329.5 |  |  | 1224.5 |  |  | 1220 |  |  | 1297.5 |  |  | 1268.5 |  |  | 1251.5 |  |  | 1133 |  |  | 1225.5 |  |  | 1149.5 |  |  | 1330.5 |  |  | 1155.5 |  |  | 1184.5 |  |  | 1221 |  |  | 1194.5 |  |  | 1220 |  |  | 1224.5 |  |  | 1257.5 |  |  | 1249.5 |  |  | 1329 |  |  | 1181.5 |  |  | 1295 |  |  | 1279 |  |  | 1211.5 |  |  | 1206.5 |  |  | 1260.5 |  |  | 1339.5 |  |  | 1317 |  |  | 1252.5 |  |  | 1218.5 |  |  | 1174.5 |  |  | 1266 |  |  | 1305.5 |  |  | 1185.5 |  |  | 1191.5 |  |  | 1206.5 |  |  | 1310 |  |  | 1166.5 |  |  | 1240.5 |  |  | 1283.5 |  |  | 1255.5 |  |  | 1213.5 |  |  | 1295.5 |  |  | 1262 |  |  | 1216.5 |  |  | 1176.5 |  |  | 1248 |  |  | 1199.5 |  |  | 1181.5 |  |  | 1260.5 |  |  | 1236 |  |  | 1227.5 |  |  | 1195.5 |  |  | 1230.5 |  |  | 1275.5 |  |  | 1308.5 |  |  | 1315 |  |  | 1237 |  |  | 1181.5 |  |  | 1255.5 |  |  | 1223.5 |  |  | 1233.5 |  |  | 1225 |  |  | 1262 |  |  | 1205 |  |  | 1304.5 |  |  | 1218 |  |  | 1281.5 |  |  | 1320.5 |  |  | 1254 |  |  | 1216.5 |  |  | 1265.5 |  |  | 1238.5 |  |  | 1356.5 |  |  | 1193.5 |  |  | 1227 |  |  | 1219 |  |  | 1132.5 |  |  | 1266.5 |  |  | 1195 |  |  | 1147.5 |  |  | 1303.5 |  |  | 1244 |  |  | 1365.5 |  |  | 1281.5 |  |  | 1165 |  |  | 1279.5 |  |  | 1265.5 |  |  | 1207 |  |  | 1272.5 |  |  | 1183 |  |  | 1318.5 |  |  | 1323 |  |  | 1173.5 |  |  | 1238.5 |  |  | 1228.5 |  |  | 1225.5 |  |  | 1234.5 |  |  | 1174.5 |  |  | 1329 |  |  | 1238.5 |  |  | 1263.5 |  |  | 1164.5 |  |  | 1282.5 |  |  | 1195.5 |  |  | 1239 |  |  | 1228.5 |  |  | 1198 |  |  | 1264.5 |  |  | 1216.5 |  |  | 1234.5 |  |  | 1172.5 |  |  | 1238.5 |  |  | 1263.5 |  |  | 1200.5 |  |  | 1327.5 |  |  | 1221.5 |  |  | 1294 |  |  | 1278.5 |  |  | 1120 |  |  | 1220 |  |  | 1239.5 |  |  | 1132 |  |  | 1175.5 |  |  | 1196.5 |  |  | 1241.5 |  |  | 1219.5 |  |  | 1254.5 |  |  | 1303.5 |  |  | 1286.5 |  |  | 1235 |  |  | 1293 |  |  | 1170.5 |  |  | 1153.5 |  |  | 1286 |  |  | 1194.5 |  |  | 1288.5 |  |  | 1197.5 |  |  | 1160.5 |  |  | 1222.5 |  |  | 1231 |  |  | 1256.5 |  |  | 1281.5 |  |  | 1208.5 |  |  | 1191 |  |  | 1290.5 |  |  | 1261.5 |  |  | 1281.5 |  |  | 1349.5 |  |  | 1308.5 |  |  | 1234.5 |  |  | 1334.5 |  |  | 1054.5 |  |  | 1215.5 |  |  | 1213 |  |  | 1300.5 |  |  | 1228.5 |  |  | 1302.5 |  |  | 1197.5 |  |  | 1136.5 |  |  | 1197.5 |  |  | 1241.5 |  |  | 1118 |  |  | 1177.5 |  |  | 1291.5 |  |  | 1318.5 |  |  | 1171 |  |  | 1196.5 |  |  | 1196 |  |  | 1240.5 |  |  | 1237.5 |  |  | 1200.5 |  |  | 1186 |  |  | 1132.5 |  |  | 1295 |  |  | 1244 |  |  | 1290.5 |  |  | 1222 |  |  | 1246 |  |  | 1291.5 |  |  | 1321.5 |  |  | 1168.5 |  |  | 1295 |  |  | 1276.5 |  |  | 1223.5 |  |  | 1132.5 |  |  | 1331.5 |  |  | 1203.5 |  |  | 1251.5 |  |  | 1216.5 |  |  | 1264.5 |  |  | 1184 |  |  | 1337.5 |  |  | 1150 |  |  | 1205.5 |  |  | 1161.5 |  |  | 1300.5 |  |  | 1286 |  |  | 1311 |  |  | 1324 |  |  | 1214.5 |  |  | 1203 |  |  | 1320.5 |  |  | 1308.5 |  |  | 1187.5 |  |  | 1243.5 |  |  | 1197.5 |  |  | 1267.5 |  |  | 1242.5 |  |  | 1255.5 |  |  | 1305 |  |  | 1152.5 |  |  | 1162.5 |  |  | 1273.5 |  |  | 1185.5 |  |  | 1165 |  |  | 1228.5 |  |  | 1272 |  |  | 1232.5 |  |  | 1230.5 |  |  | 1257.5 |  |  | 1175.5 |  |  | 1160 |  |  | 1191.5 |  |  | 1126 |  |  | 1186.5 |  |  | 1261.5 |  |  | 1336.5 |  |  | 1321.5 |  |  | 1220.5 |  |  | 1189.5 |  |  | 1180.5 |  |  | 1316.5 |  |  | 1176.5 |  |  | 1219 |  |  | 1217.5 |  |  | 1215.5 |  |  | 1187.5 |  |  | 1226.5 |  |  | 1260.5 |  |  | 1151 |  |  | 1203 |  |  | 1231.5 |  |  | 1188 |  |  | 1355.5 |  |  | 1205.5 |  |  | 1296.5 |  |  | 1353.5 |  |  | 1194.5 |  |  | 1303.5 |  |  | 1246.5 |  |  | 1213.5 |  |  | 1238 |  |  | 1282.5 |  |  | 1351.5 |  |  | 1329.5 |  |  | 1153 |  |  | 1250.5 |  |  | 1178.5 |  |  | 1331 |  |  | 1126 |  |  | 1249.5 |  |  | 1177 |  |  | 1116 |  |  | 1157.5 |  |  | 1197 |  |  | 1353.5 |  |  | 1314.5 |  |  | 1253.5 |  |  | 1228.5 |  |  | 1175.5 |  |  | 1277.5 |  |  | 1134.5 |  |  | 1220.5 |  |  | 1230.5 |  |  | 1230.5 |  |  | 1231 |  |  | 1172 |  |  | 1243.5 |  |  | 1225.5 |  |  | 1239.5 |  |  | 1299.5 |  |  | 1179.5 |  |  | 1276.5 |  |  | 1298.5 |  |  | 1222.5 |  |  | 1323 |  |  | 1145.5 |  |  | 1146 |  |  | 1187.5 |  |  | 1410.5 |  |  | 1281.5 |  |  | 1288 |  |  | 1280.5 |  |  | 1184.5 |  |  | 1151 |  |  | 1273.5 |  |  | 1204.5 |  |  | 1308.5 |  |  | 1230.5 |  |  | 1220.5 |  |  | 1231.5 |  |  | 1201 |  |  | 1217.5 |  |  | 1171.5 |  |  | 1253.5 |  |  | 1355.5 |  |  | 1145 |  |  | 1156.5 |  |  | 1355.5 |  |  | 1242 |  |  | 1249.5 |  |  | 1281.5 |  |  | 1216 |  |  | 1278.5 |  |  | 1303.5 |  |  | 1229.5 |  |  | 1157 |  |  | 1083.5 |  |  | 1283.5 |  |  | 1186 |  |  | 1211.5 |  |  | 1324.5 |  |  | 1257.5 |  |  | 1078.5 |  |  | 1300.5 |  |  | 1388.5 |  |  | 1195.5 |  |  | 1236 |  |  | 1184 |  |  | 1113.5 |  |  | 1254.5 |  |  | 1214.5 |  |  | 1219 |  |  | 1289.5 |  |  | 1229.5 |  |  | 1249.5 |  |  | 1082.5 |  |  | 1240.5 |  |  | 1209.5 |  |  | 1148.5 |  |  | 1224.5 |  |  | 1134.5 |  |  | 1284 |  |  | 1196.5 |  |  | 1224.5 |  |  | 1199.5 |  |  | 1325.5 |  |  | 1288.5 |  |  | 1214.5 |  |  | 1221.5 |  |  | 1246.5 |  |  | 1186.5 |  |  | 1284.5 |  |  | 1229.5 |  |  | 1225.5 |  |  | 1281.5 |  |  | 1321 |  |  | 1236.5 |  |  | 1245.5 |  |  | 1215 |  |  | 1310.5 |  |  | 1267.5 |  |  | 1346 |  |  | 1238.5 |  |  | 1309.5 |  |  | 1331.5 |  |  | 1322 |  |  | 1265.5 |  |  | 1287.5 |  |  | 1245.5 |  |  | 1107.5 |  |  | 1243.5 |  |  | 1167 |  |  | 1231.5 |  |  | 1330 |  |  | 1288 |  |  | 1331.5 |  |  | 1243.5 |  |  | 1216.5 |  |  | 1171.5 |  |  | 1237.5 |  |  | 1263.5 |  |  | 1195 |  |  | 1218.5 |  |  | 1300 |  |  | 1156.5 |  |  | 1283 |  |  | 1254 |  |  | 1289 |  |  | 1212.5 |  |  | 1212 |  |  | 1325.5 |  |  | 1289.5 |  |  | 1311.5 |  |  | 1410.5 |  |  | 1272.5 |  |  | 1263 |  |  | 1262.5 |  |  | 1318.5 |  |  | 1439.5 |  |  | 1312 |  |  | 1257.5 |  |  | 1244.5 |  |  | 1329.5 |  |  | 1267.5 |  |  | 1231 |  |  | 1295 |  |  | 1235 |  |  | 1274.5 |  |  | 1307 |  |  | 1314 |  |  | 1309.5 |  |  | 1179.5 |  |  | 1154.5 |  |  | 1264.5 |  |  | 1307.5 |  |  | 1354.5 |  |  | 1299.5 |  |  | 1261.5 |  |  | 1179.5 |  |  | 1161 |  |  | 1255.5 |  |  | 1227 |  |  | 1309.5 |  |  | 1288.5 |  |  | 1258.5 |  |  | 1332.5 |  |  | 1276 |  |  | 1219.5 |  |  | 1222 |  |  | 1211.5 |  |  | 1273.5 |  |  | 1127 |  |  | 1254 |  |  | 1224.5 |  |  | 1225 |  |  | 1356.5 |  |  | 1130.5 |  |  | 1192.5 |  |  | 1229.5 |  |  | 1230.5 |  |  | 1306.5 |  |  | 1202.5 |  |  | 1143 |  |  | 1285.5 |  |  | 1244.5 |  |  | 1172.5 |  |  | 1249.5 |  |  | 1168.5 |  |  | 1207.5 |  |  | 1262.5 |  |  | 1265.5 |  |  | 1242.5 |  |  | 1260.5 |  |  | 1203.5 |  |  | 1193.5 |  |  | 1264 |  |  | 1097.5 |  |  | 1193.5 |  |  | 1286 |  |  | 1171.5 |  |  | 1135.5 |  |  | 1183.5 |  |  | 1194.5 |  |  | 1312 |  |  | 1333.5 |  |  | 1299.5 |  |  | 1159.5 |  |  | 1263.5 |  |  | 1234 |  |  | 1278.5 |  |  | 1274.5 |  |  | 1265.5 |  |  | 1326.5 |  |  | 1261.5 |  |  | 1142.5 |  |  | 1296.5 |  |  | 1312.5 |  |  | 1275.5 |  |  | 1220.5 |  |  | 1289.5 |  |  | 1256 |  |  | 1252.5 |  |  | 1244.5 |  |  | 1302.5 |  |  | 1253.5 |  |  | 1192.5 |  |  | 1229.5 |  |  | 1260 |  |  | 1186.5 |  |  | 1199 |  |  | 1192.5 |  |  | 1284.5 |  |  | 1228.5 |  |  | 1205 |  |  | 1201 |  |  | 1218.5 |  |  | 1278.5 |  |  | 1130.5 |  |  | 1264.5 |  |  | 1245.5 |  |  | 1247.5 |  |  | 1173.5 |  |  | 1207.5 |  |  | 1217.5 |  |  | 1266.5 |  |  | 1190.5 |  |  | 1233.5 |  |  | 1221.5 |  |  | 1268.5 |  |  | 1262.5 |  |  | 1266.5 |  |  | 1238.5 |  |  | 1259.5 |  |  | 1216.5 |  |  | 1179.5 |  |  | 1289.5 |  |  | 1249.5 |  |  | 1299 |  |  | 1354.5 |  |  | 1238.5 |  |  | 1234.5 |  |  | 1285 |  |  | 1266.5 |  |  | 1248.5 |  |  | 1256.5 |  |  | 1254.5 |  |  | 1323 |  |  | 1140.5 |  |  | 1205.5 |  |  | 1146 |  |  | 1142 |  |  | 1214 |  |  | 1178.5 |  |  | 1262.5 |  |  | 1261.5 |  |  | 1349.5 |  |  | 1207 |  |  | 1234.5 |  |  | 1240.5 |  |  | 1134 |  |  | 1210 |  |  | 1270.5 |  |  | 1225.5 |  |  | 1264 |  |  | 1230.5 |  |  | 1323 |  |  | 1135.5 |  |  | 1162.5 |  |  | 1290 |  |  | 1289.5 |  |  | 1169.5 |  |  | 1163.5 |  |  | 1306 |  |  | 1238.5 |  |  | 1214.5 |  |  | 1192.5 |  |  | 1189.5 |  |  | 1220.5 |  |  | 1366.5 |  |  | 1190.5 |  |  | 1238.5 |  |  | 1279.5 |  |  | 1237.5 |  |  | 1287 |  |  | 1218.5 |  |  | 1263.5 |  |  | 1284.5 |  |  | 1260.5 |  |  | 1204.5 |  |  | 1349.5 |  |  | 1331.5 |  |  | 1235.5 |  |  | 1278 |  |  | 1240.5 |  |  | 1232 |  |  | 1301.5 |  |  | 1357.5 |  |  | 1375.5 |  |  | 1218.5 |  |  | 1258.5 |  |  | 1226.5 |  |  | 1113.5 |  |  | 1300.5 |  |  | 1302 |  |  | 1186.5 |  |  | 1180 |  |  | 1161.5 |  |  | 1130.5 |  |  | 1311.5 |  |  | 1291 |  |  | 1202.5 |  |  | 1265.5 |  |  | 1181 |  |  | 1185.5 |  |  | 1233 |  |  | 1213.5 |  |  | 1225.5 |  |  | 1188.5 |  |  | 1200 |  |  | 1264.5 |  |  | 1340.5 |  |  | 1186 |  |  | 1276.5 |  |  | 1125.5 |  |  | 1280 |  |  | 1281.5 |  |  | 1371.5 |  |  | 1289.5 |  |  | 1280.5 |  |  | 1212.5 |  |  | 1254.5 |  |  | 1202.5 |  |  | 1211.5 |  |  | 1149.5 |  |  | 1276.5 |  |  | 1336.5 |  |  | 1288 |  |  | 1300 |  |  | 1293.5 |  |  | 1259.5 |  |  | 1328
44 |  | 1286.5 |  |  | 1381.5 |  |  | 1316 |  |  | 1276.5 |  |  | 1394.5 |  |  | 1329.5 |  |  | 1368.5 |  |  | 1287.5 |  |  | 1268.5 |  |  | 1308.5 |  |  | 1259 |  |  | 1292.5 |  |  | 1372.5 |  |  | 1181.5 |  |  | 1208 |  |  | 1272.5 |  |  | 1417.5 |  |  | 1295.5 |  |  | 1429.5 |  |  | 1196.5 |  |  | 1239.5 |  |  | 1238.5 |  |  | 1272.5 |  |  | 1175.5 |  |  | 1194 |  |  | 1347.5 |  |  | 1261.5 |  |  | 1251.5 |  |  | 1300.5 |  |  | 1208 |  |  | 1299 |  |  | 1198.5 |  |  | 1217.5 |  |  | 1262.5 |  |  | 1184.5 |  |  | 1279 |  |  | 1225.5 |  |  | 1255 |  |  | 1213.5 |  |  | 1312.5 |  |  | 1177.5 |  |  | 1341.5 |  |  | 1198.5 |  |  | 1211 |  |  | 1432.5 |  |  | 1321 |  |  | 1246.5 |  |  | 1311.5 |  |  | 1324.5 |  |  | 1231.5 |  |  | 1234.5 |  |  | 1253.5 |  |  | 1270.5 |  |  | 1254.5 |  |  | 1301.5 |  |  | 1254.5 |  |  | 1181.5 |  |  | 1250 |  |  | 1369.5 |  |  | 1237.5 |  |  | 1235 |  |  | 1228.5 |  |  | 1349.5 |  |  | 1264.5 |  |  | 1215.5 |  |  | 1298 |  |  | 1333.5 |  |  | 1165 |  |  | 1227.5 |  |  | 1300.5 |  |  | 1282 |  |  | 1281.5 |  |  | 1242.5 |  |  | 1362.5 |  |  | 1344 |  |  | 1275 |  |  | 1258.5 |  |  | 1167.5 |  |  | 1175.5 |  |  | 1218.5 |  |  | 1218 |  |  | 1274.5 |  |  | 1299.5 |  |  | 1336.5 |  |  | 1319.5 |  |  | 1360.5 |  |  | 1332.5 |  |  | 1205.5 |  |  | 1244.5 |  |  | 1340.5 |  |  | 1328.5 |  |  | 1289 |  |  | 1191.5 |  |  | 1204 |  |  | 1257 |  |  | 1198 |  |  | 1355.5 |  |  | 1296.5 |  |  | 1262.5 |  |  | 1311.5 |  |  | 1266.5 |  |  | 1314 |  |  | 1314 |  |  | 1218.5 |  |  | 1240.5 |  |  | 1230.5 |  |  | 1266.5 |  |  | 1348.5 |  |  | 1316.5 |  |  | 1328.5 |  |  | 1327.5 |  |  | 1290.5 |  |  | 1341.5 |  |  | 1285.5 |  |  | 1286.5 |  |  | 1297.5 |  |  | 1271.5 |  |  | 1183.5 |  |  | 1306.5 |  |  | 1343.5 |  |  | 1338.5 |  |  | 1295.5 |  |  | 1261.5 |  |  | 1264.5 |  |  | 1297.5 |  |  | 1298 |  |  | 1237.5 |  |  | 1257.5 |  |  | 1163.5 |  |  | 1229.5 |  |  | 1358.5 |  |  | 1290 |  |  | 1184.5 |  |  | 1324.5 |  |  | 1227.5 |  |  | 1297.5 |  |  | 1249 |  |  | 1295.5 |  |  | 1350.5 |  |  | 1250 |  |  | 1293.5 |  |  | 1250 |  |  | 1255 |  |  | 1359.5 |  |  | 1317 |  |  | 1367.5 |  |  | 1263.5 |  |  | 1329.5 |  |  | 1209.5 |  |  | 1347.5 |  |  | 1287.5 |  |  | 1309.5 |  |  | 1272.5 |  |  | 1386.5 |  |  | 1316.5 |  |  | 1296 |  |  | 1203.5 |  |  | 1209 |  |  | 1220.5 |  |  | 1288.5 |  |  | 1309 |  |  | 1296.5 |  |  | 1246.5 |  |  | 1230.5 |  |  | 1250 |  |  | 1313.5 |  |  | 1220.5 |  |  | 1217.5 |  |  | 1304.5 |  |  | 1189.5 |  |  | 1258.5 |  |  | 1279 |  |  | 1245.5 |  |  | 1302.5 |  |  | 1252.5 |  |  | 1246.5 |  |  | 1311.5 |  |  | 1341.5 |  |  | 1162.5 |  |  | 1361 |  |  | 1342.5 |  |  | 1289.5 |  |  | 1356.5 |  |  | 1327.5 |  |  | 1212.5 |  |  | 1369.5 |  |  | 1323.5 |  |  | 1264.5 |  |  | 1299.5 |  |  | 1230.5 |  |  | 1280.5 |  |  | 1215.5 |  |  | 1135.5 |  |  | 1214 |  |  | 1237.5 |  |  | 1295.5 |  |  | 1233.5 |  |  | 1304.5 |  |  | 1351.5 |  |  | 1264.5 |  |  | 1300.5 |  |  | 1239.5 |  |  | 1267.5 |  |  | 1245.5 |  |  | 1250.5 |  |  | 1404.5 |  |  | 1291.5 |  |  | 1231.5 |  |  | 1337.5 |  |  | 1298.5 |  |  | 1280 |  |  | 1274.5 |  |  | 1244.5 |  |  | 1144 |  |  | 1378.5 |  |  | 1317 |  |  | 1302.5 |  |  | 1341.5 |  |  | 1409.5 |  |  | 1293.5 |  |  | 1245.5 |  |  | 1255.5 |  |  | 1243.5 |  |  | 1153.5 |  |  | 1204 |  |  | 1177.5 |  |  | 1119.5 |  |  | 1340.5 |  |  | 1212.5 |  |  | 1370 |  |  | 1186.5 |  |  | 1244.5 |  |  | 1294.5 |  |  | 1348.5 |  |  | 1329.5 |  |  | 1172.5 |  |  | 1219.5 |  |  | 1320.5 |  |  | 1278 |  |  | 1307 |  |  | 1176.5 |  |  | 1268.5 |  |  | 1302.5 |  |  | 1319 |  |  | 1328.5 |  |  | 1302.5 |  |  | 1246.5 |  |  | 1238 |  |  | 1285.5 |  |  | 1306.5 |  |  | 1252.5 |  |  | 1271.5 |  |  | 1264.5 |  |  | 1302.5 |  |  | 1344.5 |  |  | 1271.5 |  |  | 1366.5 |  |  | 1104 |  |  | 1182.5 |  |  | 1316.5 |  |  | 1238.5 |  |  | 1248.5 |  |  | 1275.5 |  |  | 1349 |  |  | 1253.5 |  |  | 1347.5 |  |  | 1290 |  |  | 1400.5 |  |  | 1288.5 |  |  | 1391 |  |  | 1289.5 |  |  | 1292.5 |  |  | 1403.5 |  |  | 1204.5 |  |  | 1320 |  |  | 1350 |  |  | 1319.5 |  |  | 1245.5 |  |  | 1306.5 |  |  | 1290.5 |  |  | 1376.5 |  |  | 1232.5 |  |  | 1247 |  |  | 1273.5 |  |  | 1297.5 |  |  | 1285 |  |  | 1215.5 |  |  | 1210.5 |  |  | 1264 |  |  | 1252.5 |  |  | 1245.5 |  |  | 1234.5 |  |  | 1247 |  |  | 1314.5 |  |  | 1225 |  |  | 1296.5 |  |  | 1248.5 |  |  | 1272.5 |  |  | 1253 |  |  | 1216.5 |  |  | 1351.5 |  |  | 1199.5 |  |  | 1252 |  |  | 1192.5 |  |  | 1222.5 |  |  | 1351.5 |  |  | 1383.5 |  |  | 1246.5 |  |  | 1247 |  |  | 1246.5 |  |  | 1399.5 |  |  | 1368.5 |  |  | 1240 |  |  | 1277 |  |  | 1361.5 |  |  | 1336.5 |  |  | 1211.5 |  |  | 1286.5 |  |  | 1327.5 |  |  | 1300.5 |  |  | 1250.5 |  |  | 1321.5 |  |  | 1203.5 |  |  | 1280.5 |  |  | 1285 |  |  | 1302.5 |  |  | 1376.5 |  |  | 1412.5 |  |  | 1380.5 |  |  | 1290 |  |  | 1364.5 |  |  | 1323.5 |  |  | 1274.5 |  |  | 1128.5 |  |  | 1314.5 |  |  | 1266 |  |  | 1230 |  |  | 1191 |  |  | 1281 |  |  | 1228.5 |  |  | 1279 |  |  | 1288.5 |  |  | 1233 |  |  | 1267.5 |  |  | 1352.5 |  |  | 1303.5 |  |  | 1293.5 |  |  | 1235.5 |  |  | 1269 |  |  | 1259.5 |  |  | 1334.5 |  |  | 1190.5 |  |  | 1361 |  |  | 1294.5 |  |  | 1261.5 |  |  | 1242.5 |  |  | 1345 |  |  | 1266.5 |  |  | 1161.5 |  |  | 1288.5 |  |  | 1238.5 |  |  | 1270.5 |  |  | 1197.5 |  |  | 1350.5 |  |  | 1241.5 |  |  | 1342.5 |  |  | 1160.5 |  |  | 1179 |  |  | 1293.5 |  |  | 1263.5 |  |  | 1259.5 |  |  | 1283.5 |  |  | 1399.5 |  |  | 1264 |  |  | 1225.5 |  |  | 1318 |  |  | 1245 |  |  | 1253.5 |  |  | 1368.5 |  |  | 1245.5 |  |  | 1244 |  |  | 1336.5 |  |  | 1307.5 |  |  | 1290.5 |  |  | 1162 |  |  | 1251.5 |  |  | 1173.5 |  |  | 1356.5 |  |  | 1194.5 |  |  | 1223.5 |  |  | 1260 |  |  | 1233.5 |  |  | 1259 |  |  | 1248.5 |  |  | 1272.5 |  |  | 1273.5 |  |  | 1353 |  |  | 1210.5 |  |  | 1334 |  |  | 1303 |  |  | 1250.5 |  |  | 1221.5 |  |  | 1281.5 |  |  | 1365.5 |  |  | 1343 |  |  | 1278.5 |  |  | 1257.5 |  |  | 1198.5 |  |  | 1287 |  |  | 1334.5 |  |  | 1232.5 |  |  | 1230.5 |  |  | 1230.5 |  |  | 1349 |  |  | 1181.5 |  |  | 1269.5 |  |  | 1307.5 |  |  | 1294.5 |  |  | 1260.5 |  |  | 1310.5 |  |  | 1301 |  |  | 1231.5 |  |  | 1202.5 |  |  | 1277 |  |  | 1214.5 |  |  | 1228.5 |  |  | 1286.5 |  |  | 1275 |  |  | 1266.5 |  |  | 1242.5 |  |  | 1269.5 |  |  | 1301.5 |  |  | 1332.5 |  |  | 1339 |  |  | 1276 |  |  | 1196.5 |  |  | 1279.5 |  |  | 1270.5 |  |  | 1259.5 |  |  | 1246 |  |  | 1301 |  |  | 1229 |  |  | 1343.5 |  |  | 1265 |  |  | 1310.5 |  |  | 1359.5 |  |  | 1278 |  |  | 1242.5 |  |  | 1286.5 |  |  | 1285.5 |  |  | 1395.5 |  |  | 1232.5 |  |  | 1242 |  |  | 1243 |  |  | 1156.5 |  |  | 1287.5 |  |  | 1216 |  |  | 1171.5 |  |  | 1342.5 |  |  | 1283 |  |  | 1386.5 |  |  | 1320.5 |  |  | 1191 |  |  | 1318.5 |  |  | 1289.5 |  |  | 1246 |  |  | 1319.5 |  |  | 1198 |  |  | 1365.5 |  |  | 1347 |  |  | 1212.5 |  |  | 1285.5 |  |  | 1254.5 |  |  | 1264.5 |  |  | 1263.5 |  |  | 1189.5 |  |  | 1353 |  |  | 1259.5 |  |  | 1278.5 |  |  | 1179.5 |  |  | 1321.5 |  |  | 1224.5 |  |  | 1265 |  |  | 1275.5 |  |  | 1222 |  |  | 1303.5 |  |  | 1240.5 |  |  | 1249.5 |  |  | 1211.5 |  |  | 1277.5 |  |  | 1287.5 |  |  | 1221.5 |  |  | 1342.5 |  |  | 1242.5 |  |  | 1318 |  |  | 1293.5 |  |  | 1141 |  |  | 1259 |  |  | 1278.5 |  |  | 1179 |  |  | 1204.5 |  |  | 1222.5 |  |  | 1288.5 |  |  | 1234.5 |  |  | 1283.5 |  |  | 1342.5 |  |  | 1325.5 |  |  | 1256 |  |  | 1332 |  |  | 1209.5 |  |  | 1182.5 |  |  | 1307 |  |  | 1233.5 |  |  | 1312.5 |  |  | 1236.5 |  |  | 1189.5 |  |  | 1248.5 |  |  | 1270 |  |  | 1280.5 |  |  | 1296.5 |  |  | 1223.5 |  |  | 1212 |  |  | 1329.5 |  |  | 1300.5 |  |  | 1307.5 |  |  | 1388.5 |  |  | 1355.5 |  |  | 1249.5 |  |  | 1349.5 |  |  | 1093.5 |  |  | 1239.5 |  |  | 1237 |  |  | 1347.5 |  |  | 1267.5 |  |  | 1328.5 |  |  | 1218.5 |  |  | 1160.5 |  |  | 1212.5 |  |  | 1256.5 |  |  | 1139 |  |  | 1203.5 |  |  | 1338.5 |  |  | 1339.5 |  |  | 1186 |  |  | 1225.5 |  |  | 1225 |  |  | 1287.5 |  |  | 1252.5 |  |  | 1226.5 |  |  | 1225 |  |  | 1171.5 |  |  | 1324 |  |  | 1265 |  |  | 1316.5 |  |  | 1251 |  |  | 1293 |  |  | 1312.5 |  |  | 1350.5 |  |  | 1183.5 |  |  | 1334 |  |  | 1302.5 |  |  | 1244.5 |  |  | 1147.5 |  |  | 1370.5 |  |  | 1250.5 |  |  | 1277.5 |  |  | 1231.5 |  |  | 1303.5 |  |  | 1199 |  |  | 1376.5 |  |  | 1189 |  |  | 1231.5 |  |  | 1187.5 |  |  | 1339.5 |  |  | 1310 |  |  | 1332 |  |  | 1363 |  |  | 1243.5 |  |  | 1224 |  |  | 1346.5 |  |  | 1332.5 |  |  | 1202.5 |  |  | 1282.5 |  |  | 1221.5 |  |  | 1293.5 |  |  | 1281.5 |  |  | 1279.5 |  |  | 1326 |  |  | 1191.5 |  |  | 1186.5 |  |  | 1312.5 |  |  | 1224.5 |  |  | 1186 |  |  | 1252.5 |  |  | 1301 |  |  | 1256.5 |  |  | 1269.5 |  |  | 1272.5 |  |  | 1201.5 |  |  | 1184 |  |  | 1230.5 |  |  | 1147 |  |  | 1233.5 |  |  | 1290.5 |  |  | 1375.5 |  |  | 1368.5 |  |  | 1267.5 |  |  | 1218.5 |  |  | 1201.5 |  |  | 1342.5 |  |  | 1215.5 |  |  | 1245 |  |  | 1264.5 |  |  | 1230.5 |  |  | 1226.5 |  |  | 1250.5 |  |  | 1275.5 |  |  | 1166 |  |  | 1242 |  |  | 1252.5 |  |  | 1212 |  |  | 1384.5 |  |  | 1252.5 |  |  | 1325.5 |  |  | 1382.5 |  |  | 1215.5 |  |  | 1318.5 |  |  | 1285.5 |  |  | 1228.5 |  |  | 1277 |  |  | 1321.5 |  |  | 1377.5 |  |  | 1376.5 |  |  | 1182 |  |  | 1289.5 |  |  | 1217.5 |  |  | 1378 |  |  | 1165 |  |  | 1275.5 |  |  | 1203 |  |  | 1145 |  |  | 1172.5 |  |  | 1218 |  |  | 1400.5 |  |  | 1353.5 |  |  | 1292.5 |  |  | 1254.5 |  |  | 1199.5 |  |  | 1301.5 |  |  | 1163.5 |  |  | 1259.5 |  |  | 1269.5 |  |  | 1256.5 |  |  | 1252 |  |  | 1211 |  |  | 1272.5 |  |  | 1246.5 |  |  | 1265.5 |  |  | 1320.5 |  |  | 1194.5 |  |  | 1291.5 |  |  | 1337.5 |  |  | 1243.5 |  |  | 1349 |  |  | 1171.5 |  |  | 1193 |  |  | 1226.5 |  |  | 1457.5 |  |  | 1307.5 |  |  | 1327 |  |  | 1306.5 |  |  | 1223.5 |  |  | 1180 |  |  | 1320.5 |  |  | 1225.5 |  |  | 1355.5 |  |  | 1254.5 |  |  | 1259.5 |  |  | 1252.5 |  |  | 1227 |  |  | 1246.5 |  |  | 1210.5 |  |  | 1300.5 |  |  | 1402.5 |  |  | 1174 |  |  | 1171.5 |  |  | 1370.5 |  |  | 1266 |  |  | 1270.5 |  |  | 1320.5 |  |  | 1240 |  |  | 1302.5 |  |  | 1342.5 |  |  | 1244.5 |  |  | 1196 |  |  | 1104.5 |  |  | 1312.5 |  |  | 1212 |  |  | 1258.5 |  |  | 1348.5 |  |  | 1278.5 |  |  | 1104.5 |  |  | 1329.5 |  |  | 1435.5 |  |  | 1210.5 |  |  | 1265 |  |  | 1213 |  |  | 1137.5 |  |  | 1280.5 |  |  | 1253.5 |  |  | 1258 |  |  | 1315.5 |  |  | 1268.5 |  |  | 1275.5 |  |  | 1121.5 |  |  | 1255.5 |  |  | 1248.5 |  |  | 1172.5 |  |  | 1245.5 |  |  | 1160.5 |  |  | 1308 |  |  | 1220.5 |  |  | 1248.5 |  |  | 1238.5 |  |  | 1372.5 |  |  | 1312.5 |  |  | 1238.5 |  |  | 1260.5 |  |  | 1261.5 |  |  | 1210.5 |  |  | 1308.5 |  |  | 1250.5 |  |  | 1249.5 |  |  | 1328.5 |  |  | 1350 |  |  | 1283.5 |  |  | 1271.5 |  |  | 1254 |  |  | 1331.5 |  |  | 1314.5 |  |  | 1385 |  |  | 1264.5 |  |  | 1348.5 |  |  | 1370.5 |  |  | 1346 |  |  | 1280.5 |  |  | 1311.5 |  |  | 1271.5 |  |  | 1136.5 |  |  | 1267.5 |  |  | 1182 |  |  | 1255.5 |  |  | 1354 |  |  | 1314 |  |  | 1378.5 |  |  | 1258.5 |  |  | 1255.5 |  |  | 1195.5 |  |  | 1263.5 |  |  | 1302.5 |  |  | 1242 |  |  | 1265.5 |  |  | 1339 |  |  | 1195.5 |  |  | 1312 |  |  | 1280 |  |  | 1328 |  |  | 1251.5 |  |  | 1241 |  |  | 1351.5 |  |  | 1315.5 |  |  | 1358.5 |  |  | 1431.5 |  |  | 1301.5 |  |  | 1302 |  |  | 1301.5 |  |  | 1333.5 |  |  | 1454.5 |  |  | 1333 |  |  | 1283.5 |  |  | 1268.5 |  |  | 1344.5 |  |  | 1306.5 |  |  | 1270 |  |  | 1319 |  |  | 1282 |  |  | 1295.5 |  |  | 1336 |  |  | 1353 |  |  | 1324.5 |  |  | 1205.5 |  |  | 1178.5 |  |  | 1290.5 |  |  | 1322.5 |  |  | 1383.5 |  |  | 1346.5 |  |  | 1290.5 |  |  | 1203.5 |  |  | 1176 |  |  | 1302.5 |  |  | 1242 |  |  | 1356.5 |  |  | 1312.5 |  |  | 1273.5 |  |  | 1361.5 |  |  | 1315 |  |  | 1240.5 |  |  | 1251 |  |  | 1240.5 |  |  | 1312.5 |  |  | 1142 |  |  | 1278 |  |  | 1239.5 |  |  | 1264 |  |  | 1377.5 |  |  | 1154.5 |  |  | 1231.5 |  |  | 1253.5 |  |  | 1245.5 |  |  | 1353.5 |  |  | 1228.5 |  |  | 1190 |  |  | 1309.5 |  |  | 1283.5 |  |  | 1196.5 |  |  | 1296.5 |  |  | 1215.5 |  |  | 1228.5 |  |  | 1309.5 |  |  | 1291.5 |  |  | 1257.5 |  |  | 1286.5 |  |  | 1227.5 |  |  | 1208.5 |  |  | 1293 |  |  | 1121.5 |  |  | 1222.5 |  |  | 1325 |  |  | 1210.5 |  |  | 1182.5 |  |  | 1209.5 |  |  | 1218.5 |  |  | 1359 |  |  | 1372.5 |  |  | 1314.5 |  |  | 1180.5 |  |  | 1302.5 |  |  | 1260 |  |  | 1302.5 |  |  | 1300.5 |  |  | 1312.5 |  |  | 1352.5 |  |  | 1300.5 |  |  | 1181.5 |  |  | 1343.5 |  |  | 1359.5 |  |  | 1314.5 |  |  | 1267.5 |  |  | 1336.5 |  |  | 1277 |  |  | 1273.5 |  |  | 1283.5 |  |  | 1326.5 |  |  | 1268.5 |  |  | 1213.5 |  |  | 1268.5 |  |  | 1289 |  |  | 1201.5 |  |  | 1238 |  |  | 1207.5 |  |  | 1305.5 |  |  | 1275.5 |  |  | 1229 |  |  | 1225 |  |  | 1242.5 |  |  | 1317.5 |  |  | 1145.5 |  |  | 1303.5 |  |  | 1266.5 |  |  | 1273.5 |  |  | 1220.5 |  |  | 1246.5 |  |  | 1246.5 |  |  | 1305.5 |  |  | 1229.5 |  |  | 1254.5 |  |  | 1236.5 |  |  | 1297.5 |  |  | 1301.5 |  |  | 1287.5 |  |  | 1259.5 |  |  | 1298.5 |  |  | 1255.5 |  |  | 1226.5 |  |  | 1310.5 |  |  | 1288.5 |  |  | 1323 |  |  | 1380.5 |  |  | 1253.5 |  |  | 1255.5 |  |  | 1324 |  |  | 1287.5 |  |  | 1272.5 |  |  | 1285.5 |  |  | 1293.5 |  |  | 1347 |  |  | 1161.5 |  |  | 1220.5 |  |  | 1185 |  |  | 1181 |  |  | 1253 |  |  | 1225.5 |  |  | 1283.5 |  |  | 1282.5 |  |  | 1396.5 |  |  | 1246 |  |  | 1273.5 |  |  | 1287.5 |  |  | 1181 |  |  | 1234 |  |  | 1317.5 |  |  | 1251.5 |  |  | 1290 |  |  | 1256.5 |  |  | 1344 |  |  | 1174.5 |  |  | 1188.5 |  |  | 1329 |  |  | 1315.5 |  |  | 1193.5 |  |  | 1202.5 |  |  | 1321 |  |  | 1285.5 |  |  | 1243.5 |  |  | 1239.5 |  |  | 1228.5 |  |  | 1259.5 |  |  | 1395.5 |  |  | 1216.5 |  |  | 1277.5 |  |  | 1300.5 |  |  | 1266.5 |  |  | 1326 |  |  | 1244.5 |  |  | 1289.5 |  |  | 1313.5 |  |  | 1275.5 |  |  | 1225.5 |  |  | 1388.5 |  |  | 1355.5 |  |  | 1282.5 |  |  | 1304 |  |  | 1266.5 |  |  | 1271 |  |  | 1330.5 |  |  | 1372.5 |  |  | 1404.5 |  |  | 1242.5 |  |  | 1279.5 |  |  | 1250.5 |  |  | 1134.5 |  |  | 1324.5 |  |  | 1341 |  |  | 1215.5 |  |  | 1195 |  |  | 1185.5 |  |  | 1177.5 |  |  | 1326.5 |  |  | 1315 |  |  | 1241.5 |  |  | 1304.5 |  |  | 1220 |  |  | 1224.5 |  |  | 1257 |  |  | 1260.5 |  |  | 1240.5 |  |  | 1203.5 |  |  | 1229 |  |  | 1303.5 |  |  | 1379.5 |  |  | 1212 |  |  | 1323.5 |  |  | 1172.5 |  |  | 1306 |  |  | 1307.5 |  |  | 1395.5 |  |  | 1315.5 |  |  | 1319.5 |  |  | 1227.5 |  |  | 1293.5 |  |  | 1228.5 |  |  | 1250.5 |  |  | 1173.5 |  |  | 1315.5 |  |  | 1360.5 |  |  | 1303 |  |  | 1315 |  |  | 1314.5 |  |  | 1283.5 |  |  | 1349
45 |  | 1312.5 |  |  | 1402.5 |  |  | 1345 |  |  | 1315.5 |  |  | 1415.5 |  |  | 1350.5 |  |  | 1407.5 |  |  | 1311.5 |  |  | 1289.5 |  |  | 1347.5 |  |  | 1288 |  |  | 1339.5 |  |  | 1419.5 |  |  | 1207.5 |  |  | 1247 |  |  | 1319.5 |  |  | 1446.5 |  |  | 1334.5 |  |  | 1458.5 |  |  | 1225.5 |  |  | 1278.5 |  |  | 1277.5 |  |  | 1311.5 |  |  | 1199.5 |  |  | 1220 |  |  | 1386.5 |  |  | 1276.5 |  |  | 1266.5 |  |  | 1347.5 |  |  | 1223 |  |  | 1338 |  |  | 1237.5 |  |  | 1243.5 |  |  | 1291.5 |  |  | 1213.5 |  |  | 1318 |  |  | 1249.5 |  |  | 1294 |  |  | 1260.5 |  |  | 1341.5 |  |  | 1224.5 |  |  | 1380.5 |  |  | 1213.5 |  |  | 1258 |  |  | 1471.5 |  |  | 1360 |  |  | 1285.5 |  |  | 1358.5 |  |  | 1363.5 |  |  | 1246.5 |  |  | 1263.5 |  |  | 1279.5 |  |  | 1291.5 |  |  | 1278.5 |  |  | 1325.5 |  |  | 1293.5 |  |  | 1220.5 |  |  | 1289 |  |  | 1393.5 |  |  | 1266.5 |  |  | 1274 |  |  | 1275.5 |  |  | 1364.5 |  |  | 1303.5 |  |  | 1254.5 |  |  | 1313 |  |  | 1357.5 |  |  | 1204 |  |  | 1266.5 |  |  | 1339.5 |  |  | 1321 |  |  | 1307.5 |  |  | 1271.5 |  |  | 1401.5 |  |  | 1368 |  |  | 1299 |  |  | 1273.5 |  |  | 1196.5 |  |  | 1199.5 |  |  | 1242.5 |  |  | 1257 |  |  | 1313.5 |  |  | 1314.5 |  |  | 1383.5 |  |  | 1358.5 |  |  | 1399.5 |  |  | 1358.5 |  |  | 1231.5 |  |  | 1259.5 |  |  | 1364.5 |  |  | 1357.5 |  |  | 1313 |  |  | 1217.5 |  |  | 1251 |  |  | 1283 |  |  | 1222 |  |  | 1381.5 |  |  | 1343.5 |  |  | 1277.5 |  |  | 1332.5 |  |  | 1295.5 |  |  | 1329 |  |  | 1329 |  |  | 1265.5 |  |  | 1279.5 |  |  | 1277.5 |  |  | 1313.5 |  |  | 1363.5 |  |  | 1355.5 |  |  | 1357.5 |  |  | 1374.5 |  |  | 1314.5 |  |  | 1362.5 |  |  | 1311.5 |  |  | 1312.5 |  |  | 1344.5 |  |  | 1310.5 |  |  | 1198.5 |  |  | 1353.5 |  |  | 1358.5 |  |  | 1385.5 |  |  | 1319.5 |  |  | 1276.5 |  |  | 1303.5 |  |  | 1318.5 |  |  | 1322 |  |  | 1252.5 |  |  | 1296.5 |  |  | 1210.5 |  |  | 1268.5 |  |  | 1397.5 |  |  | 1329 |  |  | 1205.5 |  |  | 1339.5 |  |  | 1256.5 |  |  | 1318.5 |  |  | 1288 |  |  | 1310.5 |  |  | 1389.5 |  |  | 1289 |  |  | 1314.5 |  |  | 1289 |  |  | 1294 |  |  | 1388.5 |  |  | 1356 |  |  | 1396.5 |  |  | 1287.5 |  |  | 1368.5 |  |  | 1233.5 |  |  | 1386.5 |  |  | 1326.5 |  |  | 1348.5 |  |  | 1311.5 |  |  | 1425.5 |  |  | 1331.5 |  |  | 1343 |  |  | 1250.5 |  |  | 1256 |  |  | 1241.5 |  |  | 1327.5 |  |  | 1348 |  |  | 1325.5 |  |  | 1285.5 |  |  | 1259.5 |  |  | 1265 |  |  | 1334.5 |  |  | 1235.5 |  |  | 1256.5 |  |  | 1343.5 |  |  | 1228.5 |  |  | 1284.5 |  |  | 1294 |  |  | 1271.5 |  |  | 1328.5 |  |  | 1278.5 |  |  | 1261.5 |  |  | 1337.5 |  |  | 1380.5 |  |  | 1186.5 |  |  | 1400 |  |  | 1368.5 |  |  | 1304.5 |  |  | 1371.5 |  |  | 1356.5 |  |  | 1241.5 |  |  | 1395.5 |  |  | 1370.5 |  |  | 1311.5 |  |  | 1346.5 |  |  | 1251.5 |  |  | 1304.5 |  |  | 1262.5 |  |  | 1156.5 |  |  | 1253 |  |  | 1252.5 |  |  | 1334.5 |  |  | 1259.5 |  |  | 1319.5 |  |  | 1372.5 |  |  | 1285.5 |  |  | 1347.5 |  |  | 1263.5 |  |  | 1293.5 |  |  | 1260.5 |  |  | 1274.5 |  |  | 1428.5 |  |  | 1306.5 |  |  | 1260.5 |  |  | 1358.5 |  |  | 1337.5 |  |  | 1319 |  |  | 1295.5 |  |  | 1270.5 |  |  | 1170 |  |  | 1399.5 |  |  | 1343 |  |  | 1331.5 |  |  | 1380.5 |  |  | 1438.5 |  |  | 1340.5 |  |  | 1269.5 |  |  | 1276.5 |  |  | 1282.5 |  |  | 1168.5 |  |  | 1243 |  |  | 1201.5 |  |  | 1158.5 |  |  | 1379.5 |  |  | 1251.5 |  |  | 1399 |  |  | 1233.5 |  |  | 1268.5 |  |  | 1315.5 |  |  | 1377.5 |  |  | 1368.5 |  |  | 1211.5 |  |  | 1266.5 |  |  | 1344.5 |  |  | 1302 |  |  | 1328 |  |  | 1215.5 |  |  | 1297.5 |  |  | 1317.5 |  |  | 1340 |  |  | 1375.5 |  |  | 1331.5 |  |  | 1261.5 |  |  | 1264 |  |  | 1314.5 |  |  | 1321.5 |  |  | 1281.5 |  |  | 1286.5 |  |  | 1303.5 |  |  | 1326.5 |  |  | 1373.5 |  |  | 1297.5 |  |  | 1405.5 |  |  | 1119 |  |  | 1206.5 |  |  | 1363.5 |  |  | 1259.5 |  |  | 1269.5 |  |  | 1301.5 |  |  | 1388 |  |  | 1277.5 |  |  | 1368.5 |  |  | 1319 |  |  | 1447.5 |  |  | 1303.5 |  |  | 1420 |  |  | 1328.5 |  |  | 1316.5 |  |  | 1424.5 |  |  | 1230.5 |  |  | 1344 |  |  | 1379 |  |  | 1348.5 |  |  | 1260.5 |  |  | 1330.5 |  |  | 1314.5 |  |  | 1415.5 |  |  | 1256.5 |  |  | 1294 |  |  | 1320.5 |  |  | 1323.5 |  |  | 1311 |  |  | 1244.5 |  |  | 1225.5 |  |  | 1311 |  |  | 1276.5 |  |  | 1284.5 |  |  | 1260.5 |  |  | 1273 |  |  | 1353.5 |  |  | 1249 |  |  | 1335.5 |  |  | 1272.5 |  |  | 1298.5 |  |  | 1274 |  |  | 1242.5 |  |  | 1380.5 |  |  | 1220.5 |  |  | 1291 |  |  | 1218.5 |  |  | 1243.5 |  |  | 1398.5 |  |  | 1409.5 |  |  | 1267.5 |  |  | 1262 |  |  | 1285.5 |  |  | 1420.5 |  |  | 1394.5 |  |  | 1255 |  |  | 1303 |  |  | 1400.5 |  |  | 1351.5 |  |  | 1237.5 |  |  | 1301.5 |  |  | 1353.5 |  |  | 1347.5 |  |  | 1289.5 |  |  | 1350.5 |  |  | 1224.5 |  |  | 1306.5 |  |  | 1324 |  |  | 1323.5 |  |  | 1415.5 |  |  | 1451.5 |  |  | 1419.5 |  |  | 1311 |  |  | 1379.5 |  |  | 1347.5 |  |  | 1321.5 |  |  | 1157.5 |  |  | 1361.5 |  |  | 1292 |  |  | 1259 |  |  | 1220 |  |  | 1307 |  |  | 1275.5 |  |  | 1318 |  |  | 1314.5 |  |  | 1248 |  |  | 1288.5 |  |  | 1391.5 |  |  | 1350.5 |  |  | 1332.5 |  |  | 1282.5 |  |  | 1308 |  |  | 1306.5 |  |  | 1349.5 |  |  | 1229.5 |  |  | 1382 |  |  | 1333.5 |  |  | 1282.5 |  |  | 1257.5 |  |  | 1374 |  |  | 1292.5 |  |  | 1185.5 |  |  | 1309.5 |  |  | 1267.5 |  |  | 1317.5 |  |  | 1221.5 |  |  | 1397.5 |  |  | 1280.5 |  |  | 1363.5 |  |  | 1199.5 |  |  | 1200 |  |  | 1317.5 |  |  | 1302.5 |  |  | 1288.5 |  |  | 1322.5 |  |  | 1446.5 |  |  | 1288 |  |  | 1272.5 |  |  | 1333 |  |  | 1271 |  |  | 1268.5 |  |  | 1383.5 |  |  | 1260.5 |  |  | 1259 |  |  | 1375.5 |  |  | 1346.5 |  |  | 1329.5 |  |  | 1183 |  |  | 1280.5 |  |  | 1199.5 |  |  | 1395.5 |  |  | 1220.5 |  |  | 1247.5 |  |  | 1289 |  |  | 1254.5 |  |  | 1298 |  |  | 1277.5 |  |  | 1287.5 |  |  | 1297.5 |  |  | 1368 |  |  | 1225.5 |  |  | 1360 |  |  | 1332 |  |  | 1274.5 |  |  | 1250.5 |  |  | 1310.5 |  |  | 1394.5 |  |  | 1358 |  |  | 1325.5 |  |  | 1272.5 |  |  | 1227.5 |  |  | 1302 |  |  | 1349.5 |  |  | 1247.5 |  |  | 1259.5 |  |  | 1259.5 |  |  | 1364 |  |  | 1202.5 |  |  | 1293.5 |  |  | 1354.5 |  |  | 1320.5 |  |  | 1286.5 |  |  | 1325.5 |  |  | 1348 |  |  | 1278.5 |  |  | 1231.5 |  |  | 1316 |  |  | 1240.5 |  |  | 1252.5 |  |  | 1315.5 |  |  | 1290 |  |  | 1305.5 |  |  | 1281.5 |  |  | 1295.5 |  |  | 1327.5 |  |  | 1347.5 |  |  | 1378 |  |  | 1297 |  |  | 1235.5 |  |  | 1326.5 |  |  | 1317.5 |  |  | 1274.5 |  |  | 1275 |  |  | 1327 |  |  | 1244 |  |  | 1372.5 |  |  | 1294 |  |  | 1357.5 |  |  | 1388.5 |  |  | 1302 |  |  | 1268.5 |  |  | 1301.5 |  |  | 1324.5 |  |  | 1416.5 |  |  | 1247.5 |  |  | 1266 |  |  | 1282 |  |  | 1185.5 |  |  | 1326.5 |  |  | 1255 |  |  | 1197.5 |  |  | 1371.5 |  |  | 1298 |  |  | 1433.5 |  |  | 1367.5 |  |  | 1212 |  |  | 1357.5 |  |  | 1310.5 |  |  | 1285 |  |  | 1358.5 |  |  | 1237 |  |  | 1412.5 |  |  | 1386 |  |  | 1251.5 |  |  | 1300.5 |  |  | 1280.5 |  |  | 1285.5 |  |  | 1302.5 |  |  | 1218.5 |  |  | 1368 |  |  | 1274.5 |  |  | 1293.5 |  |  | 1208.5 |  |  | 1347.5 |  |  | 1271.5 |  |  | 1312 |  |  | 1314.5 |  |  | 1261 |  |  | 1318.5 |  |  | 1279.5 |  |  | 1296.5 |  |  | 1250.5 |  |  | 1316.5 |  |  | 1316.5 |  |  | 1245.5 |  |  | 1366.5 |  |  | 1271.5 |  |  | 1365 |  |  | 1317.5 |  |  | 1180 |  |  | 1283 |  |  | 1325.5 |  |  | 1203 |  |  | 1230.5 |  |  | 1261.5 |  |  | 1327.5 |  |  | 1273.5 |  |  | 1322.5 |  |  | 1389.5 |  |  | 1354.5 |  |  | 1271 |  |  | 1358 |  |  | 1233.5 |  |  | 1221.5 |  |  | 1322 |  |  | 1262.5 |  |  | 1327.5 |  |  | 1260.5 |  |  | 1213.5 |  |  | 1269.5 |  |  | 1285 |  |  | 1304.5 |  |  | 1325.5 |  |  | 1247.5 |  |  | 1251 |  |  | 1353.5 |  |  | 1329.5 |  |  | 1328.5 |  |  | 1403.5 |  |  | 1402.5 |  |  | 1270.5 |  |  | 1388.5 |  |  | 1119.5 |  |  | 1263.5 |  |  | 1252 |  |  | 1368.5 |  |  | 1293.5 |  |  | 1367.5 |  |  | 1257.5 |  |  | 1189.5 |  |  | 1241.5 |  |  | 1271.5 |  |  | 1163 |  |  | 1227.5 |  |  | 1364.5 |  |  | 1386.5 |  |  | 1215 |  |  | 1251.5 |  |  | 1246 |  |  | 1308.5 |  |  | 1281.5 |  |  | 1252.5 |  |  | 1272 |  |  | 1210.5 |  |  | 1348 |  |  | 1304 |  |  | 1337.5 |  |  | 1275 |  |  | 1314 |  |  | 1341.5 |  |  | 1389.5 |  |  | 1207.5 |  |  | 1349 |  |  | 1326.5 |  |  | 1283.5 |  |  | 1168.5 |  |  | 1399.5 |  |  | 1297.5 |  |  | 1324.5 |  |  | 1260.5 |  |  | 1329.5 |  |  | 1220 |  |  | 1415.5 |  |  | 1215 |  |  | 1255.5 |  |  | 1202.5 |  |  | 1378.5 |  |  | 1357 |  |  | 1379 |  |  | 1402 |  |  | 1282.5 |  |  | 1263 |  |  | 1375.5 |  |  | 1353.5 |  |  | 1226.5 |  |  | 1311.5 |  |  | 1247.5 |  |  | 1314.5 |  |  | 1328.5 |  |  | 1308.5 |  |  | 1352 |  |  | 1230.5 |  |  | 1233.5 |  |  | 1338.5 |  |  | 1239.5 |  |  | 1210 |  |  | 1273.5 |  |  | 1330 |  |  | 1282.5 |  |  | 1308.5 |  |  | 1293.5 |  |  | 1230.5 |  |  | 1223 |  |  | 1245.5 |  |  | 1162 |  |  | 1262.5 |  |  | 1316.5 |  |  | 1396.5 |  |  | 1392.5 |  |  | 1306.5 |  |  | 1233.5 |  |  | 1227.5 |  |  | 1381.5 |  |  | 1241.5 |  |  | 1269 |  |  | 1311.5 |  |  | 1254.5 |  |  | 1241.5 |  |  | 1289.5 |  |  | 1314.5 |  |  | 1205 |  |  | 1263 |  |  | 1273.5 |  |  | 1233 |  |  | 1423.5 |  |  | 1276.5 |  |  | 1354.5 |  |  | 1403.5 |  |  | 1254.5 |  |  | 1333.5 |  |  | 1306.5 |  |  | 1267.5 |  |  | 1316 |  |  | 1350.5 |  |  | 1398.5 |  |  | 1415.5 |  |  | 1206 |  |  | 1310.5 |  |  | 1246.5 |  |  | 1393 |  |  | 1191 |  |  | 1314.5 |  |  | 1218 |  |  | 1171 |  |  | 1187.5 |  |  | 1257 |  |  | 1415.5 |  |  | 1382.5 |  |  | 1321.5 |  |  | 1283.5 |  |  | 1214.5 |  |  | 1340.5 |  |  | 1178.5 |  |  | 1285.5 |  |  | 1290.5 |  |  | 1303.5 |  |  | 1267 |  |  | 1235 |  |  | 1298.5 |  |  | 1275.5 |  |  | 1312.5 |  |  | 1359.5 |  |  | 1233.5 |  |  | 1312.5 |  |  | 1384.5 |  |  | 1258.5 |  |  | 1375 |  |  | 1195.5 |  |  | 1232 |  |  | 1252.5 |  |  | 1481.5 |  |  | 1331.5 |  |  | 1351 |  |  | 1332.5 |  |  | 1262.5 |  |  | 1204 |  |  | 1367.5 |  |  | 1254.5 |  |  | 1370.5 |  |  | 1280.5 |  |  | 1283.5 |  |  | 1281.5 |  |  | 1253 |  |  | 1261.5 |  |  | 1225.5 |  |  | 1315.5 |  |  | 1441.5 |  |  | 1213 |  |  | 1192.5 |  |  | 1409.5 |  |  | 1290 |  |  | 1309.5 |  |  | 1341.5 |  |  | 1264 |  |  | 1328.5 |  |  | 1363.5 |  |  | 1270.5 |  |  | 1235 |  |  | 1151.5 |  |  | 1327.5 |  |  | 1251 |  |  | 1273.5 |  |  | 1395.5 |  |  | 1293.5 |  |  | 1125.5 |  |  | 1376.5 |  |  | 1450.5 |  |  | 1225.5 |  |  | 1289 |  |  | 1260 |  |  | 1184.5 |  |  | 1319.5 |  |  | 1300.5 |  |  | 1284 |  |  | 1354.5 |  |  | 1292.5 |  |  | 1301.5 |  |  | 1145.5 |  |  | 1270.5 |  |  | 1295.5 |  |  | 1187.5 |  |  | 1292.5 |  |  | 1175.5 |  |  | 1323 |  |  | 1267.5 |  |  | 1274.5 |  |  | 1267.5 |  |  | 1396.5 |  |  | 1333.5 |  |  | 1264.5 |  |  | 1284.5 |  |  | 1300.5 |  |  | 1249.5 |  |  | 1347.5 |  |  | 1289.5 |  |  | 1275.5 |  |  | 1352.5 |  |  | 1376 |  |  | 1309.5 |  |  | 1318.5 |  |  | 1278 |  |  | 1360.5 |  |  | 1338.5 |  |  | 1411 |  |  | 1303.5 |  |  | 1395.5 |  |  | 1409.5 |  |  | 1385 |  |  | 1319.5 |  |  | 1358.5 |  |  | 1300.5 |  |  | 1165.5 |  |  | 1288.5 |  |  | 1211 |  |  | 1281.5 |  |  | 1380 |  |  | 1338 |  |  | 1402.5 |  |  | 1273.5 |  |  | 1270.5 |  |  | 1234.5 |  |  | 1302.5 |  |  | 1331.5 |  |  | 1281 |  |  | 1304.5 |  |  | 1363 |  |  | 1219.5 |  |  | 1338 |  |  | 1304 |  |  | 1367 |  |  | 1298.5 |  |  | 1267 |  |  | 1372.5 |  |  | 1362.5 |  |  | 1373.5 |  |  | 1470.5 |  |  | 1322.5 |  |  | 1341 |  |  | 1340.5 |  |  | 1372.5 |  |  | 1493.5 |  |  | 1362 |  |  | 1304.5 |  |  | 1283.5 |  |  | 1368.5 |  |  | 1327.5 |  |  | 1294 |  |  | 1358 |  |  | 1321 |  |  | 1310.5 |  |  | 1357 |  |  | 1400 |  |  | 1363.5 |  |  | 1244.5 |  |  | 1193.5 |  |  | 1314.5 |  |  | 1369.5 |  |  | 1422.5 |  |  | 1372.5 |  |  | 1329.5 |  |  | 1224.5 |  |  | 1205 |  |  | 1323.5 |  |  | 1281 |  |  | 1377.5 |  |  | 1359.5 |  |  | 1288.5 |  |  | 1387.5 |  |  | 1341 |  |  | 1264.5 |  |  | 1277 |  |  | 1287.5 |  |  | 1359.5 |  |  | 1189 |  |  | 1317 |  |  | 1254.5 |  |  | 1288 |  |  | 1403.5 |  |  | 1193.5 |  |  | 1246.5 |  |  | 1300.5 |  |  | 1269.5 |  |  | 1368.5 |  |  | 1254.5 |  |  | 1211 |  |  | 1348.5 |  |  | 1322.5 |  |  | 1220.5 |  |  | 1325.5 |  |  | 1239.5 |  |  | 1257.5 |  |  | 1333.5 |  |  | 1315.5 |  |  | 1296.5 |  |  | 1333.5 |  |  | 1242.5 |  |  | 1247.5 |  |  | 1308 |  |  | 1168.5 |  |  | 1261.5 |  |  | 1354 |  |  | 1249.5 |  |  | 1206.5 |  |  | 1235.5 |  |  | 1257.5 |  |  | 1406 |  |  | 1401.5 |  |  | 1340.5 |  |  | 1206.5 |  |  | 1326.5 |  |  | 1299 |  |  | 1331.5 |  |  | 1339.5 |  |  | 1359.5 |  |  | 1373.5 |  |  | 1326.5 |  |  | 1196.5 |  |  | 1372.5 |  |  | 1406.5 |  |  | 1329.5 |  |  | 1306.5 |  |  | 1375.5 |  |  | 1303 |  |  | 1299.5 |  |  | 1322.5 |  |  | 1365.5 |  |  | 1307.5 |  |  | 1228.5 |  |  | 1289.5 |  |  | 1328 |  |  | 1225.5 |  |  | 1262 |  |  | 1236.5 |  |  | 1344.5 |  |  | 1322.5 |  |  | 1250 |  |  | 1249 |  |  | 1263.5 |  |  | 1332.5 |  |  | 1192.5 |  |  | 1350.5 |  |  | 1287.5 |  |  | 1312.5 |  |  | 1249.5 |  |  | 1275.5 |  |  | 1267.5 |  |  | 1320.5 |  |  | 1255.5 |  |  | 1293.5 |  |  | 1262.5 |  |  | 1344.5 |  |  | 1325.5 |  |  | 1302.5 |  |  | 1274.5 |  |  | 1337.5 |  |  | 1276.5 |  |  | 1241.5 |  |  | 1325.5 |  |  | 1317.5 |  |  | 1362 |  |  | 1404.5 |  |  | 1268.5 |  |  | 1284.5 |  |  | 1353 |  |  | 1308.5 |  |  | 1301.5 |  |  | 1332.5 |  |  | 1314.5 |  |  | 1362 |  |  | 1185.5 |  |  | 1246.5 |  |  | 1209 |  |  | 1228 |  |  | 1292 |  |  | 1272.5 |  |  | 1307.5 |  |  | 1308.5 |  |  | 1435.5 |  |  | 1285 |  |  | 1302.5 |  |  | 1334.5 |  |  | 1196 |  |  | 1260 |  |  | 1356.5 |  |  | 1290.5 |  |  | 1329 |  |  | 1285.5 |  |  | 1383 |  |  | 1200.5 |  |  | 1227.5 |  |  | 1353 |  |  | 1362.5 |  |  | 1217.5 |  |  | 1226.5 |  |  | 1347 |  |  | 1314.5 |  |  | 1282.5 |  |  | 1254.5 |  |  | 1275.5 |  |  | 1283.5 |  |  | 1410.5 |  |  | 1255.5 |  |  | 1306.5 |  |  | 1321.5 |  |  | 1305.5 |  |  | 1373 |  |  | 1291.5 |  |  | 1336.5 |  |  | 1328.5 |  |  | 1314.5 |  |  | 1249.5 |  |  | 1414.5 |  |  | 1394.5 |  |  | 1311.5 |  |  | 1333 |  |  | 1292.5 |  |  | 1292 |  |  | 1351.5 |  |  | 1411.5 |  |  | 1443.5 |  |  | 1268.5 |  |  | 1305.5 |  |  | 1274.5 |  |  | 1149.5 |  |  | 1353.5 |  |  | 1367 |  |  | 1254.5 |  |  | 1234 |  |  | 1232.5 |  |  | 1206.5 |  |  | 1350.5 |  |  | 1339 |  |  | 1265.5 |  |  | 1330.5 |  |  | 1249 |  |  | 1248.5 |  |  | 1286 |  |  | 1286.5 |  |  | 1269.5 |  |  | 1224.5 |  |  | 1244 |  |  | 1342.5 |  |  | 1400.5 |  |  | 1227 |  |  | 1338.5 |  |  | 1196.5 |  |  | 1345 |  |  | 1336.5 |  |  | 1424.5 |  |  | 1341.5 |  |  | 1358.5 |  |  | 1242.5 |  |  | 1322.5 |  |  | 1275.5 |  |  | 1265.5 |  |  | 1220.5 |  |  | 1344.5 |  |  | 1384.5 |  |  | 1332 |  |  | 1330 |  |  | 1353.5 |  |  | 1304.5 |  |  | 1375
46 |  | 1338.5 |  |  | 1423.5 |  |  | 1366 |  |  | 1330.5 |  |  | 1436.5 |  |  | 1374.5 |  |  | 1446.5 |  |  | 1350.5 |  |  | 1313.5 |  |  | 1373.5 |  |  | 1314 |  |  | 1363.5 |  |  | 1434.5 |  |  | 1246.5 |  |  | 1268 |  |  | 1334.5 |  |  | 1470.5 |  |  | 1381.5 |  |  | 1487.5 |  |  | 1272.5 |  |  | 1325.5 |  |  | 1292.5 |  |  | 1340.5 |  |  | 1246.5 |  |  | 1246 |  |  | 1410.5 |  |  | 1323.5 |  |  | 1305.5 |  |  | 1386.5 |  |  | 1252 |  |  | 1364 |  |  | 1263.5 |  |  | 1282.5 |  |  | 1330.5 |  |  | 1234.5 |  |  | 1357 |  |  | 1275.5 |  |  | 1333 |  |  | 1289.5 |  |  | 1367.5 |  |  | 1271.5 |  |  | 1401.5 |  |  | 1252.5 |  |  | 1284 |  |  | 1510.5 |  |  | 1389 |  |  | 1300.5 |  |  | 1405.5 |  |  | 1378.5 |  |  | 1285.5 |  |  | 1289.5 |  |  | 1326.5 |  |  | 1330.5 |  |  | 1304.5 |  |  | 1364.5 |  |  | 1332.5 |  |  | 1267.5 |  |  | 1318 |  |  | 1440.5 |  |  | 1295.5 |  |  | 1289 |  |  | 1290.5 |  |  | 1403.5 |  |  | 1342.5 |  |  | 1269.5 |  |  | 1337 |  |  | 1381.5 |  |  | 1243 |  |  | 1281.5 |  |  | 1363.5 |  |  | 1342 |  |  | 1336.5 |  |  | 1310.5 |  |  | 1448.5 |  |  | 1407 |  |  | 1338 |  |  | 1302.5 |  |  | 1235.5 |  |  | 1246.5 |  |  | 1268.5 |  |  | 1283 |  |  | 1342.5 |  |  | 1343.5 |  |  | 1407.5 |  |  | 1382.5 |  |  | 1423.5 |  |  | 1379.5 |  |  | 1278.5 |  |  | 1298.5 |  |  | 1411.5 |  |  | 1404.5 |  |  | 1352 |  |  | 1241.5 |  |  | 1277 |  |  | 1304 |  |  | 1251 |  |  | 1420.5 |  |  | 1369.5 |  |  | 1303.5 |  |  | 1358.5 |  |  | 1334.5 |  |  | 1368 |  |  | 1358 |  |  | 1294.5 |  |  | 1308.5 |  |  | 1316.5 |  |  | 1342.5 |  |  | 1410.5 |  |  | 1384.5 |  |  | 1378.5 |  |  | 1403.5 |  |  | 1343.5 |  |  | 1401.5 |  |  | 1340.5 |  |  | 1351.5 |  |  | 1370.5 |  |  | 1349.5 |  |  | 1237.5 |  |  | 1377.5 |  |  | 1379.5 |  |  | 1411.5 |  |  | 1345.5 |  |  | 1315.5 |  |  | 1329.5 |  |  | 1357.5 |  |  | 1343 |  |  | 1291.5 |  |  | 1311.5 |  |  | 1231.5 |  |  | 1283.5 |  |  | 1426.5 |  |  | 1376 |  |  | 1244.5 |  |  | 1386.5 |  |  | 1295.5 |  |  | 1339.5 |  |  | 1327 |  |  | 1325.5 |  |  | 1418.5 |  |  | 1328 |  |  | 1361.5 |  |  | 1336 |  |  | 1333 |  |  | 1409.5 |  |  | 1380 |  |  | 1435.5 |  |  | 1302.5 |  |  | 1392.5 |  |  | 1272.5 |  |  | 1415.5 |  |  | 1365.5 |  |  | 1387.5 |  |  | 1358.5 |  |  | 1472.5 |  |  | 1352.5 |  |  | 1390 |  |  | 1297.5 |  |  | 1282 |  |  | 1280.5 |  |  | 1366.5 |  |  | 1363 |  |  | 1351.5 |  |  | 1332.5 |  |  | 1283.5 |  |  | 1286 |  |  | 1373.5 |  |  | 1259.5 |  |  | 1282.5 |  |  | 1382.5 |  |  | 1252.5 |  |  | 1308.5 |  |  | 1333 |  |  | 1300.5 |  |  | 1349.5 |  |  | 1307.5 |  |  | 1287.5 |  |  | 1352.5 |  |  | 1404.5 |  |  | 1225.5 |  |  | 1429 |  |  | 1415.5 |  |  | 1325.5 |  |  | 1410.5 |  |  | 1403.5 |  |  | 1256.5 |  |  | 1421.5 |  |  | 1394.5 |  |  | 1337.5 |  |  | 1370.5 |  |  | 1290.5 |  |  | 1330.5 |  |  | 1286.5 |  |  | 1182.5 |  |  | 1279 |  |  | 1278.5 |  |  | 1360.5 |  |  | 1285.5 |  |  | 1358.5 |  |  | 1387.5 |  |  | 1311.5 |  |  | 1373.5 |  |  | 1278.5 |  |  | 1317.5 |  |  | 1299.5 |  |  | 1300.5 |  |  | 1467.5 |  |  | 1330.5 |  |  | 1307.5 |  |  | 1387.5 |  |  | 1376.5 |  |  | 1366 |  |  | 1334.5 |  |  | 1309.5 |  |  | 1196 |  |  | 1438.5 |  |  | 1382 |  |  | 1346.5 |  |  | 1406.5 |  |  | 1464.5 |  |  | 1379.5 |  |  | 1284.5 |  |  | 1315.5 |  |  | 1311.5 |  |  | 1183.5 |  |  | 1290 |  |  | 1222.5 |  |  | 1182.5 |  |  | 1400.5 |  |  | 1280.5 |  |  | 1420 |  |  | 1272.5 |  |  | 1294.5 |  |  | 1362.5 |  |  | 1416.5 |  |  | 1415.5 |  |  | 1240.5 |  |  | 1292.5 |  |  | 1383.5 |  |  | 1341 |  |  | 1352 |  |  | 1254.5 |  |  | 1326.5 |  |  | 1332.5 |  |  | 1369 |  |  | 1390.5 |  |  | 1352.5 |  |  | 1300.5 |  |  | 1303 |  |  | 1329.5 |  |  | 1368.5 |  |  | 1320.5 |  |  | 1325.5 |  |  | 1332.5 |  |  | 1365.5 |  |  | 1399.5 |  |  | 1323.5 |  |  | 1444.5 |  |  | 1143 |  |  | 1245.5 |  |  | 1384.5 |  |  | 1298.5 |  |  | 1308.5 |  |  | 1348.5 |  |  | 1427 |  |  | 1298.5 |  |  | 1407.5 |  |  | 1358 |  |  | 1476.5 |  |  | 1350.5 |  |  | 1449 |  |  | 1375.5 |  |  | 1337.5 |  |  | 1453.5 |  |  | 1245.5 |  |  | 1365 |  |  | 1408 |  |  | 1374.5 |  |  | 1307.5 |  |  | 1369.5 |  |  | 1340.5 |  |  | 1439.5 |  |  | 1295.5 |  |  | 1323 |  |  | 1335.5 |  |  | 1370.5 |  |  | 1332 |  |  | 1283.5 |  |  | 1254.5 |  |  | 1332 |  |  | 1291.5 |  |  | 1305.5 |  |  | 1307.5 |  |  | 1302 |  |  | 1379.5 |  |  | 1278 |  |  | 1374.5 |  |  | 1301.5 |  |  | 1324.5 |  |  | 1298 |  |  | 1281.5 |  |  | 1427.5 |  |  | 1259.5 |  |  | 1330 |  |  | 1242.5 |  |  | 1258.5 |  |  | 1445.5 |  |  | 1430.5 |  |  | 1293.5 |  |  | 1277 |  |  | 1309.5 |  |  | 1459.5 |  |  | 1423.5 |  |  | 1276 |  |  | 1329 |  |  | 1447.5 |  |  | 1372.5 |  |  | 1276.5 |  |  | 1327.5 |  |  | 1368.5 |  |  | 1371.5 |  |  | 1313.5 |  |  | 1365.5 |  |  | 1271.5 |  |  | 1335.5 |  |  | 1345 |  |  | 1362.5 |  |  | 1436.5 |  |  | 1498.5 |  |  | 1445.5 |  |  | 1350 |  |  | 1394.5 |  |  | 1386.5 |  |  | 1360.5 |  |  | 1186.5 |  |  | 1400.5 |  |  | 1331 |  |  | 1283 |  |  | 1241 |  |  | 1331 |  |  | 1299.5 |  |  | 1357 |  |  | 1361.5 |  |  | 1274 |  |  | 1327.5 |  |  | 1430.5 |  |  | 1376.5 |  |  | 1353.5 |  |  | 1311.5 |  |  | 1347 |  |  | 1332.5 |  |  | 1375.5 |  |  | 1255.5 |  |  | 1429 |  |  | 1362.5 |  |  | 1303.5 |  |  | 1283.5 |  |  | 1398 |  |  | 1316.5 |  |  | 1209.5 |  |  | 1348.5 |  |  | 1288.5 |  |  | 1356.5 |  |  | 1260.5 |  |  | 1436.5 |  |  | 1327.5 |  |  | 1402.5 |  |  | 1220.5 |  |  | 1239 |  |  | 1338.5 |  |  | 1341.5 |  |  | 1312.5 |  |  | 1369.5 |  |  | 1461.5 |  |  | 1327 |  |  | 1293.5 |  |  | 1380 |  |  | 1310 |  |  | 1315.5 |  |  | 1422.5 |  |  | 1307.5 |  |  | 1288 |  |  | 1401.5 |  |  | 1372.5 |  |  | 1368.5 |  |  | 1209 |  |  | 1327.5 |  |  | 1214.5 |  |  | 1434.5 |  |  | 1267.5 |  |  | 1294.5 |  |  | 1304 |  |  | 1283.5 |  |  | 1313 |  |  | 1298.5 |  |  | 1326.5 |  |  | 1318.5 |  |  | 1415 |  |  | 1254.5 |  |  | 1384 |  |  | 1358 |  |  | 1298.5 |  |  | 1279.5 |  |  | 1325.5 |  |  | 1433.5 |  |  | 1397 |  |  | 1354.5 |  |  | 1311.5 |  |  | 1248.5 |  |  | 1328 |  |  | 1388.5 |  |  | 1273.5 |  |  | 1288.5 |  |  | 1283.5 |  |  | 1411 |  |  | 1226.5 |  |  | 1322.5 |  |  | 1380.5 |  |  | 1359.5 |  |  | 1310.5 |  |  | 1340.5 |  |  | 1387 |  |  | 1317.5 |  |  | 1246.5 |  |  | 1355 |  |  | 1279.5 |  |  | 1299.5 |  |  | 1330.5 |  |  | 1337 |  |  | 1344.5 |  |  | 1320.5 |  |  | 1321.5 |  |  | 1342.5 |  |  | 1386.5 |  |  | 1425 |  |  | 1344 |  |  | 1256.5 |  |  | 1373.5 |  |  | 1346.5 |  |  | 1295.5 |  |  | 1301 |  |  | 1366 |  |  | 1268 |  |  | 1396.5 |  |  | 1315 |  |  | 1378.5 |  |  | 1403.5 |  |  | 1317 |  |  | 1292.5 |  |  | 1330.5 |  |  | 1339.5 |  |  | 1445.5 |  |  | 1268.5 |  |  | 1313 |  |  | 1308 |  |  | 1206.5 |  |  | 1365.5 |  |  | 1281 |  |  | 1218.5 |  |  | 1397.5 |  |  | 1319 |  |  | 1480.5 |  |  | 1414.5 |  |  | 1236 |  |  | 1378.5 |  |  | 1339.5 |  |  | 1324 |  |  | 1373.5 |  |  | 1252 |  |  | 1459.5 |  |  | 1433 |  |  | 1266.5 |  |  | 1315.5 |  |  | 1327.5 |  |  | 1311.5 |  |  | 1317.5 |  |  | 1239.5 |  |  | 1407 |  |  | 1303.5 |  |  | 1319.5 |  |  | 1247.5 |  |  | 1368.5 |  |  | 1297.5 |  |  | 1341 |  |  | 1335.5 |  |  | 1300 |  |  | 1333.5 |  |  | 1300.5 |  |  | 1317.5 |  |  | 1297.5 |  |  | 1355.5 |  |  | 1340.5 |  |  | 1284.5 |  |  | 1390.5 |  |  | 1310.5 |  |  | 1389 |  |  | 1332.5 |  |  | 1219 |  |  | 1312 |  |  | 1364.5 |  |  | 1250 |  |  | 1251.5 |  |  | 1300.5 |  |  | 1351.5 |  |  | 1288.5 |  |  | 1337.5 |  |  | 1428.5 |  |  | 1393.5 |  |  | 1295 |  |  | 1384 |  |  | 1248.5 |  |  | 1247.5 |  |  | 1361 |  |  | 1301.5 |  |  | 1342.5 |  |  | 1281.5 |  |  | 1239.5 |  |  | 1290.5 |  |  | 1306 |  |  | 1343.5 |  |  | 1346.5 |  |  | 1294.5 |  |  | 1280 |  |  | 1392.5 |  |  | 1355.5 |  |  | 1352.5 |  |  | 1450.5 |  |  | 1428.5 |  |  | 1309.5 |  |  | 1403.5 |  |  | 1134.5 |  |  | 1302.5 |  |  | 1273 |  |  | 1415.5 |  |  | 1340.5 |  |  | 1393.5 |  |  | 1281.5 |  |  | 1213.5 |  |  | 1288.5 |  |  | 1286.5 |  |  | 1178 |  |  | 1253.5 |  |  | 1390.5 |  |  | 1425.5 |  |  | 1241 |  |  | 1290.5 |  |  | 1275 |  |  | 1347.5 |  |  | 1302.5 |  |  | 1267.5 |  |  | 1311 |  |  | 1236.5 |  |  | 1372 |  |  | 1343 |  |  | 1366.5 |  |  | 1299 |  |  | 1338 |  |  | 1380.5 |  |  | 1410.5 |  |  | 1246.5 |  |  | 1373 |  |  | 1373.5 |  |  | 1307.5 |  |  | 1183.5 |  |  | 1446.5 |  |  | 1326.5 |  |  | 1350.5 |  |  | 1289.5 |  |  | 1344.5 |  |  | 1267 |  |  | 1454.5 |  |  | 1236 |  |  | 1281.5 |  |  | 1241.5 |  |  | 1407.5 |  |  | 1404 |  |  | 1394 |  |  | 1449 |  |  | 1329.5 |  |  | 1287 |  |  | 1422.5 |  |  | 1374.5 |  |  | 1241.5 |  |  | 1350.5 |  |  | 1286.5 |  |  | 1353.5 |  |  | 1343.5 |  |  | 1355.5 |  |  | 1391 |  |  | 1269.5 |  |  | 1257.5 |  |  | 1362.5 |  |  | 1254.5 |  |  | 1249 |  |  | 1312.5 |  |  | 1351 |  |  | 1321.5 |  |  | 1332.5 |  |  | 1332.5 |  |  | 1269.5 |  |  | 1270 |  |  | 1284.5 |  |  | 1183 |  |  | 1286.5 |  |  | 1337.5 |  |  | 1443.5 |  |  | 1431.5 |  |  | 1345.5 |  |  | 1272.5 |  |  | 1242.5 |  |  | 1407.5 |  |  | 1288.5 |  |  | 1308 |  |  | 1335.5 |  |  | 1269.5 |  |  | 1280.5 |  |  | 1313.5 |  |  | 1329.5 |  |  | 1226 |  |  | 1287 |  |  | 1312.5 |  |  | 1280 |  |  | 1452.5 |  |  | 1302.5 |  |  | 1401.5 |  |  | 1432.5 |  |  | 1278.5 |  |  | 1362.5 |  |  | 1330.5 |  |  | 1306.5 |  |  | 1342 |  |  | 1365.5 |  |  | 1422.5 |  |  | 1462.5 |  |  | 1245 |  |  | 1349.5 |  |  | 1285.5 |  |  | 1419 |  |  | 1220 |  |  | 1343.5 |  |  | 1257 |  |  | 1197 |  |  | 1226.5 |  |  | 1272 |  |  | 1441.5 |  |  | 1429.5 |  |  | 1342.5 |  |  | 1298.5 |  |  | 1253.5 |  |  | 1379.5 |  |  | 1207.5 |  |  | 1314.5 |  |  | 1329.5 |  |  | 1324.5 |  |  | 1282 |  |  | 1250 |  |  | 1345.5 |  |  | 1296.5 |  |  | 1341.5 |  |  | 1380.5 |  |  | 1262.5 |  |  | 1333.5 |  |  | 1399.5 |  |  | 1279.5 |  |  | 1414 |  |  | 1234.5 |  |  | 1253 |  |  | 1276.5 |  |  | 1505.5 |  |  | 1352.5 |  |  | 1390 |  |  | 1371.5 |  |  | 1277.5 |  |  | 1225 |  |  | 1396.5 |  |  | 1283.5 |  |  | 1409.5 |  |  | 1327.5 |  |  | 1322.5 |  |  | 1328.5 |  |  | 1300 |  |  | 1285.5 |  |  | 1249.5 |  |  | 1354.5 |  |  | 1480.5 |  |  | 1234 |  |  | 1239.5 |  |  | 1435.5 |  |  | 1316 |  |  | 1348.5 |  |  | 1362.5 |  |  | 1303 |  |  | 1367.5 |  |  | 1402.5 |  |  | 1317.5 |  |  | 1282 |  |  | 1190.5 |  |  | 1342.5 |  |  | 1275 |  |  | 1312.5 |  |  | 1424.5 |  |  | 1340.5 |  |  | 1146.5 |  |  | 1391.5 |  |  | 1474.5 |  |  | 1264.5 |  |  | 1304 |  |  | 1289 |  |  | 1205.5 |  |  | 1345.5 |  |  | 1339.5 |  |  | 1313 |  |  | 1369.5 |  |  | 1321.5 |  |  | 1330.5 |  |  | 1184.5 |  |  | 1317.5 |  |  | 1316.5 |  |  | 1208.5 |  |  | 1331.5 |  |  | 1190.5 |  |  | 1347 |  |  | 1288.5 |  |  | 1300.5 |  |  | 1293.5 |  |  | 1435.5 |  |  | 1380.5 |  |  | 1293.5 |  |  | 1323.5 |  |  | 1321.5 |  |  | 1275.5 |  |  | 1373.5 |  |  | 1328.5 |  |  | 1314.5 |  |  | 1378.5 |  |  | 1423 |  |  | 1333.5 |  |  | 1347.5 |  |  | 1317 |  |  | 1399.5 |  |  | 1364.5 |  |  | 1432 |  |  | 1324.5 |  |  | 1442.5 |  |  | 1424.5 |  |  | 1414 |  |  | 1358.5 |  |  | 1397.5 |  |  | 1315.5 |  |  | 1194.5 |  |  | 1335.5 |  |  | 1237 |  |  | 1302.5 |  |  | 1395 |  |  | 1367 |  |  | 1431.5 |  |  | 1312.5 |  |  | 1285.5 |  |  | 1249.5 |  |  | 1331.5 |  |  | 1360.5 |  |  | 1307 |  |  | 1343.5 |  |  | 1378 |  |  | 1266.5 |  |  | 1367 |  |  | 1330 |  |  | 1414 |  |  | 1327.5 |  |  | 1293 |  |  | 1401.5 |  |  | 1391.5 |  |  | 1394.5 |  |  | 1494.5 |  |  | 1361.5 |  |  | 1367 |  |  | 1355.5 |  |  | 1411.5 |  |  | 1519.5 |  |  | 1377 |  |  | 1319.5 |  |  | 1298.5 |  |  | 1394.5 |  |  | 1374.5 |  |  | 1333 |  |  | 1387 |  |  | 1345 |  |  | 1349.5 |  |  | 1383 |  |  | 1429 |  |  | 1402.5 |  |  | 1268.5 |  |  | 1222.5 |  |  | 1335.5 |  |  | 1408.5 |  |  | 1446.5 |  |  | 1401.5 |  |  | 1355.5 |  |  | 1245.5 |  |  | 1226 |  |  | 1347.5 |  |  | 1307 |  |  | 1392.5 |  |  | 1383.5 |  |  | 1314.5 |  |  | 1426.5 |  |  | 1356 |  |  | 1311.5 |  |  | 1301 |  |  | 1302.5 |  |  | 1385.5 |  |  | 1213 |  |  | 1364 |  |  | 1293.5 |  |  | 1312 |  |  | 1424.5 |  |  | 1208.5 |  |  | 1293.5 |  |  | 1324.5 |  |  | 1290.5 |  |  | 1407.5 |  |  | 1269.5 |  |  | 1226 |  |  | 1374.5 |  |  | 1351.5 |  |  | 1246.5 |  |  | 1351.5 |  |  | 1254.5 |  |  | 1304.5 |  |  | 1362.5 |  |  | 1330.5 |  |  | 1343.5 |  |  | 1348.5 |  |  | 1281.5 |  |  | 1286.5 |  |  | 1337 |  |  | 1207.5 |  |  | 1285.5 |  |  | 1393 |  |  | 1273.5 |  |  | 1235.5 |  |  | 1274.5 |  |  | 1281.5 |  |  | 1421 |  |  | 1425.5 |  |  | 1364.5 |  |  | 1245.5 |  |  | 1350.5 |  |  | 1314 |  |  | 1355.5 |  |  | 1360.5 |  |  | 1406.5 |  |  | 1412.5 |  |  | 1352.5 |  |  | 1225.5 |  |  | 1393.5 |  |  | 1427.5 |  |  | 1368.5 |  |  | 1321.5 |  |  | 1396.5 |  |  | 1327 |  |  | 1338.5 |  |  | 1361.5 |  |  | 1394.5 |  |  | 1333.5 |  |  | 1243.5 |  |  | 1328.5 |  |  | 1375 |  |  | 1272.5 |  |  | 1283 |  |  | 1257.5 |  |  | 1368.5 |  |  | 1369.5 |  |  | 1297 |  |  | 1296 |  |  | 1302.5 |  |  | 1347.5 |  |  | 1213.5 |  |  | 1389.5 |  |  | 1311.5 |  |  | 1336.5 |  |  | 1270.5 |  |  | 1304.5 |  |  | 1288.5 |  |  | 1359.5 |  |  | 1284.5 |  |  | 1340.5 |  |  | 1291.5 |  |  | 1391.5 |  |  | 1364.5 |  |  | 1326.5 |  |  | 1313.5 |  |  | 1358.5 |  |  | 1291.5 |  |  | 1256.5 |  |  | 1354.5 |  |  | 1364.5 |  |  | 1383 |  |  | 1419.5 |  |  | 1315.5 |  |  | 1308.5 |  |  | 1392 |  |  | 1337.5 |  |  | 1322.5 |  |  | 1353.5 |  |  | 1329.5 |  |  | 1401 |  |  | 1206.5 |  |  | 1261.5 |  |  | 1224 |  |  | 1249 |  |  | 1331 |  |  | 1287.5 |  |  | 1322.5 |  |  | 1355.5 |  |  | 1464.5 |  |  | 1332 |  |  | 1323.5 |  |  | 1373.5 |  |  | 1220 |  |  | 1299 |  |  | 1377.5 |  |  | 1316.5 |  |  | 1376 |  |  | 1332.5 |  |  | 1407 |  |  | 1221.5 |  |  | 1248.5 |  |  | 1392 |  |  | 1409.5 |  |  | 1243.5 |  |  | 1247.5 |  |  | 1386 |  |  | 1361.5 |  |  | 1297.5 |  |  | 1283.5 |  |  | 1290.5 |  |  | 1298.5 |  |  | 1434.5 |  |  | 1279.5 |  |  | 1327.5 |  |  | 1347.5 |  |  | 1334.5 |  |  | 1397 |  |  | 1317.5 |  |  | 1360.5 |  |  | 1349.5 |  |  | 1329.5 |  |  | 1288.5 |  |  | 1453.5 |  |  | 1409.5 |  |  | 1358.5 |  |  | 1372 |  |  | 1339.5 |  |  | 1318 |  |  | 1390.5 |  |  | 1440.5 |  |  | 1469.5 |  |  | 1297.5 |  |  | 1334.5 |  |  | 1289.5 |  |  | 1173.5 |  |  | 1392.5 |  |  | 1391 |  |  | 1293.5 |  |  | 1273 |  |  | 1279.5 |  |  | 1232.5 |  |  | 1365.5 |  |  | 1386 |  |  | 1304.5 |  |  | 1377.5 |  |  | 1264 |  |  | 1263.5 |  |  | 1307 |  |  | 1301.5 |  |  | 1295.5 |  |  | 1263.5 |  |  | 1291 |  |  | 1381.5 |  |  | 1439.5 |  |  | 1256 |  |  | 1377.5 |  |  | 1235.5 |  |  | 1384 |  |  | 1362.5 |  |  | 1448.5 |  |  | 1356.5 |  |  | 1373.5 |  |  | 1281.5 |  |  | 1369.5 |  |  | 1314.5 |  |  | 1286.5 |  |  | 1249.5 |  |  | 1359.5 |  |  | 1423.5 |  |  | 1347 |  |  | 1359 |  |  | 1382.5 |  |  | 1351.5 |  |  | 1414
47 |  | 1353.5 |  |  | 1447.5 |  |  | 1381 |  |  | 1359.5 |  |  | 1483.5 |  |  | 1395.5 |  |  | 1475.5 |  |  | 1389.5 |  |  | 1352.5 |  |  | 1412.5 |  |  | 1340 |  |  | 1402.5 |  |  | 1460.5 |  |  | 1285.5 |  |  | 1289 |  |  | 1355.5 |  |  | 1496.5 |  |  | 1420.5 |  |  | 1502.5 |  |  | 1287.5 |  |  | 1364.5 |  |  | 1331.5 |  |  | 1355.5 |  |  | 1293.5 |  |  | 1261 |  |  | 1457.5 |  |  | 1370.5 |  |  | 1352.5 |  |  | 1415.5 |  |  | 1281 |  |  | 1393 |  |  | 1302.5 |  |  | 1321.5 |  |  | 1377.5 |  |  | 1263.5 |  |  | 1381 |  |  | 1301.5 |  |  | 1380 |  |  | 1313.5 |  |  | 1406.5 |  |  | 1286.5 |  |  | 1440.5 |  |  | 1291.5 |  |  | 1331 |  |  | 1531.5 |  |  | 1404 |  |  | 1326.5 |  |  | 1420.5 |  |  | 1404.5 |  |  | 1314.5 |  |  | 1313.5 |  |  | 1341.5 |  |  | 1356.5 |  |  | 1343.5 |  |  | 1411.5 |  |  | 1371.5 |  |  | 1282.5 |  |  | 1342 |  |  | 1455.5 |  |  | 1319.5 |  |  | 1315 |  |  | 1316.5 |  |  | 1424.5 |  |  | 1366.5 |  |  | 1284.5 |  |  | 1384 |  |  | 1420.5 |  |  | 1290 |  |  | 1320.5 |  |  | 1410.5 |  |  | 1381 |  |  | 1362.5 |  |  | 1325.5 |  |  | 1495.5 |  |  | 1428 |  |  | 1359 |  |  | 1323.5 |  |  | 1261.5 |  |  | 1267.5 |  |  | 1307.5 |  |  | 1312 |  |  | 1363.5 |  |  | 1382.5 |  |  | 1422.5 |  |  | 1421.5 |  |  | 1438.5 |  |  | 1405.5 |  |  | 1293.5 |  |  | 1337.5 |  |  | 1435.5 |  |  | 1419.5 |  |  | 1373 |  |  | 1280.5 |  |  | 1316 |  |  | 1328 |  |  | 1298 |  |  | 1441.5 |  |  | 1384.5 |  |  | 1318.5 |  |  | 1379.5 |  |  | 1373.5 |  |  | 1394 |  |  | 1373 |  |  | 1315.5 |  |  | 1347.5 |  |  | 1337.5 |  |  | 1381.5 |  |  | 1449.5 |  |  | 1423.5 |  |  | 1393.5 |  |  | 1442.5 |  |  | 1390.5 |  |  | 1425.5 |  |  | 1387.5 |  |  | 1375.5 |  |  | 1409.5 |  |  | 1396.5 |  |  | 1252.5 |  |  | 1416.5 |  |  | 1394.5 |  |  | 1426.5 |  |  | 1366.5 |  |  | 1339.5 |  |  | 1376.5 |  |  | 1396.5 |  |  | 1364 |  |  | 1306.5 |  |  | 1337.5 |  |  | 1278.5 |  |  | 1307.5 |  |  | 1473.5 |  |  | 1415 |  |  | 1291.5 |  |  | 1412.5 |  |  | 1321.5 |  |  | 1360.5 |  |  | 1374 |  |  | 1340.5 |  |  | 1439.5 |  |  | 1375 |  |  | 1382.5 |  |  | 1375 |  |  | 1372 |  |  | 1448.5 |  |  | 1419 |  |  | 1456.5 |  |  | 1341.5 |  |  | 1421.5 |  |  | 1293.5 |  |  | 1454.5 |  |  | 1380.5 |  |  | 1426.5 |  |  | 1405.5 |  |  | 1496.5 |  |  | 1391.5 |  |  | 1414 |  |  | 1336.5 |  |  | 1306 |  |  | 1309.5 |  |  | 1405.5 |  |  | 1392 |  |  | 1380.5 |  |  | 1358.5 |  |  | 1330.5 |  |  | 1325 |  |  | 1394.5 |  |  | 1283.5 |  |  | 1329.5 |  |  | 1421.5 |  |  | 1299.5 |  |  | 1329.5 |  |  | 1380 |  |  | 1326.5 |  |  | 1388.5 |  |  | 1346.5 |  |  | 1326.5 |  |  | 1367.5 |  |  | 1433.5 |  |  | 1249.5 |  |  | 1468 |  |  | 1441.5 |  |  | 1372.5 |  |  | 1457.5 |  |  | 1427.5 |  |  | 1295.5 |  |  | 1436.5 |  |  | 1441.5 |  |  | 1376.5 |  |  | 1409.5 |  |  | 1329.5 |  |  | 1345.5 |  |  | 1307.5 |  |  | 1203.5 |  |  | 1326 |  |  | 1293.5 |  |  | 1381.5 |  |  | 1332.5 |  |  | 1387.5 |  |  | 1408.5 |  |  | 1340.5 |  |  | 1397.5 |  |  | 1317.5 |  |  | 1356.5 |  |  | 1338.5 |  |  | 1339.5 |  |  | 1493.5 |  |  | 1369.5 |  |  | 1322.5 |  |  | 1402.5 |  |  | 1400.5 |  |  | 1413 |  |  | 1360.5 |  |  | 1335.5 |  |  | 1243 |  |  | 1485.5 |  |  | 1429 |  |  | 1370.5 |  |  | 1432.5 |  |  | 1493.5 |  |  | 1418.5 |  |  | 1308.5 |  |  | 1362.5 |  |  | 1350.5 |  |  | 1222.5 |  |  | 1329 |  |  | 1261.5 |  |  | 1203.5 |  |  | 1429.5 |  |  | 1319.5 |  |  | 1446 |  |  | 1287.5 |  |  | 1333.5 |  |  | 1401.5 |  |  | 1455.5 |  |  | 1436.5 |  |  | 1279.5 |  |  | 1313.5 |  |  | 1422.5 |  |  | 1380 |  |  | 1391 |  |  | 1293.5 |  |  | 1355.5 |  |  | 1353.5 |  |  | 1393 |  |  | 1429.5 |  |  | 1391.5 |  |  | 1326.5 |  |  | 1350 |  |  | 1368.5 |  |  | 1407.5 |  |  | 1335.5 |  |  | 1372.5 |  |  | 1353.5 |  |  | 1386.5 |  |  | 1425.5 |  |  | 1362.5 |  |  | 1491.5 |  |  | 1190 |  |  | 1260.5 |  |  | 1413.5 |  |  | 1327.5 |  |  | 1347.5 |  |  | 1363.5 |  |  | 1448 |  |  | 1313.5 |  |  | 1433.5 |  |  | 1387 |  |  | 1523.5 |  |  | 1389.5 |  |  | 1496 |  |  | 1396.5 |  |  | 1363.5 |  |  | 1474.5 |  |  | 1271.5 |  |  | 1404 |  |  | 1432 |  |  | 1413.5 |  |  | 1322.5 |  |  | 1390.5 |  |  | 1366.5 |  |  | 1465.5 |  |  | 1321.5 |  |  | 1347 |  |  | 1374.5 |  |  | 1399.5 |  |  | 1353 |  |  | 1298.5 |  |  | 1269.5 |  |  | 1353 |  |  | 1312.5 |  |  | 1334.5 |  |  | 1346.5 |  |  | 1341 |  |  | 1418.5 |  |  | 1302 |  |  | 1389.5 |  |  | 1316.5 |  |  | 1363.5 |  |  | 1345 |  |  | 1320.5 |  |  | 1453.5 |  |  | 1298.5 |  |  | 1359 |  |  | 1266.5 |  |  | 1297.5 |  |  | 1484.5 |  |  | 1451.5 |  |  | 1317.5 |  |  | 1324 |  |  | 1333.5 |  |  | 1485.5 |  |  | 1438.5 |  |  | 1300 |  |  | 1368 |  |  | 1486.5 |  |  | 1396.5 |  |  | 1302.5 |  |  | 1351.5 |  |  | 1383.5 |  |  | 1392.5 |  |  | 1360.5 |  |  | 1389.5 |  |  | 1310.5 |  |  | 1364.5 |  |  | 1371 |  |  | 1386.5 |  |  | 1457.5 |  |  | 1513.5 |  |  | 1474.5 |  |  | 1365 |  |  | 1415.5 |  |  | 1433.5 |  |  | 1407.5 |  |  | 1201.5 |  |  | 1429.5 |  |  | 1355 |  |  | 1322 |  |  | 1288 |  |  | 1360 |  |  | 1325.5 |  |  | 1383 |  |  | 1376.5 |  |  | 1303 |  |  | 1366.5 |  |  | 1469.5 |  |  | 1397.5 |  |  | 1392.5 |  |  | 1350.5 |  |  | 1362 |  |  | 1347.5 |  |  | 1422.5 |  |  | 1279.5 |  |  | 1444 |  |  | 1386.5 |  |  | 1332.5 |  |  | 1322.5 |  |  | 1424 |  |  | 1363.5 |  |  | 1256.5 |  |  | 1377.5 |  |  | 1309.5 |  |  | 1380.5 |  |  | 1289.5 |  |  | 1475.5 |  |  | 1353.5 |  |  | 1449.5 |  |  | 1246.5 |  |  | 1263 |  |  | 1353.5 |  |  | 1388.5 |  |  | 1333.5 |  |  | 1390.5 |  |  | 1487.5 |  |  | 1356 |  |  | 1340.5 |  |  | 1419 |  |  | 1336 |  |  | 1344.5 |  |  | 1469.5 |  |  | 1346.5 |  |  | 1317 |  |  | 1430.5 |  |  | 1411.5 |  |  | 1415.5 |  |  | 1235 |  |  | 1356.5 |  |  | 1229.5 |  |  | 1455.5 |  |  | 1291.5 |  |  | 1309.5 |  |  | 1330 |  |  | 1322.5 |  |  | 1337 |  |  | 1345.5 |  |  | 1347.5 |  |  | 1344.5 |  |  | 1430 |  |  | 1293.5 |  |  | 1413 |  |  | 1382 |  |  | 1313.5 |  |  | 1300.5 |  |  | 1372.5 |  |  | 1459.5 |  |  | 1421 |  |  | 1401.5 |  |  | 1358.5 |  |  | 1269.5 |  |  | 1367 |  |  | 1417.5 |  |  | 1299.5 |  |  | 1309.5 |  |  | 1298.5 |  |  | 1426 |  |  | 1247.5 |  |  | 1351.5 |  |  | 1406.5 |  |  | 1398.5 |  |  | 1331.5 |  |  | 1379.5 |  |  | 1416 |  |  | 1332.5 |  |  | 1261.5 |  |  | 1376 |  |  | 1294.5 |  |  | 1323.5 |  |  | 1351.5 |  |  | 1363 |  |  | 1373.5 |  |  | 1349.5 |  |  | 1350.5 |  |  | 1366.5 |  |  | 1425.5 |  |  | 1454 |  |  | 1373 |  |  | 1285.5 |  |  | 1412.5 |  |  | 1393.5 |  |  | 1319.5 |  |  | 1316 |  |  | 1405 |  |  | 1307 |  |  | 1417.5 |  |  | 1330 |  |  | 1399.5 |  |  | 1424.5 |  |  | 1338 |  |  | 1316.5 |  |  | 1377.5 |  |  | 1354.5 |  |  | 1471.5 |  |  | 1283.5 |  |  | 1334 |  |  | 1355 |  |  | 1221.5 |  |  | 1391.5 |  |  | 1302 |  |  | 1233.5 |  |  | 1412.5 |  |  | 1358 |  |  | 1501.5 |  |  | 1440.5 |  |  | 1251 |  |  | 1402.5 |  |  | 1386.5 |  |  | 1339 |  |  | 1412.5 |  |  | 1281 |  |  | 1506.5 |  |  | 1459 |  |  | 1313.5 |  |  | 1341.5 |  |  | 1356.5 |  |  | 1326.5 |  |  | 1356.5 |  |  | 1278.5 |  |  | 1422 |  |  | 1332.5 |  |  | 1348.5 |  |  | 1276.5 |  |  | 1407.5 |  |  | 1344.5 |  |  | 1365 |  |  | 1356.5 |  |  | 1326 |  |  | 1362.5 |  |  | 1326.5 |  |  | 1356.5 |  |  | 1312.5 |  |  | 1376.5 |  |  | 1361.5 |  |  | 1305.5 |  |  | 1429.5 |  |  | 1331.5 |  |  | 1428 |  |  | 1353.5 |  |  | 1234 |  |  | 1338 |  |  | 1393.5 |  |  | 1274 |  |  | 1266.5 |  |  | 1326.5 |  |  | 1398.5 |  |  | 1309.5 |  |  | 1376.5 |  |  | 1467.5 |  |  | 1422.5 |  |  | 1324 |  |  | 1431 |  |  | 1269.5 |  |  | 1271.5 |  |  | 1376 |  |  | 1348.5 |  |  | 1366.5 |  |  | 1328.5 |  |  | 1278.5 |  |  | 1305.5 |  |  | 1335 |  |  | 1369.5 |  |  | 1370.5 |  |  | 1309.5 |  |  | 1295 |  |  | 1439.5 |  |  | 1394.5 |  |  | 1376.5 |  |  | 1497.5 |  |  | 1449.5 |  |  | 1348.5 |  |  | 1450.5 |  |  | 1158.5 |  |  | 1349.5 |  |  | 1312 |  |  | 1444.5 |  |  | 1369.5 |  |  | 1417.5 |  |  | 1310.5 |  |  | 1260.5 |  |  | 1303.5 |  |  | 1315.5 |  |  | 1202 |  |  | 1268.5 |  |  | 1429.5 |  |  | 1451.5 |  |  | 1262 |  |  | 1337.5 |  |  | 1304 |  |  | 1368.5 |  |  | 1341.5 |  |  | 1296.5 |  |  | 1337 |  |  | 1265.5 |  |  | 1411 |  |  | 1390 |  |  | 1395.5 |  |  | 1328 |  |  | 1377 |  |  | 1404.5 |  |  | 1436.5 |  |  | 1267.5 |  |  | 1412 |  |  | 1394.5 |  |  | 1346.5 |  |  | 1209.5 |  |  | 1461.5 |  |  | 1341.5 |  |  | 1389.5 |  |  | 1313.5 |  |  | 1383.5 |  |  | 1293 |  |  | 1480.5 |  |  | 1257 |  |  | 1307.5 |  |  | 1280.5 |  |  | 1446.5 |  |  | 1443 |  |  | 1433 |  |  | 1478 |  |  | 1368.5 |  |  | 1334 |  |  | 1443.5 |  |  | 1413.5 |  |  | 1288.5 |  |  | 1371.5 |  |  | 1315.5 |  |  | 1382.5 |  |  | 1382.5 |  |  | 1384.5 |  |  | 1430 |  |  | 1308.5 |  |  | 1286.5 |  |  | 1386.5 |  |  | 1280.5 |  |  | 1278 |  |  | 1333.5 |  |  | 1380 |  |  | 1368.5 |  |  | 1371.5 |  |  | 1371.5 |  |  | 1308.5 |  |  | 1294 |  |  | 1331.5 |  |  | 1204 |  |  | 1325.5 |  |  | 1358.5 |  |  | 1490.5 |  |  | 1446.5 |  |  | 1366.5 |  |  | 1311.5 |  |  | 1266.5 |  |  | 1422.5 |  |  | 1327.5 |  |  | 1347 |  |  | 1374.5 |  |  | 1316.5 |  |  | 1309.5 |  |  | 1337.5 |  |  | 1368.5 |  |  | 1247 |  |  | 1316 |  |  | 1359.5 |  |  | 1327 |  |  | 1473.5 |  |  | 1326.5 |  |  | 1416.5 |  |  | 1471.5 |  |  | 1299.5 |  |  | 1388.5 |  |  | 1369.5 |  |  | 1335.5 |  |  | 1363 |  |  | 1391.5 |  |  | 1461.5 |  |  | 1488.5 |  |  | 1284 |  |  | 1388.5 |  |  | 1314.5 |  |  | 1466 |  |  | 1241 |  |  | 1390.5 |  |  | 1286 |  |  | 1218 |  |  | 1247.5 |  |  | 1296 |  |  | 1480.5 |  |  | 1444.5 |  |  | 1389.5 |  |  | 1324.5 |  |  | 1282.5 |  |  | 1394.5 |  |  | 1246.5 |  |  | 1335.5 |  |  | 1368.5 |  |  | 1353.5 |  |  | 1303 |  |  | 1289 |  |  | 1371.5 |  |  | 1322.5 |  |  | 1362.5 |  |  | 1395.5 |  |  | 1286.5 |  |  | 1359.5 |  |  | 1420.5 |  |  | 1300.5 |  |  | 1461 |  |  | 1263.5 |  |  | 1300 |  |  | 1302.5 |  |  | 1520.5 |  |  | 1399.5 |  |  | 1429 |  |  | 1395.5 |  |  | 1303.5 |  |  | 1264 |  |  | 1422.5 |  |  | 1322.5 |  |  | 1456.5 |  |  | 1348.5 |  |  | 1343.5 |  |  | 1349.5 |  |  | 1315 |  |  | 1306.5 |  |  | 1273.5 |  |  | 1378.5 |  |  | 1504.5 |  |  | 1273 |  |  | 1278.5 |  |  | 1459.5 |  |  | 1355 |  |  | 1387.5 |  |  | 1401.5 |  |  | 1350 |  |  | 1414.5 |  |  | 1428.5 |  |  | 1364.5 |  |  | 1308 |  |  | 1229.5 |  |  | 1381.5 |  |  | 1322 |  |  | 1359.5 |  |  | 1439.5 |  |  | 1387.5 |  |  | 1193.5 |  |  | 1438.5 |  |  | 1513.5 |  |  | 1279.5 |  |  | 1333 |  |  | 1313 |  |  | 1234.5 |  |  | 1366.5 |  |  | 1360.5 |  |  | 1352 |  |  | 1395.5 |  |  | 1347.5 |  |  | 1351.5 |  |  | 1223.5 |  |  | 1346.5 |  |  | 1337.5 |  |  | 1247.5 |  |  | 1357.5 |  |  | 1229.5 |  |  | 1368 |  |  | 1303.5 |  |  | 1339.5 |  |  | 1332.5 |  |  | 1482.5 |  |  | 1404.5 |  |  | 1332.5 |  |  | 1344.5 |  |  | 1347.5 |  |  | 1314.5 |  |  | 1399.5 |  |  | 1357.5 |  |  | 1353.5 |  |  | 1393.5 |  |  | 1449 |  |  | 1354.5 |  |  | 1371.5 |  |  | 1341 |  |  | 1423.5 |  |  | 1388.5 |  |  | 1447 |  |  | 1353.5 |  |  | 1481.5 |  |  | 1471.5 |  |  | 1435 |  |  | 1387.5 |  |  | 1426.5 |  |  | 1354.5 |  |  | 1233.5 |  |  | 1364.5 |  |  | 1258 |  |  | 1349.5 |  |  | 1442 |  |  | 1414 |  |  | 1470.5 |  |  | 1351.5 |  |  | 1324.5 |  |  | 1288.5 |  |  | 1378.5 |  |  | 1399.5 |  |  | 1354 |  |  | 1382.5 |  |  | 1407 |  |  | 1313.5 |  |  | 1406 |  |  | 1345 |  |  | 1440 |  |  | 1374.5 |  |  | 1332 |  |  | 1416.5 |  |  | 1415.5 |  |  | 1420.5 |  |  | 1509.5 |  |  | 1408.5 |  |  | 1414 |  |  | 1376.5 |  |  | 1435.5 |  |  | 1534.5 |  |  | 1403 |  |  | 1334.5 |  |  | 1313.5 |  |  | 1418.5 |  |  | 1421.5 |  |  | 1348 |  |  | 1416 |  |  | 1384 |  |  | 1373.5 |  |  | 1407 |  |  | 1455 |  |  | 1431.5 |  |  | 1283.5 |  |  | 1248.5 |  |  | 1382.5 |  |  | 1432.5 |  |  | 1472.5 |  |  | 1427.5 |  |  | 1381.5 |  |  | 1266.5 |  |  | 1250 |  |  | 1376.5 |  |  | 1322 |  |  | 1431.5 |  |  | 1430.5 |  |  | 1353.5 |  |  | 1465.5 |  |  | 1385 |  |  | 1350.5 |  |  | 1330 |  |  | 1323.5 |  |  | 1400.5 |  |  | 1260 |  |  | 1390 |  |  | 1332.5 |  |  | 1338 |  |  | 1448.5 |  |  | 1247.5 |  |  | 1322.5 |  |  | 1348.5 |  |  | 1316.5 |  |  | 1431.5 |  |  | 1290.5 |  |  | 1255 |  |  | 1395.5 |  |  | 1366.5 |  |  | 1270.5 |  |  | 1372.5 |  |  | 1293.5 |  |  | 1325.5 |  |  | 1386.5 |  |  | 1377.5 |  |  | 1390.5 |  |  | 1374.5 |  |  | 1307.5 |  |  | 1307.5 |  |  | 1358 |  |  | 1228.5 |  |  | 1324.5 |  |  | 1414 |  |  | 1312.5 |  |  | 1259.5 |  |  | 1303.5 |  |  | 1310.5 |  |  | 1447 |  |  | 1472.5 |  |  | 1379.5 |  |  | 1284.5 |  |  | 1379.5 |  |  | 1343 |  |  | 1384.5 |  |  | 1386.5 |  |  | 1421.5 |  |  | 1441.5 |  |  | 1391.5 |  |  | 1272.5 |  |  | 1422.5 |  |  | 1474.5 |  |  | 1389.5 |  |  | 1360.5 |  |  | 1435.5 |  |  | 1356 |  |  | 1367.5 |  |  | 1385.5 |  |  | 1418.5 |  |  | 1348.5 |  |  | 1264.5 |  |  | 1349.5 |  |  | 1414 |  |  | 1296.5 |  |  | 1307 |  |  | 1283.5 |  |  | 1392.5 |  |  | 1384.5 |  |  | 1336 |  |  | 1335 |  |  | 1326.5 |  |  | 1373.5 |  |  | 1228.5 |  |  | 1436.5 |  |  | 1337.5 |  |  | 1351.5 |  |  | 1309.5 |  |  | 1328.5 |  |  | 1317.5 |  |  | 1406.5 |  |  | 1308.5 |  |  | 1379.5 |  |  | 1330.5 |  |  | 1438.5 |  |  | 1403.5 |  |  | 1341.5 |  |  | 1342.5 |  |  | 1387.5 |  |  | 1320.5 |  |  | 1271.5 |  |  | 1378.5 |  |  | 1411.5 |  |  | 1412 |  |  | 1466.5 |  |  | 1344.5 |  |  | 1334.5 |  |  | 1416 |  |  | 1384.5 |  |  | 1343.5 |  |  | 1400.5 |  |  | 1344.5 |  |  | 1425 |  |  | 1232.5 |  |  | 1276.5 |  |  | 1263 |  |  | 1275 |  |  | 1370 |  |  | 1334.5 |  |  | 1351.5 |  |  | 1402.5 |  |  | 1488.5 |  |  | 1371 |  |  | 1362.5 |  |  | 1388.5 |  |  | 1259 |  |  | 1325 |  |  | 1416.5 |  |  | 1363.5 |  |  | 1402 |  |  | 1358.5 |  |  | 1446 |  |  | 1260.5 |  |  | 1263.5 |  |  | 1431 |  |  | 1433.5 |  |  | 1290.5 |  |  | 1268.5 |  |  | 1433 |  |  | 1385.5 |  |  | 1336.5 |  |  | 1304.5 |  |  | 1329.5 |  |  | 1327.5 |  |  | 1458.5 |  |  | 1326.5 |  |  | 1353.5 |  |  | 1373.5 |  |  | 1355.5 |  |  | 1436 |  |  | 1356.5 |  |  | 1399.5 |  |  | 1388.5 |  |  | 1376.5 |  |  | 1309.5 |  |  | 1474.5 |  |  | 1424.5 |  |  | 1379.5 |  |  | 1411 |  |  | 1378.5 |  |  | 1344 |  |  | 1437.5 |  |  | 1464.5 |  |  | 1508.5 |  |  | 1321.5 |  |  | 1373.5 |  |  | 1313.5 |  |  | 1197.5 |  |  | 1418.5 |  |  | 1438 |  |  | 1332.5 |  |  | 1299 |  |  | 1303.5 |  |  | 1247.5 |  |  | 1404.5 |  |  | 1401 |  |  | 1330.5 |  |  | 1424.5 |  |  | 1285 |  |  | 1302.5 |  |  | 1322 |  |  | 1340.5 |  |  | 1334.5 |  |  | 1287.5 |  |  | 1330 |  |  | 1407.5 |  |  | 1465.5 |  |  | 1303 |  |  | 1401.5 |  |  | 1250.5 |  |  | 1423 |  |  | 1388.5 |  |  | 1472.5 |  |  | 1385.5 |  |  | 1394.5 |  |  | 1296.5 |  |  | 1398.5 |  |  | 1353.5 |  |  | 1312.5 |  |  | 1264.5 |  |  | 1398.5 |  |  | 1438.5 |  |  | 1371 |  |  | 1388 |  |  | 1421.5 |  |  | 1380.5 |  |  | 1438
48 |  | 1374.5 |  |  | 1486.5 |  |  | 1420 |  |  | 1398.5 |  |  | 1504.5 |  |  | 1434.5 |  |  | 1501.5 |  |  | 1415.5 |  |  | 1391.5 |  |  | 1427.5 |  |  | 1364 |  |  | 1426.5 |  |  | 1475.5 |  |  | 1309.5 |  |  | 1318 |  |  | 1394.5 |  |  | 1543.5 |  |  | 1441.5 |  |  | 1541.5 |  |  | 1308.5 |  |  | 1379.5 |  |  | 1370.5 |  |  | 1394.5 |  |  | 1332.5 |  |  | 1285 |  |  | 1472.5 |  |  | 1396.5 |  |  | 1399.5 |  |  | 1454.5 |  |  | 1307 |  |  | 1408 |  |  | 1323.5 |  |  | 1345.5 |  |  | 1406.5 |  |  | 1292.5 |  |  | 1402 |  |  | 1330.5 |  |  | 1419 |  |  | 1360.5 |  |  | 1445.5 |  |  | 1301.5 |  |  | 1455.5 |  |  | 1338.5 |  |  | 1346 |  |  | 1578.5 |  |  | 1433 |  |  | 1347.5 |  |  | 1459.5 |  |  | 1451.5 |  |  | 1338.5 |  |  | 1339.5 |  |  | 1388.5 |  |  | 1395.5 |  |  | 1364.5 |  |  | 1432.5 |  |  | 1392.5 |  |  | 1321.5 |  |  | 1381 |  |  | 1479.5 |  |  | 1358.5 |  |  | 1354 |  |  | 1355.5 |  |  | 1450.5 |  |  | 1387.5 |  |  | 1305.5 |  |  | 1413 |  |  | 1444.5 |  |  | 1314 |  |  | 1335.5 |  |  | 1434.5 |  |  | 1420 |  |  | 1377.5 |  |  | 1351.5 |  |  | 1510.5 |  |  | 1467 |  |  | 1406 |  |  | 1344.5 |  |  | 1300.5 |  |  | 1291.5 |  |  | 1354.5 |  |  | 1351 |  |  | 1392.5 |  |  | 1421.5 |  |  | 1446.5 |  |  | 1436.5 |  |  | 1453.5 |  |  | 1444.5 |  |  | 1340.5 |  |  | 1361.5 |  |  | 1464.5 |  |  | 1445.5 |  |  | 1420 |  |  | 1309.5 |  |  | 1345 |  |  | 1354 |  |  | 1337 |  |  | 1480.5 |  |  | 1410.5 |  |  | 1333.5 |  |  | 1408.5 |  |  | 1412.5 |  |  | 1418 |  |  | 1402 |  |  | 1341.5 |  |  | 1362.5 |  |  | 1376.5 |  |  | 1396.5 |  |  | 1488.5 |  |  | 1444.5 |  |  | 1414.5 |  |  | 1471.5 |  |  | 1437.5 |  |  | 1464.5 |  |  | 1411.5 |  |  | 1399.5 |  |  | 1435.5 |  |  | 1417.5 |  |  | 1278.5 |  |  | 1431.5 |  |  | 1420.5 |  |  | 1465.5 |  |  | 1413.5 |  |  | 1363.5 |  |  | 1405.5 |  |  | 1420.5 |  |  | 1390 |  |  | 1345.5 |  |  | 1384.5 |  |  | 1304.5 |  |  | 1331.5 |  |  | 1488.5 |  |  | 1439 |  |  | 1312.5 |  |  | 1438.5 |  |  | 1350.5 |  |  | 1399.5 |  |  | 1421 |  |  | 1361.5 |  |  | 1468.5 |  |  | 1414 |  |  | 1411.5 |  |  | 1401 |  |  | 1401 |  |  | 1487.5 |  |  | 1445 |  |  | 1480.5 |  |  | 1380.5 |  |  | 1447.5 |  |  | 1340.5 |  |  | 1483.5 |  |  | 1395.5 |  |  | 1441.5 |  |  | 1431.5 |  |  | 1535.5 |  |  | 1430.5 |  |  | 1440 |  |  | 1375.5 |  |  | 1321 |  |  | 1324.5 |  |  | 1420.5 |  |  | 1407 |  |  | 1395.5 |  |  | 1384.5 |  |  | 1354.5 |  |  | 1340 |  |  | 1415.5 |  |  | 1309.5 |  |  | 1355.5 |  |  | 1468.5 |  |  | 1325.5 |  |  | 1368.5 |  |  | 1395 |  |  | 1350.5 |  |  | 1412.5 |  |  | 1367.5 |  |  | 1350.5 |  |  | 1391.5 |  |  | 1462.5 |  |  | 1273.5 |  |  | 1483 |  |  | 1465.5 |  |  | 1411.5 |  |  | 1481.5 |  |  | 1448.5 |  |  | 1321.5 |  |  | 1457.5 |  |  | 1465.5 |  |  | 1405.5 |  |  | 1456.5 |  |  | 1355.5 |  |  | 1369.5 |  |  | 1346.5 |  |  | 1232.5 |  |  | 1352 |  |  | 1319.5 |  |  | 1420.5 |  |  | 1347.5 |  |  | 1426.5 |  |  | 1455.5 |  |  | 1366.5 |  |  | 1436.5 |  |  | 1364.5 |  |  | 1403.5 |  |  | 1367.5 |  |  | 1354.5 |  |  | 1514.5 |  |  | 1393.5 |  |  | 1369.5 |  |  | 1417.5 |  |  | 1421.5 |  |  | 1437 |  |  | 1399.5 |  |  | 1382.5 |  |  | 1269 |  |  | 1532.5 |  |  | 1476 |  |  | 1385.5 |  |  | 1458.5 |  |  | 1519.5 |  |  | 1447.5 |  |  | 1332.5 |  |  | 1383.5 |  |  | 1365.5 |  |  | 1269.5 |  |  | 1350 |  |  | 1300.5 |  |  | 1232.5 |  |  | 1468.5 |  |  | 1343.5 |  |  | 1467 |  |  | 1313.5 |  |  | 1362.5 |  |  | 1448.5 |  |  | 1476.5 |  |  | 1462.5 |  |  | 1294.5 |  |  | 1360.5 |  |  | 1443.5 |  |  | 1404 |  |  | 1412 |  |  | 1332.5 |  |  | 1379.5 |  |  | 1392.5 |  |  | 1422 |  |  | 1444.5 |  |  | 1420.5 |  |  | 1355.5 |  |  | 1397 |  |  | 1383.5 |  |  | 1428.5 |  |  | 1359.5 |  |  | 1419.5 |  |  | 1392.5 |  |  | 1425.5 |  |  | 1449.5 |  |  | 1386.5 |  |  | 1506.5 |  |  | 1211 |  |  | 1289.5 |  |  | 1452.5 |  |  | 1342.5 |  |  | 1373.5 |  |  | 1378.5 |  |  | 1463 |  |  | 1352.5 |  |  | 1480.5 |  |  | 1426 |  |  | 1547.5 |  |  | 1418.5 |  |  | 1525 |  |  | 1417.5 |  |  | 1402.5 |  |  | 1513.5 |  |  | 1310.5 |  |  | 1425 |  |  | 1471 |  |  | 1452.5 |  |  | 1361.5 |  |  | 1429.5 |  |  | 1405.5 |  |  | 1489.5 |  |  | 1350.5 |  |  | 1394 |  |  | 1421.5 |  |  | 1423.5 |  |  | 1392 |  |  | 1327.5 |  |  | 1284.5 |  |  | 1368 |  |  | 1341.5 |  |  | 1349.5 |  |  | 1385.5 |  |  | 1380 |  |  | 1439.5 |  |  | 1341 |  |  | 1436.5 |  |  | 1363.5 |  |  | 1389.5 |  |  | 1384 |  |  | 1349.5 |  |  | 1492.5 |  |  | 1337.5 |  |  | 1388 |  |  | 1281.5 |  |  | 1326.5 |  |  | 1505.5 |  |  | 1480.5 |  |  | 1364.5 |  |  | 1363 |  |  | 1354.5 |  |  | 1524.5 |  |  | 1477.5 |  |  | 1326 |  |  | 1383 |  |  | 1515.5 |  |  | 1411.5 |  |  | 1317.5 |  |  | 1375.5 |  |  | 1412.5 |  |  | 1418.5 |  |  | 1399.5 |  |  | 1436.5 |  |  | 1339.5 |  |  | 1379.5 |  |  | 1395 |  |  | 1425.5 |  |  | 1504.5 |  |  | 1534.5 |  |  | 1500.5 |  |  | 1404 |  |  | 1439.5 |  |  | 1454.5 |  |  | 1446.5 |  |  | 1248.5 |  |  | 1455.5 |  |  | 1381 |  |  | 1351 |  |  | 1335 |  |  | 1407 |  |  | 1349.5 |  |  | 1412 |  |  | 1391.5 |  |  | 1329 |  |  | 1395.5 |  |  | 1516.5 |  |  | 1426.5 |  |  | 1416.5 |  |  | 1365.5 |  |  | 1409 |  |  | 1386.5 |  |  | 1461.5 |  |  | 1294.5 |  |  | 1468 |  |  | 1425.5 |  |  | 1353.5 |  |  | 1351.5 |  |  | 1471 |  |  | 1389.5 |  |  | 1280.5 |  |  | 1424.5 |  |  | 1335.5 |  |  | 1395.5 |  |  | 1328.5 |  |  | 1514.5 |  |  | 1374.5 |  |  | 1473.5 |  |  | 1275.5 |  |  | 1289 |  |  | 1400.5 |  |  | 1427.5 |  |  | 1354.5 |  |  | 1437.5 |  |  | 1511.5 |  |  | 1395 |  |  | 1379.5 |  |  | 1466 |  |  | 1362 |  |  | 1383.5 |  |  | 1495.5 |  |  | 1372.5 |  |  | 1338 |  |  | 1445.5 |  |  | 1437.5 |  |  | 1439.5 |  |  | 1274 |  |  | 1395.5 |  |  | 1268.5 |  |  | 1470.5 |  |  | 1330.5 |  |  | 1338.5 |  |  | 1356 |  |  | 1369.5 |  |  | 1376 |  |  | 1360.5 |  |  | 1362.5 |  |  | 1370.5 |  |  | 1445 |  |  | 1314.5 |  |  | 1452 |  |  | 1406 |  |  | 1334.5 |  |  | 1324.5 |  |  | 1396.5 |  |  | 1483.5 |  |  | 1460 |  |  | 1427.5 |  |  | 1384.5 |  |  | 1316.5 |  |  | 1388 |  |  | 1446.5 |  |  | 1323.5 |  |  | 1324.5 |  |  | 1337.5 |  |  | 1465 |  |  | 1271.5 |  |  | 1398.5 |  |  | 1430.5 |  |  | 1413.5 |  |  | 1370.5 |  |  | 1403.5 |  |  | 1455 |  |  | 1371.5 |  |  | 1300.5 |  |  | 1415 |  |  | 1315.5 |  |  | 1349.5 |  |  | 1380.5 |  |  | 1378 |  |  | 1412.5 |  |  | 1364.5 |  |  | 1397.5 |  |  | 1392.5 |  |  | 1472.5 |  |  | 1469 |  |  | 1420 |  |  | 1324.5 |  |  | 1441.5 |  |  | 1408.5 |  |  | 1340.5 |  |  | 1340 |  |  | 1444 |  |  | 1331 |  |  | 1432.5 |  |  | 1359 |  |  | 1420.5 |  |  | 1450.5 |  |  | 1377 |  |  | 1345.5 |  |  | 1416.5 |  |  | 1380.5 |  |  | 1510.5 |  |  | 1298.5 |  |  | 1381 |  |  | 1394 |  |  | 1247.5 |  |  | 1430.5 |  |  | 1349 |  |  | 1272.5 |  |  | 1427.5 |  |  | 1384 |  |  | 1530.5 |  |  | 1479.5 |  |  | 1266 |  |  | 1449.5 |  |  | 1412.5 |  |  | 1386 |  |  | 1436.5 |  |  | 1305 |  |  | 1532.5 |  |  | 1498 |  |  | 1360.5 |  |  | 1380.5 |  |  | 1395.5 |  |  | 1365.5 |  |  | 1403.5 |  |  | 1302.5 |  |  | 1461 |  |  | 1361.5 |  |  | 1372.5 |  |  | 1302.5 |  |  | 1433.5 |  |  | 1383.5 |  |  | 1391 |  |  | 1371.5 |  |  | 1373 |  |  | 1383.5 |  |  | 1355.5 |  |  | 1380.5 |  |  | 1351.5 |  |  | 1402.5 |  |  | 1385.5 |  |  | 1344.5 |  |  | 1476.5 |  |  | 1352.5 |  |  | 1454 |  |  | 1400.5 |  |  | 1273 |  |  | 1364 |  |  | 1432.5 |  |  | 1321 |  |  | 1292.5 |  |  | 1365.5 |  |  | 1445.5 |  |  | 1324.5 |  |  | 1415.5 |  |  | 1493.5 |  |  | 1461.5 |  |  | 1350 |  |  | 1452 |  |  | 1316.5 |  |  | 1286.5 |  |  | 1400 |  |  | 1387.5 |  |  | 1405.5 |  |  | 1343.5 |  |  | 1304.5 |  |  | 1320.5 |  |  | 1364 |  |  | 1393.5 |  |  | 1385.5 |  |  | 1324.5 |  |  | 1334 |  |  | 1465.5 |  |  | 1433.5 |  |  | 1415.5 |  |  | 1536.5 |  |  | 1464.5 |  |  | 1387.5 |  |  | 1497.5 |  |  | 1184.5 |  |  | 1370.5 |  |  | 1333 |  |  | 1483.5 |  |  | 1398.5 |  |  | 1464.5 |  |  | 1331.5 |  |  | 1307.5 |  |  | 1324.5 |  |  | 1330.5 |  |  | 1231 |  |  | 1307.5 |  |  | 1455.5 |  |  | 1490.5 |  |  | 1291 |  |  | 1361.5 |  |  | 1343 |  |  | 1383.5 |  |  | 1388.5 |  |  | 1335.5 |  |  | 1366 |  |  | 1294.5 |  |  | 1435 |  |  | 1429 |  |  | 1421.5 |  |  | 1367 |  |  | 1416 |  |  | 1451.5 |  |  | 1465.5 |  |  | 1306.5 |  |  | 1427 |  |  | 1433.5 |  |  | 1370.5 |  |  | 1248.5 |  |  | 1482.5 |  |  | 1370.5 |  |  | 1410.5 |  |  | 1352.5 |  |  | 1422.5 |  |  | 1332 |  |  | 1504.5 |  |  | 1304 |  |  | 1354.5 |  |  | 1295.5 |  |  | 1461.5 |  |  | 1464 |  |  | 1480 |  |  | 1517 |  |  | 1407.5 |  |  | 1381 |  |  | 1467.5 |  |  | 1437.5 |  |  | 1327.5 |  |  | 1397.5 |  |  | 1354.5 |  |  | 1421.5 |  |  | 1429.5 |  |  | 1399.5 |  |  | 1456 |  |  | 1334.5 |  |  | 1301.5 |  |  | 1425.5 |  |  | 1301.5 |  |  | 1325 |  |  | 1380.5 |  |  | 1419 |  |  | 1394.5 |  |  | 1400.5 |  |  | 1386.5 |  |  | 1332.5 |  |  | 1309 |  |  | 1352.5 |  |  | 1233 |  |  | 1372.5 |  |  | 1397.5 |  |  | 1519.5 |  |  | 1493.5 |  |  | 1390.5 |  |  | 1326.5 |  |  | 1295.5 |  |  | 1446.5 |  |  | 1366.5 |  |  | 1394 |  |  | 1389.5 |  |  | 1345.5 |  |  | 1338.5 |  |  | 1376.5 |  |  | 1415.5 |  |  | 1271 |  |  | 1340 |  |  | 1385.5 |  |  | 1351 |  |  | 1512.5 |  |  | 1341.5 |  |  | 1455.5 |  |  | 1500.5 |  |  | 1323.5 |  |  | 1412.5 |  |  | 1416.5 |  |  | 1364.5 |  |  | 1392 |  |  | 1415.5 |  |  | 1476.5 |  |  | 1517.5 |  |  | 1305 |  |  | 1427.5 |  |  | 1353.5 |  |  | 1481 |  |  | 1267 |  |  | 1419.5 |  |  | 1325 |  |  | 1233 |  |  | 1276.5 |  |  | 1335 |  |  | 1495.5 |  |  | 1468.5 |  |  | 1418.5 |  |  | 1371.5 |  |  | 1321.5 |  |  | 1423.5 |  |  | 1285.5 |  |  | 1374.5 |  |  | 1383.5 |  |  | 1400.5 |  |  | 1327 |  |  | 1315 |  |  | 1410.5 |  |  | 1348.5 |  |  | 1386.5 |  |  | 1442.5 |  |  | 1315.5 |  |  | 1383.5 |  |  | 1467.5 |  |  | 1347.5 |  |  | 1500 |  |  | 1292.5 |  |  | 1347 |  |  | 1341.5 |  |  | 1559.5 |  |  | 1423.5 |  |  | 1453 |  |  | 1410.5 |  |  | 1329.5 |  |  | 1303 |  |  | 1446.5 |  |  | 1343.5 |  |  | 1480.5 |  |  | 1387.5 |  |  | 1369.5 |  |  | 1370.5 |  |  | 1330 |  |  | 1327.5 |  |  | 1297.5 |  |  | 1417.5 |  |  | 1551.5 |  |  | 1320 |  |  | 1304.5 |  |  | 1498.5 |  |  | 1381 |  |  | 1434.5 |  |  | 1430.5 |  |  | 1379 |  |  | 1435.5 |  |  | 1452.5 |  |  | 1390.5 |  |  | 1323 |  |  | 1255.5 |  |  | 1410.5 |  |  | 1361 |  |  | 1388.5 |  |  | 1463.5 |  |  | 1408.5 |  |  | 1208.5 |  |  | 1467.5 |  |  | 1537.5 |  |  | 1308.5 |  |  | 1372 |  |  | 1352 |  |  | 1273.5 |  |  | 1405.5 |  |  | 1389.5 |  |  | 1367 |  |  | 1416.5 |  |  | 1373.5 |  |  | 1366.5 |  |  | 1244.5 |  |  | 1361.5 |  |  | 1361.5 |  |  | 1286.5 |  |  | 1381.5 |  |  | 1253.5 |  |  | 1407 |  |  | 1350.5 |  |  | 1365.5 |  |  | 1347.5 |  |  | 1511.5 |  |  | 1425.5 |  |  | 1371.5 |  |  | 1365.5 |  |  | 1386.5 |  |  | 1335.5 |  |  | 1438.5 |  |  | 1404.5 |  |  | 1368.5 |  |  | 1419.5 |  |  | 1478 |  |  | 1383.5 |  |  | 1418.5 |  |  | 1380 |  |  | 1462.5 |  |  | 1435.5 |  |  | 1486 |  |  | 1400.5 |  |  | 1496.5 |  |  | 1510.5 |  |  | 1482 |  |  | 1413.5 |  |  | 1465.5 |  |  | 1369.5 |  |  | 1254.5 |  |  | 1388.5 |  |  | 1273 |  |  | 1388.5 |  |  | 1463 |  |  | 1440 |  |  | 1509.5 |  |  | 1380.5 |  |  | 1348.5 |  |  | 1303.5 |  |  | 1393.5 |  |  | 1423.5 |  |  | 1393 |  |  | 1429.5 |  |  | 1428 |  |  | 1328.5 |  |  | 1445 |  |  | 1384 |  |  | 1466 |  |  | 1403.5 |  |  | 1371 |  |  | 1431.5 |  |  | 1454.5 |  |  | 1435.5 |  |  | 1556.5 |  |  | 1447.5 |  |  | 1435 |  |  | 1415.5 |  |  | 1450.5 |  |  | 1581.5 |  |  | 1442 |  |  | 1381.5 |  |  | 1352.5 |  |  | 1442.5 |  |  | 1450.5 |  |  | 1387 |  |  | 1431 |  |  | 1408 |  |  | 1420.5 |  |  | 1433 |  |  | 1494 |  |  | 1470.5 |  |  | 1312.5 |  |  | 1272.5 |  |  | 1397.5 |  |  | 1453.5 |  |  | 1493.5 |  |  | 1453.5 |  |  | 1420.5 |  |  | 1313.5 |  |  | 1265 |  |  | 1397.5 |  |  | 1346 |  |  | 1452.5 |  |  | 1469.5 |  |  | 1392.5 |  |  | 1494.5 |  |  | 1400 |  |  | 1389.5 |  |  | 1354 |  |  | 1338.5 |  |  | 1447.5 |  |  | 1299 |  |  | 1411 |  |  | 1347.5 |  |  | 1377 |  |  | 1477.5 |  |  | 1286.5 |  |  | 1351.5 |  |  | 1395.5 |  |  | 1337.5 |  |  | 1455.5 |  |  | 1314.5 |  |  | 1270 |  |  | 1434.5 |  |  | 1413.5 |  |  | 1294.5 |  |  | 1398.5 |  |  | 1317.5 |  |  | 1351.5 |  |  | 1433.5 |  |  | 1416.5 |  |  | 1429.5 |  |  | 1398.5 |  |  | 1322.5 |  |  | 1346.5 |  |  | 1405 |  |  | 1243.5 |  |  | 1345.5 |  |  | 1461 |  |  | 1333.5 |  |  | 1298.5 |  |  | 1329.5 |  |  | 1357.5 |  |  | 1486 |  |  | 1511.5 |  |  | 1405.5 |  |  | 1323.5 |  |  | 1400.5 |  |  | 1367 |  |  | 1408.5 |  |  | 1412.5 |  |  | 1468.5 |  |  | 1465.5 |  |  | 1412.5 |  |  | 1293.5 |  |  | 1461.5 |  |  | 1489.5 |  |  | 1413.5 |  |  | 1384.5 |  |  | 1474.5 |  |  | 1380 |  |  | 1393.5 |  |  | 1414.5 |  |  | 1444.5 |  |  | 1374.5 |  |  | 1311.5 |  |  | 1388.5 |  |  | 1443 |  |  | 1335.5 |  |  | 1331 |  |  | 1322.5 |  |  | 1421.5 |  |  | 1413.5 |  |  | 1362 |  |  | 1374 |  |  | 1355.5 |  |  | 1402.5 |  |  | 1267.5 |  |  | 1483.5 |  |  | 1366.5 |  |  | 1390.5 |  |  | 1338.5 |  |  | 1343.5 |  |  | 1338.5 |  |  | 1430.5 |  |  | 1334.5 |  |  | 1400.5 |  |  | 1345.5 |  |  | 1467.5 |  |  | 1442.5 |  |  | 1380.5 |  |  | 1366.5 |  |  | 1416.5 |  |  | 1346.5 |  |  | 1310.5 |  |  | 1402.5 |  |  | 1437.5 |  |  | 1438 |  |  | 1505.5 |  |  | 1383.5 |  |  | 1373.5 |  |  | 1437 |  |  | 1399.5 |  |  | 1369.5 |  |  | 1447.5 |  |  | 1383.5 |  |  | 1446 |  |  | 1258.5 |  |  | 1291.5 |  |  | 1302 |  |  | 1322 |  |  | 1391 |  |  | 1363.5 |  |  | 1372.5 |  |  | 1441.5 |  |  | 1527.5 |  |  | 1410 |  |  | 1383.5 |  |  | 1435.5 |  |  | 1274 |  |  | 1354 |  |  | 1431.5 |  |  | 1384.5 |  |  | 1417 |  |  | 1397.5 |  |  | 1472 |  |  | 1286.5 |  |  | 1278.5 |  |  | 1460 |  |  | 1454.5 |  |  | 1329.5 |  |  | 1283.5 |  |  | 1459 |  |  | 1400.5 |  |  | 1360.5 |  |  | 1330.5 |  |  | 1353.5 |  |  | 1366.5 |  |  | 1484.5 |  |  | 1355.5 |  |  | 1379.5 |  |  | 1394.5 |  |  | 1370.5 |  |  | 1457 |  |  | 1403.5 |  |  | 1423.5 |  |  | 1435.5 |  |  | 1423.5 |  |  | 1348.5 |  |  | 1489.5 |  |  | 1463.5 |  |  | 1403.5 |  |  | 1458 |  |  | 1404.5 |  |  | 1383 |  |  | 1458.5 |  |  | 1490.5 |  |  | 1534.5 |  |  | 1336.5 |  |  | 1397.5 |  |  | 1342.5 |  |  | 1223.5 |  |  | 1457.5 |  |  | 1485 |  |  | 1361.5 |  |  | 1346 |  |  | 1342.5 |  |  | 1271.5 |  |  | 1430.5 |  |  | 1430 |  |  | 1369.5 |  |  | 1445.5 |  |  | 1311 |  |  | 1331.5 |  |  | 1351 |  |  | 1366.5 |  |  | 1349.5 |  |  | 1302.5 |  |  | 1351 |  |  | 1428.5 |  |  | 1486.5 |  |  | 1332 |  |  | 1430.5 |  |  | 1265.5 |  |  | 1444 |  |  | 1412.5 |  |  | 1511.5 |  |  | 1424.5 |  |  | 1433.5 |  |  | 1317.5 |  |  | 1419.5 |  |  | 1368.5 |  |  | 1333.5 |  |  | 1285.5 |  |  | 1422.5 |  |  | 1485.5 |  |  | 1386 |  |  | 1427 |  |  | 1445.5 |  |  | 1401.5 |  |  | 1464
49 |  | 1389.5 |  |  | 1525.5 |  |  | 1446 |  |  | 1422.5 |  |  | 1519.5 |  |  | 1460.5 |  |  | 1527.5 |  |  | 1436.5 |  |  | 1430.5 |  |  | 1456.5 |  |  | 1379 |  |  | 1465.5 |  |  | 1499.5 |  |  | 1348.5 |  |  | 1344 |  |  | 1418.5 |  |  | 1569.5 |  |  | 1462.5 |  |  | 1580.5 |  |  | 1355.5 |  |  | 1426.5 |  |  | 1396.5 |  |  | 1420.5 |  |  | 1358.5 |  |  | 1314 |  |  | 1493.5 |  |  | 1417.5 |  |  | 1438.5 |  |  | 1501.5 |  |  | 1322 |  |  | 1429 |  |  | 1370.5 |  |  | 1366.5 |  |  | 1453.5 |  |  | 1331.5 |  |  | 1441 |  |  | 1359.5 |  |  | 1445 |  |  | 1381.5 |  |  | 1474.5 |  |  | 1348.5 |  |  | 1484.5 |  |  | 1364.5 |  |  | 1370 |  |  | 1607.5 |  |  | 1480 |  |  | 1394.5 |  |  | 1506.5 |  |  | 1490.5 |  |  | 1377.5 |  |  | 1378.5 |  |  | 1403.5 |  |  | 1434.5 |  |  | 1403.5 |  |  | 1453.5 |  |  | 1421.5 |  |  | 1336.5 |  |  | 1405 |  |  | 1500.5 |  |  | 1405.5 |  |  | 1401 |  |  | 1370.5 |  |  | 1474.5 |  |  | 1416.5 |  |  | 1331.5 |  |  | 1452 |  |  | 1483.5 |  |  | 1361 |  |  | 1356.5 |  |  | 1460.5 |  |  | 1444 |  |  | 1403.5 |  |  | 1390.5 |  |  | 1531.5 |  |  | 1488 |  |  | 1445 |  |  | 1370.5 |  |  | 1339.5 |  |  | 1317.5 |  |  | 1380.5 |  |  | 1390 |  |  | 1413.5 |  |  | 1460.5 |  |  | 1485.5 |  |  | 1475.5 |  |  | 1482.5 |  |  | 1483.5 |  |  | 1364.5 |  |  | 1382.5 |  |  | 1503.5 |  |  | 1471.5 |  |  | 1435 |  |  | 1324.5 |  |  | 1360 |  |  | 1375 |  |  | 1358 |  |  | 1509.5 |  |  | 1457.5 |  |  | 1359.5 |  |  | 1447.5 |  |  | 1451.5 |  |  | 1433 |  |  | 1431 |  |  | 1370.5 |  |  | 1409.5 |  |  | 1391.5 |  |  | 1425.5 |  |  | 1514.5 |  |  | 1465.5 |  |  | 1453.5 |  |  | 1500.5 |  |  | 1466.5 |  |  | 1485.5 |  |  | 1440.5 |  |  | 1414.5 |  |  | 1450.5 |  |  | 1464.5 |  |  | 1304.5 |  |  | 1446.5 |  |  | 1435.5 |  |  | 1489.5 |  |  | 1428.5 |  |  | 1389.5 |  |  | 1452.5 |  |  | 1441.5 |  |  | 1429 |  |  | 1374.5 |  |  | 1408.5 |  |  | 1343.5 |  |  | 1370.5 |  |  | 1517.5 |  |  | 1460 |  |  | 1341.5 |  |  | 1477.5 |  |  | 1376.5 |  |  | 1428.5 |  |  | 1445 |  |  | 1408.5 |  |  | 1507.5 |  |  | 1461 |  |  | 1437.5 |  |  | 1430 |  |  | 1448 |  |  | 1526.5 |  |  | 1466 |  |  | 1519.5 |  |  | 1401.5 |  |  | 1476.5 |  |  | 1379.5 |  |  | 1509.5 |  |  | 1434.5 |  |  | 1462.5 |  |  | 1470.5 |  |  | 1564.5 |  |  | 1456.5 |  |  | 1479 |  |  | 1396.5 |  |  | 1350 |  |  | 1363.5 |  |  | 1441.5 |  |  | 1433 |  |  | 1419.5 |  |  | 1413.5 |  |  | 1401.5 |  |  | 1379 |  |  | 1454.5 |  |  | 1348.5 |  |  | 1376.5 |  |  | 1497.5 |  |  | 1346.5 |  |  | 1407.5 |  |  | 1421 |  |  | 1374.5 |  |  | 1433.5 |  |  | 1406.5 |  |  | 1374.5 |  |  | 1438.5 |  |  | 1486.5 |  |  | 1312.5 |  |  | 1530 |  |  | 1480.5 |  |  | 1437.5 |  |  | 1507.5 |  |  | 1474.5 |  |  | 1345.5 |  |  | 1504.5 |  |  | 1504.5 |  |  | 1420.5 |  |  | 1482.5 |  |  | 1379.5 |  |  | 1390.5 |  |  | 1375.5 |  |  | 1279.5 |  |  | 1367 |  |  | 1340.5 |  |  | 1435.5 |  |  | 1394.5 |  |  | 1465.5 |  |  | 1479.5 |  |  | 1413.5 |  |  | 1475.5 |  |  | 1403.5 |  |  | 1450.5 |  |  | 1382.5 |  |  | 1393.5 |  |  | 1529.5 |  |  | 1419.5 |  |  | 1395.5 |  |  | 1441.5 |  |  | 1460.5 |  |  | 1476 |  |  | 1425.5 |  |  | 1403.5 |  |  | 1298 |  |  | 1579.5 |  |  | 1491 |  |  | 1424.5 |  |  | 1484.5 |  |  | 1540.5 |  |  | 1494.5 |  |  | 1371.5 |  |  | 1412.5 |  |  | 1394.5 |  |  | 1308.5 |  |  | 1389 |  |  | 1321.5 |  |  | 1271.5 |  |  | 1494.5 |  |  | 1367.5 |  |  | 1496 |  |  | 1339.5 |  |  | 1388.5 |  |  | 1477.5 |  |  | 1515.5 |  |  | 1488.5 |  |  | 1341.5 |  |  | 1375.5 |  |  | 1490.5 |  |  | 1430 |  |  | 1436 |  |  | 1379.5 |  |  | 1426.5 |  |  | 1421.5 |  |  | 1443 |  |  | 1483.5 |  |  | 1459.5 |  |  | 1376.5 |  |  | 1412 |  |  | 1422.5 |  |  | 1467.5 |  |  | 1398.5 |  |  | 1434.5 |  |  | 1416.5 |  |  | 1440.5 |  |  | 1473.5 |  |  | 1425.5 |  |  | 1521.5 |  |  | 1250 |  |  | 1328.5 |  |  | 1467.5 |  |  | 1363.5 |  |  | 1397.5 |  |  | 1407.5 |  |  | 1502 |  |  | 1373.5 |  |  | 1504.5 |  |  | 1447 |  |  | 1562.5 |  |  | 1439.5 |  |  | 1564 |  |  | 1446.5 |  |  | 1449.5 |  |  | 1537.5 |  |  | 1357.5 |  |  | 1454 |  |  | 1486 |  |  | 1481.5 |  |  | 1376.5 |  |  | 1455.5 |  |  | 1431.5 |  |  | 1536.5 |  |  | 1371.5 |  |  | 1418 |  |  | 1450.5 |  |  | 1462.5 |  |  | 1418 |  |  | 1366.5 |  |  | 1323.5 |  |  | 1407 |  |  | 1380.5 |  |  | 1370.5 |  |  | 1424.5 |  |  | 1427 |  |  | 1463.5 |  |  | 1380 |  |  | 1475.5 |  |  | 1378.5 |  |  | 1428.5 |  |  | 1423 |  |  | 1388.5 |  |  | 1507.5 |  |  | 1366.5 |  |  | 1417 |  |  | 1302.5 |  |  | 1347.5 |  |  | 1531.5 |  |  | 1504.5 |  |  | 1403.5 |  |  | 1410 |  |  | 1375.5 |  |  | 1550.5 |  |  | 1503.5 |  |  | 1347 |  |  | 1422 |  |  | 1536.5 |  |  | 1432.5 |  |  | 1346.5 |  |  | 1414.5 |  |  | 1441.5 |  |  | 1457.5 |  |  | 1438.5 |  |  | 1465.5 |  |  | 1360.5 |  |  | 1408.5 |  |  | 1419 |  |  | 1440.5 |  |  | 1525.5 |  |  | 1581.5 |  |  | 1524.5 |  |  | 1443 |  |  | 1468.5 |  |  | 1483.5 |  |  | 1485.5 |  |  | 1263.5 |  |  | 1494.5 |  |  | 1405 |  |  | 1390 |  |  | 1350 |  |  | 1446 |  |  | 1373.5 |  |  | 1438 |  |  | 1406.5 |  |  | 1368 |  |  | 1424.5 |  |  | 1531.5 |  |  | 1447.5 |  |  | 1431.5 |  |  | 1389.5 |  |  | 1438 |  |  | 1401.5 |  |  | 1500.5 |  |  | 1333.5 |  |  | 1507 |  |  | 1449.5 |  |  | 1392.5 |  |  | 1380.5 |  |  | 1518 |  |  | 1413.5 |  |  | 1319.5 |  |  | 1439.5 |  |  | 1382.5 |  |  | 1424.5 |  |  | 1357.5 |  |  | 1561.5 |  |  | 1398.5 |  |  | 1512.5 |  |  | 1299.5 |  |  | 1328 |  |  | 1447.5 |  |  | 1456.5 |  |  | 1369.5 |  |  | 1461.5 |  |  | 1550.5 |  |  | 1410 |  |  | 1418.5 |  |  | 1492 |  |  | 1391 |  |  | 1398.5 |  |  | 1534.5 |  |  | 1396.5 |  |  | 1367 |  |  | 1469.5 |  |  | 1461.5 |  |  | 1465.5 |  |  | 1313 |  |  | 1410.5 |  |  | 1289.5 |  |  | 1509.5 |  |  | 1369.5 |  |  | 1362.5 |  |  | 1395 |  |  | 1416.5 |  |  | 1423 |  |  | 1375.5 |  |  | 1386.5 |  |  | 1409.5 |  |  | 1484 |  |  | 1329.5 |  |  | 1491 |  |  | 1427 |  |  | 1373.5 |  |  | 1371.5 |  |  | 1425.5 |  |  | 1509.5 |  |  | 1489 |  |  | 1451.5 |  |  | 1408.5 |  |  | 1340.5 |  |  | 1427 |  |  | 1493.5 |  |  | 1362.5 |  |  | 1345.5 |  |  | 1361.5 |  |  | 1494 |  |  | 1300.5 |  |  | 1422.5 |  |  | 1469.5 |  |  | 1442.5 |  |  | 1409.5 |  |  | 1418.5 |  |  | 1502 |  |  | 1410.5 |  |  | 1321.5 |  |  | 1439 |  |  | 1330.5 |  |  | 1375.5 |  |  | 1406.5 |  |  | 1425 |  |  | 1436.5 |  |  | 1390.5 |  |  | 1412.5 |  |  | 1421.5 |  |  | 1511.5 |  |  | 1508 |  |  | 1459 |  |  | 1363.5 |  |  | 1462.5 |  |  | 1447.5 |  |  | 1366.5 |  |  | 1366 |  |  | 1473 |  |  | 1346 |  |  | 1461.5 |  |  | 1398 |  |  | 1444.5 |  |  | 1497.5 |  |  | 1401 |  |  | 1371.5 |  |  | 1463.5 |  |  | 1409.5 |  |  | 1549.5 |  |  | 1319.5 |  |  | 1407 |  |  | 1441 |  |  | 1268.5 |  |  | 1469.5 |  |  | 1375 |  |  | 1287.5 |  |  | 1448.5 |  |  | 1413 |  |  | 1569.5 |  |  | 1494.5 |  |  | 1313 |  |  | 1464.5 |  |  | 1451.5 |  |  | 1407 |  |  | 1462.5 |  |  | 1344 |  |  | 1579.5 |  |  | 1537 |  |  | 1384.5 |  |  | 1406.5 |  |  | 1419.5 |  |  | 1394.5 |  |  | 1432.5 |  |  | 1328.5 |  |  | 1490 |  |  | 1390.5 |  |  | 1393.5 |  |  | 1341.5 |  |  | 1472.5 |  |  | 1407.5 |  |  | 1406 |  |  | 1397.5 |  |  | 1420 |  |  | 1407.5 |  |  | 1370.5 |  |  | 1427.5 |  |  | 1377.5 |  |  | 1431.5 |  |  | 1409.5 |  |  | 1383.5 |  |  | 1497.5 |  |  | 1381.5 |  |  | 1469 |  |  | 1415.5 |  |  | 1302 |  |  | 1403 |  |  | 1471.5 |  |  | 1342 |  |  | 1331.5 |  |  | 1394.5 |  |  | 1492.5 |  |  | 1363.5 |  |  | 1436.5 |  |  | 1514.5 |  |  | 1482.5 |  |  | 1374 |  |  | 1481 |  |  | 1345.5 |  |  | 1325.5 |  |  | 1429 |  |  | 1411.5 |  |  | 1444.5 |  |  | 1382.5 |  |  | 1351.5 |  |  | 1335.5 |  |  | 1385 |  |  | 1432.5 |  |  | 1411.5 |  |  | 1363.5 |  |  | 1360 |  |  | 1504.5 |  |  | 1462.5 |  |  | 1454.5 |  |  | 1557.5 |  |  | 1479.5 |  |  | 1426.5 |  |  | 1523.5 |  |  | 1213.5 |  |  | 1399.5 |  |  | 1357 |  |  | 1512.5 |  |  | 1424.5 |  |  | 1479.5 |  |  | 1355.5 |  |  | 1354.5 |  |  | 1345.5 |  |  | 1356.5 |  |  | 1246 |  |  | 1322.5 |  |  | 1481.5 |  |  | 1514.5 |  |  | 1315 |  |  | 1385.5 |  |  | 1369 |  |  | 1398.5 |  |  | 1409.5 |  |  | 1356.5 |  |  | 1392 |  |  | 1333.5 |  |  | 1461 |  |  | 1455 |  |  | 1445.5 |  |  | 1382 |  |  | 1445 |  |  | 1480.5 |  |  | 1494.5 |  |  | 1335.5 |  |  | 1466 |  |  | 1472.5 |  |  | 1385.5 |  |  | 1277.5 |  |  | 1497.5 |  |  | 1385.5 |  |  | 1439.5 |  |  | 1373.5 |  |  | 1451.5 |  |  | 1358 |  |  | 1530.5 |  |  | 1351 |  |  | 1369.5 |  |  | 1321.5 |  |  | 1500.5 |  |  | 1490 |  |  | 1495 |  |  | 1543 |  |  | 1433.5 |  |  | 1396 |  |  | 1506.5 |  |  | 1484.5 |  |  | 1366.5 |  |  | 1412.5 |  |  | 1380.5 |  |  | 1450.5 |  |  | 1468.5 |  |  | 1438.5 |  |  | 1482 |  |  | 1355.5 |  |  | 1327.5 |  |  | 1464.5 |  |  | 1330.5 |  |  | 1340 |  |  | 1404.5 |  |  | 1458 |  |  | 1433.5 |  |  | 1439.5 |  |  | 1415.5 |  |  | 1353.5 |  |  | 1335 |  |  | 1376.5 |  |  | 1272 |  |  | 1393.5 |  |  | 1444.5 |  |  | 1558.5 |  |  | 1508.5 |  |  | 1437.5 |  |  | 1365.5 |  |  | 1319.5 |  |  | 1461.5 |  |  | 1413.5 |  |  | 1441 |  |  | 1428.5 |  |  | 1384.5 |  |  | 1359.5 |  |  | 1402.5 |  |  | 1454.5 |  |  | 1300 |  |  | 1355 |  |  | 1424.5 |  |  | 1372 |  |  | 1551.5 |  |  | 1365.5 |  |  | 1481.5 |  |  | 1524.5 |  |  | 1338.5 |  |  | 1436.5 |  |  | 1431.5 |  |  | 1411.5 |  |  | 1407 |  |  | 1439.5 |  |  | 1515.5 |  |  | 1556.5 |  |  | 1326 |  |  | 1453.5 |  |  | 1392.5 |  |  | 1507 |  |  | 1314 |  |  | 1440.5 |  |  | 1349 |  |  | 1272 |  |  | 1323.5 |  |  | 1361 |  |  | 1524.5 |  |  | 1489.5 |  |  | 1447.5 |  |  | 1418.5 |  |  | 1347.5 |  |  | 1470.5 |  |  | 1309.5 |  |  | 1421.5 |  |  | 1398.5 |  |  | 1421.5 |  |  | 1366 |  |  | 1336 |  |  | 1439.5 |  |  | 1374.5 |  |  | 1401.5 |  |  | 1468.5 |  |  | 1354.5 |  |  | 1412.5 |  |  | 1506.5 |  |  | 1376.5 |  |  | 1539 |  |  | 1316.5 |  |  | 1371 |  |  | 1388.5 |  |  | 1606.5 |  |  | 1447.5 |  |  | 1468 |  |  | 1436.5 |  |  | 1358.5 |  |  | 1327 |  |  | 1472.5 |  |  | 1358.5 |  |  | 1504.5 |  |  | 1434.5 |  |  | 1384.5 |  |  | 1385.5 |  |  | 1359 |  |  | 1353.5 |  |  | 1318.5 |  |  | 1443.5 |  |  | 1566.5 |  |  | 1359 |  |  | 1330.5 |  |  | 1537.5 |  |  | 1396 |  |  | 1481.5 |  |  | 1451.5 |  |  | 1394 |  |  | 1474.5 |  |  | 1473.5 |  |  | 1429.5 |  |  | 1338 |  |  | 1284.5 |  |  | 1431.5 |  |  | 1385 |  |  | 1417.5 |  |  | 1487.5 |  |  | 1432.5 |  |  | 1232.5 |  |  | 1506.5 |  |  | 1576.5 |  |  | 1323.5 |  |  | 1411 |  |  | 1373 |  |  | 1312.5 |  |  | 1444.5 |  |  | 1418.5 |  |  | 1393 |  |  | 1455.5 |  |  | 1420.5 |  |  | 1413.5 |  |  | 1268.5 |  |  | 1408.5 |  |  | 1390.5 |  |  | 1310.5 |  |  | 1405.5 |  |  | 1300.5 |  |  | 1446 |  |  | 1389.5 |  |  | 1389.5 |  |  | 1376.5 |  |  | 1526.5 |  |  | 1464.5 |  |  | 1400.5 |  |  | 1404.5 |  |  | 1412.5 |  |  | 1364.5 |  |  | 1477.5 |  |  | 1451.5 |  |  | 1407.5 |  |  | 1458.5 |  |  | 1525 |  |  | 1404.5 |  |  | 1457.5 |  |  | 1406 |  |  | 1488.5 |  |  | 1459.5 |  |  | 1507 |  |  | 1421.5 |  |  | 1522.5 |  |  | 1549.5 |  |  | 1511 |  |  | 1434.5 |  |  | 1480.5 |  |  | 1393.5 |  |  | 1283.5 |  |  | 1414.5 |  |  | 1297 |  |  | 1427.5 |  |  | 1487 |  |  | 1464 |  |  | 1556.5 |  |  | 1406.5 |  |  | 1377.5 |  |  | 1329.5 |  |  | 1419.5 |  |  | 1447.5 |  |  | 1419 |  |  | 1444.5 |  |  | 1449 |  |  | 1352.5 |  |  | 1466 |  |  | 1408 |  |  | 1495 |  |  | 1432.5 |  |  | 1418 |  |  | 1470.5 |  |  | 1493.5 |  |  | 1464.5 |  |  | 1582.5 |  |  | 1462.5 |  |  | 1474 |  |  | 1462.5 |  |  | 1489.5 |  |  | 1607.5 |  |  | 1471 |  |  | 1420.5 |  |  | 1367.5 |  |  | 1466.5 |  |  | 1489.5 |  |  | 1416 |  |  | 1455 |  |  | 1429 |  |  | 1467.5 |  |  | 1480 |  |  | 1509 |  |  | 1485.5 |  |  | 1341.5 |  |  | 1298.5 |  |  | 1436.5 |  |  | 1482.5 |  |  | 1540.5 |  |  | 1492.5 |  |  | 1444.5 |  |  | 1337.5 |  |  | 1304 |  |  | 1436.5 |  |  | 1375 |  |  | 1491.5 |  |  | 1495.5 |  |  | 1439.5 |  |  | 1520.5 |  |  | 1447 |  |  | 1436.5 |  |  | 1380 |  |  | 1364.5 |  |  | 1486.5 |  |  | 1346 |  |  | 1458 |  |  | 1368.5 |  |  | 1406 |  |  | 1498.5 |  |  | 1325.5 |  |  | 1390.5 |  |  | 1416.5 |  |  | 1358.5 |  |  | 1470.5 |  |  | 1338.5 |  |  | 1291 |  |  | 1481.5 |  |  | 1437.5 |  |  | 1333.5 |  |  | 1413.5 |  |  | 1364.5 |  |  | 1380.5 |  |  | 1462.5 |  |  | 1455.5 |  |  | 1468.5 |  |  | 1422.5 |  |  | 1369.5 |  |  | 1367.5 |  |  | 1444 |  |  | 1272.5 |  |  | 1369.5 |  |  | 1476 |  |  | 1354.5 |  |  | 1324.5 |  |  | 1350.5 |  |  | 1386.5 |  |  | 1501 |  |  | 1540.5 |  |  | 1431.5 |  |  | 1362.5 |  |  | 1429.5 |  |  | 1393 |  |  | 1432.5 |  |  | 1438.5 |  |  | 1497.5 |  |  | 1491.5 |  |  | 1438.5 |  |  | 1308.5 |  |  | 1508.5 |  |  | 1518.5 |  |  | 1428.5 |  |  | 1413.5 |  |  | 1521.5 |  |  | 1409 |  |  | 1432.5 |  |  | 1440.5 |  |  | 1491.5 |  |  | 1421.5 |  |  | 1350.5 |  |  | 1412.5 |  |  | 1464 |  |  | 1382.5 |  |  | 1370 |  |  | 1351.5 |  |  | 1447.5 |  |  | 1428.5 |  |  | 1383 |  |  | 1395 |  |  | 1370.5 |  |  | 1428.5 |  |  | 1293.5 |  |  | 1504.5 |  |  | 1390.5 |  |  | 1416.5 |  |  | 1364.5 |  |  | 1372.5 |  |  | 1362.5 |  |  | 1469.5 |  |  | 1373.5 |  |  | 1426.5 |  |  | 1366.5 |  |  | 1506.5 |  |  | 1466.5 |  |  | 1427.5 |  |  | 1413.5 |  |  | 1455.5 |  |  | 1367.5 |  |  | 1357.5 |  |  | 1423.5 |  |  | 1466.5 |  |  | 1453 |  |  | 1529.5 |  |  | 1404.5 |  |  | 1412.5 |  |  | 1458 |  |  | 1438.5 |  |  | 1398.5 |  |  | 1468.5 |  |  | 1430.5 |  |  | 1467 |  |  | 1287.5 |  |  | 1330.5 |  |  | 1331 |  |  | 1361 |  |  | 1438 |  |  | 1378.5 |  |  | 1396.5 |  |  | 1480.5 |  |  | 1574.5 |  |  | 1449 |  |  | 1404.5 |  |  | 1482.5 |  |  | 1313 |  |  | 1393 |  |  | 1457.5 |  |  | 1405.5 |  |  | 1464 |  |  | 1421.5 |  |  | 1493 |  |  | 1325.5 |  |  | 1302.5 |  |  | 1475 |  |  | 1480.5 |  |  | 1368.5 |  |  | 1304.5 |  |  | 1483 |  |  | 1415.5 |  |  | 1399.5 |  |  | 1345.5 |  |  | 1400.5 |  |  | 1405.5 |  |  | 1531.5 |  |  | 1379.5 |  |  | 1400.5 |  |  | 1441.5 |  |  | 1399.5 |  |  | 1486 |  |  | 1432.5 |  |  | 1470.5 |  |  | 1461.5 |  |  | 1462.5 |  |  | 1369.5 |  |  | 1536.5 |  |  | 1484.5 |  |  | 1429.5 |  |  | 1482 |  |  | 1425.5 |  |  | 1407 |  |  | 1482.5 |  |  | 1529.5 |  |  | 1573.5 |  |  | 1360.5 |  |  | 1418.5 |  |  | 1363.5 |  |  | 1252.5 |  |  | 1486.5 |  |  | 1511 |  |  | 1382.5 |  |  | 1375 |  |  | 1363.5 |  |  | 1292.5 |  |  | 1451.5 |  |  | 1454 |  |  | 1408.5 |  |  | 1474.5 |  |  | 1335 |  |  | 1360.5 |  |  | 1375 |  |  | 1405.5 |  |  | 1370.5 |  |  | 1326.5 |  |  | 1398 |  |  | 1467.5 |  |  | 1533.5 |  |  | 1356 |  |  | 1477.5 |  |  | 1280.5 |  |  | 1483 |  |  | 1427.5 |  |  | 1558.5 |  |  | 1471.5 |  |  | 1457.5 |  |  | 1341.5 |  |  | 1458.5 |  |  | 1389.5 |  |  | 1372.5 |  |  | 1314.5 |  |  | 1461.5 |  |  | 1514.5 |  |  | 1425 |  |  | 1466 |  |  | 1471.5 |  |  | 1440.5 |  |  | 1485
50 |  | 1418.5 |  |  | 1540.5 |  |  | 1472 |  |  | 1443.5 |  |  | 1534.5 |  |  | 1486.5 |  |  | 1542.5 |  |  | 1475.5 |  |  | 1454.5 |  |  | 1477.5 |  |  | 1400 |  |  | 1504.5 |  |  | 1538.5 |  |  | 1363.5 |  |  | 1368 |  |  | 1457.5 |  |  | 1608.5 |  |  | 1501.5 |  |  | 1606.5 |  |  | 1402.5 |  |  | 1441.5 |  |  | 1443.5 |  |  | 1459.5 |  |  | 1382.5 |  |  | 1329 |  |  | 1522.5 |  |  | 1446.5 |  |  | 1453.5 |  |  | 1516.5 |  |  | 1361 |  |  | 1453 |  |  | 1417.5 |  |  | 1387.5 |  |  | 1492.5 |  |  | 1357.5 |  |  | 1470 |  |  | 1383.5 |  |  | 1471 |  |  | 1410.5 |  |  | 1489.5 |  |  | 1377.5 |  |  | 1499.5 |  |  | 1403.5 |  |  | 1409 |  |  | 1628.5 |  |  | 1527 |  |  | 1433.5 |  |  | 1553.5 |  |  | 1516.5 |  |  | 1416.5 |  |  | 1425.5 |  |  | 1424.5 |  |  | 1458.5 |  |  | 1442.5 |  |  | 1474.5 |  |  | 1445.5 |  |  | 1375.5 |  |  | 1429 |  |  | 1529.5 |  |  | 1452.5 |  |  | 1440 |  |  | 1394.5 |  |  | 1498.5 |  |  | 1463.5 |  |  | 1355.5 |  |  | 1491 |  |  | 1512.5 |  |  | 1376 |  |  | 1395.5 |  |  | 1486.5 |  |  | 1459 |  |  | 1450.5 |  |  | 1437.5 |  |  | 1555.5 |  |  | 1527 |  |  | 1460 |  |  | 1391.5 |  |  | 1360.5 |  |  | 1341.5 |  |  | 1419.5 |  |  | 1411 |  |  | 1442.5 |  |  | 1481.5 |  |  | 1511.5 |  |  | 1514.5 |  |  | 1506.5 |  |  | 1498.5 |  |  | 1390.5 |  |  | 1421.5 |  |  | 1542.5 |  |  | 1492.5 |  |  | 1474 |  |  | 1350.5 |  |  | 1384 |  |  | 1404 |  |  | 1382 |  |  | 1533.5 |  |  | 1483.5 |  |  | 1380.5 |  |  | 1462.5 |  |  | 1490.5 |  |  | 1472 |  |  | 1455 |  |  | 1396.5 |  |  | 1456.5 |  |  | 1415.5 |  |  | 1464.5 |  |  | 1553.5 |  |  | 1494.5 |  |  | 1500.5 |  |  | 1547.5 |  |  | 1505.5 |  |  | 1500.5 |  |  | 1461.5 |  |  | 1443.5 |  |  | 1497.5 |  |  | 1503.5 |  |  | 1343.5 |  |  | 1485.5 |  |  | 1450.5 |  |  | 1504.5 |  |  | 1475.5 |  |  | 1404.5 |  |  | 1481.5 |  |  | 1462.5 |  |  | 1468 |  |  | 1398.5 |  |  | 1437.5 |  |  | 1382.5 |  |  | 1409.5 |  |  | 1564.5 |  |  | 1486 |  |  | 1365.5 |  |  | 1506.5 |  |  | 1391.5 |  |  | 1467.5 |  |  | 1492 |  |  | 1455.5 |  |  | 1554.5 |  |  | 1490 |  |  | 1484.5 |  |  | 1459 |  |  | 1472 |  |  | 1550.5 |  |  | 1490 |  |  | 1534.5 |  |  | 1430.5 |  |  | 1497.5 |  |  | 1400.5 |  |  | 1533.5 |  |  | 1481.5 |  |  | 1488.5 |  |  | 1499.5 |  |  | 1603.5 |  |  | 1503.5 |  |  | 1518 |  |  | 1435.5 |  |  | 1389 |  |  | 1387.5 |  |  | 1470.5 |  |  | 1454 |  |  | 1458.5 |  |  | 1437.5 |  |  | 1427.5 |  |  | 1426 |  |  | 1483.5 |  |  | 1369.5 |  |  | 1423.5 |  |  | 1536.5 |  |  | 1367.5 |  |  | 1433.5 |  |  | 1445 |  |  | 1421.5 |  |  | 1462.5 |  |  | 1432.5 |  |  | 1421.5 |  |  | 1462.5 |  |  | 1501.5 |  |  | 1351.5 |  |  | 1551 |  |  | 1504.5 |  |  | 1458.5 |  |  | 1533.5 |  |  | 1498.5 |  |  | 1392.5 |  |  | 1551.5 |  |  | 1543.5 |  |  | 1459.5 |  |  | 1511.5 |  |  | 1403.5 |  |  | 1437.5 |  |  | 1401.5 |  |  | 1308.5 |  |  | 1406 |  |  | 1379.5 |  |  | 1482.5 |  |  | 1433.5 |  |  | 1504.5 |  |  | 1508.5 |  |  | 1452.5 |  |  | 1504.5 |  |  | 1418.5 |  |  | 1489.5 |  |  | 1411.5 |  |  | 1419.5 |  |  | 1550.5 |  |  | 1448.5 |  |  | 1434.5 |  |  | 1462.5 |  |  | 1484.5 |  |  | 1491 |  |  | 1449.5 |  |  | 1442.5 |  |  | 1327 |  |  | 1605.5 |  |  | 1530 |  |  | 1453.5 |  |  | 1523.5 |  |  | 1579.5 |  |  | 1533.5 |  |  | 1400.5 |  |  | 1433.5 |  |  | 1415.5 |  |  | 1323.5 |  |  | 1436 |  |  | 1336.5 |  |  | 1310.5 |  |  | 1518.5 |  |  | 1382.5 |  |  | 1522 |  |  | 1368.5 |  |  | 1427.5 |  |  | 1501.5 |  |  | 1539.5 |  |  | 1503.5 |  |  | 1388.5 |  |  | 1404.5 |  |  | 1514.5 |  |  | 1477 |  |  | 1460 |  |  | 1418.5 |  |  | 1465.5 |  |  | 1450.5 |  |  | 1467 |  |  | 1504.5 |  |  | 1483.5 |  |  | 1397.5 |  |  | 1438 |  |  | 1461.5 |  |  | 1514.5 |  |  | 1413.5 |  |  | 1473.5 |  |  | 1455.5 |  |  | 1466.5 |  |  | 1512.5 |  |  | 1451.5 |  |  | 1550.5 |  |  | 1274 |  |  | 1375.5 |  |  | 1488.5 |  |  | 1410.5 |  |  | 1412.5 |  |  | 1431.5 |  |  | 1549 |  |  | 1397.5 |  |  | 1543.5 |  |  | 1486 |  |  | 1591.5 |  |  | 1478.5 |  |  | 1585 |  |  | 1461.5 |  |  | 1496.5 |  |  | 1561.5 |  |  | 1372.5 |  |  | 1478 |  |  | 1501 |  |  | 1505.5 |  |  | 1402.5 |  |  | 1494.5 |  |  | 1446.5 |  |  | 1557.5 |  |  | 1397.5 |  |  | 1442 |  |  | 1479.5 |  |  | 1483.5 |  |  | 1439 |  |  | 1405.5 |  |  | 1362.5 |  |  | 1446 |  |  | 1419.5 |  |  | 1385.5 |  |  | 1463.5 |  |  | 1474 |  |  | 1484.5 |  |  | 1406 |  |  | 1499.5 |  |  | 1404.5 |  |  | 1457.5 |  |  | 1462 |  |  | 1417.5 |  |  | 1536.5 |  |  | 1405.5 |  |  | 1432 |  |  | 1331.5 |  |  | 1373.5 |  |  | 1560.5 |  |  | 1543.5 |  |  | 1442.5 |  |  | 1434 |  |  | 1414.5 |  |  | 1589.5 |  |  | 1550.5 |  |  | 1386 |  |  | 1451 |  |  | 1575.5 |  |  | 1461.5 |  |  | 1375.5 |  |  | 1438.5 |  |  | 1488.5 |  |  | 1478.5 |  |  | 1477.5 |  |  | 1489.5 |  |  | 1407.5 |  |  | 1434.5 |  |  | 1466 |  |  | 1461.5 |  |  | 1564.5 |  |  | 1605.5 |  |  | 1539.5 |  |  | 1482 |  |  | 1492.5 |  |  | 1522.5 |  |  | 1509.5 |  |  | 1284.5 |  |  | 1520.5 |  |  | 1434 |  |  | 1419 |  |  | 1389 |  |  | 1475 |  |  | 1394.5 |  |  | 1453 |  |  | 1421.5 |  |  | 1397 |  |  | 1463.5 |  |  | 1555.5 |  |  | 1476.5 |  |  | 1460.5 |  |  | 1404.5 |  |  | 1477 |  |  | 1422.5 |  |  | 1515.5 |  |  | 1354.5 |  |  | 1531 |  |  | 1496.5 |  |  | 1413.5 |  |  | 1404.5 |  |  | 1544 |  |  | 1460.5 |  |  | 1358.5 |  |  | 1486.5 |  |  | 1421.5 |  |  | 1471.5 |  |  | 1381.5 |  |  | 1587.5 |  |  | 1437.5 |  |  | 1527.5 |  |  | 1325.5 |  |  | 1352 |  |  | 1462.5 |  |  | 1471.5 |  |  | 1395.5 |  |  | 1482.5 |  |  | 1589.5 |  |  | 1431 |  |  | 1457.5 |  |  | 1518 |  |  | 1412 |  |  | 1419.5 |  |  | 1563.5 |  |  | 1420.5 |  |  | 1391 |  |  | 1508.5 |  |  | 1500.5 |  |  | 1504.5 |  |  | 1352 |  |  | 1449.5 |  |  | 1315.5 |  |  | 1530.5 |  |  | 1393.5 |  |  | 1401.5 |  |  | 1410 |  |  | 1455.5 |  |  | 1438 |  |  | 1422.5 |  |  | 1425.5 |  |  | 1435.5 |  |  | 1513 |  |  | 1344.5 |  |  | 1515 |  |  | 1466 |  |  | 1412.5 |  |  | 1395.5 |  |  | 1449.5 |  |  | 1548.5 |  |  | 1528 |  |  | 1490.5 |  |  | 1423.5 |  |  | 1355.5 |  |  | 1442 |  |  | 1517.5 |  |  | 1409.5 |  |  | 1369.5 |  |  | 1376.5 |  |  | 1518 |  |  | 1339.5 |  |  | 1461.5 |  |  | 1490.5 |  |  | 1466.5 |  |  | 1433.5 |  |  | 1444.5 |  |  | 1541 |  |  | 1436.5 |  |  | 1342.5 |  |  | 1465 |  |  | 1369.5 |  |  | 1399.5 |  |  | 1445.5 |  |  | 1472 |  |  | 1483.5 |  |  | 1416.5 |  |  | 1438.5 |  |  | 1447.5 |  |  | 1550.5 |  |  | 1529 |  |  | 1498 |  |  | 1378.5 |  |  | 1477.5 |  |  | 1494.5 |  |  | 1395.5 |  |  | 1392 |  |  | 1488 |  |  | 1367 |  |  | 1500.5 |  |  | 1413 |  |  | 1465.5 |  |  | 1536.5 |  |  | 1440 |  |  | 1386.5 |  |  | 1502.5 |  |  | 1435.5 |  |  | 1570.5 |  |  | 1340.5 |  |  | 1446 |  |  | 1462 |  |  | 1294.5 |  |  | 1498.5 |  |  | 1414 |  |  | 1316.5 |  |  | 1477.5 |  |  | 1437 |  |  | 1584.5 |  |  | 1509.5 |  |  | 1352 |  |  | 1490.5 |  |  | 1472.5 |  |  | 1431 |  |  | 1488.5 |  |  | 1383 |  |  | 1600.5 |  |  | 1563 |  |  | 1410.5 |  |  | 1445.5 |  |  | 1466.5 |  |  | 1415.5 |  |  | 1479.5 |  |  | 1367.5 |  |  | 1505 |  |  | 1429.5 |  |  | 1408.5 |  |  | 1362.5 |  |  | 1511.5 |  |  | 1454.5 |  |  | 1435 |  |  | 1426.5 |  |  | 1435 |  |  | 1436.5 |  |  | 1417.5 |  |  | 1474.5 |  |  | 1416.5 |  |  | 1470.5 |  |  | 1433.5 |  |  | 1404.5 |  |  | 1536.5 |  |  | 1407.5 |  |  | 1508 |  |  | 1441.5 |  |  | 1341 |  |  | 1442 |  |  | 1486.5 |  |  | 1357 |  |  | 1370.5 |  |  | 1409.5 |  |  | 1518.5 |  |  | 1392.5 |  |  | 1451.5 |  |  | 1553.5 |  |  | 1497.5 |  |  | 1389 |  |  | 1528 |  |  | 1360.5 |  |  | 1349.5 |  |  | 1453 |  |  | 1426.5 |  |  | 1470.5 |  |  | 1397.5 |  |  | 1366.5 |  |  | 1350.5 |  |  | 1400 |  |  | 1471.5 |  |  | 1440.5 |  |  | 1387.5 |  |  | 1381 |  |  | 1533.5 |  |  | 1509.5 |  |  | 1501.5 |  |  | 1583.5 |  |  | 1500.5 |  |  | 1450.5 |  |  | 1562.5 |  |  | 1252.5 |  |  | 1438.5 |  |  | 1381 |  |  | 1536.5 |  |  | 1445.5 |  |  | 1526.5 |  |  | 1384.5 |  |  | 1375.5 |  |  | 1384.5 |  |  | 1382.5 |  |  | 1275 |  |  | 1369.5 |  |  | 1496.5 |  |  | 1540.5 |  |  | 1354 |  |  | 1409.5 |  |  | 1398 |  |  | 1419.5 |  |  | 1456.5 |  |  | 1385.5 |  |  | 1431 |  |  | 1372.5 |  |  | 1500 |  |  | 1494 |  |  | 1471.5 |  |  | 1429 |  |  | 1492 |  |  | 1506.5 |  |  | 1515.5 |  |  | 1356.5 |  |  | 1495 |  |  | 1511.5 |  |  | 1400.5 |  |  | 1316.5 |  |  | 1518.5 |  |  | 1424.5 |  |  | 1454.5 |  |  | 1397.5 |  |  | 1480.5 |  |  | 1387 |  |  | 1577.5 |  |  | 1390 |  |  | 1384.5 |  |  | 1350.5 |  |  | 1547.5 |  |  | 1516 |  |  | 1516 |  |  | 1567 |  |  | 1480.5 |  |  | 1422 |  |  | 1530.5 |  |  | 1523.5 |  |  | 1413.5 |  |  | 1433.5 |  |  | 1395.5 |  |  | 1497.5 |  |  | 1483.5 |  |  | 1462.5 |  |  | 1503 |  |  | 1379.5 |  |  | 1374.5 |  |  | 1490.5 |  |  | 1359.5 |  |  | 1366 |  |  | 1428.5 |  |  | 1484 |  |  | 1459.5 |  |  | 1465.5 |  |  | 1430.5 |  |  | 1400.5 |  |  | 1359 |  |  | 1391.5 |  |  | 1298 |  |  | 1432.5 |  |  | 1473.5 |  |  | 1584.5 |  |  | 1537.5 |  |  | 1458.5 |  |  | 1404.5 |  |  | 1340.5 |  |  | 1490.5 |  |  | 1434.5 |  |  | 1456 |  |  | 1475.5 |  |  | 1423.5 |  |  | 1383.5 |  |  | 1426.5 |  |  | 1480.5 |  |  | 1324 |  |  | 1394 |  |  | 1471.5 |  |  | 1393 |  |  | 1590.5 |  |  | 1391.5 |  |  | 1496.5 |  |  | 1548.5 |  |  | 1385.5 |  |  | 1483.5 |  |  | 1470.5 |  |  | 1440.5 |  |  | 1428 |  |  | 1478.5 |  |  | 1554.5 |  |  | 1571.5 |  |  | 1347 |  |  | 1500.5 |  |  | 1413.5 |  |  | 1522 |  |  | 1329 |  |  | 1487.5 |  |  | 1373 |  |  | 1319 |  |  | 1352.5 |  |  | 1400 |  |  | 1563.5 |  |  | 1528.5 |  |  | 1486.5 |  |  | 1433.5 |  |  | 1368.5 |  |  | 1491.5 |  |  | 1335.5 |  |  | 1447.5 |  |  | 1437.5 |  |  | 1460.5 |  |  | 1390 |  |  | 1362 |  |  | 1486.5 |  |  | 1421.5 |  |  | 1422.5 |  |  | 1494.5 |  |  | 1380.5 |  |  | 1436.5 |  |  | 1545.5 |  |  | 1405.5 |  |  | 1578 |  |  | 1345.5 |  |  | 1410 |  |  | 1427.5 |  |  | 1627.5 |  |  | 1486.5 |  |  | 1489 |  |  | 1451.5 |  |  | 1397.5 |  |  | 1353 |  |  | 1501.5 |  |  | 1384.5 |  |  | 1543.5 |  |  | 1460.5 |  |  | 1405.5 |  |  | 1432.5 |  |  | 1406 |  |  | 1379.5 |  |  | 1357.5 |  |  | 1490.5 |  |  | 1590.5 |  |  | 1388 |  |  | 1377.5 |  |  | 1566.5 |  |  | 1420 |  |  | 1510.5 |  |  | 1466.5 |  |  | 1418 |  |  | 1495.5 |  |  | 1512.5 |  |  | 1444.5 |  |  | 1385 |  |  | 1310.5 |  |  | 1452.5 |  |  | 1424 |  |  | 1446.5 |  |  | 1534.5 |  |  | 1453.5 |  |  | 1271.5 |  |  | 1521.5 |  |  | 1597.5 |  |  | 1362.5 |  |  | 1437 |  |  | 1412 |  |  | 1338.5 |  |  | 1470.5 |  |  | 1433.5 |  |  | 1419 |  |  | 1494.5 |  |  | 1435.5 |  |  | 1439.5 |  |  | 1297.5 |  |  | 1429.5 |  |  | 1414.5 |  |  | 1349.5 |  |  | 1420.5 |  |  | 1315.5 |  |  | 1472 |  |  | 1410.5 |  |  | 1418.5 |  |  | 1397.5 |  |  | 1555.5 |  |  | 1503.5 |  |  | 1439.5 |  |  | 1443.5 |  |  | 1451.5 |  |  | 1393.5 |  |  | 1492.5 |  |  | 1477.5 |  |  | 1433.5 |  |  | 1505.5 |  |  | 1554 |  |  | 1425.5 |  |  | 1496.5 |  |  | 1435 |  |  | 1527.5 |  |  | 1498.5 |  |  | 1546 |  |  | 1447.5 |  |  | 1548.5 |  |  | 1575.5 |  |  | 1550 |  |  | 1481.5 |  |  | 1519.5 |  |  | 1432.5 |  |  | 1312.5 |  |  | 1440.5 |  |  | 1336 |  |  | 1466.5 |  |  | 1502 |  |  | 1493 |  |  | 1595.5 |  |  | 1445.5 |  |  | 1403.5 |  |  | 1350.5 |  |  | 1466.5 |  |  | 1468.5 |  |  | 1458 |  |  | 1459.5 |  |  | 1470 |  |  | 1378.5 |  |  | 1492 |  |  | 1455 |  |  | 1524 |  |  | 1447.5 |  |  | 1439 |  |  | 1517.5 |  |  | 1517.5 |  |  | 1493.5 |  |  | 1597.5 |  |  | 1488.5 |  |  | 1500 |  |  | 1477.5 |  |  | 1513.5 |  |  | 1636.5 |  |  | 1492 |  |  | 1441.5 |  |  | 1391.5 |  |  | 1505.5 |  |  | 1513.5 |  |  | 1442 |  |  | 1476 |  |  | 1444 |  |  | 1488.5 |  |  | 1501 |  |  | 1556 |  |  | 1524.5 |  |  | 1367.5 |  |  | 1345.5 |  |  | 1475.5 |  |  | 1506.5 |  |  | 1579.5 |  |  | 1531.5 |  |  | 1459.5 |  |  | 1366.5 |  |  | 1330 |  |  | 1462.5 |  |  | 1404 |  |  | 1538.5 |  |  | 1542.5 |  |  | 1460.5 |  |  | 1559.5 |  |  | 1476 |  |  | 1460.5 |  |  | 1419 |  |  | 1403.5 |  |  | 1507.5 |  |  | 1372 |  |  | 1479 |  |  | 1415.5 |  |  | 1453 |  |  | 1527.5 |  |  | 1354.5 |  |  | 1416.5 |  |  | 1445.5 |  |  | 1405.5 |  |  | 1494.5 |  |  | 1362.5 |  |  | 1317 |  |  | 1520.5 |  |  | 1484.5 |  |  | 1357.5 |  |  | 1452.5 |  |  | 1393.5 |  |  | 1401.5 |  |  | 1501.5 |  |  | 1481.5 |  |  | 1507.5 |  |  | 1461.5 |  |  | 1390.5 |  |  | 1391.5 |  |  | 1483 |  |  | 1293.5 |  |  | 1408.5 |  |  | 1497 |  |  | 1378.5 |  |  | 1353.5 |  |  | 1397.5 |  |  | 1433.5 |  |  | 1530 |  |  | 1587.5 |  |  | 1457.5 |  |  | 1383.5 |  |  | 1450.5 |  |  | 1417 |  |  | 1458.5 |  |  | 1477.5 |  |  | 1523.5 |  |  | 1512.5 |  |  | 1462.5 |  |  | 1347.5 |  |  | 1537.5 |  |  | 1544.5 |  |  | 1475.5 |  |  | 1460.5 |  |  | 1542.5 |  |  | 1448 |  |  | 1456.5 |  |  | 1464.5 |  |  | 1530.5 |  |  | 1460.5 |  |  | 1374.5 |  |  | 1438.5 |  |  | 1493 |  |  | 1421.5 |  |  | 1399 |  |  | 1372.5 |  |  | 1494.5 |  |  | 1443.5 |  |  | 1422 |  |  | 1410 |  |  | 1396.5 |  |  | 1467.5 |  |  | 1319.5 |  |  | 1551.5 |  |  | 1405.5 |  |  | 1437.5 |  |  | 1379.5 |  |  | 1411.5 |  |  | 1409.5 |  |  | 1516.5 |  |  | 1399.5 |  |  | 1447.5 |  |  | 1405.5 |  |  | 1545.5 |  |  | 1505.5 |  |  | 1448.5 |  |  | 1434.5 |  |  | 1484.5 |  |  | 1382.5 |  |  | 1404.5 |  |  | 1444.5 |  |  | 1487.5 |  |  | 1468 |  |  | 1553.5 |  |  | 1443.5 |  |  | 1459.5 |  |  | 1479 |  |  | 1467.5 |  |  | 1445.5 |  |  | 1494.5 |  |  | 1445.5 |  |  | 1506 |  |  | 1311.5 |  |  | 1345.5 |  |  | 1352 |  |  | 1408 |  |  | 1477 |  |  | 1425.5 |  |  | 1443.5 |  |  | 1504.5 |  |  | 1600.5 |  |  | 1475 |  |  | 1430.5 |  |  | 1529.5 |  |  | 1334 |  |  | 1422 |  |  | 1478.5 |  |  | 1429.5 |  |  | 1493 |  |  | 1436.5 |  |  | 1532 |  |  | 1372.5 |  |  | 1341.5 |  |  | 1504 |  |  | 1495.5 |  |  | 1383.5 |  |  | 1328.5 |  |  | 1507 |  |  | 1441.5 |  |  | 1414.5 |  |  | 1360.5 |  |  | 1429.5 |  |  | 1434.5 |  |  | 1570.5 |  |  | 1394.5 |  |  | 1426.5 |  |  | 1456.5 |  |  | 1414.5 |  |  | 1510 |  |  | 1458.5 |  |  | 1491.5 |  |  | 1476.5 |  |  | 1501.5 |  |  | 1408.5 |  |  | 1565.5 |  |  | 1531.5 |  |  | 1468.5 |  |  | 1511 |  |  | 1446.5 |  |  | 1446 |  |  | 1521.5 |  |  | 1555.5 |  |  | 1599.5 |  |  | 1386.5 |  |  | 1442.5 |  |  | 1389.5 |  |  | 1291.5 |  |  | 1525.5 |  |  | 1537 |  |  | 1403.5 |  |  | 1399 |  |  | 1392.5 |  |  | 1307.5 |  |  | 1490.5 |  |  | 1483 |  |  | 1447.5 |  |  | 1495.5 |  |  | 1356 |  |  | 1389.5 |  |  | 1414 |  |  | 1431.5 |  |  | 1417.5 |  |  | 1365.5 |  |  | 1445 |  |  | 1488.5 |  |  | 1554.5 |  |  | 1380 |  |  | 1492.5 |  |  | 1304.5 |  |  | 1512 |  |  | 1442.5 |  |  | 1597.5 |  |  | 1500.5 |  |  | 1483.5 |  |  | 1362.5 |  |  | 1497.5 |  |  | 1418.5 |  |  | 1411.5 |  |  | 1338.5 |  |  | 1490.5 |  |  | 1561.5 |  |  | 1451 |  |  | 1505 |  |  | 1510.5 |  |  | 1479.5 |  |  | 1524
51 |  | 1457.5 |  |  | 1579.5 |  |  | 1496 |  |  | 1482.5 |  |  | 1581.5 |  |  | 1510.5 |  |  | 1568.5 |  |  | 1501.5 |  |  | 1501.5 |  |  | 1501.5 |  |  | 1426 |  |  | 1551.5 |  |  | 1553.5 |  |  | 1402.5 |  |  | 1394 |  |  | 1496.5 |  |  | 1637.5 |  |  | 1522.5 |  |  | 1645.5 |  |  | 1423.5 |  |  | 1467.5 |  |  | 1490.5 |  |  | 1474.5 |  |  | 1429.5 |  |  | 1358 |  |  | 1551.5 |  |  | 1461.5 |  |  | 1492.5 |  |  | 1555.5 |  |  | 1385 |  |  | 1468 |  |  | 1438.5 |  |  | 1413.5 |  |  | 1531.5 |  |  | 1386.5 |  |  | 1509 |  |  | 1422.5 |  |  | 1495 |  |  | 1449.5 |  |  | 1515.5 |  |  | 1416.5 |  |  | 1520.5 |  |  | 1432.5 |  |  | 1424 |  |  | 1667.5 |  |  | 1574 |  |  | 1448.5 |  |  | 1577.5 |  |  | 1540.5 |  |  | 1455.5 |  |  | 1454.5 |  |  | 1463.5 |  |  | 1482.5 |  |  | 1468.5 |  |  | 1521.5 |  |  | 1460.5 |  |  | 1390.5 |  |  | 1468 |  |  | 1544.5 |  |  | 1481.5 |  |  | 1466 |  |  | 1433.5 |  |  | 1537.5 |  |  | 1487.5 |  |  | 1381.5 |  |  | 1520 |  |  | 1538.5 |  |  | 1423 |  |  | 1424.5 |  |  | 1512.5 |  |  | 1498 |  |  | 1465.5 |  |  | 1476.5 |  |  | 1594.5 |  |  | 1574 |  |  | 1484 |  |  | 1430.5 |  |  | 1399.5 |  |  | 1362.5 |  |  | 1458.5 |  |  | 1435 |  |  | 1466.5 |  |  | 1502.5 |  |  | 1550.5 |  |  | 1561.5 |  |  | 1532.5 |  |  | 1519.5 |  |  | 1414.5 |  |  | 1436.5 |  |  | 1581.5 |  |  | 1518.5 |  |  | 1521 |  |  | 1389.5 |  |  | 1413 |  |  | 1451 |  |  | 1429 |  |  | 1559.5 |  |  | 1530.5 |  |  | 1419.5 |  |  | 1488.5 |  |  | 1516.5 |  |  | 1493 |  |  | 1481 |  |  | 1435.5 |  |  | 1495.5 |  |  | 1454.5 |  |  | 1511.5 |  |  | 1577.5 |  |  | 1509.5 |  |  | 1547.5 |  |  | 1573.5 |  |  | 1520.5 |  |  | 1521.5 |  |  | 1490.5 |  |  | 1464.5 |  |  | 1526.5 |  |  | 1518.5 |  |  | 1358.5 |  |  | 1532.5 |  |  | 1471.5 |  |  | 1525.5 |  |  | 1514.5 |  |  | 1430.5 |  |  | 1502.5 |  |  | 1501.5 |  |  | 1507 |  |  | 1427.5 |  |  | 1476.5 |  |  | 1411.5 |  |  | 1433.5 |  |  | 1611.5 |  |  | 1507 |  |  | 1412.5 |  |  | 1535.5 |  |  | 1420.5 |  |  | 1493.5 |  |  | 1518 |  |  | 1484.5 |  |  | 1569.5 |  |  | 1505 |  |  | 1508.5 |  |  | 1480 |  |  | 1511 |  |  | 1576.5 |  |  | 1511 |  |  | 1563.5 |  |  | 1459.5 |  |  | 1512.5 |  |  | 1421.5 |  |  | 1559.5 |  |  | 1520.5 |  |  | 1514.5 |  |  | 1546.5 |  |  | 1618.5 |  |  | 1542.5 |  |  | 1533 |  |  | 1474.5 |  |  | 1413 |  |  | 1413.5 |  |  | 1494.5 |  |  | 1501 |  |  | 1497.5 |  |  | 1476.5 |  |  | 1456.5 |  |  | 1441 |  |  | 1522.5 |  |  | 1395.5 |  |  | 1438.5 |  |  | 1565.5 |  |  | 1382.5 |  |  | 1457.5 |  |  | 1484 |  |  | 1460.5 |  |  | 1509.5 |  |  | 1458.5 |  |  | 1447.5 |  |  | 1501.5 |  |  | 1516.5 |  |  | 1372.5 |  |  | 1598 |  |  | 1543.5 |  |  | 1497.5 |  |  | 1562.5 |  |  | 1524.5 |  |  | 1407.5 |  |  | 1590.5 |  |  | 1582.5 |  |  | 1480.5 |  |  | 1526.5 |  |  | 1429.5 |  |  | 1476.5 |  |  | 1440.5 |  |  | 1329.5 |  |  | 1427 |  |  | 1426.5 |  |  | 1521.5 |  |  | 1454.5 |  |  | 1551.5 |  |  | 1529.5 |  |  | 1491.5 |  |  | 1530.5 |  |  | 1465.5 |  |  | 1515.5 |  |  | 1440.5 |  |  | 1458.5 |  |  | 1574.5 |  |  | 1474.5 |  |  | 1449.5 |  |  | 1486.5 |  |  | 1505.5 |  |  | 1520 |  |  | 1488.5 |  |  | 1466.5 |  |  | 1366 |  |  | 1652.5 |  |  | 1545 |  |  | 1477.5 |  |  | 1562.5 |  |  | 1618.5 |  |  | 1580.5 |  |  | 1424.5 |  |  | 1454.5 |  |  | 1454.5 |  |  | 1362.5 |  |  | 1460 |  |  | 1375.5 |  |  | 1349.5 |  |  | 1557.5 |  |  | 1403.5 |  |  | 1561 |  |  | 1394.5 |  |  | 1474.5 |  |  | 1540.5 |  |  | 1578.5 |  |  | 1550.5 |  |  | 1427.5 |  |  | 1425.5 |  |  | 1540.5 |  |  | 1516 |  |  | 1489 |  |  | 1447.5 |  |  | 1486.5 |  |  | 1489.5 |  |  | 1506 |  |  | 1533.5 |  |  | 1530.5 |  |  | 1436.5 |  |  | 1467 |  |  | 1490.5 |  |  | 1540.5 |  |  | 1452.5 |  |  | 1499.5 |  |  | 1481.5 |  |  | 1481.5 |  |  | 1527.5 |  |  | 1466.5 |  |  | 1589.5 |  |  | 1313 |  |  | 1414.5 |  |  | 1514.5 |  |  | 1449.5 |  |  | 1436.5 |  |  | 1455.5 |  |  | 1570 |  |  | 1426.5 |  |  | 1564.5 |  |  | 1512 |  |  | 1615.5 |  |  | 1493.5 |  |  | 1606 |  |  | 1490.5 |  |  | 1517.5 |  |  | 1600.5 |  |  | 1393.5 |  |  | 1499 |  |  | 1540 |  |  | 1529.5 |  |  | 1426.5 |  |  | 1520.5 |  |  | 1475.5 |  |  | 1583.5 |  |  | 1436.5 |  |  | 1471 |  |  | 1505.5 |  |  | 1507.5 |  |  | 1468 |  |  | 1434.5 |  |  | 1377.5 |  |  | 1470 |  |  | 1466.5 |  |  | 1432.5 |  |  | 1502.5 |  |  | 1489 |  |  | 1510.5 |  |  | 1445 |  |  | 1514.5 |  |  | 1419.5 |  |  | 1496.5 |  |  | 1483 |  |  | 1432.5 |  |  | 1557.5 |  |  | 1444.5 |  |  | 1456 |  |  | 1352.5 |  |  | 1420.5 |  |  | 1599.5 |  |  | 1590.5 |  |  | 1463.5 |  |  | 1463 |  |  | 1443.5 |  |  | 1618.5 |  |  | 1597.5 |  |  | 1410 |  |  | 1466 |  |  | 1599.5 |  |  | 1476.5 |  |  | 1390.5 |  |  | 1464.5 |  |  | 1509.5 |  |  | 1504.5 |  |  | 1516.5 |  |  | 1515.5 |  |  | 1454.5 |  |  | 1463.5 |  |  | 1505 |  |  | 1487.5 |  |  | 1593.5 |  |  | 1629.5 |  |  | 1563.5 |  |  | 1521 |  |  | 1521.5 |  |  | 1548.5 |  |  | 1538.5 |  |  | 1310.5 |  |  | 1549.5 |  |  | 1481 |  |  | 1458 |  |  | 1415 |  |  | 1514 |  |  | 1433.5 |  |  | 1492 |  |  | 1460.5 |  |  | 1436 |  |  | 1492.5 |  |  | 1594.5 |  |  | 1515.5 |  |  | 1475.5 |  |  | 1428.5 |  |  | 1503 |  |  | 1461.5 |  |  | 1544.5 |  |  | 1375.5 |  |  | 1552 |  |  | 1511.5 |  |  | 1442.5 |  |  | 1443.5 |  |  | 1573 |  |  | 1486.5 |  |  | 1382.5 |  |  | 1525.5 |  |  | 1445.5 |  |  | 1495.5 |  |  | 1420.5 |  |  | 1616.5 |  |  | 1461.5 |  |  | 1548.5 |  |  | 1340.5 |  |  | 1376 |  |  | 1509.5 |  |  | 1495.5 |  |  | 1434.5 |  |  | 1506.5 |  |  | 1615.5 |  |  | 1470 |  |  | 1478.5 |  |  | 1542 |  |  | 1459 |  |  | 1466.5 |  |  | 1589.5 |  |  | 1459.5 |  |  | 1406 |  |  | 1532.5 |  |  | 1547.5 |  |  | 1551.5 |  |  | 1367 |  |  | 1473.5 |  |  | 1339.5 |  |  | 1556.5 |  |  | 1417.5 |  |  | 1422.5 |  |  | 1449 |  |  | 1470.5 |  |  | 1464 |  |  | 1437.5 |  |  | 1440.5 |  |  | 1461.5 |  |  | 1552 |  |  | 1359.5 |  |  | 1536 |  |  | 1487 |  |  | 1459.5 |  |  | 1424.5 |  |  | 1488.5 |  |  | 1595.5 |  |  | 1554 |  |  | 1529.5 |  |  | 1462.5 |  |  | 1376.5 |  |  | 1457 |  |  | 1556.5 |  |  | 1435.5 |  |  | 1395.5 |  |  | 1423.5 |  |  | 1557 |  |  | 1360.5 |  |  | 1500.5 |  |  | 1537.5 |  |  | 1481.5 |  |  | 1448.5 |  |  | 1470.5 |  |  | 1556 |  |  | 1475.5 |  |  | 1381.5 |  |  | 1489 |  |  | 1416.5 |  |  | 1420.5 |  |  | 1474.5 |  |  | 1487 |  |  | 1522.5 |  |  | 1440.5 |  |  | 1467.5 |  |  | 1494.5 |  |  | 1576.5 |  |  | 1555 |  |  | 1527 |  |  | 1417.5 |  |  | 1503.5 |  |  | 1509.5 |  |  | 1419.5 |  |  | 1416 |  |  | 1517 |  |  | 1382 |  |  | 1539.5 |  |  | 1439 |  |  | 1504.5 |  |  | 1565.5 |  |  | 1466 |  |  | 1425.5 |  |  | 1531.5 |  |  | 1450.5 |  |  | 1591.5 |  |  | 1355.5 |  |  | 1461 |  |  | 1501 |  |  | 1315.5 |  |  | 1513.5 |  |  | 1453 |  |  | 1363.5 |  |  | 1516.5 |  |  | 1466 |  |  | 1623.5 |  |  | 1548.5 |  |  | 1391 |  |  | 1529.5 |  |  | 1493.5 |  |  | 1452 |  |  | 1535.5 |  |  | 1404 |  |  | 1639.5 |  |  | 1602 |  |  | 1434.5 |  |  | 1469.5 |  |  | 1513.5 |  |  | 1441.5 |  |  | 1518.5 |  |  | 1406.5 |  |  | 1529 |  |  | 1455.5 |  |  | 1432.5 |  |  | 1401.5 |  |  | 1537.5 |  |  | 1475.5 |  |  | 1456 |  |  | 1447.5 |  |  | 1474 |  |  | 1483.5 |  |  | 1446.5 |  |  | 1513.5 |  |  | 1431.5 |  |  | 1485.5 |  |  | 1480.5 |  |  | 1443.5 |  |  | 1575.5 |  |  | 1431.5 |  |  | 1523 |  |  | 1480.5 |  |  | 1380 |  |  | 1463 |  |  | 1525.5 |  |  | 1404 |  |  | 1394.5 |  |  | 1456.5 |  |  | 1544.5 |  |  | 1431.5 |  |  | 1498.5 |  |  | 1592.5 |  |  | 1536.5 |  |  | 1415 |  |  | 1575 |  |  | 1375.5 |  |  | 1388.5 |  |  | 1492 |  |  | 1441.5 |  |  | 1517.5 |  |  | 1426.5 |  |  | 1395.5 |  |  | 1389.5 |  |  | 1421 |  |  | 1492.5 |  |  | 1487.5 |  |  | 1413.5 |  |  | 1420 |  |  | 1559.5 |  |  | 1530.5 |  |  | 1530.5 |  |  | 1612.5 |  |  | 1539.5 |  |  | 1465.5 |  |  | 1591.5 |  |  | 1281.5 |  |  | 1485.5 |  |  | 1420 |  |  | 1575.5 |  |  | 1466.5 |  |  | 1565.5 |  |  | 1399.5 |  |  | 1422.5 |  |  | 1423.5 |  |  | 1408.5 |  |  | 1301 |  |  | 1384.5 |  |  | 1522.5 |  |  | 1579.5 |  |  | 1375 |  |  | 1435.5 |  |  | 1424 |  |  | 1434.5 |  |  | 1480.5 |  |  | 1409.5 |  |  | 1478 |  |  | 1393.5 |  |  | 1515 |  |  | 1509 |  |  | 1495.5 |  |  | 1468 |  |  | 1513 |  |  | 1532.5 |  |  | 1536.5 |  |  | 1395.5 |  |  | 1534 |  |  | 1535.5 |  |  | 1415.5 |  |  | 1342.5 |  |  | 1533.5 |  |  | 1463.5 |  |  | 1469.5 |  |  | 1436.5 |  |  | 1509.5 |  |  | 1426 |  |  | 1592.5 |  |  | 1416 |  |  | 1408.5 |  |  | 1389.5 |  |  | 1571.5 |  |  | 1542 |  |  | 1540 |  |  | 1596 |  |  | 1504.5 |  |  | 1451 |  |  | 1545.5 |  |  | 1562.5 |  |  | 1452.5 |  |  | 1480.5 |  |  | 1416.5 |  |  | 1523.5 |  |  | 1509.5 |  |  | 1509.5 |  |  | 1529 |  |  | 1405.5 |  |  | 1389.5 |  |  | 1529.5 |  |  | 1383.5 |  |  | 1387 |  |  | 1443.5 |  |  | 1505 |  |  | 1498.5 |  |  | 1504.5 |  |  | 1456.5 |  |  | 1439.5 |  |  | 1383 |  |  | 1412.5 |  |  | 1319 |  |  | 1479.5 |  |  | 1520.5 |  |  | 1608.5 |  |  | 1563.5 |  |  | 1482.5 |  |  | 1451.5 |  |  | 1379.5 |  |  | 1514.5 |  |  | 1481.5 |  |  | 1480 |  |  | 1514.5 |  |  | 1452.5 |  |  | 1422.5 |  |  | 1473.5 |  |  | 1504.5 |  |  | 1363 |  |  | 1433 |  |  | 1492.5 |  |  | 1414 |  |  | 1611.5 |  |  | 1430.5 |  |  | 1525.5 |  |  | 1587.5 |  |  | 1424.5 |  |  | 1530.5 |  |  | 1499.5 |  |  | 1487.5 |  |  | 1452 |  |  | 1499.5 |  |  | 1578.5 |  |  | 1592.5 |  |  | 1362 |  |  | 1526.5 |  |  | 1428.5 |  |  | 1537 |  |  | 1376 |  |  | 1513.5 |  |  | 1412 |  |  | 1343 |  |  | 1399.5 |  |  | 1447 |  |  | 1602.5 |  |  | 1557.5 |  |  | 1515.5 |  |  | 1472.5 |  |  | 1383.5 |  |  | 1506.5 |  |  | 1350.5 |  |  | 1468.5 |  |  | 1484.5 |  |  | 1486.5 |  |  | 1416 |  |  | 1388 |  |  | 1525.5 |  |  | 1442.5 |  |  | 1461.5 |  |  | 1515.5 |  |  | 1395.5 |  |  | 1475.5 |  |  | 1571.5 |  |  | 1429.5 |  |  | 1617 |  |  | 1374.5 |  |  | 1425 |  |  | 1474.5 |  |  | 1653.5 |  |  | 1515.5 |  |  | 1513 |  |  | 1480.5 |  |  | 1423.5 |  |  | 1368 |  |  | 1540.5 |  |  | 1431.5 |  |  | 1572.5 |  |  | 1507.5 |  |  | 1444.5 |  |  | 1447.5 |  |  | 1453 |  |  | 1418.5 |  |  | 1396.5 |  |  | 1519.5 |  |  | 1611.5 |  |  | 1414 |  |  | 1398.5 |  |  | 1595.5 |  |  | 1446 |  |  | 1536.5 |  |  | 1490.5 |  |  | 1457 |  |  | 1516.5 |  |  | 1559.5 |  |  | 1473.5 |  |  | 1424 |  |  | 1349.5 |  |  | 1476.5 |  |  | 1450 |  |  | 1475.5 |  |  | 1560.5 |  |  | 1500.5 |  |  | 1300.5 |  |  | 1545.5 |  |  | 1636.5 |  |  | 1391.5 |  |  | 1466 |  |  | 1433 |  |  | 1353.5 |  |  | 1499.5 |  |  | 1448.5 |  |  | 1445 |  |  | 1541.5 |  |  | 1459.5 |  |  | 1460.5 |  |  | 1336.5 |  |  | 1444.5 |  |  | 1429.5 |  |  | 1373.5 |  |  | 1467.5 |  |  | 1341.5 |  |  | 1498 |  |  | 1436.5 |  |  | 1439.5 |  |  | 1444.5 |  |  | 1576.5 |  |  | 1532.5 |  |  | 1486.5 |  |  | 1472.5 |  |  | 1498.5 |  |  | 1432.5 |  |  | 1539.5 |  |  | 1498.5 |  |  | 1454.5 |  |  | 1544.5 |  |  | 1569 |  |  | 1446.5 |  |  | 1522.5 |  |  | 1482 |  |  | 1556.5 |  |  | 1537.5 |  |  | 1570 |  |  | 1473.5 |  |  | 1587.5 |  |  | 1614.5 |  |  | 1589 |  |  | 1496.5 |  |  | 1545.5 |  |  | 1479.5 |  |  | 1351.5 |  |  | 1461.5 |  |  | 1360 |  |  | 1487.5 |  |  | 1531 |  |  | 1508 |  |  | 1610.5 |  |  | 1492.5 |  |  | 1442.5 |  |  | 1376.5 |  |  | 1505.5 |  |  | 1489.5 |  |  | 1482 |  |  | 1483.5 |  |  | 1509 |  |  | 1417.5 |  |  | 1521 |  |  | 1476 |  |  | 1571 |  |  | 1494.5 |  |  | 1463 |  |  | 1556.5 |  |  | 1538.5 |  |  | 1517.5 |  |  | 1626.5 |  |  | 1503.5 |  |  | 1529 |  |  | 1516.5 |  |  | 1542.5 |  |  | 1651.5 |  |  | 1516 |  |  | 1467.5 |  |  | 1406.5 |  |  | 1529.5 |  |  | 1542.5 |  |  | 1466 |  |  | 1515 |  |  | 1468 |  |  | 1517.5 |  |  | 1527 |  |  | 1580 |  |  | 1550.5 |  |  | 1414.5 |  |  | 1369.5 |  |  | 1504.5 |  |  | 1532.5 |  |  | 1594.5 |  |  | 1578.5 |  |  | 1506.5 |  |  | 1381.5 |  |  | 1377 |  |  | 1483.5 |  |  | 1451 |  |  | 1559.5 |  |  | 1571.5 |  |  | 1499.5 |  |  | 1574.5 |  |  | 1502 |  |  | 1489.5 |  |  | 1434 |  |  | 1442.5 |  |  | 1528.5 |  |  | 1387 |  |  | 1518 |  |  | 1441.5 |  |  | 1500 |  |  | 1551.5 |  |  | 1369.5 |  |  | 1440.5 |  |  | 1466.5 |  |  | 1434.5 |  |  | 1515.5 |  |  | 1383.5 |  |  | 1356 |  |  | 1549.5 |  |  | 1510.5 |  |  | 1404.5 |  |  | 1473.5 |  |  | 1408.5 |  |  | 1416.5 |  |  | 1540.5 |  |  | 1510.5 |  |  | 1554.5 |  |  | 1485.5 |  |  | 1414.5 |  |  | 1420.5 |  |  | 1509 |  |  | 1332.5 |  |  | 1423.5 |  |  | 1523 |  |  | 1404.5 |  |  | 1382.5 |  |  | 1436.5 |  |  | 1457.5 |  |  | 1577 |  |  | 1616.5 |  |  | 1481.5 |  |  | 1407.5 |  |  | 1474.5 |  |  | 1441 |  |  | 1479.5 |  |  | 1524.5 |  |  | 1562.5 |  |  | 1551.5 |  |  | 1488.5 |  |  | 1368.5 |  |  | 1566.5 |  |  | 1591.5 |  |  | 1496.5 |  |  | 1481.5 |  |  | 1589.5 |  |  | 1474 |  |  | 1495.5 |  |  | 1493.5 |  |  | 1554.5 |  |  | 1481.5 |  |  | 1413.5 |  |  | 1464.5 |  |  | 1532 |  |  | 1460.5 |  |  | 1446 |  |  | 1419.5 |  |  | 1520.5 |  |  | 1482.5 |  |  | 1446 |  |  | 1449 |  |  | 1435.5 |  |  | 1506.5 |  |  | 1348.5 |  |  | 1577.5 |  |  | 1444.5 |  |  | 1476.5 |  |  | 1426.5 |  |  | 1450.5 |  |  | 1456.5 |  |  | 1540.5 |  |  | 1420.5 |  |  | 1486.5 |  |  | 1444.5 |  |  | 1571.5 |  |  | 1544.5 |  |  | 1474.5 |  |  | 1473.5 |  |  | 1510.5 |  |  | 1406.5 |  |  | 1419.5 |  |  | 1483.5 |  |  | 1526.5 |  |  | 1483 |  |  | 1568.5 |  |  | 1467.5 |  |  | 1480.5 |  |  | 1500 |  |  | 1514.5 |  |  | 1474.5 |  |  | 1518.5 |  |  | 1474.5 |  |  | 1527 |  |  | 1350.5 |  |  | 1384.5 |  |  | 1367 |  |  | 1437 |  |  | 1506 |  |  | 1446.5 |  |  | 1490.5 |  |  | 1525.5 |  |  | 1626.5 |  |  | 1501 |  |  | 1469.5 |  |  | 1544.5 |  |  | 1373 |  |  | 1451 |  |  | 1502.5 |  |  | 1468.5 |  |  | 1508 |  |  | 1457.5 |  |  | 1571 |  |  | 1411.5 |  |  | 1380.5 |  |  | 1533 |  |  | 1534.5 |  |  | 1422.5 |  |  | 1354.5 |  |  | 1546 |  |  | 1470.5 |  |  | 1429.5 |  |  | 1384.5 |  |  | 1450.5 |  |  | 1458.5 |  |  | 1599.5 |  |  | 1420.5 |  |  | 1465.5 |  |  | 1495.5 |  |  | 1443.5 |  |  | 1531 |  |  | 1497.5 |  |  | 1517.5 |  |  | 1515.5 |  |  | 1516.5 |  |  | 1447.5 |  |  | 1580.5 |  |  | 1555.5 |  |  | 1515.5 |  |  | 1550 |  |  | 1470.5 |  |  | 1470 |  |  | 1536.5 |  |  | 1594.5 |  |  | 1614.5 |  |  | 1425.5 |  |  | 1466.5 |  |  | 1410.5 |  |  | 1312.5 |  |  | 1564.5 |  |  | 1558 |  |  | 1442.5 |  |  | 1446 |  |  | 1413.5 |  |  | 1328.5 |  |  | 1519.5 |  |  | 1522 |  |  | 1462.5 |  |  | 1542.5 |  |  | 1377 |  |  | 1428.5 |  |  | 1438 |  |  | 1457.5 |  |  | 1443.5 |  |  | 1380.5 |  |  | 1484 |  |  | 1527.5 |  |  | 1583.5 |  |  | 1409 |  |  | 1531.5 |  |  | 1351.5 |  |  | 1541 |  |  | 1489.5 |  |  | 1626.5 |  |  | 1526.5 |  |  | 1530.5 |  |  | 1383.5 |  |  | 1536.5 |  |  | 1444.5 |  |  | 1450.5 |  |  | 1377.5 |  |  | 1516.5 |  |  | 1582.5 |  |  | 1498 |  |  | 1544 |  |  | 1534.5 |  |  | 1505.5 |  |  | 1548
52 |  | 1496.5 |  |  | 1603.5 |  |  | 1517 |  |  | 1506.5 |  |  | 1620.5 |  |  | 1539.5 |  |  | 1607.5 |  |  | 1530.5 |  |  | 1540.5 |  |  | 1522.5 |  |  | 1455 |  |  | 1577.5 |  |  | 1592.5 |  |  | 1441.5 |  |  | 1423 |  |  | 1535.5 |  |  | 1658.5 |  |  | 1548.5 |  |  | 1674.5 |  |  | 1449.5 |  |  | 1493.5 |  |  | 1519.5 |  |  | 1513.5 |  |  | 1458.5 |  |  | 1384 |  |  | 1580.5 |  |  | 1500.5 |  |  | 1531.5 |  |  | 1581.5 |  |  | 1411 |  |  | 1492 |  |  | 1477.5 |  |  | 1452.5 |  |  | 1555.5 |  |  | 1412.5 |  |  | 1556 |  |  | 1461.5 |  |  | 1521 |  |  | 1488.5 |  |  | 1541.5 |  |  | 1442.5 |  |  | 1549.5 |  |  | 1447.5 |  |  | 1453 |  |  | 1691.5 |  |  | 1598 |  |  | 1469.5 |  |  | 1603.5 |  |  | 1564.5 |  |  | 1470.5 |  |  | 1483.5 |  |  | 1502.5 |  |  | 1506.5 |  |  | 1507.5 |  |  | 1568.5 |  |  | 1507.5 |  |  | 1416.5 |  |  | 1507 |  |  | 1565.5 |  |  | 1502.5 |  |  | 1492 |  |  | 1480.5 |  |  | 1552.5 |  |  | 1508.5 |  |  | 1410.5 |  |  | 1567 |  |  | 1567.5 |  |  | 1462 |  |  | 1450.5 |  |  | 1527.5 |  |  | 1524 |  |  | 1504.5 |  |  | 1500.5 |  |  | 1609.5 |  |  | 1621 |  |  | 1531 |  |  | 1456.5 |  |  | 1446.5 |  |  | 1383.5 |  |  | 1487.5 |  |  | 1464 |  |  | 1505.5 |  |  | 1528.5 |  |  | 1576.5 |  |  | 1585.5 |  |  | 1553.5 |  |  | 1548.5 |  |  | 1453.5 |  |  | 1462.5 |  |  | 1602.5 |  |  | 1557.5 |  |  | 1547 |  |  | 1413.5 |  |  | 1439 |  |  | 1477 |  |  | 1453 |  |  | 1580.5 |  |  | 1554.5 |  |  | 1443.5 |  |  | 1517.5 |  |  | 1540.5 |  |  | 1517 |  |  | 1507 |  |  | 1474.5 |  |  | 1521.5 |  |  | 1475.5 |  |  | 1558.5 |  |  | 1598.5 |  |  | 1556.5 |  |  | 1562.5 |  |  | 1597.5 |  |  | 1567.5 |  |  | 1560.5 |  |  | 1514.5 |  |  | 1490.5 |  |  | 1565.5 |  |  | 1565.5 |  |  | 1384.5 |  |  | 1571.5 |  |  | 1518.5 |  |  | 1572.5 |  |  | 1529.5 |  |  | 1459.5 |  |  | 1517.5 |  |  | 1540.5 |  |  | 1536 |  |  | 1451.5 |  |  | 1515.5 |  |  | 1458.5 |  |  | 1459.5 |  |  | 1626.5 |  |  | 1554 |  |  | 1436.5 |  |  | 1582.5 |  |  | 1446.5 |  |  | 1532.5 |  |  | 1565 |  |  | 1499.5 |  |  | 1584.5 |  |  | 1529 |  |  | 1537.5 |  |  | 1501 |  |  | 1550 |  |  | 1605.5 |  |  | 1550 |  |  | 1602.5 |  |  | 1485.5 |  |  | 1559.5 |  |  | 1468.5 |  |  | 1583.5 |  |  | 1541.5 |  |  | 1543.5 |  |  | 1570.5 |  |  | 1639.5 |  |  | 1571.5 |  |  | 1572 |  |  | 1513.5 |  |  | 1437 |  |  | 1452.5 |  |  | 1518.5 |  |  | 1525 |  |  | 1523.5 |  |  | 1523.5 |  |  | 1477.5 |  |  | 1462 |  |  | 1548.5 |  |  | 1424.5 |  |  | 1464.5 |  |  | 1591.5 |  |  | 1429.5 |  |  | 1481.5 |  |  | 1513 |  |  | 1484.5 |  |  | 1538.5 |  |  | 1479.5 |  |  | 1486.5 |  |  | 1540.5 |  |  | 1537.5 |  |  | 1393.5 |  |  | 1622 |  |  | 1564.5 |  |  | 1536.5 |  |  | 1601.5 |  |  | 1563.5 |  |  | 1436.5 |  |  | 1629.5 |  |  | 1611.5 |  |  | 1527.5 |  |  | 1565.5 |  |  | 1468.5 |  |  | 1505.5 |  |  | 1455.5 |  |  | 1344.5 |  |  | 1442 |  |  | 1452.5 |  |  | 1536.5 |  |  | 1501.5 |  |  | 1598.5 |  |  | 1553.5 |  |  | 1515.5 |  |  | 1577.5 |  |  | 1489.5 |  |  | 1562.5 |  |  | 1461.5 |  |  | 1497.5 |  |  | 1589.5 |  |  | 1521.5 |  |  | 1496.5 |  |  | 1512.5 |  |  | 1544.5 |  |  | 1559 |  |  | 1535.5 |  |  | 1505.5 |  |  | 1395 |  |  | 1667.5 |  |  | 1574 |  |  | 1501.5 |  |  | 1583.5 |  |  | 1639.5 |  |  | 1627.5 |  |  | 1439.5 |  |  | 1480.5 |  |  | 1483.5 |  |  | 1377.5 |  |  | 1475 |  |  | 1401.5 |  |  | 1388.5 |  |  | 1596.5 |  |  | 1442.5 |  |  | 1576 |  |  | 1433.5 |  |  | 1521.5 |  |  | 1555.5 |  |  | 1607.5 |  |  | 1589.5 |  |  | 1451.5 |  |  | 1464.5 |  |  | 1564.5 |  |  | 1545 |  |  | 1515 |  |  | 1468.5 |  |  | 1533.5 |  |  | 1504.5 |  |  | 1530 |  |  | 1572.5 |  |  | 1551.5 |  |  | 1465.5 |  |  | 1488 |  |  | 1529.5 |  |  | 1579.5 |  |  | 1499.5 |  |  | 1528.5 |  |  | 1520.5 |  |  | 1520.5 |  |  | 1548.5 |  |  | 1505.5 |  |  | 1604.5 |  |  | 1360 |  |  | 1453.5 |  |  | 1535.5 |  |  | 1496.5 |  |  | 1460.5 |  |  | 1494.5 |  |  | 1596 |  |  | 1447.5 |  |  | 1590.5 |  |  | 1527 |  |  | 1654.5 |  |  | 1517.5 |  |  | 1645 |  |  | 1537.5 |  |  | 1538.5 |  |  | 1639.5 |  |  | 1419.5 |  |  | 1525 |  |  | 1561 |  |  | 1553.5 |  |  | 1450.5 |  |  | 1559.5 |  |  | 1490.5 |  |  | 1622.5 |  |  | 1462.5 |  |  | 1486 |  |  | 1526.5 |  |  | 1522.5 |  |  | 1507 |  |  | 1463.5 |  |  | 1392.5 |  |  | 1517 |  |  | 1492.5 |  |  | 1453.5 |  |  | 1517.5 |  |  | 1528 |  |  | 1534.5 |  |  | 1469 |  |  | 1553.5 |  |  | 1440.5 |  |  | 1525.5 |  |  | 1507 |  |  | 1458.5 |  |  | 1604.5 |  |  | 1483.5 |  |  | 1503 |  |  | 1378.5 |  |  | 1441.5 |  |  | 1638.5 |  |  | 1614.5 |  |  | 1489.5 |  |  | 1489 |  |  | 1458.5 |  |  | 1657.5 |  |  | 1618.5 |  |  | 1457 |  |  | 1495 |  |  | 1623.5 |  |  | 1523.5 |  |  | 1416.5 |  |  | 1485.5 |  |  | 1524.5 |  |  | 1528.5 |  |  | 1555.5 |  |  | 1554.5 |  |  | 1469.5 |  |  | 1510.5 |  |  | 1520 |  |  | 1526.5 |  |  | 1614.5 |  |  | 1668.5 |  |  | 1592.5 |  |  | 1545 |  |  | 1542.5 |  |  | 1569.5 |  |  | 1559.5 |  |  | 1325.5 |  |  | 1564.5 |  |  | 1496 |  |  | 1505 |  |  | 1454 |  |  | 1553 |  |  | 1457.5 |  |  | 1521 |  |  | 1484.5 |  |  | 1475 |  |  | 1539.5 |  |  | 1633.5 |  |  | 1541.5 |  |  | 1514.5 |  |  | 1452.5 |  |  | 1518 |  |  | 1476.5 |  |  | 1583.5 |  |  | 1399.5 |  |  | 1599 |  |  | 1532.5 |  |  | 1463.5 |  |  | 1469.5 |  |  | 1599 |  |  | 1501.5 |  |  | 1408.5 |  |  | 1540.5 |  |  | 1469.5 |  |  | 1510.5 |  |  | 1435.5 |  |  | 1642.5 |  |  | 1476.5 |  |  | 1595.5 |  |  | 1355.5 |  |  | 1397 |  |  | 1524.5 |  |  | 1519.5 |  |  | 1463.5 |  |  | 1532.5 |  |  | 1639.5 |  |  | 1494 |  |  | 1502.5 |  |  | 1571 |  |  | 1474 |  |  | 1505.5 |  |  | 1636.5 |  |  | 1480.5 |  |  | 1435 |  |  | 1553.5 |  |  | 1594.5 |  |  | 1566.5 |  |  | 1388 |  |  | 1499.5 |  |  | 1368.5 |  |  | 1585.5 |  |  | 1456.5 |  |  | 1451.5 |  |  | 1464 |  |  | 1491.5 |  |  | 1511 |  |  | 1484.5 |  |  | 1464.5 |  |  | 1500.5 |  |  | 1591 |  |  | 1406.5 |  |  | 1557 |  |  | 1508 |  |  | 1498.5 |  |  | 1445.5 |  |  | 1517.5 |  |  | 1616.5 |  |  | 1569 |  |  | 1550.5 |  |  | 1488.5 |  |  | 1391.5 |  |  | 1486 |  |  | 1595.5 |  |  | 1474.5 |  |  | 1419.5 |  |  | 1470.5 |  |  | 1604 |  |  | 1375.5 |  |  | 1515.5 |  |  | 1576.5 |  |  | 1496.5 |  |  | 1474.5 |  |  | 1494.5 |  |  | 1595 |  |  | 1501.5 |  |  | 1407.5 |  |  | 1510 |  |  | 1455.5 |  |  | 1444.5 |  |  | 1513.5 |  |  | 1502 |  |  | 1561.5 |  |  | 1479.5 |  |  | 1491.5 |  |  | 1515.5 |  |  | 1615.5 |  |  | 1579 |  |  | 1566 |  |  | 1456.5 |  |  | 1542.5 |  |  | 1535.5 |  |  | 1448.5 |  |  | 1431 |  |  | 1564 |  |  | 1421 |  |  | 1565.5 |  |  | 1478 |  |  | 1525.5 |  |  | 1604.5 |  |  | 1505 |  |  | 1464.5 |  |  | 1560.5 |  |  | 1497.5 |  |  | 1638.5 |  |  | 1370.5 |  |  | 1485 |  |  | 1540 |  |  | 1362.5 |  |  | 1528.5 |  |  | 1474 |  |  | 1387.5 |  |  | 1555.5 |  |  | 1492 |  |  | 1638.5 |  |  | 1587.5 |  |  | 1417 |  |  | 1550.5 |  |  | 1519.5 |  |  | 1491 |  |  | 1582.5 |  |  | 1443 |  |  | 1686.5 |  |  | 1641 |  |  | 1458.5 |  |  | 1490.5 |  |  | 1560.5 |  |  | 1467.5 |  |  | 1539.5 |  |  | 1453.5 |  |  | 1553 |  |  | 1484.5 |  |  | 1456.5 |  |  | 1416.5 |  |  | 1552.5 |  |  | 1501.5 |  |  | 1495 |  |  | 1462.5 |  |  | 1513 |  |  | 1530.5 |  |  | 1461.5 |  |  | 1542.5 |  |  | 1470.5 |  |  | 1500.5 |  |  | 1519.5 |  |  | 1458.5 |  |  | 1614.5 |  |  | 1446.5 |  |  | 1562 |  |  | 1519.5 |  |  | 1419 |  |  | 1502 |  |  | 1549.5 |  |  | 1428 |  |  | 1433.5 |  |  | 1485.5 |  |  | 1573.5 |  |  | 1470.5 |  |  | 1522.5 |  |  | 1631.5 |  |  | 1575.5 |  |  | 1430 |  |  | 1604 |  |  | 1399.5 |  |  | 1412.5 |  |  | 1521 |  |  | 1480.5 |  |  | 1532.5 |  |  | 1452.5 |  |  | 1442.5 |  |  | 1418.5 |  |  | 1445 |  |  | 1531.5 |  |  | 1526.5 |  |  | 1442.5 |  |  | 1446 |  |  | 1580.5 |  |  | 1569.5 |  |  | 1569.5 |  |  | 1636.5 |  |  | 1578.5 |  |  | 1491.5 |  |  | 1617.5 |  |  | 1305.5 |  |  | 1532.5 |  |  | 1435 |  |  | 1590.5 |  |  | 1495.5 |  |  | 1589.5 |  |  | 1425.5 |  |  | 1448.5 |  |  | 1438.5 |  |  | 1455.5 |  |  | 1348 |  |  | 1431.5 |  |  | 1546.5 |  |  | 1600.5 |  |  | 1414 |  |  | 1482.5 |  |  | 1448 |  |  | 1449.5 |  |  | 1527.5 |  |  | 1435.5 |  |  | 1504 |  |  | 1408.5 |  |  | 1530 |  |  | 1533 |  |  | 1534.5 |  |  | 1483 |  |  | 1552 |  |  | 1571.5 |  |  | 1560.5 |  |  | 1416.5 |  |  | 1560 |  |  | 1574.5 |  |  | 1462.5 |  |  | 1371.5 |  |  | 1557.5 |  |  | 1484.5 |  |  | 1484.5 |  |  | 1483.5 |  |  | 1533.5 |  |  | 1441 |  |  | 1639.5 |  |  | 1445 |  |  | 1447.5 |  |  | 1418.5 |  |  | 1600.5 |  |  | 1557 |  |  | 1564 |  |  | 1622 |  |  | 1543.5 |  |  | 1472 |  |  | 1584.5 |  |  | 1609.5 |  |  | 1481.5 |  |  | 1501.5 |  |  | 1455.5 |  |  | 1547.5 |  |  | 1524.5 |  |  | 1530.5 |  |  | 1568 |  |  | 1444.5 |  |  | 1428.5 |  |  | 1555.5 |  |  | 1422.5 |  |  | 1413 |  |  | 1464.5 |  |  | 1544 |  |  | 1537.5 |  |  | 1530.5 |  |  | 1471.5 |  |  | 1463.5 |  |  | 1398 |  |  | 1438.5 |  |  | 1366 |  |  | 1500.5 |  |  | 1559.5 |  |  | 1629.5 |  |  | 1592.5 |  |  | 1508.5 |  |  | 1466.5 |  |  | 1403.5 |  |  | 1543.5 |  |  | 1520.5 |  |  | 1495 |  |  | 1540.5 |  |  | 1491.5 |  |  | 1469.5 |  |  | 1494.5 |  |  | 1525.5 |  |  | 1389 |  |  | 1448 |  |  | 1521.5 |  |  | 1435 |  |  | 1637.5 |  |  | 1477.5 |  |  | 1572.5 |  |  | 1608.5 |  |  | 1448.5 |  |  | 1554.5 |  |  | 1525.5 |  |  | 1516.5 |  |  | 1499 |  |  | 1514.5 |  |  | 1617.5 |  |  | 1607.5 |  |  | 1377 |  |  | 1552.5 |  |  | 1454.5 |  |  | 1561 |  |  | 1415 |  |  | 1534.5 |  |  | 1433 |  |  | 1364 |  |  | 1425.5 |  |  | 1486 |  |  | 1623.5 |  |  | 1586.5 |  |  | 1539.5 |  |  | 1519.5 |  |  | 1430.5 |  |  | 1532.5 |  |  | 1376.5 |  |  | 1489.5 |  |  | 1508.5 |  |  | 1501.5 |  |  | 1445 |  |  | 1427 |  |  | 1546.5 |  |  | 1481.5 |  |  | 1490.5 |  |  | 1544.5 |  |  | 1410.5 |  |  | 1514.5 |  |  | 1600.5 |  |  | 1468.5 |  |  | 1664 |  |  | 1421.5 |  |  | 1464 |  |  | 1489.5 |  |  | 1692.5 |  |  | 1544.5 |  |  | 1560 |  |  | 1519.5 |  |  | 1447.5 |  |  | 1415 |  |  | 1579.5 |  |  | 1470.5 |  |  | 1593.5 |  |  | 1554.5 |  |  | 1459.5 |  |  | 1486.5 |  |  | 1482 |  |  | 1439.5 |  |  | 1420.5 |  |  | 1534.5 |  |  | 1632.5 |  |  | 1461 |  |  | 1445.5 |  |  | 1634.5 |  |  | 1485 |  |  | 1551.5 |  |  | 1537.5 |  |  | 1486 |  |  | 1545.5 |  |  | 1598.5 |  |  | 1520.5 |  |  | 1448 |  |  | 1375.5 |  |  | 1491.5 |  |  | 1497 |  |  | 1496.5 |  |  | 1584.5 |  |  | 1547.5 |  |  | 1339.5 |  |  | 1584.5 |  |  | 1651.5 |  |  | 1430.5 |  |  | 1490 |  |  | 1457 |  |  | 1379.5 |  |  | 1528.5 |  |  | 1463.5 |  |  | 1484 |  |  | 1588.5 |  |  | 1480.5 |  |  | 1499.5 |  |  | 1362.5 |  |  | 1491.5 |  |  | 1476.5 |  |  | 1397.5 |  |  | 1506.5 |  |  | 1370.5 |  |  | 1527 |  |  | 1475.5 |  |  | 1463.5 |  |  | 1470.5 |  |  | 1623.5 |  |  | 1547.5 |  |  | 1525.5 |  |  | 1496.5 |  |  | 1537.5 |  |  | 1453.5 |  |  | 1563.5 |  |  | 1522.5 |  |  | 1493.5 |  |  | 1565.5 |  |  | 1616 |  |  | 1485.5 |  |  | 1561.5 |  |  | 1497 |  |  | 1580.5 |  |  | 1558.5 |  |  | 1609 |  |  | 1494.5 |  |  | 1626.5 |  |  | 1629.5 |  |  | 1618 |  |  | 1535.5 |  |  | 1592.5 |  |  | 1508.5 |  |  | 1366.5 |  |  | 1490.5 |  |  | 1381 |  |  | 1511.5 |  |  | 1546 |  |  | 1523 |  |  | 1631.5 |  |  | 1539.5 |  |  | 1457.5 |  |  | 1405.5 |  |  | 1531.5 |  |  | 1510.5 |  |  | 1503 |  |  | 1509.5 |  |  | 1533 |  |  | 1443.5 |  |  | 1536 |  |  | 1505 |  |  | 1610 |  |  | 1523.5 |  |  | 1478 |  |  | 1595.5 |  |  | 1553.5 |  |  | 1546.5 |  |  | 1665.5 |  |  | 1550.5 |  |  | 1550 |  |  | 1537.5 |  |  | 1568.5 |  |  | 1680.5 |  |  | 1531 |  |  | 1506.5 |  |  | 1432.5 |  |  | 1555.5 |  |  | 1581.5 |  |  | 1487 |  |  | 1539 |  |  | 1515 |  |  | 1532.5 |  |  | 1553 |  |  | 1601 |  |  | 1579.5 |  |  | 1453.5 |  |  | 1408.5 |  |  | 1528.5 |  |  | 1547.5 |  |  | 1618.5 |  |  | 1617.5 |  |  | 1535.5 |  |  | 1407.5 |  |  | 1403 |  |  | 1507.5 |  |  | 1466 |  |  | 1583.5 |  |  | 1586.5 |  |  | 1525.5 |  |  | 1603.5 |  |  | 1531 |  |  | 1504.5 |  |  | 1473 |  |  | 1457.5 |  |  | 1549.5 |  |  | 1426 |  |  | 1547 |  |  | 1480.5 |  |  | 1524 |  |  | 1590.5 |  |  | 1393.5 |  |  | 1479.5 |  |  | 1487.5 |  |  | 1473.5 |  |  | 1554.5 |  |  | 1430.5 |  |  | 1395 |  |  | 1570.5 |  |  | 1539.5 |  |  | 1451.5 |  |  | 1499.5 |  |  | 1434.5 |  |  | 1445.5 |  |  | 1564.5 |  |  | 1531.5 |  |  | 1601.5 |  |  | 1500.5 |  |  | 1440.5 |  |  | 1446.5 |  |  | 1556 |  |  | 1353.5 |  |  | 1447.5 |  |  | 1562 |  |  | 1419.5 |  |  | 1406.5 |  |  | 1460.5 |  |  | 1496.5 |  |  | 1606 |  |  | 1655.5 |  |  | 1520.5 |  |  | 1454.5 |  |  | 1495.5 |  |  | 1488 |  |  | 1494.5 |  |  | 1545.5 |  |  | 1609.5 |  |  | 1575.5 |  |  | 1512.5 |  |  | 1397.5 |  |  | 1613.5 |  |  | 1630.5 |  |  | 1517.5 |  |  | 1496.5 |  |  | 1610.5 |  |  | 1500 |  |  | 1510.5 |  |  | 1532.5 |  |  | 1575.5 |  |  | 1528.5 |  |  | 1460.5 |  |  | 1485.5 |  |  | 1558 |  |  | 1475.5 |  |  | 1461 |  |  | 1448.5 |  |  | 1549.5 |  |  | 1529.5 |  |  | 1475 |  |  | 1496 |  |  | 1474.5 |  |  | 1545.5 |  |  | 1363.5 |  |  | 1598.5 |  |  | 1470.5 |  |  | 1491.5 |  |  | 1452.5 |  |  | 1489.5 |  |  | 1485.5 |  |  | 1587.5 |  |  | 1467.5 |  |  | 1515.5 |  |  | 1465.5 |  |  | 1600.5 |  |  | 1583.5 |  |  | 1500.5 |  |  | 1494.5 |  |  | 1539.5 |  |  | 1445.5 |  |  | 1466.5 |  |  | 1512.5 |  |  | 1565.5 |  |  | 1504 |  |  | 1583.5 |  |  | 1514.5 |  |  | 1527.5 |  |  | 1524 |  |  | 1529.5 |  |  | 1513.5 |  |  | 1539.5 |  |  | 1500.5 |  |  | 1553 |  |  | 1365.5 |  |  | 1408.5 |  |  | 1382 |  |  | 1484 |  |  | 1532 |  |  | 1467.5 |  |  | 1511.5 |  |  | 1540.5 |  |  | 1647.5 |  |  | 1540 |  |  | 1498.5 |  |  | 1583.5 |  |  | 1394 |  |  | 1472 |  |  | 1541.5 |  |  | 1483.5 |  |  | 1534 |  |  | 1486.5 |  |  | 1586 |  |  | 1458.5 |  |  | 1419.5 |  |  | 1562 |  |  | 1581.5 |  |  | 1461.5 |  |  | 1380.5 |  |  | 1561 |  |  | 1496.5 |  |  | 1455.5 |  |  | 1408.5 |  |  | 1471.5 |  |  | 1487.5 |  |  | 1620.5 |  |  | 1459.5 |  |  | 1486.5 |  |  | 1521.5 |  |  | 1482.5 |  |  | 1560 |  |  | 1536.5 |  |  | 1538.5 |  |  | 1530.5 |  |  | 1545.5 |  |  | 1494.5 |  |  | 1604.5 |  |  | 1602.5 |  |  | 1539.5 |  |  | 1597 |  |  | 1499.5 |  |  | 1491 |  |  | 1565.5 |  |  | 1641.5 |  |  | 1653.5 |  |  | 1440.5 |  |  | 1513.5 |  |  | 1436.5 |  |  | 1351.5 |  |  | 1585.5 |  |  | 1597 |  |  | 1471.5 |  |  | 1475 |  |  | 1434.5 |  |  | 1367.5 |  |  | 1558.5 |  |  | 1561 |  |  | 1501.5 |  |  | 1581.5 |  |  | 1392 |  |  | 1467.5 |  |  | 1459 |  |  | 1481.5 |  |  | 1458.5 |  |  | 1419.5 |  |  | 1499 |  |  | 1553.5 |  |  | 1609.5 |  |  | 1448 |  |  | 1578.5 |  |  | 1375.5 |  |  | 1570 |  |  | 1528.5 |  |  | 1655.5 |  |  | 1552.5 |  |  | 1569.5 |  |  | 1404.5 |  |  | 1565.5 |  |  | 1470.5 |  |  | 1497.5 |  |  | 1398.5 |  |  | 1537.5 |  |  | 1621.5 |  |  | 1537 |  |  | 1583 |  |  | 1573.5 |  |  | 1552.5 |  |  | 1577
53 |  | 1525.5 |  |  | 1650.5 |  |  | 1538 |  |  | 1530.5 |  |  | 1667.5 |  |  | 1578.5 |  |  | 1654.5 |  |  | 1577.5 |  |  | 1561.5 |  |  | 1546.5 |  |  | 1476 |  |  | 1601.5 |  |  | 1616.5 |  |  | 1480.5 |  |  | 1452 |  |  | 1550.5 |  |  | 1682.5 |  |  | 1572.5 |  |  | 1698.5 |  |  | 1473.5 |  |  | 1514.5 |  |  | 1534.5 |  |  | 1552.5 |  |  | 1473.5 |  |  | 1423 |  |  | 1606.5 |  |  | 1521.5 |  |  | 1578.5 |  |  | 1620.5 |  |  | 1450 |  |  | 1521 |  |  | 1492.5 |  |  | 1481.5 |  |  | 1602.5 |  |  | 1427.5 |  |  | 1582 |  |  | 1490.5 |  |  | 1560 |  |  | 1535.5 |  |  | 1562.5 |  |  | 1481.5 |  |  | 1588.5 |  |  | 1471.5 |  |  | 1500 |  |  | 1738.5 |  |  | 1627 |  |  | 1516.5 |  |  | 1642.5 |  |  | 1593.5 |  |  | 1509.5 |  |  | 1498.5 |  |  | 1531.5 |  |  | 1545.5 |  |  | 1533.5 |  |  | 1597.5 |  |  | 1546.5 |  |  | 1445.5 |  |  | 1546 |  |  | 1594.5 |  |  | 1528.5 |  |  | 1521 |  |  | 1495.5 |  |  | 1599.5 |  |  | 1529.5 |  |  | 1434.5 |  |  | 1591 |  |  | 1582.5 |  |  | 1486 |  |  | 1465.5 |  |  | 1556.5 |  |  | 1553 |  |  | 1533.5 |  |  | 1524.5 |  |  | 1656.5 |  |  | 1650 |  |  | 1560 |  |  | 1477.5 |  |  | 1493.5 |  |  | 1404.5 |  |  | 1526.5 |  |  | 1503 |  |  | 1544.5 |  |  | 1575.5 |  |  | 1597.5 |  |  | 1611.5 |  |  | 1568.5 |  |  | 1572.5 |  |  | 1492.5 |  |  | 1501.5 |  |  | 1628.5 |  |  | 1596.5 |  |  | 1586 |  |  | 1460.5 |  |  | 1468 |  |  | 1498 |  |  | 1474 |  |  | 1609.5 |  |  | 1601.5 |  |  | 1464.5 |  |  | 1564.5 |  |  | 1561.5 |  |  | 1543 |  |  | 1528 |  |  | 1503.5 |  |  | 1545.5 |  |  | 1522.5 |  |  | 1597.5 |  |  | 1622.5 |  |  | 1595.5 |  |  | 1586.5 |  |  | 1636.5 |  |  | 1606.5 |  |  | 1584.5 |  |  | 1529.5 |  |  | 1516.5 |  |  | 1591.5 |  |  | 1604.5 |  |  | 1408.5 |  |  | 1597.5 |  |  | 1547.5 |  |  | 1598.5 |  |  | 1553.5 |  |  | 1480.5 |  |  | 1556.5 |  |  | 1555.5 |  |  | 1557 |  |  | 1490.5 |  |  | 1530.5 |  |  | 1497.5 |  |  | 1483.5 |  |  | 1673.5 |  |  | 1593 |  |  | 1483.5 |  |  | 1629.5 |  |  | 1467.5 |  |  | 1556.5 |  |  | 1594 |  |  | 1528.5 |  |  | 1608.5 |  |  | 1544 |  |  | 1563.5 |  |  | 1527 |  |  | 1589 |  |  | 1652.5 |  |  | 1565 |  |  | 1626.5 |  |  | 1509.5 |  |  | 1598.5 |  |  | 1492.5 |  |  | 1630.5 |  |  | 1580.5 |  |  | 1582.5 |  |  | 1599.5 |  |  | 1678.5 |  |  | 1597.5 |  |  | 1619 |  |  | 1539.5 |  |  | 1458 |  |  | 1491.5 |  |  | 1565.5 |  |  | 1546 |  |  | 1538.5 |  |  | 1570.5 |  |  | 1501.5 |  |  | 1491 |  |  | 1569.5 |  |  | 1453.5 |  |  | 1488.5 |  |  | 1630.5 |  |  | 1450.5 |  |  | 1520.5 |  |  | 1542 |  |  | 1508.5 |  |  | 1562.5 |  |  | 1508.5 |  |  | 1507.5 |  |  | 1579.5 |  |  | 1566.5 |  |  | 1440.5 |  |  | 1637 |  |  | 1593.5 |  |  | 1560.5 |  |  | 1627.5 |  |  | 1587.5 |  |  | 1460.5 |  |  | 1668.5 |  |  | 1650.5 |  |  | 1556.5 |  |  | 1594.5 |  |  | 1489.5 |  |  | 1531.5 |  |  | 1479.5 |  |  | 1359.5 |  |  | 1481 |  |  | 1499.5 |  |  | 1575.5 |  |  | 1525.5 |  |  | 1637.5 |  |  | 1579.5 |  |  | 1541.5 |  |  | 1598.5 |  |  | 1504.5 |  |  | 1609.5 |  |  | 1500.5 |  |  | 1523.5 |  |  | 1618.5 |  |  | 1550.5 |  |  | 1511.5 |  |  | 1541.5 |  |  | 1583.5 |  |  | 1598 |  |  | 1574.5 |  |  | 1534.5 |  |  | 1434 |  |  | 1688.5 |  |  | 1595 |  |  | 1522.5 |  |  | 1598.5 |  |  | 1678.5 |  |  | 1651.5 |  |  | 1454.5 |  |  | 1519.5 |  |  | 1498.5 |  |  | 1392.5 |  |  | 1501 |  |  | 1440.5 |  |  | 1427.5 |  |  | 1643.5 |  |  | 1489.5 |  |  | 1600 |  |  | 1472.5 |  |  | 1560.5 |  |  | 1594.5 |  |  | 1631.5 |  |  | 1604.5 |  |  | 1466.5 |  |  | 1488.5 |  |  | 1588.5 |  |  | 1574 |  |  | 1554 |  |  | 1492.5 |  |  | 1554.5 |  |  | 1519.5 |  |  | 1551 |  |  | 1611.5 |  |  | 1566.5 |  |  | 1491.5 |  |  | 1517 |  |  | 1550.5 |  |  | 1626.5 |  |  | 1528.5 |  |  | 1543.5 |  |  | 1559.5 |  |  | 1559.5 |  |  | 1569.5 |  |  | 1529.5 |  |  | 1643.5 |  |  | 1399 |  |  | 1479.5 |  |  | 1561.5 |  |  | 1535.5 |  |  | 1484.5 |  |  | 1523.5 |  |  | 1620 |  |  | 1476.5 |  |  | 1605.5 |  |  | 1542 |  |  | 1693.5 |  |  | 1564.5 |  |  | 1684 |  |  | 1552.5 |  |  | 1559.5 |  |  | 1654.5 |  |  | 1466.5 |  |  | 1554 |  |  | 1582 |  |  | 1600.5 |  |  | 1489.5 |  |  | 1580.5 |  |  | 1529.5 |  |  | 1643.5 |  |  | 1501.5 |  |  | 1533 |  |  | 1547.5 |  |  | 1537.5 |  |  | 1531 |  |  | 1484.5 |  |  | 1413.5 |  |  | 1546 |  |  | 1516.5 |  |  | 1482.5 |  |  | 1556.5 |  |  | 1557 |  |  | 1573.5 |  |  | 1490 |  |  | 1577.5 |  |  | 1455.5 |  |  | 1540.5 |  |  | 1522 |  |  | 1487.5 |  |  | 1643.5 |  |  | 1507.5 |  |  | 1542 |  |  | 1417.5 |  |  | 1462.5 |  |  | 1685.5 |  |  | 1643.5 |  |  | 1536.5 |  |  | 1515 |  |  | 1473.5 |  |  | 1696.5 |  |  | 1647.5 |  |  | 1504 |  |  | 1534 |  |  | 1652.5 |  |  | 1538.5 |  |  | 1445.5 |  |  | 1509.5 |  |  | 1548.5 |  |  | 1567.5 |  |  | 1584.5 |  |  | 1593.5 |  |  | 1495.5 |  |  | 1534.5 |  |  | 1544 |  |  | 1565.5 |  |  | 1661.5 |  |  | 1689.5 |  |  | 1621.5 |  |  | 1584 |  |  | 1563.5 |  |  | 1590.5 |  |  | 1585.5 |  |  | 1346.5 |  |  | 1593.5 |  |  | 1535 |  |  | 1529 |  |  | 1493 |  |  | 1582 |  |  | 1481.5 |  |  | 1536 |  |  | 1523.5 |  |  | 1514 |  |  | 1563.5 |  |  | 1672.5 |  |  | 1556.5 |  |  | 1529.5 |  |  | 1476.5 |  |  | 1533 |  |  | 1515.5 |  |  | 1604.5 |  |  | 1446.5 |  |  | 1638 |  |  | 1571.5 |  |  | 1489.5 |  |  | 1516.5 |  |  | 1614 |  |  | 1548.5 |  |  | 1447.5 |  |  | 1569.5 |  |  | 1484.5 |  |  | 1534.5 |  |  | 1482.5 |  |  | 1666.5 |  |  | 1502.5 |  |  | 1624.5 |  |  | 1394.5 |  |  | 1412 |  |  | 1553.5 |  |  | 1558.5 |  |  | 1487.5 |  |  | 1561.5 |  |  | 1663.5 |  |  | 1518 |  |  | 1541.5 |  |  | 1586 |  |  | 1498 |  |  | 1531.5 |  |  | 1665.5 |  |  | 1504.5 |  |  | 1482 |  |  | 1592.5 |  |  | 1609.5 |  |  | 1587.5 |  |  | 1427 |  |  | 1528.5 |  |  | 1383.5 |  |  | 1614.5 |  |  | 1495.5 |  |  | 1477.5 |  |  | 1479 |  |  | 1515.5 |  |  | 1558 |  |  | 1531.5 |  |  | 1503.5 |  |  | 1526.5 |  |  | 1612 |  |  | 1435.5 |  |  | 1572 |  |  | 1547 |  |  | 1513.5 |  |  | 1492.5 |  |  | 1538.5 |  |  | 1645.5 |  |  | 1608 |  |  | 1576.5 |  |  | 1527.5 |  |  | 1430.5 |  |  | 1533 |  |  | 1634.5 |  |  | 1500.5 |  |  | 1440.5 |  |  | 1499.5 |  |  | 1633 |  |  | 1396.5 |  |  | 1544.5 |  |  | 1602.5 |  |  | 1522.5 |  |  | 1489.5 |  |  | 1533.5 |  |  | 1634 |  |  | 1522.5 |  |  | 1446.5 |  |  | 1531 |  |  | 1502.5 |  |  | 1459.5 |  |  | 1528.5 |  |  | 1517 |  |  | 1576.5 |  |  | 1503.5 |  |  | 1530.5 |  |  | 1554.5 |  |  | 1636.5 |  |  | 1605 |  |  | 1581 |  |  | 1471.5 |  |  | 1557.5 |  |  | 1574.5 |  |  | 1463.5 |  |  | 1460 |  |  | 1585 |  |  | 1460 |  |  | 1586.5 |  |  | 1517 |  |  | 1564.5 |  |  | 1630.5 |  |  | 1544 |  |  | 1479.5 |  |  | 1607.5 |  |  | 1523.5 |  |  | 1685.5 |  |  | 1399.5 |  |  | 1514 |  |  | 1561 |  |  | 1401.5 |  |  | 1575.5 |  |  | 1513 |  |  | 1434.5 |  |  | 1579.5 |  |  | 1518 |  |  | 1653.5 |  |  | 1602.5 |  |  | 1446 |  |  | 1565.5 |  |  | 1534.5 |  |  | 1530 |  |  | 1597.5 |  |  | 1472 |  |  | 1701.5 |  |  | 1680 |  |  | 1497.5 |  |  | 1519.5 |  |  | 1599.5 |  |  | 1506.5 |  |  | 1554.5 |  |  | 1482.5 |  |  | 1579 |  |  | 1508.5 |  |  | 1503.5 |  |  | 1437.5 |  |  | 1591.5 |  |  | 1522.5 |  |  | 1516 |  |  | 1477.5 |  |  | 1560 |  |  | 1545.5 |  |  | 1487.5 |  |  | 1581.5 |  |  | 1517.5 |  |  | 1515.5 |  |  | 1558.5 |  |  | 1479.5 |  |  | 1661.5 |  |  | 1467.5 |  |  | 1583 |  |  | 1558.5 |  |  | 1448 |  |  | 1541 |  |  | 1564.5 |  |  | 1475 |  |  | 1454.5 |  |  | 1514.5 |  |  | 1594.5 |  |  | 1496.5 |  |  | 1537.5 |  |  | 1670.5 |  |  | 1622.5 |  |  | 1469 |  |  | 1633 |  |  | 1446.5 |  |  | 1427.5 |  |  | 1560 |  |  | 1506.5 |  |  | 1571.5 |  |  | 1481.5 |  |  | 1471.5 |  |  | 1439.5 |  |  | 1466 |  |  | 1560.5 |  |  | 1541.5 |  |  | 1466.5 |  |  | 1472 |  |  | 1619.5 |  |  | 1584.5 |  |  | 1598.5 |  |  | 1683.5 |  |  | 1602.5 |  |  | 1515.5 |  |  | 1656.5 |  |  | 1320.5 |  |  | 1571.5 |  |  | 1450 |  |  | 1629.5 |  |  | 1534.5 |  |  | 1628.5 |  |  | 1451.5 |  |  | 1472.5 |  |  | 1485.5 |  |  | 1494.5 |  |  | 1369 |  |  | 1457.5 |  |  | 1575.5 |  |  | 1621.5 |  |  | 1461 |  |  | 1521.5 |  |  | 1469 |  |  | 1470.5 |  |  | 1566.5 |  |  | 1464.5 |  |  | 1543 |  |  | 1447.5 |  |  | 1551 |  |  | 1580 |  |  | 1581.5 |  |  | 1507 |  |  | 1591 |  |  | 1597.5 |  |  | 1589.5 |  |  | 1445.5 |  |  | 1586 |  |  | 1589.5 |  |  | 1501.5 |  |  | 1386.5 |  |  | 1596.5 |  |  | 1499.5 |  |  | 1513.5 |  |  | 1498.5 |  |  | 1554.5 |  |  | 1480 |  |  | 1678.5 |  |  | 1484 |  |  | 1486.5 |  |  | 1439.5 |  |  | 1647.5 |  |  | 1572 |  |  | 1603 |  |  | 1669 |  |  | 1564.5 |  |  | 1501 |  |  | 1623.5 |  |  | 1630.5 |  |  | 1510.5 |  |  | 1540.5 |  |  | 1479.5 |  |  | 1586.5 |  |  | 1553.5 |  |  | 1554.5 |  |  | 1594 |  |  | 1459.5 |  |  | 1449.5 |  |  | 1584.5 |  |  | 1461.5 |  |  | 1434 |  |  | 1490.5 |  |  | 1559 |  |  | 1552.5 |  |  | 1556.5 |  |  | 1500.5 |  |  | 1487.5 |  |  | 1427 |  |  | 1477.5 |  |  | 1395 |  |  | 1539.5 |  |  | 1606.5 |  |  | 1668.5 |  |  | 1631.5 |  |  | 1537.5 |  |  | 1505.5 |  |  | 1424.5 |  |  | 1569.5 |  |  | 1544.5 |  |  | 1510 |  |  | 1569.5 |  |  | 1517.5 |  |  | 1508.5 |  |  | 1541.5 |  |  | 1554.5 |  |  | 1428 |  |  | 1474 |  |  | 1550.5 |  |  | 1464 |  |  | 1663.5 |  |  | 1503.5 |  |  | 1611.5 |  |  | 1647.5 |  |  | 1495.5 |  |  | 1569.5 |  |  | 1554.5 |  |  | 1537.5 |  |  | 1546 |  |  | 1540.5 |  |  | 1664.5 |  |  | 1636.5 |  |  | 1406 |  |  | 1576.5 |  |  | 1493.5 |  |  | 1585 |  |  | 1454 |  |  | 1555.5 |  |  | 1459 |  |  | 1403 |  |  | 1454.5 |  |  | 1533 |  |  | 1670.5 |  |  | 1601.5 |  |  | 1568.5 |  |  | 1540.5 |  |  | 1445.5 |  |  | 1558.5 |  |  | 1415.5 |  |  | 1528.5 |  |  | 1534.5 |  |  | 1516.5 |  |  | 1469 |  |  | 1442 |  |  | 1593.5 |  |  | 1520.5 |  |  | 1519.5 |  |  | 1591.5 |  |  | 1434.5 |  |  | 1553.5 |  |  | 1621.5 |  |  | 1483.5 |  |  | 1690 |  |  | 1468.5 |  |  | 1485 |  |  | 1518.5 |  |  | 1731.5 |  |  | 1559.5 |  |  | 1589 |  |  | 1558.5 |  |  | 1471.5 |  |  | 1462 |  |  | 1603.5 |  |  | 1509.5 |  |  | 1614.5 |  |  | 1593.5 |  |  | 1483.5 |  |  | 1525.5 |  |  | 1521 |  |  | 1465.5 |  |  | 1446.5 |  |  | 1581.5 |  |  | 1656.5 |  |  | 1487 |  |  | 1492.5 |  |  | 1658.5 |  |  | 1500 |  |  | 1590.5 |  |  | 1576.5 |  |  | 1510 |  |  | 1566.5 |  |  | 1622.5 |  |  | 1544.5 |  |  | 1487 |  |  | 1390.5 |  |  | 1520.5 |  |  | 1536 |  |  | 1525.5 |  |  | 1623.5 |  |  | 1576.5 |  |  | 1378.5 |  |  | 1623.5 |  |  | 1672.5 |  |  | 1459.5 |  |  | 1537 |  |  | 1481 |  |  | 1400.5 |  |  | 1543.5 |  |  | 1478.5 |  |  | 1523 |  |  | 1627.5 |  |  | 1509.5 |  |  | 1525.5 |  |  | 1388.5 |  |  | 1515.5 |  |  | 1500.5 |  |  | 1444.5 |  |  | 1535.5 |  |  | 1396.5 |  |  | 1574 |  |  | 1499.5 |  |  | 1478.5 |  |  | 1517.5 |  |  | 1649.5 |  |  | 1562.5 |  |  | 1546.5 |  |  | 1535.5 |  |  | 1584.5 |  |  | 1468.5 |  |  | 1610.5 |  |  | 1546.5 |  |  | 1540.5 |  |  | 1612.5 |  |  | 1637 |  |  | 1511.5 |  |  | 1587.5 |  |  | 1512 |  |  | 1606.5 |  |  | 1582.5 |  |  | 1633 |  |  | 1533.5 |  |  | 1655.5 |  |  | 1658.5 |  |  | 1647 |  |  | 1564.5 |  |  | 1616.5 |  |  | 1537.5 |  |  | 1405.5 |  |  | 1519.5 |  |  | 1396 |  |  | 1532.5 |  |  | 1567 |  |  | 1544 |  |  | 1655.5 |  |  | 1578.5 |  |  | 1483.5 |  |  | 1429.5 |  |  | 1560.5 |  |  | 1549.5 |  |  | 1529 |  |  | 1533.5 |  |  | 1562 |  |  | 1472.5 |  |  | 1557 |  |  | 1544 |  |  | 1631 |  |  | 1570.5 |  |  | 1507 |  |  | 1619.5 |  |  | 1600.5 |  |  | 1575.5 |  |  | 1689.5 |  |  | 1576.5 |  |  | 1574 |  |  | 1563.5 |  |  | 1594.5 |  |  | 1719.5 |  |  | 1578 |  |  | 1532.5 |  |  | 1447.5 |  |  | 1584.5 |  |  | 1628.5 |  |  | 1526 |  |  | 1568 |  |  | 1530 |  |  | 1556.5 |  |  | 1582 |  |  | 1616 |  |  | 1618.5 |  |  | 1500.5 |  |  | 1437.5 |  |  | 1575.5 |  |  | 1586.5 |  |  | 1657.5 |  |  | 1656.5 |  |  | 1550.5 |  |  | 1436.5 |  |  | 1432 |  |  | 1536.5 |  |  | 1513 |  |  | 1604.5 |  |  | 1607.5 |  |  | 1572.5 |  |  | 1642.5 |  |  | 1570 |  |  | 1528.5 |  |  | 1502 |  |  | 1478.5 |  |  | 1588.5 |  |  | 1450 |  |  | 1586 |  |  | 1527.5 |  |  | 1553 |  |  | 1616.5 |  |  | 1417.5 |  |  | 1500.5 |  |  | 1526.5 |  |  | 1520.5 |  |  | 1601.5 |  |  | 1445.5 |  |  | 1419 |  |  | 1585.5 |  |  | 1568.5 |  |  | 1475.5 |  |  | 1525.5 |  |  | 1449.5 |  |  | 1471.5 |  |  | 1585.5 |  |  | 1557.5 |  |  | 1625.5 |  |  | 1539.5 |  |  | 1464.5 |  |  | 1485.5 |  |  | 1603 |  |  | 1382.5 |  |  | 1471.5 |  |  | 1577 |  |  | 1443.5 |  |  | 1430.5 |  |  | 1484.5 |  |  | 1522.5 |  |  | 1627 |  |  | 1702.5 |  |  | 1549.5 |  |  | 1469.5 |  |  | 1542.5 |  |  | 1527 |  |  | 1515.5 |  |  | 1584.5 |  |  | 1630.5 |  |  | 1614.5 |  |  | 1533.5 |  |  | 1423.5 |  |  | 1652.5 |  |  | 1669.5 |  |  | 1532.5 |  |  | 1525.5 |  |  | 1649.5 |  |  | 1539 |  |  | 1531.5 |  |  | 1561.5 |  |  | 1596.5 |  |  | 1567.5 |  |  | 1484.5 |  |  | 1511.5 |  |  | 1573 |  |  | 1501.5 |  |  | 1500 |  |  | 1474.5 |  |  | 1588.5 |  |  | 1550.5 |  |  | 1504 |  |  | 1511 |  |  | 1495.5 |  |  | 1592.5 |  |  | 1378.5 |  |  | 1622.5 |  |  | 1499.5 |  |  | 1512.5 |  |  | 1478.5 |  |  | 1528.5 |  |  | 1524.5 |  |  | 1613.5 |  |  | 1493.5 |  |  | 1544.5 |  |  | 1512.5 |  |  | 1615.5 |  |  | 1604.5 |  |  | 1547.5 |  |  | 1509.5 |  |  | 1563.5 |  |  | 1484.5 |  |  | 1505.5 |  |  | 1551.5 |  |  | 1612.5 |  |  | 1551 |  |  | 1607.5 |  |  | 1553.5 |  |  | 1542.5 |  |  | 1545 |  |  | 1568.5 |  |  | 1552.5 |  |  | 1563.5 |  |  | 1547.5 |  |  | 1592 |  |  | 1389.5 |  |  | 1423.5 |  |  | 1429 |  |  | 1523 |  |  | 1553 |  |  | 1482.5 |  |  | 1537.5 |  |  | 1566.5 |  |  | 1694.5 |  |  | 1569 |  |  | 1537.5 |  |  | 1598.5 |  |  | 1423 |  |  | 1487 |  |  | 1580.5 |  |  | 1522.5 |  |  | 1560 |  |  | 1512.5 |  |  | 1610 |  |  | 1497.5 |  |  | 1458.5 |  |  | 1609 |  |  | 1605.5 |  |  | 1500.5 |  |  | 1419.5 |  |  | 1600 |  |  | 1525.5 |  |  | 1502.5 |  |  | 1447.5 |  |  | 1510.5 |  |  | 1534.5 |  |  | 1667.5 |  |  | 1480.5 |  |  | 1515.5 |  |  | 1550.5 |  |  | 1511.5 |  |  | 1586 |  |  | 1551.5 |  |  | 1559.5 |  |  | 1569.5 |  |  | 1584.5 |  |  | 1518.5 |  |  | 1625.5 |  |  | 1626.5 |  |  | 1554.5 |  |  | 1623 |  |  | 1525.5 |  |  | 1506 |  |  | 1589.5 |  |  | 1670.5 |  |  | 1679.5 |  |  | 1461.5 |  |  | 1537.5 |  |  | 1475.5 |  |  | 1390.5 |  |  | 1632.5 |  |  | 1626 |  |  | 1500.5 |  |  | 1522 |  |  | 1458.5 |  |  | 1388.5 |  |  | 1573.5 |  |  | 1576 |  |  | 1540.5 |  |  | 1620.5 |  |  | 1413 |  |  | 1488.5 |  |  | 1498 |  |  | 1520.5 |  |  | 1487.5 |  |  | 1458.5 |  |  | 1528 |  |  | 1568.5 |  |  | 1656.5 |  |  | 1487 |  |  | 1625.5 |  |  | 1414.5 |  |  | 1609 |  |  | 1575.5 |  |  | 1681.5 |  |  | 1591.5 |  |  | 1608.5 |  |  | 1419.5 |  |  | 1612.5 |  |  | 1494.5 |  |  | 1526.5 |  |  | 1422.5 |  |  | 1566.5 |  |  | 1660.5 |  |  | 1552 |  |  | 1598 |  |  | 1588.5 |  |  | 1578.5 |  |  | 1606
54 |  | 1551.5 |  |  | 1689.5 |  |  | 1562 |  |  | 1551.5 |  |  | 1691.5 |  |  | 1599.5 |  |  | 1669.5 |  |  | 1603.5 |  |  | 1576.5 |  |  | 1593.5 |  |  | 1505 |  |  | 1640.5 |  |  | 1640.5 |  |  | 1501.5 |  |  | 1491 |  |  | 1597.5 |  |  | 1703.5 |  |  | 1596.5 |  |  | 1737.5 |  |  | 1497.5 |  |  | 1553.5 |  |  | 1563.5 |  |  | 1591.5 |  |  | 1512.5 |  |  | 1452 |  |  | 1635.5 |  |  | 1536.5 |  |  | 1617.5 |  |  | 1641.5 |  |  | 1489 |  |  | 1560 |  |  | 1531.5 |  |  | 1505.5 |  |  | 1631.5 |  |  | 1442.5 |  |  | 1603 |  |  | 1529.5 |  |  | 1599 |  |  | 1582.5 |  |  | 1609.5 |  |  | 1520.5 |  |  | 1635.5 |  |  | 1486.5 |  |  | 1539 |  |  | 1764.5 |  |  | 1656 |  |  | 1555.5 |  |  | 1671.5 |  |  | 1622.5 |  |  | 1530.5 |  |  | 1519.5 |  |  | 1557.5 |  |  | 1574.5 |  |  | 1548.5 |  |  | 1636.5 |  |  | 1585.5 |  |  | 1471.5 |  |  | 1570 |  |  | 1615.5 |  |  | 1557.5 |  |  | 1542 |  |  | 1521.5 |  |  | 1625.5 |  |  | 1558.5 |  |  | 1473.5 |  |  | 1617 |  |  | 1611.5 |  |  | 1510 |  |  | 1504.5 |  |  | 1595.5 |  |  | 1582 |  |  | 1562.5 |  |  | 1563.5 |  |  | 1682.5 |  |  | 1671 |  |  | 1607 |  |  | 1503.5 |  |  | 1532.5 |  |  | 1443.5 |  |  | 1555.5 |  |  | 1542 |  |  | 1573.5 |  |  | 1596.5 |  |  | 1618.5 |  |  | 1640.5 |  |  | 1583.5 |  |  | 1611.5 |  |  | 1518.5 |  |  | 1527.5 |  |  | 1649.5 |  |  | 1620.5 |  |  | 1625 |  |  | 1481.5 |  |  | 1507 |  |  | 1537 |  |  | 1503 |  |  | 1648.5 |  |  | 1648.5 |  |  | 1503.5 |  |  | 1593.5 |  |  | 1600.5 |  |  | 1567 |  |  | 1549 |  |  | 1550.5 |  |  | 1592.5 |  |  | 1543.5 |  |  | 1644.5 |  |  | 1669.5 |  |  | 1634.5 |  |  | 1612.5 |  |  | 1683.5 |  |  | 1645.5 |  |  | 1599.5 |  |  | 1568.5 |  |  | 1555.5 |  |  | 1615.5 |  |  | 1643.5 |  |  | 1447.5 |  |  | 1636.5 |  |  | 1571.5 |  |  | 1613.5 |  |  | 1592.5 |  |  | 1519.5 |  |  | 1580.5 |  |  | 1581.5 |  |  | 1581 |  |  | 1505.5 |  |  | 1551.5 |  |  | 1536.5 |  |  | 1530.5 |  |  | 1697.5 |  |  | 1619 |  |  | 1512.5 |  |  | 1658.5 |  |  | 1488.5 |  |  | 1571.5 |  |  | 1618 |  |  | 1552.5 |  |  | 1647.5 |  |  | 1565 |  |  | 1587.5 |  |  | 1566 |  |  | 1604 |  |  | 1667.5 |  |  | 1586 |  |  | 1650.5 |  |  | 1548.5 |  |  | 1645.5 |  |  | 1513.5 |  |  | 1645.5 |  |  | 1606.5 |  |  | 1597.5 |  |  | 1623.5 |  |  | 1717.5 |  |  | 1618.5 |  |  | 1658 |  |  | 1565.5 |  |  | 1479 |  |  | 1538.5 |  |  | 1612.5 |  |  | 1593 |  |  | 1559.5 |  |  | 1585.5 |  |  | 1522.5 |  |  | 1538 |  |  | 1593.5 |  |  | 1468.5 |  |  | 1514.5 |  |  | 1677.5 |  |  | 1497.5 |  |  | 1535.5 |  |  | 1571 |  |  | 1547.5 |  |  | 1609.5 |  |  | 1555.5 |  |  | 1536.5 |  |  | 1603.5 |  |  | 1581.5 |  |  | 1479.5 |  |  | 1684 |  |  | 1632.5 |  |  | 1607.5 |  |  | 1656.5 |  |  | 1616.5 |  |  | 1507.5 |  |  | 1683.5 |  |  | 1679.5 |  |  | 1603.5 |  |  | 1609.5 |  |  | 1510.5 |  |  | 1546.5 |  |  | 1505.5 |  |  | 1385.5 |  |  | 1510 |  |  | 1525.5 |  |  | 1599.5 |  |  | 1554.5 |  |  | 1658.5 |  |  | 1618.5 |  |  | 1565.5 |  |  | 1637.5 |  |  | 1551.5 |  |  | 1633.5 |  |  | 1524.5 |  |  | 1547.5 |  |  | 1665.5 |  |  | 1579.5 |  |  | 1540.5 |  |  | 1570.5 |  |  | 1609.5 |  |  | 1627 |  |  | 1603.5 |  |  | 1558.5 |  |  | 1449 |  |  | 1703.5 |  |  | 1619 |  |  | 1543.5 |  |  | 1637.5 |  |  | 1693.5 |  |  | 1675.5 |  |  | 1469.5 |  |  | 1543.5 |  |  | 1537.5 |  |  | 1431.5 |  |  | 1516 |  |  | 1487.5 |  |  | 1453.5 |  |  | 1664.5 |  |  | 1515.5 |  |  | 1621 |  |  | 1496.5 |  |  | 1589.5 |  |  | 1618.5 |  |  | 1660.5 |  |  | 1651.5 |  |  | 1490.5 |  |  | 1514.5 |  |  | 1635.5 |  |  | 1600 |  |  | 1575 |  |  | 1521.5 |  |  | 1593.5 |  |  | 1548.5 |  |  | 1580 |  |  | 1640.5 |  |  | 1592.5 |  |  | 1517.5 |  |  | 1556 |  |  | 1565.5 |  |  | 1647.5 |  |  | 1554.5 |  |  | 1582.5 |  |  | 1606.5 |  |  | 1598.5 |  |  | 1593.5 |  |  | 1550.5 |  |  | 1658.5 |  |  | 1420 |  |  | 1494.5 |  |  | 1585.5 |  |  | 1564.5 |  |  | 1505.5 |  |  | 1549.5 |  |  | 1667 |  |  | 1523.5 |  |  | 1620.5 |  |  | 1581 |  |  | 1722.5 |  |  | 1593.5 |  |  | 1713 |  |  | 1591.5 |  |  | 1598.5 |  |  | 1693.5 |  |  | 1481.5 |  |  | 1593 |  |  | 1597 |  |  | 1621.5 |  |  | 1510.5 |  |  | 1609.5 |  |  | 1568.5 |  |  | 1664.5 |  |  | 1527.5 |  |  | 1572 |  |  | 1586.5 |  |  | 1576.5 |  |  | 1578 |  |  | 1505.5 |  |  | 1439.5 |  |  | 1585 |  |  | 1540.5 |  |  | 1511.5 |  |  | 1580.5 |  |  | 1572 |  |  | 1602.5 |  |  | 1529 |  |  | 1601.5 |  |  | 1481.5 |  |  | 1579.5 |  |  | 1561 |  |  | 1534.5 |  |  | 1664.5 |  |  | 1536.5 |  |  | 1557 |  |  | 1456.5 |  |  | 1483.5 |  |  | 1714.5 |  |  | 1690.5 |  |  | 1551.5 |  |  | 1544 |  |  | 1512.5 |  |  | 1711.5 |  |  | 1668.5 |  |  | 1525 |  |  | 1563 |  |  | 1699.5 |  |  | 1553.5 |  |  | 1492.5 |  |  | 1556.5 |  |  | 1577.5 |  |  | 1593.5 |  |  | 1599.5 |  |  | 1608.5 |  |  | 1516.5 |  |  | 1555.5 |  |  | 1568 |  |  | 1589.5 |  |  | 1685.5 |  |  | 1718.5 |  |  | 1660.5 |  |  | 1610 |  |  | 1610.5 |  |  | 1611.5 |  |  | 1606.5 |  |  | 1393.5 |  |  | 1640.5 |  |  | 1559 |  |  | 1550 |  |  | 1508 |  |  | 1621 |  |  | 1507.5 |  |  | 1575 |  |  | 1562.5 |  |  | 1538 |  |  | 1587.5 |  |  | 1687.5 |  |  | 1577.5 |  |  | 1553.5 |  |  | 1515.5 |  |  | 1559 |  |  | 1554.5 |  |  | 1643.5 |  |  | 1493.5 |  |  | 1653 |  |  | 1597.5 |  |  | 1518.5 |  |  | 1555.5 |  |  | 1629 |  |  | 1569.5 |  |  | 1473.5 |  |  | 1616.5 |  |  | 1505.5 |  |  | 1563.5 |  |  | 1521.5 |  |  | 1687.5 |  |  | 1526.5 |  |  | 1650.5 |  |  | 1433.5 |  |  | 1459 |  |  | 1574.5 |  |  | 1587.5 |  |  | 1526.5 |  |  | 1576.5 |  |  | 1687.5 |  |  | 1533 |  |  | 1588.5 |  |  | 1612 |  |  | 1545 |  |  | 1555.5 |  |  | 1694.5 |  |  | 1519.5 |  |  | 1503 |  |  | 1621.5 |  |  | 1624.5 |  |  | 1626.5 |  |  | 1451 |  |  | 1554.5 |  |  | 1398.5 |  |  | 1635.5 |  |  | 1534.5 |  |  | 1516.5 |  |  | 1526 |  |  | 1541.5 |  |  | 1573 |  |  | 1552.5 |  |  | 1527.5 |  |  | 1573.5 |  |  | 1636 |  |  | 1461.5 |  |  | 1611 |  |  | 1586 |  |  | 1560.5 |  |  | 1539.5 |  |  | 1553.5 |  |  | 1666.5 |  |  | 1623 |  |  | 1597.5 |  |  | 1548.5 |  |  | 1451.5 |  |  | 1548 |  |  | 1658.5 |  |  | 1529.5 |  |  | 1455.5 |  |  | 1538.5 |  |  | 1648 |  |  | 1425.5 |  |  | 1565.5 |  |  | 1641.5 |  |  | 1569.5 |  |  | 1518.5 |  |  | 1580.5 |  |  | 1655 |  |  | 1569.5 |  |  | 1470.5 |  |  | 1570 |  |  | 1517.5 |  |  | 1483.5 |  |  | 1549.5 |  |  | 1556 |  |  | 1615.5 |  |  | 1550.5 |  |  | 1569.5 |  |  | 1569.5 |  |  | 1675.5 |  |  | 1634 |  |  | 1607 |  |  | 1500.5 |  |  | 1586.5 |  |  | 1613.5 |  |  | 1484.5 |  |  | 1481 |  |  | 1632 |  |  | 1484 |  |  | 1607.5 |  |  | 1532 |  |  | 1585.5 |  |  | 1654.5 |  |  | 1573 |  |  | 1518.5 |  |  | 1636.5 |  |  | 1562.5 |  |  | 1724.5 |  |  | 1425.5 |  |  | 1553 |  |  | 1608 |  |  | 1440.5 |  |  | 1614.5 |  |  | 1537 |  |  | 1481.5 |  |  | 1605.5 |  |  | 1557 |  |  | 1692.5 |  |  | 1641.5 |  |  | 1485 |  |  | 1604.5 |  |  | 1563.5 |  |  | 1569 |  |  | 1621.5 |  |  | 1501 |  |  | 1727.5 |  |  | 1727 |  |  | 1521.5 |  |  | 1566.5 |  |  | 1646.5 |  |  | 1553.5 |  |  | 1583.5 |  |  | 1529.5 |  |  | 1618 |  |  | 1547.5 |  |  | 1524.5 |  |  | 1466.5 |  |  | 1612.5 |  |  | 1569.5 |  |  | 1555 |  |  | 1516.5 |  |  | 1607 |  |  | 1592.5 |  |  | 1508.5 |  |  | 1602.5 |  |  | 1532.5 |  |  | 1544.5 |  |  | 1605.5 |  |  | 1518.5 |  |  | 1685.5 |  |  | 1514.5 |  |  | 1598 |  |  | 1605.5 |  |  | 1487 |  |  | 1580 |  |  | 1588.5 |  |  | 1490 |  |  | 1501.5 |  |  | 1561.5 |  |  | 1623.5 |  |  | 1535.5 |  |  | 1584.5 |  |  | 1717.5 |  |  | 1643.5 |  |  | 1508 |  |  | 1648 |  |  | 1485.5 |  |  | 1442.5 |  |  | 1599 |  |  | 1532.5 |  |  | 1597.5 |  |  | 1520.5 |  |  | 1510.5 |  |  | 1478.5 |  |  | 1481 |  |  | 1581.5 |  |  | 1570.5 |  |  | 1495.5 |  |  | 1501 |  |  | 1640.5 |  |  | 1610.5 |  |  | 1627.5 |  |  | 1709.5 |  |  | 1628.5 |  |  | 1536.5 |  |  | 1695.5 |  |  | 1341.5 |  |  | 1597.5 |  |  | 1474 |  |  | 1644.5 |  |  | 1558.5 |  |  | 1649.5 |  |  | 1466.5 |  |  | 1496.5 |  |  | 1524.5 |  |  | 1509.5 |  |  | 1393 |  |  | 1483.5 |  |  | 1604.5 |  |  | 1660.5 |  |  | 1508 |  |  | 1560.5 |  |  | 1495 |  |  | 1494.5 |  |  | 1595.5 |  |  | 1511.5 |  |  | 1558 |  |  | 1494.5 |  |  | 1598 |  |  | 1601 |  |  | 1620.5 |  |  | 1536 |  |  | 1638 |  |  | 1644.5 |  |  | 1604.5 |  |  | 1469.5 |  |  | 1610 |  |  | 1636.5 |  |  | 1522.5 |  |  | 1425.5 |  |  | 1622.5 |  |  | 1525.5 |  |  | 1534.5 |  |  | 1524.5 |  |  | 1575.5 |  |  | 1509 |  |  | 1704.5 |  |  | 1508 |  |  | 1525.5 |  |  | 1463.5 |  |  | 1662.5 |  |  | 1587 |  |  | 1627 |  |  | 1684 |  |  | 1579.5 |  |  | 1540 |  |  | 1649.5 |  |  | 1669.5 |  |  | 1525.5 |  |  | 1579.5 |  |  | 1526.5 |  |  | 1633.5 |  |  | 1600.5 |  |  | 1569.5 |  |  | 1620 |  |  | 1474.5 |  |  | 1464.5 |  |  | 1610.5 |  |  | 1500.5 |  |  | 1458 |  |  | 1516.5 |  |  | 1583 |  |  | 1573.5 |  |  | 1580.5 |  |  | 1526.5 |  |  | 1516.5 |  |  | 1466 |  |  | 1498.5 |  |  | 1410 |  |  | 1560.5 |  |  | 1645.5 |  |  | 1697.5 |  |  | 1660.5 |  |  | 1552.5 |  |  | 1544.5 |  |  | 1445.5 |  |  | 1598.5 |  |  | 1568.5 |  |  | 1549 |  |  | 1590.5 |  |  | 1543.5 |  |  | 1529.5 |  |  | 1580.5 |  |  | 1569.5 |  |  | 1467 |  |  | 1521 |  |  | 1565.5 |  |  | 1479 |  |  | 1689.5 |  |  | 1542.5 |  |  | 1635.5 |  |  | 1686.5 |  |  | 1519.5 |  |  | 1598.5 |  |  | 1569.5 |  |  | 1576.5 |  |  | 1570 |  |  | 1579.5 |  |  | 1711.5 |  |  | 1665.5 |  |  | 1445 |  |  | 1591.5 |  |  | 1540.5 |  |  | 1606 |  |  | 1478 |  |  | 1594.5 |  |  | 1498 |  |  | 1424 |  |  | 1478.5 |  |  | 1557 |  |  | 1699.5 |  |  | 1640.5 |  |  | 1607.5 |  |  | 1569.5 |  |  | 1471.5 |  |  | 1573.5 |  |  | 1436.5 |  |  | 1567.5 |  |  | 1573.5 |  |  | 1545.5 |  |  | 1484 |  |  | 1471 |  |  | 1640.5 |  |  | 1535.5 |  |  | 1548.5 |  |  | 1615.5 |  |  | 1455.5 |  |  | 1577.5 |  |  | 1668.5 |  |  | 1507.5 |  |  | 1716 |  |  | 1507.5 |  |  | 1511 |  |  | 1542.5 |  |  | 1760.5 |  |  | 1583.5 |  |  | 1613 |  |  | 1573.5 |  |  | 1500.5 |  |  | 1486 |  |  | 1618.5 |  |  | 1548.5 |  |  | 1653.5 |  |  | 1622.5 |  |  | 1530.5 |  |  | 1564.5 |  |  | 1536 |  |  | 1504.5 |  |  | 1472.5 |  |  | 1628.5 |  |  | 1671.5 |  |  | 1513 |  |  | 1531.5 |  |  | 1679.5 |  |  | 1521 |  |  | 1605.5 |  |  | 1615.5 |  |  | 1557 |  |  | 1595.5 |  |  | 1669.5 |  |  | 1573.5 |  |  | 1526 |  |  | 1419.5 |  |  | 1567.5 |  |  | 1562 |  |  | 1549.5 |  |  | 1662.5 |  |  | 1600.5 |  |  | 1417.5 |  |  | 1644.5 |  |  | 1701.5 |  |  | 1480.5 |  |  | 1584 |  |  | 1502 |  |  | 1447.5 |  |  | 1572.5 |  |  | 1499.5 |  |  | 1549 |  |  | 1674.5 |  |  | 1538.5 |  |  | 1546.5 |  |  | 1427.5 |  |  | 1539.5 |  |  | 1526.5 |  |  | 1483.5 |  |  | 1564.5 |  |  | 1435.5 |  |  | 1613 |  |  | 1538.5 |  |  | 1493.5 |  |  | 1564.5 |  |  | 1664.5 |  |  | 1583.5 |  |  | 1585.5 |  |  | 1574.5 |  |  | 1623.5 |  |  | 1483.5 |  |  | 1649.5 |  |  | 1567.5 |  |  | 1561.5 |  |  | 1636.5 |  |  | 1658 |  |  | 1550.5 |  |  | 1608.5 |  |  | 1533 |  |  | 1645.5 |  |  | 1597.5 |  |  | 1654 |  |  | 1580.5 |  |  | 1676.5 |  |  | 1673.5 |  |  | 1676 |  |  | 1579.5 |  |  | 1642.5 |  |  | 1576.5 |  |  | 1420.5 |  |  | 1545.5 |  |  | 1435 |  |  | 1547.5 |  |  | 1591 |  |  | 1591 |  |  | 1670.5 |  |  | 1602.5 |  |  | 1509.5 |  |  | 1444.5 |  |  | 1586.5 |  |  | 1578.5 |  |  | 1555 |  |  | 1562.5 |  |  | 1588 |  |  | 1511.5 |  |  | 1586 |  |  | 1565 |  |  | 1660 |  |  | 1585.5 |  |  | 1536 |  |  | 1648.5 |  |  | 1647.5 |  |  | 1596.5 |  |  | 1728.5 |  |  | 1597.5 |  |  | 1613 |  |  | 1602.5 |  |  | 1633.5 |  |  | 1766.5 |  |  | 1602 |  |  | 1561.5 |  |  | 1486.5 |  |  | 1605.5 |  |  | 1649.5 |  |  | 1552 |  |  | 1594 |  |  | 1569 |  |  | 1577.5 |  |  | 1608 |  |  | 1655 |  |  | 1633.5 |  |  | 1539.5 |  |  | 1461.5 |  |  | 1622.5 |  |  | 1612.5 |  |  | 1678.5 |  |  | 1680.5 |  |  | 1576.5 |  |  | 1475.5 |  |  | 1479 |  |  | 1560.5 |  |  | 1552 |  |  | 1619.5 |  |  | 1636.5 |  |  | 1587.5 |  |  | 1668.5 |  |  | 1609 |  |  | 1575.5 |  |  | 1549 |  |  | 1493.5 |  |  | 1603.5 |  |  | 1497 |  |  | 1625 |  |  | 1574.5 |  |  | 1582 |  |  | 1640.5 |  |  | 1456.5 |  |  | 1539.5 |  |  | 1541.5 |  |  | 1546.5 |  |  | 1627.5 |  |  | 1469.5 |  |  | 1458 |  |  | 1624.5 |  |  | 1583.5 |  |  | 1504.5 |  |  | 1572.5 |  |  | 1470.5 |  |  | 1510.5 |  |  | 1632.5 |  |  | 1583.5 |  |  | 1664.5 |  |  | 1586.5 |  |  | 1503.5 |  |  | 1500.5 |  |  | 1642 |  |  | 1406.5 |  |  | 1510.5 |  |  | 1601 |  |  | 1472.5 |  |  | 1469.5 |  |  | 1508.5 |  |  | 1546.5 |  |  | 1653 |  |  | 1726.5 |  |  | 1596.5 |  |  | 1498.5 |  |  | 1571.5 |  |  | 1542 |  |  | 1541.5 |  |  | 1605.5 |  |  | 1651.5 |  |  | 1661.5 |  |  | 1548.5 |  |  | 1462.5 |  |  | 1678.5 |  |  | 1695.5 |  |  | 1561.5 |  |  | 1564.5 |  |  | 1673.5 |  |  | 1554 |  |  | 1578.5 |  |  | 1587.5 |  |  | 1622.5 |  |  | 1606.5 |  |  | 1505.5 |  |  | 1532.5 |  |  | 1588 |  |  | 1530.5 |  |  | 1515 |  |  | 1500.5 |  |  | 1635.5 |  |  | 1579.5 |  |  | 1530 |  |  | 1535 |  |  | 1510.5 |  |  | 1631.5 |  |  | 1399.5 |  |  | 1646.5 |  |  | 1514.5 |  |  | 1538.5 |  |  | 1504.5 |  |  | 1549.5 |  |  | 1563.5 |  |  | 1639.5 |  |  | 1522.5 |  |  | 1583.5 |  |  | 1527.5 |  |  | 1636.5 |  |  | 1619.5 |  |  | 1573.5 |  |  | 1535.5 |  |  | 1592.5 |  |  | 1505.5 |  |  | 1531.5 |  |  | 1572.5 |  |  | 1638.5 |  |  | 1598 |  |  | 1636.5 |  |  | 1568.5 |  |  | 1563.5 |  |  | 1560 |  |  | 1615.5 |  |  | 1567.5 |  |  | 1589.5 |  |  | 1562.5 |  |  | 1616 |  |  | 1428.5 |  |  | 1444.5 |  |  | 1458 |  |  | 1552 |  |  | 1600 |  |  | 1503.5 |  |  | 1558.5 |  |  | 1590.5 |  |  | 1718.5 |  |  | 1584 |  |  | 1566.5 |  |  | 1637.5 |  |  | 1470 |  |  | 1516 |  |  | 1601.5 |  |  | 1548.5 |  |  | 1575 |  |  | 1538.5 |  |  | 1649 |  |  | 1512.5 |  |  | 1479.5 |  |  | 1633 |  |  | 1644.5 |  |  | 1539.5 |  |  | 1445.5 |  |  | 1639 |  |  | 1549.5 |  |  | 1523.5 |  |  | 1486.5 |  |  | 1549.5 |  |  | 1555.5 |  |  | 1714.5 |  |  | 1509.5 |  |  | 1539.5 |  |  | 1579.5 |  |  | 1550.5 |  |  | 1615 |  |  | 1575.5 |  |  | 1580.5 |  |  | 1608.5 |  |  | 1623.5 |  |  | 1544.5 |  |  | 1640.5 |  |  | 1650.5 |  |  | 1593.5 |  |  | 1670 |  |  | 1549.5 |  |  | 1527 |  |  | 1610.5 |  |  | 1699.5 |  |  | 1700.5 |  |  | 1485.5 |  |  | 1561.5 |  |  | 1501.5 |  |  | 1429.5 |  |  | 1671.5 |  |  | 1641 |  |  | 1526.5 |  |  | 1548 |  |  | 1497.5 |  |  | 1427.5 |  |  | 1588.5 |  |  | 1623 |  |  | 1566.5 |  |  | 1635.5 |  |  | 1437 |  |  | 1527.5 |  |  | 1537 |  |  | 1567.5 |  |  | 1526.5 |  |  | 1487.5 |  |  | 1554 |  |  | 1597.5 |  |  | 1703.5 |  |  | 1534 |  |  | 1646.5 |  |  | 1453.5 |  |  | 1633 |  |  | 1590.5 |  |  | 1720.5 |  |  | 1638.5 |  |  | 1655.5 |  |  | 1440.5 |  |  | 1641.5 |  |  | 1533.5 |  |  | 1541.5 |  |  | 1446.5 |  |  | 1581.5 |  |  | 1707.5 |  |  | 1599 |  |  | 1624 |  |  | 1614.5 |  |  | 1604.5 |  |  | 1627
55 |  | 1572.5 |  |  | 1715.5 |  |  | 1583 |  |  | 1572.5 |  |  | 1715.5 |  |  | 1628.5 |  |  | 1690.5 |  |  | 1624.5 |  |  | 1623.5 |  |  | 1622.5 |  |  | 1526 |  |  | 1669.5 |  |  | 1679.5 |  |  | 1525.5 |  |  | 1506 |  |  | 1644.5 |  |  | 1732.5 |  |  | 1635.5 |  |  | 1766.5 |  |  | 1536.5 |  |  | 1592.5 |  |  | 1602.5 |  |  | 1630.5 |  |  | 1538.5 |  |  | 1473 |  |  | 1650.5 |  |  | 1560.5 |  |  | 1638.5 |  |  | 1667.5 |  |  | 1518 |  |  | 1599 |  |  | 1578.5 |  |  | 1526.5 |  |  | 1657.5 |  |  | 1481.5 |  |  | 1629 |  |  | 1544.5 |  |  | 1646 |  |  | 1611.5 |  |  | 1635.5 |  |  | 1559.5 |  |  | 1664.5 |  |  | 1525.5 |  |  | 1565 |  |  | 1785.5 |  |  | 1680 |  |  | 1602.5 |  |  | 1718.5 |  |  | 1661.5 |  |  | 1577.5 |  |  | 1558.5 |  |  | 1596.5 |  |  | 1600.5 |  |  | 1563.5 |  |  | 1657.5 |  |  | 1611.5 |  |  | 1495.5 |  |  | 1609 |  |  | 1662.5 |  |  | 1596.5 |  |  | 1568 |  |  | 1568.5 |  |  | 1664.5 |  |  | 1587.5 |  |  | 1502.5 |  |  | 1646 |  |  | 1650.5 |  |  | 1539 |  |  | 1530.5 |  |  | 1619.5 |  |  | 1597 |  |  | 1601.5 |  |  | 1589.5 |  |  | 1721.5 |  |  | 1700 |  |  | 1633 |  |  | 1527.5 |  |  | 1558.5 |  |  | 1467.5 |  |  | 1594.5 |  |  | 1589 |  |  | 1612.5 |  |  | 1643.5 |  |  | 1647.5 |  |  | 1666.5 |  |  | 1630.5 |  |  | 1635.5 |  |  | 1557.5 |  |  | 1556.5 |  |  | 1664.5 |  |  | 1644.5 |  |  | 1654 |  |  | 1496.5 |  |  | 1522 |  |  | 1561 |  |  | 1542 |  |  | 1672.5 |  |  | 1677.5 |  |  | 1518.5 |  |  | 1640.5 |  |  | 1624.5 |  |  | 1582 |  |  | 1588 |  |  | 1571.5 |  |  | 1607.5 |  |  | 1582.5 |  |  | 1683.5 |  |  | 1684.5 |  |  | 1681.5 |  |  | 1641.5 |  |  | 1722.5 |  |  | 1684.5 |  |  | 1625.5 |  |  | 1597.5 |  |  | 1581.5 |  |  | 1641.5 |  |  | 1682.5 |  |  | 1462.5 |  |  | 1662.5 |  |  | 1610.5 |  |  | 1634.5 |  |  | 1631.5 |  |  | 1558.5 |  |  | 1601.5 |  |  | 1620.5 |  |  | 1620 |  |  | 1526.5 |  |  | 1577.5 |  |  | 1575.5 |  |  | 1556.5 |  |  | 1726.5 |  |  | 1648 |  |  | 1533.5 |  |  | 1687.5 |  |  | 1517.5 |  |  | 1610.5 |  |  | 1657 |  |  | 1576.5 |  |  | 1673.5 |  |  | 1589 |  |  | 1626.5 |  |  | 1592 |  |  | 1625 |  |  | 1693.5 |  |  | 1633 |  |  | 1665.5 |  |  | 1577.5 |  |  | 1674.5 |  |  | 1552.5 |  |  | 1684.5 |  |  | 1635.5 |  |  | 1618.5 |  |  | 1652.5 |  |  | 1764.5 |  |  | 1633.5 |  |  | 1679 |  |  | 1594.5 |  |  | 1505 |  |  | 1567.5 |  |  | 1651.5 |  |  | 1614 |  |  | 1598.5 |  |  | 1624.5 |  |  | 1561.5 |  |  | 1577 |  |  | 1614.5 |  |  | 1483.5 |  |  | 1538.5 |  |  | 1716.5 |  |  | 1526.5 |  |  | 1564.5 |  |  | 1610 |  |  | 1568.5 |  |  | 1635.5 |  |  | 1581.5 |  |  | 1565.5 |  |  | 1642.5 |  |  | 1610.5 |  |  | 1505.5 |  |  | 1699 |  |  | 1679.5 |  |  | 1646.5 |  |  | 1695.5 |  |  | 1645.5 |  |  | 1531.5 |  |  | 1722.5 |  |  | 1694.5 |  |  | 1618.5 |  |  | 1656.5 |  |  | 1525.5 |  |  | 1570.5 |  |  | 1529.5 |  |  | 1432.5 |  |  | 1549 |  |  | 1549.5 |  |  | 1638.5 |  |  | 1569.5 |  |  | 1682.5 |  |  | 1644.5 |  |  | 1612.5 |  |  | 1676.5 |  |  | 1572.5 |  |  | 1659.5 |  |  | 1539.5 |  |  | 1576.5 |  |  | 1704.5 |  |  | 1600.5 |  |  | 1566.5 |  |  | 1599.5 |  |  | 1638.5 |  |  | 1666 |  |  | 1618.5 |  |  | 1587.5 |  |  | 1478 |  |  | 1729.5 |  |  | 1648 |  |  | 1569.5 |  |  | 1676.5 |  |  | 1714.5 |  |  | 1690.5 |  |  | 1498.5 |  |  | 1567.5 |  |  | 1584.5 |  |  | 1470.5 |  |  | 1555 |  |  | 1511.5 |  |  | 1477.5 |  |  | 1711.5 |  |  | 1530.5 |  |  | 1645 |  |  | 1511.5 |  |  | 1618.5 |  |  | 1657.5 |  |  | 1689.5 |  |  | 1672.5 |  |  | 1516.5 |  |  | 1553.5 |  |  | 1659.5 |  |  | 1626 |  |  | 1604 |  |  | 1547.5 |  |  | 1619.5 |  |  | 1563.5 |  |  | 1619 |  |  | 1679.5 |  |  | 1618.5 |  |  | 1546.5 |  |  | 1595 |  |  | 1612.5 |  |  | 1694.5 |  |  | 1575.5 |  |  | 1597.5 |  |  | 1630.5 |  |  | 1637.5 |  |  | 1640.5 |  |  | 1589.5 |  |  | 1697.5 |  |  | 1446 |  |  | 1509.5 |  |  | 1609.5 |  |  | 1593.5 |  |  | 1534.5 |  |  | 1573.5 |  |  | 1688 |  |  | 1562.5 |  |  | 1646.5 |  |  | 1628 |  |  | 1761.5 |  |  | 1632.5 |  |  | 1752 |  |  | 1615.5 |  |  | 1613.5 |  |  | 1740.5 |  |  | 1528.5 |  |  | 1619 |  |  | 1623 |  |  | 1642.5 |  |  | 1536.5 |  |  | 1635.5 |  |  | 1615.5 |  |  | 1703.5 |  |  | 1556.5 |  |  | 1598 |  |  | 1601.5 |  |  | 1605.5 |  |  | 1602 |  |  | 1531.5 |  |  | 1486.5 |  |  | 1624 |  |  | 1561.5 |  |  | 1526.5 |  |  | 1619.5 |  |  | 1611 |  |  | 1641.5 |  |  | 1568 |  |  | 1625.5 |  |  | 1510.5 |  |  | 1626.5 |  |  | 1582 |  |  | 1558.5 |  |  | 1711.5 |  |  | 1575.5 |  |  | 1578 |  |  | 1480.5 |  |  | 1522.5 |  |  | 1740.5 |  |  | 1716.5 |  |  | 1590.5 |  |  | 1591 |  |  | 1536.5 |  |  | 1726.5 |  |  | 1707.5 |  |  | 1549 |  |  | 1578 |  |  | 1725.5 |  |  | 1568.5 |  |  | 1513.5 |  |  | 1603.5 |  |  | 1616.5 |  |  | 1622.5 |  |  | 1614.5 |  |  | 1629.5 |  |  | 1537.5 |  |  | 1602.5 |  |  | 1589 |  |  | 1628.5 |  |  | 1706.5 |  |  | 1757.5 |  |  | 1686.5 |  |  | 1657 |  |  | 1649.5 |  |  | 1632.5 |  |  | 1621.5 |  |  | 1419.5 |  |  | 1687.5 |  |  | 1574 |  |  | 1574 |  |  | 1537 |  |  | 1660 |  |  | 1522.5 |  |  | 1614 |  |  | 1591.5 |  |  | 1559 |  |  | 1626.5 |  |  | 1713.5 |  |  | 1624.5 |  |  | 1582.5 |  |  | 1536.5 |  |  | 1598 |  |  | 1575.5 |  |  | 1682.5 |  |  | 1519.5 |  |  | 1679 |  |  | 1626.5 |  |  | 1533.5 |  |  | 1594.5 |  |  | 1655 |  |  | 1608.5 |  |  | 1488.5 |  |  | 1642.5 |  |  | 1520.5 |  |  | 1592.5 |  |  | 1542.5 |  |  | 1713.5 |  |  | 1541.5 |  |  | 1697.5 |  |  | 1480.5 |  |  | 1480 |  |  | 1598.5 |  |  | 1613.5 |  |  | 1547.5 |  |  | 1600.5 |  |  | 1734.5 |  |  | 1557 |  |  | 1627.5 |  |  | 1651 |  |  | 1592 |  |  | 1602.5 |  |  | 1720.5 |  |  | 1540.5 |  |  | 1527 |  |  | 1647.5 |  |  | 1639.5 |  |  | 1650.5 |  |  | 1466 |  |  | 1580.5 |  |  | 1437.5 |  |  | 1650.5 |  |  | 1563.5 |  |  | 1537.5 |  |  | 1573 |  |  | 1588.5 |  |  | 1620 |  |  | 1576.5 |  |  | 1542.5 |  |  | 1602.5 |  |  | 1657 |  |  | 1508.5 |  |  | 1632 |  |  | 1625 |  |  | 1586.5 |  |  | 1568.5 |  |  | 1568.5 |  |  | 1681.5 |  |  | 1649 |  |  | 1644.5 |  |  | 1569.5 |  |  | 1466.5 |  |  | 1572 |  |  | 1687.5 |  |  | 1555.5 |  |  | 1494.5 |  |  | 1559.5 |  |  | 1663 |  |  | 1449.5 |  |  | 1594.5 |  |  | 1656.5 |  |  | 1598.5 |  |  | 1565.5 |  |  | 1595.5 |  |  | 1694 |  |  | 1593.5 |  |  | 1509.5 |  |  | 1609 |  |  | 1532.5 |  |  | 1498.5 |  |  | 1564.5 |  |  | 1595 |  |  | 1636.5 |  |  | 1571.5 |  |  | 1590.5 |  |  | 1598.5 |  |  | 1701.5 |  |  | 1649 |  |  | 1631 |  |  | 1547.5 |  |  | 1633.5 |  |  | 1642.5 |  |  | 1510.5 |  |  | 1502 |  |  | 1653 |  |  | 1508 |  |  | 1622.5 |  |  | 1556 |  |  | 1600.5 |  |  | 1675.5 |  |  | 1612 |  |  | 1539.5 |  |  | 1651.5 |  |  | 1601.5 |  |  | 1739.5 |  |  | 1464.5 |  |  | 1592 |  |  | 1637 |  |  | 1469.5 |  |  | 1643.5 |  |  | 1563 |  |  | 1496.5 |  |  | 1644.5 |  |  | 1586 |  |  | 1713.5 |  |  | 1688.5 |  |  | 1509 |  |  | 1643.5 |  |  | 1592.5 |  |  | 1598 |  |  | 1645.5 |  |  | 1548 |  |  | 1766.5 |  |  | 1766 |  |  | 1547.5 |  |  | 1581.5 |  |  | 1667.5 |  |  | 1592.5 |  |  | 1622.5 |  |  | 1558.5 |  |  | 1633 |  |  | 1571.5 |  |  | 1563.5 |  |  | 1505.5 |  |  | 1633.5 |  |  | 1598.5 |  |  | 1602 |  |  | 1555.5 |  |  | 1631 |  |  | 1621.5 |  |  | 1523.5 |  |  | 1641.5 |  |  | 1558.5 |  |  | 1568.5 |  |  | 1626.5 |  |  | 1557.5 |  |  | 1700.5 |  |  | 1540.5 |  |  | 1624 |  |  | 1626.5 |  |  | 1508 |  |  | 1619 |  |  | 1617.5 |  |  | 1514 |  |  | 1530.5 |  |  | 1608.5 |  |  | 1662.5 |  |  | 1564.5 |  |  | 1631.5 |  |  | 1743.5 |  |  | 1658.5 |  |  | 1547 |  |  | 1663 |  |  | 1509.5 |  |  | 1466.5 |  |  | 1614 |  |  | 1571.5 |  |  | 1636.5 |  |  | 1541.5 |  |  | 1539.5 |  |  | 1502.5 |  |  | 1520 |  |  | 1607.5 |  |  | 1609.5 |  |  | 1534.5 |  |  | 1522 |  |  | 1669.5 |  |  | 1636.5 |  |  | 1656.5 |  |  | 1748.5 |  |  | 1652.5 |  |  | 1557.5 |  |  | 1716.5 |  |  | 1365.5 |  |  | 1636.5 |  |  | 1513 |  |  | 1670.5 |  |  | 1587.5 |  |  | 1688.5 |  |  | 1492.5 |  |  | 1535.5 |  |  | 1539.5 |  |  | 1533.5 |  |  | 1417 |  |  | 1498.5 |  |  | 1625.5 |  |  | 1689.5 |  |  | 1532 |  |  | 1589.5 |  |  | 1524 |  |  | 1520.5 |  |  | 1621.5 |  |  | 1550.5 |  |  | 1582 |  |  | 1533.5 |  |  | 1637 |  |  | 1625 |  |  | 1649.5 |  |  | 1583 |  |  | 1662 |  |  | 1683.5 |  |  | 1630.5 |  |  | 1495.5 |  |  | 1636 |  |  | 1675.5 |  |  | 1537.5 |  |  | 1472.5 |  |  | 1648.5 |  |  | 1554.5 |  |  | 1558.5 |  |  | 1539.5 |  |  | 1604.5 |  |  | 1530 |  |  | 1743.5 |  |  | 1537 |  |  | 1554.5 |  |  | 1510.5 |  |  | 1701.5 |  |  | 1611 |  |  | 1651 |  |  | 1705 |  |  | 1603.5 |  |  | 1579 |  |  | 1664.5 |  |  | 1698.5 |  |  | 1572.5 |  |  | 1600.5 |  |  | 1541.5 |  |  | 1654.5 |  |  | 1629.5 |  |  | 1598.5 |  |  | 1641 |  |  | 1500.5 |  |  | 1493.5 |  |  | 1636.5 |  |  | 1547.5 |  |  | 1497 |  |  | 1563.5 |  |  | 1609 |  |  | 1612.5 |  |  | 1606.5 |  |  | 1552.5 |  |  | 1555.5 |  |  | 1492 |  |  | 1537.5 |  |  | 1449 |  |  | 1575.5 |  |  | 1666.5 |  |  | 1744.5 |  |  | 1707.5 |  |  | 1578.5 |  |  | 1570.5 |  |  | 1471.5 |  |  | 1645.5 |  |  | 1589.5 |  |  | 1578 |  |  | 1629.5 |  |  | 1572.5 |  |  | 1576.5 |  |  | 1604.5 |  |  | 1598.5 |  |  | 1493 |  |  | 1560 |  |  | 1589.5 |  |  | 1500 |  |  | 1736.5 |  |  | 1581.5 |  |  | 1674.5 |  |  | 1707.5 |  |  | 1566.5 |  |  | 1627.5 |  |  | 1593.5 |  |  | 1623.5 |  |  | 1596 |  |  | 1603.5 |  |  | 1737.5 |  |  | 1680.5 |  |  | 1492 |  |  | 1606.5 |  |  | 1561.5 |  |  | 1627 |  |  | 1502 |  |  | 1618.5 |  |  | 1545 |  |  | 1448 |  |  | 1499.5 |  |  | 1604 |  |  | 1720.5 |  |  | 1664.5 |  |  | 1628.5 |  |  | 1584.5 |  |  | 1497.5 |  |  | 1597.5 |  |  | 1465.5 |  |  | 1588.5 |  |  | 1620.5 |  |  | 1569.5 |  |  | 1508 |  |  | 1510 |  |  | 1669.5 |  |  | 1574.5 |  |  | 1569.5 |  |  | 1662.5 |  |  | 1502.5 |  |  | 1616.5 |  |  | 1692.5 |  |  | 1546.5 |  |  | 1763 |  |  | 1536.5 |  |  | 1537 |  |  | 1566.5 |  |  | 1784.5 |  |  | 1622.5 |  |  | 1642 |  |  | 1597.5 |  |  | 1521.5 |  |  | 1525 |  |  | 1642.5 |  |  | 1587.5 |  |  | 1679.5 |  |  | 1637.5 |  |  | 1551.5 |  |  | 1593.5 |  |  | 1583 |  |  | 1528.5 |  |  | 1511.5 |  |  | 1654.5 |  |  | 1710.5 |  |  | 1552 |  |  | 1570.5 |  |  | 1708.5 |  |  | 1542 |  |  | 1644.5 |  |  | 1641.5 |  |  | 1583 |  |  | 1642.5 |  |  | 1684.5 |  |  | 1588.5 |  |  | 1552 |  |  | 1466.5 |  |  | 1606.5 |  |  | 1586 |  |  | 1588.5 |  |  | 1688.5 |  |  | 1647.5 |  |  | 1432.5 |  |  | 1691.5 |  |  | 1740.5 |  |  | 1506.5 |  |  | 1631 |  |  | 1528 |  |  | 1476.5 |  |  | 1598.5 |  |  | 1523.5 |  |  | 1578 |  |  | 1713.5 |  |  | 1567.5 |  |  | 1570.5 |  |  | 1451.5 |  |  | 1563.5 |  |  | 1565.5 |  |  | 1522.5 |  |  | 1611.5 |  |  | 1474.5 |  |  | 1639 |  |  | 1559.5 |  |  | 1532.5 |  |  | 1593.5 |  |  | 1693.5 |  |  | 1604.5 |  |  | 1606.5 |  |  | 1613.5 |  |  | 1647.5 |  |  | 1504.5 |  |  | 1670.5 |  |  | 1614.5 |  |  | 1600.5 |  |  | 1660.5 |  |  | 1697 |  |  | 1589.5 |  |  | 1647.5 |  |  | 1557 |  |  | 1674.5 |  |  | 1623.5 |  |  | 1683 |  |  | 1604.5 |  |  | 1697.5 |  |  | 1697.5 |  |  | 1697 |  |  | 1618.5 |  |  | 1666.5 |  |  | 1591.5 |  |  | 1435.5 |  |  | 1574.5 |  |  | 1461 |  |  | 1586.5 |  |  | 1612 |  |  | 1630 |  |  | 1696.5 |  |  | 1631.5 |  |  | 1524.5 |  |  | 1483.5 |  |  | 1625.5 |  |  | 1599.5 |  |  | 1594 |  |  | 1601.5 |  |  | 1603 |  |  | 1558.5 |  |  | 1625 |  |  | 1594 |  |  | 1675 |  |  | 1632.5 |  |  | 1560 |  |  | 1674.5 |  |  | 1676.5 |  |  | 1625.5 |  |  | 1757.5 |  |  | 1621.5 |  |  | 1652 |  |  | 1617.5 |  |  | 1654.5 |  |  | 1781.5 |  |  | 1641 |  |  | 1585.5 |  |  | 1525.5 |  |  | 1629.5 |  |  | 1696.5 |  |  | 1581 |  |  | 1615 |  |  | 1595 |  |  | 1601.5 |  |  | 1623 |  |  | 1681 |  |  | 1657.5 |  |  | 1578.5 |  |  | 1490.5 |  |  | 1648.5 |  |  | 1651.5 |  |  | 1702.5 |  |  | 1695.5 |  |  | 1602.5 |  |  | 1514.5 |  |  | 1518 |  |  | 1607.5 |  |  | 1581 |  |  | 1634.5 |  |  | 1665.5 |  |  | 1611.5 |  |  | 1683.5 |  |  | 1648 |  |  | 1599.5 |  |  | 1578 |  |  | 1540.5 |  |  | 1624.5 |  |  | 1536 |  |  | 1640 |  |  | 1621.5 |  |  | 1597 |  |  | 1664.5 |  |  | 1471.5 |  |  | 1568.5 |  |  | 1567.5 |  |  | 1575.5 |  |  | 1666.5 |  |  | 1516.5 |  |  | 1473 |  |  | 1653.5 |  |  | 1612.5 |  |  | 1543.5 |  |  | 1619.5 |  |  | 1491.5 |  |  | 1549.5 |  |  | 1671.5 |  |  | 1630.5 |  |  | 1688.5 |  |  | 1633.5 |  |  | 1518.5 |  |  | 1539.5 |  |  | 1666 |  |  | 1432.5 |  |  | 1536.5 |  |  | 1640 |  |  | 1498.5 |  |  | 1490.5 |  |  | 1547.5 |  |  | 1570.5 |  |  | 1679 |  |  | 1765.5 |  |  | 1617.5 |  |  | 1513.5 |  |  | 1618.5 |  |  | 1589 |  |  | 1570.5 |  |  | 1644.5 |  |  | 1666.5 |  |  | 1676.5 |  |  | 1569.5 |  |  | 1509.5 |  |  | 1693.5 |  |  | 1710.5 |  |  | 1600.5 |  |  | 1579.5 |  |  | 1720.5 |  |  | 1583 |  |  | 1604.5 |  |  | 1616.5 |  |  | 1646.5 |  |  | 1632.5 |  |  | 1531.5 |  |  | 1561.5 |  |  | 1627 |  |  | 1569.5 |  |  | 1562 |  |  | 1515.5 |  |  | 1650.5 |  |  | 1608.5 |  |  | 1554 |  |  | 1550 |  |  | 1549.5 |  |  | 1657.5 |  |  | 1428.5 |  |  | 1672.5 |  |  | 1538.5 |  |  | 1577.5 |  |  | 1519.5 |  |  | 1564.5 |  |  | 1602.5 |  |  | 1665.5 |  |  | 1551.5 |  |  | 1630.5 |  |  | 1542.5 |  |  | 1683.5 |  |  | 1645.5 |  |  | 1597.5 |  |  | 1550.5 |  |  | 1613.5 |  |  | 1529.5 |  |  | 1570.5 |  |  | 1611.5 |  |  | 1677.5 |  |  | 1627 |  |  | 1675.5 |  |  | 1592.5 |  |  | 1589.5 |  |  | 1607 |  |  | 1636.5 |  |  | 1614.5 |  |  | 1618.5 |  |  | 1588.5 |  |  | 1645 |  |  | 1467.5 |  |  | 1470.5 |  |  | 1482 |  |  | 1567 |  |  | 1639 |  |  | 1527.5 |  |  | 1579.5 |  |  | 1614.5 |  |  | 1744.5 |  |  | 1623 |  |  | 1592.5 |  |  | 1652.5 |  |  | 1509 |  |  | 1545 |  |  | 1640.5 |  |  | 1569.5 |  |  | 1622 |  |  | 1553.5 |  |  | 1664 |  |  | 1533.5 |  |  | 1494.5 |  |  | 1662 |  |  | 1665.5 |  |  | 1568.5 |  |  | 1484.5 |  |  | 1668 |  |  | 1596.5 |  |  | 1538.5 |  |  | 1525.5 |  |  | 1564.5 |  |  | 1602.5 |  |  | 1738.5 |  |  | 1530.5 |  |  | 1586.5 |  |  | 1618.5 |  |  | 1597.5 |  |  | 1630 |  |  | 1614.5 |  |  | 1601.5 |  |  | 1632.5 |  |  | 1652.5 |  |  | 1573.5 |  |  | 1679.5 |  |  | 1679.5 |  |  | 1608.5 |  |  | 1709 |  |  | 1570.5 |  |  | 1566 |  |  | 1657.5 |  |  | 1738.5 |  |  | 1726.5 |  |  | 1524.5 |  |  | 1608.5 |  |  | 1548.5 |  |  | 1453.5 |  |  | 1686.5 |  |  | 1670 |  |  | 1550.5 |  |  | 1577 |  |  | 1526.5 |  |  | 1466.5 |  |  | 1612.5 |  |  | 1649 |  |  | 1581.5 |  |  | 1661.5 |  |  | 1466 |  |  | 1551.5 |  |  | 1566 |  |  | 1588.5 |  |  | 1573.5 |  |  | 1534.5 |  |  | 1575 |  |  | 1644.5 |  |  | 1750.5 |  |  | 1555 |  |  | 1693.5 |  |  | 1474.5 |  |  | 1657 |  |  | 1616.5 |  |  | 1746.5 |  |  | 1685.5 |  |  | 1681.5 |  |  | 1487.5 |  |  | 1680.5 |  |  | 1580.5 |  |  | 1556.5 |  |  | 1475.5 |  |  | 1602.5 |  |  | 1731.5 |  |  | 1646 |  |  | 1650 |  |  | 1638.5 |  |  | 1619.5 |  |  | 1653
56 |  | 1596.5 |  |  | 1754.5 |  |  | 1622 |  |  | 1611.5 |  |  | 1754.5 |  |  | 1643.5 |  |  | 1714.5 |  |  | 1663.5 |  |  | 1652.5 |  |  | 1661.5 |  |  | 1555 |  |  | 1716.5 |  |  | 1718.5 |  |  | 1546.5 |  |  | 1553 |  |  | 1683.5 |  |  | 1758.5 |  |  | 1650.5 |  |  | 1805.5 |  |  | 1575.5 |  |  | 1613.5 |  |  | 1626.5 |  |  | 1651.5 |  |  | 1577.5 |  |  | 1497 |  |  | 1689.5 |  |  | 1586.5 |  |  | 1662.5 |  |  | 1693.5 |  |  | 1547 |  |  | 1646 |  |  | 1593.5 |  |  | 1552.5 |  |  | 1683.5 |  |  | 1528.5 |  |  | 1644 |  |  | 1570.5 |  |  | 1685 |  |  | 1650.5 |  |  | 1656.5 |  |  | 1574.5 |  |  | 1703.5 |  |  | 1549.5 |  |  | 1612 |  |  | 1806.5 |  |  | 1701 |  |  | 1623.5 |  |  | 1757.5 |  |  | 1685.5 |  |  | 1601.5 |  |  | 1597.5 |  |  | 1635.5 |  |  | 1639.5 |  |  | 1578.5 |  |  | 1678.5 |  |  | 1658.5 |  |  | 1534.5 |  |  | 1633 |  |  | 1683.5 |  |  | 1617.5 |  |  | 1597 |  |  | 1607.5 |  |  | 1711.5 |  |  | 1616.5 |  |  | 1541.5 |  |  | 1661 |  |  | 1674.5 |  |  | 1554 |  |  | 1559.5 |  |  | 1645.5 |  |  | 1621 |  |  | 1630.5 |  |  | 1628.5 |  |  | 1760.5 |  |  | 1721 |  |  | 1662 |  |  | 1556.5 |  |  | 1605.5 |  |  | 1482.5 |  |  | 1618.5 |  |  | 1604 |  |  | 1627.5 |  |  | 1658.5 |  |  | 1694.5 |  |  | 1690.5 |  |  | 1651.5 |  |  | 1664.5 |  |  | 1596.5 |  |  | 1577.5 |  |  | 1703.5 |  |  | 1683.5 |  |  | 1680 |  |  | 1520.5 |  |  | 1537 |  |  | 1600 |  |  | 1581 |  |  | 1711.5 |  |  | 1716.5 |  |  | 1539.5 |  |  | 1666.5 |  |  | 1645.5 |  |  | 1621 |  |  | 1603 |  |  | 1600.5 |  |  | 1631.5 |  |  | 1611.5 |  |  | 1698.5 |  |  | 1731.5 |  |  | 1728.5 |  |  | 1688.5 |  |  | 1769.5 |  |  | 1710.5 |  |  | 1654.5 |  |  | 1623.5 |  |  | 1607.5 |  |  | 1680.5 |  |  | 1721.5 |  |  | 1486.5 |  |  | 1701.5 |  |  | 1625.5 |  |  | 1681.5 |  |  | 1670.5 |  |  | 1597.5 |  |  | 1630.5 |  |  | 1667.5 |  |  | 1646 |  |  | 1565.5 |  |  | 1624.5 |  |  | 1596.5 |  |  | 1577.5 |  |  | 1752.5 |  |  | 1687 |  |  | 1572.5 |  |  | 1702.5 |  |  | 1538.5 |  |  | 1657.5 |  |  | 1696 |  |  | 1605.5 |  |  | 1694.5 |  |  | 1636 |  |  | 1665.5 |  |  | 1607 |  |  | 1640 |  |  | 1732.5 |  |  | 1657 |  |  | 1704.5 |  |  | 1616.5 |  |  | 1689.5 |  |  | 1567.5 |  |  | 1708.5 |  |  | 1659.5 |  |  | 1644.5 |  |  | 1676.5 |  |  | 1803.5 |  |  | 1672.5 |  |  | 1726 |  |  | 1618.5 |  |  | 1526 |  |  | 1606.5 |  |  | 1677.5 |  |  | 1635 |  |  | 1624.5 |  |  | 1639.5 |  |  | 1600.5 |  |  | 1603 |  |  | 1653.5 |  |  | 1512.5 |  |  | 1562.5 |  |  | 1731.5 |  |  | 1550.5 |  |  | 1590.5 |  |  | 1639 |  |  | 1607.5 |  |  | 1656.5 |  |  | 1620.5 |  |  | 1612.5 |  |  | 1681.5 |  |  | 1631.5 |  |  | 1544.5 |  |  | 1714 |  |  | 1700.5 |  |  | 1661.5 |  |  | 1724.5 |  |  | 1669.5 |  |  | 1546.5 |  |  | 1743.5 |  |  | 1723.5 |  |  | 1647.5 |  |  | 1671.5 |  |  | 1564.5 |  |  | 1609.5 |  |  | 1550.5 |  |  | 1471.5 |  |  | 1570 |  |  | 1588.5 |  |  | 1677.5 |  |  | 1616.5 |  |  | 1697.5 |  |  | 1659.5 |  |  | 1633.5 |  |  | 1715.5 |  |  | 1619.5 |  |  | 1680.5 |  |  | 1586.5 |  |  | 1597.5 |  |  | 1730.5 |  |  | 1624.5 |  |  | 1587.5 |  |  | 1628.5 |  |  | 1664.5 |  |  | 1687 |  |  | 1647.5 |  |  | 1626.5 |  |  | 1517 |  |  | 1768.5 |  |  | 1674 |  |  | 1608.5 |  |  | 1715.5 |  |  | 1743.5 |  |  | 1705.5 |  |  | 1545.5 |  |  | 1582.5 |  |  | 1613.5 |  |  | 1485.5 |  |  | 1602 |  |  | 1537.5 |  |  | 1503.5 |  |  | 1735.5 |  |  | 1569.5 |  |  | 1674 |  |  | 1526.5 |  |  | 1644.5 |  |  | 1704.5 |  |  | 1728.5 |  |  | 1701.5 |  |  | 1563.5 |  |  | 1600.5 |  |  | 1683.5 |  |  | 1673 |  |  | 1619 |  |  | 1586.5 |  |  | 1648.5 |  |  | 1592.5 |  |  | 1658 |  |  | 1726.5 |  |  | 1665.5 |  |  | 1572.5 |  |  | 1616 |  |  | 1633.5 |  |  | 1720.5 |  |  | 1596.5 |  |  | 1623.5 |  |  | 1669.5 |  |  | 1663.5 |  |  | 1664.5 |  |  | 1636.5 |  |  | 1744.5 |  |  | 1461 |  |  | 1548.5 |  |  | 1635.5 |  |  | 1632.5 |  |  | 1558.5 |  |  | 1612.5 |  |  | 1712 |  |  | 1601.5 |  |  | 1685.5 |  |  | 1654 |  |  | 1785.5 |  |  | 1679.5 |  |  | 1773 |  |  | 1639.5 |  |  | 1628.5 |  |  | 1761.5 |  |  | 1554.5 |  |  | 1643 |  |  | 1638 |  |  | 1657.5 |  |  | 1583.5 |  |  | 1682.5 |  |  | 1662.5 |  |  | 1727.5 |  |  | 1595.5 |  |  | 1637 |  |  | 1630.5 |  |  | 1620.5 |  |  | 1628 |  |  | 1560.5 |  |  | 1510.5 |  |  | 1663 |  |  | 1600.5 |  |  | 1573.5 |  |  | 1648.5 |  |  | 1626 |  |  | 1680.5 |  |  | 1589 |  |  | 1651.5 |  |  | 1536.5 |  |  | 1647.5 |  |  | 1606 |  |  | 1587.5 |  |  | 1726.5 |  |  | 1614.5 |  |  | 1607 |  |  | 1519.5 |  |  | 1537.5 |  |  | 1787.5 |  |  | 1742.5 |  |  | 1611.5 |  |  | 1620 |  |  | 1551.5 |  |  | 1755.5 |  |  | 1736.5 |  |  | 1596 |  |  | 1617 |  |  | 1751.5 |  |  | 1589.5 |  |  | 1528.5 |  |  | 1618.5 |  |  | 1655.5 |  |  | 1669.5 |  |  | 1635.5 |  |  | 1655.5 |  |  | 1576.5 |  |  | 1631.5 |  |  | 1628 |  |  | 1652.5 |  |  | 1721.5 |  |  | 1804.5 |  |  | 1710.5 |  |  | 1678 |  |  | 1664.5 |  |  | 1671.5 |  |  | 1660.5 |  |  | 1458.5 |  |  | 1734.5 |  |  | 1589 |  |  | 1621 |  |  | 1561 |  |  | 1699 |  |  | 1569.5 |  |  | 1643 |  |  | 1615.5 |  |  | 1585 |  |  | 1665.5 |  |  | 1752.5 |  |  | 1645.5 |  |  | 1597.5 |  |  | 1565.5 |  |  | 1637 |  |  | 1614.5 |  |  | 1711.5 |  |  | 1534.5 |  |  | 1718 |  |  | 1641.5 |  |  | 1557.5 |  |  | 1620.5 |  |  | 1684 |  |  | 1623.5 |  |  | 1527.5 |  |  | 1681.5 |  |  | 1567.5 |  |  | 1616.5 |  |  | 1566.5 |  |  | 1728.5 |  |  | 1556.5 |  |  | 1712.5 |  |  | 1519.5 |  |  | 1506 |  |  | 1613.5 |  |  | 1634.5 |  |  | 1586.5 |  |  | 1621.5 |  |  | 1773.5 |  |  | 1604 |  |  | 1674.5 |  |  | 1680 |  |  | 1616 |  |  | 1641.5 |  |  | 1746.5 |  |  | 1561.5 |  |  | 1542 |  |  | 1671.5 |  |  | 1663.5 |  |  | 1671.5 |  |  | 1505 |  |  | 1627.5 |  |  | 1463.5 |  |  | 1665.5 |  |  | 1584.5 |  |  | 1566.5 |  |  | 1599 |  |  | 1617.5 |  |  | 1659 |  |  | 1623.5 |  |  | 1563.5 |  |  | 1641.5 |  |  | 1696 |  |  | 1547.5 |  |  | 1656 |  |  | 1664 |  |  | 1625.5 |  |  | 1583.5 |  |  | 1615.5 |  |  | 1720.5 |  |  | 1673 |  |  | 1673.5 |  |  | 1616.5 |  |  | 1490.5 |  |  | 1593 |  |  | 1726.5 |  |  | 1579.5 |  |  | 1523.5 |  |  | 1598.5 |  |  | 1689 |  |  | 1496.5 |  |  | 1609.5 |  |  | 1682.5 |  |  | 1619.5 |  |  | 1604.5 |  |  | 1616.5 |  |  | 1715 |  |  | 1608.5 |  |  | 1533.5 |  |  | 1656 |  |  | 1556.5 |  |  | 1513.5 |  |  | 1585.5 |  |  | 1642 |  |  | 1665.5 |  |  | 1618.5 |  |  | 1637.5 |  |  | 1637.5 |  |  | 1722.5 |  |  | 1696 |  |  | 1657 |  |  | 1573.5 |  |  | 1659.5 |  |  | 1681.5 |  |  | 1557.5 |  |  | 1517 |  |  | 1700 |  |  | 1537 |  |  | 1661.5 |  |  | 1603 |  |  | 1626.5 |  |  | 1722.5 |  |  | 1633 |  |  | 1565.5 |  |  | 1698.5 |  |  | 1627.5 |  |  | 1763.5 |  |  | 1490.5 |  |  | 1616 |  |  | 1684 |  |  | 1493.5 |  |  | 1690.5 |  |  | 1602 |  |  | 1517.5 |  |  | 1670.5 |  |  | 1612 |  |  | 1752.5 |  |  | 1735.5 |  |  | 1524 |  |  | 1682.5 |  |  | 1639.5 |  |  | 1619 |  |  | 1684.5 |  |  | 1595 |  |  | 1787.5 |  |  | 1790 |  |  | 1586.5 |  |  | 1620.5 |  |  | 1691.5 |  |  | 1618.5 |  |  | 1643.5 |  |  | 1579.5 |  |  | 1662 |  |  | 1600.5 |  |  | 1610.5 |  |  | 1552.5 |  |  | 1657.5 |  |  | 1613.5 |  |  | 1628 |  |  | 1594.5 |  |  | 1657 |  |  | 1668.5 |  |  | 1570.5 |  |  | 1665.5 |  |  | 1584.5 |  |  | 1583.5 |  |  | 1673.5 |  |  | 1583.5 |  |  | 1729.5 |  |  | 1579.5 |  |  | 1645 |  |  | 1652.5 |  |  | 1537 |  |  | 1640 |  |  | 1638.5 |  |  | 1538 |  |  | 1556.5 |  |  | 1634.5 |  |  | 1683.5 |  |  | 1593.5 |  |  | 1670.5 |  |  | 1790.5 |  |  | 1697.5 |  |  | 1586 |  |  | 1678 |  |  | 1556.5 |  |  | 1487.5 |  |  | 1653 |  |  | 1595.5 |  |  | 1660.5 |  |  | 1580.5 |  |  | 1568.5 |  |  | 1549.5 |  |  | 1559 |  |  | 1628.5 |  |  | 1624.5 |  |  | 1555.5 |  |  | 1561 |  |  | 1693.5 |  |  | 1657.5 |  |  | 1671.5 |  |  | 1787.5 |  |  | 1676.5 |  |  | 1572.5 |  |  | 1737.5 |  |  | 1389.5 |  |  | 1675.5 |  |  | 1528 |  |  | 1709.5 |  |  | 1626.5 |  |  | 1735.5 |  |  | 1521.5 |  |  | 1582.5 |  |  | 1578.5 |  |  | 1554.5 |  |  | 1441 |  |  | 1537.5 |  |  | 1672.5 |  |  | 1718.5 |  |  | 1553 |  |  | 1604.5 |  |  | 1548 |  |  | 1535.5 |  |  | 1660.5 |  |  | 1589.5 |  |  | 1629 |  |  | 1557.5 |  |  | 1658 |  |  | 1664 |  |  | 1673.5 |  |  | 1612 |  |  | 1701 |  |  | 1709.5 |  |  | 1645.5 |  |  | 1516.5 |  |  | 1683 |  |  | 1714.5 |  |  | 1566.5 |  |  | 1511.5 |  |  | 1695.5 |  |  | 1593.5 |  |  | 1573.5 |  |  | 1563.5 |  |  | 1651.5 |  |  | 1554 |  |  | 1764.5 |  |  | 1561 |  |  | 1575.5 |  |  | 1549.5 |  |  | 1730.5 |  |  | 1632 |  |  | 1680 |  |  | 1744 |  |  | 1624.5 |  |  | 1626 |  |  | 1703.5 |  |  | 1745.5 |  |  | 1598.5 |  |  | 1624.5 |  |  | 1556.5 |  |  | 1693.5 |  |  | 1668.5 |  |  | 1637.5 |  |  | 1665 |  |  | 1539.5 |  |  | 1517.5 |  |  | 1675.5 |  |  | 1573.5 |  |  | 1536 |  |  | 1592.5 |  |  | 1656 |  |  | 1636.5 |  |  | 1645.5 |  |  | 1567.5 |  |  | 1594.5 |  |  | 1521 |  |  | 1566.5 |  |  | 1464 |  |  | 1590.5 |  |  | 1705.5 |  |  | 1783.5 |  |  | 1728.5 |  |  | 1607.5 |  |  | 1609.5 |  |  | 1495.5 |  |  | 1671.5 |  |  | 1604.5 |  |  | 1602 |  |  | 1644.5 |  |  | 1601.5 |  |  | 1591.5 |  |  | 1625.5 |  |  | 1637.5 |  |  | 1519 |  |  | 1581 |  |  | 1613.5 |  |  | 1526 |  |  | 1775.5 |  |  | 1610.5 |  |  | 1721.5 |  |  | 1722.5 |  |  | 1605.5 |  |  | 1656.5 |  |  | 1608.5 |  |  | 1652.5 |  |  | 1635 |  |  | 1629.5 |  |  | 1784.5 |  |  | 1695.5 |  |  | 1531 |  |  | 1632.5 |  |  | 1582.5 |  |  | 1674 |  |  | 1528 |  |  | 1665.5 |  |  | 1571 |  |  | 1487 |  |  | 1523.5 |  |  | 1651 |  |  | 1735.5 |  |  | 1703.5 |  |  | 1667.5 |  |  | 1623.5 |  |  | 1518.5 |  |  | 1623.5 |  |  | 1486.5 |  |  | 1603.5 |  |  | 1667.5 |  |  | 1598.5 |  |  | 1534 |  |  | 1534 |  |  | 1695.5 |  |  | 1613.5 |  |  | 1608.5 |  |  | 1688.5 |  |  | 1541.5 |  |  | 1631.5 |  |  | 1707.5 |  |  | 1575.5 |  |  | 1787 |  |  | 1560.5 |  |  | 1584 |  |  | 1595.5 |  |  | 1805.5 |  |  | 1661.5 |  |  | 1681 |  |  | 1621.5 |  |  | 1560.5 |  |  | 1572 |  |  | 1663.5 |  |  | 1616.5 |  |  | 1705.5 |  |  | 1661.5 |  |  | 1575.5 |  |  | 1619.5 |  |  | 1607 |  |  | 1557.5 |  |  | 1540.5 |  |  | 1675.5 |  |  | 1749.5 |  |  | 1576 |  |  | 1617.5 |  |  | 1737.5 |  |  | 1566 |  |  | 1691.5 |  |  | 1670.5 |  |  | 1612 |  |  | 1668.5 |  |  | 1723.5 |  |  | 1603.5 |  |  | 1576 |  |  | 1505.5 |  |  | 1621.5 |  |  | 1625 |  |  | 1617.5 |  |  | 1735.5 |  |  | 1668.5 |  |  | 1447.5 |  |  | 1730.5 |  |  | 1779.5 |  |  | 1553.5 |  |  | 1657 |  |  | 1575 |  |  | 1497.5 |  |  | 1645.5 |  |  | 1547.5 |  |  | 1617 |  |  | 1752.5 |  |  | 1606.5 |  |  | 1594.5 |  |  | 1472.5 |  |  | 1584.5 |  |  | 1594.5 |  |  | 1569.5 |  |  | 1650.5 |  |  | 1500.5 |  |  | 1654 |  |  | 1574.5 |  |  | 1571.5 |  |  | 1622.5 |  |  | 1714.5 |  |  | 1651.5 |  |  | 1632.5 |  |  | 1652.5 |  |  | 1686.5 |  |  | 1543.5 |  |  | 1699.5 |  |  | 1635.5 |  |  | 1626.5 |  |  | 1686.5 |  |  | 1736 |  |  | 1636.5 |  |  | 1686.5 |  |  | 1581 |  |  | 1703.5 |  |  | 1662.5 |  |  | 1722 |  |  | 1643.5 |  |  | 1736.5 |  |  | 1723.5 |  |  | 1744 |  |  | 1633.5 |  |  | 1692.5 |  |  | 1617.5 |  |  | 1482.5 |  |  | 1589.5 |  |  | 1500 |  |  | 1607.5 |  |  | 1636 |  |  | 1651 |  |  | 1735.5 |  |  | 1660.5 |  |  | 1539.5 |  |  | 1504.5 |  |  | 1651.5 |  |  | 1625.5 |  |  | 1609 |  |  | 1630.5 |  |  | 1624 |  |  | 1605.5 |  |  | 1654 |  |  | 1615 |  |  | 1714 |  |  | 1656.5 |  |  | 1586 |  |  | 1713.5 |  |  | 1705.5 |  |  | 1664.5 |  |  | 1786.5 |  |  | 1647.5 |  |  | 1699 |  |  | 1664.5 |  |  | 1683.5 |  |  | 1820.5 |  |  | 1662 |  |  | 1624.5 |  |  | 1549.5 |  |  | 1653.5 |  |  | 1711.5 |  |  | 1602 |  |  | 1654 |  |  | 1624 |  |  | 1630.5 |  |  | 1662 |  |  | 1720 |  |  | 1696.5 |  |  | 1602.5 |  |  | 1516.5 |  |  | 1672.5 |  |  | 1675.5 |  |  | 1731.5 |  |  | 1716.5 |  |  | 1628.5 |  |  | 1553.5 |  |  | 1544 |  |  | 1636.5 |  |  | 1605 |  |  | 1663.5 |  |  | 1680.5 |  |  | 1632.5 |  |  | 1704.5 |  |  | 1687 |  |  | 1638.5 |  |  | 1617 |  |  | 1579.5 |  |  | 1653.5 |  |  | 1583 |  |  | 1655 |  |  | 1647.5 |  |  | 1623 |  |  | 1693.5 |  |  | 1510.5 |  |  | 1592.5 |  |  | 1606.5 |  |  | 1614.5 |  |  | 1687.5 |  |  | 1542.5 |  |  | 1512 |  |  | 1700.5 |  |  | 1627.5 |  |  | 1582.5 |  |  | 1643.5 |  |  | 1530.5 |  |  | 1578.5 |  |  | 1700.5 |  |  | 1654.5 |  |  | 1727.5 |  |  | 1672.5 |  |  | 1542.5 |  |  | 1554.5 |  |  | 1687 |  |  | 1479.5 |  |  | 1562.5 |  |  | 1666 |  |  | 1522.5 |  |  | 1529.5 |  |  | 1594.5 |  |  | 1596.5 |  |  | 1700 |  |  | 1786.5 |  |  | 1643.5 |  |  | 1539.5 |  |  | 1665.5 |  |  | 1615 |  |  | 1596.5 |  |  | 1683.5 |  |  | 1692.5 |  |  | 1702.5 |  |  | 1598.5 |  |  | 1548.5 |  |  | 1708.5 |  |  | 1739.5 |  |  | 1624.5 |  |  | 1605.5 |  |  | 1741.5 |  |  | 1630 |  |  | 1643.5 |  |  | 1642.5 |  |  | 1685.5 |  |  | 1656.5 |  |  | 1570.5 |  |  | 1608.5 |  |  | 1674 |  |  | 1598.5 |  |  | 1586 |  |  | 1541.5 |  |  | 1697.5 |  |  | 1647.5 |  |  | 1583 |  |  | 1576 |  |  | 1588.5 |  |  | 1696.5 |  |  | 1454.5 |  |  | 1701.5 |  |  | 1559.5 |  |  | 1624.5 |  |  | 1558.5 |  |  | 1590.5 |  |  | 1617.5 |  |  | 1691.5 |  |  | 1577.5 |  |  | 1654.5 |  |  | 1557.5 |  |  | 1722.5 |  |  | 1660.5 |  |  | 1618.5 |  |  | 1574.5 |  |  | 1639.5 |  |  | 1568.5 |  |  | 1596.5 |  |  | 1626.5 |  |  | 1692.5 |  |  | 1648 |  |  | 1690.5 |  |  | 1613.5 |  |  | 1613.5 |  |  | 1654 |  |  | 1683.5 |  |  | 1629.5 |  |  | 1642.5 |  |  | 1612.5 |  |  | 1671 |  |  | 1506.5 |  |  | 1485.5 |  |  | 1521 |  |  | 1606 |  |  | 1686 |  |  | 1551.5 |  |  | 1603.5 |  |  | 1653.5 |  |  | 1770.5 |  |  | 1638 |  |  | 1631.5 |  |  | 1667.5 |  |  | 1530 |  |  | 1574 |  |  | 1669.5 |  |  | 1584.5 |  |  | 1661 |  |  | 1579.5 |  |  | 1688 |  |  | 1554.5 |  |  | 1520.5 |  |  | 1683 |  |  | 1704.5 |  |  | 1607.5 |  |  | 1499.5 |  |  | 1715 |  |  | 1611.5 |  |  | 1553.5 |  |  | 1546.5 |  |  | 1603.5 |  |  | 1623.5 |  |  | 1777.5 |  |  | 1545.5 |  |  | 1633.5 |  |  | 1665.5 |  |  | 1636.5 |  |  | 1669 |  |  | 1638.5 |  |  | 1622.5 |  |  | 1658.5 |  |  | 1676.5 |  |  | 1594.5 |  |  | 1718.5 |  |  | 1705.5 |  |  | 1629.5 |  |  | 1748 |  |  | 1596.5 |  |  | 1613 |  |  | 1683.5 |  |  | 1767.5 |  |  | 1755.5 |  |  | 1548.5 |  |  | 1629.5 |  |  | 1577.5 |  |  | 1492.5 |  |  | 1701.5 |  |  | 1717 |  |  | 1571.5 |  |  | 1616 |  |  | 1552.5 |  |  | 1487.5 |  |  | 1651.5 |  |  | 1696 |  |  | 1628.5 |  |  | 1687.5 |  |  | 1481 |  |  | 1577.5 |  |  | 1613 |  |  | 1627.5 |  |  | 1620.5 |  |  | 1563.5 |  |  | 1604 |  |  | 1665.5 |  |  | 1797.5 |  |  | 1579 |  |  | 1732.5 |  |  | 1521.5 |  |  | 1686 |  |  | 1642.5 |  |  | 1761.5 |  |  | 1724.5 |  |  | 1707.5 |  |  | 1511.5 |  |  | 1719.5 |  |  | 1604.5 |  |  | 1580.5 |  |  | 1499.5 |  |  | 1623.5 |  |  | 1770.5 |  |  | 1672 |  |  | 1674 |  |  | 1677.5 |  |  | 1658.5 |  |  | 1677
57 |  | 1643.5 |  |  | 1780.5 |  |  | 1637 |  |  | 1637.5 |  |  | 1778.5 |  |  | 1658.5 |  |  | 1735.5 |  |  | 1689.5 |  |  | 1699.5 |  |  | 1676.5 |  |  | 1594 |  |  | 1737.5 |  |  | 1757.5 |  |  | 1572.5 |  |  | 1592 |  |  | 1709.5 |  |  | 1779.5 |  |  | 1671.5 |  |  | 1834.5 |  |  | 1614.5 |  |  | 1639.5 |  |  | 1665.5 |  |  | 1690.5 |  |  | 1592.5 |  |  | 1536 |  |  | 1728.5 |  |  | 1625.5 |  |  | 1688.5 |  |  | 1722.5 |  |  | 1571 |  |  | 1693 |  |  | 1632.5 |  |  | 1573.5 |  |  | 1730.5 |  |  | 1552.5 |  |  | 1691 |  |  | 1609.5 |  |  | 1732 |  |  | 1665.5 |  |  | 1677.5 |  |  | 1600.5 |  |  | 1742.5 |  |  | 1588.5 |  |  | 1633 |  |  | 1832.5 |  |  | 1740 |  |  | 1644.5 |  |  | 1772.5 |  |  | 1700.5 |  |  | 1622.5 |  |  | 1626.5 |  |  | 1682.5 |  |  | 1654.5 |  |  | 1607.5 |  |  | 1725.5 |  |  | 1673.5 |  |  | 1573.5 |  |  | 1672 |  |  | 1707.5 |  |  | 1643.5 |  |  | 1636 |  |  | 1646.5 |  |  | 1735.5 |  |  | 1637.5 |  |  | 1565.5 |  |  | 1676 |  |  | 1713.5 |  |  | 1593 |  |  | 1588.5 |  |  | 1684.5 |  |  | 1660 |  |  | 1654.5 |  |  | 1675.5 |  |  | 1789.5 |  |  | 1742 |  |  | 1701 |  |  | 1571.5 |  |  | 1626.5 |  |  | 1511.5 |  |  | 1642.5 |  |  | 1619 |  |  | 1648.5 |  |  | 1697.5 |  |  | 1723.5 |  |  | 1729.5 |  |  | 1677.5 |  |  | 1690.5 |  |  | 1625.5 |  |  | 1601.5 |  |  | 1729.5 |  |  | 1712.5 |  |  | 1695 |  |  | 1544.5 |  |  | 1576 |  |  | 1639 |  |  | 1602 |  |  | 1750.5 |  |  | 1755.5 |  |  | 1554.5 |  |  | 1681.5 |  |  | 1660.5 |  |  | 1660 |  |  | 1642 |  |  | 1615.5 |  |  | 1655.5 |  |  | 1640.5 |  |  | 1727.5 |  |  | 1752.5 |  |  | 1749.5 |  |  | 1714.5 |  |  | 1808.5 |  |  | 1736.5 |  |  | 1701.5 |  |  | 1652.5 |  |  | 1646.5 |  |  | 1727.5 |  |  | 1760.5 |  |  | 1525.5 |  |  | 1725.5 |  |  | 1664.5 |  |  | 1707.5 |  |  | 1696.5 |  |  | 1618.5 |  |  | 1651.5 |  |  | 1682.5 |  |  | 1672 |  |  | 1612.5 |  |  | 1653.5 |  |  | 1611.5 |  |  | 1616.5 |  |  | 1778.5 |  |  | 1734 |  |  | 1611.5 |  |  | 1731.5 |  |  | 1559.5 |  |  | 1681.5 |  |  | 1725 |  |  | 1629.5 |  |  | 1709.5 |  |  | 1651 |  |  | 1680.5 |  |  | 1633 |  |  | 1661 |  |  | 1761.5 |  |  | 1683 |  |  | 1743.5 |  |  | 1645.5 |  |  | 1728.5 |  |  | 1588.5 |  |  | 1723.5 |  |  | 1685.5 |  |  | 1683.5 |  |  | 1715.5 |  |  | 1824.5 |  |  | 1687.5 |  |  | 1755 |  |  | 1647.5 |  |  | 1550 |  |  | 1645.5 |  |  | 1703.5 |  |  | 1659 |  |  | 1648.5 |  |  | 1665.5 |  |  | 1621.5 |  |  | 1629 |  |  | 1674.5 |  |  | 1541.5 |  |  | 1583.5 |  |  | 1746.5 |  |  | 1579.5 |  |  | 1614.5 |  |  | 1663 |  |  | 1636.5 |  |  | 1677.5 |  |  | 1635.5 |  |  | 1651.5 |  |  | 1702.5 |  |  | 1660.5 |  |  | 1573.5 |  |  | 1729 |  |  | 1739.5 |  |  | 1682.5 |  |  | 1739.5 |  |  | 1698.5 |  |  | 1572.5 |  |  | 1767.5 |  |  | 1752.5 |  |  | 1676.5 |  |  | 1718.5 |  |  | 1588.5 |  |  | 1648.5 |  |  | 1571.5 |  |  | 1518.5 |  |  | 1609 |  |  | 1609.5 |  |  | 1703.5 |  |  | 1655.5 |  |  | 1736.5 |  |  | 1685.5 |  |  | 1680.5 |  |  | 1754.5 |  |  | 1640.5 |  |  | 1719.5 |  |  | 1615.5 |  |  | 1623.5 |  |  | 1769.5 |  |  | 1645.5 |  |  | 1616.5 |  |  | 1643.5 |  |  | 1688.5 |  |  | 1726 |  |  | 1694.5 |  |  | 1655.5 |  |  | 1543 |  |  | 1815.5 |  |  | 1703 |  |  | 1632.5 |  |  | 1730.5 |  |  | 1772.5 |  |  | 1731.5 |  |  | 1571.5 |  |  | 1608.5 |  |  | 1642.5 |  |  | 1514.5 |  |  | 1623 |  |  | 1552.5 |  |  | 1527.5 |  |  | 1761.5 |  |  | 1608.5 |  |  | 1689 |  |  | 1565.5 |  |  | 1673.5 |  |  | 1730.5 |  |  | 1754.5 |  |  | 1748.5 |  |  | 1602.5 |  |  | 1647.5 |  |  | 1730.5 |  |  | 1699 |  |  | 1648 |  |  | 1612.5 |  |  | 1677.5 |  |  | 1618.5 |  |  | 1682 |  |  | 1747.5 |  |  | 1686.5 |  |  | 1596.5 |  |  | 1631 |  |  | 1672.5 |  |  | 1744.5 |  |  | 1611.5 |  |  | 1638.5 |  |  | 1698.5 |  |  | 1684.5 |  |  | 1679.5 |  |  | 1683.5 |  |  | 1791.5 |  |  | 1500 |  |  | 1563.5 |  |  | 1674.5 |  |  | 1647.5 |  |  | 1573.5 |  |  | 1638.5 |  |  | 1741 |  |  | 1627.5 |  |  | 1732.5 |  |  | 1678 |  |  | 1800.5 |  |  | 1718.5 |  |  | 1799 |  |  | 1678.5 |  |  | 1652.5 |  |  | 1787.5 |  |  | 1593.5 |  |  | 1664 |  |  | 1659 |  |  | 1681.5 |  |  | 1612.5 |  |  | 1703.5 |  |  | 1701.5 |  |  | 1766.5 |  |  | 1616.5 |  |  | 1666 |  |  | 1669.5 |  |  | 1659.5 |  |  | 1675 |  |  | 1607.5 |  |  | 1534.5 |  |  | 1710 |  |  | 1626.5 |  |  | 1599.5 |  |  | 1677.5 |  |  | 1647 |  |  | 1701.5 |  |  | 1636 |  |  | 1690.5 |  |  | 1575.5 |  |  | 1686.5 |  |  | 1635 |  |  | 1613.5 |  |  | 1773.5 |  |  | 1653.5 |  |  | 1654 |  |  | 1558.5 |  |  | 1552.5 |  |  | 1813.5 |  |  | 1781.5 |  |  | 1632.5 |  |  | 1659 |  |  | 1575.5 |  |  | 1802.5 |  |  | 1783.5 |  |  | 1611 |  |  | 1646 |  |  | 1777.5 |  |  | 1618.5 |  |  | 1554.5 |  |  | 1665.5 |  |  | 1681.5 |  |  | 1690.5 |  |  | 1650.5 |  |  | 1679.5 |  |  | 1623.5 |  |  | 1646.5 |  |  | 1654 |  |  | 1667.5 |  |  | 1747.5 |  |  | 1851.5 |  |  | 1725.5 |  |  | 1699 |  |  | 1690.5 |  |  | 1700.5 |  |  | 1686.5 |  |  | 1497.5 |  |  | 1760.5 |  |  | 1613 |  |  | 1650 |  |  | 1585 |  |  | 1738 |  |  | 1590.5 |  |  | 1690 |  |  | 1654.5 |  |  | 1606 |  |  | 1689.5 |  |  | 1791.5 |  |  | 1684.5 |  |  | 1636.5 |  |  | 1604.5 |  |  | 1676 |  |  | 1661.5 |  |  | 1735.5 |  |  | 1581.5 |  |  | 1739 |  |  | 1680.5 |  |  | 1596.5 |  |  | 1649.5 |  |  | 1713 |  |  | 1647.5 |  |  | 1566.5 |  |  | 1707.5 |  |  | 1588.5 |  |  | 1655.5 |  |  | 1605.5 |  |  | 1749.5 |  |  | 1603.5 |  |  | 1738.5 |  |  | 1540.5 |  |  | 1545 |  |  | 1642.5 |  |  | 1660.5 |  |  | 1610.5 |  |  | 1660.5 |  |  | 1788.5 |  |  | 1628 |  |  | 1721.5 |  |  | 1727 |  |  | 1642 |  |  | 1656.5 |  |  | 1785.5 |  |  | 1585.5 |  |  | 1568 |  |  | 1692.5 |  |  | 1702.5 |  |  | 1710.5 |  |  | 1534 |  |  | 1653.5 |  |  | 1502.5 |  |  | 1694.5 |  |  | 1599.5 |  |  | 1595.5 |  |  | 1620 |  |  | 1646.5 |  |  | 1683 |  |  | 1652.5 |  |  | 1587.5 |  |  | 1680.5 |  |  | 1735 |  |  | 1562.5 |  |  | 1682 |  |  | 1690 |  |  | 1664.5 |  |  | 1612.5 |  |  | 1641.5 |  |  | 1744.5 |  |  | 1720 |  |  | 1712.5 |  |  | 1642.5 |  |  | 1514.5 |  |  | 1640 |  |  | 1752.5 |  |  | 1603.5 |  |  | 1538.5 |  |  | 1637.5 |  |  | 1728 |  |  | 1511.5 |  |  | 1648.5 |  |  | 1708.5 |  |  | 1645.5 |  |  | 1633.5 |  |  | 1645.5 |  |  | 1741 |  |  | 1623.5 |  |  | 1580.5 |  |  | 1682 |  |  | 1582.5 |  |  | 1539.5 |  |  | 1609.5 |  |  | 1657 |  |  | 1686.5 |  |  | 1665.5 |  |  | 1666.5 |  |  | 1666.5 |  |  | 1761.5 |  |  | 1735 |  |  | 1672 |  |  | 1612.5 |  |  | 1685.5 |  |  | 1705.5 |  |  | 1572.5 |  |  | 1556 |  |  | 1739 |  |  | 1552 |  |  | 1685.5 |  |  | 1642 |  |  | 1641.5 |  |  | 1751.5 |  |  | 1662 |  |  | 1604.5 |  |  | 1737.5 |  |  | 1666.5 |  |  | 1810.5 |  |  | 1511.5 |  |  | 1655 |  |  | 1723 |  |  | 1519.5 |  |  | 1714.5 |  |  | 1628 |  |  | 1538.5 |  |  | 1717.5 |  |  | 1659 |  |  | 1778.5 |  |  | 1774.5 |  |  | 1571 |  |  | 1708.5 |  |  | 1663.5 |  |  | 1648 |  |  | 1710.5 |  |  | 1634 |  |  | 1808.5 |  |  | 1811 |  |  | 1601.5 |  |  | 1649.5 |  |  | 1738.5 |  |  | 1639.5 |  |  | 1682.5 |  |  | 1618.5 |  |  | 1701 |  |  | 1615.5 |  |  | 1636.5 |  |  | 1599.5 |  |  | 1683.5 |  |  | 1652.5 |  |  | 1652 |  |  | 1609.5 |  |  | 1678 |  |  | 1689.5 |  |  | 1585.5 |  |  | 1704.5 |  |  | 1599.5 |  |  | 1598.5 |  |  | 1712.5 |  |  | 1609.5 |  |  | 1758.5 |  |  | 1605.5 |  |  | 1671 |  |  | 1676.5 |  |  | 1576 |  |  | 1679 |  |  | 1664.5 |  |  | 1577 |  |  | 1580.5 |  |  | 1660.5 |  |  | 1722.5 |  |  | 1640.5 |  |  | 1696.5 |  |  | 1811.5 |  |  | 1736.5 |  |  | 1633 |  |  | 1717 |  |  | 1571.5 |  |  | 1508.5 |  |  | 1679 |  |  | 1619.5 |  |  | 1684.5 |  |  | 1606.5 |  |  | 1607.5 |  |  | 1588.5 |  |  | 1598 |  |  | 1643.5 |  |  | 1650.5 |  |  | 1579.5 |  |  | 1582 |  |  | 1719.5 |  |  | 1681.5 |  |  | 1686.5 |  |  | 1816.5 |  |  | 1723.5 |  |  | 1593.5 |  |  | 1763.5 |  |  | 1418.5 |  |  | 1699.5 |  |  | 1567 |  |  | 1748.5 |  |  | 1641.5 |  |  | 1750.5 |  |  | 1550.5 |  |  | 1629.5 |  |  | 1604.5 |  |  | 1580.5 |  |  | 1488 |  |  | 1558.5 |  |  | 1711.5 |  |  | 1744.5 |  |  | 1579 |  |  | 1643.5 |  |  | 1595 |  |  | 1582.5 |  |  | 1699.5 |  |  | 1613.5 |  |  | 1676 |  |  | 1572.5 |  |  | 1679 |  |  | 1693 |  |  | 1697.5 |  |  | 1636 |  |  | 1727 |  |  | 1738.5 |  |  | 1692.5 |  |  | 1555.5 |  |  | 1712 |  |  | 1743.5 |  |  | 1605.5 |  |  | 1537.5 |  |  | 1719.5 |  |  | 1608.5 |  |  | 1612.5 |  |  | 1584.5 |  |  | 1698.5 |  |  | 1578 |  |  | 1785.5 |  |  | 1600 |  |  | 1622.5 |  |  | 1575.5 |  |  | 1769.5 |  |  | 1656 |  |  | 1695 |  |  | 1765 |  |  | 1653.5 |  |  | 1650 |  |  | 1729.5 |  |  | 1774.5 |  |  | 1645.5 |  |  | 1639.5 |  |  | 1603.5 |  |  | 1708.5 |  |  | 1707.5 |  |  | 1684.5 |  |  | 1691 |  |  | 1560.5 |  |  | 1543.5 |  |  | 1701.5 |  |  | 1588.5 |  |  | 1565 |  |  | 1631.5 |  |  | 1682 |  |  | 1651.5 |  |  | 1666.5 |  |  | 1593.5 |  |  | 1633.5 |  |  | 1536 |  |  | 1605.5 |  |  | 1479 |  |  | 1611.5 |  |  | 1734.5 |  |  | 1798.5 |  |  | 1743.5 |  |  | 1646.5 |  |  | 1648.5 |  |  | 1519.5 |  |  | 1697.5 |  |  | 1619.5 |  |  | 1628 |  |  | 1670.5 |  |  | 1625.5 |  |  | 1606.5 |  |  | 1672.5 |  |  | 1676.5 |  |  | 1566 |  |  | 1605 |  |  | 1634.5 |  |  | 1550 |  |  | 1814.5 |  |  | 1649.5 |  |  | 1745.5 |  |  | 1737.5 |  |  | 1634.5 |  |  | 1695.5 |  |  | 1647.5 |  |  | 1691.5 |  |  | 1674 |  |  | 1644.5 |  |  | 1810.5 |  |  | 1710.5 |  |  | 1557 |  |  | 1647.5 |  |  | 1606.5 |  |  | 1713 |  |  | 1567 |  |  | 1704.5 |  |  | 1600 |  |  | 1534 |  |  | 1562.5 |  |  | 1675 |  |  | 1759.5 |  |  | 1742.5 |  |  | 1706.5 |  |  | 1649.5 |  |  | 1557.5 |  |  | 1638.5 |  |  | 1525.5 |  |  | 1632.5 |  |  | 1706.5 |  |  | 1619.5 |  |  | 1563 |  |  | 1558 |  |  | 1734.5 |  |  | 1652.5 |  |  | 1623.5 |  |  | 1703.5 |  |  | 1588.5 |  |  | 1652.5 |  |  | 1731.5 |  |  | 1614.5 |  |  | 1816 |  |  | 1586.5 |  |  | 1623 |  |  | 1619.5 |  |  | 1826.5 |  |  | 1687.5 |  |  | 1705 |  |  | 1647.5 |  |  | 1589.5 |  |  | 1601 |  |  | 1692.5 |  |  | 1637.5 |  |  | 1720.5 |  |  | 1690.5 |  |  | 1604.5 |  |  | 1648.5 |  |  | 1646 |  |  | 1581.5 |  |  | 1579.5 |  |  | 1701.5 |  |  | 1775.5 |  |  | 1602 |  |  | 1632.5 |  |  | 1752.5 |  |  | 1605 |  |  | 1712.5 |  |  | 1691.5 |  |  | 1651 |  |  | 1707.5 |  |  | 1747.5 |  |  | 1650.5 |  |  | 1615 |  |  | 1534.5 |  |  | 1660.5 |  |  | 1651 |  |  | 1664.5 |  |  | 1756.5 |  |  | 1694.5 |  |  | 1494.5 |  |  | 1777.5 |  |  | 1794.5 |  |  | 1568.5 |  |  | 1678 |  |  | 1622 |  |  | 1518.5 |  |  | 1684.5 |  |  | 1586.5 |  |  | 1632 |  |  | 1781.5 |  |  | 1621.5 |  |  | 1615.5 |  |  | 1498.5 |  |  | 1599.5 |  |  | 1633.5 |  |  | 1598.5 |  |  | 1674.5 |  |  | 1526.5 |  |  | 1678 |  |  | 1603.5 |  |  | 1597.5 |  |  | 1661.5 |  |  | 1753.5 |  |  | 1690.5 |  |  | 1658.5 |  |  | 1673.5 |  |  | 1712.5 |  |  | 1569.5 |  |  | 1746.5 |  |  | 1650.5 |  |  | 1647.5 |  |  | 1715.5 |  |  | 1751 |  |  | 1675.5 |  |  | 1733.5 |  |  | 1607 |  |  | 1724.5 |  |  | 1683.5 |  |  | 1751 |  |  | 1667.5 |  |  | 1762.5 |  |  | 1770.5 |  |  | 1783 |  |  | 1672.5 |  |  | 1713.5 |  |  | 1632.5 |  |  | 1503.5 |  |  | 1636.5 |  |  | 1539 |  |  | 1654.5 |  |  | 1665 |  |  | 1666 |  |  | 1782.5 |  |  | 1681.5 |  |  | 1586.5 |  |  | 1519.5 |  |  | 1680.5 |  |  | 1651.5 |  |  | 1648 |  |  | 1656.5 |  |  | 1648 |  |  | 1626.5 |  |  | 1669 |  |  | 1630 |  |  | 1729 |  |  | 1695.5 |  |  | 1601 |  |  | 1739.5 |  |  | 1744.5 |  |  | 1693.5 |  |  | 1801.5 |  |  | 1668.5 |  |  | 1728 |  |  | 1690.5 |  |  | 1707.5 |  |  | 1844.5 |  |  | 1683 |  |  | 1663.5 |  |  | 1588.5 |  |  | 1679.5 |  |  | 1726.5 |  |  | 1631 |  |  | 1683 |  |  | 1650 |  |  | 1669.5 |  |  | 1691 |  |  | 1746 |  |  | 1735.5 |  |  | 1631.5 |  |  | 1542.5 |  |  | 1711.5 |  |  | 1701.5 |  |  | 1770.5 |  |  | 1745.5 |  |  | 1657.5 |  |  | 1592.5 |  |  | 1591 |  |  | 1660.5 |  |  | 1644 |  |  | 1687.5 |  |  | 1709.5 |  |  | 1658.5 |  |  | 1743.5 |  |  | 1734 |  |  | 1685.5 |  |  | 1656 |  |  | 1600.5 |  |  | 1692.5 |  |  | 1598 |  |  | 1679 |  |  | 1662.5 |  |  | 1647 |  |  | 1722.5 |  |  | 1549.5 |  |  | 1631.5 |  |  | 1630.5 |  |  | 1640.5 |  |  | 1702.5 |  |  | 1557.5 |  |  | 1551 |  |  | 1721.5 |  |  | 1666.5 |  |  | 1621.5 |  |  | 1658.5 |  |  | 1551.5 |  |  | 1617.5 |  |  | 1739.5 |  |  | 1678.5 |  |  | 1774.5 |  |  | 1711.5 |  |  | 1581.5 |  |  | 1569.5 |  |  | 1711 |  |  | 1518.5 |  |  | 1586.5 |  |  | 1692 |  |  | 1569.5 |  |  | 1555.5 |  |  | 1633.5 |  |  | 1617.5 |  |  | 1747 |  |  | 1833.5 |  |  | 1672.5 |  |  | 1565.5 |  |  | 1704.5 |  |  | 1636 |  |  | 1611.5 |  |  | 1730.5 |  |  | 1707.5 |  |  | 1728.5 |  |  | 1622.5 |  |  | 1574.5 |  |  | 1729.5 |  |  | 1778.5 |  |  | 1648.5 |  |  | 1634.5 |  |  | 1762.5 |  |  | 1651 |  |  | 1690.5 |  |  | 1666.5 |  |  | 1724.5 |  |  | 1703.5 |  |  | 1609.5 |  |  | 1629.5 |  |  | 1713 |  |  | 1624.5 |  |  | 1610 |  |  | 1580.5 |  |  | 1723.5 |  |  | 1676.5 |  |  | 1622 |  |  | 1600 |  |  | 1614.5 |  |  | 1711.5 |  |  | 1501.5 |  |  | 1725.5 |  |  | 1598.5 |  |  | 1671.5 |  |  | 1605.5 |  |  | 1629.5 |  |  | 1632.5 |  |  | 1715.5 |  |  | 1616.5 |  |  | 1680.5 |  |  | 1581.5 |  |  | 1748.5 |  |  | 1699.5 |  |  | 1647.5 |  |  | 1595.5 |  |  | 1660.5 |  |  | 1615.5 |  |  | 1643.5 |  |  | 1665.5 |  |  | 1713.5 |  |  | 1672 |  |  | 1729.5 |  |  | 1634.5 |  |  | 1652.5 |  |  | 1678 |  |  | 1712.5 |  |  | 1655.5 |  |  | 1689.5 |  |  | 1651.5 |  |  | 1692 |  |  | 1535.5 |  |  | 1532.5 |  |  | 1542 |  |  | 1645 |  |  | 1710 |  |  | 1590.5 |  |  | 1642.5 |  |  | 1677.5 |  |  | 1796.5 |  |  | 1677 |  |  | 1670.5 |  |  | 1706.5 |  |  | 1554 |  |  | 1603 |  |  | 1695.5 |  |  | 1613.5 |  |  | 1682 |  |  | 1618.5 |  |  | 1717 |  |  | 1580.5 |  |  | 1549.5 |  |  | 1698 |  |  | 1733.5 |  |  | 1631.5 |  |  | 1528.5 |  |  | 1762 |  |  | 1637.5 |  |  | 1582.5 |  |  | 1572.5 |  |  | 1624.5 |  |  | 1662.5 |  |  | 1792.5 |  |  | 1566.5 |  |  | 1657.5 |  |  | 1686.5 |  |  | 1657.5 |  |  | 1684 |  |  | 1653.5 |  |  | 1646.5 |  |  | 1682.5 |  |  | 1723.5 |  |  | 1641.5 |  |  | 1757.5 |  |  | 1729.5 |  |  | 1658.5 |  |  | 1777 |  |  | 1643.5 |  |  | 1642 |  |  | 1712.5 |  |  | 1806.5 |  |  | 1794.5 |  |  | 1587.5 |  |  | 1644.5 |  |  | 1601.5 |  |  | 1507.5 |  |  | 1730.5 |  |  | 1756 |  |  | 1618.5 |  |  | 1655 |  |  | 1581.5 |  |  | 1526.5 |  |  | 1666.5 |  |  | 1720 |  |  | 1643.5 |  |  | 1702.5 |  |  | 1507 |  |  | 1624.5 |  |  | 1642 |  |  | 1642.5 |  |  | 1644.5 |  |  | 1602.5 |  |  | 1643 |  |  | 1704.5 |  |  | 1818.5 |  |  | 1605 |  |  | 1771.5 |  |  | 1560.5 |  |  | 1707 |  |  | 1671.5 |  |  | 1790.5 |  |  | 1750.5 |  |  | 1754.5 |  |  | 1526.5 |  |  | 1743.5 |  |  | 1619.5 |  |  | 1606.5 |  |  | 1538.5 |  |  | 1649.5 |  |  | 1817.5 |  |  | 1719 |  |  | 1695 |  |  | 1724.5 |  |  | 1687.5 |  |  | 1716
58 |  | 1664.5 |  |  | 1809.5 |  |  | 1661 |  |  | 1661.5 |  |  | 1817.5 |  |  | 1705.5 |  |  | 1756.5 |  |  | 1728.5 |  |  | 1720.5 |  |  | 1691.5 |  |  | 1609 |  |  | 1776.5 |  |  | 1786.5 |  |  | 1611.5 |  |  | 1631 |  |  | 1748.5 |  |  | 1818.5 |  |  | 1697.5 |  |  | 1858.5 |  |  | 1640.5 |  |  | 1678.5 |  |  | 1712.5 |  |  | 1716.5 |  |  | 1613.5 |  |  | 1551 |  |  | 1754.5 |  |  | 1654.5 |  |  | 1712.5 |  |  | 1761.5 |  |  | 1610 |  |  | 1717 |  |  | 1656.5 |  |  | 1612.5 |  |  | 1756.5 |  |  | 1567.5 |  |  | 1706 |  |  | 1648.5 |  |  | 1761 |  |  | 1691.5 |  |  | 1692.5 |  |  | 1615.5 |  |  | 1781.5 |  |  | 1609.5 |  |  | 1672 |  |  | 1856.5 |  |  | 1761 |  |  | 1673.5 |  |  | 1819.5 |  |  | 1721.5 |  |  | 1651.5 |  |  | 1665.5 |  |  | 1721.5 |  |  | 1693.5 |  |  | 1636.5 |  |  | 1772.5 |  |  | 1699.5 |  |  | 1599.5 |  |  | 1711 |  |  | 1746.5 |  |  | 1667.5 |  |  | 1662 |  |  | 1693.5 |  |  | 1764.5 |  |  | 1652.5 |  |  | 1604.5 |  |  | 1691 |  |  | 1728.5 |  |  | 1640 |  |  | 1603.5 |  |  | 1731.5 |  |  | 1681 |  |  | 1669.5 |  |  | 1701.5 |  |  | 1815.5 |  |  | 1768 |  |  | 1748 |  |  | 1610.5 |  |  | 1650.5 |  |  | 1540.5 |  |  | 1668.5 |  |  | 1634 |  |  | 1695.5 |  |  | 1736.5 |  |  | 1762.5 |  |  | 1755.5 |  |  | 1706.5 |  |  | 1737.5 |  |  | 1646.5 |  |  | 1640.5 |  |  | 1744.5 |  |  | 1727.5 |  |  | 1734 |  |  | 1570.5 |  |  | 1615 |  |  | 1668 |  |  | 1628 |  |  | 1779.5 |  |  | 1781.5 |  |  | 1601.5 |  |  | 1728.5 |  |  | 1684.5 |  |  | 1689 |  |  | 1668 |  |  | 1639.5 |  |  | 1702.5 |  |  | 1661.5 |  |  | 1766.5 |  |  | 1781.5 |  |  | 1770.5 |  |  | 1753.5 |  |  | 1855.5 |  |  | 1760.5 |  |  | 1727.5 |  |  | 1699.5 |  |  | 1661.5 |  |  | 1766.5 |  |  | 1799.5 |  |  | 1554.5 |  |  | 1740.5 |  |  | 1711.5 |  |  | 1746.5 |  |  | 1743.5 |  |  | 1642.5 |  |  | 1680.5 |  |  | 1729.5 |  |  | 1719 |  |  | 1659.5 |  |  | 1692.5 |  |  | 1650.5 |  |  | 1631.5 |  |  | 1807.5 |  |  | 1760 |  |  | 1626.5 |  |  | 1757.5 |  |  | 1598.5 |  |  | 1707.5 |  |  | 1754 |  |  | 1668.5 |  |  | 1724.5 |  |  | 1698 |  |  | 1719.5 |  |  | 1672 |  |  | 1700 |  |  | 1800.5 |  |  | 1709 |  |  | 1790.5 |  |  | 1684.5 |  |  | 1775.5 |  |  | 1627.5 |  |  | 1762.5 |  |  | 1700.5 |  |  | 1709.5 |  |  | 1730.5 |  |  | 1863.5 |  |  | 1726.5 |  |  | 1794 |  |  | 1686.5 |  |  | 1579 |  |  | 1660.5 |  |  | 1742.5 |  |  | 1683 |  |  | 1677.5 |  |  | 1704.5 |  |  | 1668.5 |  |  | 1650 |  |  | 1713.5 |  |  | 1588.5 |  |  | 1622.5 |  |  | 1793.5 |  |  | 1605.5 |  |  | 1635.5 |  |  | 1678 |  |  | 1675.5 |  |  | 1716.5 |  |  | 1656.5 |  |  | 1698.5 |  |  | 1717.5 |  |  | 1686.5 |  |  | 1588.5 |  |  | 1776 |  |  | 1765.5 |  |  | 1711.5 |  |  | 1763.5 |  |  | 1719.5 |  |  | 1619.5 |  |  | 1806.5 |  |  | 1778.5 |  |  | 1705.5 |  |  | 1742.5 |  |  | 1614.5 |  |  | 1687.5 |  |  | 1597.5 |  |  | 1544.5 |  |  | 1648 |  |  | 1635.5 |  |  | 1718.5 |  |  | 1676.5 |  |  | 1751.5 |  |  | 1700.5 |  |  | 1727.5 |  |  | 1783.5 |  |  | 1679.5 |  |  | 1743.5 |  |  | 1636.5 |  |  | 1652.5 |  |  | 1798.5 |  |  | 1660.5 |  |  | 1631.5 |  |  | 1682.5 |  |  | 1727.5 |  |  | 1773 |  |  | 1715.5 |  |  | 1681.5 |  |  | 1558 |  |  | 1854.5 |  |  | 1727 |  |  | 1656.5 |  |  | 1769.5 |  |  | 1798.5 |  |  | 1752.5 |  |  | 1610.5 |  |  | 1655.5 |  |  | 1681.5 |  |  | 1538.5 |  |  | 1638 |  |  | 1599.5 |  |  | 1553.5 |  |  | 1776.5 |  |  | 1632.5 |  |  | 1713 |  |  | 1604.5 |  |  | 1712.5 |  |  | 1756.5 |  |  | 1769.5 |  |  | 1787.5 |  |  | 1641.5 |  |  | 1686.5 |  |  | 1777.5 |  |  | 1714 |  |  | 1687 |  |  | 1633.5 |  |  | 1698.5 |  |  | 1665.5 |  |  | 1711 |  |  | 1786.5 |  |  | 1701.5 |  |  | 1622.5 |  |  | 1652 |  |  | 1711.5 |  |  | 1759.5 |  |  | 1635.5 |  |  | 1667.5 |  |  | 1719.5 |  |  | 1713.5 |  |  | 1708.5 |  |  | 1704.5 |  |  | 1817.5 |  |  | 1515 |  |  | 1602.5 |  |  | 1721.5 |  |  | 1694.5 |  |  | 1620.5 |  |  | 1667.5 |  |  | 1762 |  |  | 1666.5 |  |  | 1761.5 |  |  | 1725 |  |  | 1839.5 |  |  | 1744.5 |  |  | 1823 |  |  | 1699.5 |  |  | 1676.5 |  |  | 1813.5 |  |  | 1622.5 |  |  | 1693 |  |  | 1674 |  |  | 1702.5 |  |  | 1659.5 |  |  | 1718.5 |  |  | 1740.5 |  |  | 1790.5 |  |  | 1637.5 |  |  | 1690 |  |  | 1716.5 |  |  | 1706.5 |  |  | 1701 |  |  | 1633.5 |  |  | 1560.5 |  |  | 1731 |  |  | 1655.5 |  |  | 1625.5 |  |  | 1716.5 |  |  | 1694 |  |  | 1740.5 |  |  | 1675 |  |  | 1705.5 |  |  | 1590.5 |  |  | 1725.5 |  |  | 1661 |  |  | 1637.5 |  |  | 1802.5 |  |  | 1692.5 |  |  | 1693 |  |  | 1584.5 |  |  | 1591.5 |  |  | 1852.5 |  |  | 1805.5 |  |  | 1679.5 |  |  | 1698 |  |  | 1599.5 |  |  | 1817.5 |  |  | 1812.5 |  |  | 1626 |  |  | 1693 |  |  | 1816.5 |  |  | 1639.5 |  |  | 1601.5 |  |  | 1686.5 |  |  | 1720.5 |  |  | 1705.5 |  |  | 1671.5 |  |  | 1700.5 |  |  | 1644.5 |  |  | 1693.5 |  |  | 1693 |  |  | 1688.5 |  |  | 1762.5 |  |  | 1898.5 |  |  | 1764.5 |  |  | 1738 |  |  | 1714.5 |  |  | 1726.5 |  |  | 1710.5 |  |  | 1536.5 |  |  | 1799.5 |  |  | 1628 |  |  | 1671 |  |  | 1606 |  |  | 1785 |  |  | 1629.5 |  |  | 1719 |  |  | 1701.5 |  |  | 1627 |  |  | 1704.5 |  |  | 1817.5 |  |  | 1708.5 |  |  | 1683.5 |  |  | 1628.5 |  |  | 1697 |  |  | 1700.5 |  |  | 1750.5 |  |  | 1605.5 |  |  | 1754 |  |  | 1719.5 |  |  | 1622.5 |  |  | 1670.5 |  |  | 1752 |  |  | 1686.5 |  |  | 1587.5 |  |  | 1733.5 |  |  | 1614.5 |  |  | 1676.5 |  |  | 1644.5 |  |  | 1775.5 |  |  | 1650.5 |  |  | 1785.5 |  |  | 1579.5 |  |  | 1584 |  |  | 1666.5 |  |  | 1675.5 |  |  | 1649.5 |  |  | 1689.5 |  |  | 1812.5 |  |  | 1654 |  |  | 1745.5 |  |  | 1756 |  |  | 1666 |  |  | 1671.5 |  |  | 1832.5 |  |  | 1632.5 |  |  | 1589 |  |  | 1707.5 |  |  | 1731.5 |  |  | 1736.5 |  |  | 1558 |  |  | 1700.5 |  |  | 1541.5 |  |  | 1709.5 |  |  | 1623.5 |  |  | 1642.5 |  |  | 1646 |  |  | 1670.5 |  |  | 1712 |  |  | 1673.5 |  |  | 1613.5 |  |  | 1695.5 |  |  | 1774 |  |  | 1609.5 |  |  | 1711 |  |  | 1714 |  |  | 1679.5 |  |  | 1633.5 |  |  | 1670.5 |  |  | 1783.5 |  |  | 1759 |  |  | 1751.5 |  |  | 1663.5 |  |  | 1543.5 |  |  | 1661 |  |  | 1776.5 |  |  | 1618.5 |  |  | 1562.5 |  |  | 1676.5 |  |  | 1743 |  |  | 1537.5 |  |  | 1687.5 |  |  | 1747.5 |  |  | 1684.5 |  |  | 1662.5 |  |  | 1671.5 |  |  | 1756 |  |  | 1649.5 |  |  | 1609.5 |  |  | 1721 |  |  | 1611.5 |  |  | 1560.5 |  |  | 1656.5 |  |  | 1672 |  |  | 1725.5 |  |  | 1686.5 |  |  | 1690.5 |  |  | 1690.5 |  |  | 1782.5 |  |  | 1750 |  |  | 1719 |  |  | 1651.5 |  |  | 1711.5 |  |  | 1734.5 |  |  | 1598.5 |  |  | 1580 |  |  | 1754 |  |  | 1599 |  |  | 1711.5 |  |  | 1668 |  |  | 1680.5 |  |  | 1777.5 |  |  | 1686 |  |  | 1643.5 |  |  | 1752.5 |  |  | 1690.5 |  |  | 1831.5 |  |  | 1537.5 |  |  | 1694 |  |  | 1770 |  |  | 1558.5 |  |  | 1729.5 |  |  | 1667 |  |  | 1577.5 |  |  | 1741.5 |  |  | 1674 |  |  | 1793.5 |  |  | 1798.5 |  |  | 1600 |  |  | 1747.5 |  |  | 1702.5 |  |  | 1672 |  |  | 1731.5 |  |  | 1658 |  |  | 1855.5 |  |  | 1850 |  |  | 1625.5 |  |  | 1688.5 |  |  | 1764.5 |  |  | 1678.5 |  |  | 1721.5 |  |  | 1657.5 |  |  | 1725 |  |  | 1639.5 |  |  | 1683.5 |  |  | 1638.5 |  |  | 1704.5 |  |  | 1676.5 |  |  | 1691 |  |  | 1635.5 |  |  | 1717 |  |  | 1728.5 |  |  | 1614.5 |  |  | 1751.5 |  |  | 1646.5 |  |  | 1622.5 |  |  | 1727.5 |  |  | 1633.5 |  |  | 1805.5 |  |  | 1634.5 |  |  | 1697 |  |  | 1715.5 |  |  | 1605 |  |  | 1703 |  |  | 1703.5 |  |  | 1598 |  |  | 1595.5 |  |  | 1699.5 |  |  | 1761.5 |  |  | 1687.5 |  |  | 1720.5 |  |  | 1826.5 |  |  | 1760.5 |  |  | 1672 |  |  | 1756 |  |  | 1595.5 |  |  | 1547.5 |  |  | 1705 |  |  | 1634.5 |  |  | 1699.5 |  |  | 1627.5 |  |  | 1646.5 |  |  | 1609.5 |  |  | 1622 |  |  | 1667.5 |  |  | 1689.5 |  |  | 1608.5 |  |  | 1608 |  |  | 1740.5 |  |  | 1705.5 |  |  | 1725.5 |  |  | 1840.5 |  |  | 1770.5 |  |  | 1632.5 |  |  | 1802.5 |  |  | 1442.5 |  |  | 1714.5 |  |  | 1591 |  |  | 1787.5 |  |  | 1662.5 |  |  | 1797.5 |  |  | 1571.5 |  |  | 1644.5 |  |  | 1630.5 |  |  | 1609.5 |  |  | 1527 |  |  | 1579.5 |  |  | 1750.5 |  |  | 1765.5 |  |  | 1600 |  |  | 1667.5 |  |  | 1616 |  |  | 1611.5 |  |  | 1714.5 |  |  | 1652.5 |  |  | 1700 |  |  | 1619.5 |  |  | 1703 |  |  | 1714 |  |  | 1723.5 |  |  | 1683 |  |  | 1753 |  |  | 1777.5 |  |  | 1707.5 |  |  | 1594.5 |  |  | 1751 |  |  | 1758.5 |  |  | 1652.5 |  |  | 1558.5 |  |  | 1740.5 |  |  | 1655.5 |  |  | 1651.5 |  |  | 1623.5 |  |  | 1737.5 |  |  | 1625 |  |  | 1811.5 |  |  | 1626 |  |  | 1646.5 |  |  | 1596.5 |  |  | 1790.5 |  |  | 1695 |  |  | 1734 |  |  | 1804 |  |  | 1700.5 |  |  | 1689 |  |  | 1750.5 |  |  | 1821.5 |  |  | 1666.5 |  |  | 1678.5 |  |  | 1627.5 |  |  | 1747.5 |  |  | 1733.5 |  |  | 1713.5 |  |  | 1717 |  |  | 1581.5 |  |  | 1564.5 |  |  | 1740.5 |  |  | 1614.5 |  |  | 1612 |  |  | 1655.5 |  |  | 1703 |  |  | 1675.5 |  |  | 1705.5 |  |  | 1640.5 |  |  | 1648.5 |  |  | 1562 |  |  | 1631.5 |  |  | 1503 |  |  | 1637.5 |  |  | 1773.5 |  |  | 1819.5 |  |  | 1764.5 |  |  | 1693.5 |  |  | 1695.5 |  |  | 1545.5 |  |  | 1744.5 |  |  | 1658.5 |  |  | 1649 |  |  | 1694.5 |  |  | 1649.5 |  |  | 1627.5 |  |  | 1711.5 |  |  | 1723.5 |  |  | 1613 |  |  | 1644 |  |  | 1658.5 |  |  | 1574 |  |  | 1835.5 |  |  | 1688.5 |  |  | 1792.5 |  |  | 1784.5 |  |  | 1655.5 |  |  | 1734.5 |  |  | 1673.5 |  |  | 1720.5 |  |  | 1721 |  |  | 1670.5 |  |  | 1834.5 |  |  | 1736.5 |  |  | 1572 |  |  | 1686.5 |  |  | 1653.5 |  |  | 1739 |  |  | 1588 |  |  | 1725.5 |  |  | 1624 |  |  | 1560 |  |  | 1591.5 |  |  | 1704 |  |  | 1806.5 |  |  | 1757.5 |  |  | 1745.5 |  |  | 1670.5 |  |  | 1572.5 |  |  | 1662.5 |  |  | 1554.5 |  |  | 1653.5 |  |  | 1735.5 |  |  | 1666.5 |  |  | 1589 |  |  | 1584 |  |  | 1760.5 |  |  | 1673.5 |  |  | 1662.5 |  |  | 1742.5 |  |  | 1603.5 |  |  | 1673.5 |  |  | 1752.5 |  |  | 1653.5 |  |  | 1855 |  |  | 1610.5 |  |  | 1644 |  |  | 1643.5 |  |  | 1841.5 |  |  | 1734.5 |  |  | 1734 |  |  | 1662.5 |  |  | 1628.5 |  |  | 1640 |  |  | 1731.5 |  |  | 1663.5 |  |  | 1746.5 |  |  | 1719.5 |  |  | 1619.5 |  |  | 1663.5 |  |  | 1675 |  |  | 1620.5 |  |  | 1594.5 |  |  | 1748.5 |  |  | 1801.5 |  |  | 1641 |  |  | 1671.5 |  |  | 1767.5 |  |  | 1626 |  |  | 1741.5 |  |  | 1730.5 |  |  | 1672 |  |  | 1746.5 |  |  | 1771.5 |  |  | 1665.5 |  |  | 1639 |  |  | 1573.5 |  |  | 1675.5 |  |  | 1698 |  |  | 1688.5 |  |  | 1771.5 |  |  | 1718.5 |  |  | 1533.5 |  |  | 1801.5 |  |  | 1820.5 |  |  | 1607.5 |  |  | 1693 |  |  | 1669 |  |  | 1533.5 |  |  | 1723.5 |  |  | 1601.5 |  |  | 1658 |  |  | 1820.5 |  |  | 1660.5 |  |  | 1639.5 |  |  | 1545.5 |  |  | 1638.5 |  |  | 1659.5 |  |  | 1637.5 |  |  | 1721.5 |  |  | 1552.5 |  |  | 1717 |  |  | 1618.5 |  |  | 1636.5 |  |  | 1676.5 |  |  | 1779.5 |  |  | 1737.5 |  |  | 1697.5 |  |  | 1702.5 |  |  | 1751.5 |  |  | 1608.5 |  |  | 1785.5 |  |  | 1679.5 |  |  | 1673.5 |  |  | 1762.5 |  |  | 1798 |  |  | 1704.5 |  |  | 1772.5 |  |  | 1636 |  |  | 1748.5 |  |  | 1707.5 |  |  | 1766 |  |  | 1688.5 |  |  | 1788.5 |  |  | 1785.5 |  |  | 1812 |  |  | 1701.5 |  |  | 1742.5 |  |  | 1658.5 |  |  | 1518.5 |  |  | 1662.5 |  |  | 1568 |  |  | 1680.5 |  |  | 1704 |  |  | 1705 |  |  | 1808.5 |  |  | 1720.5 |  |  | 1625.5 |  |  | 1534.5 |  |  | 1695.5 |  |  | 1666.5 |  |  | 1687 |  |  | 1685.5 |  |  | 1669 |  |  | 1641.5 |  |  | 1693 |  |  | 1669 |  |  | 1753 |  |  | 1716.5 |  |  | 1616 |  |  | 1786.5 |  |  | 1768.5 |  |  | 1719.5 |  |  | 1840.5 |  |  | 1715.5 |  |  | 1767 |  |  | 1737.5 |  |  | 1728.5 |  |  | 1883.5 |  |  | 1704 |  |  | 1710.5 |  |  | 1614.5 |  |  | 1703.5 |  |  | 1741.5 |  |  | 1646 |  |  | 1712 |  |  | 1674 |  |  | 1708.5 |  |  | 1720 |  |  | 1793 |  |  | 1761.5 |  |  | 1670.5 |  |  | 1557.5 |  |  | 1732.5 |  |  | 1748.5 |  |  | 1785.5 |  |  | 1792.5 |  |  | 1672.5 |  |  | 1616.5 |  |  | 1615 |  |  | 1686.5 |  |  | 1670 |  |  | 1708.5 |  |  | 1724.5 |  |  | 1687.5 |  |  | 1758.5 |  |  | 1773 |  |  | 1724.5 |  |  | 1695 |  |  | 1626.5 |  |  | 1731.5 |  |  | 1637 |  |  | 1705 |  |  | 1677.5 |  |  | 1686 |  |  | 1761.5 |  |  | 1578.5 |  |  | 1660.5 |  |  | 1654.5 |  |  | 1679.5 |  |  | 1726.5 |  |  | 1581.5 |  |  | 1590 |  |  | 1745.5 |  |  | 1687.5 |  |  | 1660.5 |  |  | 1697.5 |  |  | 1572.5 |  |  | 1646.5 |  |  | 1786.5 |  |  | 1699.5 |  |  | 1795.5 |  |  | 1737.5 |  |  | 1620.5 |  |  | 1608.5 |  |  | 1735 |  |  | 1565.5 |  |  | 1625.5 |  |  | 1739 |  |  | 1608.5 |  |  | 1581.5 |  |  | 1648.5 |  |  | 1638.5 |  |  | 1762 |  |  | 1872.5 |  |  | 1693.5 |  |  | 1604.5 |  |  | 1751.5 |  |  | 1683 |  |  | 1637.5 |  |  | 1759.5 |  |  | 1733.5 |  |  | 1767.5 |  |  | 1637.5 |  |  | 1600.5 |  |  | 1750.5 |  |  | 1793.5 |  |  | 1695.5 |  |  | 1649.5 |  |  | 1791.5 |  |  | 1677 |  |  | 1711.5 |  |  | 1705.5 |  |  | 1771.5 |  |  | 1732.5 |  |  | 1633.5 |  |  | 1644.5 |  |  | 1739 |  |  | 1663.5 |  |  | 1634 |  |  | 1604.5 |  |  | 1738.5 |  |  | 1700.5 |  |  | 1661 |  |  | 1639 |  |  | 1653.5 |  |  | 1740.5 |  |  | 1525.5 |  |  | 1740.5 |  |  | 1637.5 |  |  | 1686.5 |  |  | 1634.5 |  |  | 1668.5 |  |  | 1658.5 |  |  | 1739.5 |  |  | 1637.5 |  |  | 1719.5 |  |  | 1620.5 |  |  | 1774.5 |  |  | 1714.5 |  |  | 1686.5 |  |  | 1634.5 |  |  | 1699.5 |  |  | 1636.5 |  |  | 1672.5 |  |  | 1694.5 |  |  | 1742.5 |  |  | 1698 |  |  | 1768.5 |  |  | 1660.5 |  |  | 1699.5 |  |  | 1699 |  |  | 1751.5 |  |  | 1679.5 |  |  | 1704.5 |  |  | 1675.5 |  |  | 1739 |  |  | 1564.5 |  |  | 1561.5 |  |  | 1589 |  |  | 1674 |  |  | 1749 |  |  | 1629.5 |  |  | 1663.5 |  |  | 1698.5 |  |  | 1822.5 |  |  | 1698 |  |  | 1709.5 |  |  | 1727.5 |  |  | 1593 |  |  | 1624 |  |  | 1724.5 |  |  | 1660.5 |  |  | 1697 |  |  | 1639.5 |  |  | 1746 |  |  | 1619.5 |  |  | 1570.5 |  |  | 1745 |  |  | 1754.5 |  |  | 1670.5 |  |  | 1554.5 |  |  | 1801 |  |  | 1666.5 |  |  | 1621.5 |  |  | 1611.5 |  |  | 1663.5 |  |  | 1683.5 |  |  | 1807.5 |  |  | 1605.5 |  |  | 1686.5 |  |  | 1710.5 |  |  | 1681.5 |  |  | 1708 |  |  | 1692.5 |  |  | 1685.5 |  |  | 1711.5 |  |  | 1749.5 |  |  | 1680.5 |  |  | 1778.5 |  |  | 1768.5 |  |  | 1679.5 |  |  | 1824 |  |  | 1658.5 |  |  | 1681 |  |  | 1759.5 |  |  | 1845.5 |  |  | 1833.5 |  |  | 1608.5 |  |  | 1670.5 |  |  | 1625.5 |  |  | 1546.5 |  |  | 1759.5 |  |  | 1777 |  |  | 1633.5 |  |  | 1684 |  |  | 1620.5 |  |  | 1555.5 |  |  | 1705.5 |  |  | 1759 |  |  | 1682.5 |  |  | 1731.5 |  |  | 1546 |  |  | 1648.5 |  |  | 1663 |  |  | 1681.5 |  |  | 1665.5 |  |  | 1617.5 |  |  | 1658 |  |  | 1743.5 |  |  | 1842.5 |  |  | 1634 |  |  | 1810.5 |  |  | 1581.5 |  |  | 1722 |  |  | 1697.5 |  |  | 1829.5 |  |  | 1789.5 |  |  | 1793.5 |  |  | 1573.5 |  |  | 1782.5 |  |  | 1645.5 |  |  | 1645.5 |  |  | 1577.5 |  |  | 1664.5 |  |  | 1843.5 |  |  | 1758 |  |  | 1734 |  |  | 1750.5 |  |  | 1726.5 |  |  | 1745
59 |  | 1685.5 |  |  | 1848.5 |  |  | 1708 |  |  | 1676.5 |  |  | 1864.5 |  |  | 1720.5 |  |  | 1795.5 |  |  | 1767.5 |  |  | 1735.5 |  |  | 1712.5 |  |  | 1630 |  |  | 1800.5 |  |  | 1812.5 |  |  | 1635.5 |  |  | 1657 |  |  | 1763.5 |  |  | 1839.5 |  |  | 1736.5 |  |  | 1897.5 |  |  | 1664.5 |  |  | 1704.5 |  |  | 1751.5 |  |  | 1740.5 |  |  | 1652.5 |  |  | 1572 |  |  | 1778.5 |  |  | 1680.5 |  |  | 1751.5 |  |  | 1787.5 |  |  | 1636 |  |  | 1738 |  |  | 1695.5 |  |  | 1627.5 |  |  | 1795.5 |  |  | 1606.5 |  |  | 1745 |  |  | 1669.5 |  |  | 1790 |  |  | 1712.5 |  |  | 1716.5 |  |  | 1630.5 |  |  | 1820.5 |  |  | 1635.5 |  |  | 1687 |  |  | 1877.5 |  |  | 1790 |  |  | 1712.5 |  |  | 1840.5 |  |  | 1745.5 |  |  | 1677.5 |  |  | 1691.5 |  |  | 1742.5 |  |  | 1732.5 |  |  | 1657.5 |  |  | 1801.5 |  |  | 1714.5 |  |  | 1646.5 |  |  | 1737 |  |  | 1785.5 |  |  | 1688.5 |  |  | 1677 |  |  | 1732.5 |  |  | 1811.5 |  |  | 1681.5 |  |  | 1651.5 |  |  | 1717 |  |  | 1775.5 |  |  | 1679 |  |  | 1624.5 |  |  | 1752.5 |  |  | 1720 |  |  | 1716.5 |  |  | 1727.5 |  |  | 1854.5 |  |  | 1815 |  |  | 1795 |  |  | 1649.5 |  |  | 1674.5 |  |  | 1579.5 |  |  | 1707.5 |  |  | 1673 |  |  | 1710.5 |  |  | 1762.5 |  |  | 1809.5 |  |  | 1781.5 |  |  | 1727.5 |  |  | 1763.5 |  |  | 1670.5 |  |  | 1655.5 |  |  | 1791.5 |  |  | 1774.5 |  |  | 1773 |  |  | 1585.5 |  |  | 1630 |  |  | 1715 |  |  | 1652 |  |  | 1826.5 |  |  | 1807.5 |  |  | 1627.5 |  |  | 1775.5 |  |  | 1699.5 |  |  | 1715 |  |  | 1694 |  |  | 1668.5 |  |  | 1717.5 |  |  | 1682.5 |  |  | 1795.5 |  |  | 1820.5 |  |  | 1817.5 |  |  | 1774.5 |  |  | 1876.5 |  |  | 1807.5 |  |  | 1748.5 |  |  | 1738.5 |  |  | 1687.5 |  |  | 1781.5 |  |  | 1820.5 |  |  | 1593.5 |  |  | 1761.5 |  |  | 1737.5 |  |  | 1775.5 |  |  | 1764.5 |  |  | 1668.5 |  |  | 1719.5 |  |  | 1776.5 |  |  | 1748 |  |  | 1674.5 |  |  | 1739.5 |  |  | 1676.5 |  |  | 1670.5 |  |  | 1828.5 |  |  | 1784 |  |  | 1641.5 |  |  | 1772.5 |  |  | 1627.5 |  |  | 1754.5 |  |  | 1769 |  |  | 1707.5 |  |  | 1745.5 |  |  | 1722 |  |  | 1766.5 |  |  | 1711 |  |  | 1747 |  |  | 1821.5 |  |  | 1724 |  |  | 1816.5 |  |  | 1708.5 |  |  | 1790.5 |  |  | 1666.5 |  |  | 1801.5 |  |  | 1747.5 |  |  | 1735.5 |  |  | 1777.5 |  |  | 1902.5 |  |  | 1765.5 |  |  | 1823 |  |  | 1701.5 |  |  | 1603 |  |  | 1675.5 |  |  | 1781.5 |  |  | 1709 |  |  | 1724.5 |  |  | 1730.5 |  |  | 1692.5 |  |  | 1674 |  |  | 1728.5 |  |  | 1614.5 |  |  | 1648.5 |  |  | 1808.5 |  |  | 1629.5 |  |  | 1664.5 |  |  | 1702 |  |  | 1701.5 |  |  | 1763.5 |  |  | 1695.5 |  |  | 1713.5 |  |  | 1746.5 |  |  | 1701.5 |  |  | 1603.5 |  |  | 1815 |  |  | 1812.5 |  |  | 1758.5 |  |  | 1784.5 |  |  | 1758.5 |  |  | 1648.5 |  |  | 1830.5 |  |  | 1807.5 |  |  | 1720.5 |  |  | 1789.5 |  |  | 1640.5 |  |  | 1711.5 |  |  | 1636.5 |  |  | 1583.5 |  |  | 1663 |  |  | 1682.5 |  |  | 1742.5 |  |  | 1691.5 |  |  | 1766.5 |  |  | 1715.5 |  |  | 1751.5 |  |  | 1807.5 |  |  | 1708.5 |  |  | 1764.5 |  |  | 1660.5 |  |  | 1681.5 |  |  | 1837.5 |  |  | 1689.5 |  |  | 1678.5 |  |  | 1721.5 |  |  | 1774.5 |  |  | 1797 |  |  | 1739.5 |  |  | 1720.5 |  |  | 1584 |  |  | 1869.5 |  |  | 1774 |  |  | 1671.5 |  |  | 1793.5 |  |  | 1845.5 |  |  | 1791.5 |  |  | 1649.5 |  |  | 1702.5 |  |  | 1696.5 |  |  | 1562.5 |  |  | 1653 |  |  | 1628.5 |  |  | 1577.5 |  |  | 1791.5 |  |  | 1658.5 |  |  | 1752 |  |  | 1643.5 |  |  | 1738.5 |  |  | 1785.5 |  |  | 1793.5 |  |  | 1811.5 |  |  | 1667.5 |  |  | 1712.5 |  |  | 1816.5 |  |  | 1753 |  |  | 1734 |  |  | 1654.5 |  |  | 1727.5 |  |  | 1686.5 |  |  | 1732 |  |  | 1815.5 |  |  | 1716.5 |  |  | 1637.5 |  |  | 1678 |  |  | 1750.5 |  |  | 1788.5 |  |  | 1656.5 |  |  | 1696.5 |  |  | 1740.5 |  |  | 1752.5 |  |  | 1729.5 |  |  | 1728.5 |  |  | 1841.5 |  |  | 1554 |  |  | 1626.5 |  |  | 1760.5 |  |  | 1709.5 |  |  | 1644.5 |  |  | 1714.5 |  |  | 1791 |  |  | 1690.5 |  |  | 1800.5 |  |  | 1746 |  |  | 1854.5 |  |  | 1765.5 |  |  | 1838 |  |  | 1725.5 |  |  | 1705.5 |  |  | 1852.5 |  |  | 1661.5 |  |  | 1732 |  |  | 1700 |  |  | 1741.5 |  |  | 1706.5 |  |  | 1757.5 |  |  | 1764.5 |  |  | 1829.5 |  |  | 1684.5 |  |  | 1714 |  |  | 1745.5 |  |  | 1735.5 |  |  | 1740 |  |  | 1672.5 |  |  | 1589.5 |  |  | 1770 |  |  | 1702.5 |  |  | 1654.5 |  |  | 1755.5 |  |  | 1709 |  |  | 1766.5 |  |  | 1699 |  |  | 1744.5 |  |  | 1616.5 |  |  | 1764.5 |  |  | 1700 |  |  | 1666.5 |  |  | 1841.5 |  |  | 1731.5 |  |  | 1732 |  |  | 1623.5 |  |  | 1606.5 |  |  | 1881.5 |  |  | 1826.5 |  |  | 1726.5 |  |  | 1724 |  |  | 1625.5 |  |  | 1841.5 |  |  | 1851.5 |  |  | 1647 |  |  | 1708 |  |  | 1855.5 |  |  | 1668.5 |  |  | 1630.5 |  |  | 1725.5 |  |  | 1759.5 |  |  | 1720.5 |  |  | 1695.5 |  |  | 1726.5 |  |  | 1665.5 |  |  | 1732.5 |  |  | 1722 |  |  | 1735.5 |  |  | 1791.5 |  |  | 1913.5 |  |  | 1803.5 |  |  | 1764 |  |  | 1743.5 |  |  | 1765.5 |  |  | 1725.5 |  |  | 1565.5 |  |  | 1814.5 |  |  | 1667 |  |  | 1695 |  |  | 1653 |  |  | 1824 |  |  | 1653.5 |  |  | 1740 |  |  | 1740.5 |  |  | 1666 |  |  | 1733.5 |  |  | 1864.5 |  |  | 1755.5 |  |  | 1707.5 |  |  | 1652.5 |  |  | 1736 |  |  | 1724.5 |  |  | 1789.5 |  |  | 1644.5 |  |  | 1778 |  |  | 1758.5 |  |  | 1643.5 |  |  | 1691.5 |  |  | 1781 |  |  | 1712.5 |  |  | 1613.5 |  |  | 1762.5 |  |  | 1638.5 |  |  | 1697.5 |  |  | 1665.5 |  |  | 1796.5 |  |  | 1689.5 |  |  | 1800.5 |  |  | 1608.5 |  |  | 1610 |  |  | 1690.5 |  |  | 1690.5 |  |  | 1675.5 |  |  | 1718.5 |  |  | 1836.5 |  |  | 1675 |  |  | 1769.5 |  |  | 1795 |  |  | 1681 |  |  | 1697.5 |  |  | 1856.5 |  |  | 1661.5 |  |  | 1636 |  |  | 1722.5 |  |  | 1770.5 |  |  | 1775.5 |  |  | 1605 |  |  | 1726.5 |  |  | 1588.5 |  |  | 1738.5 |  |  | 1638.5 |  |  | 1681.5 |  |  | 1685 |  |  | 1717.5 |  |  | 1759 |  |  | 1694.5 |  |  | 1639.5 |  |  | 1734.5 |  |  | 1798 |  |  | 1633.5 |  |  | 1726 |  |  | 1738 |  |  | 1700.5 |  |  | 1672.5 |  |  | 1699.5 |  |  | 1809.5 |  |  | 1798 |  |  | 1777.5 |  |  | 1678.5 |  |  | 1558.5 |  |  | 1690 |  |  | 1800.5 |  |  | 1639.5 |  |  | 1577.5 |  |  | 1723.5 |  |  | 1790 |  |  | 1584.5 |  |  | 1711.5 |  |  | 1786.5 |  |  | 1713.5 |  |  | 1709.5 |  |  | 1710.5 |  |  | 1795 |  |  | 1696.5 |  |  | 1648.5 |  |  | 1736 |  |  | 1650.5 |  |  | 1589.5 |  |  | 1671.5 |  |  | 1696 |  |  | 1764.5 |  |  | 1733.5 |  |  | 1716.5 |  |  | 1729.5 |  |  | 1806.5 |  |  | 1765 |  |  | 1734 |  |  | 1690.5 |  |  | 1732.5 |  |  | 1773.5 |  |  | 1613.5 |  |  | 1619 |  |  | 1778 |  |  | 1623 |  |  | 1737.5 |  |  | 1715 |  |  | 1709.5 |  |  | 1816.5 |  |  | 1710 |  |  | 1672.5 |  |  | 1791.5 |  |  | 1714.5 |  |  | 1852.5 |  |  | 1563.5 |  |  | 1709 |  |  | 1809 |  |  | 1587.5 |  |  | 1768.5 |  |  | 1682 |  |  | 1603.5 |  |  | 1756.5 |  |  | 1700 |  |  | 1822.5 |  |  | 1837.5 |  |  | 1621 |  |  | 1771.5 |  |  | 1723.5 |  |  | 1719 |  |  | 1746.5 |  |  | 1687 |  |  | 1881.5 |  |  | 1874 |  |  | 1654.5 |  |  | 1709.5 |  |  | 1788.5 |  |  | 1702.5 |  |  | 1747.5 |  |  | 1681.5 |  |  | 1740 |  |  | 1663.5 |  |  | 1709.5 |  |  | 1664.5 |  |  | 1730.5 |  |  | 1702.5 |  |  | 1706 |  |  | 1656.5 |  |  | 1764 |  |  | 1743.5 |  |  | 1638.5 |  |  | 1790.5 |  |  | 1670.5 |  |  | 1669.5 |  |  | 1774.5 |  |  | 1654.5 |  |  | 1844.5 |  |  | 1649.5 |  |  | 1721 |  |  | 1736.5 |  |  | 1634 |  |  | 1729 |  |  | 1718.5 |  |  | 1613 |  |  | 1610.5 |  |  | 1746.5 |  |  | 1808.5 |  |  | 1726.5 |  |  | 1746.5 |  |  | 1865.5 |  |  | 1781.5 |  |  | 1711 |  |  | 1795 |  |  | 1624.5 |  |  | 1594.5 |  |  | 1720 |  |  | 1655.5 |  |  | 1738.5 |  |  | 1648.5 |  |  | 1685.5 |  |  | 1656.5 |  |  | 1643 |  |  | 1693.5 |  |  | 1736.5 |  |  | 1647.5 |  |  | 1637 |  |  | 1761.5 |  |  | 1729.5 |  |  | 1740.5 |  |  | 1879.5 |  |  | 1785.5 |  |  | 1647.5 |  |  | 1826.5 |  |  | 1457.5 |  |  | 1729.5 |  |  | 1630 |  |  | 1826.5 |  |  | 1701.5 |  |  | 1823.5 |  |  | 1597.5 |  |  | 1665.5 |  |  | 1656.5 |  |  | 1656.5 |  |  | 1553 |  |  | 1608.5 |  |  | 1771.5 |  |  | 1812.5 |  |  | 1647 |  |  | 1696.5 |  |  | 1637 |  |  | 1640.5 |  |  | 1740.5 |  |  | 1673.5 |  |  | 1747 |  |  | 1640.5 |  |  | 1729 |  |  | 1735 |  |  | 1744.5 |  |  | 1709 |  |  | 1774 |  |  | 1806.5 |  |  | 1728.5 |  |  | 1623.5 |  |  | 1766 |  |  | 1784.5 |  |  | 1699.5 |  |  | 1605.5 |  |  | 1787.5 |  |  | 1676.5 |  |  | 1698.5 |  |  | 1652.5 |  |  | 1776.5 |  |  | 1672 |  |  | 1840.5 |  |  | 1665 |  |  | 1685.5 |  |  | 1643.5 |  |  | 1805.5 |  |  | 1710 |  |  | 1781 |  |  | 1833 |  |  | 1739.5 |  |  | 1710 |  |  | 1776.5 |  |  | 1850.5 |  |  | 1695.5 |  |  | 1702.5 |  |  | 1648.5 |  |  | 1794.5 |  |  | 1780.5 |  |  | 1734.5 |  |  | 1756 |  |  | 1596.5 |  |  | 1579.5 |  |  | 1779.5 |  |  | 1638.5 |  |  | 1651 |  |  | 1670.5 |  |  | 1729 |  |  | 1722.5 |  |  | 1752.5 |  |  | 1679.5 |  |  | 1674.5 |  |  | 1586 |  |  | 1652.5 |  |  | 1550 |  |  | 1652.5 |  |  | 1794.5 |  |  | 1848.5 |  |  | 1788.5 |  |  | 1740.5 |  |  | 1734.5 |  |  | 1574.5 |  |  | 1783.5 |  |  | 1705.5 |  |  | 1688 |  |  | 1733.5 |  |  | 1675.5 |  |  | 1666.5 |  |  | 1735.5 |  |  | 1744.5 |  |  | 1637 |  |  | 1665 |  |  | 1705.5 |  |  | 1613 |  |  | 1864.5 |  |  | 1712.5 |  |  | 1818.5 |  |  | 1823.5 |  |  | 1694.5 |  |  | 1760.5 |  |  | 1688.5 |  |  | 1767.5 |  |  | 1768 |  |  | 1709.5 |  |  | 1881.5 |  |  | 1760.5 |  |  | 1611 |  |  | 1712.5 |  |  | 1674.5 |  |  | 1765 |  |  | 1614 |  |  | 1772.5 |  |  | 1653 |  |  | 1581 |  |  | 1606.5 |  |  | 1725 |  |  | 1845.5 |  |  | 1772.5 |  |  | 1784.5 |  |  | 1717.5 |  |  | 1611.5 |  |  | 1683.5 |  |  | 1593.5 |  |  | 1692.5 |  |  | 1764.5 |  |  | 1692.5 |  |  | 1613 |  |  | 1610 |  |  | 1799.5 |  |  | 1720.5 |  |  | 1701.5 |  |  | 1771.5 |  |  | 1632.5 |  |  | 1712.5 |  |  | 1799.5 |  |  | 1682.5 |  |  | 1876 |  |  | 1625.5 |  |  | 1691 |  |  | 1667.5 |  |  | 1880.5 |  |  | 1749.5 |  |  | 1760 |  |  | 1701.5 |  |  | 1667.5 |  |  | 1669 |  |  | 1755.5 |  |  | 1684.5 |  |  | 1793.5 |  |  | 1734.5 |  |  | 1645.5 |  |  | 1702.5 |  |  | 1722 |  |  | 1644.5 |  |  | 1633.5 |  |  | 1772.5 |  |  | 1827.5 |  |  | 1680 |  |  | 1697.5 |  |  | 1791.5 |  |  | 1650 |  |  | 1770.5 |  |  | 1769.5 |  |  | 1719 |  |  | 1785.5 |  |  | 1792.5 |  |  | 1689.5 |  |  | 1678 |  |  | 1612.5 |  |  | 1722.5 |  |  | 1737 |  |  | 1703.5 |  |  | 1800.5 |  |  | 1742.5 |  |  | 1572.5 |  |  | 1825.5 |  |  | 1846.5 |  |  | 1646.5 |  |  | 1714 |  |  | 1690 |  |  | 1580.5 |  |  | 1752.5 |  |  | 1630.5 |  |  | 1697 |  |  | 1859.5 |  |  | 1681.5 |  |  | 1663.5 |  |  | 1566.5 |  |  | 1659.5 |  |  | 1698.5 |  |  | 1661.5 |  |  | 1760.5 |  |  | 1576.5 |  |  | 1746 |  |  | 1657.5 |  |  | 1660.5 |  |  | 1691.5 |  |  | 1805.5 |  |  | 1784.5 |  |  | 1718.5 |  |  | 1728.5 |  |  | 1777.5 |  |  | 1647.5 |  |  | 1824.5 |  |  | 1708.5 |  |  | 1694.5 |  |  | 1783.5 |  |  | 1822 |  |  | 1733.5 |  |  | 1793.5 |  |  | 1675 |  |  | 1777.5 |  |  | 1736.5 |  |  | 1790 |  |  | 1703.5 |  |  | 1817.5 |  |  | 1824.5 |  |  | 1838 |  |  | 1730.5 |  |  | 1781.5 |  |  | 1697.5 |  |  | 1557.5 |  |  | 1701.5 |  |  | 1607 |  |  | 1709.5 |  |  | 1730 |  |  | 1744 |  |  | 1855.5 |  |  | 1759.5 |  |  | 1646.5 |  |  | 1555.5 |  |  | 1710.5 |  |  | 1690.5 |  |  | 1702 |  |  | 1709.5 |  |  | 1690 |  |  | 1667.5 |  |  | 1732 |  |  | 1708 |  |  | 1800 |  |  | 1755.5 |  |  | 1655 |  |  | 1825.5 |  |  | 1789.5 |  |  | 1734.5 |  |  | 1861.5 |  |  | 1754.5 |  |  | 1806 |  |  | 1776.5 |  |  | 1767.5 |  |  | 1904.5 |  |  | 1725 |  |  | 1725.5 |  |  | 1643.5 |  |  | 1718.5 |  |  | 1762.5 |  |  | 1661 |  |  | 1751 |  |  | 1713 |  |  | 1729.5 |  |  | 1759 |  |  | 1817 |  |  | 1800.5 |  |  | 1709.5 |  |  | 1596.5 |  |  | 1756.5 |  |  | 1772.5 |  |  | 1806.5 |  |  | 1813.5 |  |  | 1711.5 |  |  | 1640.5 |  |  | 1641 |  |  | 1710.5 |  |  | 1694 |  |  | 1755.5 |  |  | 1748.5 |  |  | 1726.5 |  |  | 1797.5 |  |  | 1788 |  |  | 1763.5 |  |  | 1716 |  |  | 1665.5 |  |  | 1760.5 |  |  | 1684 |  |  | 1731 |  |  | 1716.5 |  |  | 1715 |  |  | 1800.5 |  |  | 1604.5 |  |  | 1699.5 |  |  | 1678.5 |  |  | 1718.5 |  |  | 1765.5 |  |  | 1620.5 |  |  | 1611 |  |  | 1774.5 |  |  | 1734.5 |  |  | 1675.5 |  |  | 1744.5 |  |  | 1611.5 |  |  | 1661.5 |  |  | 1801.5 |  |  | 1746.5 |  |  | 1842.5 |  |  | 1758.5 |  |  | 1635.5 |  |  | 1647.5 |  |  | 1782 |  |  | 1604.5 |  |  | 1651.5 |  |  | 1760 |  |  | 1632.5 |  |  | 1620.5 |  |  | 1687.5 |  |  | 1653.5 |  |  | 1786 |  |  | 1911.5 |  |  | 1708.5 |  |  | 1633.5 |  |  | 1780.5 |  |  | 1707 |  |  | 1684.5 |  |  | 1788.5 |  |  | 1748.5 |  |  | 1793.5 |  |  | 1676.5 |  |  | 1626.5 |  |  | 1765.5 |  |  | 1822.5 |  |  | 1724.5 |  |  | 1688.5 |  |  | 1815.5 |  |  | 1716 |  |  | 1740.5 |  |  | 1731.5 |  |  | 1818.5 |  |  | 1761.5 |  |  | 1657.5 |  |  | 1683.5 |  |  | 1763 |  |  | 1702.5 |  |  | 1673 |  |  | 1619.5 |  |  | 1785.5 |  |  | 1715.5 |  |  | 1676 |  |  | 1678 |  |  | 1668.5 |  |  | 1755.5 |  |  | 1564.5 |  |  | 1761.5 |  |  | 1676.5 |  |  | 1733.5 |  |  | 1681.5 |  |  | 1715.5 |  |  | 1682.5 |  |  | 1786.5 |  |  | 1684.5 |  |  | 1745.5 |  |  | 1644.5 |  |  | 1789.5 |  |  | 1753.5 |  |  | 1725.5 |  |  | 1681.5 |  |  | 1720.5 |  |  | 1651.5 |  |  | 1696.5 |  |  | 1718.5 |  |  | 1766.5 |  |  | 1727 |  |  | 1797.5 |  |  | 1699.5 |  |  | 1725.5 |  |  | 1728 |  |  | 1766.5 |  |  | 1705.5 |  |  | 1743.5 |  |  | 1714.5 |  |  | 1760 |  |  | 1603.5 |  |  | 1582.5 |  |  | 1610 |  |  | 1703 |  |  | 1778 |  |  | 1668.5 |  |  | 1702.5 |  |  | 1713.5 |  |  | 1869.5 |  |  | 1737 |  |  | 1748.5 |  |  | 1756.5 |  |  | 1617 |  |  | 1671 |  |  | 1763.5 |  |  | 1686.5 |  |  | 1736 |  |  | 1665.5 |  |  | 1772 |  |  | 1658.5 |  |  | 1599.5 |  |  | 1792 |  |  | 1783.5 |  |  | 1709.5 |  |  | 1575.5 |  |  | 1830 |  |  | 1690.5 |  |  | 1647.5 |  |  | 1640.5 |  |  | 1692.5 |  |  | 1709.5 |  |  | 1822.5 |  |  | 1644.5 |  |  | 1712.5 |  |  | 1739.5 |  |  | 1705.5 |  |  | 1737 |  |  | 1718.5 |  |  | 1724.5 |  |  | 1750.5 |  |  | 1796.5 |  |  | 1727.5 |  |  | 1804.5 |  |  | 1789.5 |  |  | 1705.5 |  |  | 1850 |  |  | 1684.5 |  |  | 1720 |  |  | 1806.5 |  |  | 1884.5 |  |  | 1872.5 |  |  | 1634.5 |  |  | 1694.5 |  |  | 1649.5 |  |  | 1585.5 |  |  | 1780.5 |  |  | 1803 |  |  | 1662.5 |  |  | 1723 |  |  | 1646.5 |  |  | 1570.5 |  |  | 1752.5 |  |  | 1798 |  |  | 1706.5 |  |  | 1770.5 |  |  | 1575 |  |  | 1669.5 |  |  | 1692 |  |  | 1696.5 |  |  | 1686.5 |  |  | 1656.5 |  |  | 1705 |  |  | 1782.5 |  |  | 1863.5 |  |  | 1660 |  |  | 1834.5 |  |  | 1605.5 |  |  | 1761 |  |  | 1718.5 |  |  | 1868.5 |  |  | 1804.5 |  |  | 1819.5 |  |  | 1612.5 |  |  | 1811.5 |  |  | 1671.5 |  |  | 1692.5 |  |  | 1603.5 |  |  | 1703.5 |  |  | 1882.5 |  |  | 1797 |  |  | 1781 |  |  | 1797.5 |  |  | 1741.5 |  |  | 1792
60 |  | 1706.5 |  |  | 1887.5 |  |  | 1737 |  |  | 1691.5 |  |  | 1903.5 |  |  | 1744.5 |  |  | 1834.5 |  |  | 1788.5 |  |  | 1774.5 |  |  | 1741.5 |  |  | 1677 |  |  | 1824.5 |  |  | 1836.5 |  |  | 1659.5 |  |  | 1672 |  |  | 1792.5 |  |  | 1863.5 |  |  | 1775.5 |  |  | 1921.5 |  |  | 1679.5 |  |  | 1725.5 |  |  | 1777.5 |  |  | 1755.5 |  |  | 1691.5 |  |  | 1611 |  |  | 1802.5 |  |  | 1719.5 |  |  | 1766.5 |  |  | 1808.5 |  |  | 1683 |  |  | 1753 |  |  | 1742.5 |  |  | 1651.5 |  |  | 1821.5 |  |  | 1645.5 |  |  | 1766 |  |  | 1708.5 |  |  | 1811 |  |  | 1741.5 |  |  | 1745.5 |  |  | 1651.5 |  |  | 1849.5 |  |  | 1650.5 |  |  | 1734 |  |  | 1924.5 |  |  | 1819 |  |  | 1736.5 |  |  | 1864.5 |  |  | 1766.5 |  |  | 1716.5 |  |  | 1715.5 |  |  | 1757.5 |  |  | 1753.5 |  |  | 1672.5 |  |  | 1840.5 |  |  | 1743.5 |  |  | 1672.5 |  |  | 1763 |  |  | 1800.5 |  |  | 1727.5 |  |  | 1716 |  |  | 1747.5 |  |  | 1850.5 |  |  | 1696.5 |  |  | 1680.5 |  |  | 1741 |  |  | 1822.5 |  |  | 1718 |  |  | 1645.5 |  |  | 1791.5 |  |  | 1746 |  |  | 1755.5 |  |  | 1751.5 |  |  | 1893.5 |  |  | 1841 |  |  | 1834 |  |  | 1688.5 |  |  | 1703.5 |  |  | 1618.5 |  |  | 1754.5 |  |  | 1694 |  |  | 1739.5 |  |  | 1801.5 |  |  | 1848.5 |  |  | 1810.5 |  |  | 1742.5 |  |  | 1802.5 |  |  | 1717.5 |  |  | 1694.5 |  |  | 1812.5 |  |  | 1813.5 |  |  | 1799 |  |  | 1606.5 |  |  | 1656 |  |  | 1754 |  |  | 1673 |  |  | 1873.5 |  |  | 1836.5 |  |  | 1653.5 |  |  | 1790.5 |  |  | 1720.5 |  |  | 1739 |  |  | 1733 |  |  | 1683.5 |  |  | 1741.5 |  |  | 1708.5 |  |  | 1810.5 |  |  | 1859.5 |  |  | 1864.5 |  |  | 1813.5 |  |  | 1900.5 |  |  | 1822.5 |  |  | 1772.5 |  |  | 1762.5 |  |  | 1726.5 |  |  | 1820.5 |  |  | 1841.5 |  |  | 1619.5 |  |  | 1800.5 |  |  | 1752.5 |  |  | 1814.5 |  |  | 1785.5 |  |  | 1707.5 |  |  | 1740.5 |  |  | 1815.5 |  |  | 1769 |  |  | 1721.5 |  |  | 1754.5 |  |  | 1700.5 |  |  | 1709.5 |  |  | 1849.5 |  |  | 1799 |  |  | 1656.5 |  |  | 1796.5 |  |  | 1653.5 |  |  | 1775.5 |  |  | 1790 |  |  | 1736.5 |  |  | 1774.5 |  |  | 1748 |  |  | 1795.5 |  |  | 1732 |  |  | 1794 |  |  | 1847.5 |  |  | 1763 |  |  | 1855.5 |  |  | 1729.5 |  |  | 1811.5 |  |  | 1695.5 |  |  | 1840.5 |  |  | 1768.5 |  |  | 1750.5 |  |  | 1798.5 |  |  | 1931.5 |  |  | 1791.5 |  |  | 1849 |  |  | 1740.5 |  |  | 1632 |  |  | 1722.5 |  |  | 1796.5 |  |  | 1730 |  |  | 1753.5 |  |  | 1756.5 |  |  | 1713.5 |  |  | 1698 |  |  | 1775.5 |  |  | 1653.5 |  |  | 1687.5 |  |  | 1832.5 |  |  | 1676.5 |  |  | 1703.5 |  |  | 1726 |  |  | 1740.5 |  |  | 1784.5 |  |  | 1721.5 |  |  | 1739.5 |  |  | 1793.5 |  |  | 1748.5 |  |  | 1642.5 |  |  | 1836 |  |  | 1833.5 |  |  | 1787.5 |  |  | 1813.5 |  |  | 1797.5 |  |  | 1663.5 |  |  | 1869.5 |  |  | 1846.5 |  |  | 1759.5 |  |  | 1804.5 |  |  | 1661.5 |  |  | 1750.5 |  |  | 1657.5 |  |  | 1598.5 |  |  | 1692 |  |  | 1697.5 |  |  | 1766.5 |  |  | 1738.5 |  |  | 1790.5 |  |  | 1736.5 |  |  | 1790.5 |  |  | 1846.5 |  |  | 1755.5 |  |  | 1811.5 |  |  | 1675.5 |  |  | 1720.5 |  |  | 1852.5 |  |  | 1715.5 |  |  | 1707.5 |  |  | 1747.5 |  |  | 1795.5 |  |  | 1823 |  |  | 1778.5 |  |  | 1741.5 |  |  | 1599 |  |  | 1884.5 |  |  | 1789 |  |  | 1686.5 |  |  | 1817.5 |  |  | 1892.5 |  |  | 1815.5 |  |  | 1688.5 |  |  | 1749.5 |  |  | 1725.5 |  |  | 1586.5 |  |  | 1692 |  |  | 1667.5 |  |  | 1603.5 |  |  | 1830.5 |  |  | 1705.5 |  |  | 1791 |  |  | 1667.5 |  |  | 1777.5 |  |  | 1800.5 |  |  | 1814.5 |  |  | 1840.5 |  |  | 1714.5 |  |  | 1751.5 |  |  | 1855.5 |  |  | 1792 |  |  | 1755 |  |  | 1693.5 |  |  | 1756.5 |  |  | 1715.5 |  |  | 1761 |  |  | 1836.5 |  |  | 1740.5 |  |  | 1661.5 |  |  | 1702 |  |  | 1774.5 |  |  | 1814.5 |  |  | 1671.5 |  |  | 1722.5 |  |  | 1766.5 |  |  | 1799.5 |  |  | 1768.5 |  |  | 1767.5 |  |  | 1880.5 |  |  | 1583 |  |  | 1673.5 |  |  | 1784.5 |  |  | 1748.5 |  |  | 1665.5 |  |  | 1729.5 |  |  | 1838 |  |  | 1737.5 |  |  | 1815.5 |  |  | 1775 |  |  | 1893.5 |  |  | 1794.5 |  |  | 1885 |  |  | 1764.5 |  |  | 1726.5 |  |  | 1891.5 |  |  | 1676.5 |  |  | 1779 |  |  | 1724 |  |  | 1780.5 |  |  | 1721.5 |  |  | 1804.5 |  |  | 1790.5 |  |  | 1868.5 |  |  | 1731.5 |  |  | 1735 |  |  | 1769.5 |  |  | 1782.5 |  |  | 1779 |  |  | 1711.5 |  |  | 1610.5 |  |  | 1817 |  |  | 1749.5 |  |  | 1669.5 |  |  | 1776.5 |  |  | 1748 |  |  | 1792.5 |  |  | 1725 |  |  | 1783.5 |  |  | 1655.5 |  |  | 1811.5 |  |  | 1726 |  |  | 1687.5 |  |  | 1880.5 |  |  | 1746.5 |  |  | 1758 |  |  | 1662.5 |  |  | 1627.5 |  |  | 1902.5 |  |  | 1841.5 |  |  | 1765.5 |  |  | 1763 |  |  | 1651.5 |  |  | 1867.5 |  |  | 1877.5 |  |  | 1676 |  |  | 1747 |  |  | 1870.5 |  |  | 1715.5 |  |  | 1669.5 |  |  | 1751.5 |  |  | 1780.5 |  |  | 1746.5 |  |  | 1742.5 |  |  | 1765.5 |  |  | 1686.5 |  |  | 1756.5 |  |  | 1761 |  |  | 1764.5 |  |  | 1806.5 |  |  | 1952.5 |  |  | 1818.5 |  |  | 1803 |  |  | 1758.5 |  |  | 1812.5 |  |  | 1754.5 |  |  | 1604.5 |  |  | 1840.5 |  |  | 1706 |  |  | 1734 |  |  | 1682 |  |  | 1850 |  |  | 1679.5 |  |  | 1764 |  |  | 1761.5 |  |  | 1705 |  |  | 1748.5 |  |  | 1885.5 |  |  | 1770.5 |  |  | 1754.5 |  |  | 1676.5 |  |  | 1783 |  |  | 1763.5 |  |  | 1836.5 |  |  | 1668.5 |  |  | 1804 |  |  | 1784.5 |  |  | 1664.5 |  |  | 1730.5 |  |  | 1796 |  |  | 1727.5 |  |  | 1642.5 |  |  | 1786.5 |  |  | 1677.5 |  |  | 1736.5 |  |  | 1689.5 |  |  | 1820.5 |  |  | 1710.5 |  |  | 1826.5 |  |  | 1655.5 |  |  | 1631 |  |  | 1716.5 |  |  | 1719.5 |  |  | 1696.5 |  |  | 1765.5 |  |  | 1875.5 |  |  | 1699 |  |  | 1795.5 |  |  | 1834 |  |  | 1705 |  |  | 1723.5 |  |  | 1880.5 |  |  | 1682.5 |  |  | 1675 |  |  | 1751.5 |  |  | 1796.5 |  |  | 1804.5 |  |  | 1629 |  |  | 1755.5 |  |  | 1612.5 |  |  | 1767.5 |  |  | 1685.5 |  |  | 1720.5 |  |  | 1732 |  |  | 1738.5 |  |  | 1783 |  |  | 1718.5 |  |  | 1665.5 |  |  | 1749.5 |  |  | 1837 |  |  | 1672.5 |  |  | 1747 |  |  | 1762 |  |  | 1715.5 |  |  | 1693.5 |  |  | 1725.5 |  |  | 1833.5 |  |  | 1837 |  |  | 1806.5 |  |  | 1704.5 |  |  | 1605.5 |  |  | 1714 |  |  | 1829.5 |  |  | 1686.5 |  |  | 1606.5 |  |  | 1749.5 |  |  | 1829 |  |  | 1623.5 |  |  | 1750.5 |  |  | 1825.5 |  |  | 1739.5 |  |  | 1738.5 |  |  | 1739.5 |  |  | 1842 |  |  | 1725.5 |  |  | 1663.5 |  |  | 1775 |  |  | 1665.5 |  |  | 1618.5 |  |  | 1710.5 |  |  | 1720 |  |  | 1779.5 |  |  | 1772.5 |  |  | 1755.5 |  |  | 1753.5 |  |  | 1835.5 |  |  | 1794 |  |  | 1755 |  |  | 1705.5 |  |  | 1756.5 |  |  | 1794.5 |  |  | 1634.5 |  |  | 1658 |  |  | 1817 |  |  | 1670 |  |  | 1776.5 |  |  | 1730 |  |  | 1756.5 |  |  | 1842.5 |  |  | 1739 |  |  | 1711.5 |  |  | 1812.5 |  |  | 1729.5 |  |  | 1878.5 |  |  | 1587.5 |  |  | 1748 |  |  | 1838 |  |  | 1616.5 |  |  | 1789.5 |  |  | 1729 |  |  | 1627.5 |  |  | 1785.5 |  |  | 1724 |  |  | 1869.5 |  |  | 1876.5 |  |  | 1668 |  |  | 1795.5 |  |  | 1749.5 |  |  | 1758 |  |  | 1785.5 |  |  | 1726 |  |  | 1896.5 |  |  | 1898 |  |  | 1701.5 |  |  | 1735.5 |  |  | 1809.5 |  |  | 1717.5 |  |  | 1771.5 |  |  | 1702.5 |  |  | 1787 |  |  | 1687.5 |  |  | 1735.5 |  |  | 1711.5 |  |  | 1745.5 |  |  | 1741.5 |  |  | 1745 |  |  | 1695.5 |  |  | 1793 |  |  | 1772.5 |  |  | 1667.5 |  |  | 1816.5 |  |  | 1696.5 |  |  | 1695.5 |  |  | 1803.5 |  |  | 1683.5 |  |  | 1870.5 |  |  | 1673.5 |  |  | 1736 |  |  | 1751.5 |  |  | 1658 |  |  | 1753 |  |  | 1733.5 |  |  | 1652 |  |  | 1625.5 |  |  | 1785.5 |  |  | 1837.5 |  |  | 1765.5 |  |  | 1767.5 |  |  | 1886.5 |  |  | 1805.5 |  |  | 1726 |  |  | 1842 |  |  | 1663.5 |  |  | 1641.5 |  |  | 1767 |  |  | 1694.5 |  |  | 1753.5 |  |  | 1687.5 |  |  | 1709.5 |  |  | 1685.5 |  |  | 1658 |  |  | 1717.5 |  |  | 1783.5 |  |  | 1671.5 |  |  | 1676 |  |  | 1800.5 |  |  | 1753.5 |  |  | 1779.5 |  |  | 1908.5 |  |  | 1811.5 |  |  | 1671.5 |  |  | 1855.5 |  |  | 1483.5 |  |  | 1750.5 |  |  | 1677 |  |  | 1841.5 |  |  | 1727.5 |  |  | 1844.5 |  |  | 1621.5 |  |  | 1712.5 |  |  | 1680.5 |  |  | 1685.5 |  |  | 1582 |  |  | 1647.5 |  |  | 1810.5 |  |  | 1841.5 |  |  | 1662 |  |  | 1735.5 |  |  | 1684 |  |  | 1661.5 |  |  | 1761.5 |  |  | 1720.5 |  |  | 1762 |  |  | 1666.5 |  |  | 1753 |  |  | 1774 |  |  | 1765.5 |  |  | 1748 |  |  | 1821 |  |  | 1835.5 |  |  | 1767.5 |  |  | 1638.5 |  |  | 1813 |  |  | 1813.5 |  |  | 1725.5 |  |  | 1644.5 |  |  | 1808.5 |  |  | 1697.5 |  |  | 1737.5 |  |  | 1691.5 |  |  | 1802.5 |  |  | 1711 |  |  | 1861.5 |  |  | 1686 |  |  | 1709.5 |  |  | 1682.5 |  |  | 1852.5 |  |  | 1736 |  |  | 1802 |  |  | 1880 |  |  | 1763.5 |  |  | 1736 |  |  | 1802.5 |  |  | 1874.5 |  |  | 1724.5 |  |  | 1731.5 |  |  | 1663.5 |  |  | 1823.5 |  |  | 1819.5 |  |  | 1773.5 |  |  | 1795 |  |  | 1635.5 |  |  | 1618.5 |  |  | 1805.5 |  |  | 1653.5 |  |  | 1680 |  |  | 1717.5 |  |  | 1768 |  |  | 1761.5 |  |  | 1767.5 |  |  | 1700.5 |  |  | 1698.5 |  |  | 1610 |  |  | 1673.5 |  |  | 1574 |  |  | 1691.5 |  |  | 1815.5 |  |  | 1872.5 |  |  | 1803.5 |  |  | 1755.5 |  |  | 1760.5 |  |  | 1613.5 |  |  | 1812.5 |  |  | 1744.5 |  |  | 1714 |  |  | 1772.5 |  |  | 1690.5 |  |  | 1692.5 |  |  | 1764.5 |  |  | 1783.5 |  |  | 1661 |  |  | 1712 |  |  | 1734.5 |  |  | 1652 |  |  | 1911.5 |  |  | 1733.5 |  |  | 1833.5 |  |  | 1838.5 |  |  | 1709.5 |  |  | 1775.5 |  |  | 1712.5 |  |  | 1782.5 |  |  | 1792 |  |  | 1748.5 |  |  | 1920.5 |  |  | 1781.5 |  |  | 1637 |  |  | 1733.5 |  |  | 1689.5 |  |  | 1780 |  |  | 1653 |  |  | 1787.5 |  |  | 1677 |  |  | 1602 |  |  | 1630.5 |  |  | 1764 |  |  | 1884.5 |  |  | 1798.5 |  |  | 1813.5 |  |  | 1756.5 |  |  | 1632.5 |  |  | 1704.5 |  |  | 1614.5 |  |  | 1718.5 |  |  | 1790.5 |  |  | 1713.5 |  |  | 1634 |  |  | 1649 |  |  | 1846.5 |  |  | 1759.5 |  |  | 1740.5 |  |  | 1810.5 |  |  | 1679.5 |  |  | 1751.5 |  |  | 1820.5 |  |  | 1708.5 |  |  | 1897 |  |  | 1654.5 |  |  | 1730 |  |  | 1688.5 |  |  | 1909.5 |  |  | 1775.5 |  |  | 1799 |  |  | 1725.5 |  |  | 1691.5 |  |  | 1708 |  |  | 1779.5 |  |  | 1708.5 |  |  | 1814.5 |  |  | 1760.5 |  |  | 1692.5 |  |  | 1741.5 |  |  | 1769 |  |  | 1683.5 |  |  | 1659.5 |  |  | 1811.5 |  |  | 1848.5 |  |  | 1719 |  |  | 1721.5 |  |  | 1838.5 |  |  | 1689 |  |  | 1796.5 |  |  | 1808.5 |  |  | 1745 |  |  | 1814.5 |  |  | 1831.5 |  |  | 1728.5 |  |  | 1693 |  |  | 1641.5 |  |  | 1748.5 |  |  | 1763 |  |  | 1724.5 |  |  | 1839.5 |  |  | 1768.5 |  |  | 1596.5 |  |  | 1840.5 |  |  | 1872.5 |  |  | 1693.5 |  |  | 1753 |  |  | 1714 |  |  | 1619.5 |  |  | 1799.5 |  |  | 1654.5 |  |  | 1744 |  |  | 1906.5 |  |  | 1702.5 |  |  | 1689.5 |  |  | 1605.5 |  |  | 1688.5 |  |  | 1724.5 |  |  | 1676.5 |  |  | 1799.5 |  |  | 1615.5 |  |  | 1770 |  |  | 1672.5 |  |  | 1707.5 |  |  | 1730.5 |  |  | 1834.5 |  |  | 1831.5 |  |  | 1744.5 |  |  | 1775.5 |  |  | 1792.5 |  |  | 1668.5 |  |  | 1845.5 |  |  | 1755.5 |  |  | 1709.5 |  |  | 1809.5 |  |  | 1846 |  |  | 1757.5 |  |  | 1832.5 |  |  | 1690 |  |  | 1798.5 |  |  | 1757.5 |  |  | 1805 |  |  | 1729.5 |  |  | 1856.5 |  |  | 1871.5 |  |  | 1877 |  |  | 1745.5 |  |  | 1807.5 |  |  | 1721.5 |  |  | 1572.5 |  |  | 1725.5 |  |  | 1622 |  |  | 1748.5 |  |  | 1751 |  |  | 1783 |  |  | 1881.5 |  |  | 1785.5 |  |  | 1685.5 |  |  | 1581.5 |  |  | 1749.5 |  |  | 1729.5 |  |  | 1741 |  |  | 1735.5 |  |  | 1729 |  |  | 1696.5 |  |  | 1756 |  |  | 1747 |  |  | 1839 |  |  | 1770.5 |  |  | 1702 |  |  | 1846.5 |  |  | 1836.5 |  |  | 1773.5 |  |  | 1887.5 |  |  | 1775.5 |  |  | 1835 |  |  | 1791.5 |  |  | 1782.5 |  |  | 1919.5 |  |  | 1764 |  |  | 1764.5 |  |  | 1664.5 |  |  | 1733.5 |  |  | 1801.5 |  |  | 1690 |  |  | 1777 |  |  | 1728 |  |  | 1758.5 |  |  | 1780 |  |  | 1864 |  |  | 1821.5 |  |  | 1724.5 |  |  | 1635.5 |  |  | 1777.5 |  |  | 1801.5 |  |  | 1835.5 |  |  | 1860.5 |  |  | 1735.5 |  |  | 1679.5 |  |  | 1688 |  |  | 1739.5 |  |  | 1733 |  |  | 1802.5 |  |  | 1787.5 |  |  | 1765.5 |  |  | 1836.5 |  |  | 1827 |  |  | 1802.5 |  |  | 1755 |  |  | 1689.5 |  |  | 1789.5 |  |  | 1731 |  |  | 1746 |  |  | 1755.5 |  |  | 1739 |  |  | 1824.5 |  |  | 1643.5 |  |  | 1720.5 |  |  | 1693.5 |  |  | 1757.5 |  |  | 1794.5 |  |  | 1646.5 |  |  | 1632 |  |  | 1795.5 |  |  | 1773.5 |  |  | 1699.5 |  |  | 1783.5 |  |  | 1658.5 |  |  | 1700.5 |  |  | 1830.5 |  |  | 1793.5 |  |  | 1866.5 |  |  | 1779.5 |  |  | 1661.5 |  |  | 1686.5 |  |  | 1803 |  |  | 1625.5 |  |  | 1690.5 |  |  | 1799 |  |  | 1661.5 |  |  | 1659.5 |  |  | 1702.5 |  |  | 1679.5 |  |  | 1833 |  |  | 1950.5 |  |  | 1729.5 |  |  | 1680.5 |  |  | 1801.5 |  |  | 1733 |  |  | 1723.5 |  |  | 1814.5 |  |  | 1774.5 |  |  | 1819.5 |  |  | 1700.5 |  |  | 1673.5 |  |  | 1789.5 |  |  | 1846.5 |  |  | 1750.5 |  |  | 1709.5 |  |  | 1839.5 |  |  | 1755 |  |  | 1755.5 |  |  | 1746.5 |  |  | 1857.5 |  |  | 1800.5 |  |  | 1683.5 |  |  | 1707.5 |  |  | 1802 |  |  | 1723.5 |  |  | 1712 |  |  | 1645.5 |  |  | 1811.5 |  |  | 1736.5 |  |  | 1715 |  |  | 1717 |  |  | 1707.5 |  |  | 1770.5 |  |  | 1585.5 |  |  | 1787.5 |  |  | 1715.5 |  |  | 1757.5 |  |  | 1707.5 |  |  | 1754.5 |  |  | 1721.5 |  |  | 1825.5 |  |  | 1713.5 |  |  | 1784.5 |  |  | 1673.5 |  |  | 1815.5 |  |  | 1792.5 |  |  | 1764.5 |  |  | 1720.5 |  |  | 1759.5 |  |  | 1677.5 |  |  | 1717.5 |  |  | 1757.5 |  |  | 1805.5 |  |  | 1756 |  |  | 1844.5 |  |  | 1725.5 |  |  | 1751.5 |  |  | 1767 |  |  | 1792.5 |  |  | 1744.5 |  |  | 1782.5 |  |  | 1743.5 |  |  | 1781 |  |  | 1642.5 |  |  | 1597.5 |  |  | 1649 |  |  | 1729 |  |  | 1804 |  |  | 1707.5 |  |  | 1723.5 |  |  | 1734.5 |  |  | 1898.5 |  |  | 1776 |  |  | 1795.5 |  |  | 1785.5 |  |  | 1632 |  |  | 1700 |  |  | 1802.5 |  |  | 1725.5 |  |  | 1760 |  |  | 1704.5 |  |  | 1811 |  |  | 1679.5 |  |  | 1646.5 |  |  | 1839 |  |  | 1812.5 |  |  | 1724.5 |  |  | 1596.5 |  |  | 1869 |  |  | 1705.5 |  |  | 1671.5 |  |  | 1679.5 |  |  | 1718.5 |  |  | 1738.5 |  |  | 1851.5 |  |  | 1683.5 |  |  | 1738.5 |  |  | 1765.5 |  |  | 1752.5 |  |  | 1758 |  |  | 1765.5 |  |  | 1771.5 |  |  | 1776.5 |  |  | 1817.5 |  |  | 1753.5 |  |  | 1843.5 |  |  | 1828.5 |  |  | 1752.5 |  |  | 1897 |  |  | 1705.5 |  |  | 1749 |  |  | 1853.5 |  |  | 1913.5 |  |  | 1911.5 |  |  | 1673.5 |  |  | 1718.5 |  |  | 1688.5 |  |  | 1609.5 |  |  | 1806.5 |  |  | 1818 |  |  | 1691.5 |  |  | 1762 |  |  | 1675.5 |  |  | 1617.5 |  |  | 1776.5 |  |  | 1845 |  |  | 1730.5 |  |  | 1817.5 |  |  | 1599 |  |  | 1708.5 |  |  | 1731 |  |  | 1735.5 |  |  | 1712.5 |  |  | 1682.5 |  |  | 1731 |  |  | 1803.5 |  |  | 1910.5 |  |  | 1681 |  |  | 1881.5 |  |  | 1629.5 |  |  | 1800 |  |  | 1757.5 |  |  | 1889.5 |  |  | 1819.5 |  |  | 1858.5 |  |  | 1636.5 |  |  | 1832.5 |  |  | 1695.5 |  |  | 1707.5 |  |  | 1642.5 |  |  | 1724.5 |  |  | 1921.5 |  |  | 1812 |  |  | 1828 |  |  | 1826.5 |  |  | 1765.5 |  |  | 1816
61 |  | 1721.5 |  |  | 1911.5 |  |  | 1776 |  |  | 1706.5 |  |  | 1929.5 |  |  | 1770.5 |  |  | 1849.5 |  |  | 1814.5 |  |  | 1795.5 |  |  | 1756.5 |  |  | 1716 |  |  | 1863.5 |  |  | 1865.5 |  |  | 1698.5 |  |  | 1698 |  |  | 1831.5 |  |  | 1884.5 |  |  | 1814.5 |  |  | 1950.5 |  |  | 1694.5 |  |  | 1764.5 |  |  | 1806.5 |  |  | 1802.5 |  |  | 1715.5 |  |  | 1640 |  |  | 1831.5 |  |  | 1758.5 |  |  | 1790.5 |  |  | 1855.5 |  |  | 1707 |  |  | 1779 |  |  | 1789.5 |  |  | 1672.5 |  |  | 1845.5 |  |  | 1666.5 |  |  | 1813 |  |  | 1723.5 |  |  | 1840 |  |  | 1770.5 |  |  | 1769.5 |  |  | 1675.5 |  |  | 1888.5 |  |  | 1665.5 |  |  | 1760 |  |  | 1971.5 |  |  | 1834 |  |  | 1760.5 |  |  | 1911.5 |  |  | 1805.5 |  |  | 1763.5 |  |  | 1741.5 |  |  | 1796.5 |  |  | 1792.5 |  |  | 1711.5 |  |  | 1879.5 |  |  | 1772.5 |  |  | 1711.5 |  |  | 1784 |  |  | 1815.5 |  |  | 1751.5 |  |  | 1755 |  |  | 1786.5 |  |  | 1897.5 |  |  | 1722.5 |  |  | 1719.5 |  |  | 1765 |  |  | 1861.5 |  |  | 1742 |  |  | 1666.5 |  |  | 1815.5 |  |  | 1770 |  |  | 1776.5 |  |  | 1772.5 |  |  | 1908.5 |  |  | 1870 |  |  | 1860 |  |  | 1735.5 |  |  | 1727.5 |  |  | 1665.5 |  |  | 1778.5 |  |  | 1720 |  |  | 1760.5 |  |  | 1816.5 |  |  | 1874.5 |  |  | 1825.5 |  |  | 1771.5 |  |  | 1841.5 |  |  | 1743.5 |  |  | 1733.5 |  |  | 1841.5 |  |  | 1852.5 |  |  | 1846 |  |  | 1630.5 |  |  | 1680 |  |  | 1775 |  |  | 1712 |  |  | 1897.5 |  |  | 1865.5 |  |  | 1692.5 |  |  | 1811.5 |  |  | 1767.5 |  |  | 1768 |  |  | 1772 |  |  | 1722.5 |  |  | 1762.5 |  |  | 1737.5 |  |  | 1825.5 |  |  | 1898.5 |  |  | 1888.5 |  |  | 1839.5 |  |  | 1929.5 |  |  | 1846.5 |  |  | 1811.5 |  |  | 1783.5 |  |  | 1755.5 |  |  | 1844.5 |  |  | 1880.5 |  |  | 1643.5 |  |  | 1821.5 |  |  | 1781.5 |  |  | 1829.5 |  |  | 1824.5 |  |  | 1754.5 |  |  | 1779.5 |  |  | 1839.5 |  |  | 1795 |  |  | 1750.5 |  |  | 1793.5 |  |  | 1739.5 |  |  | 1735.5 |  |  | 1864.5 |  |  | 1823 |  |  | 1685.5 |  |  | 1843.5 |  |  | 1682.5 |  |  | 1799.5 |  |  | 1837 |  |  | 1783.5 |  |  | 1813.5 |  |  | 1787 |  |  | 1819.5 |  |  | 1771 |  |  | 1833 |  |  | 1886.5 |  |  | 1802 |  |  | 1879.5 |  |  | 1758.5 |  |  | 1850.5 |  |  | 1724.5 |  |  | 1869.5 |  |  | 1815.5 |  |  | 1789.5 |  |  | 1837.5 |  |  | 1946.5 |  |  | 1817.5 |  |  | 1896 |  |  | 1769.5 |  |  | 1671 |  |  | 1761.5 |  |  | 1817.5 |  |  | 1777 |  |  | 1792.5 |  |  | 1771.5 |  |  | 1752.5 |  |  | 1719 |  |  | 1804.5 |  |  | 1682.5 |  |  | 1726.5 |  |  | 1879.5 |  |  | 1705.5 |  |  | 1750.5 |  |  | 1741 |  |  | 1766.5 |  |  | 1799.5 |  |  | 1742.5 |  |  | 1763.5 |  |  | 1822.5 |  |  | 1787.5 |  |  | 1689.5 |  |  | 1860 |  |  | 1872.5 |  |  | 1808.5 |  |  | 1837.5 |  |  | 1812.5 |  |  | 1687.5 |  |  | 1895.5 |  |  | 1867.5 |  |  | 1783.5 |  |  | 1833.5 |  |  | 1690.5 |  |  | 1789.5 |  |  | 1696.5 |  |  | 1622.5 |  |  | 1731 |  |  | 1723.5 |  |  | 1787.5 |  |  | 1764.5 |  |  | 1829.5 |  |  | 1783.5 |  |  | 1829.5 |  |  | 1872.5 |  |  | 1770.5 |  |  | 1840.5 |  |  | 1701.5 |  |  | 1767.5 |  |  | 1873.5 |  |  | 1754.5 |  |  | 1728.5 |  |  | 1786.5 |  |  | 1842.5 |  |  | 1847 |  |  | 1804.5 |  |  | 1756.5 |  |  | 1620 |  |  | 1905.5 |  |  | 1828 |  |  | 1701.5 |  |  | 1856.5 |  |  | 1921.5 |  |  | 1854.5 |  |  | 1727.5 |  |  | 1775.5 |  |  | 1746.5 |  |  | 1612.5 |  |  | 1716 |  |  | 1693.5 |  |  | 1629.5 |  |  | 1869.5 |  |  | 1720.5 |  |  | 1806 |  |  | 1706.5 |  |  | 1792.5 |  |  | 1829.5 |  |  | 1829.5 |  |  | 1879.5 |  |  | 1753.5 |  |  | 1772.5 |  |  | 1881.5 |  |  | 1831 |  |  | 1784 |  |  | 1740.5 |  |  | 1780.5 |  |  | 1739.5 |  |  | 1800 |  |  | 1875.5 |  |  | 1787.5 |  |  | 1700.5 |  |  | 1726 |  |  | 1795.5 |  |  | 1853.5 |  |  | 1686.5 |  |  | 1737.5 |  |  | 1795.5 |  |  | 1838.5 |  |  | 1797.5 |  |  | 1782.5 |  |  | 1909.5 |  |  | 1612 |  |  | 1712.5 |  |  | 1823.5 |  |  | 1787.5 |  |  | 1691.5 |  |  | 1750.5 |  |  | 1885 |  |  | 1761.5 |  |  | 1839.5 |  |  | 1814 |  |  | 1908.5 |  |  | 1820.5 |  |  | 1924 |  |  | 1785.5 |  |  | 1765.5 |  |  | 1915.5 |  |  | 1715.5 |  |  | 1794 |  |  | 1739 |  |  | 1795.5 |  |  | 1742.5 |  |  | 1828.5 |  |  | 1805.5 |  |  | 1894.5 |  |  | 1770.5 |  |  | 1764 |  |  | 1790.5 |  |  | 1829.5 |  |  | 1808 |  |  | 1740.5 |  |  | 1639.5 |  |  | 1846 |  |  | 1788.5 |  |  | 1698.5 |  |  | 1823.5 |  |  | 1763 |  |  | 1831.5 |  |  | 1749 |  |  | 1830.5 |  |  | 1684.5 |  |  | 1858.5 |  |  | 1750 |  |  | 1726.5 |  |  | 1906.5 |  |  | 1785.5 |  |  | 1797 |  |  | 1701.5 |  |  | 1651.5 |  |  | 1923.5 |  |  | 1880.5 |  |  | 1786.5 |  |  | 1802 |  |  | 1666.5 |  |  | 1891.5 |  |  | 1898.5 |  |  | 1723 |  |  | 1786 |  |  | 1891.5 |  |  | 1741.5 |  |  | 1695.5 |  |  | 1780.5 |  |  | 1804.5 |  |  | 1785.5 |  |  | 1781.5 |  |  | 1804.5 |  |  | 1712.5 |  |  | 1780.5 |  |  | 1785 |  |  | 1803.5 |  |  | 1821.5 |  |  | 1978.5 |  |  | 1833.5 |  |  | 1850 |  |  | 1784.5 |  |  | 1851.5 |  |  | 1778.5 |  |  | 1633.5 |  |  | 1866.5 |  |  | 1721 |  |  | 1773 |  |  | 1721 |  |  | 1889 |  |  | 1718.5 |  |  | 1803 |  |  | 1800.5 |  |  | 1752 |  |  | 1795.5 |  |  | 1932.5 |  |  | 1785.5 |  |  | 1778.5 |  |  | 1715.5 |  |  | 1822 |  |  | 1802.5 |  |  | 1883.5 |  |  | 1689.5 |  |  | 1819 |  |  | 1823.5 |  |  | 1679.5 |  |  | 1769.5 |  |  | 1835 |  |  | 1756.5 |  |  | 1681.5 |  |  | 1815.5 |  |  | 1716.5 |  |  | 1775.5 |  |  | 1736.5 |  |  | 1849.5 |  |  | 1736.5 |  |  | 1852.5 |  |  | 1670.5 |  |  | 1660 |  |  | 1763.5 |  |  | 1745.5 |  |  | 1711.5 |  |  | 1812.5 |  |  | 1922.5 |  |  | 1720 |  |  | 1816.5 |  |  | 1881 |  |  | 1729 |  |  | 1762.5 |  |  | 1909.5 |  |  | 1721.5 |  |  | 1701 |  |  | 1772.5 |  |  | 1811.5 |  |  | 1819.5 |  |  | 1653 |  |  | 1784.5 |  |  | 1651.5 |  |  | 1788.5 |  |  | 1732.5 |  |  | 1746.5 |  |  | 1771 |  |  | 1777.5 |  |  | 1812 |  |  | 1739.5 |  |  | 1680.5 |  |  | 1778.5 |  |  | 1861 |  |  | 1696.5 |  |  | 1768 |  |  | 1791 |  |  | 1736.5 |  |  | 1719.5 |  |  | 1754.5 |  |  | 1862.5 |  |  | 1863 |  |  | 1845.5 |  |  | 1719.5 |  |  | 1631.5 |  |  | 1761 |  |  | 1868.5 |  |  | 1725.5 |  |  | 1630.5 |  |  | 1788.5 |  |  | 1855 |  |  | 1652.5 |  |  | 1774.5 |  |  | 1849.5 |  |  | 1765.5 |  |  | 1767.5 |  |  | 1763.5 |  |  | 1863 |  |  | 1754.5 |  |  | 1692.5 |  |  | 1801 |  |  | 1691.5 |  |  | 1647.5 |  |  | 1757.5 |  |  | 1767 |  |  | 1800.5 |  |  | 1819.5 |  |  | 1784.5 |  |  | 1779.5 |  |  | 1859.5 |  |  | 1815 |  |  | 1776 |  |  | 1734.5 |  |  | 1803.5 |  |  | 1833.5 |  |  | 1673.5 |  |  | 1673 |  |  | 1856 |  |  | 1696 |  |  | 1823.5 |  |  | 1754 |  |  | 1771.5 |  |  | 1866.5 |  |  | 1760 |  |  | 1740.5 |  |  | 1838.5 |  |  | 1755.5 |  |  | 1917.5 |  |  | 1602.5 |  |  | 1774 |  |  | 1853 |  |  | 1655.5 |  |  | 1828.5 |  |  | 1758 |  |  | 1666.5 |  |  | 1824.5 |  |  | 1739 |  |  | 1893.5 |  |  | 1915.5 |  |  | 1715 |  |  | 1821.5 |  |  | 1796.5 |  |  | 1805 |  |  | 1806.5 |  |  | 1752 |  |  | 1935.5 |  |  | 1913 |  |  | 1740.5 |  |  | 1774.5 |  |  | 1835.5 |  |  | 1764.5 |  |  | 1810.5 |  |  | 1741.5 |  |  | 1826 |  |  | 1702.5 |  |  | 1774.5 |  |  | 1732.5 |  |  | 1766.5 |  |  | 1770.5 |  |  | 1784 |  |  | 1710.5 |  |  | 1832 |  |  | 1819.5 |  |  | 1693.5 |  |  | 1842.5 |  |  | 1743.5 |  |  | 1719.5 |  |  | 1827.5 |  |  | 1730.5 |  |  | 1891.5 |  |  | 1697.5 |  |  | 1760 |  |  | 1798.5 |  |  | 1684 |  |  | 1782 |  |  | 1748.5 |  |  | 1673 |  |  | 1654.5 |  |  | 1824.5 |  |  | 1858.5 |  |  | 1789.5 |  |  | 1814.5 |  |  | 1910.5 |  |  | 1829.5 |  |  | 1750 |  |  | 1871 |  |  | 1684.5 |  |  | 1667.5 |  |  | 1806 |  |  | 1733.5 |  |  | 1777.5 |  |  | 1702.5 |  |  | 1738.5 |  |  | 1711.5 |  |  | 1697 |  |  | 1738.5 |  |  | 1830.5 |  |  | 1686.5 |  |  | 1723 |  |  | 1826.5 |  |  | 1774.5 |  |  | 1826.5 |  |  | 1932.5 |  |  | 1832.5 |  |  | 1695.5 |  |  | 1881.5 |  |  | 1509.5 |  |  | 1765.5 |  |  | 1716 |  |  | 1862.5 |  |  | 1766.5 |  |  | 1870.5 |  |  | 1642.5 |  |  | 1759.5 |  |  | 1719.5 |  |  | 1709.5 |  |  | 1621 |  |  | 1676.5 |  |  | 1836.5 |  |  | 1880.5 |  |  | 1709 |  |  | 1761.5 |  |  | 1699 |  |  | 1700.5 |  |  | 1790.5 |  |  | 1744.5 |  |  | 1783 |  |  | 1692.5 |  |  | 1774 |  |  | 1795 |  |  | 1780.5 |  |  | 1769 |  |  | 1868 |  |  | 1856.5 |  |  | 1806.5 |  |  | 1664.5 |  |  | 1842 |  |  | 1852.5 |  |  | 1740.5 |  |  | 1683.5 |  |  | 1847.5 |  |  | 1723.5 |  |  | 1752.5 |  |  | 1706.5 |  |  | 1841.5 |  |  | 1750 |  |  | 1900.5 |  |  | 1733 |  |  | 1756.5 |  |  | 1721.5 |  |  | 1878.5 |  |  | 1775 |  |  | 1831 |  |  | 1906 |  |  | 1778.5 |  |  | 1775 |  |  | 1826.5 |  |  | 1898.5 |  |  | 1748.5 |  |  | 1752.5 |  |  | 1684.5 |  |  | 1838.5 |  |  | 1840.5 |  |  | 1802.5 |  |  | 1816 |  |  | 1674.5 |  |  | 1633.5 |  |  | 1844.5 |  |  | 1692.5 |  |  | 1695 |  |  | 1764.5 |  |  | 1807 |  |  | 1776.5 |  |  | 1791.5 |  |  | 1726.5 |  |  | 1713.5 |  |  | 1631 |  |  | 1720.5 |  |  | 1598 |  |  | 1717.5 |  |  | 1830.5 |  |  | 1898.5 |  |  | 1824.5 |  |  | 1794.5 |  |  | 1775.5 |  |  | 1652.5 |  |  | 1851.5 |  |  | 1783.5 |  |  | 1729 |  |  | 1796.5 |  |  | 1729.5 |  |  | 1713.5 |  |  | 1779.5 |  |  | 1822.5 |  |  | 1700 |  |  | 1751 |  |  | 1773.5 |  |  | 1691 |  |  | 1935.5 |  |  | 1757.5 |  |  | 1859.5 |  |  | 1885.5 |  |  | 1730.5 |  |  | 1799.5 |  |  | 1736.5 |  |  | 1797.5 |  |  | 1813 |  |  | 1787.5 |  |  | 1949.5 |  |  | 1796.5 |  |  | 1652 |  |  | 1748.5 |  |  | 1728.5 |  |  | 1804 |  |  | 1682 |  |  | 1808.5 |  |  | 1692 |  |  | 1641 |  |  | 1669.5 |  |  | 1790 |  |  | 1923.5 |  |  | 1837.5 |  |  | 1860.5 |  |  | 1771.5 |  |  | 1679.5 |  |  | 1728.5 |  |  | 1653.5 |  |  | 1733.5 |  |  | 1829.5 |  |  | 1752.5 |  |  | 1649 |  |  | 1664 |  |  | 1885.5 |  |  | 1806.5 |  |  | 1755.5 |  |  | 1849.5 |  |  | 1718.5 |  |  | 1790.5 |  |  | 1859.5 |  |  | 1732.5 |  |  | 1936 |  |  | 1669.5 |  |  | 1769 |  |  | 1727.5 |  |  | 1935.5 |  |  | 1796.5 |  |  | 1838 |  |  | 1746.5 |  |  | 1720.5 |  |  | 1732 |  |  | 1803.5 |  |  | 1729.5 |  |  | 1840.5 |  |  | 1784.5 |  |  | 1721.5 |  |  | 1788.5 |  |  | 1816 |  |  | 1707.5 |  |  | 1698.5 |  |  | 1840.5 |  |  | 1877.5 |  |  | 1758 |  |  | 1760.5 |  |  | 1885.5 |  |  | 1718 |  |  | 1822.5 |  |  | 1829.5 |  |  | 1792 |  |  | 1853.5 |  |  | 1870.5 |  |  | 1757.5 |  |  | 1732 |  |  | 1662.5 |  |  | 1774.5 |  |  | 1792 |  |  | 1771.5 |  |  | 1868.5 |  |  | 1789.5 |  |  | 1635.5 |  |  | 1866.5 |  |  | 1898.5 |  |  | 1714.5 |  |  | 1779 |  |  | 1729 |  |  | 1643.5 |  |  | 1846.5 |  |  | 1693.5 |  |  | 1791 |  |  | 1945.5 |  |  | 1723.5 |  |  | 1718.5 |  |  | 1634.5 |  |  | 1714.5 |  |  | 1748.5 |  |  | 1700.5 |  |  | 1825.5 |  |  | 1636.5 |  |  | 1809 |  |  | 1701.5 |  |  | 1746.5 |  |  | 1745.5 |  |  | 1858.5 |  |  | 1857.5 |  |  | 1770.5 |  |  | 1822.5 |  |  | 1831.5 |  |  | 1694.5 |  |  | 1884.5 |  |  | 1784.5 |  |  | 1733.5 |  |  | 1824.5 |  |  | 1875 |  |  | 1796.5 |  |  | 1847.5 |  |  | 1719 |  |  | 1824.5 |  |  | 1783.5 |  |  | 1829 |  |  | 1776.5 |  |  | 1895.5 |  |  | 1910.5 |  |  | 1898 |  |  | 1784.5 |  |  | 1828.5 |  |  | 1745.5 |  |  | 1598.5 |  |  | 1764.5 |  |  | 1643 |  |  | 1772.5 |  |  | 1780 |  |  | 1822 |  |  | 1920.5 |  |  | 1824.5 |  |  | 1732.5 |  |  | 1610.5 |  |  | 1775.5 |  |  | 1768.5 |  |  | 1756 |  |  | 1774.5 |  |  | 1744 |  |  | 1735.5 |  |  | 1785 |  |  | 1773 |  |  | 1868 |  |  | 1796.5 |  |  | 1741 |  |  | 1893.5 |  |  | 1860.5 |  |  | 1788.5 |  |  | 1926.5 |  |  | 1790.5 |  |  | 1856 |  |  | 1838.5 |  |  | 1811.5 |  |  | 1958.5 |  |  | 1803 |  |  | 1803.5 |  |  | 1688.5 |  |  | 1772.5 |  |  | 1825.5 |  |  | 1729 |  |  | 1816 |  |  | 1767 |  |  | 1797.5 |  |  | 1827 |  |  | 1888 |  |  | 1836.5 |  |  | 1763.5 |  |  | 1661.5 |  |  | 1816.5 |  |  | 1827.5 |  |  | 1856.5 |  |  | 1886.5 |  |  | 1759.5 |  |  | 1718.5 |  |  | 1709 |  |  | 1768.5 |  |  | 1754 |  |  | 1817.5 |  |  | 1808.5 |  |  | 1794.5 |  |  | 1860.5 |  |  | 1853 |  |  | 1828.5 |  |  | 1779 |  |  | 1715.5 |  |  | 1818.5 |  |  | 1770 |  |  | 1793 |  |  | 1776.5 |  |  | 1768 |  |  | 1848.5 |  |  | 1658.5 |  |  | 1735.5 |  |  | 1719.5 |  |  | 1783.5 |  |  | 1820.5 |  |  | 1672.5 |  |  | 1647 |  |  | 1842.5 |  |  | 1802.5 |  |  | 1746.5 |  |  | 1798.5 |  |  | 1684.5 |  |  | 1729.5 |  |  | 1856.5 |  |  | 1819.5 |  |  | 1887.5 |  |  | 1826.5 |  |  | 1690.5 |  |  | 1725.5 |  |  | 1829 |  |  | 1654.5 |  |  | 1729.5 |  |  | 1838 |  |  | 1700.5 |  |  | 1688.5 |  |  | 1741.5 |  |  | 1700.5 |  |  | 1854 |  |  | 1974.5 |  |  | 1755.5 |  |  | 1701.5 |  |  | 1822.5 |  |  | 1772 |  |  | 1744.5 |  |  | 1853.5 |  |  | 1821.5 |  |  | 1858.5 |  |  | 1729.5 |  |  | 1694.5 |  |  | 1818.5 |  |  | 1861.5 |  |  | 1779.5 |  |  | 1738.5 |  |  | 1878.5 |  |  | 1802 |  |  | 1770.5 |  |  | 1772.5 |  |  | 1886.5 |  |  | 1829.5 |  |  | 1712.5 |  |  | 1736.5 |  |  | 1849 |  |  | 1762.5 |  |  | 1733 |  |  | 1660.5 |  |  | 1826.5 |  |  | 1775.5 |  |  | 1754 |  |  | 1738 |  |  | 1746.5 |  |  | 1809.5 |  |  | 1609.5 |  |  | 1813.5 |  |  | 1736.5 |  |  | 1781.5 |  |  | 1722.5 |  |  | 1793.5 |  |  | 1768.5 |  |  | 1849.5 |  |  | 1752.5 |  |  | 1808.5 |  |  | 1697.5 |  |  | 1841.5 |  |  | 1816.5 |  |  | 1785.5 |  |  | 1759.5 |  |  | 1785.5 |  |  | 1724.5 |  |  | 1746.5 |  |  | 1778.5 |  |  | 1852.5 |  |  | 1777 |  |  | 1859.5 |  |  | 1764.5 |  |  | 1780.5 |  |  | 1782 |  |  | 1818.5 |  |  | 1768.5 |  |  | 1811.5 |  |  | 1790.5 |  |  | 1810 |  |  | 1671.5 |  |  | 1636.5 |  |  | 1688 |  |  | 1744 |  |  | 1843 |  |  | 1746.5 |  |  | 1762.5 |  |  | 1758.5 |  |  | 1937.5 |  |  | 1802 |  |  | 1819.5 |  |  | 1809.5 |  |  | 1679 |  |  | 1724 |  |  | 1817.5 |  |  | 1740.5 |  |  | 1784 |  |  | 1719.5 |  |  | 1850 |  |  | 1708.5 |  |  | 1670.5 |  |  | 1886 |  |  | 1859.5 |  |  | 1739.5 |  |  | 1635.5 |  |  | 1898 |  |  | 1729.5 |  |  | 1697.5 |  |  | 1718.5 |  |  | 1757.5 |  |  | 1759.5 |  |  | 1898.5 |  |  | 1704.5 |  |  | 1785.5 |  |  | 1804.5 |  |  | 1799.5 |  |  | 1779 |  |  | 1794.5 |  |  | 1818.5 |  |  | 1802.5 |  |  | 1843.5 |  |  | 1774.5 |  |  | 1864.5 |  |  | 1875.5 |  |  | 1781.5 |  |  | 1944 |  |  | 1720.5 |  |  | 1764 |  |  | 1879.5 |  |  | 1942.5 |  |  | 1926.5 |  |  | 1699.5 |  |  | 1733.5 |  |  | 1717.5 |  |  | 1633.5 |  |  | 1853.5 |  |  | 1842 |  |  | 1706.5 |  |  | 1788 |  |  | 1690.5 |  |  | 1656.5 |  |  | 1797.5 |  |  | 1871 |  |  | 1751.5 |  |  | 1864.5 |  |  | 1638 |  |  | 1747.5 |  |  | 1755 |  |  | 1756.5 |  |  | 1751.5 |  |  | 1708.5 |  |  | 1757 |  |  | 1842.5 |  |  | 1934.5 |  |  | 1696 |  |  | 1928.5 |  |  | 1650.5 |  |  | 1829 |  |  | 1786.5 |  |  | 1918.5 |  |  | 1858.5 |  |  | 1879.5 |  |  | 1683.5 |  |  | 1879.5 |  |  | 1710.5 |  |  | 1754.5 |  |  | 1689.5 |  |  | 1745.5 |  |  | 1950.5 |  |  | 1841 |  |  | 1857 |  |  | 1873.5 |  |  | 1791.5 |  |  | 1831
62 |  | 1736.5 |  |  | 1935.5 |  |  | 1805 |  |  | 1745.5 |  |  | 1968.5 |  |  | 1817.5 |  |  | 1896.5 |  |  | 1843.5 |  |  | 1842.5 |  |  | 1795.5 |  |  | 1745 |  |  | 1887.5 |  |  | 1894.5 |  |  | 1737.5 |  |  | 1713 |  |  | 1870.5 |  |  | 1931.5 |  |  | 1840.5 |  |  | 1974.5 |  |  | 1718.5 |  |  | 1788.5 |  |  | 1845.5 |  |  | 1831.5 |  |  | 1754.5 |  |  | 1664 |  |  | 1852.5 |  |  | 1784.5 |  |  | 1811.5 |  |  | 1894.5 |  |  | 1733 |  |  | 1818 |  |  | 1828.5 |  |  | 1687.5 |  |  | 1884.5 |  |  | 1695.5 |  |  | 1828 |  |  | 1762.5 |  |  | 1869 |  |  | 1796.5 |  |  | 1808.5 |  |  | 1704.5 |  |  | 1903.5 |  |  | 1680.5 |  |  | 1775 |  |  | 1986.5 |  |  | 1855 |  |  | 1784.5 |  |  | 1932.5 |  |  | 1844.5 |  |  | 1802.5 |  |  | 1770.5 |  |  | 1835.5 |  |  | 1816.5 |  |  | 1758.5 |  |  | 1908.5 |  |  | 1819.5 |  |  | 1732.5 |  |  | 1823 |  |  | 1839.5 |  |  | 1777.5 |  |  | 1794 |  |  | 1807.5 |  |  | 1936.5 |  |  | 1761.5 |  |  | 1740.5 |  |  | 1780 |  |  | 1887.5 |  |  | 1768 |  |  | 1690.5 |  |  | 1830.5 |  |  | 1785 |  |  | 1815.5 |  |  | 1801.5 |  |  | 1932.5 |  |  | 1917 |  |  | 1889 |  |  | 1761.5 |  |  | 1753.5 |  |  | 1691.5 |  |  | 1804.5 |  |  | 1759 |  |  | 1799.5 |  |  | 1837.5 |  |  | 1898.5 |  |  | 1864.5 |  |  | 1786.5 |  |  | 1880.5 |  |  | 1772.5 |  |  | 1759.5 |  |  | 1867.5 |  |  | 1873.5 |  |  | 1867 |  |  | 1669.5 |  |  | 1706 |  |  | 1814 |  |  | 1751 |  |  | 1944.5 |  |  | 1904.5 |  |  | 1718.5 |  |  | 1850.5 |  |  | 1791.5 |  |  | 1789 |  |  | 1787 |  |  | 1761.5 |  |  | 1791.5 |  |  | 1763.5 |  |  | 1851.5 |  |  | 1913.5 |  |  | 1927.5 |  |  | 1886.5 |  |  | 1944.5 |  |  | 1870.5 |  |  | 1826.5 |  |  | 1812.5 |  |  | 1779.5 |  |  | 1891.5 |  |  | 1895.5 |  |  | 1682.5 |  |  | 1860.5 |  |  | 1807.5 |  |  | 1855.5 |  |  | 1853.5 |  |  | 1780.5 |  |  | 1808.5 |  |  | 1865.5 |  |  | 1816 |  |  | 1779.5 |  |  | 1814.5 |  |  | 1754.5 |  |  | 1774.5 |  |  | 1893.5 |  |  | 1849 |  |  | 1714.5 |  |  | 1869.5 |  |  | 1729.5 |  |  | 1825.5 |  |  | 1863 |  |  | 1809.5 |  |  | 1860.5 |  |  | 1811 |  |  | 1840.5 |  |  | 1786 |  |  | 1859 |  |  | 1901.5 |  |  | 1828 |  |  | 1926.5 |  |  | 1797.5 |  |  | 1889.5 |  |  | 1745.5 |  |  | 1893.5 |  |  | 1841.5 |  |  | 1828.5 |  |  | 1866.5 |  |  | 1972.5 |  |  | 1856.5 |  |  | 1925 |  |  | 1808.5 |  |  | 1710 |  |  | 1782.5 |  |  | 1843.5 |  |  | 1798 |  |  | 1816.5 |  |  | 1795.5 |  |  | 1791.5 |  |  | 1740 |  |  | 1851.5 |  |  | 1721.5 |  |  | 1741.5 |  |  | 1926.5 |  |  | 1752.5 |  |  | 1789.5 |  |  | 1788 |  |  | 1805.5 |  |  | 1828.5 |  |  | 1768.5 |  |  | 1802.5 |  |  | 1861.5 |  |  | 1826.5 |  |  | 1728.5 |  |  | 1899 |  |  | 1887.5 |  |  | 1837.5 |  |  | 1866.5 |  |  | 1851.5 |  |  | 1726.5 |  |  | 1921.5 |  |  | 1891.5 |  |  | 1798.5 |  |  | 1880.5 |  |  | 1729.5 |  |  | 1828.5 |  |  | 1720.5 |  |  | 1648.5 |  |  | 1746 |  |  | 1749.5 |  |  | 1826.5 |  |  | 1788.5 |  |  | 1844.5 |  |  | 1822.5 |  |  | 1853.5 |  |  | 1893.5 |  |  | 1809.5 |  |  | 1864.5 |  |  | 1727.5 |  |  | 1791.5 |  |  | 1912.5 |  |  | 1778.5 |  |  | 1767.5 |  |  | 1801.5 |  |  | 1857.5 |  |  | 1876 |  |  | 1843.5 |  |  | 1771.5 |  |  | 1644 |  |  | 1926.5 |  |  | 1843 |  |  | 1722.5 |  |  | 1895.5 |  |  | 1960.5 |  |  | 1875.5 |  |  | 1742.5 |  |  | 1822.5 |  |  | 1785.5 |  |  | 1633.5 |  |  | 1740 |  |  | 1732.5 |  |  | 1668.5 |  |  | 1895.5 |  |  | 1759.5 |  |  | 1845 |  |  | 1745.5 |  |  | 1839.5 |  |  | 1876.5 |  |  | 1876.5 |  |  | 1918.5 |  |  | 1800.5 |  |  | 1793.5 |  |  | 1910.5 |  |  | 1857 |  |  | 1831 |  |  | 1766.5 |  |  | 1804.5 |  |  | 1778.5 |  |  | 1839 |  |  | 1901.5 |  |  | 1834.5 |  |  | 1747.5 |  |  | 1741 |  |  | 1821.5 |  |  | 1892.5 |  |  | 1701.5 |  |  | 1752.5 |  |  | 1824.5 |  |  | 1877.5 |  |  | 1826.5 |  |  | 1811.5 |  |  | 1948.5 |  |  | 1636 |  |  | 1733.5 |  |  | 1862.5 |  |  | 1826.5 |  |  | 1730.5 |  |  | 1779.5 |  |  | 1911 |  |  | 1776.5 |  |  | 1860.5 |  |  | 1853 |  |  | 1947.5 |  |  | 1835.5 |  |  | 1950 |  |  | 1809.5 |  |  | 1804.5 |  |  | 1936.5 |  |  | 1744.5 |  |  | 1823 |  |  | 1778 |  |  | 1834.5 |  |  | 1789.5 |  |  | 1852.5 |  |  | 1829.5 |  |  | 1915.5 |  |  | 1791.5 |  |  | 1785 |  |  | 1814.5 |  |  | 1858.5 |  |  | 1834 |  |  | 1764.5 |  |  | 1663.5 |  |  | 1885 |  |  | 1809.5 |  |  | 1737.5 |  |  | 1847.5 |  |  | 1784 |  |  | 1857.5 |  |  | 1770 |  |  | 1851.5 |  |  | 1713.5 |  |  | 1897.5 |  |  | 1789 |  |  | 1765.5 |  |  | 1945.5 |  |  | 1824.5 |  |  | 1836 |  |  | 1730.5 |  |  | 1672.5 |  |  | 1949.5 |  |  | 1906.5 |  |  | 1825.5 |  |  | 1826 |  |  | 1687.5 |  |  | 1906.5 |  |  | 1927.5 |  |  | 1749 |  |  | 1807 |  |  | 1906.5 |  |  | 1767.5 |  |  | 1719.5 |  |  | 1819.5 |  |  | 1825.5 |  |  | 1811.5 |  |  | 1802.5 |  |  | 1843.5 |  |  | 1751.5 |  |  | 1819.5 |  |  | 1824 |  |  | 1824.5 |  |  | 1860.5 |  |  | 2007.5 |  |  | 1880.5 |  |  | 1889 |  |  | 1823.5 |  |  | 1898.5 |  |  | 1799.5 |  |  | 1654.5 |  |  | 1881.5 |  |  | 1736 |  |  | 1812 |  |  | 1745 |  |  | 1913 |  |  | 1757.5 |  |  | 1827 |  |  | 1815.5 |  |  | 1791 |  |  | 1816.5 |  |  | 1961.5 |  |  | 1811.5 |  |  | 1807.5 |  |  | 1741.5 |  |  | 1861 |  |  | 1841.5 |  |  | 1907.5 |  |  | 1736.5 |  |  | 1848 |  |  | 1870.5 |  |  | 1718.5 |  |  | 1790.5 |  |  | 1856 |  |  | 1795.5 |  |  | 1720.5 |  |  | 1854.5 |  |  | 1755.5 |  |  | 1796.5 |  |  | 1775.5 |  |  | 1888.5 |  |  | 1783.5 |  |  | 1878.5 |  |  | 1696.5 |  |  | 1675 |  |  | 1789.5 |  |  | 1769.5 |  |  | 1726.5 |  |  | 1851.5 |  |  | 1937.5 |  |  | 1746 |  |  | 1837.5 |  |  | 1920 |  |  | 1744 |  |  | 1783.5 |  |  | 1948.5 |  |  | 1747.5 |  |  | 1730 |  |  | 1793.5 |  |  | 1837.5 |  |  | 1848.5 |  |  | 1692 |  |  | 1823.5 |  |  | 1666.5 |  |  | 1817.5 |  |  | 1747.5 |  |  | 1761.5 |  |  | 1792 |  |  | 1816.5 |  |  | 1859 |  |  | 1763.5 |  |  | 1701.5 |  |  | 1817.5 |  |  | 1887 |  |  | 1711.5 |  |  | 1789 |  |  | 1820 |  |  | 1762.5 |  |  | 1745.5 |  |  | 1775.5 |  |  | 1901.5 |  |  | 1889 |  |  | 1866.5 |  |  | 1766.5 |  |  | 1660.5 |  |  | 1782 |  |  | 1889.5 |  |  | 1749.5 |  |  | 1656.5 |  |  | 1809.5 |  |  | 1894 |  |  | 1681.5 |  |  | 1800.5 |  |  | 1878.5 |  |  | 1794.5 |  |  | 1782.5 |  |  | 1789.5 |  |  | 1878 |  |  | 1793.5 |  |  | 1721.5 |  |  | 1840 |  |  | 1712.5 |  |  | 1686.5 |  |  | 1778.5 |  |  | 1788 |  |  | 1839.5 |  |  | 1840.5 |  |  | 1813.5 |  |  | 1818.5 |  |  | 1874.5 |  |  | 1841 |  |  | 1815 |  |  | 1760.5 |  |  | 1850.5 |  |  | 1848.5 |  |  | 1697.5 |  |  | 1712 |  |  | 1871 |  |  | 1711 |  |  | 1870.5 |  |  | 1769 |  |  | 1810.5 |  |  | 1881.5 |  |  | 1807 |  |  | 1779.5 |  |  | 1859.5 |  |  | 1784.5 |  |  | 1938.5 |  |  | 1617.5 |  |  | 1789 |  |  | 1892 |  |  | 1684.5 |  |  | 1867.5 |  |  | 1787 |  |  | 1690.5 |  |  | 1850.5 |  |  | 1765 |  |  | 1922.5 |  |  | 1954.5 |  |  | 1754 |  |  | 1836.5 |  |  | 1835.5 |  |  | 1834 |  |  | 1832.5 |  |  | 1791 |  |  | 1950.5 |  |  | 1960 |  |  | 1755.5 |  |  | 1789.5 |  |  | 1874.5 |  |  | 1788.5 |  |  | 1825.5 |  |  | 1756.5 |  |  | 1852 |  |  | 1741.5 |  |  | 1803.5 |  |  | 1753.5 |  |  | 1787.5 |  |  | 1817.5 |  |  | 1799 |  |  | 1734.5 |  |  | 1853 |  |  | 1840.5 |  |  | 1719.5 |  |  | 1871.5 |  |  | 1764.5 |  |  | 1745.5 |  |  | 1851.5 |  |  | 1759.5 |  |  | 1917.5 |  |  | 1718.5 |  |  | 1784 |  |  | 1845.5 |  |  | 1705 |  |  | 1797 |  |  | 1795.5 |  |  | 1697 |  |  | 1693.5 |  |  | 1839.5 |  |  | 1887.5 |  |  | 1804.5 |  |  | 1853.5 |  |  | 1925.5 |  |  | 1850.5 |  |  | 1779 |  |  | 1892 |  |  | 1705.5 |  |  | 1706.5 |  |  | 1830 |  |  | 1759.5 |  |  | 1801.5 |  |  | 1741.5 |  |  | 1777.5 |  |  | 1750.5 |  |  | 1726 |  |  | 1762.5 |  |  | 1869.5 |  |  | 1715.5 |  |  | 1770 |  |  | 1850.5 |  |  | 1789.5 |  |  | 1852.5 |  |  | 1958.5 |  |  | 1858.5 |  |  | 1742.5 |  |  | 1907.5 |  |  | 1533.5 |  |  | 1780.5 |  |  | 1731 |  |  | 1883.5 |  |  | 1805.5 |  |  | 1885.5 |  |  | 1681.5 |  |  | 1774.5 |  |  | 1766.5 |  |  | 1733.5 |  |  | 1668 |  |  | 1702.5 |  |  | 1857.5 |  |  | 1895.5 |  |  | 1748 |  |  | 1782.5 |  |  | 1723 |  |  | 1726.5 |  |  | 1811.5 |  |  | 1759.5 |  |  | 1809 |  |  | 1721.5 |  |  | 1813 |  |  | 1810 |  |  | 1827.5 |  |  | 1790 |  |  | 1897 |  |  | 1880.5 |  |  | 1830.5 |  |  | 1679.5 |  |  | 1881 |  |  | 1881.5 |  |  | 1769.5 |  |  | 1707.5 |  |  | 1862.5 |  |  | 1770.5 |  |  | 1778.5 |  |  | 1732.5 |  |  | 1867.5 |  |  | 1797 |  |  | 1929.5 |  |  | 1780 |  |  | 1795.5 |  |  | 1745.5 |  |  | 1917.5 |  |  | 1796 |  |  | 1870 |  |  | 1935 |  |  | 1817.5 |  |  | 1796 |  |  | 1847.5 |  |  | 1922.5 |  |  | 1769.5 |  |  | 1767.5 |  |  | 1705.5 |  |  | 1867.5 |  |  | 1879.5 |  |  | 1831.5 |  |  | 1840 |  |  | 1689.5 |  |  | 1680.5 |  |  | 1883.5 |  |  | 1707.5 |  |  | 1734 |  |  | 1785.5 |  |  | 1833 |  |  | 1815.5 |  |  | 1830.5 |  |  | 1747.5 |  |  | 1728.5 |  |  | 1678 |  |  | 1741.5 |  |  | 1613 |  |  | 1738.5 |  |  | 1845.5 |  |  | 1927.5 |  |  | 1863.5 |  |  | 1823.5 |  |  | 1801.5 |  |  | 1699.5 |  |  | 1890.5 |  |  | 1812.5 |  |  | 1744 |  |  | 1835.5 |  |  | 1750.5 |  |  | 1760.5 |  |  | 1808.5 |  |  | 1861.5 |  |  | 1739 |  |  | 1772 |  |  | 1802.5 |  |  | 1738 |  |  | 1974.5 |  |  | 1796.5 |  |  | 1888.5 |  |  | 1900.5 |  |  | 1769.5 |  |  | 1838.5 |  |  | 1775.5 |  |  | 1844.5 |  |  | 1828 |  |  | 1808.5 |  |  | 1996.5 |  |  | 1817.5 |  |  | 1691 |  |  | 1769.5 |  |  | 1757.5 |  |  | 1843 |  |  | 1729 |  |  | 1832.5 |  |  | 1721 |  |  | 1688 |  |  | 1684.5 |  |  | 1829 |  |  | 1962.5 |  |  | 1866.5 |  |  | 1899.5 |  |  | 1800.5 |  |  | 1703.5 |  |  | 1749.5 |  |  | 1674.5 |  |  | 1772.5 |  |  | 1868.5 |  |  | 1773.5 |  |  | 1688 |  |  | 1703 |  |  | 1914.5 |  |  | 1853.5 |  |  | 1779.5 |  |  | 1875.5 |  |  | 1739.5 |  |  | 1805.5 |  |  | 1898.5 |  |  | 1747.5 |  |  | 1975 |  |  | 1698.5 |  |  | 1795 |  |  | 1753.5 |  |  | 1964.5 |  |  | 1843.5 |  |  | 1885 |  |  | 1772.5 |  |  | 1759.5 |  |  | 1771 |  |  | 1832.5 |  |  | 1768.5 |  |  | 1866.5 |  |  | 1831.5 |  |  | 1750.5 |  |  | 1803.5 |  |  | 1863 |  |  | 1736.5 |  |  | 1745.5 |  |  | 1866.5 |  |  | 1892.5 |  |  | 1805 |  |  | 1775.5 |  |  | 1911.5 |  |  | 1757 |  |  | 1848.5 |  |  | 1868.5 |  |  | 1839 |  |  | 1879.5 |  |  | 1899.5 |  |  | 1786.5 |  |  | 1771 |  |  | 1683.5 |  |  | 1798.5 |  |  | 1821 |  |  | 1810.5 |  |  | 1892.5 |  |  | 1810.5 |  |  | 1659.5 |  |  | 1881.5 |  |  | 1919.5 |  |  | 1738.5 |  |  | 1818 |  |  | 1776 |  |  | 1658.5 |  |  | 1867.5 |  |  | 1708.5 |  |  | 1838 |  |  | 1960.5 |  |  | 1744.5 |  |  | 1757.5 |  |  | 1655.5 |  |  | 1761.5 |  |  | 1787.5 |  |  | 1747.5 |  |  | 1864.5 |  |  | 1675.5 |  |  | 1838 |  |  | 1748.5 |  |  | 1770.5 |  |  | 1766.5 |  |  | 1873.5 |  |  | 1896.5 |  |  | 1799.5 |  |  | 1869.5 |  |  | 1852.5 |  |  | 1723.5 |  |  | 1923.5 |  |  | 1813.5 |  |  | 1772.5 |  |  | 1863.5 |  |  | 1890 |  |  | 1843.5 |  |  | 1862.5 |  |  | 1758 |  |  | 1850.5 |  |  | 1822.5 |  |  | 1868 |  |  | 1815.5 |  |  | 1919.5 |  |  | 1934.5 |  |  | 1913 |  |  | 1810.5 |  |  | 1857.5 |  |  | 1784.5 |  |  | 1645.5 |  |  | 1811.5 |  |  | 1690 |  |  | 1796.5 |  |  | 1819 |  |  | 1861 |  |  | 1949.5 |  |  | 1845.5 |  |  | 1771.5 |  |  | 1649.5 |  |  | 1790.5 |  |  | 1815.5 |  |  | 1782 |  |  | 1813.5 |  |  | 1773 |  |  | 1782.5 |  |  | 1824 |  |  | 1797 |  |  | 1907 |  |  | 1817.5 |  |  | 1765 |  |  | 1914.5 |  |  | 1886.5 |  |  | 1835.5 |  |  | 1965.5 |  |  | 1805.5 |  |  | 1903 |  |  | 1877.5 |  |  | 1850.5 |  |  | 1973.5 |  |  | 1827 |  |  | 1827.5 |  |  | 1712.5 |  |  | 1793.5 |  |  | 1854.5 |  |  | 1758 |  |  | 1855 |  |  | 1791 |  |  | 1818.5 |  |  | 1851 |  |  | 1903 |  |  | 1875.5 |  |  | 1802.5 |  |  | 1676.5 |  |  | 1831.5 |  |  | 1851.5 |  |  | 1895.5 |  |  | 1910.5 |  |  | 1780.5 |  |  | 1733.5 |  |  | 1756 |  |  | 1792.5 |  |  | 1778 |  |  | 1846.5 |  |  | 1832.5 |  |  | 1815.5 |  |  | 1907.5 |  |  | 1900 |  |  | 1852.5 |  |  | 1818 |  |  | 1730.5 |  |  | 1847.5 |  |  | 1799 |  |  | 1832 |  |  | 1802.5 |  |  | 1815 |  |  | 1863.5 |  |  | 1684.5 |  |  | 1750.5 |  |  | 1740.5 |  |  | 1804.5 |  |  | 1867.5 |  |  | 1687.5 |  |  | 1694 |  |  | 1889.5 |  |  | 1841.5 |  |  | 1772.5 |  |  | 1824.5 |  |  | 1723.5 |  |  | 1750.5 |  |  | 1882.5 |  |  | 1858.5 |  |  | 1902.5 |  |  | 1855.5 |  |  | 1716.5 |  |  | 1749.5 |  |  | 1850 |  |  | 1693.5 |  |  | 1768.5 |  |  | 1885 |  |  | 1747.5 |  |  | 1727.5 |  |  | 1788.5 |  |  | 1739.5 |  |  | 1893 |  |  | 2013.5 |  |  | 1784.5 |  |  | 1722.5 |  |  | 1851.5 |  |  | 1811 |  |  | 1783.5 |  |  | 1874.5 |  |  | 1847.5 |  |  | 1882.5 |  |  | 1744.5 |  |  | 1709.5 |  |  | 1842.5 |  |  | 1885.5 |  |  | 1818.5 |  |  | 1762.5 |  |  | 1907.5 |  |  | 1831 |  |  | 1799.5 |  |  | 1796.5 |  |  | 1907.5 |  |  | 1868.5 |  |  | 1736.5 |  |  | 1783.5 |  |  | 1896 |  |  | 1801.5 |  |  | 1772 |  |  | 1707.5 |  |  | 1847.5 |  |  | 1814.5 |  |  | 1778 |  |  | 1764 |  |  | 1775.5 |  |  | 1848.5 |  |  | 1630.5 |  |  | 1828.5 |  |  | 1775.5 |  |  | 1805.5 |  |  | 1761.5 |  |  | 1840.5 |  |  | 1789.5 |  |  | 1873.5 |  |  | 1767.5 |  |  | 1832.5 |  |  | 1744.5 |  |  | 1867.5 |  |  | 1863.5 |  |  | 1811.5 |  |  | 1798.5 |  |  | 1832.5 |  |  | 1763.5 |  |  | 1793.5 |  |  | 1825.5 |  |  | 1878.5 |  |  | 1824 |  |  | 1880.5 |  |  | 1790.5 |  |  | 1795.5 |  |  | 1797 |  |  | 1844.5 |  |  | 1797.5 |  |  | 1850.5 |  |  | 1829.5 |  |  | 1849 |  |  | 1692.5 |  |  | 1657.5 |  |  | 1727 |  |  | 1783 |  |  | 1867 |  |  | 1793.5 |  |  | 1777.5 |  |  | 1787.5 |  |  | 1976.5 |  |  | 1817 |  |  | 1843.5 |  |  | 1856.5 |  |  | 1718 |  |  | 1753 |  |  | 1846.5 |  |  | 1755.5 |  |  | 1823 |  |  | 1740.5 |  |  | 1876 |  |  | 1737.5 |  |  | 1696.5 |  |  | 1933 |  |  | 1874.5 |  |  | 1778.5 |  |  | 1674.5 |  |  | 1924 |  |  | 1753.5 |  |  | 1744.5 |  |  | 1757.5 |  |  | 1783.5 |  |  | 1806.5 |  |  | 1927.5 |  |  | 1733.5 |  |  | 1814.5 |  |  | 1825.5 |  |  | 1828.5 |  |  | 1803 |  |  | 1823.5 |  |  | 1857.5 |  |  | 1841.5 |  |  | 1858.5 |  |  | 1821.5 |  |  | 1885.5 |  |  | 1914.5 |  |  | 1796.5 |  |  | 1965 |  |  | 1746.5 |  |  | 1785 |  |  | 1905.5 |  |  | 1963.5 |  |  | 1955.5 |  |  | 1728.5 |  |  | 1748.5 |  |  | 1746.5 |  |  | 1680.5 |  |  | 1892.5 |  |  | 1866 |  |  | 1730.5 |  |  | 1835 |  |  | 1729.5 |  |  | 1695.5 |  |  | 1821.5 |  |  | 1886 |  |  | 1798.5 |  |  | 1885.5 |  |  | 1662 |  |  | 1776.5 |  |  | 1770 |  |  | 1803.5 |  |  | 1798.5 |  |  | 1755.5 |  |  | 1786 |  |  | 1881.5 |  |  | 1960.5 |  |  | 1743 |  |  | 1952.5 |  |  | 1697.5 |  |  | 1855 |  |  | 1801.5 |  |  | 1965.5 |  |  | 1882.5 |  |  | 1900.5 |  |  | 1704.5 |  |  | 1900.5 |  |  | 1731.5 |  |  | 1801.5 |  |  | 1718.5 |  |  | 1766.5 |  |  | 1997.5 |  |  | 1888 |  |  | 1896 |  |  | 1912.5 |  |  | 1820.5 |  |  | 1857
63 |  | 1751.5 |  |  | 1974.5 |  |  | 1834 |  |  | 1774.5 |  |  | 1997.5 |  |  | 1846.5 |  |  | 1943.5 |  |  | 1869.5 |  |  | 1889.5 |  |  | 1842.5 |  |  | 1774 |  |  | 1926.5 |  |  | 1933.5 |  |  | 1766.5 |  |  | 1742 |  |  | 1885.5 |  |  | 1955.5 |  |  | 1861.5 |  |  | 1998.5 |  |  | 1757.5 |  |  | 1835.5 |  |  | 1869.5 |  |  | 1870.5 |  |  | 1775.5 |  |  | 1703 |  |  | 1881.5 |  |  | 1823.5 |  |  | 1840.5 |  |  | 1909.5 |  |  | 1762 |  |  | 1857 |  |  | 1875.5 |  |  | 1702.5 |  |  | 1899.5 |  |  | 1719.5 |  |  | 1843 |  |  | 1786.5 |  |  | 1916 |  |  | 1811.5 |  |  | 1855.5 |  |  | 1728.5 |  |  | 1918.5 |  |  | 1719.5 |  |  | 1801 |  |  | 2007.5 |  |  | 1876 |  |  | 1805.5 |  |  | 1971.5 |  |  | 1883.5 |  |  | 1826.5 |  |  | 1791.5 |  |  | 1882.5 |  |  | 1845.5 |  |  | 1805.5 |  |  | 1929.5 |  |  | 1858.5 |  |  | 1756.5 |  |  | 1870 |  |  | 1868.5 |  |  | 1806.5 |  |  | 1820 |  |  | 1822.5 |  |  | 1957.5 |  |  | 1787.5 |  |  | 1764.5 |  |  | 1827 |  |  | 1908.5 |  |  | 1789 |  |  | 1705.5 |  |  | 1869.5 |  |  | 1809 |  |  | 1854.5 |  |  | 1840.5 |  |  | 1971.5 |  |  | 1932 |  |  | 1918 |  |  | 1800.5 |  |  | 1792.5 |  |  | 1712.5 |  |  | 1851.5 |  |  | 1788 |  |  | 1838.5 |  |  | 1876.5 |  |  | 1945.5 |  |  | 1911.5 |  |  | 1833.5 |  |  | 1901.5 |  |  | 1811.5 |  |  | 1785.5 |  |  | 1896.5 |  |  | 1912.5 |  |  | 1888 |  |  | 1716.5 |  |  | 1753 |  |  | 1838 |  |  | 1775 |  |  | 1983.5 |  |  | 1951.5 |  |  | 1747.5 |  |  | 1897.5 |  |  | 1806.5 |  |  | 1828 |  |  | 1811 |  |  | 1790.5 |  |  | 1812.5 |  |  | 1787.5 |  |  | 1880.5 |  |  | 1942.5 |  |  | 1948.5 |  |  | 1907.5 |  |  | 1970.5 |  |  | 1917.5 |  |  | 1847.5 |  |  | 1859.5 |  |  | 1826.5 |  |  | 1915.5 |  |  | 1934.5 |  |  | 1721.5 |  |  | 1875.5 |  |  | 1828.5 |  |  | 1870.5 |  |  | 1882.5 |  |  | 1806.5 |  |  | 1829.5 |  |  | 1904.5 |  |  | 1837 |  |  | 1805.5 |  |  | 1861.5 |  |  | 1793.5 |  |  | 1803.5 |  |  | 1917.5 |  |  | 1888 |  |  | 1761.5 |  |  | 1893.5 |  |  | 1744.5 |  |  | 1854.5 |  |  | 1884 |  |  | 1856.5 |  |  | 1886.5 |  |  | 1832 |  |  | 1861.5 |  |  | 1833 |  |  | 1885 |  |  | 1948.5 |  |  | 1875 |  |  | 1952.5 |  |  | 1836.5 |  |  | 1910.5 |  |  | 1792.5 |  |  | 1908.5 |  |  | 1880.5 |  |  | 1849.5 |  |  | 1890.5 |  |  | 2019.5 |  |  | 1885.5 |  |  | 1949 |  |  | 1834.5 |  |  | 1731 |  |  | 1821.5 |  |  | 1858.5 |  |  | 1819 |  |  | 1855.5 |  |  | 1819.5 |  |  | 1817.5 |  |  | 1779 |  |  | 1890.5 |  |  | 1768.5 |  |  | 1756.5 |  |  | 1955.5 |  |  | 1799.5 |  |  | 1815.5 |  |  | 1812 |  |  | 1826.5 |  |  | 1867.5 |  |  | 1792.5 |  |  | 1828.5 |  |  | 1900.5 |  |  | 1847.5 |  |  | 1767.5 |  |  | 1923 |  |  | 1916.5 |  |  | 1876.5 |  |  | 1892.5 |  |  | 1880.5 |  |  | 1752.5 |  |  | 1950.5 |  |  | 1906.5 |  |  | 1837.5 |  |  | 1919.5 |  |  | 1758.5 |  |  | 1849.5 |  |  | 1749.5 |  |  | 1669.5 |  |  | 1785 |  |  | 1775.5 |  |  | 1847.5 |  |  | 1827.5 |  |  | 1883.5 |  |  | 1861.5 |  |  | 1900.5 |  |  | 1908.5 |  |  | 1848.5 |  |  | 1911.5 |  |  | 1742.5 |  |  | 1806.5 |  |  | 1951.5 |  |  | 1807.5 |  |  | 1782.5 |  |  | 1840.5 |  |  | 1878.5 |  |  | 1897 |  |  | 1867.5 |  |  | 1810.5 |  |  | 1668 |  |  | 1950.5 |  |  | 1872 |  |  | 1748.5 |  |  | 1921.5 |  |  | 1975.5 |  |  | 1896.5 |  |  | 1781.5 |  |  | 1846.5 |  |  | 1824.5 |  |  | 1657.5 |  |  | 1755 |  |  | 1753.5 |  |  | 1707.5 |  |  | 1910.5 |  |  | 1774.5 |  |  | 1871 |  |  | 1766.5 |  |  | 1863.5 |  |  | 1923.5 |  |  | 1891.5 |  |  | 1933.5 |  |  | 1829.5 |  |  | 1840.5 |  |  | 1957.5 |  |  | 1896 |  |  | 1857 |  |  | 1805.5 |  |  | 1825.5 |  |  | 1804.5 |  |  | 1860 |  |  | 1922.5 |  |  | 1858.5 |  |  | 1794.5 |  |  | 1780 |  |  | 1868.5 |  |  | 1931.5 |  |  | 1725.5 |  |  | 1791.5 |  |  | 1839.5 |  |  | 1906.5 |  |  | 1847.5 |  |  | 1835.5 |  |  | 1995.5 |  |  | 1660 |  |  | 1780.5 |  |  | 1901.5 |  |  | 1841.5 |  |  | 1769.5 |  |  | 1794.5 |  |  | 1932 |  |  | 1815.5 |  |  | 1889.5 |  |  | 1874 |  |  | 1994.5 |  |  | 1864.5 |  |  | 1976 |  |  | 1835.5 |  |  | 1830.5 |  |  | 1975.5 |  |  | 1791.5 |  |  | 1870 |  |  | 1799 |  |  | 1849.5 |  |  | 1813.5 |  |  | 1876.5 |  |  | 1858.5 |  |  | 1936.5 |  |  | 1830.5 |  |  | 1814 |  |  | 1838.5 |  |  | 1873.5 |  |  | 1858 |  |  | 1793.5 |  |  | 1687.5 |  |  | 1906 |  |  | 1848.5 |  |  | 1776.5 |  |  | 1886.5 |  |  | 1813 |  |  | 1881.5 |  |  | 1785 |  |  | 1880.5 |  |  | 1737.5 |  |  | 1918.5 |  |  | 1818 |  |  | 1812.5 |  |  | 1960.5 |  |  | 1863.5 |  |  | 1862 |  |  | 1754.5 |  |  | 1698.5 |  |  | 1988.5 |  |  | 1921.5 |  |  | 1872.5 |  |  | 1865 |  |  | 1713.5 |  |  | 1945.5 |  |  | 1966.5 |  |  | 1770 |  |  | 1836 |  |  | 1945.5 |  |  | 1782.5 |  |  | 1758.5 |  |  | 1840.5 |  |  | 1851.5 |  |  | 1832.5 |  |  | 1817.5 |  |  | 1872.5 |  |  | 1790.5 |  |  | 1845.5 |  |  | 1871 |  |  | 1839.5 |  |  | 1907.5 |  |  | 2046.5 |  |  | 1901.5 |  |  | 1910 |  |  | 1838.5 |  |  | 1919.5 |  |  | 1825.5 |  |  | 1683.5 |  |  | 1928.5 |  |  | 1775 |  |  | 1833 |  |  | 1769 |  |  | 1934 |  |  | 1781.5 |  |  | 1866 |  |  | 1854.5 |  |  | 1812 |  |  | 1831.5 |  |  | 1976.5 |  |  | 1840.5 |  |  | 1833.5 |  |  | 1756.5 |  |  | 1887 |  |  | 1865.5 |  |  | 1946.5 |  |  | 1751.5 |  |  | 1872 |  |  | 1917.5 |  |  | 1765.5 |  |  | 1814.5 |  |  | 1880 |  |  | 1821.5 |  |  | 1746.5 |  |  | 1869.5 |  |  | 1776.5 |  |  | 1835.5 |  |  | 1799.5 |  |  | 1927.5 |  |  | 1798.5 |  |  | 1904.5 |  |  | 1725.5 |  |  | 1701 |  |  | 1828.5 |  |  | 1784.5 |  |  | 1752.5 |  |  | 1890.5 |  |  | 1966.5 |  |  | 1772 |  |  | 1866.5 |  |  | 1959 |  |  | 1783 |  |  | 1812.5 |  |  | 1987.5 |  |  | 1762.5 |  |  | 1759 |  |  | 1832.5 |  |  | 1861.5 |  |  | 1863.5 |  |  | 1731 |  |  | 1870.5 |  |  | 1705.5 |  |  | 1846.5 |  |  | 1762.5 |  |  | 1785.5 |  |  | 1807 |  |  | 1840.5 |  |  | 1874 |  |  | 1802.5 |  |  | 1740.5 |  |  | 1832.5 |  |  | 1913 |  |  | 1726.5 |  |  | 1815 |  |  | 1859 |  |  | 1809.5 |  |  | 1784.5 |  |  | 1804.5 |  |  | 1948.5 |  |  | 1936 |  |  | 1905.5 |  |  | 1781.5 |  |  | 1686.5 |  |  | 1803 |  |  | 1910.5 |  |  | 1773.5 |  |  | 1682.5 |  |  | 1833.5 |  |  | 1941 |  |  | 1720.5 |  |  | 1829.5 |  |  | 1925.5 |  |  | 1833.5 |  |  | 1821.5 |  |  | 1810.5 |  |  | 1917 |  |  | 1819.5 |  |  | 1768.5 |  |  | 1864 |  |  | 1751.5 |  |  | 1715.5 |  |  | 1804.5 |  |  | 1835 |  |  | 1860.5 |  |  | 1879.5 |  |  | 1837.5 |  |  | 1833.5 |  |  | 1889.5 |  |  | 1880 |  |  | 1839 |  |  | 1807.5 |  |  | 1889.5 |  |  | 1872.5 |  |  | 1718.5 |  |  | 1741 |  |  | 1892 |  |  | 1750 |  |  | 1909.5 |  |  | 1808 |  |  | 1857.5 |  |  | 1907.5 |  |  | 1833 |  |  | 1826.5 |  |  | 1888.5 |  |  | 1823.5 |  |  | 1964.5 |  |  | 1656.5 |  |  | 1810 |  |  | 1921 |  |  | 1723.5 |  |  | 1906.5 |  |  | 1802 |  |  | 1705.5 |  |  | 1871.5 |  |  | 1780 |  |  | 1946.5 |  |  | 1980.5 |  |  | 1793 |  |  | 1865.5 |  |  | 1882.5 |  |  | 1860 |  |  | 1847.5 |  |  | 1806 |  |  | 1971.5 |  |  | 1986 |  |  | 1794.5 |  |  | 1815.5 |  |  | 1889.5 |  |  | 1817.5 |  |  | 1846.5 |  |  | 1795.5 |  |  | 1891 |  |  | 1770.5 |  |  | 1829.5 |  |  | 1792.5 |  |  | 1802.5 |  |  | 1846.5 |  |  | 1823 |  |  | 1773.5 |  |  | 1882 |  |  | 1855.5 |  |  | 1748.5 |  |  | 1897.5 |  |  | 1793.5 |  |  | 1784.5 |  |  | 1877.5 |  |  | 1783.5 |  |  | 1938.5 |  |  | 1765.5 |  |  | 1799 |  |  | 1871.5 |  |  | 1720 |  |  | 1836 |  |  | 1834.5 |  |  | 1712 |  |  | 1722.5 |  |  | 1878.5 |  |  | 1908.5 |  |  | 1825.5 |  |  | 1892.5 |  |  | 1951.5 |  |  | 1876.5 |  |  | 1803 |  |  | 1916 |  |  | 1734.5 |  |  | 1745.5 |  |  | 1869 |  |  | 1780.5 |  |  | 1848.5 |  |  | 1767.5 |  |  | 1824.5 |  |  | 1789.5 |  |  | 1755 |  |  | 1809.5 |  |  | 1893.5 |  |  | 1762.5 |  |  | 1809 |  |  | 1871.5 |  |  | 1836.5 |  |  | 1867.5 |  |  | 2005.5 |  |  | 1887.5 |  |  | 1781.5 |  |  | 1954.5 |  |  | 1548.5 |  |  | 1819.5 |  |  | 1746 |  |  | 1922.5 |  |  | 1844.5 |  |  | 1911.5 |  |  | 1702.5 |  |  | 1813.5 |  |  | 1792.5 |  |  | 1762.5 |  |  | 1707 |  |  | 1726.5 |  |  | 1904.5 |  |  | 1934.5 |  |  | 1795 |  |  | 1829.5 |  |  | 1744 |  |  | 1750.5 |  |  | 1832.5 |  |  | 1788.5 |  |  | 1848 |  |  | 1760.5 |  |  | 1852 |  |  | 1839 |  |  | 1848.5 |  |  | 1829 |  |  | 1921 |  |  | 1919.5 |  |  | 1869.5 |  |  | 1700.5 |  |  | 1928 |  |  | 1896.5 |  |  | 1795.5 |  |  | 1728.5 |  |  | 1877.5 |  |  | 1809.5 |  |  | 1807.5 |  |  | 1761.5 |  |  | 1882.5 |  |  | 1836 |  |  | 1958.5 |  |  | 1809 |  |  | 1816.5 |  |  | 1760.5 |  |  | 1938.5 |  |  | 1820 |  |  | 1885 |  |  | 1964 |  |  | 1856.5 |  |  | 1817 |  |  | 1862.5 |  |  | 1969.5 |  |  | 1816.5 |  |  | 1788.5 |  |  | 1729.5 |  |  | 1906.5 |  |  | 1926.5 |  |  | 1870.5 |  |  | 1879 |  |  | 1728.5 |  |  | 1704.5 |  |  | 1898.5 |  |  | 1722.5 |  |  | 1763 |  |  | 1800.5 |  |  | 1872 |  |  | 1841.5 |  |  | 1869.5 |  |  | 1776.5 |  |  | 1754.5 |  |  | 1693 |  |  | 1765.5 |  |  | 1642 |  |  | 1785.5 |  |  | 1866.5 |  |  | 1974.5 |  |  | 1910.5 |  |  | 1870.5 |  |  | 1840.5 |  |  | 1720.5 |  |  | 1911.5 |  |  | 1836.5 |  |  | 1759 |  |  | 1864.5 |  |  | 1789.5 |  |  | 1784.5 |  |  | 1837.5 |  |  | 1882.5 |  |  | 1786 |  |  | 1796 |  |  | 1828.5 |  |  | 1777 |  |  | 2013.5 |  |  | 1817.5 |  |  | 1927.5 |  |  | 1929.5 |  |  | 1793.5 |  |  | 1885.5 |  |  | 1814.5 |  |  | 1883.5 |  |  | 1849 |  |  | 1832.5 |  |  | 2035.5 |  |  | 1843.5 |  |  | 1720 |  |  | 1793.5 |  |  | 1804.5 |  |  | 1882 |  |  | 1758 |  |  | 1871.5 |  |  | 1742 |  |  | 1735 |  |  | 1723.5 |  |  | 1853 |  |  | 2001.5 |  |  | 1892.5 |  |  | 1923.5 |  |  | 1815.5 |  |  | 1729.5 |  |  | 1788.5 |  |  | 1689.5 |  |  | 1811.5 |  |  | 1892.5 |  |  | 1799.5 |  |  | 1712 |  |  | 1724 |  |  | 1938.5 |  |  | 1882.5 |  |  | 1800.5 |  |  | 1899.5 |  |  | 1765.5 |  |  | 1829.5 |  |  | 1945.5 |  |  | 1786.5 |  |  | 1999 |  |  | 1745.5 |  |  | 1821 |  |  | 1779.5 |  |  | 1990.5 |  |  | 1872.5 |  |  | 1909 |  |  | 1798.5 |  |  | 1798.5 |  |  | 1795 |  |  | 1856.5 |  |  | 1794.5 |  |  | 1881.5 |  |  | 1852.5 |  |  | 1789.5 |  |  | 1832.5 |  |  | 1889 |  |  | 1775.5 |  |  | 1760.5 |  |  | 1881.5 |  |  | 1918.5 |  |  | 1831 |  |  | 1822.5 |  |  | 1937.5 |  |  | 1796 |  |  | 1877.5 |  |  | 1907.5 |  |  | 1878 |  |  | 1900.5 |  |  | 1928.5 |  |  | 1825.5 |  |  | 1810 |  |  | 1712.5 |  |  | 1837.5 |  |  | 1847 |  |  | 1849.5 |  |  | 1921.5 |  |  | 1825.5 |  |  | 1685.5 |  |  | 1905.5 |  |  | 1958.5 |  |  | 1777.5 |  |  | 1847 |  |  | 1800 |  |  | 1682.5 |  |  | 1893.5 |  |  | 1747.5 |  |  | 1864 |  |  | 1986.5 |  |  | 1765.5 |  |  | 1796.5 |  |  | 1679.5 |  |  | 1790.5 |  |  | 1826.5 |  |  | 1786.5 |  |  | 1903.5 |  |  | 1696.5 |  |  | 1864 |  |  | 1777.5 |  |  | 1794.5 |  |  | 1787.5 |  |  | 1902.5 |  |  | 1920.5 |  |  | 1838.5 |  |  | 1895.5 |  |  | 1881.5 |  |  | 1747.5 |  |  | 1944.5 |  |  | 1834.5 |  |  | 1798.5 |  |  | 1889.5 |  |  | 1929 |  |  | 1858.5 |  |  | 1886.5 |  |  | 1782 |  |  | 1871.5 |  |  | 1869.5 |  |  | 1907 |  |  | 1830.5 |  |  | 1958.5 |  |  | 1955.5 |  |  | 1934 |  |  | 1839.5 |  |  | 1904.5 |  |  | 1831.5 |  |  | 1669.5 |  |  | 1850.5 |  |  | 1737 |  |  | 1822.5 |  |  | 1858 |  |  | 1890 |  |  | 1970.5 |  |  | 1866.5 |  |  | 1810.5 |  |  | 1670.5 |  |  | 1829.5 |  |  | 1854.5 |  |  | 1806 |  |  | 1839.5 |  |  | 1820 |  |  | 1808.5 |  |  | 1850 |  |  | 1818 |  |  | 1931 |  |  | 1856.5 |  |  | 1780 |  |  | 1940.5 |  |  | 1901.5 |  |  | 1861.5 |  |  | 2004.5 |  |  | 1844.5 |  |  | 1924 |  |  | 1903.5 |  |  | 1889.5 |  |  | 1999.5 |  |  | 1856 |  |  | 1853.5 |  |  | 1727.5 |  |  | 1808.5 |  |  | 1869.5 |  |  | 1773 |  |  | 1884 |  |  | 1820 |  |  | 1857.5 |  |  | 1890 |  |  | 1942 |  |  | 1901.5 |  |  | 1823.5 |  |  | 1700.5 |  |  | 1860.5 |  |  | 1890.5 |  |  | 1910.5 |  |  | 1949.5 |  |  | 1801.5 |  |  | 1762.5 |  |  | 1777 |  |  | 1818.5 |  |  | 1804 |  |  | 1885.5 |  |  | 1861.5 |  |  | 1830.5 |  |  | 1931.5 |  |  | 1915 |  |  | 1891.5 |  |  | 1833 |  |  | 1777.5 |  |  | 1871.5 |  |  | 1814 |  |  | 1861 |  |  | 1831.5 |  |  | 1841 |  |  | 1892.5 |  |  | 1723.5 |  |  | 1771.5 |  |  | 1769.5 |  |  | 1843.5 |  |  | 1888.5 |  |  | 1702.5 |  |  | 1709 |  |  | 1910.5 |  |  | 1880.5 |  |  | 1819.5 |  |  | 1839.5 |  |  | 1749.5 |  |  | 1797.5 |  |  | 1911.5 |  |  | 1897.5 |  |  | 1931.5 |  |  | 1902.5 |  |  | 1755.5 |  |  | 1764.5 |  |  | 1865 |  |  | 1708.5 |  |  | 1794.5 |  |  | 1900 |  |  | 1776.5 |  |  | 1774.5 |  |  | 1817.5 |  |  | 1754.5 |  |  | 1940 |  |  | 2037.5 |  |  | 1813.5 |  |  | 1748.5 |  |  | 1890.5 |  |  | 1850 |  |  | 1809.5 |  |  | 1913.5 |  |  | 1886.5 |  |  | 1929.5 |  |  | 1759.5 |  |  | 1738.5 |  |  | 1857.5 |  |  | 1906.5 |  |  | 1865.5 |  |  | 1777.5 |  |  | 1928.5 |  |  | 1846 |  |  | 1825.5 |  |  | 1843.5 |  |  | 1946.5 |  |  | 1897.5 |  |  | 1775.5 |  |  | 1812.5 |  |  | 1935 |  |  | 1840.5 |  |  | 1793 |  |  | 1728.5 |  |  | 1868.5 |  |  | 1853.5 |  |  | 1825 |  |  | 1779 |  |  | 1814.5 |  |  | 1869.5 |  |  | 1651.5 |  |  | 1857.5 |  |  | 1814.5 |  |  | 1852.5 |  |  | 1808.5 |  |  | 1855.5 |  |  | 1828.5 |  |  | 1902.5 |  |  | 1788.5 |  |  | 1879.5 |  |  | 1770.5 |  |  | 1893.5 |  |  | 1878.5 |  |  | 1858.5 |  |  | 1824.5 |  |  | 1847.5 |  |  | 1802.5 |  |  | 1832.5 |  |  | 1854.5 |  |  | 1917.5 |  |  | 1845 |  |  | 1895.5 |  |  | 1819.5 |  |  | 1821.5 |  |  | 1821 |  |  | 1883.5 |  |  | 1821.5 |  |  | 1879.5 |  |  | 1868.5 |  |  | 1888 |  |  | 1718.5 |  |  | 1696.5 |  |  | 1753 |  |  | 1822 |  |  | 1891 |  |  | 1819.5 |  |  | 1816.5 |  |  | 1811.5 |  |  | 2015.5 |  |  | 1846 |  |  | 1864.5 |  |  | 1880.5 |  |  | 1739 |  |  | 1768 |  |  | 1861.5 |  |  | 1781.5 |  |  | 1838 |  |  | 1787.5 |  |  | 1905 |  |  | 1766.5 |  |  | 1735.5 |  |  | 1972 |  |  | 1921.5 |  |  | 1802.5 |  |  | 1721.5 |  |  | 1939 |  |  | 1779.5 |  |  | 1791.5 |  |  | 1804.5 |  |  | 1809.5 |  |  | 1821.5 |  |  | 1966.5 |  |  | 1757.5 |  |  | 1861.5 |  |  | 1840.5 |  |  | 1867.5 |  |  | 1818 |  |  | 1838.5 |  |  | 1886.5 |  |  | 1865.5 |  |  | 1897.5 |  |  | 1850.5 |  |  | 1906.5 |  |  | 1953.5 |  |  | 1817.5 |  |  | 1986 |  |  | 1767.5 |  |  | 1806 |  |  | 1944.5 |  |  | 2010.5 |  |  | 2002.5 |  |  | 1767.5 |  |  | 1769.5 |  |  | 1793.5 |  |  | 1719.5 |  |  | 1907.5 |  |  | 1905 |  |  | 1754.5 |  |  | 1864 |  |  | 1753.5 |  |  | 1734.5 |  |  | 1836.5 |  |  | 1915 |  |  | 1837.5 |  |  | 1909.5 |  |  | 1677 |  |  | 1791.5 |  |  | 1809 |  |  | 1824.5 |  |  | 1813.5 |  |  | 1794.5 |  |  | 1807 |  |  | 1907.5 |  |  | 2007.5 |  |  | 1758 |  |  | 1967.5 |  |  | 1736.5 |  |  | 1902 |  |  | 1816.5 |  |  | 1986.5 |  |  | 1921.5 |  |  | 1929.5 |  |  | 1751.5 |  |  | 1926.5 |  |  | 1757.5 |  |  | 1830.5 |  |  | 1744.5 |  |  | 1781.5 |  |  | 2018.5 |  |  | 1903 |  |  | 1920 |  |  | 1959.5 |  |  | 1859.5 |  |  | 1904
64 |  | 1766.5 |  |  | 2013.5 |  |  | 1873 |  |  | 1821.5 |  |  | 2044.5 |  |  | 1870.5 |  |  | 1967.5 |  |  | 1916.5 |  |  | 1913.5 |  |  | 1881.5 |  |  | 1803 |  |  | 1965.5 |  |  | 1962.5 |  |  | 1781.5 |  |  | 1768 |  |  | 1900.5 |  |  | 1994.5 |  |  | 1876.5 |  |  | 2027.5 |  |  | 1786.5 |  |  | 1874.5 |  |  | 1890.5 |  |  | 1917.5 |  |  | 1804.5 |  |  | 1742 |  |  | 1920.5 |  |  | 1852.5 |  |  | 1879.5 |  |  | 1948.5 |  |  | 1788 |  |  | 1881 |  |  | 1899.5 |  |  | 1726.5 |  |  | 1920.5 |  |  | 1745.5 |  |  | 1882 |  |  | 1815.5 |  |  | 1931 |  |  | 1837.5 |  |  | 1894.5 |  |  | 1752.5 |  |  | 1965.5 |  |  | 1743.5 |  |  | 1840 |  |  | 2036.5 |  |  | 1923 |  |  | 1820.5 |  |  | 1997.5 |  |  | 1904.5 |  |  | 1847.5 |  |  | 1830.5 |  |  | 1921.5 |  |  | 1892.5 |  |  | 1844.5 |  |  | 1968.5 |  |  | 1905.5 |  |  | 1785.5 |  |  | 1894 |  |  | 1907.5 |  |  | 1827.5 |  |  | 1841 |  |  | 1848.5 |  |  | 1981.5 |  |  | 1802.5 |  |  | 1793.5 |  |  | 1853 |  |  | 1947.5 |  |  | 1804 |  |  | 1731.5 |  |  | 1893.5 |  |  | 1856 |  |  | 1901.5 |  |  | 1869.5 |  |  | 1986.5 |  |  | 1956 |  |  | 1957 |  |  | 1839.5 |  |  | 1818.5 |  |  | 1751.5 |  |  | 1890.5 |  |  | 1817 |  |  | 1864.5 |  |  | 1902.5 |  |  | 1971.5 |  |  | 1940.5 |  |  | 1854.5 |  |  | 1927.5 |  |  | 1837.5 |  |  | 1832.5 |  |  | 1911.5 |  |  | 1933.5 |  |  | 1917 |  |  | 1731.5 |  |  | 1777 |  |  | 1877 |  |  | 1804 |  |  | 2030.5 |  |  | 1998.5 |  |  | 1762.5 |  |  | 1912.5 |  |  | 1830.5 |  |  | 1849 |  |  | 1832 |  |  | 1805.5 |  |  | 1841.5 |  |  | 1811.5 |  |  | 1906.5 |  |  | 1957.5 |  |  | 1972.5 |  |  | 1936.5 |  |  | 1985.5 |  |  | 1946.5 |  |  | 1873.5 |  |  | 1880.5 |  |  | 1855.5 |  |  | 1939.5 |  |  | 1958.5 |  |  | 1768.5 |  |  | 1896.5 |  |  | 1875.5 |  |  | 1894.5 |  |  | 1921.5 |  |  | 1845.5 |  |  | 1853.5 |  |  | 1933.5 |  |  | 1866 |  |  | 1820.5 |  |  | 1885.5 |  |  | 1822.5 |  |  | 1818.5 |  |  | 1938.5 |  |  | 1903 |  |  | 1776.5 |  |  | 1932.5 |  |  | 1768.5 |  |  | 1878.5 |  |  | 1923 |  |  | 1880.5 |  |  | 1912.5 |  |  | 1853 |  |  | 1890.5 |  |  | 1857 |  |  | 1911 |  |  | 1963.5 |  |  | 1914 |  |  | 1976.5 |  |  | 1851.5 |  |  | 1931.5 |  |  | 1818.5 |  |  | 1932.5 |  |  | 1909.5 |  |  | 1870.5 |  |  | 1919.5 |  |  | 2034.5 |  |  | 1924.5 |  |  | 1996 |  |  | 1855.5 |  |  | 1770 |  |  | 1842.5 |  |  | 1897.5 |  |  | 1840 |  |  | 1902.5 |  |  | 1840.5 |  |  | 1856.5 |  |  | 1794 |  |  | 1911.5 |  |  | 1789.5 |  |  | 1795.5 |  |  | 2002.5 |  |  | 1846.5 |  |  | 1844.5 |  |  | 1851 |  |  | 1841.5 |  |  | 1914.5 |  |  | 1831.5 |  |  | 1875.5 |  |  | 1915.5 |  |  | 1886.5 |  |  | 1782.5 |  |  | 1949 |  |  | 1955.5 |  |  | 1915.5 |  |  | 1921.5 |  |  | 1895.5 |  |  | 1778.5 |  |  | 1965.5 |  |  | 1932.5 |  |  | 1884.5 |  |  | 1948.5 |  |  | 1805.5 |  |  | 1896.5 |  |  | 1770.5 |  |  | 1684.5 |  |  | 1809 |  |  | 1822.5 |  |  | 1894.5 |  |  | 1866.5 |  |  | 1898.5 |  |  | 1908.5 |  |  | 1939.5 |  |  | 1947.5 |  |  | 1874.5 |  |  | 1926.5 |  |  | 1789.5 |  |  | 1845.5 |  |  | 1990.5 |  |  | 1846.5 |  |  | 1821.5 |  |  | 1866.5 |  |  | 1925.5 |  |  | 1936 |  |  | 1914.5 |  |  | 1839.5 |  |  | 1683 |  |  | 1997.5 |  |  | 1919 |  |  | 1772.5 |  |  | 1942.5 |  |  | 1990.5 |  |  | 1911.5 |  |  | 1810.5 |  |  | 1861.5 |  |  | 1871.5 |  |  | 1683.5 |  |  | 1776 |  |  | 1800.5 |  |  | 1746.5 |  |  | 1925.5 |  |  | 1795.5 |  |  | 1886 |  |  | 1805.5 |  |  | 1884.5 |  |  | 1938.5 |  |  | 1912.5 |  |  | 1954.5 |  |  | 1850.5 |  |  | 1869.5 |  |  | 1996.5 |  |  | 1925 |  |  | 1896 |  |  | 1831.5 |  |  | 1840.5 |  |  | 1830.5 |  |  | 1875 |  |  | 1969.5 |  |  | 1884.5 |  |  | 1815.5 |  |  | 1795 |  |  | 1894.5 |  |  | 1946.5 |  |  | 1749.5 |  |  | 1806.5 |  |  | 1860.5 |  |  | 1945.5 |  |  | 1894.5 |  |  | 1859.5 |  |  | 2016.5 |  |  | 1684 |  |  | 1804.5 |  |  | 1940.5 |  |  | 1870.5 |  |  | 1816.5 |  |  | 1820.5 |  |  | 1956 |  |  | 1836.5 |  |  | 1910.5 |  |  | 1913 |  |  | 2033.5 |  |  | 1903.5 |  |  | 2002 |  |  | 1861.5 |  |  | 1851.5 |  |  | 2014.5 |  |  | 1817.5 |  |  | 1891 |  |  | 1846 |  |  | 1888.5 |  |  | 1828.5 |  |  | 1915.5 |  |  | 1873.5 |  |  | 1951.5 |  |  | 1877.5 |  |  | 1840 |  |  | 1885.5 |  |  | 1888.5 |  |  | 1879 |  |  | 1822.5 |  |  | 1711.5 |  |  | 1927 |  |  | 1887.5 |  |  | 1802.5 |  |  | 1907.5 |  |  | 1837 |  |  | 1905.5 |  |  | 1824 |  |  | 1901.5 |  |  | 1752.5 |  |  | 1942.5 |  |  | 1839 |  |  | 1827.5 |  |  | 1981.5 |  |  | 1910.5 |  |  | 1909 |  |  | 1801.5 |  |  | 1719.5 |  |  | 2003.5 |  |  | 1936.5 |  |  | 1896.5 |  |  | 1894 |  |  | 1760.5 |  |  | 1969.5 |  |  | 1987.5 |  |  | 1817 |  |  | 1865 |  |  | 1992.5 |  |  | 1829.5 |  |  | 1773.5 |  |  | 1887.5 |  |  | 1880.5 |  |  | 1861.5 |  |  | 1846.5 |  |  | 1893.5 |  |  | 1811.5 |  |  | 1884.5 |  |  | 1895 |  |  | 1868.5 |  |  | 1922.5 |  |  | 2085.5 |  |  | 1940.5 |  |  | 1931 |  |  | 1885.5 |  |  | 1966.5 |  |  | 1849.5 |  |  | 1707.5 |  |  | 1975.5 |  |  | 1790 |  |  | 1859 |  |  | 1793 |  |  | 1973 |  |  | 1796.5 |  |  | 1881 |  |  | 1880.5 |  |  | 1836 |  |  | 1846.5 |  |  | 2000.5 |  |  | 1855.5 |  |  | 1854.5 |  |  | 1777.5 |  |  | 1916 |  |  | 1904.5 |  |  | 1985.5 |  |  | 1798.5 |  |  | 1896 |  |  | 1946.5 |  |  | 1786.5 |  |  | 1835.5 |  |  | 1909 |  |  | 1845.5 |  |  | 1775.5 |  |  | 1916.5 |  |  | 1815.5 |  |  | 1861.5 |  |  | 1825.5 |  |  | 1948.5 |  |  | 1837.5 |  |  | 1933.5 |  |  | 1772.5 |  |  | 1740 |  |  | 1857.5 |  |  | 1805.5 |  |  | 1773.5 |  |  | 1911.5 |  |  | 1992.5 |  |  | 1793 |  |  | 1905.5 |  |  | 1974 |  |  | 1822 |  |  | 1827.5 |  |  | 2011.5 |  |  | 1783.5 |  |  | 1780 |  |  | 1871.5 |  |  | 1885.5 |  |  | 1889.5 |  |  | 1770 |  |  | 1891.5 |  |  | 1726.5 |  |  | 1872.5 |  |  | 1777.5 |  |  | 1824.5 |  |  | 1846 |  |  | 1861.5 |  |  | 1921 |  |  | 1823.5 |  |  | 1761.5 |  |  | 1853.5 |  |  | 1934 |  |  | 1752.5 |  |  | 1836 |  |  | 1880 |  |  | 1835.5 |  |  | 1799.5 |  |  | 1843.5 |  |  | 1969.5 |  |  | 1975 |  |  | 1920.5 |  |  | 1807.5 |  |  | 1725.5 |  |  | 1832 |  |  | 1936.5 |  |  | 1797.5 |  |  | 1697.5 |  |  | 1857.5 |  |  | 1970 |  |  | 1759.5 |  |  | 1868.5 |  |  | 1946.5 |  |  | 1880.5 |  |  | 1868.5 |  |  | 1825.5 |  |  | 1941 |  |  | 1834.5 |  |  | 1797.5 |  |  | 1911 |  |  | 1790.5 |  |  | 1730.5 |  |  | 1825.5 |  |  | 1882 |  |  | 1899.5 |  |  | 1918.5 |  |  | 1866.5 |  |  | 1854.5 |  |  | 1928.5 |  |  | 1901 |  |  | 1863 |  |  | 1854.5 |  |  | 1928.5 |  |  | 1911.5 |  |  | 1742.5 |  |  | 1765 |  |  | 1939 |  |  | 1797 |  |  | 1924.5 |  |  | 1847 |  |  | 1872.5 |  |  | 1928.5 |  |  | 1872 |  |  | 1865.5 |  |  | 1914.5 |  |  | 1862.5 |  |  | 1993.5 |  |  | 1682.5 |  |  | 1857 |  |  | 1945 |  |  | 1747.5 |  |  | 1927.5 |  |  | 1841 |  |  | 1744.5 |  |  | 1895.5 |  |  | 1804 |  |  | 1975.5 |  |  | 2001.5 |  |  | 1817 |  |  | 1880.5 |  |  | 1906.5 |  |  | 1899 |  |  | 1871.5 |  |  | 1845 |  |  | 1995.5 |  |  | 2010 |  |  | 1833.5 |  |  | 1830.5 |  |  | 1913.5 |  |  | 1843.5 |  |  | 1875.5 |  |  | 1821.5 |  |  | 1920 |  |  | 1809.5 |  |  | 1868.5 |  |  | 1807.5 |  |  | 1828.5 |  |  | 1875.5 |  |  | 1852 |  |  | 1797.5 |  |  | 1903 |  |  | 1884.5 |  |  | 1787.5 |  |  | 1918.5 |  |  | 1840.5 |  |  | 1823.5 |  |  | 1924.5 |  |  | 1809.5 |  |  | 1953.5 |  |  | 1812.5 |  |  | 1838 |  |  | 1886.5 |  |  | 1767 |  |  | 1875 |  |  | 1860.5 |  |  | 1741 |  |  | 1761.5 |  |  | 1899.5 |  |  | 1932.5 |  |  | 1840.5 |  |  | 1931.5 |  |  | 1990.5 |  |  | 1897.5 |  |  | 1842 |  |  | 1942 |  |  | 1781.5 |  |  | 1784.5 |  |  | 1890 |  |  | 1795.5 |  |  | 1863.5 |  |  | 1793.5 |  |  | 1850.5 |  |  | 1818.5 |  |  | 1794 |  |  | 1833.5 |  |  | 1919.5 |  |  | 1791.5 |  |  | 1835 |  |  | 1897.5 |  |  | 1862.5 |  |  | 1893.5 |  |  | 2034.5 |  |  | 1908.5 |  |  | 1807.5 |  |  | 1969.5 |  |  | 1574.5 |  |  | 1840.5 |  |  | 1772 |  |  | 1969.5 |  |  | 1868.5 |  |  | 1940.5 |  |  | 1749.5 |  |  | 1837.5 |  |  | 1831.5 |  |  | 1801.5 |  |  | 1728 |  |  | 1747.5 |  |  | 1919.5 |  |  | 1958.5 |  |  | 1842 |  |  | 1855.5 |  |  | 1765 |  |  | 1789.5 |  |  | 1879.5 |  |  | 1803.5 |  |  | 1887 |  |  | 1784.5 |  |  | 1876 |  |  | 1863 |  |  | 1895.5 |  |  | 1853 |  |  | 1960 |  |  | 1945.5 |  |  | 1908.5 |  |  | 1739.5 |  |  | 1957 |  |  | 1917.5 |  |  | 1816.5 |  |  | 1752.5 |  |  | 1898.5 |  |  | 1824.5 |  |  | 1846.5 |  |  | 1808.5 |  |  | 1929.5 |  |  | 1860 |  |  | 1979.5 |  |  | 1824 |  |  | 1837.5 |  |  | 1799.5 |  |  | 1985.5 |  |  | 1844 |  |  | 1900 |  |  | 2003 |  |  | 1885.5 |  |  | 1856 |  |  | 1886.5 |  |  | 1993.5 |  |  | 1831.5 |  |  | 1827.5 |  |  | 1776.5 |  |  | 1935.5 |  |  | 1952.5 |  |  | 1909.5 |  |  | 1918 |  |  | 1775.5 |  |  | 1743.5 |  |  | 1922.5 |  |  | 1743.5 |  |  | 1810 |  |  | 1839.5 |  |  | 1887 |  |  | 1880.5 |  |  | 1908.5 |  |  | 1797.5 |  |  | 1793.5 |  |  | 1722 |  |  | 1789.5 |  |  | 1666 |  |  | 1811.5 |  |  | 1890.5 |  |  | 2013.5 |  |  | 1925.5 |  |  | 1891.5 |  |  | 1879.5 |  |  | 1735.5 |  |  | 1950.5 |  |  | 1851.5 |  |  | 1783 |  |  | 1879.5 |  |  | 1813.5 |  |  | 1813.5 |  |  | 1884.5 |  |  | 1921.5 |  |  | 1815 |  |  | 1822 |  |  | 1875.5 |  |  | 1801 |  |  | 2052.5 |  |  | 1846.5 |  |  | 1953.5 |  |  | 1953.5 |  |  | 1832.5 |  |  | 1914.5 |  |  | 1840.5 |  |  | 1930.5 |  |  | 1864 |  |  | 1871.5 |  |  | 2050.5 |  |  | 1869.5 |  |  | 1746 |  |  | 1814.5 |  |  | 1833.5 |  |  | 1921 |  |  | 1782 |  |  | 1910.5 |  |  | 1789 |  |  | 1750 |  |  | 1747.5 |  |  | 1892 |  |  | 2027.5 |  |  | 1907.5 |  |  | 1938.5 |  |  | 1841.5 |  |  | 1753.5 |  |  | 1827.5 |  |  | 1713.5 |  |  | 1850.5 |  |  | 1907.5 |  |  | 1820.5 |  |  | 1733 |  |  | 1745 |  |  | 1959.5 |  |  | 1903.5 |  |  | 1847.5 |  |  | 1938.5 |  |  | 1804.5 |  |  | 1850.5 |  |  | 1966.5 |  |  | 1833.5 |  |  | 2038 |  |  | 1792.5 |  |  | 1860 |  |  | 1818.5 |  |  | 2016.5 |  |  | 1893.5 |  |  | 1933 |  |  | 1822.5 |  |  | 1819.5 |  |  | 1842 |  |  | 1903.5 |  |  | 1823.5 |  |  | 1905.5 |  |  | 1878.5 |  |  | 1815.5 |  |  | 1879.5 |  |  | 1904 |  |  | 1790.5 |  |  | 1775.5 |  |  | 1910.5 |  |  | 1933.5 |  |  | 1878 |  |  | 1848.5 |  |  | 1984.5 |  |  | 1820 |  |  | 1901.5 |  |  | 1946.5 |  |  | 1893 |  |  | 1947.5 |  |  | 1952.5 |  |  | 1846.5 |  |  | 1825 |  |  | 1736.5 |  |  | 1866.5 |  |  | 1894 |  |  | 1878.5 |  |  | 1942.5 |  |  | 1851.5 |  |  | 1711.5 |  |  | 1944.5 |  |  | 2005.5 |  |  | 1801.5 |  |  | 1873 |  |  | 1847 |  |  | 1721.5 |  |  | 1940.5 |  |  | 1794.5 |  |  | 1903 |  |  | 2010.5 |  |  | 1794.5 |  |  | 1820.5 |  |  | 1726.5 |  |  | 1837.5 |  |  | 1865.5 |  |  | 1825.5 |  |  | 1942.5 |  |  | 1735.5 |  |  | 1903 |  |  | 1816.5 |  |  | 1820.5 |  |  | 1834.5 |  |  | 1926.5 |  |  | 1941.5 |  |  | 1862.5 |  |  | 1916.5 |  |  | 1896.5 |  |  | 1776.5 |  |  | 1959.5 |  |  | 1860.5 |  |  | 1822.5 |  |  | 1936.5 |  |  | 1953 |  |  | 1897.5 |  |  | 1933.5 |  |  | 1811 |  |  | 1910.5 |  |  | 1898.5 |  |  | 1946 |  |  | 1856.5 |  |  | 2005.5 |  |  | 1976.5 |  |  | 1949 |  |  | 1854.5 |  |  | 1928.5 |  |  | 1870.5 |  |  | 1708.5 |  |  | 1889.5 |  |  | 1758 |  |  | 1843.5 |  |  | 1897 |  |  | 1929 |  |  | 1996.5 |  |  | 1890.5 |  |  | 1836.5 |  |  | 1696.5 |  |  | 1868.5 |  |  | 1878.5 |  |  | 1827 |  |  | 1863.5 |  |  | 1841 |  |  | 1847.5 |  |  | 1897 |  |  | 1857 |  |  | 1970 |  |  | 1895.5 |  |  | 1806 |  |  | 1964.5 |  |  | 1925.5 |  |  | 1890.5 |  |  | 2028.5 |  |  | 1870.5 |  |  | 1950 |  |  | 1942.5 |  |  | 1918.5 |  |  | 2038.5 |  |  | 1882 |  |  | 1900.5 |  |  | 1756.5 |  |  | 1847.5 |  |  | 1895.5 |  |  | 1797 |  |  | 1923 |  |  | 1835 |  |  | 1881.5 |  |  | 1916 |  |  | 1981 |  |  | 1922.5 |  |  | 1862.5 |  |  | 1747.5 |  |  | 1884.5 |  |  | 1919.5 |  |  | 1925.5 |  |  | 1996.5 |  |  | 1827.5 |  |  | 1783.5 |  |  | 1816 |  |  | 1844.5 |  |  | 1825 |  |  | 1909.5 |  |  | 1900.5 |  |  | 1869.5 |  |  | 1952.5 |  |  | 1954 |  |  | 1917.5 |  |  | 1862 |  |  | 1816.5 |  |  | 1886.5 |  |  | 1861 |  |  | 1882 |  |  | 1857.5 |  |  | 1862 |  |  | 1921.5 |  |  | 1770.5 |  |  | 1795.5 |  |  | 1808.5 |  |  | 1890.5 |  |  | 1903.5 |  |  | 1726.5 |  |  | 1748 |  |  | 1936.5 |  |  | 1904.5 |  |  | 1858.5 |  |  | 1886.5 |  |  | 1770.5 |  |  | 1818.5 |  |  | 1958.5 |  |  | 1918.5 |  |  | 1978.5 |  |  | 1941.5 |  |  | 1794.5 |  |  | 1788.5 |  |  | 1880 |  |  | 1723.5 |  |  | 1818.5 |  |  | 1939 |  |  | 1797.5 |  |  | 1800.5 |  |  | 1838.5 |  |  | 1778.5 |  |  | 1987 |  |  | 2058.5 |  |  | 1852.5 |  |  | 1787.5 |  |  | 1929.5 |  |  | 1876 |  |  | 1838.5 |  |  | 1942.5 |  |  | 1925.5 |  |  | 1950.5 |  |  | 1783.5 |  |  | 1759.5 |  |  | 1886.5 |  |  | 1921.5 |  |  | 1880.5 |  |  | 1806.5 |  |  | 1975.5 |  |  | 1885 |  |  | 1851.5 |  |  | 1864.5 |  |  | 1993.5 |  |  | 1936.5 |  |  | 1814.5 |  |  | 1851.5 |  |  | 1950 |  |  | 1864.5 |  |  | 1822 |  |  | 1752.5 |  |  | 1889.5 |  |  | 1874.5 |  |  | 1846 |  |  | 1794 |  |  | 1853.5 |  |  | 1898.5 |  |  | 1675.5 |  |  | 1904.5 |  |  | 1843.5 |  |  | 1873.5 |  |  | 1847.5 |  |  | 1894.5 |  |  | 1849.5 |  |  | 1949.5 |  |  | 1803.5 |  |  | 1926.5 |  |  | 1794.5 |  |  | 1922.5 |  |  | 1917.5 |  |  | 1873.5 |  |  | 1850.5 |  |  | 1886.5 |  |  | 1849.5 |  |  | 1871.5 |  |  | 1880.5 |  |  | 1964.5 |  |  | 1869 |  |  | 1919.5 |  |  | 1866.5 |  |  | 1845.5 |  |  | 1845 |  |  | 1922.5 |  |  | 1850.5 |  |  | 1900.5 |  |  | 1889.5 |  |  | 1903 |  |  | 1757.5 |  |  | 1743.5 |  |  | 1792 |  |  | 1848 |  |  | 1930 |  |  | 1848.5 |  |  | 1831.5 |  |  | 1858.5 |  |  | 2062.5 |  |  | 1885 |  |  | 1879.5 |  |  | 1904.5 |  |  | 1763 |  |  | 1815 |  |  | 1885.5 |  |  | 1820.5 |  |  | 1877 |  |  | 1816.5 |  |  | 1944 |  |  | 1813.5 |  |  | 1774.5 |  |  | 2019 |  |  | 1945.5 |  |  | 1841.5 |  |  | 1747.5 |  |  | 1978 |  |  | 1818.5 |  |  | 1830.5 |  |  | 1830.5 |  |  | 1838.5 |  |  | 1860.5 |  |  | 1981.5 |  |  | 1783.5 |  |  | 1882.5 |  |  | 1887.5 |  |  | 1882.5 |  |  | 1857 |  |  | 1864.5 |  |  | 1901.5 |  |  | 1912.5 |  |  | 1912.5 |  |  | 1876.5 |  |  | 1945.5 |  |  | 1992.5 |  |  | 1846.5 |  |  | 2010 |  |  | 1806.5 |  |  | 1835 |  |  | 1991.5 |  |  | 2036.5 |  |  | 2041.5 |  |  | 1782.5 |  |  | 1816.5 |  |  | 1832.5 |  |  | 1758.5 |  |  | 1936.5 |  |  | 1931 |  |  | 1801.5 |  |  | 1890 |  |  | 1779.5 |  |  | 1749.5 |  |  | 1883.5 |  |  | 1962 |  |  | 1852.5 |  |  | 1938.5 |  |  | 1701 |  |  | 1830.5 |  |  | 1835 |  |  | 1845.5 |  |  | 1852.5 |  |  | 1820.5 |  |  | 1831 |  |  | 1931.5 |  |  | 2054.5 |  |  | 1797 |  |  | 1996.5 |  |  | 1765.5 |  |  | 1923 |  |  | 1845.5 |  |  | 2033.5 |  |  | 1960.5 |  |  | 1958.5 |  |  | 1777.5 |  |  | 1965.5 |  |  | 1778.5 |  |  | 1856.5 |  |  | 1783.5 |  |  | 1805.5 |  |  | 2033.5 |  |  | 1942 |  |  | 1941 |  |  | 1985.5 |  |  | 1898.5 |  |  | 1925
65 |  | 1792.5 |  |  | 2042.5 |  |  | 1912 |  |  | 1860.5 |  |  | 2083.5 |  |  | 1894.5 |  |  | 1982.5 |  |  | 1942.5 |  |  | 1952.5 |  |  | 1905.5 |  |  | 1842 |  |  | 1986.5 |  |  | 1983.5 |  |  | 1805.5 |  |  | 1797 |  |  | 1939.5 |  |  | 2023.5 |  |  | 1915.5 |  |  | 2053.5 |  |  | 1807.5 |  |  | 1903.5 |  |  | 1905.5 |  |  | 1956.5 |  |  | 1830.5 |  |  | 1766 |  |  | 1941.5 |  |  | 1873.5 |  |  | 1900.5 |  |  | 1995.5 |  |  | 1827 |  |  | 1928 |  |  | 1938.5 |  |  | 1773.5 |  |  | 1946.5 |  |  | 1760.5 |  |  | 1929 |  |  | 1830.5 |  |  | 1955 |  |  | 1876.5 |  |  | 1933.5 |  |  | 1776.5 |  |  | 1986.5 |  |  | 1782.5 |  |  | 1869 |  |  | 2062.5 |  |  | 1962 |  |  | 1846.5 |  |  | 2018.5 |  |  | 1943.5 |  |  | 1894.5 |  |  | 1856.5 |  |  | 1942.5 |  |  | 1913.5 |  |  | 1883.5 |  |  | 1992.5 |  |  | 1944.5 |  |  | 1814.5 |  |  | 1915 |  |  | 1928.5 |  |  | 1848.5 |  |  | 1880 |  |  | 1874.5 |  |  | 2002.5 |  |  | 1828.5 |  |  | 1817.5 |  |  | 1877 |  |  | 1971.5 |  |  | 1830 |  |  | 1746.5 |  |  | 1922.5 |  |  | 1895 |  |  | 1930.5 |  |  | 1898.5 |  |  | 2025.5 |  |  | 1971 |  |  | 1996 |  |  | 1868.5 |  |  | 1847.5 |  |  | 1766.5 |  |  | 1937.5 |  |  | 1843 |  |  | 1888.5 |  |  | 1941.5 |  |  | 2018.5 |  |  | 1979.5 |  |  | 1893.5 |  |  | 1953.5 |  |  | 1884.5 |  |  | 1871.5 |  |  | 1940.5 |  |  | 1959.5 |  |  | 1946 |  |  | 1757.5 |  |  | 1806 |  |  | 1892 |  |  | 1828 |  |  | 2054.5 |  |  | 2013.5 |  |  | 1783.5 |  |  | 1959.5 |  |  | 1859.5 |  |  | 1896 |  |  | 1871 |  |  | 1844.5 |  |  | 1862.5 |  |  | 1837.5 |  |  | 1921.5 |  |  | 1972.5 |  |  | 1987.5 |  |  | 1960.5 |  |  | 2006.5 |  |  | 1972.5 |  |  | 1912.5 |  |  | 1904.5 |  |  | 1879.5 |  |  | 1960.5 |  |  | 1984.5 |  |  | 1792.5 |  |  | 1911.5 |  |  | 1914.5 |  |  | 1933.5 |  |  | 1942.5 |  |  | 1866.5 |  |  | 1900.5 |  |  | 1954.5 |  |  | 1887 |  |  | 1867.5 |  |  | 1900.5 |  |  | 1851.5 |  |  | 1839.5 |  |  | 1962.5 |  |  | 1942 |  |  | 1823.5 |  |  | 1947.5 |  |  | 1789.5 |  |  | 1893.5 |  |  | 1952 |  |  | 1895.5 |  |  | 1941.5 |  |  | 1879 |  |  | 1916.5 |  |  | 1878 |  |  | 1958 |  |  | 1987.5 |  |  | 1940 |  |  | 2002.5 |  |  | 1866.5 |  |  | 1960.5 |  |  | 1847.5 |  |  | 1958.5 |  |  | 1933.5 |  |  | 1885.5 |  |  | 1958.5 |  |  | 2063.5 |  |  | 1953.5 |  |  | 2017 |  |  | 1879.5 |  |  | 1809 |  |  | 1889.5 |  |  | 1923.5 |  |  | 1879 |  |  | 1941.5 |  |  | 1864.5 |  |  | 1871.5 |  |  | 1841 |  |  | 1932.5 |  |  | 1836.5 |  |  | 1821.5 |  |  | 2026.5 |  |  | 1893.5 |  |  | 1873.5 |  |  | 1866 |  |  | 1870.5 |  |  | 1938.5 |  |  | 1860.5 |  |  | 1896.5 |  |  | 1939.5 |  |  | 1912.5 |  |  | 1797.5 |  |  | 1975 |  |  | 1994.5 |  |  | 1939.5 |  |  | 1950.5 |  |  | 1942.5 |  |  | 1802.5 |  |  | 2012.5 |  |  | 1953.5 |  |  | 1905.5 |  |  | 1969.5 |  |  | 1826.5 |  |  | 1925.5 |  |  | 1796.5 |  |  | 1699.5 |  |  | 1848 |  |  | 1861.5 |  |  | 1915.5 |  |  | 1895.5 |  |  | 1937.5 |  |  | 1934.5 |  |  | 1965.5 |  |  | 1986.5 |  |  | 1900.5 |  |  | 1941.5 |  |  | 1828.5 |  |  | 1871.5 |  |  | 2014.5 |  |  | 1885.5 |  |  | 1860.5 |  |  | 1892.5 |  |  | 1949.5 |  |  | 1957 |  |  | 1935.5 |  |  | 1868.5 |  |  | 1707 |  |  | 2026.5 |  |  | 1958 |  |  | 1796.5 |  |  | 1968.5 |  |  | 2029.5 |  |  | 1940.5 |  |  | 1849.5 |  |  | 1900.5 |  |  | 1895.5 |  |  | 1698.5 |  |  | 1823 |  |  | 1826.5 |  |  | 1767.5 |  |  | 1964.5 |  |  | 1834.5 |  |  | 1925 |  |  | 1820.5 |  |  | 1908.5 |  |  | 1977.5 |  |  | 1933.5 |  |  | 2001.5 |  |  | 1879.5 |  |  | 1890.5 |  |  | 2022.5 |  |  | 1949 |  |  | 1935 |  |  | 1878.5 |  |  | 1861.5 |  |  | 1869.5 |  |  | 1914 |  |  | 2016.5 |  |  | 1905.5 |  |  | 1839.5 |  |  | 1816 |  |  | 1933.5 |  |  | 1961.5 |  |  | 1788.5 |  |  | 1827.5 |  |  | 1881.5 |  |  | 1971.5 |  |  | 1933.5 |  |  | 1898.5 |  |  | 2055.5 |  |  | 1713 |  |  | 1828.5 |  |  | 1955.5 |  |  | 1917.5 |  |  | 1845.5 |  |  | 1846.5 |  |  | 1980 |  |  | 1857.5 |  |  | 1931.5 |  |  | 1952 |  |  | 2072.5 |  |  | 1950.5 |  |  | 2041 |  |  | 1890.5 |  |  | 1898.5 |  |  | 2038.5 |  |  | 1838.5 |  |  | 1915 |  |  | 1885 |  |  | 1912.5 |  |  | 1849.5 |  |  | 1941.5 |  |  | 1920.5 |  |  | 1990.5 |  |  | 1924.5 |  |  | 1879 |  |  | 1914.5 |  |  | 1917.5 |  |  | 1926 |  |  | 1843.5 |  |  | 1750.5 |  |  | 1951 |  |  | 1926.5 |  |  | 1823.5 |  |  | 1946.5 |  |  | 1858 |  |  | 1934.5 |  |  | 1850 |  |  | 1940.5 |  |  | 1778.5 |  |  | 1963.5 |  |  | 1878 |  |  | 1848.5 |  |  | 2020.5 |  |  | 1939.5 |  |  | 1938 |  |  | 1848.5 |  |  | 1740.5 |  |  | 2042.5 |  |  | 1983.5 |  |  | 1911.5 |  |  | 1933 |  |  | 1784.5 |  |  | 2008.5 |  |  | 2002.5 |  |  | 1843 |  |  | 1912 |  |  | 2016.5 |  |  | 1858.5 |  |  | 1812.5 |  |  | 1913.5 |  |  | 1909.5 |  |  | 1900.5 |  |  | 1870.5 |  |  | 1940.5 |  |  | 1832.5 |  |  | 1910.5 |  |  | 1916 |  |  | 1889.5 |  |  | 1961.5 |  |  | 2124.5 |  |  | 1964.5 |  |  | 1957 |  |  | 1932.5 |  |  | 1987.5 |  |  | 1888.5 |  |  | 1746.5 |  |  | 1999.5 |  |  | 1814 |  |  | 1906 |  |  | 1808 |  |  | 2002 |  |  | 1825.5 |  |  | 1928 |  |  | 1919.5 |  |  | 1860 |  |  | 1885.5 |  |  | 2015.5 |  |  | 1894.5 |  |  | 1883.5 |  |  | 1824.5 |  |  | 1945 |  |  | 1943.5 |  |  | 2011.5 |  |  | 1845.5 |  |  | 1917 |  |  | 1993.5 |  |  | 1833.5 |  |  | 1874.5 |  |  | 1933 |  |  | 1866.5 |  |  | 1799.5 |  |  | 1937.5 |  |  | 1854.5 |  |  | 1887.5 |  |  | 1864.5 |  |  | 1974.5 |  |  | 1884.5 |  |  | 1959.5 |  |  | 1819.5 |  |  | 1755 |  |  | 1872.5 |  |  | 1852.5 |  |  | 1802.5 |  |  | 1935.5 |  |  | 2013.5 |  |  | 1840 |  |  | 1952.5 |  |  | 2000 |  |  | 1837 |  |  | 1842.5 |  |  | 2050.5 |  |  | 1812.5 |  |  | 1819 |  |  | 1910.5 |  |  | 1932.5 |  |  | 1910.5 |  |  | 1809 |  |  | 1917.5 |  |  | 1741.5 |  |  | 1898.5 |  |  | 1806.5 |  |  | 1845.5 |  |  | 1875 |  |  | 1876.5 |  |  | 1968 |  |  | 1870.5 |  |  | 1776.5 |  |  | 1892.5 |  |  | 1958 |  |  | 1799.5 |  |  | 1883 |  |  | 1904 |  |  | 1850.5 |  |  | 1825.5 |  |  | 1890.5 |  |  | 2008.5 |  |  | 2014 |  |  | 1959.5 |  |  | 1846.5 |  |  | 1746.5 |  |  | 1856 |  |  | 1965.5 |  |  | 1821.5 |  |  | 1712.5 |  |  | 1883.5 |  |  | 1994 |  |  | 1780.5 |  |  | 1915.5 |  |  | 1972.5 |  |  | 1901.5 |  |  | 1889.5 |  |  | 1872.5 |  |  | 1988 |  |  | 1858.5 |  |  | 1812.5 |  |  | 1932 |  |  | 1805.5 |  |  | 1759.5 |  |  | 1864.5 |  |  | 1929 |  |  | 1914.5 |  |  | 1947.5 |  |  | 1905.5 |  |  | 1880.5 |  |  | 1975.5 |  |  | 1927 |  |  | 1902 |  |  | 1880.5 |  |  | 1952.5 |  |  | 1958.5 |  |  | 1763.5 |  |  | 1789 |  |  | 1978 |  |  | 1818 |  |  | 1971.5 |  |  | 1886 |  |  | 1898.5 |  |  | 1975.5 |  |  | 1896 |  |  | 1891.5 |  |  | 1935.5 |  |  | 1891.5 |  |  | 2008.5 |  |  | 1706.5 |  |  | 1886 |  |  | 1984 |  |  | 1786.5 |  |  | 1966.5 |  |  | 1880 |  |  | 1768.5 |  |  | 1924.5 |  |  | 1843 |  |  | 1999.5 |  |  | 2025.5 |  |  | 1843 |  |  | 1927.5 |  |  | 1932.5 |  |  | 1938 |  |  | 1910.5 |  |  | 1871 |  |  | 2021.5 |  |  | 2039 |  |  | 1857.5 |  |  | 1854.5 |  |  | 1937.5 |  |  | 1869.5 |  |  | 1914.5 |  |  | 1845.5 |  |  | 1959 |  |  | 1835.5 |  |  | 1907.5 |  |  | 1836.5 |  |  | 1852.5 |  |  | 1896.5 |  |  | 1873 |  |  | 1821.5 |  |  | 1929 |  |  | 1899.5 |  |  | 1802.5 |  |  | 1933.5 |  |  | 1869.5 |  |  | 1862.5 |  |  | 1939.5 |  |  | 1830.5 |  |  | 1979.5 |  |  | 1833.5 |  |  | 1867 |  |  | 1925.5 |  |  | 1793 |  |  | 1914 |  |  | 1889.5 |  |  | 1780 |  |  | 1785.5 |  |  | 1923.5 |  |  | 1971.5 |  |  | 1864.5 |  |  | 1978.5 |  |  | 2016.5 |  |  | 1944.5 |  |  | 1871 |  |  | 1981 |  |  | 1805.5 |  |  | 1823.5 |  |  | 1914 |  |  | 1824.5 |  |  | 1889.5 |  |  | 1808.5 |  |  | 1865.5 |  |  | 1839.5 |  |  | 1809 |  |  | 1862.5 |  |  | 1948.5 |  |  | 1820.5 |  |  | 1882 |  |  | 1936.5 |  |  | 1901.5 |  |  | 1940.5 |  |  | 2073.5 |  |  | 1947.5 |  |  | 1833.5 |  |  | 2008.5 |  |  | 1598.5 |  |  | 1864.5 |  |  | 1796 |  |  | 1998.5 |  |  | 1915.5 |  |  | 1964.5 |  |  | 1788.5 |  |  | 1861.5 |  |  | 1857.5 |  |  | 1827.5 |  |  | 1749 |  |  | 1776.5 |  |  | 1958.5 |  |  | 1997.5 |  |  | 1881 |  |  | 1894.5 |  |  | 1780 |  |  | 1804.5 |  |  | 1894.5 |  |  | 1824.5 |  |  | 1908 |  |  | 1799.5 |  |  | 1902 |  |  | 1878 |  |  | 1921.5 |  |  | 1879 |  |  | 2007 |  |  | 1984.5 |  |  | 1932.5 |  |  | 1778.5 |  |  | 1981 |  |  | 1956.5 |  |  | 1840.5 |  |  | 1799.5 |  |  | 1945.5 |  |  | 1839.5 |  |  | 1885.5 |  |  | 1855.5 |  |  | 1968.5 |  |  | 1884 |  |  | 2018.5 |  |  | 1848 |  |  | 1884.5 |  |  | 1838.5 |  |  | 2009.5 |  |  | 1868 |  |  | 1915 |  |  | 2042 |  |  | 1900.5 |  |  | 1880 |  |  | 1910.5 |  |  | 2032.5 |  |  | 1860.5 |  |  | 1848.5 |  |  | 1791.5 |  |  | 1959.5 |  |  | 1999.5 |  |  | 1933.5 |  |  | 1965 |  |  | 1804.5 |  |  | 1790.5 |  |  | 1951.5 |  |  | 1772.5 |  |  | 1836 |  |  | 1865.5 |  |  | 1926 |  |  | 1904.5 |  |  | 1934.5 |  |  | 1818.5 |  |  | 1808.5 |  |  | 1748 |  |  | 1828.5 |  |  | 1681 |  |  | 1837.5 |  |  | 1929.5 |  |  | 2052.5 |  |  | 1940.5 |  |  | 1917.5 |  |  | 1908.5 |  |  | 1759.5 |  |  | 1976.5 |  |  | 1890.5 |  |  | 1807 |  |  | 1905.5 |  |  | 1834.5 |  |  | 1828.5 |  |  | 1931.5 |  |  | 1947.5 |  |  | 1844 |  |  | 1843 |  |  | 1899.5 |  |  | 1816 |  |  | 2073.5 |  |  | 1885.5 |  |  | 2000.5 |  |  | 2000.5 |  |  | 1847.5 |  |  | 1940.5 |  |  | 1887.5 |  |  | 1945.5 |  |  | 1879 |  |  | 1900.5 |  |  | 2097.5 |  |  | 1893.5 |  |  | 1775 |  |  | 1840.5 |  |  | 1848.5 |  |  | 1968 |  |  | 1821 |  |  | 1931.5 |  |  | 1815 |  |  | 1776 |  |  | 1786.5 |  |  | 1931 |  |  | 2074.5 |  |  | 1933.5 |  |  | 1977.5 |  |  | 1867.5 |  |  | 1792.5 |  |  | 1842.5 |  |  | 1737.5 |  |  | 1874.5 |  |  | 1946.5 |  |  | 1849.5 |  |  | 1772 |  |  | 1774 |  |  | 1974.5 |  |  | 1942.5 |  |  | 1871.5 |  |  | 1959.5 |  |  | 1830.5 |  |  | 1889.5 |  |  | 1995.5 |  |  | 1854.5 |  |  | 2077 |  |  | 1831.5 |  |  | 1889 |  |  | 1857.5 |  |  | 2040.5 |  |  | 1940.5 |  |  | 1948 |  |  | 1869.5 |  |  | 1845.5 |  |  | 1881 |  |  | 1950.5 |  |  | 1862.5 |  |  | 1944.5 |  |  | 1904.5 |  |  | 1854.5 |  |  | 1908.5 |  |  | 1951 |  |  | 1829.5 |  |  | 1814.5 |  |  | 1939.5 |  |  | 1959.5 |  |  | 1899 |  |  | 1887.5 |  |  | 2013.5 |  |  | 1859 |  |  | 1925.5 |  |  | 1985.5 |  |  | 1932 |  |  | 1971.5 |  |  | 1973.5 |  |  | 1870.5 |  |  | 1872 |  |  | 1765.5 |  |  | 1887.5 |  |  | 1920 |  |  | 1917.5 |  |  | 1966.5 |  |  | 1872.5 |  |  | 1735.5 |  |  | 1973.5 |  |  | 2020.5 |  |  | 1825.5 |  |  | 1897 |  |  | 1876 |  |  | 1745.5 |  |  | 1961.5 |  |  | 1823.5 |  |  | 1950 |  |  | 2049.5 |  |  | 1823.5 |  |  | 1846.5 |  |  | 1765.5 |  |  | 1852.5 |  |  | 1904.5 |  |  | 1840.5 |  |  | 1981.5 |  |  | 1774.5 |  |  | 1942 |  |  | 1855.5 |  |  | 1846.5 |  |  | 1881.5 |  |  | 1973.5 |  |  | 1965.5 |  |  | 1901.5 |  |  | 1937.5 |  |  | 1935.5 |  |  | 1802.5 |  |  | 1985.5 |  |  | 1881.5 |  |  | 1851.5 |  |  | 1960.5 |  |  | 1992 |  |  | 1926.5 |  |  | 1959.5 |  |  | 1835 |  |  | 1939.5 |  |  | 1924.5 |  |  | 1972 |  |  | 1895.5 |  |  | 2031.5 |  |  | 1991.5 |  |  | 1988 |  |  | 1883.5 |  |  | 1975.5 |  |  | 1917.5 |  |  | 1732.5 |  |  | 1928.5 |  |  | 1773 |  |  | 1882.5 |  |  | 1921 |  |  | 1950 |  |  | 2043.5 |  |  | 1929.5 |  |  | 1860.5 |  |  | 1720.5 |  |  | 1883.5 |  |  | 1902.5 |  |  | 1848 |  |  | 1884.5 |  |  | 1867 |  |  | 1871.5 |  |  | 1912 |  |  | 1896 |  |  | 2009 |  |  | 1924.5 |  |  | 1830 |  |  | 1990.5 |  |  | 1949.5 |  |  | 1916.5 |  |  | 2067.5 |  |  | 1896.5 |  |  | 1979 |  |  | 1971.5 |  |  | 1957.5 |  |  | 2077.5 |  |  | 1908 |  |  | 1924.5 |  |  | 1785.5 |  |  | 1873.5 |  |  | 1934.5 |  |  | 1836 |  |  | 1938 |  |  | 1856 |  |  | 1905.5 |  |  | 1955 |  |  | 2020 |  |  | 1961.5 |  |  | 1901.5 |  |  | 1771.5 |  |  | 1923.5 |  |  | 1948.5 |  |  | 1949.5 |  |  | 2035.5 |  |  | 1842.5 |  |  | 1809.5 |  |  | 1840 |  |  | 1870.5 |  |  | 1840 |  |  | 1935.5 |  |  | 1926.5 |  |  | 1898.5 |  |  | 1967.5 |  |  | 1983 |  |  | 1964.5 |  |  | 1886 |  |  | 1831.5 |  |  | 1907.5 |  |  | 1885 |  |  | 1911 |  |  | 1883.5 |  |  | 1901 |  |  | 1947.5 |  |  | 1785.5 |  |  | 1842.5 |  |  | 1834.5 |  |  | 1914.5 |  |  | 1932.5 |  |  | 1765.5 |  |  | 1769 |  |  | 1951.5 |  |  | 1943.5 |  |  | 1897.5 |  |  | 1925.5 |  |  | 1799.5 |  |  | 1865.5 |  |  | 2005.5 |  |  | 1944.5 |  |  | 2002.5 |  |  | 1965.5 |  |  | 1823.5 |  |  | 1803.5 |  |  | 1904 |  |  | 1749.5 |  |  | 1865.5 |  |  | 1968 |  |  | 1821.5 |  |  | 1829.5 |  |  | 1877.5 |  |  | 1817.5 |  |  | 2016 |  |  | 2105.5 |  |  | 1881.5 |  |  | 1808.5 |  |  | 1976.5 |  |  | 1902 |  |  | 1867.5 |  |  | 1968.5 |  |  | 1940.5 |  |  | 1965.5 |  |  | 1822.5 |  |  | 1783.5 |  |  | 1912.5 |  |  | 1945.5 |  |  | 1909.5 |  |  | 1835.5 |  |  | 2014.5 |  |  | 1924 |  |  | 1890.5 |  |  | 1890.5 |  |  | 2040.5 |  |  | 1975.5 |  |  | 1838.5 |  |  | 1866.5 |  |  | 1979 |  |  | 1893.5 |  |  | 1861 |  |  | 1767.5 |  |  | 1928.5 |  |  | 1900.5 |  |  | 1867 |  |  | 1833 |  |  | 1892.5 |  |  | 1924.5 |  |  | 1722.5 |  |  | 1943.5 |  |  | 1890.5 |  |  | 1912.5 |  |  | 1868.5 |  |  | 1933.5 |  |  | 1878.5 |  |  | 1978.5 |  |  | 1827.5 |  |  | 1965.5 |  |  | 1818.5 |  |  | 1946.5 |  |  | 1956.5 |  |  | 1888.5 |  |  | 1897.5 |  |  | 1915.5 |  |  | 1888.5 |  |  | 1897.5 |  |  | 1906.5 |  |  | 1985.5 |  |  | 1916 |  |  | 1934.5 |  |  | 1905.5 |  |  | 1884.5 |  |  | 1860 |  |  | 1946.5 |  |  | 1871.5 |  |  | 1929.5 |  |  | 1904.5 |  |  | 1932 |  |  | 1772.5 |  |  | 1790.5 |  |  | 1821 |  |  | 1872 |  |  | 1969 |  |  | 1874.5 |  |  | 1878.5 |  |  | 1905.5 |  |  | 2101.5 |  |  | 1932 |  |  | 1908.5 |  |  | 1930.5 |  |  | 1802 |  |  | 1844 |  |  | 1906.5 |  |  | 1859.5 |  |  | 1916 |  |  | 1845.5 |  |  | 1959 |  |  | 1837.5 |  |  | 1798.5 |  |  | 2043 |  |  | 1969.5 |  |  | 1867.5 |  |  | 1776.5 |  |  | 2004 |  |  | 1844.5 |  |  | 1845.5 |  |  | 1854.5 |  |  | 1853.5 |  |  | 1884.5 |  |  | 2010.5 |  |  | 1807.5 |  |  | 1929.5 |  |  | 1926.5 |  |  | 1929.5 |  |  | 1883 |  |  | 1903.5 |  |  | 1922.5 |  |  | 1933.5 |  |  | 1951.5 |  |  | 1900.5 |  |  | 1984.5 |  |  | 2013.5 |  |  | 1872.5 |  |  | 2049 |  |  | 1832.5 |  |  | 1874 |  |  | 2006.5 |  |  | 2083.5 |  |  | 2062.5 |  |  | 1829.5 |  |  | 1831.5 |  |  | 1861.5 |  |  | 1782.5 |  |  | 1951.5 |  |  | 1957 |  |  | 1848.5 |  |  | 1916 |  |  | 1818.5 |  |  | 1788.5 |  |  | 1904.5 |  |  | 1977 |  |  | 1891.5 |  |  | 1959.5 |  |  | 1725 |  |  | 1877.5 |  |  | 1859 |  |  | 1892.5 |  |  | 1867.5 |  |  | 1841.5 |  |  | 1870 |  |  | 1978.5 |  |  | 2093.5 |  |  | 1812 |  |  | 2035.5 |  |  | 1812.5 |  |  | 1947 |  |  | 1884.5 |  |  | 2072.5 |  |  | 1999.5 |  |  | 2005.5 |  |  | 1803.5 |  |  | 1980.5 |  |  | 1793.5 |  |  | 1882.5 |  |  | 1798.5 |  |  | 1829.5 |  |  | 2062.5 |  |  | 1963 |  |  | 1956 |  |  | 2024.5 |  |  | 1913.5 |  |  | 1949
66 |  | 1821.5 |  |  | 2063.5 |  |  | 1933 |  |  | 1899.5 |  |  | 2122.5 |  |  | 1941.5 |  |  | 2011.5 |  |  | 1966.5 |  |  | 1976.5 |  |  | 1944.5 |  |  | 1881 |  |  | 2025.5 |  |  | 2009.5 |  |  | 1826.5 |  |  | 1826 |  |  | 1978.5 |  |  | 2052.5 |  |  | 1944.5 |  |  | 2074.5 |  |  | 1828.5 |  |  | 1942.5 |  |  | 1952.5 |  |  | 1982.5 |  |  | 1854.5 |  |  | 1792 |  |  | 1980.5 |  |  | 1902.5 |  |  | 1921.5 |  |  | 2019.5 |  |  | 1842 |  |  | 1952 |  |  | 1962.5 |  |  | 1794.5 |  |  | 1967.5 |  |  | 1807.5 |  |  | 1968 |  |  | 1845.5 |  |  | 1984 |  |  | 1891.5 |  |  | 1948.5 |  |  | 1815.5 |  |  | 2015.5 |  |  | 1821.5 |  |  | 1916 |  |  | 2109.5 |  |  | 2001 |  |  | 1885.5 |  |  | 2057.5 |  |  | 1982.5 |  |  | 1920.5 |  |  | 1885.5 |  |  | 1957.5 |  |  | 1952.5 |  |  | 1904.5 |  |  | 2018.5 |  |  | 1983.5 |  |  | 1853.5 |  |  | 1944 |  |  | 1949.5 |  |  | 1863.5 |  |  | 1919 |  |  | 1903.5 |  |  | 2017.5 |  |  | 1875.5 |  |  | 1838.5 |  |  | 1924 |  |  | 1986.5 |  |  | 1845 |  |  | 1785.5 |  |  | 1969.5 |  |  | 1916 |  |  | 1945.5 |  |  | 1937.5 |  |  | 2064.5 |  |  | 2018 |  |  | 2017 |  |  | 1883.5 |  |  | 1868.5 |  |  | 1792.5 |  |  | 1952.5 |  |  | 1882 |  |  | 1935.5 |  |  | 1980.5 |  |  | 2057.5 |  |  | 2005.5 |  |  | 1919.5 |  |  | 2000.5 |  |  | 1908.5 |  |  | 1910.5 |  |  | 1969.5 |  |  | 1983.5 |  |  | 1985 |  |  | 1781.5 |  |  | 1835 |  |  | 1916 |  |  | 1875 |  |  | 2093.5 |  |  | 2039.5 |  |  | 1798.5 |  |  | 1985.5 |  |  | 1883.5 |  |  | 1925 |  |  | 1895 |  |  | 1859.5 |  |  | 1877.5 |  |  | 1866.5 |  |  | 1968.5 |  |  | 1993.5 |  |  | 2026.5 |  |  | 1981.5 |  |  | 2030.5 |  |  | 2011.5 |  |  | 1941.5 |  |  | 1933.5 |  |  | 1900.5 |  |  | 1975.5 |  |  | 2023.5 |  |  | 1807.5 |  |  | 1937.5 |  |  | 1961.5 |  |  | 1962.5 |  |  | 1981.5 |  |  | 1895.5 |  |  | 1929.5 |  |  | 1993.5 |  |  | 1934 |  |  | 1893.5 |  |  | 1915.5 |  |  | 1872.5 |  |  | 1868.5 |  |  | 1977.5 |  |  | 1963 |  |  | 1862.5 |  |  | 1994.5 |  |  | 1810.5 |  |  | 1919.5 |  |  | 1991 |  |  | 1916.5 |  |  | 1970.5 |  |  | 1903 |  |  | 1942.5 |  |  | 1899 |  |  | 1982 |  |  | 2034.5 |  |  | 1987 |  |  | 2049.5 |  |  | 1890.5 |  |  | 1989.5 |  |  | 1862.5 |  |  | 1979.5 |  |  | 1948.5 |  |  | 1914.5 |  |  | 1979.5 |  |  | 2084.5 |  |  | 2000.5 |  |  | 2038 |  |  | 1900.5 |  |  | 1830 |  |  | 1904.5 |  |  | 1949.5 |  |  | 1926 |  |  | 1962.5 |  |  | 1893.5 |  |  | 1910.5 |  |  | 1862 |  |  | 1958.5 |  |  | 1865.5 |  |  | 1860.5 |  |  | 2073.5 |  |  | 1932.5 |  |  | 1902.5 |  |  | 1913 |  |  | 1896.5 |  |  | 1967.5 |  |  | 1881.5 |  |  | 1911.5 |  |  | 1978.5 |  |  | 1959.5 |  |  | 1818.5 |  |  | 2022 |  |  | 2018.5 |  |  | 1965.5 |  |  | 1989.5 |  |  | 1989.5 |  |  | 1831.5 |  |  | 2041.5 |  |  | 1977.5 |  |  | 1931.5 |  |  | 1984.5 |  |  | 1865.5 |  |  | 1949.5 |  |  | 1820.5 |  |  | 1738.5 |  |  | 1872 |  |  | 1900.5 |  |  | 1936.5 |  |  | 1921.5 |  |  | 1961.5 |  |  | 1960.5 |  |  | 2004.5 |  |  | 2007.5 |  |  | 1924.5 |  |  | 1956.5 |  |  | 1849.5 |  |  | 1895.5 |  |  | 2053.5 |  |  | 1914.5 |  |  | 1899.5 |  |  | 1918.5 |  |  | 1964.5 |  |  | 1996 |  |  | 1974.5 |  |  | 1889.5 |  |  | 1728 |  |  | 2065.5 |  |  | 1997 |  |  | 1825.5 |  |  | 1997.5 |  |  | 2068.5 |  |  | 1964.5 |  |  | 1873.5 |  |  | 1929.5 |  |  | 1934.5 |  |  | 1727.5 |  |  | 1862 |  |  | 1847.5 |  |  | 1796.5 |  |  | 2003.5 |  |  | 1860.5 |  |  | 1964 |  |  | 1846.5 |  |  | 1947.5 |  |  | 2001.5 |  |  | 1954.5 |  |  | 2016.5 |  |  | 1908.5 |  |  | 1916.5 |  |  | 2051.5 |  |  | 1996 |  |  | 1959 |  |  | 1902.5 |  |  | 1882.5 |  |  | 1916.5 |  |  | 1935 |  |  | 2055.5 |  |  | 1944.5 |  |  | 1886.5 |  |  | 1840 |  |  | 1980.5 |  |  | 2000.5 |  |  | 1835.5 |  |  | 1853.5 |  |  | 1902.5 |  |  | 2010.5 |  |  | 1957.5 |  |  | 1927.5 |  |  | 2081.5 |  |  | 1760 |  |  | 1854.5 |  |  | 1981.5 |  |  | 1956.5 |  |  | 1884.5 |  |  | 1867.5 |  |  | 2027 |  |  | 1883.5 |  |  | 1960.5 |  |  | 1976 |  |  | 2087.5 |  |  | 1974.5 |  |  | 2070 |  |  | 1929.5 |  |  | 1937.5 |  |  | 2062.5 |  |  | 1877.5 |  |  | 1930 |  |  | 1924 |  |  | 1927.5 |  |  | 1896.5 |  |  | 1956.5 |  |  | 1946.5 |  |  | 2029.5 |  |  | 1953.5 |  |  | 1894 |  |  | 1940.5 |  |  | 1946.5 |  |  | 1950 |  |  | 1882.5 |  |  | 1765.5 |  |  | 1980 |  |  | 1965.5 |  |  | 1847.5 |  |  | 1985.5 |  |  | 1882 |  |  | 1973.5 |  |  | 1876 |  |  | 1966.5 |  |  | 1793.5 |  |  | 1992.5 |  |  | 1899 |  |  | 1877.5 |  |  | 2035.5 |  |  | 1978.5 |  |  | 1977 |  |  | 1887.5 |  |  | 1755.5 |  |  | 2066.5 |  |  | 2022.5 |  |  | 1935.5 |  |  | 1972 |  |  | 1810.5 |  |  | 2047.5 |  |  | 2017.5 |  |  | 1867 |  |  | 1941 |  |  | 2040.5 |  |  | 1879.5 |  |  | 1838.5 |  |  | 1937.5 |  |  | 1935.5 |  |  | 1926.5 |  |  | 1917.5 |  |  | 1979.5 |  |  | 1856.5 |  |  | 1925.5 |  |  | 1955 |  |  | 1915.5 |  |  | 2000.5 |  |  | 2171.5 |  |  | 1990.5 |  |  | 1981 |  |  | 1971.5 |  |  | 2034.5 |  |  | 1903.5 |  |  | 1772.5 |  |  | 2020.5 |  |  | 1843 |  |  | 1945 |  |  | 1829 |  |  | 2041 |  |  | 1851.5 |  |  | 1952 |  |  | 1945.5 |  |  | 1899 |  |  | 1924.5 |  |  | 2054.5 |  |  | 1915.5 |  |  | 1904.5 |  |  | 1845.5 |  |  | 1969 |  |  | 1982.5 |  |  | 2058.5 |  |  | 1871.5 |  |  | 1943 |  |  | 2019.5 |  |  | 1857.5 |  |  | 1921.5 |  |  | 1959 |  |  | 1905.5 |  |  | 1825.5 |  |  | 1984.5 |  |  | 1880.5 |  |  | 1934.5 |  |  | 1888.5 |  |  | 2003.5 |  |  | 1908.5 |  |  | 1974.5 |  |  | 1834.5 |  |  | 1776 |  |  | 1898.5 |  |  | 1878.5 |  |  | 1831.5 |  |  | 1964.5 |  |  | 2034.5 |  |  | 1887 |  |  | 1967.5 |  |  | 2047 |  |  | 1863 |  |  | 1857.5 |  |  | 2089.5 |  |  | 1833.5 |  |  | 1840 |  |  | 1949.5 |  |  | 1958.5 |  |  | 1934.5 |  |  | 1830 |  |  | 1932.5 |  |  | 1756.5 |  |  | 1945.5 |  |  | 1853.5 |  |  | 1884.5 |  |  | 1890 |  |  | 1902.5 |  |  | 2007 |  |  | 1899.5 |  |  | 1791.5 |  |  | 1921.5 |  |  | 1979 |  |  | 1825.5 |  |  | 1912 |  |  | 1943 |  |  | 1879.5 |  |  | 1854.5 |  |  | 1911.5 |  |  | 2034.5 |  |  | 2053 |  |  | 1988.5 |  |  | 1872.5 |  |  | 1761.5 |  |  | 1895 |  |  | 1991.5 |  |  | 1845.5 |  |  | 1727.5 |  |  | 1930.5 |  |  | 2033 |  |  | 1804.5 |  |  | 1954.5 |  |  | 1998.5 |  |  | 1916.5 |  |  | 1928.5 |  |  | 1901.5 |  |  | 2027 |  |  | 1887.5 |  |  | 1851.5 |  |  | 1947 |  |  | 1829.5 |  |  | 1783.5 |  |  | 1903.5 |  |  | 1950 |  |  | 1953.5 |  |  | 1994.5 |  |  | 1929.5 |  |  | 1909.5 |  |  | 1996.5 |  |  | 1974 |  |  | 1923 |  |  | 1927.5 |  |  | 1999.5 |  |  | 1987.5 |  |  | 1784.5 |  |  | 1813 |  |  | 1993 |  |  | 1842 |  |  | 1997.5 |  |  | 1925 |  |  | 1937.5 |  |  | 2004.5 |  |  | 1911 |  |  | 1906.5 |  |  | 1974.5 |  |  | 1930.5 |  |  | 2037.5 |  |  | 1745.5 |  |  | 1925 |  |  | 2023 |  |  | 1833.5 |  |  | 1987.5 |  |  | 1895 |  |  | 1783.5 |  |  | 1953.5 |  |  | 1882 |  |  | 2028.5 |  |  | 2054.5 |  |  | 1858 |  |  | 1956.5 |  |  | 1961.5 |  |  | 1953 |  |  | 1934.5 |  |  | 1910 |  |  | 2068.5 |  |  | 2054 |  |  | 1878.5 |  |  | 1878.5 |  |  | 1952.5 |  |  | 1908.5 |  |  | 1940.5 |  |  | 1866.5 |  |  | 1985 |  |  | 1874.5 |  |  | 1954.5 |  |  | 1875.5 |  |  | 1878.5 |  |  | 1911.5 |  |  | 1912 |  |  | 1850.5 |  |  | 1944 |  |  | 1925.5 |  |  | 1831.5 |  |  | 1980.5 |  |  | 1898.5 |  |  | 1888.5 |  |  | 1965.5 |  |  | 1845.5 |  |  | 2018.5 |  |  | 1857.5 |  |  | 1882 |  |  | 1964.5 |  |  | 1814 |  |  | 1938 |  |  | 1910.5 |  |  | 1795 |  |  | 1806.5 |  |  | 1962.5 |  |  | 2000.5 |  |  | 1893.5 |  |  | 1999.5 |  |  | 2031.5 |  |  | 1983.5 |  |  | 1895 |  |  | 2020 |  |  | 1834.5 |  |  | 1862.5 |  |  | 1940 |  |  | 1848.5 |  |  | 1913.5 |  |  | 1834.5 |  |  | 1886.5 |  |  | 1878.5 |  |  | 1824 |  |  | 1891.5 |  |  | 1972.5 |  |  | 1859.5 |  |  | 1897 |  |  | 1960.5 |  |  | 1922.5 |  |  | 1955.5 |  |  | 2088.5 |  |  | 1973.5 |  |  | 1880.5 |  |  | 2037.5 |  |  | 1613.5 |  |  | 1893.5 |  |  | 1817 |  |  | 2037.5 |  |  | 1939.5 |  |  | 1988.5 |  |  | 1827.5 |  |  | 1876.5 |  |  | 1896.5 |  |  | 1856.5 |  |  | 1775 |  |  | 1815.5 |  |  | 1979.5 |  |  | 2018.5 |  |  | 1896 |  |  | 1918.5 |  |  | 1819 |  |  | 1843.5 |  |  | 1933.5 |  |  | 1863.5 |  |  | 1934 |  |  | 1828.5 |  |  | 1926 |  |  | 1925 |  |  | 1936.5 |  |  | 1903 |  |  | 2022 |  |  | 2031.5 |  |  | 1971.5 |  |  | 1825.5 |  |  | 1996 |  |  | 1980.5 |  |  | 1887.5 |  |  | 1820.5 |  |  | 1984.5 |  |  | 1878.5 |  |  | 1906.5 |  |  | 1879.5 |  |  | 1992.5 |  |  | 1931 |  |  | 2039.5 |  |  | 1869 |  |  | 1923.5 |  |  | 1864.5 |  |  | 2033.5 |  |  | 1889 |  |  | 1936 |  |  | 2081 |  |  | 1915.5 |  |  | 1906 |  |  | 1949.5 |  |  | 2071.5 |  |  | 1875.5 |  |  | 1887.5 |  |  | 1812.5 |  |  | 1985.5 |  |  | 2025.5 |  |  | 1962.5 |  |  | 1980 |  |  | 1830.5 |  |  | 1829.5 |  |  | 1966.5 |  |  | 1819.5 |  |  | 1875 |  |  | 1904.5 |  |  | 1950 |  |  | 1951.5 |  |  | 1960.5 |  |  | 1842.5 |  |  | 1837.5 |  |  | 1787 |  |  | 1852.5 |  |  | 1710 |  |  | 1861.5 |  |  | 1950.5 |  |  | 2073.5 |  |  | 1979.5 |  |  | 1946.5 |  |  | 1923.5 |  |  | 1780.5 |  |  | 2015.5 |  |  | 1916.5 |  |  | 1846 |  |  | 1934.5 |  |  | 1873.5 |  |  | 1867.5 |  |  | 1978.5 |  |  | 1994.5 |  |  | 1883 |  |  | 1872 |  |  | 1920.5 |  |  | 1831 |  |  | 2102.5 |  |  | 1924.5 |  |  | 2026.5 |  |  | 2015.5 |  |  | 1886.5 |  |  | 1979.5 |  |  | 1902.5 |  |  | 1969.5 |  |  | 1908 |  |  | 1929.5 |  |  | 2123.5 |  |  | 1919.5 |  |  | 1822 |  |  | 1855.5 |  |  | 1887.5 |  |  | 1994 |  |  | 1836 |  |  | 1978.5 |  |  | 1836 |  |  | 1815 |  |  | 1807.5 |  |  | 1978 |  |  | 2121.5 |  |  | 1948.5 |  |  | 2024.5 |  |  | 1893.5 |  |  | 1816.5 |  |  | 1866.5 |  |  | 1784.5 |  |  | 1913.5 |  |  | 1972.5 |  |  | 1878.5 |  |  | 1801 |  |  | 1821 |  |  | 2013.5 |  |  | 1968.5 |  |  | 1910.5 |  |  | 1974.5 |  |  | 1869.5 |  |  | 1910.5 |  |  | 2024.5 |  |  | 1893.5 |  |  | 2124 |  |  | 1878.5 |  |  | 1918 |  |  | 1872.5 |  |  | 2069.5 |  |  | 1955.5 |  |  | 1987 |  |  | 1898.5 |  |  | 1871.5 |  |  | 1910 |  |  | 1974.5 |  |  | 1883.5 |  |  | 1968.5 |  |  | 1933.5 |  |  | 1880.5 |  |  | 1947.5 |  |  | 1990 |  |  | 1868.5 |  |  | 1853.5 |  |  | 1978.5 |  |  | 2006.5 |  |  | 1938 |  |  | 1913.5 |  |  | 2037.5 |  |  | 1898 |  |  | 1964.5 |  |  | 2032.5 |  |  | 1953 |  |  | 1992.5 |  |  | 2002.5 |  |  | 1896.5 |  |  | 1911 |  |  | 1780.5 |  |  | 1908.5 |  |  | 1935 |  |  | 1941.5 |  |  | 1981.5 |  |  | 1911.5 |  |  | 1764.5 |  |  | 2020.5 |  |  | 2059.5 |  |  | 1864.5 |  |  | 1912 |  |  | 1891 |  |  | 1784.5 |  |  | 1982.5 |  |  | 1870.5 |  |  | 1976 |  |  | 2064.5 |  |  | 1852.5 |  |  | 1870.5 |  |  | 1804.5 |  |  | 1891.5 |  |  | 1928.5 |  |  | 1866.5 |  |  | 1996.5 |  |  | 1789.5 |  |  | 1957 |  |  | 1879.5 |  |  | 1867.5 |  |  | 1907.5 |  |  | 2002.5 |  |  | 1989.5 |  |  | 1940.5 |  |  | 1984.5 |  |  | 1982.5 |  |  | 1849.5 |  |  | 2000.5 |  |  | 1910.5 |  |  | 1890.5 |  |  | 1981.5 |  |  | 2018 |  |  | 1955.5 |  |  | 1974.5 |  |  | 1882 |  |  | 1978.5 |  |  | 1963.5 |  |  | 2019 |  |  | 1934.5 |  |  | 2057.5 |  |  | 2015.5 |  |  | 2014 |  |  | 1909.5 |  |  | 1999.5 |  |  | 1946.5 |  |  | 1753.5 |  |  | 1967.5 |  |  | 1799 |  |  | 1897.5 |  |  | 1942 |  |  | 1974 |  |  | 2067.5 |  |  | 1968.5 |  |  | 1881.5 |  |  | 1746.5 |  |  | 1898.5 |  |  | 1949.5 |  |  | 1872 |  |  | 1923.5 |  |  | 1914 |  |  | 1886.5 |  |  | 1933 |  |  | 1922 |  |  | 2048 |  |  | 1963.5 |  |  | 1869 |  |  | 2011.5 |  |  | 1973.5 |  |  | 1955.5 |  |  | 2093.5 |  |  | 1917.5 |  |  | 2018 |  |  | 1995.5 |  |  | 1981.5 |  |  | 2092.5 |  |  | 1932 |  |  | 1953.5 |  |  | 1811.5 |  |  | 1912.5 |  |  | 1958.5 |  |  | 1875 |  |  | 1967 |  |  | 1880 |  |  | 1920.5 |  |  | 1979 |  |  | 2044 |  |  | 1990.5 |  |  | 1927.5 |  |  | 1797.5 |  |  | 1949.5 |  |  | 1963.5 |  |  | 1988.5 |  |  | 2082.5 |  |  | 1868.5 |  |  | 1824.5 |  |  | 1869 |  |  | 1899.5 |  |  | 1887 |  |  | 1950.5 |  |  | 1941.5 |  |  | 1937.5 |  |  | 1993.5 |  |  | 2022 |  |  | 2003.5 |  |  | 1925 |  |  | 1846.5 |  |  | 1928.5 |  |  | 1911 |  |  | 1950 |  |  | 1898.5 |  |  | 1925 |  |  | 1986.5 |  |  | 1824.5 |  |  | 1889.5 |  |  | 1849.5 |  |  | 1940.5 |  |  | 1971.5 |  |  | 1789.5 |  |  | 1790 |  |  | 1966.5 |  |  | 1958.5 |  |  | 1926.5 |  |  | 1940.5 |  |  | 1838.5 |  |  | 1886.5 |  |  | 2020.5 |  |  | 1959.5 |  |  | 2023.5 |  |  | 2004.5 |  |  | 1844.5 |  |  | 1842.5 |  |  | 1933 |  |  | 1788.5 |  |  | 1886.5 |  |  | 2007 |  |  | 1847.5 |  |  | 1853.5 |  |  | 1924.5 |  |  | 1856.5 |  |  | 2037 |  |  | 2129.5 |  |  | 1920.5 |  |  | 1855.5 |  |  | 2015.5 |  |  | 1931 |  |  | 1896.5 |  |  | 1992.5 |  |  | 1955.5 |  |  | 1989.5 |  |  | 1851.5 |  |  | 1822.5 |  |  | 1951.5 |  |  | 1984.5 |  |  | 1948.5 |  |  | 1859.5 |  |  | 2061.5 |  |  | 1963 |  |  | 1919.5 |  |  | 1905.5 |  |  | 2079.5 |  |  | 2014.5 |  |  | 1853.5 |  |  | 1913.5 |  |  | 2003 |  |  | 1908.5 |  |  | 1882 |  |  | 1793.5 |  |  | 1975.5 |  |  | 1921.5 |  |  | 1906 |  |  | 1859 |  |  | 1921.5 |  |  | 1963.5 |  |  | 1751.5 |  |  | 1972.5 |  |  | 1929.5 |  |  | 1941.5 |  |  | 1915.5 |  |  | 1954.5 |  |  | 1907.5 |  |  | 2017.5 |  |  | 1874.5 |  |  | 1994.5 |  |  | 1857.5 |  |  | 1993.5 |  |  | 1982.5 |  |  | 1917.5 |  |  | 1921.5 |  |  | 1930.5 |  |  | 1927.5 |  |  | 1944.5 |  |  | 1953.5 |  |  | 2000.5 |  |  | 1931 |  |  | 1949.5 |  |  | 1931.5 |  |  | 1923.5 |  |  | 1899 |  |  | 1985.5 |  |  | 1900.5 |  |  | 1953.5 |  |  | 1928.5 |  |  | 1953 |  |  | 1811.5 |  |  | 1811.5 |  |  | 1847 |  |  | 1898 |  |  | 1984 |  |  | 1921.5 |  |  | 1893.5 |  |  | 1944.5 |  |  | 2122.5 |  |  | 1961 |  |  | 1937.5 |  |  | 1959.5 |  |  | 1841 |  |  | 1883 |  |  | 1932.5 |  |  | 1898.5 |  |  | 1942 |  |  | 1871.5 |  |  | 1988 |  |  | 1861.5 |  |  | 1824.5 |  |  | 2069 |  |  | 2008.5 |  |  | 1896.5 |  |  | 1797.5 |  |  | 2051 |  |  | 1883.5 |  |  | 1869.5 |  |  | 1880.5 |  |  | 1877.5 |  |  | 1923.5 |  |  | 2034.5 |  |  | 1822.5 |  |  | 1944.5 |  |  | 1965.5 |  |  | 1953.5 |  |  | 1930 |  |  | 1927.5 |  |  | 1948.5 |  |  | 1980.5 |  |  | 1966.5 |  |  | 1929.5 |  |  | 2010.5 |  |  | 2028.5 |  |  | 1911.5 |  |  | 2096 |  |  | 1861.5 |  |  | 1913 |  |  | 2035.5 |  |  | 2109.5 |  |  | 2083.5 |  |  | 1844.5 |  |  | 1870.5 |  |  | 1908.5 |  |  | 1829.5 |  |  | 1998.5 |  |  | 1978 |  |  | 1874.5 |  |  | 1945 |  |  | 1857.5 |  |  | 1827.5 |  |  | 1943.5 |  |  | 1992 |  |  | 1930.5 |  |  | 1988.5 |  |  | 1764 |  |  | 1892.5 |  |  | 1906 |  |  | 1907.5 |  |  | 1882.5 |  |  | 1888.5 |  |  | 1909 |  |  | 2025.5 |  |  | 2117.5 |  |  | 1838 |  |  | 2074.5 |  |  | 1851.5 |  |  | 1971 |  |  | 1905.5 |  |  | 2111.5 |  |  | 2020.5 |  |  | 2044.5 |  |  | 1850.5 |  |  | 2009.5 |  |  | 1822.5 |  |  | 1908.5 |  |  | 1837.5 |  |  | 1844.5 |  |  | 2086.5 |  |  | 1987 |  |  | 1995 |  |  | 2039.5 |  |  | 1928.5 |  |  | 1964
67 |  | 1860.5 |  |  | 2087.5 |  |  | 1980 |  |  | 1928.5 |  |  | 2143.5 |  |  | 1980.5 |  |  | 2040.5 |  |  | 1981.5 |  |  | 2015.5 |  |  | 1959.5 |  |  | 1902 |  |  | 2049.5 |  |  | 2048.5 |  |  | 1852.5 |  |  | 1850 |  |  | 1999.5 |  |  | 2076.5 |  |  | 1968.5 |  |  | 2095.5 |  |  | 1849.5 |  |  | 1989.5 |  |  | 1991.5 |  |  | 2008.5 |  |  | 1893.5 |  |  | 1818 |  |  | 1995.5 |  |  | 1926.5 |  |  | 1936.5 |  |  | 2058.5 |  |  | 1871 |  |  | 1981 |  |  | 2001.5 |  |  | 1818.5 |  |  | 2006.5 |  |  | 1836.5 |  |  | 2015 |  |  | 1869.5 |  |  | 2031 |  |  | 1915.5 |  |  | 1987.5 |  |  | 1836.5 |  |  | 2044.5 |  |  | 1850.5 |  |  | 1942 |  |  | 2138.5 |  |  | 2040 |  |  | 1906.5 |  |  | 2078.5 |  |  | 1997.5 |  |  | 1967.5 |  |  | 1911.5 |  |  | 1996.5 |  |  | 1991.5 |  |  | 1951.5 |  |  | 2042.5 |  |  | 2012.5 |  |  | 1892.5 |  |  | 1983 |  |  | 1973.5 |  |  | 1910.5 |  |  | 1958 |  |  | 1929.5 |  |  | 2041.5 |  |  | 1914.5 |  |  | 1853.5 |  |  | 1963 |  |  | 2025.5 |  |  | 1869 |  |  | 1811.5 |  |  | 2008.5 |  |  | 1931 |  |  | 1984.5 |  |  | 1961.5 |  |  | 2090.5 |  |  | 2057 |  |  | 2041 |  |  | 1907.5 |  |  | 1889.5 |  |  | 1816.5 |  |  | 1981.5 |  |  | 1929 |  |  | 1974.5 |  |  | 1995.5 |  |  | 2081.5 |  |  | 2052.5 |  |  | 1940.5 |  |  | 2047.5 |  |  | 1937.5 |  |  | 1949.5 |  |  | 2008.5 |  |  | 2022.5 |  |  | 2032 |  |  | 1820.5 |  |  | 1864 |  |  | 1942 |  |  | 1901 |  |  | 2119.5 |  |  | 2078.5 |  |  | 1837.5 |  |  | 2024.5 |  |  | 1904.5 |  |  | 1972 |  |  | 1934 |  |  | 1898.5 |  |  | 1906.5 |  |  | 1887.5 |  |  | 1994.5 |  |  | 2017.5 |  |  | 2050.5 |  |  | 2002.5 |  |  | 2069.5 |  |  | 2037.5 |  |  | 1967.5 |  |  | 1980.5 |  |  | 1939.5 |  |  | 1990.5 |  |  | 2070.5 |  |  | 1854.5 |  |  | 1958.5 |  |  | 1976.5 |  |  | 2001.5 |  |  | 2010.5 |  |  | 1916.5 |  |  | 1968.5 |  |  | 2019.5 |  |  | 1963 |  |  | 1932.5 |  |  | 1936.5 |  |  | 1911.5 |  |  | 1894.5 |  |  | 1992.5 |  |  | 1992 |  |  | 1891.5 |  |  | 2015.5 |  |  | 1857.5 |  |  | 1940.5 |  |  | 2015 |  |  | 1955.5 |  |  | 2009.5 |  |  | 1924 |  |  | 1981.5 |  |  | 1923 |  |  | 2011 |  |  | 2060.5 |  |  | 2034 |  |  | 2070.5 |  |  | 1937.5 |  |  | 2010.5 |  |  | 1888.5 |  |  | 2018.5 |  |  | 1963.5 |  |  | 1938.5 |  |  | 2000.5 |  |  | 2105.5 |  |  | 2015.5 |  |  | 2062 |  |  | 1915.5 |  |  | 1854 |  |  | 1930.5 |  |  | 1996.5 |  |  | 1965 |  |  | 1986.5 |  |  | 1940.5 |  |  | 1931.5 |  |  | 1891 |  |  | 1979.5 |  |  | 1912.5 |  |  | 1889.5 |  |  | 2112.5 |  |  | 1958.5 |  |  | 1917.5 |  |  | 1937 |  |  | 1920.5 |  |  | 1988.5 |  |  | 1902.5 |  |  | 1935.5 |  |  | 1999.5 |  |  | 1988.5 |  |  | 1839.5 |  |  | 2061 |  |  | 2057.5 |  |  | 1989.5 |  |  | 2004.5 |  |  | 2028.5 |  |  | 1857.5 |  |  | 2088.5 |  |  | 2006.5 |  |  | 1960.5 |  |  | 2010.5 |  |  | 1904.5 |  |  | 1988.5 |  |  | 1846.5 |  |  | 1767.5 |  |  | 1893 |  |  | 1939.5 |  |  | 1965.5 |  |  | 1950.5 |  |  | 2000.5 |  |  | 1999.5 |  |  | 2033.5 |  |  | 2033.5 |  |  | 1939.5 |  |  | 1980.5 |  |  | 1888.5 |  |  | 1910.5 |  |  | 2074.5 |  |  | 1961.5 |  |  | 1938.5 |  |  | 1947.5 |  |  | 1985.5 |  |  | 2020 |  |  | 1998.5 |  |  | 1936.5 |  |  | 1754 |  |  | 2104.5 |  |  | 2036 |  |  | 1851.5 |  |  | 2018.5 |  |  | 2092.5 |  |  | 1985.5 |  |  | 1899.5 |  |  | 1958.5 |  |  | 1963.5 |  |  | 1756.5 |  |  | 1877 |  |  | 1886.5 |  |  | 1822.5 |  |  | 2027.5 |  |  | 1884.5 |  |  | 1990 |  |  | 1870.5 |  |  | 1971.5 |  |  | 2025.5 |  |  | 1969.5 |  |  | 2037.5 |  |  | 1947.5 |  |  | 1942.5 |  |  | 2098.5 |  |  | 2043 |  |  | 1998 |  |  | 1949.5 |  |  | 1897.5 |  |  | 1940.5 |  |  | 1961 |  |  | 2079.5 |  |  | 1968.5 |  |  | 1925.5 |  |  | 1887 |  |  | 2019.5 |  |  | 2026.5 |  |  | 1850.5 |  |  | 1874.5 |  |  | 1917.5 |  |  | 2057.5 |  |  | 1996.5 |  |  | 1966.5 |  |  | 2110.5 |  |  | 1775 |  |  | 1875.5 |  |  | 2028.5 |  |  | 1995.5 |  |  | 1923.5 |  |  | 1896.5 |  |  | 2074 |  |  | 1922.5 |  |  | 1981.5 |  |  | 2023 |  |  | 2111.5 |  |  | 1995.5 |  |  | 2109 |  |  | 1976.5 |  |  | 1966.5 |  |  | 2101.5 |  |  | 1906.5 |  |  | 1951 |  |  | 1953 |  |  | 1951.5 |  |  | 1922.5 |  |  | 1985.5 |  |  | 1970.5 |  |  | 2053.5 |  |  | 1992.5 |  |  | 1915 |  |  | 1964.5 |  |  | 1967.5 |  |  | 1971 |  |  | 1929.5 |  |  | 1812.5 |  |  | 2001 |  |  | 1991.5 |  |  | 1862.5 |  |  | 2032.5 |  |  | 1911 |  |  | 1994.5 |  |  | 1891 |  |  | 2005.5 |  |  | 1840.5 |  |  | 2021.5 |  |  | 1925 |  |  | 1906.5 |  |  | 2082.5 |  |  | 2025.5 |  |  | 1992 |  |  | 1926.5 |  |  | 1770.5 |  |  | 2087.5 |  |  | 2046.5 |  |  | 1974.5 |  |  | 1993 |  |  | 1834.5 |  |  | 2073.5 |  |  | 2056.5 |  |  | 1888 |  |  | 1980 |  |  | 2069.5 |  |  | 1903.5 |  |  | 1867.5 |  |  | 1966.5 |  |  | 1950.5 |  |  | 1965.5 |  |  | 1964.5 |  |  | 2008.5 |  |  | 1895.5 |  |  | 1964.5 |  |  | 1994 |  |  | 1930.5 |  |  | 2029.5 |  |  | 2195.5 |  |  | 2019.5 |  |  | 2005 |  |  | 2018.5 |  |  | 2049.5 |  |  | 1950.5 |  |  | 1798.5 |  |  | 2059.5 |  |  | 1872 |  |  | 1971 |  |  | 1876 |  |  | 2080 |  |  | 1890.5 |  |  | 1999 |  |  | 1969.5 |  |  | 1923 |  |  | 1963.5 |  |  | 2075.5 |  |  | 1936.5 |  |  | 1951.5 |  |  | 1892.5 |  |  | 1990 |  |  | 2011.5 |  |  | 2097.5 |  |  | 1910.5 |  |  | 1990 |  |  | 2058.5 |  |  | 1872.5 |  |  | 1942.5 |  |  | 1983 |  |  | 1929.5 |  |  | 1864.5 |  |  | 2013.5 |  |  | 1927.5 |  |  | 1973.5 |  |  | 1912.5 |  |  | 2029.5 |  |  | 1955.5 |  |  | 2000.5 |  |  | 1858.5 |  |  | 1815 |  |  | 1937.5 |  |  | 1917.5 |  |  | 1855.5 |  |  | 1988.5 |  |  | 2058.5 |  |  | 1926 |  |  | 2006.5 |  |  | 2071 |  |  | 1887 |  |  | 1872.5 |  |  | 2110.5 |  |  | 1862.5 |  |  | 1869 |  |  | 1996.5 |  |  | 2005.5 |  |  | 1960.5 |  |  | 1854 |  |  | 1958.5 |  |  | 1795.5 |  |  | 1966.5 |  |  | 1882.5 |  |  | 1913.5 |  |  | 1905 |  |  | 1941.5 |  |  | 2046 |  |  | 1914.5 |  |  | 1817.5 |  |  | 1950.5 |  |  | 2005 |  |  | 1864.5 |  |  | 1938 |  |  | 1967 |  |  | 1926.5 |  |  | 1869.5 |  |  | 1935.5 |  |  | 2063.5 |  |  | 2082 |  |  | 2017.5 |  |  | 1893.5 |  |  | 1787.5 |  |  | 1919 |  |  | 2030.5 |  |  | 1884.5 |  |  | 1756.5 |  |  | 1954.5 |  |  | 2048 |  |  | 1828.5 |  |  | 1993.5 |  |  | 2019.5 |  |  | 1955.5 |  |  | 1967.5 |  |  | 1922.5 |  |  | 2048 |  |  | 1934.5 |  |  | 1872.5 |  |  | 1968 |  |  | 1858.5 |  |  | 1812.5 |  |  | 1942.5 |  |  | 1989 |  |  | 1992.5 |  |  | 2009.5 |  |  | 1968.5 |  |  | 1933.5 |  |  | 2035.5 |  |  | 2021 |  |  | 1949 |  |  | 1953.5 |  |  | 2014.5 |  |  | 2026.5 |  |  | 1813.5 |  |  | 1839 |  |  | 2014 |  |  | 1871 |  |  | 2036.5 |  |  | 1972 |  |  | 1984.5 |  |  | 2043.5 |  |  | 1950 |  |  | 1930.5 |  |  | 2003.5 |  |  | 1956.5 |  |  | 2052.5 |  |  | 1769.5 |  |  | 1964 |  |  | 2047 |  |  | 1848.5 |  |  | 2008.5 |  |  | 1921 |  |  | 1822.5 |  |  | 1968.5 |  |  | 1911 |  |  | 2052.5 |  |  | 2075.5 |  |  | 1897 |  |  | 2003.5 |  |  | 2000.5 |  |  | 1992 |  |  | 1963.5 |  |  | 1936 |  |  | 2092.5 |  |  | 2093 |  |  | 1899.5 |  |  | 1893.5 |  |  | 1973.5 |  |  | 1923.5 |  |  | 1979.5 |  |  | 1881.5 |  |  | 2009 |  |  | 1889.5 |  |  | 1993.5 |  |  | 1922.5 |  |  | 1899.5 |  |  | 1935.5 |  |  | 1951 |  |  | 1889.5 |  |  | 1965 |  |  | 1964.5 |  |  | 1870.5 |  |  | 2009.5 |  |  | 1937.5 |  |  | 1927.5 |  |  | 2004.5 |  |  | 1892.5 |  |  | 2033.5 |  |  | 1881.5 |  |  | 1906 |  |  | 1990.5 |  |  | 1861 |  |  | 1953 |  |  | 1957.5 |  |  | 1819 |  |  | 1830.5 |  |  | 2001.5 |  |  | 2047.5 |  |  | 1932.5 |  |  | 2038.5 |  |  | 2052.5 |  |  | 2022.5 |  |  | 1921 |  |  | 2067 |  |  | 1863.5 |  |  | 1901.5 |  |  | 1964 |  |  | 1872.5 |  |  | 1934.5 |  |  | 1873.5 |  |  | 1933.5 |  |  | 1904.5 |  |  | 1871 |  |  | 1930.5 |  |  | 1998.5 |  |  | 1906.5 |  |  | 1926 |  |  | 1975.5 |  |  | 1951.5 |  |  | 1981.5 |  |  | 2114.5 |  |  | 1994.5 |  |  | 1901.5 |  |  | 2063.5 |  |  | 1639.5 |  |  | 1940.5 |  |  | 1846 |  |  | 2058.5 |  |  | 1986.5 |  |  | 2003.5 |  |  | 1848.5 |  |  | 1905.5 |  |  | 1922.5 |  |  | 1885.5 |  |  | 1804 |  |  | 1854.5 |  |  | 2003.5 |  |  | 2057.5 |  |  | 1943 |  |  | 1939.5 |  |  | 1843 |  |  | 1858.5 |  |  | 1972.5 |  |  | 1887.5 |  |  | 1981 |  |  | 1854.5 |  |  | 1965 |  |  | 1946 |  |  | 1975.5 |  |  | 1927 |  |  | 2061 |  |  | 2046.5 |  |  | 1995.5 |  |  | 1846.5 |  |  | 2017 |  |  | 2027.5 |  |  | 1911.5 |  |  | 1846.5 |  |  | 2023.5 |  |  | 1893.5 |  |  | 1930.5 |  |  | 1926.5 |  |  | 2031.5 |  |  | 1970 |  |  | 2078.5 |  |  | 1895 |  |  | 1938.5 |  |  | 1911.5 |  |  | 2059.5 |  |  | 1928 |  |  | 1960 |  |  | 2128 |  |  | 1962.5 |  |  | 1921 |  |  | 1988.5 |  |  | 2118.5 |  |  | 1901.5 |  |  | 1926.5 |  |  | 1838.5 |  |  | 2024.5 |  |  | 2064.5 |  |  | 2009.5 |  |  | 2027 |  |  | 1869.5 |  |  | 1850.5 |  |  | 1981.5 |  |  | 1845.5 |  |  | 1904 |  |  | 1930.5 |  |  | 1971 |  |  | 1998.5 |  |  | 1986.5 |  |  | 1857.5 |  |  | 1876.5 |  |  | 1834 |  |  | 1891.5 |  |  | 1749 |  |  | 1887.5 |  |  | 1989.5 |  |  | 2112.5 |  |  | 1994.5 |  |  | 1961.5 |  |  | 1962.5 |  |  | 1806.5 |  |  | 2036.5 |  |  | 1942.5 |  |  | 1885 |  |  | 1973.5 |  |  | 1897.5 |  |  | 1906.5 |  |  | 2004.5 |  |  | 2020.5 |  |  | 1907 |  |  | 1911 |  |  | 1959.5 |  |  | 1878 |  |  | 2126.5 |  |  | 1948.5 |  |  | 2055.5 |  |  | 2041.5 |  |  | 1912.5 |  |  | 2005.5 |  |  | 1928.5 |  |  | 1998.5 |  |  | 1947 |  |  | 1955.5 |  |  | 2162.5 |  |  | 1948.5 |  |  | 1846 |  |  | 1894.5 |  |  | 1902.5 |  |  | 2020 |  |  | 1862 |  |  | 2002.5 |  |  | 1857 |  |  | 1836 |  |  | 1828.5 |  |  | 2002 |  |  | 2142.5 |  |  | 1974.5 |  |  | 2063.5 |  |  | 1932.5 |  |  | 1863.5 |  |  | 1881.5 |  |  | 1808.5 |  |  | 1939.5 |  |  | 1987.5 |  |  | 1904.5 |  |  | 1830 |  |  | 1850 |  |  | 2052.5 |  |  | 2015.5 |  |  | 1925.5 |  |  | 1995.5 |  |  | 1890.5 |  |  | 1939.5 |  |  | 2050.5 |  |  | 1917.5 |  |  | 2163 |  |  | 1893.5 |  |  | 1933 |  |  | 1896.5 |  |  | 2084.5 |  |  | 2002.5 |  |  | 2008 |  |  | 1922.5 |  |  | 1897.5 |  |  | 1957 |  |  | 1995.5 |  |  | 1912.5 |  |  | 1983.5 |  |  | 1957.5 |  |  | 1927.5 |  |  | 1962.5 |  |  | 2016 |  |  | 1894.5 |  |  | 1868.5 |  |  | 2017.5 |  |  | 2035.5 |  |  | 1977 |  |  | 1952.5 |  |  | 2066.5 |  |  | 1913 |  |  | 1993.5 |  |  | 2071.5 |  |  | 1977 |  |  | 2018.5 |  |  | 2041.5 |  |  | 1917.5 |  |  | 1935 |  |  | 1795.5 |  |  | 1934.5 |  |  | 1974 |  |  | 1970.5 |  |  | 2002.5 |  |  | 1935.5 |  |  | 1788.5 |  |  | 2059.5 |  |  | 2083.5 |  |  | 1879.5 |  |  | 1959 |  |  | 1917 |  |  | 1813.5 |  |  | 2021.5 |  |  | 1885.5 |  |  | 2000 |  |  | 2088.5 |  |  | 1899.5 |  |  | 1891.5 |  |  | 1830.5 |  |  | 1930.5 |  |  | 1975.5 |  |  | 1905.5 |  |  | 2035.5 |  |  | 1804.5 |  |  | 1978 |  |  | 1903.5 |  |  | 1896.5 |  |  | 1928.5 |  |  | 2041.5 |  |  | 2015.5 |  |  | 1961.5 |  |  | 2010.5 |  |  | 2006.5 |  |  | 1864.5 |  |  | 2029.5 |  |  | 1925.5 |  |  | 1919.5 |  |  | 2020.5 |  |  | 2044 |  |  | 1979.5 |  |  | 2013.5 |  |  | 1921 |  |  | 2025.5 |  |  | 1989.5 |  |  | 2045 |  |  | 1949.5 |  |  | 2096.5 |  |  | 2044.5 |  |  | 2043 |  |  | 1948.5 |  |  | 2038.5 |  |  | 1967.5 |  |  | 1792.5 |  |  | 1991.5 |  |  | 1838 |  |  | 1921.5 |  |  | 1989 |  |  | 2000 |  |  | 2096.5 |  |  | 1992.5 |  |  | 1902.5 |  |  | 1770.5 |  |  | 1937.5 |  |  | 1973.5 |  |  | 1919 |  |  | 1947.5 |  |  | 1961 |  |  | 1925.5 |  |  | 1954 |  |  | 1943 |  |  | 2072 |  |  | 2002.5 |  |  | 1908 |  |  | 2058.5 |  |  | 2002.5 |  |  | 1984.5 |  |  | 2132.5 |  |  | 1946.5 |  |  | 2057 |  |  | 2021.5 |  |  | 2020.5 |  |  | 2131.5 |  |  | 1961 |  |  | 1992.5 |  |  | 1837.5 |  |  | 1938.5 |  |  | 1997.5 |  |  | 1904 |  |  | 2006 |  |  | 1901 |  |  | 1944.5 |  |  | 2000 |  |  | 2059 |  |  | 2016.5 |  |  | 1942.5 |  |  | 1812.5 |  |  | 1970.5 |  |  | 2002.5 |  |  | 2012.5 |  |  | 2103.5 |  |  | 1892.5 |  |  | 1871.5 |  |  | 1908 |  |  | 1925.5 |  |  | 1913 |  |  | 1997.5 |  |  | 1962.5 |  |  | 1952.5 |  |  | 2014.5 |  |  | 2061 |  |  | 2027.5 |  |  | 1972 |  |  | 1870.5 |  |  | 1967.5 |  |  | 1950 |  |  | 1965 |  |  | 1913.5 |  |  | 1951 |  |  | 2025.5 |  |  | 1850.5 |  |  | 1910.5 |  |  | 1896.5 |  |  | 1964.5 |  |  | 1997.5 |  |  | 1813.5 |  |  | 1819 |  |  | 1990.5 |  |  | 1997.5 |  |  | 1950.5 |  |  | 1979.5 |  |  | 1877.5 |  |  | 1912.5 |  |  | 2059.5 |  |  | 1980.5 |  |  | 2052.5 |  |  | 2043.5 |  |  | 1868.5 |  |  | 1868.5 |  |  | 1959 |  |  | 1827.5 |  |  | 1912.5 |  |  | 2046 |  |  | 1894.5 |  |  | 1877.5 |  |  | 1945.5 |  |  | 1871.5 |  |  | 2061 |  |  | 2153.5 |  |  | 1946.5 |  |  | 1870.5 |  |  | 2062.5 |  |  | 1946 |  |  | 1911.5 |  |  | 2018.5 |  |  | 1979.5 |  |  | 2013.5 |  |  | 1880.5 |  |  | 1861.5 |  |  | 1990.5 |  |  | 2005.5 |  |  | 1995.5 |  |  | 1898.5 |  |  | 2076.5 |  |  | 2002 |  |  | 1943.5 |  |  | 1934.5 |  |  | 2118.5 |  |  | 2035.5 |  |  | 1877.5 |  |  | 1952.5 |  |  | 2050 |  |  | 1955.5 |  |  | 1929 |  |  | 1819.5 |  |  | 2014.5 |  |  | 1960.5 |  |  | 1953 |  |  | 1898 |  |  | 1968.5 |  |  | 2010.5 |  |  | 1798.5 |  |  | 1993.5 |  |  | 1976.5 |  |  | 1970.5 |  |  | 1954.5 |  |  | 1980.5 |  |  | 1922.5 |  |  | 2041.5 |  |  | 1913.5 |  |  | 2015.5 |  |  | 1878.5 |  |  | 2022.5 |  |  | 2029.5 |  |  | 1943.5 |  |  | 1936.5 |  |  | 1969.5 |  |  | 1966.5 |  |  | 1973.5 |  |  | 1992.5 |  |  | 2039.5 |  |  | 1970 |  |  | 1978.5 |  |  | 1955.5 |  |  | 1944.5 |  |  | 1928 |  |  | 2024.5 |  |  | 1947.5 |  |  | 1992.5 |  |  | 1957.5 |  |  | 1968 |  |  | 1835.5 |  |  | 1826.5 |  |  | 1894 |  |  | 1937 |  |  | 2005 |  |  | 1968.5 |  |  | 1940.5 |  |  | 1970.5 |  |  | 2148.5 |  |  | 2000 |  |  | 1976.5 |  |  | 1985.5 |  |  | 1880 |  |  | 1922 |  |  | 1971.5 |  |  | 1945.5 |  |  | 1968 |  |  | 1895.5 |  |  | 2035 |  |  | 1887.5 |  |  | 1848.5 |  |  | 2093 |  |  | 2023.5 |  |  | 1935.5 |  |  | 1821.5 |  |  | 2080 |  |  | 1922.5 |  |  | 1898.5 |  |  | 1909.5 |  |  | 1916.5 |  |  | 1938.5 |  |  | 2058.5 |  |  | 1869.5 |  |  | 1970.5 |  |  | 2004.5 |  |  | 1982.5 |  |  | 1959 |  |  | 1956.5 |  |  | 1972.5 |  |  | 2006.5 |  |  | 2013.5 |  |  | 1950.5 |  |  | 2034.5 |  |  | 2075.5 |  |  | 1950.5 |  |  | 2117 |  |  | 1887.5 |  |  | 1942 |  |  | 2064.5 |  |  | 2156.5 |  |  | 2122.5 |  |  | 1883.5 |  |  | 1894.5 |  |  | 1937.5 |  |  | 1853.5 |  |  | 2022.5 |  |  | 1993 |  |  | 1889.5 |  |  | 1974 |  |  | 1872.5 |  |  | 1851.5 |  |  | 1969.5 |  |  | 2031 |  |  | 1945.5 |  |  | 2003.5 |  |  | 1790 |  |  | 1916.5 |  |  | 1921 |  |  | 1922.5 |  |  | 1929.5 |  |  | 1927.5 |  |  | 1935 |  |  | 2072.5 |  |  | 2141.5 |  |  | 1877 |  |  | 2098.5 |  |  | 1890.5 |  |  | 2010 |  |  | 1926.5 |  |  | 2126.5 |  |  | 2046.5 |  |  | 2070.5 |  |  | 1879.5 |  |  | 2056.5 |  |  | 1851.5 |  |  | 1923.5 |  |  | 1858.5 |  |  | 1870.5 |  |  | 2107.5 |  |  | 2034 |  |  | 2042 |  |  | 2078.5 |  |  | 1949.5 |  |  | 2003
68 |  | 1907.5 |  |  | 2134.5 |  |  | 2019 |  |  | 1949.5 |  |  | 2167.5 |  |  | 2027.5 |  |  | 2066.5 |  |  | 2020.5 |  |  | 2030.5 |  |  | 1988.5 |  |  | 1928 |  |  | 2075.5 |  |  | 2074.5 |  |  | 1881.5 |  |  | 1871 |  |  | 2014.5 |  |  | 2123.5 |  |  | 2015.5 |  |  | 2121.5 |  |  | 1896.5 |  |  | 2028.5 |  |  | 2012.5 |  |  | 2047.5 |  |  | 1914.5 |  |  | 1844 |  |  | 2042.5 |  |  | 1973.5 |  |  | 1957.5 |  |  | 2073.5 |  |  | 1910 |  |  | 2002 |  |  | 2040.5 |  |  | 1842.5 |  |  | 2045.5 |  |  | 1883.5 |  |  | 2054 |  |  | 1895.5 |  |  | 2070 |  |  | 1954.5 |  |  | 2026.5 |  |  | 1851.5 |  |  | 2070.5 |  |  | 1889.5 |  |  | 1971 |  |  | 2167.5 |  |  | 2079 |  |  | 1953.5 |  |  | 2107.5 |  |  | 2023.5 |  |  | 1996.5 |  |  | 1926.5 |  |  | 2035.5 |  |  | 2017.5 |  |  | 1972.5 |  |  | 2081.5 |  |  | 2051.5 |  |  | 1918.5 |  |  | 2012 |  |  | 2002.5 |  |  | 1949.5 |  |  | 1997 |  |  | 1944.5 |  |  | 2080.5 |  |  | 1938.5 |  |  | 1879.5 |  |  | 2010 |  |  | 2040.5 |  |  | 1898 |  |  | 1826.5 |  |  | 2032.5 |  |  | 1970 |  |  | 2005.5 |  |  | 1985.5 |  |  | 2119.5 |  |  | 2081 |  |  | 2070 |  |  | 1946.5 |  |  | 1928.5 |  |  | 1855.5 |  |  | 2010.5 |  |  | 1955 |  |  | 2021.5 |  |  | 2021.5 |  |  | 2105.5 |  |  | 2099.5 |  |  | 1961.5 |  |  | 2071.5 |  |  | 1984.5 |  |  | 1996.5 |  |  | 2037.5 |  |  | 2061.5 |  |  | 2056 |  |  | 1859.5 |  |  | 1903 |  |  | 1966 |  |  | 1940 |  |  | 2140.5 |  |  | 2117.5 |  |  | 1876.5 |  |  | 2071.5 |  |  | 1919.5 |  |  | 1993 |  |  | 1949 |  |  | 1937.5 |  |  | 1935.5 |  |  | 1902.5 |  |  | 2018.5 |  |  | 2056.5 |  |  | 2089.5 |  |  | 2017.5 |  |  | 2090.5 |  |  | 2076.5 |  |  | 1993.5 |  |  | 2019.5 |  |  | 1965.5 |  |  | 2019.5 |  |  | 2117.5 |  |  | 1869.5 |  |  | 1997.5 |  |  | 2000.5 |  |  | 2040.5 |  |  | 2034.5 |  |  | 1942.5 |  |  | 1994.5 |  |  | 2034.5 |  |  | 2002 |  |  | 1979.5 |  |  | 1962.5 |  |  | 1932.5 |  |  | 1923.5 |  |  | 2031.5 |  |  | 2013 |  |  | 1930.5 |  |  | 2054.5 |  |  | 1904.5 |  |  | 1961.5 |  |  | 2041 |  |  | 2002.5 |  |  | 2035.5 |  |  | 1950 |  |  | 2007.5 |  |  | 1949 |  |  | 2050 |  |  | 2099.5 |  |  | 2060 |  |  | 2085.5 |  |  | 1976.5 |  |  | 2036.5 |  |  | 1909.5 |  |  | 2033.5 |  |  | 2002.5 |  |  | 1977.5 |  |  | 2029.5 |  |  | 2144.5 |  |  | 2030.5 |  |  | 2101 |  |  | 1954.5 |  |  | 1875 |  |  | 1951.5 |  |  | 2022.5 |  |  | 1980 |  |  | 2012.5 |  |  | 1961.5 |  |  | 1957.5 |  |  | 1930 |  |  | 2003.5 |  |  | 1938.5 |  |  | 1915.5 |  |  | 2138.5 |  |  | 1979.5 |  |  | 1943.5 |  |  | 1966 |  |  | 1941.5 |  |  | 2014.5 |  |  | 1928.5 |  |  | 1982.5 |  |  | 2046.5 |  |  | 2012.5 |  |  | 1886.5 |  |  | 2100 |  |  | 2072.5 |  |  | 2036.5 |  |  | 2043.5 |  |  | 2054.5 |  |  | 1896.5 |  |  | 2117.5 |  |  | 2053.5 |  |  | 1984.5 |  |  | 2057.5 |  |  | 1951.5 |  |  | 2035.5 |  |  | 1885.5 |  |  | 1806.5 |  |  | 1914 |  |  | 1978.5 |  |  | 2012.5 |  |  | 1989.5 |  |  | 2029.5 |  |  | 2014.5 |  |  | 2054.5 |  |  | 2054.5 |  |  | 1954.5 |  |  | 2019.5 |  |  | 1927.5 |  |  | 1949.5 |  |  | 2113.5 |  |  | 1982.5 |  |  | 1953.5 |  |  | 1971.5 |  |  | 2000.5 |  |  | 2059 |  |  | 2013.5 |  |  | 1951.5 |  |  | 1783 |  |  | 2151.5 |  |  | 2075 |  |  | 1875.5 |  |  | 2039.5 |  |  | 2107.5 |  |  | 2006.5 |  |  | 1923.5 |  |  | 1984.5 |  |  | 1992.5 |  |  | 1795.5 |  |  | 1901 |  |  | 1925.5 |  |  | 1837.5 |  |  | 2056.5 |  |  | 1908.5 |  |  | 2037 |  |  | 1909.5 |  |  | 2010.5 |  |  | 2064.5 |  |  | 2016.5 |  |  | 2076.5 |  |  | 1986.5 |  |  | 1963.5 |  |  | 2127.5 |  |  | 2082 |  |  | 2037 |  |  | 1978.5 |  |  | 1921.5 |  |  | 1969.5 |  |  | 1987 |  |  | 2103.5 |  |  | 1994.5 |  |  | 1940.5 |  |  | 1916 |  |  | 2066.5 |  |  | 2050.5 |  |  | 1897.5 |  |  | 1889.5 |  |  | 1941.5 |  |  | 2072.5 |  |  | 2035.5 |  |  | 2005.5 |  |  | 2149.5 |  |  | 1790 |  |  | 1922.5 |  |  | 2043.5 |  |  | 2034.5 |  |  | 1944.5 |  |  | 1935.5 |  |  | 2113 |  |  | 1961.5 |  |  | 2028.5 |  |  | 2062 |  |  | 2132.5 |  |  | 2021.5 |  |  | 2148 |  |  | 1991.5 |  |  | 2005.5 |  |  | 2130.5 |  |  | 1921.5 |  |  | 1980 |  |  | 2000 |  |  | 1980.5 |  |  | 1943.5 |  |  | 2006.5 |  |  | 1991.5 |  |  | 2079.5 |  |  | 2031.5 |  |  | 1954 |  |  | 1985.5 |  |  | 1988.5 |  |  | 1995 |  |  | 1953.5 |  |  | 1851.5 |  |  | 2030 |  |  | 2030.5 |  |  | 1891.5 |  |  | 2047.5 |  |  | 1950 |  |  | 2009.5 |  |  | 1920 |  |  | 2044.5 |  |  | 1879.5 |  |  | 2047.5 |  |  | 1951 |  |  | 1935.5 |  |  | 2121.5 |  |  | 2064.5 |  |  | 2013 |  |  | 1973.5 |  |  | 1817.5 |  |  | 2108.5 |  |  | 2085.5 |  |  | 2003.5 |  |  | 2022 |  |  | 1858.5 |  |  | 2088.5 |  |  | 2085.5 |  |  | 1914 |  |  | 2019 |  |  | 2108.5 |  |  | 1918.5 |  |  | 1906.5 |  |  | 2013.5 |  |  | 1979.5 |  |  | 1994.5 |  |  | 2003.5 |  |  | 2055.5 |  |  | 1924.5 |  |  | 1993.5 |  |  | 2023 |  |  | 1977.5 |  |  | 2058.5 |  |  | 2224.5 |  |  | 2058.5 |  |  | 2044 |  |  | 2057.5 |  |  | 2088.5 |  |  | 1974.5 |  |  | 1813.5 |  |  | 2080.5 |  |  | 1901 |  |  | 1995 |  |  | 1915 |  |  | 2104 |  |  | 1914.5 |  |  | 2025 |  |  | 1998.5 |  |  | 1962 |  |  | 1989.5 |  |  | 2114.5 |  |  | 1975.5 |  |  | 1972.5 |  |  | 1921.5 |  |  | 2019 |  |  | 2050.5 |  |  | 2136.5 |  |  | 1957.5 |  |  | 2037 |  |  | 2097.5 |  |  | 1898.5 |  |  | 1971.5 |  |  | 1998 |  |  | 1958.5 |  |  | 1890.5 |  |  | 2052.5 |  |  | 1953.5 |  |  | 1999.5 |  |  | 1941.5 |  |  | 2058.5 |  |  | 2002.5 |  |  | 2021.5 |  |  | 1873.5 |  |  | 1854 |  |  | 1963.5 |  |  | 1941.5 |  |  | 1902.5 |  |  | 2027.5 |  |  | 2097.5 |  |  | 1947 |  |  | 2032.5 |  |  | 2097 |  |  | 1913 |  |  | 1919.5 |  |  | 2136.5 |  |  | 1901.5 |  |  | 1898 |  |  | 2020.5 |  |  | 2026.5 |  |  | 1975.5 |  |  | 1893 |  |  | 1979.5 |  |  | 1834.5 |  |  | 1995.5 |  |  | 1921.5 |  |  | 1952.5 |  |  | 1931 |  |  | 1980.5 |  |  | 2085 |  |  | 1938.5 |  |  | 1838.5 |  |  | 1976.5 |  |  | 2026 |  |  | 1888.5 |  |  | 1959 |  |  | 2006 |  |  | 1947.5 |  |  | 1893.5 |  |  | 1959.5 |  |  | 2102.5 |  |  | 2106 |  |  | 2056.5 |  |  | 1932.5 |  |  | 1802.5 |  |  | 1943 |  |  | 2054.5 |  |  | 1913.5 |  |  | 1803.5 |  |  | 1993.5 |  |  | 2077 |  |  | 1867.5 |  |  | 2032.5 |  |  | 2040.5 |  |  | 1984.5 |  |  | 1993.5 |  |  | 1946.5 |  |  | 2077 |  |  | 1958.5 |  |  | 1896.5 |  |  | 1994 |  |  | 1882.5 |  |  | 1833.5 |  |  | 1963.5 |  |  | 2015 |  |  | 2039.5 |  |  | 2056.5 |  |  | 2015.5 |  |  | 1972.5 |  |  | 2064.5 |  |  | 2047 |  |  | 1978 |  |  | 2000.5 |  |  | 2061.5 |  |  | 2041.5 |  |  | 1837.5 |  |  | 1865 |  |  | 2038 |  |  | 1910 |  |  | 2075.5 |  |  | 2019 |  |  | 1999.5 |  |  | 2082.5 |  |  | 1997 |  |  | 1954.5 |  |  | 2042.5 |  |  | 1985.5 |  |  | 2076.5 |  |  | 1798.5 |  |  | 1985 |  |  | 2071 |  |  | 1895.5 |  |  | 2047.5 |  |  | 1947 |  |  | 1861.5 |  |  | 1997.5 |  |  | 1958 |  |  | 2091.5 |  |  | 2122.5 |  |  | 1918 |  |  | 2042.5 |  |  | 2015.5 |  |  | 2013 |  |  | 1978.5 |  |  | 1957 |  |  | 2121.5 |  |  | 2119 |  |  | 1928.5 |  |  | 1908.5 |  |  | 1997.5 |  |  | 1962.5 |  |  | 1994.5 |  |  | 1928.5 |  |  | 2048 |  |  | 1915.5 |  |  | 2019.5 |  |  | 1961.5 |  |  | 1914.5 |  |  | 1959.5 |  |  | 1977 |  |  | 1918.5 |  |  | 1986 |  |  | 2003.5 |  |  | 1896.5 |  |  | 2033.5 |  |  | 1984.5 |  |  | 1974.5 |  |  | 2030.5 |  |  | 1939.5 |  |  | 2048.5 |  |  | 1920.5 |  |  | 1930 |  |  | 2037.5 |  |  | 1908 |  |  | 2000 |  |  | 1996.5 |  |  | 1843 |  |  | 1869.5 |  |  | 2027.5 |  |  | 2086.5 |  |  | 1971.5 |  |  | 2059.5 |  |  | 2073.5 |  |  | 2043.5 |  |  | 1950 |  |  | 2114 |  |  | 1887.5 |  |  | 1922.5 |  |  | 2003 |  |  | 1919.5 |  |  | 1955.5 |  |  | 1897.5 |  |  | 1954.5 |  |  | 1951.5 |  |  | 1892 |  |  | 1969.5 |  |  | 2024.5 |  |  | 1932.5 |  |  | 1965 |  |  | 2022.5 |  |  | 1990.5 |  |  | 2020.5 |  |  | 2135.5 |  |  | 2033.5 |  |  | 1922.5 |  |  | 2102.5 |  |  | 1654.5 |  |  | 1979.5 |  |  | 1872 |  |  | 2082.5 |  |  | 2025.5 |  |  | 2042.5 |  |  | 1887.5 |  |  | 1920.5 |  |  | 1951.5 |  |  | 1932.5 |  |  | 1825 |  |  | 1880.5 |  |  | 2024.5 |  |  | 2072.5 |  |  | 1982 |  |  | 1978.5 |  |  | 1864 |  |  | 1882.5 |  |  | 2001.5 |  |  | 1908.5 |  |  | 2002 |  |  | 1875.5 |  |  | 2004 |  |  | 1975 |  |  | 1996.5 |  |  | 1966 |  |  | 2108 |  |  | 2070.5 |  |  | 2019.5 |  |  | 1870.5 |  |  | 2056 |  |  | 2074.5 |  |  | 1940.5 |  |  | 1893.5 |  |  | 2049.5 |  |  | 1940.5 |  |  | 1959.5 |  |  | 1952.5 |  |  | 2070.5 |  |  | 1996 |  |  | 2117.5 |  |  | 1934 |  |  | 1977.5 |  |  | 1932.5 |  |  | 2098.5 |  |  | 1952 |  |  | 1986 |  |  | 2157 |  |  | 1991.5 |  |  | 1945 |  |  | 2027.5 |  |  | 2144.5 |  |  | 1948.5 |  |  | 1941.5 |  |  | 1853.5 |  |  | 2053.5 |  |  | 2093.5 |  |  | 2056.5 |  |  | 2056 |  |  | 1908.5 |  |  | 1876.5 |  |  | 2002.5 |  |  | 1874.5 |  |  | 1943 |  |  | 1951.5 |  |  | 2018 |  |  | 2024.5 |  |  | 2010.5 |  |  | 1883.5 |  |  | 1915.5 |  |  | 1873 |  |  | 1912.5 |  |  | 1770 |  |  | 1911.5 |  |  | 2010.5 |  |  | 2127.5 |  |  | 2018.5 |  |  | 1987.5 |  |  | 2009.5 |  |  | 1853.5 |  |  | 2062.5 |  |  | 1989.5 |  |  | 1932 |  |  | 2020.5 |  |  | 1936.5 |  |  | 1945.5 |  |  | 2025.5 |  |  | 2046.5 |  |  | 1954 |  |  | 1937 |  |  | 1980.5 |  |  | 1917 |  |  | 2152.5 |  |  | 1972.5 |  |  | 2094.5 |  |  | 2062.5 |  |  | 1927.5 |  |  | 2029.5 |  |  | 1952.5 |  |  | 2013.5 |  |  | 1976 |  |  | 1979.5 |  |  | 2183.5 |  |  | 1977.5 |  |  | 1867 |  |  | 1933.5 |  |  | 1926.5 |  |  | 2067 |  |  | 1901 |  |  | 2031.5 |  |  | 1881 |  |  | 1857 |  |  | 1857.5 |  |  | 2026 |  |  | 2166.5 |  |  | 2013.5 |  |  | 2087.5 |  |  | 1961.5 |  |  | 1878.5 |  |  | 1928.5 |  |  | 1832.5 |  |  | 1978.5 |  |  | 2013.5 |  |  | 1925.5 |  |  | 1869 |  |  | 1897 |  |  | 2073.5 |  |  | 2062.5 |  |  | 1954.5 |  |  | 2024.5 |  |  | 1929.5 |  |  | 1963.5 |  |  | 2089.5 |  |  | 1956.5 |  |  | 2192 |  |  | 1932.5 |  |  | 1972 |  |  | 1911.5 |  |  | 2108.5 |  |  | 2031.5 |  |  | 2037 |  |  | 1961.5 |  |  | 1921.5 |  |  | 1996 |  |  | 2019.5 |  |  | 1936.5 |  |  | 2012.5 |  |  | 1996.5 |  |  | 1956.5 |  |  | 2009.5 |  |  | 2037 |  |  | 1933.5 |  |  | 1897.5 |  |  | 2032.5 |  |  | 2074.5 |  |  | 2006 |  |  | 1991.5 |  |  | 2087.5 |  |  | 1937 |  |  | 2022.5 |  |  | 2097.5 |  |  | 2003 |  |  | 2057.5 |  |  | 2080.5 |  |  | 1943.5 |  |  | 1982 |  |  | 1821.5 |  |  | 1981.5 |  |  | 1998 |  |  | 1999.5 |  |  | 2031.5 |  |  | 1956.5 |  |  | 1809.5 |  |  | 2074.5 |  |  | 2104.5 |  |  | 1908.5 |  |  | 1998 |  |  | 1946 |  |  | 1852.5 |  |  | 2050.5 |  |  | 1911.5 |  |  | 2015 |  |  | 2109.5 |  |  | 1914.5 |  |  | 1930.5 |  |  | 1856.5 |  |  | 1945.5 |  |  | 2001.5 |  |  | 1920.5 |  |  | 2050.5 |  |  | 1819.5 |  |  | 2004 |  |  | 1942.5 |  |  | 1911.5 |  |  | 1949.5 |  |  | 2088.5 |  |  | 2054.5 |  |  | 2000.5 |  |  | 2025.5 |  |  | 2045.5 |  |  | 1890.5 |  |  | 2053.5 |  |  | 1946.5 |  |  | 1943.5 |  |  | 2035.5 |  |  | 2059 |  |  | 1994.5 |  |  | 2039.5 |  |  | 1936 |  |  | 2040.5 |  |  | 2028.5 |  |  | 2066 |  |  | 1996.5 |  |  | 2143.5 |  |  | 2083.5 |  |  | 2058 |  |  | 1963.5 |  |  | 2067.5 |  |  | 2006.5 |  |  | 1831.5 |  |  | 2020.5 |  |  | 1885 |  |  | 1960.5 |  |  | 2036 |  |  | 2026 |  |  | 2117.5 |  |  | 2039.5 |  |  | 1928.5 |  |  | 1785.5 |  |  | 1976.5 |  |  | 1994.5 |  |  | 1948 |  |  | 1973.5 |  |  | 1985 |  |  | 1964.5 |  |  | 1980 |  |  | 1967 |  |  | 2098 |  |  | 2028.5 |  |  | 1937 |  |  | 2073.5 |  |  | 2031.5 |  |  | 2010.5 |  |  | 2161.5 |  |  | 1985.5 |  |  | 2078 |  |  | 2042.5 |  |  | 2067.5 |  |  | 2157.5 |  |  | 1985 |  |  | 2039.5 |  |  | 1884.5 |  |  | 1977.5 |  |  | 2036.5 |  |  | 1943 |  |  | 2045 |  |  | 1916 |  |  | 1959.5 |  |  | 2047 |  |  | 2098 |  |  | 2063.5 |  |  | 1966.5 |  |  | 1851.5 |  |  | 1999.5 |  |  | 2023.5 |  |  | 2036.5 |  |  | 2129.5 |  |  | 1921.5 |  |  | 1900.5 |  |  | 1923 |  |  | 1954.5 |  |  | 1934 |  |  | 2026.5 |  |  | 2001.5 |  |  | 1967.5 |  |  | 2035.5 |  |  | 2090 |  |  | 2066.5 |  |  | 1996 |  |  | 1894.5 |  |  | 2006.5 |  |  | 1989 |  |  | 1986 |  |  | 1960.5 |  |  | 1966 |  |  | 2040.5 |  |  | 1871.5 |  |  | 1939.5 |  |  | 1922.5 |  |  | 2011.5 |  |  | 2036.5 |  |  | 1860.5 |  |  | 1858 |  |  | 2011.5 |  |  | 2036.5 |  |  | 1989.5 |  |  | 2026.5 |  |  | 1892.5 |  |  | 1951.5 |  |  | 2085.5 |  |  | 2004.5 |  |  | 2091.5 |  |  | 2058.5 |  |  | 1894.5 |  |  | 1892.5 |  |  | 1988 |  |  | 1848.5 |  |  | 1951.5 |  |  | 2072 |  |  | 1920.5 |  |  | 1892.5 |  |  | 1960.5 |  |  | 1910.5 |  |  | 2108 |  |  | 2168.5 |  |  | 1975.5 |  |  | 1909.5 |  |  | 2077.5 |  |  | 1961 |  |  | 1926.5 |  |  | 2065.5 |  |  | 1994.5 |  |  | 2037.5 |  |  | 1927.5 |  |  | 1876.5 |  |  | 2037.5 |  |  | 2029.5 |  |  | 2016.5 |  |  | 1937.5 |  |  | 2091.5 |  |  | 2049 |  |  | 1982.5 |  |  | 1949.5 |  |  | 2133.5 |  |  | 2074.5 |  |  | 1916.5 |  |  | 1981.5 |  |  | 2076 |  |  | 1994.5 |  |  | 1944 |  |  | 1843.5 |  |  | 2040.5 |  |  | 1981.5 |  |  | 1982 |  |  | 1919 |  |  | 1992.5 |  |  | 2039.5 |  |  | 1824.5 |  |  | 2022.5 |  |  | 2000.5 |  |  | 1994.5 |  |  | 1978.5 |  |  | 2009.5 |  |  | 1948.5 |  |  | 2080.5 |  |  | 1952.5 |  |  | 2062.5 |  |  | 1904.5 |  |  | 2046.5 |  |  | 2076.5 |  |  | 1982.5 |  |  | 1975.5 |  |  | 1990.5 |  |  | 2013.5 |  |  | 2012.5 |  |  | 2016.5 |  |  | 2054.5 |  |  | 2009 |  |  | 2017.5 |  |  | 1970.5 |  |  | 1965.5 |  |  | 1967 |  |  | 2063.5 |  |  | 1968.5 |  |  | 2031.5 |  |  | 1981.5 |  |  | 1997 |  |  | 1864.5 |  |  | 1841.5 |  |  | 1909 |  |  | 1952 |  |  | 2031 |  |  | 1989.5 |  |  | 1969.5 |  |  | 2009.5 |  |  | 2172.5 |  |  | 2024 |  |  | 2000.5 |  |  | 2000.5 |  |  | 1919 |  |  | 1961 |  |  | 1986.5 |  |  | 1992.5 |  |  | 1994 |  |  | 1934.5 |  |  | 2064 |  |  | 1908.5 |  |  | 1877.5 |  |  | 2132 |  |  | 2062.5 |  |  | 1974.5 |  |  | 1850.5 |  |  | 2101 |  |  | 1937.5 |  |  | 1919.5 |  |  | 1948.5 |  |  | 1955.5 |  |  | 1959.5 |  |  | 2079.5 |  |  | 1908.5 |  |  | 1991.5 |  |  | 2030.5 |  |  | 2011.5 |  |  | 1983 |  |  | 1985.5 |  |  | 1996.5 |  |  | 2021.5 |  |  | 2034.5 |  |  | 1965.5 |  |  | 2058.5 |  |  | 2096.5 |  |  | 1979.5 |  |  | 2143 |  |  | 1926.5 |  |  | 1968 |  |  | 2111.5 |  |  | 2203.5 |  |  | 2169.5 |  |  | 1922.5 |  |  | 1909.5 |  |  | 1976.5 |  |  | 1877.5 |  |  | 2048.5 |  |  | 2032 |  |  | 1915.5 |  |  | 2013 |  |  | 1919.5 |  |  | 1866.5 |  |  | 2016.5 |  |  | 2057 |  |  | 1969.5 |  |  | 2018.5 |  |  | 1829 |  |  | 1955.5 |  |  | 1960 |  |  | 1961.5 |  |  | 1950.5 |  |  | 1951.5 |  |  | 1961 |  |  | 2111.5 |  |  | 2188.5 |  |  | 1916 |  |  | 2145.5 |  |  | 1911.5 |  |  | 2025 |  |  | 1955.5 |  |  | 2141.5 |  |  | 2085.5 |  |  | 2109.5 |  |  | 1894.5 |  |  | 2103.5 |  |  | 1875.5 |  |  | 1947.5 |  |  | 1873.5 |  |  | 1885.5 |  |  | 2131.5 |  |  | 2073 |  |  | 2068 |  |  | 2117.5 |  |  | 1978.5 |  |  | 2027
69 |  | 1933.5 |  |  | 2173.5 |  |  | 2058 |  |  | 1970.5 |  |  | 2191.5 |  |  | 2053.5 |  |  | 2090.5 |  |  | 2046.5 |  |  | 2059.5 |  |  | 2003.5 |  |  | 1943 |  |  | 2122.5 |  |  | 2100.5 |  |  | 1896.5 |  |  | 1892 |  |  | 2040.5 |  |  | 2144.5 |  |  | 2039.5 |  |  | 2145.5 |  |  | 1920.5 |  |  | 2054.5 |  |  | 2038.5 |  |  | 2076.5 |  |  | 1935.5 |  |  | 1883 |  |  | 2081.5 |  |  | 2002.5 |  |  | 2004.5 |  |  | 2112.5 |  |  | 1925 |  |  | 2049 |  |  | 2087.5 |  |  | 1871.5 |  |  | 2066.5 |  |  | 1909.5 |  |  | 2083 |  |  | 1942.5 |  |  | 2117 |  |  | 1969.5 |  |  | 2041.5 |  |  | 1866.5 |  |  | 2085.5 |  |  | 1918.5 |  |  | 2018 |  |  | 2193.5 |  |  | 2126 |  |  | 1982.5 |  |  | 2131.5 |  |  | 2044.5 |  |  | 2020.5 |  |  | 1965.5 |  |  | 2074.5 |  |  | 2056.5 |  |  | 1987.5 |  |  | 2105.5 |  |  | 2066.5 |  |  | 1957.5 |  |  | 2051 |  |  | 2049.5 |  |  | 1996.5 |  |  | 2018 |  |  | 1983.5 |  |  | 2106.5 |  |  | 1977.5 |  |  | 1918.5 |  |  | 2057 |  |  | 2061.5 |  |  | 1922 |  |  | 1865.5 |  |  | 2056.5 |  |  | 1999 |  |  | 2031.5 |  |  | 2024.5 |  |  | 2148.5 |  |  | 2120 |  |  | 2091 |  |  | 1961.5 |  |  | 1975.5 |  |  | 1870.5 |  |  | 2039.5 |  |  | 1994 |  |  | 2047.5 |  |  | 2060.5 |  |  | 2152.5 |  |  | 2120.5 |  |  | 2000.5 |  |  | 2118.5 |  |  | 2023.5 |  |  | 2011.5 |  |  | 2061.5 |  |  | 2082.5 |  |  | 2095 |  |  | 1898.5 |  |  | 1942 |  |  | 1990 |  |  | 1955 |  |  | 2187.5 |  |  | 2156.5 |  |  | 1915.5 |  |  | 2118.5 |  |  | 1948.5 |  |  | 2032 |  |  | 1996 |  |  | 1966.5 |  |  | 1959.5 |  |  | 1926.5 |  |  | 2039.5 |  |  | 2095.5 |  |  | 2128.5 |  |  | 2064.5 |  |  | 2129.5 |  |  | 2115.5 |  |  | 2022.5 |  |  | 2058.5 |  |  | 2012.5 |  |  | 2058.5 |  |  | 2156.5 |  |  | 1895.5 |  |  | 2018.5 |  |  | 2021.5 |  |  | 2069.5 |  |  | 2073.5 |  |  | 1981.5 |  |  | 2033.5 |  |  | 2060.5 |  |  | 2041 |  |  | 1994.5 |  |  | 2009.5 |  |  | 1956.5 |  |  | 1962.5 |  |  | 2046.5 |  |  | 2052 |  |  | 1969.5 |  |  | 2101.5 |  |  | 1925.5 |  |  | 2000.5 |  |  | 2062 |  |  | 2028.5 |  |  | 2082.5 |  |  | 1989 |  |  | 2033.5 |  |  | 1964 |  |  | 2089 |  |  | 2125.5 |  |  | 2081 |  |  | 2114.5 |  |  | 2000.5 |  |  | 2075.5 |  |  | 1933.5 |  |  | 2057.5 |  |  | 2017.5 |  |  | 2001.5 |  |  | 2058.5 |  |  | 2168.5 |  |  | 2045.5 |  |  | 2127 |  |  | 1975.5 |  |  | 1899 |  |  | 1966.5 |  |  | 2061.5 |  |  | 2004 |  |  | 2033.5 |  |  | 1985.5 |  |  | 1996.5 |  |  | 1945 |  |  | 2024.5 |  |  | 1964.5 |  |  | 1954.5 |  |  | 2153.5 |  |  | 2026.5 |  |  | 1982.5 |  |  | 2013 |  |  | 1988.5 |  |  | 2040.5 |  |  | 1975.5 |  |  | 2021.5 |  |  | 2067.5 |  |  | 2038.5 |  |  | 1933.5 |  |  | 2129 |  |  | 2093.5 |  |  | 2065.5 |  |  | 2058.5 |  |  | 2083.5 |  |  | 1943.5 |  |  | 2156.5 |  |  | 2082.5 |  |  | 2013.5 |  |  | 2083.5 |  |  | 1990.5 |  |  | 2064.5 |  |  | 1900.5 |  |  | 1835.5 |  |  | 1929 |  |  | 1993.5 |  |  | 2051.5 |  |  | 2004.5 |  |  | 2068.5 |  |  | 2053.5 |  |  | 2093.5 |  |  | 2093.5 |  |  | 1975.5 |  |  | 2066.5 |  |  | 1956.5 |  |  | 1975.5 |  |  | 2152.5 |  |  | 2008.5 |  |  | 1968.5 |  |  | 1992.5 |  |  | 2026.5 |  |  | 2098 |  |  | 2052.5 |  |  | 1990.5 |  |  | 1798 |  |  | 2177.5 |  |  | 2122 |  |  | 1899.5 |  |  | 2065.5 |  |  | 2146.5 |  |  | 2045.5 |  |  | 1947.5 |  |  | 2010.5 |  |  | 2031.5 |  |  | 1824.5 |  |  | 1940 |  |  | 1951.5 |  |  | 1866.5 |  |  | 2077.5 |  |  | 1923.5 |  |  | 2058 |  |  | 1948.5 |  |  | 2025.5 |  |  | 2090.5 |  |  | 2045.5 |  |  | 2100.5 |  |  | 2001.5 |  |  | 1984.5 |  |  | 2166.5 |  |  | 2129 |  |  | 2084 |  |  | 1993.5 |  |  | 1950.5 |  |  | 2008.5 |  |  | 2016 |  |  | 2150.5 |  |  | 2009.5 |  |  | 1987.5 |  |  | 1942 |  |  | 2092.5 |  |  | 2065.5 |  |  | 1912.5 |  |  | 1928.5 |  |  | 1965.5 |  |  | 2087.5 |  |  | 2056.5 |  |  | 2029.5 |  |  | 2173.5 |  |  | 1829 |  |  | 1969.5 |  |  | 2067.5 |  |  | 2058.5 |  |  | 1965.5 |  |  | 1961.5 |  |  | 2152 |  |  | 1976.5 |  |  | 2052.5 |  |  | 2101 |  |  | 2158.5 |  |  | 2047.5 |  |  | 2187 |  |  | 2020.5 |  |  | 2031.5 |  |  | 2156.5 |  |  | 1945.5 |  |  | 2001 |  |  | 2021 |  |  | 2001.5 |  |  | 1964.5 |  |  | 2045.5 |  |  | 2020.5 |  |  | 2100.5 |  |  | 2070.5 |  |  | 1980 |  |  | 2032.5 |  |  | 2027.5 |  |  | 2024 |  |  | 1992.5 |  |  | 1890.5 |  |  | 2051 |  |  | 2069.5 |  |  | 1917.5 |  |  | 2071.5 |  |  | 1989 |  |  | 2035.5 |  |  | 1949 |  |  | 2083.5 |  |  | 1908.5 |  |  | 2062.5 |  |  | 1972 |  |  | 1959.5 |  |  | 2160.5 |  |  | 2111.5 |  |  | 2028 |  |  | 1988.5 |  |  | 1843.5 |  |  | 2147.5 |  |  | 2106.5 |  |  | 2029.5 |  |  | 2046 |  |  | 1897.5 |  |  | 2127.5 |  |  | 2106.5 |  |  | 1953 |  |  | 2040 |  |  | 2155.5 |  |  | 1939.5 |  |  | 1945.5 |  |  | 2039.5 |  |  | 2000.5 |  |  | 2033.5 |  |  | 2042.5 |  |  | 2084.5 |  |  | 1963.5 |  |  | 2008.5 |  |  | 2049 |  |  | 2001.5 |  |  | 2079.5 |  |  | 2250.5 |  |  | 2079.5 |  |  | 2073 |  |  | 2083.5 |  |  | 2135.5 |  |  | 1989.5 |  |  | 1860.5 |  |  | 2104.5 |  |  | 1927 |  |  | 2019 |  |  | 1954 |  |  | 2151 |  |  | 1929.5 |  |  | 2072 |  |  | 2037.5 |  |  | 2001 |  |  | 2015.5 |  |  | 2129.5 |  |  | 1996.5 |  |  | 1998.5 |  |  | 1950.5 |  |  | 2058 |  |  | 2065.5 |  |  | 2160.5 |  |  | 1996.5 |  |  | 2076 |  |  | 2126.5 |  |  | 1937.5 |  |  | 1986.5 |  |  | 2019 |  |  | 1984.5 |  |  | 1937.5 |  |  | 2091.5 |  |  | 1992.5 |  |  | 2028.5 |  |  | 1962.5 |  |  | 2084.5 |  |  | 2041.5 |  |  | 2045.5 |  |  | 1912.5 |  |  | 1901 |  |  | 2010.5 |  |  | 1988.5 |  |  | 1941.5 |  |  | 2066.5 |  |  | 2136.5 |  |  | 1976 |  |  | 2056.5 |  |  | 2123 |  |  | 1952 |  |  | 1943.5 |  |  | 2151.5 |  |  | 1925.5 |  |  | 1945 |  |  | 2059.5 |  |  | 2050.5 |  |  | 2014.5 |  |  | 1917 |  |  | 2005.5 |  |  | 1863.5 |  |  | 2042.5 |  |  | 1936.5 |  |  | 1967.5 |  |  | 1946 |  |  | 1995.5 |  |  | 2111 |  |  | 1967.5 |  |  | 1885.5 |  |  | 2000.5 |  |  | 2073 |  |  | 1927.5 |  |  | 2006 |  |  | 2021 |  |  | 1976.5 |  |  | 1914.5 |  |  | 1974.5 |  |  | 2141.5 |  |  | 2135 |  |  | 2095.5 |  |  | 1971.5 |  |  | 1841.5 |  |  | 1982 |  |  | 2101.5 |  |  | 1960.5 |  |  | 1818.5 |  |  | 2008.5 |  |  | 2116 |  |  | 1891.5 |  |  | 2071.5 |  |  | 2064.5 |  |  | 2023.5 |  |  | 2032.5 |  |  | 1993.5 |  |  | 2098 |  |  | 2005.5 |  |  | 1917.5 |  |  | 2015 |  |  | 1903.5 |  |  | 1854.5 |  |  | 2002.5 |  |  | 2054 |  |  | 2078.5 |  |  | 2077.5 |  |  | 2030.5 |  |  | 2001.5 |  |  | 2111.5 |  |  | 2076 |  |  | 2025 |  |  | 2029.5 |  |  | 2085.5 |  |  | 2080.5 |  |  | 1876.5 |  |  | 1904 |  |  | 2062 |  |  | 1949 |  |  | 2122.5 |  |  | 2034 |  |  | 2014.5 |  |  | 2108.5 |  |  | 2036 |  |  | 1983.5 |  |  | 2057.5 |  |  | 2024.5 |  |  | 2100.5 |  |  | 1819.5 |  |  | 2024 |  |  | 2092 |  |  | 1934.5 |  |  | 2071.5 |  |  | 1976 |  |  | 1890.5 |  |  | 2026.5 |  |  | 1997 |  |  | 2130.5 |  |  | 2161.5 |  |  | 1947 |  |  | 2089.5 |  |  | 2044.5 |  |  | 2039 |  |  | 1993.5 |  |  | 1996 |  |  | 2160.5 |  |  | 2145 |  |  | 1954.5 |  |  | 1923.5 |  |  | 2012.5 |  |  | 2009.5 |  |  | 2015.5 |  |  | 1949.5 |  |  | 2087 |  |  | 1939.5 |  |  | 2040.5 |  |  | 1985.5 |  |  | 1961.5 |  |  | 2006.5 |  |  | 2006 |  |  | 1947.5 |  |  | 2012 |  |  | 2027.5 |  |  | 1922.5 |  |  | 2080.5 |  |  | 2013.5 |  |  | 1995.5 |  |  | 2069.5 |  |  | 1978.5 |  |  | 2074.5 |  |  | 1935.5 |  |  | 1956 |  |  | 2066.5 |  |  | 1937 |  |  | 2039 |  |  | 2043.5 |  |  | 1864 |  |  | 1893.5 |  |  | 2056.5 |  |  | 2101.5 |  |  | 2010.5 |  |  | 2098.5 |  |  | 2099.5 |  |  | 2069.5 |  |  | 1971 |  |  | 2129 |  |  | 1908.5 |  |  | 1961.5 |  |  | 2029 |  |  | 1948.5 |  |  | 1976.5 |  |  | 1944.5 |  |  | 1975.5 |  |  | 1990.5 |  |  | 1931 |  |  | 1998.5 |  |  | 2039.5 |  |  | 1947.5 |  |  | 1991 |  |  | 2061.5 |  |  | 2016.5 |  |  | 2044.5 |  |  | 2174.5 |  |  | 2080.5 |  |  | 1951.5 |  |  | 2131.5 |  |  | 1693.5 |  |  | 2018.5 |  |  | 1893 |  |  | 2111.5 |  |  | 2072.5 |  |  | 2081.5 |  |  | 1934.5 |  |  | 1941.5 |  |  | 1998.5 |  |  | 1979.5 |  |  | 1851 |  |  | 1927.5 |  |  | 2063.5 |  |  | 2087.5 |  |  | 2011 |  |  | 2017.5 |  |  | 1903 |  |  | 1911.5 |  |  | 2040.5 |  |  | 1955.5 |  |  | 2041 |  |  | 1901.5 |  |  | 2030 |  |  | 1990 |  |  | 2035.5 |  |  | 1992 |  |  | 2147 |  |  | 2091.5 |  |  | 2045.5 |  |  | 1891.5 |  |  | 2082 |  |  | 2098.5 |  |  | 1964.5 |  |  | 1914.5 |  |  | 2073.5 |  |  | 1955.5 |  |  | 1980.5 |  |  | 1991.5 |  |  | 2096.5 |  |  | 2025 |  |  | 2164.5 |  |  | 1981 |  |  | 2003.5 |  |  | 1956.5 |  |  | 2119.5 |  |  | 1973 |  |  | 2025 |  |  | 2178 |  |  | 2015.5 |  |  | 1984 |  |  | 2048.5 |  |  | 2183.5 |  |  | 1995.5 |  |  | 1980.5 |  |  | 1882.5 |  |  | 2100.5 |  |  | 2117.5 |  |  | 2095.5 |  |  | 2085 |  |  | 1923.5 |  |  | 1905.5 |  |  | 2041.5 |  |  | 1898.5 |  |  | 1964 |  |  | 1977.5 |  |  | 2033 |  |  | 2039.5 |  |  | 2049.5 |  |  | 1922.5 |  |  | 1930.5 |  |  | 1894 |  |  | 1951.5 |  |  | 1794 |  |  | 1935.5 |  |  | 2049.5 |  |  | 2153.5 |  |  | 2065.5 |  |  | 2011.5 |  |  | 2035.5 |  |  | 1868.5 |  |  | 2101.5 |  |  | 2028.5 |  |  | 1947 |  |  | 2041.5 |  |  | 1957.5 |  |  | 1984.5 |  |  | 2064.5 |  |  | 2085.5 |  |  | 1983 |  |  | 1976 |  |  | 2019.5 |  |  | 1932 |  |  | 2167.5 |  |  | 2001.5 |  |  | 2118.5 |  |  | 2083.5 |  |  | 1953.5 |  |  | 2076.5 |  |  | 1999.5 |  |  | 2042.5 |  |  | 2023 |  |  | 2003.5 |  |  | 2222.5 |  |  | 1998.5 |  |  | 1893 |  |  | 1972.5 |  |  | 1965.5 |  |  | 2106 |  |  | 1922 |  |  | 2055.5 |  |  | 1920 |  |  | 1872 |  |  | 1896.5 |  |  | 2073 |  |  | 2205.5 |  |  | 2028.5 |  |  | 2126.5 |  |  | 2000.5 |  |  | 1917.5 |  |  | 1967.5 |  |  | 1879.5 |  |  | 2007.5 |  |  | 2052.5 |  |  | 1954.5 |  |  | 1916 |  |  | 1926 |  |  | 2088.5 |  |  | 2077.5 |  |  | 1993.5 |  |  | 2050.5 |  |  | 1958.5 |  |  | 2010.5 |  |  | 2136.5 |  |  | 1977.5 |  |  | 2239 |  |  | 1958.5 |  |  | 2001 |  |  | 1935.5 |  |  | 2155.5 |  |  | 2060.5 |  |  | 2084 |  |  | 1985.5 |  |  | 1942.5 |  |  | 2035 |  |  | 2058.5 |  |  | 1965.5 |  |  | 2033.5 |  |  | 2035.5 |  |  | 1980.5 |  |  | 2048.5 |  |  | 2066 |  |  | 1962.5 |  |  | 1936.5 |  |  | 2071.5 |  |  | 2113.5 |  |  | 2035 |  |  | 2020.5 |  |  | 2116.5 |  |  | 1976 |  |  | 2069.5 |  |  | 2121.5 |  |  | 2029 |  |  | 2096.5 |  |  | 2127.5 |  |  | 1964.5 |  |  | 1997 |  |  | 1850.5 |  |  | 2005.5 |  |  | 2037 |  |  | 2020.5 |  |  | 2052.5 |  |  | 1982.5 |  |  | 1835.5 |  |  | 2113.5 |  |  | 2119.5 |  |  | 1929.5 |  |  | 2027 |  |  | 1975 |  |  | 1878.5 |  |  | 2074.5 |  |  | 1937.5 |  |  | 2054 |  |  | 2124.5 |  |  | 1961.5 |  |  | 1959.5 |  |  | 1895.5 |  |  | 1971.5 |  |  | 2048.5 |  |  | 1949.5 |  |  | 2076.5 |  |  | 1858.5 |  |  | 2033 |  |  | 1989.5 |  |  | 1932.5 |  |  | 1988.5 |  |  | 2109.5 |  |  | 2093.5 |  |  | 2021.5 |  |  | 2064.5 |  |  | 2074.5 |  |  | 1905.5 |  |  | 2092.5 |  |  | 1993.5 |  |  | 1969.5 |  |  | 2059.5 |  |  | 2088 |  |  | 2041.5 |  |  | 2054.5 |  |  | 1965 |  |  | 2066.5 |  |  | 2052.5 |  |  | 2105 |  |  | 2035.5 |  |  | 2164.5 |  |  | 2122.5 |  |  | 2084 |  |  | 1989.5 |  |  | 2106.5 |  |  | 2030.5 |  |  | 1870.5 |  |  | 2044.5 |  |  | 1932 |  |  | 2007.5 |  |  | 2075 |  |  | 2050 |  |  | 2143.5 |  |  | 2078.5 |  |  | 1943.5 |  |  | 1811.5 |  |  | 1991.5 |  |  | 2020.5 |  |  | 1987 |  |  | 1997.5 |  |  | 2009 |  |  | 2011.5 |  |  | 2019 |  |  | 1982 |  |  | 2137 |  |  | 2054.5 |  |  | 1963 |  |  | 2120.5 |  |  | 2070.5 |  |  | 2039.5 |  |  | 2200.5 |  |  | 2006.5 |  |  | 2107 |  |  | 2063.5 |  |  | 2114.5 |  |  | 2196.5 |  |  | 2024 |  |  | 2078.5 |  |  | 1899.5 |  |  | 2016.5 |  |  | 2065.5 |  |  | 1964 |  |  | 2074 |  |  | 1945 |  |  | 1988.5 |  |  | 2094 |  |  | 2119 |  |  | 2092.5 |  |  | 1981.5 |  |  | 1898.5 |  |  | 2023.5 |  |  | 2049.5 |  |  | 2057.5 |  |  | 2150.5 |  |  | 1960.5 |  |  | 1939.5 |  |  | 1944 |  |  | 1978.5 |  |  | 1955 |  |  | 2041.5 |  |  | 2048.5 |  |  | 2006.5 |  |  | 2050.5 |  |  | 2114 |  |  | 2087.5 |  |  | 2017 |  |  | 1941.5 |  |  | 2045.5 |  |  | 2004 |  |  | 2001 |  |  | 2007.5 |  |  | 2005 |  |  | 2064.5 |  |  | 1900.5 |  |  | 1954.5 |  |  | 1969.5 |  |  | 2058.5 |  |  | 2062.5 |  |  | 1899.5 |  |  | 1897 |  |  | 2037.5 |  |  | 2065.5 |  |  | 2018.5 |  |  | 2065.5 |  |  | 1931.5 |  |  | 1990.5 |  |  | 2124.5 |  |  | 2033.5 |  |  | 2120.5 |  |  | 2097.5 |  |  | 1915.5 |  |  | 1913.5 |  |  | 2012 |  |  | 1887.5 |  |  | 1972.5 |  |  | 2093 |  |  | 1959.5 |  |  | 1913.5 |  |  | 2007.5 |  |  | 1925.5 |  |  | 2137 |  |  | 2194.5 |  |  | 1996.5 |  |  | 1930.5 |  |  | 2116.5 |  |  | 2000 |  |  | 1950.5 |  |  | 2112.5 |  |  | 2033.5 |  |  | 2061.5 |  |  | 1966.5 |  |  | 1915.5 |  |  | 2066.5 |  |  | 2044.5 |  |  | 2042.5 |  |  | 1976.5 |  |  | 2106.5 |  |  | 2078 |  |  | 1997.5 |  |  | 1978.5 |  |  | 2162.5 |  |  | 2089.5 |  |  | 1937.5 |  |  | 2007.5 |  |  | 2115 |  |  | 2033.5 |  |  | 1959 |  |  | 1864.5 |  |  | 2069.5 |  |  | 2002.5 |  |  | 2029 |  |  | 1966 |  |  | 2018.5 |  |  | 2086.5 |  |  | 1863.5 |  |  | 2048.5 |  |  | 2039.5 |  |  | 2033.5 |  |  | 1999.5 |  |  | 2056.5 |  |  | 1974.5 |  |  | 2119.5 |  |  | 1967.5 |  |  | 2091.5 |  |  | 1928.5 |  |  | 2070.5 |  |  | 2123.5 |  |  | 2008.5 |  |  | 2004.5 |  |  | 2029.5 |  |  | 2028.5 |  |  | 2051.5 |  |  | 2040.5 |  |  | 2069.5 |  |  | 2030 |  |  | 2056.5 |  |  | 1996.5 |  |  | 2012.5 |  |  | 2006 |  |  | 2092.5 |  |  | 1983.5 |  |  | 2078.5 |  |  | 2020.5 |  |  | 2036 |  |  | 1890.5 |  |  | 1870.5 |  |  | 1938 |  |  | 1976 |  |  | 2046 |  |  | 2018.5 |  |  | 1995.5 |  |  | 2038.5 |  |  | 2219.5 |  |  | 2063 |  |  | 2039.5 |  |  | 2039.5 |  |  | 1943 |  |  | 2000 |  |  | 2010.5 |  |  | 2031.5 |  |  | 2020 |  |  | 1958.5 |  |  | 2079 |  |  | 1929.5 |  |  | 1916.5 |  |  | 2153 |  |  | 2109.5 |  |  | 2021.5 |  |  | 1889.5 |  |  | 2148 |  |  | 1984.5 |  |  | 1966.5 |  |  | 1969.5 |  |  | 1994.5 |  |  | 1988.5 |  |  | 2118.5 |  |  | 1923.5 |  |  | 2038.5 |  |  | 2077.5 |  |  | 2035.5 |  |  | 2022 |  |  | 2014.5 |  |  | 2035.5 |  |  | 2060.5 |  |  | 2058.5 |  |  | 2004.5 |  |  | 2079.5 |  |  | 2135.5 |  |  | 2026.5 |  |  | 2158 |  |  | 1955.5 |  |  | 1994 |  |  | 2158.5 |  |  | 2229.5 |  |  | 2198.5 |  |  | 1961.5 |  |  | 1948.5 |  |  | 1991.5 |  |  | 1901.5 |  |  | 2087.5 |  |  | 2053 |  |  | 1941.5 |  |  | 2039 |  |  | 1940.5 |  |  | 1892.5 |  |  | 2055.5 |  |  | 2096 |  |  | 1993.5 |  |  | 2047.5 |  |  | 1844 |  |  | 2002.5 |  |  | 1986 |  |  | 1985.5 |  |  | 1971.5 |  |  | 1980.5 |  |  | 2008 |  |  | 2158.5 |  |  | 2203.5 |  |  | 1955 |  |  | 2166.5 |  |  | 1937.5 |  |  | 2054 |  |  | 1979.5 |  |  | 2188.5 |  |  | 2111.5 |  |  | 2148.5 |  |  | 1920.5 |  |  | 2150.5 |  |  | 1904.5 |  |  | 1976.5 |  |  | 1902.5 |  |  | 1914.5 |  |  | 2178.5 |  |  | 2112 |  |  | 2107 |  |  | 2156.5 |  |  | 2017.5 |  |  | 2056
70 |  | 1972.5 |  |  | 2194.5 |  |  | 2073 |  |  | 2009.5 |  |  | 2215.5 |  |  | 2079.5 |  |  | 2137.5 |  |  | 2061.5 |  |  | 2074.5 |  |  | 2050.5 |  |  | 1982 |  |  | 2143.5 |  |  | 2126.5 |  |  | 1922.5 |  |  | 1913 |  |  | 2064.5 |  |  | 2191.5 |  |  | 2063.5 |  |  | 2171.5 |  |  | 1944.5 |  |  | 2093.5 |  |  | 2064.5 |  |  | 2123.5 |  |  | 1950.5 |  |  | 1930 |  |  | 2120.5 |  |  | 2041.5 |  |  | 2028.5 |  |  | 2133.5 |  |  | 1972 |  |  | 2088 |  |  | 2113.5 |  |  | 1900.5 |  |  | 2090.5 |  |  | 1948.5 |  |  | 2122 |  |  | 1968.5 |  |  | 2164 |  |  | 2008.5 |  |  | 2062.5 |  |  | 1892.5 |  |  | 2100.5 |  |  | 1942.5 |  |  | 2039 |  |  | 2232.5 |  |  | 2147 |  |  | 2011.5 |  |  | 2170.5 |  |  | 2091.5 |  |  | 2067.5 |  |  | 1989.5 |  |  | 2089.5 |  |  | 2071.5 |  |  | 2002.5 |  |  | 2134.5 |  |  | 2113.5 |  |  | 1981.5 |  |  | 2066 |  |  | 2075.5 |  |  | 2035.5 |  |  | 2039 |  |  | 2022.5 |  |  | 2145.5 |  |  | 2001.5 |  |  | 1965.5 |  |  | 2081 |  |  | 2108.5 |  |  | 1943 |  |  | 1904.5 |  |  | 2077.5 |  |  | 2046 |  |  | 2070.5 |  |  | 2048.5 |  |  | 2169.5 |  |  | 2159 |  |  | 2138 |  |  | 1976.5 |  |  | 2001.5 |  |  | 1917.5 |  |  | 2078.5 |  |  | 2041 |  |  | 2086.5 |  |  | 2084.5 |  |  | 2173.5 |  |  | 2141.5 |  |  | 2015.5 |  |  | 2165.5 |  |  | 2062.5 |  |  | 2026.5 |  |  | 2087.5 |  |  | 2106.5 |  |  | 2110 |  |  | 1913.5 |  |  | 1966 |  |  | 2014 |  |  | 1976 |  |  | 2216.5 |  |  | 2195.5 |  |  | 1936.5 |  |  | 2157.5 |  |  | 1963.5 |  |  | 2053 |  |  | 2025 |  |  | 1992.5 |  |  | 1974.5 |  |  | 1965.5 |  |  | 2078.5 |  |  | 2116.5 |  |  | 2143.5 |  |  | 2090.5 |  |  | 2144.5 |  |  | 2144.5 |  |  | 2037.5 |  |  | 2082.5 |  |  | 2038.5 |  |  | 2079.5 |  |  | 2177.5 |  |  | 1942.5 |  |  | 2047.5 |  |  | 2047.5 |  |  | 2098.5 |  |  | 2099.5 |  |  | 2020.5 |  |  | 2054.5 |  |  | 2075.5 |  |  | 2056 |  |  | 2018.5 |  |  | 2024.5 |  |  | 1982.5 |  |  | 1986.5 |  |  | 2085.5 |  |  | 2076 |  |  | 1984.5 |  |  | 2130.5 |  |  | 1964.5 |  |  | 2024.5 |  |  | 2086 |  |  | 2067.5 |  |  | 2108.5 |  |  | 2013 |  |  | 2080.5 |  |  | 1979 |  |  | 2113 |  |  | 2151.5 |  |  | 2102 |  |  | 2143.5 |  |  | 2026.5 |  |  | 2090.5 |  |  | 1972.5 |  |  | 2083.5 |  |  | 2064.5 |  |  | 2048.5 |  |  | 2084.5 |  |  | 2189.5 |  |  | 2084.5 |  |  | 2166 |  |  | 1999.5 |  |  | 1925 |  |  | 2005.5 |  |  | 2100.5 |  |  | 2028 |  |  | 2080.5 |  |  | 2011.5 |  |  | 2035.5 |  |  | 1971 |  |  | 2053.5 |  |  | 1979.5 |  |  | 1983.5 |  |  | 2177.5 |  |  | 2041.5 |  |  | 2006.5 |  |  | 2034 |  |  | 2017.5 |  |  | 2055.5 |  |  | 1990.5 |  |  | 2047.5 |  |  | 2093.5 |  |  | 2077.5 |  |  | 1980.5 |  |  | 2155 |  |  | 2140.5 |  |  | 2086.5 |  |  | 2097.5 |  |  | 2104.5 |  |  | 1972.5 |  |  | 2180.5 |  |  | 2103.5 |  |  | 2037.5 |  |  | 2122.5 |  |  | 2011.5 |  |  | 2111.5 |  |  | 1929.5 |  |  | 1861.5 |  |  | 1968 |  |  | 2032.5 |  |  | 2090.5 |  |  | 2019.5 |  |  | 2094.5 |  |  | 2100.5 |  |  | 2132.5 |  |  | 2132.5 |  |  | 2004.5 |  |  | 2095.5 |  |  | 1995.5 |  |  | 1990.5 |  |  | 2178.5 |  |  | 2037.5 |  |  | 1992.5 |  |  | 2013.5 |  |  | 2052.5 |  |  | 2122 |  |  | 2099.5 |  |  | 2029.5 |  |  | 1813 |  |  | 2216.5 |  |  | 2146 |  |  | 1928.5 |  |  | 2104.5 |  |  | 2161.5 |  |  | 2084.5 |  |  | 1971.5 |  |  | 2031.5 |  |  | 2052.5 |  |  | 1850.5 |  |  | 1961 |  |  | 1975.5 |  |  | 1890.5 |  |  | 2092.5 |  |  | 1962.5 |  |  | 2082 |  |  | 1974.5 |  |  | 2040.5 |  |  | 2129.5 |  |  | 2071.5 |  |  | 2147.5 |  |  | 2030.5 |  |  | 2010.5 |  |  | 2190.5 |  |  | 2176 |  |  | 2113 |  |  | 2008.5 |  |  | 1979.5 |  |  | 2047.5 |  |  | 2031 |  |  | 2189.5 |  |  | 2024.5 |  |  | 2034.5 |  |  | 1966 |  |  | 2113.5 |  |  | 2091.5 |  |  | 1941.5 |  |  | 1967.5 |  |  | 1991.5 |  |  | 2113.5 |  |  | 2103.5 |  |  | 2068.5 |  |  | 2197.5 |  |  | 1876 |  |  | 1998.5 |  |  | 2096.5 |  |  | 2082.5 |  |  | 2012.5 |  |  | 1982.5 |  |  | 2167 |  |  | 2015.5 |  |  | 2091.5 |  |  | 2125 |  |  | 2182.5 |  |  | 2094.5 |  |  | 2234 |  |  | 2044.5 |  |  | 2078.5 |  |  | 2203.5 |  |  | 1966.5 |  |  | 2048 |  |  | 2045 |  |  | 2027.5 |  |  | 1990.5 |  |  | 2092.5 |  |  | 2041.5 |  |  | 2147.5 |  |  | 2085.5 |  |  | 2006 |  |  | 2056.5 |  |  | 2051.5 |  |  | 2071 |  |  | 2018.5 |  |  | 1905.5 |  |  | 2090 |  |  | 2084.5 |  |  | 1932.5 |  |  | 2110.5 |  |  | 2036 |  |  | 2074.5 |  |  | 1975 |  |  | 2098.5 |  |  | 1955.5 |  |  | 2083.5 |  |  | 1987 |  |  | 1985.5 |  |  | 2175.5 |  |  | 2158.5 |  |  | 2052 |  |  | 2009.5 |  |  | 1882.5 |  |  | 2186.5 |  |  | 2127.5 |  |  | 2053.5 |  |  | 2067 |  |  | 1944.5 |  |  | 2148.5 |  |  | 2127.5 |  |  | 1977 |  |  | 2087 |  |  | 2202.5 |  |  | 1965.5 |  |  | 1960.5 |  |  | 2065.5 |  |  | 2039.5 |  |  | 2072.5 |  |  | 2071.5 |  |  | 2110.5 |  |  | 2010.5 |  |  | 2047.5 |  |  | 2075 |  |  | 2030.5 |  |  | 2100.5 |  |  | 2271.5 |  |  | 2118.5 |  |  | 2120 |  |  | 2098.5 |  |  | 2182.5 |  |  | 2036.5 |  |  | 1881.5 |  |  | 2151.5 |  |  | 1951 |  |  | 2048 |  |  | 1983 |  |  | 2166 |  |  | 1950.5 |  |  | 2098 |  |  | 2076.5 |  |  | 2030 |  |  | 2062.5 |  |  | 2168.5 |  |  | 2035.5 |  |  | 2024.5 |  |  | 1989.5 |  |  | 2097 |  |  | 2080.5 |  |  | 2199.5 |  |  | 2035.5 |  |  | 2100 |  |  | 2155.5 |  |  | 1976.5 |  |  | 2012.5 |  |  | 2058 |  |  | 2010.5 |  |  | 1961.5 |  |  | 2120.5 |  |  | 2007.5 |  |  | 2043.5 |  |  | 1991.5 |  |  | 2123.5 |  |  | 2080.5 |  |  | 2066.5 |  |  | 1941.5 |  |  | 1940 |  |  | 2049.5 |  |  | 2009.5 |  |  | 1965.5 |  |  | 2081.5 |  |  | 2183.5 |  |  | 2005 |  |  | 2085.5 |  |  | 2144 |  |  | 1976 |  |  | 1958.5 |  |  | 2190.5 |  |  | 1972.5 |  |  | 1992 |  |  | 2106.5 |  |  | 2097.5 |  |  | 2061.5 |  |  | 1946 |  |  | 2044.5 |  |  | 1910.5 |  |  | 2068.5 |  |  | 1965.5 |  |  | 1988.5 |  |  | 1975 |  |  | 2010.5 |  |  | 2158 |  |  | 2014.5 |  |  | 1924.5 |  |  | 2039.5 |  |  | 2120 |  |  | 1974.5 |  |  | 2027 |  |  | 2047 |  |  | 2000.5 |  |  | 1935.5 |  |  | 2013.5 |  |  | 2180.5 |  |  | 2174 |  |  | 2124.5 |  |  | 2010.5 |  |  | 1865.5 |  |  | 2008 |  |  | 2122.5 |  |  | 1981.5 |  |  | 1842.5 |  |  | 2047.5 |  |  | 2137 |  |  | 1912.5 |  |  | 2092.5 |  |  | 2088.5 |  |  | 2049.5 |  |  | 2047.5 |  |  | 2008.5 |  |  | 2145 |  |  | 2044.5 |  |  | 1964.5 |  |  | 2036 |  |  | 1942.5 |  |  | 1893.5 |  |  | 2031.5 |  |  | 2083 |  |  | 2102.5 |  |  | 2092.5 |  |  | 2045.5 |  |  | 2016.5 |  |  | 2126.5 |  |  | 2115 |  |  | 2064 |  |  | 2053.5 |  |  | 2106.5 |  |  | 2104.5 |  |  | 1902.5 |  |  | 1943 |  |  | 2101 |  |  | 1970 |  |  | 2161.5 |  |  | 2060 |  |  | 2043.5 |  |  | 2147.5 |  |  | 2083 |  |  | 1998.5 |  |  | 2104.5 |  |  | 2053.5 |  |  | 2126.5 |  |  | 1840.5 |  |  | 2045 |  |  | 2107 |  |  | 1949.5 |  |  | 2110.5 |  |  | 1991 |  |  | 1929.5 |  |  | 2055.5 |  |  | 2023 |  |  | 2145.5 |  |  | 2182.5 |  |  | 1976 |  |  | 2104.5 |  |  | 2070.5 |  |  | 2086 |  |  | 2008.5 |  |  | 2011 |  |  | 2175.5 |  |  | 2184 |  |  | 1983.5 |  |  | 1962.5 |  |  | 2027.5 |  |  | 2030.5 |  |  | 2062.5 |  |  | 1975.5 |  |  | 2102 |  |  | 1968.5 |  |  | 2064.5 |  |  | 2000.5 |  |  | 1976.5 |  |  | 2045.5 |  |  | 2030 |  |  | 1986.5 |  |  | 2051 |  |  | 2051.5 |  |  | 1948.5 |  |  | 2109.5 |  |  | 2060.5 |  |  | 2034.5 |  |  | 2084.5 |  |  | 2025.5 |  |  | 2098.5 |  |  | 1959.5 |  |  | 1971 |  |  | 2090.5 |  |  | 1976 |  |  | 2078 |  |  | 2082.5 |  |  | 1888 |  |  | 1917.5 |  |  | 2103.5 |  |  | 2125.5 |  |  | 2039.5 |  |  | 2137.5 |  |  | 2146.5 |  |  | 2093.5 |  |  | 1995 |  |  | 2168 |  |  | 1937.5 |  |  | 2008.5 |  |  | 2044 |  |  | 1977.5 |  |  | 2005.5 |  |  | 1991.5 |  |  | 1990.5 |  |  | 2016.5 |  |  | 1970 |  |  | 2027.5 |  |  | 2054.5 |  |  | 1986.5 |  |  | 2015 |  |  | 2108.5 |  |  | 2055.5 |  |  | 2065.5 |  |  | 2213.5 |  |  | 2119.5 |  |  | 1990.5 |  |  | 2178.5 |  |  | 1708.5 |  |  | 2042.5 |  |  | 1919 |  |  | 2150.5 |  |  | 2096.5 |  |  | 2120.5 |  |  | 1958.5 |  |  | 1970.5 |  |  | 2022.5 |  |  | 1994.5 |  |  | 1890 |  |  | 1974.5 |  |  | 2087.5 |  |  | 2116.5 |  |  | 2050 |  |  | 2064.5 |  |  | 1932 |  |  | 1940.5 |  |  | 2069.5 |  |  | 1976.5 |  |  | 2088 |  |  | 1948.5 |  |  | 2051 |  |  | 2029 |  |  | 2064.5 |  |  | 2039 |  |  | 2162 |  |  | 2120.5 |  |  | 2074.5 |  |  | 1917.5 |  |  | 2111 |  |  | 2122.5 |  |  | 1979.5 |  |  | 1953.5 |  |  | 2099.5 |  |  | 1994.5 |  |  | 2001.5 |  |  | 2020.5 |  |  | 2120.5 |  |  | 2054 |  |  | 2193.5 |  |  | 2010 |  |  | 2027.5 |  |  | 1985.5 |  |  | 2158.5 |  |  | 2002 |  |  | 2054 |  |  | 2217 |  |  | 2036.5 |  |  | 2010 |  |  | 2072.5 |  |  | 2212.5 |  |  | 2042.5 |  |  | 2019.5 |  |  | 1903.5 |  |  | 2126.5 |  |  | 2156.5 |  |  | 2124.5 |  |  | 2111 |  |  | 1947.5 |  |  | 1944.5 |  |  | 2065.5 |  |  | 1937.5 |  |  | 1990 |  |  | 2024.5 |  |  | 2072 |  |  | 2086.5 |  |  | 2078.5 |  |  | 1943.5 |  |  | 1951.5 |  |  | 1923 |  |  | 1975.5 |  |  | 1820 |  |  | 1964.5 |  |  | 2088.5 |  |  | 2177.5 |  |  | 2086.5 |  |  | 2058.5 |  |  | 2074.5 |  |  | 1894.5 |  |  | 2125.5 |  |  | 2049.5 |  |  | 1962 |  |  | 2080.5 |  |  | 1983.5 |  |  | 2005.5 |  |  | 2103.5 |  |  | 2109.5 |  |  | 2007 |  |  | 1991 |  |  | 2048.5 |  |  | 1961 |  |  | 2188.5 |  |  | 2025.5 |  |  | 2165.5 |  |  | 2107.5 |  |  | 2000.5 |  |  | 2097.5 |  |  | 2038.5 |  |  | 2071.5 |  |  | 2070 |  |  | 2032.5 |  |  | 2261.5 |  |  | 2024.5 |  |  | 1940 |  |  | 1996.5 |  |  | 1994.5 |  |  | 2153 |  |  | 1937 |  |  | 2081.5 |  |  | 1967 |  |  | 1893 |  |  | 1925.5 |  |  | 2094 |  |  | 2231.5 |  |  | 2049.5 |  |  | 2173.5 |  |  | 2026.5 |  |  | 1946.5 |  |  | 1993.5 |  |  | 1900.5 |  |  | 2036.5 |  |  | 2073.5 |  |  | 1980.5 |  |  | 1963 |  |  | 1973 |  |  | 2112.5 |  |  | 2101.5 |  |  | 2032.5 |  |  | 2071.5 |  |  | 2005.5 |  |  | 2057.5 |  |  | 2160.5 |  |  | 2003.5 |  |  | 2268 |  |  | 1997.5 |  |  | 2027 |  |  | 1974.5 |  |  | 2179.5 |  |  | 2107.5 |  |  | 2123 |  |  | 2032.5 |  |  | 1981.5 |  |  | 2074 |  |  | 2105.5 |  |  | 2004.5 |  |  | 2072.5 |  |  | 2050.5 |  |  | 2006.5 |  |  | 2072.5 |  |  | 2087 |  |  | 2009.5 |  |  | 1957.5 |  |  | 2097.5 |  |  | 2128.5 |  |  | 2074 |  |  | 2035.5 |  |  | 2142.5 |  |  | 2005 |  |  | 2108.5 |  |  | 2168.5 |  |  | 2044 |  |  | 2143.5 |  |  | 2156.5 |  |  | 1990.5 |  |  | 2044 |  |  | 1879.5 |  |  | 2044.5 |  |  | 2052 |  |  | 2059.5 |  |  | 2081.5 |  |  | 2011.5 |  |  | 1850.5 |  |  | 2134.5 |  |  | 2148.5 |  |  | 1958.5 |  |  | 2066 |  |  | 2004 |  |  | 1907.5 |  |  | 2089.5 |  |  | 1958.5 |  |  | 2093 |  |  | 2171.5 |  |  | 1990.5 |  |  | 1998.5 |  |  | 1921.5 |  |  | 1995.5 |  |  | 2095.5 |  |  | 1978.5 |  |  | 2105.5 |  |  | 1897.5 |  |  | 2057 |  |  | 2015.5 |  |  | 1958.5 |  |  | 2027.5 |  |  | 2133.5 |  |  | 2140.5 |  |  | 2060.5 |  |  | 2103.5 |  |  | 2100.5 |  |  | 1929.5 |  |  | 2131.5 |  |  | 2008.5 |  |  | 1993.5 |  |  | 2074.5 |  |  | 2114 |  |  | 2062.5 |  |  | 2083.5 |  |  | 2012 |  |  | 2090.5 |  |  | 2073.5 |  |  | 2129 |  |  | 2056.5 |  |  | 2211.5 |  |  | 2161.5 |  |  | 2131 |  |  | 2018.5 |  |  | 2135.5 |  |  | 2069.5 |  |  | 1896.5 |  |  | 2070.5 |  |  | 1979 |  |  | 2022.5 |  |  | 2114 |  |  | 2089 |  |  | 2169.5 |  |  | 2093.5 |  |  | 1967.5 |  |  | 1850.5 |  |  | 2017.5 |  |  | 2059.5 |  |  | 2008 |  |  | 2021.5 |  |  | 2030 |  |  | 2040.5 |  |  | 2066 |  |  | 2021 |  |  | 2152 |  |  | 2078.5 |  |  | 2002 |  |  | 2135.5 |  |  | 2099.5 |  |  | 2078.5 |  |  | 2239.5 |  |  | 2027.5 |  |  | 2133 |  |  | 2084.5 |  |  | 2143.5 |  |  | 2225.5 |  |  | 2039 |  |  | 2093.5 |  |  | 1946.5 |  |  | 2037.5 |  |  | 2112.5 |  |  | 1988 |  |  | 2089 |  |  | 1984 |  |  | 2027.5 |  |  | 2141 |  |  | 2134 |  |  | 2118.5 |  |  | 1996.5 |  |  | 1937.5 |  |  | 2038.5 |  |  | 2064.5 |  |  | 2072.5 |  |  | 2174.5 |  |  | 1981.5 |  |  | 1978.5 |  |  | 1965 |  |  | 1993.5 |  |  | 1970 |  |  | 2080.5 |  |  | 2087.5 |  |  | 2045.5 |  |  | 2079.5 |  |  | 2153 |  |  | 2126.5 |  |  | 2056 |  |  | 1967.5 |  |  | 2084.5 |  |  | 2019 |  |  | 2027 |  |  | 2046.5 |  |  | 2026 |  |  | 2093.5 |  |  | 1915.5 |  |  | 1975.5 |  |  | 1990.5 |  |  | 2073.5 |  |  | 2077.5 |  |  | 1938.5 |  |  | 1936 |  |  | 2076.5 |  |  | 2112.5 |  |  | 2057.5 |  |  | 2086.5 |  |  | 1970.5 |  |  | 2029.5 |  |  | 2150.5 |  |  | 2057.5 |  |  | 2146.5 |  |  | 2118.5 |  |  | 1954.5 |  |  | 1928.5 |  |  | 2051 |  |  | 1908.5 |  |  | 1998.5 |  |  | 2117 |  |  | 2006.5 |  |  | 1942.5 |  |  | 2022.5 |  |  | 1954.5 |  |  | 2176 |  |  | 2233.5 |  |  | 2020.5 |  |  | 1951.5 |  |  | 2155.5 |  |  | 2039 |  |  | 1997.5 |  |  | 2151.5 |  |  | 2054.5 |  |  | 2108.5 |  |  | 1990.5 |  |  | 1954.5 |  |  | 2087.5 |  |  | 2073.5 |  |  | 2081.5 |  |  | 2015.5 |  |  | 2130.5 |  |  | 2099 |  |  | 2021.5 |  |  | 1993.5 |  |  | 2191.5 |  |  | 2128.5 |  |  | 1961.5 |  |  | 2033.5 |  |  | 2144 |  |  | 2080.5 |  |  | 1983 |  |  | 1893.5 |  |  | 2084.5 |  |  | 2041.5 |  |  | 2068 |  |  | 1995 |  |  | 2057.5 |  |  | 2110.5 |  |  | 1892.5 |  |  | 2095.5 |  |  | 2078.5 |  |  | 2048.5 |  |  | 2023.5 |  |  | 2103.5 |  |  | 1995.5 |  |  | 2166.5 |  |  | 1982.5 |  |  | 2138.5 |  |  | 1967.5 |  |  | 2085.5 |  |  | 2170.5 |  |  | 2032.5 |  |  | 2028.5 |  |  | 2058.5 |  |  | 2057.5 |  |  | 2066.5 |  |  | 2055.5 |  |  | 2108.5 |  |  | 2059 |  |  | 2071.5 |  |  | 2022.5 |  |  | 2059.5 |  |  | 2035 |  |  | 2116.5 |  |  | 2009.5 |  |  | 2093.5 |  |  | 2046.5 |  |  | 2051 |  |  | 1929.5 |  |  | 1909.5 |  |  | 1953 |  |  | 2002 |  |  | 2075 |  |  | 2044.5 |  |  | 2034.5 |  |  | 2077.5 |  |  | 2248.5 |  |  | 2110 |  |  | 2065.5 |  |  | 2065.5 |  |  | 1972 |  |  | 2047 |  |  | 2036.5 |  |  | 2070.5 |  |  | 2067 |  |  | 2005.5 |  |  | 2118 |  |  | 1953.5 |  |  | 1940.5 |  |  | 2179 |  |  | 2135.5 |  |  | 2060.5 |  |  | 1918.5 |  |  | 2172 |  |  | 2010.5 |  |  | 2005.5 |  |  | 1993.5 |  |  | 2020.5 |  |  | 2009.5 |  |  | 2133.5 |  |  | 1944.5 |  |  | 2077.5 |  |  | 2116.5 |  |  | 2082.5 |  |  | 2037 |  |  | 2061.5 |  |  | 2074.5 |  |  | 2099.5 |  |  | 2097.5 |  |  | 2043.5 |  |  | 2103.5 |  |  | 2174.5 |  |  | 2047.5 |  |  | 2197 |  |  | 1981.5 |  |  | 2009 |  |  | 2184.5 |  |  | 2268.5 |  |  | 2227.5 |  |  | 1987.5 |  |  | 1987.5 |  |  | 2030.5 |  |  | 1940.5 |  |  | 2134.5 |  |  | 2079 |  |  | 1965.5 |  |  | 2054 |  |  | 1955.5 |  |  | 1939.5 |  |  | 2094.5 |  |  | 2120 |  |  | 2008.5 |  |  | 2062.5 |  |  | 1868 |  |  | 2026.5 |  |  | 2015 |  |  | 2024.5 |  |  | 1997.5 |  |  | 1995.5 |  |  | 2037 |  |  | 2173.5 |  |  | 2242.5 |  |  | 1981 |  |  | 2195.5 |  |  | 1961.5 |  |  | 2083 |  |  | 2003.5 |  |  | 2209.5 |  |  | 2150.5 |  |  | 2174.5 |  |  | 1949.5 |  |  | 2165.5 |  |  | 1943.5 |  |  | 2005.5 |  |  | 1941.5 |  |  | 1938.5 |  |  | 2217.5 |  |  | 2127 |  |  | 2133 |  |  | 2195.5 |  |  | 2032.5 |  |  | 2071
71 |  | 2019.5 |  |  | 2209.5 |  |  | 2099 |  |  | 2056.5 |  |  | 2230.5 |  |  | 2103.5 |  |  | 2176.5 |  |  | 2100.5 |  |  | 2095.5 |  |  | 2071.5 |  |  | 2008 |  |  | 2158.5 |  |  | 2150.5 |  |  | 1943.5 |  |  | 1937 |  |  | 2085.5 |  |  | 2206.5 |  |  | 2102.5 |  |  | 2195.5 |  |  | 1983.5 |  |  | 2140.5 |  |  | 2088.5 |  |  | 2170.5 |  |  | 1971.5 |  |  | 1954 |  |  | 2159.5 |  |  | 2088.5 |  |  | 2052.5 |  |  | 2172.5 |  |  | 1987 |  |  | 2127 |  |  | 2142.5 |  |  | 1915.5 |  |  | 2129.5 |  |  | 1987.5 |  |  | 2146 |  |  | 1992.5 |  |  | 2203 |  |  | 2047.5 |  |  | 2101.5 |  |  | 1918.5 |  |  | 2129.5 |  |  | 1968.5 |  |  | 2078 |  |  | 2261.5 |  |  | 2194 |  |  | 2040.5 |  |  | 2199.5 |  |  | 2117.5 |  |  | 2106.5 |  |  | 2010.5 |  |  | 2115.5 |  |  | 2097.5 |  |  | 2041.5 |  |  | 2173.5 |  |  | 2134.5 |  |  | 1996.5 |  |  | 2095 |  |  | 2090.5 |  |  | 2050.5 |  |  | 2054 |  |  | 2061.5 |  |  | 2169.5 |  |  | 2022.5 |  |  | 1980.5 |  |  | 2120 |  |  | 2147.5 |  |  | 1982 |  |  | 1943.5 |  |  | 2124.5 |  |  | 2093 |  |  | 2091.5 |  |  | 2072.5 |  |  | 2184.5 |  |  | 2185 |  |  | 2177 |  |  | 2000.5 |  |  | 2040.5 |  |  | 1956.5 |  |  | 2102.5 |  |  | 2062 |  |  | 2101.5 |  |  | 2131.5 |  |  | 2188.5 |  |  | 2188.5 |  |  | 2044.5 |  |  | 2186.5 |  |  | 2077.5 |  |  | 2055.5 |  |  | 2108.5 |  |  | 2127.5 |  |  | 2131 |  |  | 1952.5 |  |  | 1995 |  |  | 2038 |  |  | 2023 |  |  | 2255.5 |  |  | 2221.5 |  |  | 1965.5 |  |  | 2181.5 |  |  | 1987.5 |  |  | 2077 |  |  | 2064 |  |  | 2018.5 |  |  | 2021.5 |  |  | 2004.5 |  |  | 2104.5 |  |  | 2155.5 |  |  | 2182.5 |  |  | 2137.5 |  |  | 2173.5 |  |  | 2165.5 |  |  | 2063.5 |  |  | 2103.5 |  |  | 2085.5 |  |  | 2108.5 |  |  | 2192.5 |  |  | 1981.5 |  |  | 2094.5 |  |  | 2076.5 |  |  | 2113.5 |  |  | 2120.5 |  |  | 2059.5 |  |  | 2093.5 |  |  | 2114.5 |  |  | 2071 |  |  | 2044.5 |  |  | 2063.5 |  |  | 2003.5 |  |  | 2025.5 |  |  | 2124.5 |  |  | 2115 |  |  | 2005.5 |  |  | 2169.5 |  |  | 1988.5 |  |  | 2039.5 |  |  | 2125 |  |  | 2082.5 |  |  | 2155.5 |  |  | 2037 |  |  | 2119.5 |  |  | 2000 |  |  | 2152 |  |  | 2172.5 |  |  | 2141 |  |  | 2182.5 |  |  | 2041.5 |  |  | 2129.5 |  |  | 1987.5 |  |  | 2112.5 |  |  | 2093.5 |  |  | 2074.5 |  |  | 2110.5 |  |  | 2228.5 |  |  | 2108.5 |  |  | 2192 |  |  | 2028.5 |  |  | 1964 |  |  | 2020.5 |  |  | 2126.5 |  |  | 2043 |  |  | 2101.5 |  |  | 2035.5 |  |  | 2064.5 |  |  | 1995 |  |  | 2092.5 |  |  | 2008.5 |  |  | 2030.5 |  |  | 2203.5 |  |  | 2056.5 |  |  | 2035.5 |  |  | 2060 |  |  | 2032.5 |  |  | 2076.5 |  |  | 2014.5 |  |  | 2068.5 |  |  | 2114.5 |  |  | 2101.5 |  |  | 2006.5 |  |  | 2184 |  |  | 2166.5 |  |  | 2125.5 |  |  | 2136.5 |  |  | 2128.5 |  |  | 1993.5 |  |  | 2206.5 |  |  | 2118.5 |  |  | 2061.5 |  |  | 2169.5 |  |  | 2037.5 |  |  | 2126.5 |  |  | 1955.5 |  |  | 1882.5 |  |  | 2007 |  |  | 2079.5 |  |  | 2111.5 |  |  | 2043.5 |  |  | 2123.5 |  |  | 2147.5 |  |  | 2156.5 |  |  | 2171.5 |  |  | 2030.5 |  |  | 2116.5 |  |  | 2034.5 |  |  | 2005.5 |  |  | 2217.5 |  |  | 2061.5 |  |  | 2021.5 |  |  | 2028.5 |  |  | 2067.5 |  |  | 2143 |  |  | 2138.5 |  |  | 2068.5 |  |  | 1839 |  |  | 2245.5 |  |  | 2193 |  |  | 1943.5 |  |  | 2143.5 |  |  | 2185.5 |  |  | 2113.5 |  |  | 1997.5 |  |  | 2070.5 |  |  | 2081.5 |  |  | 1897.5 |  |  | 1982 |  |  | 2001.5 |  |  | 1914.5 |  |  | 2107.5 |  |  | 1986.5 |  |  | 2108 |  |  | 2013.5 |  |  | 2079.5 |  |  | 2155.5 |  |  | 2097.5 |  |  | 2176.5 |  |  | 2069.5 |  |  | 2057.5 |  |  | 2219.5 |  |  | 2197 |  |  | 2134 |  |  | 2047.5 |  |  | 1994.5 |  |  | 2073.5 |  |  | 2055 |  |  | 2236.5 |  |  | 2063.5 |  |  | 2060.5 |  |  | 1981 |  |  | 2160.5 |  |  | 2117.5 |  |  | 1967.5 |  |  | 2006.5 |  |  | 2017.5 |  |  | 2134.5 |  |  | 2142.5 |  |  | 2115.5 |  |  | 2223.5 |  |  | 1900 |  |  | 2027.5 |  |  | 2135.5 |  |  | 2121.5 |  |  | 2051.5 |  |  | 2021.5 |  |  | 2206 |  |  | 2041.5 |  |  | 2130.5 |  |  | 2164 |  |  | 2203.5 |  |  | 2133.5 |  |  | 2281 |  |  | 2070.5 |  |  | 2093.5 |  |  | 2242.5 |  |  | 1987.5 |  |  | 2095 |  |  | 2066 |  |  | 2056.5 |  |  | 2029.5 |  |  | 2131.5 |  |  | 2080.5 |  |  | 2194.5 |  |  | 2106.5 |  |  | 2045 |  |  | 2095.5 |  |  | 2075.5 |  |  | 2097 |  |  | 2042.5 |  |  | 1926.5 |  |  | 2137 |  |  | 2105.5 |  |  | 1953.5 |  |  | 2134.5 |  |  | 2083 |  |  | 2095.5 |  |  | 2022 |  |  | 2113.5 |  |  | 2002.5 |  |  | 2107.5 |  |  | 2002 |  |  | 2009.5 |  |  | 2204.5 |  |  | 2197.5 |  |  | 2073 |  |  | 2048.5 |  |  | 1921.5 |  |  | 2233.5 |  |  | 2166.5 |  |  | 2092.5 |  |  | 2091 |  |  | 1973.5 |  |  | 2177.5 |  |  | 2153.5 |  |  | 1998 |  |  | 2126 |  |  | 2228.5 |  |  | 1986.5 |  |  | 1986.5 |  |  | 2080.5 |  |  | 2078.5 |  |  | 2098.5 |  |  | 2110.5 |  |  | 2157.5 |  |  | 2049.5 |  |  | 2071.5 |  |  | 2096 |  |  | 2056.5 |  |  | 2147.5 |  |  | 2297.5 |  |  | 2157.5 |  |  | 2141 |  |  | 2119.5 |  |  | 2229.5 |  |  | 2083.5 |  |  | 1920.5 |  |  | 2175.5 |  |  | 1972 |  |  | 2074 |  |  | 2009 |  |  | 2181 |  |  | 1989.5 |  |  | 2145 |  |  | 2097.5 |  |  | 2051 |  |  | 2101.5 |  |  | 2189.5 |  |  | 2059.5 |  |  | 2048.5 |  |  | 2028.5 |  |  | 2118 |  |  | 2119.5 |  |  | 2228.5 |  |  | 2056.5 |  |  | 2115 |  |  | 2181.5 |  |  | 2023.5 |  |  | 2036.5 |  |  | 2105 |  |  | 2034.5 |  |  | 1985.5 |  |  | 2135.5 |  |  | 2046.5 |  |  | 2072.5 |  |  | 2012.5 |  |  | 2138.5 |  |  | 2101.5 |  |  | 2095.5 |  |  | 1970.5 |  |  | 1979 |  |  | 2078.5 |  |  | 2030.5 |  |  | 1980.5 |  |  | 2120.5 |  |  | 2209.5 |  |  | 2044 |  |  | 2132.5 |  |  | 2170 |  |  | 1997 |  |  | 1979.5 |  |  | 2229.5 |  |  | 2011.5 |  |  | 2031 |  |  | 2127.5 |  |  | 2121.5 |  |  | 2076.5 |  |  | 1967 |  |  | 2083.5 |  |  | 1949.5 |  |  | 2083.5 |  |  | 1989.5 |  |  | 2014.5 |  |  | 2014 |  |  | 2049.5 |  |  | 2182 |  |  | 2053.5 |  |  | 1945.5 |  |  | 2078.5 |  |  | 2135 |  |  | 2003.5 |  |  | 2066 |  |  | 2076 |  |  | 2026.5 |  |  | 1961.5 |  |  | 2028.5 |  |  | 2227.5 |  |  | 2221 |  |  | 2163.5 |  |  | 2034.5 |  |  | 1886.5 |  |  | 2034 |  |  | 2143.5 |  |  | 2020.5 |  |  | 1871.5 |  |  | 2062.5 |  |  | 2176 |  |  | 1951.5 |  |  | 2113.5 |  |  | 2135.5 |  |  | 2096.5 |  |  | 2073.5 |  |  | 2047.5 |  |  | 2166 |  |  | 2083.5 |  |  | 1979.5 |  |  | 2075 |  |  | 1968.5 |  |  | 1914.5 |  |  | 2060.5 |  |  | 2109 |  |  | 2141.5 |  |  | 2107.5 |  |  | 2084.5 |  |  | 2031.5 |  |  | 2155.5 |  |  | 2130 |  |  | 2093 |  |  | 2100.5 |  |  | 2153.5 |  |  | 2128.5 |  |  | 1941.5 |  |  | 1969 |  |  | 2122 |  |  | 1994 |  |  | 2208.5 |  |  | 2107 |  |  | 2090.5 |  |  | 2194.5 |  |  | 2122 |  |  | 2019.5 |  |  | 2151.5 |  |  | 2082.5 |  |  | 2150.5 |  |  | 1866.5 |  |  | 2084 |  |  | 2146 |  |  | 1970.5 |  |  | 2131.5 |  |  | 2030 |  |  | 1968.5 |  |  | 2102.5 |  |  | 2052 |  |  | 2166.5 |  |  | 2229.5 |  |  | 2015 |  |  | 2130.5 |  |  | 2096.5 |  |  | 2112 |  |  | 2029.5 |  |  | 2035 |  |  | 2201.5 |  |  | 2208 |  |  | 2022.5 |  |  | 2001.5 |  |  | 2051.5 |  |  | 2051.5 |  |  | 2088.5 |  |  | 1990.5 |  |  | 2123 |  |  | 2007.5 |  |  | 2103.5 |  |  | 2039.5 |  |  | 2015.5 |  |  | 2071.5 |  |  | 2069 |  |  | 2001.5 |  |  | 2090 |  |  | 2090.5 |  |  | 1963.5 |  |  | 2148.5 |  |  | 2107.5 |  |  | 2060.5 |  |  | 2099.5 |  |  | 2046.5 |  |  | 2137.5 |  |  | 1985.5 |  |  | 2010 |  |  | 2137.5 |  |  | 2015 |  |  | 2107 |  |  | 2103.5 |  |  | 1914 |  |  | 1941.5 |  |  | 2129.5 |  |  | 2172.5 |  |  | 2060.5 |  |  | 2161.5 |  |  | 2172.5 |  |  | 2117.5 |  |  | 2024 |  |  | 2194 |  |  | 1958.5 |  |  | 2032.5 |  |  | 2070 |  |  | 2016.5 |  |  | 2029.5 |  |  | 2020.5 |  |  | 2016.5 |  |  | 2055.5 |  |  | 1985 |  |  | 2053.5 |  |  | 2078.5 |  |  | 2010.5 |  |  | 2036 |  |  | 2132.5 |  |  | 2070.5 |  |  | 2104.5 |  |  | 2252.5 |  |  | 2158.5 |  |  | 2037.5 |  |  | 2199.5 |  |  | 1723.5 |  |  | 2071.5 |  |  | 1948 |  |  | 2189.5 |  |  | 2135.5 |  |  | 2135.5 |  |  | 1984.5 |  |  | 2009.5 |  |  | 2048.5 |  |  | 2018.5 |  |  | 1929 |  |  | 1989.5 |  |  | 2113.5 |  |  | 2145.5 |  |  | 2076 |  |  | 2093.5 |  |  | 1971 |  |  | 1955.5 |  |  | 2093.5 |  |  | 1991.5 |  |  | 2112 |  |  | 1972.5 |  |  | 2090 |  |  | 2044 |  |  | 2103.5 |  |  | 2068 |  |  | 2191 |  |  | 2141.5 |  |  | 2121.5 |  |  | 1943.5 |  |  | 2140 |  |  | 2148.5 |  |  | 2018.5 |  |  | 1982.5 |  |  | 2146.5 |  |  | 2015.5 |  |  | 2048.5 |  |  | 2044.5 |  |  | 2135.5 |  |  | 2080 |  |  | 2219.5 |  |  | 2031 |  |  | 2074.5 |  |  | 2011.5 |  |  | 2184.5 |  |  | 2049 |  |  | 2093 |  |  | 2232 |  |  | 2065.5 |  |  | 2025 |  |  | 2087.5 |  |  | 2238.5 |  |  | 2081.5 |  |  | 2058.5 |  |  | 1950.5 |  |  | 2147.5 |  |  | 2180.5 |  |  | 2163.5 |  |  | 2126 |  |  | 1962.5 |  |  | 1970.5 |  |  | 2094.5 |  |  | 1976.5 |  |  | 2029 |  |  | 2053.5 |  |  | 2093 |  |  | 2101.5 |  |  | 2099.5 |  |  | 1982.5 |  |  | 1980.5 |  |  | 1944 |  |  | 2004.5 |  |  | 1835 |  |  | 2003.5 |  |  | 2117.5 |  |  | 2216.5 |  |  | 2101.5 |  |  | 2073.5 |  |  | 2121.5 |  |  | 1941.5 |  |  | 2146.5 |  |  | 2078.5 |  |  | 1991 |  |  | 2106.5 |  |  | 2030.5 |  |  | 2020.5 |  |  | 2142.5 |  |  | 2138.5 |  |  | 2031 |  |  | 2012 |  |  | 2087.5 |  |  | 2000 |  |  | 2217.5 |  |  | 2040.5 |  |  | 2191.5 |  |  | 2128.5 |  |  | 2039.5 |  |  | 2121.5 |  |  | 2059.5 |  |  | 2110.5 |  |  | 2109 |  |  | 2058.5 |  |  | 2276.5 |  |  | 2045.5 |  |  | 1987 |  |  | 2035.5 |  |  | 2033.5 |  |  | 2168 |  |  | 1976 |  |  | 2105.5 |  |  | 1991 |  |  | 1914 |  |  | 1964.5 |  |  | 2133 |  |  | 2255.5 |  |  | 2088.5 |  |  | 2212.5 |  |  | 2050.5 |  |  | 1993.5 |  |  | 2040.5 |  |  | 1939.5 |  |  | 2062.5 |  |  | 2097.5 |  |  | 2006.5 |  |  | 2010 |  |  | 2002 |  |  | 2141.5 |  |  | 2116.5 |  |  | 2053.5 |  |  | 2097.5 |  |  | 2029.5 |  |  | 2104.5 |  |  | 2175.5 |  |  | 2027.5 |  |  | 2315 |  |  | 2012.5 |  |  | 2042 |  |  | 1995.5 |  |  | 2203.5 |  |  | 2128.5 |  |  | 2170 |  |  | 2047.5 |  |  | 1996.5 |  |  | 2121 |  |  | 2120.5 |  |  | 2025.5 |  |  | 2119.5 |  |  | 2097.5 |  |  | 2030.5 |  |  | 2093.5 |  |  | 2126 |  |  | 2038.5 |  |  | 1996.5 |  |  | 2126.5 |  |  | 2157.5 |  |  | 2095 |  |  | 2074.5 |  |  | 2168.5 |  |  | 2034 |  |  | 2123.5 |  |  | 2189.5 |  |  | 2091 |  |  | 2164.5 |  |  | 2177.5 |  |  | 2029.5 |  |  | 2068 |  |  | 1900.5 |  |  | 2065.5 |  |  | 2078 |  |  | 2083.5 |  |  | 2120.5 |  |  | 2037.5 |  |  | 1871.5 |  |  | 2155.5 |  |  | 2174.5 |  |  | 1987.5 |  |  | 2092 |  |  | 2030 |  |  | 1928.5 |  |  | 2115.5 |  |  | 1984.5 |  |  | 2114 |  |  | 2210.5 |  |  | 2019.5 |  |  | 2037.5 |  |  | 1960.5 |  |  | 2042.5 |  |  | 2134.5 |  |  | 1999.5 |  |  | 2126.5 |  |  | 1923.5 |  |  | 2096 |  |  | 2054.5 |  |  | 1973.5 |  |  | 2048.5 |  |  | 2162.5 |  |  | 2169.5 |  |  | 2081.5 |  |  | 2127.5 |  |  | 2126.5 |  |  | 1944.5 |  |  | 2160.5 |  |  | 2047.5 |  |  | 2017.5 |  |  | 2095.5 |  |  | 2153 |  |  | 2101.5 |  |  | 2098.5 |  |  | 2036 |  |  | 2111.5 |  |  | 2112.5 |  |  | 2155 |  |  | 2095.5 |  |  | 2235.5 |  |  | 2208.5 |  |  | 2178 |  |  | 2044.5 |  |  | 2164.5 |  |  | 2095.5 |  |  | 1935.5 |  |  | 2091.5 |  |  | 2000 |  |  | 2046.5 |  |  | 2129 |  |  | 2104 |  |  | 2184.5 |  |  | 2117.5 |  |  | 1982.5 |  |  | 1871.5 |  |  | 2032.5 |  |  | 2074.5 |  |  | 2047 |  |  | 2050.5 |  |  | 2054 |  |  | 2064.5 |  |  | 2087 |  |  | 2036 |  |  | 2191 |  |  | 2104.5 |  |  | 2028 |  |  | 2174.5 |  |  | 2138.5 |  |  | 2104.5 |  |  | 2278.5 |  |  | 2056.5 |  |  | 2172 |  |  | 2099.5 |  |  | 2167.5 |  |  | 2240.5 |  |  | 2063 |  |  | 2122.5 |  |  | 1985.5 |  |  | 2084.5 |  |  | 2151.5 |  |  | 2027 |  |  | 2136 |  |  | 2010 |  |  | 2066.5 |  |  | 2180 |  |  | 2155 |  |  | 2144.5 |  |  | 2035.5 |  |  | 1963.5 |  |  | 2077.5 |  |  | 2090.5 |  |  | 2093.5 |  |  | 2213.5 |  |  | 2010.5 |  |  | 2017.5 |  |  | 1994 |  |  | 2022.5 |  |  | 1991 |  |  | 2104.5 |  |  | 2134.5 |  |  | 2092.5 |  |  | 2105.5 |  |  | 2179 |  |  | 2173.5 |  |  | 2095 |  |  | 2006.5 |  |  | 2131.5 |  |  | 2043 |  |  | 2066 |  |  | 2075.5 |  |  | 2073 |  |  | 2108.5 |  |  | 1941.5 |  |  | 1996.5 |  |  | 2029.5 |  |  | 2097.5 |  |  | 2106.5 |  |  | 1985.5 |  |  | 1965 |  |  | 2123.5 |  |  | 2133.5 |  |  | 2096.5 |  |  | 2112.5 |  |  | 1985.5 |  |  | 2068.5 |  |  | 2176.5 |  |  | 2096.5 |  |  | 2161.5 |  |  | 2157.5 |  |  | 1975.5 |  |  | 1952.5 |  |  | 2090 |  |  | 1932.5 |  |  | 2019.5 |  |  | 2146 |  |  | 2030.5 |  |  | 1968.5 |  |  | 2048.5 |  |  | 1983.5 |  |  | 2202 |  |  | 2257.5 |  |  | 2041.5 |  |  | 1966.5 |  |  | 2184.5 |  |  | 2086 |  |  | 2012.5 |  |  | 2172.5 |  |  | 2083.5 |  |  | 2129.5 |  |  | 2029.5 |  |  | 1975.5 |  |  | 2134.5 |  |  | 2094.5 |  |  | 2096.5 |  |  | 2062.5 |  |  | 2156.5 |  |  | 2138 |  |  | 2068.5 |  |  | 2019.5 |  |  | 2206.5 |  |  | 2154.5 |  |  | 1987.5 |  |  | 2057.5 |  |  | 2159 |  |  | 2101.5 |  |  | 2009 |  |  | 1932.5 |  |  | 2123.5 |  |  | 2065.5 |  |  | 2097 |  |  | 2021 |  |  | 2104.5 |  |  | 2149.5 |  |  | 1931.5 |  |  | 2134.5 |  |  | 2099.5 |  |  | 2087.5 |  |  | 2070.5 |  |  | 2150.5 |  |  | 2034.5 |  |  | 2190.5 |  |  | 2029.5 |  |  | 2177.5 |  |  | 1996.5 |  |  | 2111.5 |  |  | 2191.5 |  |  | 2056.5 |  |  | 2052.5 |  |  | 2105.5 |  |  | 2086.5 |  |  | 2092.5 |  |  | 2102.5 |  |  | 2129.5 |  |  | 2098 |  |  | 2118.5 |  |  | 2061.5 |  |  | 2088.5 |  |  | 2074 |  |  | 2140.5 |  |  | 2056.5 |  |  | 2119.5 |  |  | 2067.5 |  |  | 2090 |  |  | 1968.5 |  |  | 1948.5 |  |  | 1977 |  |  | 2026 |  |  | 2090 |  |  | 2068.5 |  |  | 2073.5 |  |  | 2116.5 |  |  | 2274.5 |  |  | 2149 |  |  | 2080.5 |  |  | 2104.5 |  |  | 1993 |  |  | 2094 |  |  | 2060.5 |  |  | 2117.5 |  |  | 2114 |  |  | 2052.5 |  |  | 2133 |  |  | 1968.5 |  |  | 1966.5 |  |  | 2200 |  |  | 2150.5 |  |  | 2099.5 |  |  | 1947.5 |  |  | 2211 |  |  | 2025.5 |  |  | 2026.5 |  |  | 2022.5 |  |  | 2044.5 |  |  | 2024.5 |  |  | 2159.5 |  |  | 1983.5 |  |  | 2101.5 |  |  | 2155.5 |  |  | 2106.5 |  |  | 2066 |  |  | 2085.5 |  |  | 2098.5 |  |  | 2123.5 |  |  | 2123.5 |  |  | 2082.5 |  |  | 2127.5 |  |  | 2213.5 |  |  | 2076.5 |  |  | 2223 |  |  | 2010.5 |  |  | 2048 |  |  | 2231.5 |  |  | 2283.5 |  |  | 2266.5 |  |  | 2016.5 |  |  | 2008.5 |  |  | 2056.5 |  |  | 1969.5 |  |  | 2155.5 |  |  | 2100 |  |  | 1980.5 |  |  | 2093 |  |  | 1994.5 |  |  | 1978.5 |  |  | 2118.5 |  |  | 2159 |  |  | 2034.5 |  |  | 2109.5 |  |  | 1883 |  |  | 2050.5 |  |  | 2030 |  |  | 2048.5 |  |  | 2021.5 |  |  | 2016.5 |  |  | 2066 |  |  | 2199.5 |  |  | 2257.5 |  |  | 2002 |  |  | 2221.5 |  |  | 2008.5 |  |  | 2112 |  |  | 2029.5 |  |  | 2224.5 |  |  | 2176.5 |  |  | 2200.5 |  |  | 1988.5 |  |  | 2204.5 |  |  | 1982.5 |  |  | 2031.5 |  |  | 1965.5 |  |  | 1967.5 |  |  | 2256.5 |  |  | 2148 |  |  | 2159 |  |  | 2224.5 |  |  | 2056.5 |  |  | 2097
72 |  | 2066.5 |  |  | 2238.5 |  |  | 2123 |  |  | 2095.5 |  |  | 2256.5 |  |  | 2142.5 |  |  | 2197.5 |  |  | 2121.5 |  |  | 2142.5 |  |  | 2095.5 |  |  | 2047 |  |  | 2187.5 |  |  | 2179.5 |  |  | 1964.5 |  |  | 1963 |  |  | 2124.5 |  |  | 2232.5 |  |  | 2128.5 |  |  | 2216.5 |  |  | 2022.5 |  |  | 2155.5 |  |  | 2117.5 |  |  | 2185.5 |  |  | 1997.5 |  |  | 1975 |  |  | 2174.5 |  |  | 2117.5 |  |  | 2091.5 |  |  | 2198.5 |  |  | 2016 |  |  | 2156 |  |  | 2189.5 |  |  | 1939.5 |  |  | 2153.5 |  |  | 2002.5 |  |  | 2185 |  |  | 2016.5 |  |  | 2242 |  |  | 2076.5 |  |  | 2140.5 |  |  | 1965.5 |  |  | 2168.5 |  |  | 1983.5 |  |  | 2099 |  |  | 2287.5 |  |  | 2233 |  |  | 2087.5 |  |  | 2220.5 |  |  | 2156.5 |  |  | 2130.5 |  |  | 2031.5 |  |  | 2154.5 |  |  | 2136.5 |  |  | 2080.5 |  |  | 2202.5 |  |  | 2181.5 |  |  | 2011.5 |  |  | 2124 |  |  | 2137.5 |  |  | 2089.5 |  |  | 2101 |  |  | 2100.5 |  |  | 2193.5 |  |  | 2061.5 |  |  | 2019.5 |  |  | 2159 |  |  | 2194.5 |  |  | 2021 |  |  | 1982.5 |  |  | 2163.5 |  |  | 2122 |  |  | 2112.5 |  |  | 2111.5 |  |  | 2223.5 |  |  | 2232 |  |  | 2198 |  |  | 2021.5 |  |  | 2079.5 |  |  | 1995.5 |  |  | 2131.5 |  |  | 2091 |  |  | 2127.5 |  |  | 2155.5 |  |  | 2209.5 |  |  | 2209.5 |  |  | 2068.5 |  |  | 2225.5 |  |  | 2106.5 |  |  | 2102.5 |  |  | 2147.5 |  |  | 2166.5 |  |  | 2157 |  |  | 1991.5 |  |  | 2034 |  |  | 2077 |  |  | 2052 |  |  | 2279.5 |  |  | 2268.5 |  |  | 1994.5 |  |  | 2207.5 |  |  | 2026.5 |  |  | 2098 |  |  | 2103 |  |  | 2065.5 |  |  | 2068.5 |  |  | 2051.5 |  |  | 2151.5 |  |  | 2202.5 |  |  | 2208.5 |  |  | 2161.5 |  |  | 2212.5 |  |  | 2194.5 |  |  | 2087.5 |  |  | 2150.5 |  |  | 2124.5 |  |  | 2129.5 |  |  | 2207.5 |  |  | 1996.5 |  |  | 2133.5 |  |  | 2100.5 |  |  | 2137.5 |  |  | 2159.5 |  |  | 2106.5 |  |  | 2117.5 |  |  | 2140.5 |  |  | 2118 |  |  | 2083.5 |  |  | 2087.5 |  |  | 2050.5 |  |  | 2072.5 |  |  | 2145.5 |  |  | 2141 |  |  | 2020.5 |  |  | 2195.5 |  |  | 2027.5 |  |  | 2078.5 |  |  | 2154 |  |  | 2103.5 |  |  | 2194.5 |  |  | 2063 |  |  | 2148.5 |  |  | 2015 |  |  | 2191 |  |  | 2211.5 |  |  | 2156 |  |  | 2203.5 |  |  | 2080.5 |  |  | 2158.5 |  |  | 2002.5 |  |  | 2159.5 |  |  | 2119.5 |  |  | 2113.5 |  |  | 2136.5 |  |  | 2267.5 |  |  | 2147.5 |  |  | 2218 |  |  | 2049.5 |  |  | 1990 |  |  | 2044.5 |  |  | 2165.5 |  |  | 2064 |  |  | 2130.5 |  |  | 2082.5 |  |  | 2111.5 |  |  | 2016 |  |  | 2131.5 |  |  | 2037.5 |  |  | 2051.5 |  |  | 2232.5 |  |  | 2095.5 |  |  | 2059.5 |  |  | 2099 |  |  | 2079.5 |  |  | 2100.5 |  |  | 2035.5 |  |  | 2107.5 |  |  | 2161.5 |  |  | 2130.5 |  |  | 2035.5 |  |  | 2210 |  |  | 2192.5 |  |  | 2164.5 |  |  | 2183.5 |  |  | 2143.5 |  |  | 2032.5 |  |  | 2230.5 |  |  | 2157.5 |  |  | 2090.5 |  |  | 2208.5 |  |  | 2076.5 |  |  | 2165.5 |  |  | 1984.5 |  |  | 1903.5 |  |  | 2046 |  |  | 2100.5 |  |  | 2150.5 |  |  | 2067.5 |  |  | 2144.5 |  |  | 2171.5 |  |  | 2195.5 |  |  | 2192.5 |  |  | 2051.5 |  |  | 2131.5 |  |  | 2073.5 |  |  | 2044.5 |  |  | 2256.5 |  |  | 2085.5 |  |  | 2060.5 |  |  | 2075.5 |  |  | 2088.5 |  |  | 2169 |  |  | 2159.5 |  |  | 2097.5 |  |  | 1865 |  |  | 2274.5 |  |  | 2240 |  |  | 1982.5 |  |  | 2164.5 |  |  | 2206.5 |  |  | 2160.5 |  |  | 2044.5 |  |  | 2096.5 |  |  | 2107.5 |  |  | 1944.5 |  |  | 2011 |  |  | 2048.5 |  |  | 1940.5 |  |  | 2136.5 |  |  | 2010.5 |  |  | 2137 |  |  | 2039.5 |  |  | 2118.5 |  |  | 2194.5 |  |  | 2118.5 |  |  | 2202.5 |  |  | 2093.5 |  |  | 2096.5 |  |  | 2245.5 |  |  | 2218 |  |  | 2173 |  |  | 2086.5 |  |  | 2015.5 |  |  | 2088.5 |  |  | 2102 |  |  | 2257.5 |  |  | 2092.5 |  |  | 2084.5 |  |  | 2020 |  |  | 2181.5 |  |  | 2138.5 |  |  | 1991.5 |  |  | 2027.5 |  |  | 2046.5 |  |  | 2173.5 |  |  | 2157.5 |  |  | 2154.5 |  |  | 2249.5 |  |  | 1929 |  |  | 2074.5 |  |  | 2174.5 |  |  | 2150.5 |  |  | 2098.5 |  |  | 2042.5 |  |  | 2221 |  |  | 2088.5 |  |  | 2156.5 |  |  | 2203 |  |  | 2229.5 |  |  | 2154.5 |  |  | 2320 |  |  | 2117.5 |  |  | 2140.5 |  |  | 2263.5 |  |  | 2034.5 |  |  | 2134 |  |  | 2105 |  |  | 2103.5 |  |  | 2050.5 |  |  | 2155.5 |  |  | 2106.5 |  |  | 2241.5 |  |  | 2130.5 |  |  | 2084 |  |  | 2110.5 |  |  | 2099.5 |  |  | 2121 |  |  | 2057.5 |  |  | 1973.5 |  |  | 2163 |  |  | 2144.5 |  |  | 1982.5 |  |  | 2149.5 |  |  | 2107 |  |  | 2121.5 |  |  | 2043 |  |  | 2160.5 |  |  | 2028.5 |  |  | 2146.5 |  |  | 2049 |  |  | 2038.5 |  |  | 2243.5 |  |  | 2236.5 |  |  | 2112 |  |  | 2069.5 |  |  | 1960.5 |  |  | 2272.5 |  |  | 2205.5 |  |  | 2118.5 |  |  | 2130 |  |  | 2012.5 |  |  | 2201.5 |  |  | 2182.5 |  |  | 2037 |  |  | 2152 |  |  | 2252.5 |  |  | 2001.5 |  |  | 2007.5 |  |  | 2127.5 |  |  | 2104.5 |  |  | 2127.5 |  |  | 2134.5 |  |  | 2186.5 |  |  | 2070.5 |  |  | 2110.5 |  |  | 2122 |  |  | 2077.5 |  |  | 2176.5 |  |  | 2323.5 |  |  | 2196.5 |  |  | 2165 |  |  | 2140.5 |  |  | 2268.5 |  |  | 2098.5 |  |  | 1949.5 |  |  | 2222.5 |  |  | 2011 |  |  | 2121 |  |  | 2035 |  |  | 2220 |  |  | 2028.5 |  |  | 2166 |  |  | 2136.5 |  |  | 2072 |  |  | 2122.5 |  |  | 2210.5 |  |  | 2083.5 |  |  | 2063.5 |  |  | 2067.5 |  |  | 2147 |  |  | 2158.5 |  |  | 2254.5 |  |  | 2071.5 |  |  | 2144 |  |  | 2202.5 |  |  | 2044.5 |  |  | 2051.5 |  |  | 2144 |  |  | 2073.5 |  |  | 2009.5 |  |  | 2161.5 |  |  | 2067.5 |  |  | 2101.5 |  |  | 2059.5 |  |  | 2162.5 |  |  | 2125.5 |  |  | 2124.5 |  |  | 1991.5 |  |  | 2008 |  |  | 2104.5 |  |  | 2051.5 |  |  | 2004.5 |  |  | 2159.5 |  |  | 2235.5 |  |  | 2065 |  |  | 2153.5 |  |  | 2194 |  |  | 2044 |  |  | 2008.5 |  |  | 2244.5 |  |  | 2037.5 |  |  | 2070 |  |  | 2142.5 |  |  | 2147.5 |  |  | 2123.5 |  |  | 1993 |  |  | 2098.5 |  |  | 1975.5 |  |  | 2122.5 |  |  | 2028.5 |  |  | 2038.5 |  |  | 2029 |  |  | 2064.5 |  |  | 2203 |  |  | 2092.5 |  |  | 1971.5 |  |  | 2107.5 |  |  | 2164 |  |  | 2018.5 |  |  | 2081 |  |  | 2091 |  |  | 2073.5 |  |  | 1990.5 |  |  | 2052.5 |  |  | 2266.5 |  |  | 2247 |  |  | 2184.5 |  |  | 2058.5 |  |  | 1933.5 |  |  | 2073 |  |  | 2167.5 |  |  | 2049.5 |  |  | 1910.5 |  |  | 2086.5 |  |  | 2200 |  |  | 1966.5 |  |  | 2134.5 |  |  | 2164.5 |  |  | 2143.5 |  |  | 2102.5 |  |  | 2071.5 |  |  | 2205 |  |  | 2112.5 |  |  | 2003.5 |  |  | 2114 |  |  | 2007.5 |  |  | 1953.5 |  |  | 2107.5 |  |  | 2138 |  |  | 2170.5 |  |  | 2146.5 |  |  | 2099.5 |  |  | 2070.5 |  |  | 2176.5 |  |  | 2177 |  |  | 2122 |  |  | 2129.5 |  |  | 2200.5 |  |  | 2175.5 |  |  | 1967.5 |  |  | 1993 |  |  | 2148 |  |  | 2041 |  |  | 2234.5 |  |  | 2146 |  |  | 2129.5 |  |  | 2223.5 |  |  | 2161 |  |  | 2040.5 |  |  | 2172.5 |  |  | 2108.5 |  |  | 2176.5 |  |  | 1913.5 |  |  | 2099 |  |  | 2193 |  |  | 2017.5 |  |  | 2178.5 |  |  | 2051 |  |  | 1994.5 |  |  | 2123.5 |  |  | 2067 |  |  | 2213.5 |  |  | 2250.5 |  |  | 2044 |  |  | 2154.5 |  |  | 2120.5 |  |  | 2127 |  |  | 2053.5 |  |  | 2050 |  |  | 2240.5 |  |  | 2229 |  |  | 2061.5 |  |  | 2030.5 |  |  | 2072.5 |  |  | 2080.5 |  |  | 2127.5 |  |  | 2019.5 |  |  | 2138 |  |  | 2046.5 |  |  | 2129.5 |  |  | 2060.5 |  |  | 2054.5 |  |  | 2100.5 |  |  | 2098 |  |  | 2030.5 |  |  | 2105 |  |  | 2114.5 |  |  | 2002.5 |  |  | 2187.5 |  |  | 2131.5 |  |  | 2107.5 |  |  | 2125.5 |  |  | 2067.5 |  |  | 2158.5 |  |  | 2024.5 |  |  | 2049 |  |  | 2166.5 |  |  | 2030 |  |  | 2131 |  |  | 2129.5 |  |  | 1953 |  |  | 1980.5 |  |  | 2158.5 |  |  | 2201.5 |  |  | 2086.5 |  |  | 2208.5 |  |  | 2196.5 |  |  | 2164.5 |  |  | 2071 |  |  | 2241 |  |  | 1997.5 |  |  | 2079.5 |  |  | 2091 |  |  | 2031.5 |  |  | 2050.5 |  |  | 2041.5 |  |  | 2040.5 |  |  | 2070.5 |  |  | 2024 |  |  | 2077.5 |  |  | 2102.5 |  |  | 2034.5 |  |  | 2075 |  |  | 2171.5 |  |  | 2094.5 |  |  | 2133.5 |  |  | 2291.5 |  |  | 2182.5 |  |  | 2061.5 |  |  | 2225.5 |  |  | 1770.5 |  |  | 2100.5 |  |  | 1987 |  |  | 2215.5 |  |  | 2161.5 |  |  | 2161.5 |  |  | 2008.5 |  |  | 2033.5 |  |  | 2063.5 |  |  | 2057.5 |  |  | 1950 |  |  | 2028.5 |  |  | 2137.5 |  |  | 2184.5 |  |  | 2115 |  |  | 2140.5 |  |  | 2000 |  |  | 1979.5 |  |  | 2122.5 |  |  | 2006.5 |  |  | 2136 |  |  | 1987.5 |  |  | 2111 |  |  | 2083 |  |  | 2142.5 |  |  | 2115 |  |  | 2220 |  |  | 2170.5 |  |  | 2168.5 |  |  | 1969.5 |  |  | 2166 |  |  | 2174.5 |  |  | 2042.5 |  |  | 2011.5 |  |  | 2193.5 |  |  | 2054.5 |  |  | 2095.5 |  |  | 2073.5 |  |  | 2174.5 |  |  | 2119 |  |  | 2234.5 |  |  | 2055 |  |  | 2113.5 |  |  | 2040.5 |  |  | 2213.5 |  |  | 2096 |  |  | 2119 |  |  | 2271 |  |  | 2094.5 |  |  | 2064 |  |  | 2126.5 |  |  | 2253.5 |  |  | 2120.5 |  |  | 2073.5 |  |  | 1997.5 |  |  | 2186.5 |  |  | 2206.5 |  |  | 2184.5 |  |  | 2147 |  |  | 1988.5 |  |  | 1985.5 |  |  | 2123.5 |  |  | 2015.5 |  |  | 2055 |  |  | 2100.5 |  |  | 2140 |  |  | 2127.5 |  |  | 2146.5 |  |  | 2021.5 |  |  | 2006.5 |  |  | 1983 |  |  | 2043.5 |  |  | 1859 |  |  | 2032.5 |  |  | 2132.5 |  |  | 2240.5 |  |  | 2125.5 |  |  | 2088.5 |  |  | 2150.5 |  |  | 1967.5 |  |  | 2185.5 |  |  | 2125.5 |  |  | 2012 |  |  | 2132.5 |  |  | 2054.5 |  |  | 2041.5 |  |  | 2189.5 |  |  | 2159.5 |  |  | 2057 |  |  | 2041 |  |  | 2126.5 |  |  | 2026 |  |  | 2232.5 |  |  | 2055.5 |  |  | 2217.5 |  |  | 2157.5 |  |  | 2078.5 |  |  | 2168.5 |  |  | 2098.5 |  |  | 2136.5 |  |  | 2124 |  |  | 2073.5 |  |  | 2297.5 |  |  | 2092.5 |  |  | 2002 |  |  | 2050.5 |  |  | 2062.5 |  |  | 2207 |  |  | 2000 |  |  | 2120.5 |  |  | 2015 |  |  | 1940 |  |  | 1985.5 |  |  | 2159 |  |  | 2294.5 |  |  | 2112.5 |  |  | 2227.5 |  |  | 2089.5 |  |  | 2040.5 |  |  | 2079.5 |  |  | 1965.5 |  |  | 2083.5 |  |  | 2123.5 |  |  | 2035.5 |  |  | 2036 |  |  | 2028 |  |  | 2162.5 |  |  | 2155.5 |  |  | 2092.5 |  |  | 2144.5 |  |  | 2076.5 |  |  | 2125.5 |  |  | 2190.5 |  |  | 2056.5 |  |  | 2341 |  |  | 2051.5 |  |  | 2071 |  |  | 2034.5 |  |  | 2250.5 |  |  | 2167.5 |  |  | 2209 |  |  | 2086.5 |  |  | 2020.5 |  |  | 2147 |  |  | 2144.5 |  |  | 2064.5 |  |  | 2158.5 |  |  | 2123.5 |  |  | 2054.5 |  |  | 2117.5 |  |  | 2150 |  |  | 2059.5 |  |  | 2035.5 |  |  | 2173.5 |  |  | 2172.5 |  |  | 2121 |  |  | 2121.5 |  |  | 2207.5 |  |  | 2055 |  |  | 2138.5 |  |  | 2236.5 |  |  | 2138 |  |  | 2203.5 |  |  | 2216.5 |  |  | 2068.5 |  |  | 2097 |  |  | 1915.5 |  |  | 2089.5 |  |  | 2102 |  |  | 2122.5 |  |  | 2144.5 |  |  | 2076.5 |  |  | 1918.5 |  |  | 2202.5 |  |  | 2213.5 |  |  | 2034.5 |  |  | 2107 |  |  | 2059 |  |  | 1967.5 |  |  | 2154.5 |  |  | 2023.5 |  |  | 2161 |  |  | 2249.5 |  |  | 2058.5 |  |  | 2076.5 |  |  | 1999.5 |  |  | 2089.5 |  |  | 2173.5 |  |  | 2025.5 |  |  | 2150.5 |  |  | 1944.5 |  |  | 2125 |  |  | 2069.5 |  |  | 2002.5 |  |  | 2077.5 |  |  | 2177.5 |  |  | 2208.5 |  |  | 2120.5 |  |  | 2153.5 |  |  | 2141.5 |  |  | 1959.5 |  |  | 2175.5 |  |  | 2073.5 |  |  | 2041.5 |  |  | 2134.5 |  |  | 2192 |  |  | 2140.5 |  |  | 2127.5 |  |  | 2057 |  |  | 2150.5 |  |  | 2136.5 |  |  | 2202 |  |  | 2134.5 |  |  | 2259.5 |  |  | 2247.5 |  |  | 2225 |  |  | 2070.5 |  |  | 2179.5 |  |  | 2110.5 |  |  | 1950.5 |  |  | 2115.5 |  |  | 2039 |  |  | 2093.5 |  |  | 2153 |  |  | 2151 |  |  | 2223.5 |  |  | 2164.5 |  |  | 2006.5 |  |  | 1892.5 |  |  | 2047.5 |  |  | 2103.5 |  |  | 2068 |  |  | 2065.5 |  |  | 2093 |  |  | 2093.5 |  |  | 2102 |  |  | 2065 |  |  | 2217 |  |  | 2125.5 |  |  | 2052 |  |  | 2221.5 |  |  | 2162.5 |  |  | 2128.5 |  |  | 2317.5 |  |  | 2077.5 |  |  | 2196 |  |  | 2138.5 |  |  | 2206.5 |  |  | 2266.5 |  |  | 2102 |  |  | 2151.5 |  |  | 2006.5 |  |  | 2123.5 |  |  | 2166.5 |  |  | 2074 |  |  | 2160 |  |  | 2049 |  |  | 2092.5 |  |  | 2195 |  |  | 2194 |  |  | 2168.5 |  |  | 2050.5 |  |  | 1989.5 |  |  | 2124.5 |  |  | 2137.5 |  |  | 2122.5 |  |  | 2237.5 |  |  | 2039.5 |  |  | 2043.5 |  |  | 2020 |  |  | 2061.5 |  |  | 2020 |  |  | 2143.5 |  |  | 2160.5 |  |  | 2107.5 |  |  | 2134.5 |  |  | 2208 |  |  | 2188.5 |  |  | 2121 |  |  | 2053.5 |  |  | 2160.5 |  |  | 2064 |  |  | 2105 |  |  | 2122.5 |  |  | 2112 |  |  | 2129.5 |  |  | 1980.5 |  |  | 2011.5 |  |  | 2050.5 |  |  | 2144.5 |  |  | 2132.5 |  |  | 2006.5 |  |  | 2012 |  |  | 2152.5 |  |  | 2172.5 |  |  | 2122.5 |  |  | 2141.5 |  |  | 2009.5 |  |  | 2115.5 |  |  | 2215.5 |  |  | 2117.5 |  |  | 2200.5 |  |  | 2196.5 |  |  | 2014.5 |  |  | 1999.5 |  |  | 2137 |  |  | 1961.5 |  |  | 2040.5 |  |  | 2172 |  |  | 2069.5 |  |  | 2007.5 |  |  | 2095.5 |  |  | 2004.5 |  |  | 2228 |  |  | 2272.5 |  |  | 2062.5 |  |  | 1987.5 |  |  | 2205.5 |  |  | 2110 |  |  | 2051.5 |  |  | 2219.5 |  |  | 2107.5 |  |  | 2168.5 |  |  | 2050.5 |  |  | 2001.5 |  |  | 2158.5 |  |  | 2120.5 |  |  | 2135.5 |  |  | 2109.5 |  |  | 2195.5 |  |  | 2164 |  |  | 2107.5 |  |  | 2043.5 |  |  | 2235.5 |  |  | 2180.5 |  |  | 2011.5 |  |  | 2083.5 |  |  | 2174 |  |  | 2140.5 |  |  | 2024 |  |  | 1979.5 |  |  | 2170.5 |  |  | 2112.5 |  |  | 2112 |  |  | 2060 |  |  | 2125.5 |  |  | 2170.5 |  |  | 1952.5 |  |  | 2181.5 |  |  | 2114.5 |  |  | 2126.5 |  |  | 2099.5 |  |  | 2189.5 |  |  | 2049.5 |  |  | 2219.5 |  |  | 2055.5 |  |  | 2198.5 |  |  | 2035.5 |  |  | 2137.5 |  |  | 2238.5 |  |  | 2082.5 |  |  | 2073.5 |  |  | 2126.5 |  |  | 2133.5 |  |  | 2116.5 |  |  | 2141.5 |  |  | 2153.5 |  |  | 2127 |  |  | 2165.5 |  |  | 2087.5 |  |  | 2114.5 |  |  | 2103 |  |  | 2169.5 |  |  | 2095.5 |  |  | 2145.5 |  |  | 2106.5 |  |  | 2129 |  |  | 1992.5 |  |  | 1987.5 |  |  | 2016 |  |  | 2073 |  |  | 2105 |  |  | 2115.5 |  |  | 2120.5 |  |  | 2140.5 |  |  | 2321.5 |  |  | 2175 |  |  | 2106.5 |  |  | 2130.5 |  |  | 2017 |  |  | 2115 |  |  | 2099.5 |  |  | 2156.5 |  |  | 2138 |  |  | 2091.5 |  |  | 2172 |  |  | 1992.5 |  |  | 1981.5 |  |  | 2215 |  |  | 2189.5 |  |  | 2123.5 |  |  | 1971.5 |  |  | 2226 |  |  | 2040.5 |  |  | 2065.5 |  |  | 2037.5 |  |  | 2065.5 |  |  | 2048.5 |  |  | 2198.5 |  |  | 2009.5 |  |  | 2140.5 |  |  | 2184.5 |  |  | 2135.5 |  |  | 2105 |  |  | 2114.5 |  |  | 2122.5 |  |  | 2162.5 |  |  | 2170.5 |  |  | 2121.5 |  |  | 2153.5 |  |  | 2252.5 |  |  | 2115.5 |  |  | 2238 |  |  | 2031.5 |  |  | 2072 |  |  | 2252.5 |  |  | 2322.5 |  |  | 2313.5 |  |  | 2045.5 |  |  | 2037.5 |  |  | 2082.5 |  |  | 2008.5 |  |  | 2184.5 |  |  | 2139 |  |  | 2009.5 |  |  | 2140 |  |  | 2020.5 |  |  | 2007.5 |  |  | 2147.5 |  |  | 2206 |  |  | 2073.5 |  |  | 2133.5 |  |  | 1922 |  |  | 2079.5 |  |  | 2059 |  |  | 2095.5 |  |  | 2050.5 |  |  | 2031.5 |  |  | 2081 |  |  | 2220.5 |  |  | 2283.5 |  |  | 2023 |  |  | 2250.5 |  |  | 2034.5 |  |  | 2151 |  |  | 2068.5 |  |  | 2263.5 |  |  | 2197.5 |  |  | 2221.5 |  |  | 2012.5 |  |  | 2230.5 |  |  | 2006.5 |  |  | 2046.5 |  |  | 2004.5 |  |  | 1993.5 |  |  | 2295.5 |  |  | 2195 |  |  | 2183 |  |  | 2239.5 |  |  | 2080.5 |  |  | 2126
73 |  | 2105.5 |  |  | 2267.5 |  |  | 2162 |  |  | 2119.5 |  |  | 2295.5 |  |  | 2171.5 |  |  | 2236.5 |  |  | 2147.5 |  |  | 2157.5 |  |  | 2110.5 |  |  | 2076 |  |  | 2226.5 |  |  | 2218.5 |  |  | 1993.5 |  |  | 1978 |  |  | 2171.5 |  |  | 2247.5 |  |  | 2152.5 |  |  | 2240.5 |  |  | 2069.5 |  |  | 2202.5 |  |  | 2146.5 |  |  | 2224.5 |  |  | 2026.5 |  |  | 2014 |  |  | 2221.5 |  |  | 2164.5 |  |  | 2106.5 |  |  | 2245.5 |  |  | 2055 |  |  | 2171 |  |  | 2228.5 |  |  | 1968.5 |  |  | 2182.5 |  |  | 2026.5 |  |  | 2232 |  |  | 2055.5 |  |  | 2266 |  |  | 2097.5 |  |  | 2161.5 |  |  | 2004.5 |  |  | 2183.5 |  |  | 2022.5 |  |  | 2138 |  |  | 2313.5 |  |  | 2280 |  |  | 2116.5 |  |  | 2259.5 |  |  | 2203.5 |  |  | 2145.5 |  |  | 2078.5 |  |  | 2180.5 |  |  | 2157.5 |  |  | 2109.5 |  |  | 2223.5 |  |  | 2205.5 |  |  | 2037.5 |  |  | 2139 |  |  | 2176.5 |  |  | 2104.5 |  |  | 2116 |  |  | 2126.5 |  |  | 2232.5 |  |  | 2087.5 |  |  | 2045.5 |  |  | 2198 |  |  | 2233.5 |  |  | 2036 |  |  | 2021.5 |  |  | 2202.5 |  |  | 2137 |  |  | 2141.5 |  |  | 2126.5 |  |  | 2270.5 |  |  | 2261 |  |  | 2237 |  |  | 2068.5 |  |  | 2118.5 |  |  | 2019.5 |  |  | 2152.5 |  |  | 2115 |  |  | 2174.5 |  |  | 2181.5 |  |  | 2248.5 |  |  | 2233.5 |  |  | 2089.5 |  |  | 2246.5 |  |  | 2153.5 |  |  | 2141.5 |  |  | 2162.5 |  |  | 2205.5 |  |  | 2172 |  |  | 2017.5 |  |  | 2060 |  |  | 2103 |  |  | 2073 |  |  | 2305.5 |  |  | 2283.5 |  |  | 2033.5 |  |  | 2233.5 |  |  | 2055.5 |  |  | 2137 |  |  | 2132 |  |  | 2080.5 |  |  | 2097.5 |  |  | 2090.5 |  |  | 2177.5 |  |  | 2249.5 |  |  | 2247.5 |  |  | 2185.5 |  |  | 2241.5 |  |  | 2241.5 |  |  | 2126.5 |  |  | 2174.5 |  |  | 2163.5 |  |  | 2155.5 |  |  | 2231.5 |  |  | 2025.5 |  |  | 2148.5 |  |  | 2124.5 |  |  | 2158.5 |  |  | 2183.5 |  |  | 2145.5 |  |  | 2143.5 |  |  | 2161.5 |  |  | 2144 |  |  | 2109.5 |  |  | 2111.5 |  |  | 2074.5 |  |  | 2098.5 |  |  | 2192.5 |  |  | 2156 |  |  | 2049.5 |  |  | 2242.5 |  |  | 2056.5 |  |  | 2099.5 |  |  | 2180 |  |  | 2129.5 |  |  | 2220.5 |  |  | 2078 |  |  | 2174.5 |  |  | 2054 |  |  | 2220 |  |  | 2250.5 |  |  | 2195 |  |  | 2229.5 |  |  | 2106.5 |  |  | 2173.5 |  |  | 2026.5 |  |  | 2180.5 |  |  | 2166.5 |  |  | 2142.5 |  |  | 2183.5 |  |  | 2296.5 |  |  | 2186.5 |  |  | 2242 |  |  | 2073.5 |  |  | 2029 |  |  | 2091.5 |  |  | 2186.5 |  |  | 2090 |  |  | 2156.5 |  |  | 2121.5 |  |  | 2132.5 |  |  | 2031 |  |  | 2146.5 |  |  | 2052.5 |  |  | 2080.5 |  |  | 2256.5 |  |  | 2134.5 |  |  | 2088.5 |  |  | 2114 |  |  | 2118.5 |  |  | 2139.5 |  |  | 2074.5 |  |  | 2128.5 |  |  | 2190.5 |  |  | 2154.5 |  |  | 2074.5 |  |  | 2225 |  |  | 2213.5 |  |  | 2185.5 |  |  | 2204.5 |  |  | 2190.5 |  |  | 2079.5 |  |  | 2269.5 |  |  | 2183.5 |  |  | 2111.5 |  |  | 2247.5 |  |  | 2097.5 |  |  | 2204.5 |  |  | 2013.5 |  |  | 1942.5 |  |  | 2067 |  |  | 2126.5 |  |  | 2174.5 |  |  | 2096.5 |  |  | 2183.5 |  |  | 2210.5 |  |  | 2219.5 |  |  | 2239.5 |  |  | 2098.5 |  |  | 2157.5 |  |  | 2112.5 |  |  | 2068.5 |  |  | 2271.5 |  |  | 2124.5 |  |  | 2107.5 |  |  | 2099.5 |  |  | 2127.5 |  |  | 2208 |  |  | 2198.5 |  |  | 2118.5 |  |  | 1904 |  |  | 2300.5 |  |  | 2279 |  |  | 2008.5 |  |  | 2203.5 |  |  | 2245.5 |  |  | 2207.5 |  |  | 2091.5 |  |  | 2143.5 |  |  | 2146.5 |  |  | 1965.5 |  |  | 2035 |  |  | 2087.5 |  |  | 1961.5 |  |  | 2165.5 |  |  | 2057.5 |  |  | 2161 |  |  | 2078.5 |  |  | 2147.5 |  |  | 2223.5 |  |  | 2157.5 |  |  | 2226.5 |  |  | 2140.5 |  |  | 2111.5 |  |  | 2269.5 |  |  | 2257 |  |  | 2194 |  |  | 2110.5 |  |  | 2054.5 |  |  | 2117.5 |  |  | 2123 |  |  | 2278.5 |  |  | 2118.5 |  |  | 2105.5 |  |  | 2035 |  |  | 2228.5 |  |  | 2162.5 |  |  | 2030.5 |  |  | 2051.5 |  |  | 2085.5 |  |  | 2197.5 |  |  | 2196.5 |  |  | 2180.5 |  |  | 2296.5 |  |  | 1968 |  |  | 2100.5 |  |  | 2200.5 |  |  | 2197.5 |  |  | 2137.5 |  |  | 2057.5 |  |  | 2260 |  |  | 2103.5 |  |  | 2195.5 |  |  | 2227 |  |  | 2250.5 |  |  | 2169.5 |  |  | 2359 |  |  | 2156.5 |  |  | 2179.5 |  |  | 2284.5 |  |  | 2073.5 |  |  | 2160 |  |  | 2126 |  |  | 2127.5 |  |  | 2079.5 |  |  | 2194.5 |  |  | 2153.5 |  |  | 2267.5 |  |  | 2151.5 |  |  | 2110 |  |  | 2134.5 |  |  | 2146.5 |  |  | 2145 |  |  | 2096.5 |  |  | 1988.5 |  |  | 2187 |  |  | 2191.5 |  |  | 2006.5 |  |  | 2170.5 |  |  | 2146 |  |  | 2160.5 |  |  | 2069 |  |  | 2199.5 |  |  | 2057.5 |  |  | 2167.5 |  |  | 2078 |  |  | 2077.5 |  |  | 2258.5 |  |  | 2257.5 |  |  | 2136 |  |  | 2116.5 |  |  | 1975.5 |  |  | 2311.5 |  |  | 2234.5 |  |  | 2157.5 |  |  | 2151 |  |  | 2051.5 |  |  | 2222.5 |  |  | 2197.5 |  |  | 2066 |  |  | 2199 |  |  | 2299.5 |  |  | 2048.5 |  |  | 2046.5 |  |  | 2174.5 |  |  | 2143.5 |  |  | 2148.5 |  |  | 2173.5 |  |  | 2225.5 |  |  | 2109.5 |  |  | 2139.5 |  |  | 2161 |  |  | 2101.5 |  |  | 2215.5 |  |  | 2349.5 |  |  | 2235.5 |  |  | 2191 |  |  | 2169.5 |  |  | 2289.5 |  |  | 2127.5 |  |  | 1988.5 |  |  | 2248.5 |  |  | 2026 |  |  | 2168 |  |  | 2064 |  |  | 2249 |  |  | 2075.5 |  |  | 2195 |  |  | 2157.5 |  |  | 2119 |  |  | 2146.5 |  |  | 2249.5 |  |  | 2112.5 |  |  | 2087.5 |  |  | 2096.5 |  |  | 2162 |  |  | 2197.5 |  |  | 2280.5 |  |  | 2118.5 |  |  | 2183 |  |  | 2226.5 |  |  | 2083.5 |  |  | 2090.5 |  |  | 2173 |  |  | 2112.5 |  |  | 2038.5 |  |  | 2185.5 |  |  | 2096.5 |  |  | 2130.5 |  |  | 2098.5 |  |  | 2201.5 |  |  | 2164.5 |  |  | 2171.5 |  |  | 2038.5 |  |  | 2047 |  |  | 2119.5 |  |  | 2090.5 |  |  | 2025.5 |  |  | 2185.5 |  |  | 2261.5 |  |  | 2089 |  |  | 2200.5 |  |  | 2220 |  |  | 2091 |  |  | 2029.5 |  |  | 2283.5 |  |  | 2063.5 |  |  | 2109 |  |  | 2163.5 |  |  | 2194.5 |  |  | 2138.5 |  |  | 2019 |  |  | 2137.5 |  |  | 2001.5 |  |  | 2148.5 |  |  | 2052.5 |  |  | 2077.5 |  |  | 2058 |  |  | 2085.5 |  |  | 2218 |  |  | 2131.5 |  |  | 1992.5 |  |  | 2133.5 |  |  | 2193 |  |  | 2057.5 |  |  | 2096 |  |  | 2117 |  |  | 2120.5 |  |  | 2016.5 |  |  | 2091.5 |  |  | 2305.5 |  |  | 2271 |  |  | 2210.5 |  |  | 2105.5 |  |  | 1948.5 |  |  | 2112 |  |  | 2191.5 |  |  | 2088.5 |  |  | 1939.5 |  |  | 2110.5 |  |  | 2224 |  |  | 1987.5 |  |  | 2158.5 |  |  | 2188.5 |  |  | 2167.5 |  |  | 2126.5 |  |  | 2092.5 |  |  | 2229 |  |  | 2138.5 |  |  | 2018.5 |  |  | 2138 |  |  | 2046.5 |  |  | 1977.5 |  |  | 2128.5 |  |  | 2167 |  |  | 2191.5 |  |  | 2172.5 |  |  | 2125.5 |  |  | 2099.5 |  |  | 2215.5 |  |  | 2206 |  |  | 2143 |  |  | 2150.5 |  |  | 2215.5 |  |  | 2196.5 |  |  | 1996.5 |  |  | 2014 |  |  | 2172 |  |  | 2065 |  |  | 2249.5 |  |  | 2161 |  |  | 2176.5 |  |  | 2249.5 |  |  | 2200 |  |  | 2055.5 |  |  | 2196.5 |  |  | 2147.5 |  |  | 2197.5 |  |  | 1939.5 |  |  | 2114 |  |  | 2214 |  |  | 2056.5 |  |  | 2202.5 |  |  | 2066 |  |  | 2033.5 |  |  | 2144.5 |  |  | 2096 |  |  | 2228.5 |  |  | 2289.5 |  |  | 2083 |  |  | 2169.5 |  |  | 2144.5 |  |  | 2166 |  |  | 2068.5 |  |  | 2065 |  |  | 2279.5 |  |  | 2276 |  |  | 2090.5 |  |  | 2056.5 |  |  | 2111.5 |  |  | 2119.5 |  |  | 2166.5 |  |  | 2043.5 |  |  | 2159 |  |  | 2085.5 |  |  | 2168.5 |  |  | 2099.5 |  |  | 2101.5 |  |  | 2124.5 |  |  | 2124 |  |  | 2051.5 |  |  | 2131 |  |  | 2153.5 |  |  | 2041.5 |  |  | 2213.5 |  |  | 2146.5 |  |  | 2146.5 |  |  | 2146.5 |  |  | 2096.5 |  |  | 2197.5 |  |  | 2050.5 |  |  | 2064 |  |  | 2181.5 |  |  | 2051 |  |  | 2152 |  |  | 2176.5 |  |  | 1974 |  |  | 2019.5 |  |  | 2179.5 |  |  | 2240.5 |  |  | 2115.5 |  |  | 2234.5 |  |  | 2217.5 |  |  | 2185.5 |  |  | 2095 |  |  | 2262 |  |  | 2044.5 |  |  | 2100.5 |  |  | 2138 |  |  | 2078.5 |  |  | 2089.5 |  |  | 2062.5 |  |  | 2055.5 |  |  | 2091.5 |  |  | 2053 |  |  | 2116.5 |  |  | 2149.5 |  |  | 2060.5 |  |  | 2090 |  |  | 2197.5 |  |  | 2141.5 |  |  | 2159.5 |  |  | 2338.5 |  |  | 2206.5 |  |  | 2100.5 |  |  | 2249.5 |  |  | 1796.5 |  |  | 2124.5 |  |  | 2013 |  |  | 2254.5 |  |  | 2200.5 |  |  | 2208.5 |  |  | 2029.5 |  |  | 2072.5 |  |  | 2078.5 |  |  | 2083.5 |  |  | 1965 |  |  | 2075.5 |  |  | 2152.5 |  |  | 2223.5 |  |  | 2136 |  |  | 2179.5 |  |  | 2039 |  |  | 1994.5 |  |  | 2148.5 |  |  | 2045.5 |  |  | 2183 |  |  | 2026.5 |  |  | 2150 |  |  | 2104 |  |  | 2189.5 |  |  | 2139 |  |  | 2259 |  |  | 2196.5 |  |  | 2215.5 |  |  | 1993.5 |  |  | 2195 |  |  | 2200.5 |  |  | 2089.5 |  |  | 2032.5 |  |  | 2217.5 |  |  | 2093.5 |  |  | 2116.5 |  |  | 2097.5 |  |  | 2189.5 |  |  | 2143 |  |  | 2281.5 |  |  | 2084 |  |  | 2134.5 |  |  | 2055.5 |  |  | 2234.5 |  |  | 2111 |  |  | 2166 |  |  | 2286 |  |  | 2141.5 |  |  | 2103 |  |  | 2165.5 |  |  | 2274.5 |  |  | 2135.5 |  |  | 2120.5 |  |  | 2026.5 |  |  | 2225.5 |  |  | 2230.5 |  |  | 2210.5 |  |  | 2168 |  |  | 2012.5 |  |  | 2006.5 |  |  | 2147.5 |  |  | 2039.5 |  |  | 2076 |  |  | 2124.5 |  |  | 2179 |  |  | 2166.5 |  |  | 2170.5 |  |  | 2068.5 |  |  | 2032.5 |  |  | 2004 |  |  | 2090.5 |  |  | 1883 |  |  | 2047.5 |  |  | 2161.5 |  |  | 2287.5 |  |  | 2149.5 |  |  | 2127.5 |  |  | 2171.5 |  |  | 1996.5 |  |  | 2211.5 |  |  | 2140.5 |  |  | 2027 |  |  | 2171.5 |  |  | 2101.5 |  |  | 2070.5 |  |  | 2204.5 |  |  | 2188.5 |  |  | 2078 |  |  | 2065 |  |  | 2141.5 |  |  | 2073 |  |  | 2247.5 |  |  | 2084.5 |  |  | 2238.5 |  |  | 2196.5 |  |  | 2117.5 |  |  | 2189.5 |  |  | 2122.5 |  |  | 2183.5 |  |  | 2153 |  |  | 2112.5 |  |  | 2336.5 |  |  | 2131.5 |  |  | 2017 |  |  | 2097.5 |  |  | 2083.5 |  |  | 2236 |  |  | 2029 |  |  | 2149.5 |  |  | 2041 |  |  | 1964 |  |  | 2024.5 |  |  | 2188 |  |  | 2318.5 |  |  | 2136.5 |  |  | 2242.5 |  |  | 2104.5 |  |  | 2055.5 |  |  | 2094.5 |  |  | 1989.5 |  |  | 2098.5 |  |  | 2162.5 |  |  | 2061.5 |  |  | 2062 |  |  | 2057 |  |  | 2177.5 |  |  | 2202.5 |  |  | 2116.5 |  |  | 2183.5 |  |  | 2123.5 |  |  | 2154.5 |  |  | 2216.5 |  |  | 2103.5 |  |  | 2380 |  |  | 2090.5 |  |  | 2110 |  |  | 2058.5 |  |  | 2271.5 |  |  | 2196.5 |  |  | 2256 |  |  | 2125.5 |  |  | 2041.5 |  |  | 2186 |  |  | 2165.5 |  |  | 2088.5 |  |  | 2205.5 |  |  | 2138.5 |  |  | 2093.5 |  |  | 2156.5 |  |  | 2189 |  |  | 2083.5 |  |  | 2082.5 |  |  | 2197.5 |  |  | 2198.5 |  |  | 2142 |  |  | 2142.5 |  |  | 2228.5 |  |  | 2094 |  |  | 2153.5 |  |  | 2257.5 |  |  | 2159 |  |  | 2242.5 |  |  | 2242.5 |  |  | 2115.5 |  |  | 2121 |  |  | 1941.5 |  |  | 2128.5 |  |  | 2123 |  |  | 2151.5 |  |  | 2173.5 |  |  | 2115.5 |  |  | 1939.5 |  |  | 2226.5 |  |  | 2234.5 |  |  | 2081.5 |  |  | 2128 |  |  | 2085 |  |  | 2006.5 |  |  | 2193.5 |  |  | 2044.5 |  |  | 2182 |  |  | 2296.5 |  |  | 2079.5 |  |  | 2100.5 |  |  | 2028.5 |  |  | 2118.5 |  |  | 2212.5 |  |  | 2064.5 |  |  | 2176.5 |  |  | 1965.5 |  |  | 2146 |  |  | 2090.5 |  |  | 2023.5 |  |  | 2101.5 |  |  | 2201.5 |  |  | 2234.5 |  |  | 2159.5 |  |  | 2174.5 |  |  | 2165.5 |  |  | 1998.5 |  |  | 2204.5 |  |  | 2097.5 |  |  | 2067.5 |  |  | 2173.5 |  |  | 2231 |  |  | 2161.5 |  |  | 2148.5 |  |  | 2096 |  |  | 2171.5 |  |  | 2162.5 |  |  | 2231 |  |  | 2155.5 |  |  | 2285.5 |  |  | 2294.5 |  |  | 2254 |  |  | 2094.5 |  |  | 2205.5 |  |  | 2134.5 |  |  | 1976.5 |  |  | 2162.5 |  |  | 2063 |  |  | 2114.5 |  |  | 2179 |  |  | 2190 |  |  | 2252.5 |  |  | 2190.5 |  |  | 2045.5 |  |  | 1916.5 |  |  | 2073.5 |  |  | 2150.5 |  |  | 2107 |  |  | 2112.5 |  |  | 2108 |  |  | 2119.5 |  |  | 2126 |  |  | 2080 |  |  | 2243 |  |  | 2164.5 |  |  | 2067 |  |  | 2250.5 |  |  | 2201.5 |  |  | 2143.5 |  |  | 2356.5 |  |  | 2103.5 |  |  | 2217 |  |  | 2167.5 |  |  | 2245.5 |  |  | 2313.5 |  |  | 2117 |  |  | 2190.5 |  |  | 2045.5 |  |  | 2144.5 |  |  | 2213.5 |  |  | 2098 |  |  | 2199 |  |  | 2073 |  |  | 2131.5 |  |  | 2221 |  |  | 2220 |  |  | 2207.5 |  |  | 2065.5 |  |  | 2028.5 |  |  | 2163.5 |  |  | 2176.5 |  |  | 2151.5 |  |  | 2284.5 |  |  | 2086.5 |  |  | 2072.5 |  |  | 2035 |  |  | 2100.5 |  |  | 2049 |  |  | 2158.5 |  |  | 2207.5 |  |  | 2122.5 |  |  | 2149.5 |  |  | 2223 |  |  | 2217.5 |  |  | 2160 |  |  | 2077.5 |  |  | 2184.5 |  |  | 2103 |  |  | 2134 |  |  | 2151.5 |  |  | 2151 |  |  | 2168.5 |  |  | 2019.5 |  |  | 2058.5 |  |  | 2065.5 |  |  | 2183.5 |  |  | 2171.5 |  |  | 2053.5 |  |  | 2038 |  |  | 2191.5 |  |  | 2193.5 |  |  | 2161.5 |  |  | 2167.5 |  |  | 2056.5 |  |  | 2162.5 |  |  | 2241.5 |  |  | 2146.5 |  |  | 2226.5 |  |  | 2220.5 |  |  | 2053.5 |  |  | 2020.5 |  |  | 2152 |  |  | 2000.5 |  |  | 2061.5 |  |  | 2211 |  |  | 2090.5 |  |  | 2036.5 |  |  | 2134.5 |  |  | 2043.5 |  |  | 2257 |  |  | 2319.5 |  |  | 2077.5 |  |  | 2016.5 |  |  | 2244.5 |  |  | 2125 |  |  | 2075.5 |  |  | 2266.5 |  |  | 2128.5 |  |  | 2194.5 |  |  | 2074.5 |  |  | 2040.5 |  |  | 2205.5 |  |  | 2159.5 |  |  | 2156.5 |  |  | 2156.5 |  |  | 2219.5 |  |  | 2190 |  |  | 2136.5 |  |  | 2067.5 |  |  | 2250.5 |  |  | 2219.5 |  |  | 2032.5 |  |  | 2122.5 |  |  | 2213 |  |  | 2166.5 |  |  | 2045 |  |  | 2018.5 |  |  | 2196.5 |  |  | 2151.5 |  |  | 2138 |  |  | 2099 |  |  | 2146.5 |  |  | 2209.5 |  |  | 1991.5 |  |  | 2228.5 |  |  | 2143.5 |  |  | 2165.5 |  |  | 2120.5 |  |  | 2213.5 |  |  | 2064.5 |  |  | 2240.5 |  |  | 2094.5 |  |  | 2213.5 |  |  | 2074.5 |  |  | 2161.5 |  |  | 2267.5 |  |  | 2108.5 |  |  | 2112.5 |  |  | 2173.5 |  |  | 2159.5 |  |  | 2137.5 |  |  | 2162.5 |  |  | 2192.5 |  |  | 2166 |  |  | 2212.5 |  |  | 2134.5 |  |  | 2143.5 |  |  | 2132 |  |  | 2193.5 |  |  | 2134.5 |  |  | 2192.5 |  |  | 2130.5 |  |  | 2168 |  |  | 2013.5 |  |  | 2016.5 |  |  | 2031 |  |  | 2099 |  |  | 2129 |  |  | 2141.5 |  |  | 2144.5 |  |  | 2155.5 |  |  | 2360.5 |  |  | 2190 |  |  | 2153.5 |  |  | 2145.5 |  |  | 2041 |  |  | 2136 |  |  | 2138.5 |  |  | 2180.5 |  |  | 2185 |  |  | 2130.5 |  |  | 2219 |  |  | 2039.5 |  |  | 1996.5 |  |  | 2244 |  |  | 2228.5 |  |  | 2162.5 |  |  | 1997.5 |  |  | 2255 |  |  | 2069.5 |  |  | 2104.5 |  |  | 2058.5 |  |  | 2104.5 |  |  | 2087.5 |  |  | 2222.5 |  |  | 2048.5 |  |  | 2155.5 |  |  | 2210.5 |  |  | 2174.5 |  |  | 2131 |  |  | 2153.5 |  |  | 2169.5 |  |  | 2201.5 |  |  | 2191.5 |  |  | 2147.5 |  |  | 2168.5 |  |  | 2273.5 |  |  | 2144.5 |  |  | 2285 |  |  | 2070.5 |  |  | 2098 |  |  | 2291.5 |  |  | 2369.5 |  |  | 2352.5 |  |  | 2069.5 |  |  | 2058.5 |  |  | 2108.5 |  |  | 2034.5 |  |  | 2213.5 |  |  | 2163 |  |  | 2048.5 |  |  | 2155 |  |  | 2035.5 |  |  | 2046.5 |  |  | 2176.5 |  |  | 2245 |  |  | 2112.5 |  |  | 2180.5 |  |  | 1937 |  |  | 2108.5 |  |  | 2106 |  |  | 2134.5 |  |  | 2079.5 |  |  | 2070.5 |  |  | 2120 |  |  | 2235.5 |  |  | 2330.5 |  |  | 2049 |  |  | 2276.5 |  |  | 2081.5 |  |  | 2172 |  |  | 2094.5 |  |  | 2289.5 |  |  | 2226.5 |  |  | 2250.5 |  |  | 2051.5 |  |  | 2256.5 |  |  | 2021.5 |  |  | 2070.5 |  |  | 2030.5 |  |  | 2017.5 |  |  | 2316.5 |  |  | 2216 |  |  | 2198 |  |  | 2286.5 |  |  | 2101.5 |  |  | 2173
74 |  | 2144.5 |  |  | 2293.5 |  |  | 2201 |  |  | 2140.5 |  |  | 2321.5 |  |  | 2200.5 |  |  | 2257.5 |  |  | 2194.5 |  |  | 2183.5 |  |  | 2131.5 |  |  | 2102 |  |  | 2252.5 |  |  | 2244.5 |  |  | 2040.5 |  |  | 2002 |  |  | 2195.5 |  |  | 2273.5 |  |  | 2199.5 |  |  | 2279.5 |  |  | 2095.5 |  |  | 2241.5 |  |  | 2185.5 |  |  | 2253.5 |  |  | 2047.5 |  |  | 2043 |  |  | 2245.5 |  |  | 2203.5 |  |  | 2130.5 |  |  | 2260.5 |  |  | 2076 |  |  | 2210 |  |  | 2275.5 |  |  | 1992.5 |  |  | 2221.5 |  |  | 2050.5 |  |  | 2256 |  |  | 2094.5 |  |  | 2292 |  |  | 2136.5 |  |  | 2187.5 |  |  | 2019.5 |  |  | 2209.5 |  |  | 2048.5 |  |  | 2177 |  |  | 2337.5 |  |  | 2319 |  |  | 2137.5 |  |  | 2283.5 |  |  | 2242.5 |  |  | 2171.5 |  |  | 2093.5 |  |  | 2201.5 |  |  | 2204.5 |  |  | 2130.5 |  |  | 2238.5 |  |  | 2252.5 |  |  | 2076.5 |  |  | 2154 |  |  | 2223.5 |  |  | 2143.5 |  |  | 2145 |  |  | 2147.5 |  |  | 2253.5 |  |  | 2102.5 |  |  | 2074.5 |  |  | 2213 |  |  | 2280.5 |  |  | 2065 |  |  | 2060.5 |  |  | 2217.5 |  |  | 2176 |  |  | 2167.5 |  |  | 2173.5 |  |  | 2309.5 |  |  | 2285 |  |  | 2276 |  |  | 2107.5 |  |  | 2157.5 |  |  | 2066.5 |  |  | 2191.5 |  |  | 2136 |  |  | 2195.5 |  |  | 2220.5 |  |  | 2274.5 |  |  | 2262.5 |  |  | 2115.5 |  |  | 2285.5 |  |  | 2182.5 |  |  | 2188.5 |  |  | 2201.5 |  |  | 2220.5 |  |  | 2211 |  |  | 2056.5 |  |  | 2084 |  |  | 2127 |  |  | 2088 |  |  | 2344.5 |  |  | 2312.5 |  |  | 2048.5 |  |  | 2280.5 |  |  | 2102.5 |  |  | 2152 |  |  | 2156 |  |  | 2101.5 |  |  | 2112.5 |  |  | 2114.5 |  |  | 2224.5 |  |  | 2288.5 |  |  | 2268.5 |  |  | 2214.5 |  |  | 2280.5 |  |  | 2288.5 |  |  | 2165.5 |  |  | 2221.5 |  |  | 2192.5 |  |  | 2194.5 |  |  | 2270.5 |  |  | 2054.5 |  |  | 2174.5 |  |  | 2139.5 |  |  | 2184.5 |  |  | 2230.5 |  |  | 2169.5 |  |  | 2190.5 |  |  | 2185.5 |  |  | 2173 |  |  | 2124.5 |  |  | 2132.5 |  |  | 2095.5 |  |  | 2137.5 |  |  | 2231.5 |  |  | 2185 |  |  | 2078.5 |  |  | 2268.5 |  |  | 2095.5 |  |  | 2114.5 |  |  | 2209 |  |  | 2176.5 |  |  | 2259.5 |  |  | 2125 |  |  | 2213.5 |  |  | 2069 |  |  | 2235 |  |  | 2271.5 |  |  | 2242 |  |  | 2253.5 |  |  | 2130.5 |  |  | 2197.5 |  |  | 2065.5 |  |  | 2219.5 |  |  | 2195.5 |  |  | 2168.5 |  |  | 2212.5 |  |  | 2322.5 |  |  | 2225.5 |  |  | 2263 |  |  | 2120.5 |  |  | 2068 |  |  | 2130.5 |  |  | 2201.5 |  |  | 2119 |  |  | 2203.5 |  |  | 2145.5 |  |  | 2147.5 |  |  | 2052 |  |  | 2167.5 |  |  | 2081.5 |  |  | 2095.5 |  |  | 2271.5 |  |  | 2155.5 |  |  | 2103.5 |  |  | 2143 |  |  | 2139.5 |  |  | 2168.5 |  |  | 2121.5 |  |  | 2167.5 |  |  | 2219.5 |  |  | 2201.5 |  |  | 2100.5 |  |  | 2240 |  |  | 2242.5 |  |  | 2200.5 |  |  | 2251.5 |  |  | 2211.5 |  |  | 2118.5 |  |  | 2295.5 |  |  | 2209.5 |  |  | 2137.5 |  |  | 2286.5 |  |  | 2126.5 |  |  | 2243.5 |  |  | 2028.5 |  |  | 1981.5 |  |  | 2106 |  |  | 2155.5 |  |  | 2189.5 |  |  | 2135.5 |  |  | 2222.5 |  |  | 2249.5 |  |  | 2248.5 |  |  | 2260.5 |  |  | 2137.5 |  |  | 2186.5 |  |  | 2133.5 |  |  | 2083.5 |  |  | 2300.5 |  |  | 2171.5 |  |  | 2136.5 |  |  | 2114.5 |  |  | 2156.5 |  |  | 2232 |  |  | 2245.5 |  |  | 2157.5 |  |  | 1943 |  |  | 2329.5 |  |  | 2303 |  |  | 2034.5 |  |  | 2227.5 |  |  | 2292.5 |  |  | 2254.5 |  |  | 2138.5 |  |  | 2182.5 |  |  | 2185.5 |  |  | 2004.5 |  |  | 2056 |  |  | 2134.5 |  |  | 1987.5 |  |  | 2204.5 |  |  | 2081.5 |  |  | 2185 |  |  | 2099.5 |  |  | 2186.5 |  |  | 2262.5 |  |  | 2186.5 |  |  | 2265.5 |  |  | 2169.5 |  |  | 2158.5 |  |  | 2298.5 |  |  | 2296 |  |  | 2218 |  |  | 2157.5 |  |  | 2093.5 |  |  | 2141.5 |  |  | 2147 |  |  | 2302.5 |  |  | 2165.5 |  |  | 2129.5 |  |  | 2064 |  |  | 2254.5 |  |  | 2201.5 |  |  | 2054.5 |  |  | 2072.5 |  |  | 2132.5 |  |  | 2223.5 |  |  | 2211.5 |  |  | 2209.5 |  |  | 2335.5 |  |  | 1983 |  |  | 2139.5 |  |  | 2226.5 |  |  | 2226.5 |  |  | 2176.5 |  |  | 2104.5 |  |  | 2307 |  |  | 2129.5 |  |  | 2219.5 |  |  | 2248 |  |  | 2297.5 |  |  | 2184.5 |  |  | 2388 |  |  | 2203.5 |  |  | 2218.5 |  |  | 2299.5 |  |  | 2099.5 |  |  | 2181 |  |  | 2152 |  |  | 2174.5 |  |  | 2105.5 |  |  | 2233.5 |  |  | 2179.5 |  |  | 2296.5 |  |  | 2177.5 |  |  | 2157 |  |  | 2181.5 |  |  | 2170.5 |  |  | 2160 |  |  | 2120.5 |  |  | 2012.5 |  |  | 2208 |  |  | 2220.5 |  |  | 2032.5 |  |  | 2217.5 |  |  | 2185 |  |  | 2207.5 |  |  | 2095 |  |  | 2238.5 |  |  | 2083.5 |  |  | 2206.5 |  |  | 2117 |  |  | 2092.5 |  |  | 2297.5 |  |  | 2286.5 |  |  | 2162 |  |  | 2140.5 |  |  | 1996.5 |  |  | 2335.5 |  |  | 2260.5 |  |  | 2186.5 |  |  | 2175 |  |  | 2077.5 |  |  | 2246.5 |  |  | 2244.5 |  |  | 2113 |  |  | 2225 |  |  | 2338.5 |  |  | 2087.5 |  |  | 2072.5 |  |  | 2203.5 |  |  | 2164.5 |  |  | 2169.5 |  |  | 2197.5 |  |  | 2249.5 |  |  | 2124.5 |  |  | 2168.5 |  |  | 2187 |  |  | 2140.5 |  |  | 2239.5 |  |  | 2375.5 |  |  | 2274.5 |  |  | 2217 |  |  | 2184.5 |  |  | 2318.5 |  |  | 2153.5 |  |  | 2027.5 |  |  | 2287.5 |  |  | 2041 |  |  | 2192 |  |  | 2085 |  |  | 2264 |  |  | 2090.5 |  |  | 2224 |  |  | 2181.5 |  |  | 2166 |  |  | 2185.5 |  |  | 2288.5 |  |  | 2159.5 |  |  | 2126.5 |  |  | 2120.5 |  |  | 2188 |  |  | 2244.5 |  |  | 2306.5 |  |  | 2144.5 |  |  | 2207 |  |  | 2247.5 |  |  | 2107.5 |  |  | 2137.5 |  |  | 2199 |  |  | 2127.5 |  |  | 2059.5 |  |  | 2224.5 |  |  | 2122.5 |  |  | 2169.5 |  |  | 2122.5 |  |  | 2216.5 |  |  | 2211.5 |  |  | 2218.5 |  |  | 2067.5 |  |  | 2071 |  |  | 2143.5 |  |  | 2119.5 |  |  | 2072.5 |  |  | 2200.5 |  |  | 2276.5 |  |  | 2115 |  |  | 2239.5 |  |  | 2259 |  |  | 2130 |  |  | 2076.5 |  |  | 2298.5 |  |  | 2110.5 |  |  | 2148 |  |  | 2192.5 |  |  | 2223.5 |  |  | 2177.5 |  |  | 2058 |  |  | 2184.5 |  |  | 2022.5 |  |  | 2163.5 |  |  | 2073.5 |  |  | 2103.5 |  |  | 2097 |  |  | 2124.5 |  |  | 2242 |  |  | 2178.5 |  |  | 2031.5 |  |  | 2172.5 |  |  | 2232 |  |  | 2083.5 |  |  | 2120 |  |  | 2132 |  |  | 2159.5 |  |  | 2040.5 |  |  | 2120.5 |  |  | 2344.5 |  |  | 2310 |  |  | 2249.5 |  |  | 2134.5 |  |  | 1974.5 |  |  | 2151 |  |  | 2230.5 |  |  | 2127.5 |  |  | 1960.5 |  |  | 2149.5 |  |  | 2263 |  |  | 2034.5 |  |  | 2179.5 |  |  | 2214.5 |  |  | 2206.5 |  |  | 2173.5 |  |  | 2131.5 |  |  | 2268 |  |  | 2167.5 |  |  | 2057.5 |  |  | 2164 |  |  | 2067.5 |  |  | 2024.5 |  |  | 2149.5 |  |  | 2214 |  |  | 2206.5 |  |  | 2187.5 |  |  | 2172.5 |  |  | 2125.5 |  |  | 2262.5 |  |  | 2230 |  |  | 2169 |  |  | 2165.5 |  |  | 2262.5 |  |  | 2220.5 |  |  | 2043.5 |  |  | 2035 |  |  | 2201 |  |  | 2094 |  |  | 2296.5 |  |  | 2187 |  |  | 2202.5 |  |  | 2275.5 |  |  | 2239 |  |  | 2076.5 |  |  | 2225.5 |  |  | 2171.5 |  |  | 2244.5 |  |  | 1960.5 |  |  | 2138 |  |  | 2238 |  |  | 2077.5 |  |  | 2231.5 |  |  | 2105 |  |  | 2062.5 |  |  | 2183.5 |  |  | 2135 |  |  | 2267.5 |  |  | 2304.5 |  |  | 2104 |  |  | 2216.5 |  |  | 2173.5 |  |  | 2205 |  |  | 2097.5 |  |  | 2080 |  |  | 2305.5 |  |  | 2297 |  |  | 2129.5 |  |  | 2085.5 |  |  | 2140.5 |  |  | 2158.5 |  |  | 2195.5 |  |  | 2082.5 |  |  | 2198 |  |  | 2111.5 |  |  | 2207.5 |  |  | 2114.5 |  |  | 2130.5 |  |  | 2150.5 |  |  | 2139 |  |  | 2090.5 |  |  | 2170 |  |  | 2168.5 |  |  | 2056.5 |  |  | 2260.5 |  |  | 2167.5 |  |  | 2172.5 |  |  | 2167.5 |  |  | 2125.5 |  |  | 2218.5 |  |  | 2074.5 |  |  | 2103 |  |  | 2207.5 |  |  | 2072 |  |  | 2181 |  |  | 2205.5 |  |  | 2003 |  |  | 2048.5 |  |  | 2218.5 |  |  | 2264.5 |  |  | 2141.5 |  |  | 2273.5 |  |  | 2238.5 |  |  | 2209.5 |  |  | 2142 |  |  | 2301 |  |  | 2065.5 |  |  | 2139.5 |  |  | 2164 |  |  | 2099.5 |  |  | 2115.5 |  |  | 2083.5 |  |  | 2084.5 |  |  | 2130.5 |  |  | 2092 |  |  | 2131.5 |  |  | 2175.5 |  |  | 2089.5 |  |  | 2105 |  |  | 2226.5 |  |  | 2188.5 |  |  | 2183.5 |  |  | 2377.5 |  |  | 2227.5 |  |  | 2129.5 |  |  | 2278.5 |  |  | 1835.5 |  |  | 2150.5 |  |  | 2028 |  |  | 2301.5 |  |  | 2221.5 |  |  | 2247.5 |  |  | 2058.5 |  |  | 2111.5 |  |  | 2117.5 |  |  | 2112.5 |  |  | 2004 |  |  | 2099.5 |  |  | 2191.5 |  |  | 2238.5 |  |  | 2175 |  |  | 2205.5 |  |  | 2063 |  |  | 2009.5 |  |  | 2177.5 |  |  | 2074.5 |  |  | 2230 |  |  | 2047.5 |  |  | 2179 |  |  | 2143 |  |  | 2218.5 |  |  | 2186 |  |  | 2298 |  |  | 2211.5 |  |  | 2262.5 |  |  | 2022.5 |  |  | 2216 |  |  | 2215.5 |  |  | 2104.5 |  |  | 2047.5 |  |  | 2256.5 |  |  | 2108.5 |  |  | 2131.5 |  |  | 2136.5 |  |  | 2218.5 |  |  | 2164 |  |  | 2328.5 |  |  | 2123 |  |  | 2160.5 |  |  | 2102.5 |  |  | 2281.5 |  |  | 2150 |  |  | 2205 |  |  | 2312 |  |  | 2156.5 |  |  | 2142 |  |  | 2212.5 |  |  | 2300.5 |  |  | 2182.5 |  |  | 2146.5 |  |  | 2055.5 |  |  | 2272.5 |  |  | 2277.5 |  |  | 2249.5 |  |  | 2207 |  |  | 2041.5 |  |  | 2021.5 |  |  | 2176.5 |  |  | 2060.5 |  |  | 2102 |  |  | 2139.5 |  |  | 2226 |  |  | 2181.5 |  |  | 2209.5 |  |  | 2089.5 |  |  | 2071.5 |  |  | 2030 |  |  | 2119.5 |  |  | 1912 |  |  | 2094.5 |  |  | 2182.5 |  |  | 2316.5 |  |  | 2173.5 |  |  | 2156.5 |  |  | 2218.5 |  |  | 2025.5 |  |  | 2240.5 |  |  | 2166.5 |  |  | 2053 |  |  | 2192.5 |  |  | 2122.5 |  |  | 2117.5 |  |  | 2243.5 |  |  | 2227.5 |  |  | 2102 |  |  | 2094 |  |  | 2188.5 |  |  | 2112 |  |  | 2286.5 |  |  | 2110.5 |  |  | 2285.5 |  |  | 2211.5 |  |  | 2141.5 |  |  | 2218.5 |  |  | 2146.5 |  |  | 2209.5 |  |  | 2174 |  |  | 2136.5 |  |  | 2365.5 |  |  | 2157.5 |  |  | 2032 |  |  | 2136.5 |  |  | 2098.5 |  |  | 2275 |  |  | 2076 |  |  | 2164.5 |  |  | 2062 |  |  | 1979 |  |  | 2048.5 |  |  | 2214 |  |  | 2342.5 |  |  | 2151.5 |  |  | 2281.5 |  |  | 2151.5 |  |  | 2084.5 |  |  | 2123.5 |  |  | 2018.5 |  |  | 2124.5 |  |  | 2191.5 |  |  | 2085.5 |  |  | 2086 |  |  | 2104 |  |  | 2198.5 |  |  | 2249.5 |  |  | 2140.5 |  |  | 2222.5 |  |  | 2147.5 |  |  | 2183.5 |  |  | 2240.5 |  |  | 2129.5 |  |  | 2409 |  |  | 2119.5 |  |  | 2125 |  |  | 2097.5 |  |  | 2292.5 |  |  | 2243.5 |  |  | 2295 |  |  | 2146.5 |  |  | 2080.5 |  |  | 2212 |  |  | 2204.5 |  |  | 2127.5 |  |  | 2234.5 |  |  | 2153.5 |  |  | 2117.5 |  |  | 2185.5 |  |  | 2228 |  |  | 2104.5 |  |  | 2111.5 |  |  | 2244.5 |  |  | 2222.5 |  |  | 2181 |  |  | 2181.5 |  |  | 2267.5 |  |  | 2133 |  |  | 2192.5 |  |  | 2283.5 |  |  | 2185 |  |  | 2263.5 |  |  | 2257.5 |  |  | 2139.5 |  |  | 2147 |  |  | 1965.5 |  |  | 2149.5 |  |  | 2138 |  |  | 2190.5 |  |  | 2202.5 |  |  | 2162.5 |  |  | 1978.5 |  |  | 2255.5 |  |  | 2281.5 |  |  | 2128.5 |  |  | 2167 |  |  | 2124 |  |  | 2021.5 |  |  | 2240.5 |  |  | 2083.5 |  |  | 2211 |  |  | 2335.5 |  |  | 2105.5 |  |  | 2139.5 |  |  | 2052.5 |  |  | 2165.5 |  |  | 2241.5 |  |  | 2103.5 |  |  | 2215.5 |  |  | 1991.5 |  |  | 2185 |  |  | 2105.5 |  |  | 2049.5 |  |  | 2125.5 |  |  | 2227.5 |  |  | 2255.5 |  |  | 2198.5 |  |  | 2213.5 |  |  | 2186.5 |  |  | 2037.5 |  |  | 2243.5 |  |  | 2123.5 |  |  | 2088.5 |  |  | 2199.5 |  |  | 2260 |  |  | 2176.5 |  |  | 2195.5 |  |  | 2117 |  |  | 2218.5 |  |  | 2188.5 |  |  | 2270 |  |  | 2194.5 |  |  | 2300.5 |  |  | 2333.5 |  |  | 2269 |  |  | 2118.5 |  |  | 2231.5 |  |  | 2173.5 |  |  | 1997.5 |  |  | 2188.5 |  |  | 2084 |  |  | 2129.5 |  |  | 2226 |  |  | 2205 |  |  | 2276.5 |  |  | 2205.5 |  |  | 2071.5 |  |  | 1940.5 |  |  | 2099.5 |  |  | 2176.5 |  |  | 2128 |  |  | 2151.5 |  |  | 2132 |  |  | 2145.5 |  |  | 2152 |  |  | 2104 |  |  | 2282 |  |  | 2211.5 |  |  | 2106 |  |  | 2279.5 |  |  | 2222.5 |  |  | 2167.5 |  |  | 2371.5 |  |  | 2118.5 |  |  | 2256 |  |  | 2206.5 |  |  | 2271.5 |  |  | 2337.5 |  |  | 2146 |  |  | 2216.5 |  |  | 2092.5 |  |  | 2183.5 |  |  | 2237.5 |  |  | 2137 |  |  | 2214 |  |  | 2102 |  |  | 2170.5 |  |  | 2268 |  |  | 2241 |  |  | 2233.5 |  |  | 2086.5 |  |  | 2067.5 |  |  | 2202.5 |  |  | 2191.5 |  |  | 2166.5 |  |  | 2310.5 |  |  | 2112.5 |  |  | 2093.5 |  |  | 2061 |  |  | 2124.5 |  |  | 2075 |  |  | 2197.5 |  |  | 2222.5 |  |  | 2161.5 |  |  | 2175.5 |  |  | 2252 |  |  | 2264.5 |  |  | 2186 |  |  | 2116.5 |  |  | 2231.5 |  |  | 2118 |  |  | 2160 |  |  | 2190.5 |  |  | 2190 |  |  | 2207.5 |  |  | 2043.5 |  |  | 2097.5 |  |  | 2080.5 |  |  | 2204.5 |  |  | 2192.5 |  |  | 2068.5 |  |  | 2077 |  |  | 2230.5 |  |  | 2232.5 |  |  | 2190.5 |  |  | 2196.5 |  |  | 2077.5 |  |  | 2201.5 |  |  | 2288.5 |  |  | 2175.5 |  |  | 2273.5 |  |  | 2235.5 |  |  | 2068.5 |  |  | 2059.5 |  |  | 2167 |  |  | 2026.5 |  |  | 2085.5 |  |  | 2250 |  |  | 2105.5 |  |  | 2051.5 |  |  | 2160.5 |  |  | 2082.5 |  |  | 2296 |  |  | 2334.5 |  |  | 2098.5 |  |  | 2040.5 |  |  | 2283.5 |  |  | 2151 |  |  | 2099.5 |  |  | 2292.5 |  |  | 2143.5 |  |  | 2209.5 |  |  | 2100.5 |  |  | 2055.5 |  |  | 2226.5 |  |  | 2206.5 |  |  | 2203.5 |  |  | 2185.5 |  |  | 2245.5 |  |  | 2237 |  |  | 2175.5 |  |  | 2114.5 |  |  | 2274.5 |  |  | 2258.5 |  |  | 2061.5 |  |  | 2161.5 |  |  | 2237 |  |  | 2213.5 |  |  | 2084 |  |  | 2033.5 |  |  | 2243.5 |  |  | 2180.5 |  |  | 2177 |  |  | 2125 |  |  | 2185.5 |  |  | 2256.5 |  |  | 2012.5 |  |  | 2252.5 |  |  | 2182.5 |  |  | 2191.5 |  |  | 2135.5 |  |  | 2252.5 |  |  | 2111.5 |  |  | 2279.5 |  |  | 2133.5 |  |  | 2252.5 |  |  | 2121.5 |  |  | 2187.5 |  |  | 2291.5 |  |  | 2155.5 |  |  | 2151.5 |  |  | 2202.5 |  |  | 2206.5 |  |  | 2158.5 |  |  | 2201.5 |  |  | 2207.5 |  |  | 2213 |  |  | 2227.5 |  |  | 2160.5 |  |  | 2182.5 |  |  | 2171 |  |  | 2219.5 |  |  | 2158.5 |  |  | 2231.5 |  |  | 2169.5 |  |  | 2194 |  |  | 2028.5 |  |  | 2063.5 |  |  | 2046 |  |  | 2138 |  |  | 2144 |  |  | 2170.5 |  |  | 2183.5 |  |  | 2194.5 |  |  | 2407.5 |  |  | 2237 |  |  | 2177.5 |  |  | 2174.5 |  |  | 2065 |  |  | 2157 |  |  | 2177.5 |  |  | 2219.5 |  |  | 2224 |  |  | 2145.5 |  |  | 2245 |  |  | 2078.5 |  |  | 2043.5 |  |  | 2291 |  |  | 2243.5 |  |  | 2191.5 |  |  | 2023.5 |  |  | 2276 |  |  | 2098.5 |  |  | 2119.5 |  |  | 2082.5 |  |  | 2130.5 |  |  | 2116.5 |  |  | 2251.5 |  |  | 2074.5 |  |  | 2202.5 |  |  | 2249.5 |  |  | 2198.5 |  |  | 2157 |  |  | 2192.5 |  |  | 2184.5 |  |  | 2230.5 |  |  | 2220.5 |  |  | 2162.5 |  |  | 2189.5 |  |  | 2297.5 |  |  | 2159.5 |  |  | 2332 |  |  | 2091.5 |  |  | 2127 |  |  | 2338.5 |  |  | 2390.5 |  |  | 2381.5 |  |  | 2095.5 |  |  | 2087.5 |  |  | 2147.5 |  |  | 2081.5 |  |  | 2228.5 |  |  | 2192 |  |  | 2077.5 |  |  | 2202 |  |  | 2059.5 |  |  | 2085.5 |  |  | 2191.5 |  |  | 2260 |  |  | 2127.5 |  |  | 2206.5 |  |  | 1961 |  |  | 2147.5 |  |  | 2145 |  |  | 2160.5 |  |  | 2100.5 |  |  | 2117.5 |  |  | 2159 |  |  | 2256.5 |  |  | 2356.5 |  |  | 2078 |  |  | 2315.5 |  |  | 2128.5 |  |  | 2193 |  |  | 2133.5 |  |  | 2318.5 |  |  | 2265.5 |  |  | 2265.5 |  |  | 2090.5 |  |  | 2277.5 |  |  | 2050.5 |  |  | 2109.5 |  |  | 2056.5 |  |  | 2043.5 |  |  | 2355.5 |  |  | 2240 |  |  | 2222 |  |  | 2301.5 |  |  | 2148.5 |  |  | 2194
75 |  | 2191.5 |  |  | 2317.5 |  |  | 2225 |  |  | 2169.5 |  |  | 2360.5 |  |  | 2221.5 |  |  | 2272.5 |  |  | 2209.5 |  |  | 2222.5 |  |  | 2170.5 |  |  | 2126 |  |  | 2291.5 |  |  | 2259.5 |  |  | 2064.5 |  |  | 2041 |  |  | 2242.5 |  |  | 2288.5 |  |  | 2214.5 |  |  | 2308.5 |  |  | 2142.5 |  |  | 2270.5 |  |  | 2200.5 |  |  | 2282.5 |  |  | 2086.5 |  |  | 2058 |  |  | 2284.5 |  |  | 2218.5 |  |  | 2151.5 |  |  | 2289.5 |  |  | 2102 |  |  | 2236 |  |  | 2322.5 |  |  | 2039.5 |  |  | 2250.5 |  |  | 2089.5 |  |  | 2280 |  |  | 2109.5 |  |  | 2331 |  |  | 2183.5 |  |  | 2208.5 |  |  | 2043.5 |  |  | 2224.5 |  |  | 2063.5 |  |  | 2224 |  |  | 2384.5 |  |  | 2340 |  |  | 2166.5 |  |  | 2309.5 |  |  | 2266.5 |  |  | 2197.5 |  |  | 2108.5 |  |  | 2225.5 |  |  | 2243.5 |  |  | 2145.5 |  |  | 2253.5 |  |  | 2281.5 |  |  | 2091.5 |  |  | 2175 |  |  | 2252.5 |  |  | 2190.5 |  |  | 2192 |  |  | 2194.5 |  |  | 2277.5 |  |  | 2131.5 |  |  | 2089.5 |  |  | 2239 |  |  | 2295.5 |  |  | 2086 |  |  | 2081.5 |  |  | 2243.5 |  |  | 2215 |  |  | 2182.5 |  |  | 2212.5 |  |  | 2330.5 |  |  | 2306 |  |  | 2291 |  |  | 2131.5 |  |  | 2178.5 |  |  | 2105.5 |  |  | 2217.5 |  |  | 2165 |  |  | 2242.5 |  |  | 2246.5 |  |  | 2313.5 |  |  | 2286.5 |  |  | 2154.5 |  |  | 2324.5 |  |  | 2203.5 |  |  | 2209.5 |  |  | 2240.5 |  |  | 2235.5 |  |  | 2232 |  |  | 2103.5 |  |  | 2110 |  |  | 2153 |  |  | 2114 |  |  | 2370.5 |  |  | 2351.5 |  |  | 2087.5 |  |  | 2309.5 |  |  | 2123.5 |  |  | 2178 |  |  | 2171 |  |  | 2148.5 |  |  | 2133.5 |  |  | 2135.5 |  |  | 2245.5 |  |  | 2327.5 |  |  | 2315.5 |  |  | 2253.5 |  |  | 2295.5 |  |  | 2314.5 |  |  | 2204.5 |  |  | 2250.5 |  |  | 2216.5 |  |  | 2215.5 |  |  | 2285.5 |  |  | 2093.5 |  |  | 2200.5 |  |  | 2163.5 |  |  | 2199.5 |  |  | 2269.5 |  |  | 2216.5 |  |  | 2219.5 |  |  | 2209.5 |  |  | 2194 |  |  | 2171.5 |  |  | 2153.5 |  |  | 2134.5 |  |  | 2184.5 |  |  | 2257.5 |  |  | 2214 |  |  | 2125.5 |  |  | 2294.5 |  |  | 2142.5 |  |  | 2140.5 |  |  | 2230 |  |  | 2200.5 |  |  | 2306.5 |  |  | 2149 |  |  | 2228.5 |  |  | 2116 |  |  | 2256 |  |  | 2310.5 |  |  | 2266 |  |  | 2300.5 |  |  | 2154.5 |  |  | 2212.5 |  |  | 2104.5 |  |  | 2243.5 |  |  | 2234.5 |  |  | 2197.5 |  |  | 2236.5 |  |  | 2351.5 |  |  | 2246.5 |  |  | 2302 |  |  | 2159.5 |  |  | 2083 |  |  | 2169.5 |  |  | 2216.5 |  |  | 2158 |  |  | 2218.5 |  |  | 2171.5 |  |  | 2171.5 |  |  | 2091 |  |  | 2191.5 |  |  | 2110.5 |  |  | 2121.5 |  |  | 2310.5 |  |  | 2170.5 |  |  | 2132.5 |  |  | 2169 |  |  | 2165.5 |  |  | 2183.5 |  |  | 2147.5 |  |  | 2182.5 |  |  | 2245.5 |  |  | 2248.5 |  |  | 2147.5 |  |  | 2264 |  |  | 2257.5 |  |  | 2226.5 |  |  | 2280.5 |  |  | 2250.5 |  |  | 2133.5 |  |  | 2334.5 |  |  | 2238.5 |  |  | 2176.5 |  |  | 2325.5 |  |  | 2165.5 |  |  | 2267.5 |  |  | 2043.5 |  |  | 2020.5 |  |  | 2121 |  |  | 2170.5 |  |  | 2228.5 |  |  | 2156.5 |  |  | 2243.5 |  |  | 2288.5 |  |  | 2287.5 |  |  | 2299.5 |  |  | 2184.5 |  |  | 2225.5 |  |  | 2154.5 |  |  | 2122.5 |  |  | 2315.5 |  |  | 2192.5 |  |  | 2175.5 |  |  | 2153.5 |  |  | 2195.5 |  |  | 2258 |  |  | 2266.5 |  |  | 2172.5 |  |  | 1958 |  |  | 2368.5 |  |  | 2318 |  |  | 2073.5 |  |  | 2248.5 |  |  | 2331.5 |  |  | 2301.5 |  |  | 2162.5 |  |  | 2206.5 |  |  | 2209.5 |  |  | 2043.5 |  |  | 2085 |  |  | 2158.5 |  |  | 2002.5 |  |  | 2219.5 |  |  | 2128.5 |  |  | 2224 |  |  | 2146.5 |  |  | 2201.5 |  |  | 2288.5 |  |  | 2210.5 |  |  | 2312.5 |  |  | 2208.5 |  |  | 2197.5 |  |  | 2345.5 |  |  | 2320 |  |  | 2244 |  |  | 2196.5 |  |  | 2132.5 |  |  | 2167.5 |  |  | 2194 |  |  | 2326.5 |  |  | 2191.5 |  |  | 2150.5 |  |  | 2093 |  |  | 2283.5 |  |  | 2216.5 |  |  | 2075.5 |  |  | 2111.5 |  |  | 2171.5 |  |  | 2247.5 |  |  | 2250.5 |  |  | 2230.5 |  |  | 2359.5 |  |  | 2009 |  |  | 2165.5 |  |  | 2265.5 |  |  | 2265.5 |  |  | 2200.5 |  |  | 2125.5 |  |  | 2346 |  |  | 2155.5 |  |  | 2248.5 |  |  | 2272 |  |  | 2336.5 |  |  | 2199.5 |  |  | 2417 |  |  | 2242.5 |  |  | 2257.5 |  |  | 2328.5 |  |  | 2138.5 |  |  | 2207 |  |  | 2176 |  |  | 2213.5 |  |  | 2120.5 |  |  | 2248.5 |  |  | 2205.5 |  |  | 2322.5 |  |  | 2224.5 |  |  | 2204 |  |  | 2207.5 |  |  | 2185.5 |  |  | 2184 |  |  | 2159.5 |  |  | 2051.5 |  |  | 2255 |  |  | 2244.5 |  |  | 2058.5 |  |  | 2256.5 |  |  | 2232 |  |  | 2246.5 |  |  | 2119 |  |  | 2267.5 |  |  | 2109.5 |  |  | 2232.5 |  |  | 2156 |  |  | 2121.5 |  |  | 2318.5 |  |  | 2307.5 |  |  | 2177 |  |  | 2161.5 |  |  | 2035.5 |  |  | 2364.5 |  |  | 2299.5 |  |  | 2210.5 |  |  | 2222 |  |  | 2124.5 |  |  | 2285.5 |  |  | 2268.5 |  |  | 2139 |  |  | 2240 |  |  | 2377.5 |  |  | 2116.5 |  |  | 2087.5 |  |  | 2232.5 |  |  | 2211.5 |  |  | 2190.5 |  |  | 2226.5 |  |  | 2273.5 |  |  | 2145.5 |  |  | 2194.5 |  |  | 2211 |  |  | 2179.5 |  |  | 2265.5 |  |  | 2396.5 |  |  | 2313.5 |  |  | 2232 |  |  | 2208.5 |  |  | 2357.5 |  |  | 2182.5 |  |  | 2066.5 |  |  | 2334.5 |  |  | 2070 |  |  | 2207 |  |  | 2114 |  |  | 2303 |  |  | 2129.5 |  |  | 2263 |  |  | 2196.5 |  |  | 2205 |  |  | 2206.5 |  |  | 2309.5 |  |  | 2206.5 |  |  | 2150.5 |  |  | 2159.5 |  |  | 2227 |  |  | 2268.5 |  |  | 2321.5 |  |  | 2183.5 |  |  | 2231 |  |  | 2286.5 |  |  | 2146.5 |  |  | 2166.5 |  |  | 2223 |  |  | 2166.5 |  |  | 2098.5 |  |  | 2248.5 |  |  | 2161.5 |  |  | 2190.5 |  |  | 2148.5 |  |  | 2255.5 |  |  | 2226.5 |  |  | 2257.5 |  |  | 2106.5 |  |  | 2118 |  |  | 2164.5 |  |  | 2145.5 |  |  | 2111.5 |  |  | 2229.5 |  |  | 2300.5 |  |  | 2162 |  |  | 2268.5 |  |  | 2298 |  |  | 2151 |  |  | 2115.5 |  |  | 2337.5 |  |  | 2136.5 |  |  | 2169 |  |  | 2239.5 |  |  | 2262.5 |  |  | 2206.5 |  |  | 2087 |  |  | 2205.5 |  |  | 2037.5 |  |  | 2210.5 |  |  | 2088.5 |  |  | 2127.5 |  |  | 2123 |  |  | 2163.5 |  |  | 2257 |  |  | 2202.5 |  |  | 2070.5 |  |  | 2198.5 |  |  | 2271 |  |  | 2122.5 |  |  | 2144 |  |  | 2153 |  |  | 2185.5 |  |  | 2066.5 |  |  | 2144.5 |  |  | 2383.5 |  |  | 2357 |  |  | 2275.5 |  |  | 2173.5 |  |  | 2013.5 |  |  | 2198 |  |  | 2256.5 |  |  | 2174.5 |  |  | 1984.5 |  |  | 2175.5 |  |  | 2310 |  |  | 2063.5 |  |  | 2205.5 |  |  | 2235.5 |  |  | 2245.5 |  |  | 2199.5 |  |  | 2170.5 |  |  | 2294 |  |  | 2191.5 |  |  | 2081.5 |  |  | 2179 |  |  | 2088.5 |  |  | 2063.5 |  |  | 2196.5 |  |  | 2240 |  |  | 2230.5 |  |  | 2226.5 |  |  | 2211.5 |  |  | 2149.5 |  |  | 2283.5 |  |  | 2254 |  |  | 2190 |  |  | 2191.5 |  |  | 2277.5 |  |  | 2249.5 |  |  | 2069.5 |  |  | 2050 |  |  | 2248 |  |  | 2115 |  |  | 2335.5 |  |  | 2216 |  |  | 2231.5 |  |  | 2314.5 |  |  | 2265 |  |  | 2091.5 |  |  | 2249.5 |  |  | 2210.5 |  |  | 2283.5 |  |  | 1986.5 |  |  | 2177 |  |  | 2259 |  |  | 2092.5 |  |  | 2270.5 |  |  | 2144 |  |  | 2101.5 |  |  | 2198.5 |  |  | 2174 |  |  | 2293.5 |  |  | 2325.5 |  |  | 2133 |  |  | 2240.5 |  |  | 2212.5 |  |  | 2252 |  |  | 2126.5 |  |  | 2101 |  |  | 2344.5 |  |  | 2336 |  |  | 2144.5 |  |  | 2114.5 |  |  | 2166.5 |  |  | 2173.5 |  |  | 2216.5 |  |  | 2111.5 |  |  | 2237 |  |  | 2150.5 |  |  | 2228.5 |  |  | 2138.5 |  |  | 2169.5 |  |  | 2189.5 |  |  | 2160 |  |  | 2137.5 |  |  | 2209 |  |  | 2192.5 |  |  | 2080.5 |  |  | 2284.5 |  |  | 2193.5 |  |  | 2219.5 |  |  | 2196.5 |  |  | 2172.5 |  |  | 2233.5 |  |  | 2089.5 |  |  | 2129 |  |  | 2246.5 |  |  | 2098 |  |  | 2196 |  |  | 2226.5 |  |  | 2027 |  |  | 2069.5 |  |  | 2257.5 |  |  | 2279.5 |  |  | 2180.5 |  |  | 2299.5 |  |  | 2267.5 |  |  | 2230.5 |  |  | 2166 |  |  | 2327 |  |  | 2091.5 |  |  | 2178.5 |  |  | 2203 |  |  | 2114.5 |  |  | 2136.5 |  |  | 2122.5 |  |  | 2105.5 |  |  | 2145.5 |  |  | 2116 |  |  | 2157.5 |  |  | 2201.5 |  |  | 2118.5 |  |  | 2144 |  |  | 2255.5 |  |  | 2227.5 |  |  | 2198.5 |  |  | 2406.5 |  |  | 2266.5 |  |  | 2144.5 |  |  | 2293.5 |  |  | 1874.5 |  |  | 2179.5 |  |  | 2075 |  |  | 2327.5 |  |  | 2245.5 |  |  | 2273.5 |  |  | 2084.5 |  |  | 2150.5 |  |  | 2146.5 |  |  | 2141.5 |  |  | 2051 |  |  | 2114.5 |  |  | 2220.5 |  |  | 2259.5 |  |  | 2196 |  |  | 2244.5 |  |  | 2102 |  |  | 2024.5 |  |  | 2216.5 |  |  | 2095.5 |  |  | 2259 |  |  | 2068.5 |  |  | 2205 |  |  | 2172 |  |  | 2244.5 |  |  | 2225 |  |  | 2345 |  |  | 2250.5 |  |  | 2286.5 |  |  | 2046.5 |  |  | 2242 |  |  | 2244.5 |  |  | 2119.5 |  |  | 2076.5 |  |  | 2295.5 |  |  | 2137.5 |  |  | 2160.5 |  |  | 2157.5 |  |  | 2233.5 |  |  | 2179 |  |  | 2354.5 |  |  | 2144 |  |  | 2186.5 |  |  | 2117.5 |  |  | 2302.5 |  |  | 2189 |  |  | 2244 |  |  | 2333 |  |  | 2195.5 |  |  | 2181 |  |  | 2236.5 |  |  | 2339.5 |  |  | 2211.5 |  |  | 2175.5 |  |  | 2076.5 |  |  | 2319.5 |  |  | 2306.5 |  |  | 2273.5 |  |  | 2246 |  |  | 2080.5 |  |  | 2060.5 |  |  | 2205.5 |  |  | 2107.5 |  |  | 2131 |  |  | 2168.5 |  |  | 2273 |  |  | 2202.5 |  |  | 2233.5 |  |  | 2136.5 |  |  | 2086.5 |  |  | 2054 |  |  | 2140.5 |  |  | 1936 |  |  | 2133.5 |  |  | 2229.5 |  |  | 2355.5 |  |  | 2188.5 |  |  | 2182.5 |  |  | 2265.5 |  |  | 2072.5 |  |  | 2266.5 |  |  | 2195.5 |  |  | 2077 |  |  | 2231.5 |  |  | 2151.5 |  |  | 2141.5 |  |  | 2282.5 |  |  | 2253.5 |  |  | 2141 |  |  | 2120 |  |  | 2217.5 |  |  | 2159 |  |  | 2307.5 |  |  | 2139.5 |  |  | 2324.5 |  |  | 2232.5 |  |  | 2156.5 |  |  | 2247.5 |  |  | 2175.5 |  |  | 2238.5 |  |  | 2221 |  |  | 2157.5 |  |  | 2404.5 |  |  | 2178.5 |  |  | 2071 |  |  | 2157.5 |  |  | 2124.5 |  |  | 2290 |  |  | 2115 |  |  | 2190.5 |  |  | 2101 |  |  | 2008 |  |  | 2087.5 |  |  | 2261 |  |  | 2368.5 |  |  | 2175.5 |  |  | 2328.5 |  |  | 2190.5 |  |  | 2105.5 |  |  | 2152.5 |  |  | 2033.5 |  |  | 2163.5 |  |  | 2215.5 |  |  | 2124.5 |  |  | 2112 |  |  | 2130 |  |  | 2237.5 |  |  | 2296.5 |  |  | 2155.5 |  |  | 2243.5 |  |  | 2186.5 |  |  | 2209.5 |  |  | 2255.5 |  |  | 2158.5 |  |  | 2435 |  |  | 2166.5 |  |  | 2149 |  |  | 2112.5 |  |  | 2339.5 |  |  | 2282.5 |  |  | 2334 |  |  | 2185.5 |  |  | 2119.5 |  |  | 2241 |  |  | 2233.5 |  |  | 2151.5 |  |  | 2258.5 |  |  | 2200.5 |  |  | 2156.5 |  |  | 2224.5 |  |  | 2249 |  |  | 2143.5 |  |  | 2135.5 |  |  | 2283.5 |  |  | 2248.5 |  |  | 2207 |  |  | 2220.5 |  |  | 2314.5 |  |  | 2157 |  |  | 2216.5 |  |  | 2304.5 |  |  | 2214 |  |  | 2302.5 |  |  | 2283.5 |  |  | 2160.5 |  |  | 2162 |  |  | 2012.5 |  |  | 2178.5 |  |  | 2153 |  |  | 2219.5 |  |  | 2241.5 |  |  | 2186.5 |  |  | 2017.5 |  |  | 2279.5 |  |  | 2302.5 |  |  | 2167.5 |  |  | 2196 |  |  | 2171 |  |  | 2042.5 |  |  | 2287.5 |  |  | 2098.5 |  |  | 2250 |  |  | 2374.5 |  |  | 2131.5 |  |  | 2186.5 |  |  | 2067.5 |  |  | 2180.5 |  |  | 2262.5 |  |  | 2124.5 |  |  | 2230.5 |  |  | 2017.5 |  |  | 2206 |  |  | 2144.5 |  |  | 2078.5 |  |  | 2164.5 |  |  | 2266.5 |  |  | 2302.5 |  |  | 2227.5 |  |  | 2228.5 |  |  | 2212.5 |  |  | 2058.5 |  |  | 2267.5 |  |  | 2162.5 |  |  | 2103.5 |  |  | 2214.5 |  |  | 2289 |  |  | 2202.5 |  |  | 2234.5 |  |  | 2143 |  |  | 2257.5 |  |  | 2227.5 |  |  | 2309 |  |  | 2233.5 |  |  | 2315.5 |  |  | 2354.5 |  |  | 2308 |  |  | 2157.5 |  |  | 2270.5 |  |  | 2199.5 |  |  | 2012.5 |  |  | 2227.5 |  |  | 2123 |  |  | 2158.5 |  |  | 2250 |  |  | 2244 |  |  | 2297.5 |  |  | 2234.5 |  |  | 2092.5 |  |  | 1966.5 |  |  | 2114.5 |  |  | 2215.5 |  |  | 2149 |  |  | 2166.5 |  |  | 2156 |  |  | 2192.5 |  |  | 2191 |  |  | 2151 |  |  | 2297 |  |  | 2240.5 |  |  | 2127 |  |  | 2318.5 |  |  | 2261.5 |  |  | 2188.5 |  |  | 2386.5 |  |  | 2133.5 |  |  | 2295 |  |  | 2245.5 |  |  | 2292.5 |  |  | 2358.5 |  |  | 2167 |  |  | 2237.5 |  |  | 2131.5 |  |  | 2212.5 |  |  | 2261.5 |  |  | 2184 |  |  | 2261 |  |  | 2149 |  |  | 2185.5 |  |  | 2315 |  |  | 2265 |  |  | 2272.5 |  |  | 2110.5 |  |  | 2091.5 |  |  | 2228.5 |  |  | 2238.5 |  |  | 2205.5 |  |  | 2325.5 |  |  | 2159.5 |  |  | 2132.5 |  |  | 2108 |  |  | 2150.5 |  |  | 2114 |  |  | 2212.5 |  |  | 2237.5 |  |  | 2176.5 |  |  | 2190.5 |  |  | 2278 |  |  | 2285.5 |  |  | 2225 |  |  | 2155.5 |  |  | 2260.5 |  |  | 2144 |  |  | 2184 |  |  | 2237.5 |  |  | 2211 |  |  | 2233.5 |  |  | 2069.5 |  |  | 2136.5 |  |  | 2104.5 |  |  | 2251.5 |  |  | 2239.5 |  |  | 2097.5 |  |  | 2124 |  |  | 2259.5 |  |  | 2253.5 |  |  | 2216.5 |  |  | 2243.5 |  |  | 2098.5 |  |  | 2240.5 |  |  | 2314.5 |  |  | 2222.5 |  |  | 2312.5 |  |  | 2274.5 |  |  | 2107.5 |  |  | 2083.5 |  |  | 2206 |  |  | 2065.5 |  |  | 2132.5 |  |  | 2297 |  |  | 2120.5 |  |  | 2090.5 |  |  | 2181.5 |  |  | 2129.5 |  |  | 2343 |  |  | 2360.5 |  |  | 2137.5 |  |  | 2061.5 |  |  | 2312.5 |  |  | 2166 |  |  | 2123.5 |  |  | 2307.5 |  |  | 2182.5 |  |  | 2238.5 |  |  | 2126.5 |  |  | 2070.5 |  |  | 2252.5 |  |  | 2230.5 |  |  | 2218.5 |  |  | 2224.5 |  |  | 2266.5 |  |  | 2263 |  |  | 2214.5 |  |  | 2161.5 |  |  | 2295.5 |  |  | 2273.5 |  |  | 2100.5 |  |  | 2208.5 |  |  | 2263 |  |  | 2252.5 |  |  | 2113 |  |  | 2072.5 |  |  | 2267.5 |  |  | 2227.5 |  |  | 2224 |  |  | 2151 |  |  | 2211.5 |  |  | 2271.5 |  |  | 2033.5 |  |  | 2278.5 |  |  | 2197.5 |  |  | 2220.5 |  |  | 2161.5 |  |  | 2281.5 |  |  | 2132.5 |  |  | 2308.5 |  |  | 2154.5 |  |  | 2273.5 |  |  | 2136.5 |  |  | 2226.5 |  |  | 2338.5 |  |  | 2176.5 |  |  | 2190.5 |  |  | 2223.5 |  |  | 2227.5 |  |  | 2187.5 |  |  | 2227.5 |  |  | 2236.5 |  |  | 2252 |  |  | 2266.5 |  |  | 2199.5 |  |  | 2211.5 |  |  | 2200 |  |  | 2240.5 |  |  | 2197.5 |  |  | 2270.5 |  |  | 2184.5 |  |  | 2233 |  |  | 2043.5 |  |  | 2102.5 |  |  | 2067 |  |  | 2177 |  |  | 2173 |  |  | 2196.5 |  |  | 2198.5 |  |  | 2223.5 |  |  | 2428.5 |  |  | 2261 |  |  | 2216.5 |  |  | 2198.5 |  |  | 2104 |  |  | 2181 |  |  | 2201.5 |  |  | 2266.5 |  |  | 2263 |  |  | 2192.5 |  |  | 2271 |  |  | 2117.5 |  |  | 2082.5 |  |  | 2330 |  |  | 2282.5 |  |  | 2230.5 |  |  | 2070.5 |  |  | 2315 |  |  | 2113.5 |  |  | 2134.5 |  |  | 2103.5 |  |  | 2154.5 |  |  | 2145.5 |  |  | 2277.5 |  |  | 2098.5 |  |  | 2249.5 |  |  | 2288.5 |  |  | 2213.5 |  |  | 2186 |  |  | 2207.5 |  |  | 2231.5 |  |  | 2269.5 |  |  | 2259.5 |  |  | 2201.5 |  |  | 2228.5 |  |  | 2336.5 |  |  | 2206.5 |  |  | 2353 |  |  | 2120.5 |  |  | 2174 |  |  | 2385.5 |  |  | 2419.5 |  |  | 2420.5 |  |  | 2110.5 |  |  | 2126.5 |  |  | 2186.5 |  |  | 2110.5 |  |  | 2267.5 |  |  | 2218 |  |  | 2116.5 |  |  | 2249 |  |  | 2074.5 |  |  | 2106.5 |  |  | 2212.5 |  |  | 2275 |  |  | 2166.5 |  |  | 2245.5 |  |  | 1982 |  |  | 2176.5 |  |  | 2192 |  |  | 2199.5 |  |  | 2124.5 |  |  | 2138.5 |  |  | 2183 |  |  | 2303.5 |  |  | 2395.5 |  |  | 2107 |  |  | 2362.5 |  |  | 2175.5 |  |  | 2232 |  |  | 2159.5 |  |  | 2357.5 |  |  | 2286.5 |  |  | 2304.5 |  |  | 2111.5 |  |  | 2306.5 |  |  | 2097.5 |  |  | 2156.5 |  |  | 2085.5 |  |  | 2069.5 |  |  | 2370.5 |  |  | 2279 |  |  | 2246 |  |  | 2322.5 |  |  | 2187.5 |  |  | 2241
76 |  | 2215.5 |  |  | 2356.5 |  |  | 2240 |  |  | 2216.5 |  |  | 2386.5 |  |  | 2236.5 |  |  | 2293.5 |  |  | 2248.5 |  |  | 2243.5 |  |  | 2199.5 |  |  | 2152 |  |  | 2330.5 |  |  | 2306.5 |  |  | 2103.5 |  |  | 2056 |  |  | 2289.5 |  |  | 2335.5 |  |  | 2229.5 |  |  | 2334.5 |  |  | 2181.5 |  |  | 2309.5 |  |  | 2239.5 |  |  | 2308.5 |  |  | 2110.5 |  |  | 2082 |  |  | 2305.5 |  |  | 2244.5 |  |  | 2198.5 |  |  | 2313.5 |  |  | 2149 |  |  | 2265 |  |  | 2361.5 |  |  | 2060.5 |  |  | 2289.5 |  |  | 2128.5 |  |  | 2309 |  |  | 2156.5 |  |  | 2370 |  |  | 2222.5 |  |  | 2247.5 |  |  | 2067.5 |  |  | 2271.5 |  |  | 2102.5 |  |  | 2263 |  |  | 2410.5 |  |  | 2379 |  |  | 2205.5 |  |  | 2348.5 |  |  | 2313.5 |  |  | 2218.5 |  |  | 2123.5 |  |  | 2251.5 |  |  | 2267.5 |  |  | 2166.5 |  |  | 2277.5 |  |  | 2307.5 |  |  | 2115.5 |  |  | 2214 |  |  | 2291.5 |  |  | 2237.5 |  |  | 2231 |  |  | 2215.5 |  |  | 2303.5 |  |  | 2157.5 |  |  | 2110.5 |  |  | 2278 |  |  | 2342.5 |  |  | 2115 |  |  | 2128.5 |  |  | 2282.5 |  |  | 2254 |  |  | 2208.5 |  |  | 2238.5 |  |  | 2369.5 |  |  | 2327 |  |  | 2330 |  |  | 2170.5 |  |  | 2199.5 |  |  | 2134.5 |  |  | 2243.5 |  |  | 2194 |  |  | 2281.5 |  |  | 2275.5 |  |  | 2352.5 |  |  | 2307.5 |  |  | 2201.5 |  |  | 2339.5 |  |  | 2242.5 |  |  | 2224.5 |  |  | 2261.5 |  |  | 2259.5 |  |  | 2253 |  |  | 2118.5 |  |  | 2125 |  |  | 2168 |  |  | 2140 |  |  | 2394.5 |  |  | 2366.5 |  |  | 2134.5 |  |  | 2348.5 |  |  | 2162.5 |  |  | 2202 |  |  | 2197 |  |  | 2187.5 |  |  | 2172.5 |  |  | 2159.5 |  |  | 2260.5 |  |  | 2366.5 |  |  | 2344.5 |  |  | 2292.5 |  |  | 2316.5 |  |  | 2338.5 |  |  | 2219.5 |  |  | 2279.5 |  |  | 2263.5 |  |  | 2262.5 |  |  | 2332.5 |  |  | 2122.5 |  |  | 2239.5 |  |  | 2184.5 |  |  | 2246.5 |  |  | 2308.5 |  |  | 2255.5 |  |  | 2258.5 |  |  | 2235.5 |  |  | 2233 |  |  | 2195.5 |  |  | 2200.5 |  |  | 2149.5 |  |  | 2213.5 |  |  | 2286.5 |  |  | 2253 |  |  | 2164.5 |  |  | 2341.5 |  |  | 2181.5 |  |  | 2161.5 |  |  | 2277 |  |  | 2239.5 |  |  | 2332.5 |  |  | 2178 |  |  | 2243.5 |  |  | 2131 |  |  | 2295 |  |  | 2339.5 |  |  | 2313 |  |  | 2326.5 |  |  | 2180.5 |  |  | 2241.5 |  |  | 2130.5 |  |  | 2258.5 |  |  | 2263.5 |  |  | 2236.5 |  |  | 2260.5 |  |  | 2390.5 |  |  | 2261.5 |  |  | 2323 |  |  | 2180.5 |  |  | 2112 |  |  | 2193.5 |  |  | 2237.5 |  |  | 2197 |  |  | 2242.5 |  |  | 2210.5 |  |  | 2210.5 |  |  | 2115 |  |  | 2220.5 |  |  | 2131.5 |  |  | 2142.5 |  |  | 2336.5 |  |  | 2209.5 |  |  | 2161.5 |  |  | 2190 |  |  | 2189.5 |  |  | 2204.5 |  |  | 2162.5 |  |  | 2221.5 |  |  | 2284.5 |  |  | 2287.5 |  |  | 2186.5 |  |  | 2303 |  |  | 2286.5 |  |  | 2273.5 |  |  | 2327.5 |  |  | 2289.5 |  |  | 2172.5 |  |  | 2363.5 |  |  | 2285.5 |  |  | 2191.5 |  |  | 2354.5 |  |  | 2180.5 |  |  | 2282.5 |  |  | 2082.5 |  |  | 2049.5 |  |  | 2168 |  |  | 2217.5 |  |  | 2257.5 |  |  | 2182.5 |  |  | 2290.5 |  |  | 2327.5 |  |  | 2326.5 |  |  | 2338.5 |  |  | 2223.5 |  |  | 2254.5 |  |  | 2193.5 |  |  | 2151.5 |  |  | 2354.5 |  |  | 2231.5 |  |  | 2190.5 |  |  | 2174.5 |  |  | 2224.5 |  |  | 2297 |  |  | 2313.5 |  |  | 2219.5 |  |  | 1982 |  |  | 2407.5 |  |  | 2357 |  |  | 2120.5 |  |  | 2269.5 |  |  | 2346.5 |  |  | 2322.5 |  |  | 2209.5 |  |  | 2245.5 |  |  | 2238.5 |  |  | 2082.5 |  |  | 2106 |  |  | 2179.5 |  |  | 2049.5 |  |  | 2245.5 |  |  | 2154.5 |  |  | 2271 |  |  | 2175.5 |  |  | 2227.5 |  |  | 2327.5 |  |  | 2225.5 |  |  | 2327.5 |  |  | 2237.5 |  |  | 2236.5 |  |  | 2366.5 |  |  | 2359 |  |  | 2283 |  |  | 2211.5 |  |  | 2171.5 |  |  | 2206.5 |  |  | 2220 |  |  | 2365.5 |  |  | 2212.5 |  |  | 2165.5 |  |  | 2108 |  |  | 2322.5 |  |  | 2231.5 |  |  | 2114.5 |  |  | 2150.5 |  |  | 2210.5 |  |  | 2294.5 |  |  | 2297.5 |  |  | 2269.5 |  |  | 2383.5 |  |  | 2056 |  |  | 2180.5 |  |  | 2304.5 |  |  | 2286.5 |  |  | 2215.5 |  |  | 2151.5 |  |  | 2385 |  |  | 2170.5 |  |  | 2287.5 |  |  | 2296 |  |  | 2365.5 |  |  | 2238.5 |  |  | 2438 |  |  | 2268.5 |  |  | 2283.5 |  |  | 2343.5 |  |  | 2162.5 |  |  | 2228 |  |  | 2223 |  |  | 2252.5 |  |  | 2159.5 |  |  | 2277.5 |  |  | 2231.5 |  |  | 2343.5 |  |  | 2271.5 |  |  | 2230 |  |  | 2236.5 |  |  | 2200.5 |  |  | 2210 |  |  | 2198.5 |  |  | 2072.5 |  |  | 2270 |  |  | 2291.5 |  |  | 2105.5 |  |  | 2295.5 |  |  | 2258 |  |  | 2267.5 |  |  | 2140 |  |  | 2306.5 |  |  | 2156.5 |  |  | 2253.5 |  |  | 2203 |  |  | 2145.5 |  |  | 2339.5 |  |  | 2333.5 |  |  | 2216 |  |  | 2187.5 |  |  | 2061.5 |  |  | 2390.5 |  |  | 2346.5 |  |  | 2231.5 |  |  | 2248 |  |  | 2171.5 |  |  | 2300.5 |  |  | 2297.5 |  |  | 2178 |  |  | 2279 |  |  | 2406.5 |  |  | 2163.5 |  |  | 2108.5 |  |  | 2247.5 |  |  | 2232.5 |  |  | 2211.5 |  |  | 2247.5 |  |  | 2312.5 |  |  | 2184.5 |  |  | 2241.5 |  |  | 2237 |  |  | 2208.5 |  |  | 2280.5 |  |  | 2425.5 |  |  | 2342.5 |  |  | 2253 |  |  | 2223.5 |  |  | 2396.5 |  |  | 2206.5 |  |  | 2092.5 |  |  | 2349.5 |  |  | 2117 |  |  | 2246 |  |  | 2143 |  |  | 2329 |  |  | 2155.5 |  |  | 2302 |  |  | 2217.5 |  |  | 2229 |  |  | 2235.5 |  |  | 2338.5 |  |  | 2235.5 |  |  | 2197.5 |  |  | 2198.5 |  |  | 2266 |  |  | 2292.5 |  |  | 2347.5 |  |  | 2212.5 |  |  | 2257 |  |  | 2333.5 |  |  | 2193.5 |  |  | 2190.5 |  |  | 2244 |  |  | 2187.5 |  |  | 2119.5 |  |  | 2274.5 |  |  | 2176.5 |  |  | 2229.5 |  |  | 2187.5 |  |  | 2279.5 |  |  | 2252.5 |  |  | 2304.5 |  |  | 2121.5 |  |  | 2165 |  |  | 2211.5 |  |  | 2171.5 |  |  | 2132.5 |  |  | 2253.5 |  |  | 2324.5 |  |  | 2201 |  |  | 2292.5 |  |  | 2337 |  |  | 2175 |  |  | 2130.5 |  |  | 2361.5 |  |  | 2151.5 |  |  | 2190 |  |  | 2260.5 |  |  | 2283.5 |  |  | 2221.5 |  |  | 2102 |  |  | 2231.5 |  |  | 2063.5 |  |  | 2231.5 |  |  | 2127.5 |  |  | 2142.5 |  |  | 2162 |  |  | 2184.5 |  |  | 2296 |  |  | 2223.5 |  |  | 2085.5 |  |  | 2237.5 |  |  | 2297 |  |  | 2137.5 |  |  | 2183 |  |  | 2177 |  |  | 2200.5 |  |  | 2095.5 |  |  | 2170.5 |  |  | 2422.5 |  |  | 2404 |  |  | 2322.5 |  |  | 2197.5 |  |  | 2028.5 |  |  | 2222 |  |  | 2285.5 |  |  | 2203.5 |  |  | 2008.5 |  |  | 2204.5 |  |  | 2334 |  |  | 2110.5 |  |  | 2244.5 |  |  | 2250.5 |  |  | 2284.5 |  |  | 2223.5 |  |  | 2209.5 |  |  | 2341 |  |  | 2206.5 |  |  | 2102.5 |  |  | 2194 |  |  | 2135.5 |  |  | 2089.5 |  |  | 2225.5 |  |  | 2261 |  |  | 2256.5 |  |  | 2250.5 |  |  | 2237.5 |  |  | 2173.5 |  |  | 2298.5 |  |  | 2301 |  |  | 2219 |  |  | 2206.5 |  |  | 2316.5 |  |  | 2288.5 |  |  | 2093.5 |  |  | 2079 |  |  | 2295 |  |  | 2162 |  |  | 2350.5 |  |  | 2231 |  |  | 2257.5 |  |  | 2353.5 |  |  | 2291 |  |  | 2115.5 |  |  | 2270.5 |  |  | 2225.5 |  |  | 2307.5 |  |  | 2025.5 |  |  | 2224 |  |  | 2280 |  |  | 2139.5 |  |  | 2294.5 |  |  | 2168 |  |  | 2125.5 |  |  | 2219.5 |  |  | 2203 |  |  | 2332.5 |  |  | 2340.5 |  |  | 2157 |  |  | 2269.5 |  |  | 2251.5 |  |  | 2276 |  |  | 2152.5 |  |  | 2148 |  |  | 2368.5 |  |  | 2351 |  |  | 2191.5 |  |  | 2135.5 |  |  | 2187.5 |  |  | 2212.5 |  |  | 2263.5 |  |  | 2135.5 |  |  | 2284 |  |  | 2171.5 |  |  | 2257.5 |  |  | 2177.5 |  |  | 2184.5 |  |  | 2228.5 |  |  | 2186 |  |  | 2161.5 |  |  | 2230 |  |  | 2216.5 |  |  | 2119.5 |  |  | 2299.5 |  |  | 2232.5 |  |  | 2258.5 |  |  | 2211.5 |  |  | 2187.5 |  |  | 2280.5 |  |  | 2115.5 |  |  | 2150 |  |  | 2267.5 |  |  | 2124 |  |  | 2243 |  |  | 2247.5 |  |  | 2056 |  |  | 2090.5 |  |  | 2278.5 |  |  | 2300.5 |  |  | 2227.5 |  |  | 2323.5 |  |  | 2282.5 |  |  | 2269.5 |  |  | 2195 |  |  | 2374 |  |  | 2117.5 |  |  | 2193.5 |  |  | 2229 |  |  | 2129.5 |  |  | 2165.5 |  |  | 2161.5 |  |  | 2152.5 |  |  | 2184.5 |  |  | 2137 |  |  | 2196.5 |  |  | 2225.5 |  |  | 2157.5 |  |  | 2173 |  |  | 2302.5 |  |  | 2253.5 |  |  | 2219.5 |  |  | 2453.5 |  |  | 2281.5 |  |  | 2168.5 |  |  | 2319.5 |  |  | 1898.5 |  |  | 2218.5 |  |  | 2104 |  |  | 2342.5 |  |  | 2284.5 |  |  | 2320.5 |  |  | 2110.5 |  |  | 2174.5 |  |  | 2185.5 |  |  | 2156.5 |  |  | 2077 |  |  | 2153.5 |  |  | 2246.5 |  |  | 2274.5 |  |  | 2211 |  |  | 2265.5 |  |  | 2131 |  |  | 2063.5 |  |  | 2237.5 |  |  | 2110.5 |  |  | 2298 |  |  | 2107.5 |  |  | 2229 |  |  | 2211 |  |  | 2259.5 |  |  | 2249 |  |  | 2371 |  |  | 2289.5 |  |  | 2307.5 |  |  | 2093.5 |  |  | 2271 |  |  | 2259.5 |  |  | 2134.5 |  |  | 2123.5 |  |  | 2319.5 |  |  | 2184.5 |  |  | 2186.5 |  |  | 2196.5 |  |  | 2248.5 |  |  | 2208 |  |  | 2393.5 |  |  | 2183 |  |  | 2210.5 |  |  | 2156.5 |  |  | 2341.5 |  |  | 2213 |  |  | 2291 |  |  | 2357 |  |  | 2219.5 |  |  | 2205 |  |  | 2275.5 |  |  | 2354.5 |  |  | 2232.5 |  |  | 2222.5 |  |  | 2100.5 |  |  | 2334.5 |  |  | 2345.5 |  |  | 2320.5 |  |  | 2275 |  |  | 2119.5 |  |  | 2081.5 |  |  | 2234.5 |  |  | 2146.5 |  |  | 2146 |  |  | 2207.5 |  |  | 2299 |  |  | 2223.5 |  |  | 2257.5 |  |  | 2160.5 |  |  | 2133.5 |  |  | 2083 |  |  | 2164.5 |  |  | 1960 |  |  | 2159.5 |  |  | 2258.5 |  |  | 2376.5 |  |  | 2209.5 |  |  | 2211.5 |  |  | 2312.5 |  |  | 2119.5 |  |  | 2281.5 |  |  | 2210.5 |  |  | 2103 |  |  | 2255.5 |  |  | 2190.5 |  |  | 2170.5 |  |  | 2321.5 |  |  | 2292.5 |  |  | 2156 |  |  | 2141 |  |  | 2232.5 |  |  | 2198 |  |  | 2346.5 |  |  | 2163.5 |  |  | 2371.5 |  |  | 2271.5 |  |  | 2195.5 |  |  | 2286.5 |  |  | 2204.5 |  |  | 2277.5 |  |  | 2245 |  |  | 2196.5 |  |  | 2430.5 |  |  | 2217.5 |  |  | 2095 |  |  | 2183.5 |  |  | 2163.5 |  |  | 2337 |  |  | 2141 |  |  | 2237.5 |  |  | 2148 |  |  | 2034 |  |  | 2102.5 |  |  | 2276 |  |  | 2407.5 |  |  | 2201.5 |  |  | 2343.5 |  |  | 2229.5 |  |  | 2152.5 |  |  | 2167.5 |  |  | 2048.5 |  |  | 2189.5 |  |  | 2254.5 |  |  | 2153.5 |  |  | 2151 |  |  | 2151 |  |  | 2276.5 |  |  | 2320.5 |  |  | 2170.5 |  |  | 2290.5 |  |  | 2225.5 |  |  | 2256.5 |  |  | 2284.5 |  |  | 2184.5 |  |  | 2459 |  |  | 2187.5 |  |  | 2178 |  |  | 2141.5 |  |  | 2360.5 |  |  | 2297.5 |  |  | 2360 |  |  | 2206.5 |  |  | 2143.5 |  |  | 2256 |  |  | 2262.5 |  |  | 2180.5 |  |  | 2287.5 |  |  | 2224.5 |  |  | 2180.5 |  |  | 2245.5 |  |  | 2270 |  |  | 2172.5 |  |  | 2182.5 |  |  | 2309.5 |  |  | 2287.5 |  |  | 2236 |  |  | 2246.5 |  |  | 2329.5 |  |  | 2196 |  |  | 2263.5 |  |  | 2328.5 |  |  | 2253 |  |  | 2331.5 |  |  | 2322.5 |  |  | 2199.5 |  |  | 2191 |  |  | 2051.5 |  |  | 2217.5 |  |  | 2179 |  |  | 2258.5 |  |  | 2262.5 |  |  | 2215.5 |  |  | 2038.5 |  |  | 2300.5 |  |  | 2341.5 |  |  | 2191.5 |  |  | 2220 |  |  | 2195 |  |  | 2057.5 |  |  | 2311.5 |  |  | 2119.5 |  |  | 2279 |  |  | 2403.5 |  |  | 2152.5 |  |  | 2212.5 |  |  | 2106.5 |  |  | 2227.5 |  |  | 2288.5 |  |  | 2163.5 |  |  | 2269.5 |  |  | 2043.5 |  |  | 2232 |  |  | 2183.5 |  |  | 2099.5 |  |  | 2185.5 |  |  | 2281.5 |  |  | 2341.5 |  |  | 2266.5 |  |  | 2257.5 |  |  | 2251.5 |  |  | 2097.5 |  |  | 2306.5 |  |  | 2183.5 |  |  | 2132.5 |  |  | 2238.5 |  |  | 2328 |  |  | 2241.5 |  |  | 2249.5 |  |  | 2182 |  |  | 2286.5 |  |  | 2266.5 |  |  | 2324 |  |  | 2254.5 |  |  | 2339.5 |  |  | 2401.5 |  |  | 2347 |  |  | 2181.5 |  |  | 2309.5 |  |  | 2238.5 |  |  | 2041.5 |  |  | 2274.5 |  |  | 2138 |  |  | 2197.5 |  |  | 2265 |  |  | 2273 |  |  | 2312.5 |  |  | 2260.5 |  |  | 2113.5 |  |  | 1992.5 |  |  | 2161.5 |  |  | 2262.5 |  |  | 2173 |  |  | 2205.5 |  |  | 2171 |  |  | 2213.5 |  |  | 2212 |  |  | 2172 |  |  | 2336 |  |  | 2261.5 |  |  | 2148 |  |  | 2339.5 |  |  | 2276.5 |  |  | 2217.5 |  |  | 2433.5 |  |  | 2157.5 |  |  | 2316 |  |  | 2260.5 |  |  | 2313.5 |  |  | 2397.5 |  |  | 2196 |  |  | 2263.5 |  |  | 2155.5 |  |  | 2241.5 |  |  | 2287.5 |  |  | 2208 |  |  | 2300 |  |  | 2164 |  |  | 2232.5 |  |  | 2336 |  |  | 2294 |  |  | 2311.5 |  |  | 2139.5 |  |  | 2120.5 |  |  | 2257.5 |  |  | 2259.5 |  |  | 2244.5 |  |  | 2364.5 |  |  | 2206.5 |  |  | 2179.5 |  |  | 2129 |  |  | 2174.5 |  |  | 2129 |  |  | 2259.5 |  |  | 2263.5 |  |  | 2223.5 |  |  | 2229.5 |  |  | 2304 |  |  | 2306.5 |  |  | 2264 |  |  | 2202.5 |  |  | 2281.5 |  |  | 2159 |  |  | 2205 |  |  | 2258.5 |  |  | 2240 |  |  | 2259.5 |  |  | 2093.5 |  |  | 2157.5 |  |  | 2151.5 |  |  | 2298.5 |  |  | 2278.5 |  |  | 2126.5 |  |  | 2163 |  |  | 2298.5 |  |  | 2274.5 |  |  | 2240.5 |  |  | 2269.5 |  |  | 2145.5 |  |  | 2287.5 |  |  | 2335.5 |  |  | 2248.5 |  |  | 2333.5 |  |  | 2321.5 |  |  | 2131.5 |  |  | 2122.5 |  |  | 2227 |  |  | 2112.5 |  |  | 2161.5 |  |  | 2323 |  |  | 2144.5 |  |  | 2129.5 |  |  | 2220.5 |  |  | 2158.5 |  |  | 2390 |  |  | 2384.5 |  |  | 2176.5 |  |  | 2108.5 |  |  | 2333.5 |  |  | 2192 |  |  | 2144.5 |  |  | 2346.5 |  |  | 2208.5 |  |  | 2285.5 |  |  | 2152.5 |  |  | 2117.5 |  |  | 2299.5 |  |  | 2245.5 |  |  | 2257.5 |  |  | 2239.5 |  |  | 2305.5 |  |  | 2289 |  |  | 2253.5 |  |  | 2190.5 |  |  | 2324.5 |  |  | 2302.5 |  |  | 2126.5 |  |  | 2237.5 |  |  | 2287 |  |  | 2281.5 |  |  | 2152 |  |  | 2098.5 |  |  | 2296.5 |  |  | 2256.5 |  |  | 2245 |  |  | 2175 |  |  | 2258.5 |  |  | 2297.5 |  |  | 2048.5 |  |  | 2325.5 |  |  | 2226.5 |  |  | 2249.5 |  |  | 2182.5 |  |  | 2307.5 |  |  | 2158.5 |  |  | 2329.5 |  |  | 2201.5 |  |  | 2320.5 |  |  | 2157.5 |  |  | 2247.5 |  |  | 2353.5 |  |  | 2200.5 |  |  | 2229.5 |  |  | 2238.5 |  |  | 2242.5 |  |  | 2216.5 |  |  | 2266.5 |  |  | 2275.5 |  |  | 2273 |  |  | 2313.5 |  |  | 2220.5 |  |  | 2235.5 |  |  | 2239 |  |  | 2266.5 |  |  | 2236.5 |  |  | 2291.5 |  |  | 2223.5 |  |  | 2257 |  |  | 2058.5 |  |  | 2131.5 |  |  | 2114 |  |  | 2216 |  |  | 2199 |  |  | 2222.5 |  |  | 2237.5 |  |  | 2270.5 |  |  | 2449.5 |  |  | 2300 |  |  | 2245.5 |  |  | 2224.5 |  |  | 2143 |  |  | 2196 |  |  | 2240.5 |  |  | 2305.5 |  |  | 2292 |  |  | 2231.5 |  |  | 2318 |  |  | 2146.5 |  |  | 2121.5 |  |  | 2356 |  |  | 2303.5 |  |  | 2259.5 |  |  | 2099.5 |  |  | 2339 |  |  | 2160.5 |  |  | 2173.5 |  |  | 2132.5 |  |  | 2183.5 |  |  | 2192.5 |  |  | 2306.5 |  |  | 2145.5 |  |  | 2264.5 |  |  | 2317.5 |  |  | 2234.5 |  |  | 2207 |  |  | 2254.5 |  |  | 2252.5 |  |  | 2308.5 |  |  | 2298.5 |  |  | 2227.5 |  |  | 2275.5 |  |  | 2357.5 |  |  | 2230.5 |  |  | 2368 |  |  | 2167.5 |  |  | 2195 |  |  | 2424.5 |  |  | 2448.5 |  |  | 2446.5 |  |  | 2125.5 |  |  | 2147.5 |  |  | 2233.5 |  |  | 2131.5 |  |  | 2288.5 |  |  | 2242 |  |  | 2145.5 |  |  | 2273 |  |  | 2100.5 |  |  | 2135.5 |  |  | 2251.5 |  |  | 2296 |  |  | 2181.5 |  |  | 2284.5 |  |  | 2029 |  |  | 2200.5 |  |  | 2231 |  |  | 2228.5 |  |  | 2148.5 |  |  | 2167.5 |  |  | 2209 |  |  | 2324.5 |  |  | 2416.5 |  |  | 2136 |  |  | 2383.5 |  |  | 2214.5 |  |  | 2253 |  |  | 2198.5 |  |  | 2404.5 |  |  | 2315.5 |  |  | 2351.5 |  |  | 2137.5 |  |  | 2345.5 |  |  | 2136.5 |  |  | 2203.5 |  |  | 2132.5 |  |  | 2093.5 |  |  | 2385.5 |  |  | 2318 |  |  | 2285 |  |  | 2337.5 |  |  | 2211.5 |  |  | 2270
77 |  | 2236.5 |  |  | 2377.5 |  |  | 2279 |  |  | 2255.5 |  |  | 2425.5 |  |  | 2283.5 |  |  | 2340.5 |  |  | 2287.5 |  |  | 2267.5 |  |  | 2214.5 |  |  | 2178 |  |  | 2345.5 |  |  | 2330.5 |  |  | 2150.5 |  |  | 2082 |  |  | 2336.5 |  |  | 2361.5 |  |  | 2244.5 |  |  | 2373.5 |  |  | 2205.5 |  |  | 2324.5 |  |  | 2265.5 |  |  | 2347.5 |  |  | 2157.5 |  |  | 2121 |  |  | 2326.5 |  |  | 2283.5 |  |  | 2237.5 |  |  | 2342.5 |  |  | 2173 |  |  | 2312 |  |  | 2376.5 |  |  | 2099.5 |  |  | 2304.5 |  |  | 2149.5 |  |  | 2333 |  |  | 2180.5 |  |  | 2409 |  |  | 2261.5 |  |  | 2286.5 |  |  | 2093.5 |  |  | 2310.5 |  |  | 2128.5 |  |  | 2289 |  |  | 2457.5 |  |  | 2403 |  |  | 2226.5 |  |  | 2377.5 |  |  | 2334.5 |  |  | 2257.5 |  |  | 2170.5 |  |  | 2290.5 |  |  | 2293.5 |  |  | 2205.5 |  |  | 2298.5 |  |  | 2336.5 |  |  | 2144.5 |  |  | 2253 |  |  | 2317.5 |  |  | 2276.5 |  |  | 2255 |  |  | 2239.5 |  |  | 2318.5 |  |  | 2172.5 |  |  | 2125.5 |  |  | 2307 |  |  | 2371.5 |  |  | 2162 |  |  | 2143.5 |  |  | 2321.5 |  |  | 2283 |  |  | 2237.5 |  |  | 2262.5 |  |  | 2398.5 |  |  | 2342 |  |  | 2359 |  |  | 2194.5 |  |  | 2214.5 |  |  | 2155.5 |  |  | 2258.5 |  |  | 2241 |  |  | 2305.5 |  |  | 2314.5 |  |  | 2373.5 |  |  | 2336.5 |  |  | 2225.5 |  |  | 2378.5 |  |  | 2268.5 |  |  | 2271.5 |  |  | 2300.5 |  |  | 2298.5 |  |  | 2282 |  |  | 2165.5 |  |  | 2172 |  |  | 2192 |  |  | 2161 |  |  | 2433.5 |  |  | 2387.5 |  |  | 2155.5 |  |  | 2387.5 |  |  | 2183.5 |  |  | 2223 |  |  | 2221 |  |  | 2226.5 |  |  | 2193.5 |  |  | 2198.5 |  |  | 2284.5 |  |  | 2395.5 |  |  | 2359.5 |  |  | 2339.5 |  |  | 2340.5 |  |  | 2362.5 |  |  | 2240.5 |  |  | 2294.5 |  |  | 2310.5 |  |  | 2286.5 |  |  | 2356.5 |  |  | 2151.5 |  |  | 2263.5 |  |  | 2210.5 |  |  | 2272.5 |  |  | 2347.5 |  |  | 2276.5 |  |  | 2279.5 |  |  | 2256.5 |  |  | 2262 |  |  | 2216.5 |  |  | 2229.5 |  |  | 2164.5 |  |  | 2228.5 |  |  | 2325.5 |  |  | 2292 |  |  | 2203.5 |  |  | 2356.5 |  |  | 2205.5 |  |  | 2176.5 |  |  | 2316 |  |  | 2263.5 |  |  | 2353.5 |  |  | 2193 |  |  | 2282.5 |  |  | 2152 |  |  | 2342 |  |  | 2378.5 |  |  | 2334 |  |  | 2365.5 |  |  | 2206.5 |  |  | 2265.5 |  |  | 2156.5 |  |  | 2287.5 |  |  | 2284.5 |  |  | 2275.5 |  |  | 2299.5 |  |  | 2414.5 |  |  | 2285.5 |  |  | 2338 |  |  | 2209.5 |  |  | 2136 |  |  | 2232.5 |  |  | 2284.5 |  |  | 2212 |  |  | 2263.5 |  |  | 2236.5 |  |  | 2236.5 |  |  | 2162 |  |  | 2267.5 |  |  | 2146.5 |  |  | 2157.5 |  |  | 2362.5 |  |  | 2256.5 |  |  | 2200.5 |  |  | 2229 |  |  | 2215.5 |  |  | 2219.5 |  |  | 2177.5 |  |  | 2236.5 |  |  | 2299.5 |  |  | 2316.5 |  |  | 2215.5 |  |  | 2324 |  |  | 2315.5 |  |  | 2297.5 |  |  | 2342.5 |  |  | 2315.5 |  |  | 2219.5 |  |  | 2389.5 |  |  | 2324.5 |  |  | 2217.5 |  |  | 2393.5 |  |  | 2195.5 |  |  | 2329.5 |  |  | 2097.5 |  |  | 2088.5 |  |  | 2183 |  |  | 2241.5 |  |  | 2286.5 |  |  | 2221.5 |  |  | 2329.5 |  |  | 2366.5 |  |  | 2373.5 |  |  | 2353.5 |  |  | 2247.5 |  |  | 2293.5 |  |  | 2240.5 |  |  | 2177.5 |  |  | 2393.5 |  |  | 2260.5 |  |  | 2216.5 |  |  | 2221.5 |  |  | 2248.5 |  |  | 2318 |  |  | 2337.5 |  |  | 2243.5 |  |  | 2011 |  |  | 2446.5 |  |  | 2372 |  |  | 2146.5 |  |  | 2308.5 |  |  | 2367.5 |  |  | 2361.5 |  |  | 2256.5 |  |  | 2274.5 |  |  | 2253.5 |  |  | 2097.5 |  |  | 2130 |  |  | 2203.5 |  |  | 2075.5 |  |  | 2284.5 |  |  | 2169.5 |  |  | 2300 |  |  | 2222.5 |  |  | 2248.5 |  |  | 2374.5 |  |  | 2240.5 |  |  | 2366.5 |  |  | 2258.5 |  |  | 2257.5 |  |  | 2390.5 |  |  | 2374 |  |  | 2322 |  |  | 2235.5 |  |  | 2197.5 |  |  | 2232.5 |  |  | 2259 |  |  | 2394.5 |  |  | 2236.5 |  |  | 2186.5 |  |  | 2155 |  |  | 2361.5 |  |  | 2270.5 |  |  | 2135.5 |  |  | 2176.5 |  |  | 2239.5 |  |  | 2315.5 |  |  | 2312.5 |  |  | 2308.5 |  |  | 2404.5 |  |  | 2082 |  |  | 2201.5 |  |  | 2328.5 |  |  | 2325.5 |  |  | 2239.5 |  |  | 2198.5 |  |  | 2411 |  |  | 2199.5 |  |  | 2326.5 |  |  | 2335 |  |  | 2380.5 |  |  | 2253.5 |  |  | 2485 |  |  | 2307.5 |  |  | 2312.5 |  |  | 2364.5 |  |  | 2201.5 |  |  | 2257 |  |  | 2270 |  |  | 2291.5 |  |  | 2198.5 |  |  | 2306.5 |  |  | 2252.5 |  |  | 2382.5 |  |  | 2310.5 |  |  | 2245 |  |  | 2257.5 |  |  | 2226.5 |  |  | 2239 |  |  | 2245.5 |  |  | 2098.5 |  |  | 2291 |  |  | 2317.5 |  |  | 2131.5 |  |  | 2324.5 |  |  | 2282 |  |  | 2306.5 |  |  | 2155 |  |  | 2353.5 |  |  | 2185.5 |  |  | 2274.5 |  |  | 2242 |  |  | 2192.5 |  |  | 2378.5 |  |  | 2372.5 |  |  | 2245 |  |  | 2234.5 |  |  | 2087.5 |  |  | 2405.5 |  |  | 2385.5 |  |  | 2255.5 |  |  | 2287 |  |  | 2192.5 |  |  | 2321.5 |  |  | 2321.5 |  |  | 2217 |  |  | 2326 |  |  | 2421.5 |  |  | 2210.5 |  |  | 2129.5 |  |  | 2286.5 |  |  | 2256.5 |  |  | 2250.5 |  |  | 2262.5 |  |  | 2351.5 |  |  | 2210.5 |  |  | 2265.5 |  |  | 2276 |  |  | 2232.5 |  |  | 2304.5 |  |  | 2472.5 |  |  | 2381.5 |  |  | 2292 |  |  | 2238.5 |  |  | 2435.5 |  |  | 2235.5 |  |  | 2116.5 |  |  | 2388.5 |  |  | 2146 |  |  | 2293 |  |  | 2158 |  |  | 2344 |  |  | 2194.5 |  |  | 2326 |  |  | 2232.5 |  |  | 2268 |  |  | 2256.5 |  |  | 2362.5 |  |  | 2274.5 |  |  | 2244.5 |  |  | 2224.5 |  |  | 2305 |  |  | 2307.5 |  |  | 2373.5 |  |  | 2233.5 |  |  | 2296 |  |  | 2372.5 |  |  | 2232.5 |  |  | 2237.5 |  |  | 2265 |  |  | 2211.5 |  |  | 2158.5 |  |  | 2313.5 |  |  | 2215.5 |  |  | 2268.5 |  |  | 2211.5 |  |  | 2300.5 |  |  | 2291.5 |  |  | 2333.5 |  |  | 2147.5 |  |  | 2189 |  |  | 2235.5 |  |  | 2210.5 |  |  | 2153.5 |  |  | 2268.5 |  |  | 2363.5 |  |  | 2227 |  |  | 2321.5 |  |  | 2363 |  |  | 2190 |  |  | 2169.5 |  |  | 2390.5 |  |  | 2190.5 |  |  | 2219 |  |  | 2299.5 |  |  | 2298.5 |  |  | 2260.5 |  |  | 2141 |  |  | 2257.5 |  |  | 2087.5 |  |  | 2246.5 |  |  | 2151.5 |  |  | 2163.5 |  |  | 2188 |  |  | 2208.5 |  |  | 2335 |  |  | 2247.5 |  |  | 2114.5 |  |  | 2261.5 |  |  | 2312 |  |  | 2184.5 |  |  | 2212 |  |  | 2192 |  |  | 2229.5 |  |  | 2134.5 |  |  | 2194.5 |  |  | 2451.5 |  |  | 2430 |  |  | 2369.5 |  |  | 2236.5 |  |  | 2067.5 |  |  | 2237 |  |  | 2324.5 |  |  | 2229.5 |  |  | 2032.5 |  |  | 2230.5 |  |  | 2355 |  |  | 2134.5 |  |  | 2265.5 |  |  | 2265.5 |  |  | 2308.5 |  |  | 2247.5 |  |  | 2248.5 |  |  | 2388 |  |  | 2221.5 |  |  | 2149.5 |  |  | 2215 |  |  | 2164.5 |  |  | 2110.5 |  |  | 2264.5 |  |  | 2276 |  |  | 2282.5 |  |  | 2297.5 |  |  | 2276.5 |  |  | 2199.5 |  |  | 2327.5 |  |  | 2348 |  |  | 2240 |  |  | 2245.5 |  |  | 2337.5 |  |  | 2312.5 |  |  | 2114.5 |  |  | 2094 |  |  | 2334 |  |  | 2188 |  |  | 2374.5 |  |  | 2252 |  |  | 2296.5 |  |  | 2368.5 |  |  | 2312 |  |  | 2162.5 |  |  | 2296.5 |  |  | 2251.5 |  |  | 2322.5 |  |  | 2051.5 |  |  | 2253 |  |  | 2319 |  |  | 2154.5 |  |  | 2333.5 |  |  | 2183 |  |  | 2164.5 |  |  | 2258.5 |  |  | 2232 |  |  | 2371.5 |  |  | 2366.5 |  |  | 2196 |  |  | 2295.5 |  |  | 2298.5 |  |  | 2323 |  |  | 2167.5 |  |  | 2172 |  |  | 2407.5 |  |  | 2398 |  |  | 2206.5 |  |  | 2159.5 |  |  | 2213.5 |  |  | 2251.5 |  |  | 2292.5 |  |  | 2156.5 |  |  | 2305 |  |  | 2192.5 |  |  | 2278.5 |  |  | 2206.5 |  |  | 2223.5 |  |  | 2267.5 |  |  | 2212 |  |  | 2182.5 |  |  | 2269 |  |  | 2237.5 |  |  | 2134.5 |  |  | 2314.5 |  |  | 2271.5 |  |  | 2273.5 |  |  | 2232.5 |  |  | 2216.5 |  |  | 2319.5 |  |  | 2144.5 |  |  | 2189 |  |  | 2282.5 |  |  | 2163 |  |  | 2269 |  |  | 2268.5 |  |  | 2082 |  |  | 2119.5 |  |  | 2304.5 |  |  | 2329.5 |  |  | 2274.5 |  |  | 2349.5 |  |  | 2297.5 |  |  | 2293.5 |  |  | 2210 |  |  | 2398 |  |  | 2156.5 |  |  | 2214.5 |  |  | 2244 |  |  | 2168.5 |  |  | 2204.5 |  |  | 2200.5 |  |  | 2191.5 |  |  | 2223.5 |  |  | 2161 |  |  | 2243.5 |  |  | 2246.5 |  |  | 2178.5 |  |  | 2212 |  |  | 2331.5 |  |  | 2292.5 |  |  | 2248.5 |  |  | 2492.5 |  |  | 2296.5 |  |  | 2183.5 |  |  | 2343.5 |  |  | 1919.5 |  |  | 2239.5 |  |  | 2143 |  |  | 2366.5 |  |  | 2308.5 |  |  | 2359.5 |  |  | 2136.5 |  |  | 2195.5 |  |  | 2200.5 |  |  | 2182.5 |  |  | 2101 |  |  | 2168.5 |  |  | 2261.5 |  |  | 2289.5 |  |  | 2250 |  |  | 2312.5 |  |  | 2155 |  |  | 2089.5 |  |  | 2261.5 |  |  | 2149.5 |  |  | 2319 |  |  | 2133.5 |  |  | 2244 |  |  | 2235 |  |  | 2298.5 |  |  | 2270 |  |  | 2397 |  |  | 2315.5 |  |  | 2328.5 |  |  | 2114.5 |  |  | 2310 |  |  | 2298.5 |  |  | 2173.5 |  |  | 2138.5 |  |  | 2358.5 |  |  | 2231.5 |  |  | 2212.5 |  |  | 2225.5 |  |  | 2277.5 |  |  | 2229 |  |  | 2419.5 |  |  | 2204 |  |  | 2236.5 |  |  | 2171.5 |  |  | 2388.5 |  |  | 2252 |  |  | 2317 |  |  | 2386 |  |  | 2245.5 |  |  | 2234 |  |  | 2314.5 |  |  | 2383.5 |  |  | 2256.5 |  |  | 2237.5 |  |  | 2126.5 |  |  | 2355.5 |  |  | 2374.5 |  |  | 2349.5 |  |  | 2304 |  |  | 2158.5 |  |  | 2107.5 |  |  | 2273.5 |  |  | 2185.5 |  |  | 2175 |  |  | 2246.5 |  |  | 2325 |  |  | 2262.5 |  |  | 2278.5 |  |  | 2207.5 |  |  | 2162.5 |  |  | 2109 |  |  | 2203.5 |  |  | 1999 |  |  | 2206.5 |  |  | 2297.5 |  |  | 2402.5 |  |  | 2238.5 |  |  | 2250.5 |  |  | 2333.5 |  |  | 2158.5 |  |  | 2296.5 |  |  | 2239.5 |  |  | 2150 |  |  | 2284.5 |  |  | 2219.5 |  |  | 2217.5 |  |  | 2336.5 |  |  | 2331.5 |  |  | 2195 |  |  | 2165 |  |  | 2256.5 |  |  | 2227 |  |  | 2393.5 |  |  | 2202.5 |  |  | 2386.5 |  |  | 2297.5 |  |  | 2234.5 |  |  | 2325.5 |  |  | 2243.5 |  |  | 2316.5 |  |  | 2269 |  |  | 2243.5 |  |  | 2459.5 |  |  | 2238.5 |  |  | 2121 |  |  | 2230.5 |  |  | 2187.5 |  |  | 2361 |  |  | 2180 |  |  | 2284.5 |  |  | 2187 |  |  | 2060 |  |  | 2117.5 |  |  | 2315 |  |  | 2422.5 |  |  | 2227.5 |  |  | 2369.5 |  |  | 2253.5 |  |  | 2167.5 |  |  | 2191.5 |  |  | 2069.5 |  |  | 2204.5 |  |  | 2269.5 |  |  | 2192.5 |  |  | 2172 |  |  | 2166 |  |  | 2323.5 |  |  | 2359.5 |  |  | 2196.5 |  |  | 2305.5 |  |  | 2251.5 |  |  | 2280.5 |  |  | 2299.5 |  |  | 2199.5 |  |  | 2483 |  |  | 2226.5 |  |  | 2225 |  |  | 2156.5 |  |  | 2384.5 |  |  | 2336.5 |  |  | 2399 |  |  | 2230.5 |  |  | 2190.5 |  |  | 2295 |  |  | 2301.5 |  |  | 2219.5 |  |  | 2302.5 |  |  | 2263.5 |  |  | 2209.5 |  |  | 2292.5 |  |  | 2309 |  |  | 2219.5 |  |  | 2206.5 |  |  | 2348.5 |  |  | 2326.5 |  |  | 2275 |  |  | 2270.5 |  |  | 2355.5 |  |  | 2225 |  |  | 2284.5 |  |  | 2367.5 |  |  | 2300 |  |  | 2360.5 |  |  | 2361.5 |  |  | 2214.5 |  |  | 2215 |  |  | 2090.5 |  |  | 2243.5 |  |  | 2200 |  |  | 2279.5 |  |  | 2277.5 |  |  | 2244.5 |  |  | 2062.5 |  |  | 2324.5 |  |  | 2367.5 |  |  | 2212.5 |  |  | 2259 |  |  | 2224 |  |  | 2081.5 |  |  | 2337.5 |  |  | 2143.5 |  |  | 2308 |  |  | 2418.5 |  |  | 2199.5 |  |  | 2238.5 |  |  | 2135.5 |  |  | 2266.5 |  |  | 2327.5 |  |  | 2178.5 |  |  | 2284.5 |  |  | 2058.5 |  |  | 2271 |  |  | 2212.5 |  |  | 2114.5 |  |  | 2224.5 |  |  | 2305.5 |  |  | 2380.5 |  |  | 2305.5 |  |  | 2286.5 |  |  | 2275.5 |  |  | 2112.5 |  |  | 2353.5 |  |  | 2230.5 |  |  | 2171.5 |  |  | 2259.5 |  |  | 2367 |  |  | 2262.5 |  |  | 2288.5 |  |  | 2208 |  |  | 2301.5 |  |  | 2281.5 |  |  | 2353 |  |  | 2293.5 |  |  | 2360.5 |  |  | 2440.5 |  |  | 2394 |  |  | 2196.5 |  |  | 2338.5 |  |  | 2267.5 |  |  | 2070.5 |  |  | 2289.5 |  |  | 2177 |  |  | 2223.5 |  |  | 2312 |  |  | 2299 |  |  | 2359.5 |  |  | 2284.5 |  |  | 2152.5 |  |  | 2018.5 |  |  | 2187.5 |  |  | 2288.5 |  |  | 2197 |  |  | 2229.5 |  |  | 2200 |  |  | 2234.5 |  |  | 2251 |  |  | 2211 |  |  | 2360 |  |  | 2285.5 |  |  | 2169 |  |  | 2378.5 |  |  | 2302.5 |  |  | 2256.5 |  |  | 2454.5 |  |  | 2178.5 |  |  | 2355 |  |  | 2284.5 |  |  | 2352.5 |  |  | 2436.5 |  |  | 2235 |  |  | 2292.5 |  |  | 2181.5 |  |  | 2267.5 |  |  | 2326.5 |  |  | 2229 |  |  | 2339 |  |  | 2211 |  |  | 2256.5 |  |  | 2362 |  |  | 2323 |  |  | 2337.5 |  |  | 2154.5 |  |  | 2146.5 |  |  | 2304.5 |  |  | 2285.5 |  |  | 2259.5 |  |  | 2388.5 |  |  | 2227.5 |  |  | 2208.5 |  |  | 2168 |  |  | 2213.5 |  |  | 2168 |  |  | 2274.5 |  |  | 2278.5 |  |  | 2262.5 |  |  | 2276.5 |  |  | 2343 |  |  | 2330.5 |  |  | 2303 |  |  | 2217.5 |  |  | 2305.5 |  |  | 2183 |  |  | 2229 |  |  | 2284.5 |  |  | 2279 |  |  | 2280.5 |  |  | 2119.5 |  |  | 2181.5 |  |  | 2190.5 |  |  | 2345.5 |  |  | 2317.5 |  |  | 2155.5 |  |  | 2202 |  |  | 2327.5 |  |  | 2298.5 |  |  | 2269.5 |  |  | 2308.5 |  |  | 2169.5 |  |  | 2311.5 |  |  | 2382.5 |  |  | 2287.5 |  |  | 2372.5 |  |  | 2350.5 |  |  | 2160.5 |  |  | 2137.5 |  |  | 2248 |  |  | 2136.5 |  |  | 2190.5 |  |  | 2347 |  |  | 2183.5 |  |  | 2168.5 |  |  | 2235.5 |  |  | 2179.5 |  |  | 2429 |  |  | 2413.5 |  |  | 2197.5 |  |  | 2147.5 |  |  | 2362.5 |  |  | 2207 |  |  | 2183.5 |  |  | 2385.5 |  |  | 2223.5 |  |  | 2332.5 |  |  | 2178.5 |  |  | 2132.5 |  |  | 2346.5 |  |  | 2266.5 |  |  | 2296.5 |  |  | 2268.5 |  |  | 2331.5 |  |  | 2328 |  |  | 2292.5 |  |  | 2205.5 |  |  | 2345.5 |  |  | 2331.5 |  |  | 2155.5 |  |  | 2276.5 |  |  | 2334 |  |  | 2302.5 |  |  | 2176 |  |  | 2137.5 |  |  | 2325.5 |  |  | 2303.5 |  |  | 2266 |  |  | 2196 |  |  | 2297.5 |  |  | 2321.5 |  |  | 2069.5 |  |  | 2372.5 |  |  | 2273.5 |  |  | 2270.5 |  |  | 2221.5 |  |  | 2346.5 |  |  | 2197.5 |  |  | 2376.5 |  |  | 2248.5 |  |  | 2344.5 |  |  | 2178.5 |  |  | 2268.5 |  |  | 2368.5 |  |  | 2239.5 |  |  | 2244.5 |  |  | 2285.5 |  |  | 2268.5 |  |  | 2231.5 |  |  | 2313.5 |  |  | 2314.5 |  |  | 2320 |  |  | 2339.5 |  |  | 2267.5 |  |  | 2264.5 |  |  | 2265 |  |  | 2287.5 |  |  | 2257.5 |  |  | 2320.5 |  |  | 2262.5 |  |  | 2296 |  |  | 2087.5 |  |  | 2170.5 |  |  | 2161 |  |  | 2231 |  |  | 2228 |  |  | 2243.5 |  |  | 2258.5 |  |  | 2299.5 |  |  | 2488.5 |  |  | 2326 |  |  | 2284.5 |  |  | 2263.5 |  |  | 2164 |  |  | 2217 |  |  | 2287.5 |  |  | 2344.5 |  |  | 2331 |  |  | 2270.5 |  |  | 2365 |  |  | 2193.5 |  |  | 2160.5 |  |  | 2380 |  |  | 2332.5 |  |  | 2288.5 |  |  | 2123.5 |  |  | 2363 |  |  | 2175.5 |  |  | 2199.5 |  |  | 2179.5 |  |  | 2212.5 |  |  | 2231.5 |  |  | 2321.5 |  |  | 2192.5 |  |  | 2290.5 |  |  | 2341.5 |  |  | 2273.5 |  |  | 2236 |  |  | 2283.5 |  |  | 2281.5 |  |  | 2337.5 |  |  | 2345.5 |  |  | 2256.5 |  |  | 2296.5 |  |  | 2386.5 |  |  | 2254.5 |  |  | 2389 |  |  | 2191.5 |  |  | 2234 |  |  | 2450.5 |  |  | 2469.5 |  |  | 2493.5 |  |  | 2164.5 |  |  | 2194.5 |  |  | 2272.5 |  |  | 2160.5 |  |  | 2317.5 |  |  | 2263 |  |  | 2184.5 |  |  | 2288 |  |  | 2126.5 |  |  | 2182.5 |  |  | 2290.5 |  |  | 2325 |  |  | 2210.5 |  |  | 2308.5 |  |  | 2044 |  |  | 2224.5 |  |  | 2255 |  |  | 2267.5 |  |  | 2187.5 |  |  | 2188.5 |  |  | 2248 |  |  | 2353.5 |  |  | 2463.5 |  |  | 2160 |  |  | 2430.5 |  |  | 2253.5 |  |  | 2292 |  |  | 2237.5 |  |  | 2433.5 |  |  | 2354.5 |  |  | 2372.5 |  |  | 2184.5 |  |  | 2360.5 |  |  | 2160.5 |  |  | 2250.5 |  |  | 2161.5 |  |  | 2132.5 |  |  | 2424.5 |  |  | 2357 |  |  | 2314 |  |  | 2358.5 |  |  | 2250.5 |  |  | 2317
78 |  | 2275.5 |  |  | 2406.5 |  |  | 2318 |  |  | 2276.5 |  |  | 2449.5 |  |  | 2304.5 |  |  | 2361.5 |  |  | 2302.5 |  |  | 2306.5 |  |  | 2261.5 |  |  | 2217 |  |  | 2369.5 |  |  | 2351.5 |  |  | 2189.5 |  |  | 2103 |  |  | 2383.5 |  |  | 2400.5 |  |  | 2283.5 |  |  | 2394.5 |  |  | 2220.5 |  |  | 2371.5 |  |  | 2304.5 |  |  | 2376.5 |  |  | 2181.5 |  |  | 2150 |  |  | 2365.5 |  |  | 2304.5 |  |  | 2252.5 |  |  | 2381.5 |  |  | 2188 |  |  | 2333 |  |  | 2415.5 |  |  | 2114.5 |  |  | 2343.5 |  |  | 2173.5 |  |  | 2354 |  |  | 2219.5 |  |  | 2456 |  |  | 2300.5 |  |  | 2310.5 |  |  | 2119.5 |  |  | 2334.5 |  |  | 2152.5 |  |  | 2310 |  |  | 2496.5 |  |  | 2432 |  |  | 2273.5 |  |  | 2392.5 |  |  | 2360.5 |  |  | 2304.5 |  |  | 2194.5 |  |  | 2314.5 |  |  | 2332.5 |  |  | 2244.5 |  |  | 2345.5 |  |  | 2351.5 |  |  | 2183.5 |  |  | 2292 |  |  | 2356.5 |  |  | 2291.5 |  |  | 2294 |  |  | 2254.5 |  |  | 2342.5 |  |  | 2196.5 |  |  | 2172.5 |  |  | 2331 |  |  | 2410.5 |  |  | 2201 |  |  | 2182.5 |  |  | 2345.5 |  |  | 2309 |  |  | 2261.5 |  |  | 2301.5 |  |  | 2445.5 |  |  | 2368 |  |  | 2383 |  |  | 2220.5 |  |  | 2235.5 |  |  | 2181.5 |  |  | 2305.5 |  |  | 2256 |  |  | 2334.5 |  |  | 2353.5 |  |  | 2397.5 |  |  | 2375.5 |  |  | 2249.5 |  |  | 2417.5 |  |  | 2294.5 |  |  | 2292.5 |  |  | 2324.5 |  |  | 2313.5 |  |  | 2329 |  |  | 2204.5 |  |  | 2201 |  |  | 2231 |  |  | 2200 |  |  | 2454.5 |  |  | 2426.5 |  |  | 2181.5 |  |  | 2434.5 |  |  | 2207.5 |  |  | 2247 |  |  | 2260 |  |  | 2250.5 |  |  | 2232.5 |  |  | 2227.5 |  |  | 2331.5 |  |  | 2421.5 |  |  | 2388.5 |  |  | 2368.5 |  |  | 2387.5 |  |  | 2391.5 |  |  | 2269.5 |  |  | 2315.5 |  |  | 2349.5 |  |  | 2312.5 |  |  | 2403.5 |  |  | 2198.5 |  |  | 2278.5 |  |  | 2236.5 |  |  | 2298.5 |  |  | 2376.5 |  |  | 2302.5 |  |  | 2318.5 |  |  | 2277.5 |  |  | 2291 |  |  | 2240.5 |  |  | 2258.5 |  |  | 2203.5 |  |  | 2267.5 |  |  | 2346.5 |  |  | 2321 |  |  | 2218.5 |  |  | 2403.5 |  |  | 2244.5 |  |  | 2200.5 |  |  | 2342 |  |  | 2287.5 |  |  | 2382.5 |  |  | 2214 |  |  | 2321.5 |  |  | 2167 |  |  | 2389 |  |  | 2417.5 |  |  | 2349 |  |  | 2404.5 |  |  | 2227.5 |  |  | 2294.5 |  |  | 2203.5 |  |  | 2311.5 |  |  | 2313.5 |  |  | 2299.5 |  |  | 2325.5 |  |  | 2429.5 |  |  | 2306.5 |  |  | 2377 |  |  | 2238.5 |  |  | 2165 |  |  | 2253.5 |  |  | 2305.5 |  |  | 2227 |  |  | 2310.5 |  |  | 2260.5 |  |  | 2260.5 |  |  | 2177 |  |  | 2291.5 |  |  | 2167.5 |  |  | 2181.5 |  |  | 2386.5 |  |  | 2285.5 |  |  | 2239.5 |  |  | 2268 |  |  | 2262.5 |  |  | 2258.5 |  |  | 2201.5 |  |  | 2275.5 |  |  | 2325.5 |  |  | 2342.5 |  |  | 2230.5 |  |  | 2353 |  |  | 2339.5 |  |  | 2321.5 |  |  | 2381.5 |  |  | 2339.5 |  |  | 2245.5 |  |  | 2418.5 |  |  | 2350.5 |  |  | 2256.5 |  |  | 2432.5 |  |  | 2242.5 |  |  | 2353.5 |  |  | 2118.5 |  |  | 2127.5 |  |  | 2212 |  |  | 2256.5 |  |  | 2301.5 |  |  | 2260.5 |  |  | 2350.5 |  |  | 2405.5 |  |  | 2388.5 |  |  | 2374.5 |  |  | 2286.5 |  |  | 2314.5 |  |  | 2264.5 |  |  | 2216.5 |  |  | 2408.5 |  |  | 2284.5 |  |  | 2263.5 |  |  | 2260.5 |  |  | 2277.5 |  |  | 2339 |  |  | 2384.5 |  |  | 2267.5 |  |  | 2035 |  |  | 2475.5 |  |  | 2419 |  |  | 2167.5 |  |  | 2323.5 |  |  | 2391.5 |  |  | 2387.5 |  |  | 2277.5 |  |  | 2298.5 |  |  | 2274.5 |  |  | 2136.5 |  |  | 2169 |  |  | 2224.5 |  |  | 2099.5 |  |  | 2323.5 |  |  | 2208.5 |  |  | 2339 |  |  | 2251.5 |  |  | 2277.5 |  |  | 2421.5 |  |  | 2287.5 |  |  | 2405.5 |  |  | 2297.5 |  |  | 2281.5 |  |  | 2429.5 |  |  | 2421 |  |  | 2348 |  |  | 2261.5 |  |  | 2223.5 |  |  | 2279.5 |  |  | 2280 |  |  | 2420.5 |  |  | 2262.5 |  |  | 2233.5 |  |  | 2170 |  |  | 2382.5 |  |  | 2296.5 |  |  | 2150.5 |  |  | 2191.5 |  |  | 2254.5 |  |  | 2330.5 |  |  | 2333.5 |  |  | 2334.5 |  |  | 2443.5 |  |  | 2106 |  |  | 2227.5 |  |  | 2354.5 |  |  | 2340.5 |  |  | 2278.5 |  |  | 2227.5 |  |  | 2440 |  |  | 2223.5 |  |  | 2352.5 |  |  | 2359 |  |  | 2409.5 |  |  | 2292.5 |  |  | 2511 |  |  | 2354.5 |  |  | 2341.5 |  |  | 2403.5 |  |  | 2248.5 |  |  | 2296 |  |  | 2317 |  |  | 2306.5 |  |  | 2224.5 |  |  | 2345.5 |  |  | 2291.5 |  |  | 2421.5 |  |  | 2349.5 |  |  | 2284 |  |  | 2296.5 |  |  | 2241.5 |  |  | 2265 |  |  | 2292.5 |  |  | 2119.5 |  |  | 2312 |  |  | 2364.5 |  |  | 2170.5 |  |  | 2363.5 |  |  | 2321 |  |  | 2335.5 |  |  | 2202 |  |  | 2368.5 |  |  | 2224.5 |  |  | 2303.5 |  |  | 2281 |  |  | 2216.5 |  |  | 2417.5 |  |  | 2396.5 |  |  | 2292 |  |  | 2263.5 |  |  | 2126.5 |  |  | 2426.5 |  |  | 2424.5 |  |  | 2281.5 |  |  | 2326 |  |  | 2231.5 |  |  | 2360.5 |  |  | 2347.5 |  |  | 2241 |  |  | 2350 |  |  | 2460.5 |  |  | 2236.5 |  |  | 2155.5 |  |  | 2310.5 |  |  | 2271.5 |  |  | 2297.5 |  |  | 2301.5 |  |  | 2380.5 |  |  | 2236.5 |  |  | 2312.5 |  |  | 2302 |  |  | 2258.5 |  |  | 2325.5 |  |  | 2496.5 |  |  | 2420.5 |  |  | 2331 |  |  | 2262.5 |  |  | 2450.5 |  |  | 2282.5 |  |  | 2163.5 |  |  | 2427.5 |  |  | 2161 |  |  | 2319 |  |  | 2184 |  |  | 2370 |  |  | 2209.5 |  |  | 2347 |  |  | 2271.5 |  |  | 2315 |  |  | 2303.5 |  |  | 2401.5 |  |  | 2300.5 |  |  | 2268.5 |  |  | 2263.5 |  |  | 2326 |  |  | 2322.5 |  |  | 2420.5 |  |  | 2248.5 |  |  | 2320 |  |  | 2387.5 |  |  | 2279.5 |  |  | 2261.5 |  |  | 2312 |  |  | 2250.5 |  |  | 2205.5 |  |  | 2342.5 |  |  | 2244.5 |  |  | 2315.5 |  |  | 2232.5 |  |  | 2347.5 |  |  | 2315.5 |  |  | 2359.5 |  |  | 2171.5 |  |  | 2228 |  |  | 2261.5 |  |  | 2231.5 |  |  | 2192.5 |  |  | 2307.5 |  |  | 2389.5 |  |  | 2253 |  |  | 2345.5 |  |  | 2384 |  |  | 2229 |  |  | 2198.5 |  |  | 2405.5 |  |  | 2237.5 |  |  | 2266 |  |  | 2325.5 |  |  | 2345.5 |  |  | 2284.5 |  |  | 2165 |  |  | 2278.5 |  |  | 2126.5 |  |  | 2261.5 |  |  | 2180.5 |  |  | 2192.5 |  |  | 2203 |  |  | 2247.5 |  |  | 2356 |  |  | 2294.5 |  |  | 2129.5 |  |  | 2276.5 |  |  | 2327 |  |  | 2231.5 |  |  | 2251 |  |  | 2213 |  |  | 2250.5 |  |  | 2155.5 |  |  | 2209.5 |  |  | 2475.5 |  |  | 2454 |  |  | 2408.5 |  |  | 2251.5 |  |  | 2091.5 |  |  | 2263 |  |  | 2353.5 |  |  | 2244.5 |  |  | 2058.5 |  |  | 2277.5 |  |  | 2402 |  |  | 2181.5 |  |  | 2289.5 |  |  | 2291.5 |  |  | 2329.5 |  |  | 2262.5 |  |  | 2277.5 |  |  | 2417 |  |  | 2268.5 |  |  | 2188.5 |  |  | 2254 |  |  | 2193.5 |  |  | 2149.5 |  |  | 2293.5 |  |  | 2305 |  |  | 2329.5 |  |  | 2323.5 |  |  | 2305.5 |  |  | 2220.5 |  |  | 2348.5 |  |  | 2395 |  |  | 2264 |  |  | 2292.5 |  |  | 2384.5 |  |  | 2359.5 |  |  | 2143.5 |  |  | 2115 |  |  | 2360 |  |  | 2227 |  |  | 2395.5 |  |  | 2273 |  |  | 2335.5 |  |  | 2397.5 |  |  | 2338 |  |  | 2188.5 |  |  | 2325.5 |  |  | 2275.5 |  |  | 2346.5 |  |  | 2072.5 |  |  | 2292 |  |  | 2343 |  |  | 2175.5 |  |  | 2359.5 |  |  | 2230 |  |  | 2203.5 |  |  | 2279.5 |  |  | 2258 |  |  | 2418.5 |  |  | 2387.5 |  |  | 2225 |  |  | 2334.5 |  |  | 2319.5 |  |  | 2362 |  |  | 2214.5 |  |  | 2196 |  |  | 2446.5 |  |  | 2437 |  |  | 2227.5 |  |  | 2198.5 |  |  | 2260.5 |  |  | 2277.5 |  |  | 2313.5 |  |  | 2195.5 |  |  | 2344 |  |  | 2218.5 |  |  | 2325.5 |  |  | 2227.5 |  |  | 2262.5 |  |  | 2291.5 |  |  | 2238 |  |  | 2221.5 |  |  | 2295 |  |  | 2276.5 |  |  | 2181.5 |  |  | 2343.5 |  |  | 2292.5 |  |  | 2320.5 |  |  | 2271.5 |  |  | 2231.5 |  |  | 2334.5 |  |  | 2183.5 |  |  | 2213 |  |  | 2329.5 |  |  | 2202 |  |  | 2316 |  |  | 2307.5 |  |  | 2097 |  |  | 2140.5 |  |  | 2328.5 |  |  | 2358.5 |  |  | 2313.5 |  |  | 2396.5 |  |  | 2336.5 |  |  | 2319.5 |  |  | 2236 |  |  | 2422 |  |  | 2195.5 |  |  | 2261.5 |  |  | 2265 |  |  | 2194.5 |  |  | 2228.5 |  |  | 2221.5 |  |  | 2212.5 |  |  | 2244.5 |  |  | 2187 |  |  | 2272.5 |  |  | 2270.5 |  |  | 2204.5 |  |  | 2236 |  |  | 2360.5 |  |  | 2331.5 |  |  | 2287.5 |  |  | 2521.5 |  |  | 2311.5 |  |  | 2222.5 |  |  | 2358.5 |  |  | 1943.5 |  |  | 2278.5 |  |  | 2167 |  |  | 2395.5 |  |  | 2332.5 |  |  | 2374.5 |  |  | 2175.5 |  |  | 2224.5 |  |  | 2224.5 |  |  | 2211.5 |  |  | 2122 |  |  | 2215.5 |  |  | 2290.5 |  |  | 2318.5 |  |  | 2289 |  |  | 2333.5 |  |  | 2194 |  |  | 2113.5 |  |  | 2300.5 |  |  | 2188.5 |  |  | 2343 |  |  | 2148.5 |  |  | 2270 |  |  | 2264 |  |  | 2327.5 |  |  | 2291 |  |  | 2436 |  |  | 2362.5 |  |  | 2354.5 |  |  | 2161.5 |  |  | 2325 |  |  | 2345.5 |  |  | 2194.5 |  |  | 2159.5 |  |  | 2405.5 |  |  | 2252.5 |  |  | 2259.5 |  |  | 2246.5 |  |  | 2316.5 |  |  | 2253 |  |  | 2458.5 |  |  | 2225 |  |  | 2275.5 |  |  | 2197.5 |  |  | 2414.5 |  |  | 2278 |  |  | 2356 |  |  | 2425 |  |  | 2284.5 |  |  | 2273 |  |  | 2343.5 |  |  | 2407.5 |  |  | 2277.5 |  |  | 2284.5 |  |  | 2173.5 |  |  | 2384.5 |  |  | 2400.5 |  |  | 2378.5 |  |  | 2333 |  |  | 2173.5 |  |  | 2154.5 |  |  | 2297.5 |  |  | 2209.5 |  |  | 2196 |  |  | 2267.5 |  |  | 2354 |  |  | 2288.5 |  |  | 2325.5 |  |  | 2246.5 |  |  | 2183.5 |  |  | 2133 |  |  | 2250.5 |  |  | 2038 |  |  | 2245.5 |  |  | 2321.5 |  |  | 2431.5 |  |  | 2262.5 |  |  | 2271.5 |  |  | 2357.5 |  |  | 2197.5 |  |  | 2317.5 |  |  | 2278.5 |  |  | 2189 |  |  | 2323.5 |  |  | 2266.5 |  |  | 2241.5 |  |  | 2357.5 |  |  | 2352.5 |  |  | 2234 |  |  | 2212 |  |  | 2280.5 |  |  | 2266 |  |  | 2432.5 |  |  | 2217.5 |  |  | 2425.5 |  |  | 2344.5 |  |  | 2263.5 |  |  | 2364.5 |  |  | 2272.5 |  |  | 2342.5 |  |  | 2298 |  |  | 2282.5 |  |  | 2483.5 |  |  | 2253.5 |  |  | 2160 |  |  | 2277.5 |  |  | 2234.5 |  |  | 2390 |  |  | 2227 |  |  | 2299.5 |  |  | 2216 |  |  | 2086 |  |  | 2164.5 |  |  | 2362 |  |  | 2461.5 |  |  | 2253.5 |  |  | 2408.5 |  |  | 2279.5 |  |  | 2196.5 |  |  | 2230.5 |  |  | 2084.5 |  |  | 2230.5 |  |  | 2284.5 |  |  | 2213.5 |  |  | 2196 |  |  | 2195 |  |  | 2362.5 |  |  | 2388.5 |  |  | 2243.5 |  |  | 2326.5 |  |  | 2290.5 |  |  | 2301.5 |  |  | 2314.5 |  |  | 2214.5 |  |  | 2530 |  |  | 2241.5 |  |  | 2249 |  |  | 2195.5 |  |  | 2423.5 |  |  | 2375.5 |  |  | 2425 |  |  | 2277.5 |  |  | 2229.5 |  |  | 2334 |  |  | 2330.5 |  |  | 2243.5 |  |  | 2341.5 |  |  | 2302.5 |  |  | 2248.5 |  |  | 2313.5 |  |  | 2335 |  |  | 2266.5 |  |  | 2253.5 |  |  | 2395.5 |  |  | 2350.5 |  |  | 2290 |  |  | 2296.5 |  |  | 2384.5 |  |  | 2264 |  |  | 2323.5 |  |  | 2396.5 |  |  | 2347 |  |  | 2381.5 |  |  | 2376.5 |  |  | 2238.5 |  |  | 2241 |  |  | 2129.5 |  |  | 2290.5 |  |  | 2229 |  |  | 2318.5 |  |  | 2324.5 |  |  | 2270.5 |  |  | 2086.5 |  |  | 2348.5 |  |  | 2393.5 |  |  | 2233.5 |  |  | 2298 |  |  | 2239 |  |  | 2120.5 |  |  | 2366.5 |  |  | 2158.5 |  |  | 2347 |  |  | 2457.5 |  |  | 2228.5 |  |  | 2259.5 |  |  | 2164.5 |  |  | 2292.5 |  |  | 2366.5 |  |  | 2199.5 |  |  | 2299.5 |  |  | 2082.5 |  |  | 2318 |  |  | 2238.5 |  |  | 2129.5 |  |  | 2245.5 |  |  | 2331.5 |  |  | 2419.5 |  |  | 2331.5 |  |  | 2325.5 |  |  | 2314.5 |  |  | 2151.5 |  |  | 2392.5 |  |  | 2269.5 |  |  | 2192.5 |  |  | 2288.5 |  |  | 2396 |  |  | 2286.5 |  |  | 2335.5 |  |  | 2247 |  |  | 2340.5 |  |  | 2320.5 |  |  | 2400 |  |  | 2340.5 |  |  | 2399.5 |  |  | 2469.5 |  |  | 2420 |  |  | 2222.5 |  |  | 2385.5 |  |  | 2293.5 |  |  | 2109.5 |  |  | 2336.5 |  |  | 2206 |  |  | 2238.5 |  |  | 2333 |  |  | 2338 |  |  | 2380.5 |  |  | 2305.5 |  |  | 2199.5 |  |  | 2057.5 |  |  | 2226.5 |  |  | 2327.5 |  |  | 2218 |  |  | 2244.5 |  |  | 2247 |  |  | 2260.5 |  |  | 2290 |  |  | 2235 |  |  | 2399 |  |  | 2332.5 |  |  | 2190 |  |  | 2417.5 |  |  | 2341.5 |  |  | 2280.5 |  |  | 2469.5 |  |  | 2207.5 |  |  | 2402 |  |  | 2305.5 |  |  | 2381.5 |  |  | 2475.5 |  |  | 2282 |  |  | 2316.5 |  |  | 2210.5 |  |  | 2314.5 |  |  | 2373.5 |  |  | 2268 |  |  | 2360 |  |  | 2258 |  |  | 2277.5 |  |  | 2377 |  |  | 2349 |  |  | 2366.5 |  |  | 2180.5 |  |  | 2170.5 |  |  | 2319.5 |  |  | 2314.5 |  |  | 2288.5 |  |  | 2417.5 |  |  | 2266.5 |  |  | 2234.5 |  |  | 2197 |  |  | 2252.5 |  |  | 2194 |  |  | 2289.5 |  |  | 2302.5 |  |  | 2301.5 |  |  | 2323.5 |  |  | 2382 |  |  | 2369.5 |  |  | 2324 |  |  | 2246.5 |  |  | 2329.5 |  |  | 2204 |  |  | 2268 |  |  | 2331.5 |  |  | 2318 |  |  | 2327.5 |  |  | 2158.5 |  |  | 2210.5 |  |  | 2229.5 |  |  | 2360.5 |  |  | 2346.5 |  |  | 2194.5 |  |  | 2217 |  |  | 2351.5 |  |  | 2337.5 |  |  | 2293.5 |  |  | 2337.5 |  |  | 2216.5 |  |  | 2326.5 |  |  | 2421.5 |  |  | 2313.5 |  |  | 2411.5 |  |  | 2397.5 |  |  | 2186.5 |  |  | 2184.5 |  |  | 2272 |  |  | 2183.5 |  |  | 2237.5 |  |  | 2373 |  |  | 2212.5 |  |  | 2207.5 |  |  | 2264.5 |  |  | 2205.5 |  |  | 2468 |  |  | 2442.5 |  |  | 2223.5 |  |  | 2168.5 |  |  | 2401.5 |  |  | 2231 |  |  | 2207.5 |  |  | 2409.5 |  |  | 2247.5 |  |  | 2371.5 |  |  | 2199.5 |  |  | 2171.5 |  |  | 2393.5 |  |  | 2290.5 |  |  | 2317.5 |  |  | 2307.5 |  |  | 2346.5 |  |  | 2367 |  |  | 2331.5 |  |  | 2220.5 |  |  | 2366.5 |  |  | 2360.5 |  |  | 2170.5 |  |  | 2302.5 |  |  | 2360 |  |  | 2349.5 |  |  | 2215 |  |  | 2176.5 |  |  | 2351.5 |  |  | 2342.5 |  |  | 2305 |  |  | 2211 |  |  | 2336.5 |  |  | 2360.5 |  |  | 2090.5 |  |  | 2411.5 |  |  | 2299.5 |  |  | 2296.5 |  |  | 2236.5 |  |  | 2370.5 |  |  | 2218.5 |  |  | 2405.5 |  |  | 2272.5 |  |  | 2365.5 |  |  | 2193.5 |  |  | 2283.5 |  |  | 2407.5 |  |  | 2278.5 |  |  | 2265.5 |  |  | 2332.5 |  |  | 2283.5 |  |  | 2270.5 |  |  | 2352.5 |  |  | 2338.5 |  |  | 2335 |  |  | 2386.5 |  |  | 2288.5 |  |  | 2303.5 |  |  | 2291 |  |  | 2308.5 |  |  | 2278.5 |  |  | 2359.5 |  |  | 2309.5 |  |  | 2335 |  |  | 2126.5 |  |  | 2199.5 |  |  | 2182 |  |  | 2270 |  |  | 2243 |  |  | 2264.5 |  |  | 2273.5 |  |  | 2338.5 |  |  | 2512.5 |  |  | 2352 |  |  | 2323.5 |  |  | 2278.5 |  |  | 2190 |  |  | 2241 |  |  | 2316.5 |  |  | 2370.5 |  |  | 2357 |  |  | 2317.5 |  |  | 2394 |  |  | 2219.5 |  |  | 2199.5 |  |  | 2427 |  |  | 2371.5 |  |  | 2309.5 |  |  | 2147.5 |  |  | 2402 |  |  | 2196.5 |  |  | 2223.5 |  |  | 2218.5 |  |  | 2259.5 |  |  | 2278.5 |  |  | 2342.5 |  |  | 2213.5 |  |  | 2337.5 |  |  | 2362.5 |  |  | 2299.5 |  |  | 2260 |  |  | 2304.5 |  |  | 2320.5 |  |  | 2376.5 |  |  | 2392.5 |  |  | 2282.5 |  |  | 2317.5 |  |  | 2412.5 |  |  | 2280.5 |  |  | 2436 |  |  | 2230.5 |  |  | 2263 |  |  | 2489.5 |  |  | 2508.5 |  |  | 2517.5 |  |  | 2203.5 |  |  | 2233.5 |  |  | 2319.5 |  |  | 2199.5 |  |  | 2356.5 |  |  | 2302 |  |  | 2213.5 |  |  | 2314 |  |  | 2173.5 |  |  | 2203.5 |  |  | 2305.5 |  |  | 2340 |  |  | 2231.5 |  |  | 2323.5 |  |  | 2068 |  |  | 2253.5 |  |  | 2294 |  |  | 2314.5 |  |  | 2226.5 |  |  | 2209.5 |  |  | 2295 |  |  | 2374.5 |  |  | 2492.5 |  |  | 2184 |  |  | 2451.5 |  |  | 2274.5 |  |  | 2313 |  |  | 2276.5 |  |  | 2462.5 |  |  | 2401.5 |  |  | 2393.5 |  |  | 2208.5 |  |  | 2407.5 |  |  | 2181.5 |  |  | 2297.5 |  |  | 2190.5 |  |  | 2179.5 |  |  | 2445.5 |  |  | 2404 |  |  | 2340 |  |  | 2397.5 |  |  | 2289.5 |  |  | 2346
79 |  | 2301.5 |  |  | 2453.5 |  |  | 2342 |  |  | 2300.5 |  |  | 2473.5 |  |  | 2328.5 |  |  | 2400.5 |  |  | 2326.5 |  |  | 2330.5 |  |  | 2308.5 |  |  | 2238 |  |  | 2408.5 |  |  | 2375.5 |  |  | 2204.5 |  |  | 2142 |  |  | 2407.5 |  |  | 2439.5 |  |  | 2309.5 |  |  | 2423.5 |  |  | 2235.5 |  |  | 2418.5 |  |  | 2343.5 |  |  | 2415.5 |  |  | 2228.5 |  |  | 2171 |  |  | 2404.5 |  |  | 2351.5 |  |  | 2278.5 |  |  | 2407.5 |  |  | 2203 |  |  | 2354 |  |  | 2454.5 |  |  | 2161.5 |  |  | 2382.5 |  |  | 2199.5 |  |  | 2380 |  |  | 2266.5 |  |  | 2471 |  |  | 2326.5 |  |  | 2325.5 |  |  | 2145.5 |  |  | 2349.5 |  |  | 2181.5 |  |  | 2349 |  |  | 2525.5 |  |  | 2447 |  |  | 2312.5 |  |  | 2416.5 |  |  | 2381.5 |  |  | 2333.5 |  |  | 2233.5 |  |  | 2361.5 |  |  | 2356.5 |  |  | 2265.5 |  |  | 2384.5 |  |  | 2390.5 |  |  | 2222.5 |  |  | 2321 |  |  | 2385.5 |  |  | 2330.5 |  |  | 2315 |  |  | 2293.5 |  |  | 2363.5 |  |  | 2243.5 |  |  | 2211.5 |  |  | 2370 |  |  | 2434.5 |  |  | 2240 |  |  | 2197.5 |  |  | 2374.5 |  |  | 2324 |  |  | 2276.5 |  |  | 2330.5 |  |  | 2474.5 |  |  | 2415 |  |  | 2404 |  |  | 2241.5 |  |  | 2259.5 |  |  | 2202.5 |  |  | 2344.5 |  |  | 2285 |  |  | 2349.5 |  |  | 2368.5 |  |  | 2418.5 |  |  | 2422.5 |  |  | 2275.5 |  |  | 2432.5 |  |  | 2320.5 |  |  | 2318.5 |  |  | 2353.5 |  |  | 2334.5 |  |  | 2358 |  |  | 2251.5 |  |  | 2230 |  |  | 2278 |  |  | 2239 |  |  | 2493.5 |  |  | 2450.5 |  |  | 2207.5 |  |  | 2473.5 |  |  | 2254.5 |  |  | 2276 |  |  | 2284 |  |  | 2279.5 |  |  | 2253.5 |  |  | 2251.5 |  |  | 2360.5 |  |  | 2447.5 |  |  | 2412.5 |  |  | 2389.5 |  |  | 2434.5 |  |  | 2417.5 |  |  | 2298.5 |  |  | 2341.5 |  |  | 2378.5 |  |  | 2338.5 |  |  | 2432.5 |  |  | 2237.5 |  |  | 2302.5 |  |  | 2265.5 |  |  | 2345.5 |  |  | 2423.5 |  |  | 2341.5 |  |  | 2347.5 |  |  | 2303.5 |  |  | 2317 |  |  | 2287.5 |  |  | 2287.5 |  |  | 2227.5 |  |  | 2306.5 |  |  | 2385.5 |  |  | 2350 |  |  | 2257.5 |  |  | 2424.5 |  |  | 2268.5 |  |  | 2229.5 |  |  | 2389 |  |  | 2326.5 |  |  | 2406.5 |  |  | 2243 |  |  | 2368.5 |  |  | 2191 |  |  | 2418 |  |  | 2443.5 |  |  | 2364 |  |  | 2451.5 |  |  | 2242.5 |  |  | 2333.5 |  |  | 2242.5 |  |  | 2337.5 |  |  | 2337.5 |  |  | 2314.5 |  |  | 2351.5 |  |  | 2453.5 |  |  | 2353.5 |  |  | 2424 |  |  | 2264.5 |  |  | 2212 |  |  | 2292.5 |  |  | 2334.5 |  |  | 2256 |  |  | 2325.5 |  |  | 2275.5 |  |  | 2281.5 |  |  | 2198 |  |  | 2317.5 |  |  | 2196.5 |  |  | 2196.5 |  |  | 2415.5 |  |  | 2300.5 |  |  | 2278.5 |  |  | 2297 |  |  | 2301.5 |  |  | 2287.5 |  |  | 2216.5 |  |  | 2314.5 |  |  | 2346.5 |  |  | 2366.5 |  |  | 2259.5 |  |  | 2374 |  |  | 2368.5 |  |  | 2345.5 |  |  | 2407.5 |  |  | 2378.5 |  |  | 2271.5 |  |  | 2442.5 |  |  | 2379.5 |  |  | 2271.5 |  |  | 2447.5 |  |  | 2257.5 |  |  | 2377.5 |  |  | 2133.5 |  |  | 2142.5 |  |  | 2227 |  |  | 2280.5 |  |  | 2325.5 |  |  | 2299.5 |  |  | 2389.5 |  |  | 2431.5 |  |  | 2427.5 |  |  | 2413.5 |  |  | 2312.5 |  |  | 2329.5 |  |  | 2303.5 |  |  | 2231.5 |  |  | 2434.5 |  |  | 2323.5 |  |  | 2292.5 |  |  | 2299.5 |  |  | 2306.5 |  |  | 2378 |  |  | 2431.5 |  |  | 2314.5 |  |  | 2064 |  |  | 2496.5 |  |  | 2458 |  |  | 2182.5 |  |  | 2362.5 |  |  | 2412.5 |  |  | 2413.5 |  |  | 2316.5 |  |  | 2319.5 |  |  | 2300.5 |  |  | 2151.5 |  |  | 2193 |  |  | 2263.5 |  |  | 2128.5 |  |  | 2362.5 |  |  | 2237.5 |  |  | 2354 |  |  | 2280.5 |  |  | 2303.5 |  |  | 2442.5 |  |  | 2311.5 |  |  | 2444.5 |  |  | 2323.5 |  |  | 2296.5 |  |  | 2450.5 |  |  | 2445 |  |  | 2374 |  |  | 2308.5 |  |  | 2249.5 |  |  | 2326.5 |  |  | 2301 |  |  | 2459.5 |  |  | 2309.5 |  |  | 2272.5 |  |  | 2191 |  |  | 2421.5 |  |  | 2317.5 |  |  | 2171.5 |  |  | 2230.5 |  |  | 2293.5 |  |  | 2345.5 |  |  | 2372.5 |  |  | 2349.5 |  |  | 2464.5 |  |  | 2145 |  |  | 2253.5 |  |  | 2401.5 |  |  | 2369.5 |  |  | 2317.5 |  |  | 2256.5 |  |  | 2479 |  |  | 2238.5 |  |  | 2391.5 |  |  | 2383 |  |  | 2456.5 |  |  | 2307.5 |  |  | 2558 |  |  | 2383.5 |  |  | 2388.5 |  |  | 2450.5 |  |  | 2277.5 |  |  | 2322 |  |  | 2341 |  |  | 2327.5 |  |  | 2245.5 |  |  | 2371.5 |  |  | 2317.5 |  |  | 2460.5 |  |  | 2373.5 |  |  | 2323 |  |  | 2322.5 |  |  | 2265.5 |  |  | 2304 |  |  | 2313.5 |  |  | 2143.5 |  |  | 2327 |  |  | 2393.5 |  |  | 2196.5 |  |  | 2378.5 |  |  | 2345 |  |  | 2361.5 |  |  | 2241 |  |  | 2407.5 |  |  | 2253.5 |  |  | 2342.5 |  |  | 2307 |  |  | 2255.5 |  |  | 2432.5 |  |  | 2420.5 |  |  | 2331 |  |  | 2287.5 |  |  | 2165.5 |  |  | 2447.5 |  |  | 2463.5 |  |  | 2305.5 |  |  | 2365 |  |  | 2270.5 |  |  | 2384.5 |  |  | 2373.5 |  |  | 2262 |  |  | 2365 |  |  | 2489.5 |  |  | 2275.5 |  |  | 2176.5 |  |  | 2349.5 |  |  | 2297.5 |  |  | 2336.5 |  |  | 2330.5 |  |  | 2404.5 |  |  | 2260.5 |  |  | 2341.5 |  |  | 2341 |  |  | 2305.5 |  |  | 2364.5 |  |  | 2535.5 |  |  | 2435.5 |  |  | 2357 |  |  | 2301.5 |  |  | 2465.5 |  |  | 2306.5 |  |  | 2184.5 |  |  | 2451.5 |  |  | 2176 |  |  | 2358 |  |  | 2223 |  |  | 2385 |  |  | 2248.5 |  |  | 2373 |  |  | 2292.5 |  |  | 2341 |  |  | 2327.5 |  |  | 2448.5 |  |  | 2329.5 |  |  | 2307.5 |  |  | 2289.5 |  |  | 2352 |  |  | 2348.5 |  |  | 2441.5 |  |  | 2295.5 |  |  | 2335 |  |  | 2413.5 |  |  | 2308.5 |  |  | 2287.5 |  |  | 2351 |  |  | 2265.5 |  |  | 2220.5 |  |  | 2389.5 |  |  | 2259.5 |  |  | 2339.5 |  |  | 2253.5 |  |  | 2376.5 |  |  | 2330.5 |  |  | 2385.5 |  |  | 2210.5 |  |  | 2267 |  |  | 2290.5 |  |  | 2278.5 |  |  | 2218.5 |  |  | 2354.5 |  |  | 2436.5 |  |  | 2292 |  |  | 2384.5 |  |  | 2423 |  |  | 2253 |  |  | 2224.5 |  |  | 2426.5 |  |  | 2252.5 |  |  | 2305 |  |  | 2372.5 |  |  | 2369.5 |  |  | 2323.5 |  |  | 2189 |  |  | 2293.5 |  |  | 2150.5 |  |  | 2287.5 |  |  | 2227.5 |  |  | 2231.5 |  |  | 2227 |  |  | 2276.5 |  |  | 2385 |  |  | 2341.5 |  |  | 2155.5 |  |  | 2300.5 |  |  | 2342 |  |  | 2270.5 |  |  | 2290 |  |  | 2239 |  |  | 2289.5 |  |  | 2202.5 |  |  | 2248.5 |  |  | 2499.5 |  |  | 2483 |  |  | 2429.5 |  |  | 2290.5 |  |  | 2112.5 |  |  | 2289 |  |  | 2379.5 |  |  | 2265.5 |  |  | 2097.5 |  |  | 2324.5 |  |  | 2449 |  |  | 2220.5 |  |  | 2304.5 |  |  | 2330.5 |  |  | 2353.5 |  |  | 2277.5 |  |  | 2306.5 |  |  | 2456 |  |  | 2283.5 |  |  | 2214.5 |  |  | 2269 |  |  | 2232.5 |  |  | 2188.5 |  |  | 2319.5 |  |  | 2326 |  |  | 2368.5 |  |  | 2338.5 |  |  | 2329.5 |  |  | 2244.5 |  |  | 2363.5 |  |  | 2421 |  |  | 2285 |  |  | 2307.5 |  |  | 2410.5 |  |  | 2380.5 |  |  | 2164.5 |  |  | 2130 |  |  | 2399 |  |  | 2253 |  |  | 2421.5 |  |  | 2312 |  |  | 2364.5 |  |  | 2444.5 |  |  | 2353 |  |  | 2235.5 |  |  | 2346.5 |  |  | 2296.5 |  |  | 2385.5 |  |  | 2087.5 |  |  | 2331 |  |  | 2382 |  |  | 2222.5 |  |  | 2398.5 |  |  | 2256 |  |  | 2227.5 |  |  | 2318.5 |  |  | 2297 |  |  | 2439.5 |  |  | 2426.5 |  |  | 2264 |  |  | 2355.5 |  |  | 2358.5 |  |  | 2409 |  |  | 2253.5 |  |  | 2220 |  |  | 2493.5 |  |  | 2463 |  |  | 2251.5 |  |  | 2237.5 |  |  | 2275.5 |  |  | 2316.5 |  |  | 2339.5 |  |  | 2216.5 |  |  | 2368 |  |  | 2239.5 |  |  | 2340.5 |  |  | 2242.5 |  |  | 2291.5 |  |  | 2330.5 |  |  | 2267 |  |  | 2260.5 |  |  | 2319 |  |  | 2300.5 |  |  | 2207.5 |  |  | 2372.5 |  |  | 2331.5 |  |  | 2359.5 |  |  | 2292.5 |  |  | 2257.5 |  |  | 2381.5 |  |  | 2222.5 |  |  | 2242 |  |  | 2355.5 |  |  | 2241 |  |  | 2345 |  |  | 2336.5 |  |  | 2112 |  |  | 2187.5 |  |  | 2357.5 |  |  | 2387.5 |  |  | 2334.5 |  |  | 2425.5 |  |  | 2357.5 |  |  | 2345.5 |  |  | 2257 |  |  | 2451 |  |  | 2219.5 |  |  | 2308.5 |  |  | 2304 |  |  | 2241.5 |  |  | 2249.5 |  |  | 2260.5 |  |  | 2236.5 |  |  | 2283.5 |  |  | 2202 |  |  | 2311.5 |  |  | 2294.5 |  |  | 2233.5 |  |  | 2275 |  |  | 2389.5 |  |  | 2370.5 |  |  | 2326.5 |  |  | 2536.5 |  |  | 2350.5 |  |  | 2269.5 |  |  | 2405.5 |  |  | 1958.5 |  |  | 2304.5 |  |  | 2196 |  |  | 2442.5 |  |  | 2347.5 |  |  | 2413.5 |  |  | 2201.5 |  |  | 2263.5 |  |  | 2253.5 |  |  | 2237.5 |  |  | 2137 |  |  | 2236.5 |  |  | 2311.5 |  |  | 2333.5 |  |  | 2315 |  |  | 2372.5 |  |  | 2223 |  |  | 2142.5 |  |  | 2326.5 |  |  | 2227.5 |  |  | 2367 |  |  | 2187.5 |  |  | 2285 |  |  | 2285 |  |  | 2356.5 |  |  | 2315 |  |  | 2457 |  |  | 2391.5 |  |  | 2378.5 |  |  | 2190.5 |  |  | 2349 |  |  | 2369.5 |  |  | 2215.5 |  |  | 2198.5 |  |  | 2431.5 |  |  | 2278.5 |  |  | 2283.5 |  |  | 2285.5 |  |  | 2340.5 |  |  | 2268 |  |  | 2497.5 |  |  | 2264 |  |  | 2301.5 |  |  | 2221.5 |  |  | 2435.5 |  |  | 2317 |  |  | 2377 |  |  | 2454 |  |  | 2313.5 |  |  | 2288 |  |  | 2372.5 |  |  | 2446.5 |  |  | 2324.5 |  |  | 2299.5 |  |  | 2212.5 |  |  | 2423.5 |  |  | 2426.5 |  |  | 2425.5 |  |  | 2348 |  |  | 2188.5 |  |  | 2169.5 |  |  | 2321.5 |  |  | 2256.5 |  |  | 2225 |  |  | 2314.5 |  |  | 2369 |  |  | 2317.5 |  |  | 2364.5 |  |  | 2267.5 |  |  | 2212.5 |  |  | 2162 |  |  | 2274.5 |  |  | 2064 |  |  | 2266.5 |  |  | 2347.5 |  |  | 2457.5 |  |  | 2309.5 |  |  | 2310.5 |  |  | 2372.5 |  |  | 2236.5 |  |  | 2332.5 |  |  | 2317.5 |  |  | 2213 |  |  | 2370.5 |  |  | 2290.5 |  |  | 2288.5 |  |  | 2372.5 |  |  | 2391.5 |  |  | 2249 |  |  | 2227 |  |  | 2301.5 |  |  | 2305 |  |  | 2453.5 |  |  | 2246.5 |  |  | 2446.5 |  |  | 2359.5 |  |  | 2284.5 |  |  | 2390.5 |  |  | 2319.5 |  |  | 2371.5 |  |  | 2345 |  |  | 2329.5 |  |  | 2522.5 |  |  | 2277.5 |  |  | 2175 |  |  | 2316.5 |  |  | 2273.5 |  |  | 2429 |  |  | 2248 |  |  | 2320.5 |  |  | 2255 |  |  | 2125 |  |  | 2185.5 |  |  | 2401 |  |  | 2508.5 |  |  | 2282.5 |  |  | 2437.5 |  |  | 2318.5 |  |  | 2225.5 |  |  | 2269.5 |  |  | 2131.5 |  |  | 2256.5 |  |  | 2323.5 |  |  | 2252.5 |  |  | 2211 |  |  | 2216 |  |  | 2401.5 |  |  | 2435.5 |  |  | 2267.5 |  |  | 2365.5 |  |  | 2311.5 |  |  | 2340.5 |  |  | 2343.5 |  |  | 2261.5 |  |  | 2577 |  |  | 2262.5 |  |  | 2296 |  |  | 2221.5 |  |  | 2449.5 |  |  | 2399.5 |  |  | 2451 |  |  | 2316.5 |  |  | 2255.5 |  |  | 2363 |  |  | 2369.5 |  |  | 2269.5 |  |  | 2362.5 |  |  | 2317.5 |  |  | 2287.5 |  |  | 2337.5 |  |  | 2350 |  |  | 2305.5 |  |  | 2292.5 |  |  | 2424.5 |  |  | 2371.5 |  |  | 2337 |  |  | 2343.5 |  |  | 2410.5 |  |  | 2288 |  |  | 2349.5 |  |  | 2425.5 |  |  | 2376 |  |  | 2396.5 |  |  | 2415.5 |  |  | 2277.5 |  |  | 2265 |  |  | 2158.5 |  |  | 2316.5 |  |  | 2255 |  |  | 2365.5 |  |  | 2350.5 |  |  | 2291.5 |  |  | 2133.5 |  |  | 2377.5 |  |  | 2417.5 |  |  | 2254.5 |  |  | 2313 |  |  | 2260 |  |  | 2149.5 |  |  | 2413.5 |  |  | 2187.5 |  |  | 2394 |  |  | 2486.5 |  |  | 2257.5 |  |  | 2298.5 |  |  | 2185.5 |  |  | 2331.5 |  |  | 2381.5 |  |  | 2223.5 |  |  | 2338.5 |  |  | 2129.5 |  |  | 2342 |  |  | 2262.5 |  |  | 2144.5 |  |  | 2284.5 |  |  | 2370.5 |  |  | 2443.5 |  |  | 2360.5 |  |  | 2340.5 |  |  | 2343.5 |  |  | 2180.5 |  |  | 2439.5 |  |  | 2295.5 |  |  | 2239.5 |  |  | 2303.5 |  |  | 2417 |  |  | 2315.5 |  |  | 2364.5 |  |  | 2286 |  |  | 2369.5 |  |  | 2359.5 |  |  | 2424 |  |  | 2379.5 |  |  | 2423.5 |  |  | 2498.5 |  |  | 2446 |  |  | 2246.5 |  |  | 2409.5 |  |  | 2332.5 |  |  | 2124.5 |  |  | 2375.5 |  |  | 2227 |  |  | 2259.5 |  |  | 2380 |  |  | 2367 |  |  | 2395.5 |  |  | 2344.5 |  |  | 2223.5 |  |  | 2096.5 |  |  | 2247.5 |  |  | 2374.5 |  |  | 2239 |  |  | 2291.5 |  |  | 2286 |  |  | 2286.5 |  |  | 2337 |  |  | 2259 |  |  | 2414 |  |  | 2371.5 |  |  | 2237 |  |  | 2456.5 |  |  | 2380.5 |  |  | 2327.5 |  |  | 2495.5 |  |  | 2233.5 |  |  | 2426 |  |  | 2344.5 |  |  | 2396.5 |  |  | 2514.5 |  |  | 2297 |  |  | 2340.5 |  |  | 2257.5 |  |  | 2353.5 |  |  | 2397.5 |  |  | 2315 |  |  | 2384 |  |  | 2273 |  |  | 2292.5 |  |  | 2416 |  |  | 2370 |  |  | 2381.5 |  |  | 2227.5 |  |  | 2217.5 |  |  | 2358.5 |  |  | 2329.5 |  |  | 2314.5 |  |  | 2446.5 |  |  | 2305.5 |  |  | 2258.5 |  |  | 2226 |  |  | 2278.5 |  |  | 2215 |  |  | 2328.5 |  |  | 2323.5 |  |  | 2340.5 |  |  | 2362.5 |  |  | 2421 |  |  | 2393.5 |  |  | 2350 |  |  | 2261.5 |  |  | 2355.5 |  |  | 2219 |  |  | 2283 |  |  | 2370.5 |  |  | 2347 |  |  | 2342.5 |  |  | 2197.5 |  |  | 2231.5 |  |  | 2244.5 |  |  | 2375.5 |  |  | 2385.5 |  |  | 2220.5 |  |  | 2256 |  |  | 2377.5 |  |  | 2363.5 |  |  | 2332.5 |  |  | 2363.5 |  |  | 2255.5 |  |  | 2365.5 |  |  | 2468.5 |  |  | 2339.5 |  |  | 2450.5 |  |  | 2436.5 |  |  | 2210.5 |  |  | 2210.5 |  |  | 2311 |  |  | 2222.5 |  |  | 2258.5 |  |  | 2399 |  |  | 2233.5 |  |  | 2228.5 |  |  | 2293.5 |  |  | 2231.5 |  |  | 2515 |  |  | 2466.5 |  |  | 2270.5 |  |  | 2192.5 |  |  | 2440.5 |  |  | 2246 |  |  | 2246.5 |  |  | 2430.5 |  |  | 2271.5 |  |  | 2386.5 |  |  | 2246.5 |  |  | 2200.5 |  |  | 2440.5 |  |  | 2319.5 |  |  | 2332.5 |  |  | 2354.5 |  |  | 2367.5 |  |  | 2391 |  |  | 2360.5 |  |  | 2267.5 |  |  | 2392.5 |  |  | 2386.5 |  |  | 2199.5 |  |  | 2317.5 |  |  | 2399 |  |  | 2370.5 |  |  | 2241 |  |  | 2215.5 |  |  | 2398.5 |  |  | 2357.5 |  |  | 2320 |  |  | 2237 |  |  | 2362.5 |  |  | 2386.5 |  |  | 2105.5 |  |  | 2450.5 |  |  | 2328.5 |  |  | 2335.5 |  |  | 2260.5 |  |  | 2391.5 |  |  | 2257.5 |  |  | 2431.5 |  |  | 2301.5 |  |  | 2391.5 |  |  | 2219.5 |  |  | 2322.5 |  |  | 2431.5 |  |  | 2299.5 |  |  | 2304.5 |  |  | 2353.5 |  |  | 2298.5 |  |  | 2299.5 |  |  | 2391.5 |  |  | 2377.5 |  |  | 2356 |  |  | 2407.5 |  |  | 2314.5 |  |  | 2342.5 |  |  | 2306 |  |  | 2347.5 |  |  | 2307.5 |  |  | 2383.5 |  |  | 2333.5 |  |  | 2364 |  |  | 2173.5 |  |  | 2238.5 |  |  | 2208 |  |  | 2296 |  |  | 2290 |  |  | 2293.5 |  |  | 2312.5 |  |  | 2364.5 |  |  | 2538.5 |  |  | 2391 |  |  | 2362.5 |  |  | 2317.5 |  |  | 2205 |  |  | 2267 |  |  | 2355.5 |  |  | 2394.5 |  |  | 2404 |  |  | 2356.5 |  |  | 2423 |  |  | 2243.5 |  |  | 2238.5 |  |  | 2456 |  |  | 2395.5 |  |  | 2356.5 |  |  | 2168.5 |  |  | 2423 |  |  | 2217.5 |  |  | 2249.5 |  |  | 2242.5 |  |  | 2288.5 |  |  | 2317.5 |  |  | 2366.5 |  |  | 2239.5 |  |  | 2363.5 |  |  | 2409.5 |  |  | 2325.5 |  |  | 2299 |  |  | 2333.5 |  |  | 2346.5 |  |  | 2391.5 |  |  | 2431.5 |  |  | 2308.5 |  |  | 2338.5 |  |  | 2438.5 |  |  | 2295.5 |  |  | 2451 |  |  | 2269.5 |  |  | 2289 |  |  | 2515.5 |  |  | 2537.5 |  |  | 2546.5 |  |  | 2232.5 |  |  | 2248.5 |  |  | 2358.5 |  |  | 2246.5 |  |  | 2377.5 |  |  | 2341 |  |  | 2228.5 |  |  | 2340 |  |  | 2197.5 |  |  | 2232.5 |  |  | 2344.5 |  |  | 2355 |  |  | 2255.5 |  |  | 2370.5 |  |  | 2089 |  |  | 2274.5 |  |  | 2309 |  |  | 2353.5 |  |  | 2250.5 |  |  | 2248.5 |  |  | 2334 |  |  | 2413.5 |  |  | 2539.5 |  |  | 2208 |  |  | 2466.5 |  |  | 2295.5 |  |  | 2360 |  |  | 2323.5 |  |  | 2488.5 |  |  | 2422.5 |  |  | 2419.5 |  |  | 2223.5 |  |  | 2454.5 |  |  | 2228.5 |  |  | 2312.5 |  |  | 2216.5 |  |  | 2226.5 |  |  | 2466.5 |  |  | 2443 |  |  | 2361 |  |  | 2423.5 |  |  | 2315.5 |  |  | 2367
80 |  | 2316.5 |  |  | 2477.5 |  |  | 2381 |  |  | 2315.5 |  |  | 2512.5 |  |  | 2367.5 |  |  | 2424.5 |  |  | 2373.5 |  |  | 2345.5 |  |  | 2355.5 |  |  | 2264 |  |  | 2437.5 |  |  | 2401.5 |  |  | 2225.5 |  |  | 2171 |  |  | 2422.5 |  |  | 2463.5 |  |  | 2348.5 |  |  | 2462.5 |  |  | 2274.5 |  |  | 2457.5 |  |  | 2364.5 |  |  | 2441.5 |  |  | 2252.5 |  |  | 2200 |  |  | 2419.5 |  |  | 2390.5 |  |  | 2299.5 |  |  | 2446.5 |  |  | 2227 |  |  | 2369 |  |  | 2483.5 |  |  | 2185.5 |  |  | 2403.5 |  |  | 2238.5 |  |  | 2401 |  |  | 2305.5 |  |  | 2495 |  |  | 2365.5 |  |  | 2351.5 |  |  | 2171.5 |  |  | 2375.5 |  |  | 2228.5 |  |  | 2364 |  |  | 2540.5 |  |  | 2471 |  |  | 2338.5 |  |  | 2431.5 |  |  | 2420.5 |  |  | 2359.5 |  |  | 2248.5 |  |  | 2408.5 |  |  | 2371.5 |  |  | 2304.5 |  |  | 2423.5 |  |  | 2405.5 |  |  | 2237.5 |  |  | 2360 |  |  | 2400.5 |  |  | 2354.5 |  |  | 2339 |  |  | 2314.5 |  |  | 2392.5 |  |  | 2282.5 |  |  | 2258.5 |  |  | 2391 |  |  | 2473.5 |  |  | 2279 |  |  | 2226.5 |  |  | 2413.5 |  |  | 2353 |  |  | 2297.5 |  |  | 2354.5 |  |  | 2513.5 |  |  | 2454 |  |  | 2443 |  |  | 2262.5 |  |  | 2285.5 |  |  | 2249.5 |  |  | 2391.5 |  |  | 2324 |  |  | 2370.5 |  |  | 2415.5 |  |  | 2439.5 |  |  | 2437.5 |  |  | 2290.5 |  |  | 2456.5 |  |  | 2335.5 |  |  | 2347.5 |  |  | 2368.5 |  |  | 2358.5 |  |  | 2373 |  |  | 2280.5 |  |  | 2251 |  |  | 2307 |  |  | 2254 |  |  | 2519.5 |  |  | 2489.5 |  |  | 2233.5 |  |  | 2488.5 |  |  | 2269.5 |  |  | 2315 |  |  | 2305 |  |  | 2318.5 |  |  | 2300.5 |  |  | 2266.5 |  |  | 2384.5 |  |  | 2473.5 |  |  | 2438.5 |  |  | 2436.5 |  |  | 2458.5 |  |  | 2441.5 |  |  | 2324.5 |  |  | 2365.5 |  |  | 2393.5 |  |  | 2377.5 |  |  | 2453.5 |  |  | 2284.5 |  |  | 2341.5 |  |  | 2312.5 |  |  | 2371.5 |  |  | 2447.5 |  |  | 2388.5 |  |  | 2394.5 |  |  | 2324.5 |  |  | 2343 |  |  | 2316.5 |  |  | 2316.5 |  |  | 2251.5 |  |  | 2353.5 |  |  | 2432.5 |  |  | 2374 |  |  | 2286.5 |  |  | 2445.5 |  |  | 2292.5 |  |  | 2258.5 |  |  | 2415 |  |  | 2373.5 |  |  | 2435.5 |  |  | 2269 |  |  | 2389.5 |  |  | 2212 |  |  | 2433 |  |  | 2458.5 |  |  | 2390 |  |  | 2490.5 |  |  | 2289.5 |  |  | 2380.5 |  |  | 2266.5 |  |  | 2352.5 |  |  | 2376.5 |  |  | 2353.5 |  |  | 2398.5 |  |  | 2468.5 |  |  | 2392.5 |  |  | 2445 |  |  | 2303.5 |  |  | 2227 |  |  | 2307.5 |  |  | 2360.5 |  |  | 2295 |  |  | 2340.5 |  |  | 2304.5 |  |  | 2320.5 |  |  | 2219 |  |  | 2338.5 |  |  | 2235.5 |  |  | 2211.5 |  |  | 2454.5 |  |  | 2324.5 |  |  | 2302.5 |  |  | 2323 |  |  | 2340.5 |  |  | 2326.5 |  |  | 2255.5 |  |  | 2353.5 |  |  | 2385.5 |  |  | 2405.5 |  |  | 2280.5 |  |  | 2403 |  |  | 2394.5 |  |  | 2384.5 |  |  | 2422.5 |  |  | 2399.5 |  |  | 2318.5 |  |  | 2457.5 |  |  | 2400.5 |  |  | 2300.5 |  |  | 2486.5 |  |  | 2296.5 |  |  | 2424.5 |  |  | 2172.5 |  |  | 2168.5 |  |  | 2266 |  |  | 2309.5 |  |  | 2372.5 |  |  | 2328.5 |  |  | 2418.5 |  |  | 2460.5 |  |  | 2466.5 |  |  | 2442.5 |  |  | 2333.5 |  |  | 2358.5 |  |  | 2318.5 |  |  | 2252.5 |  |  | 2463.5 |  |  | 2362.5 |  |  | 2313.5 |  |  | 2346.5 |  |  | 2345.5 |  |  | 2407 |  |  | 2478.5 |  |  | 2335.5 |  |  | 2085 |  |  | 2511.5 |  |  | 2497 |  |  | 2206.5 |  |  | 2386.5 |  |  | 2438.5 |  |  | 2437.5 |  |  | 2337.5 |  |  | 2340.5 |  |  | 2324.5 |  |  | 2166.5 |  |  | 2217 |  |  | 2278.5 |  |  | 2167.5 |  |  | 2388.5 |  |  | 2284.5 |  |  | 2375 |  |  | 2319.5 |  |  | 2318.5 |  |  | 2466.5 |  |  | 2332.5 |  |  | 2483.5 |  |  | 2370.5 |  |  | 2335.5 |  |  | 2471.5 |  |  | 2460 |  |  | 2421 |  |  | 2337.5 |  |  | 2275.5 |  |  | 2365.5 |  |  | 2325 |  |  | 2498.5 |  |  | 2330.5 |  |  | 2301.5 |  |  | 2215 |  |  | 2468.5 |  |  | 2364.5 |  |  | 2200.5 |  |  | 2277.5 |  |  | 2322.5 |  |  | 2360.5 |  |  | 2419.5 |  |  | 2375.5 |  |  | 2479.5 |  |  | 2160 |  |  | 2279.5 |  |  | 2427.5 |  |  | 2390.5 |  |  | 2343.5 |  |  | 2277.5 |  |  | 2505 |  |  | 2277.5 |  |  | 2430.5 |  |  | 2409 |  |  | 2482.5 |  |  | 2346.5 |  |  | 2605 |  |  | 2422.5 |  |  | 2417.5 |  |  | 2489.5 |  |  | 2306.5 |  |  | 2337 |  |  | 2380 |  |  | 2351.5 |  |  | 2284.5 |  |  | 2418.5 |  |  | 2341.5 |  |  | 2499.5 |  |  | 2412.5 |  |  | 2347 |  |  | 2337.5 |  |  | 2286.5 |  |  | 2343 |  |  | 2328.5 |  |  | 2182.5 |  |  | 2366 |  |  | 2432.5 |  |  | 2217.5 |  |  | 2399.5 |  |  | 2360 |  |  | 2400.5 |  |  | 2280 |  |  | 2446.5 |  |  | 2268.5 |  |  | 2363.5 |  |  | 2328 |  |  | 2284.5 |  |  | 2453.5 |  |  | 2467.5 |  |  | 2370 |  |  | 2308.5 |  |  | 2186.5 |  |  | 2471.5 |  |  | 2478.5 |  |  | 2329.5 |  |  | 2386 |  |  | 2294.5 |  |  | 2423.5 |  |  | 2402.5 |  |  | 2309 |  |  | 2380 |  |  | 2510.5 |  |  | 2301.5 |  |  | 2223.5 |  |  | 2373.5 |  |  | 2344.5 |  |  | 2365.5 |  |  | 2369.5 |  |  | 2443.5 |  |  | 2281.5 |  |  | 2380.5 |  |  | 2380 |  |  | 2320.5 |  |  | 2403.5 |  |  | 2574.5 |  |  | 2482.5 |  |  | 2378 |  |  | 2330.5 |  |  | 2480.5 |  |  | 2353.5 |  |  | 2210.5 |  |  | 2490.5 |  |  | 2200 |  |  | 2379 |  |  | 2238 |  |  | 2409 |  |  | 2263.5 |  |  | 2388 |  |  | 2339.5 |  |  | 2380 |  |  | 2366.5 |  |  | 2477.5 |  |  | 2344.5 |  |  | 2346.5 |  |  | 2318.5 |  |  | 2378 |  |  | 2372.5 |  |  | 2480.5 |  |  | 2334.5 |  |  | 2350 |  |  | 2452.5 |  |  | 2329.5 |  |  | 2311.5 |  |  | 2390 |  |  | 2312.5 |  |  | 2259.5 |  |  | 2428.5 |  |  | 2274.5 |  |  | 2365.5 |  |  | 2292.5 |  |  | 2423.5 |  |  | 2369.5 |  |  | 2400.5 |  |  | 2239.5 |  |  | 2282 |  |  | 2305.5 |  |  | 2317.5 |  |  | 2257.5 |  |  | 2393.5 |  |  | 2451.5 |  |  | 2331 |  |  | 2408.5 |  |  | 2462 |  |  | 2282 |  |  | 2263.5 |  |  | 2441.5 |  |  | 2267.5 |  |  | 2326 |  |  | 2393.5 |  |  | 2408.5 |  |  | 2344.5 |  |  | 2236 |  |  | 2314.5 |  |  | 2189.5 |  |  | 2302.5 |  |  | 2253.5 |  |  | 2257.5 |  |  | 2274 |  |  | 2300.5 |  |  | 2414 |  |  | 2380.5 |  |  | 2194.5 |  |  | 2324.5 |  |  | 2357 |  |  | 2291.5 |  |  | 2311 |  |  | 2286 |  |  | 2328.5 |  |  | 2223.5 |  |  | 2295.5 |  |  | 2528.5 |  |  | 2522 |  |  | 2444.5 |  |  | 2329.5 |  |  | 2141.5 |  |  | 2328 |  |  | 2403.5 |  |  | 2304.5 |  |  | 2126.5 |  |  | 2363.5 |  |  | 2478 |  |  | 2246.5 |  |  | 2343.5 |  |  | 2369.5 |  |  | 2400.5 |  |  | 2324.5 |  |  | 2345.5 |  |  | 2477 |  |  | 2312.5 |  |  | 2261.5 |  |  | 2308 |  |  | 2258.5 |  |  | 2209.5 |  |  | 2358.5 |  |  | 2350 |  |  | 2407.5 |  |  | 2359.5 |  |  | 2358.5 |  |  | 2273.5 |  |  | 2378.5 |  |  | 2447 |  |  | 2300 |  |  | 2346.5 |  |  | 2439.5 |  |  | 2419.5 |  |  | 2188.5 |  |  | 2159 |  |  | 2438 |  |  | 2292 |  |  | 2436.5 |  |  | 2327 |  |  | 2385.5 |  |  | 2473.5 |  |  | 2400 |  |  | 2256.5 |  |  | 2367.5 |  |  | 2320.5 |  |  | 2406.5 |  |  | 2108.5 |  |  | 2370 |  |  | 2429 |  |  | 2261.5 |  |  | 2437.5 |  |  | 2271 |  |  | 2253.5 |  |  | 2357.5 |  |  | 2326 |  |  | 2478.5 |  |  | 2465.5 |  |  | 2279 |  |  | 2384.5 |  |  | 2397.5 |  |  | 2435 |  |  | 2292.5 |  |  | 2244 |  |  | 2519.5 |  |  | 2502 |  |  | 2277.5 |  |  | 2252.5 |  |  | 2296.5 |  |  | 2345.5 |  |  | 2368.5 |  |  | 2263.5 |  |  | 2383 |  |  | 2268.5 |  |  | 2379.5 |  |  | 2268.5 |  |  | 2315.5 |  |  | 2356.5 |  |  | 2296 |  |  | 2307.5 |  |  | 2345 |  |  | 2339.5 |  |  | 2233.5 |  |  | 2411.5 |  |  | 2360.5 |  |  | 2398.5 |  |  | 2331.5 |  |  | 2286.5 |  |  | 2420.5 |  |  | 2237.5 |  |  | 2281 |  |  | 2384.5 |  |  | 2262 |  |  | 2374 |  |  | 2351.5 |  |  | 2127 |  |  | 2213.5 |  |  | 2378.5 |  |  | 2434.5 |  |  | 2373.5 |  |  | 2449.5 |  |  | 2378.5 |  |  | 2374.5 |  |  | 2286 |  |  | 2490 |  |  | 2240.5 |  |  | 2347.5 |  |  | 2343 |  |  | 2267.5 |  |  | 2288.5 |  |  | 2289.5 |  |  | 2260.5 |  |  | 2307.5 |  |  | 2241 |  |  | 2340.5 |  |  | 2315.5 |  |  | 2248.5 |  |  | 2301 |  |  | 2428.5 |  |  | 2417.5 |  |  | 2373.5 |  |  | 2557.5 |  |  | 2389.5 |  |  | 2284.5 |  |  | 2420.5 |  |  | 1997.5 |  |  | 2328.5 |  |  | 2217 |  |  | 2471.5 |  |  | 2368.5 |  |  | 2439.5 |  |  | 2240.5 |  |  | 2310.5 |  |  | 2268.5 |  |  | 2276.5 |  |  | 2176 |  |  | 2275.5 |  |  | 2332.5 |  |  | 2354.5 |  |  | 2339 |  |  | 2411.5 |  |  | 2262 |  |  | 2181.5 |  |  | 2347.5 |  |  | 2266.5 |  |  | 2393 |  |  | 2211.5 |  |  | 2314 |  |  | 2300 |  |  | 2382.5 |  |  | 2341 |  |  | 2504 |  |  | 2417.5 |  |  | 2407.5 |  |  | 2211.5 |  |  | 2375 |  |  | 2398.5 |  |  | 2262.5 |  |  | 2237.5 |  |  | 2460.5 |  |  | 2317.5 |  |  | 2304.5 |  |  | 2324.5 |  |  | 2387.5 |  |  | 2307 |  |  | 2518.5 |  |  | 2285 |  |  | 2348.5 |  |  | 2268.5 |  |  | 2474.5 |  |  | 2343 |  |  | 2416 |  |  | 2478 |  |  | 2360.5 |  |  | 2309 |  |  | 2401.5 |  |  | 2485.5 |  |  | 2348.5 |  |  | 2325.5 |  |  | 2251.5 |  |  | 2462.5 |  |  | 2465.5 |  |  | 2446.5 |  |  | 2374 |  |  | 2227.5 |  |  | 2198.5 |  |  | 2342.5 |  |  | 2295.5 |  |  | 2272 |  |  | 2335.5 |  |  | 2408 |  |  | 2332.5 |  |  | 2388.5 |  |  | 2282.5 |  |  | 2236.5 |  |  | 2209 |  |  | 2295.5 |  |  | 2103 |  |  | 2281.5 |  |  | 2394.5 |  |  | 2496.5 |  |  | 2348.5 |  |  | 2349.5 |  |  | 2401.5 |  |  | 2283.5 |  |  | 2379.5 |  |  | 2332.5 |  |  | 2237 |  |  | 2399.5 |  |  | 2329.5 |  |  | 2312.5 |  |  | 2387.5 |  |  | 2406.5 |  |  | 2270 |  |  | 2251 |  |  | 2340.5 |  |  | 2334 |  |  | 2477.5 |  |  | 2285.5 |  |  | 2461.5 |  |  | 2380.5 |  |  | 2305.5 |  |  | 2437.5 |  |  | 2358.5 |  |  | 2395.5 |  |  | 2384 |  |  | 2376.5 |  |  | 2546.5 |  |  | 2306.5 |  |  | 2190 |  |  | 2342.5 |  |  | 2288.5 |  |  | 2450 |  |  | 2295 |  |  | 2346.5 |  |  | 2302 |  |  | 2146 |  |  | 2211.5 |  |  | 2440 |  |  | 2547.5 |  |  | 2306.5 |  |  | 2458.5 |  |  | 2333.5 |  |  | 2249.5 |  |  | 2316.5 |  |  | 2157.5 |  |  | 2277.5 |  |  | 2349.5 |  |  | 2273.5 |  |  | 2250 |  |  | 2231 |  |  | 2430.5 |  |  | 2459.5 |  |  | 2314.5 |  |  | 2386.5 |  |  | 2332.5 |  |  | 2364.5 |  |  | 2369.5 |  |  | 2287.5 |  |  | 2598 |  |  | 2291.5 |  |  | 2335 |  |  | 2260.5 |  |  | 2464.5 |  |  | 2420.5 |  |  | 2477 |  |  | 2355.5 |  |  | 2276.5 |  |  | 2384 |  |  | 2384.5 |  |  | 2308.5 |  |  | 2377.5 |  |  | 2332.5 |  |  | 2308.5 |  |  | 2352.5 |  |  | 2365 |  |  | 2329.5 |  |  | 2339.5 |  |  | 2471.5 |  |  | 2400.5 |  |  | 2361 |  |  | 2369.5 |  |  | 2457.5 |  |  | 2303 |  |  | 2364.5 |  |  | 2446.5 |  |  | 2391 |  |  | 2417.5 |  |  | 2462.5 |  |  | 2316.5 |  |  | 2304 |  |  | 2197.5 |  |  | 2345.5 |  |  | 2270 |  |  | 2380.5 |  |  | 2374.5 |  |  | 2338.5 |  |  | 2172.5 |  |  | 2403.5 |  |  | 2464.5 |  |  | 2278.5 |  |  | 2337 |  |  | 2275 |  |  | 2188.5 |  |  | 2439.5 |  |  | 2213.5 |  |  | 2433 |  |  | 2515.5 |  |  | 2304.5 |  |  | 2324.5 |  |  | 2206.5 |  |  | 2346.5 |  |  | 2405.5 |  |  | 2262.5 |  |  | 2385.5 |  |  | 2153.5 |  |  | 2368 |  |  | 2291.5 |  |  | 2191.5 |  |  | 2308.5 |  |  | 2396.5 |  |  | 2490.5 |  |  | 2407.5 |  |  | 2364.5 |  |  | 2364.5 |  |  | 2204.5 |  |  | 2463.5 |  |  | 2334.5 |  |  | 2254.5 |  |  | 2350.5 |  |  | 2456 |  |  | 2339.5 |  |  | 2388.5 |  |  | 2325 |  |  | 2395.5 |  |  | 2398.5 |  |  | 2463 |  |  | 2405.5 |  |  | 2449.5 |  |  | 2537.5 |  |  | 2461 |  |  | 2275.5 |  |  | 2448.5 |  |  | 2361.5 |  |  | 2148.5 |  |  | 2414.5 |  |  | 2253 |  |  | 2298.5 |  |  | 2419 |  |  | 2388 |  |  | 2421.5 |  |  | 2365.5 |  |  | 2262.5 |  |  | 2135.5 |  |  | 2286.5 |  |  | 2421.5 |  |  | 2268 |  |  | 2317.5 |  |  | 2301 |  |  | 2307.5 |  |  | 2358 |  |  | 2288 |  |  | 2440 |  |  | 2418.5 |  |  | 2284 |  |  | 2482.5 |  |  | 2395.5 |  |  | 2356.5 |  |  | 2516.5 |  |  | 2248.5 |  |  | 2441 |  |  | 2383.5 |  |  | 2425.5 |  |  | 2561.5 |  |  | 2336 |  |  | 2364.5 |  |  | 2296.5 |  |  | 2392.5 |  |  | 2421.5 |  |  | 2354 |  |  | 2413 |  |  | 2297 |  |  | 2339.5 |  |  | 2455 |  |  | 2396 |  |  | 2405.5 |  |  | 2266.5 |  |  | 2232.5 |  |  | 2382.5 |  |  | 2358.5 |  |  | 2343.5 |  |  | 2461.5 |  |  | 2334.5 |  |  | 2284.5 |  |  | 2265 |  |  | 2307.5 |  |  | 2254 |  |  | 2352.5 |  |  | 2338.5 |  |  | 2379.5 |  |  | 2401.5 |  |  | 2460 |  |  | 2408.5 |  |  | 2371 |  |  | 2285.5 |  |  | 2394.5 |  |  | 2243 |  |  | 2307 |  |  | 2409.5 |  |  | 2368 |  |  | 2357.5 |  |  | 2218.5 |  |  | 2257.5 |  |  | 2283.5 |  |  | 2414.5 |  |  | 2424.5 |  |  | 2235.5 |  |  | 2295 |  |  | 2416.5 |  |  | 2392.5 |  |  | 2358.5 |  |  | 2410.5 |  |  | 2284.5 |  |  | 2386.5 |  |  | 2515.5 |  |  | 2363.5 |  |  | 2489.5 |  |  | 2457.5 |  |  | 2231.5 |  |  | 2239.5 |  |  | 2337 |  |  | 2251.5 |  |  | 2273.5 |  |  | 2438 |  |  | 2262.5 |  |  | 2243.5 |  |  | 2332.5 |  |  | 2260.5 |  |  | 2562 |  |  | 2505.5 |  |  | 2299.5 |  |  | 2216.5 |  |  | 2466.5 |  |  | 2267 |  |  | 2293.5 |  |  | 2459.5 |  |  | 2300.5 |  |  | 2425.5 |  |  | 2267.5 |  |  | 2247.5 |  |  | 2461.5 |  |  | 2340.5 |  |  | 2379.5 |  |  | 2378.5 |  |  | 2406.5 |  |  | 2420 |  |  | 2375.5 |  |  | 2306.5 |  |  | 2407.5 |  |  | 2415.5 |  |  | 2246.5 |  |  | 2341.5 |  |  | 2423 |  |  | 2417.5 |  |  | 2270 |  |  | 2244.5 |  |  | 2413.5 |  |  | 2396.5 |  |  | 2359 |  |  | 2284 |  |  | 2401.5 |  |  | 2410.5 |  |  | 2126.5 |  |  | 2497.5 |  |  | 2352.5 |  |  | 2361.5 |  |  | 2284.5 |  |  | 2430.5 |  |  | 2281.5 |  |  | 2452.5 |  |  | 2348.5 |  |  | 2415.5 |  |  | 2243.5 |  |  | 2337.5 |  |  | 2460.5 |  |  | 2346.5 |  |  | 2343.5 |  |  | 2379.5 |  |  | 2319.5 |  |  | 2338.5 |  |  | 2406.5 |  |  | 2416.5 |  |  | 2385 |  |  | 2446.5 |  |  | 2338.5 |  |  | 2381.5 |  |  | 2345 |  |  | 2394.5 |  |  | 2346.5 |  |  | 2404.5 |  |  | 2372.5 |  |  | 2385 |  |  | 2202.5 |  |  | 2264.5 |  |  | 2229 |  |  | 2320 |  |  | 2337 |  |  | 2332.5 |  |  | 2333.5 |  |  | 2403.5 |  |  | 2559.5 |  |  | 2420 |  |  | 2401.5 |  |  | 2346.5 |  |  | 2234 |  |  | 2306 |  |  | 2370.5 |  |  | 2409.5 |  |  | 2433 |  |  | 2371.5 |  |  | 2444 |  |  | 2290.5 |  |  | 2264.5 |  |  | 2485 |  |  | 2442.5 |  |  | 2395.5 |  |  | 2215.5 |  |  | 2452 |  |  | 2238.5 |  |  | 2264.5 |  |  | 2271.5 |  |  | 2303.5 |  |  | 2338.5 |  |  | 2387.5 |  |  | 2286.5 |  |  | 2387.5 |  |  | 2435.5 |  |  | 2354.5 |  |  | 2328 |  |  | 2348.5 |  |  | 2385.5 |  |  | 2412.5 |  |  | 2460.5 |  |  | 2329.5 |  |  | 2377.5 |  |  | 2477.5 |  |  | 2319.5 |  |  | 2477 |  |  | 2295.5 |  |  | 2328 |  |  | 2536.5 |  |  | 2552.5 |  |  | 2575.5 |  |  | 2271.5 |  |  | 2277.5 |  |  | 2379.5 |  |  | 2272.5 |  |  | 2406.5 |  |  | 2370 |  |  | 2275.5 |  |  | 2379 |  |  | 2244.5 |  |  | 2271.5 |  |  | 2383.5 |  |  | 2384 |  |  | 2281.5 |  |  | 2394.5 |  |  | 2113 |  |  | 2321.5 |  |  | 2324 |  |  | 2368.5 |  |  | 2289.5 |  |  | 2287.5 |  |  | 2373 |  |  | 2460.5 |  |  | 2568.5 |  |  | 2237 |  |  | 2505.5 |  |  | 2334.5 |  |  | 2375 |  |  | 2362.5 |  |  | 2527.5 |  |  | 2437.5 |  |  | 2445.5 |  |  | 2270.5 |  |  | 2501.5 |  |  | 2267.5 |  |  | 2338.5 |  |  | 2240.5 |  |  | 2250.5 |  |  | 2513.5 |  |  | 2464 |  |  | 2376 |  |  | 2447.5 |  |  | 2341.5 |  |  | 2406
81 |  | 2331.5 |  |  | 2501.5 |  |  | 2428 |  |  | 2336.5 |  |  | 2551.5 |  |  | 2391.5 |  |  | 2450.5 |  |  | 2399.5 |  |  | 2374.5 |  |  | 2376.5 |  |  | 2293 |  |  | 2476.5 |  |  | 2440.5 |  |  | 2254.5 |  |  | 2218 |  |  | 2448.5 |  |  | 2510.5 |  |  | 2363.5 |  |  | 2486.5 |  |  | 2303.5 |  |  | 2496.5 |  |  | 2403.5 |  |  | 2456.5 |  |  | 2281.5 |  |  | 2215 |  |  | 2458.5 |  |  | 2414.5 |  |  | 2338.5 |  |  | 2470.5 |  |  | 2251 |  |  | 2398 |  |  | 2504.5 |  |  | 2209.5 |  |  | 2432.5 |  |  | 2285.5 |  |  | 2440 |  |  | 2331.5 |  |  | 2524 |  |  | 2404.5 |  |  | 2366.5 |  |  | 2192.5 |  |  | 2414.5 |  |  | 2254.5 |  |  | 2393 |  |  | 2564.5 |  |  | 2486 |  |  | 2385.5 |  |  | 2478.5 |  |  | 2459.5 |  |  | 2380.5 |  |  | 2272.5 |  |  | 2432.5 |  |  | 2395.5 |  |  | 2328.5 |  |  | 2452.5 |  |  | 2429.5 |  |  | 2276.5 |  |  | 2399 |  |  | 2424.5 |  |  | 2383.5 |  |  | 2354 |  |  | 2340.5 |  |  | 2439.5 |  |  | 2321.5 |  |  | 2297.5 |  |  | 2438 |  |  | 2494.5 |  |  | 2294 |  |  | 2247.5 |  |  | 2452.5 |  |  | 2368 |  |  | 2323.5 |  |  | 2375.5 |  |  | 2534.5 |  |  | 2493 |  |  | 2469 |  |  | 2277.5 |  |  | 2311.5 |  |  | 2270.5 |  |  | 2406.5 |  |  | 2353 |  |  | 2396.5 |  |  | 2444.5 |  |  | 2478.5 |  |  | 2466.5 |  |  | 2305.5 |  |  | 2471.5 |  |  | 2359.5 |  |  | 2368.5 |  |  | 2415.5 |  |  | 2397.5 |  |  | 2412 |  |  | 2301.5 |  |  | 2275 |  |  | 2328 |  |  | 2301 |  |  | 2540.5 |  |  | 2515.5 |  |  | 2259.5 |  |  | 2527.5 |  |  | 2295.5 |  |  | 2336 |  |  | 2344 |  |  | 2357.5 |  |  | 2347.5 |  |  | 2305.5 |  |  | 2405.5 |  |  | 2502.5 |  |  | 2477.5 |  |  | 2460.5 |  |  | 2479.5 |  |  | 2462.5 |  |  | 2353.5 |  |  | 2386.5 |  |  | 2432.5 |  |  | 2416.5 |  |  | 2477.5 |  |  | 2323.5 |  |  | 2370.5 |  |  | 2336.5 |  |  | 2418.5 |  |  | 2468.5 |  |  | 2414.5 |  |  | 2420.5 |  |  | 2353.5 |  |  | 2364 |  |  | 2345.5 |  |  | 2355.5 |  |  | 2290.5 |  |  | 2392.5 |  |  | 2453.5 |  |  | 2398 |  |  | 2312.5 |  |  | 2484.5 |  |  | 2316.5 |  |  | 2305.5 |  |  | 2439 |  |  | 2412.5 |  |  | 2474.5 |  |  | 2293 |  |  | 2436.5 |  |  | 2238 |  |  | 2480 |  |  | 2487.5 |  |  | 2416 |  |  | 2529.5 |  |  | 2310.5 |  |  | 2419.5 |  |  | 2295.5 |  |  | 2391.5 |  |  | 2423.5 |  |  | 2392.5 |  |  | 2437.5 |  |  | 2489.5 |  |  | 2413.5 |  |  | 2474 |  |  | 2327.5 |  |  | 2242 |  |  | 2322.5 |  |  | 2386.5 |  |  | 2316 |  |  | 2364.5 |  |  | 2325.5 |  |  | 2335.5 |  |  | 2248 |  |  | 2362.5 |  |  | 2256.5 |  |  | 2258.5 |  |  | 2480.5 |  |  | 2353.5 |  |  | 2341.5 |  |  | 2362 |  |  | 2379.5 |  |  | 2355.5 |  |  | 2281.5 |  |  | 2392.5 |  |  | 2400.5 |  |  | 2434.5 |  |  | 2319.5 |  |  | 2450 |  |  | 2418.5 |  |  | 2423.5 |  |  | 2448.5 |  |  | 2438.5 |  |  | 2344.5 |  |  | 2496.5 |  |  | 2426.5 |  |  | 2329.5 |  |  | 2525.5 |  |  | 2335.5 |  |  | 2448.5 |  |  | 2201.5 |  |  | 2183.5 |  |  | 2281 |  |  | 2324.5 |  |  | 2401.5 |  |  | 2354.5 |  |  | 2457.5 |  |  | 2489.5 |  |  | 2495.5 |  |  | 2471.5 |  |  | 2354.5 |  |  | 2387.5 |  |  | 2357.5 |  |  | 2273.5 |  |  | 2492.5 |  |  | 2409.5 |  |  | 2352.5 |  |  | 2370.5 |  |  | 2392.5 |  |  | 2428 |  |  | 2517.5 |  |  | 2359.5 |  |  | 2111 |  |  | 2540.5 |  |  | 2536 |  |  | 2232.5 |  |  | 2401.5 |  |  | 2467.5 |  |  | 2484.5 |  |  | 2361.5 |  |  | 2364.5 |  |  | 2353.5 |  |  | 2205.5 |  |  | 2241 |  |  | 2307.5 |  |  | 2206.5 |  |  | 2435.5 |  |  | 2331.5 |  |  | 2390 |  |  | 2345.5 |  |  | 2339.5 |  |  | 2495.5 |  |  | 2371.5 |  |  | 2512.5 |  |  | 2391.5 |  |  | 2382.5 |  |  | 2518.5 |  |  | 2486 |  |  | 2460 |  |  | 2352.5 |  |  | 2290.5 |  |  | 2412.5 |  |  | 2349 |  |  | 2513.5 |  |  | 2369.5 |  |  | 2348.5 |  |  | 2254 |  |  | 2489.5 |  |  | 2388.5 |  |  | 2226.5 |  |  | 2303.5 |  |  | 2343.5 |  |  | 2399.5 |  |  | 2458.5 |  |  | 2399.5 |  |  | 2500.5 |  |  | 2184 |  |  | 2300.5 |  |  | 2466.5 |  |  | 2414.5 |  |  | 2382.5 |  |  | 2306.5 |  |  | 2544 |  |  | 2298.5 |  |  | 2456.5 |  |  | 2456 |  |  | 2503.5 |  |  | 2375.5 |  |  | 2634 |  |  | 2451.5 |  |  | 2443.5 |  |  | 2518.5 |  |  | 2335.5 |  |  | 2366 |  |  | 2395 |  |  | 2377.5 |  |  | 2308.5 |  |  | 2439.5 |  |  | 2356.5 |  |  | 2546.5 |  |  | 2451.5 |  |  | 2386 |  |  | 2363.5 |  |  | 2307.5 |  |  | 2358 |  |  | 2367.5 |  |  | 2206.5 |  |  | 2413 |  |  | 2447.5 |  |  | 2241.5 |  |  | 2423.5 |  |  | 2384 |  |  | 2421.5 |  |  | 2304 |  |  | 2485.5 |  |  | 2289.5 |  |  | 2402.5 |  |  | 2352 |  |  | 2331.5 |  |  | 2500.5 |  |  | 2493.5 |  |  | 2399 |  |  | 2329.5 |  |  | 2201.5 |  |  | 2497.5 |  |  | 2517.5 |  |  | 2353.5 |  |  | 2425 |  |  | 2333.5 |  |  | 2470.5 |  |  | 2431.5 |  |  | 2335 |  |  | 2401 |  |  | 2557.5 |  |  | 2340.5 |  |  | 2238.5 |  |  | 2399.5 |  |  | 2373.5 |  |  | 2386.5 |  |  | 2390.5 |  |  | 2482.5 |  |  | 2305.5 |  |  | 2401.5 |  |  | 2406 |  |  | 2349.5 |  |  | 2429.5 |  |  | 2613.5 |  |  | 2529.5 |  |  | 2404 |  |  | 2354.5 |  |  | 2506.5 |  |  | 2382.5 |  |  | 2231.5 |  |  | 2511.5 |  |  | 2239 |  |  | 2403 |  |  | 2262 |  |  | 2448 |  |  | 2278.5 |  |  | 2414 |  |  | 2386.5 |  |  | 2404 |  |  | 2405.5 |  |  | 2503.5 |  |  | 2383.5 |  |  | 2375.5 |  |  | 2342.5 |  |  | 2425 |  |  | 2419.5 |  |  | 2509.5 |  |  | 2373.5 |  |  | 2376 |  |  | 2499.5 |  |  | 2368.5 |  |  | 2358.5 |  |  | 2437 |  |  | 2359.5 |  |  | 2285.5 |  |  | 2475.5 |  |  | 2313.5 |  |  | 2404.5 |  |  | 2331.5 |  |  | 2438.5 |  |  | 2384.5 |  |  | 2415.5 |  |  | 2260.5 |  |  | 2297 |  |  | 2334.5 |  |  | 2356.5 |  |  | 2278.5 |  |  | 2422.5 |  |  | 2477.5 |  |  | 2370 |  |  | 2437.5 |  |  | 2483 |  |  | 2303 |  |  | 2278.5 |  |  | 2462.5 |  |  | 2288.5 |  |  | 2355 |  |  | 2432.5 |  |  | 2429.5 |  |  | 2359.5 |  |  | 2265 |  |  | 2335.5 |  |  | 2228.5 |  |  | 2341.5 |  |  | 2279.5 |  |  | 2296.5 |  |  | 2298 |  |  | 2321.5 |  |  | 2429 |  |  | 2409.5 |  |  | 2223.5 |  |  | 2363.5 |  |  | 2396 |  |  | 2320.5 |  |  | 2326 |  |  | 2307 |  |  | 2367.5 |  |  | 2249.5 |  |  | 2321.5 |  |  | 2549.5 |  |  | 2537 |  |  | 2483.5 |  |  | 2376.5 |  |  | 2165.5 |  |  | 2352 |  |  | 2432.5 |  |  | 2343.5 |  |  | 2150.5 |  |  | 2378.5 |  |  | 2525 |  |  | 2285.5 |  |  | 2358.5 |  |  | 2390.5 |  |  | 2439.5 |  |  | 2371.5 |  |  | 2369.5 |  |  | 2492 |  |  | 2341.5 |  |  | 2308.5 |  |  | 2355 |  |  | 2282.5 |  |  | 2256.5 |  |  | 2379.5 |  |  | 2376 |  |  | 2431.5 |  |  | 2383.5 |  |  | 2387.5 |  |  | 2320.5 |  |  | 2407.5 |  |  | 2473 |  |  | 2315 |  |  | 2375.5 |  |  | 2463.5 |  |  | 2443.5 |  |  | 2235.5 |  |  | 2188 |  |  | 2477 |  |  | 2331 |  |  | 2460.5 |  |  | 2366 |  |  | 2409.5 |  |  | 2512.5 |  |  | 2439 |  |  | 2271.5 |  |  | 2406.5 |  |  | 2341.5 |  |  | 2421.5 |  |  | 2129.5 |  |  | 2417 |  |  | 2476 |  |  | 2300.5 |  |  | 2463.5 |  |  | 2295 |  |  | 2279.5 |  |  | 2378.5 |  |  | 2347 |  |  | 2517.5 |  |  | 2494.5 |  |  | 2305 |  |  | 2423.5 |  |  | 2418.5 |  |  | 2482 |  |  | 2321.5 |  |  | 2283 |  |  | 2548.5 |  |  | 2523 |  |  | 2316.5 |  |  | 2276.5 |  |  | 2325.5 |  |  | 2371.5 |  |  | 2415.5 |  |  | 2287.5 |  |  | 2422 |  |  | 2307.5 |  |  | 2400.5 |  |  | 2307.5 |  |  | 2339.5 |  |  | 2382.5 |  |  | 2322 |  |  | 2328.5 |  |  | 2384 |  |  | 2363.5 |  |  | 2262.5 |  |  | 2450.5 |  |  | 2375.5 |  |  | 2445.5 |  |  | 2370.5 |  |  | 2307.5 |  |  | 2441.5 |  |  | 2261.5 |  |  | 2305 |  |  | 2423.5 |  |  | 2288 |  |  | 2398 |  |  | 2377.5 |  |  | 2142 |  |  | 2228.5 |  |  | 2425.5 |  |  | 2473.5 |  |  | 2420.5 |  |  | 2473.5 |  |  | 2417.5 |  |  | 2413.5 |  |  | 2325 |  |  | 2529 |  |  | 2266.5 |  |  | 2371.5 |  |  | 2358 |  |  | 2291.5 |  |  | 2303.5 |  |  | 2313.5 |  |  | 2281.5 |  |  | 2346.5 |  |  | 2270 |  |  | 2379.5 |  |  | 2354.5 |  |  | 2295.5 |  |  | 2330 |  |  | 2443.5 |  |  | 2464.5 |  |  | 2412.5 |  |  | 2578.5 |  |  | 2428.5 |  |  | 2299.5 |  |  | 2444.5 |  |  | 2012.5 |  |  | 2375.5 |  |  | 2246 |  |  | 2486.5 |  |  | 2392.5 |  |  | 2454.5 |  |  | 2266.5 |  |  | 2357.5 |  |  | 2307.5 |  |  | 2300.5 |  |  | 2215 |  |  | 2301.5 |  |  | 2358.5 |  |  | 2369.5 |  |  | 2363 |  |  | 2450.5 |  |  | 2309 |  |  | 2220.5 |  |  | 2386.5 |  |  | 2292.5 |  |  | 2422 |  |  | 2237.5 |  |  | 2353 |  |  | 2329 |  |  | 2397.5 |  |  | 2370 |  |  | 2533 |  |  | 2438.5 |  |  | 2428.5 |  |  | 2258.5 |  |  | 2422 |  |  | 2445.5 |  |  | 2291.5 |  |  | 2266.5 |  |  | 2489.5 |  |  | 2332.5 |  |  | 2328.5 |  |  | 2339.5 |  |  | 2402.5 |  |  | 2322 |  |  | 2533.5 |  |  | 2324 |  |  | 2395.5 |  |  | 2307.5 |  |  | 2489.5 |  |  | 2390 |  |  | 2463 |  |  | 2499 |  |  | 2399.5 |  |  | 2335 |  |  | 2440.5 |  |  | 2524.5 |  |  | 2369.5 |  |  | 2349.5 |  |  | 2266.5 |  |  | 2501.5 |  |  | 2512.5 |  |  | 2461.5 |  |  | 2421 |  |  | 2251.5 |  |  | 2237.5 |  |  | 2381.5 |  |  | 2319.5 |  |  | 2319 |  |  | 2382.5 |  |  | 2432 |  |  | 2379.5 |  |  | 2427.5 |  |  | 2297.5 |  |  | 2275.5 |  |  | 2238 |  |  | 2334.5 |  |  | 2132 |  |  | 2296.5 |  |  | 2433.5 |  |  | 2511.5 |  |  | 2387.5 |  |  | 2373.5 |  |  | 2430.5 |  |  | 2330.5 |  |  | 2418.5 |  |  | 2353.5 |  |  | 2276 |  |  | 2414.5 |  |  | 2376.5 |  |  | 2338.5 |  |  | 2413.5 |  |  | 2427.5 |  |  | 2309 |  |  | 2290 |  |  | 2364.5 |  |  | 2349 |  |  | 2516.5 |  |  | 2300.5 |  |  | 2476.5 |  |  | 2409.5 |  |  | 2329.5 |  |  | 2458.5 |  |  | 2379.5 |  |  | 2434.5 |  |  | 2410 |  |  | 2397.5 |  |  | 2575.5 |  |  | 2330.5 |  |  | 2229 |  |  | 2381.5 |  |  | 2309.5 |  |  | 2489 |  |  | 2316 |  |  | 2370.5 |  |  | 2341 |  |  | 2170 |  |  | 2240.5 |  |  | 2461 |  |  | 2594.5 |  |  | 2345.5 |  |  | 2479.5 |  |  | 2359.5 |  |  | 2264.5 |  |  | 2363.5 |  |  | 2178.5 |  |  | 2303.5 |  |  | 2388.5 |  |  | 2302.5 |  |  | 2289 |  |  | 2257 |  |  | 2477.5 |  |  | 2485.5 |  |  | 2329.5 |  |  | 2410.5 |  |  | 2371.5 |  |  | 2411.5 |  |  | 2408.5 |  |  | 2308.5 |  |  | 2624 |  |  | 2317.5 |  |  | 2359 |  |  | 2299.5 |  |  | 2485.5 |  |  | 2449.5 |  |  | 2498 |  |  | 2381.5 |  |  | 2300.5 |  |  | 2399 |  |  | 2431.5 |  |  | 2355.5 |  |  | 2416.5 |  |  | 2379.5 |  |  | 2334.5 |  |  | 2399.5 |  |  | 2412 |  |  | 2344.5 |  |  | 2360.5 |  |  | 2510.5 |  |  | 2429.5 |  |  | 2382 |  |  | 2384.5 |  |  | 2496.5 |  |  | 2342 |  |  | 2385.5 |  |  | 2485.5 |  |  | 2430 |  |  | 2456.5 |  |  | 2501.5 |  |  | 2355.5 |  |  | 2351 |  |  | 2236.5 |  |  | 2360.5 |  |  | 2296 |  |  | 2419.5 |  |  | 2400.5 |  |  | 2377.5 |  |  | 2196.5 |  |  | 2418.5 |  |  | 2490.5 |  |  | 2317.5 |  |  | 2366 |  |  | 2299 |  |  | 2217.5 |  |  | 2465.5 |  |  | 2242.5 |  |  | 2472 |  |  | 2541.5 |  |  | 2333.5 |  |  | 2353.5 |  |  | 2221.5 |  |  | 2367.5 |  |  | 2444.5 |  |  | 2277.5 |  |  | 2432.5 |  |  | 2174.5 |  |  | 2407 |  |  | 2320.5 |  |  | 2206.5 |  |  | 2355.5 |  |  | 2425.5 |  |  | 2529.5 |  |  | 2436.5 |  |  | 2390.5 |  |  | 2385.5 |  |  | 2228.5 |  |  | 2489.5 |  |  | 2363.5 |  |  | 2269.5 |  |  | 2379.5 |  |  | 2477 |  |  | 2386.5 |  |  | 2435.5 |  |  | 2346 |  |  | 2421.5 |  |  | 2445.5 |  |  | 2510 |  |  | 2431.5 |  |  | 2475.5 |  |  | 2584.5 |  |  | 2508 |  |  | 2304.5 |  |  | 2487.5 |  |  | 2400.5 |  |  | 2187.5 |  |  | 2461.5 |  |  | 2300 |  |  | 2327.5 |  |  | 2458 |  |  | 2427 |  |  | 2460.5 |  |  | 2389.5 |  |  | 2301.5 |  |  | 2159.5 |  |  | 2310.5 |  |  | 2447.5 |  |  | 2307 |  |  | 2364.5 |  |  | 2340 |  |  | 2322.5 |  |  | 2397 |  |  | 2303 |  |  | 2461 |  |  | 2447.5 |  |  | 2313 |  |  | 2529.5 |  |  | 2424.5 |  |  | 2380.5 |  |  | 2545.5 |  |  | 2263.5 |  |  | 2465 |  |  | 2412.5 |  |  | 2446.5 |  |  | 2582.5 |  |  | 2383 |  |  | 2379.5 |  |  | 2320.5 |  |  | 2407.5 |  |  | 2460.5 |  |  | 2380 |  |  | 2437 |  |  | 2344 |  |  | 2378.5 |  |  | 2494 |  |  | 2435 |  |  | 2452.5 |  |  | 2292.5 |  |  | 2256.5 |  |  | 2408.5 |  |  | 2397.5 |  |  | 2390.5 |  |  | 2476.5 |  |  | 2363.5 |  |  | 2323.5 |  |  | 2294 |  |  | 2331.5 |  |  | 2301 |  |  | 2391.5 |  |  | 2377.5 |  |  | 2418.5 |  |  | 2422.5 |  |  | 2499 |  |  | 2423.5 |  |  | 2386 |  |  | 2314.5 |  |  | 2423.5 |  |  | 2269 |  |  | 2336 |  |  | 2448.5 |  |  | 2407 |  |  | 2404.5 |  |  | 2244.5 |  |  | 2296.5 |  |  | 2330.5 |  |  | 2435.5 |  |  | 2450.5 |  |  | 2261.5 |  |  | 2310 |  |  | 2440.5 |  |  | 2416.5 |  |  | 2387.5 |  |  | 2431.5 |  |  | 2308.5 |  |  | 2425.5 |  |  | 2530.5 |  |  | 2387.5 |  |  | 2528.5 |  |  | 2481.5 |  |  | 2260.5 |  |  | 2268.5 |  |  | 2376 |  |  | 2275.5 |  |  | 2320.5 |  |  | 2467 |  |  | 2277.5 |  |  | 2282.5 |  |  | 2361.5 |  |  | 2286.5 |  |  | 2601 |  |  | 2520.5 |  |  | 2325.5 |  |  | 2255.5 |  |  | 2505.5 |  |  | 2306 |  |  | 2317.5 |  |  | 2480.5 |  |  | 2324.5 |  |  | 2464.5 |  |  | 2306.5 |  |  | 2273.5 |  |  | 2500.5 |  |  | 2379.5 |  |  | 2405.5 |  |  | 2407.5 |  |  | 2427.5 |  |  | 2446 |  |  | 2414.5 |  |  | 2332.5 |  |  | 2428.5 |  |  | 2454.5 |  |  | 2293.5 |  |  | 2356.5 |  |  | 2447 |  |  | 2456.5 |  |  | 2309 |  |  | 2283.5 |  |  | 2439.5 |  |  | 2443.5 |  |  | 2388 |  |  | 2308 |  |  | 2422.5 |  |  | 2431.5 |  |  | 2150.5 |  |  | 2512.5 |  |  | 2391.5 |  |  | 2400.5 |  |  | 2310.5 |  |  | 2454.5 |  |  | 2302.5 |  |  | 2491.5 |  |  | 2395.5 |  |  | 2444.5 |  |  | 2272.5 |  |  | 2384.5 |  |  | 2486.5 |  |  | 2375.5 |  |  | 2358.5 |  |  | 2394.5 |  |  | 2343.5 |  |  | 2353.5 |  |  | 2430.5 |  |  | 2437.5 |  |  | 2406 |  |  | 2475.5 |  |  | 2377.5 |  |  | 2402.5 |  |  | 2392 |  |  | 2433.5 |  |  | 2370.5 |  |  | 2451.5 |  |  | 2419.5 |  |  | 2411 |  |  | 2241.5 |  |  | 2293.5 |  |  | 2253 |  |  | 2359 |  |  | 2361 |  |  | 2358.5 |  |  | 2357.5 |  |  | 2442.5 |  |  | 2580.5 |  |  | 2467 |  |  | 2425.5 |  |  | 2361.5 |  |  | 2249 |  |  | 2345 |  |  | 2409.5 |  |  | 2448.5 |  |  | 2480 |  |  | 2395.5 |  |  | 2473 |  |  | 2319.5 |  |  | 2293.5 |  |  | 2524 |  |  | 2457.5 |  |  | 2419.5 |  |  | 2241.5 |  |  | 2491 |  |  | 2277.5 |  |  | 2290.5 |  |  | 2310.5 |  |  | 2350.5 |  |  | 2385.5 |  |  | 2434.5 |  |  | 2325.5 |  |  | 2413.5 |  |  | 2474.5 |  |  | 2393.5 |  |  | 2352 |  |  | 2374.5 |  |  | 2411.5 |  |  | 2436.5 |  |  | 2481.5 |  |  | 2355.5 |  |  | 2392.5 |  |  | 2506.5 |  |  | 2348.5 |  |  | 2498 |  |  | 2334.5 |  |  | 2357 |  |  | 2583.5 |  |  | 2599.5 |  |  | 2590.5 |  |  | 2310.5 |  |  | 2316.5 |  |  | 2418.5 |  |  | 2293.5 |  |  | 2421.5 |  |  | 2409 |  |  | 2296.5 |  |  | 2405 |  |  | 2265.5 |  |  | 2310.5 |  |  | 2398.5 |  |  | 2431 |  |  | 2302.5 |  |  | 2409.5 |  |  | 2128 |  |  | 2360.5 |  |  | 2345 |  |  | 2407.5 |  |  | 2310.5 |  |  | 2316.5 |  |  | 2420 |  |  | 2486.5 |  |  | 2597.5 |  |  | 2276 |  |  | 2531.5 |  |  | 2363.5 |  |  | 2414 |  |  | 2386.5 |  |  | 2542.5 |  |  | 2458.5 |  |  | 2471.5 |  |  | 2285.5 |  |  | 2540.5 |  |  | 2306.5 |  |  | 2364.5 |  |  | 2287.5 |  |  | 2289.5 |  |  | 2552.5 |  |  | 2503 |  |  | 2405 |  |  | 2462.5 |  |  | 2380.5 |  |  | 2427
82 |  | 2360.5 |  |  | 2527.5 |  |  | 2452 |  |  | 2357.5 |  |  | 2580.5 |  |  | 2438.5 |  |  | 2465.5 |  |  | 2438.5 |  |  | 2389.5 |  |  | 2415.5 |  |  | 2332 |  |  | 2502.5 |  |  | 2464.5 |  |  | 2278.5 |  |  | 2244 |  |  | 2474.5 |  |  | 2525.5 |  |  | 2378.5 |  |  | 2510.5 |  |  | 2350.5 |  |  | 2522.5 |  |  | 2427.5 |  |  | 2477.5 |  |  | 2320.5 |  |  | 2230 |  |  | 2487.5 |  |  | 2438.5 |  |  | 2367.5 |  |  | 2509.5 |  |  | 2266 |  |  | 2424 |  |  | 2533.5 |  |  | 2230.5 |  |  | 2453.5 |  |  | 2324.5 |  |  | 2479 |  |  | 2378.5 |  |  | 2548 |  |  | 2425.5 |  |  | 2390.5 |  |  | 2221.5 |  |  | 2461.5 |  |  | 2301.5 |  |  | 2419 |  |  | 2611.5 |  |  | 2501 |  |  | 2424.5 |  |  | 2499.5 |  |  | 2488.5 |  |  | 2427.5 |  |  | 2298.5 |  |  | 2453.5 |  |  | 2410.5 |  |  | 2375.5 |  |  | 2499.5 |  |  | 2450.5 |  |  | 2291.5 |  |  | 2425 |  |  | 2448.5 |  |  | 2412.5 |  |  | 2393 |  |  | 2387.5 |  |  | 2478.5 |  |  | 2350.5 |  |  | 2326.5 |  |  | 2464 |  |  | 2541.5 |  |  | 2315 |  |  | 2271.5 |  |  | 2476.5 |  |  | 2392 |  |  | 2352.5 |  |  | 2401.5 |  |  | 2560.5 |  |  | 2532 |  |  | 2490 |  |  | 2298.5 |  |  | 2326.5 |  |  | 2309.5 |  |  | 2453.5 |  |  | 2374 |  |  | 2443.5 |  |  | 2473.5 |  |  | 2499.5 |  |  | 2513.5 |  |  | 2331.5 |  |  | 2500.5 |  |  | 2380.5 |  |  | 2389.5 |  |  | 2441.5 |  |  | 2418.5 |  |  | 2436 |  |  | 2316.5 |  |  | 2304 |  |  | 2375 |  |  | 2316 |  |  | 2566.5 |  |  | 2530.5 |  |  | 2306.5 |  |  | 2556.5 |  |  | 2334.5 |  |  | 2357 |  |  | 2383 |  |  | 2372.5 |  |  | 2386.5 |  |  | 2326.5 |  |  | 2420.5 |  |  | 2517.5 |  |  | 2492.5 |  |  | 2499.5 |  |  | 2508.5 |  |  | 2509.5 |  |  | 2392.5 |  |  | 2425.5 |  |  | 2471.5 |  |  | 2463.5 |  |  | 2516.5 |  |  | 2349.5 |  |  | 2417.5 |  |  | 2375.5 |  |  | 2447.5 |  |  | 2489.5 |  |  | 2461.5 |  |  | 2441.5 |  |  | 2377.5 |  |  | 2385 |  |  | 2371.5 |  |  | 2394.5 |  |  | 2337.5 |  |  | 2421.5 |  |  | 2492.5 |  |  | 2437 |  |  | 2359.5 |  |  | 2523.5 |  |  | 2345.5 |  |  | 2344.5 |  |  | 2465 |  |  | 2433.5 |  |  | 2495.5 |  |  | 2317 |  |  | 2451.5 |  |  | 2253 |  |  | 2506 |  |  | 2513.5 |  |  | 2455 |  |  | 2568.5 |  |  | 2339.5 |  |  | 2445.5 |  |  | 2334.5 |  |  | 2412.5 |  |  | 2470.5 |  |  | 2416.5 |  |  | 2452.5 |  |  | 2515.5 |  |  | 2452.5 |  |  | 2513 |  |  | 2342.5 |  |  | 2266 |  |  | 2343.5 |  |  | 2425.5 |  |  | 2342 |  |  | 2403.5 |  |  | 2354.5 |  |  | 2361.5 |  |  | 2295 |  |  | 2388.5 |  |  | 2271.5 |  |  | 2297.5 |  |  | 2527.5 |  |  | 2374.5 |  |  | 2356.5 |  |  | 2377 |  |  | 2426.5 |  |  | 2384.5 |  |  | 2320.5 |  |  | 2431.5 |  |  | 2415.5 |  |  | 2473.5 |  |  | 2358.5 |  |  | 2497 |  |  | 2439.5 |  |  | 2447.5 |  |  | 2487.5 |  |  | 2477.5 |  |  | 2368.5 |  |  | 2511.5 |  |  | 2473.5 |  |  | 2355.5 |  |  | 2554.5 |  |  | 2361.5 |  |  | 2469.5 |  |  | 2225.5 |  |  | 2207.5 |  |  | 2320 |  |  | 2353.5 |  |  | 2430.5 |  |  | 2401.5 |  |  | 2483.5 |  |  | 2504.5 |  |  | 2542.5 |  |  | 2510.5 |  |  | 2383.5 |  |  | 2426.5 |  |  | 2386.5 |  |  | 2312.5 |  |  | 2516.5 |  |  | 2433.5 |  |  | 2381.5 |  |  | 2409.5 |  |  | 2431.5 |  |  | 2449 |  |  | 2556.5 |  |  | 2398.5 |  |  | 2137 |  |  | 2561.5 |  |  | 2565 |  |  | 2261.5 |  |  | 2425.5 |  |  | 2488.5 |  |  | 2508.5 |  |  | 2385.5 |  |  | 2403.5 |  |  | 2374.5 |  |  | 2244.5 |  |  | 2262 |  |  | 2322.5 |  |  | 2253.5 |  |  | 2461.5 |  |  | 2357.5 |  |  | 2419 |  |  | 2392.5 |  |  | 2360.5 |  |  | 2510.5 |  |  | 2395.5 |  |  | 2536.5 |  |  | 2417.5 |  |  | 2429.5 |  |  | 2533.5 |  |  | 2525 |  |  | 2489 |  |  | 2391.5 |  |  | 2329.5 |  |  | 2451.5 |  |  | 2375 |  |  | 2552.5 |  |  | 2408.5 |  |  | 2387.5 |  |  | 2278 |  |  | 2536.5 |  |  | 2435.5 |  |  | 2250.5 |  |  | 2318.5 |  |  | 2364.5 |  |  | 2428.5 |  |  | 2473.5 |  |  | 2425.5 |  |  | 2521.5 |  |  | 2210 |  |  | 2321.5 |  |  | 2505.5 |  |  | 2429.5 |  |  | 2421.5 |  |  | 2353.5 |  |  | 2573 |  |  | 2324.5 |  |  | 2503.5 |  |  | 2495 |  |  | 2518.5 |  |  | 2404.5 |  |  | 2663 |  |  | 2490.5 |  |  | 2490.5 |  |  | 2557.5 |  |  | 2356.5 |  |  | 2387 |  |  | 2410 |  |  | 2416.5 |  |  | 2347.5 |  |  | 2486.5 |  |  | 2382.5 |  |  | 2593.5 |  |  | 2477.5 |  |  | 2407 |  |  | 2384.5 |  |  | 2322.5 |  |  | 2384 |  |  | 2388.5 |  |  | 2253.5 |  |  | 2442 |  |  | 2486.5 |  |  | 2288.5 |  |  | 2452.5 |  |  | 2423 |  |  | 2447.5 |  |  | 2333 |  |  | 2524.5 |  |  | 2328.5 |  |  | 2426.5 |  |  | 2373 |  |  | 2346.5 |  |  | 2539.5 |  |  | 2540.5 |  |  | 2438 |  |  | 2368.5 |  |  | 2227.5 |  |  | 2518.5 |  |  | 2556.5 |  |  | 2392.5 |  |  | 2451 |  |  | 2348.5 |  |  | 2509.5 |  |  | 2470.5 |  |  | 2374 |  |  | 2422 |  |  | 2586.5 |  |  | 2361.5 |  |  | 2277.5 |  |  | 2438.5 |  |  | 2412.5 |  |  | 2415.5 |  |  | 2429.5 |  |  | 2511.5 |  |  | 2326.5 |  |  | 2430.5 |  |  | 2430 |  |  | 2388.5 |  |  | 2455.5 |  |  | 2637.5 |  |  | 2555.5 |  |  | 2443 |  |  | 2383.5 |  |  | 2535.5 |  |  | 2429.5 |  |  | 2255.5 |  |  | 2537.5 |  |  | 2265 |  |  | 2450 |  |  | 2301 |  |  | 2495 |  |  | 2304.5 |  |  | 2429 |  |  | 2425.5 |  |  | 2428 |  |  | 2426.5 |  |  | 2527.5 |  |  | 2409.5 |  |  | 2404.5 |  |  | 2371.5 |  |  | 2454 |  |  | 2458.5 |  |  | 2556.5 |  |  | 2397.5 |  |  | 2400 |  |  | 2525.5 |  |  | 2397.5 |  |  | 2405.5 |  |  | 2476 |  |  | 2380.5 |  |  | 2324.5 |  |  | 2504.5 |  |  | 2328.5 |  |  | 2428.5 |  |  | 2346.5 |  |  | 2477.5 |  |  | 2423.5 |  |  | 2462.5 |  |  | 2286.5 |  |  | 2344 |  |  | 2373.5 |  |  | 2385.5 |  |  | 2293.5 |  |  | 2461.5 |  |  | 2516.5 |  |  | 2391 |  |  | 2463.5 |  |  | 2507 |  |  | 2350 |  |  | 2299.5 |  |  | 2483.5 |  |  | 2314.5 |  |  | 2394 |  |  | 2461.5 |  |  | 2450.5 |  |  | 2398.5 |  |  | 2304 |  |  | 2350.5 |  |  | 2267.5 |  |  | 2365.5 |  |  | 2303.5 |  |  | 2343.5 |  |  | 2345 |  |  | 2350.5 |  |  | 2468 |  |  | 2456.5 |  |  | 2244.5 |  |  | 2389.5 |  |  | 2435 |  |  | 2359.5 |  |  | 2352 |  |  | 2322 |  |  | 2388.5 |  |  | 2296.5 |  |  | 2345.5 |  |  | 2575.5 |  |  | 2584 |  |  | 2507.5 |  |  | 2415.5 |  |  | 2204.5 |  |  | 2391 |  |  | 2447.5 |  |  | 2390.5 |  |  | 2174.5 |  |  | 2417.5 |  |  | 2572 |  |  | 2306.5 |  |  | 2379.5 |  |  | 2405.5 |  |  | 2465.5 |  |  | 2410.5 |  |  | 2416.5 |  |  | 2513 |  |  | 2370.5 |  |  | 2329.5 |  |  | 2394 |  |  | 2306.5 |  |  | 2271.5 |  |  | 2408.5 |  |  | 2405 |  |  | 2470.5 |  |  | 2409.5 |  |  | 2416.5 |  |  | 2335.5 |  |  | 2428.5 |  |  | 2488 |  |  | 2330 |  |  | 2414.5 |  |  | 2492.5 |  |  | 2482.5 |  |  | 2264.5 |  |  | 2212 |  |  | 2506 |  |  | 2355 |  |  | 2507.5 |  |  | 2392 |  |  | 2433.5 |  |  | 2533.5 |  |  | 2486 |  |  | 2292.5 |  |  | 2421.5 |  |  | 2362.5 |  |  | 2447.5 |  |  | 2144.5 |  |  | 2438 |  |  | 2523 |  |  | 2339.5 |  |  | 2502.5 |  |  | 2319 |  |  | 2308.5 |  |  | 2399.5 |  |  | 2386 |  |  | 2538.5 |  |  | 2520.5 |  |  | 2334 |  |  | 2449.5 |  |  | 2457.5 |  |  | 2521 |  |  | 2342.5 |  |  | 2312 |  |  | 2563.5 |  |  | 2538 |  |  | 2363.5 |  |  | 2315.5 |  |  | 2351.5 |  |  | 2395.5 |  |  | 2430.5 |  |  | 2311.5 |  |  | 2461 |  |  | 2346.5 |  |  | 2439.5 |  |  | 2333.5 |  |  | 2378.5 |  |  | 2411.5 |  |  | 2351 |  |  | 2367.5 |  |  | 2431 |  |  | 2378.5 |  |  | 2291.5 |  |  | 2471.5 |  |  | 2422.5 |  |  | 2460.5 |  |  | 2399.5 |  |  | 2333.5 |  |  | 2480.5 |  |  | 2290.5 |  |  | 2331 |  |  | 2452.5 |  |  | 2303 |  |  | 2422 |  |  | 2416.5 |  |  | 2171 |  |  | 2252.5 |  |  | 2472.5 |  |  | 2497.5 |  |  | 2467.5 |  |  | 2497.5 |  |  | 2443.5 |  |  | 2437.5 |  |  | 2364 |  |  | 2558 |  |  | 2287.5 |  |  | 2410.5 |  |  | 2397 |  |  | 2317.5 |  |  | 2332.5 |  |  | 2337.5 |  |  | 2305.5 |  |  | 2361.5 |  |  | 2285 |  |  | 2418.5 |  |  | 2378.5 |  |  | 2324.5 |  |  | 2369 |  |  | 2472.5 |  |  | 2485.5 |  |  | 2436.5 |  |  | 2604.5 |  |  | 2443.5 |  |  | 2323.5 |  |  | 2459.5 |  |  | 2036.5 |  |  | 2414.5 |  |  | 2285 |  |  | 2525.5 |  |  | 2421.5 |  |  | 2493.5 |  |  | 2281.5 |  |  | 2396.5 |  |  | 2336.5 |  |  | 2324.5 |  |  | 2254 |  |  | 2322.5 |  |  | 2405.5 |  |  | 2408.5 |  |  | 2402 |  |  | 2489.5 |  |  | 2335 |  |  | 2259.5 |  |  | 2415.5 |  |  | 2331.5 |  |  | 2443 |  |  | 2263.5 |  |  | 2400 |  |  | 2376 |  |  | 2426.5 |  |  | 2399 |  |  | 2557 |  |  | 2477.5 |  |  | 2467.5 |  |  | 2305.5 |  |  | 2461 |  |  | 2474.5 |  |  | 2338.5 |  |  | 2292.5 |  |  | 2504.5 |  |  | 2371.5 |  |  | 2375.5 |  |  | 2363.5 |  |  | 2441.5 |  |  | 2351 |  |  | 2580.5 |  |  | 2371 |  |  | 2419.5 |  |  | 2322.5 |  |  | 2515.5 |  |  | 2419 |  |  | 2478 |  |  | 2520 |  |  | 2420.5 |  |  | 2374 |  |  | 2455.5 |  |  | 2545.5 |  |  | 2408.5 |  |  | 2364.5 |  |  | 2295.5 |  |  | 2527.5 |  |  | 2533.5 |  |  | 2482.5 |  |  | 2445 |  |  | 2266.5 |  |  | 2266.5 |  |  | 2407.5 |  |  | 2358.5 |  |  | 2348 |  |  | 2403.5 |  |  | 2447 |  |  | 2418.5 |  |  | 2442.5 |  |  | 2344.5 |  |  | 2301.5 |  |  | 2267 |  |  | 2381.5 |  |  | 2161 |  |  | 2322.5 |  |  | 2472.5 |  |  | 2558.5 |  |  | 2402.5 |  |  | 2412.5 |  |  | 2451.5 |  |  | 2369.5 |  |  | 2457.5 |  |  | 2368.5 |  |  | 2323 |  |  | 2440.5 |  |  | 2397.5 |  |  | 2359.5 |  |  | 2434.5 |  |  | 2466.5 |  |  | 2335 |  |  | 2329 |  |  | 2390.5 |  |  | 2364 |  |  | 2537.5 |  |  | 2329.5 |  |  | 2505.5 |  |  | 2448.5 |  |  | 2358.5 |  |  | 2505.5 |  |  | 2426.5 |  |  | 2473.5 |  |  | 2425 |  |  | 2412.5 |  |  | 2614.5 |  |  | 2359.5 |  |  | 2255 |  |  | 2407.5 |  |  | 2338.5 |  |  | 2536 |  |  | 2363 |  |  | 2391.5 |  |  | 2380 |  |  | 2217 |  |  | 2261.5 |  |  | 2476 |  |  | 2623.5 |  |  | 2384.5 |  |  | 2503.5 |  |  | 2380.5 |  |  | 2311.5 |  |  | 2387.5 |  |  | 2204.5 |  |  | 2318.5 |  |  | 2414.5 |  |  | 2341.5 |  |  | 2328 |  |  | 2286 |  |  | 2501.5 |  |  | 2524.5 |  |  | 2376.5 |  |  | 2457.5 |  |  | 2395.5 |  |  | 2450.5 |  |  | 2437.5 |  |  | 2334.5 |  |  | 2653 |  |  | 2332.5 |  |  | 2398 |  |  | 2338.5 |  |  | 2532.5 |  |  | 2478.5 |  |  | 2522 |  |  | 2396.5 |  |  | 2329.5 |  |  | 2446 |  |  | 2470.5 |  |  | 2379.5 |  |  | 2455.5 |  |  | 2394.5 |  |  | 2381.5 |  |  | 2438.5 |  |  | 2451 |  |  | 2365.5 |  |  | 2399.5 |  |  | 2525.5 |  |  | 2450.5 |  |  | 2408 |  |  | 2413.5 |  |  | 2543.5 |  |  | 2389 |  |  | 2409.5 |  |  | 2500.5 |  |  | 2469 |  |  | 2495.5 |  |  | 2530.5 |  |  | 2394.5 |  |  | 2372 |  |  | 2275.5 |  |  | 2399.5 |  |  | 2325 |  |  | 2434.5 |  |  | 2421.5 |  |  | 2424.5 |  |  | 2243.5 |  |  | 2433.5 |  |  | 2537.5 |  |  | 2332.5 |  |  | 2392 |  |  | 2328 |  |  | 2256.5 |  |  | 2491.5 |  |  | 2289.5 |  |  | 2519 |  |  | 2580.5 |  |  | 2362.5 |  |  | 2379.5 |  |  | 2242.5 |  |  | 2414.5 |  |  | 2483.5 |  |  | 2301.5 |  |  | 2461.5 |  |  | 2195.5 |  |  | 2428 |  |  | 2359.5 |  |  | 2227.5 |  |  | 2376.5 |  |  | 2440.5 |  |  | 2568.5 |  |  | 2475.5 |  |  | 2414.5 |  |  | 2409.5 |  |  | 2252.5 |  |  | 2504.5 |  |  | 2402.5 |  |  | 2298.5 |  |  | 2405.5 |  |  | 2498 |  |  | 2410.5 |  |  | 2474.5 |  |  | 2372 |  |  | 2460.5 |  |  | 2484.5 |  |  | 2539 |  |  | 2457.5 |  |  | 2499.5 |  |  | 2608.5 |  |  | 2555 |  |  | 2319.5 |  |  | 2511.5 |  |  | 2429.5 |  |  | 2213.5 |  |  | 2500.5 |  |  | 2326 |  |  | 2374.5 |  |  | 2497 |  |  | 2453 |  |  | 2486.5 |  |  | 2415.5 |  |  | 2340.5 |  |  | 2174.5 |  |  | 2325.5 |  |  | 2494.5 |  |  | 2346 |  |  | 2385.5 |  |  | 2355 |  |  | 2369.5 |  |  | 2412 |  |  | 2318 |  |  | 2500 |  |  | 2473.5 |  |  | 2337 |  |  | 2576.5 |  |  | 2448.5 |  |  | 2395.5 |  |  | 2584.5 |  |  | 2284.5 |  |  | 2494 |  |  | 2451.5 |  |  | 2485.5 |  |  | 2606.5 |  |  | 2412 |  |  | 2394.5 |  |  | 2341.5 |  |  | 2431.5 |  |  | 2484.5 |  |  | 2395 |  |  | 2476 |  |  | 2391 |  |  | 2393.5 |  |  | 2541 |  |  | 2459 |  |  | 2476.5 |  |  | 2339.5 |  |  | 2295.5 |  |  | 2423.5 |  |  | 2423.5 |  |  | 2419.5 |  |  | 2502.5 |  |  | 2387.5 |  |  | 2352.5 |  |  | 2323 |  |  | 2346.5 |  |  | 2316 |  |  | 2415.5 |  |  | 2406.5 |  |  | 2433.5 |  |  | 2461.5 |  |  | 2528 |  |  | 2438.5 |  |  | 2425 |  |  | 2353.5 |  |  | 2470.5 |  |  | 2284 |  |  | 2357 |  |  | 2487.5 |  |  | 2446 |  |  | 2425.5 |  |  | 2291.5 |  |  | 2311.5 |  |  | 2356.5 |  |  | 2461.5 |  |  | 2465.5 |  |  | 2285.5 |  |  | 2357 |  |  | 2466.5 |  |  | 2463.5 |  |  | 2426.5 |  |  | 2470.5 |  |  | 2355.5 |  |  | 2464.5 |  |  | 2569.5 |  |  | 2408.5 |  |  | 2557.5 |  |  | 2528.5 |  |  | 2281.5 |  |  | 2292.5 |  |  | 2415 |  |  | 2304.5 |  |  | 2346.5 |  |  | 2491 |  |  | 2301.5 |  |  | 2321.5 |  |  | 2400.5 |  |  | 2301.5 |  |  | 2627 |  |  | 2546.5 |  |  | 2340.5 |  |  | 2281.5 |  |  | 2544.5 |  |  | 2345 |  |  | 2356.5 |  |  | 2527.5 |  |  | 2345.5 |  |  | 2490.5 |  |  | 2335.5 |  |  | 2312.5 |  |  | 2515.5 |  |  | 2408.5 |  |  | 2434.5 |  |  | 2454.5 |  |  | 2474.5 |  |  | 2467 |  |  | 2443.5 |  |  | 2358.5 |  |  | 2467.5 |  |  | 2501.5 |  |  | 2332.5 |  |  | 2385.5 |  |  | 2471 |  |  | 2480.5 |  |  | 2333 |  |  | 2304.5 |  |  | 2460.5 |  |  | 2482.5 |  |  | 2427 |  |  | 2332 |  |  | 2461.5 |  |  | 2478.5 |  |  | 2176.5 |  |  | 2551.5 |  |  | 2417.5 |  |  | 2447.5 |  |  | 2334.5 |  |  | 2501.5 |  |  | 2326.5 |  |  | 2517.5 |  |  | 2419.5 |  |  | 2473.5 |  |  | 2319.5 |  |  | 2413.5 |  |  | 2525.5 |  |  | 2401.5 |  |  | 2373.5 |  |  | 2418.5 |  |  | 2372.5 |  |  | 2374.5 |  |  | 2469.5 |  |  | 2476.5 |  |  | 2421 |  |  | 2504.5 |  |  | 2424.5 |  |  | 2449.5 |  |  | 2431 |  |  | 2472.5 |  |  | 2394.5 |  |  | 2498.5 |  |  | 2434.5 |  |  | 2426 |  |  | 2280.5 |  |  | 2319.5 |  |  | 2300 |  |  | 2383 |  |  | 2400 |  |  | 2384.5 |  |  | 2396.5 |  |  | 2463.5 |  |  | 2619.5 |  |  | 2482 |  |  | 2472.5 |  |  | 2408.5 |  |  | 2264 |  |  | 2371 |  |  | 2433.5 |  |  | 2487.5 |  |  | 2509 |  |  | 2434.5 |  |  | 2512 |  |  | 2343.5 |  |  | 2332.5 |  |  | 2539 |  |  | 2496.5 |  |  | 2445.5 |  |  | 2288.5 |  |  | 2517 |  |  | 2316.5 |  |  | 2316.5 |  |  | 2334.5 |  |  | 2397.5 |  |  | 2424.5 |  |  | 2473.5 |  |  | 2340.5 |  |  | 2437.5 |  |  | 2513.5 |  |  | 2422.5 |  |  | 2391 |  |  | 2413.5 |  |  | 2450.5 |  |  | 2465.5 |  |  | 2502.5 |  |  | 2384.5 |  |  | 2431.5 |  |  | 2545.5 |  |  | 2395.5 |  |  | 2524 |  |  | 2373.5 |  |  | 2381 |  |  | 2607.5 |  |  | 2623.5 |  |  | 2614.5 |  |  | 2334.5 |  |  | 2337.5 |  |  | 2447.5 |  |  | 2308.5 |  |  | 2436.5 |  |  | 2435 |  |  | 2320.5 |  |  | 2431 |  |  | 2294.5 |  |  | 2357.5 |  |  | 2445.5 |  |  | 2470 |  |  | 2349.5 |  |  | 2448.5 |  |  | 2167 |  |  | 2407.5 |  |  | 2366 |  |  | 2422.5 |  |  | 2336.5 |  |  | 2355.5 |  |  | 2441 |  |  | 2501.5 |  |  | 2626.5 |  |  | 2291 |  |  | 2578.5 |  |  | 2410.5 |  |  | 2443 |  |  | 2425.5 |  |  | 2557.5 |  |  | 2473.5 |  |  | 2495.5 |  |  | 2324.5 |  |  | 2564.5 |  |  | 2332.5 |  |  | 2390.5 |  |  | 2326.5 |  |  | 2328.5 |  |  | 2576.5 |  |  | 2527 |  |  | 2444 |  |  | 2501.5 |  |  | 2401.5 |  |  | 2453
83 |  | 2384.5 |  |  | 2556.5 |  |  | 2491 |  |  | 2396.5 |  |  | 2604.5 |  |  | 2477.5 |  |  | 2489.5 |  |  | 2477.5 |  |  | 2436.5 |  |  | 2439.5 |  |  | 2356 |  |  | 2526.5 |  |  | 2488.5 |  |  | 2317.5 |  |  | 2291 |  |  | 2489.5 |  |  | 2546.5 |  |  | 2404.5 |  |  | 2525.5 |  |  | 2389.5 |  |  | 2561.5 |  |  | 2451.5 |  |  | 2516.5 |  |  | 2367.5 |  |  | 2245 |  |  | 2516.5 |  |  | 2459.5 |  |  | 2382.5 |  |  | 2524.5 |  |  | 2305 |  |  | 2453 |  |  | 2559.5 |  |  | 2251.5 |  |  | 2468.5 |  |  | 2348.5 |  |  | 2500 |  |  | 2393.5 |  |  | 2569 |  |  | 2454.5 |  |  | 2416.5 |  |  | 2250.5 |  |  | 2482.5 |  |  | 2330.5 |  |  | 2434 |  |  | 2637.5 |  |  | 2540 |  |  | 2448.5 |  |  | 2520.5 |  |  | 2512.5 |  |  | 2466.5 |  |  | 2327.5 |  |  | 2479.5 |  |  | 2457.5 |  |  | 2422.5 |  |  | 2523.5 |  |  | 2465.5 |  |  | 2306.5 |  |  | 2440 |  |  | 2474.5 |  |  | 2451.5 |  |  | 2417 |  |  | 2434.5 |  |  | 2517.5 |  |  | 2389.5 |  |  | 2341.5 |  |  | 2485 |  |  | 2580.5 |  |  | 2339 |  |  | 2310.5 |  |  | 2497.5 |  |  | 2416 |  |  | 2367.5 |  |  | 2422.5 |  |  | 2581.5 |  |  | 2561 |  |  | 2529 |  |  | 2319.5 |  |  | 2347.5 |  |  | 2333.5 |  |  | 2474.5 |  |  | 2398 |  |  | 2490.5 |  |  | 2512.5 |  |  | 2520.5 |  |  | 2560.5 |  |  | 2352.5 |  |  | 2539.5 |  |  | 2419.5 |  |  | 2415.5 |  |  | 2462.5 |  |  | 2444.5 |  |  | 2451 |  |  | 2342.5 |  |  | 2319 |  |  | 2399 |  |  | 2337 |  |  | 2587.5 |  |  | 2554.5 |  |  | 2330.5 |  |  | 2603.5 |  |  | 2363.5 |  |  | 2396 |  |  | 2404 |  |  | 2419.5 |  |  | 2433.5 |  |  | 2373.5 |  |  | 2467.5 |  |  | 2538.5 |  |  | 2521.5 |  |  | 2523.5 |  |  | 2555.5 |  |  | 2530.5 |  |  | 2413.5 |  |  | 2440.5 |  |  | 2510.5 |  |  | 2502.5 |  |  | 2545.5 |  |  | 2370.5 |  |  | 2432.5 |  |  | 2404.5 |  |  | 2486.5 |  |  | 2515.5 |  |  | 2476.5 |  |  | 2456.5 |  |  | 2424.5 |  |  | 2406 |  |  | 2395.5 |  |  | 2415.5 |  |  | 2366.5 |  |  | 2468.5 |  |  | 2513.5 |  |  | 2466 |  |  | 2388.5 |  |  | 2544.5 |  |  | 2392.5 |  |  | 2370.5 |  |  | 2494 |  |  | 2462.5 |  |  | 2542.5 |  |  | 2343 |  |  | 2490.5 |  |  | 2282 |  |  | 2545 |  |  | 2552.5 |  |  | 2479 |  |  | 2589.5 |  |  | 2363.5 |  |  | 2484.5 |  |  | 2373.5 |  |  | 2438.5 |  |  | 2496.5 |  |  | 2440.5 |  |  | 2467.5 |  |  | 2536.5 |  |  | 2491.5 |  |  | 2552 |  |  | 2366.5 |  |  | 2290 |  |  | 2369.5 |  |  | 2449.5 |  |  | 2357 |  |  | 2442.5 |  |  | 2369.5 |  |  | 2400.5 |  |  | 2324 |  |  | 2427.5 |  |  | 2297.5 |  |  | 2336.5 |  |  | 2548.5 |  |  | 2421.5 |  |  | 2403.5 |  |  | 2392 |  |  | 2452.5 |  |  | 2405.5 |  |  | 2341.5 |  |  | 2470.5 |  |  | 2439.5 |  |  | 2502.5 |  |  | 2405.5 |  |  | 2536 |  |  | 2478.5 |  |  | 2471.5 |  |  | 2508.5 |  |  | 2524.5 |  |  | 2407.5 |  |  | 2526.5 |  |  | 2499.5 |  |  | 2394.5 |  |  | 2583.5 |  |  | 2382.5 |  |  | 2498.5 |  |  | 2264.5 |  |  | 2246.5 |  |  | 2349 |  |  | 2379.5 |  |  | 2459.5 |  |  | 2448.5 |  |  | 2509.5 |  |  | 2519.5 |  |  | 2589.5 |  |  | 2549.5 |  |  | 2422.5 |  |  | 2465.5 |  |  | 2412.5 |  |  | 2351.5 |  |  | 2537.5 |  |  | 2448.5 |  |  | 2407.5 |  |  | 2433.5 |  |  | 2452.5 |  |  | 2496 |  |  | 2571.5 |  |  | 2413.5 |  |  | 2163 |  |  | 2608.5 |  |  | 2604 |  |  | 2308.5 |  |  | 2464.5 |  |  | 2512.5 |  |  | 2555.5 |  |  | 2400.5 |  |  | 2418.5 |  |  | 2421.5 |  |  | 2283.5 |  |  | 2277 |  |  | 2343.5 |  |  | 2292.5 |  |  | 2476.5 |  |  | 2396.5 |  |  | 2466 |  |  | 2413.5 |  |  | 2375.5 |  |  | 2534.5 |  |  | 2421.5 |  |  | 2562.5 |  |  | 2456.5 |  |  | 2444.5 |  |  | 2580.5 |  |  | 2551 |  |  | 2510 |  |  | 2406.5 |  |  | 2344.5 |  |  | 2477.5 |  |  | 2414 |  |  | 2599.5 |  |  | 2429.5 |  |  | 2426.5 |  |  | 2317 |  |  | 2575.5 |  |  | 2450.5 |  |  | 2276.5 |  |  | 2347.5 |  |  | 2393.5 |  |  | 2467.5 |  |  | 2520.5 |  |  | 2464.5 |  |  | 2542.5 |  |  | 2225 |  |  | 2342.5 |  |  | 2529.5 |  |  | 2468.5 |  |  | 2445.5 |  |  | 2392.5 |  |  | 2620 |  |  | 2363.5 |  |  | 2529.5 |  |  | 2521 |  |  | 2544.5 |  |  | 2451.5 |  |  | 2684 |  |  | 2514.5 |  |  | 2505.5 |  |  | 2604.5 |  |  | 2382.5 |  |  | 2426 |  |  | 2431 |  |  | 2437.5 |  |  | 2373.5 |  |  | 2533.5 |  |  | 2403.5 |  |  | 2617.5 |  |  | 2516.5 |  |  | 2454 |  |  | 2399.5 |  |  | 2361.5 |  |  | 2399 |  |  | 2409.5 |  |  | 2292.5 |  |  | 2471 |  |  | 2510.5 |  |  | 2335.5 |  |  | 2478.5 |  |  | 2470 |  |  | 2468.5 |  |  | 2348 |  |  | 2550.5 |  |  | 2354.5 |  |  | 2447.5 |  |  | 2397 |  |  | 2361.5 |  |  | 2565.5 |  |  | 2555.5 |  |  | 2477 |  |  | 2392.5 |  |  | 2256.5 |  |  | 2557.5 |  |  | 2595.5 |  |  | 2416.5 |  |  | 2490 |  |  | 2363.5 |  |  | 2535.5 |  |  | 2485.5 |  |  | 2400 |  |  | 2446 |  |  | 2633.5 |  |  | 2390.5 |  |  | 2298.5 |  |  | 2477.5 |  |  | 2433.5 |  |  | 2430.5 |  |  | 2455.5 |  |  | 2558.5 |  |  | 2365.5 |  |  | 2459.5 |  |  | 2469 |  |  | 2427.5 |  |  | 2494.5 |  |  | 2684.5 |  |  | 2594.5 |  |  | 2464 |  |  | 2430.5 |  |  | 2561.5 |  |  | 2468.5 |  |  | 2302.5 |  |  | 2558.5 |  |  | 2286 |  |  | 2497 |  |  | 2327 |  |  | 2534 |  |  | 2330.5 |  |  | 2444 |  |  | 2446.5 |  |  | 2457 |  |  | 2441.5 |  |  | 2566.5 |  |  | 2424.5 |  |  | 2443.5 |  |  | 2395.5 |  |  | 2478 |  |  | 2473.5 |  |  | 2577.5 |  |  | 2444.5 |  |  | 2439 |  |  | 2554.5 |  |  | 2426.5 |  |  | 2434.5 |  |  | 2500 |  |  | 2419.5 |  |  | 2348.5 |  |  | 2543.5 |  |  | 2352.5 |  |  | 2449.5 |  |  | 2370.5 |  |  | 2492.5 |  |  | 2444.5 |  |  | 2486.5 |  |  | 2312.5 |  |  | 2391 |  |  | 2394.5 |  |  | 2409.5 |  |  | 2332.5 |  |  | 2490.5 |  |  | 2540.5 |  |  | 2430 |  |  | 2502.5 |  |  | 2546 |  |  | 2389 |  |  | 2314.5 |  |  | 2504.5 |  |  | 2361.5 |  |  | 2441 |  |  | 2500.5 |  |  | 2489.5 |  |  | 2445.5 |  |  | 2328 |  |  | 2389.5 |  |  | 2282.5 |  |  | 2389.5 |  |  | 2327.5 |  |  | 2364.5 |  |  | 2384 |  |  | 2376.5 |  |  | 2494 |  |  | 2480.5 |  |  | 2268.5 |  |  | 2404.5 |  |  | 2456 |  |  | 2385.5 |  |  | 2373 |  |  | 2348 |  |  | 2417.5 |  |  | 2322.5 |  |  | 2371.5 |  |  | 2599.5 |  |  | 2610 |  |  | 2546.5 |  |  | 2444.5 |  |  | 2225.5 |  |  | 2420 |  |  | 2494.5 |  |  | 2405.5 |  |  | 2213.5 |  |  | 2456.5 |  |  | 2611 |  |  | 2330.5 |  |  | 2394.5 |  |  | 2452.5 |  |  | 2504.5 |  |  | 2449.5 |  |  | 2445.5 |  |  | 2528 |  |  | 2394.5 |  |  | 2368.5 |  |  | 2441 |  |  | 2353.5 |  |  | 2310.5 |  |  | 2423.5 |  |  | 2434 |  |  | 2485.5 |  |  | 2456.5 |  |  | 2445.5 |  |  | 2364.5 |  |  | 2443.5 |  |  | 2503 |  |  | 2354 |  |  | 2438.5 |  |  | 2539.5 |  |  | 2503.5 |  |  | 2290.5 |  |  | 2233 |  |  | 2532 |  |  | 2384 |  |  | 2546.5 |  |  | 2413 |  |  | 2448.5 |  |  | 2562.5 |  |  | 2512 |  |  | 2313.5 |  |  | 2468.5 |  |  | 2391.5 |  |  | 2494.5 |  |  | 2191.5 |  |  | 2453 |  |  | 2544 |  |  | 2360.5 |  |  | 2523.5 |  |  | 2334 |  |  | 2347.5 |  |  | 2423.5 |  |  | 2401 |  |  | 2585.5 |  |  | 2567.5 |  |  | 2358 |  |  | 2496.5 |  |  | 2481.5 |  |  | 2545 |  |  | 2381.5 |  |  | 2351 |  |  | 2584.5 |  |  | 2553 |  |  | 2384.5 |  |  | 2354.5 |  |  | 2377.5 |  |  | 2442.5 |  |  | 2445.5 |  |  | 2332.5 |  |  | 2485 |  |  | 2375.5 |  |  | 2478.5 |  |  | 2372.5 |  |  | 2417.5 |  |  | 2450.5 |  |  | 2372 |  |  | 2393.5 |  |  | 2470 |  |  | 2417.5 |  |  | 2317.5 |  |  | 2500.5 |  |  | 2469.5 |  |  | 2499.5 |  |  | 2420.5 |  |  | 2357.5 |  |  | 2501.5 |  |  | 2329.5 |  |  | 2355 |  |  | 2491.5 |  |  | 2329 |  |  | 2446 |  |  | 2445.5 |  |  | 2210 |  |  | 2273.5 |  |  | 2501.5 |  |  | 2518.5 |  |  | 2488.5 |  |  | 2536.5 |  |  | 2482.5 |  |  | 2476.5 |  |  | 2403 |  |  | 2584 |  |  | 2311.5 |  |  | 2439.5 |  |  | 2436 |  |  | 2356.5 |  |  | 2371.5 |  |  | 2384.5 |  |  | 2320.5 |  |  | 2408.5 |  |  | 2309 |  |  | 2439.5 |  |  | 2407.5 |  |  | 2350.5 |  |  | 2416 |  |  | 2487.5 |  |  | 2511.5 |  |  | 2465.5 |  |  | 2651.5 |  |  | 2472.5 |  |  | 2362.5 |  |  | 2474.5 |  |  | 2051.5 |  |  | 2438.5 |  |  | 2332 |  |  | 2564.5 |  |  | 2447.5 |  |  | 2508.5 |  |  | 2320.5 |  |  | 2425.5 |  |  | 2360.5 |  |  | 2339.5 |  |  | 2278 |  |  | 2343.5 |  |  | 2429.5 |  |  | 2429.5 |  |  | 2449 |  |  | 2515.5 |  |  | 2350 |  |  | 2306.5 |  |  | 2462.5 |  |  | 2378.5 |  |  | 2472 |  |  | 2284.5 |  |  | 2447 |  |  | 2415 |  |  | 2450.5 |  |  | 2414 |  |  | 2586 |  |  | 2492.5 |  |  | 2491.5 |  |  | 2329.5 |  |  | 2482 |  |  | 2489.5 |  |  | 2359.5 |  |  | 2307.5 |  |  | 2543.5 |  |  | 2386.5 |  |  | 2414.5 |  |  | 2410.5 |  |  | 2467.5 |  |  | 2398 |  |  | 2601.5 |  |  | 2392 |  |  | 2466.5 |  |  | 2351.5 |  |  | 2554.5 |  |  | 2440 |  |  | 2493 |  |  | 2559 |  |  | 2459.5 |  |  | 2421 |  |  | 2502.5 |  |  | 2571.5 |  |  | 2432.5 |  |  | 2385.5 |  |  | 2342.5 |  |  | 2566.5 |  |  | 2580.5 |  |  | 2508.5 |  |  | 2466 |  |  | 2295.5 |  |  | 2305.5 |  |  | 2436.5 |  |  | 2397.5 |  |  | 2374 |  |  | 2442.5 |  |  | 2486 |  |  | 2457.5 |  |  | 2466.5 |  |  | 2391.5 |  |  | 2322.5 |  |  | 2306 |  |  | 2428.5 |  |  | 2200 |  |  | 2351.5 |  |  | 2511.5 |  |  | 2597.5 |  |  | 2431.5 |  |  | 2451.5 |  |  | 2490.5 |  |  | 2408.5 |  |  | 2483.5 |  |  | 2407.5 |  |  | 2347 |  |  | 2464.5 |  |  | 2418.5 |  |  | 2398.5 |  |  | 2473.5 |  |  | 2481.5 |  |  | 2359 |  |  | 2368 |  |  | 2414.5 |  |  | 2403 |  |  | 2552.5 |  |  | 2368.5 |  |  | 2544.5 |  |  | 2469.5 |  |  | 2387.5 |  |  | 2552.5 |  |  | 2473.5 |  |  | 2499.5 |  |  | 2446 |  |  | 2438.5 |  |  | 2629.5 |  |  | 2385.5 |  |  | 2276 |  |  | 2431.5 |  |  | 2362.5 |  |  | 2575 |  |  | 2402 |  |  | 2415.5 |  |  | 2419 |  |  | 2256 |  |  | 2282.5 |  |  | 2515 |  |  | 2647.5 |  |  | 2423.5 |  |  | 2524.5 |  |  | 2409.5 |  |  | 2332.5 |  |  | 2402.5 |  |  | 2228.5 |  |  | 2342.5 |  |  | 2438.5 |  |  | 2380.5 |  |  | 2349 |  |  | 2307 |  |  | 2516.5 |  |  | 2539.5 |  |  | 2402.5 |  |  | 2504.5 |  |  | 2416.5 |  |  | 2479.5 |  |  | 2466.5 |  |  | 2355.5 |  |  | 2682 |  |  | 2371.5 |  |  | 2413 |  |  | 2364.5 |  |  | 2571.5 |  |  | 2502.5 |  |  | 2546 |  |  | 2417.5 |  |  | 2358.5 |  |  | 2485 |  |  | 2491.5 |  |  | 2405.5 |  |  | 2502.5 |  |  | 2409.5 |  |  | 2396.5 |  |  | 2477.5 |  |  | 2498 |  |  | 2386.5 |  |  | 2446.5 |  |  | 2564.5 |  |  | 2489.5 |  |  | 2434 |  |  | 2442.5 |  |  | 2567.5 |  |  | 2415 |  |  | 2433.5 |  |  | 2529.5 |  |  | 2493 |  |  | 2521.5 |  |  | 2556.5 |  |  | 2433.5 |  |  | 2398 |  |  | 2314.5 |  |  | 2438.5 |  |  | 2346 |  |  | 2463.5 |  |  | 2450.5 |  |  | 2450.5 |  |  | 2264.5 |  |  | 2454.5 |  |  | 2576.5 |  |  | 2358.5 |  |  | 2431 |  |  | 2343 |  |  | 2282.5 |  |  | 2506.5 |  |  | 2310.5 |  |  | 2545 |  |  | 2601.5 |  |  | 2386.5 |  |  | 2400.5 |  |  | 2257.5 |  |  | 2440.5 |  |  | 2504.5 |  |  | 2340.5 |  |  | 2485.5 |  |  | 2234.5 |  |  | 2457 |  |  | 2398.5 |  |  | 2266.5 |  |  | 2405.5 |  |  | 2469.5 |  |  | 2597.5 |  |  | 2490.5 |  |  | 2443.5 |  |  | 2435.5 |  |  | 2291.5 |  |  | 2530.5 |  |  | 2426.5 |  |  | 2322.5 |  |  | 2452.5 |  |  | 2537 |  |  | 2439.5 |  |  | 2513.5 |  |  | 2393 |  |  | 2489.5 |  |  | 2531.5 |  |  | 2565 |  |  | 2481.5 |  |  | 2520.5 |  |  | 2632.5 |  |  | 2594 |  |  | 2340.5 |  |  | 2550.5 |  |  | 2444.5 |  |  | 2228.5 |  |  | 2521.5 |  |  | 2341 |  |  | 2389.5 |  |  | 2526 |  |  | 2500 |  |  | 2501.5 |  |  | 2430.5 |  |  | 2369.5 |  |  | 2200.5 |  |  | 2372.5 |  |  | 2523.5 |  |  | 2361 |  |  | 2400.5 |  |  | 2376 |  |  | 2408.5 |  |  | 2438 |  |  | 2344 |  |  | 2526 |  |  | 2502.5 |  |  | 2376 |  |  | 2615.5 |  |  | 2487.5 |  |  | 2410.5 |  |  | 2605.5 |  |  | 2323.5 |  |  | 2533 |  |  | 2477.5 |  |  | 2509.5 |  |  | 2653.5 |  |  | 2427 |  |  | 2409.5 |  |  | 2370.5 |  |  | 2452.5 |  |  | 2531.5 |  |  | 2434 |  |  | 2515 |  |  | 2406 |  |  | 2417.5 |  |  | 2567 |  |  | 2480 |  |  | 2502.5 |  |  | 2378.5 |  |  | 2316.5 |  |  | 2452.5 |  |  | 2462.5 |  |  | 2458.5 |  |  | 2531.5 |  |  | 2408.5 |  |  | 2391.5 |  |  | 2347 |  |  | 2393.5 |  |  | 2331 |  |  | 2444.5 |  |  | 2421.5 |  |  | 2480.5 |  |  | 2487.5 |  |  | 2575 |  |  | 2477.5 |  |  | 2454 |  |  | 2400.5 |  |  | 2485.5 |  |  | 2308 |  |  | 2381 |  |  | 2526.5 |  |  | 2485 |  |  | 2451.5 |  |  | 2312.5 |  |  | 2335.5 |  |  | 2395.5 |  |  | 2482.5 |  |  | 2486.5 |  |  | 2324.5 |  |  | 2381 |  |  | 2492.5 |  |  | 2478.5 |  |  | 2447.5 |  |  | 2494.5 |  |  | 2384.5 |  |  | 2503.5 |  |  | 2590.5 |  |  | 2437.5 |  |  | 2596.5 |  |  | 2575.5 |  |  | 2328.5 |  |  | 2307.5 |  |  | 2436 |  |  | 2328.5 |  |  | 2385.5 |  |  | 2506 |  |  | 2325.5 |  |  | 2350.5 |  |  | 2421.5 |  |  | 2316.5 |  |  | 2656 |  |  | 2567.5 |  |  | 2379.5 |  |  | 2320.5 |  |  | 2583.5 |  |  | 2366 |  |  | 2395.5 |  |  | 2566.5 |  |  | 2371.5 |  |  | 2529.5 |  |  | 2359.5 |  |  | 2336.5 |  |  | 2554.5 |  |  | 2429.5 |  |  | 2473.5 |  |  | 2480.5 |  |  | 2489.5 |  |  | 2491 |  |  | 2467.5 |  |  | 2387.5 |  |  | 2491.5 |  |  | 2540.5 |  |  | 2356.5 |  |  | 2409.5 |  |  | 2510 |  |  | 2519.5 |  |  | 2359 |  |  | 2343.5 |  |  | 2499.5 |  |  | 2506.5 |  |  | 2442 |  |  | 2353 |  |  | 2500.5 |  |  | 2517.5 |  |  | 2215.5 |  |  | 2580.5 |  |  | 2443.5 |  |  | 2494.5 |  |  | 2363.5 |  |  | 2548.5 |  |  | 2347.5 |  |  | 2556.5 |  |  | 2466.5 |  |  | 2502.5 |  |  | 2340.5 |  |  | 2460.5 |  |  | 2540.5 |  |  | 2427.5 |  |  | 2412.5 |  |  | 2465.5 |  |  | 2401.5 |  |  | 2403.5 |  |  | 2508.5 |  |  | 2500.5 |  |  | 2436 |  |  | 2525.5 |  |  | 2453.5 |  |  | 2488.5 |  |  | 2470 |  |  | 2511.5 |  |  | 2441.5 |  |  | 2545.5 |  |  | 2463.5 |  |  | 2465 |  |  | 2306.5 |  |  | 2345.5 |  |  | 2339 |  |  | 2430 |  |  | 2429 |  |  | 2431.5 |  |  | 2425.5 |  |  | 2502.5 |  |  | 2640.5 |  |  | 2511 |  |  | 2496.5 |  |  | 2447.5 |  |  | 2311 |  |  | 2410 |  |  | 2462.5 |  |  | 2526.5 |  |  | 2538 |  |  | 2473.5 |  |  | 2559 |  |  | 2372.5 |  |  | 2371.5 |  |  | 2565 |  |  | 2535.5 |  |  | 2460.5 |  |  | 2312.5 |  |  | 2556 |  |  | 2363.5 |  |  | 2342.5 |  |  | 2358.5 |  |  | 2426.5 |  |  | 2450.5 |  |  | 2499.5 |  |  | 2379.5 |  |  | 2466.5 |  |  | 2534.5 |  |  | 2437.5 |  |  | 2412 |  |  | 2439.5 |  |  | 2489.5 |  |  | 2491.5 |  |  | 2531.5 |  |  | 2408.5 |  |  | 2478.5 |  |  | 2571.5 |  |  | 2416.5 |  |  | 2548 |  |  | 2412.5 |  |  | 2407 |  |  | 2631.5 |  |  | 2652.5 |  |  | 2653.5 |  |  | 2363.5 |  |  | 2361.5 |  |  | 2486.5 |  |  | 2329.5 |  |  | 2475.5 |  |  | 2459 |  |  | 2367.5 |  |  | 2460 |  |  | 2320.5 |  |  | 2381.5 |  |  | 2474.5 |  |  | 2494 |  |  | 2388.5 |  |  | 2472.5 |  |  | 2206 |  |  | 2433.5 |  |  | 2413 |  |  | 2461.5 |  |  | 2362.5 |  |  | 2379.5 |  |  | 2467 |  |  | 2525.5 |  |  | 2641.5 |  |  | 2315 |  |  | 2617.5 |  |  | 2431.5 |  |  | 2472 |  |  | 2464.5 |  |  | 2596.5 |  |  | 2512.5 |  |  | 2534.5 |  |  | 2363.5 |  |  | 2590.5 |  |  | 2353.5 |  |  | 2419.5 |  |  | 2373.5 |  |  | 2352.5 |  |  | 2600.5 |  |  | 2556 |  |  | 2468 |  |  | 2540.5 |  |  | 2440.5 |  |  | 2479
84 |  | 2431.5 |  |  | 2577.5 |  |  | 2520 |  |  | 2443.5 |  |  | 2633.5 |  |  | 2516.5 |  |  | 2528.5 |  |  | 2503.5 |  |  | 2483.5 |  |  | 2463.5 |  |  | 2395 |  |  | 2565.5 |  |  | 2527.5 |  |  | 2356.5 |  |  | 2330 |  |  | 2510.5 |  |  | 2570.5 |  |  | 2433.5 |  |  | 2549.5 |  |  | 2413.5 |  |  | 2608.5 |  |  | 2472.5 |  |  | 2545.5 |  |  | 2414.5 |  |  | 2284 |  |  | 2555.5 |  |  | 2498.5 |  |  | 2421.5 |  |  | 2548.5 |  |  | 2344 |  |  | 2468 |  |  | 2606.5 |  |  | 2277.5 |  |  | 2483.5 |  |  | 2369.5 |  |  | 2515 |  |  | 2432.5 |  |  | 2608 |  |  | 2493.5 |  |  | 2445.5 |  |  | 2276.5 |  |  | 2521.5 |  |  | 2345.5 |  |  | 2449 |  |  | 2658.5 |  |  | 2587 |  |  | 2495.5 |  |  | 2535.5 |  |  | 2551.5 |  |  | 2505.5 |  |  | 2366.5 |  |  | 2505.5 |  |  | 2486.5 |  |  | 2461.5 |  |  | 2544.5 |  |  | 2504.5 |  |  | 2345.5 |  |  | 2455 |  |  | 2498.5 |  |  | 2477.5 |  |  | 2443 |  |  | 2481.5 |  |  | 2556.5 |  |  | 2436.5 |  |  | 2380.5 |  |  | 2506 |  |  | 2627.5 |  |  | 2365 |  |  | 2334.5 |  |  | 2518.5 |  |  | 2431 |  |  | 2393.5 |  |  | 2448.5 |  |  | 2602.5 |  |  | 2585 |  |  | 2568 |  |  | 2345.5 |  |  | 2373.5 |  |  | 2372.5 |  |  | 2500.5 |  |  | 2419 |  |  | 2514.5 |  |  | 2527.5 |  |  | 2544.5 |  |  | 2584.5 |  |  | 2373.5 |  |  | 2568.5 |  |  | 2458.5 |  |  | 2462.5 |  |  | 2477.5 |  |  | 2483.5 |  |  | 2475 |  |  | 2389.5 |  |  | 2334 |  |  | 2446 |  |  | 2361 |  |  | 2626.5 |  |  | 2569.5 |  |  | 2369.5 |  |  | 2632.5 |  |  | 2378.5 |  |  | 2417 |  |  | 2443 |  |  | 2448.5 |  |  | 2472.5 |  |  | 2412.5 |  |  | 2506.5 |  |  | 2559.5 |  |  | 2545.5 |  |  | 2562.5 |  |  | 2594.5 |  |  | 2545.5 |  |  | 2442.5 |  |  | 2469.5 |  |  | 2536.5 |  |  | 2523.5 |  |  | 2571.5 |  |  | 2394.5 |  |  | 2479.5 |  |  | 2451.5 |  |  | 2533.5 |  |  | 2544.5 |  |  | 2515.5 |  |  | 2503.5 |  |  | 2463.5 |  |  | 2435 |  |  | 2442.5 |  |  | 2444.5 |  |  | 2413.5 |  |  | 2507.5 |  |  | 2552.5 |  |  | 2481 |  |  | 2409.5 |  |  | 2565.5 |  |  | 2418.5 |  |  | 2409.5 |  |  | 2518 |  |  | 2501.5 |  |  | 2581.5 |  |  | 2358 |  |  | 2529.5 |  |  | 2321 |  |  | 2574 |  |  | 2591.5 |  |  | 2503 |  |  | 2615.5 |  |  | 2410.5 |  |  | 2508.5 |  |  | 2402.5 |  |  | 2477.5 |  |  | 2535.5 |  |  | 2461.5 |  |  | 2514.5 |  |  | 2562.5 |  |  | 2517.5 |  |  | 2581 |  |  | 2395.5 |  |  | 2319 |  |  | 2408.5 |  |  | 2473.5 |  |  | 2396 |  |  | 2489.5 |  |  | 2408.5 |  |  | 2424.5 |  |  | 2339 |  |  | 2466.5 |  |  | 2326.5 |  |  | 2365.5 |  |  | 2574.5 |  |  | 2442.5 |  |  | 2427.5 |  |  | 2431 |  |  | 2481.5 |  |  | 2444.5 |  |  | 2370.5 |  |  | 2517.5 |  |  | 2486.5 |  |  | 2523.5 |  |  | 2420.5 |  |  | 2560 |  |  | 2504.5 |  |  | 2497.5 |  |  | 2532.5 |  |  | 2545.5 |  |  | 2428.5 |  |  | 2565.5 |  |  | 2546.5 |  |  | 2433.5 |  |  | 2604.5 |  |  | 2403.5 |  |  | 2524.5 |  |  | 2293.5 |  |  | 2275.5 |  |  | 2364 |  |  | 2403.5 |  |  | 2498.5 |  |  | 2487.5 |  |  | 2535.5 |  |  | 2566.5 |  |  | 2618.5 |  |  | 2596.5 |  |  | 2446.5 |  |  | 2504.5 |  |  | 2433.5 |  |  | 2398.5 |  |  | 2576.5 |  |  | 2463.5 |  |  | 2428.5 |  |  | 2448.5 |  |  | 2481.5 |  |  | 2535 |  |  | 2610.5 |  |  | 2460.5 |  |  | 2202 |  |  | 2629.5 |  |  | 2643 |  |  | 2334.5 |  |  | 2493.5 |  |  | 2551.5 |  |  | 2581.5 |  |  | 2439.5 |  |  | 2433.5 |  |  | 2468.5 |  |  | 2298.5 |  |  | 2298 |  |  | 2382.5 |  |  | 2316.5 |  |  | 2505.5 |  |  | 2443.5 |  |  | 2492 |  |  | 2442.5 |  |  | 2414.5 |  |  | 2563.5 |  |  | 2468.5 |  |  | 2583.5 |  |  | 2471.5 |  |  | 2468.5 |  |  | 2604.5 |  |  | 2575 |  |  | 2549 |  |  | 2427.5 |  |  | 2359.5 |  |  | 2516.5 |  |  | 2438 |  |  | 2625.5 |  |  | 2450.5 |  |  | 2447.5 |  |  | 2341 |  |  | 2596.5 |  |  | 2471.5 |  |  | 2315.5 |  |  | 2386.5 |  |  | 2440.5 |  |  | 2488.5 |  |  | 2535.5 |  |  | 2511.5 |  |  | 2568.5 |  |  | 2272 |  |  | 2371.5 |  |  | 2568.5 |  |  | 2515.5 |  |  | 2466.5 |  |  | 2431.5 |  |  | 2646 |  |  | 2378.5 |  |  | 2576.5 |  |  | 2560 |  |  | 2583.5 |  |  | 2490.5 |  |  | 2723 |  |  | 2540.5 |  |  | 2529.5 |  |  | 2630.5 |  |  | 2408.5 |  |  | 2465 |  |  | 2478 |  |  | 2463.5 |  |  | 2394.5 |  |  | 2548.5 |  |  | 2427.5 |  |  | 2656.5 |  |  | 2531.5 |  |  | 2469 |  |  | 2425.5 |  |  | 2390.5 |  |  | 2428 |  |  | 2438.5 |  |  | 2307.5 |  |  | 2486 |  |  | 2534.5 |  |  | 2374.5 |  |  | 2499.5 |  |  | 2517 |  |  | 2483.5 |  |  | 2377 |  |  | 2589.5 |  |  | 2401.5 |  |  | 2486.5 |  |  | 2436 |  |  | 2382.5 |  |  | 2594.5 |  |  | 2579.5 |  |  | 2516 |  |  | 2431.5 |  |  | 2277.5 |  |  | 2604.5 |  |  | 2642.5 |  |  | 2463.5 |  |  | 2511 |  |  | 2378.5 |  |  | 2574.5 |  |  | 2511.5 |  |  | 2439 |  |  | 2461 |  |  | 2659.5 |  |  | 2405.5 |  |  | 2313.5 |  |  | 2503.5 |  |  | 2459.5 |  |  | 2454.5 |  |  | 2494.5 |  |  | 2573.5 |  |  | 2389.5 |  |  | 2488.5 |  |  | 2495 |  |  | 2456.5 |  |  | 2533.5 |  |  | 2731.5 |  |  | 2633.5 |  |  | 2511 |  |  | 2477.5 |  |  | 2608.5 |  |  | 2489.5 |  |  | 2349.5 |  |  | 2579.5 |  |  | 2312 |  |  | 2518 |  |  | 2356 |  |  | 2573 |  |  | 2356.5 |  |  | 2459 |  |  | 2485.5 |  |  | 2496 |  |  | 2465.5 |  |  | 2595.5 |  |  | 2463.5 |  |  | 2469.5 |  |  | 2416.5 |  |  | 2504 |  |  | 2488.5 |  |  | 2624.5 |  |  | 2468.5 |  |  | 2486 |  |  | 2583.5 |  |  | 2441.5 |  |  | 2473.5 |  |  | 2539 |  |  | 2445.5 |  |  | 2387.5 |  |  | 2564.5 |  |  | 2381.5 |  |  | 2496.5 |  |  | 2399.5 |  |  | 2507.5 |  |  | 2470.5 |  |  | 2533.5 |  |  | 2351.5 |  |  | 2420 |  |  | 2423.5 |  |  | 2438.5 |  |  | 2358.5 |  |  | 2516.5 |  |  | 2587.5 |  |  | 2469 |  |  | 2531.5 |  |  | 2570 |  |  | 2436 |  |  | 2340.5 |  |  | 2528.5 |  |  | 2376.5 |  |  | 2470 |  |  | 2521.5 |  |  | 2528.5 |  |  | 2474.5 |  |  | 2343 |  |  | 2418.5 |  |  | 2311.5 |  |  | 2428.5 |  |  | 2356.5 |  |  | 2388.5 |  |  | 2399 |  |  | 2397.5 |  |  | 2533 |  |  | 2506.5 |  |  | 2283.5 |  |  | 2419.5 |  |  | 2503 |  |  | 2414.5 |  |  | 2399 |  |  | 2387 |  |  | 2438.5 |  |  | 2337.5 |  |  | 2386.5 |  |  | 2614.5 |  |  | 2649 |  |  | 2585.5 |  |  | 2491.5 |  |  | 2272.5 |  |  | 2441 |  |  | 2520.5 |  |  | 2429.5 |  |  | 2228.5 |  |  | 2503.5 |  |  | 2650 |  |  | 2351.5 |  |  | 2441.5 |  |  | 2499.5 |  |  | 2525.5 |  |  | 2470.5 |  |  | 2492.5 |  |  | 2552 |  |  | 2409.5 |  |  | 2389.5 |  |  | 2462 |  |  | 2382.5 |  |  | 2349.5 |  |  | 2470.5 |  |  | 2481 |  |  | 2524.5 |  |  | 2485.5 |  |  | 2471.5 |  |  | 2388.5 |  |  | 2490.5 |  |  | 2518 |  |  | 2378 |  |  | 2453.5 |  |  | 2554.5 |  |  | 2527.5 |  |  | 2337.5 |  |  | 2254 |  |  | 2561 |  |  | 2405 |  |  | 2585.5 |  |  | 2434 |  |  | 2487.5 |  |  | 2591.5 |  |  | 2551 |  |  | 2342.5 |  |  | 2494.5 |  |  | 2430.5 |  |  | 2515.5 |  |  | 2212.5 |  |  | 2474 |  |  | 2559 |  |  | 2384.5 |  |  | 2552.5 |  |  | 2381 |  |  | 2386.5 |  |  | 2470.5 |  |  | 2440 |  |  | 2624.5 |  |  | 2606.5 |  |  | 2382 |  |  | 2520.5 |  |  | 2505.5 |  |  | 2569 |  |  | 2410.5 |  |  | 2377 |  |  | 2623.5 |  |  | 2568 |  |  | 2405.5 |  |  | 2378.5 |  |  | 2398.5 |  |  | 2481.5 |  |  | 2484.5 |  |  | 2358.5 |  |  | 2511 |  |  | 2401.5 |  |  | 2517.5 |  |  | 2398.5 |  |  | 2432.5 |  |  | 2465.5 |  |  | 2411 |  |  | 2419.5 |  |  | 2509 |  |  | 2456.5 |  |  | 2332.5 |  |  | 2526.5 |  |  | 2498.5 |  |  | 2523.5 |  |  | 2441.5 |  |  | 2381.5 |  |  | 2525.5 |  |  | 2353.5 |  |  | 2381 |  |  | 2520.5 |  |  | 2358 |  |  | 2461 |  |  | 2492.5 |  |  | 2249 |  |  | 2320.5 |  |  | 2530.5 |  |  | 2565.5 |  |  | 2509.5 |  |  | 2575.5 |  |  | 2497.5 |  |  | 2515.5 |  |  | 2429 |  |  | 2605 |  |  | 2340.5 |  |  | 2478.5 |  |  | 2460 |  |  | 2403.5 |  |  | 2418.5 |  |  | 2413.5 |  |  | 2367.5 |  |  | 2437.5 |  |  | 2348 |  |  | 2478.5 |  |  | 2446.5 |  |  | 2365.5 |  |  | 2431 |  |  | 2508.5 |  |  | 2540.5 |  |  | 2504.5 |  |  | 2690.5 |  |  | 2487.5 |  |  | 2383.5 |  |  | 2513.5 |  |  | 2090.5 |  |  | 2477.5 |  |  | 2379 |  |  | 2603.5 |  |  | 2471.5 |  |  | 2547.5 |  |  | 2346.5 |  |  | 2440.5 |  |  | 2386.5 |  |  | 2368.5 |  |  | 2325 |  |  | 2372.5 |  |  | 2468.5 |  |  | 2450.5 |  |  | 2470 |  |  | 2539.5 |  |  | 2365 |  |  | 2321.5 |  |  | 2483.5 |  |  | 2425.5 |  |  | 2511 |  |  | 2305.5 |  |  | 2473 |  |  | 2441 |  |  | 2476.5 |  |  | 2461 |  |  | 2607 |  |  | 2531.5 |  |  | 2530.5 |  |  | 2368.5 |  |  | 2521 |  |  | 2510.5 |  |  | 2380.5 |  |  | 2331.5 |  |  | 2569.5 |  |  | 2401.5 |  |  | 2453.5 |  |  | 2449.5 |  |  | 2496.5 |  |  | 2437 |  |  | 2616.5 |  |  | 2413 |  |  | 2505.5 |  |  | 2380.5 |  |  | 2578.5 |  |  | 2487 |  |  | 2522 |  |  | 2583 |  |  | 2498.5 |  |  | 2436 |  |  | 2531.5 |  |  | 2618.5 |  |  | 2479.5 |  |  | 2424.5 |  |  | 2389.5 |  |  | 2592.5 |  |  | 2601.5 |  |  | 2523.5 |  |  | 2513 |  |  | 2324.5 |  |  | 2326.5 |  |  | 2483.5 |  |  | 2444.5 |  |  | 2400 |  |  | 2466.5 |  |  | 2510 |  |  | 2504.5 |  |  | 2490.5 |  |  | 2420.5 |  |  | 2361.5 |  |  | 2345 |  |  | 2454.5 |  |  | 2224 |  |  | 2390.5 |  |  | 2537.5 |  |  | 2618.5 |  |  | 2460.5 |  |  | 2480.5 |  |  | 2529.5 |  |  | 2429.5 |  |  | 2509.5 |  |  | 2422.5 |  |  | 2362 |  |  | 2485.5 |  |  | 2444.5 |  |  | 2445.5 |  |  | 2520.5 |  |  | 2520.5 |  |  | 2398 |  |  | 2397 |  |  | 2435.5 |  |  | 2418 |  |  | 2591.5 |  |  | 2394.5 |  |  | 2570.5 |  |  | 2490.5 |  |  | 2416.5 |  |  | 2576.5 |  |  | 2494.5 |  |  | 2520.5 |  |  | 2493 |  |  | 2464.5 |  |  | 2655.5 |  |  | 2400.5 |  |  | 2302 |  |  | 2457.5 |  |  | 2386.5 |  |  | 2604 |  |  | 2431 |  |  | 2462.5 |  |  | 2458 |  |  | 2295 |  |  | 2308.5 |  |  | 2554 |  |  | 2686.5 |  |  | 2438.5 |  |  | 2563.5 |  |  | 2456.5 |  |  | 2356.5 |  |  | 2426.5 |  |  | 2267.5 |  |  | 2371.5 |  |  | 2477.5 |  |  | 2395.5 |  |  | 2373 |  |  | 2354 |  |  | 2540.5 |  |  | 2578.5 |  |  | 2417.5 |  |  | 2519.5 |  |  | 2440.5 |  |  | 2526.5 |  |  | 2487.5 |  |  | 2402.5 |  |  | 2697 |  |  | 2392.5 |  |  | 2452 |  |  | 2403.5 |  |  | 2586.5 |  |  | 2528.5 |  |  | 2561 |  |  | 2432.5 |  |  | 2387.5 |  |  | 2514 |  |  | 2530.5 |  |  | 2444.5 |  |  | 2541.5 |  |  | 2448.5 |  |  | 2443.5 |  |  | 2501.5 |  |  | 2545 |  |  | 2407.5 |  |  | 2467.5 |  |  | 2593.5 |  |  | 2510.5 |  |  | 2455 |  |  | 2481.5 |  |  | 2606.5 |  |  | 2430 |  |  | 2448.5 |  |  | 2553.5 |  |  | 2514 |  |  | 2560.5 |  |  | 2582.5 |  |  | 2472.5 |  |  | 2413 |  |  | 2361.5 |  |  | 2464.5 |  |  | 2361 |  |  | 2484.5 |  |  | 2489.5 |  |  | 2497.5 |  |  | 2311.5 |  |  | 2493.5 |  |  | 2615.5 |  |  | 2397.5 |  |  | 2457 |  |  | 2372 |  |  | 2303.5 |  |  | 2545.5 |  |  | 2349.5 |  |  | 2560 |  |  | 2630.5 |  |  | 2425.5 |  |  | 2429.5 |  |  | 2304.5 |  |  | 2479.5 |  |  | 2525.5 |  |  | 2379.5 |  |  | 2524.5 |  |  | 2273.5 |  |  | 2478 |  |  | 2424.5 |  |  | 2281.5 |  |  | 2429.5 |  |  | 2493.5 |  |  | 2636.5 |  |  | 2516.5 |  |  | 2467.5 |  |  | 2456.5 |  |  | 2330.5 |  |  | 2577.5 |  |  | 2447.5 |  |  | 2346.5 |  |  | 2476.5 |  |  | 2563 |  |  | 2478.5 |  |  | 2537.5 |  |  | 2422 |  |  | 2536.5 |  |  | 2546.5 |  |  | 2589 |  |  | 2520.5 |  |  | 2559.5 |  |  | 2658.5 |  |  | 2623 |  |  | 2355.5 |  |  | 2574.5 |  |  | 2468.5 |  |  | 2252.5 |  |  | 2550.5 |  |  | 2356 |  |  | 2413.5 |  |  | 2547 |  |  | 2539 |  |  | 2530.5 |  |  | 2459.5 |  |  | 2408.5 |  |  | 2221.5 |  |  | 2411.5 |  |  | 2562.5 |  |  | 2408 |  |  | 2424.5 |  |  | 2397 |  |  | 2432.5 |  |  | 2464 |  |  | 2368 |  |  | 2552 |  |  | 2528.5 |  |  | 2402 |  |  | 2639.5 |  |  | 2526.5 |  |  | 2449.5 |  |  | 2631.5 |  |  | 2338.5 |  |  | 2580 |  |  | 2492.5 |  |  | 2548.5 |  |  | 2700.5 |  |  | 2466 |  |  | 2438.5 |  |  | 2417.5 |  |  | 2481.5 |  |  | 2570.5 |  |  | 2463 |  |  | 2544 |  |  | 2427 |  |  | 2443.5 |  |  | 2596 |  |  | 2504 |  |  | 2541.5 |  |  | 2425.5 |  |  | 2355.5 |  |  | 2473.5 |  |  | 2501.5 |  |  | 2487.5 |  |  | 2555.5 |  |  | 2432.5 |  |  | 2420.5 |  |  | 2376 |  |  | 2419.5 |  |  | 2370 |  |  | 2465.5 |  |  | 2447.5 |  |  | 2504.5 |  |  | 2508.5 |  |  | 2596 |  |  | 2501.5 |  |  | 2493 |  |  | 2415.5 |  |  | 2514.5 |  |  | 2329 |  |  | 2407 |  |  | 2550.5 |  |  | 2514 |  |  | 2477.5 |  |  | 2338.5 |  |  | 2382.5 |  |  | 2416.5 |  |  | 2511.5 |  |  | 2507.5 |  |  | 2350.5 |  |  | 2420 |  |  | 2521.5 |  |  | 2507.5 |  |  | 2494.5 |  |  | 2515.5 |  |  | 2423.5 |  |  | 2518.5 |  |  | 2616.5 |  |  | 2463.5 |  |  | 2611.5 |  |  | 2601.5 |  |  | 2352.5 |  |  | 2333.5 |  |  | 2457 |  |  | 2367.5 |  |  | 2432.5 |  |  | 2532 |  |  | 2372.5 |  |  | 2376.5 |  |  | 2460.5 |  |  | 2342.5 |  |  | 2682 |  |  | 2582.5 |  |  | 2405.5 |  |  | 2346.5 |  |  | 2622.5 |  |  | 2413 |  |  | 2424.5 |  |  | 2592.5 |  |  | 2392.5 |  |  | 2576.5 |  |  | 2383.5 |  |  | 2375.5 |  |  | 2569.5 |  |  | 2450.5 |  |  | 2497.5 |  |  | 2495.5 |  |  | 2513.5 |  |  | 2520 |  |  | 2506.5 |  |  | 2411.5 |  |  | 2515.5 |  |  | 2579.5 |  |  | 2395.5 |  |  | 2438.5 |  |  | 2539 |  |  | 2566.5 |  |  | 2388 |  |  | 2358.5 |  |  | 2538.5 |  |  | 2545.5 |  |  | 2466 |  |  | 2392 |  |  | 2515.5 |  |  | 2556.5 |  |  | 2230.5 |  |  | 2619.5 |  |  | 2469.5 |  |  | 2515.5 |  |  | 2402.5 |  |  | 2577.5 |  |  | 2394.5 |  |  | 2595.5 |  |  | 2481.5 |  |  | 2523.5 |  |  | 2361.5 |  |  | 2507.5 |  |  | 2566.5 |  |  | 2474.5 |  |  | 2451.5 |  |  | 2494.5 |  |  | 2425.5 |  |  | 2429.5 |  |  | 2532.5 |  |  | 2547.5 |  |  | 2475 |  |  | 2564.5 |  |  | 2479.5 |  |  | 2535.5 |  |  | 2509 |  |  | 2540.5 |  |  | 2480.5 |  |  | 2574.5 |  |  | 2492.5 |  |  | 2504 |  |  | 2321.5 |  |  | 2366.5 |  |  | 2368 |  |  | 2456 |  |  | 2444 |  |  | 2470.5 |  |  | 2454.5 |  |  | 2541.5 |  |  | 2661.5 |  |  | 2550 |  |  | 2535.5 |  |  | 2486.5 |  |  | 2358 |  |  | 2449 |  |  | 2509.5 |  |  | 2552.5 |  |  | 2567 |  |  | 2488.5 |  |  | 2580 |  |  | 2398.5 |  |  | 2418.5 |  |  | 2580 |  |  | 2582.5 |  |  | 2481.5 |  |  | 2338.5 |  |  | 2595 |  |  | 2402.5 |  |  | 2389.5 |  |  | 2405.5 |  |  | 2465.5 |  |  | 2476.5 |  |  | 2523.5 |  |  | 2418.5 |  |  | 2495.5 |  |  | 2555.5 |  |  | 2461.5 |  |  | 2441 |  |  | 2460.5 |  |  | 2515.5 |  |  | 2538.5 |  |  | 2570.5 |  |  | 2423.5 |  |  | 2499.5 |  |  | 2597.5 |  |  | 2431.5 |  |  | 2587 |  |  | 2433.5 |  |  | 2436 |  |  | 2670.5 |  |  | 2681.5 |  |  | 2677.5 |  |  | 2402.5 |  |  | 2387.5 |  |  | 2501.5 |  |  | 2344.5 |  |  | 2504.5 |  |  | 2506 |  |  | 2406.5 |  |  | 2507 |  |  | 2335.5 |  |  | 2396.5 |  |  | 2500.5 |  |  | 2520 |  |  | 2435.5 |  |  | 2511.5 |  |  | 2253 |  |  | 2472.5 |  |  | 2428 |  |  | 2482.5 |  |  | 2391.5 |  |  | 2418.5 |  |  | 2493 |  |  | 2554.5 |  |  | 2670.5 |  |  | 2330 |  |  | 2656.5 |  |  | 2446.5 |  |  | 2511 |  |  | 2488.5 |  |  | 2635.5 |  |  | 2551.5 |  |  | 2581.5 |  |  | 2402.5 |  |  | 2629.5 |  |  | 2379.5 |  |  | 2445.5 |  |  | 2412.5 |  |  | 2399.5 |  |  | 2621.5 |  |  | 2595 |  |  | 2494 |  |  | 2579.5 |  |  | 2464.5 |  |  | 2526
85 |  | 2452.5 |  |  | 2601.5 |  |  | 2559 |  |  | 2482.5 |  |  | 2654.5 |  |  | 2537.5 |  |  | 2567.5 |  |  | 2518.5 |  |  | 2512.5 |  |  | 2484.5 |  |  | 2416 |  |  | 2594.5 |  |  | 2556.5 |  |  | 2395.5 |  |  | 2369 |  |  | 2525.5 |  |  | 2591.5 |  |  | 2480.5 |  |  | 2588.5 |  |  | 2428.5 |  |  | 2647.5 |  |  | 2519.5 |  |  | 2571.5 |  |  | 2443.5 |  |  | 2299 |  |  | 2570.5 |  |  | 2524.5 |  |  | 2445.5 |  |  | 2577.5 |  |  | 2370 |  |  | 2507 |  |  | 2632.5 |  |  | 2306.5 |  |  | 2509.5 |  |  | 2395.5 |  |  | 2530 |  |  | 2456.5 |  |  | 2632 |  |  | 2514.5 |  |  | 2492.5 |  |  | 2302.5 |  |  | 2542.5 |  |  | 2384.5 |  |  | 2475 |  |  | 2697.5 |  |  | 2613 |  |  | 2524.5 |  |  | 2559.5 |  |  | 2598.5 |  |  | 2529.5 |  |  | 2395.5 |  |  | 2552.5 |  |  | 2515.5 |  |  | 2487.5 |  |  | 2565.5 |  |  | 2533.5 |  |  | 2384.5 |  |  | 2494 |  |  | 2537.5 |  |  | 2516.5 |  |  | 2469 |  |  | 2505.5 |  |  | 2603.5 |  |  | 2451.5 |  |  | 2406.5 |  |  | 2535 |  |  | 2656.5 |  |  | 2380 |  |  | 2373.5 |  |  | 2533.5 |  |  | 2478 |  |  | 2440.5 |  |  | 2487.5 |  |  | 2617.5 |  |  | 2632 |  |  | 2594 |  |  | 2371.5 |  |  | 2412.5 |  |  | 2419.5 |  |  | 2524.5 |  |  | 2458 |  |  | 2540.5 |  |  | 2566.5 |  |  | 2568.5 |  |  | 2613.5 |  |  | 2412.5 |  |  | 2607.5 |  |  | 2505.5 |  |  | 2509.5 |  |  | 2498.5 |  |  | 2522.5 |  |  | 2501 |  |  | 2428.5 |  |  | 2373 |  |  | 2485 |  |  | 2382 |  |  | 2673.5 |  |  | 2608.5 |  |  | 2408.5 |  |  | 2671.5 |  |  | 2393.5 |  |  | 2456 |  |  | 2467 |  |  | 2472.5 |  |  | 2519.5 |  |  | 2427.5 |  |  | 2521.5 |  |  | 2598.5 |  |  | 2571.5 |  |  | 2609.5 |  |  | 2633.5 |  |  | 2584.5 |  |  | 2457.5 |  |  | 2508.5 |  |  | 2551.5 |  |  | 2538.5 |  |  | 2592.5 |  |  | 2441.5 |  |  | 2505.5 |  |  | 2475.5 |  |  | 2572.5 |  |  | 2568.5 |  |  | 2554.5 |  |  | 2524.5 |  |  | 2502.5 |  |  | 2464 |  |  | 2489.5 |  |  | 2483.5 |  |  | 2434.5 |  |  | 2528.5 |  |  | 2581.5 |  |  | 2496 |  |  | 2435.5 |  |  | 2612.5 |  |  | 2447.5 |  |  | 2448.5 |  |  | 2547 |  |  | 2527.5 |  |  | 2602.5 |  |  | 2397 |  |  | 2544.5 |  |  | 2336 |  |  | 2603 |  |  | 2638.5 |  |  | 2532 |  |  | 2639.5 |  |  | 2434.5 |  |  | 2529.5 |  |  | 2441.5 |  |  | 2524.5 |  |  | 2550.5 |  |  | 2482.5 |  |  | 2553.5 |  |  | 2601.5 |  |  | 2556.5 |  |  | 2605 |  |  | 2416.5 |  |  | 2343 |  |  | 2434.5 |  |  | 2512.5 |  |  | 2443 |  |  | 2518.5 |  |  | 2447.5 |  |  | 2463.5 |  |  | 2363 |  |  | 2492.5 |  |  | 2341.5 |  |  | 2404.5 |  |  | 2589.5 |  |  | 2457.5 |  |  | 2448.5 |  |  | 2460 |  |  | 2520.5 |  |  | 2465.5 |  |  | 2409.5 |  |  | 2532.5 |  |  | 2501.5 |  |  | 2562.5 |  |  | 2444.5 |  |  | 2599 |  |  | 2543.5 |  |  | 2536.5 |  |  | 2579.5 |  |  | 2569.5 |  |  | 2452.5 |  |  | 2586.5 |  |  | 2585.5 |  |  | 2472.5 |  |  | 2643.5 |  |  | 2432.5 |  |  | 2571.5 |  |  | 2314.5 |  |  | 2301.5 |  |  | 2411 |  |  | 2442.5 |  |  | 2537.5 |  |  | 2516.5 |  |  | 2556.5 |  |  | 2581.5 |  |  | 2633.5 |  |  | 2643.5 |  |  | 2467.5 |  |  | 2543.5 |  |  | 2462.5 |  |  | 2419.5 |  |  | 2615.5 |  |  | 2502.5 |  |  | 2475.5 |  |  | 2472.5 |  |  | 2507.5 |  |  | 2561 |  |  | 2634.5 |  |  | 2507.5 |  |  | 2249 |  |  | 2658.5 |  |  | 2672 |  |  | 2349.5 |  |  | 2522.5 |  |  | 2590.5 |  |  | 2607.5 |  |  | 2465.5 |  |  | 2459.5 |  |  | 2515.5 |  |  | 2319.5 |  |  | 2319 |  |  | 2406.5 |  |  | 2337.5 |  |  | 2544.5 |  |  | 2464.5 |  |  | 2507 |  |  | 2481.5 |  |  | 2461.5 |  |  | 2610.5 |  |  | 2507.5 |  |  | 2622.5 |  |  | 2500.5 |  |  | 2489.5 |  |  | 2643.5 |  |  | 2614 |  |  | 2564 |  |  | 2451.5 |  |  | 2398.5 |  |  | 2545.5 |  |  | 2464 |  |  | 2646.5 |  |  | 2489.5 |  |  | 2486.5 |  |  | 2380 |  |  | 2622.5 |  |  | 2495.5 |  |  | 2354.5 |  |  | 2433.5 |  |  | 2479.5 |  |  | 2512.5 |  |  | 2574.5 |  |  | 2558.5 |  |  | 2607.5 |  |  | 2296 |  |  | 2418.5 |  |  | 2607.5 |  |  | 2536.5 |  |  | 2490.5 |  |  | 2478.5 |  |  | 2672 |  |  | 2393.5 |  |  | 2602.5 |  |  | 2586 |  |  | 2622.5 |  |  | 2529.5 |  |  | 2752 |  |  | 2587.5 |  |  | 2568.5 |  |  | 2656.5 |  |  | 2423.5 |  |  | 2480 |  |  | 2517 |  |  | 2510.5 |  |  | 2418.5 |  |  | 2569.5 |  |  | 2453.5 |  |  | 2680.5 |  |  | 2570.5 |  |  | 2484 |  |  | 2451.5 |  |  | 2416.5 |  |  | 2443 |  |  | 2485.5 |  |  | 2346.5 |  |  | 2507 |  |  | 2573.5 |  |  | 2421.5 |  |  | 2523.5 |  |  | 2543 |  |  | 2504.5 |  |  | 2416 |  |  | 2636.5 |  |  | 2422.5 |  |  | 2525.5 |  |  | 2460 |  |  | 2408.5 |  |  | 2633.5 |  |  | 2605.5 |  |  | 2531 |  |  | 2455.5 |  |  | 2324.5 |  |  | 2633.5 |  |  | 2671.5 |  |  | 2502.5 |  |  | 2532 |  |  | 2404.5 |  |  | 2613.5 |  |  | 2526.5 |  |  | 2478 |  |  | 2500 |  |  | 2674.5 |  |  | 2434.5 |  |  | 2337.5 |  |  | 2542.5 |  |  | 2483.5 |  |  | 2483.5 |  |  | 2520.5 |  |  | 2602.5 |  |  | 2413.5 |  |  | 2517.5 |  |  | 2521 |  |  | 2477.5 |  |  | 2554.5 |  |  | 2752.5 |  |  | 2662.5 |  |  | 2558 |  |  | 2492.5 |  |  | 2637.5 |  |  | 2528.5 |  |  | 2364.5 |  |  | 2608.5 |  |  | 2327 |  |  | 2557 |  |  | 2395 |  |  | 2599 |  |  | 2380.5 |  |  | 2506 |  |  | 2500.5 |  |  | 2511 |  |  | 2480.5 |  |  | 2642.5 |  |  | 2510.5 |  |  | 2490.5 |  |  | 2445.5 |  |  | 2519 |  |  | 2527.5 |  |  | 2663.5 |  |  | 2489.5 |  |  | 2515 |  |  | 2622.5 |  |  | 2456.5 |  |  | 2502.5 |  |  | 2586 |  |  | 2474.5 |  |  | 2402.5 |  |  | 2603.5 |  |  | 2410.5 |  |  | 2535.5 |  |  | 2428.5 |  |  | 2554.5 |  |  | 2494.5 |  |  | 2572.5 |  |  | 2377.5 |  |  | 2467 |  |  | 2452.5 |  |  | 2462.5 |  |  | 2387.5 |  |  | 2531.5 |  |  | 2613.5 |  |  | 2490 |  |  | 2570.5 |  |  | 2599 |  |  | 2475 |  |  | 2379.5 |  |  | 2575.5 |  |  | 2402.5 |  |  | 2491 |  |  | 2550.5 |  |  | 2557.5 |  |  | 2498.5 |  |  | 2367 |  |  | 2442.5 |  |  | 2337.5 |  |  | 2452.5 |  |  | 2371.5 |  |  | 2427.5 |  |  | 2438 |  |  | 2436.5 |  |  | 2562 |  |  | 2535.5 |  |  | 2298.5 |  |  | 2443.5 |  |  | 2518 |  |  | 2453.5 |  |  | 2425 |  |  | 2426 |  |  | 2477.5 |  |  | 2366.5 |  |  | 2410.5 |  |  | 2643.5 |  |  | 2673 |  |  | 2606.5 |  |  | 2506.5 |  |  | 2287.5 |  |  | 2480 |  |  | 2567.5 |  |  | 2450.5 |  |  | 2254.5 |  |  | 2542.5 |  |  | 2674 |  |  | 2375.5 |  |  | 2465.5 |  |  | 2520.5 |  |  | 2554.5 |  |  | 2509.5 |  |  | 2516.5 |  |  | 2591 |  |  | 2424.5 |  |  | 2428.5 |  |  | 2501 |  |  | 2406.5 |  |  | 2375.5 |  |  | 2485.5 |  |  | 2505 |  |  | 2563.5 |  |  | 2509.5 |  |  | 2497.5 |  |  | 2427.5 |  |  | 2529.5 |  |  | 2533 |  |  | 2407 |  |  | 2474.5 |  |  | 2575.5 |  |  | 2553.5 |  |  | 2352.5 |  |  | 2269 |  |  | 2585 |  |  | 2444 |  |  | 2609.5 |  |  | 2473 |  |  | 2534.5 |  |  | 2612.5 |  |  | 2577 |  |  | 2366.5 |  |  | 2533.5 |  |  | 2469.5 |  |  | 2562.5 |  |  | 2227.5 |  |  | 2495 |  |  | 2574 |  |  | 2423.5 |  |  | 2591.5 |  |  | 2405 |  |  | 2425.5 |  |  | 2485.5 |  |  | 2461 |  |  | 2653.5 |  |  | 2632.5 |  |  | 2406 |  |  | 2567.5 |  |  | 2531.5 |  |  | 2598 |  |  | 2457.5 |  |  | 2416 |  |  | 2638.5 |  |  | 2592 |  |  | 2420.5 |  |  | 2402.5 |  |  | 2424.5 |  |  | 2505.5 |  |  | 2510.5 |  |  | 2379.5 |  |  | 2550 |  |  | 2422.5 |  |  | 2541.5 |  |  | 2437.5 |  |  | 2447.5 |  |  | 2494.5 |  |  | 2426 |  |  | 2458.5 |  |  | 2530 |  |  | 2495.5 |  |  | 2347.5 |  |  | 2565.5 |  |  | 2545.5 |  |  | 2549.5 |  |  | 2488.5 |  |  | 2396.5 |  |  | 2564.5 |  |  | 2374.5 |  |  | 2402 |  |  | 2546.5 |  |  | 2387 |  |  | 2500 |  |  | 2531.5 |  |  | 2278 |  |  | 2359.5 |  |  | 2577.5 |  |  | 2604.5 |  |  | 2535.5 |  |  | 2596.5 |  |  | 2518.5 |  |  | 2541.5 |  |  | 2468 |  |  | 2644 |  |  | 2379.5 |  |  | 2504.5 |  |  | 2489 |  |  | 2442.5 |  |  | 2442.5 |  |  | 2442.5 |  |  | 2382.5 |  |  | 2484.5 |  |  | 2374 |  |  | 2504.5 |  |  | 2470.5 |  |  | 2394.5 |  |  | 2470 |  |  | 2529.5 |  |  | 2579.5 |  |  | 2525.5 |  |  | 2729.5 |  |  | 2516.5 |  |  | 2409.5 |  |  | 2537.5 |  |  | 2119.5 |  |  | 2492.5 |  |  | 2400 |  |  | 2629.5 |  |  | 2518.5 |  |  | 2586.5 |  |  | 2361.5 |  |  | 2466.5 |  |  | 2401.5 |  |  | 2394.5 |  |  | 2364 |  |  | 2398.5 |  |  | 2492.5 |  |  | 2465.5 |  |  | 2499 |  |  | 2554.5 |  |  | 2389 |  |  | 2360.5 |  |  | 2522.5 |  |  | 2472.5 |  |  | 2558 |  |  | 2326.5 |  |  | 2512 |  |  | 2480 |  |  | 2497.5 |  |  | 2487 |  |  | 2646 |  |  | 2578.5 |  |  | 2569.5 |  |  | 2389.5 |  |  | 2568 |  |  | 2525.5 |  |  | 2401.5 |  |  | 2352.5 |  |  | 2608.5 |  |  | 2440.5 |  |  | 2482.5 |  |  | 2488.5 |  |  | 2511.5 |  |  | 2476 |  |  | 2637.5 |  |  | 2428 |  |  | 2531.5 |  |  | 2401.5 |  |  | 2593.5 |  |  | 2513 |  |  | 2543 |  |  | 2630 |  |  | 2519.5 |  |  | 2483 |  |  | 2570.5 |  |  | 2644.5 |  |  | 2500.5 |  |  | 2463.5 |  |  | 2413.5 |  |  | 2631.5 |  |  | 2627.5 |  |  | 2547.5 |  |  | 2560 |  |  | 2339.5 |  |  | 2355.5 |  |  | 2522.5 |  |  | 2459.5 |  |  | 2421 |  |  | 2487.5 |  |  | 2549 |  |  | 2533.5 |  |  | 2505.5 |  |  | 2449.5 |  |  | 2382.5 |  |  | 2384 |  |  | 2469.5 |  |  | 2253 |  |  | 2437.5 |  |  | 2584.5 |  |  | 2642.5 |  |  | 2481.5 |  |  | 2504.5 |  |  | 2544.5 |  |  | 2453.5 |  |  | 2524.5 |  |  | 2451.5 |  |  | 2386 |  |  | 2511.5 |  |  | 2483.5 |  |  | 2466.5 |  |  | 2549.5 |  |  | 2559.5 |  |  | 2427 |  |  | 2436 |  |  | 2459.5 |  |  | 2444 |  |  | 2638.5 |  |  | 2433.5 |  |  | 2609.5 |  |  | 2505.5 |  |  | 2445.5 |  |  | 2602.5 |  |  | 2541.5 |  |  | 2559.5 |  |  | 2532 |  |  | 2511.5 |  |  | 2694.5 |  |  | 2439.5 |  |  | 2323 |  |  | 2483.5 |  |  | 2401.5 |  |  | 2625 |  |  | 2460 |  |  | 2483.5 |  |  | 2487 |  |  | 2334 |  |  | 2347.5 |  |  | 2601 |  |  | 2712.5 |  |  | 2464.5 |  |  | 2610.5 |  |  | 2471.5 |  |  | 2382.5 |  |  | 2465.5 |  |  | 2314.5 |  |  | 2410.5 |  |  | 2516.5 |  |  | 2421.5 |  |  | 2394 |  |  | 2383 |  |  | 2587.5 |  |  | 2599.5 |  |  | 2432.5 |  |  | 2566.5 |  |  | 2479.5 |  |  | 2550.5 |  |  | 2534.5 |  |  | 2423.5 |  |  | 2712 |  |  | 2431.5 |  |  | 2476 |  |  | 2432.5 |  |  | 2615.5 |  |  | 2557.5 |  |  | 2590 |  |  | 2471.5 |  |  | 2416.5 |  |  | 2543 |  |  | 2545.5 |  |  | 2473.5 |  |  | 2588.5 |  |  | 2463.5 |  |  | 2490.5 |  |  | 2548.5 |  |  | 2571 |  |  | 2431.5 |  |  | 2482.5 |  |  | 2632.5 |  |  | 2525.5 |  |  | 2470 |  |  | 2496.5 |  |  | 2630.5 |  |  | 2459 |  |  | 2474.5 |  |  | 2592.5 |  |  | 2553 |  |  | 2575.5 |  |  | 2621.5 |  |  | 2496.5 |  |  | 2452 |  |  | 2400.5 |  |  | 2490.5 |  |  | 2390 |  |  | 2505.5 |  |  | 2504.5 |  |  | 2523.5 |  |  | 2358.5 |  |  | 2514.5 |  |  | 2654.5 |  |  | 2423.5 |  |  | 2481 |  |  | 2401 |  |  | 2327.5 |  |  | 2566.5 |  |  | 2370.5 |  |  | 2599 |  |  | 2659.5 |  |  | 2446.5 |  |  | 2468.5 |  |  | 2330.5 |  |  | 2494.5 |  |  | 2546.5 |  |  | 2400.5 |  |  | 2545.5 |  |  | 2294.5 |  |  | 2502 |  |  | 2450.5 |  |  | 2320.5 |  |  | 2468.5 |  |  | 2517.5 |  |  | 2683.5 |  |  | 2563.5 |  |  | 2496.5 |  |  | 2485.5 |  |  | 2369.5 |  |  | 2603.5 |  |  | 2473.5 |  |  | 2393.5 |  |  | 2523.5 |  |  | 2587 |  |  | 2504.5 |  |  | 2566.5 |  |  | 2443 |  |  | 2575.5 |  |  | 2567.5 |  |  | 2636 |  |  | 2535.5 |  |  | 2580.5 |  |  | 2673.5 |  |  | 2662 |  |  | 2394.5 |  |  | 2595.5 |  |  | 2483.5 |  |  | 2276.5 |  |  | 2565.5 |  |  | 2403 |  |  | 2439.5 |  |  | 2573 |  |  | 2563 |  |  | 2569.5 |  |  | 2498.5 |  |  | 2434.5 |  |  | 2250.5 |  |  | 2435.5 |  |  | 2588.5 |  |  | 2447 |  |  | 2453.5 |  |  | 2412 |  |  | 2471.5 |  |  | 2503 |  |  | 2392 |  |  | 2573 |  |  | 2567.5 |  |  | 2423 |  |  | 2654.5 |  |  | 2552.5 |  |  | 2478.5 |  |  | 2670.5 |  |  | 2353.5 |  |  | 2606 |  |  | 2507.5 |  |  | 2572.5 |  |  | 2726.5 |  |  | 2492 |  |  | 2477.5 |  |  | 2446.5 |  |  | 2507.5 |  |  | 2617.5 |  |  | 2502 |  |  | 2583 |  |  | 2442 |  |  | 2482.5 |  |  | 2622 |  |  | 2525 |  |  | 2562.5 |  |  | 2440.5 |  |  | 2370.5 |  |  | 2512.5 |  |  | 2522.5 |  |  | 2511.5 |  |  | 2570.5 |  |  | 2471.5 |  |  | 2446.5 |  |  | 2405 |  |  | 2434.5 |  |  | 2385 |  |  | 2512.5 |  |  | 2486.5 |  |  | 2551.5 |  |  | 2547.5 |  |  | 2622 |  |  | 2516.5 |  |  | 2508 |  |  | 2430.5 |  |  | 2538.5 |  |  | 2355 |  |  | 2431 |  |  | 2576.5 |  |  | 2538 |  |  | 2501.5 |  |  | 2353.5 |  |  | 2408.5 |  |  | 2442.5 |  |  | 2532.5 |  |  | 2522.5 |  |  | 2397.5 |  |  | 2449 |  |  | 2545.5 |  |  | 2531.5 |  |  | 2533.5 |  |  | 2530.5 |  |  | 2444.5 |  |  | 2547.5 |  |  | 2640.5 |  |  | 2510.5 |  |  | 2635.5 |  |  | 2648.5 |  |  | 2376.5 |  |  | 2362.5 |  |  | 2504 |  |  | 2396.5 |  |  | 2453.5 |  |  | 2556 |  |  | 2411.5 |  |  | 2405.5 |  |  | 2475.5 |  |  | 2381.5 |  |  | 2711 |  |  | 2603.5 |  |  | 2434.5 |  |  | 2372.5 |  |  | 2651.5 |  |  | 2460 |  |  | 2445.5 |  |  | 2607.5 |  |  | 2421.5 |  |  | 2605.5 |  |  | 2422.5 |  |  | 2404.5 |  |  | 2584.5 |  |  | 2474.5 |  |  | 2512.5 |  |  | 2516.5 |  |  | 2560.5 |  |  | 2559 |  |  | 2521.5 |  |  | 2437.5 |  |  | 2554.5 |  |  | 2618.5 |  |  | 2419.5 |  |  | 2462.5 |  |  | 2563 |  |  | 2592.5 |  |  | 2414 |  |  | 2397.5 |  |  | 2564.5 |  |  | 2569.5 |  |  | 2505 |  |  | 2418 |  |  | 2544.5 |  |  | 2577.5 |  |  | 2269.5 |  |  | 2666.5 |  |  | 2493.5 |  |  | 2544.5 |  |  | 2428.5 |  |  | 2606.5 |  |  | 2423.5 |  |  | 2642.5 |  |  | 2507.5 |  |  | 2552.5 |  |  | 2376.5 |  |  | 2554.5 |  |  | 2613.5 |  |  | 2503.5 |  |  | 2490.5 |  |  | 2515.5 |  |  | 2440.5 |  |  | 2453.5 |  |  | 2547.5 |  |  | 2568.5 |  |  | 2490 |  |  | 2593.5 |  |  | 2494.5 |  |  | 2564.5 |  |  | 2530 |  |  | 2555.5 |  |  | 2501.5 |  |  | 2598.5 |  |  | 2531.5 |  |  | 2528 |  |  | 2368.5 |  |  | 2381.5 |  |  | 2407 |  |  | 2495 |  |  | 2459 |  |  | 2517.5 |  |  | 2493.5 |  |  | 2565.5 |  |  | 2690.5 |  |  | 2571 |  |  | 2556.5 |  |  | 2501.5 |  |  | 2387 |  |  | 2478 |  |  | 2535.5 |  |  | 2576.5 |  |  | 2614 |  |  | 2503.5 |  |  | 2604 |  |  | 2437.5 |  |  | 2457.5 |  |  | 2604 |  |  | 2611.5 |  |  | 2520.5 |  |  | 2367.5 |  |  | 2610 |  |  | 2428.5 |  |  | 2404.5 |  |  | 2444.5 |  |  | 2512.5 |  |  | 2500.5 |  |  | 2544.5 |  |  | 2457.5 |  |  | 2542.5 |  |  | 2576.5 |  |  | 2500.5 |  |  | 2480 |  |  | 2486.5 |  |  | 2541.5 |  |  | 2585.5 |  |  | 2617.5 |  |  | 2462.5 |  |  | 2514.5 |  |  | 2612.5 |  |  | 2446.5 |  |  | 2602 |  |  | 2459.5 |  |  | 2451 |  |  | 2717.5 |  |  | 2696.5 |  |  | 2716.5 |  |  | 2428.5 |  |  | 2416.5 |  |  | 2540.5 |  |  | 2368.5 |  |  | 2543.5 |  |  | 2545 |  |  | 2421.5 |  |  | 2546 |  |  | 2356.5 |  |  | 2443.5 |  |  | 2515.5 |  |  | 2567 |  |  | 2459.5 |  |  | 2535.5 |  |  | 2279 |  |  | 2498.5 |  |  | 2449 |  |  | 2506.5 |  |  | 2406.5 |  |  | 2444.5 |  |  | 2522 |  |  | 2593.5 |  |  | 2709.5 |  |  | 2369 |  |  | 2682.5 |  |  | 2493.5 |  |  | 2550 |  |  | 2503.5 |  |  | 2659.5 |  |  | 2580.5 |  |  | 2605.5 |  |  | 2441.5 |  |  | 2668.5 |  |  | 2394.5 |  |  | 2466.5 |  |  | 2433.5 |  |  | 2425.5 |  |  | 2668.5 |  |  | 2616 |  |  | 2518 |  |  | 2618.5 |  |  | 2503.5 |  |  | 2573
86 |  | 2491.5 |  |  | 2616.5 |  |  | 2585 |  |  | 2521.5 |  |  | 2701.5 |  |  | 2552.5 |  |  | 2588.5 |  |  | 2557.5 |  |  | 2527.5 |  |  | 2510.5 |  |  | 2431 |  |  | 2615.5 |  |  | 2580.5 |  |  | 2410.5 |  |  | 2416 |  |  | 2549.5 |  |  | 2620.5 |  |  | 2504.5 |  |  | 2603.5 |  |  | 2454.5 |  |  | 2671.5 |  |  | 2558.5 |  |  | 2618.5 |  |  | 2464.5 |  |  | 2325 |  |  | 2609.5 |  |  | 2545.5 |  |  | 2484.5 |  |  | 2601.5 |  |  | 2394 |  |  | 2546 |  |  | 2647.5 |  |  | 2345.5 |  |  | 2548.5 |  |  | 2434.5 |  |  | 2569 |  |  | 2477.5 |  |  | 2679 |  |  | 2529.5 |  |  | 2516.5 |  |  | 2317.5 |  |  | 2571.5 |  |  | 2405.5 |  |  | 2514 |  |  | 2726.5 |  |  | 2637 |  |  | 2571.5 |  |  | 2606.5 |  |  | 2645.5 |  |  | 2576.5 |  |  | 2419.5 |  |  | 2591.5 |  |  | 2554.5 |  |  | 2526.5 |  |  | 2589.5 |  |  | 2572.5 |  |  | 2423.5 |  |  | 2541 |  |  | 2552.5 |  |  | 2555.5 |  |  | 2508 |  |  | 2544.5 |  |  | 2642.5 |  |  | 2477.5 |  |  | 2445.5 |  |  | 2564 |  |  | 2685.5 |  |  | 2395 |  |  | 2402.5 |  |  | 2559.5 |  |  | 2517 |  |  | 2455.5 |  |  | 2526.5 |  |  | 2638.5 |  |  | 2658 |  |  | 2609 |  |  | 2392.5 |  |  | 2451.5 |  |  | 2448.5 |  |  | 2545.5 |  |  | 2497 |  |  | 2579.5 |  |  | 2605.5 |  |  | 2615.5 |  |  | 2660.5 |  |  | 2427.5 |  |  | 2628.5 |  |  | 2544.5 |  |  | 2538.5 |  |  | 2522.5 |  |  | 2546.5 |  |  | 2540 |  |  | 2475.5 |  |  | 2399 |  |  | 2500 |  |  | 2403 |  |  | 2697.5 |  |  | 2623.5 |  |  | 2429.5 |  |  | 2710.5 |  |  | 2440.5 |  |  | 2480 |  |  | 2496 |  |  | 2511.5 |  |  | 2566.5 |  |  | 2474.5 |  |  | 2547.5 |  |  | 2645.5 |  |  | 2586.5 |  |  | 2648.5 |  |  | 2662.5 |  |  | 2610.5 |  |  | 2496.5 |  |  | 2547.5 |  |  | 2572.5 |  |  | 2585.5 |  |  | 2631.5 |  |  | 2480.5 |  |  | 2531.5 |  |  | 2490.5 |  |  | 2593.5 |  |  | 2583.5 |  |  | 2580.5 |  |  | 2571.5 |  |  | 2528.5 |  |  | 2493 |  |  | 2504.5 |  |  | 2530.5 |  |  | 2473.5 |  |  | 2549.5 |  |  | 2596.5 |  |  | 2511 |  |  | 2456.5 |  |  | 2651.5 |  |  | 2494.5 |  |  | 2495.5 |  |  | 2594 |  |  | 2574.5 |  |  | 2628.5 |  |  | 2412 |  |  | 2583.5 |  |  | 2351 |  |  | 2632 |  |  | 2677.5 |  |  | 2571 |  |  | 2663.5 |  |  | 2481.5 |  |  | 2576.5 |  |  | 2462.5 |  |  | 2563.5 |  |  | 2579.5 |  |  | 2503.5 |  |  | 2579.5 |  |  | 2622.5 |  |  | 2571.5 |  |  | 2620 |  |  | 2431.5 |  |  | 2382 |  |  | 2460.5 |  |  | 2536.5 |  |  | 2464 |  |  | 2542.5 |  |  | 2476.5 |  |  | 2484.5 |  |  | 2384 |  |  | 2531.5 |  |  | 2362.5 |  |  | 2430.5 |  |  | 2615.5 |  |  | 2496.5 |  |  | 2487.5 |  |  | 2499 |  |  | 2559.5 |  |  | 2486.5 |  |  | 2433.5 |  |  | 2571.5 |  |  | 2540.5 |  |  | 2591.5 |  |  | 2465.5 |  |  | 2638 |  |  | 2582.5 |  |  | 2565.5 |  |  | 2603.5 |  |  | 2593.5 |  |  | 2478.5 |  |  | 2610.5 |  |  | 2600.5 |  |  | 2493.5 |  |  | 2658.5 |  |  | 2471.5 |  |  | 2600.5 |  |  | 2343.5 |  |  | 2330.5 |  |  | 2426 |  |  | 2471.5 |  |  | 2552.5 |  |  | 2555.5 |  |  | 2582.5 |  |  | 2605.5 |  |  | 2672.5 |  |  | 2658.5 |  |  | 2514.5 |  |  | 2582.5 |  |  | 2509.5 |  |  | 2434.5 |  |  | 2636.5 |  |  | 2517.5 |  |  | 2496.5 |  |  | 2511.5 |  |  | 2536.5 |  |  | 2576 |  |  | 2658.5 |  |  | 2546.5 |  |  | 2273 |  |  | 2679.5 |  |  | 2711 |  |  | 2364.5 |  |  | 2548.5 |  |  | 2619.5 |  |  | 2654.5 |  |  | 2480.5 |  |  | 2480.5 |  |  | 2562.5 |  |  | 2340.5 |  |  | 2348 |  |  | 2430.5 |  |  | 2361.5 |  |  | 2565.5 |  |  | 2490.5 |  |  | 2536 |  |  | 2507.5 |  |  | 2482.5 |  |  | 2631.5 |  |  | 2546.5 |  |  | 2646.5 |  |  | 2526.5 |  |  | 2518.5 |  |  | 2682.5 |  |  | 2653 |  |  | 2585 |  |  | 2477.5 |  |  | 2413.5 |  |  | 2584.5 |  |  | 2511 |  |  | 2672.5 |  |  | 2515.5 |  |  | 2525.5 |  |  | 2401 |  |  | 2646.5 |  |  | 2524.5 |  |  | 2369.5 |  |  | 2454.5 |  |  | 2526.5 |  |  | 2551.5 |  |  | 2613.5 |  |  | 2584.5 |  |  | 2633.5 |  |  | 2335 |  |  | 2457.5 |  |  | 2622.5 |  |  | 2551.5 |  |  | 2511.5 |  |  | 2517.5 |  |  | 2693 |  |  | 2414.5 |  |  | 2641.5 |  |  | 2615 |  |  | 2648.5 |  |  | 2568.5 |  |  | 2778 |  |  | 2616.5 |  |  | 2597.5 |  |  | 2703.5 |  |  | 2449.5 |  |  | 2519 |  |  | 2538 |  |  | 2536.5 |  |  | 2433.5 |  |  | 2616.5 |  |  | 2492.5 |  |  | 2695.5 |  |  | 2585.5 |  |  | 2523 |  |  | 2477.5 |  |  | 2431.5 |  |  | 2490 |  |  | 2506.5 |  |  | 2367.5 |  |  | 2528 |  |  | 2594.5 |  |  | 2460.5 |  |  | 2562.5 |  |  | 2590 |  |  | 2533.5 |  |  | 2455 |  |  | 2675.5 |  |  | 2446.5 |  |  | 2546.5 |  |  | 2484 |  |  | 2437.5 |  |  | 2672.5 |  |  | 2620.5 |  |  | 2560 |  |  | 2502.5 |  |  | 2363.5 |  |  | 2659.5 |  |  | 2718.5 |  |  | 2541.5 |  |  | 2561 |  |  | 2451.5 |  |  | 2652.5 |  |  | 2555.5 |  |  | 2504 |  |  | 2529 |  |  | 2713.5 |  |  | 2449.5 |  |  | 2352.5 |  |  | 2589.5 |  |  | 2522.5 |  |  | 2522.5 |  |  | 2559.5 |  |  | 2626.5 |  |  | 2439.5 |  |  | 2538.5 |  |  | 2560 |  |  | 2492.5 |  |  | 2575.5 |  |  | 2767.5 |  |  | 2701.5 |  |  | 2597 |  |  | 2539.5 |  |  | 2663.5 |  |  | 2552.5 |  |  | 2390.5 |  |  | 2647.5 |  |  | 2342 |  |  | 2572 |  |  | 2416 |  |  | 2620 |  |  | 2419.5 |  |  | 2530 |  |  | 2524.5 |  |  | 2550 |  |  | 2519.5 |  |  | 2666.5 |  |  | 2534.5 |  |  | 2529.5 |  |  | 2492.5 |  |  | 2558 |  |  | 2548.5 |  |  | 2692.5 |  |  | 2515.5 |  |  | 2554 |  |  | 2669.5 |  |  | 2482.5 |  |  | 2541.5 |  |  | 2607 |  |  | 2489.5 |  |  | 2441.5 |  |  | 2629.5 |  |  | 2449.5 |  |  | 2582.5 |  |  | 2457.5 |  |  | 2593.5 |  |  | 2518.5 |  |  | 2611.5 |  |  | 2392.5 |  |  | 2482 |  |  | 2473.5 |  |  | 2509.5 |  |  | 2426.5 |  |  | 2570.5 |  |  | 2652.5 |  |  | 2505 |  |  | 2609.5 |  |  | 2625 |  |  | 2522 |  |  | 2418.5 |  |  | 2614.5 |  |  | 2428.5 |  |  | 2520 |  |  | 2574.5 |  |  | 2581.5 |  |  | 2545.5 |  |  | 2391 |  |  | 2481.5 |  |  | 2361.5 |  |  | 2491.5 |  |  | 2392.5 |  |  | 2456.5 |  |  | 2477 |  |  | 2475.5 |  |  | 2586 |  |  | 2550.5 |  |  | 2337.5 |  |  | 2482.5 |  |  | 2542 |  |  | 2492.5 |  |  | 2472 |  |  | 2473 |  |  | 2516.5 |  |  | 2395.5 |  |  | 2449.5 |  |  | 2690.5 |  |  | 2712 |  |  | 2632.5 |  |  | 2535.5 |  |  | 2334.5 |  |  | 2495 |  |  | 2591.5 |  |  | 2471.5 |  |  | 2278.5 |  |  | 2566.5 |  |  | 2721 |  |  | 2401.5 |  |  | 2480.5 |  |  | 2559.5 |  |  | 2593.5 |  |  | 2556.5 |  |  | 2555.5 |  |  | 2620 |  |  | 2453.5 |  |  | 2457.5 |  |  | 2540 |  |  | 2427.5 |  |  | 2399.5 |  |  | 2524.5 |  |  | 2520 |  |  | 2602.5 |  |  | 2538.5 |  |  | 2512.5 |  |  | 2474.5 |  |  | 2555.5 |  |  | 2559 |  |  | 2428 |  |  | 2521.5 |  |  | 2601.5 |  |  | 2582.5 |  |  | 2381.5 |  |  | 2308 |  |  | 2606 |  |  | 2491 |  |  | 2630.5 |  |  | 2497 |  |  | 2573.5 |  |  | 2651.5 |  |  | 2606 |  |  | 2387.5 |  |  | 2548.5 |  |  | 2490.5 |  |  | 2586.5 |  |  | 2266.5 |  |  | 2534 |  |  | 2613 |  |  | 2449.5 |  |  | 2630.5 |  |  | 2420 |  |  | 2449.5 |  |  | 2524.5 |  |  | 2485 |  |  | 2692.5 |  |  | 2671.5 |  |  | 2435 |  |  | 2614.5 |  |  | 2578.5 |  |  | 2637 |  |  | 2472.5 |  |  | 2431 |  |  | 2667.5 |  |  | 2639 |  |  | 2435.5 |  |  | 2441.5 |  |  | 2445.5 |  |  | 2520.5 |  |  | 2549.5 |  |  | 2418.5 |  |  | 2571 |  |  | 2437.5 |  |  | 2570.5 |  |  | 2463.5 |  |  | 2494.5 |  |  | 2509.5 |  |  | 2441 |  |  | 2473.5 |  |  | 2577 |  |  | 2534.5 |  |  | 2386.5 |  |  | 2580.5 |  |  | 2571.5 |  |  | 2588.5 |  |  | 2517.5 |  |  | 2443.5 |  |  | 2603.5 |  |  | 2398.5 |  |  | 2441 |  |  | 2567.5 |  |  | 2426 |  |  | 2526 |  |  | 2555.5 |  |  | 2293 |  |  | 2383.5 |  |  | 2598.5 |  |  | 2630.5 |  |  | 2556.5 |  |  | 2622.5 |  |  | 2565.5 |  |  | 2570.5 |  |  | 2507 |  |  | 2665 |  |  | 2405.5 |  |  | 2543.5 |  |  | 2528 |  |  | 2471.5 |  |  | 2481.5 |  |  | 2457.5 |  |  | 2421.5 |  |  | 2505.5 |  |  | 2403 |  |  | 2519.5 |  |  | 2491.5 |  |  | 2441.5 |  |  | 2494 |  |  | 2550.5 |  |  | 2626.5 |  |  | 2572.5 |  |  | 2776.5 |  |  | 2540.5 |  |  | 2424.5 |  |  | 2563.5 |  |  | 2158.5 |  |  | 2516.5 |  |  | 2439 |  |  | 2658.5 |  |  | 2542.5 |  |  | 2633.5 |  |  | 2390.5 |  |  | 2513.5 |  |  | 2416.5 |  |  | 2415.5 |  |  | 2385 |  |  | 2445.5 |  |  | 2521.5 |  |  | 2489.5 |  |  | 2523 |  |  | 2583.5 |  |  | 2410 |  |  | 2399.5 |  |  | 2543.5 |  |  | 2501.5 |  |  | 2597 |  |  | 2350.5 |  |  | 2536 |  |  | 2519 |  |  | 2544.5 |  |  | 2526 |  |  | 2685 |  |  | 2593.5 |  |  | 2616.5 |  |  | 2415.5 |  |  | 2594 |  |  | 2540.5 |  |  | 2440.5 |  |  | 2367.5 |  |  | 2623.5 |  |  | 2455.5 |  |  | 2511.5 |  |  | 2535.5 |  |  | 2535.5 |  |  | 2491 |  |  | 2663.5 |  |  | 2467 |  |  | 2570.5 |  |  | 2422.5 |  |  | 2614.5 |  |  | 2534 |  |  | 2582 |  |  | 2669 |  |  | 2558.5 |  |  | 2530 |  |  | 2596.5 |  |  | 2673.5 |  |  | 2524.5 |  |  | 2502.5 |  |  | 2434.5 |  |  | 2646.5 |  |  | 2642.5 |  |  | 2571.5 |  |  | 2584 |  |  | 2378.5 |  |  | 2402.5 |  |  | 2561.5 |  |  | 2506.5 |  |  | 2450 |  |  | 2513.5 |  |  | 2564 |  |  | 2559.5 |  |  | 2529.5 |  |  | 2464.5 |  |  | 2397.5 |  |  | 2408 |  |  | 2498.5 |  |  | 2277 |  |  | 2463.5 |  |  | 2605.5 |  |  | 2689.5 |  |  | 2496.5 |  |  | 2528.5 |  |  | 2583.5 |  |  | 2482.5 |  |  | 2548.5 |  |  | 2472.5 |  |  | 2425 |  |  | 2532.5 |  |  | 2507.5 |  |  | 2490.5 |  |  | 2588.5 |  |  | 2598.5 |  |  | 2456 |  |  | 2457 |  |  | 2485.5 |  |  | 2465 |  |  | 2653.5 |  |  | 2448.5 |  |  | 2648.5 |  |  | 2534.5 |  |  | 2471.5 |  |  | 2649.5 |  |  | 2580.5 |  |  | 2588.5 |  |  | 2571 |  |  | 2535.5 |  |  | 2718.5 |  |  | 2478.5 |  |  | 2362 |  |  | 2522.5 |  |  | 2422.5 |  |  | 2664 |  |  | 2489 |  |  | 2498.5 |  |  | 2508 |  |  | 2373 |  |  | 2394.5 |  |  | 2640 |  |  | 2727.5 |  |  | 2511.5 |  |  | 2625.5 |  |  | 2486.5 |  |  | 2411.5 |  |  | 2512.5 |  |  | 2340.5 |  |  | 2449.5 |  |  | 2555.5 |  |  | 2436.5 |  |  | 2433 |  |  | 2430 |  |  | 2616.5 |  |  | 2638.5 |  |  | 2447.5 |  |  | 2592.5 |  |  | 2500.5 |  |  | 2574.5 |  |  | 2563.5 |  |  | 2462.5 |  |  | 2741 |  |  | 2460.5 |  |  | 2497 |  |  | 2461.5 |  |  | 2641.5 |  |  | 2581.5 |  |  | 2637 |  |  | 2510.5 |  |  | 2445.5 |  |  | 2569 |  |  | 2569.5 |  |  | 2520.5 |  |  | 2627.5 |  |  | 2502.5 |  |  | 2514.5 |  |  | 2569.5 |  |  | 2610 |  |  | 2452.5 |  |  | 2506.5 |  |  | 2653.5 |  |  | 2564.5 |  |  | 2517 |  |  | 2522.5 |  |  | 2669.5 |  |  | 2485 |  |  | 2513.5 |  |  | 2618.5 |  |  | 2582 |  |  | 2614.5 |  |  | 2660.5 |  |  | 2517.5 |  |  | 2473 |  |  | 2424.5 |  |  | 2529.5 |  |  | 2429 |  |  | 2552.5 |  |  | 2525.5 |  |  | 2570.5 |  |  | 2382.5 |  |  | 2538.5 |  |  | 2693.5 |  |  | 2447.5 |  |  | 2502 |  |  | 2440 |  |  | 2353.5 |  |  | 2590.5 |  |  | 2409.5 |  |  | 2628 |  |  | 2683.5 |  |  | 2485.5 |  |  | 2507.5 |  |  | 2345.5 |  |  | 2533.5 |  |  | 2575.5 |  |  | 2429.5 |  |  | 2566.5 |  |  | 2309.5 |  |  | 2541 |  |  | 2476.5 |  |  | 2346.5 |  |  | 2507.5 |  |  | 2538.5 |  |  | 2709.5 |  |  | 2592.5 |  |  | 2535.5 |  |  | 2506.5 |  |  | 2384.5 |  |  | 2642.5 |  |  | 2512.5 |  |  | 2432.5 |  |  | 2562.5 |  |  | 2634 |  |  | 2551.5 |  |  | 2605.5 |  |  | 2467 |  |  | 2590.5 |  |  | 2596.5 |  |  | 2675 |  |  | 2574.5 |  |  | 2619.5 |  |  | 2702.5 |  |  | 2701 |  |  | 2441.5 |  |  | 2619.5 |  |  | 2504.5 |  |  | 2315.5 |  |  | 2604.5 |  |  | 2432 |  |  | 2454.5 |  |  | 2594 |  |  | 2584 |  |  | 2608.5 |  |  | 2519.5 |  |  | 2455.5 |  |  | 2276.5 |  |  | 2464.5 |  |  | 2627.5 |  |  | 2471 |  |  | 2482.5 |  |  | 2459 |  |  | 2497.5 |  |  | 2518 |  |  | 2418 |  |  | 2597 |  |  | 2614.5 |  |  | 2462 |  |  | 2675.5 |  |  | 2591.5 |  |  | 2504.5 |  |  | 2685.5 |  |  | 2368.5 |  |  | 2645 |  |  | 2531.5 |  |  | 2593.5 |  |  | 2752.5 |  |  | 2531 |  |  | 2501.5 |  |  | 2467.5 |  |  | 2531.5 |  |  | 2632.5 |  |  | 2517 |  |  | 2604 |  |  | 2489 |  |  | 2497.5 |  |  | 2669 |  |  | 2546 |  |  | 2601.5 |  |  | 2455.5 |  |  | 2409.5 |  |  | 2533.5 |  |  | 2569.5 |  |  | 2550.5 |  |  | 2599.5 |  |  | 2486.5 |  |  | 2493.5 |  |  | 2444 |  |  | 2458.5 |  |  | 2411 |  |  | 2551.5 |  |  | 2525.5 |  |  | 2590.5 |  |  | 2568.5 |  |  | 2651 |  |  | 2563.5 |  |  | 2537 |  |  | 2454.5 |  |  | 2577.5 |  |  | 2394 |  |  | 2470 |  |  | 2605.5 |  |  | 2585 |  |  | 2540.5 |  |  | 2382.5 |  |  | 2432.5 |  |  | 2457.5 |  |  | 2561.5 |  |  | 2537.5 |  |  | 2423.5 |  |  | 2475 |  |  | 2569.5 |  |  | 2557.5 |  |  | 2554.5 |  |  | 2577.5 |  |  | 2459.5 |  |  | 2571.5 |  |  | 2664.5 |  |  | 2536.5 |  |  | 2674.5 |  |  | 2663.5 |  |  | 2405.5 |  |  | 2391.5 |  |  | 2525 |  |  | 2422.5 |  |  | 2482.5 |  |  | 2595 |  |  | 2450.5 |  |  | 2429.5 |  |  | 2504.5 |  |  | 2420.5 |  |  | 2735 |  |  | 2624.5 |  |  | 2455.5 |  |  | 2398.5 |  |  | 2680.5 |  |  | 2499 |  |  | 2492.5 |  |  | 2628.5 |  |  | 2436.5 |  |  | 2626.5 |  |  | 2461.5 |  |  | 2419.5 |  |  | 2631.5 |  |  | 2489.5 |  |  | 2536.5 |  |  | 2563.5 |  |  | 2599.5 |  |  | 2588 |  |  | 2545.5 |  |  | 2452.5 |  |  | 2575.5 |  |  | 2647.5 |  |  | 2445.5 |  |  | 2486.5 |  |  | 2592 |  |  | 2631.5 |  |  | 2453 |  |  | 2421.5 |  |  | 2579.5 |  |  | 2584.5 |  |  | 2526 |  |  | 2457 |  |  | 2591.5 |  |  | 2624.5 |  |  | 2298.5 |  |  | 2705.5 |  |  | 2522.5 |  |  | 2565.5 |  |  | 2475.5 |  |  | 2645.5 |  |  | 2462.5 |  |  | 2681.5 |  |  | 2531.5 |  |  | 2573.5 |  |  | 2397.5 |  |  | 2578.5 |  |  | 2652.5 |  |  | 2527.5 |  |  | 2529.5 |  |  | 2536.5 |  |  | 2479.5 |  |  | 2477.5 |  |  | 2573.5 |  |  | 2589.5 |  |  | 2529 |  |  | 2622.5 |  |  | 2509.5 |  |  | 2588.5 |  |  | 2551 |  |  | 2581.5 |  |  | 2525.5 |  |  | 2627.5 |  |  | 2555.5 |  |  | 2567 |  |  | 2383.5 |  |  | 2407.5 |  |  | 2428 |  |  | 2510 |  |  | 2498 |  |  | 2543.5 |  |  | 2508.5 |  |  | 2604.5 |  |  | 2719.5 |  |  | 2618 |  |  | 2585.5 |  |  | 2540.5 |  |  | 2434 |  |  | 2507 |  |  | 2574.5 |  |  | 2597.5 |  |  | 2661 |  |  | 2542.5 |  |  | 2643 |  |  | 2458.5 |  |  | 2504.5 |  |  | 2628 |  |  | 2637.5 |  |  | 2541.5 |  |  | 2388.5 |  |  | 2657 |  |  | 2467.5 |  |  | 2433.5 |  |  | 2468.5 |  |  | 2527.5 |  |  | 2547.5 |  |  | 2573.5 |  |  | 2472.5 |  |  | 2571.5 |  |  | 2600.5 |  |  | 2529.5 |  |  | 2506 |  |  | 2525.5 |  |  | 2580.5 |  |  | 2600.5 |  |  | 2632.5 |  |  | 2509.5 |  |  | 2535.5 |  |  | 2627.5 |  |  | 2472.5 |  |  | 2631 |  |  | 2480.5 |  |  | 2490 |  |  | 2764.5 |  |  | 2717.5 |  |  | 2745.5 |  |  | 2475.5 |  |  | 2442.5 |  |  | 2579.5 |  |  | 2407.5 |  |  | 2582.5 |  |  | 2584 |  |  | 2447.5 |  |  | 2585 |  |  | 2395.5 |  |  | 2458.5 |  |  | 2544.5 |  |  | 2588 |  |  | 2498.5 |  |  | 2556.5 |  |  | 2318 |  |  | 2524.5 |  |  | 2488 |  |  | 2553.5 |  |  | 2421.5 |  |  | 2468.5 |  |  | 2561 |  |  | 2617.5 |  |  | 2756.5 |  |  | 2408 |  |  | 2697.5 |  |  | 2508.5 |  |  | 2589 |  |  | 2524.5 |  |  | 2685.5 |  |  | 2619.5 |  |  | 2626.5 |  |  | 2488.5 |  |  | 2697.5 |  |  | 2420.5 |  |  | 2492.5 |  |  | 2462.5 |  |  | 2464.5 |  |  | 2694.5 |  |  | 2642 |  |  | 2544 |  |  | 2644.5 |  |  | 2550.5 |  |  | 2588
87 |  | 2506.5 |  |  | 2642.5 |  |  | 2632 |  |  | 2536.5 |  |  | 2716.5 |  |  | 2573.5 |  |  | 2614.5 |  |  | 2604.5 |  |  | 2566.5 |  |  | 2549.5 |  |  | 2457 |  |  | 2630.5 |  |  | 2604.5 |  |  | 2439.5 |  |  | 2455 |  |  | 2573.5 |  |  | 2649.5 |  |  | 2551.5 |  |  | 2632.5 |  |  | 2475.5 |  |  | 2718.5 |  |  | 2582.5 |  |  | 2657.5 |  |  | 2503.5 |  |  | 2349 |  |  | 2635.5 |  |  | 2566.5 |  |  | 2531.5 |  |  | 2616.5 |  |  | 2418 |  |  | 2567 |  |  | 2686.5 |  |  | 2371.5 |  |  | 2569.5 |  |  | 2463.5 |  |  | 2598 |  |  | 2516.5 |  |  | 2705 |  |  | 2568.5 |  |  | 2563.5 |  |  | 2332.5 |  |  | 2618.5 |  |  | 2431.5 |  |  | 2561 |  |  | 2741.5 |  |  | 2661 |  |  | 2592.5 |  |  | 2627.5 |  |  | 2671.5 |  |  | 2597.5 |  |  | 2443.5 |  |  | 2612.5 |  |  | 2593.5 |  |  | 2565.5 |  |  | 2610.5 |  |  | 2593.5 |  |  | 2438.5 |  |  | 2565 |  |  | 2581.5 |  |  | 2576.5 |  |  | 2555 |  |  | 2565.5 |  |  | 2681.5 |  |  | 2516.5 |  |  | 2469.5 |  |  | 2603 |  |  | 2724.5 |  |  | 2410 |  |  | 2423.5 |  |  | 2598.5 |  |  | 2538 |  |  | 2476.5 |  |  | 2550.5 |  |  | 2685.5 |  |  | 2682 |  |  | 2648 |  |  | 2407.5 |  |  | 2490.5 |  |  | 2495.5 |  |  | 2566.5 |  |  | 2536 |  |  | 2626.5 |  |  | 2644.5 |  |  | 2639.5 |  |  | 2681.5 |  |  | 2456.5 |  |  | 2657.5 |  |  | 2583.5 |  |  | 2577.5 |  |  | 2548.5 |  |  | 2570.5 |  |  | 2569 |  |  | 2514.5 |  |  | 2425 |  |  | 2539 |  |  | 2450 |  |  | 2726.5 |  |  | 2649.5 |  |  | 2453.5 |  |  | 2757.5 |  |  | 2464.5 |  |  | 2509 |  |  | 2517 |  |  | 2550.5 |  |  | 2605.5 |  |  | 2495.5 |  |  | 2568.5 |  |  | 2671.5 |  |  | 2625.5 |  |  | 2672.5 |  |  | 2709.5 |  |  | 2625.5 |  |  | 2535.5 |  |  | 2571.5 |  |  | 2593.5 |  |  | 2600.5 |  |  | 2660.5 |  |  | 2519.5 |  |  | 2578.5 |  |  | 2537.5 |  |  | 2608.5 |  |  | 2598.5 |  |  | 2619.5 |  |  | 2597.5 |  |  | 2567.5 |  |  | 2532 |  |  | 2525.5 |  |  | 2559.5 |  |  | 2512.5 |  |  | 2596.5 |  |  | 2635.5 |  |  | 2537 |  |  | 2480.5 |  |  | 2680.5 |  |  | 2533.5 |  |  | 2524.5 |  |  | 2620 |  |  | 2600.5 |  |  | 2667.5 |  |  | 2438 |  |  | 2607.5 |  |  | 2366 |  |  | 2671 |  |  | 2716.5 |  |  | 2586 |  |  | 2687.5 |  |  | 2510.5 |  |  | 2602.5 |  |  | 2501.5 |  |  | 2587.5 |  |  | 2603.5 |  |  | 2542.5 |  |  | 2618.5 |  |  | 2637.5 |  |  | 2592.5 |  |  | 2644 |  |  | 2455.5 |  |  | 2421 |  |  | 2499.5 |  |  | 2560.5 |  |  | 2493 |  |  | 2571.5 |  |  | 2502.5 |  |  | 2505.5 |  |  | 2423 |  |  | 2555.5 |  |  | 2391.5 |  |  | 2456.5 |  |  | 2641.5 |  |  | 2543.5 |  |  | 2513.5 |  |  | 2525 |  |  | 2583.5 |  |  | 2525.5 |  |  | 2472.5 |  |  | 2610.5 |  |  | 2579.5 |  |  | 2630.5 |  |  | 2504.5 |  |  | 2659 |  |  | 2621.5 |  |  | 2591.5 |  |  | 2642.5 |  |  | 2622.5 |  |  | 2499.5 |  |  | 2634.5 |  |  | 2629.5 |  |  | 2522.5 |  |  | 2697.5 |  |  | 2500.5 |  |  | 2624.5 |  |  | 2364.5 |  |  | 2377.5 |  |  | 2441 |  |  | 2495.5 |  |  | 2581.5 |  |  | 2594.5 |  |  | 2597.5 |  |  | 2629.5 |  |  | 2701.5 |  |  | 2679.5 |  |  | 2540.5 |  |  | 2608.5 |  |  | 2535.5 |  |  | 2473.5 |  |  | 2675.5 |  |  | 2541.5 |  |  | 2525.5 |  |  | 2532.5 |  |  | 2560.5 |  |  | 2605 |  |  | 2682.5 |  |  | 2570.5 |  |  | 2302 |  |  | 2726.5 |  |  | 2735 |  |  | 2390.5 |  |  | 2569.5 |  |  | 2658.5 |  |  | 2680.5 |  |  | 2501.5 |  |  | 2495.5 |  |  | 2577.5 |  |  | 2387.5 |  |  | 2387 |  |  | 2445.5 |  |  | 2387.5 |  |  | 2589.5 |  |  | 2505.5 |  |  | 2565 |  |  | 2554.5 |  |  | 2521.5 |  |  | 2660.5 |  |  | 2561.5 |  |  | 2661.5 |  |  | 2555.5 |  |  | 2557.5 |  |  | 2729.5 |  |  | 2692 |  |  | 2606 |  |  | 2506.5 |  |  | 2437.5 |  |  | 2610.5 |  |  | 2526 |  |  | 2696.5 |  |  | 2554.5 |  |  | 2572.5 |  |  | 2425 |  |  | 2685.5 |  |  | 2548.5 |  |  | 2395.5 |  |  | 2493.5 |  |  | 2565.5 |  |  | 2590.5 |  |  | 2639.5 |  |  | 2599.5 |  |  | 2672.5 |  |  | 2361 |  |  | 2478.5 |  |  | 2648.5 |  |  | 2566.5 |  |  | 2540.5 |  |  | 2538.5 |  |  | 2732 |  |  | 2461.5 |  |  | 2680.5 |  |  | 2636 |  |  | 2672.5 |  |  | 2589.5 |  |  | 2825 |  |  | 2642.5 |  |  | 2621.5 |  |  | 2742.5 |  |  | 2496.5 |  |  | 2558 |  |  | 2577 |  |  | 2575.5 |  |  | 2454.5 |  |  | 2645.5 |  |  | 2531.5 |  |  | 2719.5 |  |  | 2624.5 |  |  | 2562 |  |  | 2501.5 |  |  | 2457.5 |  |  | 2511 |  |  | 2527.5 |  |  | 2382.5 |  |  | 2575 |  |  | 2620.5 |  |  | 2486.5 |  |  | 2577.5 |  |  | 2614 |  |  | 2548.5 |  |  | 2494 |  |  | 2722.5 |  |  | 2475.5 |  |  | 2585.5 |  |  | 2510 |  |  | 2476.5 |  |  | 2696.5 |  |  | 2644.5 |  |  | 2584 |  |  | 2541.5 |  |  | 2389.5 |  |  | 2706.5 |  |  | 2747.5 |  |  | 2580.5 |  |  | 2608 |  |  | 2480.5 |  |  | 2678.5 |  |  | 2581.5 |  |  | 2551 |  |  | 2568 |  |  | 2752.5 |  |  | 2475.5 |  |  | 2381.5 |  |  | 2610.5 |  |  | 2546.5 |  |  | 2546.5 |  |  | 2606.5 |  |  | 2665.5 |  |  | 2465.5 |  |  | 2585.5 |  |  | 2584 |  |  | 2516.5 |  |  | 2599.5 |  |  | 2788.5 |  |  | 2740.5 |  |  | 2621 |  |  | 2554.5 |  |  | 2702.5 |  |  | 2581.5 |  |  | 2419.5 |  |  | 2686.5 |  |  | 2366 |  |  | 2611 |  |  | 2445 |  |  | 2635 |  |  | 2443.5 |  |  | 2556 |  |  | 2553.5 |  |  | 2576 |  |  | 2545.5 |  |  | 2687.5 |  |  | 2563.5 |  |  | 2550.5 |  |  | 2518.5 |  |  | 2597 |  |  | 2572.5 |  |  | 2716.5 |  |  | 2539.5 |  |  | 2580 |  |  | 2708.5 |  |  | 2506.5 |  |  | 2588.5 |  |  | 2633 |  |  | 2510.5 |  |  | 2465.5 |  |  | 2668.5 |  |  | 2496.5 |  |  | 2606.5 |  |  | 2483.5 |  |  | 2614.5 |  |  | 2547.5 |  |  | 2637.5 |  |  | 2407.5 |  |  | 2521 |  |  | 2494.5 |  |  | 2530.5 |  |  | 2455.5 |  |  | 2585.5 |  |  | 2681.5 |  |  | 2544 |  |  | 2648.5 |  |  | 2664 |  |  | 2561 |  |  | 2457.5 |  |  | 2643.5 |  |  | 2467.5 |  |  | 2559 |  |  | 2595.5 |  |  | 2596.5 |  |  | 2560.5 |  |  | 2406 |  |  | 2510.5 |  |  | 2387.5 |  |  | 2530.5 |  |  | 2431.5 |  |  | 2495.5 |  |  | 2498 |  |  | 2499.5 |  |  | 2625 |  |  | 2589.5 |  |  | 2376.5 |  |  | 2521.5 |  |  | 2557 |  |  | 2516.5 |  |  | 2493 |  |  | 2512 |  |  | 2563.5 |  |  | 2434.5 |  |  | 2475.5 |  |  | 2719.5 |  |  | 2751 |  |  | 2647.5 |  |  | 2564.5 |  |  | 2363.5 |  |  | 2519 |  |  | 2620.5 |  |  | 2497.5 |  |  | 2302.5 |  |  | 2595.5 |  |  | 2736 |  |  | 2440.5 |  |  | 2506.5 |  |  | 2574.5 |  |  | 2622.5 |  |  | 2603.5 |  |  | 2594.5 |  |  | 2659 |  |  | 2492.5 |  |  | 2478.5 |  |  | 2561 |  |  | 2451.5 |  |  | 2438.5 |  |  | 2563.5 |  |  | 2549 |  |  | 2626.5 |  |  | 2585.5 |  |  | 2551.5 |  |  | 2500.5 |  |  | 2584.5 |  |  | 2574 |  |  | 2452 |  |  | 2560.5 |  |  | 2616.5 |  |  | 2611.5 |  |  | 2396.5 |  |  | 2337 |  |  | 2653 |  |  | 2530 |  |  | 2677.5 |  |  | 2544 |  |  | 2599.5 |  |  | 2690.5 |  |  | 2653 |  |  | 2408.5 |  |  | 2569.5 |  |  | 2505.5 |  |  | 2610.5 |  |  | 2305.5 |  |  | 2549 |  |  | 2637 |  |  | 2470.5 |  |  | 2645.5 |  |  | 2441 |  |  | 2488.5 |  |  | 2571.5 |  |  | 2506 |  |  | 2713.5 |  |  | 2710.5 |  |  | 2474 |  |  | 2643.5 |  |  | 2602.5 |  |  | 2661 |  |  | 2487.5 |  |  | 2446 |  |  | 2706.5 |  |  | 2686 |  |  | 2459.5 |  |  | 2480.5 |  |  | 2484.5 |  |  | 2546.5 |  |  | 2564.5 |  |  | 2447.5 |  |  | 2600 |  |  | 2461.5 |  |  | 2585.5 |  |  | 2489.5 |  |  | 2533.5 |  |  | 2548.5 |  |  | 2480 |  |  | 2512.5 |  |  | 2592 |  |  | 2581.5 |  |  | 2401.5 |  |  | 2604.5 |  |  | 2600.5 |  |  | 2612.5 |  |  | 2532.5 |  |  | 2458.5 |  |  | 2629.5 |  |  | 2413.5 |  |  | 2488 |  |  | 2591.5 |  |  | 2473 |  |  | 2573 |  |  | 2579.5 |  |  | 2319 |  |  | 2412.5 |  |  | 2619.5 |  |  | 2654.5 |  |  | 2595.5 |  |  | 2651.5 |  |  | 2589.5 |  |  | 2617.5 |  |  | 2536 |  |  | 2686 |  |  | 2444.5 |  |  | 2564.5 |  |  | 2567 |  |  | 2510.5 |  |  | 2520.5 |  |  | 2496.5 |  |  | 2468.5 |  |  | 2552.5 |  |  | 2442 |  |  | 2545.5 |  |  | 2515.5 |  |  | 2488.5 |  |  | 2523 |  |  | 2589.5 |  |  | 2647.5 |  |  | 2619.5 |  |  | 2797.5 |  |  | 2564.5 |  |  | 2463.5 |  |  | 2592.5 |  |  | 2173.5 |  |  | 2542.5 |  |  | 2465 |  |  | 2679.5 |  |  | 2563.5 |  |  | 2648.5 |  |  | 2429.5 |  |  | 2552.5 |  |  | 2455.5 |  |  | 2439.5 |  |  | 2406 |  |  | 2469.5 |  |  | 2560.5 |  |  | 2510.5 |  |  | 2552 |  |  | 2598.5 |  |  | 2431 |  |  | 2438.5 |  |  | 2564.5 |  |  | 2522.5 |  |  | 2618 |  |  | 2371.5 |  |  | 2575 |  |  | 2543 |  |  | 2591.5 |  |  | 2573 |  |  | 2700 |  |  | 2640.5 |  |  | 2655.5 |  |  | 2462.5 |  |  | 2641 |  |  | 2564.5 |  |  | 2455.5 |  |  | 2393.5 |  |  | 2670.5 |  |  | 2484.5 |  |  | 2537.5 |  |  | 2574.5 |  |  | 2574.5 |  |  | 2515 |  |  | 2710.5 |  |  | 2491 |  |  | 2596.5 |  |  | 2443.5 |  |  | 2661.5 |  |  | 2555 |  |  | 2621 |  |  | 2708 |  |  | 2597.5 |  |  | 2545 |  |  | 2620.5 |  |  | 2712.5 |  |  | 2548.5 |  |  | 2517.5 |  |  | 2460.5 |  |  | 2667.5 |  |  | 2666.5 |  |  | 2586.5 |  |  | 2605 |  |  | 2402.5 |  |  | 2423.5 |  |  | 2587.5 |  |  | 2545.5 |  |  | 2476 |  |  | 2537.5 |  |  | 2585 |  |  | 2583.5 |  |  | 2553.5 |  |  | 2490.5 |  |  | 2436.5 |  |  | 2432 |  |  | 2522.5 |  |  | 2306 |  |  | 2484.5 |  |  | 2644.5 |  |  | 2728.5 |  |  | 2535.5 |  |  | 2543.5 |  |  | 2622.5 |  |  | 2508.5 |  |  | 2569.5 |  |  | 2487.5 |  |  | 2464 |  |  | 2558.5 |  |  | 2522.5 |  |  | 2519.5 |  |  | 2617.5 |  |  | 2619.5 |  |  | 2485 |  |  | 2504 |  |  | 2511.5 |  |  | 2494 |  |  | 2700.5 |  |  | 2469.5 |  |  | 2674.5 |  |  | 2581.5 |  |  | 2510.5 |  |  | 2670.5 |  |  | 2595.5 |  |  | 2635.5 |  |  | 2610 |  |  | 2582.5 |  |  | 2739.5 |  |  | 2507.5 |  |  | 2388 |  |  | 2569.5 |  |  | 2448.5 |  |  | 2703 |  |  | 2536 |  |  | 2545.5 |  |  | 2523 |  |  | 2412 |  |  | 2409.5 |  |  | 2655 |  |  | 2766.5 |  |  | 2535.5 |  |  | 2646.5 |  |  | 2507.5 |  |  | 2426.5 |  |  | 2559.5 |  |  | 2361.5 |  |  | 2488.5 |  |  | 2570.5 |  |  | 2465.5 |  |  | 2457 |  |  | 2454 |  |  | 2655.5 |  |  | 2667.5 |  |  | 2473.5 |  |  | 2631.5 |  |  | 2529.5 |  |  | 2600.5 |  |  | 2578.5 |  |  | 2486.5 |  |  | 2765 |  |  | 2507.5 |  |  | 2536 |  |  | 2500.5 |  |  | 2680.5 |  |  | 2610.5 |  |  | 2676 |  |  | 2525.5 |  |  | 2492.5 |  |  | 2598 |  |  | 2616.5 |  |  | 2549.5 |  |  | 2653.5 |  |  | 2549.5 |  |  | 2529.5 |  |  | 2584.5 |  |  | 2625 |  |  | 2473.5 |  |  | 2545.5 |  |  | 2682.5 |  |  | 2603.5 |  |  | 2546 |  |  | 2543.5 |  |  | 2695.5 |  |  | 2509 |  |  | 2552.5 |  |  | 2639.5 |  |  | 2608 |  |  | 2643.5 |  |  | 2699.5 |  |  | 2532.5 |  |  | 2497 |  |  | 2439.5 |  |  | 2553.5 |  |  | 2468 |  |  | 2567.5 |  |  | 2564.5 |  |  | 2596.5 |  |  | 2403.5 |  |  | 2562.5 |  |  | 2717.5 |  |  | 2494.5 |  |  | 2517 |  |  | 2479 |  |  | 2377.5 |  |  | 2629.5 |  |  | 2448.5 |  |  | 2643 |  |  | 2709.5 |  |  | 2509.5 |  |  | 2546.5 |  |  | 2374.5 |  |  | 2580.5 |  |  | 2601.5 |  |  | 2468.5 |  |  | 2595.5 |  |  | 2333.5 |  |  | 2570 |  |  | 2515.5 |  |  | 2375.5 |  |  | 2546.5 |  |  | 2564.5 |  |  | 2733.5 |  |  | 2607.5 |  |  | 2556.5 |  |  | 2530.5 |  |  | 2410.5 |  |  | 2689.5 |  |  | 2536.5 |  |  | 2447.5 |  |  | 2583.5 |  |  | 2673 |  |  | 2590.5 |  |  | 2644.5 |  |  | 2496 |  |  | 2619.5 |  |  | 2625.5 |  |  | 2696 |  |  | 2613.5 |  |  | 2643.5 |  |  | 2726.5 |  |  | 2740 |  |  | 2480.5 |  |  | 2645.5 |  |  | 2543.5 |  |  | 2344.5 |  |  | 2628.5 |  |  | 2479 |  |  | 2483.5 |  |  | 2641 |  |  | 2623 |  |  | 2629.5 |  |  | 2543.5 |  |  | 2476.5 |  |  | 2300.5 |  |  | 2511.5 |  |  | 2653.5 |  |  | 2518 |  |  | 2508.5 |  |  | 2498 |  |  | 2536.5 |  |  | 2542 |  |  | 2465 |  |  | 2626 |  |  | 2643.5 |  |  | 2483 |  |  | 2704.5 |  |  | 2612.5 |  |  | 2533.5 |  |  | 2724.5 |  |  | 2394.5 |  |  | 2671 |  |  | 2546.5 |  |  | 2608.5 |  |  | 2791.5 |  |  | 2555 |  |  | 2527.5 |  |  | 2514.5 |  |  | 2560.5 |  |  | 2656.5 |  |  | 2532 |  |  | 2651 |  |  | 2513 |  |  | 2523.5 |  |  | 2716 |  |  | 2585 |  |  | 2648.5 |  |  | 2481.5 |  |  | 2435.5 |  |  | 2572.5 |  |  | 2598.5 |  |  | 2571.5 |  |  | 2628.5 |  |  | 2533.5 |  |  | 2540.5 |  |  | 2459 |  |  | 2497.5 |  |  | 2426 |  |  | 2566.5 |  |  | 2546.5 |  |  | 2611.5 |  |  | 2615.5 |  |  | 2690 |  |  | 2584.5 |  |  | 2552 |  |  | 2475.5 |  |  | 2616.5 |  |  | 2418 |  |  | 2509 |  |  | 2644.5 |  |  | 2632 |  |  | 2555.5 |  |  | 2408.5 |  |  | 2458.5 |  |  | 2504.5 |  |  | 2576.5 |  |  | 2558.5 |  |  | 2438.5 |  |  | 2499 |  |  | 2598.5 |  |  | 2596.5 |  |  | 2593.5 |  |  | 2616.5 |  |  | 2485.5 |  |  | 2592.5 |  |  | 2685.5 |  |  | 2565.5 |  |  | 2713.5 |  |  | 2710.5 |  |  | 2452.5 |  |  | 2430.5 |  |  | 2551 |  |  | 2448.5 |  |  | 2521.5 |  |  | 2624 |  |  | 2489.5 |  |  | 2468.5 |  |  | 2533.5 |  |  | 2435.5 |  |  | 2759 |  |  | 2663.5 |  |  | 2470.5 |  |  | 2437.5 |  |  | 2709.5 |  |  | 2514 |  |  | 2518.5 |  |  | 2667.5 |  |  | 2475.5 |  |  | 2650.5 |  |  | 2487.5 |  |  | 2466.5 |  |  | 2652.5 |  |  | 2510.5 |  |  | 2562.5 |  |  | 2589.5 |  |  | 2628.5 |  |  | 2627 |  |  | 2566.5 |  |  | 2499.5 |  |  | 2599.5 |  |  | 2686.5 |  |  | 2492.5 |  |  | 2515.5 |  |  | 2613 |  |  | 2655.5 |  |  | 2474 |  |  | 2445.5 |  |  | 2605.5 |  |  | 2623.5 |  |  | 2552 |  |  | 2481 |  |  | 2612.5 |  |  | 2639.5 |  |  | 2337.5 |  |  | 2752.5 |  |  | 2543.5 |  |  | 2612.5 |  |  | 2490.5 |  |  | 2674.5 |  |  | 2488.5 |  |  | 2710.5 |  |  | 2560.5 |  |  | 2612.5 |  |  | 2436.5 |  |  | 2617.5 |  |  | 2676.5 |  |  | 2551.5 |  |  | 2553.5 |  |  | 2557.5 |  |  | 2505.5 |  |  | 2498.5 |  |  | 2612.5 |  |  | 2615.5 |  |  | 2550 |  |  | 2646.5 |  |  | 2538.5 |  |  | 2609.5 |  |  | 2572 |  |  | 2602.5 |  |  | 2549.5 |  |  | 2653.5 |  |  | 2602.5 |  |  | 2593 |  |  | 2430.5 |  |  | 2422.5 |  |  | 2475 |  |  | 2539 |  |  | 2524 |  |  | 2590.5 |  |  | 2529.5 |  |  | 2651.5 |  |  | 2766.5 |  |  | 2657 |  |  | 2606.5 |  |  | 2579.5 |  |  | 2458 |  |  | 2536 |  |  | 2621.5 |  |  | 2612.5 |  |  | 2700 |  |  | 2589.5 |  |  | 2669 |  |  | 2473.5 |  |  | 2543.5 |  |  | 2649 |  |  | 2661.5 |  |  | 2567.5 |  |  | 2414.5 |  |  | 2696 |  |  | 2482.5 |  |  | 2462.5 |  |  | 2497.5 |  |  | 2551.5 |  |  | 2571.5 |  |  | 2602.5 |  |  | 2519.5 |  |  | 2618.5 |  |  | 2626.5 |  |  | 2544.5 |  |  | 2530 |  |  | 2546.5 |  |  | 2601.5 |  |  | 2624.5 |  |  | 2656.5 |  |  | 2548.5 |  |  | 2561.5 |  |  | 2642.5 |  |  | 2501.5 |  |  | 2678 |  |  | 2504.5 |  |  | 2529 |  |  | 2803.5 |  |  | 2743.5 |  |  | 2766.5 |  |  | 2504.5 |  |  | 2481.5 |  |  | 2608.5 |  |  | 2422.5 |  |  | 2608.5 |  |  | 2631 |  |  | 2486.5 |  |  | 2624 |  |  | 2434.5 |  |  | 2473.5 |  |  | 2565.5 |  |  | 2635 |  |  | 2524.5 |  |  | 2582.5 |  |  | 2342 |  |  | 2545.5 |  |  | 2514 |  |  | 2574.5 |  |  | 2442.5 |  |  | 2515.5 |  |  | 2585 |  |  | 2656.5 |  |  | 2795.5 |  |  | 2432 |  |  | 2736.5 |  |  | 2534.5 |  |  | 2628 |  |  | 2563.5 |  |  | 2732.5 |  |  | 2658.5 |  |  | 2650.5 |  |  | 2512.5 |  |  | 2736.5 |  |  | 2446.5 |  |  | 2521.5 |  |  | 2509.5 |  |  | 2503.5 |  |  | 2718.5 |  |  | 2666 |  |  | 2573 |  |  | 2665.5 |  |  | 2571.5 |  |  | 2617
88 |  | 2545.5 |  |  | 2657.5 |  |  | 2653 |  |  | 2551.5 |  |  | 2755.5 |  |  | 2599.5 |  |  | 2643.5 |  |  | 2625.5 |  |  | 2605.5 |  |  | 2575.5 |  |  | 2478 |  |  | 2651.5 |  |  | 2630.5 |  |  | 2478.5 |  |  | 2479 |  |  | 2597.5 |  |  | 2675.5 |  |  | 2575.5 |  |  | 2653.5 |  |  | 2499.5 |  |  | 2744.5 |  |  | 2621.5 |  |  | 2704.5 |  |  | 2542.5 |  |  | 2388 |  |  | 2674.5 |  |  | 2592.5 |  |  | 2557.5 |  |  | 2631.5 |  |  | 2444 |  |  | 2606 |  |  | 2701.5 |  |  | 2392.5 |  |  | 2593.5 |  |  | 2492.5 |  |  | 2624 |  |  | 2555.5 |  |  | 2734 |  |  | 2594.5 |  |  | 2589.5 |  |  | 2358.5 |  |  | 2657.5 |  |  | 2455.5 |  |  | 2582 |  |  | 2765.5 |  |  | 2687 |  |  | 2613.5 |  |  | 2666.5 |  |  | 2718.5 |  |  | 2623.5 |  |  | 2482.5 |  |  | 2651.5 |  |  | 2608.5 |  |  | 2586.5 |  |  | 2639.5 |  |  | 2617.5 |  |  | 2467.5 |  |  | 2604 |  |  | 2605.5 |  |  | 2602.5 |  |  | 2579 |  |  | 2612.5 |  |  | 2720.5 |  |  | 2545.5 |  |  | 2493.5 |  |  | 2627 |  |  | 2763.5 |  |  | 2457 |  |  | 2447.5 |  |  | 2624.5 |  |  | 2577 |  |  | 2491.5 |  |  | 2589.5 |  |  | 2709.5 |  |  | 2721 |  |  | 2687 |  |  | 2428.5 |  |  | 2529.5 |  |  | 2521.5 |  |  | 2605.5 |  |  | 2562 |  |  | 2647.5 |  |  | 2665.5 |  |  | 2654.5 |  |  | 2696.5 |  |  | 2495.5 |  |  | 2672.5 |  |  | 2630.5 |  |  | 2601.5 |  |  | 2595.5 |  |  | 2585.5 |  |  | 2616 |  |  | 2553.5 |  |  | 2449 |  |  | 2554 |  |  | 2471 |  |  | 2752.5 |  |  | 2673.5 |  |  | 2474.5 |  |  | 2772.5 |  |  | 2479.5 |  |  | 2524 |  |  | 2564 |  |  | 2589.5 |  |  | 2644.5 |  |  | 2510.5 |  |  | 2607.5 |  |  | 2692.5 |  |  | 2664.5 |  |  | 2711.5 |  |  | 2730.5 |  |  | 2672.5 |  |  | 2556.5 |  |  | 2610.5 |  |  | 2622.5 |  |  | 2639.5 |  |  | 2675.5 |  |  | 2548.5 |  |  | 2599.5 |  |  | 2576.5 |  |  | 2647.5 |  |  | 2637.5 |  |  | 2648.5 |  |  | 2621.5 |  |  | 2606.5 |  |  | 2571 |  |  | 2554.5 |  |  | 2583.5 |  |  | 2559.5 |  |  | 2643.5 |  |  | 2674.5 |  |  | 2576 |  |  | 2519.5 |  |  | 2709.5 |  |  | 2557.5 |  |  | 2563.5 |  |  | 2649 |  |  | 2621.5 |  |  | 2714.5 |  |  | 2459 |  |  | 2654.5 |  |  | 2381 |  |  | 2697 |  |  | 2742.5 |  |  | 2633 |  |  | 2726.5 |  |  | 2557.5 |  |  | 2626.5 |  |  | 2525.5 |  |  | 2608.5 |  |  | 2642.5 |  |  | 2581.5 |  |  | 2657.5 |  |  | 2684.5 |  |  | 2621.5 |  |  | 2683 |  |  | 2481.5 |  |  | 2447 |  |  | 2546.5 |  |  | 2575.5 |  |  | 2532 |  |  | 2600.5 |  |  | 2541.5 |  |  | 2534.5 |  |  | 2462 |  |  | 2581.5 |  |  | 2417.5 |  |  | 2503.5 |  |  | 2680.5 |  |  | 2572.5 |  |  | 2534.5 |  |  | 2554 |  |  | 2598.5 |  |  | 2554.5 |  |  | 2511.5 |  |  | 2636.5 |  |  | 2603.5 |  |  | 2645.5 |  |  | 2519.5 |  |  | 2688 |  |  | 2642.5 |  |  | 2617.5 |  |  | 2671.5 |  |  | 2661.5 |  |  | 2538.5 |  |  | 2673.5 |  |  | 2676.5 |  |  | 2569.5 |  |  | 2736.5 |  |  | 2521.5 |  |  | 2671.5 |  |  | 2385.5 |  |  | 2424.5 |  |  | 2470 |  |  | 2516.5 |  |  | 2602.5 |  |  | 2623.5 |  |  | 2644.5 |  |  | 2655.5 |  |  | 2727.5 |  |  | 2694.5 |  |  | 2566.5 |  |  | 2634.5 |  |  | 2582.5 |  |  | 2502.5 |  |  | 2722.5 |  |  | 2588.5 |  |  | 2546.5 |  |  | 2553.5 |  |  | 2584.5 |  |  | 2631 |  |  | 2729.5 |  |  | 2591.5 |  |  | 2331 |  |  | 2750.5 |  |  | 2764 |  |  | 2414.5 |  |  | 2593.5 |  |  | 2673.5 |  |  | 2719.5 |  |  | 2540.5 |  |  | 2524.5 |  |  | 2603.5 |  |  | 2426.5 |  |  | 2434 |  |  | 2460.5 |  |  | 2408.5 |  |  | 2636.5 |  |  | 2534.5 |  |  | 2580 |  |  | 2578.5 |  |  | 2560.5 |  |  | 2681.5 |  |  | 2587.5 |  |  | 2682.5 |  |  | 2602.5 |  |  | 2596.5 |  |  | 2744.5 |  |  | 2716 |  |  | 2627 |  |  | 2545.5 |  |  | 2484.5 |  |  | 2634.5 |  |  | 2547 |  |  | 2722.5 |  |  | 2583.5 |  |  | 2596.5 |  |  | 2454 |  |  | 2732.5 |  |  | 2563.5 |  |  | 2419.5 |  |  | 2532.5 |  |  | 2589.5 |  |  | 2629.5 |  |  | 2686.5 |  |  | 2620.5 |  |  | 2687.5 |  |  | 2382 |  |  | 2502.5 |  |  | 2677.5 |  |  | 2595.5 |  |  | 2587.5 |  |  | 2553.5 |  |  | 2761 |  |  | 2482.5 |  |  | 2719.5 |  |  | 2665 |  |  | 2719.5 |  |  | 2613.5 |  |  | 2851 |  |  | 2657.5 |  |  | 2660.5 |  |  | 2757.5 |  |  | 2543.5 |  |  | 2584 |  |  | 2616 |  |  | 2604.5 |  |  | 2493.5 |  |  | 2660.5 |  |  | 2557.5 |  |  | 2766.5 |  |  | 2663.5 |  |  | 2583 |  |  | 2540.5 |  |  | 2472.5 |  |  | 2540 |  |  | 2566.5 |  |  | 2397.5 |  |  | 2601 |  |  | 2635.5 |  |  | 2533.5 |  |  | 2601.5 |  |  | 2643 |  |  | 2587.5 |  |  | 2533 |  |  | 2743.5 |  |  | 2514.5 |  |  | 2609.5 |  |  | 2557 |  |  | 2497.5 |  |  | 2735.5 |  |  | 2683.5 |  |  | 2623 |  |  | 2565.5 |  |  | 2428.5 |  |  | 2753.5 |  |  | 2768.5 |  |  | 2604.5 |  |  | 2637 |  |  | 2495.5 |  |  | 2699.5 |  |  | 2605.5 |  |  | 2590 |  |  | 2607 |  |  | 2776.5 |  |  | 2490.5 |  |  | 2420.5 |  |  | 2649.5 |  |  | 2593.5 |  |  | 2572.5 |  |  | 2653.5 |  |  | 2689.5 |  |  | 2512.5 |  |  | 2624.5 |  |  | 2623 |  |  | 2537.5 |  |  | 2620.5 |  |  | 2814.5 |  |  | 2787.5 |  |  | 2645 |  |  | 2569.5 |  |  | 2728.5 |  |  | 2610.5 |  |  | 2458.5 |  |  | 2733.5 |  |  | 2395 |  |  | 2650 |  |  | 2471 |  |  | 2674 |  |  | 2490.5 |  |  | 2595 |  |  | 2592.5 |  |  | 2602 |  |  | 2566.5 |  |  | 2713.5 |  |  | 2578.5 |  |  | 2597.5 |  |  | 2533.5 |  |  | 2618 |  |  | 2611.5 |  |  | 2755.5 |  |  | 2563.5 |  |  | 2606 |  |  | 2732.5 |  |  | 2535.5 |  |  | 2627.5 |  |  | 2657 |  |  | 2549.5 |  |  | 2512.5 |  |  | 2694.5 |  |  | 2517.5 |  |  | 2645.5 |  |  | 2509.5 |  |  | 2661.5 |  |  | 2586.5 |  |  | 2676.5 |  |  | 2436.5 |  |  | 2560 |  |  | 2509.5 |  |  | 2569.5 |  |  | 2494.5 |  |  | 2632.5 |  |  | 2705.5 |  |  | 2568 |  |  | 2687.5 |  |  | 2688 |  |  | 2585 |  |  | 2504.5 |  |  | 2669.5 |  |  | 2491.5 |  |  | 2583 |  |  | 2634.5 |  |  | 2620.5 |  |  | 2599.5 |  |  | 2421 |  |  | 2531.5 |  |  | 2411.5 |  |  | 2545.5 |  |  | 2446.5 |  |  | 2542.5 |  |  | 2527 |  |  | 2514.5 |  |  | 2640 |  |  | 2610.5 |  |  | 2402.5 |  |  | 2568.5 |  |  | 2572 |  |  | 2540.5 |  |  | 2514 |  |  | 2541 |  |  | 2584.5 |  |  | 2460.5 |  |  | 2501.5 |  |  | 2766.5 |  |  | 2780 |  |  | 2668.5 |  |  | 2585.5 |  |  | 2392.5 |  |  | 2543 |  |  | 2641.5 |  |  | 2518.5 |  |  | 2328.5 |  |  | 2642.5 |  |  | 2762 |  |  | 2464.5 |  |  | 2521.5 |  |  | 2600.5 |  |  | 2648.5 |  |  | 2650.5 |  |  | 2633.5 |  |  | 2688 |  |  | 2531.5 |  |  | 2502.5 |  |  | 2576 |  |  | 2475.5 |  |  | 2464.5 |  |  | 2610.5 |  |  | 2596 |  |  | 2655.5 |  |  | 2600.5 |  |  | 2566.5 |  |  | 2529.5 |  |  | 2623.5 |  |  | 2598 |  |  | 2473 |  |  | 2599.5 |  |  | 2645.5 |  |  | 2626.5 |  |  | 2443.5 |  |  | 2366 |  |  | 2679 |  |  | 2577 |  |  | 2716.5 |  |  | 2565 |  |  | 2638.5 |  |  | 2719.5 |  |  | 2679 |  |  | 2447.5 |  |  | 2584.5 |  |  | 2544.5 |  |  | 2649.5 |  |  | 2344.5 |  |  | 2575 |  |  | 2666 |  |  | 2494.5 |  |  | 2666.5 |  |  | 2467 |  |  | 2509.5 |  |  | 2592.5 |  |  | 2532 |  |  | 2739.5 |  |  | 2725.5 |  |  | 2495 |  |  | 2682.5 |  |  | 2641.5 |  |  | 2690 |  |  | 2526.5 |  |  | 2467 |  |  | 2745.5 |  |  | 2715 |  |  | 2480.5 |  |  | 2501.5 |  |  | 2523.5 |  |  | 2570.5 |  |  | 2603.5 |  |  | 2468.5 |  |  | 2624 |  |  | 2476.5 |  |  | 2611.5 |  |  | 2515.5 |  |  | 2554.5 |  |  | 2587.5 |  |  | 2509 |  |  | 2551.5 |  |  | 2621 |  |  | 2620.5 |  |  | 2440.5 |  |  | 2625.5 |  |  | 2639.5 |  |  | 2651.5 |  |  | 2558.5 |  |  | 2482.5 |  |  | 2653.5 |  |  | 2442.5 |  |  | 2517 |  |  | 2638.5 |  |  | 2520 |  |  | 2612 |  |  | 2608.5 |  |  | 2340 |  |  | 2459.5 |  |  | 2643.5 |  |  | 2701.5 |  |  | 2642.5 |  |  | 2680.5 |  |  | 2628.5 |  |  | 2656.5 |  |  | 2551 |  |  | 2710 |  |  | 2491.5 |  |  | 2603.5 |  |  | 2614 |  |  | 2557.5 |  |  | 2541.5 |  |  | 2522.5 |  |  | 2515.5 |  |  | 2578.5 |  |  | 2481 |  |  | 2592.5 |  |  | 2554.5 |  |  | 2527.5 |  |  | 2562 |  |  | 2610.5 |  |  | 2673.5 |  |  | 2666.5 |  |  | 2844.5 |  |  | 2603.5 |  |  | 2502.5 |  |  | 2631.5 |  |  | 2199.5 |  |  | 2571.5 |  |  | 2512 |  |  | 2708.5 |  |  | 2602.5 |  |  | 2687.5 |  |  | 2455.5 |  |  | 2599.5 |  |  | 2479.5 |  |  | 2454.5 |  |  | 2432 |  |  | 2508.5 |  |  | 2589.5 |  |  | 2525.5 |  |  | 2591 |  |  | 2613.5 |  |  | 2478 |  |  | 2464.5 |  |  | 2579.5 |  |  | 2548.5 |  |  | 2633 |  |  | 2400.5 |  |  | 2622 |  |  | 2558 |  |  | 2615.5 |  |  | 2588 |  |  | 2729 |  |  | 2661.5 |  |  | 2684.5 |  |  | 2501.5 |  |  | 2670 |  |  | 2611.5 |  |  | 2481.5 |  |  | 2419.5 |  |  | 2699.5 |  |  | 2508.5 |  |  | 2584.5 |  |  | 2600.5 |  |  | 2603.5 |  |  | 2539 |  |  | 2731.5 |  |  | 2520 |  |  | 2643.5 |  |  | 2472.5 |  |  | 2700.5 |  |  | 2594 |  |  | 2660 |  |  | 2747 |  |  | 2621.5 |  |  | 2592 |  |  | 2635.5 |  |  | 2751.5 |  |  | 2587.5 |  |  | 2543.5 |  |  | 2475.5 |  |  | 2696.5 |  |  | 2687.5 |  |  | 2615.5 |  |  | 2620 |  |  | 2428.5 |  |  | 2462.5 |  |  | 2613.5 |  |  | 2584.5 |  |  | 2515 |  |  | 2576.5 |  |  | 2624 |  |  | 2604.5 |  |  | 2592.5 |  |  | 2519.5 |  |  | 2457.5 |  |  | 2456 |  |  | 2551.5 |  |  | 2345 |  |  | 2531.5 |  |  | 2659.5 |  |  | 2775.5 |  |  | 2550.5 |  |  | 2569.5 |  |  | 2661.5 |  |  | 2547.5 |  |  | 2608.5 |  |  | 2511.5 |  |  | 2493 |  |  | 2579.5 |  |  | 2561.5 |  |  | 2558.5 |  |  | 2656.5 |  |  | 2640.5 |  |  | 2514 |  |  | 2525 |  |  | 2550.5 |  |  | 2523 |  |  | 2739.5 |  |  | 2498.5 |  |  | 2695.5 |  |  | 2596.5 |  |  | 2525.5 |  |  | 2691.5 |  |  | 2610.5 |  |  | 2650.5 |  |  | 2639 |  |  | 2603.5 |  |  | 2763.5 |  |  | 2533.5 |  |  | 2427 |  |  | 2616.5 |  |  | 2474.5 |  |  | 2732 |  |  | 2562 |  |  | 2571.5 |  |  | 2544 |  |  | 2441 |  |  | 2456.5 |  |  | 2694 |  |  | 2792.5 |  |  | 2574.5 |  |  | 2685.5 |  |  | 2536.5 |  |  | 2452.5 |  |  | 2598.5 |  |  | 2400.5 |  |  | 2527.5 |  |  | 2617.5 |  |  | 2491.5 |  |  | 2504 |  |  | 2501 |  |  | 2670.5 |  |  | 2696.5 |  |  | 2502.5 |  |  | 2660.5 |  |  | 2550.5 |  |  | 2629.5 |  |  | 2617.5 |  |  | 2501.5 |  |  | 2804 |  |  | 2528.5 |  |  | 2560 |  |  | 2529.5 |  |  | 2701.5 |  |  | 2631.5 |  |  | 2702 |  |  | 2572.5 |  |  | 2516.5 |  |  | 2627 |  |  | 2655.5 |  |  | 2575.5 |  |  | 2679.5 |  |  | 2588.5 |  |  | 2558.5 |  |  | 2605.5 |  |  | 2649 |  |  | 2499.5 |  |  | 2584.5 |  |  | 2721.5 |  |  | 2632.5 |  |  | 2585 |  |  | 2572.5 |  |  | 2734.5 |  |  | 2524 |  |  | 2567.5 |  |  | 2654.5 |  |  | 2629 |  |  | 2669.5 |  |  | 2738.5 |  |  | 2558.5 |  |  | 2512 |  |  | 2460.5 |  |  | 2574.5 |  |  | 2497 |  |  | 2614.5 |  |  | 2593.5 |  |  | 2617.5 |  |  | 2432.5 |  |  | 2601.5 |  |  | 2743.5 |  |  | 2515.5 |  |  | 2556 |  |  | 2494 |  |  | 2424.5 |  |  | 2668.5 |  |  | 2474.5 |  |  | 2690 |  |  | 2730.5 |  |  | 2548.5 |  |  | 2572.5 |  |  | 2400.5 |  |  | 2619.5 |  |  | 2640.5 |  |  | 2497.5 |  |  | 2634.5 |  |  | 2359.5 |  |  | 2609 |  |  | 2562.5 |  |  | 2396.5 |  |  | 2585.5 |  |  | 2588.5 |  |  | 2759.5 |  |  | 2628.5 |  |  | 2577.5 |  |  | 2559.5 |  |  | 2425.5 |  |  | 2710.5 |  |  | 2560.5 |  |  | 2471.5 |  |  | 2604.5 |  |  | 2694 |  |  | 2629.5 |  |  | 2670.5 |  |  | 2525 |  |  | 2643.5 |  |  | 2646.5 |  |  | 2711 |  |  | 2637.5 |  |  | 2667.5 |  |  | 2773.5 |  |  | 2787 |  |  | 2509.5 |  |  | 2684.5 |  |  | 2558.5 |  |  | 2383.5 |  |  | 2675.5 |  |  | 2526 |  |  | 2522.5 |  |  | 2680 |  |  | 2647 |  |  | 2653.5 |  |  | 2582.5 |  |  | 2523.5 |  |  | 2329.5 |  |  | 2537.5 |  |  | 2700.5 |  |  | 2565 |  |  | 2523.5 |  |  | 2527 |  |  | 2575.5 |  |  | 2589 |  |  | 2489 |  |  | 2652 |  |  | 2690.5 |  |  | 2498 |  |  | 2725.5 |  |  | 2638.5 |  |  | 2572.5 |  |  | 2771.5 |  |  | 2420.5 |  |  | 2718 |  |  | 2561.5 |  |  | 2632.5 |  |  | 2817.5 |  |  | 2594 |  |  | 2542.5 |  |  | 2538.5 |  |  | 2607.5 |  |  | 2703.5 |  |  | 2553 |  |  | 2672 |  |  | 2537 |  |  | 2562.5 |  |  | 2742 |  |  | 2624 |  |  | 2695.5 |  |  | 2496.5 |  |  | 2482.5 |  |  | 2593.5 |  |  | 2619.5 |  |  | 2592.5 |  |  | 2643.5 |  |  | 2572.5 |  |  | 2555.5 |  |  | 2506 |  |  | 2521.5 |  |  | 2450 |  |  | 2605.5 |  |  | 2561.5 |  |  | 2650.5 |  |  | 2630.5 |  |  | 2729 |  |  | 2623.5 |  |  | 2567 |  |  | 2514.5 |  |  | 2631.5 |  |  | 2442 |  |  | 2538 |  |  | 2659.5 |  |  | 2671 |  |  | 2579.5 |  |  | 2432.5 |  |  | 2473.5 |  |  | 2525.5 |  |  | 2591.5 |  |  | 2579.5 |  |  | 2459.5 |  |  | 2523 |  |  | 2645.5 |  |  | 2635.5 |  |  | 2632.5 |  |  | 2640.5 |  |  | 2524.5 |  |  | 2607.5 |  |  | 2709.5 |  |  | 2586.5 |  |  | 2760.5 |  |  | 2739.5 |  |  | 2499.5 |  |  | 2445.5 |  |  | 2590 |  |  | 2463.5 |  |  | 2550.5 |  |  | 2671 |  |  | 2510.5 |  |  | 2494.5 |  |  | 2562.5 |  |  | 2450.5 |  |  | 2806 |  |  | 2710.5 |  |  | 2499.5 |  |  | 2484.5 |  |  | 2730.5 |  |  | 2553 |  |  | 2542.5 |  |  | 2706.5 |  |  | 2490.5 |  |  | 2697.5 |  |  | 2508.5 |  |  | 2487.5 |  |  | 2673.5 |  |  | 2549.5 |  |  | 2577.5 |  |  | 2604.5 |  |  | 2675.5 |  |  | 2648 |  |  | 2605.5 |  |  | 2546.5 |  |  | 2623.5 |  |  | 2733.5 |  |  | 2531.5 |  |  | 2541.5 |  |  | 2628 |  |  | 2681.5 |  |  | 2513 |  |  | 2492.5 |  |  | 2631.5 |  |  | 2670.5 |  |  | 2576 |  |  | 2507 |  |  | 2659.5 |  |  | 2678.5 |  |  | 2363.5 |  |  | 2767.5 |  |  | 2567.5 |  |  | 2659.5 |  |  | 2529.5 |  |  | 2700.5 |  |  | 2517.5 |  |  | 2749.5 |  |  | 2599.5 |  |  | 2636.5 |  |  | 2475.5 |  |  | 2664.5 |  |  | 2691.5 |  |  | 2598.5 |  |  | 2568.5 |  |  | 2583.5 |  |  | 2529.5 |  |  | 2524.5 |  |  | 2636.5 |  |  | 2654.5 |  |  | 2576 |  |  | 2670.5 |  |  | 2567.5 |  |  | 2648.5 |  |  | 2611 |  |  | 2641.5 |  |  | 2564.5 |  |  | 2692.5 |  |  | 2649.5 |  |  | 2617 |  |  | 2477.5 |  |  | 2443.5 |  |  | 2514 |  |  | 2560 |  |  | 2553 |  |  | 2619.5 |  |  | 2558.5 |  |  | 2680.5 |  |  | 2805.5 |  |  | 2672 |  |  | 2621.5 |  |  | 2594.5 |  |  | 2473 |  |  | 2551 |  |  | 2647.5 |  |  | 2627.5 |  |  | 2724 |  |  | 2615.5 |  |  | 2693 |  |  | 2520.5 |  |  | 2582.5 |  |  | 2664 |  |  | 2700.5 |  |  | 2606.5 |  |  | 2453.5 |  |  | 2717 |  |  | 2508.5 |  |  | 2509.5 |  |  | 2536.5 |  |  | 2566.5 |  |  | 2600.5 |  |  | 2628.5 |  |  | 2558.5 |  |  | 2657.5 |  |  | 2665.5 |  |  | 2565.5 |  |  | 2551 |  |  | 2585.5 |  |  | 2630.5 |  |  | 2653.5 |  |  | 2685.5 |  |  | 2572.5 |  |  | 2600.5 |  |  | 2668.5 |  |  | 2548.5 |  |  | 2702 |  |  | 2528.5 |  |  | 2568 |  |  | 2850.5 |  |  | 2772.5 |  |  | 2805.5 |  |  | 2528.5 |  |  | 2528.5 |  |  | 2623.5 |  |  | 2448.5 |  |  | 2647.5 |  |  | 2657 |  |  | 2510.5 |  |  | 2645 |  |  | 2481.5 |  |  | 2502.5 |  |  | 2580.5 |  |  | 2674 |  |  | 2550.5 |  |  | 2597.5 |  |  | 2371 |  |  | 2560.5 |  |  | 2543 |  |  | 2603.5 |  |  | 2481.5 |  |  | 2544.5 |  |  | 2611 |  |  | 2703.5 |  |  | 2842.5 |  |  | 2447 |  |  | 2765.5 |  |  | 2581.5 |  |  | 2652 |  |  | 2610.5 |  |  | 2761.5 |  |  | 2705.5 |  |  | 2679.5 |  |  | 2533.5 |  |  | 2751.5 |  |  | 2485.5 |  |  | 2547.5 |  |  | 2524.5 |  |  | 2542.5 |  |  | 2742.5 |  |  | 2705 |  |  | 2620 |  |  | 2704.5 |  |  | 2597.5 |  |  | 2643
89 |  | 2584.5 |  |  | 2683.5 |  |  | 2668 |  |  | 2566.5 |  |  | 2781.5 |  |  | 2646.5 |  |  | 2690.5 |  |  | 2646.5 |  |  | 2629.5 |  |  | 2614.5 |  |  | 2525 |  |  | 2677.5 |  |  | 2651.5 |  |  | 2517.5 |  |  | 2526 |  |  | 2618.5 |  |  | 2714.5 |  |  | 2596.5 |  |  | 2692.5 |  |  | 2525.5 |  |  | 2783.5 |  |  | 2636.5 |  |  | 2743.5 |  |  | 2566.5 |  |  | 2417 |  |  | 2721.5 |  |  | 2613.5 |  |  | 2596.5 |  |  | 2655.5 |  |  | 2465 |  |  | 2645 |  |  | 2740.5 |  |  | 2439.5 |  |  | 2608.5 |  |  | 2531.5 |  |  | 2653 |  |  | 2570.5 |  |  | 2773 |  |  | 2615.5 |  |  | 2610.5 |  |  | 2397.5 |  |  | 2696.5 |  |  | 2502.5 |  |  | 2603 |  |  | 2780.5 |  |  | 2734 |  |  | 2642.5 |  |  | 2705.5 |  |  | 2765.5 |  |  | 2649.5 |  |  | 2529.5 |  |  | 2690.5 |  |  | 2632.5 |  |  | 2601.5 |  |  | 2678.5 |  |  | 2646.5 |  |  | 2514.5 |  |  | 2625 |  |  | 2631.5 |  |  | 2617.5 |  |  | 2600 |  |  | 2651.5 |  |  | 2759.5 |  |  | 2592.5 |  |  | 2519.5 |  |  | 2666 |  |  | 2784.5 |  |  | 2504 |  |  | 2486.5 |  |  | 2653.5 |  |  | 2616 |  |  | 2530.5 |  |  | 2628.5 |  |  | 2738.5 |  |  | 2760 |  |  | 2716 |  |  | 2449.5 |  |  | 2558.5 |  |  | 2560.5 |  |  | 2631.5 |  |  | 2609 |  |  | 2686.5 |  |  | 2704.5 |  |  | 2680.5 |  |  | 2725.5 |  |  | 2519.5 |  |  | 2701.5 |  |  | 2651.5 |  |  | 2622.5 |  |  | 2610.5 |  |  | 2611.5 |  |  | 2655 |  |  | 2577.5 |  |  | 2464 |  |  | 2578 |  |  | 2500 |  |  | 2799.5 |  |  | 2712.5 |  |  | 2513.5 |  |  | 2819.5 |  |  | 2526.5 |  |  | 2563 |  |  | 2603 |  |  | 2628.5 |  |  | 2668.5 |  |  | 2549.5 |  |  | 2646.5 |  |  | 2713.5 |  |  | 2711.5 |  |  | 2750.5 |  |  | 2769.5 |  |  | 2711.5 |  |  | 2580.5 |  |  | 2657.5 |  |  | 2648.5 |  |  | 2678.5 |  |  | 2722.5 |  |  | 2587.5 |  |  | 2646.5 |  |  | 2615.5 |  |  | 2662.5 |  |  | 2666.5 |  |  | 2677.5 |  |  | 2636.5 |  |  | 2653.5 |  |  | 2592 |  |  | 2583.5 |  |  | 2598.5 |  |  | 2580.5 |  |  | 2667.5 |  |  | 2698.5 |  |  | 2623 |  |  | 2534.5 |  |  | 2735.5 |  |  | 2604.5 |  |  | 2584.5 |  |  | 2675 |  |  | 2660.5 |  |  | 2735.5 |  |  | 2506 |  |  | 2693.5 |  |  | 2402 |  |  | 2736 |  |  | 2768.5 |  |  | 2662 |  |  | 2765.5 |  |  | 2583.5 |  |  | 2652.5 |  |  | 2564.5 |  |  | 2655.5 |  |  | 2666.5 |  |  | 2620.5 |  |  | 2681.5 |  |  | 2731.5 |  |  | 2650.5 |  |  | 2722 |  |  | 2520.5 |  |  | 2462 |  |  | 2593.5 |  |  | 2622.5 |  |  | 2556 |  |  | 2626.5 |  |  | 2580.5 |  |  | 2558.5 |  |  | 2491 |  |  | 2610.5 |  |  | 2446.5 |  |  | 2550.5 |  |  | 2727.5 |  |  | 2601.5 |  |  | 2563.5 |  |  | 2575 |  |  | 2627.5 |  |  | 2593.5 |  |  | 2550.5 |  |  | 2665.5 |  |  | 2650.5 |  |  | 2684.5 |  |  | 2566.5 |  |  | 2709 |  |  | 2668.5 |  |  | 2638.5 |  |  | 2686.5 |  |  | 2690.5 |  |  | 2577.5 |  |  | 2702.5 |  |  | 2715.5 |  |  | 2616.5 |  |  | 2775.5 |  |  | 2545.5 |  |  | 2710.5 |  |  | 2411.5 |  |  | 2450.5 |  |  | 2499 |  |  | 2540.5 |  |  | 2649.5 |  |  | 2649.5 |  |  | 2683.5 |  |  | 2702.5 |  |  | 2753.5 |  |  | 2723.5 |  |  | 2613.5 |  |  | 2660.5 |  |  | 2621.5 |  |  | 2526.5 |  |  | 2743.5 |  |  | 2627.5 |  |  | 2585.5 |  |  | 2600.5 |  |  | 2608.5 |  |  | 2657 |  |  | 2776.5 |  |  | 2638.5 |  |  | 2370 |  |  | 2774.5 |  |  | 2790 |  |  | 2435.5 |  |  | 2640.5 |  |  | 2712.5 |  |  | 2758.5 |  |  | 2579.5 |  |  | 2563.5 |  |  | 2624.5 |  |  | 2473.5 |  |  | 2473 |  |  | 2481.5 |  |  | 2447.5 |  |  | 2683.5 |  |  | 2560.5 |  |  | 2606 |  |  | 2617.5 |  |  | 2586.5 |  |  | 2720.5 |  |  | 2611.5 |  |  | 2706.5 |  |  | 2631.5 |  |  | 2611.5 |  |  | 2768.5 |  |  | 2731 |  |  | 2656 |  |  | 2574.5 |  |  | 2523.5 |  |  | 2658.5 |  |  | 2573 |  |  | 2769.5 |  |  | 2622.5 |  |  | 2622.5 |  |  | 2493 |  |  | 2747.5 |  |  | 2602.5 |  |  | 2445.5 |  |  | 2561.5 |  |  | 2636.5 |  |  | 2676.5 |  |  | 2715.5 |  |  | 2667.5 |  |  | 2726.5 |  |  | 2406 |  |  | 2523.5 |  |  | 2698.5 |  |  | 2634.5 |  |  | 2611.5 |  |  | 2568.5 |  |  | 2782 |  |  | 2508.5 |  |  | 2758.5 |  |  | 2694 |  |  | 2743.5 |  |  | 2637.5 |  |  | 2872 |  |  | 2683.5 |  |  | 2699.5 |  |  | 2796.5 |  |  | 2572.5 |  |  | 2605 |  |  | 2640 |  |  | 2643.5 |  |  | 2519.5 |  |  | 2699.5 |  |  | 2572.5 |  |  | 2790.5 |  |  | 2678.5 |  |  | 2607 |  |  | 2566.5 |  |  | 2487.5 |  |  | 2561 |  |  | 2592.5 |  |  | 2412.5 |  |  | 2640 |  |  | 2674.5 |  |  | 2548.5 |  |  | 2627.5 |  |  | 2667 |  |  | 2616.5 |  |  | 2572 |  |  | 2758.5 |  |  | 2538.5 |  |  | 2638.5 |  |  | 2578 |  |  | 2544.5 |  |  | 2750.5 |  |  | 2722.5 |  |  | 2644 |  |  | 2586.5 |  |  | 2467.5 |  |  | 2779.5 |  |  | 2792.5 |  |  | 2643.5 |  |  | 2663 |  |  | 2534.5 |  |  | 2738.5 |  |  | 2644.5 |  |  | 2619 |  |  | 2628 |  |  | 2791.5 |  |  | 2537.5 |  |  | 2444.5 |  |  | 2675.5 |  |  | 2619.5 |  |  | 2598.5 |  |  | 2679.5 |  |  | 2715.5 |  |  | 2541.5 |  |  | 2653.5 |  |  | 2644 |  |  | 2576.5 |  |  | 2641.5 |  |  | 2840.5 |  |  | 2816.5 |  |  | 2674 |  |  | 2584.5 |  |  | 2743.5 |  |  | 2639.5 |  |  | 2482.5 |  |  | 2748.5 |  |  | 2442 |  |  | 2689 |  |  | 2518 |  |  | 2713 |  |  | 2537.5 |  |  | 2610 |  |  | 2639.5 |  |  | 2628 |  |  | 2587.5 |  |  | 2728.5 |  |  | 2593.5 |  |  | 2612.5 |  |  | 2559.5 |  |  | 2657 |  |  | 2640.5 |  |  | 2779.5 |  |  | 2592.5 |  |  | 2627 |  |  | 2771.5 |  |  | 2550.5 |  |  | 2656.5 |  |  | 2704 |  |  | 2575.5 |  |  | 2527.5 |  |  | 2709.5 |  |  | 2538.5 |  |  | 2684.5 |  |  | 2533.5 |  |  | 2685.5 |  |  | 2601.5 |  |  | 2697.5 |  |  | 2465.5 |  |  | 2607 |  |  | 2524.5 |  |  | 2595.5 |  |  | 2515.5 |  |  | 2679.5 |  |  | 2744.5 |  |  | 2607 |  |  | 2716.5 |  |  | 2727 |  |  | 2614 |  |  | 2519.5 |  |  | 2693.5 |  |  | 2530.5 |  |  | 2630 |  |  | 2663.5 |  |  | 2649.5 |  |  | 2646.5 |  |  | 2442 |  |  | 2552.5 |  |  | 2435.5 |  |  | 2566.5 |  |  | 2475.5 |  |  | 2581.5 |  |  | 2566 |  |  | 2535.5 |  |  | 2679 |  |  | 2634.5 |  |  | 2441.5 |  |  | 2594.5 |  |  | 2611 |  |  | 2566.5 |  |  | 2543 |  |  | 2580 |  |  | 2623.5 |  |  | 2484.5 |  |  | 2525.5 |  |  | 2795.5 |  |  | 2819 |  |  | 2697.5 |  |  | 2609.5 |  |  | 2431.5 |  |  | 2590 |  |  | 2680.5 |  |  | 2547.5 |  |  | 2367.5 |  |  | 2668.5 |  |  | 2783 |  |  | 2503.5 |  |  | 2542.5 |  |  | 2621.5 |  |  | 2672.5 |  |  | 2697.5 |  |  | 2648.5 |  |  | 2709 |  |  | 2546.5 |  |  | 2549.5 |  |  | 2615 |  |  | 2504.5 |  |  | 2503.5 |  |  | 2634.5 |  |  | 2635 |  |  | 2684.5 |  |  | 2647.5 |  |  | 2581.5 |  |  | 2568.5 |  |  | 2647.5 |  |  | 2613 |  |  | 2520 |  |  | 2638.5 |  |  | 2684.5 |  |  | 2650.5 |  |  | 2467.5 |  |  | 2395 |  |  | 2726 |  |  | 2592 |  |  | 2740.5 |  |  | 2580 |  |  | 2667.5 |  |  | 2748.5 |  |  | 2718 |  |  | 2476.5 |  |  | 2610.5 |  |  | 2570.5 |  |  | 2696.5 |  |  | 2359.5 |  |  | 2601 |  |  | 2695 |  |  | 2509.5 |  |  | 2705.5 |  |  | 2488 |  |  | 2530.5 |  |  | 2631.5 |  |  | 2558 |  |  | 2754.5 |  |  | 2764.5 |  |  | 2521 |  |  | 2706.5 |  |  | 2670.5 |  |  | 2729 |  |  | 2555.5 |  |  | 2506 |  |  | 2760.5 |  |  | 2754 |  |  | 2527.5 |  |  | 2527.5 |  |  | 2547.5 |  |  | 2617.5 |  |  | 2627.5 |  |  | 2492.5 |  |  | 2648 |  |  | 2502.5 |  |  | 2650.5 |  |  | 2530.5 |  |  | 2593.5 |  |  | 2634.5 |  |  | 2556 |  |  | 2590.5 |  |  | 2642 |  |  | 2659.5 |  |  | 2469.5 |  |  | 2654.5 |  |  | 2686.5 |  |  | 2675.5 |  |  | 2587.5 |  |  | 2503.5 |  |  | 2679.5 |  |  | 2481.5 |  |  | 2541 |  |  | 2659.5 |  |  | 2559 |  |  | 2659 |  |  | 2655.5 |  |  | 2355 |  |  | 2480.5 |  |  | 2682.5 |  |  | 2727.5 |  |  | 2657.5 |  |  | 2704.5 |  |  | 2649.5 |  |  | 2695.5 |  |  | 2590 |  |  | 2736 |  |  | 2520.5 |  |  | 2642.5 |  |  | 2635 |  |  | 2596.5 |  |  | 2556.5 |  |  | 2551.5 |  |  | 2539.5 |  |  | 2602.5 |  |  | 2510 |  |  | 2631.5 |  |  | 2578.5 |  |  | 2566.5 |  |  | 2609 |  |  | 2649.5 |  |  | 2699.5 |  |  | 2681.5 |  |  | 2870.5 |  |  | 2650.5 |  |  | 2531.5 |  |  | 2678.5 |  |  | 2228.5 |  |  | 2600.5 |  |  | 2551 |  |  | 2747.5 |  |  | 2649.5 |  |  | 2702.5 |  |  | 2494.5 |  |  | 2638.5 |  |  | 2494.5 |  |  | 2493.5 |  |  | 2471 |  |  | 2532.5 |  |  | 2604.5 |  |  | 2554.5 |  |  | 2615 |  |  | 2652.5 |  |  | 2504 |  |  | 2488.5 |  |  | 2618.5 |  |  | 2569.5 |  |  | 2657 |  |  | 2421.5 |  |  | 2646 |  |  | 2605 |  |  | 2639.5 |  |  | 2614 |  |  | 2776 |  |  | 2690.5 |  |  | 2710.5 |  |  | 2516.5 |  |  | 2699 |  |  | 2626.5 |  |  | 2507.5 |  |  | 2443.5 |  |  | 2728.5 |  |  | 2537.5 |  |  | 2608.5 |  |  | 2615.5 |  |  | 2624.5 |  |  | 2565 |  |  | 2770.5 |  |  | 2549 |  |  | 2664.5 |  |  | 2519.5 |  |  | 2715.5 |  |  | 2615 |  |  | 2684 |  |  | 2773 |  |  | 2668.5 |  |  | 2631 |  |  | 2650.5 |  |  | 2790.5 |  |  | 2626.5 |  |  | 2590.5 |  |  | 2490.5 |  |  | 2735.5 |  |  | 2708.5 |  |  | 2662.5 |  |  | 2649 |  |  | 2457.5 |  |  | 2501.5 |  |  | 2634.5 |  |  | 2631.5 |  |  | 2541 |  |  | 2623.5 |  |  | 2639 |  |  | 2625.5 |  |  | 2616.5 |  |  | 2558.5 |  |  | 2472.5 |  |  | 2480 |  |  | 2590.5 |  |  | 2384 |  |  | 2557.5 |  |  | 2680.5 |  |  | 2801.5 |  |  | 2571.5 |  |  | 2584.5 |  |  | 2700.5 |  |  | 2571.5 |  |  | 2637.5 |  |  | 2550.5 |  |  | 2514 |  |  | 2618.5 |  |  | 2608.5 |  |  | 2587.5 |  |  | 2671.5 |  |  | 2679.5 |  |  | 2553 |  |  | 2551 |  |  | 2597.5 |  |  | 2544 |  |  | 2768.5 |  |  | 2519.5 |  |  | 2721.5 |  |  | 2625.5 |  |  | 2549.5 |  |  | 2715.5 |  |  | 2625.5 |  |  | 2679.5 |  |  | 2663 |  |  | 2642.5 |  |  | 2802.5 |  |  | 2562.5 |  |  | 2451 |  |  | 2655.5 |  |  | 2513.5 |  |  | 2758 |  |  | 2609 |  |  | 2600.5 |  |  | 2573 |  |  | 2470 |  |  | 2485.5 |  |  | 2741 |  |  | 2816.5 |  |  | 2589.5 |  |  | 2732.5 |  |  | 2560.5 |  |  | 2499.5 |  |  | 2637.5 |  |  | 2415.5 |  |  | 2548.5 |  |  | 2664.5 |  |  | 2506.5 |  |  | 2528 |  |  | 2540 |  |  | 2691.5 |  |  | 2735.5 |  |  | 2517.5 |  |  | 2699.5 |  |  | 2576.5 |  |  | 2668.5 |  |  | 2641.5 |  |  | 2525.5 |  |  | 2843 |  |  | 2543.5 |  |  | 2581 |  |  | 2544.5 |  |  | 2727.5 |  |  | 2670.5 |  |  | 2731 |  |  | 2619.5 |  |  | 2555.5 |  |  | 2648 |  |  | 2694.5 |  |  | 2622.5 |  |  | 2726.5 |  |  | 2614.5 |  |  | 2597.5 |  |  | 2644.5 |  |  | 2673 |  |  | 2538.5 |  |  | 2605.5 |  |  | 2750.5 |  |  | 2661.5 |  |  | 2632 |  |  | 2619.5 |  |  | 2773.5 |  |  | 2553 |  |  | 2606.5 |  |  | 2693.5 |  |  | 2658 |  |  | 2684.5 |  |  | 2753.5 |  |  | 2597.5 |  |  | 2527 |  |  | 2475.5 |  |  | 2589.5 |  |  | 2526 |  |  | 2661.5 |  |  | 2614.5 |  |  | 2656.5 |  |  | 2458.5 |  |  | 2616.5 |  |  | 2790.5 |  |  | 2544.5 |  |  | 2603 |  |  | 2515 |  |  | 2448.5 |  |  | 2689.5 |  |  | 2513.5 |  |  | 2719 |  |  | 2769.5 |  |  | 2574.5 |  |  | 2598.5 |  |  | 2424.5 |  |  | 2666.5 |  |  | 2679.5 |  |  | 2536.5 |  |  | 2673.5 |  |  | 2398.5 |  |  | 2648 |  |  | 2601.5 |  |  | 2422.5 |  |  | 2606.5 |  |  | 2603.5 |  |  | 2783.5 |  |  | 2667.5 |  |  | 2616.5 |  |  | 2598.5 |  |  | 2451.5 |  |  | 2749.5 |  |  | 2586.5 |  |  | 2492.5 |  |  | 2628.5 |  |  | 2741 |  |  | 2668.5 |  |  | 2717.5 |  |  | 2564 |  |  | 2682.5 |  |  | 2670.5 |  |  | 2726 |  |  | 2652.5 |  |  | 2706.5 |  |  | 2797.5 |  |  | 2813 |  |  | 2548.5 |  |  | 2710.5 |  |  | 2582.5 |  |  | 2409.5 |  |  | 2714.5 |  |  | 2565 |  |  | 2561.5 |  |  | 2701 |  |  | 2668 |  |  | 2674.5 |  |  | 2606.5 |  |  | 2538.5 |  |  | 2358.5 |  |  | 2563.5 |  |  | 2739.5 |  |  | 2612 |  |  | 2570.5 |  |  | 2566 |  |  | 2601.5 |  |  | 2628 |  |  | 2515 |  |  | 2699 |  |  | 2737.5 |  |  | 2522 |  |  | 2772.5 |  |  | 2662.5 |  |  | 2619.5 |  |  | 2795.5 |  |  | 2435.5 |  |  | 2733 |  |  | 2585.5 |  |  | 2661.5 |  |  | 2864.5 |  |  | 2609 |  |  | 2563.5 |  |  | 2577.5 |  |  | 2646.5 |  |  | 2750.5 |  |  | 2574 |  |  | 2719 |  |  | 2552 |  |  | 2601.5 |  |  | 2757 |  |  | 2663 |  |  | 2742.5 |  |  | 2517.5 |  |  | 2506.5 |  |  | 2617.5 |  |  | 2666.5 |  |  | 2621.5 |  |  | 2667.5 |  |  | 2601.5 |  |  | 2570.5 |  |  | 2527 |  |  | 2560.5 |  |  | 2471 |  |  | 2634.5 |  |  | 2590.5 |  |  | 2697.5 |  |  | 2669.5 |  |  | 2750 |  |  | 2644.5 |  |  | 2596 |  |  | 2543.5 |  |  | 2670.5 |  |  | 2466 |  |  | 2585 |  |  | 2698.5 |  |  | 2695 |  |  | 2618.5 |  |  | 2453.5 |  |  | 2512.5 |  |  | 2549.5 |  |  | 2612.5 |  |  | 2594.5 |  |  | 2485.5 |  |  | 2562 |  |  | 2674.5 |  |  | 2661.5 |  |  | 2661.5 |  |  | 2679.5 |  |  | 2548.5 |  |  | 2633.5 |  |  | 2756.5 |  |  | 2625.5 |  |  | 2807.5 |  |  | 2765.5 |  |  | 2525.5 |  |  | 2492.5 |  |  | 2616 |  |  | 2502.5 |  |  | 2597.5 |  |  | 2692 |  |  | 2549.5 |  |  | 2520.5 |  |  | 2601.5 |  |  | 2489.5 |  |  | 2827 |  |  | 2757.5 |  |  | 2520.5 |  |  | 2531.5 |  |  | 2754.5 |  |  | 2568 |  |  | 2589.5 |  |  | 2735.5 |  |  | 2537.5 |  |  | 2712.5 |  |  | 2523.5 |  |  | 2516.5 |  |  | 2694.5 |  |  | 2588.5 |  |  | 2601.5 |  |  | 2633.5 |  |  | 2696.5 |  |  | 2687 |  |  | 2634.5 |  |  | 2585.5 |  |  | 2670.5 |  |  | 2772.5 |  |  | 2557.5 |  |  | 2562.5 |  |  | 2649 |  |  | 2720.5 |  |  | 2552 |  |  | 2518.5 |  |  | 2678.5 |  |  | 2691.5 |  |  | 2591 |  |  | 2536 |  |  | 2683.5 |  |  | 2704.5 |  |  | 2389.5 |  |  | 2806.5 |  |  | 2588.5 |  |  | 2685.5 |  |  | 2558.5 |  |  | 2729.5 |  |  | 2564.5 |  |  | 2796.5 |  |  | 2625.5 |  |  | 2683.5 |  |  | 2501.5 |  |  | 2688.5 |  |  | 2730.5 |  |  | 2613.5 |  |  | 2592.5 |  |  | 2604.5 |  |  | 2555.5 |  |  | 2553.5 |  |  | 2675.5 |  |  | 2701.5 |  |  | 2597 |  |  | 2694.5 |  |  | 2596.5 |  |  | 2695.5 |  |  | 2632 |  |  | 2680.5 |  |  | 2579.5 |  |  | 2731.5 |  |  | 2673.5 |  |  | 2646 |  |  | 2498.5 |  |  | 2458.5 |  |  | 2535 |  |  | 2589 |  |  | 2592 |  |  | 2643.5 |  |  | 2573.5 |  |  | 2706.5 |  |  | 2826.5 |  |  | 2711 |  |  | 2636.5 |  |  | 2618.5 |  |  | 2520 |  |  | 2577 |  |  | 2686.5 |  |  | 2666.5 |  |  | 2745 |  |  | 2654.5 |  |  | 2722 |  |  | 2541.5 |  |  | 2603.5 |  |  | 2685 |  |  | 2721.5 |  |  | 2632.5 |  |  | 2482.5 |  |  | 2738 |  |  | 2532.5 |  |  | 2535.5 |  |  | 2565.5 |  |  | 2581.5 |  |  | 2647.5 |  |  | 2667.5 |  |  | 2605.5 |  |  | 2678.5 |  |  | 2686.5 |  |  | 2604.5 |  |  | 2572 |  |  | 2614.5 |  |  | 2654.5 |  |  | 2700.5 |  |  | 2709.5 |  |  | 2587.5 |  |  | 2615.5 |  |  | 2689.5 |  |  | 2574.5 |  |  | 2741 |  |  | 2567.5 |  |  | 2589 |  |  | 2889.5 |  |  | 2787.5 |  |  | 2826.5 |  |  | 2549.5 |  |  | 2543.5 |  |  | 2652.5 |  |  | 2472.5 |  |  | 2673.5 |  |  | 2704 |  |  | 2549.5 |  |  | 2674 |  |  | 2507.5 |  |  | 2531.5 |  |  | 2604.5 |  |  | 2695 |  |  | 2574.5 |  |  | 2644.5 |  |  | 2410 |  |  | 2575.5 |  |  | 2590 |  |  | 2642.5 |  |  | 2528.5 |  |  | 2559.5 |  |  | 2632 |  |  | 2742.5 |  |  | 2881.5 |  |  | 2462 |  |  | 2780.5 |  |  | 2628.5 |  |  | 2676 |  |  | 2634.5 |  |  | 2800.5 |  |  | 2726.5 |  |  | 2718.5 |  |  | 2548.5 |  |  | 2790.5 |  |  | 2514.5 |  |  | 2562.5 |  |  | 2539.5 |  |  | 2557.5 |  |  | 2789.5 |  |  | 2729 |  |  | 2667 |  |  | 2743.5 |  |  | 2621.5 |  |  | 2658
90 |  | 2605.5 |  |  | 2704.5 |  |  | 2697 |  |  | 2587.5 |  |  | 2820.5 |  |  | 2675.5 |  |  | 2714.5 |  |  | 2675.5 |  |  | 2655.5 |  |  | 2653.5 |  |  | 2546 |  |  | 2703.5 |  |  | 2680.5 |  |  | 2538.5 |  |  | 2573 |  |  | 2657.5 |  |  | 2735.5 |  |  | 2622.5 |  |  | 2731.5 |  |  | 2549.5 |  |  | 2807.5 |  |  | 2683.5 |  |  | 2782.5 |  |  | 2592.5 |  |  | 2441 |  |  | 2768.5 |  |  | 2652.5 |  |  | 2643.5 |  |  | 2694.5 |  |  | 2486 |  |  | 2674 |  |  | 2764.5 |  |  | 2465.5 |  |  | 2634.5 |  |  | 2570.5 |  |  | 2677 |  |  | 2585.5 |  |  | 2812 |  |  | 2636.5 |  |  | 2649.5 |  |  | 2436.5 |  |  | 2720.5 |  |  | 2523.5 |  |  | 2642 |  |  | 2827.5 |  |  | 2773 |  |  | 2689.5 |  |  | 2734.5 |  |  | 2786.5 |  |  | 2688.5 |  |  | 2550.5 |  |  | 2729.5 |  |  | 2647.5 |  |  | 2627.5 |  |  | 2717.5 |  |  | 2670.5 |  |  | 2561.5 |  |  | 2664 |  |  | 2670.5 |  |  | 2656.5 |  |  | 2615 |  |  | 2666.5 |  |  | 2798.5 |  |  | 2631.5 |  |  | 2566.5 |  |  | 2687 |  |  | 2805.5 |  |  | 2530 |  |  | 2501.5 |  |  | 2679.5 |  |  | 2631 |  |  | 2569.5 |  |  | 2643.5 |  |  | 2785.5 |  |  | 2775 |  |  | 2737 |  |  | 2496.5 |  |  | 2579.5 |  |  | 2589.5 |  |  | 2655.5 |  |  | 2638 |  |  | 2707.5 |  |  | 2719.5 |  |  | 2695.5 |  |  | 2751.5 |  |  | 2540.5 |  |  | 2727.5 |  |  | 2690.5 |  |  | 2646.5 |  |  | 2634.5 |  |  | 2658.5 |  |  | 2670 |  |  | 2601.5 |  |  | 2511 |  |  | 2593 |  |  | 2529 |  |  | 2820.5 |  |  | 2741.5 |  |  | 2552.5 |  |  | 2858.5 |  |  | 2565.5 |  |  | 2584 |  |  | 2642 |  |  | 2667.5 |  |  | 2683.5 |  |  | 2573.5 |  |  | 2672.5 |  |  | 2760.5 |  |  | 2758.5 |  |  | 2789.5 |  |  | 2795.5 |  |  | 2737.5 |  |  | 2601.5 |  |  | 2678.5 |  |  | 2687.5 |  |  | 2693.5 |  |  | 2769.5 |  |  | 2611.5 |  |  | 2670.5 |  |  | 2654.5 |  |  | 2709.5 |  |  | 2687.5 |  |  | 2724.5 |  |  | 2675.5 |  |  | 2674.5 |  |  | 2631 |  |  | 2604.5 |  |  | 2637.5 |  |  | 2609.5 |  |  | 2691.5 |  |  | 2727.5 |  |  | 2644 |  |  | 2581.5 |  |  | 2782.5 |  |  | 2643.5 |  |  | 2599.5 |  |  | 2699 |  |  | 2684.5 |  |  | 2761.5 |  |  | 2527 |  |  | 2740.5 |  |  | 2428 |  |  | 2762 |  |  | 2789.5 |  |  | 2683 |  |  | 2794.5 |  |  | 2630.5 |  |  | 2678.5 |  |  | 2603.5 |  |  | 2679.5 |  |  | 2690.5 |  |  | 2641.5 |  |  | 2705.5 |  |  | 2778.5 |  |  | 2671.5 |  |  | 2761 |  |  | 2544.5 |  |  | 2501 |  |  | 2640.5 |  |  | 2648.5 |  |  | 2595 |  |  | 2650.5 |  |  | 2627.5 |  |  | 2582.5 |  |  | 2520 |  |  | 2634.5 |  |  | 2467.5 |  |  | 2565.5 |  |  | 2756.5 |  |  | 2630.5 |  |  | 2602.5 |  |  | 2599 |  |  | 2653.5 |  |  | 2640.5 |  |  | 2565.5 |  |  | 2712.5 |  |  | 2679.5 |  |  | 2713.5 |  |  | 2605.5 |  |  | 2756 |  |  | 2707.5 |  |  | 2653.5 |  |  | 2701.5 |  |  | 2716.5 |  |  | 2616.5 |  |  | 2723.5 |  |  | 2744.5 |  |  | 2640.5 |  |  | 2814.5 |  |  | 2566.5 |  |  | 2725.5 |  |  | 2450.5 |  |  | 2479.5 |  |  | 2514 |  |  | 2579.5 |  |  | 2670.5 |  |  | 2688.5 |  |  | 2722.5 |  |  | 2717.5 |  |  | 2792.5 |  |  | 2762.5 |  |  | 2660.5 |  |  | 2699.5 |  |  | 2636.5 |  |  | 2565.5 |  |  | 2782.5 |  |  | 2648.5 |  |  | 2614.5 |  |  | 2626.5 |  |  | 2637.5 |  |  | 2683 |  |  | 2823.5 |  |  | 2677.5 |  |  | 2385 |  |  | 2789.5 |  |  | 2811 |  |  | 2450.5 |  |  | 2679.5 |  |  | 2751.5 |  |  | 2782.5 |  |  | 2594.5 |  |  | 2578.5 |  |  | 2645.5 |  |  | 2494.5 |  |  | 2512 |  |  | 2502.5 |  |  | 2486.5 |  |  | 2712.5 |  |  | 2581.5 |  |  | 2635 |  |  | 2643.5 |  |  | 2601.5 |  |  | 2759.5 |  |  | 2626.5 |  |  | 2730.5 |  |  | 2678.5 |  |  | 2658.5 |  |  | 2794.5 |  |  | 2757 |  |  | 2685 |  |  | 2598.5 |  |  | 2547.5 |  |  | 2697.5 |  |  | 2599 |  |  | 2790.5 |  |  | 2669.5 |  |  | 2651.5 |  |  | 2508 |  |  | 2786.5 |  |  | 2641.5 |  |  | 2471.5 |  |  | 2600.5 |  |  | 2660.5 |  |  | 2715.5 |  |  | 2754.5 |  |  | 2682.5 |  |  | 2752.5 |  |  | 2445 |  |  | 2538.5 |  |  | 2713.5 |  |  | 2658.5 |  |  | 2632.5 |  |  | 2597.5 |  |  | 2811 |  |  | 2537.5 |  |  | 2805.5 |  |  | 2709 |  |  | 2790.5 |  |  | 2658.5 |  |  | 2887 |  |  | 2722.5 |  |  | 2725.5 |  |  | 2817.5 |  |  | 2596.5 |  |  | 2644 |  |  | 2669 |  |  | 2667.5 |  |  | 2540.5 |  |  | 2738.5 |  |  | 2587.5 |  |  | 2829.5 |  |  | 2717.5 |  |  | 2654 |  |  | 2581.5 |  |  | 2511.5 |  |  | 2582 |  |  | 2621.5 |  |  | 2459.5 |  |  | 2687 |  |  | 2698.5 |  |  | 2572.5 |  |  | 2666.5 |  |  | 2696 |  |  | 2655.5 |  |  | 2619 |  |  | 2779.5 |  |  | 2559.5 |  |  | 2662.5 |  |  | 2593 |  |  | 2591.5 |  |  | 2789.5 |  |  | 2737.5 |  |  | 2683 |  |  | 2607.5 |  |  | 2482.5 |  |  | 2803.5 |  |  | 2839.5 |  |  | 2672.5 |  |  | 2702 |  |  | 2560.5 |  |  | 2777.5 |  |  | 2668.5 |  |  | 2648 |  |  | 2649 |  |  | 2817.5 |  |  | 2552.5 |  |  | 2468.5 |  |  | 2722.5 |  |  | 2666.5 |  |  | 2613.5 |  |  | 2718.5 |  |  | 2744.5 |  |  | 2580.5 |  |  | 2692.5 |  |  | 2683 |  |  | 2615.5 |  |  | 2656.5 |  |  | 2869.5 |  |  | 2855.5 |  |  | 2689 |  |  | 2610.5 |  |  | 2772.5 |  |  | 2678.5 |  |  | 2497.5 |  |  | 2787.5 |  |  | 2468 |  |  | 2715 |  |  | 2544 |  |  | 2734 |  |  | 2584.5 |  |  | 2634 |  |  | 2686.5 |  |  | 2649 |  |  | 2626.5 |  |  | 2743.5 |  |  | 2617.5 |  |  | 2633.5 |  |  | 2574.5 |  |  | 2683 |  |  | 2679.5 |  |  | 2800.5 |  |  | 2621.5 |  |  | 2674 |  |  | 2800.5 |  |  | 2565.5 |  |  | 2703.5 |  |  | 2719 |  |  | 2590.5 |  |  | 2566.5 |  |  | 2738.5 |  |  | 2564.5 |  |  | 2710.5 |  |  | 2580.5 |  |  | 2732.5 |  |  | 2630.5 |  |  | 2712.5 |  |  | 2486.5 |  |  | 2628 |  |  | 2539.5 |  |  | 2634.5 |  |  | 2544.5 |  |  | 2718.5 |  |  | 2783.5 |  |  | 2646 |  |  | 2742.5 |  |  | 2774 |  |  | 2643 |  |  | 2548.5 |  |  | 2722.5 |  |  | 2556.5 |  |  | 2669 |  |  | 2684.5 |  |  | 2664.5 |  |  | 2667.5 |  |  | 2481 |  |  | 2591.5 |  |  | 2461.5 |  |  | 2592.5 |  |  | 2496.5 |  |  | 2610.5 |  |  | 2605 |  |  | 2550.5 |  |  | 2708 |  |  | 2660.5 |  |  | 2465.5 |  |  | 2641.5 |  |  | 2632 |  |  | 2605.5 |  |  | 2582 |  |  | 2595 |  |  | 2649.5 |  |  | 2510.5 |  |  | 2564.5 |  |  | 2821.5 |  |  | 2834 |  |  | 2723.5 |  |  | 2638.5 |  |  | 2470.5 |  |  | 2629 |  |  | 2695.5 |  |  | 2586.5 |  |  | 2393.5 |  |  | 2689.5 |  |  | 2822 |  |  | 2550.5 |  |  | 2557.5 |  |  | 2636.5 |  |  | 2687.5 |  |  | 2726.5 |  |  | 2687.5 |  |  | 2735 |  |  | 2567.5 |  |  | 2578.5 |  |  | 2654 |  |  | 2530.5 |  |  | 2529.5 |  |  | 2673.5 |  |  | 2659 |  |  | 2723.5 |  |  | 2686.5 |  |  | 2620.5 |  |  | 2607.5 |  |  | 2694.5 |  |  | 2628 |  |  | 2567 |  |  | 2659.5 |  |  | 2705.5 |  |  | 2665.5 |  |  | 2493.5 |  |  | 2442 |  |  | 2741 |  |  | 2607 |  |  | 2766.5 |  |  | 2606 |  |  | 2696.5 |  |  | 2763.5 |  |  | 2765 |  |  | 2491.5 |  |  | 2657.5 |  |  | 2594.5 |  |  | 2720.5 |  |  | 2374.5 |  |  | 2616 |  |  | 2724 |  |  | 2533.5 |  |  | 2726.5 |  |  | 2527 |  |  | 2545.5 |  |  | 2670.5 |  |  | 2579 |  |  | 2793.5 |  |  | 2788.5 |  |  | 2560 |  |  | 2727.5 |  |  | 2699.5 |  |  | 2768 |  |  | 2570.5 |  |  | 2530 |  |  | 2799.5 |  |  | 2793 |  |  | 2566.5 |  |  | 2553.5 |  |  | 2594.5 |  |  | 2646.5 |  |  | 2666.5 |  |  | 2539.5 |  |  | 2677 |  |  | 2526.5 |  |  | 2697.5 |  |  | 2577.5 |  |  | 2622.5 |  |  | 2660.5 |  |  | 2585 |  |  | 2614.5 |  |  | 2671 |  |  | 2706.5 |  |  | 2484.5 |  |  | 2701.5 |  |  | 2701.5 |  |  | 2696.5 |  |  | 2608.5 |  |  | 2542.5 |  |  | 2700.5 |  |  | 2505.5 |  |  | 2588 |  |  | 2674.5 |  |  | 2598 |  |  | 2680 |  |  | 2681.5 |  |  | 2402 |  |  | 2519.5 |  |  | 2703.5 |  |  | 2751.5 |  |  | 2686.5 |  |  | 2751.5 |  |  | 2670.5 |  |  | 2742.5 |  |  | 2605 |  |  | 2783 |  |  | 2541.5 |  |  | 2689.5 |  |  | 2656 |  |  | 2635.5 |  |  | 2571.5 |  |  | 2572.5 |  |  | 2565.5 |  |  | 2623.5 |  |  | 2534 |  |  | 2660.5 |  |  | 2604.5 |  |  | 2595.5 |  |  | 2638 |  |  | 2678.5 |  |  | 2738.5 |  |  | 2696.5 |  |  | 2899.5 |  |  | 2679.5 |  |  | 2578.5 |  |  | 2725.5 |  |  | 2254.5 |  |  | 2639.5 |  |  | 2575 |  |  | 2786.5 |  |  | 2688.5 |  |  | 2749.5 |  |  | 2515.5 |  |  | 2653.5 |  |  | 2533.5 |  |  | 2508.5 |  |  | 2486 |  |  | 2558.5 |  |  | 2619.5 |  |  | 2578.5 |  |  | 2654 |  |  | 2691.5 |  |  | 2533 |  |  | 2514.5 |  |  | 2647.5 |  |  | 2598.5 |  |  | 2681 |  |  | 2445.5 |  |  | 2661 |  |  | 2652 |  |  | 2678.5 |  |  | 2643 |  |  | 2791 |  |  | 2716.5 |  |  | 2757.5 |  |  | 2531.5 |  |  | 2723 |  |  | 2655.5 |  |  | 2528.5 |  |  | 2490.5 |  |  | 2752.5 |  |  | 2584.5 |  |  | 2655.5 |  |  | 2636.5 |  |  | 2663.5 |  |  | 2594 |  |  | 2809.5 |  |  | 2573 |  |  | 2703.5 |  |  | 2545.5 |  |  | 2741.5 |  |  | 2654 |  |  | 2713 |  |  | 2797 |  |  | 2697.5 |  |  | 2655 |  |  | 2679.5 |  |  | 2814.5 |  |  | 2647.5 |  |  | 2619.5 |  |  | 2529.5 |  |  | 2759.5 |  |  | 2737.5 |  |  | 2688.5 |  |  | 2670 |  |  | 2478.5 |  |  | 2530.5 |  |  | 2660.5 |  |  | 2652.5 |  |  | 2565 |  |  | 2670.5 |  |  | 2663 |  |  | 2651.5 |  |  | 2631.5 |  |  | 2587.5 |  |  | 2496.5 |  |  | 2501 |  |  | 2619.5 |  |  | 2431 |  |  | 2581.5 |  |  | 2701.5 |  |  | 2827.5 |  |  | 2597.5 |  |  | 2623.5 |  |  | 2747.5 |  |  | 2600.5 |  |  | 2684.5 |  |  | 2576.5 |  |  | 2529 |  |  | 2647.5 |  |  | 2637.5 |  |  | 2613.5 |  |  | 2695.5 |  |  | 2700.5 |  |  | 2592 |  |  | 2575 |  |  | 2636.5 |  |  | 2559 |  |  | 2807.5 |  |  | 2558.5 |  |  | 2742.5 |  |  | 2640.5 |  |  | 2564.5 |  |  | 2730.5 |  |  | 2672.5 |  |  | 2708.5 |  |  | 2702 |  |  | 2681.5 |  |  | 2849.5 |  |  | 2601.5 |  |  | 2477 |  |  | 2676.5 |  |  | 2539.5 |  |  | 2797 |  |  | 2633 |  |  | 2629.5 |  |  | 2597 |  |  | 2517 |  |  | 2524.5 |  |  | 2780 |  |  | 2863.5 |  |  | 2604.5 |  |  | 2771.5 |  |  | 2584.5 |  |  | 2528.5 |  |  | 2652.5 |  |  | 2439.5 |  |  | 2569.5 |  |  | 2690.5 |  |  | 2545.5 |  |  | 2567 |  |  | 2587 |  |  | 2706.5 |  |  | 2756.5 |  |  | 2564.5 |  |  | 2714.5 |  |  | 2615.5 |  |  | 2707.5 |  |  | 2667.5 |  |  | 2546.5 |  |  | 2890 |  |  | 2572.5 |  |  | 2610 |  |  | 2573.5 |  |  | 2751.5 |  |  | 2709.5 |  |  | 2778 |  |  | 2645.5 |  |  | 2581.5 |  |  | 2687 |  |  | 2733.5 |  |  | 2648.5 |  |  | 2765.5 |  |  | 2640.5 |  |  | 2612.5 |  |  | 2670.5 |  |  | 2712 |  |  | 2559.5 |  |  | 2620.5 |  |  | 2797.5 |  |  | 2700.5 |  |  | 2656 |  |  | 2634.5 |  |  | 2802.5 |  |  | 2592 |  |  | 2627.5 |  |  | 2732.5 |  |  | 2673 |  |  | 2699.5 |  |  | 2774.5 |  |  | 2621.5 |  |  | 2542 |  |  | 2496.5 |  |  | 2613.5 |  |  | 2552 |  |  | 2676.5 |  |  | 2653.5 |  |  | 2677.5 |  |  | 2497.5 |  |  | 2631.5 |  |  | 2811.5 |  |  | 2583.5 |  |  | 2624 |  |  | 2541 |  |  | 2474.5 |  |  | 2713.5 |  |  | 2528.5 |  |  | 2766 |  |  | 2793.5 |  |  | 2595.5 |  |  | 2624.5 |  |  | 2439.5 |  |  | 2687.5 |  |  | 2700.5 |  |  | 2575.5 |  |  | 2720.5 |  |  | 2437.5 |  |  | 2663 |  |  | 2640.5 |  |  | 2446.5 |  |  | 2653.5 |  |  | 2629.5 |  |  | 2830.5 |  |  | 2706.5 |  |  | 2640.5 |  |  | 2624.5 |  |  | 2490.5 |  |  | 2788.5 |  |  | 2625.5 |  |  | 2518.5 |  |  | 2657.5 |  |  | 2780 |  |  | 2692.5 |  |  | 2764.5 |  |  | 2593 |  |  | 2697.5 |  |  | 2691.5 |  |  | 2765 |  |  | 2676.5 |  |  | 2732.5 |  |  | 2823.5 |  |  | 2839 |  |  | 2577.5 |  |  | 2739.5 |  |  | 2608.5 |  |  | 2430.5 |  |  | 2743.5 |  |  | 2586 |  |  | 2582.5 |  |  | 2727 |  |  | 2694 |  |  | 2689.5 |  |  | 2635.5 |  |  | 2553.5 |  |  | 2384.5 |  |  | 2587.5 |  |  | 2778.5 |  |  | 2633 |  |  | 2609.5 |  |  | 2605 |  |  | 2648.5 |  |  | 2667 |  |  | 2530 |  |  | 2725 |  |  | 2752.5 |  |  | 2548 |  |  | 2811.5 |  |  | 2688.5 |  |  | 2634.5 |  |  | 2834.5 |  |  | 2450.5 |  |  | 2748 |  |  | 2624.5 |  |  | 2690.5 |  |  | 2911.5 |  |  | 2633 |  |  | 2610.5 |  |  | 2606.5 |  |  | 2675.5 |  |  | 2779.5 |  |  | 2595 |  |  | 2745 |  |  | 2573 |  |  | 2625.5 |  |  | 2783 |  |  | 2689 |  |  | 2781.5 |  |  | 2546.5 |  |  | 2532.5 |  |  | 2643.5 |  |  | 2713.5 |  |  | 2668.5 |  |  | 2691.5 |  |  | 2630.5 |  |  | 2596.5 |  |  | 2566 |  |  | 2599.5 |  |  | 2510 |  |  | 2681.5 |  |  | 2619.5 |  |  | 2712.5 |  |  | 2695.5 |  |  | 2789 |  |  | 2670.5 |  |  | 2625 |  |  | 2567.5 |  |  | 2694.5 |  |  | 2490 |  |  | 2624 |  |  | 2713.5 |  |  | 2716 |  |  | 2657.5 |  |  | 2500.5 |  |  | 2541.5 |  |  | 2575.5 |  |  | 2636.5 |  |  | 2618.5 |  |  | 2511.5 |  |  | 2577 |  |  | 2698.5 |  |  | 2685.5 |  |  | 2690.5 |  |  | 2703.5 |  |  | 2587.5 |  |  | 2659.5 |  |  | 2795.5 |  |  | 2651.5 |  |  | 2854.5 |  |  | 2789.5 |  |  | 2546.5 |  |  | 2518.5 |  |  | 2655 |  |  | 2517.5 |  |  | 2636.5 |  |  | 2713 |  |  | 2575.5 |  |  | 2546.5 |  |  | 2627.5 |  |  | 2518.5 |  |  | 2856 |  |  | 2804.5 |  |  | 2559.5 |  |  | 2557.5 |  |  | 2780.5 |  |  | 2607 |  |  | 2628.5 |  |  | 2756.5 |  |  | 2566.5 |  |  | 2733.5 |  |  | 2552.5 |  |  | 2531.5 |  |  | 2720.5 |  |  | 2609.5 |  |  | 2648.5 |  |  | 2680.5 |  |  | 2722.5 |  |  | 2702 |  |  | 2655.5 |  |  | 2624.5 |  |  | 2699.5 |  |  | 2796.5 |  |  | 2586.5 |  |  | 2609.5 |  |  | 2670 |  |  | 2759.5 |  |  | 2567 |  |  | 2533.5 |  |  | 2725.5 |  |  | 2712.5 |  |  | 2606 |  |  | 2560 |  |  | 2709.5 |  |  | 2743.5 |  |  | 2436.5 |  |  | 2830.5 |  |  | 2617.5 |  |  | 2706.5 |  |  | 2597.5 |  |  | 2776.5 |  |  | 2593.5 |  |  | 2822.5 |  |  | 2640.5 |  |  | 2709.5 |  |  | 2522.5 |  |  | 2717.5 |  |  | 2777.5 |  |  | 2660.5 |  |  | 2631.5 |  |  | 2643.5 |  |  | 2594.5 |  |  | 2592.5 |  |  | 2704.5 |  |  | 2727.5 |  |  | 2618 |  |  | 2723.5 |  |  | 2622.5 |  |  | 2721.5 |  |  | 2647 |  |  | 2719.5 |  |  | 2608.5 |  |  | 2760.5 |  |  | 2694.5 |  |  | 2672 |  |  | 2527.5 |  |  | 2497.5 |  |  | 2582 |  |  | 2628 |  |  | 2631 |  |  | 2690.5 |  |  | 2602.5 |  |  | 2735.5 |  |  | 2841.5 |  |  | 2758 |  |  | 2651.5 |  |  | 2657.5 |  |  | 2559 |  |  | 2598 |  |  | 2712.5 |  |  | 2705.5 |  |  | 2769 |  |  | 2693.5 |  |  | 2743 |  |  | 2580.5 |  |  | 2642.5 |  |  | 2714 |  |  | 2745.5 |  |  | 2671.5 |  |  | 2508.5 |  |  | 2764 |  |  | 2558.5 |  |  | 2550.5 |  |  | 2604.5 |  |  | 2607.5 |  |  | 2686.5 |  |  | 2706.5 |  |  | 2620.5 |  |  | 2717.5 |  |  | 2707.5 |  |  | 2619.5 |  |  | 2611 |  |  | 2629.5 |  |  | 2678.5 |  |  | 2739.5 |  |  | 2738.5 |  |  | 2626.5 |  |  | 2662.5 |  |  | 2710.5 |  |  | 2600.5 |  |  | 2767 |  |  | 2591.5 |  |  | 2604 |  |  | 2928.5 |  |  | 2808.5 |  |  | 2852.5 |  |  | 2588.5 |  |  | 2582.5 |  |  | 2678.5 |  |  | 2493.5 |  |  | 2720.5 |  |  | 2725 |  |  | 2588.5 |  |  | 2698 |  |  | 2533.5 |  |  | 2578.5 |  |  | 2619.5 |  |  | 2716 |  |  | 2621.5 |  |  | 2665.5 |  |  | 2436 |  |  | 2614.5 |  |  | 2629 |  |  | 2671.5 |  |  | 2543.5 |  |  | 2585.5 |  |  | 2661 |  |  | 2781.5 |  |  | 2902.5 |  |  | 2488 |  |  | 2819.5 |  |  | 2657.5 |  |  | 2715 |  |  | 2649.5 |  |  | 2839.5 |  |  | 2755.5 |  |  | 2765.5 |  |  | 2587.5 |  |  | 2811.5 |  |  | 2553.5 |  |  | 2609.5 |  |  | 2578.5 |  |  | 2596.5 |  |  | 2828.5 |  |  | 2768 |  |  | 2693 |  |  | 2772.5 |  |  | 2645.5 |  |  | 2679
91 |  | 2644.5 |  |  | 2728.5 |  |  | 2744 |  |  | 2608.5 |  |  | 2841.5 |  |  | 2722.5 |  |  | 2761.5 |  |  | 2722.5 |  |  | 2684.5 |  |  | 2700.5 |  |  | 2570 |  |  | 2732.5 |  |  | 2701.5 |  |  | 2567.5 |  |  | 2602 |  |  | 2681.5 |  |  | 2764.5 |  |  | 2646.5 |  |  | 2778.5 |  |  | 2570.5 |  |  | 2836.5 |  |  | 2730.5 |  |  | 2821.5 |  |  | 2631.5 |  |  | 2456 |  |  | 2815.5 |  |  | 2667.5 |  |  | 2667.5 |  |  | 2723.5 |  |  | 2525 |  |  | 2700 |  |  | 2803.5 |  |  | 2491.5 |  |  | 2673.5 |  |  | 2591.5 |  |  | 2724 |  |  | 2609.5 |  |  | 2859 |  |  | 2675.5 |  |  | 2670.5 |  |  | 2465.5 |  |  | 2744.5 |  |  | 2547.5 |  |  | 2689 |  |  | 2851.5 |  |  | 2802 |  |  | 2715.5 |  |  | 2763.5 |  |  | 2833.5 |  |  | 2727.5 |  |  | 2565.5 |  |  | 2755.5 |  |  | 2676.5 |  |  | 2648.5 |  |  | 2746.5 |  |  | 2699.5 |  |  | 2582.5 |  |  | 2679 |  |  | 2694.5 |  |  | 2695.5 |  |  | 2654 |  |  | 2705.5 |  |  | 2819.5 |  |  | 2670.5 |  |  | 2590.5 |  |  | 2716 |  |  | 2831.5 |  |  | 2554 |  |  | 2540.5 |  |  | 2726.5 |  |  | 2652 |  |  | 2593.5 |  |  | 2690.5 |  |  | 2824.5 |  |  | 2796 |  |  | 2763 |  |  | 2511.5 |  |  | 2626.5 |  |  | 2628.5 |  |  | 2670.5 |  |  | 2685 |  |  | 2733.5 |  |  | 2740.5 |  |  | 2710.5 |  |  | 2772.5 |  |  | 2566.5 |  |  | 2742.5 |  |  | 2705.5 |  |  | 2685.5 |  |  | 2649.5 |  |  | 2705.5 |  |  | 2709 |  |  | 2625.5 |  |  | 2532 |  |  | 2619 |  |  | 2576 |  |  | 2859.5 |  |  | 2780.5 |  |  | 2578.5 |  |  | 2897.5 |  |  | 2612.5 |  |  | 2623 |  |  | 2666 |  |  | 2693.5 |  |  | 2704.5 |  |  | 2602.5 |  |  | 2696.5 |  |  | 2784.5 |  |  | 2787.5 |  |  | 2828.5 |  |  | 2816.5 |  |  | 2761.5 |  |  | 2640.5 |  |  | 2717.5 |  |  | 2726.5 |  |  | 2714.5 |  |  | 2808.5 |  |  | 2635.5 |  |  | 2709.5 |  |  | 2675.5 |  |  | 2738.5 |  |  | 2726.5 |  |  | 2763.5 |  |  | 2701.5 |  |  | 2713.5 |  |  | 2657 |  |  | 2630.5 |  |  | 2684.5 |  |  | 2624.5 |  |  | 2706.5 |  |  | 2766.5 |  |  | 2670 |  |  | 2607.5 |  |  | 2803.5 |  |  | 2664.5 |  |  | 2625.5 |  |  | 2725 |  |  | 2708.5 |  |  | 2782.5 |  |  | 2556 |  |  | 2761.5 |  |  | 2457 |  |  | 2786 |  |  | 2836.5 |  |  | 2704 |  |  | 2841.5 |  |  | 2654.5 |  |  | 2693.5 |  |  | 2627.5 |  |  | 2700.5 |  |  | 2729.5 |  |  | 2680.5 |  |  | 2744.5 |  |  | 2817.5 |  |  | 2700.5 |  |  | 2790 |  |  | 2583.5 |  |  | 2540 |  |  | 2679.5 |  |  | 2687.5 |  |  | 2621 |  |  | 2679.5 |  |  | 2653.5 |  |  | 2603.5 |  |  | 2567 |  |  | 2673.5 |  |  | 2482.5 |  |  | 2604.5 |  |  | 2771.5 |  |  | 2651.5 |  |  | 2631.5 |  |  | 2620 |  |  | 2700.5 |  |  | 2655.5 |  |  | 2594.5 |  |  | 2741.5 |  |  | 2726.5 |  |  | 2742.5 |  |  | 2626.5 |  |  | 2795 |  |  | 2722.5 |  |  | 2677.5 |  |  | 2727.5 |  |  | 2742.5 |  |  | 2631.5 |  |  | 2762.5 |  |  | 2765.5 |  |  | 2679.5 |  |  | 2853.5 |  |  | 2581.5 |  |  | 2751.5 |  |  | 2489.5 |  |  | 2526.5 |  |  | 2561 |  |  | 2605.5 |  |  | 2717.5 |  |  | 2717.5 |  |  | 2746.5 |  |  | 2764.5 |  |  | 2831.5 |  |  | 2801.5 |  |  | 2684.5 |  |  | 2738.5 |  |  | 2675.5 |  |  | 2591.5 |  |  | 2829.5 |  |  | 2677.5 |  |  | 2661.5 |  |  | 2650.5 |  |  | 2684.5 |  |  | 2704 |  |  | 2862.5 |  |  | 2692.5 |  |  | 2424 |  |  | 2813.5 |  |  | 2826 |  |  | 2465.5 |  |  | 2718.5 |  |  | 2766.5 |  |  | 2821.5 |  |  | 2609.5 |  |  | 2625.5 |  |  | 2660.5 |  |  | 2533.5 |  |  | 2551 |  |  | 2531.5 |  |  | 2501.5 |  |  | 2738.5 |  |  | 2602.5 |  |  | 2682 |  |  | 2682.5 |  |  | 2640.5 |  |  | 2798.5 |  |  | 2647.5 |  |  | 2759.5 |  |  | 2725.5 |  |  | 2705.5 |  |  | 2820.5 |  |  | 2804 |  |  | 2714 |  |  | 2627.5 |  |  | 2571.5 |  |  | 2736.5 |  |  | 2625 |  |  | 2837.5 |  |  | 2695.5 |  |  | 2672.5 |  |  | 2523 |  |  | 2833.5 |  |  | 2670.5 |  |  | 2510.5 |  |  | 2629.5 |  |  | 2689.5 |  |  | 2730.5 |  |  | 2801.5 |  |  | 2706.5 |  |  | 2776.5 |  |  | 2471 |  |  | 2562.5 |  |  | 2728.5 |  |  | 2697.5 |  |  | 2671.5 |  |  | 2612.5 |  |  | 2850 |  |  | 2552.5 |  |  | 2820.5 |  |  | 2733 |  |  | 2811.5 |  |  | 2687.5 |  |  | 2908 |  |  | 2743.5 |  |  | 2764.5 |  |  | 2841.5 |  |  | 2617.5 |  |  | 2670 |  |  | 2684 |  |  | 2682.5 |  |  | 2561.5 |  |  | 2762.5 |  |  | 2608.5 |  |  | 2868.5 |  |  | 2741.5 |  |  | 2701 |  |  | 2602.5 |  |  | 2540.5 |  |  | 2621 |  |  | 2650.5 |  |  | 2485.5 |  |  | 2711 |  |  | 2724.5 |  |  | 2619.5 |  |  | 2705.5 |  |  | 2725 |  |  | 2694.5 |  |  | 2658 |  |  | 2826.5 |  |  | 2583.5 |  |  | 2709.5 |  |  | 2608 |  |  | 2615.5 |  |  | 2804.5 |  |  | 2752.5 |  |  | 2722 |  |  | 2636.5 |  |  | 2529.5 |  |  | 2824.5 |  |  | 2854.5 |  |  | 2693.5 |  |  | 2741 |  |  | 2599.5 |  |  | 2824.5 |  |  | 2694.5 |  |  | 2672 |  |  | 2688 |  |  | 2846.5 |  |  | 2567.5 |  |  | 2489.5 |  |  | 2746.5 |  |  | 2690.5 |  |  | 2652.5 |  |  | 2747.5 |  |  | 2759.5 |  |  | 2619.5 |  |  | 2731.5 |  |  | 2707 |  |  | 2636.5 |  |  | 2695.5 |  |  | 2893.5 |  |  | 2881.5 |  |  | 2715 |  |  | 2649.5 |  |  | 2793.5 |  |  | 2707.5 |  |  | 2526.5 |  |  | 2834.5 |  |  | 2507 |  |  | 2754 |  |  | 2573 |  |  | 2773 |  |  | 2608.5 |  |  | 2655 |  |  | 2707.5 |  |  | 2673 |  |  | 2650.5 |  |  | 2782.5 |  |  | 2656.5 |  |  | 2657.5 |  |  | 2600.5 |  |  | 2698 |  |  | 2700.5 |  |  | 2847.5 |  |  | 2645.5 |  |  | 2700 |  |  | 2821.5 |  |  | 2586.5 |  |  | 2724.5 |  |  | 2734 |  |  | 2611.5 |  |  | 2587.5 |  |  | 2762.5 |  |  | 2579.5 |  |  | 2749.5 |  |  | 2595.5 |  |  | 2779.5 |  |  | 2677.5 |  |  | 2736.5 |  |  | 2525.5 |  |  | 2675 |  |  | 2578.5 |  |  | 2663.5 |  |  | 2591.5 |  |  | 2747.5 |  |  | 2830.5 |  |  | 2685 |  |  | 2757.5 |  |  | 2813 |  |  | 2690 |  |  | 2569.5 |  |  | 2761.5 |  |  | 2580.5 |  |  | 2693 |  |  | 2713.5 |  |  | 2703.5 |  |  | 2682.5 |  |  | 2528 |  |  | 2615.5 |  |  | 2508.5 |  |  | 2607.5 |  |  | 2522.5 |  |  | 2649.5 |  |  | 2631 |  |  | 2571.5 |  |  | 2723 |  |  | 2689.5 |  |  | 2504.5 |  |  | 2667.5 |  |  | 2671 |  |  | 2620.5 |  |  | 2621 |  |  | 2610 |  |  | 2688.5 |  |  | 2549.5 |  |  | 2585.5 |  |  | 2836.5 |  |  | 2881 |  |  | 2770.5 |  |  | 2667.5 |  |  | 2509.5 |  |  | 2653 |  |  | 2742.5 |  |  | 2625.5 |  |  | 2408.5 |  |  | 2713.5 |  |  | 2846 |  |  | 2576.5 |  |  | 2586.5 |  |  | 2665.5 |  |  | 2734.5 |  |  | 2741.5 |  |  | 2726.5 |  |  | 2761 |  |  | 2606.5 |  |  | 2617.5 |  |  | 2693 |  |  | 2569.5 |  |  | 2544.5 |  |  | 2720.5 |  |  | 2685 |  |  | 2744.5 |  |  | 2725.5 |  |  | 2635.5 |  |  | 2654.5 |  |  | 2723.5 |  |  | 2643 |  |  | 2596 |  |  | 2698.5 |  |  | 2731.5 |  |  | 2712.5 |  |  | 2508.5 |  |  | 2466 |  |  | 2770 |  |  | 2654 |  |  | 2795.5 |  |  | 2627 |  |  | 2711.5 |  |  | 2802.5 |  |  | 2794 |  |  | 2512.5 |  |  | 2704.5 |  |  | 2615.5 |  |  | 2741.5 |  |  | 2398.5 |  |  | 2655 |  |  | 2763 |  |  | 2580.5 |  |  | 2755.5 |  |  | 2574 |  |  | 2592.5 |  |  | 2699.5 |  |  | 2626 |  |  | 2819.5 |  |  | 2835.5 |  |  | 2599 |  |  | 2756.5 |  |  | 2738.5 |  |  | 2797 |  |  | 2609.5 |  |  | 2556 |  |  | 2838.5 |  |  | 2840 |  |  | 2587.5 |  |  | 2592.5 |  |  | 2623.5 |  |  | 2667.5 |  |  | 2695.5 |  |  | 2554.5 |  |  | 2698 |  |  | 2565.5 |  |  | 2736.5 |  |  | 2616.5 |  |  | 2651.5 |  |  | 2689.5 |  |  | 2606 |  |  | 2640.5 |  |  | 2692 |  |  | 2745.5 |  |  | 2505.5 |  |  | 2748.5 |  |  | 2740.5 |  |  | 2725.5 |  |  | 2647.5 |  |  | 2566.5 |  |  | 2739.5 |  |  | 2526.5 |  |  | 2627 |  |  | 2713.5 |  |  | 2613 |  |  | 2727 |  |  | 2705.5 |  |  | 2441 |  |  | 2543.5 |  |  | 2727.5 |  |  | 2772.5 |  |  | 2710.5 |  |  | 2780.5 |  |  | 2691.5 |  |  | 2763.5 |  |  | 2634 |  |  | 2822 |  |  | 2556.5 |  |  | 2715.5 |  |  | 2695 |  |  | 2650.5 |  |  | 2595.5 |  |  | 2619.5 |  |  | 2594.5 |  |  | 2644.5 |  |  | 2558 |  |  | 2684.5 |  |  | 2625.5 |  |  | 2624.5 |  |  | 2653 |  |  | 2717.5 |  |  | 2762.5 |  |  | 2735.5 |  |  | 2923.5 |  |  | 2718.5 |  |  | 2593.5 |  |  | 2754.5 |  |  | 2278.5 |  |  | 2665.5 |  |  | 2622 |  |  | 2825.5 |  |  | 2712.5 |  |  | 2773.5 |  |  | 2536.5 |  |  | 2679.5 |  |  | 2554.5 |  |  | 2532.5 |  |  | 2533 |  |  | 2579.5 |  |  | 2666.5 |  |  | 2604.5 |  |  | 2669 |  |  | 2712.5 |  |  | 2548 |  |  | 2553.5 |  |  | 2662.5 |  |  | 2627.5 |  |  | 2696 |  |  | 2474.5 |  |  | 2690 |  |  | 2699 |  |  | 2717.5 |  |  | 2658 |  |  | 2812 |  |  | 2763.5 |  |  | 2804.5 |  |  | 2557.5 |  |  | 2749 |  |  | 2676.5 |  |  | 2552.5 |  |  | 2516.5 |  |  | 2773.5 |  |  | 2613.5 |  |  | 2681.5 |  |  | 2665.5 |  |  | 2702.5 |  |  | 2609 |  |  | 2824.5 |  |  | 2599 |  |  | 2724.5 |  |  | 2584.5 |  |  | 2780.5 |  |  | 2680 |  |  | 2728 |  |  | 2836 |  |  | 2744.5 |  |  | 2684 |  |  | 2705.5 |  |  | 2861.5 |  |  | 2694.5 |  |  | 2643.5 |  |  | 2550.5 |  |  | 2783.5 |  |  | 2784.5 |  |  | 2735.5 |  |  | 2685 |  |  | 2517.5 |  |  | 2569.5 |  |  | 2689.5 |  |  | 2691.5 |  |  | 2586 |  |  | 2691.5 |  |  | 2678 |  |  | 2666.5 |  |  | 2657.5 |  |  | 2626.5 |  |  | 2517.5 |  |  | 2525 |  |  | 2658.5 |  |  | 2446 |  |  | 2607.5 |  |  | 2748.5 |  |  | 2842.5 |  |  | 2636.5 |  |  | 2647.5 |  |  | 2768.5 |  |  | 2626.5 |  |  | 2705.5 |  |  | 2605.5 |  |  | 2553 |  |  | 2671.5 |  |  | 2663.5 |  |  | 2652.5 |  |  | 2721.5 |  |  | 2721.5 |  |  | 2631 |  |  | 2590 |  |  | 2675.5 |  |  | 2606 |  |  | 2833.5 |  |  | 2597.5 |  |  | 2781.5 |  |  | 2669.5 |  |  | 2585.5 |  |  | 2759.5 |  |  | 2701.5 |  |  | 2732.5 |  |  | 2726 |  |  | 2720.5 |  |  | 2878.5 |  |  | 2625.5 |  |  | 2506 |  |  | 2715.5 |  |  | 2565.5 |  |  | 2818 |  |  | 2659 |  |  | 2655.5 |  |  | 2623 |  |  | 2556 |  |  | 2539.5 |  |  | 2801 |  |  | 2889.5 |  |  | 2630.5 |  |  | 2786.5 |  |  | 2605.5 |  |  | 2543.5 |  |  | 2699.5 |  |  | 2468.5 |  |  | 2593.5 |  |  | 2737.5 |  |  | 2592.5 |  |  | 2593 |  |  | 2634 |  |  | 2732.5 |  |  | 2785.5 |  |  | 2603.5 |  |  | 2753.5 |  |  | 2654.5 |  |  | 2746.5 |  |  | 2682.5 |  |  | 2567.5 |  |  | 2937 |  |  | 2593.5 |  |  | 2639 |  |  | 2588.5 |  |  | 2772.5 |  |  | 2748.5 |  |  | 2807 |  |  | 2669.5 |  |  | 2620.5 |  |  | 2708 |  |  | 2748.5 |  |  | 2674.5 |  |  | 2804.5 |  |  | 2666.5 |  |  | 2638.5 |  |  | 2709.5 |  |  | 2759 |  |  | 2583.5 |  |  | 2667.5 |  |  | 2836.5 |  |  | 2747.5 |  |  | 2695 |  |  | 2649.5 |  |  | 2841.5 |  |  | 2639 |  |  | 2666.5 |  |  | 2756.5 |  |  | 2699 |  |  | 2738.5 |  |  | 2789.5 |  |  | 2650.5 |  |  | 2571 |  |  | 2535.5 |  |  | 2652.5 |  |  | 2591 |  |  | 2715.5 |  |  | 2692.5 |  |  | 2716.5 |  |  | 2518.5 |  |  | 2657.5 |  |  | 2850.5 |  |  | 2604.5 |  |  | 2648 |  |  | 2567 |  |  | 2513.5 |  |  | 2739.5 |  |  | 2549.5 |  |  | 2805 |  |  | 2814.5 |  |  | 2619.5 |  |  | 2663.5 |  |  | 2486.5 |  |  | 2713.5 |  |  | 2715.5 |  |  | 2622.5 |  |  | 2746.5 |  |  | 2463.5 |  |  | 2687 |  |  | 2655.5 |  |  | 2470.5 |  |  | 2674.5 |  |  | 2650.5 |  |  | 2851.5 |  |  | 2730.5 |  |  | 2679.5 |  |  | 2650.5 |  |  | 2505.5 |  |  | 2809.5 |  |  | 2649.5 |  |  | 2557.5 |  |  | 2672.5 |  |  | 2827 |  |  | 2707.5 |  |  | 2793.5 |  |  | 2617 |  |  | 2726.5 |  |  | 2738.5 |  |  | 2780 |  |  | 2700.5 |  |  | 2747.5 |  |  | 2862.5 |  |  | 2868 |  |  | 2606.5 |  |  | 2760.5 |  |  | 2632.5 |  |  | 2451.5 |  |  | 2769.5 |  |  | 2615 |  |  | 2611.5 |  |  | 2748 |  |  | 2715 |  |  | 2728.5 |  |  | 2674.5 |  |  | 2568.5 |  |  | 2423.5 |  |  | 2626.5 |  |  | 2807.5 |  |  | 2648 |  |  | 2635.5 |  |  | 2644 |  |  | 2677.5 |  |  | 2706 |  |  | 2545 |  |  | 2740 |  |  | 2778.5 |  |  | 2577 |  |  | 2832.5 |  |  | 2717.5 |  |  | 2673.5 |  |  | 2873.5 |  |  | 2474.5 |  |  | 2787 |  |  | 2650.5 |  |  | 2714.5 |  |  | 2926.5 |  |  | 2657 |  |  | 2649.5 |  |  | 2653.5 |  |  | 2696.5 |  |  | 2803.5 |  |  | 2634 |  |  | 2766 |  |  | 2612 |  |  | 2640.5 |  |  | 2822 |  |  | 2704 |  |  | 2820.5 |  |  | 2575.5 |  |  | 2579.5 |  |  | 2669.5 |  |  | 2760.5 |  |  | 2697.5 |  |  | 2730.5 |  |  | 2677.5 |  |  | 2622.5 |  |  | 2605 |  |  | 2625.5 |  |  | 2549 |  |  | 2702.5 |  |  | 2658.5 |  |  | 2736.5 |  |  | 2719.5 |  |  | 2815 |  |  | 2694.5 |  |  | 2654 |  |  | 2582.5 |  |  | 2733.5 |  |  | 2514 |  |  | 2663 |  |  | 2760.5 |  |  | 2755 |  |  | 2704.5 |  |  | 2547.5 |  |  | 2570.5 |  |  | 2604.5 |  |  | 2683.5 |  |  | 2665.5 |  |  | 2558.5 |  |  | 2601 |  |  | 2713.5 |  |  | 2714.5 |  |  | 2705.5 |  |  | 2742.5 |  |  | 2608.5 |  |  | 2685.5 |  |  | 2834.5 |  |  | 2675.5 |  |  | 2878.5 |  |  | 2818.5 |  |  | 2567.5 |  |  | 2539.5 |  |  | 2702 |  |  | 2556.5 |  |  | 2675.5 |  |  | 2752 |  |  | 2604.5 |  |  | 2575.5 |  |  | 2642.5 |  |  | 2542.5 |  |  | 2903 |  |  | 2833.5 |  |  | 2583.5 |  |  | 2586.5 |  |  | 2804.5 |  |  | 2631 |  |  | 2657.5 |  |  | 2795.5 |  |  | 2595.5 |  |  | 2772.5 |  |  | 2581.5 |  |  | 2570.5 |  |  | 2759.5 |  |  | 2624.5 |  |  | 2663.5 |  |  | 2704.5 |  |  | 2761.5 |  |  | 2741 |  |  | 2694.5 |  |  | 2671.5 |  |  | 2720.5 |  |  | 2822.5 |  |  | 2615.5 |  |  | 2630.5 |  |  | 2694 |  |  | 2798.5 |  |  | 2588 |  |  | 2559.5 |  |  | 2772.5 |  |  | 2751.5 |  |  | 2645 |  |  | 2589 |  |  | 2748.5 |  |  | 2764.5 |  |  | 2457.5 |  |  | 2845.5 |  |  | 2641.5 |  |  | 2753.5 |  |  | 2623.5 |  |  | 2800.5 |  |  | 2617.5 |  |  | 2869.5 |  |  | 2661.5 |  |  | 2735.5 |  |  | 2569.5 |  |  | 2746.5 |  |  | 2816.5 |  |  | 2686.5 |  |  | 2657.5 |  |  | 2664.5 |  |  | 2633.5 |  |  | 2616.5 |  |  | 2751.5 |  |  | 2766.5 |  |  | 2647 |  |  | 2762.5 |  |  | 2669.5 |  |  | 2747.5 |  |  | 2694 |  |  | 2745.5 |  |  | 2647.5 |  |  | 2775.5 |  |  | 2733.5 |  |  | 2701 |  |  | 2566.5 |  |  | 2523.5 |  |  | 2621 |  |  | 2643 |  |  | 2655 |  |  | 2729.5 |  |  | 2641.5 |  |  | 2756.5 |  |  | 2880.5 |  |  | 2805 |  |  | 2675.5 |  |  | 2704.5 |  |  | 2580 |  |  | 2619 |  |  | 2738.5 |  |  | 2731.5 |  |  | 2793 |  |  | 2732.5 |  |  | 2782 |  |  | 2619.5 |  |  | 2681.5 |  |  | 2753 |  |  | 2792.5 |  |  | 2700.5 |  |  | 2532.5 |  |  | 2785 |  |  | 2597.5 |  |  | 2565.5 |  |  | 2643.5 |  |  | 2631.5 |  |  | 2715.5 |  |  | 2745.5 |  |  | 2667.5 |  |  | 2756.5 |  |  | 2754.5 |  |  | 2666.5 |  |  | 2632 |  |  | 2650.5 |  |  | 2707.5 |  |  | 2765.5 |  |  | 2753.5 |  |  | 2673.5 |  |  | 2701.5 |  |  | 2731.5 |  |  | 2626.5 |  |  | 2782 |  |  | 2638.5 |  |  | 2643 |  |  | 2949.5 |  |  | 2847.5 |  |  | 2867.5 |  |  | 2627.5 |  |  | 2603.5 |  |  | 2693.5 |  |  | 2519.5 |  |  | 2735.5 |  |  | 2764 |  |  | 2609.5 |  |  | 2713 |  |  | 2572.5 |  |  | 2617.5 |  |  | 2658.5 |  |  | 2731 |  |  | 2636.5 |  |  | 2680.5 |  |  | 2483 |  |  | 2638.5 |  |  | 2676 |  |  | 2718.5 |  |  | 2582.5 |  |  | 2632.5 |  |  | 2690 |  |  | 2810.5 |  |  | 2941.5 |  |  | 2527 |  |  | 2866.5 |  |  | 2672.5 |  |  | 2736 |  |  | 2688.5 |  |  | 2865.5 |  |  | 2794.5 |  |  | 2812.5 |  |  | 2613.5 |  |  | 2850.5 |  |  | 2579.5 |  |  | 2656.5 |  |  | 2617.5 |  |  | 2622.5 |  |  | 2843.5 |  |  | 2794 |  |  | 2732 |  |  | 2801.5 |  |  | 2692.5 |  |  | 2700
92 |  | 2683.5 |  |  | 2743.5 |  |  | 2791 |  |  | 2647.5 |  |  | 2870.5 |  |  | 2769.5 |  |  | 2790.5 |  |  | 2751.5 |  |  | 2708.5 |  |  | 2724.5 |  |  | 2585 |  |  | 2758.5 |  |  | 2722.5 |  |  | 2606.5 |  |  | 2628 |  |  | 2710.5 |  |  | 2803.5 |  |  | 2661.5 |  |  | 2825.5 |  |  | 2609.5 |  |  | 2875.5 |  |  | 2751.5 |  |  | 2836.5 |  |  | 2670.5 |  |  | 2482 |  |  | 2830.5 |  |  | 2706.5 |  |  | 2706.5 |  |  | 2747.5 |  |  | 2572 |  |  | 2724 |  |  | 2832.5 |  |  | 2517.5 |  |  | 2697.5 |  |  | 2615.5 |  |  | 2750 |  |  | 2633.5 |  |  | 2906 |  |  | 2714.5 |  |  | 2709.5 |  |  | 2504.5 |  |  | 2773.5 |  |  | 2571.5 |  |  | 2728 |  |  | 2866.5 |  |  | 2841 |  |  | 2744.5 |  |  | 2784.5 |  |  | 2862.5 |  |  | 2774.5 |  |  | 2586.5 |  |  | 2802.5 |  |  | 2702.5 |  |  | 2674.5 |  |  | 2785.5 |  |  | 2720.5 |  |  | 2629.5 |  |  | 2703 |  |  | 2718.5 |  |  | 2742.5 |  |  | 2680 |  |  | 2744.5 |  |  | 2840.5 |  |  | 2709.5 |  |  | 2614.5 |  |  | 2745 |  |  | 2857.5 |  |  | 2593 |  |  | 2564.5 |  |  | 2752.5 |  |  | 2673 |  |  | 2619.5 |  |  | 2729.5 |  |  | 2871.5 |  |  | 2822 |  |  | 2787 |  |  | 2537.5 |  |  | 2665.5 |  |  | 2652.5 |  |  | 2696.5 |  |  | 2732 |  |  | 2772.5 |  |  | 2779.5 |  |  | 2739.5 |  |  | 2793.5 |  |  | 2587.5 |  |  | 2781.5 |  |  | 2731.5 |  |  | 2706.5 |  |  | 2688.5 |  |  | 2744.5 |  |  | 2738 |  |  | 2672.5 |  |  | 2553 |  |  | 2658 |  |  | 2591 |  |  | 2883.5 |  |  | 2804.5 |  |  | 2617.5 |  |  | 2918.5 |  |  | 2633.5 |  |  | 2638 |  |  | 2681 |  |  | 2719.5 |  |  | 2719.5 |  |  | 2626.5 |  |  | 2711.5 |  |  | 2799.5 |  |  | 2802.5 |  |  | 2867.5 |  |  | 2831.5 |  |  | 2808.5 |  |  | 2661.5 |  |  | 2746.5 |  |  | 2752.5 |  |  | 2753.5 |  |  | 2834.5 |  |  | 2674.5 |  |  | 2735.5 |  |  | 2701.5 |  |  | 2759.5 |  |  | 2773.5 |  |  | 2810.5 |  |  | 2727.5 |  |  | 2737.5 |  |  | 2681 |  |  | 2677.5 |  |  | 2705.5 |  |  | 2671.5 |  |  | 2730.5 |  |  | 2781.5 |  |  | 2699 |  |  | 2646.5 |  |  | 2824.5 |  |  | 2711.5 |  |  | 2640.5 |  |  | 2751 |  |  | 2734.5 |  |  | 2811.5 |  |  | 2585 |  |  | 2790.5 |  |  | 2481 |  |  | 2815 |  |  | 2865.5 |  |  | 2728 |  |  | 2880.5 |  |  | 2701.5 |  |  | 2732.5 |  |  | 2666.5 |  |  | 2724.5 |  |  | 2753.5 |  |  | 2727.5 |  |  | 2768.5 |  |  | 2832.5 |  |  | 2724.5 |  |  | 2837 |  |  | 2604.5 |  |  | 2561 |  |  | 2726.5 |  |  | 2711.5 |  |  | 2660 |  |  | 2726.5 |  |  | 2692.5 |  |  | 2642.5 |  |  | 2593 |  |  | 2699.5 |  |  | 2521.5 |  |  | 2651.5 |  |  | 2810.5 |  |  | 2677.5 |  |  | 2660.5 |  |  | 2646 |  |  | 2715.5 |  |  | 2676.5 |  |  | 2623.5 |  |  | 2788.5 |  |  | 2741.5 |  |  | 2781.5 |  |  | 2665.5 |  |  | 2819 |  |  | 2748.5 |  |  | 2706.5 |  |  | 2742.5 |  |  | 2781.5 |  |  | 2660.5 |  |  | 2801.5 |  |  | 2791.5 |  |  | 2708.5 |  |  | 2877.5 |  |  | 2596.5 |  |  | 2772.5 |  |  | 2518.5 |  |  | 2565.5 |  |  | 2576 |  |  | 2629.5 |  |  | 2741.5 |  |  | 2764.5 |  |  | 2785.5 |  |  | 2811.5 |  |  | 2852.5 |  |  | 2840.5 |  |  | 2723.5 |  |  | 2762.5 |  |  | 2701.5 |  |  | 2638.5 |  |  | 2868.5 |  |  | 2724.5 |  |  | 2687.5 |  |  | 2676.5 |  |  | 2723.5 |  |  | 2730 |  |  | 2886.5 |  |  | 2718.5 |  |  | 2471 |  |  | 2828.5 |  |  | 2850 |  |  | 2504.5 |  |  | 2733.5 |  |  | 2813.5 |  |  | 2845.5 |  |  | 2648.5 |  |  | 2640.5 |  |  | 2681.5 |  |  | 2572.5 |  |  | 2572 |  |  | 2570.5 |  |  | 2516.5 |  |  | 2764.5 |  |  | 2623.5 |  |  | 2706 |  |  | 2697.5 |  |  | 2687.5 |  |  | 2824.5 |  |  | 2668.5 |  |  | 2774.5 |  |  | 2754.5 |  |  | 2734.5 |  |  | 2844.5 |  |  | 2851 |  |  | 2738 |  |  | 2653.5 |  |  | 2592.5 |  |  | 2762.5 |  |  | 2651 |  |  | 2876.5 |  |  | 2742.5 |  |  | 2719.5 |  |  | 2562 |  |  | 2857.5 |  |  | 2709.5 |  |  | 2525.5 |  |  | 2658.5 |  |  | 2728.5 |  |  | 2769.5 |  |  | 2827.5 |  |  | 2745.5 |  |  | 2805.5 |  |  | 2510 |  |  | 2591.5 |  |  | 2775.5 |  |  | 2721.5 |  |  | 2710.5 |  |  | 2636.5 |  |  | 2879 |  |  | 2578.5 |  |  | 2867.5 |  |  | 2780 |  |  | 2835.5 |  |  | 2708.5 |  |  | 2932 |  |  | 2767.5 |  |  | 2785.5 |  |  | 2870.5 |  |  | 2643.5 |  |  | 2694 |  |  | 2723 |  |  | 2729.5 |  |  | 2585.5 |  |  | 2777.5 |  |  | 2637.5 |  |  | 2894.5 |  |  | 2767.5 |  |  | 2748 |  |  | 2641.5 |  |  | 2561.5 |  |  | 2645 |  |  | 2697.5 |  |  | 2511.5 |  |  | 2732 |  |  | 2748.5 |  |  | 2645.5 |  |  | 2726.5 |  |  | 2772 |  |  | 2720.5 |  |  | 2687 |  |  | 2852.5 |  |  | 2604.5 |  |  | 2724.5 |  |  | 2647 |  |  | 2654.5 |  |  | 2828.5 |  |  | 2791.5 |  |  | 2761 |  |  | 2675.5 |  |  | 2550.5 |  |  | 2853.5 |  |  | 2901.5 |  |  | 2732.5 |  |  | 2780 |  |  | 2623.5 |  |  | 2848.5 |  |  | 2709.5 |  |  | 2698 |  |  | 2727 |  |  | 2872.5 |  |  | 2582.5 |  |  | 2513.5 |  |  | 2775.5 |  |  | 2719.5 |  |  | 2667.5 |  |  | 2771.5 |  |  | 2785.5 |  |  | 2648.5 |  |  | 2755.5 |  |  | 2733 |  |  | 2651.5 |  |  | 2710.5 |  |  | 2919.5 |  |  | 2896.5 |  |  | 2754 |  |  | 2664.5 |  |  | 2832.5 |  |  | 2754.5 |  |  | 2565.5 |  |  | 2873.5 |  |  | 2536 |  |  | 2793 |  |  | 2602 |  |  | 2799 |  |  | 2629.5 |  |  | 2681 |  |  | 2746.5 |  |  | 2702 |  |  | 2689.5 |  |  | 2803.5 |  |  | 2695.5 |  |  | 2672.5 |  |  | 2629.5 |  |  | 2745 |  |  | 2721.5 |  |  | 2886.5 |  |  | 2669.5 |  |  | 2726 |  |  | 2860.5 |  |  | 2615.5 |  |  | 2745.5 |  |  | 2758 |  |  | 2635.5 |  |  | 2626.5 |  |  | 2786.5 |  |  | 2626.5 |  |  | 2796.5 |  |  | 2610.5 |  |  | 2794.5 |  |  | 2706.5 |  |  | 2775.5 |  |  | 2549.5 |  |  | 2714 |  |  | 2625.5 |  |  | 2684.5 |  |  | 2638.5 |  |  | 2786.5 |  |  | 2859.5 |  |  | 2711 |  |  | 2796.5 |  |  | 2852 |  |  | 2729 |  |  | 2590.5 |  |  | 2800.5 |  |  | 2619.5 |  |  | 2717 |  |  | 2728.5 |  |  | 2742.5 |  |  | 2703.5 |  |  | 2549 |  |  | 2639.5 |  |  | 2547.5 |  |  | 2646.5 |  |  | 2569.5 |  |  | 2688.5 |  |  | 2660 |  |  | 2618.5 |  |  | 2749 |  |  | 2715.5 |  |  | 2543.5 |  |  | 2706.5 |  |  | 2695 |  |  | 2635.5 |  |  | 2642 |  |  | 2631 |  |  | 2727.5 |  |  | 2588.5 |  |  | 2624.5 |  |  | 2860.5 |  |  | 2920 |  |  | 2794.5 |  |  | 2706.5 |  |  | 2524.5 |  |  | 2674 |  |  | 2766.5 |  |  | 2649.5 |  |  | 2432.5 |  |  | 2760.5 |  |  | 2867 |  |  | 2600.5 |  |  | 2612.5 |  |  | 2680.5 |  |  | 2773.5 |  |  | 2788.5 |  |  | 2755.5 |  |  | 2787 |  |  | 2621.5 |  |  | 2656.5 |  |  | 2708 |  |  | 2590.5 |  |  | 2565.5 |  |  | 2744.5 |  |  | 2700 |  |  | 2791.5 |  |  | 2754.5 |  |  | 2650.5 |  |  | 2701.5 |  |  | 2762.5 |  |  | 2682 |  |  | 2622 |  |  | 2719.5 |  |  | 2760.5 |  |  | 2727.5 |  |  | 2534.5 |  |  | 2495 |  |  | 2817 |  |  | 2680 |  |  | 2834.5 |  |  | 2666 |  |  | 2732.5 |  |  | 2823.5 |  |  | 2818 |  |  | 2533.5 |  |  | 2730.5 |  |  | 2654.5 |  |  | 2762.5 |  |  | 2424.5 |  |  | 2681 |  |  | 2784 |  |  | 2619.5 |  |  | 2784.5 |  |  | 2589 |  |  | 2618.5 |  |  | 2738.5 |  |  | 2647 |  |  | 2858.5 |  |  | 2859.5 |  |  | 2625 |  |  | 2771.5 |  |  | 2762.5 |  |  | 2823 |  |  | 2656.5 |  |  | 2571 |  |  | 2877.5 |  |  | 2861 |  |  | 2626.5 |  |  | 2621.5 |  |  | 2647.5 |  |  | 2693.5 |  |  | 2710.5 |  |  | 2583.5 |  |  | 2722 |  |  | 2586.5 |  |  | 2751.5 |  |  | 2655.5 |  |  | 2666.5 |  |  | 2704.5 |  |  | 2632 |  |  | 2679.5 |  |  | 2731 |  |  | 2784.5 |  |  | 2529.5 |  |  | 2787.5 |  |  | 2787.5 |  |  | 2772.5 |  |  | 2673.5 |  |  | 2592.5 |  |  | 2786.5 |  |  | 2573.5 |  |  | 2642 |  |  | 2760.5 |  |  | 2637 |  |  | 2766 |  |  | 2744.5 |  |  | 2480 |  |  | 2582.5 |  |  | 2766.5 |  |  | 2801.5 |  |  | 2731.5 |  |  | 2827.5 |  |  | 2715.5 |  |  | 2787.5 |  |  | 2655 |  |  | 2869 |  |  | 2595.5 |  |  | 2744.5 |  |  | 2724 |  |  | 2697.5 |  |  | 2642.5 |  |  | 2658.5 |  |  | 2618.5 |  |  | 2673.5 |  |  | 2584 |  |  | 2723.5 |  |  | 2672.5 |  |  | 2653.5 |  |  | 2692 |  |  | 2738.5 |  |  | 2788.5 |  |  | 2774.5 |  |  | 2970.5 |  |  | 2739.5 |  |  | 2608.5 |  |  | 2775.5 |  |  | 2317.5 |  |  | 2689.5 |  |  | 2661 |  |  | 2851.5 |  |  | 2738.5 |  |  | 2802.5 |  |  | 2551.5 |  |  | 2718.5 |  |  | 2593.5 |  |  | 2558.5 |  |  | 2562 |  |  | 2626.5 |  |  | 2705.5 |  |  | 2619.5 |  |  | 2684 |  |  | 2751.5 |  |  | 2595 |  |  | 2574.5 |  |  | 2677.5 |  |  | 2642.5 |  |  | 2743 |  |  | 2513.5 |  |  | 2737 |  |  | 2738 |  |  | 2746.5 |  |  | 2673 |  |  | 2833 |  |  | 2787.5 |  |  | 2833.5 |  |  | 2578.5 |  |  | 2788 |  |  | 2715.5 |  |  | 2581.5 |  |  | 2537.5 |  |  | 2820.5 |  |  | 2642.5 |  |  | 2720.5 |  |  | 2686.5 |  |  | 2741.5 |  |  | 2624 |  |  | 2863.5 |  |  | 2638 |  |  | 2753.5 |  |  | 2631.5 |  |  | 2806.5 |  |  | 2709 |  |  | 2767 |  |  | 2875 |  |  | 2768.5 |  |  | 2713 |  |  | 2731.5 |  |  | 2900.5 |  |  | 2720.5 |  |  | 2690.5 |  |  | 2576.5 |  |  | 2812.5 |  |  | 2831.5 |  |  | 2761.5 |  |  | 2709 |  |  | 2556.5 |  |  | 2595.5 |  |  | 2718.5 |  |  | 2720.5 |  |  | 2625 |  |  | 2717.5 |  |  | 2699 |  |  | 2705.5 |  |  | 2681.5 |  |  | 2665.5 |  |  | 2564.5 |  |  | 2540 |  |  | 2697.5 |  |  | 2470 |  |  | 2646.5 |  |  | 2763.5 |  |  | 2881.5 |  |  | 2657.5 |  |  | 2662.5 |  |  | 2807.5 |  |  | 2655.5 |  |  | 2726.5 |  |  | 2652.5 |  |  | 2600 |  |  | 2695.5 |  |  | 2710.5 |  |  | 2676.5 |  |  | 2747.5 |  |  | 2760.5 |  |  | 2652 |  |  | 2605 |  |  | 2722.5 |  |  | 2632 |  |  | 2859.5 |  |  | 2636.5 |  |  | 2828.5 |  |  | 2698.5 |  |  | 2600.5 |  |  | 2798.5 |  |  | 2748.5 |  |  | 2747.5 |  |  | 2765 |  |  | 2735.5 |  |  | 2904.5 |  |  | 2654.5 |  |  | 2545 |  |  | 2730.5 |  |  | 2594.5 |  |  | 2857 |  |  | 2674 |  |  | 2694.5 |  |  | 2652 |  |  | 2582 |  |  | 2560.5 |  |  | 2840 |  |  | 2915.5 |  |  | 2645.5 |  |  | 2807.5 |  |  | 2620.5 |  |  | 2564.5 |  |  | 2723.5 |  |  | 2489.5 |  |  | 2632.5 |  |  | 2766.5 |  |  | 2631.5 |  |  | 2608 |  |  | 2649 |  |  | 2756.5 |  |  | 2832.5 |  |  | 2624.5 |  |  | 2800.5 |  |  | 2693.5 |  |  | 2785.5 |  |  | 2706.5 |  |  | 2588.5 |  |  | 2958 |  |  | 2622.5 |  |  | 2678 |  |  | 2627.5 |  |  | 2796.5 |  |  | 2772.5 |  |  | 2854 |  |  | 2708.5 |  |  | 2659.5 |  |  | 2737 |  |  | 2772.5 |  |  | 2700.5 |  |  | 2851.5 |  |  | 2681.5 |  |  | 2659.5 |  |  | 2733.5 |  |  | 2780 |  |  | 2598.5 |  |  | 2714.5 |  |  | 2883.5 |  |  | 2773.5 |  |  | 2734 |  |  | 2696.5 |  |  | 2870.5 |  |  | 2665 |  |  | 2692.5 |  |  | 2777.5 |  |  | 2723 |  |  | 2753.5 |  |  | 2828.5 |  |  | 2671.5 |  |  | 2618 |  |  | 2550.5 |  |  | 2673.5 |  |  | 2615 |  |  | 2762.5 |  |  | 2731.5 |  |  | 2742.5 |  |  | 2557.5 |  |  | 2686.5 |  |  | 2879.5 |  |  | 2630.5 |  |  | 2687 |  |  | 2588 |  |  | 2552.5 |  |  | 2768.5 |  |  | 2570.5 |  |  | 2826 |  |  | 2838.5 |  |  | 2658.5 |  |  | 2702.5 |  |  | 2512.5 |  |  | 2734.5 |  |  | 2754.5 |  |  | 2648.5 |  |  | 2767.5 |  |  | 2502.5 |  |  | 2734 |  |  | 2670.5 |  |  | 2496.5 |  |  | 2698.5 |  |  | 2697.5 |  |  | 2875.5 |  |  | 2745.5 |  |  | 2705.5 |  |  | 2697.5 |  |  | 2544.5 |  |  | 2856.5 |  |  | 2688.5 |  |  | 2581.5 |  |  | 2698.5 |  |  | 2848 |  |  | 2754.5 |  |  | 2822.5 |  |  | 2656 |  |  | 2755.5 |  |  | 2785.5 |  |  | 2795 |  |  | 2747.5 |  |  | 2786.5 |  |  | 2891.5 |  |  | 2897 |  |  | 2645.5 |  |  | 2786.5 |  |  | 2671.5 |  |  | 2480.5 |  |  | 2793.5 |  |  | 2630 |  |  | 2632.5 |  |  | 2763 |  |  | 2730 |  |  | 2775.5 |  |  | 2695.5 |  |  | 2607.5 |  |  | 2449.5 |  |  | 2650.5 |  |  | 2854.5 |  |  | 2672 |  |  | 2674.5 |  |  | 2668 |  |  | 2724.5 |  |  | 2745 |  |  | 2566 |  |  | 2755 |  |  | 2804.5 |  |  | 2616 |  |  | 2871.5 |  |  | 2756.5 |  |  | 2688.5 |  |  | 2912.5 |  |  | 2513.5 |  |  | 2802 |  |  | 2671.5 |  |  | 2729.5 |  |  | 2965.5 |  |  | 2704 |  |  | 2664.5 |  |  | 2668.5 |  |  | 2711.5 |  |  | 2842.5 |  |  | 2663 |  |  | 2781 |  |  | 2641 |  |  | 2687.5 |  |  | 2837 |  |  | 2719 |  |  | 2859.5 |  |  | 2622.5 |  |  | 2618.5 |  |  | 2690.5 |  |  | 2781.5 |  |  | 2712.5 |  |  | 2754.5 |  |  | 2716.5 |  |  | 2661.5 |  |  | 2644 |  |  | 2654.5 |  |  | 2596 |  |  | 2728.5 |  |  | 2679.5 |  |  | 2765.5 |  |  | 2748.5 |  |  | 2839 |  |  | 2733.5 |  |  | 2701 |  |  | 2603.5 |  |  | 2772.5 |  |  | 2561 |  |  | 2692 |  |  | 2784.5 |  |  | 2770 |  |  | 2728.5 |  |  | 2586.5 |  |  | 2617.5 |  |  | 2643.5 |  |  | 2709.5 |  |  | 2712.5 |  |  | 2573.5 |  |  | 2627 |  |  | 2742.5 |  |  | 2740.5 |  |  | 2752.5 |  |  | 2781.5 |  |  | 2632.5 |  |  | 2724.5 |  |  | 2849.5 |  |  | 2690.5 |  |  | 2893.5 |  |  | 2833.5 |  |  | 2614.5 |  |  | 2563.5 |  |  | 2726 |  |  | 2603.5 |  |  | 2714.5 |  |  | 2791 |  |  | 2625.5 |  |  | 2590.5 |  |  | 2681.5 |  |  | 2581.5 |  |  | 2950 |  |  | 2854.5 |  |  | 2609.5 |  |  | 2607.5 |  |  | 2843.5 |  |  | 2670 |  |  | 2681.5 |  |  | 2834.5 |  |  | 2634.5 |  |  | 2811.5 |  |  | 2596.5 |  |  | 2591.5 |  |  | 2806.5 |  |  | 2648.5 |  |  | 2710.5 |  |  | 2719.5 |  |  | 2785.5 |  |  | 2756 |  |  | 2733.5 |  |  | 2710.5 |  |  | 2744.5 |  |  | 2861.5 |  |  | 2636.5 |  |  | 2645.5 |  |  | 2715 |  |  | 2845.5 |  |  | 2612 |  |  | 2598.5 |  |  | 2796.5 |  |  | 2780.5 |  |  | 2684 |  |  | 2636 |  |  | 2774.5 |  |  | 2793.5 |  |  | 2496.5 |  |  | 2884.5 |  |  | 2667.5 |  |  | 2768.5 |  |  | 2652.5 |  |  | 2821.5 |  |  | 2643.5 |  |  | 2908.5 |  |  | 2708.5 |  |  | 2750.5 |  |  | 2608.5 |  |  | 2770.5 |  |  | 2837.5 |  |  | 2715.5 |  |  | 2696.5 |  |  | 2690.5 |  |  | 2672.5 |  |  | 2645.5 |  |  | 2780.5 |  |  | 2781.5 |  |  | 2673 |  |  | 2777.5 |  |  | 2698.5 |  |  | 2768.5 |  |  | 2733 |  |  | 2784.5 |  |  | 2671.5 |  |  | 2799.5 |  |  | 2754.5 |  |  | 2727 |  |  | 2590.5 |  |  | 2538.5 |  |  | 2636 |  |  | 2682 |  |  | 2679 |  |  | 2750.5 |  |  | 2656.5 |  |  | 2795.5 |  |  | 2909.5 |  |  | 2820 |  |  | 2714.5 |  |  | 2743.5 |  |  | 2595 |  |  | 2648 |  |  | 2762.5 |  |  | 2752.5 |  |  | 2817 |  |  | 2756.5 |  |  | 2829 |  |  | 2658.5 |  |  | 2720.5 |  |  | 2792 |  |  | 2818.5 |  |  | 2715.5 |  |  | 2571.5 |  |  | 2811 |  |  | 2623.5 |  |  | 2594.5 |  |  | 2667.5 |  |  | 2660.5 |  |  | 2744.5 |  |  | 2769.5 |  |  | 2706.5 |  |  | 2803.5 |  |  | 2801.5 |  |  | 2695.5 |  |  | 2658 |  |  | 2689.5 |  |  | 2746.5 |  |  | 2804.5 |  |  | 2779.5 |  |  | 2697.5 |  |  | 2725.5 |  |  | 2755.5 |  |  | 2641.5 |  |  | 2806 |  |  | 2677.5 |  |  | 2664 |  |  | 2988.5 |  |  | 2871.5 |  |  | 2882.5 |  |  | 2674.5 |  |  | 2642.5 |  |  | 2717.5 |  |  | 2558.5 |  |  | 2782.5 |  |  | 2785 |  |  | 2648.5 |  |  | 2760 |  |  | 2601.5 |  |  | 2656.5 |  |  | 2682.5 |  |  | 2770 |  |  | 2662.5 |  |  | 2695.5 |  |  | 2507 |  |  | 2677.5 |  |  | 2715 |  |  | 2739.5 |  |  | 2611.5 |  |  | 2679.5 |  |  | 2714 |  |  | 2849.5 |  |  | 2956.5 |  |  | 2556 |  |  | 2895.5 |  |  | 2701.5 |  |  | 2760 |  |  | 2712.5 |  |  | 2891.5 |  |  | 2815.5 |  |  | 2859.5 |  |  | 2637.5 |  |  | 2871.5 |  |  | 2618.5 |  |  | 2682.5 |  |  | 2638.5 |  |  | 2637.5 |  |  | 2872.5 |  |  | 2815 |  |  | 2753 |  |  | 2848.5 |  |  | 2716.5 |  |  | 2739
93 |  | 2698.5 |  |  | 2764.5 |  |  | 2820 |  |  | 2686.5 |  |  | 2909.5 |  |  | 2784.5 |  |  | 2814.5 |  |  | 2780.5 |  |  | 2723.5 |  |  | 2750.5 |  |  | 2611 |  |  | 2779.5 |  |  | 2761.5 |  |  | 2645.5 |  |  | 2652 |  |  | 2749.5 |  |  | 2824.5 |  |  | 2676.5 |  |  | 2872.5 |  |  | 2648.5 |  |  | 2899.5 |  |  | 2777.5 |  |  | 2857.5 |  |  | 2717.5 |  |  | 2508 |  |  | 2851.5 |  |  | 2745.5 |  |  | 2745.5 |  |  | 2762.5 |  |  | 2593 |  |  | 2763 |  |  | 2871.5 |  |  | 2546.5 |  |  | 2718.5 |  |  | 2662.5 |  |  | 2789 |  |  | 2672.5 |  |  | 2945 |  |  | 2753.5 |  |  | 2730.5 |  |  | 2551.5 |  |  | 2788.5 |  |  | 2586.5 |  |  | 2749 |  |  | 2895.5 |  |  | 2870 |  |  | 2768.5 |  |  | 2810.5 |  |  | 2891.5 |  |  | 2789.5 |  |  | 2601.5 |  |  | 2828.5 |  |  | 2717.5 |  |  | 2721.5 |  |  | 2814.5 |  |  | 2749.5 |  |  | 2655.5 |  |  | 2742 |  |  | 2739.5 |  |  | 2757.5 |  |  | 2719 |  |  | 2765.5 |  |  | 2869.5 |  |  | 2738.5 |  |  | 2653.5 |  |  | 2769 |  |  | 2878.5 |  |  | 2640 |  |  | 2611.5 |  |  | 2773.5 |  |  | 2702 |  |  | 2643.5 |  |  | 2776.5 |  |  | 2892.5 |  |  | 2851 |  |  | 2813 |  |  | 2584.5 |  |  | 2704.5 |  |  | 2681.5 |  |  | 2743.5 |  |  | 2758 |  |  | 2811.5 |  |  | 2805.5 |  |  | 2754.5 |  |  | 2817.5 |  |  | 2611.5 |  |  | 2820.5 |  |  | 2752.5 |  |  | 2735.5 |  |  | 2709.5 |  |  | 2759.5 |  |  | 2785 |  |  | 2698.5 |  |  | 2600 |  |  | 2682 |  |  | 2606 |  |  | 2930.5 |  |  | 2851.5 |  |  | 2643.5 |  |  | 2942.5 |  |  | 2654.5 |  |  | 2677 |  |  | 2702 |  |  | 2740.5 |  |  | 2758.5 |  |  | 2652.5 |  |  | 2735.5 |  |  | 2814.5 |  |  | 2823.5 |  |  | 2882.5 |  |  | 2870.5 |  |  | 2847.5 |  |  | 2690.5 |  |  | 2785.5 |  |  | 2781.5 |  |  | 2779.5 |  |  | 2881.5 |  |  | 2695.5 |  |  | 2764.5 |  |  | 2722.5 |  |  | 2806.5 |  |  | 2812.5 |  |  | 2825.5 |  |  | 2774.5 |  |  | 2763.5 |  |  | 2728 |  |  | 2716.5 |  |  | 2744.5 |  |  | 2692.5 |  |  | 2751.5 |  |  | 2802.5 |  |  | 2738 |  |  | 2667.5 |  |  | 2863.5 |  |  | 2726.5 |  |  | 2661.5 |  |  | 2790 |  |  | 2749.5 |  |  | 2840.5 |  |  | 2614 |  |  | 2829.5 |  |  | 2505 |  |  | 2839 |  |  | 2880.5 |  |  | 2767 |  |  | 2906.5 |  |  | 2725.5 |  |  | 2761.5 |  |  | 2681.5 |  |  | 2763.5 |  |  | 2792.5 |  |  | 2748.5 |  |  | 2783.5 |  |  | 2871.5 |  |  | 2739.5 |  |  | 2876 |  |  | 2628.5 |  |  | 2600 |  |  | 2765.5 |  |  | 2758.5 |  |  | 2689 |  |  | 2741.5 |  |  | 2731.5 |  |  | 2668.5 |  |  | 2614 |  |  | 2714.5 |  |  | 2568.5 |  |  | 2675.5 |  |  | 2849.5 |  |  | 2716.5 |  |  | 2681.5 |  |  | 2693 |  |  | 2741.5 |  |  | 2697.5 |  |  | 2638.5 |  |  | 2812.5 |  |  | 2780.5 |  |  | 2820.5 |  |  | 2712.5 |  |  | 2840 |  |  | 2772.5 |  |  | 2745.5 |  |  | 2766.5 |  |  | 2805.5 |  |  | 2689.5 |  |  | 2825.5 |  |  | 2830.5 |  |  | 2737.5 |  |  | 2916.5 |  |  | 2611.5 |  |  | 2796.5 |  |  | 2547.5 |  |  | 2604.5 |  |  | 2615 |  |  | 2676.5 |  |  | 2788.5 |  |  | 2790.5 |  |  | 2811.5 |  |  | 2826.5 |  |  | 2899.5 |  |  | 2861.5 |  |  | 2752.5 |  |  | 2801.5 |  |  | 2716.5 |  |  | 2653.5 |  |  | 2897.5 |  |  | 2771.5 |  |  | 2716.5 |  |  | 2715.5 |  |  | 2752.5 |  |  | 2745 |  |  | 2915.5 |  |  | 2747.5 |  |  | 2492 |  |  | 2843.5 |  |  | 2889 |  |  | 2525.5 |  |  | 2757.5 |  |  | 2839.5 |  |  | 2866.5 |  |  | 2669.5 |  |  | 2687.5 |  |  | 2710.5 |  |  | 2611.5 |  |  | 2611 |  |  | 2591.5 |  |  | 2531.5 |  |  | 2790.5 |  |  | 2662.5 |  |  | 2735 |  |  | 2723.5 |  |  | 2716.5 |  |  | 2850.5 |  |  | 2707.5 |  |  | 2813.5 |  |  | 2780.5 |  |  | 2763.5 |  |  | 2891.5 |  |  | 2880 |  |  | 2767 |  |  | 2674.5 |  |  | 2631.5 |  |  | 2809.5 |  |  | 2675 |  |  | 2923.5 |  |  | 2771.5 |  |  | 2748.5 |  |  | 2586 |  |  | 2896.5 |  |  | 2748.5 |  |  | 2564.5 |  |  | 2705.5 |  |  | 2775.5 |  |  | 2793.5 |  |  | 2848.5 |  |  | 2784.5 |  |  | 2820.5 |  |  | 2539 |  |  | 2620.5 |  |  | 2814.5 |  |  | 2760.5 |  |  | 2757.5 |  |  | 2662.5 |  |  | 2918 |  |  | 2593.5 |  |  | 2891.5 |  |  | 2827 |  |  | 2850.5 |  |  | 2737.5 |  |  | 2953 |  |  | 2806.5 |  |  | 2800.5 |  |  | 2885.5 |  |  | 2682.5 |  |  | 2715 |  |  | 2770 |  |  | 2768.5 |  |  | 2600.5 |  |  | 2816.5 |  |  | 2676.5 |  |  | 2915.5 |  |  | 2788.5 |  |  | 2774 |  |  | 2670.5 |  |  | 2600.5 |  |  | 2674 |  |  | 2723.5 |  |  | 2550.5 |  |  | 2771 |  |  | 2769.5 |  |  | 2674.5 |  |  | 2747.5 |  |  | 2811 |  |  | 2759.5 |  |  | 2711 |  |  | 2876.5 |  |  | 2625.5 |  |  | 2750.5 |  |  | 2668 |  |  | 2678.5 |  |  | 2854.5 |  |  | 2838.5 |  |  | 2776 |  |  | 2699.5 |  |  | 2597.5 |  |  | 2868.5 |  |  | 2927.5 |  |  | 2779.5 |  |  | 2819 |  |  | 2662.5 |  |  | 2869.5 |  |  | 2733.5 |  |  | 2737 |  |  | 2742 |  |  | 2893.5 |  |  | 2606.5 |  |  | 2537.5 |  |  | 2790.5 |  |  | 2734.5 |  |  | 2706.5 |  |  | 2810.5 |  |  | 2806.5 |  |  | 2669.5 |  |  | 2781.5 |  |  | 2748 |  |  | 2672.5 |  |  | 2736.5 |  |  | 2948.5 |  |  | 2943.5 |  |  | 2769 |  |  | 2690.5 |  |  | 2871.5 |  |  | 2793.5 |  |  | 2594.5 |  |  | 2902.5 |  |  | 2575 |  |  | 2822 |  |  | 2617 |  |  | 2838 |  |  | 2655.5 |  |  | 2705 |  |  | 2770.5 |  |  | 2717 |  |  | 2728.5 |  |  | 2824.5 |  |  | 2734.5 |  |  | 2711.5 |  |  | 2653.5 |  |  | 2792 |  |  | 2750.5 |  |  | 2907.5 |  |  | 2684.5 |  |  | 2765 |  |  | 2881.5 |  |  | 2630.5 |  |  | 2784.5 |  |  | 2797 |  |  | 2682.5 |  |  | 2652.5 |  |  | 2807.5 |  |  | 2650.5 |  |  | 2822.5 |  |  | 2649.5 |  |  | 2820.5 |  |  | 2745.5 |  |  | 2801.5 |  |  | 2575.5 |  |  | 2735 |  |  | 2672.5 |  |  | 2723.5 |  |  | 2662.5 |  |  | 2812.5 |  |  | 2898.5 |  |  | 2732 |  |  | 2820.5 |  |  | 2891 |  |  | 2776 |  |  | 2637.5 |  |  | 2839.5 |  |  | 2648.5 |  |  | 2746 |  |  | 2749.5 |  |  | 2771.5 |  |  | 2732.5 |  |  | 2578 |  |  | 2678.5 |  |  | 2562.5 |  |  | 2675.5 |  |  | 2608.5 |  |  | 2709.5 |  |  | 2707 |  |  | 2657.5 |  |  | 2770 |  |  | 2754.5 |  |  | 2582.5 |  |  | 2735.5 |  |  | 2716 |  |  | 2656.5 |  |  | 2663 |  |  | 2678 |  |  | 2751.5 |  |  | 2612.5 |  |  | 2653.5 |  |  | 2884.5 |  |  | 2944 |  |  | 2818.5 |  |  | 2732.5 |  |  | 2545.5 |  |  | 2713 |  |  | 2787.5 |  |  | 2670.5 |  |  | 2479.5 |  |  | 2789.5 |  |  | 2891 |  |  | 2626.5 |  |  | 2633.5 |  |  | 2695.5 |  |  | 2802.5 |  |  | 2817.5 |  |  | 2776.5 |  |  | 2811 |  |  | 2668.5 |  |  | 2703.5 |  |  | 2747 |  |  | 2611.5 |  |  | 2604.5 |  |  | 2783.5 |  |  | 2715 |  |  | 2838.5 |  |  | 2769.5 |  |  | 2671.5 |  |  | 2725.5 |  |  | 2801.5 |  |  | 2721 |  |  | 2661 |  |  | 2745.5 |  |  | 2784.5 |  |  | 2753.5 |  |  | 2581.5 |  |  | 2519 |  |  | 2843 |  |  | 2709 |  |  | 2873.5 |  |  | 2687 |  |  | 2753.5 |  |  | 2870.5 |  |  | 2844 |  |  | 2580.5 |  |  | 2777.5 |  |  | 2678.5 |  |  | 2783.5 |  |  | 2463.5 |  |  | 2710 |  |  | 2805 |  |  | 2658.5 |  |  | 2823.5 |  |  | 2618 |  |  | 2633.5 |  |  | 2777.5 |  |  | 2673 |  |  | 2905.5 |  |  | 2880.5 |  |  | 2651 |  |  | 2818.5 |  |  | 2788.5 |  |  | 2862 |  |  | 2677.5 |  |  | 2600 |  |  | 2892.5 |  |  | 2908 |  |  | 2673.5 |  |  | 2668.5 |  |  | 2668.5 |  |  | 2740.5 |  |  | 2731.5 |  |  | 2598.5 |  |  | 2743 |  |  | 2607.5 |  |  | 2798.5 |  |  | 2702.5 |  |  | 2692.5 |  |  | 2733.5 |  |  | 2679 |  |  | 2705.5 |  |  | 2760 |  |  | 2831.5 |  |  | 2553.5 |  |  | 2826.5 |  |  | 2826.5 |  |  | 2811.5 |  |  | 2712.5 |  |  | 2618.5 |  |  | 2807.5 |  |  | 2594.5 |  |  | 2668 |  |  | 2789.5 |  |  | 2684 |  |  | 2795 |  |  | 2783.5 |  |  | 2495 |  |  | 2608.5 |  |  | 2805.5 |  |  | 2827.5 |  |  | 2770.5 |  |  | 2856.5 |  |  | 2762.5 |  |  | 2811.5 |  |  | 2676 |  |  | 2898 |  |  | 2624.5 |  |  | 2765.5 |  |  | 2739 |  |  | 2736.5 |  |  | 2681.5 |  |  | 2679.5 |  |  | 2642.5 |  |  | 2688.5 |  |  | 2599 |  |  | 2744.5 |  |  | 2696.5 |  |  | 2682.5 |  |  | 2718 |  |  | 2777.5 |  |  | 2809.5 |  |  | 2821.5 |  |  | 3017.5 |  |  | 2754.5 |  |  | 2647.5 |  |  | 2796.5 |  |  | 2338.5 |  |  | 2718.5 |  |  | 2676 |  |  | 2866.5 |  |  | 2762.5 |  |  | 2823.5 |  |  | 2590.5 |  |  | 2757.5 |  |  | 2617.5 |  |  | 2587.5 |  |  | 2586 |  |  | 2641.5 |  |  | 2734.5 |  |  | 2648.5 |  |  | 2713 |  |  | 2777.5 |  |  | 2634 |  |  | 2598.5 |  |  | 2692.5 |  |  | 2663.5 |  |  | 2764 |  |  | 2552.5 |  |  | 2761 |  |  | 2753 |  |  | 2761.5 |  |  | 2688 |  |  | 2859 |  |  | 2826.5 |  |  | 2872.5 |  |  | 2617.5 |  |  | 2803 |  |  | 2762.5 |  |  | 2605.5 |  |  | 2576.5 |  |  | 2841.5 |  |  | 2666.5 |  |  | 2741.5 |  |  | 2725.5 |  |  | 2762.5 |  |  | 2645 |  |  | 2887.5 |  |  | 2653 |  |  | 2779.5 |  |  | 2655.5 |  |  | 2821.5 |  |  | 2730 |  |  | 2791 |  |  | 2899 |  |  | 2807.5 |  |  | 2760 |  |  | 2760.5 |  |  | 2929.5 |  |  | 2741.5 |  |  | 2716.5 |  |  | 2623.5 |  |  | 2851.5 |  |  | 2846.5 |  |  | 2790.5 |  |  | 2748 |  |  | 2580.5 |  |  | 2619.5 |  |  | 2739.5 |  |  | 2759.5 |  |  | 2654 |  |  | 2756.5 |  |  | 2725 |  |  | 2744.5 |  |  | 2707.5 |  |  | 2704.5 |  |  | 2603.5 |  |  | 2566 |  |  | 2718.5 |  |  | 2509 |  |  | 2693.5 |  |  | 2789.5 |  |  | 2896.5 |  |  | 2672.5 |  |  | 2709.5 |  |  | 2846.5 |  |  | 2694.5 |  |  | 2747.5 |  |  | 2691.5 |  |  | 2626 |  |  | 2724.5 |  |  | 2734.5 |  |  | 2705.5 |  |  | 2776.5 |  |  | 2781.5 |  |  | 2691 |  |  | 2626 |  |  | 2761.5 |  |  | 2671 |  |  | 2906.5 |  |  | 2675.5 |  |  | 2867.5 |  |  | 2719.5 |  |  | 2647.5 |  |  | 2824.5 |  |  | 2777.5 |  |  | 2773.5 |  |  | 2786 |  |  | 2764.5 |  |  | 2933.5 |  |  | 2693.5 |  |  | 2571 |  |  | 2756.5 |  |  | 2615.5 |  |  | 2878 |  |  | 2703 |  |  | 2723.5 |  |  | 2699 |  |  | 2597 |  |  | 2599.5 |  |  | 2855 |  |  | 2954.5 |  |  | 2684.5 |  |  | 2846.5 |  |  | 2649.5 |  |  | 2579.5 |  |  | 2752.5 |  |  | 2513.5 |  |  | 2647.5 |  |  | 2787.5 |  |  | 2660.5 |  |  | 2647 |  |  | 2696 |  |  | 2803.5 |  |  | 2861.5 |  |  | 2639.5 |  |  | 2839.5 |  |  | 2732.5 |  |  | 2811.5 |  |  | 2753.5 |  |  | 2612.5 |  |  | 2997 |  |  | 2651.5 |  |  | 2704 |  |  | 2666.5 |  |  | 2835.5 |  |  | 2793.5 |  |  | 2878 |  |  | 2734.5 |  |  | 2698.5 |  |  | 2763 |  |  | 2793.5 |  |  | 2724.5 |  |  | 2890.5 |  |  | 2728.5 |  |  | 2683.5 |  |  | 2780.5 |  |  | 2819 |  |  | 2613.5 |  |  | 2761.5 |  |  | 2909.5 |  |  | 2797.5 |  |  | 2749 |  |  | 2735.5 |  |  | 2894.5 |  |  | 2686 |  |  | 2731.5 |  |  | 2803.5 |  |  | 2762 |  |  | 2779.5 |  |  | 2843.5 |  |  | 2710.5 |  |  | 2639 |  |  | 2574.5 |  |  | 2688.5 |  |  | 2641 |  |  | 2801.5 |  |  | 2770.5 |  |  | 2766.5 |  |  | 2578.5 |  |  | 2725.5 |  |  | 2905.5 |  |  | 2659.5 |  |  | 2711 |  |  | 2609 |  |  | 2591.5 |  |  | 2792.5 |  |  | 2609.5 |  |  | 2852 |  |  | 2885.5 |  |  | 2687.5 |  |  | 2726.5 |  |  | 2551.5 |  |  | 2758.5 |  |  | 2769.5 |  |  | 2663.5 |  |  | 2782.5 |  |  | 2528.5 |  |  | 2773 |  |  | 2691.5 |  |  | 2543.5 |  |  | 2737.5 |  |  | 2712.5 |  |  | 2890.5 |  |  | 2771.5 |  |  | 2744.5 |  |  | 2721.5 |  |  | 2570.5 |  |  | 2903.5 |  |  | 2717.5 |  |  | 2610.5 |  |  | 2727.5 |  |  | 2863 |  |  | 2780.5 |  |  | 2861.5 |  |  | 2671 |  |  | 2794.5 |  |  | 2809.5 |  |  | 2816 |  |  | 2786.5 |  |  | 2801.5 |  |  | 2920.5 |  |  | 2936 |  |  | 2669.5 |  |  | 2833.5 |  |  | 2700.5 |  |  | 2501.5 |  |  | 2822.5 |  |  | 2659 |  |  | 2658.5 |  |  | 2802 |  |  | 2777 |  |  | 2814.5 |  |  | 2734.5 |  |  | 2628.5 |  |  | 2464.5 |  |  | 2671.5 |  |  | 2880.5 |  |  | 2698 |  |  | 2703.5 |  |  | 2683 |  |  | 2771.5 |  |  | 2784 |  |  | 2592 |  |  | 2781 |  |  | 2830.5 |  |  | 2631 |  |  | 2900.5 |  |  | 2795.5 |  |  | 2714.5 |  |  | 2941.5 |  |  | 2552.5 |  |  | 2817 |  |  | 2710.5 |  |  | 2768.5 |  |  | 2991.5 |  |  | 2728 |  |  | 2685.5 |  |  | 2715.5 |  |  | 2750.5 |  |  | 2889.5 |  |  | 2702 |  |  | 2810 |  |  | 2665 |  |  | 2702.5 |  |  | 2863 |  |  | 2743 |  |  | 2888.5 |  |  | 2646.5 |  |  | 2639.5 |  |  | 2714.5 |  |  | 2820.5 |  |  | 2727.5 |  |  | 2775.5 |  |  | 2763.5 |  |  | 2690.5 |  |  | 2665 |  |  | 2675.5 |  |  | 2643 |  |  | 2754.5 |  |  | 2694.5 |  |  | 2812.5 |  |  | 2787.5 |  |  | 2863 |  |  | 2772.5 |  |  | 2740 |  |  | 2632.5 |  |  | 2787.5 |  |  | 2587 |  |  | 2716 |  |  | 2823.5 |  |  | 2799 |  |  | 2767.5 |  |  | 2615.5 |  |  | 2641.5 |  |  | 2672.5 |  |  | 2748.5 |  |  | 2751.5 |  |  | 2599.5 |  |  | 2674 |  |  | 2771.5 |  |  | 2779.5 |  |  | 2799.5 |  |  | 2820.5 |  |  | 2671.5 |  |  | 2763.5 |  |  | 2878.5 |  |  | 2729.5 |  |  | 2940.5 |  |  | 2859.5 |  |  | 2653.5 |  |  | 2587.5 |  |  | 2755 |  |  | 2632.5 |  |  | 2740.5 |  |  | 2820 |  |  | 2664.5 |  |  | 2614.5 |  |  | 2707.5 |  |  | 2605.5 |  |  | 2971 |  |  | 2869.5 |  |  | 2633.5 |  |  | 2646.5 |  |  | 2882.5 |  |  | 2685 |  |  | 2707.5 |  |  | 2863.5 |  |  | 2681.5 |  |  | 2835.5 |  |  | 2643.5 |  |  | 2630.5 |  |  | 2821.5 |  |  | 2687.5 |  |  | 2757.5 |  |  | 2743.5 |  |  | 2809.5 |  |  | 2780 |  |  | 2757.5 |  |  | 2731.5 |  |  | 2783.5 |  |  | 2885.5 |  |  | 2665.5 |  |  | 2674.5 |  |  | 2762 |  |  | 2871.5 |  |  | 2641 |  |  | 2627.5 |  |  | 2843.5 |  |  | 2795.5 |  |  | 2713 |  |  | 2683 |  |  | 2803.5 |  |  | 2808.5 |  |  | 2520.5 |  |  | 2899.5 |  |  | 2691.5 |  |  | 2807.5 |  |  | 2699.5 |  |  | 2842.5 |  |  | 2682.5 |  |  | 2932.5 |  |  | 2734.5 |  |  | 2789.5 |  |  | 2629.5 |  |  | 2809.5 |  |  | 2876.5 |  |  | 2736.5 |  |  | 2711.5 |  |  | 2737.5 |  |  | 2711.5 |  |  | 2684.5 |  |  | 2819.5 |  |  | 2820.5 |  |  | 2699 |  |  | 2798.5 |  |  | 2722.5 |  |  | 2807.5 |  |  | 2759 |  |  | 2810.5 |  |  | 2710.5 |  |  | 2846.5 |  |  | 2801.5 |  |  | 2748 |  |  | 2629.5 |  |  | 2577.5 |  |  | 2651 |  |  | 2703 |  |  | 2708 |  |  | 2789.5 |  |  | 2695.5 |  |  | 2816.5 |  |  | 2938.5 |  |  | 2835 |  |  | 2740.5 |  |  | 2769.5 |  |  | 2634 |  |  | 2663 |  |  | 2801.5 |  |  | 2767.5 |  |  | 2864 |  |  | 2771.5 |  |  | 2876 |  |  | 2697.5 |  |  | 2735.5 |  |  | 2831 |  |  | 2865.5 |  |  | 2762.5 |  |  | 2597.5 |  |  | 2840 |  |  | 2649.5 |  |  | 2618.5 |  |  | 2693.5 |  |  | 2699.5 |  |  | 2765.5 |  |  | 2798.5 |  |  | 2745.5 |  |  | 2850.5 |  |  | 2825.5 |  |  | 2742.5 |  |  | 2679 |  |  | 2704.5 |  |  | 2772.5 |  |  | 2830.5 |  |  | 2803.5 |  |  | 2718.5 |  |  | 2772.5 |  |  | 2779.5 |  |  | 2680.5 |  |  | 2853 |  |  | 2716.5 |  |  | 2679 |  |  | 3003.5 |  |  | 2897.5 |  |  | 2906.5 |  |  | 2695.5 |  |  | 2663.5 |  |  | 2738.5 |  |  | 2582.5 |  |  | 2803.5 |  |  | 2832 |  |  | 2687.5 |  |  | 2775 |  |  | 2627.5 |  |  | 2695.5 |  |  | 2697.5 |  |  | 2794 |  |  | 2686.5 |  |  | 2721.5 |  |  | 2522 |  |  | 2716.5 |  |  | 2736 |  |  | 2763.5 |  |  | 2650.5 |  |  | 2708.5 |  |  | 2738 |  |  | 2878.5 |  |  | 2977.5 |  |  | 2577 |  |  | 2942.5 |  |  | 2727.5 |  |  | 2775 |  |  | 2751.5 |  |  | 2906.5 |  |  | 2854.5 |  |  | 2898.5 |  |  | 2661.5 |  |  | 2892.5 |  |  | 2657.5 |  |  | 2721.5 |  |  | 2677.5 |  |  | 2652.5 |  |  | 2911.5 |  |  | 2844 |  |  | 2792 |  |  | 2887.5 |  |  | 2755.5 |  |  | 2786
94 |  | 2719.5 |  |  | 2788.5 |  |  | 2835 |  |  | 2701.5 |  |  | 2956.5 |  |  | 2823.5 |  |  | 2829.5 |  |  | 2819.5 |  |  | 2762.5 |  |  | 2797.5 |  |  | 2650 |  |  | 2803.5 |  |  | 2785.5 |  |  | 2684.5 |  |  | 2678 |  |  | 2778.5 |  |  | 2853.5 |  |  | 2715.5 |  |  | 2911.5 |  |  | 2687.5 |  |  | 2938.5 |  |  | 2792.5 |  |  | 2896.5 |  |  | 2756.5 |  |  | 2529 |  |  | 2890.5 |  |  | 2792.5 |  |  | 2784.5 |  |  | 2801.5 |  |  | 2617 |  |  | 2810 |  |  | 2918.5 |  |  | 2593.5 |  |  | 2739.5 |  |  | 2677.5 |  |  | 2813 |  |  | 2698.5 |  |  | 2974 |  |  | 2768.5 |  |  | 2769.5 |  |  | 2598.5 |  |  | 2827.5 |  |  | 2612.5 |  |  | 2796 |  |  | 2919.5 |  |  | 2896 |  |  | 2794.5 |  |  | 2849.5 |  |  | 2938.5 |  |  | 2810.5 |  |  | 2625.5 |  |  | 2854.5 |  |  | 2738.5 |  |  | 2768.5 |  |  | 2843.5 |  |  | 2796.5 |  |  | 2681.5 |  |  | 2768 |  |  | 2768.5 |  |  | 2772.5 |  |  | 2740 |  |  | 2789.5 |  |  | 2908.5 |  |  | 2753.5 |  |  | 2692.5 |  |  | 2798 |  |  | 2899.5 |  |  | 2664 |  |  | 2637.5 |  |  | 2820.5 |  |  | 2717 |  |  | 2667.5 |  |  | 2791.5 |  |  | 2931.5 |  |  | 2890 |  |  | 2860 |  |  | 2599.5 |  |  | 2725.5 |  |  | 2702.5 |  |  | 2769.5 |  |  | 2787 |  |  | 2826.5 |  |  | 2820.5 |  |  | 2780.5 |  |  | 2843.5 |  |  | 2640.5 |  |  | 2844.5 |  |  | 2773.5 |  |  | 2759.5 |  |  | 2724.5 |  |  | 2783.5 |  |  | 2814 |  |  | 2745.5 |  |  | 2615 |  |  | 2711 |  |  | 2645 |  |  | 2969.5 |  |  | 2866.5 |  |  | 2682.5 |  |  | 2971.5 |  |  | 2680.5 |  |  | 2703 |  |  | 2726 |  |  | 2761.5 |  |  | 2797.5 |  |  | 2673.5 |  |  | 2759.5 |  |  | 2838.5 |  |  | 2847.5 |  |  | 2906.5 |  |  | 2909.5 |  |  | 2871.5 |  |  | 2737.5 |  |  | 2832.5 |  |  | 2802.5 |  |  | 2818.5 |  |  | 2907.5 |  |  | 2721.5 |  |  | 2788.5 |  |  | 2748.5 |  |  | 2853.5 |  |  | 2841.5 |  |  | 2854.5 |  |  | 2795.5 |  |  | 2778.5 |  |  | 2767 |  |  | 2763.5 |  |  | 2783.5 |  |  | 2707.5 |  |  | 2790.5 |  |  | 2831.5 |  |  | 2764 |  |  | 2691.5 |  |  | 2910.5 |  |  | 2747.5 |  |  | 2700.5 |  |  | 2819 |  |  | 2770.5 |  |  | 2887.5 |  |  | 2640 |  |  | 2850.5 |  |  | 2526 |  |  | 2863 |  |  | 2919.5 |  |  | 2806 |  |  | 2945.5 |  |  | 2754.5 |  |  | 2787.5 |  |  | 2728.5 |  |  | 2787.5 |  |  | 2821.5 |  |  | 2774.5 |  |  | 2822.5 |  |  | 2910.5 |  |  | 2778.5 |  |  | 2915 |  |  | 2643.5 |  |  | 2639 |  |  | 2794.5 |  |  | 2805.5 |  |  | 2713 |  |  | 2780.5 |  |  | 2752.5 |  |  | 2707.5 |  |  | 2640 |  |  | 2738.5 |  |  | 2607.5 |  |  | 2690.5 |  |  | 2873.5 |  |  | 2755.5 |  |  | 2720.5 |  |  | 2714 |  |  | 2756.5 |  |  | 2712.5 |  |  | 2659.5 |  |  | 2836.5 |  |  | 2804.5 |  |  | 2835.5 |  |  | 2759.5 |  |  | 2864 |  |  | 2801.5 |  |  | 2760.5 |  |  | 2813.5 |  |  | 2834.5 |  |  | 2713.5 |  |  | 2851.5 |  |  | 2869.5 |  |  | 2763.5 |  |  | 2963.5 |  |  | 2632.5 |  |  | 2835.5 |  |  | 2562.5 |  |  | 2651.5 |  |  | 2644 |  |  | 2705.5 |  |  | 2827.5 |  |  | 2829.5 |  |  | 2858.5 |  |  | 2865.5 |  |  | 2928.5 |  |  | 2885.5 |  |  | 2773.5 |  |  | 2827.5 |  |  | 2755.5 |  |  | 2692.5 |  |  | 2936.5 |  |  | 2800.5 |  |  | 2731.5 |  |  | 2754.5 |  |  | 2781.5 |  |  | 2769 |  |  | 2939.5 |  |  | 2773.5 |  |  | 2531 |  |  | 2867.5 |  |  | 2910 |  |  | 2564.5 |  |  | 2796.5 |  |  | 2878.5 |  |  | 2895.5 |  |  | 2708.5 |  |  | 2711.5 |  |  | 2725.5 |  |  | 2650.5 |  |  | 2640 |  |  | 2612.5 |  |  | 2578.5 |  |  | 2816.5 |  |  | 2686.5 |  |  | 2750 |  |  | 2747.5 |  |  | 2737.5 |  |  | 2865.5 |  |  | 2754.5 |  |  | 2860.5 |  |  | 2804.5 |  |  | 2802.5 |  |  | 2938.5 |  |  | 2919 |  |  | 2791 |  |  | 2721.5 |  |  | 2670.5 |  |  | 2848.5 |  |  | 2704 |  |  | 2962.5 |  |  | 2792.5 |  |  | 2795.5 |  |  | 2615 |  |  | 2922.5 |  |  | 2772.5 |  |  | 2585.5 |  |  | 2726.5 |  |  | 2790.5 |  |  | 2832.5 |  |  | 2869.5 |  |  | 2813.5 |  |  | 2859.5 |  |  | 2554 |  |  | 2667.5 |  |  | 2853.5 |  |  | 2799.5 |  |  | 2772.5 |  |  | 2677.5 |  |  | 2939 |  |  | 2632.5 |  |  | 2917.5 |  |  | 2851 |  |  | 2897.5 |  |  | 2776.5 |  |  | 2968 |  |  | 2821.5 |  |  | 2815.5 |  |  | 2900.5 |  |  | 2729.5 |  |  | 2736 |  |  | 2785 |  |  | 2794.5 |  |  | 2639.5 |  |  | 2840.5 |  |  | 2723.5 |  |  | 2954.5 |  |  | 2827.5 |  |  | 2789 |  |  | 2691.5 |  |  | 2629.5 |  |  | 2721 |  |  | 2762.5 |  |  | 2565.5 |  |  | 2810 |  |  | 2784.5 |  |  | 2713.5 |  |  | 2786.5 |  |  | 2840 |  |  | 2806.5 |  |  | 2750 |  |  | 2902.5 |  |  | 2672.5 |  |  | 2789.5 |  |  | 2707 |  |  | 2702.5 |  |  | 2901.5 |  |  | 2864.5 |  |  | 2797 |  |  | 2725.5 |  |  | 2621.5 |  |  | 2883.5 |  |  | 2966.5 |  |  | 2808.5 |  |  | 2834 |  |  | 2701.5 |  |  | 2908.5 |  |  | 2772.5 |  |  | 2752 |  |  | 2763 |  |  | 2940.5 |  |  | 2645.5 |  |  | 2563.5 |  |  | 2816.5 |  |  | 2773.5 |  |  | 2735.5 |  |  | 2834.5 |  |  | 2845.5 |  |  | 2693.5 |  |  | 2807.5 |  |  | 2763 |  |  | 2698.5 |  |  | 2757.5 |  |  | 2987.5 |  |  | 2967.5 |  |  | 2795 |  |  | 2729.5 |  |  | 2900.5 |  |  | 2840.5 |  |  | 2615.5 |  |  | 2917.5 |  |  | 2601 |  |  | 2837 |  |  | 2643 |  |  | 2867 |  |  | 2684.5 |  |  | 2731 |  |  | 2799.5 |  |  | 2732 |  |  | 2749.5 |  |  | 2839.5 |  |  | 2755.5 |  |  | 2737.5 |  |  | 2700.5 |  |  | 2831 |  |  | 2765.5 |  |  | 2946.5 |  |  | 2723.5 |  |  | 2791 |  |  | 2902.5 |  |  | 2669.5 |  |  | 2823.5 |  |  | 2844 |  |  | 2729.5 |  |  | 2699.5 |  |  | 2833.5 |  |  | 2671.5 |  |  | 2837.5 |  |  | 2678.5 |  |  | 2835.5 |  |  | 2760.5 |  |  | 2822.5 |  |  | 2614.5 |  |  | 2750 |  |  | 2701.5 |  |  | 2738.5 |  |  | 2677.5 |  |  | 2859.5 |  |  | 2937.5 |  |  | 2771 |  |  | 2846.5 |  |  | 2930 |  |  | 2815 |  |  | 2661.5 |  |  | 2865.5 |  |  | 2674.5 |  |  | 2761 |  |  | 2788.5 |  |  | 2810.5 |  |  | 2761.5 |  |  | 2602 |  |  | 2699.5 |  |  | 2601.5 |  |  | 2714.5 |  |  | 2637.5 |  |  | 2748.5 |  |  | 2736 |  |  | 2672.5 |  |  | 2796 |  |  | 2769.5 |  |  | 2603.5 |  |  | 2759.5 |  |  | 2737 |  |  | 2682.5 |  |  | 2678 |  |  | 2699 |  |  | 2766.5 |  |  | 2651.5 |  |  | 2692.5 |  |  | 2931.5 |  |  | 2973 |  |  | 2842.5 |  |  | 2756.5 |  |  | 2592.5 |  |  | 2739 |  |  | 2826.5 |  |  | 2699.5 |  |  | 2494.5 |  |  | 2828.5 |  |  | 2915 |  |  | 2655.5 |  |  | 2657.5 |  |  | 2719.5 |  |  | 2823.5 |  |  | 2864.5 |  |  | 2823.5 |  |  | 2826 |  |  | 2707.5 |  |  | 2729.5 |  |  | 2762 |  |  | 2626.5 |  |  | 2633.5 |  |  | 2812.5 |  |  | 2754 |  |  | 2862.5 |  |  | 2784.5 |  |  | 2710.5 |  |  | 2764.5 |  |  | 2840.5 |  |  | 2768 |  |  | 2676 |  |  | 2784.5 |  |  | 2810.5 |  |  | 2792.5 |  |  | 2620.5 |  |  | 2558 |  |  | 2890 |  |  | 2748 |  |  | 2902.5 |  |  | 2711 |  |  | 2800.5 |  |  | 2917.5 |  |  | 2868 |  |  | 2609.5 |  |  | 2806.5 |  |  | 2704.5 |  |  | 2830.5 |  |  | 2502.5 |  |  | 2725 |  |  | 2831 |  |  | 2684.5 |  |  | 2849.5 |  |  | 2639 |  |  | 2672.5 |  |  | 2806.5 |  |  | 2712 |  |  | 2929.5 |  |  | 2919.5 |  |  | 2690 |  |  | 2833.5 |  |  | 2803.5 |  |  | 2886 |  |  | 2724.5 |  |  | 2626 |  |  | 2918.5 |  |  | 2929 |  |  | 2712.5 |  |  | 2689.5 |  |  | 2689.5 |  |  | 2766.5 |  |  | 2778.5 |  |  | 2613.5 |  |  | 2772 |  |  | 2646.5 |  |  | 2827.5 |  |  | 2741.5 |  |  | 2739.5 |  |  | 2754.5 |  |  | 2694 |  |  | 2729.5 |  |  | 2799 |  |  | 2870.5 |  |  | 2600.5 |  |  | 2850.5 |  |  | 2865.5 |  |  | 2840.5 |  |  | 2751.5 |  |  | 2657.5 |  |  | 2828.5 |  |  | 2641.5 |  |  | 2689 |  |  | 2828.5 |  |  | 2710 |  |  | 2842 |  |  | 2804.5 |  |  | 2524 |  |  | 2623.5 |  |  | 2852.5 |  |  | 2856.5 |  |  | 2785.5 |  |  | 2903.5 |  |  | 2801.5 |  |  | 2832.5 |  |  | 2691 |  |  | 2945 |  |  | 2663.5 |  |  | 2804.5 |  |  | 2760 |  |  | 2775.5 |  |  | 2710.5 |  |  | 2703.5 |  |  | 2671.5 |  |  | 2727.5 |  |  | 2614 |  |  | 2783.5 |  |  | 2720.5 |  |  | 2706.5 |  |  | 2747 |  |  | 2798.5 |  |  | 2833.5 |  |  | 2845.5 |  |  | 3056.5 |  |  | 2793.5 |  |  | 2668.5 |  |  | 2835.5 |  |  | 2377.5 |  |  | 2739.5 |  |  | 2700 |  |  | 2913.5 |  |  | 2801.5 |  |  | 2838.5 |  |  | 2619.5 |  |  | 2783.5 |  |  | 2643.5 |  |  | 2613.5 |  |  | 2610 |  |  | 2665.5 |  |  | 2749.5 |  |  | 2674.5 |  |  | 2760 |  |  | 2816.5 |  |  | 2658 |  |  | 2637.5 |  |  | 2731.5 |  |  | 2687.5 |  |  | 2803 |  |  | 2591.5 |  |  | 2808 |  |  | 2792 |  |  | 2790.5 |  |  | 2709 |  |  | 2874 |  |  | 2850.5 |  |  | 2911.5 |  |  | 2664.5 |  |  | 2842 |  |  | 2801.5 |  |  | 2626.5 |  |  | 2615.5 |  |  | 2880.5 |  |  | 2705.5 |  |  | 2767.5 |  |  | 2772.5 |  |  | 2791.5 |  |  | 2684 |  |  | 2926.5 |  |  | 2692 |  |  | 2818.5 |  |  | 2679.5 |  |  | 2836.5 |  |  | 2769 |  |  | 2817 |  |  | 2920 |  |  | 2833.5 |  |  | 2799 |  |  | 2784.5 |  |  | 2968.5 |  |  | 2770.5 |  |  | 2742.5 |  |  | 2638.5 |  |  | 2877.5 |  |  | 2867.5 |  |  | 2811.5 |  |  | 2763 |  |  | 2627.5 |  |  | 2658.5 |  |  | 2768.5 |  |  | 2785.5 |  |  | 2693 |  |  | 2771.5 |  |  | 2764 |  |  | 2791.5 |  |  | 2746.5 |  |  | 2743.5 |  |  | 2629.5 |  |  | 2581 |  |  | 2733.5 |  |  | 2538 |  |  | 2722.5 |  |  | 2828.5 |  |  | 2935.5 |  |  | 2711.5 |  |  | 2748.5 |  |  | 2867.5 |  |  | 2741.5 |  |  | 2773.5 |  |  | 2715.5 |  |  | 2673 |  |  | 2748.5 |  |  | 2760.5 |  |  | 2744.5 |  |  | 2823.5 |  |  | 2820.5 |  |  | 2712 |  |  | 2665 |  |  | 2800.5 |  |  | 2718 |  |  | 2927.5 |  |  | 2704.5 |  |  | 2914.5 |  |  | 2745.5 |  |  | 2662.5 |  |  | 2863.5 |  |  | 2816.5 |  |  | 2802.5 |  |  | 2810 |  |  | 2793.5 |  |  | 2972.5 |  |  | 2732.5 |  |  | 2610 |  |  | 2777.5 |  |  | 2654.5 |  |  | 2917 |  |  | 2742 |  |  | 2762.5 |  |  | 2720 |  |  | 2626 |  |  | 2638.5 |  |  | 2870 |  |  | 2993.5 |  |  | 2713.5 |  |  | 2861.5 |  |  | 2670.5 |  |  | 2605.5 |  |  | 2791.5 |  |  | 2552.5 |  |  | 2662.5 |  |  | 2826.5 |  |  | 2707.5 |  |  | 2668 |  |  | 2743 |  |  | 2842.5 |  |  | 2882.5 |  |  | 2678.5 |  |  | 2865.5 |  |  | 2758.5 |  |  | 2858.5 |  |  | 2800.5 |  |  | 2633.5 |  |  | 3026 |  |  | 2677.5 |  |  | 2743 |  |  | 2705.5 |  |  | 2856.5 |  |  | 2840.5 |  |  | 2893 |  |  | 2763.5 |  |  | 2737.5 |  |  | 2787 |  |  | 2832.5 |  |  | 2750.5 |  |  | 2929.5 |  |  | 2767.5 |  |  | 2709.5 |  |  | 2806.5 |  |  | 2866 |  |  | 2639.5 |  |  | 2776.5 |  |  | 2930.5 |  |  | 2821.5 |  |  | 2788 |  |  | 2756.5 |  |  | 2920.5 |  |  | 2701 |  |  | 2760.5 |  |  | 2850.5 |  |  | 2801 |  |  | 2794.5 |  |  | 2882.5 |  |  | 2736.5 |  |  | 2678 |  |  | 2598.5 |  |  | 2727.5 |  |  | 2670 |  |  | 2830.5 |  |  | 2796.5 |  |  | 2792.5 |  |  | 2604.5 |  |  | 2754.5 |  |  | 2920.5 |  |  | 2683.5 |  |  | 2758 |  |  | 2638 |  |  | 2606.5 |  |  | 2813.5 |  |  | 2624.5 |  |  | 2867 |  |  | 2924.5 |  |  | 2726.5 |  |  | 2747.5 |  |  | 2598.5 |  |  | 2782.5 |  |  | 2808.5 |  |  | 2710.5 |  |  | 2806.5 |  |  | 2557.5 |  |  | 2788 |  |  | 2730.5 |  |  | 2582.5 |  |  | 2776.5 |  |  | 2738.5 |  |  | 2905.5 |  |  | 2818.5 |  |  | 2759.5 |  |  | 2760.5 |  |  | 2617.5 |  |  | 2942.5 |  |  | 2756.5 |  |  | 2649.5 |  |  | 2756.5 |  |  | 2878 |  |  | 2809.5 |  |  | 2887.5 |  |  | 2686 |  |  | 2820.5 |  |  | 2833.5 |  |  | 2855 |  |  | 2807.5 |  |  | 2840.5 |  |  | 2946.5 |  |  | 2965 |  |  | 2690.5 |  |  | 2848.5 |  |  | 2739.5 |  |  | 2540.5 |  |  | 2837.5 |  |  | 2698 |  |  | 2684.5 |  |  | 2828 |  |  | 2803 |  |  | 2838.5 |  |  | 2781.5 |  |  | 2649.5 |  |  | 2485.5 |  |  | 2692.5 |  |  | 2909.5 |  |  | 2724 |  |  | 2750.5 |  |  | 2722 |  |  | 2810.5 |  |  | 2808 |  |  | 2639 |  |  | 2805 |  |  | 2877.5 |  |  | 2655 |  |  | 2915.5 |  |  | 2821.5 |  |  | 2735.5 |  |  | 2988.5 |  |  | 2591.5 |  |  | 2856 |  |  | 2736.5 |  |  | 2794.5 |  |  | 3006.5 |  |  | 2775 |  |  | 2700.5 |  |  | 2739.5 |  |  | 2771.5 |  |  | 2928.5 |  |  | 2731 |  |  | 2831 |  |  | 2691 |  |  | 2717.5 |  |  | 2902 |  |  | 2782 |  |  | 2917.5 |  |  | 2667.5 |  |  | 2660.5 |  |  | 2753.5 |  |  | 2859.5 |  |  | 2748.5 |  |  | 2814.5 |  |  | 2810.5 |  |  | 2714.5 |  |  | 2712 |  |  | 2714.5 |  |  | 2669 |  |  | 2801.5 |  |  | 2723.5 |  |  | 2836.5 |  |  | 2808.5 |  |  | 2902 |  |  | 2819.5 |  |  | 2766 |  |  | 2658.5 |  |  | 2811.5 |  |  | 2608 |  |  | 2745 |  |  | 2844.5 |  |  | 2823 |  |  | 2791.5 |  |  | 2644.5 |  |  | 2667.5 |  |  | 2687.5 |  |  | 2787.5 |  |  | 2780.5 |  |  | 2638.5 |  |  | 2698 |  |  | 2810.5 |  |  | 2803.5 |  |  | 2838.5 |  |  | 2846.5 |  |  | 2692.5 |  |  | 2784.5 |  |  | 2907.5 |  |  | 2776.5 |  |  | 2979.5 |  |  | 2898.5 |  |  | 2692.5 |  |  | 2602.5 |  |  | 2781 |  |  | 2661.5 |  |  | 2787.5 |  |  | 2859 |  |  | 2690.5 |  |  | 2653.5 |  |  | 2746.5 |  |  | 2620.5 |  |  | 2997 |  |  | 2893.5 |  |  | 2659.5 |  |  | 2661.5 |  |  | 2906.5 |  |  | 2724 |  |  | 2728.5 |  |  | 2889.5 |  |  | 2720.5 |  |  | 2856.5 |  |  | 2690.5 |  |  | 2677.5 |  |  | 2836.5 |  |  | 2702.5 |  |  | 2804.5 |  |  | 2782.5 |  |  | 2848.5 |  |  | 2804 |  |  | 2804.5 |  |  | 2760.5 |  |  | 2807.5 |  |  | 2909.5 |  |  | 2694.5 |  |  | 2689.5 |  |  | 2791 |  |  | 2910.5 |  |  | 2665 |  |  | 2653.5 |  |  | 2864.5 |  |  | 2842.5 |  |  | 2734 |  |  | 2722 |  |  | 2842.5 |  |  | 2837.5 |  |  | 2567.5 |  |  | 2923.5 |  |  | 2730.5 |  |  | 2828.5 |  |  | 2720.5 |  |  | 2868.5 |  |  | 2706.5 |  |  | 2971.5 |  |  | 2773.5 |  |  | 2836.5 |  |  | 2653.5 |  |  | 2830.5 |  |  | 2902.5 |  |  | 2775.5 |  |  | 2740.5 |  |  | 2761.5 |  |  | 2737.5 |  |  | 2713.5 |  |  | 2848.5 |  |  | 2859.5 |  |  | 2723 |  |  | 2813.5 |  |  | 2761.5 |  |  | 2854.5 |  |  | 2806 |  |  | 2849.5 |  |  | 2757.5 |  |  | 2885.5 |  |  | 2825.5 |  |  | 2769 |  |  | 2676.5 |  |  | 2616.5 |  |  | 2672 |  |  | 2742 |  |  | 2755 |  |  | 2815.5 |  |  | 2724.5 |  |  | 2840.5 |  |  | 2962.5 |  |  | 2864 |  |  | 2779.5 |  |  | 2793.5 |  |  | 2673 |  |  | 2687 |  |  | 2816.5 |  |  | 2793.5 |  |  | 2879 |  |  | 2792.5 |  |  | 2902 |  |  | 2712.5 |  |  | 2774.5 |  |  | 2857 |  |  | 2904.5 |  |  | 2777.5 |  |  | 2644.5 |  |  | 2864 |  |  | 2688.5 |  |  | 2657.5 |  |  | 2719.5 |  |  | 2728.5 |  |  | 2789.5 |  |  | 2819.5 |  |  | 2774.5 |  |  | 2879.5 |  |  | 2851.5 |  |  | 2789.5 |  |  | 2703 |  |  | 2730.5 |  |  | 2787.5 |  |  | 2856.5 |  |  | 2824.5 |  |  | 2757.5 |  |  | 2796.5 |  |  | 2808.5 |  |  | 2727.5 |  |  | 2874 |  |  | 2742.5 |  |  | 2703 |  |  | 3029.5 |  |  | 2918.5 |  |  | 2945.5 |  |  | 2734.5 |  |  | 2702.5 |  |  | 2777.5 |  |  | 2621.5 |  |  | 2832.5 |  |  | 2853 |  |  | 2726.5 |  |  | 2790 |  |  | 2642.5 |  |  | 2716.5 |  |  | 2736.5 |  |  | 2818 |  |  | 2733.5 |  |  | 2745.5 |  |  | 2561 |  |  | 2763.5 |  |  | 2775 |  |  | 2802.5 |  |  | 2674.5 |  |  | 2755.5 |  |  | 2753 |  |  | 2904.5 |  |  | 3024.5 |  |  | 2603 |  |  | 2968.5 |  |  | 2756.5 |  |  | 2822 |  |  | 2766.5 |  |  | 2945.5 |  |  | 2901.5 |  |  | 2945.5 |  |  | 2700.5 |  |  | 2939.5 |  |  | 2672.5 |  |  | 2747.5 |  |  | 2692.5 |  |  | 2681.5 |  |  | 2932.5 |  |  | 2868 |  |  | 2816 |  |  | 2926.5 |  |  | 2794.5 |  |  | 2825
95 |  | 2758.5 |  |  | 2814.5 |  |  | 2874 |  |  | 2740.5 |  |  | 2985.5 |  |  | 2862.5 |  |  | 2868.5 |  |  | 2858.5 |  |  | 2783.5 |  |  | 2823.5 |  |  | 2665 |  |  | 2827.5 |  |  | 2824.5 |  |  | 2699.5 |  |  | 2725 |  |  | 2793.5 |  |  | 2892.5 |  |  | 2754.5 |  |  | 2935.5 |  |  | 2726.5 |  |  | 2977.5 |  |  | 2821.5 |  |  | 2920.5 |  |  | 2771.5 |  |  | 2555 |  |  | 2911.5 |  |  | 2839.5 |  |  | 2831.5 |  |  | 2825.5 |  |  | 2632 |  |  | 2831 |  |  | 2947.5 |  |  | 2632.5 |  |  | 2768.5 |  |  | 2706.5 |  |  | 2852 |  |  | 2737.5 |  |  | 3021 |  |  | 2797.5 |  |  | 2798.5 |  |  | 2613.5 |  |  | 2842.5 |  |  | 2651.5 |  |  | 2843 |  |  | 2943.5 |  |  | 2935 |  |  | 2820.5 |  |  | 2878.5 |  |  | 2977.5 |  |  | 2857.5 |  |  | 2664.5 |  |  | 2883.5 |  |  | 2767.5 |  |  | 2789.5 |  |  | 2882.5 |  |  | 2822.5 |  |  | 2720.5 |  |  | 2783 |  |  | 2794.5 |  |  | 2796.5 |  |  | 2766 |  |  | 2804.5 |  |  | 2932.5 |  |  | 2779.5 |  |  | 2718.5 |  |  | 2822 |  |  | 2925.5 |  |  | 2703 |  |  | 2652.5 |  |  | 2835.5 |  |  | 2756 |  |  | 2691.5 |  |  | 2817.5 |  |  | 2978.5 |  |  | 2929 |  |  | 2907 |  |  | 2623.5 |  |  | 2740.5 |  |  | 2717.5 |  |  | 2793.5 |  |  | 2816 |  |  | 2841.5 |  |  | 2849.5 |  |  | 2804.5 |  |  | 2890.5 |  |  | 2679.5 |  |  | 2873.5 |  |  | 2788.5 |  |  | 2785.5 |  |  | 2763.5 |  |  | 2822.5 |  |  | 2840 |  |  | 2792.5 |  |  | 2654 |  |  | 2740 |  |  | 2669 |  |  | 3016.5 |  |  | 2890.5 |  |  | 2729.5 |  |  | 2992.5 |  |  | 2704.5 |  |  | 2732 |  |  | 2773 |  |  | 2787.5 |  |  | 2821.5 |  |  | 2694.5 |  |  | 2783.5 |  |  | 2867.5 |  |  | 2873.5 |  |  | 2927.5 |  |  | 2938.5 |  |  | 2892.5 |  |  | 2752.5 |  |  | 2858.5 |  |  | 2841.5 |  |  | 2857.5 |  |  | 2936.5 |  |  | 2760.5 |  |  | 2814.5 |  |  | 2787.5 |  |  | 2879.5 |  |  | 2880.5 |  |  | 2878.5 |  |  | 2810.5 |  |  | 2807.5 |  |  | 2806 |  |  | 2789.5 |  |  | 2807.5 |  |  | 2754.5 |  |  | 2837.5 |  |  | 2878.5 |  |  | 2779 |  |  | 2717.5 |  |  | 2957.5 |  |  | 2794.5 |  |  | 2739.5 |  |  | 2843 |  |  | 2794.5 |  |  | 2916.5 |  |  | 2664 |  |  | 2876.5 |  |  | 2547 |  |  | 2910 |  |  | 2945.5 |  |  | 2853 |  |  | 2969.5 |  |  | 2793.5 |  |  | 2834.5 |  |  | 2749.5 |  |  | 2834.5 |  |  | 2847.5 |  |  | 2803.5 |  |  | 2837.5 |  |  | 2931.5 |  |  | 2825.5 |  |  | 2954 |  |  | 2672.5 |  |  | 2660 |  |  | 2823.5 |  |  | 2826.5 |  |  | 2742 |  |  | 2809.5 |  |  | 2778.5 |  |  | 2731.5 |  |  | 2669 |  |  | 2785.5 |  |  | 2631.5 |  |  | 2729.5 |  |  | 2899.5 |  |  | 2784.5 |  |  | 2744.5 |  |  | 2761 |  |  | 2782.5 |  |  | 2738.5 |  |  | 2674.5 |  |  | 2857.5 |  |  | 2825.5 |  |  | 2882.5 |  |  | 2798.5 |  |  | 2885 |  |  | 2848.5 |  |  | 2799.5 |  |  | 2837.5 |  |  | 2860.5 |  |  | 2737.5 |  |  | 2872.5 |  |  | 2908.5 |  |  | 2789.5 |  |  | 3002.5 |  |  | 2679.5 |  |  | 2850.5 |  |  | 2577.5 |  |  | 2675.5 |  |  | 2670 |  |  | 2731.5 |  |  | 2842.5 |  |  | 2876.5 |  |  | 2897.5 |  |  | 2894.5 |  |  | 2957.5 |  |  | 2924.5 |  |  | 2797.5 |  |  | 2866.5 |  |  | 2784.5 |  |  | 2707.5 |  |  | 2975.5 |  |  | 2815.5 |  |  | 2770.5 |  |  | 2780.5 |  |  | 2807.5 |  |  | 2795 |  |  | 2978.5 |  |  | 2812.5 |  |  | 2546 |  |  | 2882.5 |  |  | 2934 |  |  | 2585.5 |  |  | 2835.5 |  |  | 2907.5 |  |  | 2916.5 |  |  | 2723.5 |  |  | 2758.5 |  |  | 2751.5 |  |  | 2689.5 |  |  | 2661 |  |  | 2641.5 |  |  | 2604.5 |  |  | 2840.5 |  |  | 2715.5 |  |  | 2776 |  |  | 2786.5 |  |  | 2766.5 |  |  | 2894.5 |  |  | 2793.5 |  |  | 2875.5 |  |  | 2843.5 |  |  | 2841.5 |  |  | 2962.5 |  |  | 2940 |  |  | 2815 |  |  | 2745.5 |  |  | 2709.5 |  |  | 2887.5 |  |  | 2719 |  |  | 3001.5 |  |  | 2831.5 |  |  | 2819.5 |  |  | 2644 |  |  | 2946.5 |  |  | 2811.5 |  |  | 2609.5 |  |  | 2752.5 |  |  | 2829.5 |  |  | 2879.5 |  |  | 2893.5 |  |  | 2842.5 |  |  | 2883.5 |  |  | 2601 |  |  | 2706.5 |  |  | 2868.5 |  |  | 2838.5 |  |  | 2811.5 |  |  | 2701.5 |  |  | 2963 |  |  | 2661.5 |  |  | 2932.5 |  |  | 2875 |  |  | 2918.5 |  |  | 2802.5 |  |  | 2994 |  |  | 2847.5 |  |  | 2862.5 |  |  | 2924.5 |  |  | 2744.5 |  |  | 2775 |  |  | 2811 |  |  | 2833.5 |  |  | 2665.5 |  |  | 2861.5 |  |  | 2747.5 |  |  | 2969.5 |  |  | 2853.5 |  |  | 2804 |  |  | 2730.5 |  |  | 2653.5 |  |  | 2736 |  |  | 2809.5 |  |  | 2580.5 |  |  | 2825 |  |  | 2810.5 |  |  | 2728.5 |  |  | 2833.5 |  |  | 2887 |  |  | 2830.5 |  |  | 2776 |  |  | 2923.5 |  |  | 2693.5 |  |  | 2828.5 |  |  | 2731 |  |  | 2741.5 |  |  | 2940.5 |  |  | 2890.5 |  |  | 2812 |  |  | 2740.5 |  |  | 2660.5 |  |  | 2930.5 |  |  | 2987.5 |  |  | 2847.5 |  |  | 2855 |  |  | 2740.5 |  |  | 2955.5 |  |  | 2811.5 |  |  | 2781 |  |  | 2792 |  |  | 2969.5 |  |  | 2692.5 |  |  | 2602.5 |  |  | 2863.5 |  |  | 2812.5 |  |  | 2750.5 |  |  | 2860.5 |  |  | 2869.5 |  |  | 2717.5 |  |  | 2846.5 |  |  | 2810 |  |  | 2737.5 |  |  | 2781.5 |  |  | 3016.5 |  |  | 2993.5 |  |  | 2834 |  |  | 2744.5 |  |  | 2924.5 |  |  | 2864.5 |  |  | 2639.5 |  |  | 2946.5 |  |  | 2625 |  |  | 2876 |  |  | 2690 |  |  | 2914 |  |  | 2699.5 |  |  | 2760 |  |  | 2828.5 |  |  | 2756 |  |  | 2773.5 |  |  | 2865.5 |  |  | 2781.5 |  |  | 2763.5 |  |  | 2729.5 |  |  | 2852 |  |  | 2791.5 |  |  | 2967.5 |  |  | 2749.5 |  |  | 2817 |  |  | 2917.5 |  |  | 2693.5 |  |  | 2862.5 |  |  | 2859 |  |  | 2755.5 |  |  | 2738.5 |  |  | 2872.5 |  |  | 2695.5 |  |  | 2852.5 |  |  | 2717.5 |  |  | 2850.5 |  |  | 2799.5 |  |  | 2843.5 |  |  | 2643.5 |  |  | 2779 |  |  | 2727.5 |  |  | 2785.5 |  |  | 2706.5 |  |  | 2906.5 |  |  | 2976.5 |  |  | 2792 |  |  | 2867.5 |  |  | 2956 |  |  | 2862 |  |  | 2700.5 |  |  | 2912.5 |  |  | 2700.5 |  |  | 2800 |  |  | 2803.5 |  |  | 2857.5 |  |  | 2800.5 |  |  | 2628 |  |  | 2746.5 |  |  | 2640.5 |  |  | 2753.5 |  |  | 2663.5 |  |  | 2772.5 |  |  | 2775 |  |  | 2711.5 |  |  | 2820 |  |  | 2808.5 |  |  | 2624.5 |  |  | 2798.5 |  |  | 2763 |  |  | 2697.5 |  |  | 2717 |  |  | 2714 |  |  | 2790.5 |  |  | 2690.5 |  |  | 2731.5 |  |  | 2970.5 |  |  | 3012 |  |  | 2881.5 |  |  | 2795.5 |  |  | 2607.5 |  |  | 2778 |  |  | 2852.5 |  |  | 2723.5 |  |  | 2518.5 |  |  | 2867.5 |  |  | 2936 |  |  | 2702.5 |  |  | 2696.5 |  |  | 2758.5 |  |  | 2847.5 |  |  | 2888.5 |  |  | 2844.5 |  |  | 2847 |  |  | 2746.5 |  |  | 2744.5 |  |  | 2791 |  |  | 2647.5 |  |  | 2657.5 |  |  | 2851.5 |  |  | 2778 |  |  | 2901.5 |  |  | 2808.5 |  |  | 2725.5 |  |  | 2788.5 |  |  | 2887.5 |  |  | 2807 |  |  | 2697 |  |  | 2831.5 |  |  | 2839.5 |  |  | 2821.5 |  |  | 2646.5 |  |  | 2584 |  |  | 2914 |  |  | 2772 |  |  | 2926.5 |  |  | 2758 |  |  | 2829.5 |  |  | 2946.5 |  |  | 2889 |  |  | 2633.5 |  |  | 2821.5 |  |  | 2743.5 |  |  | 2869.5 |  |  | 2531.5 |  |  | 2764 |  |  | 2878 |  |  | 2713.5 |  |  | 2896.5 |  |  | 2660 |  |  | 2711.5 |  |  | 2853.5 |  |  | 2733 |  |  | 2968.5 |  |  | 2958.5 |  |  | 2737 |  |  | 2862.5 |  |  | 2832.5 |  |  | 2915 |  |  | 2753.5 |  |  | 2641 |  |  | 2957.5 |  |  | 2953 |  |  | 2727.5 |  |  | 2718.5 |  |  | 2704.5 |  |  | 2787.5 |  |  | 2802.5 |  |  | 2660.5 |  |  | 2787 |  |  | 2661.5 |  |  | 2874.5 |  |  | 2756.5 |  |  | 2786.5 |  |  | 2780.5 |  |  | 2715 |  |  | 2753.5 |  |  | 2814 |  |  | 2909.5 |  |  | 2621.5 |  |  | 2874.5 |  |  | 2886.5 |  |  | 2879.5 |  |  | 2780.5 |  |  | 2696.5 |  |  | 2852.5 |  |  | 2680.5 |  |  | 2704 |  |  | 2875.5 |  |  | 2739 |  |  | 2889 |  |  | 2843.5 |  |  | 2553 |  |  | 2662.5 |  |  | 2876.5 |  |  | 2877.5 |  |  | 2811.5 |  |  | 2924.5 |  |  | 2830.5 |  |  | 2858.5 |  |  | 2730 |  |  | 2966 |  |  | 2702.5 |  |  | 2825.5 |  |  | 2786 |  |  | 2801.5 |  |  | 2725.5 |  |  | 2724.5 |  |  | 2718.5 |  |  | 2751.5 |  |  | 2629 |  |  | 2798.5 |  |  | 2759.5 |  |  | 2730.5 |  |  | 2776 |  |  | 2827.5 |  |  | 2862.5 |  |  | 2884.5 |  |  | 3071.5 |  |  | 2817.5 |  |  | 2707.5 |  |  | 2859.5 |  |  | 2424.5 |  |  | 2765.5 |  |  | 2715 |  |  | 2942.5 |  |  | 2816.5 |  |  | 2853.5 |  |  | 2645.5 |  |  | 2812.5 |  |  | 2682.5 |  |  | 2652.5 |  |  | 2634 |  |  | 2712.5 |  |  | 2770.5 |  |  | 2721.5 |  |  | 2789 |  |  | 2842.5 |  |  | 2679 |  |  | 2676.5 |  |  | 2770.5 |  |  | 2702.5 |  |  | 2827 |  |  | 2620.5 |  |  | 2847 |  |  | 2821 |  |  | 2811.5 |  |  | 2748 |  |  | 2913 |  |  | 2865.5 |  |  | 2935.5 |  |  | 2693.5 |  |  | 2863 |  |  | 2816.5 |  |  | 2641.5 |  |  | 2644.5 |  |  | 2919.5 |  |  | 2731.5 |  |  | 2793.5 |  |  | 2811.5 |  |  | 2812.5 |  |  | 2708 |  |  | 2955.5 |  |  | 2731 |  |  | 2839.5 |  |  | 2726.5 |  |  | 2883.5 |  |  | 2784 |  |  | 2864 |  |  | 2959 |  |  | 2857.5 |  |  | 2823 |  |  | 2823.5 |  |  | 3007.5 |  |  | 2785.5 |  |  | 2771.5 |  |  | 2659.5 |  |  | 2906.5 |  |  | 2896.5 |  |  | 2835.5 |  |  | 2810 |  |  | 2651.5 |  |  | 2705.5 |  |  | 2794.5 |  |  | 2806.5 |  |  | 2740 |  |  | 2792.5 |  |  | 2811 |  |  | 2815.5 |  |  | 2785.5 |  |  | 2769.5 |  |  | 2655.5 |  |  | 2607 |  |  | 2772.5 |  |  | 2577 |  |  | 2761.5 |  |  | 2852.5 |  |  | 2974.5 |  |  | 2740.5 |  |  | 2769.5 |  |  | 2906.5 |  |  | 2788.5 |  |  | 2820.5 |  |  | 2744.5 |  |  | 2694 |  |  | 2795.5 |  |  | 2786.5 |  |  | 2759.5 |  |  | 2844.5 |  |  | 2841.5 |  |  | 2751 |  |  | 2689 |  |  | 2824.5 |  |  | 2765 |  |  | 2951.5 |  |  | 2743.5 |  |  | 2929.5 |  |  | 2766.5 |  |  | 2709.5 |  |  | 2878.5 |  |  | 2855.5 |  |  | 2826.5 |  |  | 2831 |  |  | 2808.5 |  |  | 2998.5 |  |  | 2758.5 |  |  | 2649 |  |  | 2816.5 |  |  | 2693.5 |  |  | 2956 |  |  | 2781 |  |  | 2801.5 |  |  | 2744 |  |  | 2665 |  |  | 2685.5 |  |  | 2885 |  |  | 3008.5 |  |  | 2752.5 |  |  | 2876.5 |  |  | 2694.5 |  |  | 2634.5 |  |  | 2812.5 |  |  | 2578.5 |  |  | 2701.5 |  |  | 2850.5 |  |  | 2746.5 |  |  | 2715 |  |  | 2764 |  |  | 2889.5 |  |  | 2903.5 |  |  | 2707.5 |  |  | 2889.5 |  |  | 2797.5 |  |  | 2887.5 |  |  | 2847.5 |  |  | 2680.5 |  |  | 3041 |  |  | 2701.5 |  |  | 2764 |  |  | 2752.5 |  |  | 2885.5 |  |  | 2864.5 |  |  | 2940 |  |  | 2792.5 |  |  | 2763.5 |  |  | 2826 |  |  | 2858.5 |  |  | 2774.5 |  |  | 2950.5 |  |  | 2782.5 |  |  | 2748.5 |  |  | 2832.5 |  |  | 2905 |  |  | 2663.5 |  |  | 2815.5 |  |  | 2954.5 |  |  | 2847.5 |  |  | 2817 |  |  | 2771.5 |  |  | 2949.5 |  |  | 2725 |  |  | 2786.5 |  |  | 2871.5 |  |  | 2825 |  |  | 2818.5 |  |  | 2911.5 |  |  | 2783.5 |  |  | 2707 |  |  | 2637.5 |  |  | 2774.5 |  |  | 2717 |  |  | 2877.5 |  |  | 2811.5 |  |  | 2839.5 |  |  | 2651.5 |  |  | 2780.5 |  |  | 2959.5 |  |  | 2712.5 |  |  | 2805 |  |  | 2653 |  |  | 2632.5 |  |  | 2839.5 |  |  | 2639.5 |  |  | 2906 |  |  | 2948.5 |  |  | 2765.5 |  |  | 2776.5 |  |  | 2613.5 |  |  | 2803.5 |  |  | 2829.5 |  |  | 2739.5 |  |  | 2832.5 |  |  | 2604.5 |  |  | 2803 |  |  | 2754.5 |  |  | 2621.5 |  |  | 2797.5 |  |  | 2777.5 |  |  | 2931.5 |  |  | 2842.5 |  |  | 2806.5 |  |  | 2789.5 |  |  | 2643.5 |  |  | 2981.5 |  |  | 2803.5 |  |  | 2675.5 |  |  | 2795.5 |  |  | 2893 |  |  | 2835.5 |  |  | 2911.5 |  |  | 2733 |  |  | 2849.5 |  |  | 2848.5 |  |  | 2876 |  |  | 2836.5 |  |  | 2866.5 |  |  | 2985.5 |  |  | 2989 |  |  | 2705.5 |  |  | 2887.5 |  |  | 2763.5 |  |  | 2561.5 |  |  | 2861.5 |  |  | 2724 |  |  | 2708.5 |  |  | 2854 |  |  | 2827 |  |  | 2859.5 |  |  | 2807.5 |  |  | 2696.5 |  |  | 2514.5 |  |  | 2716.5 |  |  | 2948.5 |  |  | 2753 |  |  | 2797.5 |  |  | 2737 |  |  | 2857.5 |  |  | 2855 |  |  | 2678 |  |  | 2852 |  |  | 2898.5 |  |  | 2694 |  |  | 2944.5 |  |  | 2860.5 |  |  | 2774.5 |  |  | 3027.5 |  |  | 2630.5 |  |  | 2885 |  |  | 2775.5 |  |  | 2809.5 |  |  | 3053.5 |  |  | 2822 |  |  | 2747.5 |  |  | 2786.5 |  |  | 2810.5 |  |  | 2975.5 |  |  | 2770 |  |  | 2860 |  |  | 2706 |  |  | 2756.5 |  |  | 2931 |  |  | 2811 |  |  | 2956.5 |  |  | 2693.5 |  |  | 2681.5 |  |  | 2792.5 |  |  | 2888.5 |  |  | 2769.5 |  |  | 2861.5 |  |  | 2849.5 |  |  | 2753.5 |  |  | 2736 |  |  | 2761.5 |  |  | 2708 |  |  | 2830.5 |  |  | 2770.5 |  |  | 2860.5 |  |  | 2855.5 |  |  | 2923 |  |  | 2840.5 |  |  | 2792 |  |  | 2682.5 |  |  | 2835.5 |  |  | 2637 |  |  | 2784 |  |  | 2870.5 |  |  | 2852 |  |  | 2817.5 |  |  | 2673.5 |  |  | 2706.5 |  |  | 2716.5 |  |  | 2813.5 |  |  | 2819.5 |  |  | 2662.5 |  |  | 2722 |  |  | 2849.5 |  |  | 2842.5 |  |  | 2867.5 |  |  | 2872.5 |  |  | 2718.5 |  |  | 2823.5 |  |  | 2946.5 |  |  | 2815.5 |  |  | 3018.5 |  |  | 2924.5 |  |  | 2718.5 |  |  | 2631.5 |  |  | 2807 |  |  | 2685.5 |  |  | 2834.5 |  |  | 2883 |  |  | 2705.5 |  |  | 2677.5 |  |  | 2761.5 |  |  | 2641.5 |  |  | 3044 |  |  | 2908.5 |  |  | 2674.5 |  |  | 2690.5 |  |  | 2921.5 |  |  | 2771 |  |  | 2767.5 |  |  | 2918.5 |  |  | 2767.5 |  |  | 2895.5 |  |  | 2716.5 |  |  | 2716.5 |  |  | 2875.5 |  |  | 2728.5 |  |  | 2825.5 |  |  | 2803.5 |  |  | 2863.5 |  |  | 2843 |  |  | 2819.5 |  |  | 2781.5 |  |  | 2822.5 |  |  | 2956.5 |  |  | 2723.5 |  |  | 2710.5 |  |  | 2838 |  |  | 2939.5 |  |  | 2680 |  |  | 2674.5 |  |  | 2888.5 |  |  | 2881.5 |  |  | 2773 |  |  | 2769 |  |  | 2866.5 |  |  | 2861.5 |  |  | 2606.5 |  |  | 2949.5 |  |  | 2777.5 |  |  | 2852.5 |  |  | 2767.5 |  |  | 2897.5 |  |  | 2727.5 |  |  | 3018.5 |  |  | 2788.5 |  |  | 2875.5 |  |  | 2692.5 |  |  | 2851.5 |  |  | 2941.5 |  |  | 2804.5 |  |  | 2755.5 |  |  | 2790.5 |  |  | 2776.5 |  |  | 2752.5 |  |  | 2887.5 |  |  | 2880.5 |  |  | 2752 |  |  | 2834.5 |  |  | 2776.5 |  |  | 2901.5 |  |  | 2853 |  |  | 2878.5 |  |  | 2783.5 |  |  | 2932.5 |  |  | 2840.5 |  |  | 2808 |  |  | 2697.5 |  |  | 2663.5 |  |  | 2719 |  |  | 2789 |  |  | 2784 |  |  | 2854.5 |  |  | 2739.5 |  |  | 2869.5 |  |  | 3009.5 |  |  | 2893 |  |  | 2805.5 |  |  | 2814.5 |  |  | 2688 |  |  | 2713 |  |  | 2845.5 |  |  | 2808.5 |  |  | 2908 |  |  | 2807.5 |  |  | 2931 |  |  | 2736.5 |  |  | 2813.5 |  |  | 2872 |  |  | 2928.5 |  |  | 2816.5 |  |  | 2691.5 |  |  | 2885 |  |  | 2727.5 |  |  | 2696.5 |  |  | 2758.5 |  |  | 2752.5 |  |  | 2813.5 |  |  | 2866.5 |  |  | 2813.5 |  |  | 2905.5 |  |  | 2875.5 |  |  | 2828.5 |  |  | 2742 |  |  | 2777.5 |  |  | 2802.5 |  |  | 2880.5 |  |  | 2848.5 |  |  | 2796.5 |  |  | 2835.5 |  |  | 2834.5 |  |  | 2774.5 |  |  | 2921 |  |  | 2757.5 |  |  | 2729 |  |  | 3076.5 |  |  | 2944.5 |  |  | 2960.5 |  |  | 2758.5 |  |  | 2726.5 |  |  | 2816.5 |  |  | 2660.5 |  |  | 2856.5 |  |  | 2877 |  |  | 2765.5 |  |  | 2829 |  |  | 2668.5 |  |  | 2745.5 |  |  | 2765.5 |  |  | 2857 |  |  | 2762.5 |  |  | 2769.5 |  |  | 2590 |  |  | 2802.5 |  |  | 2796 |  |  | 2817.5 |  |  | 2700.5 |  |  | 2802.5 |  |  | 2779 |  |  | 2925.5 |  |  | 3045.5 |  |  | 2642 |  |  | 2983.5 |  |  | 2795.5 |  |  | 2848 |  |  | 2792.5 |  |  | 2984.5 |  |  | 2940.5 |  |  | 2984.5 |  |  | 2726.5 |  |  | 2954.5 |  |  | 2698.5 |  |  | 2773.5 |  |  | 2739.5 |  |  | 2728.5 |  |  | 2971.5 |  |  | 2907 |  |  | 2831 |  |  | 2947.5 |  |  | 2809.5 |  |  | 2872
96 |  | 2797.5 |  |  | 2838.5 |  |  | 2898 |  |  | 2755.5 |  |  | 3011.5 |  |  | 2888.5 |  |  | 2907.5 |  |  | 2879.5 |  |  | 2807.5 |  |  | 2847.5 |  |  | 2689 |  |  | 2848.5 |  |  | 2839.5 |  |  | 2723.5 |  |  | 2764 |  |  | 2832.5 |  |  | 2931.5 |  |  | 2778.5 |  |  | 2950.5 |  |  | 2765.5 |  |  | 3024.5 |  |  | 2842.5 |  |  | 2949.5 |  |  | 2792.5 |  |  | 2576 |  |  | 2937.5 |  |  | 2878.5 |  |  | 2860.5 |  |  | 2840.5 |  |  | 2671 |  |  | 2855 |  |  | 2971.5 |  |  | 2658.5 |  |  | 2797.5 |  |  | 2745.5 |  |  | 2876 |  |  | 2776.5 |  |  | 3060 |  |  | 2812.5 |  |  | 2827.5 |  |  | 2639.5 |  |  | 2881.5 |  |  | 2666.5 |  |  | 2882 |  |  | 2969.5 |  |  | 2974 |  |  | 2835.5 |  |  | 2917.5 |  |  | 2992.5 |  |  | 2896.5 |  |  | 2693.5 |  |  | 2909.5 |  |  | 2796.5 |  |  | 2815.5 |  |  | 2911.5 |  |  | 2837.5 |  |  | 2759.5 |  |  | 2804 |  |  | 2818.5 |  |  | 2811.5 |  |  | 2805 |  |  | 2843.5 |  |  | 2971.5 |  |  | 2794.5 |  |  | 2757.5 |  |  | 2861 |  |  | 2949.5 |  |  | 2718 |  |  | 2699.5 |  |  | 2856.5 |  |  | 2780 |  |  | 2717.5 |  |  | 2864.5 |  |  | 3007.5 |  |  | 2968 |  |  | 2931 |  |  | 2644.5 |  |  | 2779.5 |  |  | 2756.5 |  |  | 2808.5 |  |  | 2837 |  |  | 2880.5 |  |  | 2864.5 |  |  | 2825.5 |  |  | 2911.5 |  |  | 2726.5 |  |  | 2920.5 |  |  | 2827.5 |  |  | 2824.5 |  |  | 2792.5 |  |  | 2851.5 |  |  | 2861 |  |  | 2813.5 |  |  | 2693 |  |  | 2787 |  |  | 2684 |  |  | 3040.5 |  |  | 2911.5 |  |  | 2758.5 |  |  | 3007.5 |  |  | 2743.5 |  |  | 2756 |  |  | 2812 |  |  | 2826.5 |  |  | 2850.5 |  |  | 2718.5 |  |  | 2822.5 |  |  | 2906.5 |  |  | 2897.5 |  |  | 2948.5 |  |  | 2953.5 |  |  | 2907.5 |  |  | 2781.5 |  |  | 2882.5 |  |  | 2880.5 |  |  | 2886.5 |  |  | 2975.5 |  |  | 2799.5 |  |  | 2853.5 |  |  | 2816.5 |  |  | 2905.5 |  |  | 2919.5 |  |  | 2902.5 |  |  | 2834.5 |  |  | 2833.5 |  |  | 2821 |  |  | 2828.5 |  |  | 2846.5 |  |  | 2793.5 |  |  | 2861.5 |  |  | 2893.5 |  |  | 2803 |  |  | 2738.5 |  |  | 2972.5 |  |  | 2818.5 |  |  | 2760.5 |  |  | 2858 |  |  | 2833.5 |  |  | 2931.5 |  |  | 2679 |  |  | 2900.5 |  |  | 2586 |  |  | 2936 |  |  | 2984.5 |  |  | 2877 |  |  | 3008.5 |  |  | 2840.5 |  |  | 2860.5 |  |  | 2788.5 |  |  | 2863.5 |  |  | 2871.5 |  |  | 2829.5 |  |  | 2858.5 |  |  | 2952.5 |  |  | 2849.5 |  |  | 2993 |  |  | 2711.5 |  |  | 2699 |  |  | 2862.5 |  |  | 2855.5 |  |  | 2757 |  |  | 2824.5 |  |  | 2825.5 |  |  | 2770.5 |  |  | 2695 |  |  | 2806.5 |  |  | 2646.5 |  |  | 2768.5 |  |  | 2914.5 |  |  | 2823.5 |  |  | 2770.5 |  |  | 2800 |  |  | 2806.5 |  |  | 2777.5 |  |  | 2698.5 |  |  | 2886.5 |  |  | 2864.5 |  |  | 2906.5 |  |  | 2822.5 |  |  | 2932 |  |  | 2877.5 |  |  | 2825.5 |  |  | 2852.5 |  |  | 2884.5 |  |  | 2761.5 |  |  | 2896.5 |  |  | 2932.5 |  |  | 2810.5 |  |  | 3049.5 |  |  | 2700.5 |  |  | 2897.5 |  |  | 2598.5 |  |  | 2714.5 |  |  | 2685 |  |  | 2752.5 |  |  | 2871.5 |  |  | 2900.5 |  |  | 2936.5 |  |  | 2923.5 |  |  | 2983.5 |  |  | 2948.5 |  |  | 2836.5 |  |  | 2913.5 |  |  | 2805.5 |  |  | 2754.5 |  |  | 3014.5 |  |  | 2836.5 |  |  | 2799.5 |  |  | 2819.5 |  |  | 2846.5 |  |  | 2824 |  |  | 3025.5 |  |  | 2841.5 |  |  | 2575 |  |  | 2921.5 |  |  | 2981 |  |  | 2606.5 |  |  | 2850.5 |  |  | 2946.5 |  |  | 2945.5 |  |  | 2738.5 |  |  | 2773.5 |  |  | 2790.5 |  |  | 2728.5 |  |  | 2685 |  |  | 2688.5 |  |  | 2643.5 |  |  | 2866.5 |  |  | 2741.5 |  |  | 2802 |  |  | 2825.5 |  |  | 2790.5 |  |  | 2941.5 |  |  | 2817.5 |  |  | 2901.5 |  |  | 2864.5 |  |  | 2856.5 |  |  | 2977.5 |  |  | 2964 |  |  | 2836 |  |  | 2784.5 |  |  | 2748.5 |  |  | 2908.5 |  |  | 2766 |  |  | 3030.5 |  |  | 2870.5 |  |  | 2845.5 |  |  | 2683 |  |  | 2993.5 |  |  | 2858.5 |  |  | 2633.5 |  |  | 2767.5 |  |  | 2858.5 |  |  | 2903.5 |  |  | 2917.5 |  |  | 2863.5 |  |  | 2907.5 |  |  | 2625 |  |  | 2735.5 |  |  | 2892.5 |  |  | 2853.5 |  |  | 2840.5 |  |  | 2722.5 |  |  | 2992 |  |  | 2676.5 |  |  | 2947.5 |  |  | 2914 |  |  | 2933.5 |  |  | 2831.5 |  |  | 3018 |  |  | 2862.5 |  |  | 2891.5 |  |  | 2939.5 |  |  | 2768.5 |  |  | 2801 |  |  | 2832 |  |  | 2859.5 |  |  | 2704.5 |  |  | 2900.5 |  |  | 2768.5 |  |  | 2993.5 |  |  | 2868.5 |  |  | 2843 |  |  | 2751.5 |  |  | 2692.5 |  |  | 2765 |  |  | 2830.5 |  |  | 2604.5 |  |  | 2864 |  |  | 2839.5 |  |  | 2752.5 |  |  | 2848.5 |  |  | 2908 |  |  | 2859.5 |  |  | 2800 |  |  | 2952.5 |  |  | 2722.5 |  |  | 2867.5 |  |  | 2770 |  |  | 2770.5 |  |  | 2969.5 |  |  | 2911.5 |  |  | 2833 |  |  | 2779.5 |  |  | 2686.5 |  |  | 2945.5 |  |  | 3002.5 |  |  | 2862.5 |  |  | 2884 |  |  | 2769.5 |  |  | 2976.5 |  |  | 2835.5 |  |  | 2820 |  |  | 2831 |  |  | 2984.5 |  |  | 2731.5 |  |  | 2617.5 |  |  | 2902.5 |  |  | 2859.5 |  |  | 2774.5 |  |  | 2884.5 |  |  | 2908.5 |  |  | 2756.5 |  |  | 2872.5 |  |  | 2834 |  |  | 2763.5 |  |  | 2796.5 |  |  | 3063.5 |  |  | 3019.5 |  |  | 2873 |  |  | 2765.5 |  |  | 2953.5 |  |  | 2911.5 |  |  | 2665.5 |  |  | 2975.5 |  |  | 2640 |  |  | 2905 |  |  | 2729 |  |  | 2953 |  |  | 2746.5 |  |  | 2775 |  |  | 2843.5 |  |  | 2777 |  |  | 2802.5 |  |  | 2886.5 |  |  | 2820.5 |  |  | 2787.5 |  |  | 2768.5 |  |  | 2878 |  |  | 2806.5 |  |  | 2993.5 |  |  | 2778.5 |  |  | 2843 |  |  | 2964.5 |  |  | 2732.5 |  |  | 2891.5 |  |  | 2880 |  |  | 2779.5 |  |  | 2753.5 |  |  | 2911.5 |  |  | 2742.5 |  |  | 2873.5 |  |  | 2756.5 |  |  | 2874.5 |  |  | 2823.5 |  |  | 2872.5 |  |  | 2690.5 |  |  | 2803 |  |  | 2756.5 |  |  | 2824.5 |  |  | 2745.5 |  |  | 2945.5 |  |  | 3015.5 |  |  | 2831 |  |  | 2914.5 |  |  | 3003 |  |  | 2901 |  |  | 2747.5 |  |  | 2941.5 |  |  | 2747.5 |  |  | 2815 |  |  | 2842.5 |  |  | 2896.5 |  |  | 2839.5 |  |  | 2667 |  |  | 2785.5 |  |  | 2679.5 |  |  | 2779.5 |  |  | 2702.5 |  |  | 2793.5 |  |  | 2801 |  |  | 2750.5 |  |  | 2846 |  |  | 2834.5 |  |  | 2663.5 |  |  | 2819.5 |  |  | 2784 |  |  | 2736.5 |  |  | 2743 |  |  | 2735 |  |  | 2805.5 |  |  | 2714.5 |  |  | 2755.5 |  |  | 3009.5 |  |  | 3036 |  |  | 2920.5 |  |  | 2834.5 |  |  | 2646.5 |  |  | 2799 |  |  | 2881.5 |  |  | 2738.5 |  |  | 2539.5 |  |  | 2914.5 |  |  | 2957 |  |  | 2741.5 |  |  | 2720.5 |  |  | 2805.5 |  |  | 2894.5 |  |  | 2903.5 |  |  | 2870.5 |  |  | 2876 |  |  | 2772.5 |  |  | 2759.5 |  |  | 2830 |  |  | 2694.5 |  |  | 2696.5 |  |  | 2872.5 |  |  | 2817 |  |  | 2930.5 |  |  | 2837.5 |  |  | 2754.5 |  |  | 2817.5 |  |  | 2916.5 |  |  | 2828 |  |  | 2736 |  |  | 2860.5 |  |  | 2854.5 |  |  | 2860.5 |  |  | 2670.5 |  |  | 2623 |  |  | 2929 |  |  | 2819 |  |  | 2947.5 |  |  | 2782 |  |  | 2868.5 |  |  | 2985.5 |  |  | 2913 |  |  | 2657.5 |  |  | 2850.5 |  |  | 2758.5 |  |  | 2898.5 |  |  | 2560.5 |  |  | 2790 |  |  | 2904 |  |  | 2760.5 |  |  | 2911.5 |  |  | 2686 |  |  | 2758.5 |  |  | 2868.5 |  |  | 2759 |  |  | 2994.5 |  |  | 2997.5 |  |  | 2761 |  |  | 2888.5 |  |  | 2879.5 |  |  | 2944 |  |  | 2792.5 |  |  | 2667 |  |  | 2996.5 |  |  | 2974 |  |  | 2751.5 |  |  | 2744.5 |  |  | 2751.5 |  |  | 2808.5 |  |  | 2841.5 |  |  | 2686.5 |  |  | 2811 |  |  | 2708.5 |  |  | 2903.5 |  |  | 2785.5 |  |  | 2825.5 |  |  | 2819.5 |  |  | 2762 |  |  | 2792.5 |  |  | 2861 |  |  | 2935.5 |  |  | 2660.5 |  |  | 2895.5 |  |  | 2925.5 |  |  | 2918.5 |  |  | 2819.5 |  |  | 2725.5 |  |  | 2891.5 |  |  | 2695.5 |  |  | 2751 |  |  | 2890.5 |  |  | 2778 |  |  | 2936 |  |  | 2858.5 |  |  | 2577 |  |  | 2677.5 |  |  | 2891.5 |  |  | 2906.5 |  |  | 2832.5 |  |  | 2948.5 |  |  | 2869.5 |  |  | 2887.5 |  |  | 2754 |  |  | 2992 |  |  | 2731.5 |  |  | 2854.5 |  |  | 2810 |  |  | 2848.5 |  |  | 2746.5 |  |  | 2763.5 |  |  | 2765.5 |  |  | 2777.5 |  |  | 2658 |  |  | 2837.5 |  |  | 2798.5 |  |  | 2751.5 |  |  | 2802 |  |  | 2874.5 |  |  | 2883.5 |  |  | 2923.5 |  |  | 3110.5 |  |  | 2832.5 |  |  | 2746.5 |  |  | 2888.5 |  |  | 2471.5 |  |  | 2794.5 |  |  | 2754 |  |  | 2981.5 |  |  | 2855.5 |  |  | 2874.5 |  |  | 2674.5 |  |  | 2838.5 |  |  | 2697.5 |  |  | 2676.5 |  |  | 2673 |  |  | 2727.5 |  |  | 2796.5 |  |  | 2760.5 |  |  | 2804 |  |  | 2871.5 |  |  | 2726 |  |  | 2715.5 |  |  | 2794.5 |  |  | 2723.5 |  |  | 2874 |  |  | 2667.5 |  |  | 2868 |  |  | 2868 |  |  | 2826.5 |  |  | 2772 |  |  | 2928 |  |  | 2904.5 |  |  | 2961.5 |  |  | 2719.5 |  |  | 2902 |  |  | 2845.5 |  |  | 2680.5 |  |  | 2691.5 |  |  | 2958.5 |  |  | 2752.5 |  |  | 2808.5 |  |  | 2850.5 |  |  | 2833.5 |  |  | 2747 |  |  | 2994.5 |  |  | 2770 |  |  | 2878.5 |  |  | 2765.5 |  |  | 2922.5 |  |  | 2799 |  |  | 2879 |  |  | 2983 |  |  | 2881.5 |  |  | 2862 |  |  | 2862.5 |  |  | 3036.5 |  |  | 2806.5 |  |  | 2810.5 |  |  | 2685.5 |  |  | 2932.5 |  |  | 2922.5 |  |  | 2874.5 |  |  | 2849 |  |  | 2690.5 |  |  | 2729.5 |  |  | 2833.5 |  |  | 2835.5 |  |  | 2766 |  |  | 2818.5 |  |  | 2850 |  |  | 2830.5 |  |  | 2800.5 |  |  | 2816.5 |  |  | 2681.5 |  |  | 2628 |  |  | 2793.5 |  |  | 2616 |  |  | 2808.5 |  |  | 2876.5 |  |  | 3000.5 |  |  | 2766.5 |  |  | 2808.5 |  |  | 2935.5 |  |  | 2835.5 |  |  | 2835.5 |  |  | 2791.5 |  |  | 2733 |  |  | 2834.5 |  |  | 2807.5 |  |  | 2806.5 |  |  | 2870.5 |  |  | 2862.5 |  |  | 2780 |  |  | 2704 |  |  | 2863.5 |  |  | 2780 |  |  | 2980.5 |  |  | 2782.5 |  |  | 2953.5 |  |  | 2805.5 |  |  | 2733.5 |  |  | 2917.5 |  |  | 2894.5 |  |  | 2865.5 |  |  | 2860 |  |  | 2829.5 |  |  | 3027.5 |  |  | 2773.5 |  |  | 2670 |  |  | 2842.5 |  |  | 2722.5 |  |  | 2977 |  |  | 2820 |  |  | 2840.5 |  |  | 2765 |  |  | 2694 |  |  | 2714.5 |  |  | 2906 |  |  | 3047.5 |  |  | 2767.5 |  |  | 2891.5 |  |  | 2733.5 |  |  | 2663.5 |  |  | 2859.5 |  |  | 2617.5 |  |  | 2716.5 |  |  | 2871.5 |  |  | 2767.5 |  |  | 2744 |  |  | 2788 |  |  | 2936.5 |  |  | 2932.5 |  |  | 2746.5 |  |  | 2913.5 |  |  | 2836.5 |  |  | 2908.5 |  |  | 2876.5 |  |  | 2706.5 |  |  | 3088 |  |  | 2722.5 |  |  | 2803 |  |  | 2767.5 |  |  | 2924.5 |  |  | 2888.5 |  |  | 2964 |  |  | 2831.5 |  |  | 2802.5 |  |  | 2865 |  |  | 2882.5 |  |  | 2789.5 |  |  | 2989.5 |  |  | 2806.5 |  |  | 2777.5 |  |  | 2858.5 |  |  | 2920 |  |  | 2689.5 |  |  | 2830.5 |  |  | 2975.5 |  |  | 2871.5 |  |  | 2838 |  |  | 2786.5 |  |  | 2988.5 |  |  | 2764 |  |  | 2812.5 |  |  | 2886.5 |  |  | 2840 |  |  | 2842.5 |  |  | 2937.5 |  |  | 2830.5 |  |  | 2736 |  |  | 2663.5 |  |  | 2813.5 |  |  | 2741 |  |  | 2924.5 |  |  | 2837.5 |  |  | 2865.5 |  |  | 2675.5 |  |  | 2819.5 |  |  | 3006.5 |  |  | 2741.5 |  |  | 2826 |  |  | 2679 |  |  | 2653.5 |  |  | 2868.5 |  |  | 2668.5 |  |  | 2935 |  |  | 2977.5 |  |  | 2812.5 |  |  | 2823.5 |  |  | 2639.5 |  |  | 2832.5 |  |  | 2876.5 |  |  | 2786.5 |  |  | 2847.5 |  |  | 2651.5 |  |  | 2824 |  |  | 2783.5 |  |  | 2636.5 |  |  | 2812.5 |  |  | 2816.5 |  |  | 2955.5 |  |  | 2857.5 |  |  | 2827.5 |  |  | 2815.5 |  |  | 2658.5 |  |  | 3020.5 |  |  | 2842.5 |  |  | 2704.5 |  |  | 2834.5 |  |  | 2917 |  |  | 2874.5 |  |  | 2935.5 |  |  | 2772 |  |  | 2864.5 |  |  | 2872.5 |  |  | 2897 |  |  | 2875.5 |  |  | 2890.5 |  |  | 3024.5 |  |  | 3028 |  |  | 2744.5 |  |  | 2902.5 |  |  | 2802.5 |  |  | 2600.5 |  |  | 2876.5 |  |  | 2763 |  |  | 2747.5 |  |  | 2893 |  |  | 2866 |  |  | 2874.5 |  |  | 2828.5 |  |  | 2743.5 |  |  | 2543.5 |  |  | 2737.5 |  |  | 2969.5 |  |  | 2782 |  |  | 2826.5 |  |  | 2752 |  |  | 2881.5 |  |  | 2876 |  |  | 2699 |  |  | 2873 |  |  | 2919.5 |  |  | 2715 |  |  | 2973.5 |  |  | 2875.5 |  |  | 2813.5 |  |  | 3074.5 |  |  | 2654.5 |  |  | 2900 |  |  | 2814.5 |  |  | 2835.5 |  |  | 3082.5 |  |  | 2869 |  |  | 2773.5 |  |  | 2801.5 |  |  | 2849.5 |  |  | 2999.5 |  |  | 2817 |  |  | 2899 |  |  | 2745 |  |  | 2777.5 |  |  | 2946 |  |  | 2850 |  |  | 2985.5 |  |  | 2714.5 |  |  | 2707.5 |  |  | 2831.5 |  |  | 2927.5 |  |  | 2784.5 |  |  | 2882.5 |  |  | 2864.5 |  |  | 2792.5 |  |  | 2775 |  |  | 2776.5 |  |  | 2729 |  |  | 2869.5 |  |  | 2809.5 |  |  | 2899.5 |  |  | 2876.5 |  |  | 2949 |  |  | 2887.5 |  |  | 2807 |  |  | 2711.5 |  |  | 2874.5 |  |  | 2684 |  |  | 2810 |  |  | 2896.5 |  |  | 2891 |  |  | 2832.5 |  |  | 2712.5 |  |  | 2732.5 |  |  | 2737.5 |  |  | 2860.5 |  |  | 2845.5 |  |  | 2691.5 |  |  | 2748 |  |  | 2888.5 |  |  | 2866.5 |  |  | 2888.5 |  |  | 2911.5 |  |  | 2757.5 |  |  | 2862.5 |  |  | 2970.5 |  |  | 2830.5 |  |  | 3042.5 |  |  | 2953.5 |  |  | 2757.5 |  |  | 2657.5 |  |  | 2836 |  |  | 2714.5 |  |  | 2860.5 |  |  | 2904 |  |  | 2720.5 |  |  | 2724.5 |  |  | 2776.5 |  |  | 2680.5 |  |  | 3059 |  |  | 2929.5 |  |  | 2713.5 |  |  | 2705.5 |  |  | 2960.5 |  |  | 2810 |  |  | 2791.5 |  |  | 2957.5 |  |  | 2796.5 |  |  | 2934.5 |  |  | 2740.5 |  |  | 2737.5 |  |  | 2896.5 |  |  | 2775.5 |  |  | 2849.5 |  |  | 2842.5 |  |  | 2910.5 |  |  | 2882 |  |  | 2848.5 |  |  | 2802.5 |  |  | 2861.5 |  |  | 2971.5 |  |  | 2770.5 |  |  | 2731.5 |  |  | 2862 |  |  | 2965.5 |  |  | 2709 |  |  | 2695.5 |  |  | 2909.5 |  |  | 2907.5 |  |  | 2820 |  |  | 2784 |  |  | 2890.5 |  |  | 2900.5 |  |  | 2632.5 |  |  | 2970.5 |  |  | 2801.5 |  |  | 2899.5 |  |  | 2793.5 |  |  | 2918.5 |  |  | 2742.5 |  |  | 3047.5 |  |  | 2803.5 |  |  | 2914.5 |  |  | 2707.5 |  |  | 2875.5 |  |  | 2956.5 |  |  | 2843.5 |  |  | 2802.5 |  |  | 2811.5 |  |  | 2815.5 |  |  | 2773.5 |  |  | 2911.5 |  |  | 2901.5 |  |  | 2778 |  |  | 2860.5 |  |  | 2802.5 |  |  | 2922.5 |  |  | 2892 |  |  | 2917.5 |  |  | 2822.5 |  |  | 2953.5 |  |  | 2887.5 |  |  | 2834 |  |  | 2736.5 |  |  | 2692.5 |  |  | 2743 |  |  | 2810 |  |  | 2831 |  |  | 2875.5 |  |  | 2763.5 |  |  | 2893.5 |  |  | 3033.5 |  |  | 2914 |  |  | 2844.5 |  |  | 2835.5 |  |  | 2727 |  |  | 2760 |  |  | 2874.5 |  |  | 2823.5 |  |  | 2947 |  |  | 2846.5 |  |  | 2960 |  |  | 2762.5 |  |  | 2860.5 |  |  | 2896 |  |  | 2943.5 |  |  | 2863.5 |  |  | 2730.5 |  |  | 2900 |  |  | 2766.5 |  |  | 2720.5 |  |  | 2782.5 |  |  | 2767.5 |  |  | 2842.5 |  |  | 2913.5 |  |  | 2852.5 |  |  | 2926.5 |  |  | 2922.5 |  |  | 2867.5 |  |  | 2781 |  |  | 2824.5 |  |  | 2828.5 |  |  | 2901.5 |  |  | 2887.5 |  |  | 2820.5 |  |  | 2850.5 |  |  | 2873.5 |  |  | 2821.5 |  |  | 2960 |  |  | 2796.5 |  |  | 2768 |  |  | 3097.5 |  |  | 2983.5 |  |  | 2975.5 |  |  | 2787.5 |  |  | 2773.5 |  |  | 2855.5 |  |  | 2686.5 |  |  | 2871.5 |  |  | 2924 |  |  | 2804.5 |  |  | 2868 |  |  | 2692.5 |  |  | 2792.5 |  |  | 2804.5 |  |  | 2904 |  |  | 2777.5 |  |  | 2808.5 |  |  | 2637 |  |  | 2841.5 |  |  | 2825 |  |  | 2856.5 |  |  | 2715.5 |  |  | 2828.5 |  |  | 2794 |  |  | 2940.5 |  |  | 3092.5 |  |  | 2681 |  |  | 3007.5 |  |  | 2842.5 |  |  | 2863 |  |  | 2816.5 |  |  | 3013.5 |  |  | 2979.5 |  |  | 3008.5 |  |  | 2765.5 |  |  | 2978.5 |  |  | 2713.5 |  |  | 2799.5 |  |  | 2778.5 |  |  | 2757.5 |  |  | 2997.5 |  |  | 2931 |  |  | 2857 |  |  | 2973.5 |  |  | 2833.5 |  |  | 2911
97 |  | 2823.5 |  |  | 2864.5 |  |  | 2945 |  |  | 2779.5 |  |  | 3058.5 |  |  | 2903.5 |  |  | 2933.5 |  |  | 2918.5 |  |  | 2836.5 |  |  | 2886.5 |  |  | 2715 |  |  | 2869.5 |  |  | 2878.5 |  |  | 2762.5 |  |  | 2788 |  |  | 2853.5 |  |  | 2952.5 |  |  | 2802.5 |  |  | 2976.5 |  |  | 2812.5 |  |  | 3063.5 |  |  | 2881.5 |  |  | 2975.5 |  |  | 2807.5 |  |  | 2623 |  |  | 2976.5 |  |  | 2917.5 |  |  | 2884.5 |  |  | 2869.5 |  |  | 2710 |  |  | 2879 |  |  | 2995.5 |  |  | 2705.5 |  |  | 2826.5 |  |  | 2771.5 |  |  | 2905 |  |  | 2823.5 |  |  | 3089 |  |  | 2851.5 |  |  | 2856.5 |  |  | 2678.5 |  |  | 2907.5 |  |  | 2695.5 |  |  | 2921 |  |  | 2984.5 |  |  | 2998 |  |  | 2874.5 |  |  | 2938.5 |  |  | 3031.5 |  |  | 2922.5 |  |  | 2722.5 |  |  | 2935.5 |  |  | 2835.5 |  |  | 2830.5 |  |  | 2958.5 |  |  | 2852.5 |  |  | 2785.5 |  |  | 2851 |  |  | 2865.5 |  |  | 2837.5 |  |  | 2852 |  |  | 2882.5 |  |  | 2986.5 |  |  | 2815.5 |  |  | 2778.5 |  |  | 2882 |  |  | 2988.5 |  |  | 2757 |  |  | 2723.5 |  |  | 2895.5 |  |  | 2804 |  |  | 2746.5 |  |  | 2903.5 |  |  | 3028.5 |  |  | 2989 |  |  | 2946 |  |  | 2659.5 |  |  | 2826.5 |  |  | 2777.5 |  |  | 2855.5 |  |  | 2861 |  |  | 2895.5 |  |  | 2903.5 |  |  | 2840.5 |  |  | 2937.5 |  |  | 2747.5 |  |  | 2949.5 |  |  | 2866.5 |  |  | 2845.5 |  |  | 2821.5 |  |  | 2866.5 |  |  | 2900 |  |  | 2852.5 |  |  | 2732 |  |  | 2826 |  |  | 2708 |  |  | 3069.5 |  |  | 2940.5 |  |  | 2779.5 |  |  | 3028.5 |  |  | 2772.5 |  |  | 2795 |  |  | 2859 |  |  | 2841.5 |  |  | 2871.5 |  |  | 2744.5 |  |  | 2837.5 |  |  | 2953.5 |  |  | 2936.5 |  |  | 2995.5 |  |  | 2992.5 |  |  | 2946.5 |  |  | 2820.5 |  |  | 2908.5 |  |  | 2906.5 |  |  | 2925.5 |  |  | 2999.5 |  |  | 2823.5 |  |  | 2877.5 |  |  | 2863.5 |  |  | 2944.5 |  |  | 2934.5 |  |  | 2949.5 |  |  | 2863.5 |  |  | 2872.5 |  |  | 2847 |  |  | 2843.5 |  |  | 2870.5 |  |  | 2840.5 |  |  | 2876.5 |  |  | 2914.5 |  |  | 2842 |  |  | 2777.5 |  |  | 2996.5 |  |  | 2842.5 |  |  | 2807.5 |  |  | 2879 |  |  | 2862.5 |  |  | 2946.5 |  |  | 2705 |  |  | 2921.5 |  |  | 2612 |  |  | 2957 |  |  | 3023.5 |  |  | 2924 |  |  | 3047.5 |  |  | 2879.5 |  |  | 2886.5 |  |  | 2827.5 |  |  | 2902.5 |  |  | 2910.5 |  |  | 2844.5 |  |  | 2897.5 |  |  | 2981.5 |  |  | 2888.5 |  |  | 3032 |  |  | 2732.5 |  |  | 2725 |  |  | 2909.5 |  |  | 2876.5 |  |  | 2804 |  |  | 2853.5 |  |  | 2846.5 |  |  | 2794.5 |  |  | 2716 |  |  | 2845.5 |  |  | 2685.5 |  |  | 2794.5 |  |  | 2961.5 |  |  | 2862.5 |  |  | 2785.5 |  |  | 2839 |  |  | 2821.5 |  |  | 2824.5 |  |  | 2713.5 |  |  | 2933.5 |  |  | 2903.5 |  |  | 2932.5 |  |  | 2848.5 |  |  | 2958 |  |  | 2901.5 |  |  | 2872.5 |  |  | 2891.5 |  |  | 2931.5 |  |  | 2800.5 |  |  | 2922.5 |  |  | 2971.5 |  |  | 2836.5 |  |  | 3088.5 |  |  | 2739.5 |  |  | 2918.5 |  |  | 2637.5 |  |  | 2761.5 |  |  | 2706 |  |  | 2778.5 |  |  | 2897.5 |  |  | 2939.5 |  |  | 2962.5 |  |  | 2949.5 |  |  | 2998.5 |  |  | 2995.5 |  |  | 2875.5 |  |  | 2937.5 |  |  | 2844.5 |  |  | 2775.5 |  |  | 3029.5 |  |  | 2851.5 |  |  | 2838.5 |  |  | 2866.5 |  |  | 2893.5 |  |  | 2863 |  |  | 3049.5 |  |  | 2867.5 |  |  | 2604 |  |  | 2942.5 |  |  | 3002 |  |  | 2621.5 |  |  | 2874.5 |  |  | 2970.5 |  |  | 2974.5 |  |  | 2777.5 |  |  | 2799.5 |  |  | 2837.5 |  |  | 2767.5 |  |  | 2709 |  |  | 2727.5 |  |  | 2672.5 |  |  | 2913.5 |  |  | 2756.5 |  |  | 2823 |  |  | 2851.5 |  |  | 2829.5 |  |  | 2970.5 |  |  | 2832.5 |  |  | 2930.5 |  |  | 2911.5 |  |  | 2895.5 |  |  | 2992.5 |  |  | 2979 |  |  | 2862 |  |  | 2813.5 |  |  | 2763.5 |  |  | 2937.5 |  |  | 2805 |  |  | 3045.5 |  |  | 2909.5 |  |  | 2871.5 |  |  | 2722 |  |  | 3008.5 |  |  | 2882.5 |  |  | 2657.5 |  |  | 2788.5 |  |  | 2897.5 |  |  | 2918.5 |  |  | 2941.5 |  |  | 2910.5 |  |  | 2933.5 |  |  | 2646 |  |  | 2774.5 |  |  | 2916.5 |  |  | 2877.5 |  |  | 2861.5 |  |  | 2751.5 |  |  | 3018 |  |  | 2723.5 |  |  | 2962.5 |  |  | 2961 |  |  | 2957.5 |  |  | 2870.5 |  |  | 3057 |  |  | 2909.5 |  |  | 2938.5 |  |  | 2954.5 |  |  | 2807.5 |  |  | 2848 |  |  | 2871 |  |  | 2885.5 |  |  | 2730.5 |  |  | 2924.5 |  |  | 2815.5 |  |  | 3032.5 |  |  | 2915.5 |  |  | 2890 |  |  | 2766.5 |  |  | 2716.5 |  |  | 2812 |  |  | 2859.5 |  |  | 2643.5 |  |  | 2903 |  |  | 2865.5 |  |  | 2778.5 |  |  | 2872.5 |  |  | 2947 |  |  | 2888.5 |  |  | 2826 |  |  | 2978.5 |  |  | 2737.5 |  |  | 2882.5 |  |  | 2785 |  |  | 2791.5 |  |  | 2984.5 |  |  | 2935.5 |  |  | 2862 |  |  | 2808.5 |  |  | 2725.5 |  |  | 2960.5 |  |  | 3017.5 |  |  | 2901.5 |  |  | 2923 |  |  | 2816.5 |  |  | 3002.5 |  |  | 2864.5 |  |  | 2841 |  |  | 2846 |  |  | 2999.5 |  |  | 2778.5 |  |  | 2632.5 |  |  | 2941.5 |  |  | 2874.5 |  |  | 2800.5 |  |  | 2923.5 |  |  | 2932.5 |  |  | 2777.5 |  |  | 2896.5 |  |  | 2881 |  |  | 2787.5 |  |  | 2835.5 |  |  | 3087.5 |  |  | 3058.5 |  |  | 2894 |  |  | 2794.5 |  |  | 2977.5 |  |  | 2937.5 |  |  | 2712.5 |  |  | 3022.5 |  |  | 2679 |  |  | 2929 |  |  | 2758 |  |  | 2968 |  |  | 2785.5 |  |  | 2790 |  |  | 2882.5 |  |  | 2816 |  |  | 2841.5 |  |  | 2933.5 |  |  | 2849.5 |  |  | 2808.5 |  |  | 2789.5 |  |  | 2902 |  |  | 2827.5 |  |  | 3032.5 |  |  | 2793.5 |  |  | 2864 |  |  | 3003.5 |  |  | 2761.5 |  |  | 2915.5 |  |  | 2901 |  |  | 2803.5 |  |  | 2768.5 |  |  | 2937.5 |  |  | 2789.5 |  |  | 2920.5 |  |  | 2795.5 |  |  | 2900.5 |  |  | 2844.5 |  |  | 2901.5 |  |  | 2737.5 |  |  | 2824 |  |  | 2803.5 |  |  | 2863.5 |  |  | 2784.5 |  |  | 2992.5 |  |  | 3054.5 |  |  | 2846 |  |  | 2953.5 |  |  | 3018 |  |  | 2925 |  |  | 2776.5 |  |  | 2980.5 |  |  | 2786.5 |  |  | 2862 |  |  | 2863.5 |  |  | 2917.5 |  |  | 2863.5 |  |  | 2696 |  |  | 2809.5 |  |  | 2708.5 |  |  | 2803.5 |  |  | 2741.5 |  |  | 2840.5 |  |  | 2816 |  |  | 2789.5 |  |  | 2885 |  |  | 2881.5 |  |  | 2702.5 |  |  | 2840.5 |  |  | 2805 |  |  | 2762.5 |  |  | 2767 |  |  | 2782 |  |  | 2831.5 |  |  | 2740.5 |  |  | 2784.5 |  |  | 3048.5 |  |  | 3060 |  |  | 2935.5 |  |  | 2863.5 |  |  | 2685.5 |  |  | 2814 |  |  | 2902.5 |  |  | 2767.5 |  |  | 2578.5 |  |  | 2940.5 |  |  | 2986 |  |  | 2767.5 |  |  | 2767.5 |  |  | 2831.5 |  |  | 2933.5 |  |  | 2924.5 |  |  | 2909.5 |  |  | 2915 |  |  | 2787.5 |  |  | 2798.5 |  |  | 2856 |  |  | 2720.5 |  |  | 2725.5 |  |  | 2896.5 |  |  | 2841 |  |  | 2956.5 |  |  | 2852.5 |  |  | 2793.5 |  |  | 2856.5 |  |  | 2955.5 |  |  | 2875 |  |  | 2762 |  |  | 2875.5 |  |  | 2875.5 |  |  | 2899.5 |  |  | 2709.5 |  |  | 2649 |  |  | 2976 |  |  | 2866 |  |  | 2968.5 |  |  | 2808 |  |  | 2897.5 |  |  | 3011.5 |  |  | 2952 |  |  | 2683.5 |  |  | 2889.5 |  |  | 2797.5 |  |  | 2922.5 |  |  | 2589.5 |  |  | 2829 |  |  | 2919 |  |  | 2775.5 |  |  | 2958.5 |  |  | 2710 |  |  | 2782.5 |  |  | 2915.5 |  |  | 2798 |  |  | 3015.5 |  |  | 3044.5 |  |  | 2808 |  |  | 2914.5 |  |  | 2900.5 |  |  | 2965 |  |  | 2813.5 |  |  | 2688 |  |  | 3035.5 |  |  | 3003 |  |  | 2790.5 |  |  | 2768.5 |  |  | 2772.5 |  |  | 2855.5 |  |  | 2880.5 |  |  | 2733.5 |  |  | 2850 |  |  | 2734.5 |  |  | 2932.5 |  |  | 2824.5 |  |  | 2846.5 |  |  | 2834.5 |  |  | 2801 |  |  | 2831.5 |  |  | 2908 |  |  | 2950.5 |  |  | 2689.5 |  |  | 2934.5 |  |  | 2964.5 |  |  | 2947.5 |  |  | 2845.5 |  |  | 2764.5 |  |  | 2915.5 |  |  | 2710.5 |  |  | 2780 |  |  | 2919.5 |  |  | 2802 |  |  | 2951 |  |  | 2897.5 |  |  | 2603 |  |  | 2703.5 |  |  | 2912.5 |  |  | 2932.5 |  |  | 2847.5 |  |  | 2977.5 |  |  | 2895.5 |  |  | 2926.5 |  |  | 2769 |  |  | 3031 |  |  | 2770.5 |  |  | 2893.5 |  |  | 2836 |  |  | 2874.5 |  |  | 2785.5 |  |  | 2802.5 |  |  | 2812.5 |  |  | 2803.5 |  |  | 2687 |  |  | 2858.5 |  |  | 2824.5 |  |  | 2772.5 |  |  | 2841 |  |  | 2921.5 |  |  | 2904.5 |  |  | 2947.5 |  |  | 3157.5 |  |  | 2847.5 |  |  | 2761.5 |  |  | 2903.5 |  |  | 2518.5 |  |  | 2815.5 |  |  | 2793 |  |  | 2996.5 |  |  | 2902.5 |  |  | 2900.5 |  |  | 2698.5 |  |  | 2867.5 |  |  | 2721.5 |  |  | 2705.5 |  |  | 2699 |  |  | 2748.5 |  |  | 2817.5 |  |  | 2775.5 |  |  | 2825 |  |  | 2900.5 |  |  | 2765 |  |  | 2754.5 |  |  | 2823.5 |  |  | 2762.5 |  |  | 2903 |  |  | 2706.5 |  |  | 2897 |  |  | 2907 |  |  | 2855.5 |  |  | 2787 |  |  | 2967 |  |  | 2933.5 |  |  | 2985.5 |  |  | 2748.5 |  |  | 2941 |  |  | 2874.5 |  |  | 2695.5 |  |  | 2720.5 |  |  | 2984.5 |  |  | 2773.5 |  |  | 2834.5 |  |  | 2889.5 |  |  | 2862.5 |  |  | 2762 |  |  | 3020.5 |  |  | 2794 |  |  | 2917.5 |  |  | 2789.5 |  |  | 2937.5 |  |  | 2823 |  |  | 2905 |  |  | 3012 |  |  | 2896.5 |  |  | 2888 |  |  | 2891.5 |  |  | 3075.5 |  |  | 2845.5 |  |  | 2836.5 |  |  | 2732.5 |  |  | 2979.5 |  |  | 2946.5 |  |  | 2903.5 |  |  | 2875 |  |  | 2729.5 |  |  | 2753.5 |  |  | 2880.5 |  |  | 2850.5 |  |  | 2792 |  |  | 2844.5 |  |  | 2879 |  |  | 2869.5 |  |  | 2815.5 |  |  | 2842.5 |  |  | 2720.5 |  |  | 2657 |  |  | 2819.5 |  |  | 2663 |  |  | 2837.5 |  |  | 2897.5 |  |  | 3021.5 |  |  | 2813.5 |  |  | 2847.5 |  |  | 2974.5 |  |  | 2882.5 |  |  | 2861.5 |  |  | 2830.5 |  |  | 2780 |  |  | 2873.5 |  |  | 2846.5 |  |  | 2827.5 |  |  | 2909.5 |  |  | 2909.5 |  |  | 2801 |  |  | 2743 |  |  | 2902.5 |  |  | 2801 |  |  | 3009.5 |  |  | 2806.5 |  |  | 2982.5 |  |  | 2834.5 |  |  | 2748.5 |  |  | 2941.5 |  |  | 2923.5 |  |  | 2880.5 |  |  | 2899 |  |  | 2876.5 |  |  | 3074.5 |  |  | 2797.5 |  |  | 2709 |  |  | 2857.5 |  |  | 2737.5 |  |  | 3016 |  |  | 2867 |  |  | 2855.5 |  |  | 2791 |  |  | 2709 |  |  | 2729.5 |  |  | 2932 |  |  | 3086.5 |  |  | 2793.5 |  |  | 2938.5 |  |  | 2757.5 |  |  | 2689.5 |  |  | 2888.5 |  |  | 2664.5 |  |  | 2763.5 |  |  | 2910.5 |  |  | 2814.5 |  |  | 2783 |  |  | 2835 |  |  | 2962.5 |  |  | 2953.5 |  |  | 2770.5 |  |  | 2937.5 |  |  | 2851.5 |  |  | 2937.5 |  |  | 2891.5 |  |  | 2745.5 |  |  | 3103 |  |  | 2761.5 |  |  | 2842 |  |  | 2788.5 |  |  | 2945.5 |  |  | 2912.5 |  |  | 2979 |  |  | 2878.5 |  |  | 2849.5 |  |  | 2880 |  |  | 2903.5 |  |  | 2813.5 |  |  | 3028.5 |  |  | 2821.5 |  |  | 2806.5 |  |  | 2897.5 |  |  | 2944 |  |  | 2736.5 |  |  | 2856.5 |  |  | 2990.5 |  |  | 2895.5 |  |  | 2867 |  |  | 2825.5 |  |  | 3003.5 |  |  | 2779 |  |  | 2851.5 |  |  | 2915.5 |  |  | 2861 |  |  | 2868.5 |  |  | 2963.5 |  |  | 2859.5 |  |  | 2775 |  |  | 2692.5 |  |  | 2852.5 |  |  | 2770 |  |  | 2939.5 |  |  | 2861.5 |  |  | 2904.5 |  |  | 2696.5 |  |  | 2843.5 |  |  | 3030.5 |  |  | 2762.5 |  |  | 2865 |  |  | 2703 |  |  | 2682.5 |  |  | 2897.5 |  |  | 2707.5 |  |  | 2982 |  |  | 3024.5 |  |  | 2827.5 |  |  | 2847.5 |  |  | 2678.5 |  |  | 2879.5 |  |  | 2905.5 |  |  | 2815.5 |  |  | 2876.5 |  |  | 2677.5 |  |  | 2848 |  |  | 2804.5 |  |  | 2660.5 |  |  | 2833.5 |  |  | 2837.5 |  |  | 3002.5 |  |  | 2878.5 |  |  | 2866.5 |  |  | 2862.5 |  |  | 2679.5 |  |  | 3059.5 |  |  | 2866.5 |  |  | 2719.5 |  |  | 2855.5 |  |  | 2956 |  |  | 2895.5 |  |  | 2956.5 |  |  | 2796 |  |  | 2890.5 |  |  | 2896.5 |  |  | 2936 |  |  | 2899.5 |  |  | 2916.5 |  |  | 3048.5 |  |  | 3075 |  |  | 2773.5 |  |  | 2923.5 |  |  | 2828.5 |  |  | 2639.5 |  |  | 2900.5 |  |  | 2787 |  |  | 2794.5 |  |  | 2917 |  |  | 2887 |  |  | 2913.5 |  |  | 2867.5 |  |  | 2764.5 |  |  | 2590.5 |  |  | 2766.5 |  |  | 2990.5 |  |  | 2821 |  |  | 2847.5 |  |  | 2767 |  |  | 2910.5 |  |  | 2891 |  |  | 2738 |  |  | 2920 |  |  | 2948.5 |  |  | 2730 |  |  | 3020.5 |  |  | 2901.5 |  |  | 2828.5 |  |  | 3095.5 |  |  | 2693.5 |  |  | 2939 |  |  | 2835.5 |  |  | 2861.5 |  |  | 3121.5 |  |  | 2916 |  |  | 2802.5 |  |  | 2830.5 |  |  | 2873.5 |  |  | 3028.5 |  |  | 2856 |  |  | 2938 |  |  | 2784 |  |  | 2798.5 |  |  | 2967 |  |  | 2897 |  |  | 3024.5 |  |  | 2743.5 |  |  | 2722.5 |  |  | 2870.5 |  |  | 2956.5 |  |  | 2805.5 |  |  | 2921.5 |  |  | 2903.5 |  |  | 2816.5 |  |  | 2790 |  |  | 2823.5 |  |  | 2755 |  |  | 2908.5 |  |  | 2848.5 |  |  | 2920.5 |  |  | 2915.5 |  |  | 2973 |  |  | 2916.5 |  |  | 2831 |  |  | 2726.5 |  |  | 2889.5 |  |  | 2731 |  |  | 2834 |  |  | 2943.5 |  |  | 2906 |  |  | 2853.5 |  |  | 2751.5 |  |  | 2753.5 |  |  | 2766.5 |  |  | 2884.5 |  |  | 2884.5 |  |  | 2717.5 |  |  | 2787 |  |  | 2912.5 |  |  | 2905.5 |  |  | 2927.5 |  |  | 2932.5 |  |  | 2772.5 |  |  | 2886.5 |  |  | 2985.5 |  |  | 2851.5 |  |  | 3068.5 |  |  | 2974.5 |  |  | 2783.5 |  |  | 2696.5 |  |  | 2851 |  |  | 2738.5 |  |  | 2881.5 |  |  | 2933 |  |  | 2744.5 |  |  | 2748.5 |  |  | 2815.5 |  |  | 2706.5 |  |  | 3080 |  |  | 2955.5 |  |  | 2752.5 |  |  | 2731.5 |  |  | 2986.5 |  |  | 2849 |  |  | 2830.5 |  |  | 2978.5 |  |  | 2822.5 |  |  | 2973.5 |  |  | 2779.5 |  |  | 2776.5 |  |  | 2922.5 |  |  | 2814.5 |  |  | 2878.5 |  |  | 2871.5 |  |  | 2949.5 |  |  | 2903 |  |  | 2887.5 |  |  | 2826.5 |  |  | 2900.5 |  |  | 2986.5 |  |  | 2785.5 |  |  | 2770.5 |  |  | 2901 |  |  | 2986.5 |  |  | 2733 |  |  | 2734.5 |  |  | 2924.5 |  |  | 2928.5 |  |  | 2846 |  |  | 2823 |  |  | 2905.5 |  |  | 2929.5 |  |  | 2653.5 |  |  | 3017.5 |  |  | 2825.5 |  |  | 2914.5 |  |  | 2814.5 |  |  | 2933.5 |  |  | 2766.5 |  |  | 3071.5 |  |  | 2827.5 |  |  | 2940.5 |  |  | 2754.5 |  |  | 2899.5 |  |  | 2995.5 |  |  | 2872.5 |  |  | 2826.5 |  |  | 2850.5 |  |  | 2854.5 |  |  | 2812.5 |  |  | 2935.5 |  |  | 2927.5 |  |  | 2825 |  |  | 2881.5 |  |  | 2849.5 |  |  | 2943.5 |  |  | 2939 |  |  | 2946.5 |  |  | 2861.5 |  |  | 2992.5 |  |  | 2902.5 |  |  | 2881 |  |  | 2783.5 |  |  | 2707.5 |  |  | 2767 |  |  | 2849 |  |  | 2857 |  |  | 2890.5 |  |  | 2792.5 |  |  | 2932.5 |  |  | 3054.5 |  |  | 2938 |  |  | 2873.5 |  |  | 2864.5 |  |  | 2756 |  |  | 2789 |  |  | 2913.5 |  |  | 2862.5 |  |  | 2971 |  |  | 2885.5 |  |  | 2981 |  |  | 2783.5 |  |  | 2899.5 |  |  | 2935 |  |  | 2972.5 |  |  | 2910.5 |  |  | 2769.5 |  |  | 2939 |  |  | 2805.5 |  |  | 2735.5 |  |  | 2803.5 |  |  | 2796.5 |  |  | 2881.5 |  |  | 2937.5 |  |  | 2878.5 |  |  | 2973.5 |  |  | 2969.5 |  |  | 2891.5 |  |  | 2810 |  |  | 2839.5 |  |  | 2849.5 |  |  | 2940.5 |  |  | 2913.5 |  |  | 2846.5 |  |  | 2897.5 |  |  | 2912.5 |  |  | 2842.5 |  |  | 2986 |  |  | 2843.5 |  |  | 2797 |  |  | 3136.5 |  |  | 3022.5 |  |  | 3022.5 |  |  | 2826.5 |  |  | 2799.5 |  |  | 2876.5 |  |  | 2710.5 |  |  | 2918.5 |  |  | 2945 |  |  | 2819.5 |  |  | 2907 |  |  | 2721.5 |  |  | 2831.5 |  |  | 2851.5 |  |  | 2919 |  |  | 2798.5 |  |  | 2847.5 |  |  | 2663 |  |  | 2867.5 |  |  | 2864 |  |  | 2871.5 |  |  | 2754.5 |  |  | 2852.5 |  |  | 2833 |  |  | 2964.5 |  |  | 3139.5 |  |  | 2696 |  |  | 3022.5 |  |  | 2868.5 |  |  | 2889 |  |  | 2845.5 |  |  | 3037.5 |  |  | 3003.5 |  |  | 3037.5 |  |  | 2780.5 |  |  | 3017.5 |  |  | 2728.5 |  |  | 2814.5 |  |  | 2817.5 |  |  | 2778.5 |  |  | 3021.5 |  |  | 2960 |  |  | 2883 |  |  | 2994.5 |  |  | 2872.5 |  |  | 2935
98 |  | 2862.5 |  |  | 2903.5 |  |  | 2969 |  |  | 2794.5 |  |  | 3087.5 |  |  | 2927.5 |  |  | 2962.5 |  |  | 2957.5 |  |  | 2883.5 |  |  | 2915.5 |  |  | 2730 |  |  | 2916.5 |  |  | 2893.5 |  |  | 2801.5 |  |  | 2803 |  |  | 2900.5 |  |  | 2976.5 |  |  | 2841.5 |  |  | 3005.5 |  |  | 2827.5 |  |  | 3102.5 |  |  | 2920.5 |  |  | 3022.5 |  |  | 2846.5 |  |  | 2644 |  |  | 3005.5 |  |  | 2943.5 |  |  | 2910.5 |  |  | 2916.5 |  |  | 2739 |  |  | 2908 |  |  | 3034.5 |  |  | 2720.5 |  |  | 2873.5 |  |  | 2795.5 |  |  | 2929 |  |  | 2852.5 |  |  | 3128 |  |  | 2890.5 |  |  | 2877.5 |  |  | 2717.5 |  |  | 2936.5 |  |  | 2721.5 |  |  | 2936 |  |  | 3005.5 |  |  | 3037 |  |  | 2921.5 |  |  | 2964.5 |  |  | 3070.5 |  |  | 2937.5 |  |  | 2751.5 |  |  | 2950.5 |  |  | 2859.5 |  |  | 2854.5 |  |  | 2987.5 |  |  | 2873.5 |  |  | 2806.5 |  |  | 2877 |  |  | 2886.5 |  |  | 2852.5 |  |  | 2899 |  |  | 2906.5 |  |  | 3033.5 |  |  | 2844.5 |  |  | 2802.5 |  |  | 2897 |  |  | 3017.5 |  |  | 2804 |  |  | 2744.5 |  |  | 2921.5 |  |  | 2843 |  |  | 2785.5 |  |  | 2929.5 |  |  | 3057.5 |  |  | 3036 |  |  | 2985 |  |  | 2685.5 |  |  | 2852.5 |  |  | 2792.5 |  |  | 2876.5 |  |  | 2882 |  |  | 2916.5 |  |  | 2924.5 |  |  | 2866.5 |  |  | 2958.5 |  |  | 2771.5 |  |  | 2970.5 |  |  | 2892.5 |  |  | 2871.5 |  |  | 2836.5 |  |  | 2905.5 |  |  | 2924 |  |  | 2881.5 |  |  | 2779 |  |  | 2855 |  |  | 2729 |  |  | 3095.5 |  |  | 2955.5 |  |  | 2805.5 |  |  | 3067.5 |  |  | 2811.5 |  |  | 2821 |  |  | 2898 |  |  | 2880.5 |  |  | 2910.5 |  |  | 2768.5 |  |  | 2876.5 |  |  | 2974.5 |  |  | 2951.5 |  |  | 3034.5 |  |  | 3039.5 |  |  | 2961.5 |  |  | 2844.5 |  |  | 2947.5 |  |  | 2945.5 |  |  | 2972.5 |  |  | 3020.5 |  |  | 2847.5 |  |  | 2906.5 |  |  | 2902.5 |  |  | 2983.5 |  |  | 2949.5 |  |  | 2988.5 |  |  | 2887.5 |  |  | 2896.5 |  |  | 2894 |  |  | 2882.5 |  |  | 2909.5 |  |  | 2866.5 |  |  | 2923.5 |  |  | 2953.5 |  |  | 2868 |  |  | 2816.5 |  |  | 3025.5 |  |  | 2866.5 |  |  | 2846.5 |  |  | 2918 |  |  | 2883.5 |  |  | 2985.5 |  |  | 2734 |  |  | 2968.5 |  |  | 2638 |  |  | 3004 |  |  | 3044.5 |  |  | 2963 |  |  | 3071.5 |  |  | 2926.5 |  |  | 2901.5 |  |  | 2874.5 |  |  | 2931.5 |  |  | 2939.5 |  |  | 2891.5 |  |  | 2921.5 |  |  | 3028.5 |  |  | 2912.5 |  |  | 3053 |  |  | 2758.5 |  |  | 2764 |  |  | 2930.5 |  |  | 2915.5 |  |  | 2843 |  |  | 2882.5 |  |  | 2893.5 |  |  | 2833.5 |  |  | 2755 |  |  | 2860.5 |  |  | 2724.5 |  |  | 2809.5 |  |  | 2985.5 |  |  | 2901.5 |  |  | 2811.5 |  |  | 2854 |  |  | 2842.5 |  |  | 2845.5 |  |  | 2737.5 |  |  | 2972.5 |  |  | 2924.5 |  |  | 2971.5 |  |  | 2869.5 |  |  | 2987 |  |  | 2948.5 |  |  | 2898.5 |  |  | 2938.5 |  |  | 2960.5 |  |  | 2839.5 |  |  | 2961.5 |  |  | 3000.5 |  |  | 2862.5 |  |  | 3127.5 |  |  | 2768.5 |  |  | 2957.5 |  |  | 2658.5 |  |  | 2808.5 |  |  | 2745 |  |  | 2807.5 |  |  | 2936.5 |  |  | 2963.5 |  |  | 3001.5 |  |  | 2996.5 |  |  | 3019.5 |  |  | 3021.5 |  |  | 2896.5 |  |  | 2984.5 |  |  | 2883.5 |  |  | 2790.5 |  |  | 3068.5 |  |  | 2877.5 |  |  | 2864.5 |  |  | 2905.5 |  |  | 2914.5 |  |  | 2889 |  |  | 3075.5 |  |  | 2893.5 |  |  | 2643 |  |  | 2966.5 |  |  | 3023 |  |  | 2636.5 |  |  | 2889.5 |  |  | 2999.5 |  |  | 3000.5 |  |  | 2801.5 |  |  | 2820.5 |  |  | 2858.5 |  |  | 2796.5 |  |  | 2733 |  |  | 2742.5 |  |  | 2701.5 |  |  | 2934.5 |  |  | 2780.5 |  |  | 2849 |  |  | 2877.5 |  |  | 2868.5 |  |  | 2994.5 |  |  | 2861.5 |  |  | 2969.5 |  |  | 2950.5 |  |  | 2921.5 |  |  | 3016.5 |  |  | 3005 |  |  | 2901 |  |  | 2839.5 |  |  | 2810.5 |  |  | 2952.5 |  |  | 2826 |  |  | 3084.5 |  |  | 2948.5 |  |  | 2910.5 |  |  | 2761 |  |  | 3047.5 |  |  | 2903.5 |  |  | 2704.5 |  |  | 2803.5 |  |  | 2936.5 |  |  | 2942.5 |  |  | 2956.5 |  |  | 2934.5 |  |  | 2972.5 |  |  | 2685 |  |  | 2789.5 |  |  | 2963.5 |  |  | 2906.5 |  |  | 2900.5 |  |  | 2780.5 |  |  | 3033 |  |  | 2762.5 |  |  | 2988.5 |  |  | 3000 |  |  | 3004.5 |  |  | 2909.5 |  |  | 3081 |  |  | 2956.5 |  |  | 2967.5 |  |  | 2983.5 |  |  | 2846.5 |  |  | 2887 |  |  | 2895 |  |  | 2909.5 |  |  | 2751.5 |  |  | 2950.5 |  |  | 2839.5 |  |  | 3047.5 |  |  | 2941.5 |  |  | 2929 |  |  | 2781.5 |  |  | 2742.5 |  |  | 2836 |  |  | 2888.5 |  |  | 2682.5 |  |  | 2950 |  |  | 2904.5 |  |  | 2802.5 |  |  | 2901.5 |  |  | 2971 |  |  | 2917.5 |  |  | 2841 |  |  | 3017.5 |  |  | 2758.5 |  |  | 2906.5 |  |  | 2814 |  |  | 2815.5 |  |  | 3031.5 |  |  | 2961.5 |  |  | 2901 |  |  | 2832.5 |  |  | 2746.5 |  |  | 2981.5 |  |  | 3064.5 |  |  | 2940.5 |  |  | 2938 |  |  | 2845.5 |  |  | 3031.5 |  |  | 2893.5 |  |  | 2880 |  |  | 2861 |  |  | 3038.5 |  |  | 2825.5 |  |  | 2671.5 |  |  | 2967.5 |  |  | 2913.5 |  |  | 2839.5 |  |  | 2952.5 |  |  | 2961.5 |  |  | 2806.5 |  |  | 2935.5 |  |  | 2920 |  |  | 2816.5 |  |  | 2861.5 |  |  | 3126.5 |  |  | 3097.5 |  |  | 2918 |  |  | 2833.5 |  |  | 3006.5 |  |  | 2952.5 |  |  | 2751.5 |  |  | 3048.5 |  |  | 2705 |  |  | 2958 |  |  | 2784 |  |  | 3015 |  |  | 2832.5 |  |  | 2829 |  |  | 2921.5 |  |  | 2845 |  |  | 2865.5 |  |  | 2962.5 |  |  | 2888.5 |  |  | 2832.5 |  |  | 2828.5 |  |  | 2941 |  |  | 2842.5 |  |  | 3047.5 |  |  | 2832.5 |  |  | 2893 |  |  | 3050.5 |  |  | 2808.5 |  |  | 2944.5 |  |  | 2922 |  |  | 2842.5 |  |  | 2807.5 |  |  | 2952.5 |  |  | 2813.5 |  |  | 2941.5 |  |  | 2816.5 |  |  | 2926.5 |  |  | 2865.5 |  |  | 2948.5 |  |  | 2776.5 |  |  | 2845 |  |  | 2842.5 |  |  | 2910.5 |  |  | 2810.5 |  |  | 3021.5 |  |  | 3093.5 |  |  | 2867 |  |  | 2982.5 |  |  | 3047 |  |  | 2949 |  |  | 2823.5 |  |  | 3009.5 |  |  | 2812.5 |  |  | 2901 |  |  | 2902.5 |  |  | 2964.5 |  |  | 2889.5 |  |  | 2717 |  |  | 2830.5 |  |  | 2732.5 |  |  | 2832.5 |  |  | 2780.5 |  |  | 2861.5 |  |  | 2855 |  |  | 2813.5 |  |  | 2924 |  |  | 2905.5 |  |  | 2723.5 |  |  | 2861.5 |  |  | 2829 |  |  | 2801.5 |  |  | 2788 |  |  | 2797 |  |  | 2852.5 |  |  | 2769.5 |  |  | 2810.5 |  |  | 3087.5 |  |  | 3075 |  |  | 2974.5 |  |  | 2902.5 |  |  | 2714.5 |  |  | 2861 |  |  | 2949.5 |  |  | 2791.5 |  |  | 2599.5 |  |  | 2964.5 |  |  | 3025 |  |  | 2782.5 |  |  | 2806.5 |  |  | 2878.5 |  |  | 2980.5 |  |  | 2971.5 |  |  | 2933.5 |  |  | 2954 |  |  | 2813.5 |  |  | 2837.5 |  |  | 2877 |  |  | 2735.5 |  |  | 2746.5 |  |  | 2943.5 |  |  | 2880 |  |  | 3003.5 |  |  | 2876.5 |  |  | 2832.5 |  |  | 2895.5 |  |  | 2994.5 |  |  | 2914 |  |  | 2783 |  |  | 2890.5 |  |  | 2914.5 |  |  | 2920.5 |  |  | 2730.5 |  |  | 2675 |  |  | 3015 |  |  | 2887 |  |  | 2997.5 |  |  | 2823 |  |  | 2912.5 |  |  | 3058.5 |  |  | 2973 |  |  | 2709.5 |  |  | 2913.5 |  |  | 2823.5 |  |  | 2937.5 |  |  | 2615.5 |  |  | 2868 |  |  | 2943 |  |  | 2804.5 |  |  | 2984.5 |  |  | 2734 |  |  | 2811.5 |  |  | 2930.5 |  |  | 2824 |  |  | 3054.5 |  |  | 3068.5 |  |  | 2847 |  |  | 2943.5 |  |  | 2939.5 |  |  | 2989 |  |  | 2842.5 |  |  | 2714 |  |  | 3074.5 |  |  | 3032 |  |  | 2837.5 |  |  | 2807.5 |  |  | 2811.5 |  |  | 2884.5 |  |  | 2919.5 |  |  | 2759.5 |  |  | 2879 |  |  | 2773.5 |  |  | 2953.5 |  |  | 2850.5 |  |  | 2893.5 |  |  | 2849.5 |  |  | 2830 |  |  | 2870.5 |  |  | 2947 |  |  | 2989.5 |  |  | 2715.5 |  |  | 2958.5 |  |  | 2985.5 |  |  | 2971.5 |  |  | 2869.5 |  |  | 2811.5 |  |  | 2941.5 |  |  | 2731.5 |  |  | 2827 |  |  | 2945.5 |  |  | 2849 |  |  | 2975 |  |  | 2918.5 |  |  | 2624 |  |  | 2750.5 |  |  | 2938.5 |  |  | 2971.5 |  |  | 2886.5 |  |  | 3003.5 |  |  | 2924.5 |  |  | 2973.5 |  |  | 2808 |  |  | 3070 |  |  | 2809.5 |  |  | 2932.5 |  |  | 2860 |  |  | 2895.5 |  |  | 2800.5 |  |  | 2831.5 |  |  | 2827.5 |  |  | 2824.5 |  |  | 2726 |  |  | 2897.5 |  |  | 2845.5 |  |  | 2819.5 |  |  | 2888 |  |  | 2947.5 |  |  | 2943.5 |  |  | 2971.5 |  |  | 3204.5 |  |  | 2886.5 |  |  | 2785.5 |  |  | 2927.5 |  |  | 2565.5 |  |  | 2862.5 |  |  | 2808 |  |  | 3022.5 |  |  | 2917.5 |  |  | 2915.5 |  |  | 2719.5 |  |  | 2914.5 |  |  | 2742.5 |  |  | 2752.5 |  |  | 2738 |  |  | 2763.5 |  |  | 2846.5 |  |  | 2814.5 |  |  | 2854 |  |  | 2926.5 |  |  | 2780 |  |  | 2783.5 |  |  | 2862.5 |  |  | 2786.5 |  |  | 2950 |  |  | 2730.5 |  |  | 2918 |  |  | 2946 |  |  | 2881.5 |  |  | 2808 |  |  | 2991 |  |  | 2972.5 |  |  | 3009.5 |  |  | 2787.5 |  |  | 2988 |  |  | 2898.5 |  |  | 2724.5 |  |  | 2759.5 |  |  | 3013.5 |  |  | 2820.5 |  |  | 2855.5 |  |  | 2928.5 |  |  | 2891.5 |  |  | 2783 |  |  | 3046.5 |  |  | 2820 |  |  | 2938.5 |  |  | 2818.5 |  |  | 2961.5 |  |  | 2838 |  |  | 2944 |  |  | 3051 |  |  | 2925.5 |  |  | 2927 |  |  | 2906.5 |  |  | 3104.5 |  |  | 2860.5 |  |  | 2883.5 |  |  | 2758.5 |  |  | 2994.5 |  |  | 2967.5 |  |  | 2927.5 |  |  | 2901 |  |  | 2744.5 |  |  | 2779.5 |  |  | 2895.5 |  |  | 2865.5 |  |  | 2813 |  |  | 2873.5 |  |  | 2903 |  |  | 2916.5 |  |  | 2854.5 |  |  | 2889.5 |  |  | 2759.5 |  |  | 2696 |  |  | 2866.5 |  |  | 2692 |  |  | 2852.5 |  |  | 2921.5 |  |  | 3036.5 |  |  | 2860.5 |  |  | 2886.5 |  |  | 3000.5 |  |  | 2908.5 |  |  | 2908.5 |  |  | 2869.5 |  |  | 2801 |  |  | 2902.5 |  |  | 2875.5 |  |  | 2874.5 |  |  | 2935.5 |  |  | 2935.5 |  |  | 2816 |  |  | 2790 |  |  | 2931.5 |  |  | 2827 |  |  | 3048.5 |  |  | 2832.5 |  |  | 3011.5 |  |  | 2863.5 |  |  | 2787.5 |  |  | 2988.5 |  |  | 2944.5 |  |  | 2909.5 |  |  | 2914 |  |  | 2923.5 |  |  | 3113.5 |  |  | 2836.5 |  |  | 2730 |  |  | 2896.5 |  |  | 2784.5 |  |  | 3042 |  |  | 2891 |  |  | 2902.5 |  |  | 2830 |  |  | 2735 |  |  | 2776.5 |  |  | 2953 |  |  | 3125.5 |  |  | 2840.5 |  |  | 2962.5 |  |  | 2796.5 |  |  | 2713.5 |  |  | 2927.5 |  |  | 2679.5 |  |  | 2784.5 |  |  | 2939.5 |  |  | 2843.5 |  |  | 2807 |  |  | 2856 |  |  | 2983.5 |  |  | 2977.5 |  |  | 2791.5 |  |  | 2952.5 |  |  | 2898.5 |  |  | 2963.5 |  |  | 2906.5 |  |  | 2760.5 |  |  | 3127 |  |  | 2790.5 |  |  | 2863 |  |  | 2835.5 |  |  | 2971.5 |  |  | 2936.5 |  |  | 3008 |  |  | 2917.5 |  |  | 2888.5 |  |  | 2904 |  |  | 2918.5 |  |  | 2839.5 |  |  | 3054.5 |  |  | 2860.5 |  |  | 2845.5 |  |  | 2923.5 |  |  | 2983 |  |  | 2775.5 |  |  | 2903.5 |  |  | 3029.5 |  |  | 2919.5 |  |  | 2896 |  |  | 2854.5 |  |  | 3032.5 |  |  | 2803 |  |  | 2890.5 |  |  | 2962.5 |  |  | 2900 |  |  | 2894.5 |  |  | 2987.5 |  |  | 2906.5 |  |  | 2796 |  |  | 2731.5 |  |  | 2878.5 |  |  | 2796 |  |  | 2960.5 |  |  | 2882.5 |  |  | 2925.5 |  |  | 2720.5 |  |  | 2882.5 |  |  | 3059.5 |  |  | 2786.5 |  |  | 2894 |  |  | 2742 |  |  | 2706.5 |  |  | 2921.5 |  |  | 2746.5 |  |  | 3008 |  |  | 3050.5 |  |  | 2866.5 |  |  | 2871.5 |  |  | 2707.5 |  |  | 2894.5 |  |  | 2952.5 |  |  | 2854.5 |  |  | 2900.5 |  |  | 2692.5 |  |  | 2895 |  |  | 2819.5 |  |  | 2699.5 |  |  | 2857.5 |  |  | 2852.5 |  |  | 3028.5 |  |  | 2917.5 |  |  | 2892.5 |  |  | 2877.5 |  |  | 2708.5 |  |  | 3098.5 |  |  | 2887.5 |  |  | 2758.5 |  |  | 2894.5 |  |  | 2980 |  |  | 2916.5 |  |  | 2985.5 |  |  | 2822 |  |  | 2914.5 |  |  | 2922.5 |  |  | 2960 |  |  | 2946.5 |  |  | 2942.5 |  |  | 3063.5 |  |  | 3101 |  |  | 2788.5 |  |  | 2962.5 |  |  | 2849.5 |  |  | 2686.5 |  |  | 2921.5 |  |  | 2802 |  |  | 2818.5 |  |  | 2956 |  |  | 2916 |  |  | 2937.5 |  |  | 2888.5 |  |  | 2788.5 |  |  | 2616.5 |  |  | 2781.5 |  |  | 3014.5 |  |  | 2845 |  |  | 2886.5 |  |  | 2814 |  |  | 2957.5 |  |  | 2920 |  |  | 2753 |  |  | 2946 |  |  | 2977.5 |  |  | 2745 |  |  | 3059.5 |  |  | 2940.5 |  |  | 2867.5 |  |  | 3124.5 |  |  | 2717.5 |  |  | 2986 |  |  | 2874.5 |  |  | 2908.5 |  |  | 3150.5 |  |  | 2942 |  |  | 2817.5 |  |  | 2869.5 |  |  | 2888.5 |  |  | 3049.5 |  |  | 2877 |  |  | 2953 |  |  | 2813 |  |  | 2827.5 |  |  | 2993 |  |  | 2912 |  |  | 3071.5 |  |  | 2772.5 |  |  | 2751.5 |  |  | 2917.5 |  |  | 2980.5 |  |  | 2826.5 |  |  | 2968.5 |  |  | 2918.5 |  |  | 2840.5 |  |  | 2814 |  |  | 2852.5 |  |  | 2781 |  |  | 2929.5 |  |  | 2877.5 |  |  | 2946.5 |  |  | 2930.5 |  |  | 2999 |  |  | 2940.5 |  |  | 2860 |  |  | 2752.5 |  |  | 2928.5 |  |  | 2746 |  |  | 2858 |  |  | 2958.5 |  |  | 2953 |  |  | 2892.5 |  |  | 2790.5 |  |  | 2774.5 |  |  | 2790.5 |  |  | 2899.5 |  |  | 2913.5 |  |  | 2746.5 |  |  | 2826 |  |  | 2938.5 |  |  | 2920.5 |  |  | 2953.5 |  |  | 2971.5 |  |  | 2819.5 |  |  | 2925.5 |  |  | 3009.5 |  |  | 2866.5 |  |  | 3092.5 |  |  | 3003.5 |  |  | 2804.5 |  |  | 2711.5 |  |  | 2872 |  |  | 2759.5 |  |  | 2896.5 |  |  | 2962 |  |  | 2765.5 |  |  | 2795.5 |  |  | 2841.5 |  |  | 2721.5 |  |  | 3101 |  |  | 2981.5 |  |  | 2767.5 |  |  | 2770.5 |  |  | 3015.5 |  |  | 2888 |  |  | 2869.5 |  |  | 3002.5 |  |  | 2861.5 |  |  | 2994.5 |  |  | 2818.5 |  |  | 2802.5 |  |  | 2946.5 |  |  | 2853.5 |  |  | 2925.5 |  |  | 2892.5 |  |  | 2996.5 |  |  | 2942 |  |  | 2908.5 |  |  | 2847.5 |  |  | 2915.5 |  |  | 3025.5 |  |  | 2824.5 |  |  | 2791.5 |  |  | 2930 |  |  | 3007.5 |  |  | 2757 |  |  | 2773.5 |  |  | 2939.5 |  |  | 2957.5 |  |  | 2861 |  |  | 2852 |  |  | 2952.5 |  |  | 2958.5 |  |  | 2677.5 |  |  | 3043.5 |  |  | 2849.5 |  |  | 2943.5 |  |  | 2838.5 |  |  | 2972.5 |  |  | 2795.5 |  |  | 3097.5 |  |  | 2848.5 |  |  | 2955.5 |  |  | 2793.5 |  |  | 2920.5 |  |  | 3010.5 |  |  | 2896.5 |  |  | 2852.5 |  |  | 2874.5 |  |  | 2893.5 |  |  | 2851.5 |  |  | 2961.5 |  |  | 2953.5 |  |  | 2849 |  |  | 2902.5 |  |  | 2896.5 |  |  | 2972.5 |  |  | 2954 |  |  | 2961.5 |  |  | 2885.5 |  |  | 3007.5 |  |  | 2931.5 |  |  | 2928 |  |  | 2812.5 |  |  | 2722.5 |  |  | 2796 |  |  | 2878 |  |  | 2896 |  |  | 2929.5 |  |  | 2816.5 |  |  | 2979.5 |  |  | 3093.5 |  |  | 2977 |  |  | 2912.5 |  |  | 2890.5 |  |  | 2782 |  |  | 2813 |  |  | 2937.5 |  |  | 2901.5 |  |  | 3010 |  |  | 2924.5 |  |  | 3020 |  |  | 2807.5 |  |  | 2914.5 |  |  | 2959 |  |  | 2993.5 |  |  | 2934.5 |  |  | 2784.5 |  |  | 2960 |  |  | 2829.5 |  |  | 2782.5 |  |  | 2832.5 |  |  | 2825.5 |  |  | 2896.5 |  |  | 2952.5 |  |  | 2902.5 |  |  | 2997.5 |  |  | 2990.5 |  |  | 2920.5 |  |  | 2849 |  |  | 2886.5 |  |  | 2888.5 |  |  | 2979.5 |  |  | 2960.5 |  |  | 2872.5 |  |  | 2936.5 |  |  | 2938.5 |  |  | 2868.5 |  |  | 3025 |  |  | 2867.5 |  |  | 2818 |  |  | 3165.5 |  |  | 3069.5 |  |  | 3061.5 |  |  | 2847.5 |  |  | 2846.5 |  |  | 2915.5 |  |  | 2739.5 |  |  | 2957.5 |  |  | 2984 |  |  | 2843.5 |  |  | 2946 |  |  | 2768.5 |  |  | 2855.5 |  |  | 2877.5 |  |  | 2966 |  |  | 2813.5 |  |  | 2894.5 |  |  | 2678 |  |  | 2893.5 |  |  | 2893 |  |  | 2892.5 |  |  | 2783.5 |  |  | 2867.5 |  |  | 2857 |  |  | 2979.5 |  |  | 3165.5 |  |  | 2735 |  |  | 3061.5 |  |  | 2894.5 |  |  | 2918 |  |  | 2892.5 |  |  | 3058.5 |  |  | 3032.5 |  |  | 3052.5 |  |  | 2819.5 |  |  | 3041.5 |  |  | 2767.5 |  |  | 2853.5 |  |  | 2843.5 |  |  | 2799.5 |  |  | 3047.5 |  |  | 2999 |  |  | 2898 |  |  | 3015.5 |  |  | 2901.5 |  |  | 2964
99 |  | 2888.5 |  |  | 2942.5 |  |  | 2998 |  |  | 2833.5 |  |  | 3108.5 |  |  | 2966.5 |  |  | 2977.5 |  |  | 2981.5 |  |  | 2922.5 |  |  | 2939.5 |  |  | 2745 |  |  | 2945.5 |  |  | 2932.5 |  |  | 2816.5 |  |  | 2824 |  |  | 2926.5 |  |  | 2991.5 |  |  | 2880.5 |  |  | 3034.5 |  |  | 2853.5 |  |  | 3117.5 |  |  | 2946.5 |  |  | 3061.5 |  |  | 2885.5 |  |  | 2673 |  |  | 3020.5 |  |  | 2967.5 |  |  | 2934.5 |  |  | 2931.5 |  |  | 2763 |  |  | 2929 |  |  | 3073.5 |  |  | 2746.5 |  |  | 2912.5 |  |  | 2816.5 |  |  | 2958 |  |  | 2891.5 |  |  | 3167 |  |  | 2929.5 |  |  | 2903.5 |  |  | 2738.5 |  |  | 2960.5 |  |  | 2742.5 |  |  | 2960 |  |  | 3026.5 |  |  | 3052 |  |  | 2945.5 |  |  | 3003.5 |  |  | 3096.5 |  |  | 2958.5 |  |  | 2798.5 |  |  | 2971.5 |  |  | 2874.5 |  |  | 2878.5 |  |  | 3011.5 |  |  | 2920.5 |  |  | 2835.5 |  |  | 2898 |  |  | 2925.5 |  |  | 2878.5 |  |  | 2925 |  |  | 2935.5 |  |  | 3072.5 |  |  | 2873.5 |  |  | 2828.5 |  |  | 2936 |  |  | 3032.5 |  |  | 2828 |  |  | 2759.5 |  |  | 2947.5 |  |  | 2864 |  |  | 2824.5 |  |  | 2950.5 |  |  | 3086.5 |  |  | 3065 |  |  | 3011 |  |  | 2724.5 |  |  | 2873.5 |  |  | 2807.5 |  |  | 2923.5 |  |  | 2911 |  |  | 2931.5 |  |  | 2953.5 |  |  | 2913.5 |  |  | 2982.5 |  |  | 2797.5 |  |  | 2991.5 |  |  | 2939.5 |  |  | 2897.5 |  |  | 2860.5 |  |  | 2934.5 |  |  | 2971 |  |  | 2902.5 |  |  | 2808 |  |  | 2894 |  |  | 2768 |  |  | 3134.5 |  |  | 2981.5 |  |  | 2844.5 |  |  | 3082.5 |  |  | 2850.5 |  |  | 2847 |  |  | 2945 |  |  | 2895.5 |  |  | 2949.5 |  |  | 2807.5 |  |  | 2891.5 |  |  | 3021.5 |  |  | 2966.5 |  |  | 3060.5 |  |  | 3063.5 |  |  | 2987.5 |  |  | 2891.5 |  |  | 2986.5 |  |  | 2984.5 |  |  | 3019.5 |  |  | 3067.5 |  |  | 2886.5 |  |  | 2930.5 |  |  | 2941.5 |  |  | 3030.5 |  |  | 2970.5 |  |  | 3014.5 |  |  | 2926.5 |  |  | 2911.5 |  |  | 2909 |  |  | 2897.5 |  |  | 2948.5 |  |  | 2887.5 |  |  | 2952.5 |  |  | 2992.5 |  |  | 2889 |  |  | 2831.5 |  |  | 3064.5 |  |  | 2895.5 |  |  | 2893.5 |  |  | 2942 |  |  | 2898.5 |  |  | 3024.5 |  |  | 2760 |  |  | 3015.5 |  |  | 2685 |  |  | 3033 |  |  | 3065.5 |  |  | 2989 |  |  | 3095.5 |  |  | 2973.5 |  |  | 2925.5 |  |  | 2903.5 |  |  | 2970.5 |  |  | 2963.5 |  |  | 2930.5 |  |  | 2945.5 |  |  | 3067.5 |  |  | 2938.5 |  |  | 3077 |  |  | 2787.5 |  |  | 2803 |  |  | 2977.5 |  |  | 2939.5 |  |  | 2890 |  |  | 2911.5 |  |  | 2919.5 |  |  | 2854.5 |  |  | 2781 |  |  | 2899.5 |  |  | 2748.5 |  |  | 2838.5 |  |  | 3024.5 |  |  | 2930.5 |  |  | 2835.5 |  |  | 2875 |  |  | 2866.5 |  |  | 2871.5 |  |  | 2763.5 |  |  | 3011.5 |  |  | 2948.5 |  |  | 3010.5 |  |  | 2890.5 |  |  | 3016 |  |  | 2974.5 |  |  | 2919.5 |  |  | 2977.5 |  |  | 2975.5 |  |  | 2868.5 |  |  | 3000.5 |  |  | 3039.5 |  |  | 2901.5 |  |  | 3151.5 |  |  | 2792.5 |  |  | 2996.5 |  |  | 2687.5 |  |  | 2855.5 |  |  | 2784 |  |  | 2828.5 |  |  | 2975.5 |  |  | 3002.5 |  |  | 3025.5 |  |  | 3017.5 |  |  | 3058.5 |  |  | 3042.5 |  |  | 2920.5 |  |  | 3005.5 |  |  | 2912.5 |  |  | 2805.5 |  |  | 3092.5 |  |  | 2898.5 |  |  | 2903.5 |  |  | 2920.5 |  |  | 2943.5 |  |  | 2913 |  |  | 3101.5 |  |  | 2908.5 |  |  | 2664 |  |  | 2995.5 |  |  | 3049 |  |  | 2665.5 |  |  | 2910.5 |  |  | 3023.5 |  |  | 3039.5 |  |  | 2848.5 |  |  | 2849.5 |  |  | 2887.5 |  |  | 2835.5 |  |  | 2780 |  |  | 2789.5 |  |  | 2740.5 |  |  | 2973.5 |  |  | 2806.5 |  |  | 2870 |  |  | 2924.5 |  |  | 2889.5 |  |  | 3023.5 |  |  | 2890.5 |  |  | 3008.5 |  |  | 2976.5 |  |  | 2950.5 |  |  | 3037.5 |  |  | 3031 |  |  | 2927 |  |  | 2886.5 |  |  | 2839.5 |  |  | 2991.5 |  |  | 2847 |  |  | 3123.5 |  |  | 2995.5 |  |  | 2957.5 |  |  | 2782 |  |  | 3062.5 |  |  | 2927.5 |  |  | 2743.5 |  |  | 2850.5 |  |  | 2962.5 |  |  | 2989.5 |  |  | 2982.5 |  |  | 2973.5 |  |  | 2996.5 |  |  | 2700 |  |  | 2810.5 |  |  | 3002.5 |  |  | 2932.5 |  |  | 2939.5 |  |  | 2795.5 |  |  | 3057 |  |  | 2801.5 |  |  | 3027.5 |  |  | 3015 |  |  | 3043.5 |  |  | 2935.5 |  |  | 3105 |  |  | 2977.5 |  |  | 2991.5 |  |  | 3004.5 |  |  | 2867.5 |  |  | 2911 |  |  | 2919 |  |  | 2948.5 |  |  | 2766.5 |  |  | 2979.5 |  |  | 2860.5 |  |  | 3094.5 |  |  | 2962.5 |  |  | 2968 |  |  | 2805.5 |  |  | 2757.5 |  |  | 2860 |  |  | 2903.5 |  |  | 2708.5 |  |  | 2979 |  |  | 2925.5 |  |  | 2823.5 |  |  | 2916.5 |  |  | 3010 |  |  | 2941.5 |  |  | 2888 |  |  | 3041.5 |  |  | 2773.5 |  |  | 2930.5 |  |  | 2829 |  |  | 2844.5 |  |  | 3078.5 |  |  | 3008.5 |  |  | 2940 |  |  | 2879.5 |  |  | 2767.5 |  |  | 3020.5 |  |  | 3093.5 |  |  | 2987.5 |  |  | 2964 |  |  | 2892.5 |  |  | 3052.5 |  |  | 2914.5 |  |  | 2901 |  |  | 2908 |  |  | 3085.5 |  |  | 2872.5 |  |  | 2710.5 |  |  | 2993.5 |  |  | 2942.5 |  |  | 2860.5 |  |  | 2973.5 |  |  | 3000.5 |  |  | 2845.5 |  |  | 2974.5 |  |  | 2959 |  |  | 2845.5 |  |  | 2890.5 |  |  | 3152.5 |  |  | 3136.5 |  |  | 2965 |  |  | 2880.5 |  |  | 3045.5 |  |  | 2991.5 |  |  | 2775.5 |  |  | 3072.5 |  |  | 2720 |  |  | 2987 |  |  | 2799 |  |  | 3054 |  |  | 2871.5 |  |  | 2855 |  |  | 2945.5 |  |  | 2869 |  |  | 2880.5 |  |  | 3001.5 |  |  | 2914.5 |  |  | 2856.5 |  |  | 2854.5 |  |  | 2956 |  |  | 2863.5 |  |  | 3094.5 |  |  | 2879.5 |  |  | 2932 |  |  | 3071.5 |  |  | 2834.5 |  |  | 2983.5 |  |  | 2937 |  |  | 2866.5 |  |  | 2854.5 |  |  | 2976.5 |  |  | 2839.5 |  |  | 2970.5 |  |  | 2845.5 |  |  | 2965.5 |  |  | 2912.5 |  |  | 2995.5 |  |  | 2791.5 |  |  | 2892 |  |  | 2868.5 |  |  | 2936.5 |  |  | 2831.5 |  |  | 3045.5 |  |  | 3140.5 |  |  | 2882 |  |  | 3008.5 |  |  | 3086 |  |  | 2964 |  |  | 2862.5 |  |  | 3048.5 |  |  | 2833.5 |  |  | 2940 |  |  | 2926.5 |  |  | 3011.5 |  |  | 2910.5 |  |  | 2743 |  |  | 2859.5 |  |  | 2779.5 |  |  | 2856.5 |  |  | 2819.5 |  |  | 2876.5 |  |  | 2879 |  |  | 2852.5 |  |  | 2971 |  |  | 2944.5 |  |  | 2770.5 |  |  | 2882.5 |  |  | 2850 |  |  | 2840.5 |  |  | 2827 |  |  | 2823 |  |  | 2881.5 |  |  | 2816.5 |  |  | 2825.5 |  |  | 3126.5 |  |  | 3114 |  |  | 2998.5 |  |  | 2949.5 |  |  | 2729.5 |  |  | 2885 |  |  | 2996.5 |  |  | 2817.5 |  |  | 2614.5 |  |  | 3003.5 |  |  | 3040 |  |  | 2806.5 |  |  | 2845.5 |  |  | 2893.5 |  |  | 3006.5 |  |  | 2992.5 |  |  | 2980.5 |  |  | 2978 |  |  | 2834.5 |  |  | 2861.5 |  |  | 2916 |  |  | 2750.5 |  |  | 2793.5 |  |  | 2964.5 |  |  | 2904 |  |  | 3027.5 |  |  | 2923.5 |  |  | 2861.5 |  |  | 2919.5 |  |  | 3018.5 |  |  | 2953 |  |  | 2812 |  |  | 2929.5 |  |  | 2938.5 |  |  | 2944.5 |  |  | 2756.5 |  |  | 2699 |  |  | 3036 |  |  | 2908 |  |  | 3023.5 |  |  | 2870 |  |  | 2927.5 |  |  | 3087.5 |  |  | 3012 |  |  | 2724.5 |  |  | 2960.5 |  |  | 2849.5 |  |  | 2984.5 |  |  | 2630.5 |  |  | 2897 |  |  | 2982 |  |  | 2843.5 |  |  | 3031.5 |  |  | 2758 |  |  | 2837.5 |  |  | 2956.5 |  |  | 2863 |  |  | 3075.5 |  |  | 3083.5 |  |  | 2868 |  |  | 2982.5 |  |  | 2965.5 |  |  | 3010 |  |  | 2866.5 |  |  | 2735 |  |  | 3098.5 |  |  | 3061 |  |  | 2852.5 |  |  | 2836.5 |  |  | 2858.5 |  |  | 2899.5 |  |  | 2945.5 |  |  | 2798.5 |  |  | 2918 |  |  | 2812.5 |  |  | 2992.5 |  |  | 2865.5 |  |  | 2940.5 |  |  | 2878.5 |  |  | 2877 |  |  | 2917.5 |  |  | 2986 |  |  | 3028.5 |  |  | 2744.5 |  |  | 2982.5 |  |  | 3024.5 |  |  | 2992.5 |  |  | 2895.5 |  |  | 2858.5 |  |  | 2970.5 |  |  | 2755.5 |  |  | 2853 |  |  | 2992.5 |  |  | 2875 |  |  | 2996 |  |  | 2947.5 |  |  | 2671 |  |  | 2774.5 |  |  | 2977.5 |  |  | 2992.5 |  |  | 2925.5 |  |  | 3042.5 |  |  | 2963.5 |  |  | 2997.5 |  |  | 2834 |  |  | 3109 |  |  | 2848.5 |  |  | 2961.5 |  |  | 2881 |  |  | 2934.5 |  |  | 2839.5 |  |  | 2870.5 |  |  | 2866.5 |  |  | 2848.5 |  |  | 2765 |  |  | 2926.5 |  |  | 2860.5 |  |  | 2848.5 |  |  | 2935 |  |  | 2976.5 |  |  | 2982.5 |  |  | 2995.5 |  |  | 3251.5 |  |  | 2910.5 |  |  | 2824.5 |  |  | 2966.5 |  |  | 2604.5 |  |  | 2901.5 |  |  | 2829 |  |  | 3037.5 |  |  | 2964.5 |  |  | 2944.5 |  |  | 2766.5 |  |  | 2961.5 |  |  | 2781.5 |  |  | 2778.5 |  |  | 2767 |  |  | 2789.5 |  |  | 2893.5 |  |  | 2853.5 |  |  | 2893 |  |  | 2965.5 |  |  | 2819 |  |  | 2830.5 |  |  | 2877.5 |  |  | 2807.5 |  |  | 2979 |  |  | 2769.5 |  |  | 2957 |  |  | 2985 |  |  | 2928.5 |  |  | 2829 |  |  | 3006 |  |  | 3011.5 |  |  | 3048.5 |  |  | 2811.5 |  |  | 3014 |  |  | 2945.5 |  |  | 2748.5 |  |  | 2785.5 |  |  | 3034.5 |  |  | 2849.5 |  |  | 2876.5 |  |  | 2975.5 |  |  | 2917.5 |  |  | 2804 |  |  | 3075.5 |  |  | 2867 |  |  | 2953.5 |  |  | 2842.5 |  |  | 2987.5 |  |  | 2877 |  |  | 2968 |  |  | 3072 |  |  | 2972.5 |  |  | 2942 |  |  | 2945.5 |  |  | 3119.5 |  |  | 2899.5 |  |  | 2922.5 |  |  | 2782.5 |  |  | 3033.5 |  |  | 2996.5 |  |  | 2953.5 |  |  | 2922 |  |  | 2773.5 |  |  | 2803.5 |  |  | 2942.5 |  |  | 2889.5 |  |  | 2852 |  |  | 2894.5 |  |  | 2932 |  |  | 2955.5 |  |  | 2880.5 |  |  | 2918.5 |  |  | 2774.5 |  |  | 2743 |  |  | 2905.5 |  |  | 2739 |  |  | 2867.5 |  |  | 2950.5 |  |  | 3051.5 |  |  | 2881.5 |  |  | 2925.5 |  |  | 3026.5 |  |  | 2934.5 |  |  | 2923.5 |  |  | 2890.5 |  |  | 2840 |  |  | 2923.5 |  |  | 2904.5 |  |  | 2913.5 |  |  | 2964.5 |  |  | 2964.5 |  |  | 2863 |  |  | 2819 |  |  | 2957.5 |  |  | 2848 |  |  | 3069.5 |  |  | 2853.5 |  |  | 3040.5 |  |  | 2910.5 |  |  | 2813.5 |  |  | 3035.5 |  |  | 2968.5 |  |  | 2948.5 |  |  | 2940 |  |  | 2947.5 |  |  | 3139.5 |  |  | 2883.5 |  |  | 2754 |  |  | 2935.5 |  |  | 2831.5 |  |  | 3068 |  |  | 2912 |  |  | 2941.5 |  |  | 2859 |  |  | 2774 |  |  | 2815.5 |  |  | 2974 |  |  | 3149.5 |  |  | 2864.5 |  |  | 2977.5 |  |  | 2822.5 |  |  | 2742.5 |  |  | 2956.5 |  |  | 2708.5 |  |  | 2799.5 |  |  | 2963.5 |  |  | 2864.5 |  |  | 2846 |  |  | 2871 |  |  | 3004.5 |  |  | 3001.5 |  |  | 2830.5 |  |  | 2991.5 |  |  | 2924.5 |  |  | 2989.5 |  |  | 2945.5 |  |  | 2799.5 |  |  | 3156 |  |  | 2837.5 |  |  | 2889 |  |  | 2864.5 |  |  | 3010.5 |  |  | 2957.5 |  |  | 3047 |  |  | 2964.5 |  |  | 2909.5 |  |  | 2943 |  |  | 2939.5 |  |  | 2878.5 |  |  | 3093.5 |  |  | 2889.5 |  |  | 2884.5 |  |  | 2944.5 |  |  | 3004 |  |  | 2804.5 |  |  | 2924.5 |  |  | 3050.5 |  |  | 2958.5 |  |  | 2935 |  |  | 2901.5 |  |  | 3053.5 |  |  | 2818 |  |  | 2919.5 |  |  | 3001.5 |  |  | 2939 |  |  | 2918.5 |  |  | 3016.5 |  |  | 2945.5 |  |  | 2835 |  |  | 2760.5 |  |  | 2917.5 |  |  | 2835 |  |  | 2999.5 |  |  | 2929.5 |  |  | 2972.5 |  |  | 2749.5 |  |  | 2921.5 |  |  | 3085.5 |  |  | 2825.5 |  |  | 2933 |  |  | 2763 |  |  | 2745.5 |  |  | 2947.5 |  |  | 2775.5 |  |  | 3029 |  |  | 3089.5 |  |  | 2905.5 |  |  | 2918.5 |  |  | 2746.5 |  |  | 2918.5 |  |  | 2991.5 |  |  | 2893.5 |  |  | 2924.5 |  |  | 2718.5 |  |  | 2934 |  |  | 2848.5 |  |  | 2738.5 |  |  | 2904.5 |  |  | 2891.5 |  |  | 3054.5 |  |  | 2941.5 |  |  | 2931.5 |  |  | 2924.5 |  |  | 2734.5 |  |  | 3119.5 |  |  | 2908.5 |  |  | 2805.5 |  |  | 2920.5 |  |  | 3027 |  |  | 2963.5 |  |  | 3011.5 |  |  | 2846 |  |  | 2943.5 |  |  | 2946.5 |  |  | 2984 |  |  | 2972.5 |  |  | 2963.5 |  |  | 3092.5 |  |  | 3140 |  |  | 2809.5 |  |  | 3009.5 |  |  | 2875.5 |  |  | 2715.5 |  |  | 2947.5 |  |  | 2828 |  |  | 2842.5 |  |  | 2980 |  |  | 2955 |  |  | 2958.5 |  |  | 2909.5 |  |  | 2835.5 |  |  | 2642.5 |  |  | 2828.5 |  |  | 3043.5 |  |  | 2871 |  |  | 2901.5 |  |  | 2853 |  |  | 3004.5 |  |  | 2941 |  |  | 2792 |  |  | 2993 |  |  | 3016.5 |  |  | 2774 |  |  | 3085.5 |  |  | 2955.5 |  |  | 2882.5 |  |  | 3163.5 |  |  | 2756.5 |  |  | 3001 |  |  | 2898.5 |  |  | 2923.5 |  |  | 3165.5 |  |  | 2981 |  |  | 2832.5 |  |  | 2908.5 |  |  | 2927.5 |  |  | 3073.5 |  |  | 2916 |  |  | 2992 |  |  | 2860 |  |  | 2842.5 |  |  | 3022 |  |  | 2927 |  |  | 3095.5 |  |  | 2787.5 |  |  | 2772.5 |  |  | 2943.5 |  |  | 3019.5 |  |  | 2865.5 |  |  | 3007.5 |  |  | 2947.5 |  |  | 2861.5 |  |  | 2853 |  |  | 2878.5 |  |  | 2810 |  |  | 2955.5 |  |  | 2924.5 |  |  | 2985.5 |  |  | 2977.5 |  |  | 3046 |  |  | 2969.5 |  |  | 2907 |  |  | 2781.5 |  |  | 2975.5 |  |  | 2775 |  |  | 2879 |  |  | 2982.5 |  |  | 2977 |  |  | 2939.5 |  |  | 2811.5 |  |  | 2803.5 |  |  | 2829.5 |  |  | 2928.5 |  |  | 2952.5 |  |  | 2785.5 |  |  | 2865 |  |  | 2977.5 |  |  | 2946.5 |  |  | 2982.5 |  |  | 2992.5 |  |  | 2858.5 |  |  | 2951.5 |  |  | 3035.5 |  |  | 2887.5 |  |  | 3107.5 |  |  | 3027.5 |  |  | 2819.5 |  |  | 2750.5 |  |  | 2901 |  |  | 2780.5 |  |  | 2935.5 |  |  | 2977 |  |  | 2804.5 |  |  | 2816.5 |  |  | 2856.5 |  |  | 2768.5 |  |  | 3127 |  |  | 3020.5 |  |  | 2788.5 |  |  | 2799.5 |  |  | 3054.5 |  |  | 2914 |  |  | 2916.5 |  |  | 3026.5 |  |  | 2885.5 |  |  | 3020.5 |  |  | 2865.5 |  |  | 2841.5 |  |  | 2985.5 |  |  | 2879.5 |  |  | 2940.5 |  |  | 2918.5 |  |  | 3017.5 |  |  | 2963 |  |  | 2937.5 |  |  | 2876.5 |  |  | 2962.5 |  |  | 3054.5 |  |  | 2839.5 |  |  | 2817.5 |  |  | 2959 |  |  | 3022.5 |  |  | 2783 |  |  | 2788.5 |  |  | 2986.5 |  |  | 3004.5 |  |  | 2900 |  |  | 2899 |  |  | 2991.5 |  |  | 2997.5 |  |  | 2703.5 |  |  | 3082.5 |  |  | 2896.5 |  |  | 2982.5 |  |  | 2867.5 |  |  | 2987.5 |  |  | 2824.5 |  |  | 3123.5 |  |  | 2872.5 |  |  | 3002.5 |  |  | 2808.5 |  |  | 2946.5 |  |  | 3025.5 |  |  | 2935.5 |  |  | 2891.5 |  |  | 2921.5 |  |  | 2919.5 |  |  | 2898.5 |  |  | 3000.5 |  |  | 2979.5 |  |  | 2878 |  |  | 2926.5 |  |  | 2925.5 |  |  | 3011.5 |  |  | 2983 |  |  | 3008.5 |  |  | 2924.5 |  |  | 3031.5 |  |  | 2952.5 |  |  | 2957 |  |  | 2836.5 |  |  | 2769.5 |  |  | 2825 |  |  | 2899 |  |  | 2917 |  |  | 2968.5 |  |  | 2842.5 |  |  | 3018.5 |  |  | 3108.5 |  |  | 3016 |  |  | 2951.5 |  |  | 2929.5 |  |  | 2821 |  |  | 2860 |  |  | 2966.5 |  |  | 2940.5 |  |  | 3049 |  |  | 2953.5 |  |  | 3041 |  |  | 2833.5 |  |  | 2943.5 |  |  | 2974 |  |  | 3022.5 |  |  | 2960.5 |  |  | 2799.5 |  |  | 2986 |  |  | 2868.5 |  |  | 2797.5 |  |  | 2858.5 |  |  | 2849.5 |  |  | 2917.5 |  |  | 2991.5 |  |  | 2931.5 |  |  | 3023.5 |  |  | 3016.5 |  |  | 2944.5 |  |  | 2878 |  |  | 2907.5 |  |  | 2903.5 |  |  | 2994.5 |  |  | 2989.5 |  |  | 2911.5 |  |  | 2960.5 |  |  | 2964.5 |  |  | 2915.5 |  |  | 3040 |  |  | 2882.5 |  |  | 2865 |  |  | 3204.5 |  |  | 3108.5 |  |  | 3087.5 |  |  | 2876.5 |  |  | 2885.5 |  |  | 2962.5 |  |  | 2768.5 |  |  | 2972.5 |  |  | 3005 |  |  | 2882.5 |  |  | 2970 |  |  | 2797.5 |  |  | 2876.5 |  |  | 2916.5 |  |  | 2981 |  |  | 2839.5 |  |  | 2941.5 |  |  | 2707 |  |  | 2917.5 |  |  | 2932 |  |  | 2918.5 |  |  | 2798.5 |  |  | 2891.5 |  |  | 2896 |  |  | 2994.5 |  |  | 3180.5 |  |  | 2759 |  |  | 3076.5 |  |  | 2918.5 |  |  | 2957 |  |  | 2918.5 |  |  | 3097.5 |  |  | 3047.5 |  |  | 3078.5 |  |  | 2840.5 |  |  | 3070.5 |  |  | 2806.5 |  |  | 2900.5 |  |  | 2882.5 |  |  | 2814.5 |  |  | 3062.5 |  |  | 3025 |  |  | 2945 |  |  | 3030.5 |  |  | 2940.5 |  |  | 3003
100 |  | 2914.5 |  |  | 2957.5 |  |  | 3013 |  |  | 2854.5 |  |  | 3134.5 |  |  | 3005.5 |  |  | 3024.5 |  |  | 3007.5 |  |  | 2943.5 |  |  | 2978.5 |  |  | 2784 |  |  | 2966.5 |  |  | 2953.5 |  |  | 2842.5 |  |  | 2839 |  |  | 2973.5 |  |  | 3006.5 |  |  | 2909.5 |  |  | 3073.5 |  |  | 2868.5 |  |  | 3143.5 |  |  | 2961.5 |  |  | 3100.5 |  |  | 2911.5 |  |  | 2697 |  |  | 3067.5 |  |  | 2996.5 |  |  | 2960.5 |  |  | 2970.5 |  |  | 2789 |  |  | 2976 |  |  | 3094.5 |  |  | 2772.5 |  |  | 2951.5 |  |  | 2842.5 |  |  | 2997 |  |  | 2906.5 |  |  | 3214 |  |  | 2955.5 |  |  | 2924.5 |  |  | 2777.5 |  |  | 3007.5 |  |  | 2768.5 |  |  | 2981 |  |  | 3047.5 |  |  | 3067 |  |  | 2971.5 |  |  | 3027.5 |  |  | 3120.5 |  |  | 2997.5 |  |  | 2845.5 |  |  | 3010.5 |  |  | 2889.5 |  |  | 2917.5 |  |  | 3050.5 |  |  | 2946.5 |  |  | 2864.5 |  |  | 2919 |  |  | 2951.5 |  |  | 2904.5 |  |  | 2964 |  |  | 2956.5 |  |  | 3098.5 |  |  | 2902.5 |  |  | 2867.5 |  |  | 2975 |  |  | 3071.5 |  |  | 2857 |  |  | 2785.5 |  |  | 2962.5 |  |  | 2903 |  |  | 2845.5 |  |  | 2971.5 |  |  | 3101.5 |  |  | 3091 |  |  | 3037 |  |  | 2763.5 |  |  | 2899.5 |  |  | 2831.5 |  |  | 2947.5 |  |  | 2932 |  |  | 2978.5 |  |  | 3000.5 |  |  | 2960.5 |  |  | 3021.5 |  |  | 2826.5 |  |  | 3038.5 |  |  | 2968.5 |  |  | 2912.5 |  |  | 2875.5 |  |  | 2949.5 |  |  | 3010 |  |  | 2941.5 |  |  | 2823 |  |  | 2915 |  |  | 2815 |  |  | 3155.5 |  |  | 3020.5 |  |  | 2883.5 |  |  | 3111.5 |  |  | 2865.5 |  |  | 2894 |  |  | 2971 |  |  | 2916.5 |  |  | 2978.5 |  |  | 2822.5 |  |  | 2938.5 |  |  | 3045.5 |  |  | 3005.5 |  |  | 3099.5 |  |  | 3078.5 |  |  | 3026.5 |  |  | 2917.5 |  |  | 3001.5 |  |  | 3023.5 |  |  | 3048.5 |  |  | 3096.5 |  |  | 2925.5 |  |  | 2954.5 |  |  | 2980.5 |  |  | 3051.5 |  |  | 2991.5 |  |  | 3038.5 |  |  | 2955.5 |  |  | 2926.5 |  |  | 2935 |  |  | 2923.5 |  |  | 2969.5 |  |  | 2913.5 |  |  | 2967.5 |  |  | 3039.5 |  |  | 2910 |  |  | 2855.5 |  |  | 3090.5 |  |  | 2934.5 |  |  | 2914.5 |  |  | 2989 |  |  | 2945.5 |  |  | 3063.5 |  |  | 2807 |  |  | 3030.5 |  |  | 2700 |  |  | 3054 |  |  | 3094.5 |  |  | 3013 |  |  | 3134.5 |  |  | 3002.5 |  |  | 2972.5 |  |  | 2927.5 |  |  | 3009.5 |  |  | 2992.5 |  |  | 2945.5 |  |  | 2960.5 |  |  | 3114.5 |  |  | 2964.5 |  |  | 3092 |  |  | 2826.5 |  |  | 2827 |  |  | 3016.5 |  |  | 2986.5 |  |  | 2929 |  |  | 2926.5 |  |  | 2943.5 |  |  | 2878.5 |  |  | 2820 |  |  | 2938.5 |  |  | 2769.5 |  |  | 2867.5 |  |  | 3063.5 |  |  | 2977.5 |  |  | 2859.5 |  |  | 2914 |  |  | 2905.5 |  |  | 2892.5 |  |  | 2792.5 |  |  | 3058.5 |  |  | 2977.5 |  |  | 3049.5 |  |  | 2905.5 |  |  | 3031 |  |  | 3000.5 |  |  | 2958.5 |  |  | 3016.5 |  |  | 3014.5 |  |  | 2889.5 |  |  | 3047.5 |  |  | 3060.5 |  |  | 2940.5 |  |  | 3180.5 |  |  | 2816.5 |  |  | 3043.5 |  |  | 2708.5 |  |  | 2881.5 |  |  | 2823 |  |  | 2843.5 |  |  | 3004.5 |  |  | 3017.5 |  |  | 3072.5 |  |  | 3041.5 |  |  | 3105.5 |  |  | 3068.5 |  |  | 2944.5 |  |  | 3034.5 |  |  | 2941.5 |  |  | 2820.5 |  |  | 3107.5 |  |  | 2913.5 |  |  | 2942.5 |  |  | 2944.5 |  |  | 2967.5 |  |  | 2928 |  |  | 3122.5 |  |  | 2937.5 |  |  | 2711 |  |  | 3010.5 |  |  | 3064 |  |  | 2704.5 |  |  | 2934.5 |  |  | 3044.5 |  |  | 3060.5 |  |  | 2874.5 |  |  | 2888.5 |  |  | 2926.5 |  |  | 2850.5 |  |  | 2827 |  |  | 2828.5 |  |  | 2787.5 |  |  | 2994.5 |  |  | 2832.5 |  |  | 2891 |  |  | 2963.5 |  |  | 2918.5 |  |  | 3038.5 |  |  | 2914.5 |  |  | 3047.5 |  |  | 3005.5 |  |  | 2976.5 |  |  | 3076.5 |  |  | 3060 |  |  | 2951 |  |  | 2910.5 |  |  | 2868.5 |  |  | 3006.5 |  |  | 2873 |  |  | 3149.5 |  |  | 3034.5 |  |  | 2986.5 |  |  | 2821 |  |  | 3086.5 |  |  | 2942.5 |  |  | 2758.5 |  |  | 2876.5 |  |  | 3001.5 |  |  | 3013.5 |  |  | 3021.5 |  |  | 2999.5 |  |  | 3022.5 |  |  | 2721 |  |  | 2849.5 |  |  | 3049.5 |  |  | 2947.5 |  |  | 2978.5 |  |  | 2819.5 |  |  | 3083 |  |  | 2822.5 |  |  | 3053.5 |  |  | 3036 |  |  | 3082.5 |  |  | 2956.5 |  |  | 3129 |  |  | 2992.5 |  |  | 3020.5 |  |  | 3019.5 |  |  | 2891.5 |  |  | 2950 |  |  | 2958 |  |  | 2977.5 |  |  | 2792.5 |  |  | 2994.5 |  |  | 2884.5 |  |  | 3133.5 |  |  | 2991.5 |  |  | 2997 |  |  | 2829.5 |  |  | 2778.5 |  |  | 2881 |  |  | 2924.5 |  |  | 2737.5 |  |  | 2994 |  |  | 2940.5 |  |  | 2847.5 |  |  | 2955.5 |  |  | 3034 |  |  | 2962.5 |  |  | 2927 |  |  | 3070.5 |  |  | 2799.5 |  |  | 2959.5 |  |  | 2853 |  |  | 2873.5 |  |  | 3107.5 |  |  | 3032.5 |  |  | 2979 |  |  | 2903.5 |  |  | 2793.5 |  |  | 3059.5 |  |  | 3119.5 |  |  | 3011.5 |  |  | 2985 |  |  | 2931.5 |  |  | 3099.5 |  |  | 2929.5 |  |  | 2940 |  |  | 2937 |  |  | 3111.5 |  |  | 2911.5 |  |  | 2725.5 |  |  | 3032.5 |  |  | 2968.5 |  |  | 2889.5 |  |  | 3012.5 |  |  | 3039.5 |  |  | 2892.5 |  |  | 3013.5 |  |  | 2988 |  |  | 2869.5 |  |  | 2929.5 |  |  | 3199.5 |  |  | 3162.5 |  |  | 2989 |  |  | 2895.5 |  |  | 3060.5 |  |  | 3030.5 |  |  | 2822.5 |  |  | 3111.5 |  |  | 2759 |  |  | 3008 |  |  | 2838 |  |  | 3101 |  |  | 2900.5 |  |  | 2884 |  |  | 2966.5 |  |  | 2916 |  |  | 2909.5 |  |  | 3048.5 |  |  | 2961.5 |  |  | 2895.5 |  |  | 2869.5 |  |  | 2982 |  |  | 2902.5 |  |  | 3133.5 |  |  | 2903.5 |  |  | 2971 |  |  | 3095.5 |  |  | 2855.5 |  |  | 3012.5 |  |  | 2961 |  |  | 2890.5 |  |  | 2880.5 |  |  | 2991.5 |  |  | 2860.5 |  |  | 2985.5 |  |  | 2884.5 |  |  | 3004.5 |  |  | 2959.5 |  |  | 3016.5 |  |  | 2830.5 |  |  | 2918 |  |  | 2892.5 |  |  | 2975.5 |  |  | 2860.5 |  |  | 3069.5 |  |  | 3161.5 |  |  | 2921 |  |  | 3037.5 |  |  | 3112 |  |  | 2979 |  |  | 2901.5 |  |  | 3077.5 |  |  | 2859.5 |  |  | 2955 |  |  | 2965.5 |  |  | 3058.5 |  |  | 2931.5 |  |  | 2790 |  |  | 2874.5 |  |  | 2818.5 |  |  | 2895.5 |  |  | 2858.5 |  |  | 2915.5 |  |  | 2894 |  |  | 2891.5 |  |  | 2986 |  |  | 2959.5 |  |  | 2794.5 |  |  | 2911.5 |  |  | 2879 |  |  | 2879.5 |  |  | 2856 |  |  | 2870 |  |  | 2928.5 |  |  | 2837.5 |  |  | 2846.5 |  |  | 3141.5 |  |  | 3153 |  |  | 3013.5 |  |  | 2988.5 |  |  | 2776.5 |  |  | 2900 |  |  | 3017.5 |  |  | 2856.5 |  |  | 2653.5 |  |  | 3024.5 |  |  | 3069 |  |  | 2853.5 |  |  | 2884.5 |  |  | 2914.5 |  |  | 3035.5 |  |  | 3018.5 |  |  | 3019.5 |  |  | 3017 |  |  | 2863.5 |  |  | 2876.5 |  |  | 2937 |  |  | 2774.5 |  |  | 2817.5 |  |  | 3003.5 |  |  | 2919 |  |  | 3042.5 |  |  | 2947.5 |  |  | 2900.5 |  |  | 2945.5 |  |  | 3042.5 |  |  | 2992 |  |  | 2838 |  |  | 2953.5 |  |  | 2977.5 |  |  | 2970.5 |  |  | 2795.5 |  |  | 2738 |  |  | 3075 |  |  | 2932 |  |  | 3047.5 |  |  | 2917 |  |  | 2953.5 |  |  | 3111.5 |  |  | 3041 |  |  | 2748.5 |  |  | 2999.5 |  |  | 2875.5 |  |  | 3023.5 |  |  | 2651.5 |  |  | 2944 |  |  | 3006 |  |  | 2890.5 |  |  | 3078.5 |  |  | 2787 |  |  | 2858.5 |  |  | 2980.5 |  |  | 2902 |  |  | 3096.5 |  |  | 3130.5 |  |  | 2915 |  |  | 3021.5 |  |  | 2980.5 |  |  | 3049 |  |  | 2892.5 |  |  | 2774 |  |  | 3113.5 |  |  | 3100 |  |  | 2878.5 |  |  | 2860.5 |  |  | 2905.5 |  |  | 2946.5 |  |  | 2974.5 |  |  | 2837.5 |  |  | 2957 |  |  | 2841.5 |  |  | 3031.5 |  |  | 2904.5 |  |  | 2987.5 |  |  | 2904.5 |  |  | 2892 |  |  | 2938.5 |  |  | 3025 |  |  | 3049.5 |  |  | 2770.5 |  |  | 3021.5 |  |  | 3050.5 |  |  | 3031.5 |  |  | 2919.5 |  |  | 2905.5 |  |  | 2996.5 |  |  | 2770.5 |  |  | 2877 |  |  | 3018.5 |  |  | 2914 |  |  | 3011 |  |  | 2986.5 |  |  | 2692 |  |  | 2789.5 |  |  | 2998.5 |  |  | 3016.5 |  |  | 2940.5 |  |  | 3089.5 |  |  | 3002.5 |  |  | 3023.5 |  |  | 2849 |  |  | 3130 |  |  | 2869.5 |  |  | 2985.5 |  |  | 2896 |  |  | 2960.5 |  |  | 2878.5 |  |  | 2894.5 |  |  | 2890.5 |  |  | 2887.5 |  |  | 2804 |  |  | 2941.5 |  |  | 2899.5 |  |  | 2895.5 |  |  | 2982 |  |  | 2997.5 |  |  | 3008.5 |  |  | 3019.5 |  |  | 3266.5 |  |  | 2957.5 |  |  | 2863.5 |  |  | 3005.5 |  |  | 2628.5 |  |  | 2940.5 |  |  | 2858 |  |  | 3084.5 |  |  | 2990.5 |  |  | 2983.5 |  |  | 2813.5 |  |  | 2976.5 |  |  | 2828.5 |  |  | 2817.5 |  |  | 2793 |  |  | 2836.5 |  |  | 2932.5 |  |  | 2892.5 |  |  | 2922 |  |  | 3004.5 |  |  | 2843 |  |  | 2869.5 |  |  | 2892.5 |  |  | 2846.5 |  |  | 3026 |  |  | 2798.5 |  |  | 2972 |  |  | 3011 |  |  | 2957.5 |  |  | 2855 |  |  | 3030 |  |  | 3037.5 |  |  | 3069.5 |  |  | 2850.5 |  |  | 3040 |  |  | 2974.5 |  |  | 2787.5 |  |  | 2814.5 |  |  | 3060.5 |  |  | 2873.5 |  |  | 2891.5 |  |  | 3014.5 |  |  | 2938.5 |  |  | 2833 |  |  | 3101.5 |  |  | 2882 |  |  | 2982.5 |  |  | 2857.5 |  |  | 3002.5 |  |  | 2903 |  |  | 3015 |  |  | 3093 |  |  | 2987.5 |  |  | 2963 |  |  | 2974.5 |  |  | 3148.5 |  |  | 2938.5 |  |  | 2969.5 |  |  | 2808.5 |  |  | 3059.5 |  |  | 3043.5 |  |  | 2968.5 |  |  | 2969 |  |  | 2797.5 |  |  | 2850.5 |  |  | 2989.5 |  |  | 2904.5 |  |  | 2876 |  |  | 2915.5 |  |  | 2958 |  |  | 2979.5 |  |  | 2904.5 |  |  | 2944.5 |  |  | 2821.5 |  |  | 2782 |  |  | 2934.5 |  |  | 2778 |  |  | 2906.5 |  |  | 2965.5 |  |  | 3098.5 |  |  | 2928.5 |  |  | 2940.5 |  |  | 3052.5 |  |  | 2981.5 |  |  | 2947.5 |  |  | 2916.5 |  |  | 2869 |  |  | 2949.5 |  |  | 2943.5 |  |  | 2952.5 |  |  | 2985.5 |  |  | 2985.5 |  |  | 2910 |  |  | 2834 |  |  | 2981.5 |  |  | 2869 |  |  | 3093.5 |  |  | 2892.5 |  |  | 3055.5 |  |  | 2931.5 |  |  | 2842.5 |  |  | 3059.5 |  |  | 2989.5 |  |  | 2969.5 |  |  | 2961 |  |  | 2973.5 |  |  | 3160.5 |  |  | 2907.5 |  |  | 2783 |  |  | 2974.5 |  |  | 2852.5 |  |  | 3097 |  |  | 2936 |  |  | 2980.5 |  |  | 2898 |  |  | 2803 |  |  | 2862.5 |  |  | 3013 |  |  | 3196.5 |  |  | 2903.5 |  |  | 2998.5 |  |  | 2846.5 |  |  | 2781.5 |  |  | 2980.5 |  |  | 2737.5 |  |  | 2814.5 |  |  | 2989.5 |  |  | 2893.5 |  |  | 2885 |  |  | 2886 |  |  | 3051.5 |  |  | 3025.5 |  |  | 2845.5 |  |  | 3017.5 |  |  | 2953.5 |  |  | 3004.5 |  |  | 2974.5 |  |  | 2820.5 |  |  | 3182 |  |  | 2852.5 |  |  | 2915 |  |  | 2903.5 |  |  | 3057.5 |  |  | 3004.5 |  |  | 3076 |  |  | 2990.5 |  |  | 2924.5 |  |  | 2982 |  |  | 2965.5 |  |  | 2893.5 |  |  | 3108.5 |  |  | 2904.5 |  |  | 2910.5 |  |  | 2973.5 |  |  | 3043 |  |  | 2851.5 |  |  | 2945.5 |  |  | 3097.5 |  |  | 2987.5 |  |  | 2964 |  |  | 2940.5 |  |  | 3092.5 |  |  | 2865 |  |  | 2948.5 |  |  | 3030.5 |  |  | 2963 |  |  | 2944.5 |  |  | 3031.5 |  |  | 2960.5 |  |  | 2882 |  |  | 2799.5 |  |  | 2932.5 |  |  | 2874 |  |  | 3025.5 |  |  | 2968.5 |  |  | 3001.5 |  |  | 2775.5 |  |  | 2936.5 |  |  | 3132.5 |  |  | 2864.5 |  |  | 2948 |  |  | 2802 |  |  | 2784.5 |  |  | 2968.5 |  |  | 2814.5 |  |  | 3055 |  |  | 3118.5 |  |  | 2934.5 |  |  | 2939.5 |  |  | 2767.5 |  |  | 2939.5 |  |  | 3015.5 |  |  | 2917.5 |  |  | 2963.5 |  |  | 2739.5 |  |  | 2973 |  |  | 2887.5 |  |  | 2785.5 |  |  | 2943.5 |  |  | 2912.5 |  |  | 3101.5 |  |  | 2967.5 |  |  | 2970.5 |  |  | 2945.5 |  |  | 2758.5 |  |  | 3148.5 |  |  | 2929.5 |  |  | 2834.5 |  |  | 2941.5 |  |  | 3074 |  |  | 3002.5 |  |  | 3032.5 |  |  | 2872 |  |  | 2990.5 |  |  | 2985.5 |  |  | 3031 |  |  | 3001.5 |  |  | 2984.5 |  |  | 3113.5 |  |  | 3166 |  |  | 2830.5 |  |  | 3030.5 |  |  | 2899.5 |  |  | 2744.5 |  |  | 2976.5 |  |  | 2857 |  |  | 2863.5 |  |  | 2995 |  |  | 3002 |  |  | 2997.5 |  |  | 2956.5 |  |  | 2874.5 |  |  | 2689.5 |  |  | 2875.5 |  |  | 3082.5 |  |  | 2897 |  |  | 2940.5 |  |  | 2892 |  |  | 3019.5 |  |  | 2965 |  |  | 2813 |  |  | 3019 |  |  | 3040.5 |  |  | 2803 |  |  | 3124.5 |  |  | 2981.5 |  |  | 2906.5 |  |  | 3202.5 |  |  | 2771.5 |  |  | 3025 |  |  | 2919.5 |  |  | 2938.5 |  |  | 3180.5 |  |  | 3020 |  |  | 2858.5 |  |  | 2923.5 |  |  | 2948.5 |  |  | 3099.5 |  |  | 2955 |  |  | 3021 |  |  | 2886 |  |  | 2881.5 |  |  | 3046 |  |  | 2951 |  |  | 3134.5 |  |  | 2834.5 |  |  | 2811.5 |  |  | 2990.5 |  |  | 3058.5 |  |  | 2904.5 |  |  | 3031.5 |  |  | 2962.5 |  |  | 2908.5 |  |  | 2882 |  |  | 2917.5 |  |  | 2849 |  |  | 3002.5 |  |  | 2953.5 |  |  | 3024.5 |  |  | 3006.5 |  |  | 3067 |  |  | 2998.5 |  |  | 2936 |  |  | 2802.5 |  |  | 3004.5 |  |  | 2814 |  |  | 2894 |  |  | 3008.5 |  |  | 3001 |  |  | 2986.5 |  |  | 2850.5 |  |  | 2842.5 |  |  | 2853.5 |  |  | 2967.5 |  |  | 2967.5 |  |  | 2814.5 |  |  | 2894 |  |  | 3016.5 |  |  | 2967.5 |  |  | 3029.5 |  |  | 3018.5 |  |  | 2873.5 |  |  | 2975.5 |  |  | 3074.5 |  |  | 2916.5 |  |  | 3128.5 |  |  | 3066.5 |  |  | 2834.5 |  |  | 2779.5 |  |  | 2948 |  |  | 2827.5 |  |  | 2961.5 |  |  | 2992 |  |  | 2851.5 |  |  | 2855.5 |  |  | 2880.5 |  |  | 2794.5 |  |  | 3142 |  |  | 3067.5 |  |  | 2809.5 |  |  | 2846.5 |  |  | 3093.5 |  |  | 2943 |  |  | 2963.5 |  |  | 3065.5 |  |  | 2911.5 |  |  | 3041.5 |  |  | 2912.5 |  |  | 2856.5 |  |  | 3014.5 |  |  | 2918.5 |  |  | 2969.5 |  |  | 2957.5 |  |  | 3043.5 |  |  | 2984 |  |  | 2963.5 |  |  | 2923.5 |  |  | 2991.5 |  |  | 3069.5 |  |  | 2878.5 |  |  | 2841.5 |  |  | 2998 |  |  | 3037.5 |  |  | 2807 |  |  | 2827.5 |  |  | 3015.5 |  |  | 3043.5 |  |  | 2924 |  |  | 2914 |  |  | 3038.5 |  |  | 3036.5 |  |  | 2727.5 |  |  | 3097.5 |  |  | 2920.5 |  |  | 3021.5 |  |  | 2906.5 |  |  | 3026.5 |  |  | 2871.5 |  |  | 3170.5 |  |  | 2887.5 |  |  | 3028.5 |  |  | 2829.5 |  |  | 2993.5 |  |  | 3040.5 |  |  | 2961.5 |  |  | 2930.5 |  |  | 2960.5 |  |  | 2940.5 |  |  | 2919.5 |  |  | 3039.5 |  |  | 3008.5 |  |  | 2917 |  |  | 2947.5 |  |  | 2964.5 |  |  | 3026.5 |  |  | 3004 |  |  | 3023.5 |  |  | 2963.5 |  |  | 3057.5 |  |  | 2999.5 |  |  | 2978 |  |  | 2860.5 |  |  | 2784.5 |  |  | 2864 |  |  | 2928 |  |  | 2956 |  |  | 2989.5 |  |  | 2881.5 |  |  | 3033.5 |  |  | 3132.5 |  |  | 3055 |  |  | 2977.5 |  |  | 2968.5 |  |  | 2868 |  |  | 2886 |  |  | 3005.5 |  |  | 2979.5 |  |  | 3075 |  |  | 2977.5 |  |  | 3062 |  |  | 2848.5 |  |  | 2990.5 |  |  | 3000 |  |  | 3051.5 |  |  | 2986.5 |  |  | 2820.5 |  |  | 3025 |  |  | 2897.5 |  |  | 2821.5 |  |  | 2873.5 |  |  | 2888.5 |  |  | 2964.5 |  |  | 3020.5 |  |  | 2957.5 |  |  | 3062.5 |  |  | 3045.5 |  |  | 2968.5 |  |  | 2893 |  |  | 2928.5 |  |  | 2929.5 |  |  | 3041.5 |  |  | 3010.5 |  |  | 2935.5 |  |  | 2981.5 |  |  | 2993.5 |  |  | 2944.5 |  |  | 3055 |  |  | 2908.5 |  |  | 2894 |  |  | 3230.5 |  |  | 3147.5 |  |  | 3108.5 |  |  | 2900.5 |  |  | 2932.5 |  |  | 2977.5 |  |  | 2789.5 |  |  | 3011.5 |  |  | 3020 |  |  | 2908.5 |  |  | 3009 |  |  | 2836.5 |  |  | 2915.5 |  |  | 2937.5 |  |  | 3020 |  |  | 2878.5 |  |  | 2980.5 |  |  | 2746 |  |  | 2932.5 |  |  | 2958 |  |  | 2944.5 |  |  | 2822.5 |  |  | 2915.5 |  |  | 2911 |  |  | 3033.5 |  |  | 3209.5 |  |  | 2806 |  |  | 3102.5 |  |  | 2957.5 |  |  | 2986 |  |  | 2947.5 |  |  | 3144.5 |  |  | 3071.5 |  |  | 3107.5 |  |  | 2879.5 |  |  | 3091.5 |  |  | 2845.5 |  |  | 2921.5 |  |  | 2921.5 |  |  | 2853.5 |  |  | 3088.5 |  |  | 3072 |  |  | 2969 |  |  | 3077.5 |  |  | 2987.5 |  |  | 3042
8.4346 | ← Std. Deviation |  | 43.6875 |  |  | 33.9844 |  |  | 63.1094 |  |  | 30.6094 |  |  | 105.8594 |  |  | 47.1094 |  |  | 40.3594 |  |  | 126.25 |  |  | 89.1094 |  |  | 43.3594 |  |  | 126.25 |  |  | 94.3594 |  |  | 135.1875 |  |  | 90.4844 |  |  | 102.25 |  |  | 99.75 |  |  | 39.9375 |  |  | 25.9375 |  |  | 79.1875 |  |  | 53.5 |  |  | 80.7344 |  |  | 40.1875 |  |  | 91.3594 |  |  | 97.5 |  |  | 20.8594 |  |  | 33.9844 |  |  | 65.5 |  |  | 84.8594 |  |  | 37.2344 |  |  | 61.2344 |  |  | 26.8594 |  |  | 76.3594 |  |  | 23.1094 |  |  | 105.25 |  |  | 18.9375 |  |  | 82.6875 |  |  | 57.1875 |  |  | 17.1094 |  |  | 87.75 |  |  | 88.6094 |  |  | 60.1875 |  |  | 83.8594 |  |  | 109.5 |  |  | 113.25 |  |  | 69.9844 |  |  | 79.7344 |  |  | 25.9375 |  |  | 59.5 |  |  | 96.1875 |  |  | 61.5 |  |  | 59.5 |  |  | 61.3594 |  |  | 61.5 |  |  | 69.9844 |  |  | 78.2344 |  |  | 34.9844 |  |  | 57.6094 |  |  | 76.1875 |  |  | 87.6094 |  |  | 69.9844 |  |  | 71.3594 |  |  | 60.1875 |  |  | 56.4375 |  |  | 91.5 |  |  | 62.3594 |  |  | 46.3594 |  |  | 55.7344 |  |  | 57.75 |  |  | 39.1875 |  |  | 55.7344 |  |  | 92.4844 |  |  | 44.1094 |  |  | 91.5 |  |  | 126.25 |  |  | 94.3594 |  |  | 41.25 |  |  | 36.6094 |  |  | 97.5 |  |  | 41.25 |  |  | 65.1094 |  |  | 123.9844 |  |  | 27 |  |  | 60.1875 |  |  | 110.4844 |  |  | 69.25 |  |  | 40.3594 |  |  | 57.25 |  |  | 73 |  |  | 18.9375 |  |  | 74.25 |  |  | 74.8594 |  |  | 53.8594 |  |  | 74.25 |  |  | 41.25 |  |  | 75 |  |  | 38.3594 |  |  | 82.9844 |  |  | 91.75 |  |  | 124.6094 |  |  | 61.7344 |  |  | 18.75 |  |  | 126.25 |  |  | 93.1875 |  |  | 99.75 |  |  | 118.7344 |  |  | 40.1875 |  |  | 63.1094 |  |  | 75.2344 |  |  | 106.7344 |  |  | 91.6875 |  |  | 79.3594 |  |  | 42.2344 |  |  | 106.7344 |  |  | 38.25 |  |  | 66.9844 |  |  | 43.6875 |  |  | 42.9844 |  |  | 42.9844 |  |  | 99.75 |  |  | 52.2344 |  |  | 94.3594 |  |  | 38.3594 |  |  | 65.25 |  |  | 33.25 |  |  | 45.1094 |  |  | 123.6094 |  |  | 32.4844 |  |  | 141.9844 |  |  | 140.8594 |  |  | 42.6094 |  |  | 92.8594 |  |  | 37.5 |  |  | 88.6094 |  |  | 86.1094 |  |  | 53.8594 |  |  | 57.4844 |  |  | 70.7344 |  |  | 91.6875 |  |  | 49.7344 |  |  | 92.1094 |  |  | 51.6094 |  |  | 45.1875 |  |  | 71.3594 |  |  | 69.9844 |  |  | 74.4844 |  |  | 88.75 |  |  | 69.25 |  |  | 51.6094 |  |  | 33.6094 |  |  | 115.3594 |  |  | 57.25 |  |  | 22.1875 |  |  | 6.9375 |  |  | 51 |  |  | 33.9844 |  |  | 102.6094 |  |  | 46.3594 |  |  | 42.6094 |  |  | 56.1094 |  |  | 41.25 |  |  | 74.25 |  |  | 55.5 |  |  | 120.75 |  |  | 73.5 |  |  | 105.25 |  |  | 61.1875 |  |  | 65.6875 |  |  | 55.3594 |  |  | 84.8594 |  |  | 43 |  |  | 65.5 |  |  | 25.9844 |  |  | 74.4844 |  |  | 61.5 |  |  | 79.6875 |  |  | 57.4844 |  |  | 79.3594 |  |  | 69.75 |  |  | 54.4844 |  |  | 61.6875 |  |  | 128.4844 |  |  | 48.4844 |  |  | 43 |  |  | 95.4844 |  |  | 23.5 |  |  | 49.5 |  |  | 69.9844 |  |  | 93.1875 |  |  | 153.2344 |  |  | 69.2344 |  |  | 43.2344 |  |  | 27.2344 |  |  | 108.9844 |  |  | 114.2344 |  |  | 30.9375 |  |  | 92.3594 |  |  | 54.1094 |  |  | 70.6875 |  |  | 115.1875 |  |  | 19.7344 |  |  | 106.7344 |  |  | 25.9375 |  |  | 89.7344 |  |  | 75.8594 |  |  | 66.6094 |  |  | 126.25 |  |  | 65.25 |  |  | 106.6875 |  |  | 101.3594 |  |  | 44.1094 |  |  | 106.6875 |  |  | 118.7344 |  |  | 39.8594 |  |  | 91.5 |  |  | 103.6875 |  |  | 63.8594 |  |  | 92.1094 |  |  | 82.9844 |  |  | 37 |  |  | 69.75 |  |  | 69.9844 |  |  | 60.2344 |  |  | 22.1875 |  |  | 53.8594 |  |  | 61.5 |  |  | 29.6875 |  |  | 69.9844 |  |  | 47.4844 |  |  | 117.2344 |  |  | 96.1875 |  |  | 48.4844 |  |  | 75.9375 |  |  | 145.1875 |  |  | 87.9375 |  |  | 66.8594 |  |  | 135.2344 |  |  | 84.8594 |  |  | 104.4844 |  |  | 110.4844 |  |  | 56.8594 |  |  | 95.7344 |  |  | 40.2344 |  |  | 59.4844 |  |  | 84.4844 |  |  | 73.5 |  |  | 91.6875 |  |  | 129.1875 |  |  | 42.1094 |  |  | 39.8594 |  |  | 70.1875 |  |  | 61.9375 |  |  | 21.75 |  |  | 27.8594 |  |  | 89.8594 |  |  | 38.4844 |  |  | 60.1875 |  |  | 69.75 |  |  | 55.1875 |  |  | 19 |  |  | 120.8594 |  |  | 102.6094 |  |  | 16.3594 |  |  | 49.7344 |  |  | 96.1875 |  |  | 38.25 |  |  | 134.25 |  |  | 75 |  |  | 120.75 |  |  | 53.8594 |  |  | 69.9844 |  |  | 72.9375 |  |  | 77.25 |  |  | 100.7344 |  |  | 51 |  |  | 99.75 |  |  | 99.75 |  |  | 88.6094 |  |  | 61.75 |  |  | 77.25 |  |  | 89.4375 |  |  | 87.9375 |  |  | 51 |  |  | 72.9844 |  |  | 50.1094 |  |  | 88.6094 |  |  | 109.7344 |  |  | 79.7344 |  |  | 87.6094 |  |  | 18.4375 |  |  | 90.1875 |  |  | 83.5 |  |  | 172.75 |  |  | 110.25 |  |  | 95.8594 |  |  | 85.5 |  |  | 67.6094 |  |  | 91.5 |  |  | 55.3594 |  |  | 54.1875 |  |  | 91.5 |  |  | 74.4844 |  |  | 118.6875 |  |  | 84.8594 |  |  | 18 |  |  | 48.9375 |  |  | 93.1875 |  |  | 91.5 |  |  | 84.8594 |  |  | 89.6875 |  |  | 110.25 |  |  | 65.6875 |  |  | 88.75 |  |  | 78.2344 |  |  | 102.8594 |  |  | 74.25 |  |  | 23.4844 |  |  | 29.7344 |  |  | 106.7344 |  |  | 51.9844 |  |  | 95.4844 |  |  | 60.75 |  |  | 70.3594 |  |  | 111.1875 |  |  | 85.9375 |  |  | 99.2344 |  |  | 38.3594 |  |  | 66.2344 |  |  | 78.1875 |  |  | 88.2344 |  |  | 116.4844 |  |  | 94.6875 |  |  | 103.6875 |  |  | 84.4844 |  |  | 69.1875 |  |  | 97.6875 |  |  | 75 |  |  | 87.9375 |  |  | 40.9375 |  |  | 79.3594 |  |  | 72.9844 |  |  | 75.1094 |  |  | 43.6875 |  |  | 60.75 |  |  | 72.9844 |  |  | 65.1094 |  |  | 56.6875 |  |  | 98.1094 |  |  | 55.3594 |  |  | 95.4844 |  |  | 76.1875 |  |  | 123.4844 |  |  | 69.1875 |  |  | 99.1094 |  |  | 41.25 |  |  | 59.7344 |  |  | 55.5 |  |  | 43.3594 |  |  | 87 |  |  | 55.6875 |  |  | 53.8594 |  |  | 75.8594 |  |  | 101.25 |  |  | 46.3594 |  |  | 88.75 |  |  | 27.2344 |  |  | 61.5 |  |  | 14.6875 |  |  | 25.9375 |  |  | 126.2344 |  |  | 69.9844 |  |  | 79.3594 |  |  | 84.8594 |  |  | 61.6875 |  |  | 41.25 |  |  | 13.9844 |  |  | 126.8594 |  |  | 61.3594 |  |  | 110.4844 |  |  | 91.75 |  |  | 45 |  |  | 42.6094 |  |  | 112.2344 |  |  | 67.6094 |  |  | 7.7344 |  |  | 100.6875 |  |  | 56.1094 |  |  | 92.1094 |  |  | 85.7344 |  |  | 43 |  |  | 71.25 |  |  | 78.2344 |  |  | 116.6875 |  |  | 69.75 |  |  | 95.8594 |  |  | 51.6094 |  |  | 88.2344 |  |  | 79.1875 |  |  | 95.8594 |  |  | 128.4844 |  |  | 88.6094 |  |  | 76.6094 |  |  | 24.6094 |  |  | 129.1875 |  |  | 76.3594 |  |  | 74.25 |  |  | 71.3594 |  |  | 61.9844 |  |  | 20.7344 |  |  | 29.4375 |  |  | 63.1094 |  |  | 42.9844 |  |  | 91.5 |  |  | 33.9844 |  |  | 105.25 |  |  | 20.7344 |  |  | 20.8594 |  |  | 126.25 |  |  | 77.6875 |  |  | 25.9844 |  |  | 67.6094 |  |  | 76.3594 |  |  | 123.4844 |  |  | 57.6094 |  |  | 60.75 |  |  | 111.6094 |  |  | 49.5 |  |  | 97.5 |  |  | 25.9844 |  |  | 41.25 |  |  | 30.9375 |  |  | 51 |  |  | 83.5 |  |  | 63 |  |  | 89.1094 |  |  | 20.4844 |  |  | 56.8594 |  |  | 39.1875 |  |  | 49.7344 |  |  | 41.4375 |  |  | 45.1875 |  |  | 122.8594 |  |  | 134.25 |  |  | 84.4844 |  |  | 65.1094 |  |  | 63.1094 |  |  | 51.6094 |  |  | 67.6094 |  |  | 21.6094 |  |  | 65.1094 |  |  | 92.3594 |  |  | 59.5 |  |  | 42.1094 |  |  | 77.6875 |  |  | 66.4375 |  |  | 61.9844 |  |  | 29.6875 |  |  | 99.75 |  |  | 61.1875 |  |  | 92.1094 |  |  | 97.5 |  |  | 69.75 |  |  | 92.6875 |  |  | 53.8594 |  |  | 97.9375 |  |  | 88.6094 |  |  | 89.7344 |  |  | 47.1094 |  |  | 33.1875 |  |  | 51.6094 |  |  | 61.6875 |  |  | 69.25 |  |  | 69.25 |  |  | 92.4844 |  |  | 38.3594 |  |  | 56.1094 |  |  | 82.7344 |  |  | 59.25 |  |  | 75.1875 |  |  | 126.6094 |  |  | 109.6094 |  |  | 66.2344 |  |  | 91.5 |  |  | 41.4375 |  |  | 122.8594 |  |  | 66.2344 |  |  | 95.8594 |  |  | 55.6875 |  |  | 108.75 |  |  | 23.25 |  |  | 90.4844 |  |  | 49.5 |  |  | 53.1094 |  |  | 59.5 |  |  | 60.2344 |  |  | 95.5 |  |  | 51.6094 |  |  | 54.75 |  |  | 29.3594 |  |  | 30.2344 |  |  | 61.7344 |  |  | 33.9844 |  |  | 86.8594 |  |  | 56.4375 |  |  | 65.25 |  |  | 85.9375 |  |  | 79.1875 |  |  | 79.1875 |  |  | 170.1094 |  |  | 80.1094 |  |  | 37 |  |  | 90.1875 |  |  | 69.25 |  |  | 118.6875 |  |  | 58.9375 |  |  | 17.8594 |  |  | 30 |  |  | 76.1875 |  |  | 76.1875 |  |  | 61.5 |  |  | 91.5 |  |  | 92.1094 |  |  | 60.75 |  |  | 116.6875 |  |  | 59.5 |  |  | 72.9375 |  |  | 116.6875 |  |  | 111.6094 |  |  | 74.25 |  |  | 89.7344 |  |  | 25.9375 |  |  | 75.75 |  |  | 78.2344 |  |  | 63.1094 |  |  | 6.2344 |  |  | 62.3594 |  |  | 142.9844 |  |  | 30.2344 |  |  | 39.9375 |  |  | 45 |  |  | 43.3594 |  |  | 74.25 |  |  | 29.6875 |  |  | 63.4844 |  |  | 51.75 |  |  | 20.8594 |  |  | 30.75 |  |  | 123.4844 |  |  | 6.4844 |  |  | 42.1094 |  |  | 88.6875 |  |  | 23.4844 |  |  | 63.1094 |  |  | 52.2344 |  |  | 54.1094 |  |  | 40.7344 |  |  | 63.4844 |  |  | 82.6875 |  |  | 96.1875 |  |  | 38.3594 |  |  | 97.6875 |  |  | 61.3594 |  |  | 55.6875 |  |  | 89.4375 |  |  | 96.1875 |  |  | 84.8594 |  |  | 74.25 |  |  | 74.8594 |  |  | 49.7344 |  |  | 116.1094 |  |  | 52.2344 |  |  | 88.75 |  |  | 57.6094 |  |  | 30.6094 |  |  | 106.1875 |  |  | 76.1875 |  |  | 95.4844 |  |  | 79.3594 |  |  | 61.3594 |  |  | 135.2344 |  |  | 73.7344 |  |  | 60.6094 |  |  | 92.3594 |  |  | 50.8594 |  |  | 44.1094 |  |  | 61.5 |  |  | 103.6875 |  |  | 56.8594 |  |  | 101.25 |  |  | 55.5 |  |  | 65.6875 |  |  | 91.5 |  |  | 42.9375 |  |  | 120.75 |  |  | 92.7344 |  |  | 63.1094 |  |  | 53.5 |  |  | 65.1094 |  |  | 61.6875 |  |  | 72.1094 |  |  | 39.4375 |  |  | 100.2344 |  |  | 123.9844 |  |  | 84.8594 |  |  | 92.4844 |  |  | 70.3594 |  |  | 89.6875 |  |  | 76.3594 |  |  | 35.4375 |  |  | 79.1875 |  |  | 81.1875 |  |  | 5.8594 |  |  | 95.5 |  |  | 61.6875 |  |  | 8.4375 |  |  | 75.25 |  |  | 87.9375 |  |  | 63.2344 |  |  | 27.2344 |  |  | 76.75 |  |  | 117.2344 |  |  | 75.8594 |  |  | 65.1094 |  |  | 95.4844 |  |  | 51.6094 |  |  | 76.3594 |  |  | 49.7344 |  |  | 45.1875 |  |  | 73.2344 |  |  | 84.4844 |  |  | 74.4844 |  |  | 84.4844 |  |  | 91.5 |  |  | 101.3594 |  |  | 74.25 |  |  | 94.3594 |  |  | 91.1875 |  |  | 75.2344 |  |  | 27 |  |  | 66.2344 |  |  | 96.1875 |  |  | 47.1094 |  |  | 59.25 |  |  | 42.9844 |  |  | 88.2344 |  |  | 114.9844 |  |  | 89.4375 |  |  | 76.5 |  |  | 54.1094 |  |  | 84.8594 |  |  | 55.5 |  |  | 112.2344 |  |  | 78.2344 |  |  | 119.7344 |  |  | 22 |  |  | 93.1875 |  |  | 79.3594 |  |  | 45 |  |  | 45 |  |  | 49.6094 |  |  | 91.5 |  |  | 103.6094 |  |  | 106.7344 |  |  | 74.25 |  |  | 159.9844 |  |  | 63 |  |  | 55.5 |  |  | 39.9375 |  |  | 52.2344 |  |  | 120.75 |  |  | 70.1875 |  |  | 95.8594 |  |  | 85.7344 |  |  | 19.9844 |  |  | 138.2344 |  |  | 72.9844 |  |  | 65.1094 |  |  | 82.6875 |  |  | 114.2344 |  |  | 19.6094 |  |  | 18.9375 |  |  | 125.4844 |  |  | 147.75 |  |  | 39.2344 |  |  | 115.1875 |  |  | 18.75 |  |  | 91.1875 |  |  | 92.1094 |  |  | 35.4375 |  |  | 43.2344 |  |  | 51.2344 |  |  | 63.2344 |  |  | 43.75 |  |  | 91.5 |  |  | 89.6875 |  |  | 42.1875 |  |  | 101.6875 |  |  | 85.5 |  |  | 125.4844 |  |  | 47.1094 |  |  | 60.6094 |  |  | 77.25 |  |  | 45 |  |  | 112.2344 |  |  | 79.1875 |  |  | 79.6875 |  |  | 69.9844 |  |  | 96.1875 |  |  | 27.2344 |  |  | 74.4844 |  |  | 30 |  |  | 65.1094 |  |  | 89.7344 |  |  | 71.1094 |  |  | 116.6875 |  |  | 39.9375 |  |  | 82.9844 |  |  | 40.3594 |  |  | 18.1094 |  |  | 56.8594 |  |  | 41.5 |  |  | 119.5 |  |  | 33.9844 |  |  | 74.25 |  |  | 46.6875 |  |  | 44.1094 |  |  | 88.6094 |  |  | 95.4844 |  |  | 39.8594 |  |  | 63.1094 |  |  | 62.3594 |  |  | 55.1875 |  |  | 85.9375 |  |  | 56.4375 |  |  | 70.1875 |  |  | 74.25 |  |  | 55.6875 |  |  | 128.4844 |  |  | 55.5 |  |  | 38.3594 |  |  | 79.3594 |  |  | 73.5 |  |  | 93.1875 |  |  | 101.25 |  |  | 73.5 |  |  | 93.25 |  |  | 61.3594 |  |  | 30.4375 |  |  | 33.25 |  |  | 2.8594 |  |  | 60.1875 |  |  | 24.1875 |  |  | 43 |  |  | 51.6094 |  |  | 62.3594 |  |  | 39.25 |  |  | 38.3594 |  |  | 46.6875 |  |  | 93.6094 |  |  | 113.4375 |  |  | 66.8594 |  |  | 27.9375 |  |  | 78.1875 |  |  | 33.9844 |  |  | 65.1094 |  |  | 92.7344 |  |  | 61.5 |  |  | 82.6875 |  |  | 88.6094 |  |  | 20.8594 |  |  | 70.1875 |  |  | 59.5 |  |  | 97.9375 |  |  | 83.4844 |  |  | 67.6094 |  |  | 92.4844 |  |  | 81.1875 |  |  | 89.4844 |  |  | 59.5 |  |  | 93.1875 |  |  | 69.25 |  |  | 82.6875 |  |  | 5.8594 |  |  | 101.25 |  |  | 43.3594 |  |  | 119.5 |  |  | 63 |  |  | 65.6875 |  |  | 91.75 |  |  | 102.8594 |  |  | 99.2344 |  |  | 49.5 |  |  | 21 |  |  | 39.9375 |  |  | 83.8594 |  |  | 59.5 |  |  | 69.25 |  |  | 94.3594 |  |  | 106.7344 |  |  | 76.1875 |  |  | 87.6094 |  |  | 69.2344 |  |  | 73.2344 |  |  | 45 |  |  | 101.3594 |  |  | 56.1094 |  |  | 118.6875 |  |  | 22 |  |  | 153.2344 |  |  | 111.6094 |  |  | 90.25 |  |  | 53.4844 |  |  | 84 |  |  | 46.6875 |  |  | 93.25 |  |  | 55.6875 |  |  | 32.1094 |  |  | 83.8594 |  |  | 84.8594 |  |  | 89.4375 |  |  | 93.1875 |  |  | 45 |  |  | 22 |  |  | 40.1875 |  |  | 85.5 |  |  | 64.6875 |  |  | 76.1875 |  |  | 106.6875 |  |  | 40.3594 |  |  | 103.6875 |  |  | 18.75 |  |  | 43 |  |  | 104.4844 |  |  | 42.2344 |  |  | 123.75 |  |  | 129.9844 |  |  | 79.6094 |  |  | 103.6875 |  |  | 89.25 |  |  | 53.7344 |  |  | 91.5 |  |  | 93.6094 |  |  | 59.5 |  |  | 63.9375 |  |  | 118.6875 |  |  | 42.9375 |  |  | 73.5 |  |  | 82.9844 |  |  | 47.1094 |  |  | 79.3594 |  |  | 109.5 |  |  | 90.2344 |  |  | 65.6875 |  |  | 33.1875 |  |  | 96.1875 |  |  | 107.8594 |  |  | 97.6875 |  |  | 80.1094 |  |  | 37 |  |  | 89.25 |  |  | 103.6875 |  |  | 111.1875 |  |  | 116.4844 |  |  | 93.25 |  |  | 57.6094 |  |  | 30.9375 |  |  | 38.3594 |  |  | 46.6875 |  |  | 96.1875 |  |  | 103.6875 |  |  | 74.25 |  |  | 89.1094 |  |  | 60.1875 |  |  | 43.6875 |  |  | 53.4844 |  |  | 81.1875 |  |  | 147.75 |  |  | 87.8594 |  |  | 91.75 |  |  | 65.5 |  |  | 25.9844 |  |  | 67.6875 |  |  | 110.4844 |  |  | 116.6875 |  |  | 71.4375 |  |  | 57.6094 |  |  | 140.1094 |  |  | 8.4844 |  |  | 71.4375 |  |  | 117.2344 |  |  | 70.1875 |  |  | 59.7344 |  |  | 51.9375 |  |  | 86.4375 |  |  | 42.1094 |  |  | 58 |  |  | 112.2344 |  |  | 75.25 |  |  | 68.4844 |  |  | 89.8594 |  |  | 89.7344 |  |  | 75.1094 |  |  | 90.1875 |  |  | 69.2344 |  |  | 73.2344 |  |  | 49.7344 |  |  | 69.2344 |  |  | 43.6094 |  |  | 8.25 |  |  | 75.9375 |  |  | 119.5 |  |  | 83.5 |  |  | 93.6094 |  |  | 29.1094 |  |  | 74.25 |  |  | 45.1875 |  |  | 111.6094 |  |  | 67.6094 |  |  | 79.3594 |  |  | 76.1875 |  |  | 65.25 |  |  | 79.9844 |  |  | 63 |  |  | 126.25 |  |  | 65.1094 |  |  | 78.2344 |  |  | 74.4844 |  |  | 53.8594 |  |  | 79 |  |  | 70.1875 |  |  | 55.6875 |  |  | 29.4844 |  |  | 63.1094 |  |  | 55.3594 |  |  | 66.9844 |  |  | 43.6094 |  |  | 95.7344 |  |  | 95.7344 |  |  | 95.5 |  |  | 30.6094 |  |  | 35.4375 |  |  | 87.75 |  |  | 44.1094 |  |  | 101.25 |  |  | 142.9844 |  |  | 79.3594 |  |  | 80.1094 |  |  | 56.4375 |  |  | 103.6875 |  |  | 99.4844 |  |  | 88.75 |  |  | 72.4375 |  |  | 85.7344 |  |  | 82.7344 |  |  | 79.7344 |  |  | 91.5 |  |  | 59.4844 |  |  | 63 |  |  | 42.2344 |  |  | 70.1875 |  |  | 40.5 |  |  | 26.4375 |  |  | 69.2344 |  |  | 51.75 |  |  | 26.4844 |  |  | 18.4375 |  |  | 63 |  |  | 38.4844 |  |  | 90.1875 |  |  | 97.6875 |  |  | 24.1875 |  |  | 74.25 |  |  | 169.6875 |  |  | 117.2344 |  |  | 23.4844 |  |  | 75.8594 |  |  | 113.25 |  |  | 38.8594 |  |  | 91.6875 |  |  | 72.1094 |  |  | 73.5 |  |  | 60.1875 |  |  | 43.3594 |  |  | 95.4844 |  |  | 27 |  |  | 105.25 |  |  | 55.3594 |  |  | 82.9844 |  |  | 73.5 |  |  | 88.6094 |  |  | 91.9844 |  |  | 23.25 |  |  | 59.7344 |  |  | 55.6875 |  |  | 73.2344 |  |  | 37 |  |  | 85.5 |  |  | 119.7344 |  |  | 22 |  |  | 72.9844 |  |  | 42.9375
29.1822 | ← Mean |  | 26.25 |  |  | 33.375 |  |  | 32.125 |  |  | 22.875 |  |  | 35.125 |  |  | 27.875 |  |  | 31.125 |  |  | 31 |  |  | 34.125 |  |  | 30.875 |  |  | 31 |  |  | 33.875 |  |  | 34.25 |  |  | 28.375 |  |  | 25 |  |  | 32 |  |  | 26.25 |  |  | 27.25 |  |  | 34.75 |  |  | 23.5 |  |  | 28.375 |  |  | 27.25 |  |  | 30.125 |  |  | 27.5 |  |  | 24.875 |  |  | 26.625 |  |  | 26.5 |  |  | 29.125 |  |  | 31.375 |  |  | 22.375 |  |  | 22.875 |  |  | 31.125 |  |  | 22.875 |  |  | 28 |  |  | 25.25 |  |  | 30.75 |  |  | 29.75 |  |  | 24.875 |  |  | 28.5 |  |  | 29.125 |  |  | 27.75 |  |  | 33.125 |  |  | 31.5 |  |  | 32 |  |  | 33.375 |  |  | 34.625 |  |  | 27.25 |  |  | 29.5 |  |  | 27.75 |  |  | 27.5 |  |  | 29.5 |  |  | 30.125 |  |  | 27.5 |  |  | 29.625 |  |  | 26.375 |  |  | 22.375 |  |  | 25.125 |  |  | 28.75 |  |  | 33.125 |  |  | 33.375 |  |  | 29.125 |  |  | 28.25 |  |  | 27.75 |  |  | 28.5 |  |  | 26.875 |  |  | 25.875 |  |  | 28.625 |  |  | 27.5 |  |  | 29.25 |  |  | 28.625 |  |  | 32.625 |  |  | 31.125 |  |  | 24.5 |  |  | 31 |  |  | 33.875 |  |  | 28.5 |  |  | 28.875 |  |  | 27.5 |  |  | 25.5 |  |  | 27.125 |  |  | 26.625 |  |  | 27 |  |  | 27.75 |  |  | 27.375 |  |  | 29.5 |  |  | 31.125 |  |  | 34 |  |  | 29.5 |  |  | 25.25 |  |  | 27 |  |  | 27.125 |  |  | 24.875 |  |  | 27 |  |  | 28.5 |  |  | 27.5 |  |  | 29.125 |  |  | 30.625 |  |  | 32.5 |  |  | 29.125 |  |  | 23.375 |  |  | 28.5 |  |  | 31 |  |  | 30.75 |  |  | 32 |  |  | 29.375 |  |  | 27.25 |  |  | 32.125 |  |  | 37.625 |  |  | 31.625 |  |  | 32.75 |  |  | 30.875 |  |  | 32.625 |  |  | 27.375 |  |  | 33 |  |  | 29.625 |  |  | 26.25 |  |  | 25.625 |  |  | 25.625 |  |  | 32 |  |  | 34.375 |  |  | 33.875 |  |  | 29.125 |  |  | 30 |  |  | 29.5 |  |  | 29.875 |  |  | 33.125 |  |  | 25.625 |  |  | 32.375 |  |  | 27.875 |  |  | 25.875 |  |  | 30.875 |  |  | 29 |  |  | 29.125 |  |  | 31.125 |  |  | 24.875 |  |  | 28.375 |  |  | 31.625 |  |  | 32.75 |  |  | 32.375 |  |  | 28.125 |  |  | 30.125 |  |  | 25.25 |  |  | 29.875 |  |  | 33.375 |  |  | 26.375 |  |  | 37 |  |  | 29.5 |  |  | 30.125 |  |  | 22.125 |  |  | 30.125 |  |  | 34 |  |  | 27.25 |  |  | 26.25 |  |  | 31.5 |  |  | 34.625 |  |  | 31.875 |  |  | 25.875 |  |  | 25.875 |  |  | 28.125 |  |  | 25.5 |  |  | 29 |  |  | 28.5 |  |  | 29 |  |  | 27 |  |  | 28 |  |  | 22.75 |  |  | 27.25 |  |  | 30.125 |  |  | 29.125 |  |  | 26.5 |  |  | 26.5 |  |  | 27.625 |  |  | 26.375 |  |  | 27.5 |  |  | 26.25 |  |  | 28.375 |  |  | 30.875 |  |  | 31.5 |  |  | 28.375 |  |  | 33.75 |  |  | 32.625 |  |  | 27.625 |  |  | 26.5 |  |  | 30.375 |  |  | 20.5 |  |  | 30.5 |  |  | 29.625 |  |  | 30.75 |  |  | 29.625 |  |  | 29.375 |  |  | 24.625 |  |  | 27.375 |  |  | 29.375 |  |  | 26.375 |  |  | 29.75 |  |  | 26.125 |  |  | 23.125 |  |  | 28.25 |  |  | 34.75 |  |  | 28.625 |  |  | 31.625 |  |  | 27.25 |  |  | 25.375 |  |  | 26.875 |  |  | 31.875 |  |  | 31 |  |  | 30 |  |  | 27.75 |  |  | 29.875 |  |  | 28.875 |  |  | 27.75 |  |  | 29.375 |  |  | 26.875 |  |  | 28.5 |  |  | 29.75 |  |  | 29.875 |  |  | 28.125 |  |  | 30.625 |  |  | 29.5 |  |  | 31.5 |  |  | 29.625 |  |  | 27.375 |  |  | 27.25 |  |  | 24.875 |  |  | 27.5 |  |  | 27.25 |  |  | 29.625 |  |  | 29.625 |  |  | 29.625 |  |  | 27.75 |  |  | 27.625 |  |  | 26.25 |  |  | 30.25 |  |  | 32.75 |  |  | 32.125 |  |  | 30.375 |  |  | 29.125 |  |  | 35.375 |  |  | 27.375 |  |  | 30.875 |  |  | 30.625 |  |  | 28.375 |  |  | 32.375 |  |  | 34.375 |  |  | 31.5 |  |  | 32.75 |  |  | 30.75 |  |  | 26.125 |  |  | 26.875 |  |  | 31.75 |  |  | 30.25 |  |  | 24 |  |  | 26.125 |  |  | 25.125 |  |  | 28.625 |  |  | 27.75 |  |  | 31.5 |  |  | 25.75 |  |  | 25 |  |  | 29.125 |  |  | 31.875 |  |  | 24.125 |  |  | 35.625 |  |  | 32.25 |  |  | 33 |  |  | 29 |  |  | 27.5 |  |  | 33 |  |  | 25.125 |  |  | 34.625 |  |  | 31.25 |  |  | 26 |  |  | 35.375 |  |  | 29 |  |  | 32 |  |  | 32 |  |  | 29.125 |  |  | 28 |  |  | 26 |  |  | 28.25 |  |  | 32.75 |  |  | 31.5 |  |  | 29.375 |  |  | 28.875 |  |  | 29.125 |  |  | 32.375 |  |  | 34.625 |  |  | 33.125 |  |  | 24.25 |  |  | 31.25 |  |  | 29.5 |  |  | 31 |  |  | 27 |  |  | 28.125 |  |  | 30.5 |  |  | 29.875 |  |  | 28.5 |  |  | 30.125 |  |  | 23.75 |  |  | 28.5 |  |  | 26.375 |  |  | 29.25 |  |  | 29.125 |  |  | 24 |  |  | 29.25 |  |  | 30.75 |  |  | 28.5 |  |  | 29.125 |  |  | 28.75 |  |  | 27 |  |  | 30.25 |  |  | 37 |  |  | 26.375 |  |  | 32.125 |  |  | 33 |  |  | 28.625 |  |  | 27.625 |  |  | 31.625 |  |  | 28.625 |  |  | 30.375 |  |  | 27.5 |  |  | 33.125 |  |  | 26.75 |  |  | 28.75 |  |  | 30.375 |  |  | 26.125 |  |  | 29.625 |  |  | 32.75 |  |  | 34.375 |  |  | 31.625 |  |  | 35.75 |  |  | 29.75 |  |  | 34.375 |  |  | 26.25 |  |  | 33.75 |  |  | 27.5 |  |  | 32.75 |  |  | 25.75 |  |  | 30.125 |  |  | 29.375 |  |  | 32.875 |  |  | 26.25 |  |  | 27.5 |  |  | 29.375 |  |  | 30.125 |  |  | 31.75 |  |  | 30.125 |  |  | 37.875 |  |  | 30.375 |  |  | 27.25 |  |  | 31.375 |  |  | 26.25 |  |  | 32.125 |  |  | 25.5 |  |  | 30.625 |  |  | 24.5 |  |  | 30.875 |  |  | 31.5 |  |  | 24.75 |  |  | 25.125 |  |  | 26.875 |  |  | 30 |  |  | 25.875 |  |  | 37 |  |  | 26.375 |  |  | 27.5 |  |  | 24.25 |  |  | 21.25 |  |  | 25.625 |  |  | 33.375 |  |  | 30.125 |  |  | 29.125 |  |  | 33.75 |  |  | 25.5 |  |  | 22.375 |  |  | 35.875 |  |  | 27.125 |  |  | 27.375 |  |  | 32.5 |  |  | 25.5 |  |  | 25.875 |  |  | 33.625 |  |  | 29.875 |  |  | 26.625 |  |  | 23.75 |  |  | 28.125 |  |  | 28.125 |  |  | 35.625 |  |  | 26.5 |  |  | 27.5 |  |  | 28.625 |  |  | 33.25 |  |  | 31.5 |  |  | 28.125 |  |  | 30.125 |  |  | 34.375 |  |  | 34.75 |  |  | 28.125 |  |  | 32.625 |  |  | 29.125 |  |  | 32.125 |  |  | 27.875 |  |  | 30.75 |  |  | 31.125 |  |  | 33 |  |  | 29.125 |  |  | 33.625 |  |  | 24.625 |  |  | 26.25 |  |  | 32.125 |  |  | 25.625 |  |  | 28.5 |  |  | 29.625 |  |  | 28 |  |  | 24.625 |  |  | 24.875 |  |  | 31 |  |  | 25.75 |  |  | 27.625 |  |  | 29.875 |  |  | 31.125 |  |  | 31.375 |  |  | 27.875 |  |  | 35 |  |  | 30.125 |  |  | 30.5 |  |  | 27.5 |  |  | 27.625 |  |  | 28.5 |  |  | 29.75 |  |  | 31.5 |  |  | 29.5 |  |  | 27 |  |  | 34.125 |  |  | 25.625 |  |  | 30.875 |  |  | 29.25 |  |  | 35.625 |  |  | 25.25 |  |  | 25.25 |  |  | 28.875 |  |  | 29 |  |  | 34.375 |  |  | 27.125 |  |  | 32.125 |  |  | 30.125 |  |  | 29.875 |  |  | 21.875 |  |  | 30.125 |  |  | 26.125 |  |  | 32.5 |  |  | 26.125 |  |  | 25.75 |  |  | 31.75 |  |  | 27.625 |  |  | 27.25 |  |  | 32 |  |  | 22.75 |  |  | 28.125 |  |  | 27.5 |  |  | 31.5 |  |  | 34.75 |  |  | 24.875 |  |  | 30.25 |  |  | 26.125 |  |  | 25.375 |  |  | 27.875 |  |  | 21.75 |  |  | 30.125 |  |  | 33.75 |  |  | 29.5 |  |  | 29.5 |  |  | 32.625 |  |  | 29.125 |  |  | 28.125 |  |  | 29.375 |  |  | 30.5 |  |  | 29.25 |  |  | 30.875 |  |  | 26.875 |  |  | 33.375 |  |  | 28.5 |  |  | 25.25 |  |  | 31.125 |  |  | 33.375 |  |  | 28.125 |  |  | 24.75 |  |  | 39 |  |  | 22.5 |  |  | 28.375 |  |  | 30.5 |  |  | 24.125 |  |  | 32.5 |  |  | 27.375 |  |  | 32.5 |  |  | 30.125 |  |  | 29 |  |  | 26.875 |  |  | 26.625 |  |  | 23.375 |  |  | 29.625 |  |  | 28.875 |  |  | 30.75 |  |  | 30 |  |  | 28.75 |  |  | 34.75 |  |  | 34.75 |  |  | 28.875 |  |  | 31.125 |  |  | 29.5 |  |  | 28.25 |  |  | 29.5 |  |  | 29.25 |  |  | 27.25 |  |  | 28.875 |  |  | 26 |  |  | 28.75 |  |  | 27.25 |  |  | 27.5 |  |  | 28.5 |  |  | 28.125 |  |  | 27.5 |  |  | 31.75 |  |  | 32.5 |  |  | 31.25 |  |  | 31.75 |  |  | 34.875 |  |  | 29 |  |  | 25.375 |  |  | 27.25 |  |  | 36 |  |  | 26.375 |  |  | 32.125 |  |  | 24.375 |  |  | 26.875 |  |  | 30.625 |  |  | 26.625 |  |  | 26.25 |  |  | 25.5 |  |  | 30.875 |  |  | 29 |  |  | 27.25 |  |  | 31.375 |  |  | 24.5 |  |  | 24.875 |  |  | 27 |  |  | 31.375 |  |  | 25.375 |  |  | 26.125 |  |  | 26.75 |  |  | 27.375 |  |  | 32.125 |  |  | 34.375 |  |  | 29.875 |  |  | 26.625 |  |  | 31.375 |  |  | 37.25 |  |  | 27.75 |  |  | 29.125 |  |  | 33.75 |  |  | 27.125 |  |  | 32.75 |  |  | 28.25 |  |  | 32.25 |  |  | 29.125 |  |  | 27 |  |  | 27.125 |  |  | 35.625 |  |  | 31.125 |  |  | 34.375 |  |  | 25 |  |  | 27.875 |  |  | 21.125 |  |  | 31.75 |  |  | 28.75 |  |  | 32.375 |  |  | 30.875 |  |  | 27.125 |  |  | 30.375 |  |  | 26.625 |  |  | 30.875 |  |  | 26.125 |  |  | 27.875 |  |  | 31.125 |  |  | 27.5 |  |  | 29.75 |  |  | 24.125 |  |  | 30 |  |  | 24.5 |  |  | 30.25 |  |  | 25.5 |  |  | 28.25 |  |  | 29 |  |  | 30.625 |  |  | 32.125 |  |  | 23.5 |  |  | 30.125 |  |  | 33.75 |  |  | 26.875 |  |  | 28.75 |  |  | 24.625 |  |  | 26.625 |  |  | 29.125 |  |  | 32.625 |  |  | 33.125 |  |  | 28.75 |  |  | 31.125 |  |  | 29.25 |  |  | 34.75 |  |  | 29.75 |  |  | 24.125 |  |  | 32.5 |  |  | 33.75 |  |  | 25.25 |  |  | 26.5 |  |  | 32.75 |  |  | 30.375 |  |  | 27.375 |  |  | 31 |  |  | 29.625 |  |  | 26.875 |  |  | 30.125 |  |  | 35.625 |  |  | 30.125 |  |  | 31.125 |  |  | 32.375 |  |  | 25.25 |  |  | 31.375 |  |  | 34.375 |  |  | 27.375 |  |  | 34.375 |  |  | 28.5 |  |  | 29.875 |  |  | 29 |  |  | 33.875 |  |  | 25.75 |  |  | 37.625 |  |  | 22.5 |  |  | 29.625 |  |  | 27.75 |  |  | 27.875 |  |  | 30.5 |  |  | 25.625 |  |  | 34.375 |  |  | 36.375 |  |  | 28.25 |  |  | 26 |  |  | 23.125 |  |  | 29.125 |  |  | 24.5 |  |  | 33.625 |  |  | 26.375 |  |  | 31.375 |  |  | 28 |  |  | 30.75 |  |  | 30.875 |  |  | 25.5 |  |  | 28.5 |  |  | 32.125 |  |  | 24.5 |  |  | 29.875 |  |  | 31.625 |  |  | 27 |  |  | 26.625 |  |  | 27 |  |  | 28.5 |  |  | 26.25 |  |  | 33.625 |  |  | 29 |  |  | 36.25 |  |  | 28.125 |  |  | 32.375 |  |  | 21.625 |  |  | 32.625 |  |  | 26.625 |  |  | 30.125 |  |  | 30.75 |  |  | 26.375 |  |  | 23.875 |  |  | 25.25 |  |  | 28.625 |  |  | 30 |  |  | 25.625 |  |  | 34.75 |  |  | 28.5 |  |  | 25.75 |  |  | 28.125 |  |  | 29.25 |  |  | 24.625 |  |  | 29.625 |  |  | 30.375 |  |  | 34 |  |  | 25.5 |  |  | 28.75 |  |  | 32.75 |  |  | 30.25 |  |  | 30.5 |  |  | 28.625 |  |  | 27.875 |  |  | 30.875 |  |  | 26 |  |  | 25.5 |  |  | 33.625 |  |  | 34.75 |  |  | 26.25 |  |  | 33.375 |  |  | 27.75 |  |  | 26.375 |  |  | 26.375 |  |  | 26 |  |  | 30.125 |  |  | 25.375 |  |  | 27.875 |  |  | 31.75 |  |  | 26.25 |  |  | 30.625 |  |  | 31.125 |  |  | 20.875 |  |  | 30.875 |  |  | 25 |  |  | 29.5 |  |  | 34.625 |  |  | 29 |  |  | 28.25 |  |  | 28.875 |  |  | 29.125 |  |  | 32.375 |  |  | 26.875 |  |  | 32.125 |  |  | 26.875 |  |  | 25.75 |  |  | 28.75 |  |  | 28.25 |  |  | 31.75 |  |  | 33 |  |  | 24.75 |  |  | 32.625 |  |  | 24.5 |  |  | 29.125 |  |  | 30.125 |  |  | 31.5 |  |  | 30.75 |  |  | 30 |  |  | 31.5 |  |  | 34 |  |  | 27.125 |  |  | 25.75 |  |  | 29.5 |  |  | 24.875 |  |  | 27.75 |  |  | 28.25 |  |  | 26.5 |  |  | 30.125 |  |  | 26.875 |  |  | 26.5 |  |  | 29.125 |  |  | 30.75 |  |  | 27.875 |  |  | 29.75 |  |  | 32.125 |  |  | 26.75 |  |  | 32.75 |  |  | 33.375 |  |  | 30.125 |  |  | 30.625 |  |  | 27.5 |  |  | 28.25 |  |  | 26.125 |  |  | 24.875 |  |  | 31.75 |  |  | 32.5 |  |  | 30.25 |  |  | 31.625 |  |  | 29.875 |  |  | 32.625 |  |  | 29.75 |  |  | 28.625 |  |  | 32.5 |  |  | 30.75 |  |  | 29.5 |  |  | 30.75 |  |  | 25.875 |  |  | 30 |  |  | 24.875 |  |  | 29.5 |  |  | 30.5 |  |  | 30.25 |  |  | 28 |  |  | 32.125 |  |  | 30.375 |  |  | 30.5 |  |  | 27.5 |  |  | 26.25 |  |  | 33.125 |  |  | 29.5 |  |  | 29.5 |  |  | 33.875 |  |  | 27.375 |  |  | 28.75 |  |  | 33.125 |  |  | 29.375 |  |  | 31.375 |  |  | 25.5 |  |  | 29.875 |  |  | 28.125 |  |  | 29.25 |  |  | 28 |  |  | 29.625 |  |  | 30.125 |  |  | 31 |  |  | 24.375 |  |  | 29 |  |  | 30.75 |  |  | 34 |  |  | 32.75 |  |  | 21.875 |  |  | 33.125 |  |  | 29.125 |  |  | 28.25 |  |  | 30.75 |  |  | 25.5 |  |  | 28 |  |  | 27.25 |  |  | 30.5 |  |  | 23.75 |  |  | 28.75 |  |  | 27.75 |  |  | 28.875 |  |  | 29.75 |  |  | 28.5 |  |  | 26.5 |  |  | 35.375 |  |  | 32.625 |  |  | 26 |  |  | 33.375 |  |  | 26.875 |  |  | 29.75 |  |  | 36 |  |  | 28.375 |  |  | 24.5 |  |  | 25.125 |  |  | 32.5 |  |  | 26.75 |  |  | 29.25 |  |  | 30.75 |  |  | 31.5 |  |  | 30.625 |  |  | 27.875 |  |  | 30.125 |  |  | 31.5 |  |  | 25.625 |  |  | 30.25 |  |  | 26.25 |  |  | 32.25 |  |  | 27.125 |  |  | 33.75 |  |  | 28.875 |  |  | 29.5 |  |  | 36 |  |  | 29.75 |  |  | 33.75 |  |  | 31.625 |  |  | 34 |  |  | 27.875 |  |  | 29.75 |  |  | 29.125 |  |  | 30.75 |  |  | 27.75 |  |  | 29.75 |  |  | 27 |  |  | 34.125 |  |  | 27.75 |  |  | 26.25 |  |  | 24.375 |  |  | 29.75 |  |  | 30 |  |  | 32.875 |  |  | 32.5 |  |  | 26.5 |  |  | 27.625 |  |  | 29.75 |  |  | 27.375 |  |  | 33.25 |  |  | 29.25 |  |  | 25.125 |  |  | 36.875 |  |  | 26.375 |  |  | 29.25 |  |  | 29.625 |  |  | 31.75 |  |  | 30.625 |  |  | 24.75 |  |  | 31.25 |  |  | 26.125 |  |  | 28 |  |  | 33.625 |  |  | 26.5 |  |  | 35.375 |  |  | 25.125 |  |  | 25.375 |  |  | 26.125 |  |  | 28.25 |  |  | 29.375 |  |  | 31.375 |  |  | 32.375 |  |  | 29.375 |  |  | 26.875 |  |  | 24.5 |  |  | 26.25 |  |  | 29.5 |  |  | 29.5 |  |  | 27.875 |  |  | 30.125 |  |  | 33 |  |  | 25.25 |  |  | 30.125 |  |  | 29.875 |  |  | 30.875 |  |  | 28.75 |  |  | 30 |  |  | 25.375 |  |  | 30.5 |  |  | 31 |  |  | 30.125 |  |  | 26.375 |  |  | 26.375 |  |  | 25.125 |  |  | 26.5 |  |  | 31.75 |  |  | 24.75 |  |  | 23.625 |  |  | 32.125 |  |  | 30.125 |  |  | 29.625 |  |  | 26.875 |  |  | 30.625 |  |  | 27.625 |  |  | 32.5 |  |  | 21.125 |  |  | 29.25 |  |  | 28.5 |  |  | 36.875 |  |  | 30 |  |  | 30.625 |  |  | 30.875 |  |  | 28.875 |  |  | 27.75 |  |  | 29.75 |  |  | 36.625 |  |  | 37 |  |  | 27.25 |  |  | 35.625 |  |  | 29.375 |  |  | 33.375 |  |  | 28.5 |  |  | 32.375 |  |  | 30.5 |  |  | 32.625 |  |  | 31.75 |  |  | 26 |  |  | 23.25 |  |  | 29.375 |  |  | 24.5 |  |  | 26.625 |  |  | 24.25 |  |  | 30.5 |  |  | 28.625 |  |  | 31.25 |  |  | 33.75 |  |  | 28.25 |  |  | 33 |  |  | 31.25 |  |  | 29.625 |  |  | 27.375 |  |  | 26.875 |  |  | 32 |  |  | 25.875 |  |  | 32.75 |  |  | 26.875 |  |  | 31.5 |  |  | 27.75 |  |  | 30.875 |  |  | 30.375 |  |  | 30.5 |  |  | 28 |  |  | 30.125 |  |  | 30.625 |  |  | 31.5 |  |  | 26.125 |  |  | 30.625 |  |  | 22.5 |  |  | 30.625 |  |  | 24.75 |  |  | 31.375 |  |  | 29.5 |  |  | 30.5 |  |  | 31.375 |  |  | 28 |  |  | 29.375 |  |  | 30.75
Kanban | Trial 1 |  |  | Trial 2 |  |  | Trial 3 |  |  | Trial 4 |  |  | Trial 5 |  |  | Trial 6 |  |  | Trial 7 |  |  | Trial 8 |  |  | Trial 9 |  |  | Trial 10 |  |  | Trial 11 |  |  | Trial 12 |  |  | Trial 13 |  |  | Trial 14 |  |  | Trial 15 |  |  | Trial 16 |  |  | Trial 17 |  |  | Trial 18 |  |  | Trial 19 |  |  | Trial 20 |  |  | Trial 21 |  |  | Trial 22 |  |  | Trial 23 |  |  | Trial 24 |  |  | Trial 25 |  |  | Trial 26 |  |  | Trial 27 |  |  | Trial 28 |  |  | Trial 29 |  |  | Trial 30 |  |  | Trial 31 |  |  | Trial 32 |  |  | Trial 33 |  |  | Trial 34 |  |  | Trial 35 |  |  | Trial 36 |  |  | Trial 37 |  |  | Trial 38 |  |  | Trial 39 |  |  | Trial 40 |  |  | Trial 41 |  |  | Trial 42 |  |  | Trial 43 |  |  | Trial 44 |  |  | Trial 45 |  |  | Trial 46 |  |  | Trial 47 |  |  | Trial 48 |  |  | Trial 49 |  |  | Trial 50 |  |  | Trial 51 |  |  | Trial 52 |  |  | Trial 53 |  |  | Trial 54 |  |  | Trial 55 |  |  | Trial 56 |  |  | Trial 57 |  |  | Trial 58 |  |  | Trial 59 |  |  | Trial 60 |  |  | Trial 61 |  |  | Trial 62 |  |  | Trial 63 |  |  | Trial 64 |  |  | Trial 65 |  |  | Trial 66 |  |  | Trial 67 |  |  | Trial 68 |  |  | Trial 69 |  |  | Trial 70 |  |  | Trial 71 |  |  | Trial 72 |  |  | Trial 73 |  |  | Trial 74 |  |  | Trial 75 |  |  | Trial 76 |  |  | Trial 77 |  |  | Trial 78 |  |  | Trial 79 |  |  | Trial 80 |  |  | Trial 81 |  |  | Trial 82 |  |  | Trial 83 |  |  | Trial 84 |  |  | Trial 85 |  |  | Trial 86 |  |  | Trial 87 |  |  | Trial 88 |  |  | Trial 89 |  |  | Trial 90 |  |  | Trial 91 |  |  | Trial 92 |  |  | Trial 93 |  |  | Trial 94 |  |  | Trial 95 |  |  | Trial 96 |  |  | Trial 97 |  |  | Trial 98 |  |  | Trial 99 |  |  | Trial 100 |  |  | Trial 101 |  |  | Trial 102 |  |  | Trial 103 |  |  | Trial 104 |  |  | Trial 105 |  |  | Trial 106 |  |  | Trial 107 |  |  | Trial 108 |  |  | Trial 109 |  |  | Trial 110 |  |  | Trial 111 |  |  | Trial 112 |  |  | Trial 113 |  |  | Trial 114 |  |  | Trial 115 |  |  | Trial 116 |  |  | Trial 117 |  |  | Trial 118 |  |  | Trial 119 |  |  | Trial 120 |  |  | Trial 121 |  |  | Trial 122 |  |  | Trial 123 |  |  | Trial 124 |  |  | Trial 125 |  |  | Trial 126 |  |  | Trial 127 |  |  | Trial 128 |  |  | Trial 129 |  |  | Trial 130 |  |  | Trial 131 |  |  | Trial 132 |  |  | Trial 133 |  |  | Trial 134 |  |  | Trial 135 |  |  | Trial 136 |  |  | Trial 137 |  |  | Trial 138 |  |  | Trial 139 |  |  | Trial 140 |  |  | Trial 141 |  |  | Trial 142 |  |  | Trial 143 |  |  | Trial 144 |  |  | Trial 145 |  |  | Trial 146 |  |  | Trial 147 |  |  | Trial 148 |  |  | Trial 149 |  |  | Trial 150 |  |  | Trial 151 |  |  | Trial 152 |  |  | Trial 153 |  |  | Trial 154 |  |  | Trial 155 |  |  | Trial 156 |  |  | Trial 157 |  |  | Trial 158 |  |  | Trial 159 |  |  | Trial 160 |  |  | Trial 161 |  |  | Trial 162 |  |  | Trial 163 |  |  | Trial 164 |  |  | Trial 165 |  |  | Trial 166 |  |  | Trial 167 |  |  | Trial 168 |  |  | Trial 169 |  |  | Trial 170 |  |  | Trial 171 |  |  | Trial 172 |  |  | Trial 173 |  |  | Trial 174 |  |  | Trial 175 |  |  | Trial 176 |  |  | Trial 177 |  |  | Trial 178 |  |  | Trial 179 |  |  | Trial 180 |  |  | Trial 181 |  |  | Trial 182 |  |  | Trial 183 |  |  | Trial 184 |  |  | Trial 185 |  |  | Trial 186 |  |  | Trial 187 |  |  | Trial 188 |  |  | Trial 189 |  |  | Trial 190 |  |  | Trial 191 |  |  | Trial 192 |  |  | Trial 193 |  |  | Trial 194 |  |  | Trial 195 |  |  | Trial 196 |  |  | Trial 197 |  |  | Trial 198 |  |  | Trial 199 |  |  | Trial 200 |  |  | Trial 201 |  |  | Trial 202 |  |  | Trial 203 |  |  | Trial 204 |  |  | Trial 205 |  |  | Trial 206 |  |  | Trial 207 |  |  | Trial 208 |  |  | Trial 209 |  |  | Trial 210 |  |  | Trial 211 |  |  | Trial 212 |  |  | Trial 213 |  |  | Trial 214 |  |  | Trial 215 |  |  | Trial 216 |  |  | Trial 217 |  |  | Trial 218 |  |  | Trial 219 |  |  | Trial 220 |  |  | Trial 221 |  |  | Trial 222 |  |  | Trial 223 |  |  | Trial 224 |  |  | Trial 225 |  |  | Trial 226 |  |  | Trial 227 |  |  | Trial 228 |  |  | Trial 229 |  |  | Trial 230 |  |  | Trial 231 |  |  | Trial 232 |  |  | Trial 233 |  |  | Trial 234 |  |  | Trial 235 |  |  | Trial 236 |  |  | Trial 237 |  |  | Trial 238 |  |  | Trial 239 |  |  | Trial 240 |  |  | Trial 241 |  |  | Trial 242 |  |  | Trial 243 |  |  | Trial 244 |  |  | Trial 245 |  |  | Trial 246 |  |  | Trial 247 |  |  | Trial 248 |  |  | Trial 249 |  |  | Trial 250 |  |  | Trial 251 |  |  | Trial 252 |  |  | Trial 253 |  |  | Trial 254 |  |  | Trial 255 |  |  | Trial 256 |  |  | Trial 257 |  |  | Trial 258 |  |  | Trial 259 |  |  | Trial 260 |  |  | Trial 261 |  |  | Trial 262 |  |  | Trial 263 |  |  | Trial 264 |  |  | Trial 265 |  |  | Trial 266 |  |  | Trial 267 |  |  | Trial 268 |  |  | Trial 269 |  |  | Trial 270 |  |  | Trial 271 |  |  | Trial 272 |  |  | Trial 273 |  |  | Trial 274 |  |  | Trial 275 |  |  | Trial 276 |  |  | Trial 277 |  |  | Trial 278 |  |  | Trial 279 |  |  | Trial 280 |  |  | Trial 281 |  |  | Trial 282 |  |  | Trial 283 |  |  | Trial 284 |  |  | Trial 285 |  |  | Trial 286 |  |  | Trial 287 |  |  | Trial 288 |  |  | Trial 289 |  |  | Trial 290 |  |  | Trial 291 |  |  | Trial 292 |  |  | Trial 293 |  |  | Trial 294 |  |  | Trial 295 |  |  | Trial 296 |  |  | Trial 297 |  |  | Trial 298 |  |  | Trial 299 |  |  | Trial 300 |  |  | Trial 301 |  |  | Trial 302 |  |  | Trial 303 |  |  | Trial 304 |  |  | Trial 305 |  |  | Trial 306 |  |  | Trial 307 |  |  | Trial 308 |  |  | Trial 309 |  |  | Trial 310 |  |  | Trial 311 |  |  | Trial 312 |  |  | Trial 313 |  |  | Trial 314 |  |  | Trial 315 |  |  | Trial 316 |  |  | Trial 317 |  |  | Trial 318 |  |  | Trial 319 |  |  | Trial 320 |  |  | Trial 321 |  |  | Trial 322 |  |  | Trial 323 |  |  | Trial 324 |  |  | Trial 325 |  |  | Trial 326 |  |  | Trial 327 |  |  | Trial 328 |  |  | Trial 329 |  |  | Trial 330 |  |  | Trial 331 |  |  | Trial 332 |  |  | Trial 333 |  |  | Trial 334 |  |  | Trial 335 |  |  | Trial 336 |  |  | Trial 337 |  |  | Trial 338 |  |  | Trial 339 |  |  | Trial 340 |  |  | Trial 341 |  |  | Trial 342 |  |  | Trial 343 |  |  | Trial 344 |  |  | Trial 345 |  |  | Trial 346 |  |  | Trial 347 |  |  | Trial 348 |  |  | Trial 349 |  |  | Trial 350 |  |  | Trial 351 |  |  | Trial 352 |  |  | Trial 353 |  |  | Trial 354 |  |  | Trial 355 |  |  | Trial 356 |  |  | Trial 357 |  |  | Trial 358 |  |  | Trial 359 |  |  | Trial 360 |  |  | Trial 361 |  |  | Trial 362 |  |  | Trial 363 |  |  | Trial 364 |  |  | Trial 365 |  |  | Trial 366 |  |  | Trial 367 |  |  | Trial 368 |  |  | Trial 369 |  |  | Trial 370 |  |  | Trial 371 |  |  | Trial 372 |  |  | Trial 373 |  |  | Trial 374 |  |  | Trial 375 |  |  | Trial 376 |  |  | Trial 377 |  |  | Trial 378 |  |  | Trial 379 |  |  | Trial 380 |  |  | Trial 381 |  |  | Trial 382 |  |  | Trial 383 |  |  | Trial 384 |  |  | Trial 385 |  |  | Trial 386 |  |  | Trial 387 |  |  | Trial 388 |  |  | Trial 389 |  |  | Trial 390 |  |  | Trial 391 |  |  | Trial 392 |  |  | Trial 393 |  |  | Trial 394 |  |  | Trial 395 |  |  | Trial 396 |  |  | Trial 397 |  |  | Trial 398 |  |  | Trial 399 |  |  | Trial 400 |  |  | Trial 401 |  |  | Trial 402 |  |  | Trial 403 |  |  | Trial 404 |  |  | Trial 405 |  |  | Trial 406 |  |  | Trial 407 |  |  | Trial 408 |  |  | Trial 409 |  |  | Trial 410 |  |  | Trial 411 |  |  | Trial 412 |  |  | Trial 413 |  |  | Trial 414 |  |  | Trial 415 |  |  | Trial 416 |  |  | Trial 417 |  |  | Trial 418 |  |  | Trial 419 |  |  | Trial 420 |  |  | Trial 421 |  |  | Trial 422 |  |  | Trial 423 |  |  | Trial 424 |  |  | Trial 425 |  |  | Trial 426 |  |  | Trial 427 |  |  | Trial 428 |  |  | Trial 429 |  |  | Trial 430 |  |  | Trial 431 |  |  | Trial 432 |  |  | Trial 433 |  |  | Trial 434 |  |  | Trial 435 |  |  | Trial 436 |  |  | Trial 437 |  |  | Trial 438 |  |  | Trial 439 |  |  | Trial 440 |  |  | Trial 441 |  |  | Trial 442 |  |  | Trial 443 |  |  | Trial 444 |  |  | Trial 445 |  |  | Trial 446 |  |  | Trial 447 |  |  | Trial 448 |  |  | Trial 449 |  |  | Trial 450 |  |  | Trial 451 |  |  | Trial 452 |  |  | Trial 453 |  |  | Trial 454 |  |  | Trial 455 |  |  | Trial 456 |  |  | Trial 457 |  |  | Trial 458 |  |  | Trial 459 |  |  | Trial 460 |  |  | Trial 461 |  |  | Trial 462 |  |  | Trial 463 |  |  | Trial 464 |  |  | Trial 465 |  |  | Trial 466 |  |  | Trial 467 |  |  | Trial 468 |  |  | Trial 469 |  |  | Trial 470 |  |  | Trial 471 |  |  | Trial 472 |  |  | Trial 473 |  |  | Trial 474 |  |  | Trial 475 |  |  | Trial 476 |  |  | Trial 477 |  |  | Trial 478 |  |  | Trial 479 |  |  | Trial 480 |  |  | Trial 481 |  |  | Trial 482 |  |  | Trial 483 |  |  | Trial 484 |  |  | Trial 485 |  |  | Trial 486 |  |  | Trial 487 |  |  | Trial 488 |  |  | Trial 489 |  |  | Trial 490 |  |  | Trial 491 |  |  | Trial 492 |  |  | Trial 493 |  |  | Trial 494 |  |  | Trial 495 |  |  | Trial 496 |  |  | Trial 497 |  |  | Trial 498 |  |  | Trial 499 |  |  | Trial 500 |  |  | Trial 501 |  |  | Trial 502 |  |  | Trial 503 |  |  | Trial 504 |  |  | Trial 505 |  |  | Trial 506 |  |  | Trial 507 |  |  | Trial 508 |  |  | Trial 509 |  |  | Trial 510 |  |  | Trial 511 |  |  | Trial 512 |  |  | Trial 513 |  |  | Trial 514 |  |  | Trial 515 |  |  | Trial 516 |  |  | Trial 517 |  |  | Trial 518 |  |  | Trial 519 |  |  | Trial 520 |  |  | Trial 521 |  |  | Trial 522 |  |  | Trial 523 |  |  | Trial 524 |  |  | Trial 525 |  |  | Trial 526 |  |  | Trial 527 |  |  | Trial 528 |  |  | Trial 529 |  |  | Trial 530 |  |  | Trial 531 |  |  | Trial 532 |  |  | Trial 533 |  |  | Trial 534 |  |  | Trial 535 |  |  | Trial 536 |  |  | Trial 537 |  |  | Trial 538 |  |  | Trial 539 |  |  | Trial 540 |  |  | Trial 541 |  |  | Trial 542 |  |  | Trial 543 |  |  | Trial 544 |  |  | Trial 545 |  |  | Trial 546 |  |  | Trial 547 |  |  | Trial 548 |  |  | Trial 549 |  |  | Trial 550 |  |  | Trial 551 |  |  | Trial 552 |  |  | Trial 553 |  |  | Trial 554 |  |  | Trial 555 |  |  | Trial 556 |  |  | Trial 557 |  |  | Trial 558 |  |  | Trial 559 |  |  | Trial 560 |  |  | Trial 561 |  |  | Trial 562 |  |  | Trial 563 |  |  | Trial 564 |  |  | Trial 565 |  |  | Trial 566 |  |  | Trial 567 |  |  | Trial 568 |  |  | Trial 569 |  |  | Trial 570 |  |  | Trial 571 |  |  | Trial 572 |  |  | Trial 573 |  |  | Trial 574 |  |  | Trial 575 |  |  | Trial 576 |  |  | Trial 577 |  |  | Trial 578 |  |  | Trial 579 |  |  | Trial 580 |  |  | Trial 581 |  |  | Trial 582 |  |  | Trial 583 |  |  | Trial 584 |  |  | Trial 585 |  |  | Trial 586 |  |  | Trial 587 |  |  | Trial 588 |  |  | Trial 589 |  |  | Trial 590 |  |  | Trial 591 |  |  | Trial 592 |  |  | Trial 593 |  |  | Trial 594 |  |  | Trial 595 |  |  | Trial 596 |  |  | Trial 597 |  |  | Trial 598 |  |  | Trial 599 |  |  | Trial 600 |  |  | Trial 601 |  |  | Trial 602 |  |  | Trial 603 |  |  | Trial 604 |  |  | Trial 605 |  |  | Trial 606 |  |  | Trial 607 |  |  | Trial 608 |  |  | Trial 609 |  |  | Trial 610 |  |  | Trial 611 |  |  | Trial 612 |  |  | Trial 613 |  |  | Trial 614 |  |  | Trial 615 |  |  | Trial 616 |  |  | Trial 617 |  |  | Trial 618 |  |  | Trial 619 |  |  | Trial 620 |  |  | Trial 621 |  |  | Trial 622 |  |  | Trial 623 |  |  | Trial 624 |  |  | Trial 625 |  |  | Trial 626 |  |  | Trial 627 |  |  | Trial 628 |  |  | Trial 629 |  |  | Trial 630 |  |  | Trial 631 |  |  | Trial 632 |  |  | Trial 633 |  |  | Trial 634 |  |  | Trial 635 |  |  | Trial 636 |  |  | Trial 637 |  |  | Trial 638 |  |  | Trial 639 |  |  | Trial 640 |  |  | Trial 641 |  |  | Trial 642 |  |  | Trial 643 |  |  | Trial 644 |  |  | Trial 645 |  |  | Trial 646 |  |  | Trial 647 |  |  | Trial 648 |  |  | Trial 649 |  |  | Trial 650 |  |  | Trial 651 |  |  | Trial 652 |  |  | Trial 653 |  |  | Trial 654 |  |  | Trial 655 |  |  | Trial 656 |  |  | Trial 657 |  |  | Trial 658 |  |  | Trial 659 |  |  | Trial 660 |  |  | Trial 661 |  |  | Trial 662 |  |  | Trial 663 |  |  | Trial 664 |  |  | Trial 665 |  |  | Trial 666 |  |  | Trial 667 |  |  | Trial 668 |  |  | Trial 669 |  |  | Trial 670 |  |  | Trial 671 |  |  | Trial 672 |  |  | Trial 673 |  |  | Trial 674 |  |  | Trial 675 |  |  | Trial 676 |  |  | Trial 677 |  |  | Trial 678 |  |  | Trial 679 |  |  | Trial 680 |  |  | Trial 681 |  |  | Trial 682 |  |  | Trial 683 |  |  | Trial 684 |  |  | Trial 685 |  |  | Trial 686 |  |  | Trial 687 |  |  | Trial 688 |  |  | Trial 689 |  |  | Trial 690 |  |  | Trial 691 |  |  | Trial 692 |  |  | Trial 693 |  |  | Trial 694 |  |  | Trial 695 |  |  | Trial 696 |  |  | Trial 697 |  |  | Trial 698 |  |  | Trial 699 |  |  | Trial 700 |  |  | Trial 701 |  |  | Trial 702 |  |  | Trial 703 |  |  | Trial 704 |  |  | Trial 705 |  |  | Trial 706 |  |  | Trial 707 |  |  | Trial 708 |  |  | Trial 709 |  |  | Trial 710 |  |  | Trial 711 |  |  | Trial 712 |  |  | Trial 713 |  |  | Trial 714 |  |  | Trial 715 |  |  | Trial 716 |  |  | Trial 717 |  |  | Trial 718 |  |  | Trial 719 |  |  | Trial 720 |  |  | Trial 721 |  |  | Trial 722 |  |  | Trial 723 |  |  | Trial 724 |  |  | Trial 725 |  |  | Trial 726 |  |  | Trial 727 |  |  | Trial 728 |  |  | Trial 729 |  |  | Trial 730 |  |  | Trial 731 |  |  | Trial 732 |  |  | Trial 733 |  |  | Trial 734 |  |  | Trial 735 |  |  | Trial 736 |  |  | Trial 737 |  |  | Trial 738 |  |  | Trial 739 |  |  | Trial 740 |  |  | Trial 741 |  |  | Trial 742 |  |  | Trial 743 |  |  | Trial 744 |  |  | Trial 745 |  |  | Trial 746 |  |  | Trial 747 |  |  | Trial 748 |  |  | Trial 749 |  |  | Trial 750 |  |  | Trial 751 |  |  | Trial 752 |  |  | Trial 753 |  |  | Trial 754 |  |  | Trial 755 |  |  | Trial 756 |  |  | Trial 757 |  |  | Trial 758 |  |  | Trial 759 |  |  | Trial 760 |  |  | Trial 761 |  |  | Trial 762 |  |  | Trial 763 |  |  | Trial 764 |  |  | Trial 765 |  |  | Trial 766 |  |  | Trial 767 |  |  | Trial 768 |  |  | Trial 769 |  |  | Trial 770 |  |  | Trial 771 |  |  | Trial 772 |  |  | Trial 773 |  |  | Trial 774 |  |  | Trial 775 |  |  | Trial 776 |  |  | Trial 777 |  |  | Trial 778 |  |  | Trial 779 |  |  | Trial 780 |  |  | Trial 781 |  |  | Trial 782 |  |  | Trial 783 |  |  | Trial 784 |  |  | Trial 785 |  |  | Trial 786 |  |  | Trial 787 |  |  | Trial 788 |  |  | Trial 789 |  |  | Trial 790 |  |  | Trial 791 |  |  | Trial 792 |  |  | Trial 793 |  |  | Trial 794 |  |  | Trial 795 |  |  | Trial 796 |  |  | Trial 797 |  |  | Trial 798 |  |  | Trial 799 |  |  | Trial 800 |  |  | Trial 801 |  |  | Trial 802 |  |  | Trial 803 |  |  | Trial 804 |  |  | Trial 805 |  |  | Trial 806 |  |  | Trial 807 |  |  | Trial 808 |  |  | Trial 809 |  |  | Trial 810 |  |  | Trial 811 |  |  | Trial 812 |  |  | Trial 813 |  |  | Trial 814 |  |  | Trial 815 |  |  | Trial 816 |  |  | Trial 817 |  |  | Trial 818 |  |  | Trial 819 |  |  | Trial 820 |  |  | Trial 821 |  |  | Trial 822 |  |  | Trial 823 |  |  | Trial 824 |  |  | Trial 825 |  |  | Trial 826 |  |  | Trial 827 |  |  | Trial 828 |  |  | Trial 829 |  |  | Trial 830 |  |  | Trial 831 |  |  | Trial 832 |  |  | Trial 833 |  |  | Trial 834 |  |  | Trial 835 |  |  | Trial 836 |  |  | Trial 837 |  |  | Trial 838 |  |  | Trial 839 |  |  | Trial 840 |  |  | Trial 841 |  |  | Trial 842 |  |  | Trial 843 |  |  | Trial 844 |  |  | Trial 845 |  |  | Trial 846 |  |  | Trial 847 |  |  | Trial 848 |  |  | Trial 849 |  |  | Trial 850 |  |  | Trial 851 |  |  | Trial 852 |  |  | Trial 853 |  |  | Trial 854 |  |  | Trial 855 |  |  | Trial 856 |  |  | Trial 857 |  |  | Trial 858 |  |  | Trial 859 |  |  | Trial 860 |  |  | Trial 861 |  |  | Trial 862 |  |  | Trial 863 |  |  | Trial 864 |  |  | Trial 865 |  |  | Trial 866 |  |  | Trial 867 |  |  | Trial 868 |  |  | Trial 869 |  |  | Trial 870 |  |  | Trial 871 |  |  | Trial 872 |  |  | Trial 873 |  |  | Trial 874 |  |  | Trial 875 |  |  | Trial 876 |  |  | Trial 877 |  |  | Trial 878 |  |  | Trial 879 |  |  | Trial 880 |  |  | Trial 881 |  |  | Trial 882 |  |  | Trial 883 |  |  | Trial 884 |  |  | Trial 885 |  |  | Trial 886 |  |  | Trial 887 |  |  | Trial 888 |  |  | Trial 889 |  |  | Trial 890 |  |  | Trial 891 |  |  | Trial 892 |  |  | Trial 893 |  |  | Trial 894 |  |  | Trial 895 |  |  | Trial 896 |  |  | Trial 897 |  |  | Trial 898 |  |  | Trial 899 |  |  | Trial 900 |  |  | Trial 901 |  |  | Trial 902 |  |  | Trial 903 |  |  | Trial 904 |  |  | Trial 905 |  |  | Trial 906 |  |  | Trial 907 |  |  | Trial 908 |  |  | Trial 909 |  |  | Trial 910 |  |  | Trial 911 |  |  | Trial 912 |  |  | Trial 913 |  |  | Trial 914 |  |  | Trial 915 |  |  | Trial 916 |  |  | Trial 917 |  |  | Trial 918 |  |  | Trial 919 |  |  | Trial 920 |  |  | Trial 921 |  |  | Trial 922 |  |  | Trial 923 |  |  | Trial 924 |  |  | Trial 925 |  |  | Trial 926 |  |  | Trial 927 |  |  | Trial 928 |  |  | Trial 929 |  |  | Trial 930 |  |  | Trial 931 |  |  | Trial 932 |  |  | Trial 933 |  |  | Trial 934 |  |  | Trial 935 |  |  | Trial 936 |  |  | Trial 937 |  |  | Trial 938 |  |  | Trial 939 |  |  | Trial 940 |  |  | Trial 941 |  |  | Trial 942 |  |  | Trial 943 |  |  | Trial 944 |  |  | Trial 945 |  |  | Trial 946 |  |  | Trial 947 |  |  | Trial 948 |  |  | Trial 949 |  |  | Trial 950 |  |  | Trial 951 |  |  | Trial 952 |  |  | Trial 953 |  |  | Trial 954 |  |  | Trial 955 |  |  | Trial 956 |  |  | Trial 957 |  |  | Trial 958 |  |  | Trial 959 |  |  | Trial 960 |  |  | Trial 961 |  |  | Trial 962 |  |  | Trial 963 |  |  | Trial 964 |  |  | Trial 965 |  |  | Trial 966 |  |  | Trial 967 |  |  | Trial 968 |  |  | Trial 969 |  |  | Trial 970 |  |  | Trial 971 |  |  | Trial 972 |  |  | Trial 973 |  |  | Trial 974 |  |  | Trial 975 |  |  | Trial 976 |  |  | Trial 977 |  |  | Trial 978 |  |  | Trial 979 |  |  | Trial 980 |  |  | Trial 981 |  |  | Trial 982 |  |  | Trial 983 |  |  | Trial 984 |  |  | Trial 985 |  |  | Trial 986 |  |  | Trial 987 |  |  | Trial 988 |  |  | Trial 989 |  |  | Trial 990 |  |  | Trial 991 |  |  | Trial 992 |  |  | Trial 993 |  |  | Trial 994 |  |  | Trial 995 |  |  | Trial 996 |  |  | Trial 997 |  |  | Trial 998 |  |  | Trial 999 |  |  | Trial 1000
Iteration | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base | RAND | Result | Base
1 | 3 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 5 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47 | 6 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 3 | 47 | 47 | 2 | 47 | 47 | 6 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 1 | 47 | 47 | 3 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 5 | 47 | 47 | 1 | 47 | 47 | 6 | 47 | 47 | 7 | 47 | 47 | 1 | 47 | 47 | 5 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 5 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 2 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 4 | 47 | 47 | 6 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 8 | 47 | 47 | 3 | 47 | 47 | 4 | 47 | 47 | 2 | 47 | 47 | 8 | 47 | 47 | 2 | 47 | 47 | 2 | 47 | 47 | 4 | 47 | 47 | 4 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 1 | 47 | 47 | 2 | 47 | 47 | 5 | 47 | 47 | 8 | 47 | 47 | 4 | 47 | 47 | 7 | 47 | 47 | 7 | 47 | 47 | 3 | 47 | 47
2 | 8 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 5 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 3 | 26 | 26 | 5 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 5 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 2 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 6 | 26 | 26 | 5 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 2 | 26 | 26 | 8 | 26 | 26 | 4 | 26 | 26 | 2 | 26 | 26 | 3 | 26 | 26 | 4 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 1 | 26 | 26 | 5 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 5 | 26 | 26 | 1 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 1 | 26 | 26 | 7 | 26 | 26 | 8 | 26 | 26 | 1 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 4 | 26 | 26 | 1 | 26 | 26 | 4 | 26 | 26 | 8 | 26 | 26 | 2 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 6 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 7 | 26 | 26 | 7 | 26 | 26 | 3 | 26 | 26 | 8 | 26 | 26 | 6 | 26 | 26 | 2 | 26 | 26 | 1 | 26 | 26 | 8 | 26 | 26
3 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39
4 | 3 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 2 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 5 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 7 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 2 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 21 | 21 | 1 | 21 | 21 | 2 | 21 | 21 | 8 | 21 | 21 | 5 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 7 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 6 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 7 | 21 | 21 | 2 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 5 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 3 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 4 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 6 | 21 | 21 | 6 | 21 | 21 | 1 | 21 | 21 | 8 | 21 | 21 | 8 | 21 | 21 | 3 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 7 | 21 | 21 | 3 | 21 | 21 | 4 | 21 | 21 | 5 | 21 | 21 | 3 | 21 | 21
5 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 4 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 4 | 39 | 39 | 4 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 5 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 2 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 2 | 39 | 39 | 8 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 39 | 39 | 4 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 8 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 2 | 39 | 39 | 3 | 39 | 39 | 7 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 7 | 39 | 39 | 7 | 39 | 39 | 2 | 39 | 39 | 1 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 39 | 39 | 3 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 3 | 39 | 39 | 4 | 39 | 39 | 1 | 39 | 39 | 1 | 39 | 39 | 6 | 39 | 39 | 6 | 39 | 39 | 8 | 39 | 39 | 7 | 39 | 39
6 | 5 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 4 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 8 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 1 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 2 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 7 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 2 | 15 | 15 | 1 | 15 | 15 | 3 | 15 | 15 | 5 | 15 | 15 | 1 | 15 | 15 | 4 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 1 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 15 | 15 | 2 | 15 | 15 | 3 | 15 | 15 | 7 | 15 | 15 | 3 | 15 | 15 | 4 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 8 | 15 | 15 | 1 | 15 | 15 | 5 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 4 | 15 | 15 | 7 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 6 | 15 | 15 | 8 | 15 | 15 | 6 | 15 | 15 | 3 | 15 | 15 | 8 | 15 | 15 | 5 | 15 | 15 | 5 | 15 | 15 | 2 | 15 | 15 | 2 | 15 | 15 | 6 | 15 | 15
7 | 6 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 1 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 2 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 8 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 2 | 29 | 29 | 3 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 29 | 29 | 2 | 29 | 29 | 4 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 3 | 29 | 29 | 6 | 29 | 29 | 4 | 29 | 29 | 3 | 29 | 29 | 1 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 8 | 29 | 29 | 6 | 29 | 29 | 2 | 29 | 29 | 2 | 29 | 29 | 8 | 29 | 29 | 5 | 29 | 29 | 5 | 29 | 29 | 2 | 29 | 29 | 7 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 7 | 29 | 29 | 6 | 29 | 29 | 7 | 29 | 29 | 5 | 29 | 29 | 8 | 29 | 29 | 4 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 4 | 29 | 29 | 1 | 29 | 29 | 5 | 29 | 29 | 6 | 29 | 29 | 3 | 29 | 29 | 7 | 29 | 29 | 8 | 29 | 29 | 3 | 29 | 29
8 | 8 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 3 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 8 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 1 | 24 | 24 | 1 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 5 | 24 | 24 | 8 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 2 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 4 | 24 | 24 | 4 | 24 | 24 | 2 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 4 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 7 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 8 | 24 | 24 | 1 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 7 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 5 | 24 | 24 | 7 | 24 | 24 | 4 | 24 | 24 | 8 | 24 | 24 | 2 | 24 | 24 | 5 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 6 | 24 | 24 | 1 | 24 | 24 | 6 | 24 | 24 | 3 | 24 | 24 | 6 | 24 | 24 | 4 | 24 | 24 | 3 | 24 | 24 | 7 | 24 | 24 | 5 | 24 | 24 | 1 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24
9 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15
10 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24
11 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24
12 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39
13 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26
14 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47
15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39
16 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47
17 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47
18 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29
19 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39
20 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26
21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15
22 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39
23 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24
24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 8 | 12 | 24 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 2 | 13 | 26 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 8 | 12 | 24 | 2 | 13 | 26 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 8 | 12 | 24 | 3 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 2 | 13 | 26 | 2 | 13 | 26 | 4 | 10.5 | 21 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 2 | 13 | 26 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 2 | 13 | 26 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 2 | 13 | 26 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 2 | 13 | 26 | 2 | 13 | 26 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 2 | 13 | 26 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 6 | 7.5 | 15 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 7 | 14.5 | 29 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 8 | 12 | 24 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 2 | 13 | 26 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 8 | 12 | 24 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 2 | 13 | 26 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 2 | 13 | 26 | 8 | 12 | 24 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 8 | 12 | 24 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 2 | 13 | 26 | 8 | 12 | 24 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 2 | 13 | 26 | 2 | 13 | 26 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 2 | 13 | 26 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 2 | 13 | 26 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 8 | 12 | 24 | 1 | 23.5 | 47 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 2 | 13 | 26 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 5 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 2 | 13 | 26 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 8 | 12 | 24 | 8 | 12 | 24 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 2 | 13 | 26 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24
25 | 1 | 0 | 47 | 1 | 0 | 47 | 5 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 2 | 0 | 26 | 8 | 0 | 24 | 6 | 0 | 15 | 5 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 3 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 3 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 8 | 0 | 24 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 8 | 0 | 24 | 6 | 0 | 15 | 8 | 0 | 24 | 2 | 0 | 26 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 5 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 8 | 0 | 24 | 6 | 0 | 15 | 8 | 0 | 24 | 3 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 7 | 0 | 29 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 3 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 3 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 3 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 4 | 0 | 21 | 7 | 0 | 29 | 8 | 0 | 24 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 3 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 2 | 0 | 26 | 5 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 2 | 0 | 26 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 5 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 8 | 0 | 24 | 2 | 0 | 26 | 6 | 0 | 15 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 6 | 0 | 15 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 2 | 0 | 26 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 2 | 0 | 26 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 2 | 0 | 26 | 5 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 3 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 6 | 0 | 15 | 1 | 0 | 47 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 3 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 3 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 2 | 0 | 26 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 1 | 0 | 47 | 1 | 0 | 47 | 2 | 0 | 26 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 6 | 0 | 15 | 3 | 0 | 39 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 8 | 0 | 24 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 7 | 0 | 29 | 7 | 0 | 29 | 3 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 8 | 0 | 24 | 3 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 3 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 1 | 0 | 47 | 1 | 0 | 47 | 7 | 0 | 29 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 5 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 1 | 0 | 47 | 1 | 0 | 47 | 4 | 0 | 21 | 3 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 8 | 0 | 24 | 6 | 0 | 15 | 8 | 0 | 24 | 3 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 8 | 0 | 24 | 2 | 0 | 26 | 3 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 1 | 0 | 47 | 5 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 4 | 0 | 21 | 5 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 3 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 3 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 6 | 0 | 15 | 6 | 0 | 15 | 6 | 0 | 15 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 2 | 0 | 26 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 3 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 6 | 0 | 15 | 8 | 0 | 24 | 6 | 0 | 15 | 7 | 0 | 29 | 2 | 0 | 26 | 8 | 0 | 24 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 3 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 7 | 0 | 29 | 8 | 0 | 24 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 2 | 0 | 26 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 2 | 0 | 26 | 5 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 4 | 0 | 21 | 3 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 5 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 6 | 0 | 15 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 4 | 0 | 21 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 3 | 0 | 39 | 4 | 0 | 21 | 3 | 0 | 39 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 6 | 0 | 15 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 8 | 0 | 24 | 3 | 0 | 39 | 4 | 0 | 21 | 5 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 1 | 0 | 47 | 3 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 2 | 0 | 26 | 8 | 0 | 24 | 5 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 6 | 0 | 15 | 1 | 0 | 47 | 5 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 3 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 8 | 0 | 24 | 3 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 2 | 0 | 26 | 6 | 0 | 15 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 3 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 3 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 2 | 0 | 26 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 8 | 0 | 24 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 4 | 0 | 21 | 5 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 2 | 0 | 26 | 7 | 0 | 29 | 7 | 0 | 29 | 7 | 0 | 29 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 1 | 0 | 47 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 1 | 0 | 47 | 6 | 0 | 15 | 7 | 0 | 29 | 6 | 0 | 15 | 4 | 0 | 21 | 8 | 0 | 24 | 4 | 0 | 21 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 8 | 0 | 24 | 5 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 2 | 0 | 26 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 6 | 0 | 15 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 1 | 0 | 47 | 8 | 0 | 24 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 8 | 0 | 24 | 2 | 0 | 26 | 8 | 0 | 24 | 5 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 1 | 0 | 47 | 5 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 3 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 8 | 0 | 24 | 7 | 0 | 29 | 4 | 0 | 21 | 8 | 0 | 24 | 5 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 6 | 0 | 15 | 7 | 0 | 29 | 2 | 0 | 26 | 2 | 0 | 26 | 3 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 5 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 2 | 0 | 26 | 1 | 0 | 47 | 8 | 0 | 24 | 6 | 0 | 15 | 5 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 4 | 0 | 21 | 8 | 0 | 24 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 2 | 0 | 26 | 3 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 1 | 0 | 47 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 6 | 0 | 15 | 1 | 0 | 47 | 5 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 3 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 7 | 0 | 29 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 7 | 0 | 29 | 6 | 0 | 15 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 4 | 0 | 21 | 6 | 0 | 15 | 8 | 0 | 24 | 6 | 0 | 15 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 2 | 0 | 26 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 8 | 0 | 24 | 6 | 0 | 15 | 4 | 0 | 21 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 1 | 0 | 47 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 4 | 0 | 21 | 3 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 3 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 8 | 0 | 24 | 1 | 0 | 47 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 1 | 0 | 47 | 3 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 7 | 0 | 29 | 4 | 0 | 21 | 3 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 1 | 0 | 47 | 8 | 0 | 24 | 5 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 2 | 0 | 26 | 7 | 0 | 29 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 1 | 0 | 47 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21
26 | 5 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 4 | 0 | 21 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 5 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 1 | 0 | 47 | 8 | 0 | 24 | 3 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 1 | 0 | 47 | 4 | 0 | 21 | 8 | 0 | 24 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 2 | 0 | 26 | 2 | 0 | 26 | 3 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 8 | 0 | 24 | 4 | 0 | 21 | 1 | 0 | 47 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 3 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 5 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 2 | 0 | 26 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 3 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 2 | 0 | 26 | 6 | 0 | 15 | 8 | 0 | 24 | 2 | 0 | 26 | 1 | 0 | 47 | 5 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 2 | 0 | 26 | 8 | 0 | 24 | 7 | 0 | 29 | 8 | 0 | 24 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 6 | 0 | 15 | 7 | 0 | 29 | 6 | 0 | 15 | 8 | 0 | 24 | 2 | 0 | 26 | 2 | 0 | 26 | 2 | 0 | 26 | 6 | 0 | 15 | 4 | 0 | 21 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 4 | 0 | 21 | 7 | 0 | 29 | 7 | 0 | 29 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 1 | 0 | 47 | 5 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 5 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 4 | 0 | 21 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 6 | 0 | 15 | 6 | 0 | 15 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 6 | 0 | 15 | 2 | 0 | 26 | 3 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 6 | 0 | 15 | 3 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 3 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 1 | 0 | 47 | 6 | 0 | 15 | 1 | 0 | 47 | 2 | 0 | 26 | 3 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 8 | 0 | 24 | 8 | 0 | 24 | 5 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 1 | 0 | 47 | 8 | 0 | 24 | 4 | 0 | 21 | 1 | 0 | 47 | 2 | 0 | 26 | 8 | 0 | 24 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 4 | 0 | 21 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 3 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 1 | 0 | 47 | 8 | 0 | 24 | 5 | 0 | 39 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 3 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 8 | 0 | 24 | 8 | 0 | 24 | 5 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 5 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 1 | 0 | 47 | 5 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 2 | 0 | 26 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 1 | 0 | 47 | 6 | 0 | 15 | 6 | 0 | 15 | 8 | 0 | 24 | 1 | 0 | 47 | 8 | 0 | 24 | 3 | 0 | 39 | 3 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 5 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 3 | 0 | 39 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 6 | 0 | 15 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 1 | 0 | 47 | 3 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 2 | 0 | 26 | 1 | 0 | 47 | 5 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 5 | 0 | 39 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 4 | 0 | 21 | 6 | 0 | 15 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 2 | 0 | 26 | 1 | 0 | 47 | 5 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 8 | 0 | 24 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 3 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 2 | 0 | 26 | 3 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 6 | 0 | 15 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 4 | 0 | 21 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 1 | 0 | 47 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 5 | 0 | 39 | 2 | 0 | 26 | 7 | 0 | 29 | 1 | 0 | 47 | 2 | 0 | 26 | 3 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 6 | 0 | 15 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 5 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 7 | 0 | 29 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 3 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 6 | 0 | 15 | 5 | 0 | 39 | 5 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 2 | 0 | 26 | 4 | 0 | 21 | 6 | 0 | 15 | 3 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 1 | 0 | 47 | 4 | 0 | 21 | 5 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 2 | 0 | 26 | 5 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 5 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 4 | 0 | 21 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 7 | 0 | 29 | 2 | 0 | 26 | 7 | 0 | 29 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 1 | 0 | 47 | 1 | 0 | 47 | 4 | 0 | 21 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 1 | 0 | 47 | 7 | 0 | 29 | 8 | 0 | 24 | 3 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 3 | 0 | 39 | 4 | 0 | 21 | 8 | 0 | 24 | 2 | 0 | 26 | 5 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 5 | 0 | 39 | 6 | 0 | 15 | 4 | 0 | 21 | 5 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 2 | 0 | 26 | 6 | 0 | 15 | 4 | 0 | 21 | 6 | 0 | 15 | 4 | 0 | 21 | 4 | 0 | 21 | 6 | 0 | 15 | 1 | 0 | 47 | 4 | 0 | 21 | 8 | 0 | 24 | 7 | 0 | 29 | 7 | 0 | 29 | 4 | 0 | 21 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 7 | 0 | 29 | 8 | 0 | 24 | 2 | 0 | 26 | 3 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 8 | 0 | 24 | 7 | 0 | 29 | 2 | 0 | 26 | 5 | 0 | 39 | 5 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 3 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 6 | 0 | 15 | 8 | 0 | 24 | 6 | 0 | 15 | 8 | 0 | 24 | 3 | 0 | 39 | 6 | 0 | 15 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 5 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 4 | 0 | 21 | 1 | 0 | 47 | 1 | 0 | 47 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 4 | 0 | 21 | 8 | 0 | 24 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 5 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 8 | 0 | 24 | 5 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 5 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 3 | 0 | 39 | 5 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 1 | 0 | 47 | 7 | 0 | 29 | 6 | 0 | 15 | 8 | 0 | 24 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 5 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 6 | 0 | 15 | 4 | 0 | 21 | 7 | 0 | 29 | 2 | 0 | 26 | 1 | 0 | 47 | 5 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 7 | 0 | 29 | 3 | 0 | 39 | 5 | 0 | 39 | 5 | 0 | 39 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 8 | 0 | 24 | 5 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 3 | 0 | 39 | 8 | 0 | 24 | 3 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 1 | 0 | 47 | 1 | 0 | 47 | 6 | 0 | 15 | 7 | 0 | 29 | 5 | 0 | 39 | 2 | 0 | 26 | 5 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 3 | 0 | 39 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 4 | 0 | 21 | 4 | 0 | 21 | 5 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 3 | 0 | 39 | 7 | 0 | 29 | 1 | 0 | 47 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 6 | 0 | 15 | 2 | 0 | 26 | 3 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 4 | 0 | 21 | 6 | 0 | 15 | 6 | 0 | 15 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 4 | 0 | 21 | 7 | 0 | 29 | 8 | 0 | 24 | 2 | 0 | 26 | 6 | 0 | 15 | 4 | 0 | 21 | 2 | 0 | 26 | 2 | 0 | 26 | 5 | 0 | 39 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 7 | 0 | 29 | 5 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 7 | 0 | 29 | 2 | 0 | 26 | 2 | 0 | 26 | 4 | 0 | 21 | 6 | 0 | 15 | 3 | 0 | 39 | 6 | 0 | 15 | 8 | 0 | 24 | 6 | 0 | 15 | 5 | 0 | 39 | 2 | 0 | 26 | 8 | 0 | 24 | 3 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 1 | 0 | 47 | 8 | 0 | 24 | 3 | 0 | 39 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 4 | 0 | 21 | 2 | 0 | 26 | 1 | 0 | 47 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 1 | 0 | 47 | 7 | 0 | 29 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 3 | 0 | 39 | 8 | 0 | 24 | 2 | 0 | 26 | 4 | 0 | 21 | 4 | 0 | 21 | 4 | 0 | 21 | 7 | 0 | 29 | 7 | 0 | 29 | 6 | 0 | 15 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 7 | 0 | 29 | 5 | 0 | 39 | 6 | 0 | 15 | 1 | 0 | 47 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 6 | 0 | 15 | 7 | 0 | 29 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 1 | 0 | 47 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 3 | 0 | 39 | 1 | 0 | 47 | 3 | 0 | 39 | 7 | 0 | 29 | 8 | 0 | 24 | 1 | 0 | 47 | 2 | 0 | 26 | 1 | 0 | 47 | 3 | 0 | 39 | 1 | 0 | 47 | 6 | 0 | 15 | 7 | 0 | 29 | 7 | 0 | 29 | 5 | 0 | 39 | 6 | 0 | 15 | 5 | 0 | 39 | 4 | 0 | 21 | 2 | 0 | 26 | 4 | 0 | 21 | 4 | 0 | 21 | 3 | 0 | 39 | 4 | 0 | 21 | 5 | 0 | 39 | 7 | 0 | 29 | 6 | 0 | 15 | 8 | 0 | 24 | 4 | 0 | 21 | 4 | 0 | 21 | 2 | 0 | 26 | 8 | 0 | 24 | 5 | 0 | 39 | 1 | 0 | 47 | 4 | 0 | 21 | 7 | 0 | 29 | 8 | 0 | 24 | 6 | 0 | 15 | 2 | 0 | 26 | 7 | 0 | 29 | 3 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 6 | 0 | 15 | 2 | 0 | 26 | 2 | 0 | 26 | 8 | 0 | 24 | 8 | 0 | 24 | 8 | 0 | 24 | 7 | 0 | 29 | 8 | 0 | 24 | 8 | 0 | 24 | 5 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 4 | 0 | 21 | 8 | 0 | 24 | 3 | 0 | 39 | 3 | 0 | 39 | 5 | 0 | 39 | 2 | 0 | 26 | 1 | 0 | 47 | 4 | 0 | 21 | 3 | 0 | 39 | 8 | 0 | 24 | 6 | 0 | 15 | 4 | 0 | 21 | 1 | 0 | 47 | 6 | 0 | 15 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 7 | 0 | 29 | 5 | 0 | 39 | 6 | 0 | 15 | 7 | 0 | 29 | 4 | 0 | 21 | 5 | 0 | 39 | 1 | 0 | 47 | 8 | 0 | 24 | 8 | 0 | 24 | 1 | 0 | 47 | 7 | 0 | 29 | 3 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 4 | 0 | 21 | 5 | 0 | 39 | 1 | 0 | 47 | 5 | 0 | 39 | 6 | 0 | 15 | 6 | 0 | 15 | 2 | 0 | 26 | 6 | 0 | 15 | 6 | 0 | 15 | 3 | 0 | 39 | 2 | 0 | 26 | 4 | 0 | 21 | 3 | 0 | 39 | 2 | 0 | 26 | 6 | 0 | 15 | 3 | 0 | 39 | 7 | 0 | 29 | 7 | 0 | 29 | 8 | 0 | 24 | 7 | 0 | 29 | 3 | 0 | 39 | 1 | 0 | 47 | 2 | 0 | 26 | 5 | 0 | 39 | 3 | 0 | 39 | 3 | 0 | 39 | 8 | 0 | 24 | 7 | 0 | 29
27 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 2 | 13 | 26 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 2 | 13 | 26 | 8 | 12 | 24 | 2 | 13 | 26 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 2 | 13 | 26 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 2 | 13 | 26 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 8 | 12 | 24 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 2 | 13 | 26 | 2 | 13 | 26 | 2 | 13 | 26 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 8 | 12 | 24 | 8 | 12 | 24 | 2 | 13 | 26 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 8 | 12 | 24 | 6 | 7.5 | 15 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 2 | 13 | 26 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 2 | 13 | 26 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 8 | 12 | 24 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 2 | 13 | 26 | 8 | 12 | 24 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 2 | 13 | 26 | 1 | 23.5 | 47 | 8 | 12 | 24 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 2 | 13 | 26 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 2 | 13 | 26 | 8 | 12 | 24 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 5 | 19.5 | 39 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 2 | 13 | 26 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 8 | 12 | 24 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 2 | 13 | 26 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 2 | 13 | 26 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 2 | 13 | 26 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 2 | 13 | 26 | 8 | 12 | 24 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 8 | 12 | 24 | 8 | 12 | 24 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 8 | 12 | 24 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 2 | 13 | 26 | 1 | 23.5 | 47 | 2 | 13 | 26 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 2 | 13 | 26 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 8 | 12 | 24 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 2 | 13 | 26 | 2 | 13 | 26 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 2 | 13 | 26 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 8 | 12 | 24 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 8 | 12 | 24 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 2 | 13 | 26 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 8 | 12 | 24 | 4 | 10.5 | 21 | 8 | 12 | 24 | 2 | 13 | 26 | 2 | 13 | 26 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 2 | 13 | 26 | 4 | 10.5 | 21 | 7 | 14.5 | 29 | 2 | 13 | 26 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 2 | 13 | 26 | 2 | 13 | 26 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 2 | 13 | 26 | 4 | 10.5 | 21 | 8 | 12 | 24 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 2 | 13 | 26 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 8 | 12 | 24 | 1 | 23.5 | 47 | 2 | 13 | 26 | 3 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 8 | 12 | 24 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 4 | 10.5 | 21 | 2 | 13 | 26 | 1 | 23.5 | 47 | 8 | 12 | 24 | 4 | 10.5 | 21 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 2 | 13 | 26 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 2 | 13 | 26 | 5 | 19.5 | 39 | 8 | 12 | 24 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 8 | 12 | 24 | 8 | 12 | 24 | 6 | 7.5 | 15 | 5 | 19.5 | 39 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 8 | 12 | 24 | 7 | 14.5 | 29 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 8 | 12 | 24 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 8 | 12 | 24 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 2 | 13 | 26 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 7 | 14.5 | 29 | 8 | 12 | 24 | 5 | 19.5 | 39 | 2 | 13 | 26 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 3 | 19.5 | 39 | 8 | 12 | 24 | 8 | 12 | 24 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 8 | 12 | 24 | 5 | 19.5 | 39 | 4 | 10.5 | 21 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 8 | 12 | 24 | 7 | 14.5 | 29 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 8 | 12 | 24 | 8 | 12 | 24 | 3 | 19.5 | 39 | 1 | 23.5 | 47 | 5 | 19.5 | 39 | 7 | 14.5 | 29 | 2 | 13 | 26 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 8 | 12 | 24 | 8 | 12 | 24 | 1 | 23.5 | 47 | 8 | 12 | 24 | 5 | 19.5 | 39 | 6 | 7.5 | 15 | 2 | 13 | 26 | 1 | 23.5 | 47 | 4 | 10.5 | 21 | 2 | 13 | 26 | 2 | 13 | 26 | 2 | 13 | 26 | 7 | 14.5 | 29 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 4 | 10.5 | 21 | 4 | 10.5 | 21 | 8 | 12 | 24 | 4 | 10.5 | 21 | 1 | 23.5 | 47 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 1 | 23.5 | 47 | 6 | 7.5 | 15 | 2 | 13 | 26 | 7 | 14.5 | 29 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 8 | 12 | 24 | 3 | 19.5 | 39 | 2 | 13 | 26 | 1 | 23.5 | 47 | 7 | 14.5 | 29 | 7 | 14.5 | 29 | 2 | 13 | 26 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 7 | 14.5 | 29 | 6 | 7.5 | 15 | 3 | 19.5 | 39 | 3 | 19.5 | 39 | 4 | 10.5 | 21 | 8 | 12 | 24 | 5 | 19.5 | 39 | 2 | 13 | 26 | 3 | 19.5 | 39 | 5 | 19.5 | 39 | 5 | 19.5 | 39 | 1 | 23.5 | 47 | 3 | 19.5 | 39 | 6 | 7.5 | 15 | 6 | 7.5 | 15 | 2 | 13 | 26 | 6 | 7.5 | 15 | 2 | 13 | 26
28 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15
29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47
30 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29
31 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39
32 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39
33 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24
34 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39
35 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39
36 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29
37 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47
38 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47
39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29
40 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39
41 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24
42 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29
43 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39
44 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21
45 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26
46 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15
47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21
48 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47
49 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15
50 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26
51 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29
52 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26
53 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39
54 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15
55 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39
56 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47
57 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29
58 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21
59 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24
60 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39
61 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39
62 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47
63 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21
64 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 3 | 39 | 39 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 7 | 29 | 29 | 8 | 24 | 24 | 5 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 1 | 47 | 47 | 4 | 21 | 21 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 5 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 2 | 26 | 26 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 2 | 26 | 26 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 4 | 21 | 21 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 8 | 24 | 24 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 7 | 29 | 29 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 4 | 21 | 21 | 7 | 29 | 29 | 2 | 26 | 26 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 6 | 15 | 15 | 1 | 47 | 47 | 5 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 3 | 39 | 39 | 7 | 29 | 29 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 1 | 47 | 47 | 8 | 24 | 24 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 2 | 26 | 26 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 4 | 21 | 21 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 7 | 29 | 29 | 4 | 21 | 21 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 1 | 47 | 47 | 1 | 47 | 47 | 2 | 26 | 26 | 7 | 29 | 29 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 2 | 26 | 26 | 7 | 29 | 29 | 8 | 24 | 24 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 4 | 21 | 21 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 7 | 29 | 29 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 1 | 47 | 47 | 6 | 15 | 15 | 2 | 26 | 26 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 3 | 39 | 39 | 3 | 39 | 39 | 4 | 21 | 21 | 5 | 39 | 39 | 8 | 24 | 24 | 4 | 21 | 21 | 1 | 47 | 47 | 7 | 29 | 29 | 5 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 8 | 24 | 24 | 4 | 21 | 21 | 5 | 39 | 39 | 5 | 39 | 39 | 2 | 26 | 26 | 5 | 39 | 39 | 6 | 15 | 15 | 8 | 24 | 24 | 7 | 29 | 29 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 6 | 15 | 15 | 5 | 39 | 39 | 4 | 21 | 21 | 2 | 26 | 26 | 4 | 21 | 21 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 3 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 8 | 24 | 24 | 1 | 47 | 47 | 7 | 29 | 29 | 1 | 47 | 47 | 4 | 21 | 21 | 3 | 39 | 39 | 4 | 21 | 21 | 4 | 21 | 21 | 2 | 26 | 26 | 3 | 39 | 39 | 3 | 39 | 39 | 1 | 47 | 47 | 3 | 39 | 39 | 1 | 47 | 47 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 2 | 26 | 26 | 5 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 7 | 29 | 29 | 1 | 47 | 47 | 5 | 39 | 39 | 8 | 24 | 24 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 3 | 39 | 39 | 7 | 29 | 29 | 6 | 15 | 15 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 2 | 26 | 26 | 7 | 29 | 29 | 6 | 15 | 15 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 1 | 47 | 47 | 4 | 21 | 21 | 4 | 21 | 21 | 7 | 29 | 29 | 6 | 15 | 15 | 2 | 26 | 26 | 5 | 39 | 39 | 1 | 47 | 47 | 6 | 15 | 15 | 8 | 24 | 24 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 3 | 39 | 39 | 3 | 39 | 39 | 5 | 39 | 39 | 1 | 47 | 47 | 7 | 29 | 29 | 4 | 21 | 21 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 1 | 47 | 47 | 3 | 39 | 39 | 8 | 24 | 24 | 7 | 29 | 29 | 8 | 24 | 24 | 2 | 26 | 26 | 1 | 47 | 47 | 7 | 29 | 29 | 2 | 26 | 26 | 2 | 26 | 26 | 2 | 26 | 26 | 1 | 47 | 47 | 8 | 24 | 24 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 7 | 29 | 29 | 4 | 21 | 21 | 3 | 39 | 39 | 3 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 8 | 24 | 24 | 6 | 15 | 15 | 4 | 21 | 21 | 4 | 21 | 21 | 3 | 39 | 39 | 5 | 39 | 39 | 4 | 21 | 21 | 8 | 24 | 24 | 4 | 21 | 21 | 6 | 15 | 15 | 3 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39 | 7 | 29 | 29 | 8 | 24 | 24 | 8 | 24 | 24 | 1 | 47 | 47 | 1 | 47 | 47 | 6 | 15 | 15 | 1 | 47 | 47 | 3 | 39 | 39 | 7 | 29 | 29 | 5 | 39 | 39 | 3 | 39 | 39 | 8 | 24 | 24 | 3 | 39 | 39 | 8 | 24 | 24 | 2 | 26 | 26 | 6 | 15 | 15 | 2 | 26 | 26 | 1 | 47 | 47 | 1 | 47 | 47 | 4 | 21 | 21 | 6 | 15 | 15 | 5 | 39 | 39 | 6 | 15 | 15 | 6 | 15 | 15 | 5 | 39 | 39